## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | Assistant Engineer,HQ | Junior Engineer | ORD/000083/2020-2021 | 1268/JD | 18/11/2020 | 90 | NARAYAN CHAKRABORTY | 36.96 | 13.76 | 1
2 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Sajnapara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000190/2020-2021 | 1543/JD | 31/12/2020 | 75 | RAGHU DAS | 39.54 | 71.4 | 1
3 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000311/2020-2021 | 289/JD | 23/02/2021 | 30 | HARIPADA BANERJEE | 24.4 | 47.06 | 1
4 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Pradhanpara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000327/2020-2021 | 221/JD | 12/02/2021 | 30 | RAGHU DAS | 23.09 | 0 | 1
5 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). | Assistant Engineer,HQ | Junior Engineer | ORD/000477/2020-2021 | 61/RWS | 09/02/2021 | 15 | NEW KUNDU ENTERPRISE | 4.09 | 8.18 | 1
6 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000215/2020-2021 | 1549/JD | 31/12/2020 | 60 | CALCON CONSTRUCTIONS | 40.32 | 0 | 0
7 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000216/2020-2021 | 1550/JD | 31/12/2020 | 30 | PARAMJYOTI ENTERPRISE | 12.27 | 24.51 | 1
8 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000250/2020-2021 | 563/JSSD | 01/02/2021 | 15 | NARAYAN CHANDRA ADHIKARY | 4.44 | 8.85 | 0
9 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 5th Tubewell site of Mallicksova PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000024/2023-2024 | 124/JD | 28/04/2023 | 14 | PINTU DAS | 5.01 | 1.76 | 100
10 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250 mm x 150mm dia 3rd tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000031/2022-2023 | 977/JD | 20/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 7.45 | 1
11 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250 mm x 150mm dia 4th tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000032/2022-2023 | 985/JD | 21/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 7.14 | 1
12 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000075/2022-2023 | 1314/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 11.69 | 1
13 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of 3rd Tube Well Site, 2nd Tube Well Site and Head Work Site Pump House at Mallicksova Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000496/2024-2025 | 2374/JD | 18/12/2024 | 20 | SUKUMAR KUNDU | 2.88 | 0 | 0
14 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000510/2021-2022 | 93/JD | 10/01/2022 | 60 | TECHNO CRACY | 4.65 | 4.69 | 100
15 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000511/2021-2022 | 94/JD | 10/01/2022 | 60 | DEBABRATA SARKAR | 4.64 | 4.73 | 100
16 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna of Khathiar line, Girza line and Chamru line within the command area of Jogesh Ch. T.G. PWSS at Mal Block under Jalpaiguri Division, P.H.E. Dte. (Part-C) | Assistant Engineer,HQ | Junior Engineer | ORD/000573/2021-2022 | 730/JD | 17/03/2022 | 21 | SANDIP BANIK | 17.59 | 16.99 | 1
17 | Jalpaiguri Division | Jalpaiguri Division | Laying of Paver Block with development of approach pathway as a restoration work due to delivery main and Rising main laying for Augmentation of Purba Daukimari Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000102/2023-2024 | 445/JD. | 08/06/2023 | 21 | TARAKESWAR PRASAD | 4.59 | 0 | 0
18 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Purba Daukimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000289/2021-2022 | 1258/JD | 10/08/2021 | 15 | RABINDRANATH DUTTA | 4.81 | 4.78 | 0
19 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with FHTC work for Augmentation of Purba Daukimari Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000373/2021-2022 | 333/JD | 02/02/2022 | 120 | SUKES BASU MAJUMDAR | 328.7 | 227.41 | 1
20 | Jalpaiguri Division | Jalpaiguri Division | Construction of 250 CuM. Capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) for the Head Works Site and other related works including pump connection of different pump for Augmentation of Purba Daukimari Piped Water Supply Scheme of Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2021-2022 | 196/JD | 21/01/2022 | 180 | PRADIP SAHA | 75.21 | 72.89 | 1
21 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including culvert crossing and road restoration for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) | Assistant Engineer,HQ | Junior Engineer | ORD/000389/2023-2024 | 1553/JD | 01/11/2023 | 21 | B.M CONSTRUCTION | 9.41 | 9.65 | 100
22 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including road boaring, Supplying and fitting fixing specials, Jeffy Coupling and other miscelleneous works for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | Assistant Engineer,HQ | Junior Engineer | ORD/000391/2023-2024 | 1555/JD | 01/11/2023 | 30 | B.M CONSTRUCTION | 14.3 | 14.33 | 100
23 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000520/2021-2022 | 156/RWS | 24/02/2022 | 15 | ANUP SARKAR | 4.73 | 4.73 | 0
24 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Chanadipa Mouza of Dakshin Salbari W/S/S Under Jalpaiguri Division ,P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000521/2021-2022 | 157/RWS | 24/02/2022 | 15 | ANUP SARKAR | 4.73 | 4.72 | 0
25 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna at Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III | Assistant Engineer,HQ | Junior Engineer | ORD/000532/2021-2022 | 130/JD | 14/01/2022 | 21 | RABINDRANATH DUTTA | 4.84 | 4.83 | 1
26 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 1 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Daukimari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000561/2021-2022 | 441/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 7.92 | 6.67 | 100
27 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000690/2021-2022 | 1064/JSSD | 24/01/2022 | 20 | G. TECH INDIA | 1.83 | 0.74 | 0
28 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000019/2021-2022 | 556/JD | 01/03/2022 | 0 | Resource Division | 17.98 | 0 | 0
29 | Jalpaiguri Division | Jalpaiguri Division | b-wall for kharija berubari pwsss | Assistant Engineer,HQ | Junior Engineer | VCH/000023/2022-2023 | BP-2021-23-4 | 21/04/2022 | 0 | GANAPATI ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.41 | 0 | 0
30 | Jalpaiguri Division | Jalpaiguri Division | IEP FOR MAYNAGURI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001249/2021-2022 | BP-2021-22-388 | 17/03/2022 | 0 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0
31 | Jalpaiguri Division | Jalpaiguri Division | REJUNATION 2ND TUBE WELL SITE CHALSA | Assistant Engineer,HQ | Junior Engineer | VCH/001291/2021-2022 | BP-2021-22-422 | 25/03/2022 | 0 | SUKUMAR KUNDU | 0.94 | 0 | 0
32 | Jalpaiguri Division | Jalpaiguri Division | IEP MAYNAGURI ZONE II | Assistant Engineer,HQ | Junior Engineer | VCH/001319/2021-2022 | BP-2021-22-388 | 17/03/2022 | 0 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0
33 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | FUEL SUPPLY |  | Junior Engineer | BILL/00128/2022-2023 | BP-2022-23-403 | 17/01/2023 | 0 | FILL & SMILE | 1.71 | 0 | 0
34 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ETDS |  | Junior Engineer | BILL/00129/2022-2023 | BP-2022-23-405 | 17/01/2023 | 0 | SUSHIL KUMAR SINGHA | 0.08 | 0 | 0
35 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ETDS |  | Junior Engineer | BILL/00130/2022-2023 | BP-2022-23-406 | 17/01/2023 | 0 | SUSHIL KUMAR SINGHA | 0.13 | 0 | 0
36 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF SHARP TONNER CARTRIDGE |  | Junior Engineer | BILL/00131/2022-2023 | BP-2022-23-404 | 17/01/2023 | 0 | QUATTRON | 0.17 | 0 | 0
37 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | hire chages |  | Junior Engineer | BILL/00247/2022-2023 | BP-2022-23-438 | 03/02/2023 | 0 | LOKNATH CONSTRUCTION | 0.52 | 0 | 0
38 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 250mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000010/2022-2023 | 871/JD | 04/04/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 8 | 7.72 | 100
39 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Dakshin Chak Moulani PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000022/2024-2025 | 671/JD | 16/07/2024 | 625 | M/S S. G. ENTERPRISE | 19.97 | 3.26 | 80
40 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Dakshin Chakmoulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000107/2022-2023 | 83/JSSD | 22/07/2022 | 20 | CHANDAN GHOSH | 4.56 | 4.41 | 100
41 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Rig approach for Installation of tubewell 3rd Tube Well site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000108/2022-2023 | 85/JSSD | 22/07/2022 | 7 | ALICK DUTTA | 0.81 | 0.81 | 100
42 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work i.c.w Laying Rising Main from 1st, 2nd & 3rd Tubewell site OHR Aug. of Dakshin Chak Moulani PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000117/2024-2025 | 230/JSSD | 10/09/2024 | 10 | SADHAN KARMAKAR | 0.64 | 0 | 0
43 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jal Swapna / JJM for Augmentation of Dakhin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000348/2021-2022 | 211/JD | 24/01/2022 | 60 | UNIBRO INFRASERV PRIVATE LIMITED | 426.83 | 307.35 | 80
44 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000349/2023-2024 | 1437/JD | 05/10/2023 | 667 | M/S. D.K. DEY & CO.. | 91.09 | 29.66 | 35
45 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work ¿Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub- Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)¿ from 01.10.2022 to 31.12.2022. |  | Junior Engineer | ORD/000358/2022-2023 | 248/JSSD | 28/09/2022 | 93 | TANMOY CHOUDHURY | 0.46 | 0.33 | 0
46 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 |  | Junior Engineer | ORD/000368/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.44 | 0.4 | 0
47 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Dakshin Chalk Moulani P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000691/2021-2022 | 1066/JSSD | 24/01/2022 | 20 | ASIS ENTERPRISE | 1.83 | 1.81 | 0
48 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000811/2023-2024 | 566/JSSD | 05/03/2024 | 30 | GOURAV CONSTRUCTION CO. | 4.03 | 2.32 | 90
49 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000831/2021-2022 | 1109/W/JSSD | 27/01/2022 | 45 | M/S M G CONSTRUCTION | 4.76 | 4.71 | 100
50 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PREPARATION OF DPR DAKHIN CHAKMOULANI |  | Junior Engineer | VCH/001282/2021-2022 | BP-2021-22-490 | 09/04/2022 | 0 | SUBHANKAR GHOSH | 1.56 | 0 | 0
51 | Jalpaiguri Division | Jalpaiguri Division | supply for fuel | Assistant Engineer,HQ | Junior Engineer | BILL/00264/2023-2024 | BP-2023-24-250 | 21/07/2023 | 0 | FILL & SMILE | 0.58 | 0 | 0
52 | Jalpaiguri Division | Jalpaiguri Division | TEMPORARY HIRING OF ONE MAXI CAB WITH DRIVER | Assistant Engineer,HQ | Junior Engineer | BILL/00265/2023-2024 | BP-2023-24-251 | 21/07/2023 | 0 | RUPA PRASAD | 0.34 | 0 | 0
53 | Jalpaiguri Division | Jalpaiguri Division |  | Assistant Engineer,HQ | Junior Engineer | BILL/00266/2023-2024 | BP-2023-24-252 | 21/07/2023 | 0 | APIKUL ALI | 0.35 | 0 | 0
54 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Kathapara Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000016/2022-2023 | 972/JD | 20/04/2022 | 1199 | SCEC BOENTER KDAS JOINT VENTURE | 430.18 | 104.72 | 60
55 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall with ancillary works for the Pump House No. 1 Premises of the Bhatia para Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000128/2020-2021 | 1196/JD | 06/11/2020 | 30 | RABINDRANATH DUTTA | 4.99 | 5.09 | 100
56 | Jalpaiguri Division | Jalpaiguri Division | Restoration of damaged DI Pipeline at Kathapara Piped W/S at Dhupguri Development Block Under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000128/2022-2023 | 1320/JD | 16/06/2022 | 15 | SADHAN KARMAKAR | 0.96 | 0.96 | 1
57 | Jalpaiguri Division | Jalpaiguri Division | Shifting and Laying of Parallel pipeline in place of partially damaged pipeline for widening and strengthening BRO Road from Chamurchi to Banerhat more including minor retrofitting works to the Division line under Haritalguri T.G. P.W.S.S. command area under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000148/2022-2023 | 1553/JD | 05/08/2022 | 21 | NARAYAN CHANDRA SAHA | 25.32 | 25.28 | 0
58 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C. Over Head Reservoir for the Head Works Site of Augmentation of Kathapara P.W.S.S. under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000190/2022-2023 | 1693/JD | 06/09/2022 | 21 | MOYTEC | 0.97 | 0.71 | 100
59 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000229/2022-2023 | 1746/JD | 08/09/2022 | 1058 | SCEC BOENTER KDAS JOINT VENTURE | 76.15 | 0 | 15
60 | Jalpaiguri Division | Jalpaiguri Division | Land Developmrent at Head Works site under Jabramali Piped Water Supply Scheme whithin Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000280/2022-2023 | 645/RWS | 21/10/2022 | 15 | M/S RATAN KUMAR DAS GUPTA AND CO | 2.59 | 2.56 | 0
61 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Kathapara at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000324/2022-2023 | 2411/JD | 19/12/2022 | 30 | SAUMENDU DUTTA | 8.61 | 8.02 | 0
62 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site for Kathapara PWSS i.c.w. Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2022-2023 | 299/JD | 10/02/2023 | 45 | ABHIK BHOWMIK | 4.64 | 4.73 | 100
63 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of 2nd Tube Well Site and Head Work Site Pump House at Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000378/2024-2025 | 2027/JD | 19/11/2024 | 20 | ABHIK BHOWMIK | 2.41 | 0 | 0
64 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd TW Site for Kathapara PWSS i.c.w. JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000488/2024-2025 | 2427/JD | 24/12/2024 | 261 | ABHIK BHOWMIK | 11.54 | 0 | 80
65 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main of 3rd Tube Well site of Kathapara PWSS, in connection with Rejuvenation of Kathapara Piped Water Supply Scheme under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000529/2023-2024 | 1850/JD | 15/12/2023 | 383 | ABHIK BHOWMIK | 4.73 | 0 | 100
66 | Jalpaiguri Division | Jalpaiguri Division | Construction of 400 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing at Head Works site for Augmentation of Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000585/2021-2022 | 734/JD | 17/03/2022 | 180 | SCEC BOENTER KDAS JOINT VENTURE | 82.2 | 34.61 | 75
67 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000007/2024-2025 | 58/JD | 09/04/2024 | 0 | Resource Division | 18.24 | 0 | 0
68 | Jalpaiguri Division | Jalpaiguri Division | Shifting and repairing of damaged/chokage pipe line due to development, widening of roads and agricultural land related to L.D.S. within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000209/2022-2023 | 1799/JD | 14/09/2022 | 21 | ARATI CONSTRUCTION | 4.85 | 4.87 | 0
69 | Jalpaiguri Division | Jalpaiguri Division | Permanent restoration of G.I. lines across the small stream in two places along with others ancillary works related to distribution system, strengthening of valve chambers due to strengthening of village/PWD roads and culvert works in various places within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division,P.H.E. Dte.Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000210/2022-2023 | 1800/JD | 14/09/2022 | 21 | ARATI CONSTRUCTION | 4.5 | 4.44 | 0
70 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 30
71 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000503/2021-2022 | 104/JD | 11/01/2022 | 60 | LOKNATH CONSTRUCTION | 4.65 | 4.78 | 1
72 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000506/2021-2022 | 105/JD | 11/01/2022 | 60 | PRITAM DUTTA | 4.65 | 4.76 | 1
73 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 2 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000562/2021-2022 | 442/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 15.63 | 15.19 | 1
74 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No. Tube Well by ODEX-165 Method of drilling and Construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement for direct boosting under the command area of Manabari Chaa Sundari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000097/2024-2025 | 1293/JD | 05/09/2024 | 90 | RANJEET SINGH BENIWAL | 13.9 | 0 | 100
75 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Land development of H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000268/2022-2023 | 207/JSSD | 14/09/2022 | 30 | M/S A.B.G. CONSTRUCTION | 1.41 | 1.4 | 100
76 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 100 cum OHR as per departmental design & drawing switch room, laying distribution system sinking of tube well etc. supply of potable drinking water to Manabari Tea Garden in relation with CHAA Sundari Project Piped Water Supply Scheme Block. Nagrakata Dist. Jalpaiguri. |  | Junior Engineer | ORD/000335/2020-2021 | 321/JD | 25/02/2021 | 120 | RANJIT SINGH BENIWAL | 72.76 | 51.53 | 0
77 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL FOR THEB HIRED VEHICLES UNDER JALPAIGURI DIVISION AND SUB DIVISION |  | Junior Engineer | BILL/00480/2023-2024 | BP-2023-24-375 | 19/09/2023 | 0 | FILL & SMILE | 0.7 | 0 | 0
78 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL AND LUBRICANTS FOR THE VEHICLES UNDER JALPAIGURI |  | Junior Engineer | BILL/00610/2023-2024 | BP-2023-24-416 | 06/10/2023 | 0 | FILL & SMILE | 2.41 | 0 | 0
79 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of 1(one) Maxi cab with engine capacity less than or equal to 2000c.c on hire basis including driver for the Executive Engineer ,planing & Design Division-III, P.H.E. Dte., silliguri |  | Junior Engineer | BILL/00664/2023-2024 | BP-2023-24-467 | 17/10/2023 | 0 | SHREYANSH AUTO MOBILE | 1.14 | 0 | 0
80 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL BILL |  | Junior Engineer | BILL/00685/2023-2024 | BP-2023-24-491 | 08/11/2023 | 0 | FILL & SMILE | 0.32 | 0 | 0
81 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL & LUBRICANT FOR THE VEHICLE RUNNING UNDER JALPAIGURI RWS FOR THE MONTH OF OCTOBER-2023 |  | Junior Engineer | BILL/00894/2023-2024 | BP-2023-24-508 | 29/11/2023 | 0 | FILL & SMILE | 0.22 | 0 | 0
82 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250 mm X 150 mm dia tube well by Reverse Rotary method of drilling at 4th Site of A Dakshin Berubari PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000204/2024-2025 | 1591/JD | 23/10/2024 | 30 | NARESH SEN | 9.11 | 0 | 0
83 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) |  | Junior Engineer | ORD/000252/2023-2024 | 683/JD | 11/07/2023 | 184 | RAKESH SARKAR | 0.88 | 1.04 | 50
84 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) |  | Junior Engineer | ORD/000253/2023-2024 | 672/JD | 10/07/2023 | 184 | APIKUL ALI | 0.88 | 0.82 | 30
85 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Soil Investigation Work, Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall (H/W and 2nd Site) along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Satkhaya Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000284/2023-2024 | 1255/JD | 13/09/2023 | 626 | B RAI CONSTRUCTION COMPANY | 183 | 0 | 14
86 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 4th Tubewell site for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000352/2022-2023 | 164/JD | 19/01/2023 | 45 | KAUSHIK SEN | 10.78 | 0 | 0
87 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000367/2021-2022 | 347/JD | 03/02/2022 | 1518 | M/S RATAN KUMAR DAS GUPTA AND CO | 175.44 | 136.33 | 100
88 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-B). |  | Junior Engineer | ORD/000368/2021-2022 | 340/JD | 03/02/2022 | 1518 | M/S RATAN KUMAR DAS GUPTA AND CO | 162.92 | 83.77 | 100
89 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works at Jakhai bari, Kathal Tali, Kalirhat & adjacent area of Dwarikamari W/S/S under Jalpaiguri Division , P.H.E .Dte. (Part-F). Block-Maynaguri. District- Jalpaiguri. |  | Junior Engineer | ORD/000426/2022-2023 | 625/JD | 13/03/2023 | 45 | ARATI CONSTRUCTION | 45 | 0 | 100
90 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections (at 4th TW site) including other necessary arrangement for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000436/2022-2023 | 167/RWS | 28/02/2023 | 14 | SAPTASWA SARKAR | 1.58 | 0 | 1
91 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000455/2021-2022 | 337/JD | 02/02/2022 | 120 | M/S RATAN KUMAR DAS GUPTA AND CO | 143.72 | 110.73 | 100
92 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-C). |  | Junior Engineer | ORD/000461/2021-2022 | 341/JD | 03/02/2022 | 1468 | M/S A.B.G. CONSTRUCTION | 174.6 | 92.67 | 100
93 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000462/2021-2022 | 343/JD | 03/02/2022 | 90 | SUKES BASU MAJUMDAR | 177.1 | 94.69 | 100
94 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-E). |  | Junior Engineer | ORD/000463/2021-2022 | 344/JD | 03/02/2022 | 749 | R.S CONSTRUCTION | 177.82 | 124.31 | 100
95 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-F). |  | Junior Engineer | ORD/000464/2021-2022 | 346/JD | 03/02/2022 | 1518 | M/S SURAJIT DEY AND CO. | 197.49 | 67.35 | 100
96 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional work of OHR including IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Dakshin Berubari Pipe Water Supply Scheme under Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000548/2024-2025 | 128/JD | 16/01/2025 | 440 | M/S RATAN KUMAR DAS GUPTA AND CO | 78.71 | 0 | 85
97 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000011/2021-2022 | 560/JD | 01/03/2022 | 0 | Resource Division | 53.75 | 0 | 0
98 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000086/2024-2025 | 2213/JD | 01/12/2024 | 0 | Resource Division | 30.21 | 0 | 0
99 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC GHASMARI |  | Junior Engineer | VCH/001355/2021-2022 | BP-2021-22-499 | 29/03/2022 | 0 | M/S R.N. TRADERS | 56.2 | 0 | 0
100 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING INSPECTION VEHICLE FOR OFFICIAL USE OF THE OFFICE OF THE EXECUTIVE ENGINEER,JALPAIGURI DIVISION, P.H.E. Dte. |  | Junior Engineer | BILL/00621/2023-2024 | BP-2023-24-426 | 10/10/2023 | 0 | SADHAN KARMAKAR | 0.16 | 0 | 0
101 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of 1(one) Maxi cab on hire basis including driver for the office of the Executive Engineer , planning & Design Division -III,P.H.E. Dte. Silliguri |  | Junior Engineer | BILL/00904/2023-2024 | BP-2023-24-515 | 06/12/2023 | 0 | SHREYANSH AUTO MOBILE | 1.15 | 0 | 0
102 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2023 to 31/10/2023 |  | Junior Engineer | ORD/000117/2023-2024 | 44/JSSD | 27/04/2023 | 183 | MRITYUNJAY SIKDAR | 0.88 | 0.88 | 34
103 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) |  | Junior Engineer | ORD/000202/2022-2023 | 1741/JD | 08/09/2022 | 45 | PROVA CONSTRUCTION | 75.59 | 47.84 | 100
104 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional pipeline works for Augmentation of Baikur (Part-I) Piped Water Supply Scheme. |  | Junior Engineer | ORD/000239/2022-2023 | 1861/JD | 20/09/2022 | 30 | PRADIP KR SEN | 18 | 18.53 | 1
105 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000286/2022-2023 | 2014/JD | 01/11/2022 | 45 | M/S R.N. TRADERS | 17.88 | 17.37 | 100
106 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000340/2022-2023 | 275/JD | 22/11/2022 | 15 | DREAM CONSTRUCTION | 6.32 | 5.15 | 0
107 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000344/2022-2023 | 137/JD | 17/01/2023 | 45 | SADHAN KARMAKAR | 17.86 | 17.27 | 100
108 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-II) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000360/2021-2022 | 323/JD | 02/02/2022 | 90 | UNIBRO INFRASERV PRIVATE LIMITED | 224.83 | 217.04 | 1
109 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-I) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000361/2021-2022 | 322/JD | 02/02/2022 | 90 | UNIBRO INFRASERV PRIVATE LIMITED | 224.8 | 210.42 | 100
110 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-III) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000362/2021-2022 | 324/JD | 02/02/2022 | 90 | CALCON CONSTRUCTIONS | 218.39 | 175.31 | 50
111 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-IV) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000363/2021-2022 | 325/JD | 02/02/2022 | 90 | NARAYAN CHANDRA SAHA | 221.81 | 146.12 | 1
112 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-V) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000364/2021-2022 | 326/JD | 02/02/2022 | 719 | MINTU CHAKRABORTY | 220.34 | 68.71 | 100
113 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-VI) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000365/2021-2022 | 327/JD | 02/02/2022 | 799 | M/S S.G. CONSTRUCTION | 213.61 | 142.01 | 100
114 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Minor Repairing work for Pump House & construction of CC path for Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000365/2022-2023 | 191/JD | 20/01/2023 | 15 | DREAM CONSTRUCTION | 2.55 | 1.79 | 0
115 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of Additional 75 mm dia pipeline for providing FHTC for Augmentation of Baikur PWSS for Part-VI area. |  | Junior Engineer | ORD/000530/2023-2024 | 1876/JD | 20/12/2023 | 21 | PRADIP KR SEN | 13.08 | 12.47 | 100
116 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional Laying Distribution System and Providing Functional House Hold Tap Connection at Baikur (Part-V) PWSS Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000609/2024-2025 | 483/JD | 11/03/2025 | 296 | DREAM CONSTRUCTION | 19.67 | 0 | 85
117 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000616/2021-2022 | 2238/JD | 29/12/2021 | 60 | ABHIJIT SARKAR | 11.44 | 9.84 | 1
118 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000710/2021-2022 | 2223/JD | 27/12/2021 | 60 | DREAM CONSTRUCTION | 11.43 | 10.39 | 1
119 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000009/2021-2022 | 557/JD | 01/03/2022 | 0 | Resource Division | 1.82 | 0 | 0
120 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000088/2024-2025 | 2219/JD | 01/12/2024 | 0 | Resource Division | 44.19 | 0 | 0
121 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | TUBE WELL BILL |  | Junior Engineer | VCH/001151/2021-2022 | BP-2021-22-266 | 16/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0
122 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS MOGALKATA T.G PWSS |  | Junior Engineer | VCH/001262/2021-2022 | BP-2021-22-554 | 31/03/2022 | 0 | DULAL CHOUDHURY | 10.11 | 0 | 0
123 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | AUG LATAGURI ZONE III |  | Junior Engineer | VCH/001396/2021-2022 | BP-2021-22-552 | 31/03/2022 | 0 | RAGHU DAS | 22.91 | 0 | 0
124 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of existing LDS under the command area of Khalaigram Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) | Assistant Engineer,HQ | Junior Engineer | ORD/000249/2021-2022 | 1990/JD | 03/12/2021 | 30 | M/S R.N. TRADERS | 47.9 | 9.31 | 1
125 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000314/2020-2021 | 296/JD | 24/02/2021 | 30 | M/S SIBU DEY AND CO. | 24.41 | 0 | 1
126 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000315/2020-2021 | 290/JD | 23/02/2021 | 20 | PARESH CHANDRA ROY | 12.8 | 0 | 1
127 | Jalpaiguri Division | Jalpaiguri Division | IEP FOR RAIPUR T.G | Assistant Engineer,HQ | Junior Engineer | VCH/000060/2022-2023 | BP-2021-22-24 | 26/04/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 2.39 | 0 | 0
128 | Jalpaiguri Division | Jalpaiguri Division | shifting of pipe line khalaigram | Assistant Engineer,HQ | Junior Engineer | VCH/000341/2021-2022 |  | 05/10/2021 | 0 | LOKNATH CONSTRUCTION | 9.83 | 0 | 0
129 | Jalpaiguri Division | Jalpaiguri Division | FHTC KHALAIGRAM | Assistant Engineer,HQ | Junior Engineer | VCH/000482/2021-2022 |  | 29/10/2021 | 0 | M/S SIBU DEY AND CO. | 22.47 | 0 | 0
130 | Jalpaiguri Division | Jalpaiguri Division | SHIFTING OF PIPE LINE FOR KHALAIGRAM PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000673/2021-2022 | BP-2021-22-77 | 08/10/2021 | 0 | LOKNATH CONSTRUCTION | 9.83 | 0 | 0
131 | Jalpaiguri Division | Jalpaiguri Division | fhtc khalaigram | Assistant Engineer,HQ | Junior Engineer | VCH/000807/2021-2022 | BP-2021-22-94 | 13/11/2021 | 0 | M/S SIBU DEY AND CO. | 22.47 | 0 | 0
132 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Barogari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000166/2025-2026 | 1958/JD | 18/09/2025 | 45 | DEBASISH DEY | 29.65 | 0 | 0
133 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of MADHYA BORAGARI ZONE-II PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division, P.H.E DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000239/2025-2026 | 2345/JD | 04/11/2025 | 210 | BISWANATH GHOSH | 327.82 | 0 | 0
134 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000037/2023-2024 | 1110/JD | 24/08/2023 | 0 | Resource Division | 14.91 | 0 | 0
135 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000129/2023-2024 | 1843/JD | 15/12/2023 | 0 | Resource Division | 8.21 | 0 | 0
136 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
137 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
138 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Gaurgram PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000453/2024-2025 | 633/JD | 28/03/2025 | 45 | RABINDRA NATH DUTTA | 34.39 | 0 | 0
139 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Gaurgram PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal JeevanMission at Block- Maynaguri under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000476/2022-2023 | 787/JD | 27/03/2023 | 1062 | M/S S.G. CONSTRUCTION | 346.83 | 168.71 | 100
140 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd site of GAUGRAM PWSS in connection with Jal Jeevan Mission at Block - MAYNAGURI under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000686/2023-2024 | 152/RWS | 15/02/2024 | 30 | JAGORAN SARKAR | 5.23 | 5.22 | 100
141 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000015/2023-2024 | 159/JD | 28/04/2023 | 0 | Resource Division | 62.06 | 0 | 0
142 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000191/2023-2024 | 2040/JD | 09/01/2024 | 0 | Resource Division | 14.78 | 0 | 0
143 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
144 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
145 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain, at 2nd site of Shakati PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000111/2025-2026 | 489/RWS | 29/05/2025 | 30 | MS DEBABRATA SARKAR | 6.24 | 0 | 0
146 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Shakati PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000465/2022-2023 | 753/JD | 24/03/2023 | 902 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 346.92 | 250.01 | 95
147 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Shakati PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000676/2024-2025 | 468/JD | 11/03/2025 | 40 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 17.67 | 0 | 0
148 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000042/2023-2024 | 1107/JD | 24/08/2023 | 0 | Resource Division | 25.88 | 0 | 0
149 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000146/2023-2024 | 2002/JD | 08/01/2024 | 0 | Resource Division | 7.26 | 0 | 0
150 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Amguri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc.i.c.w. Jal Jeevan Missionat Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte |  | Junior Engineer | ORD/000011/2023-2024 | 29/JD | 10/04/2023 | 1088 | SUKES BASU MAJUMDAR | 514.99 | 337.97 | 77
151 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of RCC Pillers for Delivery & Rising Line and Laying Distribution System for Amguri Piped Water Supply Scheme in connection with Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000169/2025-2026 | 2003/JD | 25/09/2025 | 30 | SUKES BASU MAJUMDAR | 44.57 | 0 | 100
152 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional Household Tap Connection in connection with Jal Jeevan Mission at Amguri PWSS in Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000512/2024-2025 | 45/JD | 09/01/2025 | 416 | B. M CONSTRUCTION | 70.87 | 0 | 60
153 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site Including raising main and interconnection of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000674/2023-2024 | 165/RWS | 15/02/2024 | 30 | DEEP CONSTRUCTION | 6.17 | 6.16 | 100
154 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000007/2023-2024 | 151/JD | 28/04/2023 | 0 | Resource Division | 105.47 | 0 | 0
155 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000170/2023-2024 | 2056/JD | 09/01/2024 | 0 | Resource Division | 14.62 | 0 | 0
156 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Drainage arrangement for back wash water from Iron Elemation Plant at 3rd & 4th tube well site of Charerbari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000033/2023-2024 | 387/RWS | 25/04/2023 | 14 | PRITAM DUTTA | 2.73 | 2.73 | 100
157 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000144/2022-2023 | 1578/JD | 12/08/2022 | 45 | NEW KUNDU ENTERPRISE | 14.43 | 13.22 | 0
158 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000150/2022-2023 | 1563/JD | 10/08/2022 | 45 | A.P CONSTRUCTION | 14.45 | 13.19 | 0
159 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000288/2022-2023 | 2012/JD | 01/11/2022 | 15 | M/S DEY & ROY CHOUDHURY | 3.7 | 3.1 | 1
160 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Minor Repairing work for OHR, Pump Houses, Boundary walls, Blower Room, IEP etc. for Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000400/2022-2023 | 605/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.69 | 0 | 0
161 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Approach road by Paver Block inside the Reservior Compound at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000402/2022-2023 | 603/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.92 | 3.84 | 100
162 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000479/2021-2022 | 2212/JD | 27/12/2021 | 60 | M/S DEY & ROY CHOUDHURY | 11.44 | 11.38 | 1
163 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000480/2021-2022 | 2213/JD | 27/12/2021 | 60 | JAYA SARKAR | 11.42 | 11.38 | 1
164 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Charerbari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000730/2021-2022 | 634/JD | 07/03/2022 | 30 | MECHANO TRADING CO. | 15.51 | 12.5 | 1
165 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000083/2023-2024 | 1059/JD | 24/08/2023 | 0 | Resource Division | 3.24 | 0 | 0
166 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | HIRE CHARGES BILL OF VEHICLE UNDER NBC-I,PHE Dte. |  | Junior Engineer | BILL/00912/2023-2024 | BP-2023-24-517 | 07/12/2023 | 0 | RUPA PRASAD | 0.62 | 0 | 0
167 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
168 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Different components of Dharmapur Zone-I PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. I.c.w. Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000029/2023-2024 | 96/JD | 25/04/2023 | 857 | GLOBAL POWER & CONSTRUCTION CO. | 314.13 | 168.71 | 70
169 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
170 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dharmmapur Zone-I PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000451/2024-2025 | 2330./JD | 12/12/2024 | 639 | BISWAJIT BHADURI | 41.39 | 0 | 70
171 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd site of Dharamapur Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000684/2023-2024 | 154/RWS | 15/02/2024 | 287 | ARATI CONSTRUCTION | 7.29 | 7.2 | 100
172 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W Site including Rising main interconnection of Dharamapur Zone - I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000707/2023-2024 | 2460/JD | 23/02/2024 | 768 | ARUP SARKAR | 22.91 | 0 | 0
173 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000183/2023-2024 | 2037/JD | 09/01/2024 | 0 | Resource Division | 6.57 | 0 | 0
174 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
175 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
176 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance Laying Distribution System with providing Functional Household Tap Connection (FHTC) including sinking of One No Additional Tube Well by ODEX-165 method of drilling, construction of Pump House (3.60m x 2.40m) with sanitary plumbing arrangement, Boundary Wall and direct boosting for 5th site in the command area of Ranichera Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000681/2024-2025 | 460/JD | 11/03/2025 | 142 | GOEL CONSTRUCTION CO. | 80.53 | 0 | 90
177 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000061/2023-2024 | 1098/JD | 24/08/2023 | 0 | Resource Division | 49.85 | 0 | 0
178 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000141/2023-2024 | 1887/JD | 20/12/2023 | 0 | Resource Division | 16.42 | 0 | 0
179 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
180 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
181 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dakshin Dangapara PWSS Zone- I i.e, TW, Pump Houses, Water distribution Network, OHR, IEP, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block Maynaguri under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000065/2023-2024 | 375/A/JD | 30/05/2023 | 763 | PARESH CHANDRA GUHA | 384.43 | 248.47 | 100
182 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dakshin Dangapara Zone-I PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000448/2024-2025 | 2163/JD | 27/11/2024 | 287 | PARESH CHANDRA GUHA | 49.63 | 0 | 0
183 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000167/2023-2024 | 2031/JD | 09/01/2024 | 0 | Resource Division | 9.97 | 0 | 0
184 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Arji Maria Kamala Pukhari PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) |  | Junior Engineer | ORD/000079/2023-2024 | 432/JD. | 08/06/2023 | 28 | GOUTAM DAS | 55.33 | 55.47 | 100
185 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Washout line at 4th Site and Replacement of damaged higher dia pipeline at Arjimaria Kamalapukuri Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri District, PHE Dte. |  | Junior Engineer | ORD/000187/2025-2026 | 2169/JD | 30/10/2025 | 153 | SOUVIK SAHA | 14 | 0 | 100
186 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of 2 Nos of Iron Elimination Plant (20m3/hr.) including construction of 2 nos of Blower room (3.60MX3.00M) Size & concrete platform , drain, valve chamber etc at 3rd and 4th Site of Arji maria kamala pukhari piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000560/2023-2024 | 2175/JD | 22/01/2024 | 60 | R.S CONSTRUCTION | 28.19 | 28.12 | 100
187 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Chotachand Fapri PWSS i.e, TW, Pump House, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000044/2023-2024 | 221/JD | 03/05/2023 | 943 | NARENDRA KUMAR | 196.33 | 42.77 | 45
188 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000002/2024-2025 | 52/JD | 09/04/2024 | 0 | Resource Division | 12.25 | 0 | 0
189 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000184/2023-2024 | 2047/JD | 09/01/2024 | 0 | Resource Division | 4.67 | 0 | 0
190 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
191 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Rangamati Tea Garden PWSS i.e. Tube Well, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000012/2025-2026 | 894/JD | 08/05/2025 | 90 | UMA CONSTRUCTION | 41.93 | 0 | 0
192 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
193 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rangamati Tea Garden PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000262/2023-2024 | 940/JD | 08/08/2023 | 718 | M/S SARKAR ENTERPRISE | 360.92 | 70.39 | 22
194 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution Network and Functional Household Tap Connection (FHTC) of Rangamati Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000432/2024-2025 | 2273/JD | 05/12/2024 | 60 | LAKSHMI IRON | 26.64 | 0 | 0
195 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000151/2023-2024 | 2019/JD | 09/01/2024 | 0 | Resource Division | 12.63 | 0 | 0
196 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
197 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site of Kaoagap PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000007/2025-2026 | 679/JD | 04/04/2025 | 45 | M/S RATAN KUMAR DAS GUPTA AND CO | 23.37 | 0 | 100
198 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
199 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site of Kaoagap PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000100/2024-2025 | 831/RWS | 28/08/2024 | 30 | TAPASH MOHANTA | 7.46 | 0 | 0
200 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Kaoagap PWSS i.e. TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. .C.W. Jal Jeevan Mission at Block:- Maynaguri under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000474/2022-2023 | 777/JD | 27/03/2023 | 1101 | M/S RATAN KUMAR DAS GUPTA AND CO | 412.26 | 231.75 | 80
201 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Kaoagap PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000480/2024-2025 | 2428/JD | 24/12/2024 | 464 | ALICK DUTTA | 34.87 | 0 | 0
202 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000011/2023-2024 | 155/JD | 28/04/2023 | 0 | Resource Division | 41.26 | 0 | 0
203 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000173/2023-2024 | 2028/JD | 09/01/2024 | 0 | Resource Division | 6.06 | 0 | 0
204 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Char Charabari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block ¿ Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000051/2023-2024 | 243JD | 08/05/2023 | 732 | SRINIWAS AGARWAL | 328.17 | 205.15 | 50
205 | Jalpaiguri Division | Northern Mechanical Division | Balance work of distribution system and Functional House Hold Tap Connection (FHTC) including Construction of Boundary wall, drain, footpath at 2 nd site of Charchara Bari PWSS at Banarhat Block under Jalapiguri Division PHE. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000459/2024-2025 | 2345/JD | 12/12/2024 | 60 | SRINIWAS AGARWAL | 70.88 | 0 | 0
206 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Char Chara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000586/2024-2025 | 634/JD | 28/03/2025 | 45 | JITENDRA NATH ROY | 30.36 | 0 | 0
207 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000040/2023-2024 | 1108/JD | 24/08/2023 | 0 | Resource Division | 9.53 | 0 | 0
208 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000131/2023-2024 | 1845/JD | 15/12/2023 | 0 | Resource Division | 8.44 | 0 | 0
209 | Jalpaiguri Division | Jalpaiguri Division | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000179/2022-2023 | 558/RWS | 01/09/2022 | 30 | SAHA CONSTRUCTION | 3.5 | 0 | 1
210 | Jalpaiguri Division | Jalpaiguri Division | Construction of different balance component of PASCHIM SALBARI ZONE-I PWSS i.e. Pump Houses, water distribution Network, OHR, Rising Main, FHTC etc.in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000240/2025-2026 | 2346/JD | 04/11/2025 | 120 | MD HAKIMUDDIN | 227.97 | 0 | 0
211 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Paschim Salbari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000608/2024-2025 | 635/JD | 28/03/2025 | 45 | GOURAB GUHA ROY | 22.72 | 0 | 0
212 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000035/2023-2024 | 1114/JD | 24/08/2023 | 0 | Resource Division | 9.67 | 0 | 0
213 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000123/2023-2024 | 1837/JD | 15/12/2023 | 0 | Resource Division | 5.41 | 0 | 0
214 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000211/2023-2024 | 2073/JD | 10/01/2024 | 0 | Resource Division | 5.79 | 0 | 0
215 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Paharpur Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000026/2024-2025 | 739/JD | 26/07/2024 | 614 | GOUTAM DAS | 108.29 | 17.91 | 60
216 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PAHARPUR ZONE - I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000109/2025-2026 | 487/RWS | 29/05/2025 | 30 | GURUKUL INFOTECH | 4.32 | 0 | 0
217 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 4.9 | 90
218 | Jalpaiguri Division |  | Construction of different components of Paharpur Zone - I Piped Water Supply Scheme i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  |  | ORD/000437/2023-2024 | 1820/JD | 14/12/2023 | 535 | UNIBRO INFRASERV PRIVATE LIMITED | 616.92 | 141.91 | 80
219 | Jalpaiguri Division |  | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Paharpur Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000531/2024-2025 | 113/JD | 16/01/2025 | 40 | TEESTA CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCITY LIMITED. | 17.91 | 0 | 0
220 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1081/JD | 24/08/2023 | 0 | Resource Division | 40.23 | 0 | 0
221 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 2005/JD | 08/01/2024 | 0 | Resource Division | 20.68 | 0 | 0
222 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
223 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
224 | Jalpaiguri Division |  | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain , Land Development etc. at HW Site for Kumarpara PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000074/2024-2025 | 1296/JD | 05/09/2024 | 60 | M/S BOSE ENTERPRISE | 22.73 | 0 | 0
225 | Jalpaiguri Division |  | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 2nd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000084/2024-2025 | 803/RWS | 20/08/2024 | 377 | RANA DEY | 7.43 | 0 | 70
226 | Jalpaiguri Division |  | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 3rd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000102/2024-2025 | 839/RWS | 29/08/2024 | 412 | SUKUMAR KUNDU | 7.46 | 0 | 90
227 | Jalpaiguri Division |  | Construction of different components of Kumarpara PWSS i.e, TW, Pump Houses, Water distribution network , OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. |  |  | ORD/000269/2023-2024 | 945/JD | 08/08/2023 | 966 | SCEC BOENTER KDAS JOINT VENTURE | 601.28 | 288.21 | 25
228 | Jalpaiguri Division |  | Balance Laying Distribution System including Providing Functional Household Tap Connection in connection with JJM under Kumarpara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000621/2024-2025 | 467/JD | 11/03/2025 | 50 | M/S BOSE ENTERPRISE | 40.13 | 0 | 0
229 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 57/JD | 09/04/2024 | 0 | Resource Division | 31.48 | 0 | 0
230 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 2052/JD | 09/01/2024 | 0 | Resource Division | 14.78 | 0 | 0
231 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
232 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
233 | Jalpaiguri Division |  | Construction of different components of Basusuba (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000179/2023-2024 | 850/JD. | 28/07/2023 | 1131 | R.S CONSTRUCTION | 200.42 | 67.6 | 37
234 | Jalpaiguri Division |  | Construction of different components of Basusuba Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000180/2023-2024 | 846/JD | 28/07/2023 | 1131 | R.S CONSTRUCTION | 368.89 | 144.41 | 40
235 | Jalpaiguri Division |  | Construction of different components of Basusuba Zone- II PWSS i.e . TW, Pump House, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000181/2023-2024 | 851/JD | 28/07/2023 | 180 | R.S CONSTRUCTION | 303.82 | 0 | 0
236 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1083/JD | 24/08/2023 | 0 | Resource Division | 60.79 | 0 | 0
237 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 2075/JD | 10/01/2024 | 0 | Resource Division | 17.38 | 0 | 0
238 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000024/2024-2025 | 741/JD | 26/07/2024 | 614 | PRADIP SAHA | 152.08 | 0 | 60
239 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PATKATA ZONE - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000108/2025-2026 | 486/RWS | 29/05/2025 | 30 | EDIFICE ENTERPRISE | 8.05 | 0 | 0
240 | Jalpaiguri Division |  | Construction of different components of Patkata Zone- II Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  |  | ORD/000445/2023-2024 | 1707/JD | 04/12/2023 | 462 | M/S KAMAK ENGINEERS AND CO. | 650.27 | 215.91 | 65
241 | Jalpaiguri Division |  | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000549/2024-2025 | 114/JD | 16/01/2025 | 40 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 23.77 | 0 | 0
242 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1079/JD | 24/08/2023 | 0 | Resource Division | 42.92 | 0 | 0
243 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 2000/JD | 08/01/2024 | 0 | Resource Division | 26.02 | 0 | 0
244 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte.(Phase-I) |  | Junior Engineer | ORD/000033/2021-2022 | 07/JSSD | 13/04/2021 | 20 | R.S CONSTRUCTION | 4.13 | 8.24 | 0
245 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte.(Phase-II). |  | Junior Engineer | ORD/000034/2021-2022 | 09/JSSD | 13/04/2021 | 20 | M/S PAMPA CONSTRUCTION | 3.52 | 7.01 | 0
246 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of YOUNGTONG T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte |  | Junior Engineer | ORD/000161/2020-2021 | 1080/JD | 15/10/2020 | 45 | ASHIT KUMAR SINGHA | 26.73 | 35.62 | 0
247 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | iep for young tong t.g pwss |  | Junior Engineer | VCH/000377/2021-2022 | 291 | 05/09/2021 | 0 | ASHIT KUMAR SINGHA | 3.74 | 0 | 0
248 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fhtc mohit nagar |  | Junior Engineer | VCH/000526/2022-2023 | BP-2021-22-168 | 29/09/2022 | 0 | M/S DEY & ROY CHOUDHURY | 1.14 | 0 | 0
249 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | supply stesonarry |  | Junior Engineer | VCH/000541/2022-2023 | BP-2021-23-169 | 29/09/2022 | 0 | NEW KUNDU ENTERPRISE | 0.03 | 0 | 0
250 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ADDITIONAL LDS FOR YOUNGTONG T.G PWSS |  | Junior Engineer | VCH/000549/2021-2022 | 338/21-22 | 01/10/2021 | 0 | M/S PAMPA CONSTRUCTION | 0.75 | 0 | 0
251 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PROVIDING FHTC AT YOUNGTONG T.G PWSS |  | Junior Engineer | VCH/001154/2020-2021 | 1102 | 22/01/2021 | 0 | M/S.PAMPA CONSTRACTION | 4.49 | 0 | 0
252 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Paschim Mullickpara Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. |  |  | ORD/000208/2020-2021 | 41/JD | 06/01/2021 | 60 | BALAJI UDDYOG | 36.46 | 30.51 | 1
253 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dakshin Altagram Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. |  |  | ORD/000209/2020-2021 | 51/JD | 08/01/2021 | 60 | UMWELT ENGINEER PRIVATE LIMITED | 38.7 | 66.45 | 1
254 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Maynatali Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  |  | ORD/000325/2020-2021 | 310/JD | 26/02/2021 | 30 | SANJIT SAHA | 22.93 | 0 | 1
255 | Jalpaiguri Division |  | Construction of Drain, Plinth Protection, Guard wall including Land Development at H/W site and stand posts for samsing T.G W/S/S under Jalpaiguri Division P.H.E.Dte. |  |  | ORD/000891/2021-2022 | 1009/W/JSSD | 10/01/2022 | 20 | SUBIR GHOSH | 4.65 | 4.34 | 1
256 | Jalpaiguri Division |  | fhtc for khalaigram pwss |  |  | VCH/000363/2021-2022 | 348 | 13/09/2021 | 0 | PARESH CHANDRA GUHA | 12 | 0 | 0
257 | Jalpaiguri Division |  | RETROFITTING OF DISTRIBUTION PIPE LINE DAKSHIN DANGA PARAMOUZA |  |  | VCH/001347/2021-2022 | BP-2021-22-444 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 4.77 | 0 | 0
258 | Jalpaiguri Division |  | FHTC DAKSHIN DANGA PARA |  |  | VCH/001348/2021-2022 | BP-2021-22-442 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 2.6 | 0 | 0
259 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at balance portion of Arjimaria Kamalapokhori W/S Scheme in connection with JJM under Jalpaiguri Division, PHE Dte (Part-G). |  | Junior Engineer | ORD/000138/2023-2024 | 707/JD | 13/07/2023 | 30 | M/S R.K SINGHA & SONS | 30.55 | 0 | 90
260 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna including retrofitting of existing LDS under the command area of Dabgram-II piped Water Supply Scheme (South Zone) at Rajganj Block under Jalpaiguri Division, PHE Dte. Phase-I |  | Junior Engineer | ORD/000141/2020-2021 | 1250/JD | 11/11/2020 | 21 | ASIM GUPTA . | 4.32 | 6.09 | 0
261 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Argimaria Kamalapokori Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000166/2020-2021 | 469/RWS | 15/10/2020 | 30 | PINTU DAS | 4.73 | 4.85 | 1
262 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000186/2020-2021 | 1494/JD | 22/12/2020 | 45 | R.S CONSTRUCTION | 23.66 | 23.9 | 1
263 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-D) |  | Junior Engineer | ORD/000193/2020-2021 | 1545/JD | 31/12/2020 | 45 | R.S CONSTRUCTION | 28.69 | 57.89 | 1
264 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000200/2020-2021 | 1536/JD | 31/12/2020 | 30 | PRADIP SAHA | 15.67 | 31.2 | 1
265 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Repairing of Pipe Line With Other allied works related to Pipeline Under Luksaan Bazaar water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000392/2020-2021 | 612/JSSD | 18/02/2021 | 20 | MONOTOSH ROY | 4.9 | 9.72 | 0
266 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works at related to FHTC for Arjimaria Kamalapukuri Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000434/2020-2021 | 67/RWS | 12/02/2021 | 10 | R.S CONSTRUCTION | 4.17 | 4.25 | 1
267 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000639/2020-2021 | 19/JD | 14/01/2021 | 60 | BILTU DAS | 36.92 | 0 | 1
268 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing FHTC for arajimaria Kamla Pukhari |  | Junior Engineer | VCH/001171/2021-2022 | BP-2021-22-238 | 23/02/2022 | 0 | R.S CONSTRUCTION | 4.94 | 0 | 0
269 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000025/2021-2022 | 745/JD | 13/05/2021 | 20 | GOURAB GUHA ROY | 14.13 | 14.12 | 1
270 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000043/2021-2022 | 1069/JD | 02/07/2021 | 21 | PRAHLAD PRASAD SAHA | 4.83 | 0 | 1
271 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000102/2021-2022 | 1340 /JD | 23/08/2021 | 30 | MONTOSH GHOSH | 30.21 | 0 | 1
272 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- V) | Assistant Engineer,HQ | Junior Engineer | ORD/000132/2021-2022 | 1441/JD | 09/09/2021 | 30 | RAGHU DAS | 31.64 | 0 | 1
273 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting with Jal Sapna under the command area of Husludanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-E) | Assistant Engineer,HQ | Junior Engineer | ORD/000233/2022-2023 | 1906/JD | 27/09/2022 | 25 | SWAPAN SAHA | 17.2 | 14.03 | 0
274 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2022-2023 | 702/JD | 17/03/2023 | 45 | SUBIR GHOSH | 52.54 | 0 | 20
275 | Jalpaiguri Division | Jalpaiguri Division | FHTC BARADIGHI WORK | Assistant Engineer,HQ | Junior Engineer | VCH/000288/2022-2023 | BP-2022-23-115 | 17/08/2022 | 0 | PRIYABRATA KARMAKAR | 4.6 | 0 | 0
276 | Jalpaiguri Division | Jalpaiguri Division | FHTC SAMSING TG | Assistant Engineer,HQ | Junior Engineer | VCH/000289/2022-2023 | BP-2022-23-116 | 18/08/2022 | 0 | PINTU DAS | 4.75 | 0 | 0
277 | Jalpaiguri Division | Jalpaiguri Division | FHTC KILKOTE | Assistant Engineer,HQ | Junior Engineer | VCH/000290/2022-2023 | BP-2022-23-118 | 18/08/2022 | 0 | VEDATRAYEE AND CO. | 1.11 | 0 | 0
278 | Jalpaiguri Division | Jalpaiguri Division | FHTC FOR LUKSHAN BAZAR . | Assistant Engineer,HQ | Junior Engineer | VCH/000311/2022-2023 | BP-2022-23-89 | 02/08/2022 | 0 | ANUP SARKAR | 24.13 | 0 | 0
279 | Jalpaiguri Division | Jalpaiguri Division | fhtc for ambari falakata | Assistant Engineer,HQ | Junior Engineer | VCH/000463/2021-2022 |  | 21/10/2021 | 0 | NARAYAN SARKAR | 23.7 | 0 | 0
280 | Jalpaiguri Division | Jalpaiguri Division | LDS AMBARI FALAKATA PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000479/2021-2022 |  | 29/10/2021 | 0 | GOURAB GUHA ROY | 4.72 | 0 | 0
281 | Jalpaiguri Division | Jalpaiguri Division | AMBARIFALAKATA FHTC | Assistant Engineer,HQ | Junior Engineer | VCH/000796/2021-2022 | BP-2021-22-88 | 01/11/2021 | 0 | NARAYAN SARKAR | 23.7 | 0 | 0
282 | Jalpaiguri Division | Jalpaiguri Division | ambarifalakata fhtc | Assistant Engineer,HQ | Junior Engineer | VCH/000810/2021-2022 | BP-2021-22-98 | 16/11/2021 | 0 | GOURAB GUHA ROY | 4.72 | 0 | 0
283 | Jalpaiguri Division | Jalpaiguri Division | AMBARI FALAKATA | Assistant Engineer,HQ | Junior Engineer | VCH/001051/2021-2022 | BP-2021-22-186 | 14/01/2022 | 0 | RAGHU DAS | 31.53 | 0 | 0
284 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi Tea Garden piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-C) | Assistant Engineer,HQ | Junior Engineer | VCH/001154/2021-2022 | BP-2021-22-272 | 22/02/2022 | 0 | R.S CONSTRUCTION | 13.45 | 0 | 0
285 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi T.G. piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-D) | Assistant Engineer,HQ | Junior Engineer | VCH/001155/2021-2022 | BP-2021-22-271 | 22/02/2022 | 0 | R.S CONSTRUCTION | 5.04 | 0 | 0
286 | Jalpaiguri Division | Jalpaiguri Division | FHTC AMBARI FALAKATA | Assistant Engineer,HQ | Junior Engineer | VCH/001197/2021-2022 | BP-2021-22-329 | 28/02/2022 | 0 | SAPTASWA SARKAR | 21.58 | 0 | 0
287 | Jalpaiguri Division | Jalpaiguri Division | FHTC DAKSHIN SALBARI | Assistant Engineer,HQ | Junior Engineer | VCH/001254/2021-2022 | BP-2021-22-409 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 4.8 | 0 | 0
288 | Jalpaiguri Division | Jalpaiguri Division | FHTC PURBADURAMARI | Assistant Engineer,HQ | Junior Engineer | VCH/001263/2021-2022 | BP-2021-22-465 | 27/03/2022 | 0 | SIBU DEY | 28.4 | 0 | 0
289 | Jalpaiguri Division | Jalpaiguri Division | FHTC PATKIDAHA | Assistant Engineer,HQ | Junior Engineer | VCH/001380/2021-2022 | BP-2021-22-544 | 31/03/2022 | 0 | PRABIR SHOME | 5.89 | 0 | 0
290 | Jalpaiguri Division | Jalpaiguri Division | FHTC JOGESH CH T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001391/2021-2022 | BP-2021-22-535 | 31/03/2022 | 0 | SANDIP BANIK | 19.98 | 0 | 0
291 | Jalpaiguri Division | Jalpaiguri Division | FHTC RAIPUR T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001406/2021-2022 | BP-2021-22-549 | 31/03/2022 | 0 | ANUP KUMAR KUNDU | 2.19 | 0 | 0
292 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORK FOR DAKSHIN SHALBARI | Assistant Engineer,HQ | Junior Engineer | VCH/001436/2021-2022 | BP-2021-22-409 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 4.8 | 0 | 0
293 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000179/2022-2023 | 558/RWS | 01/09/2022 | 30 | SAHA CONSTRUCTION | 3.5 | 3.49 | 1
294 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Caron T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000213/2020-2021 | 1548/JD | 31/12/2020 | 45 | SANDIP BANIK | 28.61 | 57.21 | 0
295 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 3 No. 250 mm x 150 mm x 132 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Goralbari Piped Water Supply Scheme (I, II, III) under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2022-2023 | 1217/JD | 26/05/2022 | 30 | JAYANTA GHOSH | 22.7 | 21.88 | 0
296 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Repair works of O.H.R. Pump Houses and Boundary walls .at Goralbari Zone-III Piped Water Supply Scheme Under Jalpaiguri Division PHE Dte. (2nd Call) |  | Junior Engineer | ORD/000154/2023-2024 | 814/RWS | 14/07/2023 | 21 | TAPASH MOHANTA | 4.33 | 0 | 100
297 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting at Barodhighi,CWC Road, Baroghoria, Koharapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000238/2022-2023 | 1890/JD | 22/09/2022 | 30 | MONOJ GHOSH | 26.94 | 26.87 | 100
298 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works including FHTC at Shubhachandi, Futkibari Including FHTC for Garalbari Zone ¿ II . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000274/2021-2022 | 818/RWS | 30/11/2021 | 15 | BISWAJIT BHADURI | 4.38 | 0 | 1
299 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 3 Nos. 20.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc for Rejuvenation of Garalbari water supply scheme (for Zone-I, Zone-II & Zone-III) under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000438/2022-2023 | 678/JD | 16/03/2023 | 45 | D. S. ENTERPRISE | 53.46 | 31.31 | 100
300 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(3 Nos.) including other necessary arrangement for Rejuvenation of Goralbari Piped Water Supply Scheme( Zone-I, Zone-II & Zone-III) under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000491/2022-2023 | 290/RWS | 29/03/2023 | 21 | BAJRANG ENTERPRISE | 5.97 | 0 | 100
301 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Sarkar Para, along PWD Road, Pranabananda Para, Baruapara, Moulani, Konpakri, Berubari More, Dangapara, Dhapganj etc. within Garalbari Zone-III W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000514/2021-2022 | 538/JD | 25/02/2022 | 60 | ASIM GUPTA | 92.47 | 30.02 | 1
302 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Pradhan Para, Choudhury Para, Haripukuri, Uttar & Dakshin Danga para, Jamuri bari and Camperhat within Garalbari Zone-II W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000515/2021-2022 | 539/JD | 25/02/2022 | 30 | BISWAJIT BHADURI | 29.32 | 0 | 100
303 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Garalbari Zone-I W/S Scheme under Jalpaiguri Division PHE Dte. (Part-E) |  | Junior Engineer | ORD/000541/2021-2022 | 545/JD | 28/02/2022 | 21 | RABINDRANATH DUTTA | 15.82 | 0 | 1
304 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | rep. and renovetion of garalbari zone-ii |  | Junior Engineer | VCH/000045/2022-2023 | BP-2021-22-17 | 26/04/2022 | 0 | ASIT PAUL | 4.35 | 0 | 0
305 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI PWSS |  | Junior Engineer | VCH/000242/2022-2023 | bp2022-23-52 | 08/06/2022 | 0 | BISWAJIT BHADURI | 14.47 | 0 | 0
306 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BHANDANI |  | Junior Engineer | VCH/000250/2022-2023 | BP-2022-23-71 | 04/07/2022 | 0 | DULAL CHOUDHURY | 3.34 | 0 | 0
307 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REP OF PUMP HOUSE FOR GORALBARI PWSS |  | Junior Engineer | VCH/000318/2022-2023 | BP-2022-23-127 | 25/08/2022 | 0 | ASIT PAUL | 0.48 | 0 | 0
308 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RE OF PUMP HOUSE B-WAAL FOR GORALBARI PWSS |  | Junior Engineer | VCH/000323/2022-2023 | bp2022-23 | 25/08/2022 | 0 | PRADIP SAHA | 0.47 | 0 | 0
309 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REP OF PUMP HOUSE FOR GORALBARI PWSS |  | Junior Engineer | VCH/000324/2022-2023 | BP-2022-23-128 | 23/08/2022 | 0 | BISWAJIT BHADURI | 0.42 | 0 | 0
310 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ. GORALBARI PWSS |  | Junior Engineer | VCH/000907/2021-2022 | BP-2021-22-138 | 14/12/2021 | 0 | BISWAJIT BHADURI | 3.12 | 0 | 0
311 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ, GORALBARI |  | Junior Engineer | VCH/000908/2021-2022 | BP-2021-22-139 | 14/12/2021 | 0 | BISWAJIT BHADURI | 2.66 | 0 | 0
312 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ. GORALBARI PWSS |  | Junior Engineer | VCH/000913/2021-2022 | BP-2021-22-136 | 14/12/2021 | 0 | RANJIT KARMAKAR | 4.88 | 0 | 0
313 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORALBARI |  | Junior Engineer | VCH/001204/2021-2022 | BP-2021-22-322 | 28/02/2022 | 0 | DREAM CONSTRACTION | 3.85 | 0 | 0
314 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORAL BARI |  | Junior Engineer | VCH/001205/2021-2022 | BP-2021-22-323 | 28/02/2022 | 0 | RAGHU DAS | 3.87 | 0 | 0
315 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORAL BARI |  | Junior Engineer | VCH/001206/2021-2022 | BP-2021-22-319 | 28/02/2022 | 0 | BISWAJIT BHADURI | 3.85 | 0 | 0
316 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC AUG BAIKUR PART V |  | Junior Engineer | VCH/001317/2021-2022 | BP-2021-22-438 | 26/03/2022 | 0 | MINTU CHAKRABORTY | 78.25 | 0 | 0
317 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REPAIRING H/W GORALBARI ZONE -II |  | Junior Engineer | VCH/001375/2021-2022 | BP-2021-22-538 | 31/03/2022 | 0 | ASIT PAUL | 4.35 | 0 | 0
318 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REPAIRING & RENOVATION OHR GORALBARI ZONE -II |  | Junior Engineer | VCH/001376/2021-2022 | BP-2021-22-539 | 31/03/2022 | 0 | BISWAJIT BHADURI | 3.76 | 0 | 0
319 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REPAIRING & MAINTENANCE GORALBARI WSS |  | Junior Engineer | VCH/001378/2021-2022 | BP-2021-22-537 | 31/03/2022 | 0 | PRADIP SAHA | 4.2 | 0 | 0
320 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI ZONE-I |  | Junior Engineer | VCH/001387/2021-2022 | BP-2021-22-548 | 31/03/2022 | 0 | RABINDRANATH DUTTA | 14.9 | 0 | 0
321 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in Connection with Jal Jeevan Mission under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000006/2024-2025 | 472/JD | 20/06/2024 | 20 | SUBIR GHOSH | 63.03 | 0 | 0
322 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with Functional Household Tap Connection for Sitaguri of Ambari Falakata Water Supply Scheme i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000372/2022-2023 | 297/JD | 10/02/2023 | 14 | RAGHU DAS | 2.53 | 2.52 | 1
323 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2022-2023 | 702/JD | 17/03/2023 | 45 | SUBIR GHOSH | 52.54 | 4.9 | 20
324 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway including laying pipe line for 5th tubewell at Amabari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte i.c.w. JJM . | Assistant Engineer,HQ | Junior Engineer | ORD/000511/2024-2025 | 1214 | 24/12/2024 | 30 | KANAI LAL SEN | 0 | 0 | 0
325 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000613/2021-2022 | 665/JD | 09/03/2022 | 30 | STAR CONSTRUCTION | 9.34 | 8.09 | 1
326 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000614/2021-2022 | 666/JD | 09/03/2022 | 30 | BONANZA ENTERPRISE | 9.34 | 7.86 | 1
327 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000616/2023-2024 | 2313/JD | 07/02/2024 | 30 | SOUVIK SAHA | 8.28 | 7.19 | 100
328 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 4th tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000617/2023-2024 | 2314/JD | 07/02/2024 | 30 | ARUP SARKAR | 8.34 | 6.88 | 100
329 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000046/2023-2024 | 1103/JD | 24/08/2023 | 0 | Resource Division | 2.95 | 0 | 0
330 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of CHAKIAVITA piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000020/2021-2022 | 754/JD | 13/05/2021 | 21 | ANUP SARKAR | 23.75 | 0 | 1
331 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000100/2021-2022 | 1339/JD | 23/08/2021 | 30 | PRADIP SAHA | 30.16 | 25.87 | 1
332 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- III) | Assistant Engineer,HQ | Junior Engineer | ORD/000110/2021-2022 | 1404/JD | 03/09/2021 | 30 | SAPTASWA SARKAR | 30.86 | 1.79 | 1
333 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna within the area of Chakiavita and Kamarvita village under the command area of Chakiavita piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000270/2021-2022 | 2045/JD | 07/12/2021 | 21 | BARUN KUMAR DUTTA | 39.68 | 32.95 | 1
334 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with Functional House Hold Tap connection under "JAL SWAPNA" for Baniapara of Chakiavita Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000283/2021-2022 | 1827/JD | 18/11/2021 | 21 | JAYDEB SAHA | 11.32 | 0 | 1
335 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works related to FHTC inconnection with Jalsapna at different locations of Chanadipa and Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000518/2021-2022 | 163/RWS | 28/02/2022 | 15 | NARAYAN SARKAR | 4.47 | 4.49 | 1
336 | Jalpaiguri Division | Jalpaiguri Division | FHTC ENGO | Assistant Engineer,HQ | Junior Engineer | VCH/000324/2021-2022 |  | 01/10/2021 | 0 | BIMAN DAS | 2.2 | 0 | 0
337 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000472/2021-2022 |  | 29/10/2021 | 0 | PRADIP SAHA | 25.87 | 0 | 0
338 | Jalpaiguri Division | Jalpaiguri Division | RETREOFITTING WORK FOR BOAL MARI | Assistant Engineer,HQ | Junior Engineer | VCH/000476/2021-2022 |  | 29/10/2021 | 0 | KANAI LAL SEN | 9.37 | 0 | 0
339 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORK FOR ARAGI GORALBARI | Assistant Engineer,HQ | Junior Engineer | VCH/000483/2021-2022 |  | 29/10/2021 | 0 | NARAYAN CHAKRABORTY | 4.84 | 0 | 0
340 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORK FOR ARAJI GORALBARI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000484/2021-2022 |  | 29/10/2021 | 0 | SAPTASWA SARKAR | 11.02 | 0 | 0
341 | Jalpaiguri Division | Jalpaiguri Division | CHAKIAVITA FHTC | Assistant Engineer,HQ | Junior Engineer | VCH/000797/2021-2022 | BP-2021-22-111 | 16/11/2021 | 0 | SAPTASWA SARKAR | 4.86 | 0 | 0
342 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000799/2021-2022 | BP-2021-22-109 | 16/11/2021 | 0 | SAPTASWA SARKAR | 4.37 | 0 | 0
343 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000800/2021-2022 | BP-2021-22-112 | 16/11/2021 | 0 | NARAYAN CHAKRABORTY | 4.84 | 0 | 0
344 | Jalpaiguri Division | Jalpaiguri Division | fhtc chakiavita | Assistant Engineer,HQ | Junior Engineer | VCH/000808/2021-2022 | BP-2021-22-95 | 16/11/2021 | 0 | KANAI LAL SEN | 4.59 | 0 | 0
345 | Jalpaiguri Division | Jalpaiguri Division | fhtc chakiavita | Assistant Engineer,HQ | Junior Engineer | VCH/000809/2021-2022 | BP-2021-22-96 | 16/11/2021 | 0 | KANAI LAL SEN | 4.78 | 0 | 0
346 | Jalpaiguri Division | Jalpaiguri Division | CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000922/2021-2022 | BP-2021-22-116 | 03/12/2021 | 0 | SAPTASWA SARKAR | 3.98 | 0 | 0
347 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/001096/2021-2022 | BP-2021-22-167 | 14/01/2022 | 0 | SAPTASWA SARKAR | 29.39 | 0 | 0
348 | Jalpaiguri Division | Jalpaiguri Division | FHTC JITI | Assistant Engineer,HQ | Junior Engineer | VCH/001185/2021-2022 | BP-2021-22-280 | 23/02/2022 | 0 | CALCON CONSTRUCTIONS | 22.07 | 0 | 0
349 | Jalpaiguri Division | Jalpaiguri Division | FHTC MADHYA KHUTTIMARI | Assistant Engineer,HQ | Junior Engineer | VCH/001187/2021-2022 | BP-2021-22-280 | 23/02/2022 | 0 | KAMALESH SEN | 9.42 | 0 | 0
350 | Jalpaiguri Division | Jalpaiguri Division | FHTC RIABARI | Assistant Engineer,HQ | Junior Engineer | VCH/001251/2021-2022 | BP-2021-22-394 | 22/03/2022 | 0 | SAPTASWA SARKAR | 5.63 | 0 | 0
351 | Jalpaiguri Division | Jalpaiguri Division | FHTC RIABARI TG PWSS (PHASE-II) | Assistant Engineer,HQ | Junior Engineer | VCH/001294/2021-2022 | BP-2021-22-394 | 22/03/2022 | 0 | SAPTASWA SARKAR | 5.63 | 0 | 0
352 | Jalpaiguri Division | Jalpaiguri Division | FHTC NAKHATI T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001302/2021-2022 | BP-2021-22-348 | 08/03/2022 | 0 | R.S CONSTRUCTION | 4.81 | 0 | 0
353 | Jalpaiguri Division | Jalpaiguri Division | FHTC JOGESH CHANDRA T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001350/2021-2022 | BP-2021-22-357 | 09/03/2022 | 0 | M/S SURAJIT DEY AND CO. | 28.14 | 0 | 0
354 | Jalpaiguri Division | Jalpaiguri Division | FHTC BHANGAMALI WSS | Assistant Engineer,HQ | Junior Engineer | VCH/001358/2021-2022 | BP-2021-22-496 | 29/03/2022 | 0 | RABINDRANATH DUTTA | 16.94 | 0 | 0
355 | Jalpaiguri Division | Jalpaiguri Division | CONST RCC JURANTI T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001365/2021-2022 | BP[-2021-22-463 | 27/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 3.43 | 0 | 0
356 | Jalpaiguri Division | Jalpaiguri Division | FHTC BARADIGHI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001366/2021-2022 | BP-2021-22-476 | 28/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 41.29 | 0 | 0
357 | Jalpaiguri Division | Jalpaiguri Division | FHTC AWC IN MAYNAGURI BLOCK | Assistant Engineer,HQ | Junior Engineer | VCH/001389/2021-2022 | BP-2021-22-502 | 30/03/2022 | 0 | DREAM CONSTRUCTION | 4.84 | 0 | 0
358 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 300 mm x 200 mm x 123 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Boalmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000062/2022-2023 | 1231/JD | 02/06/2022 | 30 | JAYANTA GHOSH | 17.43 | 16.72 | 0
359 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000300/2021-2022 | 73/JD | 06/01/2022 | 60 | NARESH SEN | 11.21 | 11.2 | 0
360 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000301/2021-2022 | 42/JD | 04/01/2022 | 60 | NARESH SEN | 11.16 | 10.95 | 0
361 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Boalmari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000428/2022-2023 | 624/JD | 13/03/2023 | 45 | KANAI LAL SEN | 33.83 | 30.02 | 100
362 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Maintenance O.H.R.Boundary walls and pump house for rejuvenation of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000694/2021-2022 | 212/RWS | 11/03/2022 | 30 | NARAYAN CHAKRABORTY | 4.8 | 4.91 | 1
363 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000050/2023-2024 | 1101/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0
364 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000138/2022-2023 | 1442/JD | 20/07/2022 | 45 | SADHAN KARMAKAR | 15.34 | 13.83 | 0
365 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 4th tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000141/2022-2023 | 1447/JD | 20/07/2022 | 45 | SADHAN KARMAKAR | 15.34 | 14.29 | 0
366 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Shifting of Pipeline damaged due to construction of Rest area and Truck lay bye by the NHAI in between Maynaguri BDO Office and Tekatuli for Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000198/2022-2023 | 1739/JD | 08/09/2022 | 21 | BARUN KUMAR DUTTA | 6.49 | 6.29 | 1
367 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000273/2022-2023 | 2010/JD | 01/11/2022 | 15 | ABHIJIT SARKAR | 5.77 | 4.43 | 1
368 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Dwarikamari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000466/2021-2022 | 2285JD | 31/12/2021 | 30 | SUBRATA GOSWAMI | 17.42 | 7.23 | 1
369 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000483/2021-2022 | 2216/JD | 27/12/2021 | 60 | BARUN KUMAR DUTTA | 11.45 | 11.47 | 1
370 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000484/2021-2022 | 2217/JD | 27/12/2021 | 60 | PINTU DAS | 11.44 | 11.42 | 1
371 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | TUBE WELL BILL |  | Junior Engineer | VCH/001151/2021-2022 | BP-2021-22-266 | 16/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0
372 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF ALL TYPES OF PETROLEUM PRODUCTS |  | Junior Engineer 2 | BILL/00354/2022-2023 | BP-2023-24-112 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 1.03 | 0 | 0
373 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte. |  | Junior Engineer 2 | BILL/00391/2024-2025 | BP-2024-25-242 | 26/07/2024 | 0 | FILL & SMILE | 0.29 | 0 | 0
374 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply mobil to vehicle no WB 71 A 5774 |  | Junior Engineer 2 | BILL/00392/2024-2025 | BP-2024-25-241 | 26/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
375 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF DIFFERENT STATINARY ITEMS FOR OFFICE USE UNDER JALPAIGURI DIVISION P.H.E DTE. |  | Junior Engineer 2 | BILL/00963/2023-2024 | BP-2023-24-548 | 20/12/2023 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 3.53 | 0 | 0
376 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL (DIESEL) FOR VEHICLES FOR P.H.E JALPAIGURI |  | Junior Engineer 2 | BILL/00985/2023-2024 | BP-2023-24-563 | 05/01/2024 | 0 | FILL & SMILE | 2.6 | 0 | 0
377 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF DIFFERENT STATIONARY ITEMS FOR OFFICE USE UNDER JALPAIGURI R.W.S SUB DIVISION, P.H.E. Dte. |  | Junior Engineer 2 | BILL/01006/2023-2024 | BP-2023-24-573 | 09/01/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.21 | 0 | 0
378 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL BILL FOR GOVT. VEHICLE FOR THE MONTH OF NOVEMBER-2023 |  | Junior Engineer 2 | BILL/01007/2023-2024 | BP-2023-24-571 | 09/01/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0
379 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) |  | Junior Engineer 2 | BILL/01016/2023-2024 | BP-2023-24-574 | 09/01/2024 | 0 | APIKUL ALI | 0.37 | 0 | 0
380 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  | Junior Engineer 2 | BILL/01017/2023-2024 | BP-2023-24-575 | 09/01/2024 | 0 | SOUMEN GHOSH | 0.68 | 0 | 0
381 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & lubricant for EXECUTIVE ENGINEER , P.H.E Dte. JALPAIGURI |  | Junior Engineer 2 | BILL/01018/2023-2024 | BP-2023-24-578 | 10/01/2024 | 0 | FILL & SMILE | 0.83 | 0 | 0
382 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Extension of pipe lines at different locations and provision of a new by pass line near NBSTC Bus Depot to facilitate FHTC L.c.w. JJM under Augmentation of Maynaguri Water Supply Scheme, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000007/2023-2024 | 331/RWS | 10/04/2023 | 14 | ARUP SARKAR | 2.96 | 2.96 | 100
383 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Replacement of old damaged pipe by new HDPE Pipe line at Sahidgarh area, Ward no. 15 under Augmentation of Maynaguri Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000008/2023-2024 | 333/RWS | 10/04/2023 | 21 | SUKES BASU MAJUMDAR | 4.95 | 5.06 | 100
384 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution line crossing through Bridge and main distribution connections at Augmentation of Maynaguri Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000095/2024-2025 | 814/RWS | 22/08/2024 | 30 | M/S SURAJIT DEY AND CO. | 8.68 | 0 | 100
385 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall, Pump House and Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60M x 3.00M) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000126/2022-2023 | 1392/JD | 05/07/2022 | 30 | SUKES BASU MAJUMDAR | 77.4 | 63.44 | 1
386 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 300 mm x 200 mm x 128 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer 2 | ORD/000127/2022-2023 | 1393/JD | 05/07/2022 | 21 | B.M CONSTRUCTION | 19.95 | 19.62 | 1
387 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Rig approach with partial land development for 1st site & 2nd site under Maynaguri piped Water Supply Scheme within Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer 2 | ORD/000183/2022-2023 | 562/RWS | 01/09/2022 | 15 | B.M CONSTRUCTION | 3.56 | 3.54 | 1
388 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of new pipe line beside diversion of PWD road (damaged by PWD for connection of sasan road culvert under Maynaguri Water Supply Scheme (Zone-I). |  | Junior Engineer 2 | ORD/000184/2022-2023 | 563/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 1.16 | 1.03 | 1
389 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  | Junior Engineer 2 | ORD/000275/2022-2023 | 640/RWS | 21/10/2022 | 30 | M/S SURAJIT DEY AND CO. | 4 | 4 | 0
390 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-B) |  | Junior Engineer 2 | ORD/000276/2022-2023 | 641/RWS | 21/10/2022 | 30 | M/S SURAJIT DEY AND CO. | 3.27 | 2.18 | 0
391 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Bleaching Powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/000290/2022-2023 | 13/RWS | 03/11/2022 | 92 | BHOWMIK ENTERPRISES | 0.4 | 0.4 | 0
392 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MAYNAGURI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer 2 | ORD/000333/2021-2022 | 205/JD | 24/01/2022 | 120 | SUKES BASU MAJUMDAR | 97.41 | 94.45 | 1
393 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System and Functional House Hold Connection for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme Block- Maynaguri, Dist. Jalpaiguri. |  | Junior Engineer 2 | ORD/000349/2021-2022 | 225/JD | 25/01/2022 | 1224 | M/S SURAJIT DEY AND CO. | 197.12 | 107.65 | 100
394 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System and Functional House Hold Tap Connection for Augmentation of Maynaguri (Zone-II) Piped Water Supply Scheme. Block- Maynaguri. District - Jalpaiguri. |  | Junior Engineer 2 | ORD/000350/2021-2022 | 226/JD | 25/01/2022 | 1224 | M/S SURAJIT DEY AND CO. | 197.94 | 66.23 | 100
395 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connection for Augmentation of Maynaguri (Zone-I) piped Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri |  | Junior Engineer 2 | ORD/000378/2022-2023 | 243/JD | 04/02/2023 | 30 | ARATI CONSTRUCTION | 3.57 | 3.56 | 100
396 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-II) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000474/2021-2022 | 397/JD | 10/02/2022 | 45 | SUKES BASU MAJUMDAR | 39.13 | 12.95 | 1
397 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation work order for "Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01/02/2025 to 31/07/2025)" |  | Junior Engineer 2 | ORD/000673/2024-2025 | 76/RWS | 30/01/2025 | 181 | ASHIM SARKAR | 0.88 | 0.44 | 32
398 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 2nd Tube well site of Augmentation Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000708/2021-2022 | 2208/JD | 27/12/2021 | 60 | PRIYABRATA KARMAKAR | 11.45 | 7.78 | 1
399 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Alam) for I.E.P at Head Work site under Maynaguri W/S/S for 3 months under Jalpaiguri Division P.H.E. Dte. Period from - 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001055/2021-2022 | 08/RWS | 04/01/2022 | 90 | SUKES BASU MAJUMDAR | 0.67 | 0.67 | 1
400 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001056/2021-2022 | 07/RWS | 04/01/2022 | 90 | SUKES BASU MAJUMDAR | 0.73 | 0.73 | 1
401 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Bleaching powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001057/2021-2022 | 11/RWS | 04/01/2022 | 90 | SADHAN KARMAKAR | 0.4 | 0.4 | 1
402 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Alam) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001058/2021-2022 | 10/RWS | 04/01/2022 | 90 | A.P CONSTRUCTION | 0.24 | 0.24 | 1
403 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001059/2021-2022 | 09/RWS | 04/01/2022 | 90 | PROFULLA GHOSH | 0.26 | 0.26 | 1
404 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000005/2021-2022 | 178/JD | 21/01/2022 | 0 | Resource Division | 69.48 | 0 | 0
405 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000079/2024-2025 | 2210/JD | 01/12/2024 | 0 | Resource Division | 44.3 | 0 | 0
406 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of fuel |  | Junior Engineer 2 | VCH/000595/2022-2023 | BP-2022-23-375 | 18/11/2022 | 0 | FILL & SMILE | 0.29 | 0 | 0
407 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | KAYING OF PIPELINE FOR MADHABDANGA PWSS |  | Junior Engineer 2 | VCH/001258/2021-2022 | BP-2021-22-404 | 23/03/2022 | 0 | M/S SIBU DEY AND CO. | 2.65 | 0 | 0
408 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC RAMSAI PART - II |  | Junior Engineer 2 | VCH/001315/2021-2022 | BP-2021-22-427 | 25/03/2022 | 0 | ASHIT KUMAR SINGHA | 64.85 | 0 | 0
409 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST RCC KHALAIGRAM |  | Junior Engineer 2 | VCH/001397/2021-2022 | BP-2021-22-555 | 31/03/2022 | 0 | DULAL CHOUDHURY | 4.48 | 0 | 0
410 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING OF NEW PIPE LINE CHAMURCHI BAZAR W/S/S |  | Junior Engineer 2 | VCH/001405/2021-2022 | BP-2021-22-556 | 31/03/2022 | 0 | NARAYAN CHANDRA SAHA | 13.02 | 0 | 0
411 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST MAYNAGURI PWSS |  | Junior Engineer 2 | VCH/001441/2021-2022 | BP-2021-22-484 | 29/03/2022 | 0 | PRIYA ASSOCITED | 1.69 | 0 | 0
412 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Nagaisuree Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000008/2022-2023 | 869/JD | 04/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 12.19 | 0
413 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different for Rejuvenation of Nagaisuree Tea Garden Piped Water Supply Scheme i.e. 2 (Two) Nos Pump House, Boundary Wall, Rising Main including Functional Household Tap Connection (FHTC) etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000182/2025-2026 | 2165/JD | 30/10/2025 | 45 | PRASENJIT BASAK | 30.87 | 0 | 0
414 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000269/2022-2023 | 217/JSSD | 16/09/2022 | 60 | ARUP SARKAR | 4.65 | 4.65 | 100
415 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000270/2022-2023 | 216/JSSD | 16/09/2022 | 60 | BAJRANG ENTERPRISE | 4.65 | 4.65 | 0
416 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works for laying Distribution System of Rejuvenation of Nagaisuree T.G. Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000700/2021-2022 | 767/JD | 23/03/2022 | 1145 | SADHAN KARMAKAR | 64.75 | 50.42 | 60
417 | Jalpaiguri Division | Jalpaiguri Division | Replacement of existing defunct sluice valve for Gairkata Water Supply Scheme at Banarhat Development block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000027/2023-2024 | 127/JD | 28/04/2023 | 7 | SHANTI CONSTRUCTION | 1.66 | 1.49 | 100
418 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation Gairkata P.W.S.S under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000049/2022-2023 | 1191/JD | 20/05/2022 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.65 | 4.65 | 100
419 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including providing CI/DI Rising Main connection and providing FHTC in connection with JJM for Augmentation of Gairkata Piped Water Supply Scheme at Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000442/2022-2023 | 695/JD | 17/03/2023 | 730 | M/S R.N. TRADERS | 333.21 | 58.05 | 8
420 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd Tube Well Site of Gairkata Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000495/2024-2025 | 2057/JD | 25/11/2024 | 401 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 8.51 | 0 | 60
421 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Gairkata PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000563/2021-2022 | 455/JD | 18/02/2022 | 21 | MAA ENTERPRISES | 7.93 | 5.71 | 100
422 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000017/2021-2022 | 554/JD | 01/03/2022 | 0 | Resource Division | 14.26 | 0 | 0
423 | Jalpaiguri Division | Jalpaiguri Division | Laying of New Pipeline adjacent to the National Highway for implementation of Jalswapa programme along with minor retrofitting works(laying of parallel line)within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000162/2022-2023 | 1448/JD | 20/07/2022 | 15 | JAYDEB SAHA | 4.85 | 3.46 | 1
424 | Jalpaiguri Division | Jalpaiguri Division | Minor Repairing of Distribution System along with FHTC works under Jalswapna Programme along with other retrofitting works ,chokage removal alog ,repairing of partially damaged C.I.D.F delivery main with other ancillary works within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division, P.H.E.Dte.(Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000216/2022-2023 | 1806/JD | 14/09/2022 | 21 | JAYDEB SAHA | 4.84 | 4.85 | 1
425 | Jalpaiguri Division | Jalpaiguri Division | Construction of One no Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Rejuvenation of Debpara TG Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000276/2023-2024 | 1268/JD | 13/09/2023 | 45 | BOSE ENTERPRISE | 17.67 | 4.9 | 20
426 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of old demage distribution system and other allied work related to pipe line at gara line area of Devpara PWSS in conection with Jal Jeevan Mission Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000315/2024-2025 | 1652/JD | 29/10/2024 | 20 | JAYDEB SAHA | 10.16 | 4.46 | 70
427 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000041/2024-2025 | 2066/JD | 25/11/2024 | 0 | Resource Division | 0.67 | 0 | 0
428 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000004/2022-2023 | 881/JD | 05/04/2022 | 1214 | CALCON CONSTRUCTIONS | 234.41 | 104.98 | 75
429 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000005/2022-2023 | 880/JD | 05/04/2022 | 1367 | M/S SURAJIT DEY AND CO. | 275.87 | 134.75 | 70
430 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Oodlabari (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/000040/2022-2023 | 1067/JD | 28/04/2022 | 979 | TARAKESWAR PRASAD | 84.41 | 56.54 | 70
431 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at HW site of Aug. of Oodlabari PWSS (Z-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000088/2025-2026 | 101/JSSD | 30/05/2025 | 30 | PRIYABRATA KARMAKAR | 6.59 | 0 | 0
432 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
433 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000104/2022-2023 | 80/JSSD | 22/07/2022 | 20 | BIMAN DAS | 4.57 | 4.38 | 100
434 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000105/2022-2023 | 81/JSSD | 22/07/2022 | 20 | BIMAN DAS | 4.57 | 4.39 | 100
435 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari-Kranti Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-III) |  | Junior Engineer | ORD/000246/2022-2023 | 162/JSSD | 24/08/2022 | 30 | BIMAN DAS | 4.77 | 4.76 | 0
436 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from 1st, 2nd & 3rd Tubewell site to OHR for Augmentation of Oodlabari (Zone-II) PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000254/2023-2024 | 1259/JD | 13/09/2023 | 21 | PRITAM DUTTA | 11.83 | 11.73 | 100
437 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Damdim Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-II) |  | Junior Engineer | ORD/000263/2022-2023 | 186/JSSD | 31/08/2022 | 30 | BIMAN DAS | 4.83 | 4.82 | 0
438 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Bagrakote Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-I) |  | Junior Engineer | ORD/000264/2022-2023 | 191/JSSD | 02/09/2022 | 30 | BIMAN DAS | 3.83 | 3.81 | 100
439 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 3 Nos. Deep Rig Bored Tube well by Odex - 165 Method of drilling for Augmentation of Oodlabari (Zone-II) Piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000392/2022-2023 | 2527/JD | 30/12/2022 | 30 | MS S R CONSTRUCTION CO | 16.6 | 17.1 | 0
440 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Water Distribution Network for Node No 200 to 130 Along the NH-17 from Ghish to Chell River for Augmentation of Odlabari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000434/2024-2025 | 2312./JD | 11/12/2024 | 45 | SRINIWAS AGARWAL | 16.84 | 0 | 0
441 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Facelifting and Interior furnishing works for Establishment Section and computer Room in ground floor at PHE Division Office under Jal;paiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000557/2023-2024 | 504/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 10.3 | 9.84 | 100
442 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m X2.40 m) size including Sanitary and Plumbing works at 3rd Tube-Well site for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PH.E. Dte. |  | Junior Engineer | ORD/000656/2022-2023 | 100/JSSD | 25/07/2022 | 45 | BIMAN DAS | 4.75 | 4.64 | 100
443 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60mx2.40m) size including sanitary and plumbing works at 2nd Tube well site for Augmentation of Oolabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000706/2021-2022 | .1051/JSSD | 24/01/2022 | 45 | BIMAN DAS | 4.75 | 4.64 | 100
444 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at H/W site for Augmentation of Oodlabari(Zone-I) piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000809/2023-2024 | 565/JSSD | 05/03/2024 | 30 | SUBHANKAR DEY | 2.76 | 2.73 | 100
445 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No Big dia tube well (200mm x 150mm) by Modified DTH - ODEX method of drilling at H/W Site in Augmentation of Oodlabari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000825/2023-2024 | 2751/JD | 14/03/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 14.01 | 100
446 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing Over Head Reservoir (OHR) with 2 Nos Pump House Head Works Boundary Wall and other ancillary works related to H/W site at Oodlabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001070/2021-2022 | 165/JD | 20/01/2022 | 45 | U TURN CONSTRUCTION | 18.63 | 18.64 | 0
447 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Oodlabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001072/2021-2022 | 1070/JSSD | 25/01/2022 | 20 | SHINE ENGINEERING CONSULTANT | 1.83 | 1.51 | 1
448 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000056/2023-2024 | 1088/JD | 24/08/2023 | 0 | Resource Division | 100.49 | 0 | 0
449 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000082/2024-2025 | 2220/JD | 01/12/2024 | 0 | Resource Division | 20.62 | 0 | 0
450 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
451 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different components of Neora Majhiali (Zone-I, II and III) PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Matiali under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000052/2023-2024 | 244/JD | 08/05/2023 | 696 | SRINIWAS AGARWAL | 424.24 | 226.64 | 55
452 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
453 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Laying distribution system along with providing FHTC at Zone I , II & III of Neora Majhiali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000433/2024-2025 | 2315./JD | 11/12/2024 | 45 | SRINIWAS AGARWAL | 55.21 | 0 | 0
454 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000032/2023-2024 | 145/JD | 28/04/2023 | 0 | Resource Division | 14.77 | 0 | 0
455 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000175/2023-2024 | 2030/JD | 09/01/2024 | 0 | Resource Division | 9.41 | 0 | 0
456 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
457 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dharmapur (Zone-II) PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc I.c.w. Jal Jeevan Mission at Block :- Maynaguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000028/2023-2024 | 95/JD | 25/04/2023 | 921 | K.R. ENTERPRISE | 322.05 | 155.86 | 70
458 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
459 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dharmapur Zone II PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000424/2024-2025 | 2267/JD | 04/12/2024 | 45 | SOMNATH ROY | 32.43 | 0 | 0
460 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd site of Dharamapur Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000685/2023-2024 | 153/RWS | 15/02/2024 | 286 | SANKAR DAS | 5.32 | 5.26 | 100
461 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W Site including Rising main interconnection of Dharamapur Zone - II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000708/2023-2024 | 2461/JD | 23/02/2024 | 45 | PINTU DAS | 14.74 | 0 | 10
462 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000185/2023-2024 | 2048/JD | 09/01/2024 | 0 | Resource Division | 6.84 | 0 | 0
463 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Nipuchhapur PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000049/2023-2024 | 242/JD | 08/05/2023 | 821 | M/S SURAJIT DEY AND CO. | 335.86 | 179.3 | 60
464 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
465 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Nipucchapur TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000176/2025-2026 | 175/JSSD | 25/07/2025 | 30 | TEESTA CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCITY LIMITED. | 7.59 | 0 | 0
466 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Nipucchapur TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000420/2024-2025 | 2266/JD | 04/12/2024 | 70 | MALAY BHOWMIK | 49.56 | 0 | 0
467 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000071/2023-2024 | 1076/JD | 24/08/2023 | 0 | Resource Division | 32.73 | 0 | 0
468 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000194/2023-2024 | 2039/JD | 09/01/2024 | 0 | Resource Division | 11.29 | 0 | 0
469 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Barokamat, Dhaurapara for Argi Garalbari W/S Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) |  | Junior Engineer | ORD/000040/2023-2024 | 392/RWS | 25/04/2023 | 14 | BISWAJIT BHADURI | 3.54 | 3.53 | 100
470 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Arji Garalbari PWSS i.e. TW, Pump Houses, IEP, Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri sadar under Jalpaiguri Division, P.H.E.Dte |  | Junior Engineer | ORD/000109/2023-2024 | 434/JD. | 08/06/2023 | 568 | ASIM GUPTA | 40.15 | 9.44 | 40
471 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site for Rejuvenation of Araji Garalbari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000255/2023-2024 | 941/JD | 08/08/2023 | 45 | LOKNATH CONSTRUCTION | 17.31 | 17.24 | 100
472 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60M X 2.40M) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Arji Garalbari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000379/2022-2023 | 169/JD | 19/01/2023 | 30 | ABHIJIT SARKAR | 10.88 | 10.82 | 100
473 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap connection (FHTC) at Paharer Hat in connection with JJM at Arji Garalbari Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P.H.E. Dte.(Part-I) |  | Junior Engineer | ORD/000420/2022-2023 | 600/JD | 09/03/2023 | 21 | RANJIT KARMAKAR | 4.85 | 4.82 | 100
474 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(at 3rd TW site) including other necessary arrangement for Rejuvenation of Araji Garalbari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000490/2022-2023 | 289/RWS | 29/03/2023 | 14 | ALICK DATTA | 1.81 | 1.79 | 100
475 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System including Providing FHTC and other allied work related to pipe line at Bhangerhat PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000450/2024-2025 | 103/JD | 15/01/2025 | 300 | ARATI CONSTRUCTION | 34.03 | 0 | 0
476 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for balanced DI pipeline from Ranirhat More towards Dhupguri for Bhangarhat PWSS at Maynaguri Block under Jalapaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000734/2023-2024 | 2454/JD | 23/02/2024 | 14 | DIPAK KUMAR CHAKRABORTY | 11.62 | 11.9 | 100
477 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000100/2023-2024 | 1053/JD | 24/08/2023 | 0 | Resource Division | 2.59 | 0 | 0
478 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Purba Dolaigaon PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000070/2023-2024 | 355/JD | 24/05/2023 | 861 | BHUWALKA DEVELOPMENTS PRIVATE LIMITED | 423.12 | 120.16 | 50
479 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
480 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Purba Dolaigaon PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000101/2025-2026 | 480/RWS | 29/05/2025 | 30 | ADITRI ENTERPRISE | 8.36 | 0 | 0
481 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Kranti block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000475/2023-2024 | 1294/RWS | 29/11/2023 | 30 | SUKES BASU MAJUMDAR | 2.34 | 2.34 | 100
482 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance Laying Distribution Network including Construction of Additional Components of Purba Dolaigaon PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000677/2024-2025 | 487/JD | 11/03/2025 | 60 | DEBASISH DEY | 47.56 | 0 | 0
483 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000108/2023-2024 | 1368/JD | 27/09/2023 | 0 | Resource Division | 22.35 | 0 | 0
484 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000149/2023-2024 | 2018/JD | 09/01/2024 | 0 | Resource Division | 12.97 | 0 | 0
485 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Paschim Salbari PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer 2 | ORD/000039/2023-2024 | 129/JD | 28/04/2023 | 734 | NARAYAN CHANDRA SAHA | 112.5 | 0 | 50
486 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Emergency repairing of pipe line damaged due to rural road construction and provision for laying of Gas pipe line at different location under Paschim Salbari (Zone - I) Water Supply Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) |  | Junior Engineer 2 | ORD/000148/2023-2024 | 812/RWS | 14/07/2023 | 21 | SAHA CONSTRUCTION | 2.99 | 2.84 | 100
487 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | "Restoration of DI pipeline earlier damaged under Paschim Salbari Water Supply Scheme (Zone-1) under Jalpaiguri Division PHE Dte. " |  | Junior Engineer 2 | ORD/000188/2022-2023 | 554/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 3.28 | 2.56 | 0
488 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000418/2022-2023 | 170/RWS | 28/02/2023 | 21 | SAHA CONSTRUCTION | 4.91 | 4.51 | 1
489 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-II) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000486/2022-2023 | 284/RWS | 29/03/2023 | 21 | PARAMJYOTI ENTERPRISE | 4.94 | 4.91 | 100
490 | Jalpaiguri Division | Jalpaiguri Division | Emergency restoration work of pucca road that was damaged during pipe laying at Uttar Dangapara & Dakshin Sakoajhora Piped Water Supply Scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000022/2023-2024 | 122/JD | 28/04/2023 | 14 | PARESH CHANDRA GUHA | 3.91 | 3.9 | 100
491 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Uttar Dangapara & Dakshin Sakoajhora PWSS , in connection with Rejuvenation of Uttar Dangapara & Dakshin Sakoajhora PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000093/2023-2024 | 2000/JD | 19/05/2023 | 60 | NARESH SEN | 19.29 | 9.08 | 15
492 | Jalpaiguri Division | Jalpaiguri Division | Providing FHTC with LDS for direct boosting and Installation of Sluice Valve at different strategic point in connection with JJM of Uttar Dangapara and Dakshin Sakoajhora Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000533/2024-2025 | 124/JD | 16/01/2025 | 50 | SUNIL ROY | 26.06 | 0 | 0
493 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000097/2023-2024 | 1056/JD | 24/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
494 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Samarnagar Pwss (Zone-I and II) i.e.TW,Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc. under Jal Jeevan Mission at Block-Rajganj under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000451/2022-2023 | 714/JD | 20/03/2023 | 180 | SANTALALL & BROTHERS | 431.94 | 199.78 | 52
495 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000021/2023-2024 | 165/JD | 28/04/2023 | 0 | Resource Division | 36.86 | 0 | 0
496 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000115/2023-2024 | 1509/JD | 13/10/2023 | 0 | Resource Division | 16.29 | 0 | 0
497 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain,Land development and pathway and laying pipe line at Zone- I (H/W Site , 2 nd TW site) Zone_II,(H/W Site,2nd TW Site,3rd TW Site) and Zone-III (H/W Site,2nd TW site, 3rd TW site ) of PANIKAURI piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. inconnection with JJM. | Assistant Engineer,HQ | Junior Engineer | ORD/000023/2025-2026 | 2152/JD | 17/10/2025 | 75 | KAMAL GHOSH | 113.94 | 0 | 0
498 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000036/2025-2026 | 823/JD | 30/04/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
499 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000126/2025-2026 | 1502/JD | 30/06/2025 | 31 | PRADIP SAHA | 0.4 | 0 | 0
500 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Panikauri PWSS Zone-I,II and III PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block -Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2023-2024 | 1764/JD | 08/12/2023 | 481 | UNIBRO INFRASERV PRIVATE LIMITED | 822.43 | 219.6 | 25
501 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.04.2025 to 30.04.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000788/2024-2025 | 109-HQ/JD | 28/03/2025 | 31 | MD AMIRUL ISLAM | 0.15 | 0 | 0
502 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation of proposed 150 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000798/2024-2025 | 85-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
503 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000799/2024-2025 | 86-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
504 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000002/2023-2024 | 146/JD | 28/04/2023 | 0 | Resource Division | 32.86 | 0 | 0
505 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000177/2023-2024 | 2043/JD | 09/01/2024 | 0 | Resource Division | 23.97 | 0 | 0
506 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Sonakhuli PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte | Assistant Engineer , Head Quarters , NMD |  | ORD/000013/2023-2024 | 39/JD | 13/04/2023 | 812 | JAYANTA GHOSH | 196.47 | 35.42 | 11
507 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Sonakhuli Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000452/2024-2025 | 2332./JD | 12/12/2024 | 45 | ABHIJIT SARKAR | 20.17 | 0 | 0
508 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000013/2023-2024 | 157/JD | 28/04/2023 | 0 | Resource Division | 12.08 | 0 | 0
509 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000126/2023-2024 | 1840/JD | 15/12/2023 | 0 | Resource Division | 4.51 | 0 | 0
510 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Paharpur Zone - II PWSS i.e TW, pump houses,water distribution network, OHR, Rising Main, FHTC etc. at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000050/2023-2024 | 130/JD | 28/04/2023 | 706 | GARGO TRADERS | 459.33 | 89.61 | 50
511 | Jalpaiguri Division | Northern Mechanical Division | Balance Work of Distribution System for Paharpur Zone - II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000052/2024-2025 | 945/JD | 07/08/2024 | 240 | PRIYABRATA KARMAKAR | 24.12 | 0 | 95
512 | Jalpaiguri Division | Northern Mechanical Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000122/2023-2024 | 383/A/JD | 01/06/2023 | 183 | RUPA PRASAD | 0.88 | 0.38 | 50
513 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 90
514 | Jalpaiguri Division | Northern Mechanical Division | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2023 to 31.05.2024)". | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000533/2023-2024 | 1677/JD | 24/11/2023 | 182 | RUPA PRASAD | 0.88 | 2.11 | 100
515 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000072/2023-2024 | 1077/JD | 24/08/2023 | 0 | Resource Division | 35.1 | 0 | 0
516 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000114/2023-2024 | 1508/JD | 13/10/2023 | 0 | Resource Division | 13.79 | 0 | 0
517 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000137/2023-2024 | 1886/JD | 20/12/2023 | 0 | Resource Division | 13.79 | 0 | 0
518 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different stationary items for office use under Jalpaiguri R.W.S Sub Division, P.H.E Dte. |  | Junior Engineer | BILL/00185/2024-2025 | BP-2024-25-121 | 05/06/2024 | 0 | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 0.25 | 0 | 0
519 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00385/2024-2025 | BP-2024-25-226 | 15/07/2024 | 0 | FILL & SMILE | 0.18 | 0 | 0
520 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 78 3405) |  | Junior Engineer | BILL/00386/2024-2025 | BP-2024-25-225 | 15/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
521 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 78 3405) |  | Junior Engineer | BILL/00387/2024-2025 | BP-2024-25-227 | 15/07/2024 | 0 | FILL & SMILE | 0.18 | 0 | 0
522 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00388/2024-2025 | BP-2024-25-228 | 15/07/2024 | 0 | FILL & SMILE | 0.14 | 0 | 0
523 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (Diesel) of Vehicle No. WB 25 K 9449 for the Month of July 2024. |  | Junior Engineer | BILL/00542/2024-2025 | BP-2024-25-311 | 20/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
524 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000025/2024-2025 | 735/JD | 26/07/2024 | 75 | PROVA CONSTRUCTION | 103.17 | 0 | 0
525 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000107/2025-2026 | 485/RWS | 29/05/2025 | 30 | DEEP CONSTRUCTION | 8.05 | 0 | 0
526 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Barapatina Nutanbus Zone-I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000118/2023-2024 | 352/JD | 05/06/2023 | 667 | JAYANTA GHOSH | 379.06 | 139.2 | 70
527 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 90
528 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/08/2025 to 30/09/2025) |  | Junior Engineer | ORD/000154/2025-2026 | 1735/JD | 31/07/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 100
529 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". |  | Junior Engineer | ORD/000202/2025-2026 | 2001/JD | 25/09/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 50
530 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.11.2023 to 31.03.2024) |  | Junior Engineer | ORD/000400/2023-2024 | 1601/JD | 08/11/2023 | 152 | SOMNATH ROY | 0.94 | 0.94 | 100
531 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". |  | Junior Engineer | ORD/000475/2025-2026 | 2404/JD | 19/11/2025 | 30 | AJIJUL HAQUE | 0.4 | 0 | 0
532 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Barapatina Nutanbus Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000551/2024-2025 | 118/JD | 16/01/2025 | 40 | ALOKE DEY | 18.75 | 0 | 0
533 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." |  | Junior Engineer | ORD/000570/2023-2024 | 2197/JD | 25/01/2024 | 182 | SOUMEN GHOSH | 0.88 | 0.39 | 0
534 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.04.2024 to 30.08.2024) |  | Junior Engineer | ORD/000837/2023-2024 | 2946/JD | 28/03/2024 | 152 | SOMNATH ROY | 0.93 | 0.93 | 100
535 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000013/2024-2025 | 2017/JD | 19/11/2024 | 0 | Resource Division | 36.79 | 0 | 0
536 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000138/2023-2024 | 1885/JD | 20/12/2023 | 0 | Resource Division | 12.09 | 0 | 0
537 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No Big Dia Tube Well by Modified DTH - ODEX method for 3rd tube well site at Rejuvenation of Gatia Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000029/2025-2026 | 2154/JD | 17/10/2025 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 16.63 | 0 | 100
538 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000085/2023-2024 | 1060/JD | 24/08/2023 | 0 | Resource Division | 3.73 | 0 | 0
539 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Porapara piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-E) |  | Junior Engineer 2 | ORD/000028/2021-2022 | 748/JD | 13/05/2021 | 30 | DEBASISH DEY | 30 | 0 | 1
540 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna, retrofitting of LDS and rising main connection of 3rd tube well & 4th Tube well site under Porapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-I) |  | Junior Engineer 2 | ORD/000072/2022-2023 | 1298/JD | 14/06/2022 | 60 | B.M CONSTRUCTION | 91.26 | 82.32 | 0
541 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PORAPARA Water Supply Scheme at Sadar Block under under Jalpaiguri Division, PHE Dte. (PART-F) |  | Junior Engineer 2 | ORD/000095/2021-2022 | 1334/JD | 23/08/2021 | 15 | B.M CONSTRUCTION | 14.64 | 16 | 1
542 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional House hold tap Connection (FHTC ) in connection with Jaldhara/ Jalsapna under the command area of PORAPARA W/S/S at Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) |  | Junior Engineer 2 | ORD/000165/2021-2022 | 674/RWS | 27/09/2021 | 15 | SUKES BASU MAJUMDAR | 4.98 | 4.98 | 0
543 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting work related to FHTC in connection to Jalswapna at Haldibari Bypass, Najir Para under Pora para Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000279/2022-2023 | 644/RWS | 21/10/2022 | 20 | B.M CONSTRUCTION | 4.34 | 4.34 | 0
544 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Porapara PWSS at block- Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000538/2023-2024 | 1973/JD | 03/01/2024 | 21 | B.M CONSTRUCTION | 21.19 | 21.15 | 100
545 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000083/2024-2025 | 2218/JD | 01/12/2024 | 0 | Resource Division | 36.07 | 0 | 0
546 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PORA PARA PWSS |  | Junior Engineer 2 | VCH/000332/2021-2022 |  | 01/10/2021 | 0 | B.M CONSTRUCTION | 8 | 0 | 0
547 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PORA PARA |  | Junior Engineer 2 | VCH/000919/2021-2022 | BP-2021-22-117 | 03/12/2021 | 0 | SUKES BASU MAJUMDAR | 4.56 | 0 | 0
548 | Jalpaiguri Division | Jalpaiguri Division | Construction of 250 CuM Over Head Reservoir (OHR) (Staging height 20 Mtr.) as per departmental design and drawing for Augmentation of Jalapara Piped Water Supply Scheme at Block - Dhupguri in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000139/2023-2024 | 700/JD | 13/07/2023 | 859 | M/S. D.K. DEY & CO.. | 78.88 | 34.14 | 20
549 | Jalpaiguri Division | Jalpaiguri Division | Retrofiting works i.c.w.FHTC under Jalsapna including repair of damaged pipe lines during road construction at different areas under Dakshin Salbari Piped W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000175/2022-2023 | 553/RWS | 01/09/2022 | 30 | NEW KUNDU ENTERPRISE | 3.16 | 3.14 | 1
550 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Jalapara Piped Water Supply Scheme at Nagrakata & Dhupguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000286/2023-2024 | 1413/JD | 03/10/2023 | 90 | BOSE ENTERPRISE | 256.04 | 175.93 | 25
551 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of 2nd Tube Well Site and Head Work Site Pump House at Jalapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000497/2024-2025 | 2375/JD | 18/12/2024 | 177 | BALARAM GHOSH & SONS | 2.88 | 0 | 90
552 | Jalpaiguri Division | Jalpaiguri Division | Construction of different balance components of Jalapara PWSS in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000829/2023-2024 | 2757/JD | 15/03/2024 | 746 | ANUP KUMAR KUNDU | 88.77 | 0 | 5
553 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000008/2024-2025 | 54/JD | 09/04/2024 | 0 | Resource Division | 114.02 | 0 | 0
554 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
555 | Jalpaiguri Division |  | Construction of different components of Changmarihat Zone-III PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000176/2023-2024 | 847/JD | 28/07/2023 | 882 | S & P ENTERPRISE | 234.9 | 10.29 | 10
556 | Jalpaiguri Division |  | Construction of different components of Changmarihat Zone-II PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000177/2023-2024 | 848/JD. | 28/07/2023 | 882 | S & P ENTERPRISE | 367.87 | 118.79 | 65
557 | Jalpaiguri Division |  | Construction of different components of changmarihat Zone-I PWSS i.e TW, Pump House , Water distribution Network , OHR , Boundary wall , RISING MAIN , FHTC etc . In connection with Jal Jeevan Mission at Block kranti under Jalpaiguri Division , P.H.E Dte. |  |  | ORD/000178/2023-2024 | 849/JD. | 28/07/2023 | 882 | S & P ENTERPRISE | 398.61 | 241.91 | 25
558 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 148/JD | 28/04/2023 | 0 | Resource Division | 76.45 | 0 | 0
559 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 2071/JD | 10/01/2024 | 0 | Resource Division | 22.22 | 0 | 0
560 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-II) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000050/2021-2022 | 1073/JD | 02/07/2021 | 30 | BISWAJIT BHADURI | 27.41 | 0 | 0
561 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000053/2021-2022 | 1072/JD | 02/07/2021 | 30 | SAHA CONSTRUCTION | 23.05 | 0 | 1
562 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-F) |  | Junior Engineer | ORD/000054/2021-2022 | 1074/JD | 02/07/2021 | 45 | M/S SIBU DEY AND CO. | 36.93 | 0 | 0
563 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under Arji Garalbari piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. (Part ¿ E) |  | Junior Engineer | ORD/000122/2021-2022 | 521/RWS | 30/07/2021 | 15 | RANJIT KARMAKAR | 4.75 | 0 | 0
564 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting work related to FHTC at Balipara, Hazaripara and adjacent area within Garalbari zone-II W/S Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000133/2022-2023 | 1552/JD | 05/08/2022 | 21 | BISWAJIT BHADURI | 18.01 | 18 | 0
565 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under garalbari Zone- iii piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. ( part - c) |  | Junior Engineer | ORD/000158/2021-2022 | 479/RWS | 23/07/2021 | 15 | NARAYAN SARKAR | 2.53 | 0 | 0
566 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing and renovation of Boundary walls ( 2nd site ),pump house , including O.H.R for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte Jalpaiguri. |  | Junior Engineer | ORD/000175/2021-2022 | 681/RWS | 27/09/2021 | 30 | BISWAJIT BHADURI | 4.67 | 0 | 1
567 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Over Hauling of the Iron Elimination plant at 2nd site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000176/2021-2022 | 682/RWS | 27/09/2021 | 20 | BISWAJIT BHADURI | 3.9 | 0 | 0
568 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Over Hauling of the Iron Elimination plant at H/W site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000179/2021-2022 | 684/RWS | 27/09/2021 | 20 | BISWAJIT BHADURI | 3.9 | 0 | 1
569 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri |  | Junior Engineer | ORD/000200/2019-2020 | 302/JD | 17/03/2020 | 120 | BILTU DAS | 47.59 | 0 | 0
570 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) |  | Junior Engineer | ORD/000202/2022-2023 | 1741/JD | 08/09/2022 | 45 | PROVA CONSTRUCTION | 75.59 | 0 | 100
571 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Krishimandi, Petrol pump and adjacent area within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-L) |  | Junior Engineer | ORD/000234/2022-2023 | 1862/JD | 20/09/2022 | 25 | ASIM GUPTA | 15.65 | 15.64 | 1
572 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-G) |  | Junior Engineer | ORD/000268/2021-2022 | 2035/JD | 07/12/2021 | 21 | SOMNATH ROY | 17.26 | 0 | 0
573 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-H) |  | Junior Engineer | ORD/000269/2021-2022 | 2036/JD | 07/12/2021 | 21 | J.M. CONSTRUCTION | 13.14 | 0 | 0
574 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Garalbari Zone ¿ I . W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ C ) |  | Junior Engineer | ORD/000323/2021-2022 | 874/RWS | 08/12/2021 | 10 | SAPTASWA SARKAR | 2.71 | 0 | 0
575 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000354/2020-2021 | 34/RWS | 28/01/2021 | 15 | NARAYAN SARKAR | 4.82 | 0 | 0
576 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Nijbari,Hazari Para,Ambari,Harinagar for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000517/2021-2022 | 161/RWS | 28/02/2022 | 15 | BISWAJIT BHADURI | 4.85 | 0 | 0
577 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Baraghaoria, Bhutiakhola for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000519/2021-2022 | 164/RWS | 28/02/2022 | 15 | BISWAJIT BHADURI | 2.21 | 0 | 0
578 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofiting works at Tariapara, Barua para, Nawa para, Khansaheb para related to FHTC for Garalbari Zone ¿I WSS under Jalpaiguri Division , P.H.E. Dte. |  | Junior Engineer | ORD/000523/2021-2022 | 171/RWS | 03/03/2022 | 15 | SAPTASWA SARKAR | 3.84 | 0 | 0
579 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal sapna under the command area of Garalbari zone - I. Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte ( Part - D ) |  | Junior Engineer | ORD/000524/2021-2022 | 172/RWS | 03/03/2022 | 15 | SAHA CONSTRUCTION | 3.41 | 0 | 0
580 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001084/2021-2022 | BP-2021-22-160 | 14/01/2022 | 0 | NARAYAN SARKAR | 2.6 | 0 | 0
581 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001092/2021-2022 | BP-2021-22-145 | 14/01/2022 | 0 | M/S SIBU DEY AND CO. | 37.86 | 0 | 0
582 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001093/2021-2022 | BP-2021-22-146 | 14/01/2022 | 0 | SAHA CONSTRUCTION | 23.03 | 0 | 0
583 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | retrofitting work for goralbari pwss |  | Junior Engineer | VCH/001156/2021-2022 | BP-2021-22-253 | 22/02/2022 | 0 | NEW KUNDU ENTERPRISE | 1.33 | 0 | 0
584 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing fhtc for boalmari pwss |  | Junior Engineer | VCH/001157/2021-2022 | BP-2021-22-254 | 22/02/2022 | 0 | KANAI LAL SEN | 3.62 | 0 | 0
585 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FROVIDING FHTC FOR SAMSING T.G |  | Junior Engineer | VCH/001160/2021-2022 | BP-2021-22-258 | 22/02/2022 | 0 | M/S. D.K. DEY & CO.. | 29.06 | 0 | 0
586 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC PORAPARA |  | Junior Engineer | VCH/001164/2021-2022 | BP-2021-22-270 | 22/02/2022 | 0 | DEBASISH DEY | 5.57 | 0 | 0
587 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | water sup[ply arrangement for angawari center |  | Junior Engineer | VCH/001167/2021-2022 | BP-2021-22-277 | 22/02/2022 | 0 | R.S CONSTRUCTION | 18.98 | 0 | 0
588 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | retrofittinbg work for kajaldighi |  | Junior Engineer | VCH/001168/2021-2022 | BP-2021-22-237 | 22/02/2022 | 0 | R.S CONSTRUCTION | 4.54 | 0 | 0
589 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing fhtc yong tong t.g |  | Junior Engineer | VCH/001170/2021-2022 | BP-2021-22-236 | 23/02/2022 | 0 | ASHIT KUMAR SINGHA | 8.71 | 0 | 0
590 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DABGRAM |  | Junior Engineer | VCH/001181/2021-2022 | BP-2021-22-282 | 23/02/2022 | 0 | NARAYAN CHAKRABORTY | 24.81 | 0 | 0
591 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SONGACHI T.GG |  | Junior Engineer | VCH/001184/2021-2022 | BP-2021-22-2291 | 23/02/2022 | 0 | M/S M.B. DESIGN | 15.73 | 0 | 0
592 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORALBARI |  | Junior Engineer | VCH/001209/2021-2022 | BP-2021-22-324 | 28/02/2022 | 0 | BISWAJIT BHADURI | 3.87 | 0 | 0
593 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBA MAGURMARI |  | Junior Engineer | VCH/001220/2021-2022 | BP-2021-22-335 | 03/03/2022 | 0 | MONOJ GHOSH | 7.74 | 0 | 0
594 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBA MAGURMARI |  | Junior Engineer | VCH/001221/2021-2022 | BP-2021-22-334 | 03/03/2022 | 0 | ARATI CONSTRUCTION | 7.42 | 0 | 0
595 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC NAYASYLI |  | Junior Engineer | VCH/001222/2021-2022 | BP-2021-22-336 | 03/03/2022 | 0 | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0
596 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc rej nagrakata |  | Junior Engineer | VCH/001226/2021-2022 | BP-2021-22-338 | 03/03/2022 | 0 | ANUP KUMAR KUNDU | 28.29 | 0 | 0
597 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc charer bari |  | Junior Engineer | VCH/001227/2021-2022 | BP-2021-22-337 | 03/03/2022 | 0 | NEW KUNDU ENTERPRISE | 2.44 | 0 | 0
598 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc bhangarhat |  | Junior Engineer | VCH/001228/2021-2022 | BP-2021-22-341 | 03/03/2022 | 0 | BILTU DAS | 26.16 | 0 | 0
599 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORKS GORALBARI ZONE II |  | Junior Engineer | VCH/001344/2021-2022 | BP-2021-22-413 | 23/03/2022 | 0 | BISWAJIT BHADURI | 2.21 | 0 | 0
600 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001428/2021-2022 | BP-2021-22-448 | 26/03/2022 | 0 | ASHIM GUPTA | 62.4 | 0 | 0
601 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001429/2021-2022 | BP-2021-22-450 | 26/03/2022 | 0 | BISWAJIT BHADURI | 27 | 0 | 0
602 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORKS FHTC GORALBARI ZONE II |  | Junior Engineer | VCH/001800/2020-2021 | BP-2021-22- 414 | 23/03/2022 | 0 | BISWAJIT BHADURI | 4.84 | 0 | 0
603 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-D) |  | Junior Engineer | ORD/000067/2021-2022 | 59/JSSD | 12/05/2021 | 15 | PRITAM DUTTA | 1.87 | 3.47 | 0
604 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-C) |  | Junior Engineer | ORD/000072/2021-2022 | 63/JSSD | 13/05/2021 | 15 | BIMAN DAS | 2.34 | 0 | 0
605 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-B) |  | Junior Engineer | ORD/000075/2021-2022 | 68/JSSD | 19/05/2021 | 15 | NABIN PRODHAN | 2.35 | 0 | 0
606 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Engo T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000243/2020-2021 | 561/JSSD | 01/02/2021 | 15 | JOYDEB SAHA | 4.64 | 9.28 | 0
607 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Preparation of D.P.R. (consultancy work) in connection with Augmentation of Matially PWSS (Matially block) under Jalpaiguri Division PHED |  | Junior Engineer | ORD/000539/2021-2022 | .93/JSSD | 10/06/2021 | 30 | SUBHANKAR GHOSH | 1.99 | 0 | 0
608 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000055/2021-2022 | 1075/JD | 02/07/2021 | 30 | ARATI CONSTRUCTION | 24.34 | 17.45 | 1
609 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works at various mouza under command area of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2022-2023 | 1291/JD | 14/06/2022 | 21 | ARATI CONSTRUCTION | 4.8 | 4.78 | 1
610 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna at Purba Magurmari and Paschim Magurmari village under the command area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000188/2021-2022 | 1690/JD | 28/10/2021 | 30 | ANUP SARKAR | 24.44 | 0 | 1
611 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Purba Magurmari and Paschim Magurmari and Jhar Magurmari village under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000266/2021-2022 | 2044/JD | 07/12/2021 | 21 | ARATI CONSTRUCTION | 39.59 | 0 | 1
612 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PURBA MAGURMARI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000313/2020-2021 | 291/JD | 23/02/2021 | 30 | A.P CONSTRUCTION | 24.41 | 0 | 1
613 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 30
614 | Jalpaiguri Division | Jalpaiguri Division | Laying of Distribution System along with Functional Household Tap Connection (Phase-VI) in connection with Jal Jeevan Mission under Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000425/2022-2023 | 628/JD | 13/03/2023 | 765 | SANKAR DAS | 43.78 | 35.59 | 60
615 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000074/2024-2025 | 2205/JD | 01/12/2024 | 0 | Resource Division | 28.93 | 0 | 0
616 | Jalpaiguri Division | Jalpaiguri Division | fhtc for purba magurmari pwsws | Assistant Engineer,HQ | Junior Engineer | VCH/000461/2021-2022 |  | 21/10/2021 | 0 | ARATI CONSTRUCTION | 17.45 | 0 | 0
617 | Jalpaiguri Division | Jalpaiguri Division | fhtc for purba magurmari pwss | Assistant Engineer,HQ | Junior Engineer | VCH/000462/2021-2022 |  | 21/10/2021 | 0 | MONOJ GHOSH | 16.71 | 0 | 0
618 | Jalpaiguri Division | Jalpaiguri Division | FHTC PURBA MAGURMARI | Assistant Engineer,HQ | Junior Engineer | VCH/000793/2021-2022 | BP-2021-22-90 | 01/11/2021 | 0 | MANOJ GHOSH | 16.71 | 0 | 0
619 | Jalpaiguri Division | Jalpaiguri Division | Construction of Different Components of Supply Of Potable Drinking Water To Red Bank Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000589/2023-2024 | 2331/JD | 08/02/2024 | 449 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 90.89 | 35.71 | 75
620 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000022/2024-2025 | 2104/JD | 25/11/2024 | 0 | Resource Division | 3.02 | 0 | 0
621 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF DIFFERENT STATIONARY FOR OFFICE USE |  | Junior Engineer | BILL/00462/2023-2024 | BP-2023-24-363 | 13/09/2023 | 0 | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 4.59 | 0 | 0
622 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & lubricant for Vehicle No:- WMA-2539, WB-71A-5774 FOR THE MONTH OF APRIL, MAY ,& OCTOBER |  | Junior Engineer | BILL/00948/2023-2024 | BP-2023-24-545 | 18/12/2023 | 0 | FILL & SMILE | 0.54 | 0 | 0
623 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF ONE MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 C.C. ON HIRE BESIS INCLUDING DRIVER UNDER OFFICE OF THE ASSISTANT ENGINEER ,JALPAIGURI SADAR SUB DIVISION , P.H.E Dte. |  | Junior Engineer | BILL/01046/2023-2024 | BP-2023-24-592 | 16/01/2024 | 0 | MRITYUNJAY SIKDAR | 0.54 | 0 | 0
624 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL for vehicle FOR OFFICE OF THE ASSISTANT ENGINEER , JALPAIGURI SADAR SUB DIVISION, P.H.E Dte. |  | Junior Engineer | BILL/01047/2023-2024 | BP-2023-24-591 | 16/01/2024 | 0 | FILL & SMILE | 1.02 | 0 | 0
625 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250mm x 150mm dia tube wells by Reverse Rotary method of drilling for Augmentation of Kharija Berubari Zone-I PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division (H/W and 2nd Site) |  | Junior Engineer | ORD/000003/2023-2024 | 848/JD | 06/04/2023 | 30 | SHYAMAL KUMARSAHA | 17.39 | 17.17 | 100
626 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of Additional 1 No Tube Well by Reverse Rotary Method including construction Pump House, Boundary Wall and installation of Iron Elimination Plant (IEP) and Inter Connection work at Gosaimore under Nagar Berubari GP of Augmentation of Kharija Berubari Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000006/2025-2026 | 678/JD | 04/04/2025 | 120 | KANAI LAL SEN | 38.97 | 0 | 0
627 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution system and functional household tap connection for Augmentation of Kharija Berubari Zone-I piped Water Supply Scheme Block- Jalapiguri, District - Jalpaiguri. |  | Junior Engineer | ORD/000019/2022-2023 | 1066/JD | 28/04/2022 | 1283 | M/S R.N. TRADERS | 605.44 | 385.99 | 85
628 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection for Augmentation of Kharija Berubari Zone-II Piped Water Supply Scheme Block - Jalpaiguri District - Jalpaiguri. |  | Junior Engineer | ORD/000038/2022-2023 | 1099/JD | 12/05/2022 | 120 | BANSBERIA CONSTRUCTION CO. | 554.56 | 503.06 | 90
629 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Kharija Berubari - II Pipe Water Supply Scheme under Jalpaiguri Sadar Block Within Jalpaiguri PHE Division, Jalpaiguri. |  | Junior Engineer | ORD/000086/2024-2025 | 1176/JD | 23/08/2024 | 586 | NARAYAN CHANDRA SAHA | 72.2 | 0 | 80
630 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement and Boundary Wall, Foot Path, Drain of 2nd Site at Kharija - I Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000124/2024-2025 | 1369/JD | 13/09/2024 | 566 | ALICK DUTTA | 12.67 | 6.41 | 65
631 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 400 m3 OHR as per Departmental Design & Drawing & Pump House (3.60m x 2.40m) internal size with sanitary & Plumbing arrangement at Head Work site for AUGMENTATION OF KHARIJA BERUBARI (Zone-I) Piped Water Supply Scheme Block- Jalpaiguri, District : Jalpaiguri. |  | Junior Engineer | ORD/000250/2022-2023 | 1845//JD | 15/09/2022 | 180 | SUKES BASU MAJUMDAR | 87.97 | 89.05 | 100
632 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF KHARIJA BERUBARI PIPED WATER SUPPLY SCHEME (ZONE-II), Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000454/2021-2022 | 335/JD | 02/02/2022 | 120 | NARAYAN CHANDRA SAHA | 97.85 | 71.39 | 100
633 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.01.2024 to 29.02.2024) |  | Junior Engineer | ORD/000563/2023-2024 | 2121/JD | 17/01/2024 | 60 | GURUKUL INFOTECH | 3.16 | 3.16 | 50
634 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different forms for office use under jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000822/2023-2024 | 2721/JD | 12/03/2024 | 7 | SUBRATA ART PRESS | 0.7 | 0.7 | 100
635 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.03.2024 to 30.04.2024)" |  | Junior Engineer | ORD/000865/2023-2024 | 2488/JD | 27/02/2024 | 60 | GURUKUL INFOTECH | 3.16 | 3.16 | 100
636 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall including repairing of Pump House at 2nd Site for Kharija Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001044/2021-2022 | 1438/JD | 09/09/2021 | 30 | PROFULLA GHOSH | 9.74 | 0 | 0
637 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000012/2021-2022 | 559/JD | 01/03/2022 | 0 | Resource Division | 96.47 | 0 | 0
638 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000087/2024-2025 | 2215/JD | 01/12/2024 | 0 | Resource Division | 35.61 | 0 | 0
639 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION |  | Junior Engineer | VCH/001199/2021-2022 | BP-2021-22-316 | 28/02/2022 | 0 | MOYTEC | 2.03 | 0 | 0
640 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK AUGMENTATION KHARIJA BERUBARI (ZONE -I) PWSS |  | Junior Engineer | VCH/001276/2021-2022 | BP-2021-22-353 | 08/03/2022 | 0 | GEOCON INDIA | 2.03 | 0 | 0
641 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of fuel |  | Junior Engineer | BILL/00209/2023-2024 | BP-2023-24-117 | 01/06/2023 | 0 | FILL & SMILE | 0.66 | 0 | 0
642 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Caron Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000009/2022-2023 | 870/JD | 04/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 13.46 | 100
643 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of rejuvenation of Carron Tea Garden PWSS at 4th TW site i.e. Steel staging OHR, Water Distribution Network, FHTC, interconnection, etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000036/2024-2025 | 939/JD | 07/08/2024 | 603 | SANKAR DAS | 15.03 | 0 | 90
644 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at CARRON Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. |  | Junior Engineer | ORD/000114/2022-2023 | 112/JSSD | 27/07/2022 | 15 | SANDIP BANIK | 4.75 | 3.32 | 100
645 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Carron T.G piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000197/2021-2022 | 470/JSSD | 05/10/2021 | 15 | SANDIP BANIK | 4.63 | 9.07 | 0
646 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 |  | Junior Engineer | ORD/000368/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.44 | 0 | 0
647 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Rejuvenation of Carron Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000481/2022-2023 | 800/JD.. | 29/03/2023 | 614 | TECHNO CRACY | 2.84 | 1.89 | 100
648 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.04.2023 to 30.04.2023. |  | Junior Engineer | ORD/000510/2022-2023 | 503/JSSD | 30/03/2023 | 30 | TANMOY CHOUDHURY | 0.15 | 0.24 | 0
649 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 |  | Junior Engineer | ORD/000597/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.45 | 0.06 | 0
650 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall with gate, drain and pathway for 4th tube well site at Caron T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000727/2021-2022 | 1042/JSSD | 24/01/2022 | 20 | SK. MOBIN HUSSAIN | 3.75 | 0 | 0
651 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M X 2.40 M)size with sanitary & plumbing arrangement at 3rd Tube-Well site for Caron T.G.PWSS under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000893/2021-2022 | 1027/W/JSSD | 31/01/2022 | 1021 | SARKAR ASSOCIATES | 4.64 | 4.64 | 100
652 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Caron T.G. P.W.S.S under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/001127/2021-2022 | 1011/W/JSSD | 27/01/2022 | 1071 | GOURAB GUHA ROY | 3.76 | 0 | 100
653 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000027/2024-2025 | 2096/JD | 25/11/2024 | 0 | Resource Division | 5.22 | 0 | 0
654 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
655 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
656 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional work for Laying pipe line at Dakshin Putimari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000081/2024-2025 | 1171/JD | 23/08/2024 | 586 | PAMPA CONSTRUCTION | 20.26 | 0 | 65
657 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dakshin Putimari PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN , FHTC etc. in connection with JJM at Block - Maynaguri under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000467/2022-2023 | 778/JD | 27/03/2023 | 1102 | ASHIT KUMAR SINGHA | 363.4 | 145.33 | 45
658 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with gate, drain, Land development, pathway at H/W site and 2nd site including laying pipe line and FHTC work at Dakshin Putimari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte i.c.w. JJM . |  | Junior Engineer | ORD/000561/2024-2025 | 115/JD | 16/01/2025 | 440 | ASHIT KUMAR SINGHA | 35.9 | 0 | 65
659 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000017/2023-2024 | 161/JD | 28/04/2023 | 0 | Resource Division | 131.96 | 0 | 0
660 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000176/2023-2024 | 2058/JD | 09/01/2024 | 0 | Resource Division | 8.7 | 0 | 0
661 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
662 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
663 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of IEP and Blower Room of Uttar Dhupjhora PWSS in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000232/2024-2025 | 2329./JD | 12/12/2024 | 264 | BOSE ENTERPRISE | 17.26 | 0 | 20
664 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Uttar Dhupjhora PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000446/2022-2023 | 716/JD | 20/03/2023 | 835 | BOSE ENTERPRISE | 231.68 | 202.41 | 50
665 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000001/2023-2024 | 176/JD | 28/04/2023 | 0 | Resource Division | 16.8 | 0 | 0
666 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000169/2023-2024 | 2035/JD | 09/01/2024 | 0 | Resource Division | 7.13 | 0 | 0
667 | Jalpaiguri Division | Jalpaiguri Division | Balance work of Distribution System for Uttar Altagram Piped Water Supply Scheme within Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000167/2025-2026 | 2002/JD | 25/09/2025 | 90 | KAMAL DAS | 72.36 | 0 | 60
668 | Jalpaiguri Division | Jalpaiguri Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Dhupguri block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer,HQ | Junior Engineer | ORD/000473/2023-2024 | 1293/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
669 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000036/2023-2024 | 1116/JD | 24/08/2023 | 0 | Resource Division | 23.05 | 0 | 0
670 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000127/2023-2024 | 1841/JD | 15/12/2023 | 0 | Resource Division | 11.08 | 0 | 0
671 | Jalpaiguri Division | Jalpaiguri Division | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000030/2024-2025 | 692/JD | 19/07/2024 | 120 | B.M CONSTRUCTION | 50.78 | 50.78 | 100
672 | Jalpaiguri Division | Jalpaiguri Division | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. (Part- B) | Assistant Engineer,HQ | Junior Engineer | ORD/000177/2024-2025 | 1533/JD | 01/10/2024 | 45 | SUKES BASU MAJUMDAR | 66.83 | 24.95 | 100
673 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Sinking of Additional Tube Well by Reverse Rotary including construction of Pump House and laying Rising Main etc. in connection with Jal Jeevan Mission of Madhya Daukimari PWSS at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000606/2024-2025 | 456/JD | 10/03/2025 | 387 | B. M CONSTRUCTION | 71.85 | 0 | 0
674 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000018/2023-2024 | 162/JD | 28/04/2023 | 0 | Resource Division | 103.77 | 0 | 0
675 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000133/2023-2024 | 1879/JD | 20/12/2023 | 0 | Resource Division | 11.14 | 0 | 0
676 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with FHTC works for the habitation of Dangar Bari , Fokkorer Bari , near Chandrakanta School & Providing balanced Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangamali Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000167/2022-2023 | 1418/JD | 14/07/2022 | 15 | MRINMOY KANTI DUTTA | 4.62 | 2.11 | 1
677 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORK SITES OF DIFFERENT PWSS AT NAGRAKATA ,MATIALI , AND MAL BLOCK UNDER JALPAIGURI |  | Junior Engineer | BILL/00936/2024-2025 |  | 22/11/2024 | 0 | DR. AMBARISH GHOSH | 17.82 | 0 | 0
678 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.05.2024 to 30.06.2024)" |  | Junior Engineer | ORD/000037/2024-2025 | 143/JD | 29/04/2024 | 61 | GURUKUL INFOTECH | 3.16 | 3.16 | 100
679 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Gajoldoba Tea Garden Piped Water Supply Scheme i.e, TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000071/2023-2024 | 422/A/JD | 07/06/2023 | 938 | M/S SIBU DEY AND CO. | 262.74 | 89.62 | 20
680 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
681 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Gajoldoba TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000317/2024-2025 | 2038/JD | 21/11/2024 | 90 | M/S SIBU DEY AND CO. | 83.02 | 0 | 50
682 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Protective Boulder Work, Land Development and approach road inside the premises at H/W Site for Gajaldoba Tea Garden PWSS in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000478/2024-2025 | 2429/JD | 24/12/2024 | 45 | M/S SIBU DEY AND CO. | 23.79 | 1.56 | 50
683 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sub-Soil Investigation of proposed 300 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Gajaldoba Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000801/2024-2025 | 88-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
684 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000077/2023-2024 | 1080/JD | 24/08/2023 | 0 | Resource Division | 25.38 | 0 | 0
685 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000159/2023-2024 | 2025/JD | 09/01/2024 | 0 | Resource Division | 12.26 | 0 | 0
686 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
687 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Washabari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000115/2023-2024 | 395/A/JD | 05/06/2023 | 844 | S.S. CONSTRUCTION | 269.38 | 0 | 65
688 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000067/2023-2024 | 1072/JD | 24/08/2023 | 0 | Resource Division | 27.2 | 0 | 0
689 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000157/2023-2024 | 2021/JD | 09/01/2024 | 0 | Resource Division | 8.08 | 0 | 0
690 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Rejuvenation of Jabramali PWSS i.e. TW, Pump Houses, Water distribution Network, Boundary wall, RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000361/2023-2024 | 1435/JD | 05/10/2023 | 910 | RAGHU DAS | 83.33 | 17.58 | 80
691 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works & other ancillary works related to FHTC at different places of Jabramali PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000433/2022-2023 | 629/JD | 13/03/2023 | 30 | DREAM CONSTRUCTION | 12.41 | 12.39 | 100
692 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Drainage line for IEP & other ancillary works at Head work site of JABRAMALI PWSS under Jalpaiguri Divisiopn PHE Dte. |  | Junior Engineer | ORD/000447/2023-2024 | 1281/RWS | 28/11/2023 | 20 | RAGHU DAS | 3.04 | 2.96 | 100
693 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000094/2023-2024 | 1050/JD | 24/08/2023 | 0 | Resource Division | 4.8 | 0 | 0
694 | Jalpaiguri Division | Jalpaiguri Division | Construction of 4th Pump House Site Boundary Wall, Foot Path, Drain pipeline for washout including interconnection works at Chauhaddi PWSS in connection with Jal Jeevan Mission at Block - Dhupguri Block under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000044/2025-2026 | 76/JSSD | 02/06/2025 | 30 | HARIPADA BANERJEE | 9.54 | 0 | 0
695 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 30
696 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Samsing Tea Garden Piped Water Supply Scheme i.e TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000140/2023-2024 | 698/JD | 13/07/2023 | 903 | M/S. D.K. DEY & CO.. | 137.45 | 16.12 | 38
697 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Samsing T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000170/2020-2021 | 1304/JD | 24/11/2020 | 60 | LOKNATH CONSTRUCTIOIN | 32.08 | 0 | 1
698 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Water Distribution Network in Chalsa Zone-I in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000838/2023-2024 | 1938/JD | 02/01/2024 | 30 | ALICK DUTTA | 17.21 | 17.08 | 50
699 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000081/2023-2024 | 1070/JD | 24/08/2023 | 0 | Resource Division | 19.77 | 0 | 0
700 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Dakshin Kantadighi Kumarpara PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Mal under |  | Junior Engineer | ORD/000468/2022-2023 | 754/JD | 24/03/2023 | 817 | B RAI CONSTRUCTION COMPANY | 134.73 | 48.21 | 50
701 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000005/2023-2024 | 149/JD | 28/04/2023 | 0 | Resource Division | 13.53 | 0 | 0
702 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000153/2023-2024 | 2011/JD | 09/01/2024 | 0 | Resource Division | 2.64 | 0 | 0
703 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
704 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
705 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Uttar Mouamari PWSS i.e TW, Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc,i.c.w.Jal Jeevan Mission at Block-Maynaguri under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000072/2023-2024 | 699/JD | 13/07/2023 | 993 | M/S SIBU DEY AND CO. | 250.23 | 149.78 | 60
706 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall with gate, drain, Land Development and pathway and Laying Pipe line at H/W site of Uttar Mouamari Piped Water Supply Scheme under Jalpaiguri Division PHE, DTE. |  | Junior Engineer | ORD/000088/2024-2025 | 1298/JD | 05/09/2024 | 191 | M/S SIBU DEY AND CO. | 24 | 3.02 | 85
707 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000075/2023-2024 | 1084/JD | 24/08/2023 | 0 | Resource Division | 47.75 | 0 | 0
708 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000196/2023-2024 | 2059/JD | 10/01/2024 | 0 | Resource Division | 7.17 | 0 | 0
709 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000059/2021-2022 | 1085/JD | 05/07/2021 | 20 | GOUTAM DAS | 10.27 | 0 | 0
710 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KAJALDIGI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-C). |  | Junior Engineer | ORD/000088/2020-2021 | 1276/JD | 18/11/2020 | 90 | NISHITH RANJAN KARMAKAR | 39.12 | 78.21 | 0
711 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldigi Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000106/2020-2021 | 442/RWS | 09/10/2020 | 30 | M/S.PAMPA CONSTRACTION | 4.73 | 4.71 | 0
712 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-D). |  | Junior Engineer | ORD/000398/2020-2021 | 74/RWS | 19/02/2021 | 15 | R.S CONSTRUCTION | 4.76 | 9.5 | 0
713 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc jiti |  | Junior Engineer | VCH/000347/2021-2022 |  | 05/10/2021 | 0 | CALCON CONSTRUCTIONS | 17.1 | 0 | 0
714 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC KAJAL DIGHI |  | Junior Engineer | VCH/000906/2021-2022 | BP-2021-22-133 | 14/12/2021 | 0 | PRAHLAD PRASAD SAHA | 4.83 | 0 | 0
715 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC KAJALDIGHI |  | Junior Engineer | VCH/000909/2021-2022 | BP-2021-22-131 | 14/12/2021 | 0 | R.S CONSTRUCTION | 4.71 | 0 | 0
716 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING HOUSE CONNECYTION AT KAJALDIGHI PWSS |  | Junior Engineer | VCH/001152/2020-2021 | 1055 | 11/01/2021 | 0 | R.S CONSTRUCTION | 4.44 | 0 | 0
717 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC LATAGURI, MOULANI, KRANTI GP |  | Junior Engineer | VCH/001298/2021-2022 | BP-2021-22-467 | 28/03/2022 | 0 | SAHA CONSTRUCTION | 2.2 | 0 | 0
718 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Simulguri PWSS Zone-I, II and III i.e. TW, Pump Houses, Water distribution , Water distribution Network , OHR, Rising Main , FHTC etc. Block - Rajganj under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000493/2022-2023 | 823/JD | 30/03/2023 | 733 | S.S. CONSTRUCTION | 709.21 | 586.27 | 75
719 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall with gate, Drain, Land development ,Pathway at H/W Site & 2nd T/W site at Zone-I, H/W site , 2nd T/W & 3rd T/W site at Zone-II and H/W Site & 2nd T/W site at Zone-III including balance portion of laying distribution system with providing FHTC at SIMULGURI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000537/2024-2025 | 571/JD | 25/03/2025 | 372 | NEW KUNDU ENTERPRISE | 165.71 | 0 | 55
720 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000009/2023-2024 | 153/JD | 28/04/2023 | 0 | Resource Division | 38.37 | 0 | 0
721 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000180/2023-2024 | 2045/JD | 09/01/2024 | 0 | Resource Division | 18.16 | 0 | 0
722 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
723 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
724 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dakshin Dangapara PWSS Zone- II i.e, TW, Pump Houses, Water distribution Network, OHR, IEP, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block Maynaguri under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000084/2023-2024 | 296/JD | 15/05/2023 | 903 | M/S SURAJIT DEY AND CO. | 375.71 | 223.28 | 60
725 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site of Dakhindangapara Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE DTE. |  | Junior Engineer | ORD/000087/2024-2025 | 1172/JD | 23/08/2024 | 528 | M/S SURAJIT DEY AND CO. | 23.37 | 0 | 80
726 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dakshin Dangapara Zone II PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000527/2024-2025 | 109/JD | 16/01/2025 | 45 | M/S SURAJIT DEY AND CO. | 48.72 | 0 | 0
727 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000193/2023-2024 | 2032/JD | 09/01/2024 | 0 | Resource Division | 8.53 | 0 | 0
728 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Bhemtia PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000005/2023-2024 | 02/JD | 06/04/2023 | 947 | SCEC BOENTER KDAS JOINT VENTURE | 209.41 | 0 | 30
729 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation including liquefaction due to close proximity of railway track near the proposed 100 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Bhemtia Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000803/2024-2025 | 93-HQ/JD | 17/03/2025 | 20 | R.B TESTING | 0.98 | 0 | 0
730 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000012/2023-2024 | 156/JD | 28/04/2023 | 0 | Resource Division | 16.82 | 0 | 0
731 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000135/2023-2024 | 1882/JD | 20/12/2023 | 0 | Resource Division | 4.11 | 0 | 0
732 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Purba Dobbari PWSS i.e. TW, Pump Houses, Water distribution Network, Stand alone Mini OHR, RISING MAIN, FHTC etc.i.c.w. Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000076/2023-2024 | 946/JD | 08/08/2023 | 693 | SOMNATH ROY | 38.25 | 8.92 | 70
733 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000195/2023-2024 | 2054/JD | 09/01/2024 | 0 | Resource Division | 0.18 | 0 | 0
734 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall at H/W site including rising main and interconnections of Tandu Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000013/2024-2025 | 474/JD | 21/06/2024 | 45 | PRADIP SAHA | 15.98 | 16.2 | 100
735 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
736 | Jalpaiguri Division | Northern Mechanical Division | Sinking of 2 (Two) Nos. Big Dia Tube well by Modified DTH - ODEX Method at 1st & 2nd tube well site of Chhar Tandu and adjacent area Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000110/2024-2025 | 1415/JD | 20/09/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 27.63 | 100
737 | Jalpaiguri Division | Northern Mechanical Division | Laying Distribution System along with laying of Rising Main, Pump Connection & Construction of 2 Nos. Pump House at 1st & 2nd Tube Well Site of Adjacent area of Chhar Tandu and Adjacent area Piped Water Sypply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000465/2025-2026 | 2498/JD | 09/12/2025 | 75 | ARUP SARKAR | 36.8 | 0 | 0
738 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall at H/W site of Upper Tendu Forest (M) PWSS in connection with Jal Jeevan Mission at Block Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000540/2023-2024 | 295/JSSD | 27/09/2023 | 45 | NISHITH RANJAN KARMAKAR | 7.99 | 7.96 | 100
739 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
740 | Jalpaiguri Division | Northern Mechanical Division | Construction of Different Components of Tesimla PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000266/2023-2024 | 938/JD | 08/08/2023 | 180 | M/S RATAN KUMAR DAS GUPTA AND CO | 218.57 | 105.44 | 68
741 | Jalpaiguri Division | Northern Mechanical Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Tesimala PWSS i.e. Tube Well, Pump House, Boundary Wall in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000547/2024-2025 | 104/JD | 15/01/2025 | 70 | APEX ENGINEERING | 39.7 | 0 | 0
742 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000161/2023-2024 | 2014/JD | 09/01/2024 | 0 | Resource Division | 7.02 | 0 | 0
743 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Maynatali PWSS , in connection with Rejuvenation of Maynatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000132/2023-2024 | 405/A/JD | 06/06/2023 | 792 | ABHIJIT SARKAR | 47.88 | 36.8 | 25
744 | Jalpaiguri Division | Jalpaiguri Division | Providing FHTC and Installation of Sluice Valve at different strategic point in connection with JJM of Mainatali Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000591/2024-2025 | 466/JD | 11/03/2025 | 385 | ARUP SARKAR | 24.16 | 0 | 0
745 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000101/2023-2024 | 1057/JD | 24/08/2023 | 0 | Resource Division | 4.7 | 0 | 0
746 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of BHANDANI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-II |  |  | ORD/000207/2020-2021 | 42/JD | 06/01/2021 | 90 | DULAL CHOUDHURY | 38.46 | 12.41 | 1
747 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Bhandani piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) |  |  | ORD/000210/2020-2021 | 49/JD | 07/01/2021 | 60 | ASIM GUPTA | 39.45 | 78.83 | 1
748 | Jalpaiguri Division |  | FHTC BHANDANI |  |  | VCH/000249/2022-2023 | BP-2022-23-66 | 04/07/2022 | 0 | DULAL CHOUDHURY | 8.03 | 0 | 0
749 | Jalpaiguri Division |  | FHTC BHANDABNI PWSS |  |  | VCH/000325/2021-2022 |  | 01/10/2021 | 0 | ASIM GUPTA | 18.14 | 0 | 0
750 | Jalpaiguri Division |  | FHTC BHANDANI PWSS |  |  | VCH/000339/2021-2022 |  | 04/10/2021 | 0 | ASIM GUPTA | 18.14 | 0 | 0
751 | Jalpaiguri Division |  | providing fhtc for Mathachulka pwss |  |  | VCH/000376/2021-2022 | 281 | 26/09/2021 | 0 | DEEP CONSTRUCTION | 4.67 | 0 | 0
752 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00760/2024-2025 | BP-2024-25-448 | 03/10/2024 | 0 | FILL & SMILE | 0.09 | 0 | 0
753 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00852/2024-2025 | BP-2024-25-484 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
754 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00985/2024-2025 | BP-2024-25-549 | 17/12/2024 | 0 | FILL & SMILE | 0.16 | 0 | 0
755 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19/08/2024 to 18/02/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000079/2024-2025 | 1025/JD | 16/08/2024 | 184 | AJIJUL HAQUE | 0.88 | 0.91 | 0
756 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Salugara PWSS zone-II i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000282/2023-2024 | 1256/JD | 13/09/2023 | 180 | S. N. POLYMERS PVT. LTD. | 335.88 | 61.22 | 25
757 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Salugara PWSS zone-I i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000283/2023-2024 | 1258/JD | 13/09/2023 | 180 | S. N. POLYMERS PVT. LTD. | 346.56 | 100.54 | 35
758 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19.02.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000689/2024-2025 | 53/HQ/JD | 18/02/2025 | 41 | AJIJUL HAQUE | 0.2 | 0.05 | 0
759 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000045/2023-2024 | 1102/JD | 24/08/2023 | 0 | Resource Division | 65.27 | 0 | 0
760 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000113/2023-2024 | 1507/JD | 13/10/2023 | 0 | Resource Division | 32.56 | 0 | 0
761 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF DIFFERENT COMPONENTS OF DAKSHIN JHARALTA PWSS i.e, TW, PUMP HOUSES, WATER DISTRIBUTION NETWORK, OHR, RISING MAIN, FHTC etc. IN CONNECTION WITH JAL JEEVAN MISSION AT BLOCK- DHUPGURI UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000378/2023-2024 | 1540/JD | 23/10/2023 | 914 | SCEC BOENTER AND KDAS JOINT VENTURE | 864.13 | 286.94 | 70
762 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000004/2024-2025 | 55/JD | 09/04/2024 | 0 | Resource Division | 108.57 | 0 | 0
763 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000128/2023-2024 | 1842/JD | 15/12/2023 | 0 | Resource Division | 21.75 | 0 | 0
764 | Jalpaiguri Division | Jalpaiguri Division | CONST OF OHR FOR DABGRAM SOUTH ZONE PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000518/2021-2022 | 448/21-22 | 04/10/2021 | 0 | PARESH CHANDRA GUHA | 1.57 | 0 | 0
765 | Jalpaiguri Division | Jalpaiguri Division | FHTC PATKIDAHA | Assistant Engineer,HQ | Junior Engineer | VCH/001430/2021-2022 | BP-2021-22-441 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 4.77 | 0 | 0
766 | Jalpaiguri Division | Jalpaiguri Division | FHTC PATKIDAHA | Assistant Engineer,HQ | Junior Engineer | VCH/001431/2021-2022 | BP-2021-22-442 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 2.6 | 0 | 0
767 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dambari Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000197/2020-2021 | 1541/JD | 31/12/2020 | 45 | KULDIP KAPOOR | 24.3 | 32.14 | 80
768 | Jalpaiguri Division | Jalpaiguri Division | PROVIDING FHTC UNDER PORA PARA | Assistant Engineer,HQ | Junior Engineer | VCH/001174/2020-2021 | 1044 | 11/01/2021 | 0 | SUKES BASU MAJUMDAR | 4.45 | 0 | 0
769 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Chrarbari Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000107/2020-2021 | 466/RWS | 15/10/2020 | 30 | M/S.DEY & ROY CHOUDHURY | 4.71 | 8.84 | 0
770 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHARERBARI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000112/2020-2021 | 1284/JD | 18/11/2020 | 45 | RAGHU DAS | 15.22 | 14.94 | 0
771 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-D) |  | Junior Engineer | ORD/000192/2020-2021 | 1552/JD | 31/12/2020 | 45 | NEW KUNDU ENTERPRISE | 27.7 | 55.03 | 1
772 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000222/2020-2021 | 100/JD | 18/01/2021 | 45 | SANKAR DAS | 21.16 | 19.59 | 100
773 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (Part-F) |  | Junior Engineer | ORD/000227/2020-2021 | 91/JD | 14/01/2021 | 45 | KAMALESH SEN | 20.95 | 20.58 | 100
774 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with under the command area of Charerbari Water Supply Scheme at Managuri Block under Jalpaiguri Division, P.H.E. Dte. (PHASE - G) |  | Junior Engineer | ORD/000285/2022-2023 | 650/RWS | 21/10/2022 | 20 | NEW KUNDU ENTERPRISE | 2.42 | 1.83 | 100
775 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000328/2020-2021 | 222/JD | 12/02/2021 | 45 | M/S DEY & ROY CHOUDHURY | 24.4 | 11.28 | 40
776 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Restoration work in connection with FHTC works for the habitation of Bideshi Para,Chobarbari, Thonthonerbari and Dakshin Ghutkara under Charerbari W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000530/2021-2022 | 176/RWS | 03/03/2022 | 15 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0
777 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing fhtc for charer bari pwss |  | Junior Engineer | VCH/000316/2021-2022 |  | 01/10/2021 | 0 | NEW KUNDU ENTERPRISE | 2.02 | 0 | 0
778 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC CHARERBARI WSS |  | Junior Engineer | VCH/001295/2021-2022 | BP-2021-22-415 | 23/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0
779 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DWARIKAMARI |  | Junior Engineer | VCH/001362/2021-2022 | BP-2021-22-524 | 30/03/2022 | 0 | SUBRATA GOSWAMI | 8.41 | 0 | 0
780 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JALDHARA /JAL SAPNA UNDER THE COMMAND AREA OF HILLA T.G. AREA PIPED WATER SUPPLY SCHEME AT NAGRAKATA BLOCK UNDER JALPAIGURI DIVISION, PHE DTE. |  | Junior Engineer | ORD/000326/2021-2022 | 149/JD | 19/01/2022 | 30 | SCEC BOENTER KDAS JOINT VENTURE | 26.95 | 0 | 100
781 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | hire charge |  | Junior Engineer | VCH/000534/2022-2023 | BP-2021-22-208 | 29/09/2022 | 0 | RAKESH SARKAR | 0.34 | 0 | 0
782 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | car hire charge |  | Junior Engineer | VCH/000535/2022-2023 | BP-2021-22-207 | 29/09/2022 | 0 | APIKUL ALI | 0.34 | 0 | 0
783 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No WB 76 9978 for the Month of July 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00589/2024-2025 | BP-2024-25-338 | 30/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
784 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 15.07.2024 to 14.10.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000020/2024-2025 | 561/JD | 03/07/2024 | 92 | APIKUL ALI | 0.44 | 0.27 | 0
785 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-I) udner Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000033/2022-2023 | 967/JD | 20/04/2022 | 90 | NARAYAN CHANDRA SAHA | 85.51 | 59.46 | 100
786 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-III) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000041/2022-2023 | 864/JD | 01/04/2022 | 1007 | M/S. D.K. DEY & CO.. | 63.77 | 35.4 | 100
787 | Jalpaiguri Division | Jalpaiguri Division | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 2nd tube well site of Chamurchi Piped Water Supply Scheme (Zone-III, Chunabhati) of Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000063/2024-2025 | 932/JD | 07/08/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 17.61 | 17.99 | 100
788 | Jalpaiguri Division | Jalpaiguri Division | Construction of 200 Cu.M. R.C.C. Over Head Reservoir of 16 Mtr. Staging Height one No Pump House (5.40m x 3.60m) and other related works at Zone - I of Chamurchi Tea Garden Area Augmentation P.W.S.S. udner Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000147/2022-2023 | 1540/JD | 04/08/2022 | 180 | SAPTASWA SARKAR | 63.69 | 62.46 | 100
789 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000149/2022-2023 | 1423/JD | 15/07/2022 | 1267 | M/S A.B.G. CONSTRUCTION | 151.77 | 50.68 | 10
790 | Jalpaiguri Division | Jalpaiguri Division | Construction of rig approach road for the various zone of augmentation Chamurchi T.G.PWSS under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000159/2022-2023 | 1500/JD | 27/07/2022 | 15 | PARAMJYOTI ENTERPRISE | 1.77 | 1.78 | 0
791 | Jalpaiguri Division | Jalpaiguri Division | Sinking of one no. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at chunavati chamurchi Zone-III under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000163/2023-2024 | 801/JD. | 24/07/2023 | 30 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 16.55 | 16.03 | 80
792 | Jalpaiguri Division | Jalpaiguri Division | Sinking of two nos. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at Siv Mandir area of Chamurchi zone-II under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2023-2024 | 802/JD. | 24/07/2023 | 30 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 33.1 | 32.57 | 54
793 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall at 3rd T/W site of Chamurchi Tea Garden Piped W/S scheme (Zone-II, Gumpha Line) along with pipeline repairing and other allied works in connection with JJM at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000190/2025-2026 | 2156/JD | 29/10/2025 | 30 | DITIPRIYA CHOWDHURY | 11.72 | 0 | 0
794 | Jalpaiguri Division | Jalpaiguri Division | Shifting of Rising main due to widening and Construction of New Culvert at Hatinala and other ancillary works related to the Rising main inside the Head works site of Chamurchi Bazar P.W.S.S. under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000217/2022-2023 | 1807/JD | 14/09/2022 | 21 | RANA DEY | 3.57 | 3.56 | 0
795 | Jalpaiguri Division | Jalpaiguri Division | Two nos Pump House with restoration of Sanitary Plumbing System including repairing of C.W.R. raising of valve chamber height and making of Cement Concrete Pathway at Chamurchi Forest Busty Head Works Site under Augmentation of Chamurchi T.G. Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000218/2022-2023 | 1808/JD | 14/09/2022 | 21 | M/S KARMAKAR CONSTRACTION | 4.17 | 3.69 | 100
796 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Chamurchi T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000224/2022-2023 | 1853/JD | 16/09/2022 | 45 | PARAMJYOTI ENTERPRISE | 4.65 | 4.78 | 0
797 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (Phase - II ) in connection with Jal Jeevan Mission for Augmentation of Chamurchi T.G. P.W.S.S (Zone -III) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000368/2023-2024 | 1463/JD | 06/10/2023 | 697 | MALAY BHOWMIK | 27.18 | 0 | 50
798 | Jalpaiguri Division | Jalpaiguri Division | Laying of Individual D.I. Rising Main Including common manifold from 1st Tube Well to 2nd Tube Well and to Head Works site including internal connection of 1st and 2nd Tube Well site with Functional Household Tap Connection in connection with Jal Jeevan Mission under Augmentation of Chamurchi T.G. Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000399/2022-2023 | 627/JD | 13/03/2023 | 45 | SANKAR DAS | 47.49 | 35.55 | 50
799 | Jalpaiguri Division | Jalpaiguri Division | Special repairing of RCC Over Head Reservoir for Chamurchi Bazar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte.. | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2021-2022 | 284/JD | 02/02/2022 | 60 | SUKES BASU MAJUMDAR | 8.29 | 8.32 | 1
800 | Jalpaiguri Division | Jalpaiguri Division | Construction of Two Nos Boundary Wall (at OHR site and alternate 1 st tube well Site) including construction of surface drain,making of pathway,Land development work,with supplying fitting fixing CIDF pipe,modification of pump house and constructionof rest rooms with construction of culvert along with scouring prevention work on the approach way including development of approach way with other allied works for the various site within the command area of augmentation of Chamurchi T.G. Area P.W.S.S.Zone - I under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000523/2023-2024 | 1819/JD | 14/12/2023 | 45 | SAPTASWA SARKAR | 64.94 | 54.31 | 100
801 | Jalpaiguri Division | Jalpaiguri Division | Resistivity Test for Four Nos.Tube Well for Chamurchi Tea Garden area Augmentation Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000576/2021-2022 | 142/JD | 18/01/2022 | 15 | PARAMJYOTI ENTERPRISE | 0.6 | 0.6 | 0
802 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000600/2023-2024 | 1982/JD | 03/01/2024 | 182 | APIKUL ALI | 0.88 | 1.01 | 30
803 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000601/2023-2024 | 1983/JD | 03/01/2024 | 182 | RAKESH SARKAR | 0.88 | 1.11 | 30
804 | Jalpaiguri Division | Jalpaiguri Division | Construction of 3rd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2023-2024 | 2303/JD | 07/02/2024 | 45 | DITIPRIYA CHOWDHURY | 4.9 | 4.9 | 100
805 | Jalpaiguri Division | Jalpaiguri Division | Construction of 2nd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement for at airtel site of Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000603/2023-2024 | 2304/JD | 07/02/2024 | 45 | MAA SHANTI BUILDERS | 4.9 | 4.9 | 100
806 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000049/2023-2024 | 1105/JD | 24/08/2023 | 0 | Resource Division | 160.42 | 0 | 0
807 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000091/2024-2025 | 2222/JD | 01/12/2024 | 0 | Resource Division | 21.08 | 0 | 0
808 | Jalpaiguri Division | Jalpaiguri Division | CHAMURCHI BAZAR | Assistant Engineer,HQ | Junior Engineer | VCH/000085/2022-2023 | BP-2022-2023-42 | 24/05/2022 | 0 | RANA DEY | 3.83 | 0 | 0
809 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction Of approach roads for Arjimaria Kamala Pokhari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(3rd & 4thSite) |  | Junior Engineer | ORD/000411/2022-2023 | 166/RWS | 28/02/2023 | 14 | R.S CONSTRUCTION | 1.61 | 1.3 | 1
810 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Araji Maria Kamala Pukhari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000489/2022-2023 | 288/RWS | 29/03/2023 | 21 | JAYDEB SAHA | 3.54 | 3.53 | 100
811 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000640/2020-2021 | 19/JD | 14/01/2021 | 60 | BILTU DAS | 36.92 | 1.99 | 1
812 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000716/2021-2022 | 2229/JD | 27/12/2021 | 60 | SABITA ENTERPRISE | 11.43 | 11.52 | 1
813 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000884/2021-2022 | 386/JD | 10/02/2022 | 60 | SUSANTA GHOSH | 11.44 | 11.34 | 100
814 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000053/2023-2024 | 1086/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0
815 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ. ARAJIMARIA KAMLA PUKARI PWSS |  | Junior Engineer | VCH/000912/2021-2022 | BP-2021-22-137 | 14/12/2021 | 0 | R.S CONSTRUCTION | 5.05 | 0 | 0
816 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation Banerhat Bazar Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000008/2024-2025 | 421/JD | 12/06/2024 | 30 | PRADIP SAHA | 19.04 | 0 | 60
817 | Jalpaiguri Division | Jalpaiguri Division | Emergent minor repairing of Pump House and Chlorine room with Construction of Toilet and Sanitary plumbing system located near Banarhat Thana and repairing works of Pump House near Banarhat Panchayat Office with other ancillary works for Augmentation of Banarhat Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2022-2023 | 1305/JD | 14/06/2022 | 21 | SANKAR DAS | 3.54 | 3.5 | 100
818 | Jalpaiguri Division | Jalpaiguri Division | Minor Repairing of Overhead Reservoir, Boundary Wall and Pathway and Allied Works under Augmentation of Banarhat Bazar Zone - I in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000121/2024-2025 | 1266/JD | 02/09/2024 | 30 | PRADIP SAHA | 8.05 | 7.69 | 100
819 | Jalpaiguri Division | Jalpaiguri Division | Construction of Approach Culvert at Head Work Site of Banarhat Bazar Zone-II PWSS in Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000123/2024-2025 | 1273 | 03/09/2024 | 30 | PRADIP SAHA | 8.67 | 6.41 | 100
820 | Jalpaiguri Division | Jalpaiguri Division | Shifting and Extension of pipeline for widening and strengthening of B.R.O Road From Chamurchi More to Moraghat More along with other L.D.S. Repairing and other anciellary works related to L.D.S. within the command area of Augmentation of Banerhat Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000242/2022-2023 | 1949/JD | 13/10/2022 | 902 | SANKAR DAS | 8.96 | 5.79 | 100
821 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with Rising Main Connection of Banarhat Bazar (Zone-II) Piped water supply Scheme, at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000293/2022-2023 | 2051/JD | 02/11/2022 | 842 | GLOBAL POWER & CONSTRUCTION CO. | 108.22 | 71.76 | 41
822 | Jalpaiguri Division | Jalpaiguri Division | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing and Boundary Wall with land development at Head Works site for Augmentation of Banarhat Bazar (zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000331/2022-2023 | 2486/JD | 28/12/2022 | 150 | PRADIP SAHA | 107.22 | 102.52 | 95
823 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with Rising Main Connection, of Banarhat Bazar ( Zone-I) Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000338/2022-2023 | 2518/JD | 30/12/2022 | 1099 | PRADIP SAHA | 68.1 | 33.17 | 70
824 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main Connection between Head works Pump House site and Tube Well site including Internal Pump Connection along with Construction of Pump House for Zone-I of Augmentation of Banarhat PWSS i.c.w. Jal Jeevan Mission at under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000393/2022-2023 | 569/JD | 03/03/2023 | 21 | PARAMJYOTI ENTERPRISE | 9.04 | 8.42 | 100
825 | Jalpaiguri Division | Jalpaiguri Division | Emergency reparing and laying of distribution system near Gadi khana parallel to the Hatinala and indian oil pipeline in connection with for augmentation of Banarhat Bazar PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000439/2022-2023 | 681/JD | 16/03/2023 | 21 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 5.54 | 5.53 | 100
826 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (5.40m x 3.60m) internal size with sanitary & plumbing arrangement at Head work site and Providing Functional Household Tap Connection (FHTC) for Augmentation of Banarhat Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000531/2023-2024 | 1851/JD | 15/12/2023 | 262 | SOUVIK SAHA | 10.02 | 9.65 | 100
827 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Augmentation of Banerhat Bazar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000586/2023-2024 | 2335/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 16.67 | 100
828 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation of Banerhat Bazar Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000667/2023-2024 | 2459/JD | 23/02/2024 | 192 | PRADIP SAHA | 19.04 | 0 | 100
829 | Jalpaiguri Division | Jalpaiguri Division | Interconnection work to connect Pump House, reservoir and distribution network and other allied work of Banarhat Bazar zone- II piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000824/2023-2024 | 2752/JD | 14/03/2024 | 15 | PRADIP SAHA | 18.08 | 16.27 | 100
830 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000054/2023-2024 | 1096/JD | 24/08/2023 | 0 | Resource Division | 106.7 | 0 | 0
831 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000080/2024-2025 | 2211/JD | 01/12/2024 | 0 | Resource Division | 24.1 | 0 | 0
832 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAYASAILYA T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-IV) |  | Junior Engineer | ORD/000032/2021-2022 | 752/JD | 13/05/2021 | 1183 | GAP ENGINEERS ENTERPRISE | 22.63 | 0 | 90
833 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasailya T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000219/2020-2021 | 13/JD | 04/01/2021 | 45 | GOUTAM DAS | 26.22 | 52.25 | 0
834 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) |  | Junior Engineer | ORD/000223/2020-2021 | 94/JD | 14/01/2021 | 45 | SAPTASWA SARKAR | 28 | 33.18 | 0
835 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasaily T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000245/2020-2021 | 560/JSSD | 01/02/2021 | 15 | PRIYABRATA KARMAKAR | 4.84 | 9.66 | 0
836 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) |  | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0.37 | 0
837 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fuel charges |  | Junior Engineer | BILL/00249/2022-2023 | BP-2022-23-469 | 23/02/2023 | 0 | FILL & SMILE | 0.8 | 0 | 0
838 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | supply of fuel |  | Junior Engineer | BILL/00395/2022-2023 | BP-2022-23-557 | 29/03/2023 | 0 | FILL & SMILE | 0.36 | 0 | 0
839 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
840 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Rising Main, Internal Delivery & Iron Elimination Plant (IEP) connection for Zone-II under Augmentation of Kranti Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000009/2025-2026 | 892/JD | 08/05/2025 | 20 | BIMAN DAS | 14.85 | 0 | 0
841 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repairing of 3rd T/W site Pump House with Sanitary and Plumbing arrangement for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000020/2023-2024 | 253/JD | 10/05/2023 | 21 | NARAYAN CHANDRA ADHIKARY | 2.34 | 2.32 | 100
842 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent restoration of pipeline at Kodalkati area under Kranti GP and construction of periferial boundary including retaining structure at H/W Site for Augmentation of Kranti zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000024/2022-2023 | 1033/JD | 27/04/2022 | 30 | D. S. ENTERPRISE | 29.73 | 30.17 | 0
843 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Kranti (Zone-II) Piped Water supply scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000029/2022-2023 | 914/JD | 07/04/2022 | 120 | M/S A.B.G. CONSTRUCTION | 468.36 | 328.8 | 70
844 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No. WB71B-8742) |  | Junior Engineer | ORD/000078/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 0.15 | 0 | 0
845 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
846 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall including Rising main Interconnection of Existing 2nd TW Site of Augmentation of Kranti Zone-I PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000136/2024-2025 | 1526/JD | 01/10/2024 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.61 | 0 | 0
847 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at 2(two) Nos. Head Works sites for Augmentation works of Kranti (Zone-I and II) Piped Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000161/2023-2024 | 797/JD. | 24/07/2023 | 982 | MD HAKIMUDDIN | 291.65 | 64.39 | 50
848 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) |  | Junior Engineer | ORD/000343/2021-2022 | 207/JD | 24/01/2022 | 60 | M/S A.B.G. CONSTRUCTION | 239.47 | 196.16 | 70
849 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000344/2021-2022 | 209/JD | 24/01/2022 | 90 | M/S SIBU DEY AND CO. | 130.99 | 94.27 | 0
850 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-C) |  | Junior Engineer | ORD/000345/2021-2022 | 210/JD | 24/01/2022 | 90 | BOSE ENTERPRISE | 156.83 | 107.43 | 80
851 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) |  | Junior Engineer | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0.74 | 1
852 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Guard Wall at pond side for existing Boundary Wall and joining the pipeline at Kodalkati for Augmentation of Kranti Zone - II Piped Water Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000369/2023-2024 | 291/JSSD | 26/09/2023 | 30 | D. S. ENTERPRISE | 1.55 | 1.49 | 100
853 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of approach for Head Works Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000386/2022-2023 | 361/JD | 20/02/2023 | 7 | LOKNATH CONSTRUCTION | 0.61 | 0.61 | 100
854 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent Laying Distribution System for inter connection to main line at Bhujari Para and Cana bridge at Kranti zone-II P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000550/2021-2022 | 1050/JSSD | 24/01/2022 | 15 | BARUN KUMAR DUTTA | 4.71 | 0 | 0
855 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supplying and Installation of 45 nos. Display Board at different piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000550/2023-2024 | 497/JSSD | 02/01/2024 | 30 | GOUTAM DAS | 7.17 | 7.13 | 100
856 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of pipeline near at Debijhora High School towards Kranti Bazar including Jhora Crossing under Kranti Zone-II Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000592/2021-2022 | 992/JSSD | 03/01/2022 | 15 | NARAYAN CHANDRA ADHIKARY | 2.5 | 2.14 | 0
857 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Shifting of pipeline due to widening and strengthening of PWD road from Jhak Para Petrol Pump towards Head Work Site Pump House at Kranti zone- I Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000593/2021-2022 | 993/JSSD | 03/01/2022 | 20 | NARAYAN CHANDRA ADHIKARY | 3.96 | 3.9 | 0
858 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000610/2021-2022 | 410/JD | 15/02/2022 | 21 | LOKNATH CONSTRUCTION | 7.62 | 7.49 | 0
859 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000612/2021-2022 | 411/JD | 15/02/2022 | 21 | LOKNATH CONSTRUCTION | 7.62 | 7.38 | 100
860 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-II Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000808/2023-2024 | 571/JSSD | 05/03/2024 | 378 | SIDDHARTHA KAR | 8.44 | 4.06 | 85
861 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000812/2023-2024 | 567/JSSD | 05/03/2024 | 30 | KOHINOOR ISLAM | 3.22 | 0.97 | 70
862 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | LDS FHTC PURBA DURAMARI |  | Junior Engineer | VCH/001287/2021-2022 | BP-2021-22-493 | 29/03/2022 | 0 | SUKES BASU MAJUMDAR | 46.78 | 0 | 0
863 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | DPR PREPARATION FOR ANGRABHASA PWSS |  | Junior Engineer | VCH/001411/2021-2022 | BP-2021-22-547 | 31/03/2022 | 0 | SUBHANKAR GHOSH | 1.05 | 0 | 0
864 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | LDS FHTC AUG MONDALGHAT |  | Junior Engineer | VCH/001418/2021-2022 | BP-2021-22-462 | 27/03/2022 | 0 | M/S R.N. TRADERS | 38.53 | 0 | 0
865 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system and construction of Boundary Wall ,Foot Path, Drain at HW site of Bhagatpur Zone-II PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000011/2024-2025 | 427/JD | 13/06/2024 | 30 | LOKNATH CONSTRUCTION | 34.67 | 4.96 | 45
866 | Jalpaiguri Division | Jalpaiguri Division | Restoration of existing damaged pipeline near railway crossing at Jhahaji line in connection with Jal Jeevan Mission under Bhagatpur Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000012/2024-2025 | 428/JD | 13/06/2024 | 657 | LOKNATH CONSTRUCTION | 25.24 | 0 | 25
867 | Jalpaiguri Division | Jalpaiguri Division | Construction of 150 Cu.M. Capacity R.C.C. Over Head Reservoir of 17 Mtr. Staging Height, Construction of One No Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site Zone-II of Bhagatpur PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000023/2022-2023 | 1055/JD | 27/04/2022 | 1161 | LOKNATH CONSTRUCTION | 63.09 | 24.54 | 50
868 | Jalpaiguri Division | Jalpaiguri Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
869 | Jalpaiguri Division | Jalpaiguri Division | Rising Main and FHTC at Bhagatpur PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2025-2026 | 1953/JD | 18/09/2025 | 195 | ADITRI ENTERPRISE | 14.59 | 0 | 30
870 | Jalpaiguri Division | Jalpaiguri Division | Construction of approach road including development of the approach way for the Head works site of Bhagatpur T.G. Piped water supply Scheme Zone -II under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000208/2022-2023 | 1798/JD | 14/09/2022 | 21 | ASIT PAUL | 2.84 | 2.83 | 0
871 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Bhagatpur T.G. P.W.S.S. zone-II under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000225/2022-2023 | 1854/JD | 16/09/2022 | 45 | RANA DEY | 4.65 | 4.77 | 1
872 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Bhagatpur T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000226/2022-2023 | 1855/JD | 16/09/2022 | 45 | ADITRI ENTERPRISE | 4.65 | 4.75 | 1
873 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer,HQ | Junior Engineer | ORD/000300/2022-2023 | 2189/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.5 | 2.5 | 1
874 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer,HQ | Junior Engineer | ORD/000302/2022-2023 | 2191/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.17 | 2.17 | 1
875 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Jeeven Mission under Bhagatpur Piped Water Supply Scheme Zone-II Command area under Jalpaiguri Division P.H.E. Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000328/2022-2023 | 2458/JD | 22/12/2022 | 952 | UDAYAN BOSE | 23.71 | 17.05 | 100
876 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with Rising Main Connection, of Bhagatpur Piped water Supply Scheme , Zone-II at Nagrakata Block under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000337/2021-2022 | 212/JD | 24/01/2022 | 60 | LOKNATH CONSTRUCTION | 93.12 | 87.08 | 100
877 | Jalpaiguri Division | Jalpaiguri Division | Resistivity Test for Four Nos.Tube Well for Bhagatpur Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000495/2021-2022 | 1938/JD | 29/11/2021 | 15 | PARAMJYOTI ENTERPRISE | 0.6 | 0.6 | 0
878 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000212/2023-2024 | 2060/JD | 10/01/2024 | 0 | Resource Division | 11.74 | 0 | 0
879 | Jalpaiguri Division | Jalpaiguri Division | shifting of pipe line pwd nagrakata | Assistant Engineer,HQ | Junior Engineer | VCH/000580/2022-2023 | 342/22-23 | 15/09/2022 | 0 | PRADIP SAHA | 0.04 | 0 | 0
880 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Madhya Boragari Zone-I PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000285/2023-2024 | 1521/JD | 16/10/2023 | 899 | R.S CONSTRUCTION | 430.92 | 155.57 | 65
881 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Boragari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000541/2024-2025 | 110/JD | 16/01/2025 | 45 | BISWANATH GHOSH | 47.44 | 0 | 0
882 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000038/2023-2024 | 1109/JD | 24/08/2023 | 0 | Resource Division | 25.74 | 0 | 0
883 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000143/2023-2024 | 2004/JD | 08/01/2024 | 0 | Resource Division | 13.46 | 0 | 0
884 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00454/2024-2025 | BP-2024-25-279 | 01/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
885 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
886 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Commissioning of Baradighi Tea Garden Area Piped water supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000253/2022-2023 | 173/JSSD | 25/08/2022 | 60 | PRIYABRATA KARMAKAR | 4.59 | 4.57 | 0
887 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of BaraDighi PWSS i.e. TW, Pump Houses, Water distribution Network,OHR,RISING MAIN,FHTC etc. i.c.w Jal Jeevan Mission at Block-Matiali under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000471/2022-2023 | 775/JD | 27/03/2023 | 1099 | RAGHU DAS | 107.46 | 73.31 | 90
888 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000027/2023-2024 | 171/JD | 28/04/2023 | 0 | Resource Division | 3.55 | 0 | 0
889 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000179/2023-2024 | 2044/JD | 09/01/2024 | 0 | Resource Division | 1.29 | 0 | 0
890 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00525/2024-2025 | BP-2024-25-297 | 14/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
891 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00866/2024-2025 | BP-2024-25-487 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
892 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
893 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 |  | Junior Engineer | ORD/000001/2024-2025 | 022/JSSD | 30/04/2024 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0.17 | 70
894 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Dhumpara (N) (Zone-I & II) PWSS i.e, TW Pump House , Water distribution Network, OHR, RISING MAIN , FHTC etc. I.c.w Jal Jeevan Mission at Block - Nagrakata Under Jalpaiguri Divison P.H.E Dte. |  | Junior Engineer | ORD/000055/2023-2024 | 262/JD | 10/05/2023 | 180 | S. N. POLYMERS PVT. LTD. | 471.75 | 135.86 | 33
895 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Construction of Boundary Wall & Rising main with inter connection at 2nd TW & 3rd TW site of Dhumpara(Zone -II) PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000077/2025-2026 | 98/JSSD | 30/05/2025 | 30 | ARUP SARKAR | 3.01 | 0 | 100
896 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
897 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 |  | Junior Engineer | ORD/000113/2024-2025 | .142/2/JSSD | 29/07/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0.16 | 0
898 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/11/2023 to 31/01/2025 |  | Junior Engineer | ORD/000470/2024-2025 | 326/JSSD | 30/10/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0
899 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/11/2024 to 31/01/2025 |  | Junior Engineer | ORD/000471/2024-2025 | 325/1/JSSD | 30/10/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0.44 | 0
900 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 |  | Junior Engineer | ORD/000511/2023-2024 | 378/JSSD | 30/10/2023 | 180 | MRITYUNJAY SIKDAR | 0.88 | 0.41 | 0
901 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/02/2025 to 30/04/2025(Vehicle No WB 71B 9430) |  | Junior Engineer | ORD/000700/2024-2025 | 416/JSSD | 28/01/2025 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0.63 | 0
902 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall & Rising main with inter connection at 2nd TW & 3rd TW site of Dhumpara(Zone -II) PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000803/2023-2024 | 570/JSSD | 05/03/2024 | 45 | ARUP SARKAR | 8.23 | 8.3 | 100
903 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000019/2023-2024 | 163/JD | 28/04/2023 | 0 | Resource Division | 44.06 | 0 | 0
904 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000165/2023-2024 | 2055/JD | 09/01/2024 | 0 | Resource Division | 14.08 | 0 | 0
905 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
906 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Neoranadi Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000045/2023-2024 | 238/JD | 08/05/2023 | 878 | PRASENJIT BASAK | 286.38 | 232.92 | 100
907 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
908 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Neoranadi TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000175/2025-2026 | 174/JSSD | 25/07/2025 | 30 | ADWIJA CONSTRUCTION | 7.51 | 0 | 0
909 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Neoranadi TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000431/2024-2025 | 2275/JD | 05/12/2024 | 90 | PRASENJIT BASAK | 67.08 | 0 | 0
910 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000065/2023-2024 | 1074/JD | 24/08/2023 | 0 | Resource Division | 47.59 | 0 | 0
911 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000155/2023-2024 | 2013/JD | 09/01/2024 | 0 | Resource Division | 8.43 | 0 | 0
912 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF 1(ONE) MAXI CAB WITH ENGINE CAPACITY MORE THAN 2000C.C ON HIRE BASIS INCLUDING DRIVER FOR ASSISTANT ENGINEER (SADAR), JALPAIGURI SADAR SUB DIVISION, P.H.E. DTE. DIST-JALPAIGURI (WITH VALID PERMIT) |  | Junior Engineer | BILL/00322/2023-2024 | BP-2023-24-292 | 10/08/2023 | 0 | MANIK RAY | 0.25 | 0 | 0
913 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  | Junior Engineer | BILL/00356/2022-2023 | BP-2023-24-111 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 2.85 | 0 | 0
914 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00855/2024-2025 | BP-2024-25-499 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
915 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF FUEL(DISEL) FOR THE VEHICLE NO. WB-78-3405 FOR THE MONTH OF FEBRUARY2024 FOR THE OFFICE USE OF THE ASSISTANT ENGINEER ,SADAR SUB DIVISION, UNDER EXECUTIVE ENGINEER ,JALPAIGURI DIVISION. |  | Junior Engineer | BILL/01356/2023-2024 | BP-2024-25-15 | 12/04/2024 | 0 | FILL & SMILE | 0.25 | 0 | 0
916 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 |  | Junior Engineer | ORD/000001/2024-2025 | 022/JSSD | 30/04/2024 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0.22 | 70
917 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000006/2022-2023 | 877/JD | 05/04/2022 | 1367 | SCEC BOENTER KDAS JOINT VENTURE | 237.94 | 126.1 | 88
918 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Rejuvenation of different components of PWSS of Over Head Reservoir site at Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000010/2024-2025 | 423/JD | 12/06/2024 | 45 | APEX ENGINEERING | 22.45 | 3.28 | 100
919 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000022/2022-2023 | 1031/JD | 26/04/2022 | 180 | RAGHU DAS | 96.77 | 98.75 | 1
920 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-III) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/000069/2022-2023 | 1922/JD | 28/09/2022 | 180 | J.M. CONSTRUCTION | 84.24 | 83.45 | 100
921 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.6x2.4) m with Land Development, Boundary Wall, approach, Retrofitting work of Lataguri Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte |  | Junior Engineer | ORD/000092/2021-2022 | 1331/JD | 23/08/2021 | 1472 | R.K. SINGHA & SONS | 15.94 | 11.1 | 100
922 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
923 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000099/2022-2023 | 78/JSSD | 22/07/2022 | 20 | SURAJIT KUNDU | 4.57 | 4.52 | 100
924 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000103/2022-2023 | 79/JSSD | 22/07/2022 | 20 | SURAJIT KUNDU | 4.57 | 4.47 | 100
925 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Rig approach for Installation of tubewell of Head Works, 2nd Tubewell and 3rd Tube Well site for Augmentation of Lataguri Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000109/2022-2023 | 86/JSSD | 22/07/2022 | 7 | ALICK DUTTA | 1.46 | 1.45 | 1
926 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent Laying of pipeline at Purba Lataguri Station Para and repairing old stand post (broken)due to widening and strengthening of PWD lataguri-Kranti Road at Lataguri Water Supply Scheme under Jalpaiguri Division,PHE Dte. |  | Junior Engineer | ORD/000110/2022-2023 | 87/JSSD | 22/07/2022 | 10 | KAMALESH SEN | 1.11 | 1.11 | 1
927 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 3rd & 4th TW including Rising main for Augmentation of Lataguri PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000111/2024-2025 | 1417/JD | 20/09/2024 | 236 | M/S SIBU DEY AND CO. | 40.12 | 0 | 40
928 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 |  | Junior Engineer | ORD/000113/2024-2025 | .142/2/JSSD | 29/07/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0.16 | 0
929 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/06/2023 to 31/07/2023. |  | Junior Engineer | ORD/000134/2023-2024 | 558/RWS | 31/05/2023 | 61 | APIKUL ALI | 0.29 | 0.29 | 100
930 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work for Laying Distribution System with Providing FHTC for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.¿. Dte. |  | Junior Engineer | ORD/000198/2024-2025 | 298/JSSD | 03/10/2024 | 15 | CALCON CONSTRUCTIONS | 8.06 | 0 | 100
931 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of 2nd Pump House, office-cum-godown, IEP platform and construction of drain with earth filling in H/W site and ancillary works with over hauling of 3-unit IEP plant for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000230/2022-2023 | 1946/JD | 13/10/2022 | 21 | D. S. ENTERPRISE | 18.91 | 18.8 | 0
932 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000289/2022-2023 | 1899/JD | 26/09/2022 | 90 | CALCON CONSTRUCTIONS | 267.26 | 211.29 | 80
933 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000291/2022-2023 | 2059/JD | 03/11/2022 | 993 | M/S SURAJIT DEY AND CO. | 383.43 | 260.59 | 95
934 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of Rising Main from 1st, 2nd & 3rd Tube Well site to OHR for Augmentation of Lataguri (Zone-I) PWSS in connection with Jal Jeevan Mission at Block -Kranti under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000359/2023-2024 | 277/JSSD | 21/09/2023 | 30 | ARUP SARKAR | 6.5 | 0 | 0
935 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Lataguri (Zone-III) in connection with PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000365/2023-2024 | 281/JSSD | 26/09/2023 | 30 | GOPRO CONSTRUCTION | 3.62 | 3.55 | 100
936 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of approach for Head Works Site for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000384/2022-2023 | 360/JD | 20/02/2023 | 7 | RAGHU DAS | 0.56 | 0.56 | 0
937 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 |  | Junior Engineer | ORD/000511/2023-2024 | 378/JSSD | 30/10/2023 | 180 | MRITYUNJAY SIKDAR | 0.88 | 0.42 | 0
938 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Rising Line Connection with wash line and balance work in Head Works site at Augmentation of Lataguri(zone-II) PWSS under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000549/2023-2024 | 506/JSSD | 02/01/2024 | 30 | RAGHU DAS | 9.22 | 9.2 | 100
939 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent Laying of diverted line damaged by excavator due to construction of Market Complex at Lataguri Bazar and replacing the damaged GI line at Lal Setu at Lataguri Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000552/2021-2022 | 990/JSSD | 03/01/2022 | 10 | LOKNATH CONSTRUCTION | 1.47 | 1.12 | 100
940 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Minor repairing and renovation of 3rd T/W site and H/W site Pump Houses at Lataguri Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000553/2021-2022 | 987/JSSD | 03/01/2022 | 20 | D. S. ENTERPRISE | 2.63 | 2.64 | 0
941 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in HW site at Zone-III of Augmentation of Lataguri PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000590/2024-2025 | 455/JD | 10/03/2025 | 30 | J.M. CONSTRUCTION | 16.72 | 0 | 0
942 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M x 2.40 M) size including sanitary plumbing works at 2nd tube well site for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000596/2021-2022 | 1054/JSSD | 24/01/2022 | 45 | KABYA ENTERPRISE | 4.76 | 4.76 | 100
943 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M x 2.40 M) size including sanitary and Plumbing Works at 3rd tube well site for Augmentation of Lataguri (zone-II) PWSS under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000600/2021-2022 | 1066/JSSD | 24/02/2022 | 45 | ROY CONSTRUCTION | 4.76 | 4.7 | 1
944 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM Over Head Reservoir Augmentation of Lataguri (Zone-III) PWSS, under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000692/2021-2022 | 1067/JSSD | 24/01/2022 | 20 | MABCO CONSULTANT | 1.83 | 1.73 | 1
945 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 350 CuM Over Head Reservoir for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000702/2021-2022 | 1069/JSSD | 25/01/2022 | 20 | GLORY ENGINEERS SYNDICATE | 1.83 | 1.62 | 1
946 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jalswapna with retrofitting work for Mahalaxmi Colony, Lataguri for Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001064/2021-2022 | 995/JSSD | 05/01/2022 | 15 | ALICK DATTA | 4.6 | 0 | 0
947 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional House hold Tap connection in connection with Jalswapna with retroffiting work for Mahalaxmi Colony, Lataguri for Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001065/2021-2022 | 995/JSSD | 05/01/2022 | 15 | ALICK DATTA | 4.6 | 4.7 | 1
948 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000088/2023-2024 | 1066/JD | 24/08/2023 | 0 | Resource Division | 342.41 | 0 | 0
949 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000090/2024-2025 | 2216/JD | 01/12/2024 | 0 | Resource Division | 30.66 | 0 | 0
950 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Tunbari Tea Garden (P) PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block ¿ Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000060/2023-2024 | 265/JD | 10/05/2023 | 180 | M/S SARKAR ENTERPRISE | 304.78 | 0 | 70
951 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
952 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system with other allied works in connection with Jal Jeevan Mission at Tunbari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000092/2025-2026 | 105/JSSD | 30/05/2025 | 45 | GURUKUL INFOTECH | 4.97 | 0 | 0
953 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Malbazar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000463/2023-2024 | 1291/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
954 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Tunbari Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000469/2023-2024 | 1762/JD | 08/12/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 31.58 | 100
955 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000062/2023-2024 | 1091/JD | 24/08/2023 | 0 | Resource Division | 35.62 | 0 | 0
956 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000142/2023-2024 | 1888/JD | 20/12/2023 | 0 | Resource Division | 9.92 | 0 | 0
957 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Mahit Nagar PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) |  | Junior Engineer | ORD/000080/2023-2024 | 433/JD. | 08/06/2023 | 28 | RAGHU DAS | 52.95 | 52.93 | 98
958 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at balance portion of Mohitnagar W/S Scheme in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (PART-J) |  | Junior Engineer | ORD/000259/2023-2024 | 1269/JD | 13/09/2023 | 30 | M/S DEY & ROY CHOUDHURY | 63.37 | 22.41 | 90
959 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply mobil to vehicle no WB 71 A 5774 |  | Junior Engineer | BILL/00518/2024-2025 | BP-2024-25-296 | 14/08/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
960 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of July 2024 |  | Junior Engineer | BILL/00519/2024-2025 | BP-2024-25-295 | 14/08/2024 | 0 | FILL & SMILE | 0.2 | 0 | 0
961 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL BILL |  | Junior Engineer | BILL/00631/2023-2024 | BP-2023-24-433 | 11/10/2023 | 0 | FILL & SMILE | 0.53 | 0 | 0
962 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of deep tube well by ODEX-195 method of drilling for Songachi T.G. Piped Water Supply Scheme, Block- Matiali, Dist- Jalpaiguri. |  | Junior Engineer | ORD/000195/2022-2023 | 1592/JD | 17/08/2022 | 21 | R.S CONSTRUCTION | 9.32 | 7.76 | 100
963 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.08.2023 to 31.01.2024) |  | Junior Engineer | ORD/000268/2023-2024 | 877/RWS | 31/07/2023 | 184 | ASHIM SARKAR | 0.88 | 0.88 | 20
964 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 (Two) Nos Additional Tube Well by ODEX-165 method including Construction of different components i.e. Pump Houses, Boundary Walls, Rising Mains etc. for 4th and 5th site of Songachi Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000701/2024-2025 | 630/JD | 28/03/2025 | 60 | PINAKI MITRA | 36.19 | 0 | 0
965 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.02.2024 to 31.07.2024) |  | Junior Engineer | ORD/000793/2023-2024 | 93/RWS | 29/01/2024 | 182 | ASHIM SARKAR | 0.88 | 0.88 | 50
966 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000095/2023-2024 | 1049/JD | 24/08/2023 | 0 | Resource Division | 2.45 | 0 | 0
967 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Kurti Tea Garden (Zone-I, II and III) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000056/2023-2024 | 263/JD | 10/05/2023 | 180 | S. N. POLYMERS PVT. LTD. | 308.54 | 0 | 0
968 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000023/2023-2024 | 167/JD | 28/04/2023 | 0 | Resource Division | 56.03 | 0 | 0
969 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000166/2023-2024 | 2038/JD | 09/01/2024 | 0 | Resource Division | 6.64 | 0 | 0
970 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
971 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 3rd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000102/2025-2026 | 481/RWS | 29/05/2025 | 30 | GOURAV CONSTRUCTION CO. | 6.98 | 0 | 0
972 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000104/2025-2026 | 482/RWS | 29/05/2025 | 30 | M/S. D.K. DEY & CO.. | 8.36 | 0 | 0
973 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Dakshin Hanskhali PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc.In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000162/2023-2024 | 799/JD. | 24/07/2023 | 1135 | M/S. D.K. DEY & CO.. | 465.94 | 161.43 | 45
974 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution Network and Providing Functional Household Tap connection (FHTC) including Construction of additional components of Dakshin Hanskhali PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000678/2024-2025 | 465/JD | 11/03/2025 | 60 | M/S. D.K. DEY & CO.. | 74.53 | 0 | 0
975 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Land Development, Pathway, Surface Drain etc. at H/W site of Dakshin Hanskhali PWSS i.c.w. Jal Jeevan Mission at block- Kranti under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000684/2024-2025 | 484/JD | 11/03/2025 | 45 | M/S. D.K. DEY & CO.. | 21.14 | 0 | 0
976 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000111/2023-2024 | 1370/JD | 27/09/2023 | 0 | Resource Division | 87.93 | 0 | 0
977 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000150/2023-2024 | 2016/JD | 09/01/2024 | 0 | Resource Division | 17.2 | 0 | 0
978 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Khuklung Mini PWSS ie. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Dhupguri Block, under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000274/2023-2024 | 1265/JD | 13/09/2023 | 656 | DEBASISH DEY | 63.25 | 34.97 | 90
979 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000144/2023-2024 | 2001/JD | 08/01/2024 | 0 | Resource Division | 0.73 | 0 | 0
980 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of HAIHAIPATHAR PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000048/2023-2024 | 454/JD. | 08/06/2023 | 663 | M/S R.N. TRADERS | 444.76 | 221.18 | 75
981 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
982 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 (Two) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of Hai Hai Pather PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000435/2024-2025 | 2311./JD | 11/12/2024 | 70 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 34.93 | 0 | 0
983 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000069/2023-2024 | 1085/JD | 24/08/2023 | 0 | Resource Division | 28.59 | 0 | 0
984 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000160/2023-2024 | 2022/JD | 09/01/2024 | 0 | Resource Division | 14.2 | 0 | 0
985 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Sukani Piped Water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000035/2022-2023 | 1102/JD | 12/05/2022 | 1420 | M/S A.B.G. CONSTRUCTION | 886.96 | 593.17 | 78
986 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including FHTC for Augmentation of Sukani Piped Water Supply Scheme Zone-III at Rajganj Block Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000037/2022-2023 | 1101/JD | 12/05/2022 | 120 | BANSBERIA CONSTRUCTION CO. | 668.61 | 433.35 | 1
987 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000051/2022-2023 | 1196/JD | 20/05/2022 | 45 | SHYAMAL KUMARSAHA | 4.64 | 4.64 | 0
988 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000052/2022-2023 | 1198/JD | 20/05/2022 | 45 | DILIP SINGHA | 4.65 | 4.65 | 1
989 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000054/2022-2023 | 1201/JD | 20/05/2022 | 45 | KABYA ENTERPRISE | 4.64 | 4.64 | 100
990 | Jalpaiguri Division | Jalpaiguri Division | HDD Boring with MS pipe and other ancillary work at post office more of rajganj and fatapukur to belakoba road of sukani pwss under jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2024-2025 | 937/JD | 07/08/2024 | 60 | SANKAR DAS | 34.63 | 34.47 | 100
991 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000057/2022-2023 | 1197/JD | 20/05/2022 | 45 | UNIQUE CONSTRUCTION | 4.64 | 0 | 0
992 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000058/2022-2023 | 1200/JD | 20/05/2022 | 45 | M/S A.P. DEVELOPERS | 4.65 | 4.65 | 0
993 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System with FHTC for Augmentation of Sukhani Piped Water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000059/2022-2023 | 1229/JD | 01/06/2022 | 120 | MINTU CHAKRABORTY | 746.92 | 569 | 88
994 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site (ZONE-I) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT ¿ JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2022-2023 | 1273/JD | 07/06/2022 | 45 | M/S SURAJIT DEY AND CO. | 29.51 | 0 | 0
995 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd tube well site ( ZONE-II) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT - JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000070/2022-2023 | 1272/JD | 07/06/2022 | 45 | MINTU CHAKRABORTY | 17.91 | 16.88 | 100
996 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000077/2022-2023 | 1373/JD | 30/06/2022 | 45 | PARESH CHAND GHOSH ROY | 4.64 | 4.64 | 1
997 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at 3rd Tube Well site for Sukhani Piped Water Supply Scheme Zone-II at Rajganj block under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000114/2023-2024 | 449/JD. | 08/06/2023 | 45 | JAGORAN SARKAR | 4.9 | 4.9 | 100
998 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall with drain, land development including interconnection work at Augmentation of Sukani PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000125/2024-2025 | 1414/JD | 20/09/2024 | 30 | D. S. ENTERPRISE | 10.17 | 0 | 100
999 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-1) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000142/2023-2024 | 709/JD | 13/07/2023 | 629 | MRINMOY KANTI DUTTA | 29.51 | 10.46 | 55
1000 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-II zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000165/2022-2023 | 1433/JD | 18/07/2022 | 15 | MOYTEC | 2.25 | 2.03 | 100
1001 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (750 cum) at Sukhani Zone-III under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000166/2022-2023 | 1424/JD | 15/07/2022 | 15 | M S PRANTIK ASSOCIATES | 2.22 | 2.12 | 100
1002 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-I zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000173/2022-2023 | 1400/JD | 11/07/2022 | 15 | AGAC | 2.26 | 2.24 | 100
1003 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site to sukhanii zone - II (H/W site T/W ) under Jalpaiguri Division PHE Dte. Part B ( Left & Right) | Assistant Engineer,HQ | Junior Engineer | ORD/000179/2019-2020 | 291/JD | 13/03/2020 | 60 | SADHAN KARMAKAR | 9.7 | 0 | 1
1004 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant (IEP) with Construction of Blower Room, Drain, Road including necessary connections and other ancillary work at Zone-I 4th Site of Sukani Piped Water Supply Scheme in connection with Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000186/2025-2026 | 2503/JD | 09/12/2025 | 120 | D. S. ENTERPRISE | 25.17 | 0 | 0
1005 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site for " SUKHANI ZONE-II WATER SUPPLY SCHEME ( H/ W SITE T/W )" under Jalpaiguri Divition , P.H.E. Dte. Part-"A" (Front Side) | Assistant Engineer,HQ | Junior Engineer | ORD/000187/2019-2020 | 248/JD | 03/03/2020 | 60 | SUBRATA GOSWAMI | 14.17 | 13.81 | 1
1006 | Jalpaiguri Division | Jalpaiguri Division | Support 300 mm DI pipe line near Fatapukur and construction 1 no. stand post and other ancillary works at Sukani Zone I under Rajganj block under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000219/2022-2023 | 1809/JD | 14/09/2022 | 21 | R.K. SARKAR | 1.8 | 1.2 | 1
1007 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessary connections for Augmentation of Sukhani Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000249/2023-2024 | 1270/JD | 13/09/2023 | 810 | SANJIT SAHA | 30.41 | 25.29 | 55
1008 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-3) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000250/2023-2024 | 1263/JD | 13/09/2023 | 931 | ANUP KUMAR KUNDU | 40.53 | 0 | 0
1009 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000256/2023-2024 | 1264/JD | 13/09/2023 | 45 | A P CONSTRUCTION | 31.69 | 31.02 | 100
1010 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-4) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000260/2023-2024 | 1262/JD | 13/09/2023 | 705 | BILTU DAS | 40.83 | 0 | 50
1011 | Jalpaiguri Division | Jalpaiguri Division | Fitting fixing DI specials along with laying distribution for Augmentation of Sukhani Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/000263/2023-2024 | 948/JD | 08/08/2023 | 60 | MINTU CHAKRABORTY | 82.49 | 60.5 | 45
1012 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) for Augmentation at 3rd tubewell site Sukani (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000277/2023-2024 | 1358/JD | 26/09/2023 | 45 | D. S. ENTERPRISE | 18.23 | 18.23 | 100
1013 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at 4th Tubewell site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000278/2023-2024 | 1359/JD | 26/09/2023 | 45 | SANDIP BANIK | 17.65 | 17.58 | 100
1014 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-2) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000280/2023-2024 | 1434/JD | 05/10/2023 | 786 | SUBRATA GOSWAMI | 29.29 | 0 | 40
1015 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer,HQ | Junior Engineer | ORD/000295/2023-2024 | 855/JD | 31/07/2023 | 184 | SOUMEN GHOSH | 0.88 | 0.79 | 20
1016 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-III) PIPED WATER SUPPLY SCHEME. | Assistant Engineer,HQ | Junior Engineer | ORD/000372/2023-2024 | 1519/JD | 16/10/2023 | 481 | M/S. SURYA I PVT. LTD COMPANY | 147.2 | 64.02 | 68
1017 | Jalpaiguri Division | Jalpaiguri Division | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) | Assistant Engineer,HQ | Junior Engineer | ORD/000391/2022-2023 | 2186/JD | 10/11/2022 | 151 | SUKES BASU MAJUMDAR | 0.94 | 0.47 | 0
1018 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000472/2022-2023 | 780/JD | 27/03/2023 | 21 | ASIT PAUL | 19.36 | 18.41 | 100
1019 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-III) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000485/2022-2023 | 804/JD | 29/03/2023 | 734 | JITENDRA NATH ROY | 13.79 | 11.26 | 100
1020 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000504/2021-2022 | 511/JD | 23/02/2022 | 21 | B.M CONSTRUCTION | 8.09 | 0 | 1
1021 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000505/2021-2022 | 512/JD | 23/02/2022 | 21 | B.M CONSTRUCTION | 8.09 | 0 | 1
1022 | Jalpaiguri Division | Jalpaiguri Division | Fitting fixing DI specials along with laying distribution and Pump House (5.40m x 3.60 m) at Head work site for Augmentation of Sukhani Piped water supply scheme Zone-III at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000564/2023-2024 | 2391/JD | 16/02/2024 | 20 | BANSBERIA CONSTRUCTION CO. | 96.25 | 0 | 0
1023 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III head work site at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000582/2021-2022 | 513/JD | 23/02/2022 | 21 | M/S R.N. TRADERS | 8.09 | 7.35 | 1
1024 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 2nd Tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000583/2021-2022 | 514/JD | 23/02/2022 | 21 | M/S R.N. TRADERS | 8.09 | 7.33 | 1
1025 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying pipe line for H/W Site at Sukani zone III PWSS site piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000591/2023-2024 | 2329/JD | 08/02/2024 | 45 | LOPCHAN ENTERPRISE | 18.11 | 0 | 0
1026 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000607/2023-2024 | 2308/JD | 07/02/2024 | 30 | M/S A.P. DEVELOPERS | 7.76 | 0 | 0
1027 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000608/2023-2024 | 2309/JD | 07/02/2024 | 30 | D. S. ENTERPRISE | 7.78 | 7.61 | 100
1028 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000609/2023-2024 | 2310/JD | 07/02/2024 | 30 | JAGORAN SARKAR | 8.51 | 7.82 | 100
1029 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukhani (zone-III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000612/2023-2024 | 2311/JD | 07/02/2024 | 30 | R.K. SINGHA & SONS | 8.42 | 8.1 | 100
1030 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Providing guarding arrangement at Stack Yard under Resource Division at the Head Work Site of SUKHANI PWSS (ZONE-I) under Jalpaiguri Division P.H.E. Dte. for the period from 01/08/2022 to 31/07/2023." | Assistant Engineer,HQ | Junior Engineer | ORD/000642/2022-2023 | 1504/A/JD | 28/07/2022 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD. | 16.62 | 0 | 0
1031 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-II) PIPED WATER SUPPLY SCHEME . | Assistant Engineer,HQ | Junior Engineer | ORD/000690/2023-2024 | 2392/JD | 16/02/2024 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 145.22 | 0 | 0
1032 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 750 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKANI (ZONE I) PIPED WATER SUPPLY SCHEME IN CONNECTION WITH JAL JEEVAN MISSION AT BLOCK: RAJGANJ UNDER JALPAIGURI DIVISION, P.H.E DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000694/2023-2024 | 2411/JD | 19/02/2024 | 548 | AMINUL HOQUE | 207.67 | 81.6 | 50
1033 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd TubeWell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS zone -III at Rajganj Block under Jalpaiguri Division P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000701/2021-2022 | 766/JD | 23/03/2022 | 21 | M/S KARMAKAR CONSTRACTION | 8.09 | 7.6 | 1
1034 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000730/2023-2024 | 2452/JD | 23/02/2024 | 30 | M/S SAHA ENTERPRISE | 8.31 | 0 | 0
1035 | Jalpaiguri Division | Jalpaiguri Division | Shifting AC pipes ,Coumpound clearing, Cutting trees and other ancillary works at Sukani zone -II under Sukani piped water supply scheme under Jalpaiguri water supply Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000732/2023-2024 | 2453/JD | 23/02/2024 | 14 | NEW KUNDU ENTERPRISE | 2.83 | 2.9 | 100
1036 | Jalpaiguri Division | Jalpaiguri Division | Interconnection work for Iron Elimination Plant to Rising main, Construction Platform land development and other ancillary works at Sukani zone I and zone II in connection with Jal Jeevan Mission at sukani PWSS at Rajganj Block,under Jalpaiguri Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000792/2023-2024 | 2633/JD | 07/03/2024 | 15 | D. S. ENTERPRISE | 12.81 | 12.74 | 100
1037 | Jalpaiguri Division | Jalpaiguri Division | Shifting AC pipes, Coumpound clearing ,Cutting trees ,Land development ,inter connection of IEP and other ancillary works at Sukani zone -II Head work site under Sukani piped water supply scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000806/2023-2024 | 2635/JD | 07/03/2024 | 15 | A P CONSTRUCTION | 6.53 | 6.68 | 100
1038 | Jalpaiguri Division | Jalpaiguri Division | Construction of Different Component like Pump House, Tube Well, IEP, Boundary wall and ancillary work at Mogradangi of Sukani PWSS (Zone-I) of Raiganj Block under Jalpaiguri Division, PHE, Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000821/2023-2024 | 2729/JD | 13/03/2024 | 748 | D. S. ENTERPRISE | 54.2 | 0 | 20
1039 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell site at Sukani Zone- III piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000832/2023-2024 | 08/01/JD | 15/03/2024 | 30 | PARESH CHAND GHOSH ROY | 8.32 | 0 | 100
1040 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000885/2021-2022 | 842/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 7.79 | 1
1041 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000886/2021-2022 | 843/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 7.7 | 1
1042 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000055/2023-2024 | 1097/JD | 24/08/2023 | 0 | Resource Division | 208.46 | 0 | 0
1043 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000081/2024-2025 | 2221/JD | 01/12/2024 | 0 | Resource Division | 88.05 | 0 | 0
1044 | Jalpaiguri Division | Jalpaiguri Division | LDS PURBA DAUKIMARI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000093/2022-2023 | BP-2022-23-45 | 24/05/2022 | 0 | SUKES BASU MAJUMDAR | 58.14 | 0 | 0
1045 | Jalpaiguri Division | Jalpaiguri Division | LDS FHTC DAKHIN CHAK MAULANI | Assistant Engineer,HQ | Junior Engineer | VCH/001271/2021-2022 | BP-2021-22-472 | 28/03/2022 | 0 | UNIBRO INFRASERV PRIVATE LIMITED | 21.09 | 0 | 0
1046 | Jalpaiguri Division | Jalpaiguri Division | SINKING OF 300MM X 200MM DIA 3RD T/WELL SUKHANI PWSS ZONE-II | Assistant Engineer,HQ | Junior Engineer | VCH/001280/2021-2022 | BP-2021-22-479 | 29/03/2022 | 0 | B.M CONSTRUCTION | 6.93 | 0 | 0
1047 | Jalpaiguri Division | Jalpaiguri Division | CONST 250 M3 B/WALL BARADIGHI T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001369/2021-2022 | BP-2021-22-471 | 28/03/2022 | 0 | BOSE ENTERPRISE | 49.78 | 0 | 0
1048 | Jalpaiguri Division | Jalpaiguri Division | LDS BARADIGHI TG PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001374/2021-2022 | BP-2021-22-475 | 31/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 7.66 | 0 | 0
1049 | Jalpaiguri Division | Jalpaiguri Division | EXT PIPE LINE SUKHANI ZONE - II | Assistant Engineer,HQ | Junior Engineer | VCH/001399/2021-2022 | BP-2021-22-503 | 30/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0
1050 | Jalpaiguri Division | Jalpaiguri Division | TUBE WELL SUKHANI ZONE-II | Assistant Engineer,HQ | Junior Engineer | VCH/001438/2021-2022 | BP-2021-22-479 | 29/03/2022 | 0 | SUKES BASU MAJUMDAR | 6.93 | 0 | 0
1051 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 4.83 | 100
1052 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000083/2024-2025 | 802/RWS | 20/08/2024 | 30 | TECHNO CRACY | 7.49 | 0 | 0
1053 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 3rd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division PHE, DTE. |  | Junior Engineer | ORD/000098/2024-2025 | 1299/JD | 05/09/2024 | 60 | M/S KARMAKAR CONSTRUCTION | 10.93 | 0 | 0
1054 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Brahmapur PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000436/2023-2024 | 1670/JD | 24/11/2023 | 495 | NARAYAN CHANDRA SAHA | 597.49 | 147.47 | 50
1055 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Brahmapur PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000458/2024-2025 | 2335./JD | 12/12/2024 | 60 | SANDIP BANIK | 61.25 | 0 | 0
1056 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000043/2023-2024 | 1112/JD | 24/08/2023 | 0 | Resource Division | 122.36 | 0 | 0
1057 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000112/2023-2024 | 1506/JD | 13/10/2023 | 0 | Resource Division | 15.68 | 0 | 0
1058 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000192/2023-2024 | 2053/JD | 09/01/2024 | 0 | Resource Division | 15.68 | 0 | 0
1059 | Jalpaiguri Division |  | Supply of Fuel (Petrol) of Vehicle No. WB 49 K 9449 for the Month of August 2024. |  |  | BILL/00648/2024-2025 | BP-2024-25-365 | 13/09/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
1060 | Jalpaiguri Division |  | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of September 2024. |  |  | BILL/00851/2024-2025 | BP-2024-25-486 | 07/10/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
1061 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1062 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000023/2024-2025 | 737/JD | 26/07/2024 | 524 | ASIM GUPTA | 166.13 | 0 | 100
1063 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000027/2024-2025 | 738/JD | 26/07/2024 | 615 | ANUP KUNDU CONSTRUCTION CO | 142.74 | 0 | 95
1064 | Jalpaiguri Division |  | Construction of Boundary wall, Foot Path, Drain, pipeline for washout at HW site Satkhamar - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, PHE Dte. |  |  | ORD/000089/2024-2025 | 1174/JD | 23/08/2024 | 587 | M/S A.B.G. CONSTRUCTION | 31.86 | 0 | 0
1065 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1066 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  |  | ORD/000101/2024-2025 | 874/JD | 31/07/2024 | 184 | SOUMEN GHOSH | 0.88 | 0.51 | 0
1067 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - II of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000112/2025-2026 | 490/RWS | 29/05/2025 | 30 | CHANDAN GHOSH | 5.77 | 0 | 0
1068 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - I of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000113/2025-2026 | 491/RWS | 29/05/2025 | 308 | SUKES BASU MAJUMDAR | 6.1 | 0 | 100
1069 | Jalpaiguri Division |  | Laying Additional Distribution line with providing and installation of Sluice Valve and Specials at Zone-I of Satkhamar Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000170/2025-2026 | 2108/JD | 15/10/2025 | 168 | SUKES BASU MAJUMDAR | 32.96 | 0 | 100
1070 | Jalpaiguri Division |  | Construction of different components of Satkhamar Zone- II Piped Water Supply Scheme i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  |  | ORD/000440/2023-2024 | 1705/JD | 04/12/2023 | 850 | M/S A.B.G. CONSTRUCTION | 590.4 | 0 | 90
1071 | Jalpaiguri Division |  | Construction of Iron Elemination Plant (IEP) including interconnection work and washout line at H/W site in Zone-II Satkhamar PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000529/2024-2025 | 46/JD | 09/01/2025 | 240 | M/S M.B. DESIGN | 43.97 | 0 | 80
1072 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 2063/JD | 10/01/2024 | 0 | Resource Division | 43.48 | 0 | 0
1073 | Jalpaiguri Division |  | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain etc. at HW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000075/2024-2025 | 1297/JD | 05/09/2024 | 60 | KAMAL DAS | 20.16 | 0 | 0
1074 | Jalpaiguri Division |  | Construction of different components of Singimari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000328/2023-2024 | 1349/JD | 26/09/2023 | 548 | M/S R.N. TRADERS | 724.62 | 217.56 | 15
1075 | Jalpaiguri Division |  | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, Land Development etc. at 2nd TW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000429/2024-2025 | 1152/RWS | 03/12/2024 | 30 | PRABIR SHOME | 9.14 | 0 | 0
1076 | Jalpaiguri Division |  | Balance Laying Distribution System including providing Functional Household Tap Connection in connection with JJM under Singimari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000550/2024-2025 | 127/JD | 16/01/2025 | 60 | SWAPAN SAHA | 34.8 | 0 | 0
1077 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 56/JD | 09/04/2024 | 0 | Resource Division | 21.92 | 0 | 0
1078 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 2042/JD | 09/01/2024 | 0 | Resource Division | 17.33 | 0 | 0
1079 | Jalpaiguri Division |  | Supply of Toner and Mouse for Office use. |  |  | BILL/00819/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.08 | 0 | 0
1080 | Jalpaiguri Division |  | Supply of Printer Teflon, Toner for Office use. |  |  | BILL/00820/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1081 | Jalpaiguri Division |  | Supply of Toner, SSD and Ink for Office use. |  |  | BILL/00821/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1082 | Jalpaiguri Division |  | Supply of Processor, RAM, SMPS and SSD for Office use. |  |  | BILL/00822/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.06 | 0 | 0
1083 | Jalpaiguri Division |  | Supply of RAM, Logic Board, Pickup Roller and Teflon for Office use. |  |  | BILL/00823/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1084 | Jalpaiguri Division |  | Supply of Magnetic Relay, Logic Board and Pickup Roller for Office use. |  |  | BILL/00824/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1085 | Jalpaiguri Division |  | Supply of Printer Logic Board and Pickup Roller for Office use. |  |  | BILL/00825/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1086 | Jalpaiguri Division |  | Supply of Printer Power Supply, Teflon for Office use. |  |  | BILL/00826/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1087 | Jalpaiguri Division |  | Supply of Motherboard and Power Supply Unit for Office use. |  |  | BILL/00827/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1088 | Jalpaiguri Division |  | Supply of Toner and Desktop RAM for Office use. |  |  | BILL/00828/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1089 | Jalpaiguri Division |  | Supply of Brother 263 Toner, 88A Toner, 110A Toner, Keyboard and Mouse for Office use. |  |  | BILL/00829/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1090 | Jalpaiguri Division |  | Supply of Motherboard, SSD & Keyboard and Mouse for Office use. |  |  | BILL/00830/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1091 | Jalpaiguri Division |  | Supply of 88A Compatible Toner for Office use. |  |  | BILL/00831/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.07 | 0 | 0
1092 | Jalpaiguri Division |  | Supply of Motherboard, RAM and Printer Relay Unit for Office use. |  |  | BILL/00832/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1093 | Jalpaiguri Division |  | Supply of Motherboard, Toner and Printer Fuser Unit for Office use. |  |  | BILL/00833/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1094 | Jalpaiguri Division |  | Supply of SSD, Hard Disk and Printer Power Supply Board for Office use. |  |  | BILL/00834/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1095 | Jalpaiguri Division |  | Supply of SSD, Motherboard, Processor, SMPS and Mouse for Office use. |  |  | BILL/00835/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1096 | Jalpaiguri Division |  | Supply of Motherboard, RAM, Pickup Roller and Toner for Office use. |  |  | BILL/00836/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1097 | Jalpaiguri Division |  | Supply of Brother Toner and SMPS for Office use. |  |  | BILL/00837/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1098 | Jalpaiguri Division |  | Supply of Toner for Office use. |  |  | BILL/00838/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1099 | Jalpaiguri Division |  | Supply of Logic Board, Power Supply and Teflon for Office use. |  |  | BILL/00839/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1100 | Jalpaiguri Division |  | Supply of Logic Board, Magnetic Relay and Teflon for Office use. |  |  | BILL/00840/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1101 | Jalpaiguri Division |  | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Rajganj block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  |  | ORD/000467/2023-2024 | 1292/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
1102 | Jalpaiguri Division |  | Construction of different components of Shikarpur Bhandarpur Zone - I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block - RAJGANJ under Jalpaiguri Division, P.H.E.Dte. of North Bengal Circle-I, PHE Dte under JJM Programme. |  |  | ORD/000817/2023-2024 | 2623/JD | 07/03/2024 | 908 | ASHIT KUMAR SINGHA | 682.9 | 363.2 | 85
1103 | Jalpaiguri Division |  | Construction of different components of Shikarpur Bhandarpur Zone - II PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block - RAJGANJ under Jalpaiguri Division, P.H.E.Dte. of North Bengal Circle-I, PHE Dte under JJM Programme. |  |  | ORD/000818/2023-2024 | 2624/JD | 07/03/2024 | 600 | M/S SURAJIT DEY AND CO. | 714.03 | 204.87 | 65
1104 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of October 2024. |  | Junior Engineer | BILL/00938/2024-2025 | BP-2024-25-525 | 29/11/2024 | 0 | FILL & SMILE | 0.13 | 0 | 0
1105 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Barapatina Nutanbus Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000011/2025-2026 | 895/JD | 08/05/2025 | 40 | PRADIP KUMAR SHIL | 18.52 | 0 | 0
1106 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000029/2024-2025 | 736/JD | 26/07/2024 | 524 | MOTI INDUSTRIES | 128.89 | 82.7 | 85
1107 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) |  | Junior Engineer | ORD/000033/2025-2026 | 820/JD | 30/04/2025 | 61 | SUKES BASU MAJUMDAR | 0.8 | 0 | 0
1108 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  | Junior Engineer | ORD/000101/2024-2025 | 874/JD | 31/07/2024 | 184 | SOUMEN GHOSH | 0.88 | 0.44 | 0
1109 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000106/2025-2026 | 484/RWS | 29/05/2025 | 307 | JAYA SARKAR | 8.04 | 0 | 0
1110 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 90
1111 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" |  | Junior Engineer | ORD/000123/2025-2026 | 1499/JD | 30/06/2025 | 31 | SUKES BASU MAJUMDAR | 0.4 | 0 | 0
1112 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Barapatina Nutanbus Zone-II PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000128/2023-2024 | 408/A/JD | 07/06/2023 | 705 | UNIBRO INFRASERV PRIVATE LIMITED | 434.44 | 213.71 | 70
1113 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  | Junior Engineer | ORD/000295/2023-2024 | 855/JD | 31/07/2023 | 184 | SOUMEN GHOSH | 0.88 | 0 | 20
1114 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." |  | Junior Engineer | ORD/000570/2023-2024 | 2197/JD | 25/01/2024 | 182 | SOUMEN GHOSH | 0.88 | 0.56 | 0
1115 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000012/2024-2025 | 2016/JD | 19/11/2024 | 0 | Resource Division | 156.48 | 0 | 0
1116 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000139/2023-2024 | 1884/JD | 20/12/2023 | 0 | Resource Division | 14.51 | 0 | 0
1117 | Jalpaiguri Division |  | Surveying, Planning, Designing, Construction, Supply and installation and commissioning of surface (River) based water treatment unit to yield 1430 KLD drinking water (Phase-I) on EPC- Turnkey basis for Augmentation of Chengmari Tea Garden Pipe Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000205/2024-2025 | 1590/JD | 23/10/2024 | 504 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 936.29 | 0 | 0
1118 | Jalpaiguri Division |  | Construction of Intake Well for Sub-Surface Water Source at River Bed of Diana under Nagrakata Block of Jalpaiguri District i.c.w Chengmari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000740/2023-2024 | 2495/JD | 28/02/2024 | 21 | GOUTAM DAS | 37.37 | 37.49 | 100
1119 | Jalpaiguri Division |  | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Soil Investigation Work, Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall (H/W and 2nd Site) along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Satkhaya Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000284/2023-2024 | 1255/JD | 13/09/2023 | 626 | B RAI CONSTRUCTION COMPANY | 183 | 13.3 | 14
1120 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 1063/JD | 24/08/2023 | 0 | Resource Division | 8.3 | 0 | 0
1121 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 2067/JD | 10/01/2024 | 0 | Resource Division | 6.28 | 0 | 0
1122 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.06.2024 to 30.11.2024)". | Assistant Engineer,HQ | Junior Engineer | ORD/000005/2024-2025 | 347/JD | 31/05/2024 | 183 | RUPA PRASAD | 0.88 | 2.22 | 100
1123 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Nowapara Piped Water Supply Scheme Block - Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000010/2025-2026 | 893/JD | 08/05/2025 | 328 | SAHA CONSTRUCTION | 75.34 | 0 | 0
1124 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000034/2025-2026 | 821/JD | 30/04/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0
1125 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000035/2025-2026 | 822/JD | 30/04/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 0
1126 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000124/2025-2026 | 1500/JD | 30/06/2025 | 31 | MD AMIRUL ISLAM | 0.4 | 0 | 0
1127 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000125/2025-2026 | 1501/JD | 30/06/2025 | 31 | AJIJUL HAQUE | 0.4 | 0 | 0
1128 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000150/2025-2026 | 1731/JD | 31/07/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0
1129 | Jalpaiguri Division | Jalpaiguri Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000198/2025-2026 | 1997/JD | 25/09/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0
1130 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Nowapara PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN , FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Divison , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000444/2023-2024 | 1775/JD | 08/12/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 686.37 | 0 | 0
1131 | Jalpaiguri Division | Jalpaiguri Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000471/2025-2026 | 2438/JD | 27/11/2025 | 30 | MD AMIRUL ISLAM | 0.4 | 0 | 0
1132 | Jalpaiguri Division | Jalpaiguri Division | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 100
1133 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000044/2023-2024 | 1106/JD | 24/08/2023 | 0 | Resource Division | 28.96 | 0 | 0
1134 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000188/2023-2024 | 2033/JD | 09/01/2024 | 0 | Resource Division | 22.38 | 0 | 0
1135 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Dwarikamari Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000160/2020-2021 | 476/RWS | 15/10/2020 | 30 | GOUTAM DAS | 4.84 | 0 | 0
1136 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Dwarikamari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000185/2020-2021 | 1497/JD | 22/12/2020 | 30 | GOUTAM DAS | 21.72 | 41.14 | 1
1137 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System Mogalkata Tea Garden Area Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-K) |  | Junior Engineer | ORD/000203/2021-2022 | 1655/JD | 08/10/2021 | 15 | PRABIR SHOME | 9.87 | 0.94 | 0
1138 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works at Jakhai bari, Kathal Tali, Kalirhat & adjacent area of Dwarikamari W/S/S under Jalpaiguri Division , P.H.E .Dte. (Part-F). Block-Maynaguri. District- Jalpaiguri. |  | Junior Engineer | ORD/000426/2022-2023 | 625/JD | 13/03/2023 | 45 | ARATI CONSTRUCTION | 45 | 22.64 | 100
1139 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PREPARATION OF DPR FOR SOUTH BERUBARI PWSS |  | Junior Engineer | VCH/000505/2021-2022 | 440/21-22 | 04/10/2021 | 0 | SUBHANKAR GHOSH | 2.32 | 0 | 0
1140 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC under Dwarikamari WSS |  | Junior Engineer | VCH/001146/2020-2021 | 1053 | 11/01/2021 | 0 | BARUN KUMAR DUTTA | 4.43 | 0 | 0
1141 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC AT DWARIKAMARI PWSS |  | Junior Engineer | VCH/001293/2020-2021 | 1189 | 02/02/2021 | 0 | GOUTAM DAS | 4.83 | 0 | 0
1142 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Madabdanga Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000168/2020-2021 | 471/RWS | 15/10/2020 | 30 | ALICK DUTTA | 4.72 | 9.48 | 1
1143 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madab danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000202/2020-2021 | 1537/JD | 31/12/2020 | 60 | ANUP SARKAR | 32.76 | 59.31 | 1
1144 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madabdanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000211/2020-2021 | 48/JD | 07/01/2021 | 60 | M/S SIBU DEY AND CO. | 39.4 | 0 | 0
1145 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of store below OHR , plinth protection and construction of valve chamber etc. including through reparing of pipe line with cleaning to provide water facility near Jalpesh more under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000319/2021-2022 | 870/RWS | 08/12/2021 | 15 | M/S SURAJIT DEY AND CO. | 4.85 | 0 | 0
1146 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works in connection with FHTC at Kadamtala, Indira More and Baman para under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000395/2021-2022 | 849/RWS | 03/12/2021 | 10 | ANUP SARKAR | 2.25 | 0 | 0
1147 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC FOR JURANTI T.G PWSS |  | Junior Engineer | VCH/000336/2021-2022 |  | 04/10/2021 | 0 | NARAYAN CH SAHA & SONS | 18.42 | 0 | 0
1148 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC AT MADHABDANGA PWSS |  | Junior Engineer | VCH/001156/2020-2021 | 1054 | 11/01/2021 | 0 | BHOWMIK ENTERPRISES | 4.41 | 0 | 0
1149 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MADHAB DANFGA |  | Junior Engineer | VCH/001179/2021-2022 | BP-2021-22-234 | 23/02/2022 | 0 | ANUP SARKAR | 3.99 | 0 | 0
1150 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST SULICE VALVE CHEMBER FOR DAKSHIN SHALBARI PWSS |  | Junior Engineer | VCH/001248/2021-2022 | BP-2021-22-389 | 17/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0
1151 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORK MADHAB DANGA PWSS |  | Junior Engineer | VCH/001257/2021-2022 | BP-2021-22-405 | 23/03/2022 | 0 | ANUP SARKAR | 2.25 | 0 | 0
1152 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST. SLUICE VALVE DAKSHIN SALBARI |  | Junior Engineer | VCH/001320/2021-2022 | BP-2021-22-389 | 17/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0
1153 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MADHYA KHUTTIMARI |  | Junior Engineer | VCH/001326/2021-2022 | BP-2021-22-369 | 16/03/2022 | 0 | ALOKE DEY | 16.81 | 0 | 0
1154 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fuel bill |  | Junior Engineer | BILL/00030/2023-2024 | BP-2023-24-30 | 12/04/2023 | 0 | FILL & SMILE | 1.9 | 0 | 0
1155 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangarhat piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000056/2021-2022 | 1076/JD | 02/07/2021 | 30 | DIPANKAR DUTTA | 24.38 | 46.35 | 0
1156 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Hope T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000220/2020-2021 | 30/JD | 05/01/2021 | 75 | UMWELT ENGINEER PRIVATE LIMITED | 43.55 | 0 | 0
1157 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | FHTC FOR BHANGARHAT PWSS |  | Junior Engineer | VCH/000367/2021-2022 | 376/21-22 | 20/09/2021 | 0 | MRINMOY KANTI DUTTA | 23.75 | 0 | 0
1158 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall gate, drain and pathway for 4th Tube well site of Rejuvenation of Pora Para Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000028/2022-2023 | 913/JD | 07/04/2022 | 60 | JAYDEB SAHA | 11.2 | 10.27 | 100
1159 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Guard Shed including supply and installation of 300 dia Sluice valve and chamber and the other allied works under Porapara Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000176/2022-2023 | 555/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 4.81 | 4.64 | 0
1160 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of C.C. pathway repairing drain and boundary wall etc. at Head work site campus of Porapara W/S Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000180/2022-2023 | 559/RWS | 01/09/2022 | 30 | SOMNATH ROY | 2.22 | 2.18 | 1
1161 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rectrofting and reparing of pipe line, IEP and other allied works at Fakir Para, Bairagi danga, Brahatal Para due to widening and new construction of road by P.W.D. under Porapara Water Supply Scheme Jalpaiguri Division PHE Dte |  | Junior Engineer 2 | ORD/000182/2022-2023 | 561/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 4.82 | 4.65 | 1
1162 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Rig approach with partial land development for 3rd tube well site under Porapara piped Water Supply Scheme within Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer 2 | ORD/000185/2022-2023 | 564/RWS | 01/09/2022 | 15 | B.M CONSTRUCTION | 4.32 | 2.74 | 1
1163 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Pora Para water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer 2 | ORD/000327/2022-2023 | 1932/JD | 29/09/2022 | 45 | SUKES BASU MAJUMDAR | 16.22 | 16.21 | 0
1164 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of Tubewell at 4th Tube Well site for Rejuvenation of Porapara PWSS in connection with JJM at block - Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000376/2023-2024 | 1517/JD | 16/10/2023 | 30 | RANJEET SINGH BENIWAL | 9.79 | 9.77 | 100
1165 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying new pipe line from Canal near OHR to Taltala near Haldibari Road to facilitate Functional Household Tap Connection in connection with JJM under Porapara Piped Water Supply Scheme under Jalpaiguri |  | Junior Engineer 2 | ORD/000437/2022-2023 | 682/JD | 16/03/2023 | 30 | B.M CONSTRUCTION | 14.92 | 14.92 | 0
1166 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Rejuvenation of Pora Para Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000779/2021-2022 | 473/JD | 22/02/2022 | 60 | SOMNATH ROY | 11.28 | 16.23 | 1
1167 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works in connection with FHTC works for the habitation of Monosha Mandir para & Bura Amtolar Gali under Bhuskadanga W/S/S under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000018/2022-2023 | 307/RWS | 28/04/2022 | 15 | BALARAM GHOSH | 0.77 | 0.77 | 0
1168 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF UTTAR BHUSKADANGA & GARTALI JALPESH PIPED WATER SUPPLY SCHEME, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000030/2022-2023 | 976/JD | 20/04/2022 | 120 | UNIBRO INFRASERV PRIVATE LIMITED | 57.66 | 57.61 | 100
1169 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of cement concrete drain , pathway , store below OHR and culvert etc. at H/W site campus of Dakshin Salbari W/S/S under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000170/2021-2022 | 679/RWS | 27/09/2021 | 30 | R.S CONSTRUCTION | 4.85 | 4.86 | 1
1170 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone- III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-J) |  | Junior Engineer | ORD/000277/2022-2023 | 642/RWS | 21/10/2022 | 20 | SOMNATH ROY | 4.82 | 4.68 | 0
1171 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-K) |  | Junior Engineer | ORD/000278/2022-2023 | 643/RWS | 21/10/2022 | 20 | J.M. CONSTRUCTION | 3.73 | 3.1 | 0
1172 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works in connection with FHTC of Natun para , Borobari and Malar Math under Uttar Bhuskadanga W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000332/2021-2022 | 743/RWS | 08/10/2021 | 15 | BALARAM GHOSH | 2.86 | 0 | 0
1173 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF UTTAR BHUSKADANGA PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000356/2021-2022 | 254/JD | 31/01/2022 | 1246 | MRINMOY KANTI DUTTA | 79.88 | 35.24 | 90
1174 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/02/2023 to 31/05/2023. |  | Junior Engineer | ORD/000496/2022-2023 | 72/RWS | 31/01/2023 | 120 | APIKUL ALI | 0.59 | 0.59 | 100
1175 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | UTTAR BHUSKA DANGA |  | Junior Engineer | VCH/000924/2021-2022 | BP-2021-22-114 | 03/12/2021 | 0 | BALARAM GHOSH | 4.8 | 0 | 0
1176 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Restoration of pipe line at different places including construction of sluice valve chamber with supply of sluice valv etc.at head work site campus under Mohitnagar W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000017/2022-2023 | 306/RWS | 28/04/2022 | 15 | M/S DEY & ROY CHOUDHURY | 4.83 | 4.83 | 1
1177 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Renovation of Boundary wall including Approach Road, Earth filling, Valve Chambers at Head Work Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000236/2022-2023 | 1813/JD | 14/09/2022 | 21 | M/S DEY & ROY CHOUDHURY | 8.1 | 7.79 | 1
1178 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000296/2021-2022 | 38/JD | 04/01/2022 | 60 | SAUMENDU DUTTA | 10.87 | 0 | 100
1179 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  | Junior Engineer | ORD/000301/2022-2023 | 2190/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.32 | 3.32 | 0
1180 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  | Junior Engineer | ORD/000305/2022-2023 | 2194/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.56 | 3.56 | 0
1181 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) |  | Junior Engineer | ORD/000325/2021-2022 | 879/RWS | 10/12/2021 | 10 | M/S DEY & ROY CHOUDHURY | 1.28 | 0 | 1
1182 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 25.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Mohitnagar water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000347/2022-2023 | 132/JD | 17/01/2023 | 45 | R.S CONSTRUCTION | 30.33 | 18.18 | 100
1183 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000403/2022-2023 | 598/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 4.79 | 0 | 100
1184 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections (at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Mohit Nagar Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000405/2022-2023 | 165/RWS | 28/02/2023 | 21 | SOUVIK SAHA | 3.28 | 3.24 | 100
1185 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000408/2022-2023 | 602/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.33 | 0 | 100
1186 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-H) |  | Junior Engineer | ORD/000409/2022-2023 | 599/JD | 09/03/2023 | 21 | M/S DEY & ROY CHOUDHURY | 4.51 | 0 | 100
1187 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) |  | Junior Engineer | ORD/000410/2022-2023 | 601/JD | 09/03/2023 | 21 | M/S DEY & ROY CHOUDHURY | 4.84 | 0 | 100
1188 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Guard wall including additional part of Boundary wall at 3rd Tubewell Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000457/2022-2023 | 743/JD | 23/03/2023 | 15 | SAUMENDU DUTTA | 1.76 | 0 | 0
1189 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Mohit Nagar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Part-G) |  | Junior Engineer | ORD/000513/2021-2022 | 537/JD | 25/02/2022 | 30 | M/S DEY & ROY CHOUDHURY | 21.77 | 0 | 0
1190 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001068/2021-2022 | 39/JD | 04/12/2021 | 60 | NARESH SEN | 11.12 | 11.45 | 1
1191 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001074/2021-2022 | 38/JD | 04/01/2022 | 60 | SAUMENDU DUTTA | 10.87 | 0.28 | 1
1192 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000033/2023-2024 | 1117/JD | 24/08/2023 | 0 | Resource Division | 3.55 | 0 | 0
1193 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SAMSING |  | Junior Engineer | VCH/001149/2021-2022 | BP-2021-22-235 | 16/02/2022 | 0 | SUJAN LAMA | 4.79 | 0 | 0
1194 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC LIKSAN BAZAR (ZONE - III) |  | Junior Engineer | VCH/001394/2021-2022 | BP-2021-22515 | 30/03/2022 | 0 | ALICK DUTTA | 13.19 | 0 | 0
1195 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | DEV LAND & REPAIRING SANITARY & PLUMBING ARRANGEMENT |  | Junior Engineer | VCH/001402/2021-2022 | BP-2021-22-506 | 30/03/2022 | 0 | SANDIP BANIK | 4.55 | 0 | 0
1196 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 9 (nine) villages under different blocks having less than 100 households under Jalpaiguri district in connection with Jal Swapna |  | Junior Engineer | ORD/000063/2022-2023 | 1226/JD | 01/06/2022 | 30 | M/S NANDY ENTERPRISE | 355.27 | 40.51 | 0
1197 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 4 (Four) no. village under different blocks having less than 100 household under Jalpaiguri district in connection with Jal Swapna. |  | Junior Engineer | ORD/000064/2022-2023 | 1227/JD | 01/06/2022 | 1400 | M/S SIBU DEY AND CO. | 142.11 | 34.23 | 60
1198 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1199 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Juranteeee TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000019/2023-2024 | 252/JD | 10/05/2023 | 45 | SARKAR CONSTRUCTION | 4.64 | 4.64 | 100
1200 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing balance Functional Household Tap Connection (FHTC) at Juranti TG PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000095/2025-2026 | 115/JSSD | 03/06/2025 | 30 | ASIT PAUL | 9.61 | 0 | 100
1201 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate,drain and pathway for 3rd tube-well site of Rejuvenation of Jurantee tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000320/2022-2023 | 62/JSSD | 19/07/2022 | 20 | ARINDAM CHATTERJEE | 3.88 | 3.86 | 100
1202 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System of Rejuvenation of Jurantee Tea Garden Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000325/2022-2023 | 2456/JD | 22/12/2022 | 30 | SANDIP BANIK | 71.54 | 71.52 | 100
1203 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Jurantee Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000590/2021-2022 | 737/JD | 17/03/2022 | 30 | ASHIS DUTTA | 13.5 | 9.81 | 100
1204 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation of Jurantee Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000596/2022-2023 | 05/JSSD | 16/05/2022 | 45 | RAJAT GHOSH | 4.65 | 0 | 0
1205 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Jurantee Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000798/2023-2024 | 2628/JD | 07/03/2024 | 45 | ASIT PAUL | 5.61 | 4.65 | 100
1206 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of peripherial drain with Land development and RBT at 4th tubewell site of Hila Tea Garden in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000021/2023-2024 | 254/JD | 10/05/2023 | 14 | GOPAL DEY | 1.19 | 1.19 | 100
1207 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 4th tube-well site of Rejuvenation of Piped Water Supply Scheme for HILA under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000086/2022-2023 | 1364/JSSD | 19/04/2022 | 20 | GOPAL DEY | 3.89 | 3.91 | 100
1208 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 6th tube well site of Rejuvenation of Hila Tea Garden Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000107/2024-2025 | 1389/JD | 18/09/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0
1209 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 5th tube well site for Hila TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000271/2022-2023 | 215/JSSD | 16/09/2022 | 60 | U TURN CONSTRUCTION | 4.65 | 4.65 | 100
1210 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall at 3rd Tube well site for Hila T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000417/2020-2021 | 552/JSSD | 29/01/2021 | 30 | SAHA CONSTRUCTION | 4.55 | 3.66 | 1
1211 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works for Laying Distribution System of Rejuvenation of water supply scheme for Hilla Tea Garden Mouza under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000441/2022-2023 | 733/JD | 22/03/2023 | 30 | PROFULLA GHOSH | 32.91 | 24.85 | 100
1212 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works of 3rd Pump House site at Hila Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000553/2023-2024 | 503/JSSD | 02/01/2024 | 30 | SCEC BOENTER AND KDAS JOINT VENTURE | 6.04 | 0 | 0
1213 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hila Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000611/2021-2022 | 561/JD | 01/03/2022 | 30 | ASHIS DUTTA | 13.22 | 13.51 | 1
1214 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection 261Nos. in Connection with Jal Jeevan Mission Hila Tea Garden Piped Water Supply Scheme Under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000799/2023-2024 | 564/JSSD | 05/03/2024 | 30 | SAHA CONSTRUCTION | 9.52 | 9.46 | 100
1215 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m X 2.40m size with sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Water Supply Scheme for HILA Tea Garden under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000835/2021-2022 | 1105/W/JSSD | 27/01/2022 | 45 | TECHNOCRACY ELECTRICAL CONTRACTOR & GENERAL ORDER SUPPLIER | 4.64 | 4.64 | 1
1216 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | FHTC HILLA T.G PWSS |  | Junior Engineer | VCH/001356/2021-2022 | BP-2021-22-473 | 28/03/2022 | 0 | SCEC BOENTER KDAS JOINT VENTURE | 19.05 | 0 | 0
1217 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RECONNECTION OF PIPE LINE RETROFITTING HILLA T.G WSS |  | Junior Engineer | VCH/001357/2021-2022 | BP-2021-22-474 | 28/03/2022 | 0 | SCEC BOENTER KDAS JOINT VENTURE | 17.01 | 0 | 0
1218 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | EARTH FILLING WORK H/W DAKSHIN SALBARI WSS |  | Junior Engineer | VCH/001381/2021-2022 | BP-2021-22-534 | 31/03/2022 | 0 | R.S CONSTRUCTION | 4.66 | 0 | 0
1219 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY INSTALATION COMMISSIONING AND TRIAL OPERATION OF HILA T.G PWSS |  | Junior Engineer | VCH/001443/2021-2022 | BP-2021-22-483 | 29/03/2022 | 0 | S P ENTERPRISE | 8.09 | 0 | 0
1220 | Jalpaiguri Division | Northern Mechanical Division | SUPPLY OF FUEL | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00396/2022-2023 | BP-2022-23-545 | 25/03/2023 | 0 | FILL & SMILE | 0.3 | 0 | 0
1221 | Jalpaiguri Division | Northern Mechanical Division | SUPPLY OF FUEL | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00397/2022-2023 | BP-2022-23-544 | 25/03/2023 | 0 | FILL & SMILE | 0.25 | 0 | 0
1222 | Jalpaiguri Division | Northern Mechanical Division | Work of DI Pipe (Raising main), Drain, Chamber, flower block & other ancillary works at 4th site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000151/2023-2024 | 816/RWS | 14/07/2023 | 14 | ARATI CONSTRUCTION | 2.65 | 2.65 | 100
1223 | Jalpaiguri Division | Northern Mechanical Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000152/2023-2024 | 817/RWS | 14/07/2023 | 14 | SOMNATH ROY | 2.65 | 2.6 | 100
1224 | Jalpaiguri Division | Northern Mechanical Division | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PH.E Dte Jalpaiguri (with valid Taxi permit). Period from 01/10/2022 to 31/01/2023 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000249/2022-2023 | 616/RWS | 29/09/2022 | 122 | APIKUL ALI | 0.59 | 0.49 | 1
1225 | Jalpaiguri Division | Northern Mechanical Division | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MADHYA KHAGRABARI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000329/2021-2022 | 186/JD | 21/01/2022 | 120 | M/S A.B.G. CONSTRUCTION | 108.63 | 69.86 | 1
1226 | Jalpaiguri Division | Northern Mechanical Division | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-B). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000335/2021-2022 | 189/JD | 21/01/2022 | 1530 | M/S A.B.G. CONSTRUCTION | 181.29 | 94.98 | 100
1227 | Jalpaiguri Division | Northern Mechanical Division | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-A). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000336/2021-2022 | 194/JD | 21/01/2022 | 1166 | M/S A.B.G. CONSTRUCTION | 173.57 | 51.19 | 100
1228 | Jalpaiguri Division | Northern Mechanical Division | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-C`). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000339/2021-2022 | 213/JD | 24/01/2022 | 1142 | NARAYAN CHANDRA SAHA | 169.95 | 98.07 | 75
1229 | Jalpaiguri Division | Northern Mechanical Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000419/2022-2023 | 135/JD | 17/01/2023 | 45 | M/S SURAJIT DEY AND CO. | 16.44 | 15.36 | 100
1230 | Jalpaiguri Division | Northern Mechanical Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000423/2022-2023 | 680/JD | 16/03/2023 | 45 | M/S RATAN KUMAR DAS GUPTA AND CO | 16.43 | 15.36 | 80
1231 | Jalpaiguri Division | Northern Mechanical Division | ADDITIONAL WORK FOR LAYING & DISTRIBUTION SYSTEM IN MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000536/2023-2024 | 1895/JD | 20/12/2023 | 15 | JAYA SARKAR | 9 | 9.1 | 100
1232 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000711/2021-2022 | 223/JD | 24/01/2022 | 60 | SOMNATH ROY | 11.44 | 0 | 0
1233 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000712/2021-2022 | 2225/JD | 27/12/2021 | 60 | ARATI CONSTRUCTION | 11.44 | 11.42 | 1
1234 | Jalpaiguri Division | Northern Mechanical Division | Construction of pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001107/2021-2022 | 2224/JD | 23/12/2021 | 60 | SOMNATH ROY | 11.44 | 11.43 | 100
1235 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000006/2021-2022 | 179/JD | 21/01/2022 | 0 | Resource Division | 127.45 | 0 | 0
1236 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000013/2021-2022 | 551/JD | 01/03/2022 | 0 | Resource Division | 27.35 | 0 | 0
1237 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000084/2024-2025 | 2214/JD | 01/12/2024 | 0 | Resource Division | 22.14 | 0 | 0
1238 | Jalpaiguri Division | Northern Mechanical Division | Providing car on daily hire basis @12.00/Km for official use of the office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000555/2022-2023 | BP-2022-23-155 | 02/09/2022 | 0 | RAKESH SARKAR | 0.19 | 0 | 0
1239 | Jalpaiguri Division | Northern Mechanical Division | LDS REJ NAGRAKATA | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/001261/2021-2022 | BP-2021-22-517 | 30/03/2022 | 0 | UDAYAN BOSE | 6.91 | 0 | 0
1240 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of valve chember & Blower room(3.60MX3.00M ) Size for Iron Elimination Plant at Head Work Site of Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000043/2023-2024 | 390/RWS | 25/04/2023 | 14 | SWAPAN SAHA | 4.8 | 4.49 | 100
1241 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall and land development at Head Work Site for Mandalghat Water Supply Scheme under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/000136/2021-2022 | 1442/JD | 09/09/2021 | 30 | M/S UNITED CONSTRUCTION | 10.53 | 10.53 | 100
1242 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing of pump houses & construction of Boundary wall at 2nd site for Mandalghat W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000278/2021-2022 | 820/RWS | 30/11/2021 | 30 | ALICK DUTTA | 4.83 | 4.6 | 99
1243 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with drain for 3rd site of Mondal ghat piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000283/2022-2023 | 648/RWS | 21/10/2022 | 30 | ALICK DUTTA | 4.84 | 4.81 | 100
1244 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Mandolghat PWSS under JJM work at Jalpaiguri sadar Block under PHE Dte., Jalpaiguri Division |  | Junior Engineer | ORD/000334/2023-2024 | 1082/RWS | 19/09/2023 | 30 | TIRTHANKAR CHOWDHURY | 9.24 | 9.03 | 100
1245 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000446/2021-2022 | 342/JD | 03/02/2022 | 90 | M/S R.N. TRADERS | 158.04 | 65.57 | 1
1246 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MANDALGHAT PWSS, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000447/2021-2022 | 336/JD | 02/02/2022 | 120 | M/S R.N. TRADERS | 110.23 | 110.18 | 1
1247 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-C). |  | Junior Engineer | ORD/000459/2021-2022 | 338/JD | 03/02/2022 | 1343 | SIBU DEY | 212.74 | 138.86 | 100
1248 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000460/2021-2022 | 339/JD | 03/02/2022 | 1518 | BISWANATH GHOSH | 150.63 | 91.81 | 60
1249 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-B). |  | Junior Engineer | ORD/000465/2021-2022 | 345/JD | 03/02/2022 | 1518 | M/S SURAJIT DEY AND CO. | 195.6 | 74.55 | 85
1250 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Repair work of Pump house , bath room of H/W site & ancilliary works at Mondalghat PWSS under Jalpaiguri Division. |  | Junior Engineer | ORD/000487/2022-2023 | 285/RWS | 29/03/2023 | 14 | M/S UNITED CONSTRUCTION | 1.53 | 1.47 | 100
1251 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site for Augmentation Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000615/2021-2022 | 402/JD | 11/02/2022 | 357 | M/S R.N. TRADERS | 27.54 | 22.98 | 100
1252 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for MondalghatP/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 |  | Junior Engineer | ORD/000723/2021-2022 | 400/RWS | 30/06/2021 | 184 | UNITED CONSTRUCTION | 2.01 | 0 | 1
1253 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000014/2021-2022 | 550/JD | 01/03/2022 | 0 | Resource Division | 60.75 | 0 | 0
1254 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000033/2024-2025 | 2095/JD | 25/11/2024 | 0 | Resource Division | 70.02 | 0 | 0
1255 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000085/2024-2025 | 2212/JD | 01/12/2024 | 0 | Resource Division | 23.36 | 0 | 0
1256 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing drainage system for mondalghat pwss |  | Junior Engineer | VCH/000021/2022-2023 | BP-2021-23-7 | 21/04/2022 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0
1257 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING DRAINAGE SYSTEM FOR MONDALGHAT PWSS |  | Junior Engineer | VCH/000057/2022-2023 | BP-2021-22-7 | 21/04/2022 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0
1258 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GRASS MORE |  | Junior Engineer | VCH/000061/2022-2023 | BP-2021-22-25 | 26/04/2022 | 0 | M/S R.N. TRADERS | 7.08 | 0 | 0
1259 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONSTRUCTION 550 M3 AUG MANDALGHAT PWSS |  | Junior Engineer | VCH/001306/2021-2022 | BP-2021-22-391 | 17/03/2022 | 0 | R.N.TRADER'S | 51.64 | 0 | 0
1260 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST FOR MANDALGHAT |  | Junior Engineer | VCH/001437/2021-2022 | BP-2021-22 | 22/03/2022 | 0 | R.B TESTING | 2.02 | 0 | 0
1261 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  | Junior Engineer | BILL/00355/2022-2023 | BP-2023-24-109 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.55 | 0 | 0
1262 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of one maxi cab on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar sub Division,P.H.E Dte. |  | Junior Engineer | BILL/00623/2023-2024 | BP-2023-24-428 | 11/10/2023 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0
1263 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Barnish piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000010/2023-2024 | 335/RWS | 10/04/2023 | 14 | SADHAN KARMAKAR | 3.21 | 3.21 | 100
1264 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with gate,drain, Pipe line,rising line, Approach road & other ancillary works for OHR site of Barnish piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000017/2023-2024 | 60/JD | 18/04/2023 | 30 | ASHIT KUMAR SINGHA | 25.62 | 25.6 | 100
1265 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Pathway, Drain,Chember,flower block,Partial land Development , approach & other ancillary works at 4th site of Barnish Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000035/2023-2024 | 388/RWS | 25/04/2023 | 14 | JITENDRA NATH ROY | 5.18 | 4.81 | 100
1266 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 4th T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. |  | Junior Engineer | ORD/000320/2023-2024 | 1266/JD | 13/09/2023 | 45 | ASHIT KUMAR SINGHA | 16.44 | 16.38 | 100
1267 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 3rd T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. |  | Junior Engineer | ORD/000339/2022-2023 | 2519/JD | 30/12/2022 | 45 | GIYASUDDIN SEKH | 16.44 | 15.94 | 100
1268 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-B). |  | Junior Engineer | ORD/000359/2021-2022 | 329/JD | 02/02/2022 | 90 | ASHIT KUMAR SINGHA | 146.7 | 121.15 | 80
1269 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-C). |  | Junior Engineer | ORD/000371/2021-2022 | 330/JD | 02/02/2022 | 90 | R.S CONSTRUCTION | 170.45 | 156.41 | 100
1270 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000445/2021-2022 | 331/JD | 02/02/2022 | 90 | SUKES BASU MAJUMDAR | 155.8 | 58.03 | 1
1271 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000452/2021-2022 | 328/JD | 02/02/2022 | 1304 | ASHIT KUMAR SINGHA | 163.38 | 125.78 | 100
1272 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at different places of Barnes PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000454/2022-2023 | 731/JD | 22/03/2023 | 30 | ASHIT KUMAR SINGHA | 17.49 | 17.49 | 100
1273 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Extention of pipe line at different places of Barnes PWSS under Jalpiaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000484/2022-2023 | 803/JD | 29/03/2023 | 21 | R.S CONSTRUCTION | 10.28 | 10.28 | 100
1274 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site of Augmentation Barnish piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000603/2021-2022 | 409/JD | 15/02/2022 | 45 | ASHIT KUMAR SINGHA | 26.37 | 25.86 | 20
1275 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000713/2021-2022 | 2226/JD | 27/12/2021 | 60 | JITENDRA NATH ROY | 11.44 | 11.45 | 1
1276 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000714/2021-2022 | 2227/JD | 27/12/2021 | 60 | SADHAN KARMAKAR | 11.45 | 11.38 | 1
1277 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for Barnish P/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 |  | Junior Engineer | ORD/000717/2021-2022 | 408/RWS | 30/06/2021 | 184 | JITENDRA NATH ROY | 0.86 | 0 | 1
1278 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/001015/2021-2022 | 185/JD | 21/01/2022 | 120 | ASHIT KUMAR SINGHA | 141.66 | 176.05 | 1
1279 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000010/2021-2022 | 558/JD | 01/03/2022 | 0 | Resource Division | 124.02 | 0 | 0
1280 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000073/2024-2025 | 2204/JD | 01/12/2024 | 0 | Resource Division | 24.92 | 0 | 0
1281 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PREPARATION OF DPR ODLABARI PWSS |  | Junior Engineer | VCH/001283/2021-2022 | BP-2021-22-492 | 09/04/2022 | 0 | SUBHANKAR GHOSH | 1.94 | 0 | 0
1282 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION AUG BARNES PWSS |  | Junior Engineer | VCH/001338/2021-2022 | BP-2021-22-398 | 22/03/2022 | 0 | M S PRANTIK ASSOCIATES | 2.02 | 0 | 0
1283 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | BARNESH PWSS |  | Junior Engineer | VCH/001442/2021-2022 | BP-2021-22- | 24/03/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 16.99 | 0 | 0
1284 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of Laying Distribution System for Rejuvenation of Purba Salbari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000003/2022-2023 | 879/JD | 05/04/2022 | 210 | M/S GARGO TRADERS | 417.6 | 418.3 | 64
1285 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System with Providing Functional House Hold Tap Connection in connection with JJM at Purbba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000008/2025-2026 | 677/JD | 04/04/2025 | 45 | A P CONSTRUCTION | 36.26 | 0 | 0
1286 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation of Purba Salbari PWSS i.e. RISING MAIN, Boundary wall etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000039/2024-2025 | 986/JD | 14/08/2024 | 595 | SAHA CONSTRUCTION | 29.57 | 12.95 | 50
1287 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 3rd Tubewell site of Purba Salbari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000057/2023-2024 | 323/JD | 18/05/2023 | 14 | ABHIJIT SARKAR | 4.59 | 3.31 | 80
1288 | Jalpaiguri Division | Jalpaiguri Division | Shifting of DI pipeline due to widening of road of Purba Salbari Area Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000154/2022-2023 | 1534/JD | 02/08/2022 | 15 | ABHIJIT SARKAR | 1.52 | 1.51 | 1
1289 | Jalpaiguri Division | Jalpaiguri Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing for Rejuvenation of Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000201/2022-2023 | 1964/JD | 18/10/2022 | 180 | SAHA CONSTRUCTION | 69.07 | 66.66 | 60
1290 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation Purba Salbari P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000212/2022-2023 | 1802/JD | 14/09/2022 | 21 | ABHIJIT SARKAR | 4.65 | 4.74 | 0
1291 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Purba Salbari PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000475/2021-2022 | 349/JD | 22/02/2022 | 21 | ABHIJIT SARKAR | 7.97 | 0 | 0
1292 | Jalpaiguri Division | Jalpaiguri Division | Repairing of 2 nos. of Pump House (Head Work site & 2nd site) ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement and other allied works at Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000641/2020-2021 | 251/JD | 19/02/2021 | 30 | ABHIJIT SARKAR | 4.85 | 0.46 | 1
1293 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000018/2021-2022 | 553/JD | 01/03/2022 | 0 | Resource Division | 39.86 | 0 | 0
1294 | Jalpaiguri Division | Jalpaiguri Division | FUEL BILL | Assistant Engineer,HQ | Junior Engineer | VCH/000665/2022-2023 | BP-2022-23-350 | 09/12/2022 | 0 | FILL & SMILE | 0.62 | 0 | 0
1295 | Jalpaiguri Division | Jalpaiguri Division | CONST H/W BHANGARHAT WSS | Assistant Engineer,HQ | Junior Engineer | VCH/001371/2021-2022 | BP-2021-22-516 | 30/03/2022 | 0 | SAHA CONSTRUCTION | 4.83 | 0 | 0
1296 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 250mm x 150mm x 132m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000011/2022-2023 | 872/JD | 04/04/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 7.8 | 7.58 | 0
1297 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supplying and Installation of 77 nos Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division PHE Dte |  | Junior Engineer | ORD/000014/2024-2025 | 88/JSSD | 20/06/2024 | 10 | GOUTAM DAS | 14.3 | 14.25 | 100
1298 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supplying and Installation of 24 nos. Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000015/2024-2025 | 89/JSSD | 20/06/2024 | 10 | GURUKUL INFOTECH | 4.46 | 4.43 | 100
1299 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmention of Purba Batabati Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000025/2022-2023 | 863/JD | 01/04/2022 | 1280 | UNIBRO INFRASERV PRIVATE LIMITED | 236.61 | 176.55 | 100
1300 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1301 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Sluice Valves at Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000115/2024-2025 | 331/JSSD | 10/09/2024 | 7 | SWAPAN SAHA | 0.55 | 0 | 100
1302 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000124/2022-2023 | 84/JSSD | 22/07/2022 | 20 | N S CONSTRUCTION & SUPPLIER | 4.57 | 4.51 | 100
1303 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/08/2025 to 30/09/2025) |  | Junior Engineer | ORD/000153/2025-2026 | 1734/JD | 31/07/2025 | 61 | APIKUL ALI | 0.8 | 0 | 0
1304 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000160/2023-2024 | 793/JD | 24/07/2023 | 180 | TIRTHANKAR CHOWDHURY | 91.24 | 40.38 | 70
1305 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". |  | Junior Engineer | ORD/000201/2025-2026 | 2000/JD | 25/09/2025 | 61 | APIKUL ALI | 0.8 | 0 | 0
1306 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Purba Batabari PWSS in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000404/2023-2024 | 388/JSSD | 09/11/2023 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 3.64 | 0 | 0
1307 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Purba Batabari PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000461/2024-2025 | 108/JD | 16/01/2025 | 60 | M/S. S.D. ENTERPRISE | 19.96 | 0 | 0
1308 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". |  | Junior Engineer | ORD/000474/2025-2026 | 2405/JD | 19/11/2025 | 30 | APIKUL ALI | 0.4 | 0 | 0
1309 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of paver block approach road with land development, inside drain etc. and fixing R.B.T. in boundary wall at H/W Site for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000531/2021-2022 | 134/JD | 14/01/2022 | 15 | SUNIL ROY | 4.46 | 3.52 | 0
1310 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Restoration of pipeline at Purba Batabari PWSS (damaged part) under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000551/2021-2022 | 991/JSSD | 03/01/2022 | 10 | BIMAN DAS | 2.99 | 0 | 0
1311 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000551/2023-2024 | 499/JSSD | 02/01/2024 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 0 | 0 | 0
1312 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000552/2023-2024 | 499/JSSD | 02/01/2024 | 30 | TIRTHANKAR CHOWDHURY | 2.8 | 0 | 0
1313 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of Pump House (2nd T/W Site) and extension of pipeline repairing of pipeline under Purba Batabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000560/2020-2021 | 169/JSSD | 13/08/2020 | 30 | BIMAN DAS | 4.77 | 0 | 0
1314 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jalswapna for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) |  | Junior Engineer | ORD/000788/2021-2022 | 667/JD | 09/03/2022 | 1394 | BOSE ENTERPRISE | 221.99 | 176.41 | 90
1315 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. |  | Junior Engineer | ORD/000830/2021-2022 | 1108/W/JSSD | 27/01/2022 | 45 | N S CONSTRUCTION & SUPPLIER | 4.75 | 4.75 | 100
1316 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain, culvert, Pipe line for H/W site of Purba Batabari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001010/2021-2022 | 1332/JD | 23/08/2021 | 30 | R.S CONSTRUCTION | 15.53 | 14.66 | 0
1317 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Sluice valve Chamber and GI line over culvert for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001047/2021-2022 | 1931/JD | 29/11/2021 | 15 | SUNIL ROY | 1.63 | 1.58 | 0
1318 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Diviion, P.H.E. Dte. |  | Junior Engineer | ORD/001066/2021-2022 | 1064/JSSD | 24/01/2022 | 20 | G. TECH INDIA | 1.83 | 0.74 | 0
1319 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RENOVATION OF B-WALL SOUTH BERUBARI |  | Junior Engineer | VCH/000088/2022-2023 | BP-2022-2023-46 | 24/05/2022 | 0 | A.P CONSTRUCTION | 2.2 | 0 | 0
1320 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | HIRE CHARGES |  | Junior Engineer | VCH/000663/2022-2023 | BP-2022-23-344 | 09/12/2022 | 0 | APIKUL ALI | 0.34 | 0 | 0
1321 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | HIRE CHARGES |  | Junior Engineer | VCH/000664/2022-2023 | BP-2022-23-344 | 09/12/2022 | 0 | RAKESH SARKAR | 0.33 | 0 | 0
1322 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | AUG PURBA BATABARI |  | Junior Engineer | VCH/001080/2021-2022 | BP-2021-22-169 | 14/01/2022 | 0 | BIMAN DAS | 4.36 | 0 | 0
1323 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RESTORATION OF PIPE LINE PURBA BATABARI PWSS |  | Junior Engineer | VCH/001275/2021-2022 | BP-2021-22-508 | 30/03/2022 | 0 | BIMAN DAS | 2.99 | 0 | 0
1324 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PREPARATION OF DPR PURBA BATABARI PWSS |  | Junior Engineer | VCH/001281/2021-2022 | BP-2021-22-489 | 29/03/2022 | 0 | SUBHANKAR GHOSH | 1.57 | 0 | 0
1325 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PROVIDING DRINKING ARRANGEMENT AWC MAL SUB-DIVISION |  | Junior Engineer | VCH/001363/2021-2022 | BP-2021-22-541 | 31/03/2022 | 0 | DREAM CONSTRUCTION | 4.61 | 0 | 0
1326 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SINKING OF TUBEWELL FOR LATAGURI |  | Junior Engineer | VCH/001403/2021-2022 | BP-2021-22-542 | 31/03/2022 | 0 | DREAM CONSTRUCTION | 7.63 | 0 | 0
1327 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM at various House hold and Govt. Aided Educational/ Health Institute under the command area of Rejuvenation of Kathalguri T.G. Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000094/2022-2023 | 1300/JD | 14/06/2022 | 15 | SAHA CONSTRUCTION | 2.15 | 2.18 | 0
1328 | Jalpaiguri Division | Jalpaiguri Division | Repairing of Damaged distribution line due to drain construction by T.G. authority, Land development, re modification of distribution main along with other ancillary works within the command area of rejuvenation of Kathalguri T.G. P.W.S.S. under Jalpaiguri Division, P.H.E.Dte.and I.E.Plant etc. under Jalpaiguri Division, P.H.E.Dte. (from 01.08.2022 to 31.01.2023) | Assistant Engineer,HQ | Junior Engineer | ORD/000215/2022-2023 | 1805/JD | 14/09/2022 | 21 | RABINDRANATH DUTTA | 4.83 | 4.83 | 0
1329 | Jalpaiguri Division | Jalpaiguri Division | Resistivity test at two alternative Site and two reserved sites for sinking of Tube Well at Zone-II for Augmentation of Chamurchi Tea Garden Area Piped Water Supply Scheme and at Two Sites for Rejuvenation of Khthalguri T.G. P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000227/2022-2023 | 1856/JD | 16/09/2022 | 21 | PARAMJYOTI ENTERPRISE | 1.25 | 1.25 | 0
1330 | Jalpaiguri Division | Jalpaiguri Division | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000284/2022-2023 | 649/RWS | 21/10/2022 | 20 | PARAMJYOTI ENTERPRISE | 4.32 | 4.32 | 1
1331 | Jalpaiguri Division | Jalpaiguri Division | Laying of Distribution Line, Along with Rising Main Connection between Head works pump House site and Additional tube well site including common manifold with balanced Functional Household Tap Connection (Phase -IV) in connection with Jal Jeevan Mission under Rejuvenation of Kathalguri T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000429/2022-2023 | 630/JD | 13/03/2023 | 920 | J.M. CONSTRUCTION | 46.3 | 0 | 80
1332 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Kathalguri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000508/2021-2022 | 107/JD | 11/01/2022 | 60 | JITENDRA NATH ROY | 4.65 | 4.65 | 100
1333 | Jalpaiguri Division | Jalpaiguri Division | Construction of 200 Cu.M. capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site and other related works including pump connection of different pump for Rejuvenation of Kathalguri Tea Garden area piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000512/2021-2022 | 352/JD | 03/03/2022 | 180 | NEW KUNDU ENTERPRISE | 81.56 | 72.38 | 100
1334 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (5.40m x 3.60m) with sanitary & plumbing arrangement including Rising Main & interconnections at Head Work site for Augmentation of Kathalguri Water Supply Scheme at Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000604/2023-2024 | 2305/JD | 07/02/2024 | 45 | NEW KUNDU ENTERPRISE | 7.39 | 6.62 | 100
1335 | Jalpaiguri Division | Jalpaiguri Division | Shifting of existing pipeline of Khalaigram W/S Scheme between the Khalaigram Khetifullbari P.W.D. Road under Jalpaiguri Division P.H.E. Dte. (PART - A) | Assistant Engineer,HQ | Junior Engineer | ORD/000633/2020-2021 | 423/JD | 04/06/2020 | 90 | LOKNATH CONSTRUCTION | 28.18 | 1.75 | 0
1336 | Jalpaiguri Division | Jalpaiguri Division | Construction of Foot Path, Drain including rising main interconnections at HW site of Kathalguri PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000813/2023-2024 | 2634/JD | 07/03/2024 | 21 | NEW KUNDU ENTERPRISE | 13.52 | 8.51 | 100
1337 | Jalpaiguri Division | Jalpaiguri Division | LDS FHTC AUG KRANTI (ZONE -I) | Assistant Engineer,HQ | Junior Engineer | VCH/001372/2021-2022 | BP-2021-22-527 | 30/03/2022 | 0 | M/S SIBU DEY AND CO. | 9.39 | 0 | 0
1338 | Jalpaiguri Division | Jalpaiguri Division | LDS BARADIGHI | Assistant Engineer,HQ | Junior Engineer | VCH/001385/2021-2022 | BP-2021-22-528 | 30/03/2022 | 0 | GOUTAM DAS | 4.52 | 0 | 0
1339 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 3rd Tubewell site of Mainatali PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000059/2023-2024 | 324/JD | 18/05/2023 | 14 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.64 | 2.39 | 50
1340 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 183 mm x 125mm dia tube well by ODEX-165 method of drilling for Rejuvenation of Mainatali PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000450/2021-2022 | 198/JD | 21/01/2022 | 30 | M/S BABUN BISWAS | 7.89 | 5.33 | 100
1341 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Mainatali P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000500/2021-2022 | 95/JD | 10/01/2022 | 60 | ABHIJIT SARKAR | 4.65 | 4.68 | 100
1342 | Jalpaiguri Division | Jalpaiguri Division | Construction of Blower Room & IEP (40m3/hr.) of Mainatali PWSS, in connection with Rejuvenation of Mainatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000510/2023-2024 | 1778/JD | 08/12/2023 | 60 | D. S. ENTERPRISE | 16.9 | 15.26 | 75
1343 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Chhaophali PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000042/2023-2024 | 138/JD | 28/04/2023 | 180 | RANJEET SINGH BENIWAL | 131.18 | 58.34 | 50
1344 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of Rising Main along with pump connection for commissioning of the scheme and remaining part of laying distribution system with providing FHTC at Chhaoaphali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000139/2024-2025 | 1531/JD | 01/10/2024 | 30 | PRIYABRATA KARMAKAR | 18.45 | 18.94 | 100
1345 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with approach road at H/W site including rising main and interconnections of Chhaophali PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000699/2023-2024 | 2412/JD | 19/02/2024 | 45 | RANJEET SINGH BENIWAL | 19.17 | 0 | 0
1346 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000034/2023-2024 | 1115/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0
1347 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000182/2023-2024 | 2041/JD | 09/01/2024 | 0 | Resource Division | 2.85 | 0 | 0
1348 | Jalpaiguri Division |  | Construction of different components of Gadang Pratham Khanda PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000475/2022-2023 | 779/JD | 27/03/2023 | 180 | M/S. DOLPHIN CONSTRUCTION CO. | 222.91 | 127.77 | 20
1349 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 152/JD | 28/04/2023 | 0 | Resource Division | 26.83 | 0 | 0
1350 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1838/JD | 15/12/2023 | 0 | Resource Division | 2.62 | 0 | 0
1351 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1352 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
1353 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Paschimbaragila PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000455/2024-2025 | 2334./JD | 12/12/2024 | 45 | PRITAM DUTTA | 21.76 | 0 | 0
1354 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Paschim Baragila PWSS i.e. TW, pump Houses, Water distribution network, OHR, RISING MAIN, FHTC etc. under Jal Jeeban Mission at Block - Maynaguri under Jalpaiguri Divission, P.H.E. Dte. |  | Junior Engineer | ORD/000470/2022-2023 | 776/JD | 27/03/2023 | 180 | TIRTHANKAR CHOWDHURY | 234.57 | 159.05 | 75
1355 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000672/2023-2024 | 167/RWS | 15/02/2024 | 358 | EDIFICE ENTERPRISE | 7.52 | 0 | 100
1356 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site including rising main and interconnections of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000779/2023-2024 | 2496/JD | 28/02/2024 | 45 | TIRTHANKAR CHOWDHURY | 16.53 | 0 | 0
1357 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000022/2023-2024 | 166/JD | 28/04/2023 | 0 | Resource Division | 15.92 | 0 | 0
1358 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000187/2023-2024 | 2050/JD | 09/01/2024 | 0 | Resource Division | 2.89 | 0 | 0
1359 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000075/2022-2023 | 1314/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 0 | 1
1360 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 3rd tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000087/2022-2023 | 74/JSSD | 22/07/2022 | 45 | SUJAN LAMA | 4.65 | 4.65 | 100
1361 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 4th tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000123/2022-2023 | 75/JSSD | 22/07/2022 | 45 | SUJOY CHOWDHURY | 4.65 | 4.65 | 100
1362 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Chilouni Tea Garden PWSS i.e. OHR, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000182/2023-2024 | 852/JD | 28/07/2023 | 569 | NARAYAN CHANDRA SAHA | 147.52 | 118.57 | 58
1363 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retroffitting works, repairing of 2 nos pump house 2 nos boundary wall, repairing of Rising main line and other allied works at Chilaoni TG Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000398/2022-2023 | 607/JD | 09/03/2023 | 30 | SUJAN LAMA | 29.35 | 0 | 0
1364 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Matiali block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000454/2023-2024 | 1286/RWS | 28/11/2023 | 30 | B.M CONSTRUCTION | 3.11 | 3.11 | 100
1365 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000082/2023-2024 | 1069/JD | 24/08/2023 | 0 | Resource Division | 15.45 | 0 | 0
1366 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system along with ancillary works for Rejuvenation of Bhandani Piped water supply scheme in connection with Jal Jeevan mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000009/2024-2025 | 422/JD | 12/06/2024 | 323 | SANJIT SAHA | 29.06 | 0 | 50
1367 | Jalpaiguri Division | Jalpaiguri Division | Providing FHTC Including Restoration of Existing FHTC in the Command Area of Bhandani PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000505/2024-2025 | 2398/JD | 19/12/2024 | 30 | SANJIT SAHA | 6.96 | 0 | 0
1368 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000099/2023-2024 | 1054/JD | 24/08/2023 | 0 | Resource Division | 1.25 | 0 | 0
1369 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1370 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Drain, Footpath including Balance Portion of Distribution Network and other Allied Works related to Pipe Line at Diana Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000362/2024-2025 | 2012/JD | 18/11/2024 | 30 | VISHAL ENTERPRISES | 9.7 | 0 | 0
1371 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Diana Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Banerhat under Jalpaiguri Division. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000477/2022-2023 | 750/JD | 24/03/2023 | 180 | VISHAL ENTERPRISES | 227.13 | 130.75 | 50
1372 | Jalpaiguri Division | Northern Mechanical Division | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No. WB71B-8742) (From 01.04.2025 to 30.04.2025) | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000787/2024-2025 | 108-HQ/JD | 28/03/2025 | 31 | RAKESH SARKAR | 0.15 | 0.15 | 0
1373 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000006/2023-2024 | 150/JD | 28/04/2023 | 0 | Resource Division | 15.68 | 0 | 0
1374 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000119/2023-2024 | 1830/JD | 15/12/2023 | 0 | Resource Division | 5.95 | 0 | 0
1375 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1376 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Lakhipara Tea Garden PWSS i.e. TW, Pump House, Water distribution Network, OHR , Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000492/2022-2023 | 824/JD | 30/03/2023 | 1007 | S.S. CONSTRUCTION | 297.96 | 225.12 | 60
1377 | Jalpaiguri Division | Northern Mechanical Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (From 01.04.2025 to 30.04.2025) | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000789/2024-2025 | 110-HQ/JD | 28/03/2025 | 31 | AJIJUL HAQUE | 0.15 | 0 | 0
1378 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000025/2023-2024 | 169/JD | 28/04/2023 | 0 | Resource Division | 12.25 | 0 | 0
1379 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000120/2023-2024 | 1834/JD | 15/12/2023 | 0 | Resource Division | 7.44 | 0 | 0
1380 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Kholachand Fapri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. under Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000064/2023-2024 | 266/JD | 10/05/2023 | 180 | M/S SARKAR ENTERPRISE | 262.01 | 0 | 35
1381 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Kholachand Fapri Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000800/2024-2025 | 87-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
1382 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000005/2024-2025 | 53/JD | 09/04/2024 | 0 | Resource Division | 13.2 | 0 | 0
1383 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000186/2023-2024 | 2049/JD | 09/01/2024 | 0 | Resource Division | 7.47 | 0 | 0
1384 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation Of Palashbari Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000082/2023-2024 | 435/JD. | 08/06/2023 | 798 | LOKNATH CONSTRUCTION | 77.09 | 21.8 | 41
1385 | Jalpaiguri Division | Jalpaiguri Division | Consturction of 3rd Tube Well site Boundary wall, Drain, Pathway at Palashbari PWSS i.c.w. Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000535/2024-2025 | 126/JD | 16/01/2025 | 30 | LOKNATH CONSTRUCTION | 11.68 | 0 | 0
1386 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall Surface, Drain, Pathway with related ancillary work at Head Works site of Palashbari Tea Garden Area PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000783/2021-2022 | 839/JD | 31/03/2022 | 30 | DULAL CHOUDHURY | 28.53 | 13.25 | 1
1387 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Different Stationary Items for Office Use under Jalpaiguri RWS Sub Division. PHE Dte. |  | Junior Engineer 2 | BILL/00927/2024-2025 | BP-2024-25-515 | 14/11/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.23 | 0 | 0
1388 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of one No. tube well (250mm x 200mm) by Reverse Rotary Method of Drilling and Construction of Pump House (5.40m x 3.60m) and Iron Elimination Plant for direct boosting arrangement for Augmentation of Porapara Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000069/2024-2025 | 988/JD | 14/08/2024 | 120 | SADHAN KARMAKAR | 38.03 | 0 | 0
1389 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Porapara PWSS I.e. TW, Pump Houses, Boundary wall IEP, Rising main etc. at Block - Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000075/2023-2024 | 1003/JD | 17/05/2023 | 45 | B.M CONSTRUCTION | 51.2 | 51.2 | 100
1390 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000100/2025-2026 | 479/RWS | 29/05/2025 | 30 | JAYDEB SAHA | 7.95 | 0 | 100
1391 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Emergency extension and reparing of pipe line to facilite FHTC at different location Pora Para Water Supply Scheme under Jalpaiguri Division, PHE Dte. Under JJM. |  | Junior Engineer 2 | ORD/000448/2023-2024 | 1282/RWS | 28/11/2023 | 20 | B.M CONSTRUCTION | 6.16 | 6.12 | 100
1392 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Sadar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer 2 | ORD/000457/2023-2024 | 1290/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
1393 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000077/2024-2025 | 2208/JD | 01/12/2024 | 0 | Resource Division | 24.23 | 0 | 0
1394 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Khasjangal-I PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Mal under Jalpaiguri Division. |  | Junior Engineer | ORD/000257/2023-2024 | 942/JD | 08/08/2023 | 721 | A. K. INDUSTRIES | 133.2 | 0 | 30
1395 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000066/2023-2024 | 1082/JD | 24/08/2023 | 0 | Resource Division | 8.97 | 0 | 0
1396 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000156/2023-2024 | 2024/JD | 09/01/2024 | 0 | Resource Division | 2.81 | 0 | 0
1397 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Augmentation of Angrabhasa PWSS i.e. TW, Pump Houses, Boundary Walls. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000362/2023-2024 | 1436/JD | 05/10/2023 | 60 | M/S ROY & SARKAR CONSTRUCTION | 27.72 | 11.42 | 35
1398 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Nagrakata block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000453/2023-2024 | 1287/RWS | 28/11/2023 | 30 | B.M CONSTRUCTION | 3.11 | 3.11 | 100
1399 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000091/2023-2024 | 1071/JD | 24/08/2023 | 0 | Resource Division | 41.27 | 0 | 0
1400 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1401 | Jalpaiguri Division |  | Construction of different components of Ellenburry Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000270/2023-2024 | 939/JD | 08/08/2023 | 966 | NARENDRA KUMAR | 175.96 | 44.96 | 55
1402 | Jalpaiguri Division |  | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 3rd tube well site of Ellenbari Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  |  | ORD/000442/2024-2025 | 2318/JD | 11/12/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0
1403 | Jalpaiguri Division |  | Balance laying Distribution Network and Providing Functional House Hold Tap Connection including TW, Pump House, Boundary Wall of Ellenbari Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000478/2025-2026 | 2511/JD | 10/12/2025 | 60 | NARENDRA KUMAR | 40.39 | 0 | 0
1404 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 2020/JD | 09/01/2024 | 0 | Resource Division | 4.28 | 0 | 0
1405 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Patharjhora Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000067/2023-2024 | 346/JD. | 23/05/2023 | 180 | SRINIWAS AGARWAL | 208.93 | 99.4 | 62
1406 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1407 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of one no. Tube Well by Modified DTH - ODEX big dia tube well 200x150 mm dia for Pathorjhora piped water supply scheme i.c.w. Jal jeevan Mission at Mal Block under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000300/2023-2024 | 1357/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.54 | 15.48 | 100
1408 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 (Two) Nos Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Patharjohra Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000826/2023-2024 | 2750/JD | 14/03/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.26 | 33.38 | 100
1409 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Drilling of 200mm Big Dia Tube Well by Modified DTH-ODEX method at 2nd tube well site of Pathorjhora Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000976/2023-2024 | 588/A/AE/JSSD/CAMP | 18/03/2024 | 2 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 4.36 | 4.36 | 100
1410 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000203/2023-2024 | 2062/JD | 10/01/2024 | 0 | Resource Division | 6.09 | 0 | 0
1411 | Jalpaiguri Division | Northern Mechanical Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1412 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1413 | Jalpaiguri Division | Northern Mechanical Division | Sinking of 1 (One) No Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling at Meanglass Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000106/2024-2025 | 1416/JD | 20/09/2024 | 20 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 20.88 | 0 | 0
1414 | Jalpaiguri Division | Northern Mechanical Division | Sinking of Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling for one no. tube well at Meenglass Tea Garden Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000468/2023-2024 | 1761/JD | 08/12/2023 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.46 | 19.19 | 100
1415 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000202/2023-2024 | 2072/JD | 10/01/2024 | 0 | Resource Division | 6.75 | 0 | 0
1416 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1417 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1418 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Sisubari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000145/2023-2024 | 710/JD | 13/07/2023 | 180 | PRADIP SAHA | 148.34 | 71.73 | 48
1419 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000162/2023-2024 | 2015/JD | 09/01/2024 | 0 | Resource Division | 4.08 | 0 | 0
1420 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of June 2024 |  |  | BILL/00397/2024-2025 | BP-2024-25-232 | 18/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1421 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of April 2024 |  |  | BILL/00398/2024-2025 | BP-2024-25-233 | 18/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1422 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00399/2024-2025 | BP-2024-25-270 | 30/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
1423 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of August 2024 |  |  | BILL/00650/2024-2025 | BP-2024-25-363 | 13/09/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
1424 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00651/2024-2025 | BP-2024-25-362 | 13/09/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
1425 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of September 2024 |  |  | BILL/00868/2024-2025 | BP-2024-25-494 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1426 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00869/2024-2025 | BP-2024-25-495 | 07/10/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
1427 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00934/2024-2025 | BP-2024-25-519 | 25/11/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
1428 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of October 2024 |  |  | BILL/00935/2024-2025 | BP-2024-25-520 | 25/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1429 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1430 | Jalpaiguri Division |  | Continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R. W.S Sub-Division P.HE. Dte. for 6 month (Period from 01/08/2024 to 31/01/2025) |  |  | ORD/000054/2024-2025 | 709/RWS | 31/07/2024 | 184 | ASHIM SARKAR | 0.88 | 0.88 | 0
1431 | Jalpaiguri Division |  | Construction of different components of Chapgar (Zone-I & II) PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block -Maynaguri under Jalpaiguri Division, P.H.E Dte. |  |  | ORD/000264/2023-2024 | 944/JD | 08/08/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 488 | 89.09 | 34
1432 | Jalpaiguri Division |  | Facelifting and Interior furishing works for Junior Engineer Room-1 and DPMU Room under Jalpaiguri Division, PHE Dte. |  |  | ORD/000555/2023-2024 | 501/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.65 | 8.58 | 100
1433 | Jalpaiguri Division |  | Facelifting and Interior furnishing works for Junior Engineer Room-2 and Estimating Section under Jal;paiguri Division,P.H.E.Dte. |  |  | ORD/000556/2023-2024 | 502/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.66 | 9.5 | 100
1434 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 2061/JD | 10/01/2024 | 0 | Resource Division | 9.79 | 0 | 0
1435 | Jalpaiguri Division | Jalpaiguri Division | Shifting of pipeline in connection with PWD road widning work from Domohani PWSS at Moynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000027/2022-2023 | 975/JD | 20/04/2022 | 45 | PROVA CONSTRUCTION | 38.07 | 0 | 0
1436 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement at 3rd tube well site of Augmentation Domohoni W/S Scheme under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000048/2022-2023 | 1193/JD | 20/05/2022 | 45 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.65 | 4.65 | 100
1437 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Domohani piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000051/2021-2022 | 1066/JD | 02/07/2021 | 21 | PRADIP KR SEN | 4.82 | 4.57 | 0
1438 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) with retrofitting works in connection with Jaldhara / Jal Sapna under the command area of Domohani Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, P.H.E Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000055/2022-2023 | 939/JD | 18/04/2022 | 45 | PRADIP KR SEN | 4.85 | 4.85 | 1
1439 | Jalpaiguri Division | Jalpaiguri Division | ADDITIONAL RISING MAIN FOR AUGMENTATION OF DOMOHANI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000199/2024-2025 | 1592/JD | 23/10/2024 | 20 | M/S PRAFULLA GHOSH | 10.26 | 0 | 0
1440 | Jalpaiguri Division | Jalpaiguri Division | Renovation of front side boundary wall and construction of shade over front door of the pump house and ancillary works of the 2nd tube well site of Domohani Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000213/2022-2023 | 1803/JD | 14/09/2022 | 21 | M/S SURAJIT DEY AND CO. | 2.41 | 0 | 0
1441 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Domohani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000232/2022-2023 | 2008/JD | 01/11/2022 | 30 | ALOKE DEY | 40.21 | 33.14 | 1
1442 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall, Blower Room, IEP of 3rd Pump House & Providing FHTC of Domohani PWSS, in connection with Augmentation of Domohani PWSS under Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000390/2023-2024 | 1554/JD | 01/11/2023 | 60 | B.M CONSTRUCTION | 67.78 | 68.45 | 100
1443 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of different components of Head Work Site of Domohani PWSS under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000537/2023-2024 | 1972/JD | 03/01/2024 | 45 | SUKES BASU MAJUMDAR | 39.34 | 40.38 | 100
1444 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Domohani Piped Water Supply Scheme at Moynaguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000546/2021-2022 | 661/JD | 09/03/2022 | 90 | SUKES BASU MAJUMDAR | 335.53 | 345.54 | 1
1445 | Jalpaiguri Division | Jalpaiguri Division | Sinking of One No. tube Well (250mm x 200mm) by Reverse Rotary Method of Drilling and others components for boosting in Augmentation of Domohoni Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000802/2023-2024 | 2629/JD | 07/03/2024 | 542 | M/S PRAFULLA GHOSH | 52.42 | 10.12 | 50
1446 | Jalpaiguri Division | Jalpaiguri Division | Engagement of Block Level Staff (Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Maynaguri block in Connection with JJM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. (2nd Call) | Assistant Engineer,HQ | Junior Engineer | ORD/000804/2023-2024 | 256/RWS | 07/03/2024 | 30 | B.M CONSTRUCTION | 3.11 | 3.11 | 100
1447 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000004/2021-2022 | 54/JD | 05/01/2022 | 0 | Resource Division | 5.5 | 0 | 0
1448 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000031/2024-2025 | 2099/JD | 25/11/2024 | 0 | Resource Division | 80.22 | 0 | 0
1449 | Jalpaiguri Division | Jalpaiguri Division | fhtc domohani | Assistant Engineer,HQ | Junior Engineer | VCH/000024/2022-2023 | BP-2021-23-1 | 21/04/2022 | 0 | PRADIP KR SEN | 4.57 | 0 | 0
1450 | Jalpaiguri Division | Jalpaiguri Division | DPR PREPARATION | Assistant Engineer,HQ | Junior Engineer | VCH/001143/2021-2022 | BP-2021-22-262 | 16/02/2022 | 0 | SUBHANKAR GHOSH | 2.37 | 0 | 0
1451 | Jalpaiguri Division | Jalpaiguri Division | SINKING REJ CHOUHADDI | Assistant Engineer,HQ | Junior Engineer | VCH/001379/2021-2022 | BP-2021-22-545 | 31/03/2022 | 0 | J.M. CONSTRUCTION | 7 | 0 | 0
1452 | Jalpaiguri Division | Jalpaiguri Division | FHTC MOGOLKATA T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001383/2021-2022 | BP-2021-22-498 | 29/03/2022 | 0 | PROFULLA GHOSH | 30.06 | 0 | 0
1453 | Jalpaiguri Division | Jalpaiguri Division | LDS INDONG T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001412/2021-2022 | BP-2021-22-546 | 31/03/2022 | 0 | KANAI LAL SEN | 16.3 | 0 | 0
1454 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of May 2024 | Assistant Engineer | Junior Engineer | BILL/00365/2024-2025 | BP-2024-25-191 | 08/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1455 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply mobil to vehicle no WB 71 A 5774 | Assistant Engineer | Junior Engineer | BILL/00366/2024-2025 | BP-2024-25-271 | 30/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
1456 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | Assistant Engineer | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1457 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Saptibari Zone- II Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2024-2025 | 987/JD | 14/08/2024 | 360 | MONOJ GHOSH | 59.77 | 0 | 85
1458 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Saptibari Zone- III Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000188/2024-2025 | 1534/JD | 01/10/2024 | 243 | KAMALESH SEN | 52.66 | 0 | 90
1459 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Saptibari (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 1350/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 571.97 | 214.5 | 90
1460 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Saptibari (Zone-II) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000326/2023-2024 | 1351/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 445.3 | 317.61 | 90
1461 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Saptibari (Zone-III) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000327/2023-2024 | 1352/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 432.29 | 224.47 | 79
1462 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Saptibari Zone-I Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000674/2024-2025 | 486/JD | 11/03/2025 | 120 | DIPAK KUMAR CHAKRABORTY | 71.83 | 0 | 0
1463 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2023-2024 | 151/RWS | 15/02/2024 | 30 | DEBABRATA SARKAR | 6.97 | 5.62 | 100
1464 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000688/2023-2024 | 150/RWS | 15/02/2024 | 30 | SOUVIK SAHA | 7.24 | 7.23 | 100
1465 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000777/2023-2024 | 2498/JD | 28/02/2024 | 45 | M/S BOSE ENTERPRISE | 22.62 | 0 | 0
1466 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2023-2024 | 2497/JD | 28/02/2024 | 45 | KAMAL DAS | 23.41 | 0 | 100
1467 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2023-2024 | 2627/JD | 07/03/2024 | 45 | SWAPAN SAHA | 23.15 | 0 | 0
1468 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, pipeline for washout at 2nd Tubewell site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000805/2023-2024 | 257/RWS | 07/03/2024 | 30 | UCO LABOUR CO-OPERATIVE SOCIETY LTD. | 7.24 | 7 | 100
1469 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2024-2025 | 51/JD | 09/04/2024 | 0 | Resource Division | 64.27 | 0 | 0
1470 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000168/2023-2024 | 2036/JD | 09/01/2024 | 0 | Resource Division | 37.59 | 0 | 0
1471 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000024/2021-2022 | 744/JD | 13/05/2021 | 30 | KAMALESH SEN | 23.73 | 0 | 1
1472 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000026/2021-2022 | 746/JD | 13/05/2021 | 20 | RABINDRANATH DUTTA | 13.97 | 6.15 | 1
1473 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2021-2022 | 1065/JD | 02/07/2021 | 21 | GANAPATI CO-OP LABOUR CONT. & CONST. SOCIETY LTD. | 4.83 | 0 | 1
1474 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000098/2021-2022 | 1337/JD | 23/08/2021 | 30 | DULAL CHOUDHURY | 30.23 | 0 | 0
1475 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-IV. | Assistant Engineer,HQ | Junior Engineer | ORD/000106/2021-2022 | 1257/JD | 10/08/2021 | 15 | ALICK DUTTA | 4.81 | 0 | 1
1476 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- V) | Assistant Engineer,HQ | Junior Engineer | ORD/000135/2021-2022 | 1444/JD | 09/09/2021 | 30 | ALOKE DEY | 30.23 | 0 | 1
1477 | Jalpaiguri Division | Jalpaiguri Division | FHTC MADHYAKHUTTIMARI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000475/2021-2022 |  | 29/10/2021 | 0 | RABINDRANATH DUTTA | 5.9 | 0 | 0
1478 | Jalpaiguri Division | Jalpaiguri Division | fhtc madhyakhuttimari | Assistant Engineer,HQ | Junior Engineer | VCH/000803/2021-2022 | BP-2021-22-107 | 16/11/2021 | 0 | KAMALESH SEN | 11.92 | 0 | 0
1479 | Jalpaiguri Division | Jalpaiguri Division | fhtc madhya khuttimari pwss | Assistant Engineer,HQ | Junior Engineer | VCH/000804/2021-2022 | BP-2021-22-106 | 16/11/2021 | 0 | RABINDRANATH DUTTA | 5.9 | 0 | 0
1480 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000091/2020-2021 | 1278/JD | 18/11/2020 | 60 | SANDIP BANIK | 28.51 | 0 | 1
1481 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000092/2020-2021 | 1279/JD | 18/11/2020 | 30 | NEW KUNDU ENTERPRISE | 14.38 | 0 | 1
1482 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FOR PURBA DURAMARI PWSS |  | Junior Engineer | VCH/000045/2021-2022 | 08 | 07/05/2021 | 0 | SANJIT SAHA | 8.91 | 0 | 0
1483 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC FOR AMBARI T.G PWSS |  | Junior Engineer | VCH/001128/2020-2021 | 1077 | 14/01/2021 | 0 | SAHA CONSTRUCTION | 4.03 | 0 | 0
1484 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PRIVIDING FHTC AT AMBARI T.G PWWSS |  | Junior Engineer | VCH/001194/2020-2021 | 919 | 04/01/2021 | 0 | SANDIP BANIK | 4.21 | 0 | 0
1485 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC AT AMBARI T.G PWSS |  | Junior Engineer | VCH/001213/2020-2021 | 1123 | 22/01/2021 | 0 | SANDIP BANIK | 28.5 | 0 | 0
1486 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC Ambari TG Part D |  | Junior Engineer | VCH/001214/2020-2021 | 1124 | 22/01/2021 | 0 | NEW KUNDU ENTERPRISE | 11.95 | 0 | 0
1487 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SADAR BLOCK ZONE II |  | Junior Engineer | VCH/001345/2021-2022 | BP-2021-22- 412 | 23/03/2022 | 0 | BISWAJIT BHADURI | 4.92 | 0 | 0
1488 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works & other ancillary works related to FHTC at different places of Ambari TG PWSS.under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | VCH/001485/2020-2021 | 1589 | 23/04/2021 | 0 | SANDIP BANIK | 1.82 | 0 | 0
1489 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORK & OTHER ANCILLARY WORK RELATED FHTC FOR AMBARI T.G PWSS |  | Junior Engineer | VCH/001795/2020-2021 | 1589 | 21/03/2021 | 0 | SANDIP BANIK | 1.82 | 0 | 0
1490 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Boalmari Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000151/2020-2021 | 475/RWS | 15/10/2020 | 30 | KABYA ENTERPRISE | 4.7 | 4.23 | 1
1491 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of BOALMARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  | Junior Engineer | ORD/000173/2020-2021 | 1105/JD | 20/10/2020 | 90 | UMWEL ENGINEER PRIVATE LIMITED | 39.23 | 45.87 | 1
1492 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri.(3rd Call) |  | Junior Engineer | ORD/000294/2023-2024 | 971/RWS | 18/08/2023 | 200 | KANAI LAL SEN | 3.13 | 0 | 100
1493 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing house connection under Boalmari Water Supply Scheme at Sadar Block under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000486/2021-2022 | 296/RWS | 20/04/2021 | 15 | DEBABRATA GHOSH | 4.44 | 0 | 0
1494 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing functional household tap connection (FHTC) with Jalsapna including Retrofitting works under the command area of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte.(Part ¿ F) |  | Junior Engineer | ORD/000571/2021-2022 | 182/RWS | 04/03/2022 | 15 | KANAI LAL SEN | 4.51 | 0 | 0
1495 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BOALMARI |  | Junior Engineer | VCH/000327/2021-2022 |  | 01/10/2021 | 0 | KANAI LAL SEN | 22.04 | 0 | 0
1496 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting Boalmari WSS |  | Junior Engineer | VCH/000465/2021-2022 |  | 26/10/2021 | 0 | KANAI LAL SEN | 4.78 | 0 | 0
1497 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  | Junior Engineer | ORD/000083/2020-2021 | 1268/JD | 18/11/2020 | 90 | NARAYAN CHAKRABORTY | 36.96 | 60.24 | 1
1498 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional House hold tap Connection(FHTC) In connection with Jaldhara/ Jalsapna at Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) |  | Junior Engineer | ORD/000178/2021-2022 | 683/RWS | 27/09/2021 | 15 | BISWAJIT BHADURI | 3.4 | 0 | 1
1499 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional House hold tap Connection (FHTC)in connection with Jaldhara/ Jalsapna a t Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ H) |  | Junior Engineer | ORD/000180/2021-2022 | 685/RWS | 27/09/2021 | 15 | NARAYAN CHAKRABORTY | 4.25 | 3.47 | 1
1500 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000183/2020-2021 | 1498/JD | 22/12/2020 | 30 | BISWAJIT BHADURI | 17.51 | 13.16 | 1
1501 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing & renovation of Boundary wall, approach At H/W site for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000212/2021-2022 | 699/RWS | 27/09/2021 | 30 | ASIT PAUL | 4.84 | 0 | 1
1502 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Kamar para, Taltala line , Purba Madati para, Purba Kamar Para for Argi Garalbari . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000273/2021-2022 | 817/RWS | 30/11/2021 | 10 | BISWAJIT BHADURI | 4.85 | 0 | 1
1503 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement of Rejuvenation Garalbari . W/S/S ( zone - I ) 3rd T/W site under Jalpaiguri Division , P.H.E. Dte. |  | Junior Engineer | ORD/000318/2021-2022 | 869/RWS | 08/12/2021 | 30 | ABHIJIT SARKAR | 4.65 | 9.37 | 0
1504 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBAMAGURMARI PWSS |  | Junior Engineer | VCH/001312/2021-2022 | BP-2021-22-334 | 03/03/2022 | 0 | ARATI CONSTRUCTION | 7.42 | 0 | 0
1505 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBAMAGUR MARI PWSS |  | Junior Engineer | VCH/001313/2021-2022 | BP-2021-22-335 | 03/03/2022 | 0 | MONOJ GHOSH | 7.74 | 0 | 0
1506 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC NAYASAILYA T.G PWSS |  | Junior Engineer | VCH/001314/2021-2022 | BP-2021-22-336 | 03/03/2022 | 0 | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0
1507 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC ENGO T.G PWSS |  | Junior Engineer | VCH/001327/2021-2022 | BP-2021-22-464 | 27/03/2022 | 0 | NABIN PRODHAN | 2.26 | 0 | 0
1508 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retroftting of existing LDS under the command area of Red Bank Tea Garden area piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- II) | Assistant Engineer,HQ | Junior Engineer | ORD/000176/2020-2021 | 1295/JD | 23/11/2020 | 90 | M/S R.N. TRADERS | 39.75 | 15.72 | 1
1509 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NGAISUREE T.G. Area piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte.(Phase-II). |  | Junior Engineer | ORD/000085/2020-2021 | 1273/JD | 18/11/2020 | 1625 | SADHAN KARMAKAR | 43.64 | 0 | 100
1510 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) |  | Junior Engineer | ORD/000223/2020-2021 | 94/JD | 14/01/2021 | 45 | SAPTASWA SARKAR | 28 | 24.49 | 0
1511 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | providing fhtc for maynatali pwss |  | Junior Engineer | VCH/000362/2021-2022 | 357/21-22 | 16/09/2021 | 0 | SANJIT SAHA | 19.92 | 0 | 0
1512 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | LDS FOR D-SHALBARI PWSS |  | Junior Engineer | VCH/000509/2021-2022 | 336/21-22 | 04/10/2021 | 0 | ROY & SARKAR CONSTRUCTION | 5.85 | 0 | 0
1513 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORK AT BOALMARI PWSS |  | Junior Engineer | VCH/001782/2020-2021 | 1564 | 19/03/2021 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 4.34 | 0 | 0
1514 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORK RELATED FHTC FOR BOALMARI PWSS |  | Junior Engineer | VCH/001786/2020-2021 | 1563 | 19/03/2021 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 4.21 | 0 | 0
1515 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | NH Road(4 Lane) crossing through underpass at Assam More .i.c.w. FHTC of Mohit Nagar W/S Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000281/2022-2023 | 646/RWS | 21/10/2022 | 30 | M/S DEY & ROY CHOUDHURY | 3.86 | 0 | 0
1516 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at Sebagram In connection with Jaldhara/ Jal Sapna under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) |  | Junior Engineer | ORD/000333/2023-2024 | 1081/RWS | 19/09/2023 | 30 | M/S DEY & ROY CHOUDHURY | 6.68 | 0 | 100
1517 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Thorough repairing and overhauling of the Iron Elimination Plant (double Unit) at Mohitnagar Water Supply Scheme (H/W Site), under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000335/2023-2024 | 1083/RWS | 19/09/2023 | 15 | M/S DEY & ROY CHOUDHURY | 5.41 | 0 | 100
1518 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MOHITNAGAR |  | Junior Engineer | VCH/000087/2022-2023 | BP-2022-2023-41 | 24/05/2022 | 0 | M/S DEY & ROY CHOUDHURY | 7.1 | 0 | 0
1519 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SATHKAYA TG PWSS |  | Junior Engineer | VCH/000338/2021-2022 |  | 04/10/2021 | 0 | LOKNATH CONSTRUCTION | 22.44 | 0 | 0
1520 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MOHIT NAGAR |  | Junior Engineer | VCH/001147/2021-2022 | BP-2021-22-252 | 16/02/2022 | 0 | ANUP KUMAR KUNDU | 20.15 | 0 | 0
1521 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC CHALAUNI |  | Junior Engineer | VCH/001161/2021-2022 | BP-2021-22-240 | 22/02/2022 | 0 | BILTU DAS | 10.56 | 0 | 0
1522 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BATABARI T.G |  | Junior Engineer | VCH/001162/2021-2022 | BP-2021-22-264 | 22/02/2022 | 0 | PRIYABRATA KARMAKAR | 7.52 | 0 | 0
1523 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc matiali bazar |  | Junior Engineer | VCH/001173/2021-2022 | BP-2021-22-233 | 23/02/2022 | 0 | M/S DEY & ROY CHOUDHURY | 15.39 | 0 | 0
1524 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC JABRAMALI |  | Junior Engineer | VCH/001210/2021-2022 | BP-2021-22-332 | 28/02/2022 | 0 | SUKES BASU MAJUMDAR | 12.67 | 0 | 0
1525 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DABGRAM-II |  | Junior Engineer | VCH/001256/2021-2022 | BP-2021-22-410 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 52.17 | 0 | 0
1526 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DAKSHIN SALBARI PWSS |  | Junior Engineer | VCH/001259/2021-2022 | BP-2021-22-402 | 23/03/2022 | 0 | NARAYAN SARKAR | 20.51 | 0 | 0
1527 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BHANGARHAT PWSS |  | Junior Engineer | VCH/001311/2021-2022 | BP-2021-22-341 | 03/03/2022 | 0 | BILTU DAS | 26.16 | 0 | 0
1528 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DAKSHIN SALBARI PWSS |  | Junior Engineer | VCH/001342/2021-2022 | BP-2021-22402 | 23/03/2022 | 0 | NARAYAN SARKAR | 20.51 | 0 | 0
1529 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MOHIT NAGAR PWSS |  | Junior Engineer | VCH/001392/2021-2022 | BP-2021-22-550 | 31/03/2022 | 0 | M/S DEY & ROY CHOUDHURY | 15.24 | 0 | 0
1530 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000214/2020-2021 | 1547/JD | 31/12/2020 | 75 | SCEC BOENTER KDAS JOINT VENTURE | 42.4 | 38.32 | 0
1531 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000341/2020-2021 | 566/JSSD | 01/02/2021 | 15 | ALICK DUTTA | 4.61 | 0 | 0
1532 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORK FOR FHTC FOR JABRAMALI PWSS |  | Junior Engineer | VCH/000121/2021-2022 | 124/21-22 | 07/07/2021 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 13.89 | 0 | 0
1533 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ADD BILL |  | Junior Engineer | VCH/000769/2021-2022 | 536/21-22 | 17/11/2021 | 0 | GENESIS ADVERTISING PVT LTD | 2.89 | 0 | 0
1534 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna under the command area of Sajnapara Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000211/2022-2023 | 1801/JD | 14/09/2022 | 21 | RAGHU DAS | 4.37 | 4.36 | 1
1535 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sajnapara P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000502/2021-2022 | 97/JD | 10/01/2022 | 60 | DEEP CONSTRUCTION | 4.65 | 4.65 | 0
1536 | Jalpaiguri Division | Jalpaiguri Division | Supply of fuel against vehicle WB-71B-3112 under Assistant Engineer Jalpaiguri Sadar Sub-Division PHE Dte for the month April 2023 | Assistant Engineer,HQ | Junior Engineer | BILL/00208/2023-2024 | BP-2023-24-116 | 01/06/2023 | 0 | FILL & SMILE | 0.26 | 0 | 0
1537 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | Assistant Engineer,HQ | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0.36 | 0
1538 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | Assistant Engineer,HQ | Junior Engineer | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0.34 | 1
1539 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000533/2021-2022 | 131/JD | 14/01/2022 | 60 | SUKUMAR KUNDU | 4.65 | 4.65 | 100
1540 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000558/2021-2022 | 452/JD | 18/02/2022 | 30 | MECHANO TRADING CO. | 7.79 | 7.36 | 1
1541 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000559/2021-2022 | 453/JD | 18/02/2022 | 30 | MECHANO TRADING CO. | 7.79 | 6.18 | 1
1542 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000577/2021-2022 | 143/JD | 18/01/2022 | 60 | PRIYABRATA KARMAKAR | 4.65 | 4.65 | 0
1543 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000605/2023-2024 | 2306/JD | 07/02/2024 | 30 | SUKUMAR KUNDU | 8.82 | 6.77 | 100
1544 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000606/2023-2024 | 2307/JD | 07/02/2024 | 30 | PRIYABRATA KARMAKAR | 9.03 | 8.72 | 100
1545 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORKS SAMSING T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001269/2021-2022 | BP-2021-22-518 | 30/03/2022 | 0 | SUJAN LAMA | 11.66 | 0 | 0
1546 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two No. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method, at Indong TG area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000074/2022-2023 | 1313/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 13.47 | 0
1547 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system (Phase - II) & Rising Main for Ingdong Tea Garden piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000137/2023-2024 | 705/JD | 13/07/2023 | 21 | KANAI LAL SEN | 21.42 | 21.76 | 100
1548 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m X 3.60 m) size with Sanitary & Plumbing arrangement at Head Works Site for Indong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000356/2022-2023 | 856/JD | 01/04/2022 | 60 | SUJOY CHOWDHURY | 5.61 | 5.61 | 0
1549 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system including Providing Functional Household Tap Connection in connection with Jal Swapna for Indong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000566/2021-2022 | 690/JD | 15/03/2022 | 1236 | KANAI LAL SEN | 112.93 | 79.86 | 90
1550 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) at Indong T.G. Area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000695/2021-2022 | 1068/JSSD | 25/01/2022 | 20 | MOYTEC | 2.02 | 2.02 | 0
1551 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 200 Cum OHR as per Departmental Design & Drawing for INDONG Tea Garden Area Piped Water Supply Scheme Block : Matiali District- Jalpaiguri. |  | Junior Engineer | ORD/000697/2021-2022 | 472/JD | 21/02/2022 | 180 | M/S SIBU DEY AND CO. | 54.95 | 49.29 | 100
1552 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size with Sanitary & Plumbing arrangement at 2nd Tube well site for Indong T.G. area of P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000709/2021-2022 | 1043/JSSD | 24/01/2022 | 45 | ABHISEK KUNDU | 4.63 | 4.63 | 0
1553 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 2nd tubewell site of Indong Tea Garden Area piped water supply scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001008/2021-2022 | 1039/JSSD | 21/01/2022 | 20 | BISWAJIT MANDAL | 3.76 | 0 | 0
1554 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000001/2022-2023 | 1064/JD | 28/04/2022 | 0 | Resource Division | 37.54 | 0 | 0
1555 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000031/2023-2024 | 175/JD | 28/04/2023 | 0 | Resource Division | 14.68 | 0 | 0
1556 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000206/2023-2024 | 2065/JD | 10/01/2024 | 0 | Resource Division | 7.61 | 0 | 0
1557 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil investigation work for 200 CUM Over head reservoir (OHR) at Indong TG |  | Junior Engineer | VCH/000365/2022-2023 |  | 27/09/2022 | 0 | MOYTEC | 1.01 | 0 | 0
1558 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA pipe water Supply schme at Matialy Block under Jalpaiguri Division, P.H.E Dte.(Phase-IX) |  | Junior Engineer | ORD/000088/2022-2023 | 76/JSSD | 22/07/2022 | 15 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.84 | 4.67 | 0
1559 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) inconnection with JJM/Jalswapna under command area of MATHACHULKA (GOBRABUSTY,UPORDHARA areas) pipe water supply scheme at Matiali Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000116/2022-2023 | 93/JSSD | 22/07/2022 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 3.61 | 3.32 | 0
1560 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of valve and valve Chamber at different location under command area of MATHACHULKA pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000119/2022-2023 | 96/JSSD | 22/07/2022 | 30 | DEEP CONSTRUCTION | 1.97 | 1.93 | 0
1561 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection(FHTC) in connection with Jaldhara/Jal Swapna under Command area of Mathachulka Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,PHE Dte(Phase-I) |  | Junior Engineer | ORD/000234/2021-2022 | 510/JSSD | 03/11/2021 | 15 | DEEP CONSTRUCTION | 4.65 | 0 | 0
1562 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA (Gobra Busty & Salbari Part) at Mathachulka pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000247/2022-2023 | 163/JSSD | 24/08/2022 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.78 | 4.28 | 0
1563 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000340/2020-2021 | 453JSSD | 30/12/2020 | 15 | DEEP CONSTRUCTION | 4.6 | 0 | 0
1564 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000342/2020-2021 | 570/JSSD | 01/02/2021 | 15 | ARUP SARKAR | 4.39 | 0 | 0
1565 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of MATHACHULKA T.G Area piped Water Supply Scheme at Matially Block under Jalpaiguri Division, PHE Dte. (Phase-IV) |  | Junior Engineer | ORD/000426/2020-2021 | 654/JSSD | 25/02/2021 | 15 | DEEP CONSTRUCTION | 4.69 | 0 | 0
1566 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka ( Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase - VIII) |  | Junior Engineer | ORD/000890/2021-2022 | 1029/W/JSSD | 31/01/2022 | 15 | SUBIR GHOSH | 4.82 | 4.82 | 0
1567 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka (Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase-VIII) |  | Junior Engineer | ORD/001075/2021-2022 | .1029/W/JSSD | 31/01/2022 | 15 | SUBIR GHOSH | 4.82 | 0 | 0
1568 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) | Assistant Engineer,HQ | Junior Engineer | ORD/000002/2022-2023 | 882/JD | 05/04/2022 | 60 | M/S NANDY ENTERPRISE | 182.16 | 69.91 | 0
1569 | Jalpaiguri Division | Jalpaiguri Division | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri | Assistant Engineer,HQ | Junior Engineer | ORD/000200/2019-2020 | 302/JD | 17/03/2020 | 120 | BILTU DAS | 47.59 | 15.74 | 0
1570 | Jalpaiguri Division | Jalpaiguri Division | Partial Retrofitting work for Riabari T.G.Area with repairing of rising main, including damaged/Chokage line repairing due to local developmnet works, direct Pumping arrangement from 2nd pump within the command area of Riabari T.G. P.W.S.S. under Jalsapna programme at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000203/2022-2023 | 1742/JD | 08/09/2022 | 21 | SAPTASWA SARKAR | 15.65 | 15.81 | 1
1571 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000338/2021-2022 | 193/JD | 21/01/2022 | 60 | BOSE ENTERPRISE | 172.88 | 62.22 | 1
1572 | Jalpaiguri Division | Jalpaiguri Division | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000377/2021-2022 | 350/JD | 03/02/2022 | 120 | NARENDRA KUMAR | 57.75 | 8.61 | 100
1573 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000008/2021-2022 | 180/JD | 21/01/2022 | 0 | Resource Division | 2.99 | 0 | 0
1574 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000075/2024-2025 | 2206/JD | 01/12/2024 | 0 | Resource Division | 26.77 | 0 | 0
1575 | Jalpaiguri Division | Jalpaiguri Division | FHTC GRASSMORE T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001330/2021-2022 | BP-2021-22-469 | 28/03/2022 | 0 | SWAPAN SAHA | 9.59 | 0 | 0
1576 | Jalpaiguri Division | Jalpaiguri Division | FHTC MALLICKSOVA PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001353/2021-2022 | BP-2021-22-466 | 27/03/2022 | 0 | BOSE ENTERPRISE | 65.35 | 0 | 0
1577 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250mm x 150mm dia Two nos tube well by Reverse Rotary method of drilling for Augmentation at 3rd & 4th Tube well site of Kajaldighi PWSS within Maynaguri Block under PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000004/2023-2024 | 850/JD | 06/04/2023 | 45 | M/S S. G. ENTERPRISE | 16.86 | 15.78 | 100
1578 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline at Kajaldighi Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000097/2025-2026 | 476/RWS | 29/05/2025 | 30 | M/S TRINATH CONSTRUCTION AND CO. | 4.03 | 0 | 0
1579 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of approach Road for 3rd & 4th site for Kajaldighi Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000098/2025-2026 | 477/RWS | 29/05/2025 | 30 | M/S S. G. ENTERPRISE | 0.5 | 0 | 0
1580 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000145/2022-2023 | 1562/JD | 08/08/2022 | 936 | DEBASISH DEY | 13.78 | 10.4 | 80
1581 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000199/2022-2023 | 1740/JD | 08/09/2022 | 997 | SAHA CONSTRUCTION | 14.44 | 10.87 | 100
1582 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000481/2021-2022 | 2214/JD | 27/12/2021 | 60 | SUBIR GHOSH | 11.45 | 11.44 | 100
1583 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000482/2021-2022 | 2215/JD | 27/12/2021 | 60 | M/S TRINATH CONSTRUCTION AND CO. | 11.44 | 11.43 | 100
1584 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000007/2022-2023 | 878/JD | 05/04/2022 | 1368 | M/S R.N. TRADERS | 282.14 | 193.85 | 1
1585 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of dedicated pipeline along with commissioning of Augmentation of Angrabhasa Piped W/S Scheme in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000079/2025-2026 | 99/JSSD | 30/05/2025 | 30 | RAGHU DAS | 12.42 | 0 | 0
1586 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Angrabhasa Piped Water Supply Scheme Block- Dhupguri, District - Jalpaiguri. |  | Junior Engineer | ORD/000137/2022-2023 | 1554/JD | 05/08/2022 | 1336 | SWAPAN SAHA | 54.69 | 31.22 | 100
1587 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 3rd tubewell Site for Augmentation of Angrabhasa PWSS, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000192/2022-2023 | .99/JSSD | 22/07/2022 | 864 | CHANDAN GHOSH | 4.78 | 0 | 100
1588 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Augmenmtation of Angrabhasa piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000479/2022-2023 | 798/JD.. | 29/03/2023 | 14 | M/S ROY & SARKAR CONSTRUCTION | 6.39 | 2.72 | 70
1589 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 250 mm x 200 mm x 147 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for the Augmentation of Angrabhasa piped water supply scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000785/2021-2022 | 840/JD | 31/03/2022 | 21 | MALAY BHOWMIK | 8.83 | 5.52 | 100
1590 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil investigation work for 200 Cum over head Reservoir (OHR)for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. |  | Junior Engineer | ORD/000834/2021-2022 | 1183/W/JSSD | 08/03/2022 | 20 | G MITRA & ASSOCIATES | 2 | 1.99 | 0
1591 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division. |  | Junior Engineer | ORD/001000/2021-2022 | 1242/JSSD | 25/03/2022 | 45 | SURAJIT KUNDU | 4.65 | 0 | 0
1592 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001006/2021-2022 | 1262/JSSD | 25/03/2022 | 20 | SURAJIT KUNDU | 4.8 | 0 | 0
1593 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Replacing Old Damaged Pipeline With Laying New UPVC Pipeline Due To Construction of Rural Road at Angravasa Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001032/2021-2022 | 56 /JSSD | 12/05/2021 | 30 | ROY & SARKAR CONSTRUCTION | 3.76 | 1.17 | 1
1594 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Work order for the work of Annual Maintenance of pipe line and other misc. work related to pipe line including maintenance of I.E.Plant (if any)for Angravasa T.G. PWSS under Jalpaiguri Division, P.H.E Dte. period from 15/07/2021 to 31/12/2021. |  | Junior Engineer | ORD/001037/2021-2022 | 162 /JSSD | 15/07/2021 | 170 | ROY & SARKAR CONSTRUCTION | 2.23 | 0 | 1
1595 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000016/2021-2022 | 555/JD | 01/03/2022 | 0 | Resource Division | 52.27 | 0 | 0
1596 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Tow Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Jiti Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000067/2022-2023 | 1222/JD | 31/05/2022 | 30 | M/S BABUN BISWAS | 13.84 | 0 | 0
1597 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of JITI pipe water supply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000106/2022-2023 | 82/JSSD | 22/07/2022 | 20 | ARUP SARKAR | 4.85 | 4.71 | 100
1598 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works and installation of valerelated to Functional Household Tap Connection(FHTC)inconnection with JJM/Jalswapna under command area of Jiti pipe watersupply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000117/2022-2023 | 94/JSSD | 22/07/2022 | 30 | ARUP SARKAR | 3.25 | 1.98 | 100
1599 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big dia Tube Well by Modified DTH-ODEX method at 3rd & 4th tube well site in connection with Jal Jeevan Mission of JITI Tea Garden piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000299/2023-2024 | 1356/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 32.57 | 24.77 | 100
1600 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of 2 nos of Pump House (1st site & 2nd site ), 2Nos boundary wall (1st site & 2nd site) and other Allied works at Jiti TG Piped Water Supply Scheme under Jalpaiguri Division .P.H.E. Dte. |  | Junior Engineer | ORD/000308/2022-2023 | 90/JSSD | 22/07/2022 | 15 | SOUVIK SAHA | 4.7 | 3.61 | 0
1601 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Rejuvenation of Jiti Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000482/2022-2023 | 801/JD.. | 29/03/2023 | 914 | KSMC CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION | 2.48 | 0 | 100
1602 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M x 2.40 M) size with sanitary & Plumbing arrangement at 3rd Tube well site for Jiti T.G. PWSS under Jalpaiguri Division, |  | Junior Engineer | ORD/000597/2021-2022 | 1055/JSSD | 24/01/2022 | 45 | ADWIJA CONSTRUCTION | 4.64 | 4.64 | 100
1603 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate drain and pathway for 3rd tube well site of Jiti T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000707/2021-2022 | 1044/JSSD | 24/01/2022 | 20 | ADWIJA CONSTRUCTION | 3.76 | 3.82 | 100
1604 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000104/2023-2024 | 1374/JD | 27/09/2023 | 0 | Resource Division | 9.21 | 0 | 0
1605 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | lds jabarmali pwss |  | Junior Engineer | VCH/000542/2022-2023 | BP-2021-22-170 | 29/09/2022 | 0 | BOSE ENTERPRISE | 2.43 | 0 | 0
1606 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORKS BHANGARHAT PWSS |  | Junior Engineer | VCH/001289/2021-2022 | BP-2021-22-500 | 29/03/2022 | 0 | MRINMOY KANTI DUTTA | 1.55 | 0 | 0
1607 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SINKING 250MX150 MM DIA PURBASALBARI PWSS |  | Junior Engineer | VCH/001307/2021-2022 | BP-2021-22- 470 | 28/03/2022 | 0 | ABHIJIT SARKAR | 7.92 | 0 | 0
1608 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  | Junior Engineer | BILL/00357/2022-2023 | BP-2023-24-110 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 4.99 | 0 | 0
1609 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with Sanitary & Plumbing arrangement at Head works site for Augmentation of Luksan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000039/2022-2023 | 1080/JD | 29/04/2022 | 60 | MONOTOSH ROY | 5.61 | 5.61 | 1
1610 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Redevelopment of Boundary Wall with gate, drain and pathway for Existing tubewell (2nd site as per new drawing) site for Augmentation of Luksan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000058/2024-2025 | 959/JD | 09/08/2024 | 602 | ALICK DUTTA | 22.33 | 3.46 | 75
1611 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at Head Work (OHR) site of Augmentation of Luksan Bazar (Zone-II) i.c.w. Jal Jeevan Mission at block Nagrakata in Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000059/2024-2025 | 960/JD | 09/08/2024 | 601 | ALICK DUTTA | 12.36 | 0 | 0
1612 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 2nd tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000065/2022-2023 | 1218/JD | 26/05/2022 | 21 | J.M. CONSTRUCTION | 7.16 | 5.53 | 1
1613 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000066/2022-2023 | 1232/JD | 02/06/2022 | 21 | J.M. CONSTRUCTION | 7.16 | 4.67 | 1
1614 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Land development works at the Zone-II H/W Site along with pump connection and other allied works at Augmentation of Luksan Bazar Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000142/2024-2025 | 257/JSSD | 25/09/2024 | 464 | ARUP SARKAR | 2.61 | 0 | 0
1615 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | -Interconnection work including FHTC with allied works at Augmentation of Looksan Bazar Piped W/S Scheme ( zone-I & III) in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000148/2024-2025 | 267/JSSD | 25/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 2.25 | 0 | 0
1616 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Laying Rising Main for Augmentation of Luksan Bazar (Zone -I ,Zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000150/2024-2025 | 263/JSSD | 25/09/2024 | 99 | MONTOSH GHOSH | 2.78 | 1.5 | 100
1617 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big Dia 2nd Tube well by Modified DTH - ODEX Method at 1st tube well site of Augmentation of Luksan Bazar Piped Water Supply Scheme of (zone-I) of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000441/2024-2025 | 2319/JD | 11/12/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 100
1618 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Augmenmtation of Luksan Bazar (Zone -I ,zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000478/2022-2023 | 797/JD.. | 29/03/2023 | 599 | MONTOSH GHOSH | 7.71 | 7.5 | 100
1619 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repair of damage pipe line and FHTC at Lukshan Bazar (Zone-III) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000547/2023-2024 | 498/JSSD | 02/01/2024 | 30 | ALICK DUTTA | 4.81 | 2.61 | 100
1620 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work for construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement at 2nd T/W site for Augmentation of Lukshan Bazar (Zone - II) Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000554/2023-2024 | 505/JSSD | 02/01/2024 | 335 | ARUP SARKAR | 2.75 | 2.75 | 100
1621 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000570/2021-2022 | 548/JD | 28/02/2022 | 1312 | GAP ENGINEERS ENTERPRISES | 79.03 | 18.53 | 75
1622 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000581/2021-2022 | 547/JD | 28/02/2022 | 30 | ALICK DUTTA | 21.58 | 4.67 | 15
1623 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Lukshan Bazar Piped Water Supply Scheme at Zone-II Block- Nagrakata, District - Jalpaiguri. |  | Junior Engineer | ORD/000587/2021-2022 | 735/JD | 17/03/2022 | 180 | SCEC BOENTER KDAS JOINT VENTURE | 55.08 | 22.21 | 100
1624 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000704/2021-2022 | 817/JD | 30/03/2022 | 21 | PINAKI MITRA | 7.15 | 6.25 | 1
1625 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- I) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000705/2021-2022 | 818/JD | 30/03/2022 | 21 | PINAKI MITRA | 7.15 | 7.01 | 1
1626 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-1) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000827/2021-2022 | 1184/W/JSSD | 08/03/2022 | 20 | MABCO CONSULTANT | 2.02 | 0.85 | 0
1627 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-11) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000833/2021-2022 | 1182/W/JSSD | 08/03/2022 | 20 | M K KAYAL & ASSOCIATES | 2.02 | 2 | 0
1628 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m ) size with sanitary & plumbing arrangement at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme for under Jalpaiguri Division. |  | Junior Engineer | ORD/001002/2021-2022 | 1243/JSSD | 25/03/2022 | 45 | KABYA ENTERPRISE | 4.64 | 4.64 | 100
1629 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at Lukshan Bazar (Zone-III) for Augmentation of Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001003/2021-2022 | 1244/JSSD | 25/03/2022 | 45 | SURAJIT KUNDU | 4.65 | 4.65 | 100
1630 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size including sanitary & plumbing works at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-II) Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001004/2021-2022 | 1245/JSSD | 25/03/2022 | 45 | DEBABRATA SARKAR | 4.65 | 0 | 100
1631 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Lukshan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/001005/2021-2022 | 1261/JSSD | 25/03/2022 | 20 | SURAJIT KUNDU | 4.79 | 3.37 | 100
1632 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 1st tube-well site for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/001007/2021-2022 | 1263/JSSD | 25/03/2022 | 20 | JAYA SARKAR | 4.79 | 4.24 | 100
1633 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Uttar Khuttimari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000129/2023-2024 | 405/JD | 06/06/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 280.55 | 163.06 | 45
1634 | Jalpaiguri Division | Jalpaiguri Division | Providing Balance Functional Household Tap Connection (FHTC) in the command area of Uttar Kuttimari PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000605/2024-2025 | 485/JD | 11/03/2025 | 25 | KABYA ENTERPRISE | 12.58 | 0 | 0
1635 | Jalpaiguri Division | Jalpaiguri Division | Supply and Delivery at site of UPVC pipe of 250mm dia for tube well of Uttar Khuttimari PWSS under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000736/2023-2024 | 2456/JD | 23/02/2024 | 7 | UNIBRO INFRASERV PRIVATE LIMITED | 2.46 | 0 | 0
1636 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000020/2023-2024 | 164/JD | 28/04/2023 | 0 | Resource Division | 13.57 | 0 | 0
1637 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000132/2023-2024 | 1881/JD | 20/12/2023 | 0 | Resource Division | 6.62 | 0 | 0
1638 | Jalpaiguri Division | Jalpaiguri Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1639 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Gairkhata Tea Garden (D) PWSS i.e. T.W. Pump House, Water Distribution Network, OHR, Rising Main,FHTC etc. In connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000440/2022-2023 | 677/JD | 16/03/2023 | 455 | SUKES BASU MAJUMDAR | 448.24 | 432.96 | 100
1640 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Rising Main, Laying Distribution System at 3rd Tube Well Site and Providing Functional Household Tap Connection of Sajnapara around Gairkata Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000680/2024-2025 | 459/JD | 11/03/2025 | 143 | ALOKE DEY | 56.41 | 0 | 20
1641 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000003/2023-2024 | 147/JD | 28/04/2023 | 0 | Resource Division | 32.33 | 0 | 0
1642 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000117/2023-2024 | 1828/JD | 15/12/2023 | 0 | Resource Division | 14.29 | 0 | 0
1643 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1644 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Gendrapara Tea Garden Piped Water Supply Scheme Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000528/2024-2025 | 125/JD | 16/01/2025 | 50 | SANJIT SAHA | 56.46 | 0 | 0
1645 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000060/2023-2024 | 1093/JD | 24/08/2023 | 0 | Resource Division | 27.95 | 0 | 0
1646 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000118/2023-2024 | 1829/JD | 15/12/2023 | 0 | Resource Division | 14.72 | 0 | 0
1647 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different components of Upper Tandu Forest (M) i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Nagrakata under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000444/2022-2023 | 676/JD | 16/03/2023 | 180 | NISHITH RANJAN KARMAKAR | 96 | 76.78 | 100
1648 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000016/2023-2024 | 160/JD | 28/04/2023 | 0 | Resource Division | 2.08 | 0 | 0
1649 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000171/2023-2024 | 2057/JD | 09/01/2024 | 0 | Resource Division | 2.22 | 0 | 0
1650 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation Of Grassmore Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000126/2023-2024 | 413/A/JD | 07/06/2023 | 60 | JAYDEB SAHA | 30.89 | 23.73 | 90
1651 | Jalpaiguri Division | Jalpaiguri Division | Direct boosting arrangement from 2 nd Pump to the Nandu more to Ghasmari Road area due to low tail end pressure along with leftout distribution system and FHTC at Grassmore T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000135/2023-2024 | 794/JD | 24/07/2023 | 617 | SUNIL ROY | 11.3 | 0 | 100
1652 | Jalpaiguri Division | Jalpaiguri Division | Construction of Hume Pipe Culvert along with approach way development at 2 nd Pump House Site of Grassmore T.G. Piped water supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2022-2023 | 1434/JD | 18/07/2022 | 15 | DEEP CONSTRUCTION | 1.18 | 1.17 | 1
1653 | Jalpaiguri Division | Jalpaiguri Division | Remaining part of Laying Distribution System (PART-C ) for Grassmore T.G. AREA P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000181/2020-2021 | 1266/JD | 18/11/2020 | 60 | ASHIT KUMAR SINGHA | 61.96 | 0 | 1
1654 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1655 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Patkata Zone- III Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000055/2024-2025 | 957/JD | 09/08/2024 | 601 | JAYA SARKAR | 49.34 | 0 | 80
1656 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Patkata Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc In connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000069/2023-2024 | 398/A/JD | 06/06/2023 | 1037 | GARGO TRADERS | 434.09 | 191.65 | 70
1657 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site of PATKATA ZONE - III PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000110/2025-2026 | 488/RWS | 29/05/2025 | 30 | PARESH CHANDRA GHOSH ROY | 5.49 | 0 | 0
1658 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-III PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000530/2024-2025 | 117/JD | 16/01/2025 | 440 | PRADIP KUMAR SEN | 26.83 | 0 | 90
1659 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000110/2023-2024 | 1369/JD | 27/09/2023 | 0 | Resource Division | 23.28 | 0 | 0
1660 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000136/2023-2024 | 1883/JD | 20/12/2023 | 0 | Resource Division | 15.62 | 0 | 0
1661 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling for Karbala Tea Garden Pipe Water Supply Scheme in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000297/2023-2024 | 1355/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.38 | 15.96 | 100
1662 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000057/2023-2024 | 1095/JD | 24/08/2023 | 0 | Resource Division | 12.32 | 0 | 0
1663 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of Pipe line in uncovered area including installation of Sluice Valves at different strategic point within the command area of Mogolkata T.G. P.W.S.S. at Dhupguri Block under Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000191/2022-2023 | 1694/JD | 06/09/2022 | 21 | DIPAK KUMAR CHAKRABORTY | 4.1 | 4.11 | 1
1664 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC including retrofitting works near Totapara Bazar for Mogalkata Piped Water Supply Scheme at Banarhat Block in under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000539/2023-2024 | 1971/JD | 03/01/2024 | 20 | JITENDRA NATH ROY | 12.57 | 9.73 | 100
1665 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000051/2023-2024 | 1099/JD | 24/08/2023 | 0 | Resource Division | 2.59 | 0 | 0
1666 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 250 cum capacity 20 m staging height OHR, tube well, pump house 3.60x2.40m with sanitary arrangement, boundary wall, Laying distribution system, Rising Main for BARADIGHI T.G. under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000042/2020-2021 | 1060/JD | 13/10/2020 | 120 | BOSE ENTERPRISE | 126.27 | 0 | 1
1667 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Baradighi Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000110/2023-2024 | 404/A/JD | 06/06/2023 | 1030 | ALICK DUTTA | 32.52 | 10.25 | 25
1668 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (150 nos) in connection with JJM near Dipu line, Mangla line, Bhouka line and allied areas for Barodighi T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000351/2022-2023 | 613/JD | 09/03/2023 | 15 | PRIYABRATA KARMAKAR | 7.12 | 7.05 | 1
1669 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jaldhara/Jalswapna near factory line and allied areas for Barodighi TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000387/2022-2023 | 362/JD | 20/02/2023 | 14 | PRIYABRATA KARMAKAR | 6.38 | 6.37 | 1
1670 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Conctruction of approach road with paver block inside the premises and outside approach, R.B.T fixing in boundary wall and inside drain at H/W site for Barodighi TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000406/2022-2023 | 612/JD | 09/03/2023 | 21 | BOSE ENTERPRISE | 13.4 | 13.34 | 100
1671 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000058/2023-2024 | 1089/JD | 24/08/2023 | 0 | Resource Division | 5.42 | 0 | 0
1672 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Manabari Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000267/2023-2024 | 937/JD | 08/08/2023 | 754 | TARAKESWAR PRASAD | 97.86 | 0 | 60
1673 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Approach Culvert with Guard Wall at H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000381/2022-2023 | 359/JD | 20/02/2023 | 21 | M/S A.B.G. CONSTRUCTION | 2.93 | 2.92 | 100
1674 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of G. I. line & concrete block & piller for culvert for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000483/2022-2023 | 802/JD | 29/03/2023 | 21 | M/S A.B.G. CONSTRUCTION | 3.02 | 2.98 | 100
1675 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Rejuvenation of Manabari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000593/2023-2024 | 2332/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 14.02 | 100
1676 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000089/2023-2024 | 1064/JD | 24/08/2023 | 0 | Resource Division | 19.68 | 0 | 0
1677 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1678 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Uttar Marichbari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000501/2022-2023 | 773/JD | 27/03/2023 | 710 | UNIBRO INFRASERV PRIVATE LIMITED | 182.48 | 93.19 | 80
1679 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site including rising main and interconnections of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000565/2023-2024 | 2174/JD | 22/01/2024 | 679 | SUBRATA GOSWAMI | 15.52 | 0 | 100
1680 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000673/2023-2024 | 166/RWS | 15/02/2024 | 30 | PINTU DAS | 6.14 | 6.11 | 100
1681 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000026/2023-2024 | 170/JD | 28/04/2023 | 0 | Resource Division | 15.65 | 0 | 0
1682 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000181/2023-2024 | 2046/JD | 09/01/2024 | 0 | Resource Division | 5.49 | 0 | 0
1683 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1684 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000028/2024-2025 | 740/JD | 26/07/2024 | 150 | M/S SIBU DEY AND CO. | 118.85 | 18.19 | 60
1685 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PATKATA ZONE -I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000105/2025-2026 | 483/RWS | 29/05/2025 | 30 | PINTU DAS | 7.76 | 0 | 0
1686 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Patkata Zone- I Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000441/2023-2024 | 1706/JD | 04/12/2023 | 637 | GARGO TRADERS | 546.65 | 109.05 | 60
1687 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including Iron Elemination Plant and interconnection work at 3rd site of Patkata Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000466/2025-2026 | 2497/JD | 09/12/2025 | 120 | KANAI LAL SEN | 21.13 | 0 | 0
1688 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000534/2024-2025 | 112/JD | 16/01/2025 | 440 | DINABANDHU ROY | 17.84 | 0 | 0
1689 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000109/2023-2024 | 1371/JD | 27/09/2023 | 0 | Resource Division | 48.31 | 0 | 0
1690 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000199/2023-2024 | 2076/JD | 10/01/2024 | 0 | Resource Division | 26.02 | 0 | 0
1691 | Jalpaiguri Division | Jalpaiguri Division | Construction of diferent components of Paschim Salbari Zone-II pwss i.e TW, Pump Houses, water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000058/2023-2024 | 264/JD | 10/05/2023 | 1057 | ANUP SARKAR | 213 | 163.63 | 35
1692 | Jalpaiguri Division | Jalpaiguri Division | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000284/2022-2023 | 649/RWS | 21/10/2022 | 20 | PARAMJYOTI ENTERPRISE | 4.32 | 0 | 1
1693 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Paschim Salbari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000457/2024-2025 | 2333./JD | 12/12/2024 | 475 | ANUP SARKAR | 18.22 | 0 | 100
1694 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000041/2023-2024 | 1113/JD | 24/08/2023 | 0 | Resource Division | 9.93 | 0 | 0
1695 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000134/2023-2024 | 1880/JD | 20/12/2023 | 0 | Resource Division | 4.77 | 0 | 0
1696 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rejuvenation work for Pump House & Additional Backwash line for Uttar Bhuskadanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000683/2023-2024 | 155/RWS | 15/02/2024 | 30 | MRINMOY KANTI DUTTA | 6.13 | 6.01 | 100
1697 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Additional pipeline to improve the water distribution network for Uttar Bhuskadanga Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000702/2024-2025 | 631/JD | 28/03/2025 | 218 | MRINMOY KANTI DUTTA | 23.85 | 0 | 0
1698 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000098/2023-2024 | 1055/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0
1699 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Bagrakote T.G. W/S/S under Jalpaiguri Division , P.H.E. Dte. |  | Junior Engineer | ORD/000293/2021-2022 | 825/RWS | 30/11/2021 | 1187 | BIMAN DAS | 4.65 | 0 | 100
1700 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Emergency water supply arrangement to the dengue effected area related to Bagrakote water supply Scheme for 45 days . ( from 29.06.2022 to 12.08.2022) |  | Junior Engineer | ORD/000299/2022-2023 | 437/RWS | 07/07/2022 | 45 | SWAPAN SAHA | 4.47 | 0 | 0
1701 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall, drain and pathway for 2nd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000349/2022-2023 | 134/JD | 17/01/2023 | 30 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.01 | 6.44 | 100
1702 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 3 Nos. Tubewell by ODEX-165 method for Bagrakote W/S Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000375/2023-2024 | 1516/JD | 16/10/2023 | 30 | RANJEET SINGH BENIWAL | 20.54 | 16.66 | 100
1703 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution system and functional household tap connection for Bagrakote Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. |  | Junior Engineer | ORD/000378/2021-2022 | 351/JD | 03/02/2022 | 1305 | M/S GARGO TRADERS | 184.25 | 48.31 | 60
1704 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK FOR BAGRAKOTE T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000398/2021-2022 | 852/RWS | 03/12/2021 | 15 | G. TECH INDIA | 2.03 | 1.63 | 1
1705 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000433/2023-2024 | 1674/JD | 24/11/2023 | 45 | KAPIL MANI BRAHMAN | 11.66 | 9.48 | 100
1706 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. .(H/W Site) .(4th Call) |  | Junior Engineer | ORD/000438/2023-2024 | 1275/RWS | 24/11/2023 | 14 | RANJEET SINGH BENIWAL | 1.37 | 0 | 100
1707 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(2nd Site) .(4th Call) |  | Junior Engineer | ORD/000439/2023-2024 | 1274/RWS | 24/11/2023 | 14 | RANJEET SINGH BENIWAL | 0.8 | 0 | 100
1708 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 400 CuM Capacity R.C.C. Over Head Reservoir (OHR) of 20 Mtr Staging Height at Bagrakote Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000590/2023-2024 | 2410/JD | 19/02/2024 | 180 | D.C RAKSHIT AND SONS INDIA PRIVATE LTD. | 106.62 | 0 | 0
1709 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000001/2021-2022 | 1940/JD | 02/12/2021 | 0 | Resource Division | 12.32 | 0 | 0
1710 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000028/2023-2024 | 172/JD | 28/04/2023 | 0 | Resource Division | 82.59 | 0 | 0
1711 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000208/2023-2024 | 2068/JD | 10/01/2024 | 0 | Resource Division | 14.15 | 0 | 0
1712 | Jalpaiguri Division | Jalpaiguri Division | Supply of Different stationary for office under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | BILL/00119/2024-2025 | BP-2024-25-84 | 17/05/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.85 | 0 | 0
1713 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No WB 71 B 8742 for the Month of July 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00594/2024-2025 | BP-2024-25-341 | 30/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
1714 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00658/2024-2025 | BP-2024-25-368 | 13/09/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
1715 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00857/2024-2025 | BP-2024-25-496 | 07/10/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
1716 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00986/2024-2025 | BP-2024-25-548 | 17/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0
1717 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00996/2024-2025 | BP-2024-25-552 | 17/12/2024 | 0 | FILL & SMILE | 0.09 | 0 | 0
1718 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00999/2024-2025 | BP-2024-25-550 | 17/12/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
1719 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/01000/2024-2025 | BP-2024-25-551 | 17/12/2024 | 0 | FILL & SMILE | 0.13 | 0 | 0
1720 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Executive Engineer, Jalpaiguri Division, P.H.E. Dte.(For the period from01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000030/2025-2026 | 817/JD | 30/04/2025 | 61 | BISWANATH GHOSH | 0.8 | 0 | 0
1721 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000031/2025-2026 | 818/JD | 30/04/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
1722 | Jalpaiguri Division | Jalpaiguri Division | Continuation for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.07.2024 to 13.01.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000072/2024-2025 | 649/JD | 11/07/2024 | 184 | RAKESH SARKAR | 0.88 | 0.97 | 0
1723 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/08/2024 to 09/02/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000077/2024-2025 | 963/JD | 09/08/2024 | 184 | RABINDRA NATH DUTTA | 0.88 | 0.79 | 0
1724 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Supply of 1 (One) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit) (w.e.f. 01.06.2025 to 30.11.2025)." | Assistant Engineer,HQ | Junior Engineer | ORD/000116/2025-2026 | 983/JD | 26/05/2025 | 184 | RUPA PRASAD | 0.88 | 0 | 0
1725 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000120/2025-2026 | 1496/JD | 30/06/2025 | 31 | BISWANATH GHOSH | 0.4 | 0 | 0
1726 | Jalpaiguri Division | Jalpaiguri Division | Thorough repair and overhauling of the IEP reparing Pump House and other ancillary work at Dabgram Central zone at Dabgram -II G.P. under Dabgram piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000146/2023-2024 | 795/JD | 24/07/2023 | 861 | NARENDRA KUMAR | 6.8 | 0 | 0
1727 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings works including Functional House Hold Tap connection under JJM for Dabgram Water Supply Scheme ( Central Zone ) under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000147/2023-2024 | 796/JD | 24/07/2023 | 21 | NARENDRA KUMAR | 36.22 | 27.87 | 100
1728 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000151/2025-2026 | 1732/JD | 31/07/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
1729 | Jalpaiguri Division | Jalpaiguri Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000199/2025-2026 | 1998/JD | 25/09/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
1730 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Dabgram PWSS (Central Zone) i.e. TW, Pump Houses, Water Distribution Network, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block, Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000248/2023-2024 | 936/JD | 08/08/2023 | 779 | MAA MANASA VYAPAAR | 708.57 | 69.05 | 43
1731 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Dabgram PWSS (North Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000395/2023-2024 | 1552/JD | 01/11/2023 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 414.28 | 0 | 0
1732 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Dabgram PWSS (South Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000446/2023-2024 | 1708/JD | 04/12/2023 | 759 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 526.38 | 138.18 | 45
1733 | Jalpaiguri Division | Jalpaiguri Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000472/2025-2026 | 2428/JD | 25/11/2025 | 30 | PRADIP SAHA | 0.4 | 0 | 0
1734 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2024 to 31.05.2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000516/2024-2025 | 2201/JD | 30/11/2024 | 182 | RUPA PRASAD | 0.88 | 1.77 | 0
1735 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.01.2025 to 28.02.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000553/2024-2025 | 04/HQ/JD | 13/01/2025 | 46 | RAKESH SARKAR | 0.23 | 0.23 | 0
1736 | Jalpaiguri Division | Jalpaiguri Division | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 100
1737 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 01.03.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000686/2024-2025 | 70/HQ/JD | 28/02/2025 | 31 | RAKESH SARKAR | 0.15 | 0.28 | 0
1738 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/02/2025 to 31/03/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000688/2024-2025 | 41/HQ/JD | 09/02/2025 | 50 | RABINDRA NATH DUTTA | 0.25 | 0 | 0
1739 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer,HQ | Junior Engineer | ORD/000695/2024-2025 | 212/JD | 29/01/2025 | 181 | SOUMEN GHOSH | 0.88 | 0.44 | 0
1740 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 01/04/2025 to 30/04/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000786/2024-2025 | 107-HQ/JD | 28/03/2025 | 31 | RABINDRA NATH DUTTA | 0.15 | 0 | 0
1741 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000047/2023-2024 | 1104/JD | 24/08/2023 | 0 | Resource Division | 184.96 | 0 | 0
1742 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000116/2023-2024 | 1827/JD | 14/12/2023 | 0 | Resource Division | 121.48 | 0 | 0
1743 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAKHATI T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte |  | Junior Engineer | ORD/000163/2020-2021 | 1118/JD | 02/11/2020 | 60 | R.S CONSTRUCTION | 38.19 | 20.56 | 0
1744 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fhtc nakhati |  | Junior Engineer | VCH/000351/2021-2022 |  | 05/10/2021 | 0 | R.S CONSTRUCTION | 10 | 0 | 0
1745 | Jalpaiguri Division |  | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works under Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) |  |  | ORD/000093/2022-2023 | 1292/JD | 14/06/2022 | 15 | ASIT PAUL | 1.69 | 1.72 | 0
1746 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  |  | ORD/000099/2021-2022 | 1338/JD | 23/08/2021 | 30 | ASIT PAUL | 30.22 | 44.3 | 1
1747 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Chauhaddi piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III |  |  | ORD/000105/2021-2022 | 1256/JD | 10/08/2021 | 15 | HARIPADA BANERJEE | 4.81 | 0 | 1
1748 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- IV) |  |  | ORD/000111/2021-2022 | 1405/JD | 03/09/2021 | 30 | RABINDRANATH DUTTA | 23.6 | 19.54 | 1
1749 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  |  | ORD/000311/2020-2021 | 289/JD | 23/02/2021 | 30 | HARIPADA BANERJEE | 24.4 | 0 | 1
1750 | Jalpaiguri Division |  | fhtc chauhaddi |  |  | VCH/000344/2021-2022 |  | 06/10/2021 | 0 | RABINDRANATH DUTTA | 9.77 | 0 | 0
1751 | Jalpaiguri Division |  | fhtc chauhaddi |  |  | VCH/000345/2021-2022 |  | 05/10/2021 | 0 | ASIT PAUL | 22.15 | 0 | 0
1752 | Jalpaiguri Division |  | HDPE UTTAR ANGRAVASA PWSS |  |  | VCH/001328/2021-2022 | BP-2021-22-461 | 27/03/2022 | 0 | ROY & SARKAR CONSTRUCTION | 4.89 | 0 | 0
1753 | Jalpaiguri Division |  | FHTC GORALBARI |  |  | VCH/001349/2021-2022 | BP-2021-22-454 | 27/03/2022 | 0 | SAPTASWA SARKAR | 2.69 | 0 | 0
1754 | Jalpaiguri Division |  | FHTC KAMARVITA VILLAGE RAJGANJ BLOCK |  |  | VCH/001382/2021-2022 | BP-2021-22-444 | 26/03/2022 | 0 | BARUN KUMAR DUTTA | 3.63 | 0 | 0
1755 | Jalpaiguri Division |  | FHTC GORALBARI ZONE - I |  |  | VCH/001419/2021-2022 | BP-2021-22-453 | 27/03/2022 | 0 | SAHA CONSTRUCTION | 3.49 | 0 | 0
1756 | Jalpaiguri Division |  | RETRO FITTING WOR FOR GORALBARI ZONE -I |  |  | VCH/001427/2021-2022 | BP-2021-22-455 | 27/03/2022 | 0 | SAPTASWA SARKAR | 3.67 | 0 | 0
1757 | Jalpaiguri Division | Northern Mechanical Division | fuel charges | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00253/2022-2023 | BP-2022-23-439 | 06/02/2023 | 0 | FILL & SMILE | 0.29 | 0 | 0
1758 | Jalpaiguri Division | Northern Mechanical Division | Rig approach for Installation of tube well at Ghasmari Piped water supply Scheme head works site & 2nd site under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000120/2022-2023 | 97/JSSD | 22/07/2022 | 30 | ALICK DUTTA | 1.22 | 1.22 | 0
1759 | Jalpaiguri Division | Northern Mechanical Division | Construction of 150 CUM Capacity R.C.C. Elevated Reservoir, 20 Mtrs staging Height including pump house (5.4x3.6) size, Boundary wall and Drain for GHASMARI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000127/2023-2024 | 708/JD | 13/07/2023 | 612 | M/S R.N. TRADERS | 76.58 | 20.58 | 85
1760 | Jalpaiguri Division | Northern Mechanical Division | Installation of R.B.T fixing in boundary wall and other allied works at 2nd site for Ghasmari TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000259/2022-2023 | 183/JSSD | 29/08/2022 | 30 | PRITAM DUTTA | 1.78 | 1.77 | 100
1761 | Jalpaiguri Division | Northern Mechanical Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000303/2022-2023 | 2192/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.97 | 2.97 | 0
1762 | Jalpaiguri Division | Northern Mechanical Division | Laying distribution system with Rising Main Connection and Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Ghasmari Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000346/2021-2022 | 208/JD | 24/01/2022 | 1123 | M/S R.N. TRADERS | 118.35 | 20.51 | 100
1763 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary wall with gate drain and pathway for 2nd tube well site of Ghasmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000644/2021-2022 | 1061/JSSD | 24/01/2022 | 20 | PRITAM DUTTA | 3.76 | 3.78 | 0
1764 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60m x 2.40m) size with sanitary and plumbing arrangement at 2nd Tube well site for Ghasmari PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000726/2021-2022 | 1071/JSSD | 25/01/2022 | 45 | ARUP SARKAR | 4.65 | 4.65 | 0
1765 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000029/2023-2024 | 173/JD | 28/04/2023 | 0 | Resource Division | 17.75 | 0 | 0
1766 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000205/2023-2024 | 2064/JD | 10/01/2024 | 0 | Resource Division | 4.8 | 0 | 0
1767 | Jalpaiguri Division | Northern Mechanical Division | Maintainance of Jalpaiguri division office including RWS/ Sadar Sub-Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000557/2022-2023 | BP-2022-23-180 | 15/09/2022 | 0 | SUKUMAR KUNDU | 1.64 | 0 | 0
1768 | Jalpaiguri Division | Northern Mechanical Division | supply of fuel | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000593/2022-2023 | BP-2022-23-261 | 17/11/2022 | 0 | FILL & SMILE | 1.26 | 0 | 0
1769 | Jalpaiguri Division | Northern Mechanical Division | supply of fuel | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000594/2022-2023 | BP-2022-23-262 | 17/11/2022 | 0 | FILL & SMILE | 0.98 | 0 | 0
1770 | Jalpaiguri Division | Northern Mechanical Division | HIRE CHARGES | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000622/2022-2023 | BP-2022-23-348 | 09/12/2022 | 0 | APIKUL ALI | 0.29 | 0 | 0
1771 | Jalpaiguri Division | Northern Mechanical Division | CONST OF OHR FOR UTTAR DANGAPRA DAKSHIN SAKOAJHORA PWSS | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/001260/2021-2022 | BP-2021-22-403 | 23/03/2022 | 0 | PARESH CHANDRA GUHA | 25.96 | 0 | 0
1772 | Jalpaiguri Division | Northern Mechanical Division | CONST 250 MM CAPACITY UTTAR DANGA PARA & DAKSHIN SAKOJHORA | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/001309/2021-2022 | BP-2021-22-403 | 23/03/2022 | 0 | PARESH CHANDRA GUHA | 25.96 | 0 | 0
1773 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 3rd Tubewell site of Madhya Khuttimari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000061/2023-2024 | 325/JD | 18/05/2023 | 14 | CHOWDHURY CONSTRUCTION | 4.63 | 3.34 | 10
1774 | Jalpaiguri Division | Jalpaiguri Division | Laying of higher dia. pipeline within the Command Area of Madhya Khuttimary and adjoining mouzas Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000237/2025-2026 | 2163/JD | 30/10/2025 | 75 | BILTU DAS | 152.02 | 0 | 0
1775 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Madhya Khattimari PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000449/2021-2022 | 197/JD | 21/01/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 7.1 | 1
1776 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Madhya Khattiamri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000501/2021-2022 | 96/JD | 10/01/2022 | 60 | ALICK DUTTA | 4.65 | 4.75 | 0
1777 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with Rejuvination of Chauhaddi PWSS for FHTC work of Jal Swapna at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000015/2022-2023 | 971/JD | 20/04/2022 | 90 | SCEC BOENTER KDAS JOINT VENTURE | 168.05 | 127.33 | 1
1778 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pathway inside the Head Works Site of Chauhaddi and adjoining mouzas .P.W.S.S. under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000161/2022-2023 | 1468/JD | 25/07/2022 | 21 | HARIPADA BANERJEE | 3.53 | 3.53 | 100
1779 | Jalpaiguri Division | Jalpaiguri Division | Repairing of choakaged and damaged branch lines due to road development and widening of near by area of Garialtari within the command area of Chauhaddi and adjoining mouzas Piped Water Supply Scheme under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000163/2022-2023 | 1435/JD | 18/07/2022 | 21 | HARIPADA BANERJEE | 4.84 | 4.84 | 0
1780 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | Assistant Engineer,HQ | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0.34 | 0
1781 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (Phase - VI) in connection with Jal Jeevan Mission for Rejuvenation of Chouhaddi and adjoining Mouzas P.W.S.S under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000431/2022-2023 | 626/JD | 13/03/2023 | 30 | SOMNATH ROY | 17.57 | 0 | 0
1782 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 1 No. 250mm x 150mm x 135 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000476/2021-2022 | 348/JD | 03/02/2022 | 30 | J.M. CONSTRUCTION | 7.85 | 0 | 1
1783 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chauhaddi P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000507/2021-2022 | 106/JD | 11/01/2022 | 60 | J.M. CONSTRUCTION | 4.65 | 4.78 | 1
1784 | Jalpaiguri Division | Jalpaiguri Division | Repairing of damaged line near Harinkhwa School with other ancillary repairing work related to the Laying Distribution System at Chauhaddi P.W.S.S. under Jalpaiguri Division, | Assistant Engineer,HQ | Junior Engineer | ORD/000580/2021-2022 | 166/JD | 20/01/2022 | 21 | HARIPADA BANERJEE | 3.68 | 3.63 | 1
1785 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 | Assistant Engineer,HQ | Junior Engineer | ORD/000597/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.45 | 0.39 | 0
1786 | Jalpaiguri Division | Jalpaiguri Division | FUEL BILL | Assistant Engineer,HQ | Junior Engineer | VCH/000281/2022-2023 | BP-2022-23-137 | 25/08/2022 | 0 | FILL & SMILE | 0.74 | 0 | 0
1787 | Jalpaiguri Division | Jalpaiguri Division | BOUNDARY WALL 2ND T/WELL SITE RED BANK T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001308/2021-2022 | BP-2021-22- 459 | 27/03/2022 | 0 | DEEP CONSTRUCTION | 3.58 | 0 | 0
1788 | Jalpaiguri Division | Northern Mechanical Division | Laying Rising Main at 3rd Tube Well site of Khalaigram PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000023/2023-2024 | 123/JD | 28/04/2023 | 14 | PRIYABRATA KARMAKAR | 8.33 | 6.11 | 80
1789 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Khalaigram P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000222/2022-2023 | 1851/JD | 16/09/2022 | 45 | MANAB BAKSHI | 4.65 | 4.72 | 0
1790 | Jalpaiguri Division | Northern Mechanical Division | Sinking of 250 mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Khalaigram PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000451/2021-2022 | 199/JD | 21/01/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 7.05 | 1
1791 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PAYMENT FOR FUEL BILL |  | Junior Engineer | BILL/00360/2023-2024 | BP-2023-24-315 | 18/08/2023 | 0 | FILL & SMILE | 3.34 | 0 | 0
1792 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection for Jaldhara/Jal Sapna under the command area of Jabramali piped Water Supply Scheme at MATIALI Block under Jalpaiguri Division, PHE Dte. (Part-E) |  | Junior Engineer | ORD/000186/2022-2023 | 565/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 2.65 | 2.58 | 0
1793 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall Path way, block drain for 2 nd site of kumlai T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Die. |  | Junior Engineer | ORD/000282/2022-2023 | 647/RWS | 21/10/2022 | 20 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.83 | 4.83 | 1
1794 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  | Junior Engineer | ORD/000304/2022-2023 | 2193/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.42 | 3.42 | 0
1795 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Model estimate for construction of pump house ( 3.60 m X 2.40 m) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Kumlai T.G . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000324/2021-2022 | 875/RWS | 08/12/2021 | 30 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.65 | 4.65 | 1
1796 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) |  | Junior Engineer | ORD/000325/2021-2022 | 879/RWS | 10/12/2021 | 10 | M/S DEY & ROY CHOUDHURY | 1.28 | 0.13 | 1
1797 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising main connection for Kumlai TG PWSS including supply of Sluice valve/ Jeffy coupling ,C.I.D.F. Specials etc. under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000334/2022-2023 | 27/JD | 05/01/2023 | 21 | ADITRI ENTERPRISE | 4.81 | 3.6 | 100
1798 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution system and functional household tap connection for Kumlai Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. |  | Junior Engineer | ORD/000340/2021-2022 | 192/JD | 21/01/2022 | 60 | R.S CONSTRUCTION | 116.87 | 92.64 | 70
1799 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 150 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing RCC including pipe connection and cost of pipes, specials, Construction of Pump House (5.4m x 3.60 m) & Boundary wall at H/W site Kumlai Tea Garden Area Piped Water Supply Scheme, Block- Mal, Dist. Jalpaiguri. Under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000354/2021-2022 | 252/JD | 31/01/2022 | 150 | SANDIP BANIK | 64.43 | 64.71 | 1
1800 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK FOR KUMLAI T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000401/2021-2022 | 853/RWS | 03/12/2021 | 15 | G. TECH INDIA | 2.03 | 0 | 0
1801 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000030/2023-2024 | 174/JD | 28/04/2023 | 0 | Resource Division | 21.11 | 0 | 0
1802 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000207/2023-2024 | 2066/JD | 10/01/2024 | 0 | Resource Division | 6.1 | 0 | 0
1803 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RENOVATION B/W H/W SOUTH BERUBARI WSS |  | Junior Engineer | VCH/001377/2021-2022 | BP-2021-22-540 | 31/03/2022 | 0 | A.P CONSTRUCTION | 19.8 | 0 | 0
1804 | Jalpaiguri Division | Jalpaiguri Division | SUPPLY OF FUEL | Assistant Engineer,HQ | Junior Engineer | BILL/00398/2022-2023 | BP-2022-23-522 | 15/03/2023 | 0 | FILL & SMILE | 0.33 | 0 | 0
1805 | Jalpaiguri Division | Jalpaiguri Division | SUPPLY OF FUEL (DIESEL) FOR VEHICLES UNDER JALPAIGURI DIVISION PHE DTE. FOR THE MONTH OF DECEMBER 2023 AND JANUARY 2024 | Assistant Engineer,HQ | Junior Engineer | BILL/01247/2023-2024 | BP-2023-24-665 | 22/02/2024 | 0 | FILL & SMILE | 1.9 | 0 | 0
1806 | Jalpaiguri Division | Jalpaiguri Division | Supply of Sluice valve C.I. Specials at Binnaguri for laying of DI line from OHR to UPVC Pipe line in connection with Augmentation of Binnaguri W/S Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000036/2023-2024 | 389/RWS | 25/04/2023 | 14 | B.M CONSTRUCTION | 3.31 | 3.31 | 0
1807 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall with gate, drain for 3rd Tube well site of Binnaguri Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000101/2023-2024 | 444/JD. | 08/06/2023 | 21 | ETHERIA EDIFICE (OPC) PVT. LTD. | 5.29 | 0 | 0
1808 | Jalpaiguri Division | Jalpaiguri Division | Extra Laying of Water Distribution System, construction of valve chamber and other ancillary works for Augmentation of Binnaguri PWSS at Binnaguri at Block - Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000136/2023-2024 | 706/JD | 13/07/2023 | 21 | M/S KARMAKAR CONSTRUCTION | 29.75 | 25.32 | 80
1809 | Jalpaiguri Division | Jalpaiguri Division | Repairing of OHR and repairing valve chamber & other ancillary works Binnaguri Head Work site under Binnaguri Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000316/2023-2024 | 1228/JD | 11/09/2023 | 21 | KANAI LAL SEN | 6.87 | 6.54 | 100
1810 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant (Capacity 20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd Tubewell site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT - JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/000348/2022-2023 | 136/JD | 17/01/2023 | 45 | SUBIR GHOSH | 14.72 | 11.2 | 0
1811 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) with sanitary & plumbing arrangement at 3rd Tube well site for Binnaguri (Fulbari) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000350/2022-2023 | 133/JD | 17/01/2023 | 45 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 4.65 | 100
1812 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant (capacity-50m3/hr.) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000353/2022-2023 | 165/JD | 19/01/2023 | 45 | KANAI LAL SEN | 19.8 | 19.46 | 100
1813 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Binnaguri Piped water Supply Scheme at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000453/2021-2022 | 332/JD | 02/02/2022 | 120 | M/S NANDY ENTERPRISE | 458.51 | 274.45 | 1
1814 | Jalpaiguri Division | Jalpaiguri Division | Laying of Water Distribution System and other ancillary works for Augmentation of Binnaguri PWSS at Block-Rajganj under Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000482/2024-2025 | 2408./JD | 20/12/2024 | 224 | M/S KARMAKAR CONSTRUCTION | 40.9 | 0 | 100
1815 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission under the command area of Binnaguri (Fulbari-II) for Augmentation of Binnaguri Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000532/2023-2024 | 1852/JD | 15/12/2023 | 45 | SUNIL ROY | 17.04 | 0 | 0
1816 | Jalpaiguri Division | Jalpaiguri Division | Repairing of pump house, boundary wall, land development and construction of drain, repairing valve chamber & other ancillary works at Augmentation of Binnaguri head works site under Binnaguri piped water supply scheme under Jalpaiguri Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000543/2023-2024 | 1934/JD | 02/01/2024 | 21 | GOPRO CONSTRUCTION | 4.2 | 4.12 | 100
1817 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000029/2024-2025 | 2102/JD | 25/11/2024 | 0 | Resource Division | 101.9 | 0 | 0
1818 | Jalpaiguri Division | Jalpaiguri Division | VEHICLE DRIVER | Assistant Engineer,HQ | Junior Engineer | BILL/01178/2023-2024 |  | 25/01/2024 | 0 | RAKESH SARKAR | 0.37 | 0 | 0
1819 | Jalpaiguri Division | Jalpaiguri Division | VEHICLE BILL | Assistant Engineer,HQ | Junior Engineer | BILL/01179/2023-2024 |  | 25/01/2024 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0
1820 | Jalpaiguri Division | Jalpaiguri Division | FUEL BILL | Assistant Engineer,HQ | Junior Engineer | BILL/01181/2023-2024 | BP-2023-24-631 | 06/02/2024 | 0 | FILL & SMILE | 0.82 | 0 | 0
1821 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation work for Pump houses and laying UPVC pipe line at H/W site of Augmentation of Shikarpur Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000019/2024-2025 | 519/JD | 27/06/2024 | 115 | KANAI LAL SEN | 7.02 | 6.86 | 100
1822 | Jalpaiguri Division | Jalpaiguri Division | Dismantiling old IEP, old Pump house and filling old CWR and other ancillary works at Sikarpur under Sikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000111/2023-2024 | 446/JD. | 08/06/2023 | 14 | GOUTAM DAS | 6 | 6 | 100
1823 | Jalpaiguri Division | Jalpaiguri Division | Construction of Room and other ancillary work at Belakoba primary school near H/W site for Shikarpur piped water supply schemer at Rajganj block under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000112/2023-2024 | 447/JD. | 08/06/2023 | 45 | DEBABRATA SARKAR | 2.94 | 2.99 | 100
1824 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.07.2025 to 29.11.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000142/2025-2026 | 1495/JD | 30/06/2025 | 152 | SOMNATH ROY | 0.94 | 0 | 0
1825 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall with gate, drain, land development, pathway including interconnection work and laying pipe line at Augmentation of Shikarpur PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000156/2024-2025 | 1530/JD | 01/10/2024 | 76 | GOUTAM DAS | 16.48 | 0 | 100
1826 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (350 cum) at Shikarpur under Shikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000170/2022-2023 | 1411/JD | 12/07/2022 | 15 | MABCO CONSULTANT | 2.26 | 2.11 | 1
1827 | Jalpaiguri Division | Jalpaiguri Division | Thorough repair and overhauling of the Iron Elimination Plant installed at Shikarpur Water Supply Scheme, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000207/2022-2023 | 1797/JD | 14/09/2022 | 21 | KANAI LAL SEN | 3.04 | 2.89 | 1
1828 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site of Shikarpur PWSS i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000373/2022-2023 | 298/JD | 10/02/2023 | 45 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 4.69 | 4.69 | 1
1829 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) for Augmentation of Shikarpur Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000542/2023-2024 | 1933/JD | 02/01/2024 | 45 | JAYA SARKAR | 17.09 | 0 | 0
1830 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Augmentation of Shikarpur PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000560/2021-2022 | 440/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 7.23 | 7 | 1
1831 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOIUR CAPACITY 350 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SHIKARPUR PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT:JALPAIGURI, UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000584/2021-2022 | 733/JD | 17/03/2022 | 1046 | GOUTAM DAS | 83.34 | 75.13 | 100
1832 | Jalpaiguri Division | Jalpaiguri Division | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 100
1833 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Shikarpur piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000619/2023-2024 | 2315/JD | 07/02/2024 | 30 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 8.28 | 7.21 | 100
1834 | Jalpaiguri Division | Jalpaiguri Division | Laying of Water Distribution System with Functional Household Tap Connection (FHTC) including construction valve chamber and other ancillary works in connection with Jal Jeevan Mission for Augumentation of Shikarpur Piped Water Supply Scheme at Block - Rajganj under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000816/2023-2024 | 2622/JD | 07/03/2024 | 600 | SCEC BOENTER AND KDAS JOINT VENTURE | 559.19 | 158.28 | 59
1835 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Madhab danga Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000009/2023-2024 | 334/RWS | 10/04/2023 | 14 | M/S KARMAKAR CONSTRACTION | 2.62 | 2.62 | 1
1836 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 4th site of Mathab danga Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000038/2023-2024 | 391/RWS | 25/04/2023 | 14 | NISHITH RANJAN KARMAKAR | 2.62 | 2.62 | 100
1837 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Madhabdanga piped water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000196/2022-2023 | 1593/JD | 18/08/2022 | 45 | M/S SIBU DEY AND CO. | 14.4 | 13.76 | 100
1838 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works including Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Madhab Danga Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-F) |  | Junior Engineer | ORD/000243/2022-2023 | 1898/JD | 26/09/2022 | 21 | ANUP SARKAR | 6.48 | 6.23 | 0
1839 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection(FHTC) in connection for JJM under the command area of Madhab Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000394/2022-2023 | 399/JD | 24/02/2023 | 21 | M/S SIBU DEY AND CO. | 4.75 | 3.78 | 1
1840 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retro fitting works due to FHTC in connection and other ancillary works for JJM under the command area of Madhab Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000395/2022-2023 | 400/JD | 24/02/2023 | 15 | M/S SIBU DEY AND CO. | 1.64 | 1.64 | 0
1841 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Madhab Danga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000477/2021-2022 | 2210/JD | 27/12/2021 | 60 | M/S KARMAKAR CONSTRACTION | 12.24 | 12.4 | 1
1842 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Madhab Danga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000478/2021-2022 | 2211/JD | 21/12/2021 | 60 | NISHITH RANJAN KARMAKAR | 12.26 | 12.25 | 0
1843 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No WB 71 A 5131 for the Month of July 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00583/2024-2025 | BP-2024-25-333 | 28/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1844 | Jalpaiguri Division | Jalpaiguri Division | HIRE CHARGES BILL OF VEHICLE UNDER NBC-I, PHE Dte. For the month of june to august 2023 | Assistant Engineer,HQ | Junior Engineer | BILL/00615/2023-2024 | BP-2023-24-418 | 06/10/2023 | 0 | RUPA PRASAD | 1.03 | 0 | 0
1845 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) ofVehicle No. WB 71 A 5131 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00656/2024-2025 | BP-2024-25-370 | 13/09/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1846 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00853/2024-2025 | BP-2024-25-482 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1847 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00940/2024-2025 | BP-2024-25-524 | 29/11/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0
1848 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 400 CUM AND 20 M STAGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPARMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE I) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ DISTRICT:JALPAIGURI UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2022-2023 | 876/JD | 05/04/2022 | 180 | UMWELT ENGINEER PRIVATE LIMITED | 94.23 | 84.1 | 100
1849 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-I) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2023-2024 | 840/JD | 04/04/2023 | 697 | ARUP SARKAR | 10.16 | 7.98 | 50
1850 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000018/2023-2024 | 62/JD | 18/04/2023 | 928 | RANJIT KARMAKAR | 31.21 | 24.05 | 100
1851 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.07.2024 to 21.01.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000033/2024-2025 | 659/JD | 12/07/2024 | 184 | MD AMIRUL ISLAM | 0.88 | 0.92 | 0
1852 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Sannyasikata Piped water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000034/2022-2023 | 1100/JD | 12/05/2022 | 90 | UMWELT ENGINEER PRIVATE LIMITED | 540.04 | 506.81 | 100
1853 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000036/2022-2023 | 1020/JD | 26/04/2022 | 21 | NARESH SEN | 8.09 | 7.92 | 1
1854 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000050/2022-2023 | 1194/JD | 20/05/2022 | 45 | MANAB BAKSHI | 4.65 | 0 | 0
1855 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m ) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-ii Water Supply Scheme under Jalpaiguri Division , P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2022-2023 | 1195/JD | 20/05/2022 | 45 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 4.65 | 1
1856 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with FHTC for Augmentation of Sannyasikata Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000060/2022-2023 | 1228/JD | 01/06/2022 | 120 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 788.85 | 629.96 | 100
1857 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying pipe line for Sannyasikata zone II H/W Site at Sannyasikata PWSS Site piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000120/2024-2025 | 1419/JD | 20/09/2024 | 147 | PRABIR SHOME | 18.38 | 0 | 0
1858 | Jalpaiguri Division | Jalpaiguri Division | Interconnection of Iron Elimination Plant to Rising Main, and other Ancillary Works at Sannyasikata Zone-II Head Work Site at Sannyasikata PWSS Rajganj Block, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000131/2024-2025 | 1285/JD | 03/09/2024 | 30 | RAGHU DAS | 8.11 | 7.98 | 100
1859 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-I under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000168/2022-2023 | 1414/JD | 13/07/2022 | 15 | M.K. KAYAL & ASSOCIATES | 2.26 | 2.11 | 1
1860 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-II under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000169/2022-2023 | 1413/JD | 13/07/2022 | 15 | MABCO CONSULTANT | 2.26 | 2.11 | 1
1861 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-I under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000279/2023-2024 | 1020/JD | 21/08/2023 | 45 | M/S M.B. DESIGN | 33.17 | 0 | 0
1862 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-II under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000332/2023-2024 | 1353/JD | 26/09/2023 | 45 | RAGHU DAS | 48.86 | 49.55 | 100
1863 | Jalpaiguri Division | Jalpaiguri Division | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) | Assistant Engineer,HQ | Junior Engineer | ORD/000391/2022-2023 | 2186/JD | 10/11/2022 | 151 | SUKES BASU MAJUMDAR | 0.94 | 0.47 | 0
1864 | Jalpaiguri Division | Jalpaiguri Division | Supply of different stationary for office use under Jalpaiguri Division, P.H.E. Dte. as per Annexure- I. | Assistant Engineer,HQ | Junior Engineer | ORD/000502/2022-2023 | 357/JD | 17/02/2023 | 7 | JAGRITI PRESS | 1.71 | 1.71 | 1
1865 | Jalpaiguri Division | Jalpaiguri Division | Supply of different stationary for office use under Jalpaiguri division, P.H.E. Dte. as per annexure- I. | Assistant Engineer,HQ | Junior Engineer | ORD/000503/2022-2023 | 358/JD | 17/02/2023 | 7 | SUBRATA ART PRESS | 1.64 | 0 | 1
1866 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer,HQ | Junior Engineer | ORD/000566/2023-2024 | 2128/JD | 18/01/2024 | 182 | MD AMIRUL ISLAM | 0.88 | 0.98 | 30
1867 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.01.2025 to 28.02.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000595/2024-2025 | 15/HQ/JD | 20/01/2025 | 38 | MD AMIRUL ISLAM | 0.19 | 0.19 | 0
1868 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell Site at Sannyasikata Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000613/2023-2024 | 2312/JD | 07/02/2024 | 30 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.81 | 0 | 100
1869 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.03.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000687/2024-2025 | 71/HQ/JD | 28/02/2025 | 31 | MD AMIRUL ISLAM | 0.15 | 0 | 0
1870 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOUR CAPACITY 550 CUM AND 20 M STAGING HEIGHT INCLUDING AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE- II) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT,JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000691/2023-2024 | 2393/JD | 16/02/2024 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 113.02 | 0 | 0
1871 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for H/W Site at Sannyasikata Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000810/2023-2024 | 2630/JD | 07/03/2024 | 294 | SADHAN KARMAKAR | 26.72 | 18.21 | 85
1872 | Jalpaiguri Division | Jalpaiguri Division | Construction of Different Component of water supply work and other ancillary work at Kalinagar Hospital More at Sannyasikata Zone-II under Sannyasikata PWSS of Rajganj Block under Jalpaiguri Division PHE, Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000828/2023-2024 | 2756/JD | 15/03/2024 | 550 | SHREE KRISHNA ENTERPRISE | 75.06 | 0 | 75
1873 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000887/2021-2022 | 844/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 7.77 | 1
1874 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000076/2024-2025 | 2207/JD | 01/12/2024 | 0 | Resource Division | 39.29 | 0 | 0
1875 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000103/2023-2024 | 1233/JD | 12/09/2023 | 0 | Resource Division | 41 | 0 | 0
1876 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Mahanbhita (Zone-I and II) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc under Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000066/2023-2024 | 367/JD | 26/05/2023 | 965 | MINTU CHAKRABORTY | 512 | 206.47 | 40
1877 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain, Land development and pathway including laying pipe line at Mahanbhita Zone-I (HW site & 2nd site) and Mahanbhita Zone-II (HW site, 2nd site and 3rd site) of Mahanbhita piped water supply scheme i.c.w. JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000585/2024-2025 | 270/JD | 07/02/2025 | 75 | SANKAR DAS | 80.69 | 0 | 30
1878 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000024/2023-2024 | 168/JD | 28/04/2023 | 0 | Resource Division | 23.28 | 0 | 0
1879 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000189/2023-2024 | 2051/JD | 09/01/2024 | 0 | Resource Division | 13.02 | 0 | 0
1880 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling i.c.w Rejuvenation of Syli Tea Garden Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000296/2023-2024 | 1354/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 40.77 | 40.41 | 60
1881 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repairing of Over Head Reservior(OHR) at Syli Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000382/2022-2023 | 346/JD | 16/02/2023 | 30 | RAGHU DAS | 4.12 | 4.11 | 1
1882 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000059/2023-2024 | 1094/JD | 24/08/2023 | 0 | Resource Division | 9.89 | 0 | 0
1883 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation of Ambari Falakata PWSS ie. TW, Pump Houses, Water distribution Network, IEP etc. in connection with Jal Jeevan Mission at Rajganj Block, under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000074/2023-2024 | 429/JD. | 08/06/2023 | 663 | KANAI LAL SEN | 82.62 | 9.86 | 85
1884 | Jalpaiguri Division | Jalpaiguri Division | Overhauling and Reconditioning of The IEP (2 Unit) other Ancillary Works at Ambari Falakata H/W Site at Block Rajganj, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000133/2024-2025 | 1292/JD | 04/09/2024 | 30 | BAJRANG ENTERPRISE | 12.02 | 11.56 | 100
1885 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Ambari Falakata P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000578/2021-2022 | 158/JD | 19/01/2022 | 60 | MAA ENTERPRISES | 4.65 | 0 | 100
1886 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at MATHACHULKA Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. |  | Junior Engineer | ORD/000115/2022-2023 | 92/JSSD | 22/07/2022 | 15 | DEBABRATA SARKAR | 4.62 | 0 | 100
1887 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Mathachulka PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000141/2023-2024 | 701/JD | 13/07/2023 | 539 | M/S. D.K. DEY & CO.. | 77.02 | 48.5 | 85
1888 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Laying Distribution System at Mathachulka Piped Water Supply Scheme in connection with Jal Jeevan Mission at Matiali Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000180/2025-2026 | 2166/JD | 30/10/2025 | 30 | DEEP CONSTRUCTION | 24.8 | 0 | 0
1889 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000086/2023-2024 | 1067/JD | 24/08/2023 | 0 | Resource Division | 17.44 | 0 | 0
1890 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000209/2023-2024 | 2069/JD | 10/01/2024 | 0 | Resource Division | 4 | 0 | 0
1891 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1892 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Nidam Jhora Tea Garden Pwss i.e TW, Pump House, Water Distribution Network,OHR, BW, Rising Main, FHTC etc. i.c.w Jal Jeevan mission at Block - Mal under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000258/2023-2024 | 943/JD | 08/08/2023 | 602 | J.M. CONSTRUCTION | 138.12 | 60.56 | 80
1893 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Nidam Jhora Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000587/2023-2024 | 2334/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 16.9 | 100
1894 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000068/2023-2024 | 1073/JD | 24/08/2023 | 0 | Resource Division | 17.26 | 0 | 0
1895 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000158/2023-2024 | 2023/JD | 09/01/2024 | 0 | Resource Division | 3.63 | 0 | 0
1896 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Land devlopment at 2nd site under Raipur T.G. Piped Water Supply Scheme under Jalpiaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000494/2022-2023 | 286/RWS | 29/03/2023 | 10 | NEW KUNDU ENTERPRISE | 0.98 | 0.98 | 100
1897 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of Wash out line and distribution line over jhora at Dakshin Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000021/2024-2025 | 518/JD | 27/06/2024 | 14 | NEW KUNDU ENTERPRISE | 1.9 | 1.48 | 100
1898 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of C.C. drain (extension) at front side of head work site along the road to drain out over flow water of OHR under Dakshin Salbari Water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000032/2023-2024 | 386/RWS | 25/04/2023 | 14 | NEW KUNDU ENTERPRISE | 2.41 | 2.44 | 100
1899 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Dakshin Shalbari PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block ¿ Banarhat under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer 2 | ORD/000106/2023-2024 | 437/JD. | 08/06/2023 | 784 | RABINDRANATH DUTTA | 56.71 | 15.41 | 70
1900 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Dakshin Salbari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000415/2022-2023 | 169/RWS | 28/02/2023 | 21 | NEW KUNDU ENTERPRISE | 2.99 | 2.46 | 100
1901 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000084/2023-2024 | 1068/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0
1902 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1903 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Binnaguri PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000469/2022-2023 | 751/JD | 24/03/2023 | 725 | BISWANATH GHOSH | 226.15 | 130.79 | 100
1904 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Functional Household Tap Connection for Binnaguri PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000599/2024-2025 | 482/JD | 11/03/2025 | 333 | BISWANATH GHOSH | 18.65 | 0 | 0
1905 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000010/2023-2024 | 154/JD | 28/04/2023 | 0 | Resource Division | 17.1 | 0 | 0
1906 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000147/2023-2024 | 2003/JD | 08/01/2024 | 0 | Resource Division | 6.23 | 0 | 0
1907 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of differet components of Baragharia Zone-II PWSS i.e TW, Pump Houses, Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. in connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000053/2023-2024 | 357/JD. | 25/05/2023 | 180 | M.S ENTERPRISE | 166.28 | 64.33 | 65
1908 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of differet components of Baragharia Zone-I PWSS i.e TW, Pump Houses , Water distribution Network, OHR, Boundary Wall , RISING MAIN , FHTC etc. in connection with Jal Jeevan Mission at Block Kranti under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000054/2023-2024 | 356/JD | 25/05/2023 | 860 | M.S ENTERPRISE | 246.82 | 113.98 | 40
1909 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1910 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Additional Components for uncovered TANTY PARA AREA of BARAGHARIA PWSS i.e. TW, Pump House ,Boundary Wall, Water distribution Network ,FHTC, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000543/2024-2025 | 570/JD | 25/03/2025 | 75 | SADHAN KARMAKAR | 113.85 | 0 | 0
1911 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000073/2023-2024 | 1078/JD | 24/08/2023 | 0 | Resource Division | 38.3 | 0 | 0
1912 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000204/2023-2024 | 2074/JD | 10/01/2024 | 0 | Resource Division | 8.03 | 0 | 0
1913 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation Of Haritalguri Tea Garden Area PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000131/2023-2024 | 418/A/JD | 07/06/2023 | 60 | M/S ROY & SARKAR CONSTRUCTION | 69.21 | 20.04 | 11
1914 | Jalpaiguri Division | Jalpaiguri Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Banarhat block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer,HQ | Junior Engineer | ORD/000451/2023-2024 | 1288/RWS | 28/11/2023 | 30 | SUKES BASU MAJUMDAR | 3.11 | 3.11 | 100
1915 | Jalpaiguri Division | Jalpaiguri Division | Balance work of Laying pipeline & providing FHTC with allied works at Haritalguri Piped Water Supply Scheme in connection with JJM within Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000487/2024-2025 | 2425/JD | 24/12/2024 | 45 | M/S ROY & SARKAR CONSTRUCTION | 32.68 | 0 | 0
1916 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Baragharia PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000026/2023-2024 | 93/JD | 25/04/2023 | 1096 | SCEC BOENTER KDAS JOINT VENTURE | 431.11 | 223.45 | 75
1917 | Jalpaiguri Division | Northern Mechanical Division | Balance work for Laying Distribution System at Baragharia Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Dhupguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000179/2025-2026 | 2167/JD | 30/10/2025 | 30 | S. DUTTA | 26.33 | 0 | 0
1918 | Jalpaiguri Division | Northern Mechanical Division | Providing FHTC in the command area of Baragharia PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000540/2024-2025 | 111/JD | 16/01/2025 | 45 | SWAPAN SAHA | 22.58 | 0 | 0
1919 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000125/2023-2024 | 1839/JD | 15/12/2023 | 0 | Resource Division | 12.71 | 0 | 0
1920 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of JuLY,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00756/2024-2025 | BP-2024-25-416 | 01/10/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
1921 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of June,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00758/2024-2025 | BP-2024-25-418 | 01/10/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0
1922 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of August'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01032/2024-2025 | BP-2024-25-563 | 20/12/2024 | 0 | FILL & SMILE | 0.24 | 0 | 0
1923 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1924 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1925 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) |  |  | ORD/000112/2024-2025 | 142/1/JSSD | 29/07/2024 | 184 | APIKUL ALI | 0.88 | 0.47 | 0
1926 | Jalpaiguri Division |  | Construction of different components of New Clenco T.G. (P) (Zone-I & II) PWSS i.e. TW, Pump Housese,Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000159/2023-2024 | 798/JD. | 24/07/2023 | 601 | MD HAKIMUDDIN | 554.35 | 438.04 | 100
1927 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000212/2024-2025 | 137/JSSD | 29/07/2024 | 60 | DHIRAJ BISWAS | 0.88 | 0.44 | 50
1928 | Jalpaiguri Division |  | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including construction of Hume Pipe Culvert at New Clenco Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000225/2024-2025 | 1571/JD | 04/10/2024 | 244 | MD HAKIMUDDIN | 88.52 | 0 | 80
1929 | Jalpaiguri Division |  | Sinking of 3 (Three) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of New Clenco TG PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000484/2024-2025 | 2432/JD | 24/12/2024 | 373 | MD HAKIMUDDIN | 53.54 | 0 | 100
1930 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  |  | ORD/000819/2023-2024 | 524/JSSD | 29/01/2024 | 182 | APIKUL ALI | 0.88 | 0.56 | 70
1931 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000820/2023-2024 | 525/JSSD | 29/01/2024 | 182 | DHIRAJ BISWAS | 0.88 | 0.59 | 0
1932 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 1373/JD | 27/09/2023 | 0 | Resource Division | 39.87 | 0 | 0
1933 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 2026/JD | 09/01/2024 | 0 | Resource Division | 20.96 | 0 | 0
1934 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | 200 Cum OHR as per Departmental Design & Drawing for Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme Block- Nagrakata, District - Jalpaiguri. |  | Junior Engineer | ORD/000043/2022-2023 | 1081/JD | 29/04/2022 | 180 | SABITA ENTERPRISE | 55.26 | 33.84 | 100
1935 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Tap Water Supply Connection in Connection with Jaldhara /Jalswapna in School, ICDS Centre and Health Centre at Hope TG,Naya Sily TG, Jiti TG,Nagrakata & Nagrakata TG Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000111/2022-2023 | 88/JSSD | 22/07/2022 | 10 | GOUTAM DAS | 3.64 | 3.63 | 0
1936 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40m) size with sanitary and plumbing arrangement at 3rd tubewell site for Rejuvenation of Water Supply of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000125/2022-2023 | 24/JSSD | 21/06/2022 | 45 | SANJIT SARKAR | 4.76 | 4.76 | 100
1937 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with providing Functional Household Tap Connection (FHTC) i.c.w. Jal Jeevan Mission under the command area of Rejuvenation of Nayasayli T.G. Area Piped W/S Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. (Phase-IV). |  | Junior Engineer | ORD/000138/2024-2025 | 1527/JD | 01/10/2024 | 20 | GAP ENGINEERS ENTERPRISES | 14.48 | 12.05 | 90
1938 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with laying rising main with other allied works for Rejuvenation of Nayasayli Tea Garden Piped W/S Scheme under JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000146/2024-2025 | 259/JSSD | 25/09/2024 | 280 | GOLDEN KEY ENTERPRISE | 7.07 | 0 | 75
1939 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Replacement of UPVC pipeline with other allied works at Jungle Busty area i.c.w. Rejuvenation of Nayasaili Piped W/S Scheme under JJM at Nagrakata BLOCK, under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000154/2024-2025 | 266/JSSD | 25/09/2024 | 38 | NEW KUNDU ENTERPRISE | 2.24 | 2.24 | 100
1940 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size including sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Nayasaily Tea Garden Water Supply Scheme for under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000310/2022-2023 | 63/JSSD | 19/07/2022 | 45 | N.M. CONSTRUCTION | 4.75 | 4.75 | 100
1941 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 4th tube-well site for Rejuvenation of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000311/2022-2023 | 64/JSSD | 19/07/2022 | 20 | N.M. CONSTRUCTION | 4.77 | 3.39 | 100
1942 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of a Rig Bored Tubewell by ODEX-165 method of drilling along with pump connection and other allied works at Champaguri Bazar area (5th TW Site) in connection with Jal Jeevan Mission of Rejuvenation of Naya Saily TG Piped Water Supply Scheme, Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000624/2024-2025 | 463/JD | 11/03/2025 | 30 | NARESH SEN | 10.09 | 0 | 0
1943 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) for Nayasaily T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000693/2021-2022 | .1065/JSSD | 24/01/2022 | 20 | R.B TESTING | 2.01 | 2.01 | 100
1944 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by Odex - 165 Method of drilling at 3rd tube well site for Rejuvenation of Nayasily Tea Garden Piped water Supply scheme under Jalpaiguri Division, P.H.E. Dte." |  | Junior Engineer | ORD/000773/2021-2022 | 837/JD | 31/03/2022 | 21 | M/S S. G. ENTERPRISE | 7.61 | 6.14 | 0
1945 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube Well by Odex -165 Method of drilling at 4th tube well site for Rejuvenation of Nayasily Tea Garden Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte." |  | Junior Engineer | ORD/000774/2021-2022 | 838/JD | 31/03/2022 | 21 | M/S S. G. ENTERPRISE | 7.62 | 6.05 | 0
1946 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 3rd tube-well site of Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/001001/2021-2022 | 1260/JSSD | 25/03/2022 | 20 | ROY CONSTRUCTION | 4.79 | 3.57 | 100
1947 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000024/2024-2025 | 2110/JD | 25/11/2024 | 0 | Resource Division | 5.22 | 0 | 0
1948 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) |  | Junior Engineer | ORD/000432/2022-2023 | 631/JD | 13/03/2023 | 45 | PARESH CHANDRA GUHA | 40.48 | 25.68 | 100
1949 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc basilar danga |  | Junior Engineer | VCH/000343/2021-2022 |  | 05/10/2021 | 0 | PARESH CHANDRA GUHA | 15 | 0 | 0
1950 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc basilardanga |  | Junior Engineer | VCH/000464/2021-2022 |  | 21/10/2021 | 0 | PARESH CHANDRA GUHA | 16.39 | 0 | 0
1951 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BASILARDANGA |  | Junior Engineer | VCH/000794/2021-2022 | BP-2021-22-87 | 01/11/2021 | 0 | PARESH CHANDRA GUHA | 16.39 | 0 | 0
1952 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BHANGARHAT PWSS |  | Junior Engineer | VCH/001359/2021-2022 | BP-2021-22-497 | 29/03/2022 | 0 | M/S DEY & ROY CHOUDHURY | 10.33 | 0 | 0
1953 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PALASBARI PWSS |  | Junior Engineer | VCH/001395/2021-2022 | BP-2021-22-553 | 30/03/2022 | 0 | SANKAR DAS | 4.73 | 0 | 0
1954 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) |  |  | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0.35 | 1
1955 | Jalpaiguri Division |  | Retrofitting works in connection with FHTC works along with PWD road from Prodhan Para to Putimari and different places at Bhangamali under Bhangamali Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000569/2021-2022 | 1811/JD | 18/11/2021 | 15 | RABINDRANATH DUTTA | 17.81 | 0.05 | 1
1956 | Jalpaiguri Division |  | BHANGAMALI |  |  | VCH/001052/2021-2022 | BP-2021-22-203 | 19/01/2022 | 0 | MRINMOY KANTI DUTTA | 14.38 | 0 | 0
1957 | Jalpaiguri Division |  | PROVIDING FHTC FOR BHANGAMALI PWSS |  |  | VCH/001333/2020-2021 | 1195 | 04/02/2021 | 0 | MRINMOY KANTI DUTTA | 14.66 | 0 | 0
1958 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000377/2021-2022 | 350/JD | 03/02/2022 | 120 | NARENDRA KUMAR | 57.75 | 39.59 | 100
1959 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with gate,drain, Pipe line for H/W site of KILLKOTE T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000562/2020-2021 | 202/JD | 10/02/2021 | 30 | M/S SURAJIT DEY AND CO. | 14.94 | 14.98 | 0
1960 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | soil test for kilkote |  | Junior Engineer | VCH/000239/2022-2023 | bp2022-23- | 14/06/2022 | 0 | G. TECH INDIA | 2.03 | 0 | 0
1961 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST OF RISING MAIN CONNECTION FOR KILKOTE T.G |  | Junior Engineer | VCH/000240/2022-2023 | bp2022-23-49 | 07/06/2022 | 0 | GOUR KUMAR MITRA | 4.8 | 0 | 0
1962 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC KILKOTE |  | Junior Engineer | VCH/001201/2021-2022 | BP-2021-22-328 | 28/02/2022 | 0 | M/S SURAJIT DEY AND CO. | 11.92 | 0 | 0
1963 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETRO FITTING WORK HOPE |  | Junior Engineer | VCH/001202/2021-2022 | BP-2021-22-327 | 28/02/2022 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 0.7 | 0 | 0
1964 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | INSTALLATION IRON ELIMINATION PLANT |  | Junior Engineer | VCH/001288/2021-2022 | BP-2021-22-519 | 30/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 5.1 | 0 | 0
1965 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION BHUSKA DANGA PWSS |  | Junior Engineer | VCH/001305/2021-2022 | BP-2021-22-424 | 25/03/2022 | 0 | MABCO CONSULTANT | 2.01 | 0 | 0
1966 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK KILKOTE T.G |  | Junior Engineer | VCH/001318/2021-2022 | BP-2021-22-436 | 26/03/2022 | 0 | MABCO CONSULTANT | 2.01 | 0 | 0
1967 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST BLOWER ROOM PURBA DURAMARI WSS |  | Junior Engineer | VCH/001368/2021-2022 | BP-2021-22-520 | 30/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 5.78 | 0 | 0
1968 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 3rd tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000140/2022-2023 | 1603/JD | 18/08/2022 | 45 | SANDIP BANIK | 13.65 | 12.43 | 0
1969 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Basilardanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000274/2022-2023 | 2011/JD | 01/11/2022 | 15 | SANKAR DAS | 6.64 | 4.9 | 1
1970 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000294/2022-2023 | 2067/JD | 04/11/2022 | 45 | R.S CONSTRUCTION | 13.65 | 13.6 | 100
1971 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works & other ancillary works related to FHTC at different places of Basilardanga PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000383/2022-2023 | 368/JD | 20/02/2023 | 15 | DIPAK KUMAR CHAKRABORTY | 1.81 | 1.81 | 0
1972 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) |  | Junior Engineer | ORD/000432/2022-2023 | 631/JD | 13/03/2023 | 45 | PARESH CHANDRA GUHA | 40.48 | 1.67 | 100
1973 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000473/2021-2022 | 2219/JD | 27/12/2021 | 60 | PARESH CHANDRA ROY | 11.45 | 11.44 | 1
1974 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000485/2021-2022 | 2218/JD | 27/12/2021 | 60 | M/S DEY & ROY CHOUDHURY | 11.44 | 11.43 | 1
1975 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing on OHR , pump house , IEP Room , boundary wall , construction of pathway , & other ancillary works for Basilardanga piped W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000588/2021-2022 | 178/RWS | 03/03/2022 | 30 | PARESH CHANDRA GUHA | 4.85 | 4.02 | 0
1976 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Basilardanga Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000731/2021-2022 | 642/JD | 08/03/2022 | 30 | MECHANO TRADING CO. | 15.51 | 12.87 | 1
1977 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Supply Of Potable Drinking Water To Dharanipur Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000827/2023-2024 | 2755/JD | 15/03/2024 | 413 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 71.04 | 35.75 | 55
1978 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000287/2022-2023 | 2015/JD | 01/11/2022 | 927 | M/S R.N. TRADERS | 14.7 | 12.61 | 100
1979 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall at H/W Site & 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF RAMSAI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000330/2021-2022 | 187/JD | 21/01/2022 | 120 | PARESH CHANDRA GUHA | 108.89 | 108.02 | 100
1980 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-II) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT - JALPAIGURI. |  | Junior Engineer | ORD/000334/2021-2022 | 206/JD | 24/01/2022 | 90 | ASHIT KUMAR SINGHA | 221.07 | 139.13 | 100
1981 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF RAMSAI (PART-III) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT, JALPAIGURI. |  | Junior Engineer | ORD/000341/2021-2022 | 191/JD | 21/01/2022 | 1319 | M/S R.N. TRADERS | 187.78 | 126.62 | 100
1982 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-I) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT ¿ JALPAIGURI. |  | Junior Engineer | ORD/000342/2021-2022 | 190/JD | 21/01/2022 | 1118 | PARESH CHANDRA GUHA | 203.47 | 189.67 | 100
1983 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000343/2022-2023 | 140/JD | 17/01/2023 | 850 | R.S CONSTRUCTION | 14.7 | 12.74 | 60
1984 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (35 m3/hr) including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain...etc at H/W Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000380/2022-2023 | 2268/JD | 21/11/2022 | 585 | M/S A.B.G. CONSTRUCTION | 29.33 | 29.32 | 100
1985 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System ( node 2-4-287-288-289-290-291-292 & node 5-134) for Augmentation of Ramsai Piped Water Supply Scheme under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. Block-Maynaguri. District- Jalpaiguri. |  | Junior Engineer | ORD/000452/2022-2023 | 730/JD | 22/03/2023 | 45 | R.S CONSTRUCTION | 25.64 | 25.64 | 100
1986 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000715/2021-2022 | 2228/JD | 27/12/2021 | 60 | SANKAR DAS | 11.45 | 11.33 | 100
1987 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 250 mm x 150 mm x 123 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Augmentation of Ramsai Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000729/2021-2022 | 633/JD | 07/03/2022 | 30 | MECHANO TRADING CO. | 15.35 | 13.91 | 0
1988 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000883/2021-2022 | 217/JD | 24/01/2022 | 60 | GOURAB GUHA ROY | 11.44 | 11.36 | 100
1989 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000007/2021-2022 | 181/JD | 21/01/2022 | 0 | Resource Division | 31.71 | 0 | 0
1990 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000015/2021-2022 | 552/JD | 01/03/2022 | 0 | Resource Division | 28.13 | 0 | 0
1991 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000089/2024-2025 | 2217/JD | 01/12/2024 | 0 | Resource Division | 20.02 | 0 | 0
1992 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS BHUJARI PARA KRANTI ZONE II |  | Junior Engineer | VCH/001417/2021-2022 | BP-2021-22-439 | 26/03/2022 | 0 | BARUN KUMAR DUTTA | 4.7 | 0 | 0
1993 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hope Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000132/2022-2023 | 1467/JD | 25/07/2022 | 30 | PROSENJIT BASAK | 13.84 | 13.14 | 0
1994 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Urgent Retrofitting works at LW Bungalow back side under Hope T.G. Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000261/2022-2023 | 187/JSSD | 31/08/2022 | 30 | NARAYAN CHANDRA ADHIKARY | 1.91 | 1.89 | 0
1995 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection 257 Nos. in connection with Jal Jeevan Mission at Hope Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000347/2023-2024 | 293/JSSD | 27/09/2023 | 30 | GOUTAM DAS | 9.47 | 7.29 | 91
1996 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | EMERGENT REPAIRING OF PIPE LINE INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER HOPE TG PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE. |  | Junior Engineer | ORD/000350/2023-2024 | 299/JSSD | 27/09/2023 | 45 | GOUTAM DAS | 3.37 | 3.37 | 100
1997 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Disconnecting illegeal connections and street stand posts with repairing of distribution line at Rejuvenation of Chalsa (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000390/2022-2023 | 363/JD | 20/02/2023 | 14 | ALICK DATTA | 2.91 | 2.9 | 100
1998 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 2 nos. Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement and 2 nos. boundary wall with gate,drain and pathway for 3rd & 4th tubewell site of Hope TG piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000430/2022-2023 | 632/JD | 13/03/2023 | 60 | PRADIP KUMAR SHIL | 16.98 | 17.3 | 100
1999 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of 2 nos. of pump house (1st site & 2nd site) 3 nos. Boundary wall (Head work site, 1st site & 2nd site) with sanitary & plumbing arrangement and other allied works at Hope T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000547/2021-2022 | 1065/JSSD | 24/02/2022 | 30 | GOUTAM DAS | 4.08 | 4.03 | 0
2000 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jalswapna near 18 no. line 15 no. line and allied areas for Hope T.G. PWSS under Jalpaiguri Division, PHE Dte. (Part-B) |  | Junior Engineer | ORD/000549/2021-2022 | 1049/JSSD | 24/01/2022 | 15 | GOUTAM DAS | 4.75 | 4.75 | 0
2001 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2023-2024 | 849/JD | 06/04/2023 | 45 | M/S YADAV CONSTRUCTION | 5.44 | 5.44 | 100
2002 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system For Rejuvenation Of Meteli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000021/2022-2023 | 1030/JD | 26/04/2022 | 1158 | NARAYAN CHAKRABORTY | 97.34 | 86.6 | 100
2003 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 3 Nos. Big Dia Tube well by Modified DTH - ODEX Method at 6th, 7th & 8th tube well site of Rejuvenation of Mateli Bazar (Zone- I & II) Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000062/2024-2025 | 931/JD | 07/08/2024 | 45 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 52.84 | 50.1 | 100
2004 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Water Tap Connection including laying pipeline in the command area of Metelibazar PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000091/2025-2026 | 104/JSSD | 30/05/2025 | 30 | SUJAN LAMA | 4.83 | 0 | 100
2005 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in Connection with Jaldhara/Jal Swapna near Jyoti Colony for Matiali Bazar Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000189/2022-2023 | 89/JSSD | 22/07/2022 | 10 | GOURAB GUHA ROY | 4.53 | 4.51 | 100
2006 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Urgent Retrofitting works at Prem Nagar & Thakur line under Meteli Bazar Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000255/2022-2023 | 175/JSSD | 25/08/2022 | 30 | SUJAN LAMA | 3.14 | 3.03 | 1
2007 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system For Rejuvenation Of Meteli Bazar (Zone-I) Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000295/2022-2023 | 2061/JD | 03/11/2022 | 1245 | SAHA CONSTRUCTION | 115.22 | 16.97 | 45
2008 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-I) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000345/2022-2023 | 138/JD | 17/01/2023 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.88 | 0 | 0
2009 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000346/2022-2023 | 139//JD | 17/01/2023 | 30 | M/S KARMAKAR CONSTRACTION | 14.88 | 0 | 0
2010 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repairing of HW site & 1st site Pump House with Sanitary and plumbing arrangement for Augmentation of Mateli Bazar(Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000360/2023-2024 | 283/JSSD | 26/09/2023 | 366 | M/S YADAV CONSTRUCTION | 6.32 | 0 | 100
2011 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing including Rising Main in connection with Jal Jeevan Mission for Meteli Bazar Zone-II area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000396/2023-2024 | 1582/JD | 03/11/2023 | 180 | UNIVERSAL ENTERPRISES | 73.78 | 0 | 0
2012 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000398/2023-2024 | 1586/JD | 06/11/2023 | 45 | M/S SUNSHINE | 5.61 | 0 | 0
2013 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Household Tap Connection 846 Nos. in connection with Jal Jeevan Mission at Mateli Bazar Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000402/2023-2024 | 1669/JD | 24/11/2023 | 30 | DIPAK KUMAR CHAKRABORTY | 30.54 | 0 | 0
2014 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Restoration work of damaged road due to lying of pipeline, GI works and other allied works under Rejuvenatioin of Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000545/2023-2024 | 496/JSSD | 02/01/2024 | 30 | NARAYAN CHAKRABORTY | 8.47 | 8.35 | 100
2015 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000556/2021-2022 | 457/JD | 18/02/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 6.38 | 0 | 100
2016 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000557/2021-2022 | 456/JD | 18/02/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 12.75 | 13.11 | 100
2017 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related with Jal swapna / JJM for Mateli Bazar area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001031/2021-2022 | 1053 /JSSD | 24/01/2022 | 15 | GOURAB GUHA ROY | 3.1 | 3.03 | 0
2018 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000052/2023-2024 | 1087/JD | 24/08/2023 | 0 | Resource Division | 9.2 | 0 | 0
2019 | Jalpaiguri Division | Jalpaiguri Division | Construction of 450 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at Head Works site for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2023-2024 | 240/JD | 08/05/2023 | 721 | JAYANTA GHOSH | 140.51 | 44.48 | 60
2020 | Jalpaiguri Division | Jalpaiguri Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2021 | Jalpaiguri Division | Jalpaiguri Division | Minor repairing of Two nos. Pump House with Construction of Toilet and Sanitary Plumbing System located at head work site including Land Development work at 2nd Pummp house site and adjacent area along with ancillary work of Augmentation of Bhatiapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000098/2022-2023 | 1306/JD | 14/06/2022 | 21 | RABINDRANATH DUTTA | 3.93 | 3.88 | 100
2022 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara (Zone-II ) Piped water Supply Scheme(Part-B) at Nagrakata Block under Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000146/2022-2023 | 1889/JD | 22/09/2022 | 1073 | RANA DEY | 65.49 | 63.94 | 97
2023 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-II )Piped water Supply Scheme (Part-E) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000240/2022-2023 | 1959/JD | 17/10/2022 | 21 | M/S SIBU DEY AND CO. | 81.95 | 79.77 | 95
2024 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme (Part A & D) at Nagrakata Block Under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000260/2022-2023 | 1948/JD | 13/10/2022 | 120 | JAYANTA GHOSH | 241.53 | 179.67 | 60
2025 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000272/2022-2023 | 2013/JD | 01/11/2022 | 21 | NEW KUNDU ENTERPRISE | 58.51 | 56.08 | 96
2026 | Jalpaiguri Division | Jalpaiguri Division | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-I under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000272/2023-2024 | 1260/JD | 13/09/2023 | 719 | NARAYAN CHAKRABORTY | 56.64 | 4.9 | 6
2027 | Jalpaiguri Division | Jalpaiguri Division | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-II under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000273/2023-2024 | 1261/JD | 13/09/2023 | 718 | RANA DEY | 90.44 | 4.9 | 50
2028 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-B) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000296/2022-2023 | 2060/JD | 03/11/2022 | 21 | SAPTASWA SARKAR | 74.86 | 71.6 | 100
2029 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-II ) Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000319/2022-2023 | 2004/JD | 28/10/2022 | 21 | GOURAB GUHA ROY | 33.43 | 23.05 | 100
2030 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Bhatia Para (Zone-II) Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000525/2023-2024 | 1970/JD | 03/01/2024 | 21 | RABINDRANATH DUTTA | 18.51 | 0 | 0
2031 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of BHATIAPARA (ZONE-I) Piped Water Supply Scheme (PART-A) at Banarhut Block under Jalpaiguri Division, P.H.E Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000536/2024-2025 | 569/JD | 25/03/2025 | 372 | ANUP SARKAR | 146.75 | 0 | 0
2032 | Jalpaiguri Division | Jalpaiguri Division | Construction of 2nd Tube well site Boundary wall, Drain, Pathway and Laying of Rising main at Zone-I of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000596/2024-2025 | 268/JD | 07/02/2025 | 328 | RANA DEY | 9.33 | 0 | 0
2033 | Jalpaiguri Division | Jalpaiguri Division | Construction of 3rd site Tube well Boundary wall, Drain, Pathway and Laying of Rising main at Zone-II of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000597/2024-2025 | 269/JD | 07/02/2025 | 147 | RANA DEY | 9.24 | 0 | 0
2034 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000078/2024-2025 | 2209/JD | 01/12/2024 | 0 | Resource Division | 31.51 | 0 | 0
2035 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000092/2023-2024 | 1065/JD | 24/08/2023 | 0 | Resource Division | 7.18 | 0 | 0
2036 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
2037 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Tandu PWSS i.e TW Pump Houses, Water distribution Network, OHR,RISING MAIN,FHTC etc. i.c.w JAL JEEVAN MISSION at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000466/2022-2023 | 755/JD | 24/03/2023 | 1015 | PRADIP SAHA | 114.12 | 63.69 | 35
2038 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000014/2023-2024 | 158/JD | 28/04/2023 | 0 | Resource Division | 2.39 | 0 | 0
2039 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000174/2023-2024 | 2029/JD | 09/01/2024 | 0 | Resource Division | 2.44 | 0 | 0
2040 | Jalpaiguri Division |  | Construction of different components of Niranjan Pat PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000130/2023-2024 | 406/JD | 06/06/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 231.81 | 102.99 | 65
2041 | Jalpaiguri Division |  | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Niranjanpat Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000682/2024-2025 | 632/JD | 28/03/2025 | 45 | TIRTHANKAR CHOWDHURY | 24.06 | 0 | 0
2042 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 1375/JD | 27/09/2023 | 0 | Resource Division | 18.27 | 0 | 0
2043 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1836/JD | 15/12/2023 | 0 | Resource Division | 5.33 | 0 | 0
2044 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different Components of ANANDAPUR T.G. PWSS i.e. 2 Nos Tube well, 2 Nos Pump house, Iron Elimination plant, 2 Nos Boundary Wall, Blower Room, Water distribution Network, 350 Cum OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000024/2025-2026 | 2153/JD | 17/10/2025 | 210 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 481.86 | 0 | 0
2045 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2046 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sub-Soil Investigation of proposed 350 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Anandapur Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000802/2024-2025 | 89-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
2047 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000106/2023-2024 | 1372/JD | 27/09/2023 | 0 | Resource Division | 27.51 | 0 | 0
2048 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Chalsa Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Matiali under Jalpaiguri Division. |  | Junior Engineer | ORD/000006/2023-2024 | 24/JD | 10/04/2023 | 905 | PRASENJIT BASAK | 195.5 | 118.79 | 90
2049 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2050 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) of Chalsa Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000184/2025-2026 | 2157/JD | 29/10/2025 | 30 | PRASENJIT BASAK | 14.85 | 0 | 0
2051 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos Deep Rig Bored Tube Well by ODEX-195 method of drilling with 2 Nos Pump House(3.6m X 2.4m) and Boundary Wall including Pump House to distribution Line Connection for Rejuvenation of Chalsa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000275/2023-2024 | 614/JD | 30/06/2023 | 30 | S. N. POLYMERS PVT. LTD. | 40.47 | 13.79 | 35
2052 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting and Repairing work related to Laying Distribution System in Mangal Bar market area at Chalsa Rejuvenation Water Supply Scheme under Jalpaiguri Division, PHE DTE. |  | Junior Engineer | ORD/000829/2021-2022 | 1072/W/JSSD | 25/01/2022 | 20 | DEEP CONSTRUCTION | 4.14 | 4.09 | 0
2053 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000172/2023-2024 | 2034/JD | 09/01/2024 | 0 | Resource Division | 6.65 | 0 | 0
2054 | Jalpaiguri Division | Jalpaiguri Division | Relaying of Rising Main from Head Works Site to Pump House No.-II due to the Damage of HDPE Pipeline at Riabari T.G PWSS under Jalpaiguri Division, P.H.E. | Assistant Engineer,HQ | Junior Engineer | ORD/000507/2024-2025 | 2403/JD | 20/12/2024 | 20 | SAPTASWA SARKAR | 1.32 | 0 | 0
2055 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000016/2024-2025 | 532/JD | 28/06/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 26.33 | 100
2056 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components for Rejuvenation of Yongtong Tea garden PWSS i.e. TW, Pump Housese, Boundary Wall, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000087/2023-2024 | 439/JD. | 08/06/2023 | 605 | ASHIS DUTTA | 69.4 | 0 | 50
2057 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of drain, development of land, Painting works of 250 Cu.M. capacity R.C.C. Elevated Reservoir, Pump House & Boundary Wall at Head works site for YongTong TG Piped Water Supply Scheme under Jalpaiguri Divition , P.H.E. Dte. |  | Junior Engineer | ORD/000434/2022-2023 | 606/JD | 09/03/2023 | 30 | PAMPA CONSTRUCTION | 6.2 | 6.16 | 0
2058 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of YongTong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000548/2023-2024 | 500/JSSD | 02/01/2024 | 30 | D. S. ENTERPRISE | 2.34 | 2.29 | 100
2059 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000048/2023-2024 | 1100/JD | 24/08/2023 | 0 | Resource Division | 14.64 | 0 | 0
2060 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components for Rejuvenation of Nagrakata Tea garden PWSS i.e. TW, Pump Housese, Boundary Wall, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000108/2023-2024 | 438/JD. | 08/06/2023 | 573 | NARAYAN CHANDRA SAHA | 85.68 | 75.36 | 90
2061 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Commissioning of Rejuvenation of Nagrakata Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. (Phase-I) |  | Junior Engineer | ORD/000351/2023-2024 | 300/JSSD | 27/09/2023 | 30 | PARAMJYOTI ENTERPRISE | 9.59 | 4.89 | 100
2062 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System (Part-L) along with 120 nos FHTC related to Rejuvenation of Nagrakata PWSS in connection with Jal Jeevan Mission at Block-Nagrakata under under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000353/2023-2024 | 294/JSSD | 27/09/2023 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.68 | 9.67 | 60
2063 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | EMERGENT REPAIRING OF PIPE LINE, R.B.T FIXING IN BOUNDARY WALL, INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER NAGRAKATA T.G. PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE |  | Junior Engineer | ORD/000354/2023-2024 | 301/JSSD | 27/09/2023 | 30 | PARAMJYOTI ENTERPRISE | 5.37 | 5.37 | 100
2064 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000080/2023-2024 | 1058/JD | 24/08/2023 | 0 | Resource Division | 11.54 | 0 | 0
2065 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retro fitting works due to FHTC in connection for JJM under the command area of Huslu Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000435/2022-2023 | 675/JD | 16/03/2023 | 15 | M/S ROY & SARKAR CONSTRUCTION | 2.92 | 2.92 | 0
2066 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000102/2023-2024 | 1048/JD | 24/08/2023 | 0 | Resource Division | 4.8 | 0 | 0
2067 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
2068 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
2069 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Kantadighi Kumarpara T.G. PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000063/2023-2024 | 247/JD | 10/05/2023 | 875 | S.S. CONSTRUCTION | 465.21 | 350.39 | 20
2070 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance works Distribtion System and Functional Household Tap Connection (FHTC) including Different Components of Kantadighi Kumar Para TG PWSS i.e. TW, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000456/2024-2025 | 2037/JD | 21/11/2024 | 496 | SAPTASWA SARKAR | 82.16 | 0 | 40
2071 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000064/2023-2024 | 1092/JD | 24/08/2023 | 0 | Resource Division | 60.02 | 0 | 0
2072 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000154/2023-2024 | 2012/JD | 09/01/2024 | 0 | Resource Division | 15.28 | 0 | 0
2073 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Inspection Vehicle WB-71B-9586 for JJM on daily basis @12.00/Km for Official use of the Assistant Engineer, Jalpaiguri Sadar-Sub Division P.H.E. Dte (OCT 2023 TO DEC 2023) |  | Junior Engineer | BILL/01202/2023-2024 | BP-2023-24-637 | 09/02/2024 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0
2074 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000016/2024-2025 | 532/JD | 28/06/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 0 | 100
2075 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 3rd Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-A) |  | Junior Engineer | ORD/000096/2023-2024 | 335/JD | 22/05/2023 | 30 | BAJRANG ENTERPRISE | 7.79 | 7.73 | 100
2076 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 5th & 6th tube well site of Nagaisuree Tea Garden Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000108/2024-2025 | 1361/JD | 11/09/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 27.14 | 100
2077 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 4th Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-B) |  | Junior Engineer | ORD/000293/2023-2024 | 1414/JD | 03/10/2023 | 30 | ARUP SARKAR | 7.02 | 6.97 | 100
2078 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000093/2023-2024 | 1052/JD | 24/08/2023 | 0 | Resource Division | 23.38 | 0 | 0
2079 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000079/2023-2024 | 1061/JD | 24/08/2023 | 0 | Resource Division | 1.25 | 0 | 0
2080 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Dakhsin Dangapara Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2022-2023 | 940/JD | 18/04/2022 | 15 | SUKES BASU MAJUMDAR | 1.25 | 1.25 | 100
2081 | Jalpaiguri Division | Jalpaiguri Division | Restoration of damaged DI pipeline at Patkidaha Piped W/S Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000100/2022-2023 | 1312/JD | 15/06/2022 | 15 | M/S SIBU DEY AND CO. | 1.82 | 1.24 | 100
2082 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Pathway, Drain, Providing FHTC, IEP Washout etc. at 3rd TW Site for Patkidaha PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000140/2024-2025 | 1529/JD | 01/10/2024 | 273 | SADHAN KARMAKAR | 15.77 | 0 | 40
2083 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000223/2022-2023 | 1852/JD | 16/09/2022 | 21 | SADHAN KARMAKAR | 2.8 | 2.58 | 1
2084 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Dambari Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000492/2021-2022 | 1935/JD | 29/11/2021 | 15 | KULDIP KAPOOR | 1.47 | 0 | 100
2085 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000493/2021-2022 | 1936/JD | 29/11/2021 | 15 | PRABIR SHOME | 3.75 | 3.63 | 1
2086 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings of distribution pipeline network within Dambari Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri development Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000527/2023-2024 | 1786/JD | 08/12/2023 | 21 | KULDIP KAPOOR | 4.3 | 4.03 | 100
2087 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000090/2023-2024 | 1062/JD | 24/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
2088 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jaldhara / Jalswapna near Dhangkali road, Simul Jhora and allied area for Purba Duramari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-IV) |  | Junior Engineer | ORD/000125/2023-2024 | 803/JD. | 24/07/2023 | 207 | DEEP CONSTRUCTION | 10.93 | 4.19 | 40
2089 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000096/2023-2024 | 1051/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0
2090 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Jhar Salbari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000041/2023-2024 | 139/JD | 28/04/2023 | 795 | ALLIED INSTRUMENTS | 310.52 | 157.24 | 10
2091 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Jhar Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000425/2024-2025 | 2268/JD | 04/12/2024 | 45 | J.M. CONSTRUCTION | 32.13 | 0 | 0
2092 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 3rd Tube well by Reverse Rotary Method of drilling inlucing Construction of Pump House (3.6m x 2.4m) and Laying Rising main for Jhar Salbari PWSS under Dhupguri Block icw Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000607/2024-2025 | 454/JD | 10/03/2025 | 50 | M/S S. G. ENTERPRISE | 17.55 | 0 | 0
2093 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000039/2023-2024 | 1111/JD | 24/08/2023 | 0 | Resource Division | 20.09 | 0 | 0
2094 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000130/2023-2024 | 1844/JD | 15/12/2023 | 0 | Resource Division | 8.57 | 0 | 0
2095 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000070/2023-2024 | 1075/JD | 24/08/2023 | 0 | Resource Division | 1.55 | 0 | 0
2096 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000121/2023-2024 | 1835/JD | 15/12/2023 | 0 | Resource Division | 0.71 | 0 | 0
2097 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of JURANTI T.G. Area piped Water Supply Scheme at Metiali Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000093/2020-2021 | 1277/JD | 18/11/2020 | 90 | NARAYAN CHANDRA SAHA | 43.68 | 0 | 80
2098 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PALASHBARI TEA GARDEN area piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000115/2020-2021 | 1280/JD | 18/11/2020 | 45 | SANKAR DAS | 16.96 | 33.88 | 0
2099 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
2100 | Jalpaiguri Division |  | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Damdim TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000081/2025-2026 | 100/JSSD | 30/05/2025 | 306 | JAYA SARKAR | 6.37 | 0 | 0
2101 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2102 | Jalpaiguri Division |  | Construction of different components of Damdim Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000281/2023-2024 | 1257/JD | 13/09/2023 | 607 | PRASENJIT BASAK | 297.11 | 188.6 | 40
2103 | Jalpaiguri Division |  | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Damdim TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000430/2024-2025 | 2274/JD | 05/12/2024 | 90 | PRASENJIT BASAK | 91.26 | 0 | 0
2104 | Jalpaiguri Division |  | Estimate for Balance work of Water Distribution Network in Damdim Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000801/2023-2024 | 569/JSSD | 05/03/2024 | 30 | PRABIR SHOME | 9.05 | 7.79 | 100
2105 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000051/2024-2025 | 2071/JD | 25/11/2024 | 0 | Resource Division | 38.02 | 0 | 0
2106 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 2017/JD | 09/01/2024 | 0 | Resource Division | 12.02 | 0 | 0
2107 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  |  | ORD/000183/2020-2021 | 1498/JD | 22/12/2020 | 30 | BISWAJIT BHADURI | 17.51 | 21.53 | 1
2108 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Patkidaha and Jakhaikona Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte |  |  | ORD/000326/2020-2021 | 209/JD | 11/02/2021 | 30 | PRABIR SHOME | 21.88 | 0 | 1
2109 | Jalpaiguri Division |  | PROVIDING FHTC FOR PURBA MAGURMARI PWSS |  |  | VCH/000239/2021-2022 | 192/21-22 | 02/08/2021 | 0 | A.P CONSTRUCTION | 25.1 | 0 | 0
2110 | Jalpaiguri Division |  | Supply of fuel (Diesel) for vehicle no. WB-71B-9430 for the month of February-2024 |  |  | BILL/00097/2024-2025 | BP-2024-25-64 | 14/05/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2111 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00130/2024-2025 | BP-2024-25-97 | 22/05/2024 | 0 | FILL & SMILE | 0.36 | 0 | 0
2112 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00131/2024-2025 | BP-2024-25-98 | 22/05/2024 | 0 | FILL & SMILE | 0.28 | 0 | 0
2113 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of March,2024 Vide Vehicle no-WB71B9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00320/2024-2025 | BP-2024-25-182 | 28/06/2024 | 0 | FILL & SMILE | 0.14 | 0 | 0
2114 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of April,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00321/2024-2025 | BP-2024-25-183 | 28/06/2024 | 0 | FILL & SMILE | 0.29 | 0 | 0
2115 | Jalpaiguri Division |  | Supply of Engine oil, Gear Oil and Kool plus Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte |  |  | BILL/00324/2024-2025 | BP-2024-25-181 | 28/06/2024 | 0 | FILL & SMILE | 0.07 | 0 | 0
2116 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00384/2024-2025 | BP-2024-25-269 | 30/07/2024 | 0 | FILL & SMILE | 0.19 | 0 | 0
2117 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month January'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00402/2024-2025 | BP-2024-25-240 | 26/07/2024 | 0 | FILL & SMILE | 0.19 | 0 | 0
2118 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00523/2024-2025 | BP-2024-25-294 | 14/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
2119 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00873/2024-2025 | BP-2024-25-497 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2120 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 76 7338) |  |  | BILL/00929/2024-2025 | BP-2024-25-522 | 29/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2121 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00932/2024-2025 | BP-2024-25-523 | 29/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2122 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00965/2024-2025 | BP-2024-25-532 | 13/12/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
2123 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00966/2024-2025 | BP-2024-25-530 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2124 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 76 7338) |  |  | BILL/00969/2024-2025 | BP-2024-25-529 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2125 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00979/2024-2025 | BP-2024-25-533 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2126 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00980/2024-2025 | BP-2024-25-531 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2127 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of October'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01036/2024-2025 | BP-2024-25-560 | 20/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0
2128 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of November'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01037/2024-2025 | BP-2024-25-561 | 20/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0
2129 | Jalpaiguri Division |  | Bill for supply of fuel (Petrol) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 71 B 9586) |  |  | BILL/01038/2024-2025 | BP-2024-25-559 | 20/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2130 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
2131 | Jalpaiguri Division |  | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) |  |  | ORD/000032/2025-2026 | 819/JD | 30/04/2025 | 61 | PARAMJYOTI ENTERPRISE | 0.8 | 0.4 | 100
2132 | Jalpaiguri Division |  | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/05/2025 to 30/06/2025) |  |  | ORD/000037/2025-2026 | 824/JD | 30/04/2025 | 61 | PARAMJYOTI ENTERPRISE | 0.8 | 0.79 | 100
2133 | Jalpaiguri Division |  | Designing, fabrication and erection of Display Board including vinyl pasting ( 0.9 mtr x 0.6 mtr) for demarcation of land at different PWSS work sites in connection with JJM at MALBAZAR BLOCK in the district of Jalpaiguri, under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000048/2025-2026 | 80/JSSD | 30/05/2025 | 30 | GURUKUL INFOTECH | 3.66 | 0 | 100
2134 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
2135 | Jalpaiguri Division |  | Construction of different components of Oodlabari Tea Garden (Zone-I) PWSS i.e. OHR,TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. of North Bengal Circle-I, PHE Dte. |  |  | ORD/000065/2024-2025 | 936/JD | 07/08/2024 | 300 | SUJIT KUMAR SAHA | 183.05 | 0 | 0
2136 | Jalpaiguri Division |  | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.07.2024 to 31.08.2024)" |  |  | ORD/000091/2024-2025 | 531/JD | 28/06/2024 | 61 | GURUKUL INFOTECH | 3.16 | 3.16 | 100
2137 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission. Period from 01/08/2024 to 31/01/2025. |  |  | ORD/000093/2024-2025 | 125/JSSD | 18/07/2024 | 184 | APIKUL ALI | 0.88 | 1.29 | 0
2138 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) |  |  | ORD/000112/2024-2025 | 142/1/JSSD | 29/07/2024 | 184 | APIKUL ALI | 0.88 | 0.29 | 0
2139 | Jalpaiguri Division |  | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" |  |  | ORD/000122/2025-2026 | 1498/JD | 30/06/2025 | 31 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 100
2140 | Jalpaiguri Division |  | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" |  |  | ORD/000127/2025-2026 | 1503/JD | 30/06/2025 | 31 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 100
2141 | Jalpaiguri Division |  | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali & other Blocks. (For the period from 01/08/2025 to 30/09/2025) |  |  | ORD/000152/2025-2026 | 1733/JD | 31/07/2025 | 61 | DHIRAJ BISWAS | 0.8 | 0 | 50
2142 | Jalpaiguri Division |  | Construction of different components of Oodlabari Tea Garden (Zone-II) PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000158/2023-2024 | 800/JD. | 24/07/2023 | 892 | GHANASHYAM SARKAR | 281.55 | 178.49 | 40
2143 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM From 01.09.2024 to 28.02.2025 (Vehicle No.: - WB 76 9978) |  |  | ORD/000159/2024-2025 | 206/JSSD | 30/08/2024 | 182 | APIKUL ALI | 0.88 | 2.1 | 0
2144 | Jalpaiguri Division |  | Construction approach with paver block inside the premises and land ment at HW site & 2nd TW Site of Oodlabari TG (Z-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000178/2025-2026 | 170/JSSD | 24/07/2025 | 30 | SUBHANKAR DEY | 6.57 | 0 | 0
2145 | Jalpaiguri Division |  | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". |  |  | ORD/000200/2025-2026 | 1999/JD | 25/09/2025 | 61 | DHIRAJ BISWAS | 0.8 | 0 | 0
2146 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000212/2024-2025 | 137/JSSD | 29/07/2024 | 60 | DHIRAJ BISWAS | 0.88 | 0.44 | 50
2147 | Jalpaiguri Division |  | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". |  |  | ORD/000473/2025-2026 | 2423/JD | 21/11/2025 | 30 | DHIRAJ BISWAS | 0.4 | 0 | 0
2148 | Jalpaiguri Division |  | Continuation work of " Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission". Period from 01.02.2025 to 31.07.2025. (Vichle No. WB 78 3405) |  |  | ORD/000696/2024-2025 | 418/JSSD | 28/01/2025 | 181 | APIKUL ALI | 0.88 | 0.69 | 0
2149 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st February 2025 to 31st July 2025) |  |  | ORD/000697/2024-2025 | 417/JSSD | 28/01/2025 | 181 | APIKUL ALI | 0.88 | 0.79 | 0
2150 | Jalpaiguri Division |  | Continuation of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. (Vehicle No-WB 71B 9586) w.e.f. 1.02.2025-31.07.2025. |  |  | ORD/000703/2024-2025 | 434/JSSD | 31/01/2025 | 181 | DHIRAJ BISWAS | 0.88 | 0.15 | 30
2151 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  |  | ORD/000819/2023-2024 | 524/JSSD | 29/01/2024 | 182 | APIKUL ALI | 0.88 | 0.54 | 70
2152 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000820/2023-2024 | 525/JSSD | 29/01/2024 | 182 | DHIRAJ BISWAS | 0.88 | 0.77 | 0
2153 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 2029/JD | 19/11/2024 | 0 | Resource Division | 108.92 | 0 | 0
2154 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1090/JD | 24/08/2023 | 0 | Resource Division | 24.92 | 0 | 0
2155 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 2070/JD | 10/01/2024 | 0 | Resource Division | 17.24 | 0 | 0
Total | [10 empty] | 92969.75 | 36794.05