## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM THUKCHUK KHOLA 20TH MILE AND ITS ADJOINING AREA UNDER SAKIYONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT-KALIMPONG | Assistant Engineer I | Junior Engineer IV | ORD/000003/2022-2023 | 10/NKWSMD | 04/04/2022 | 720 | THUPDEN BHUTIA | 740.54 | 382.53 | 70
2 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer IV | RTOR000088/2022-2023 | 1370/NKWSMD | 22/09/2022 | 0 | Resource Division | 2.96 | 0 | 0
3 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Piped Water Supply Scheme from Kamzer Khola to Lolay Dokan Dara Busty under Lolay G.P. Kalimpaong under Jal Swapno Programme within Kalimpong District | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000049/2021-2022 | 428/NKWSMD | 07/01/2022 | 1000 | DIPESH RAI | 138.85 | 60 | 100
4 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000012/2021-2022 | 646/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.27 | 0 | 0
5 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S. Scheme from Sisney Jhora to North Pedong under Pedong G.P. Block II under Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | ORD/000059/2021-2022 | 450/NKWSMD | 14/01/2022 | 90 | GETEN NAMGYAL BHUTIA | 138.27 | 45.78 | 95
6 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | RTOR000027/2021-2022 | 661/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.21 | 0 | 0
7 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM NIMBONG KHOLA TO SALDARA MAIDAN, DOVAN AND ITS ADJOINING AREA UNDER NIMBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000041/2021-2022 | 420/NKWSMD | 07/01/2022 | 90 | SANTOSH TAMANG | 117.78 | 68.95 | 100
8 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000006/2021-2022 | 640/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.36 | 0 | 0
9 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom 3rd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009298 SM Code-SM/08938 |  | Sub-Assistant Engineer | ORD/000030/2022-2023 | 493/NKWSMD | 24/05/2022 | 60 | MS JAGANNATH PRASAD | 14.04 | 13.51 | 98
10 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000033/2022-2023 | 1260/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.8 | 0 | 0
11 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation & extension for PWS Scheme for Samadhin Forest Villa, Gram Panchyat -Sirkhola Danra Gaon, Block Bijanbari -PullBazar. TSM No. 009470 SM Code-SM/08924 |  | Sub-Assistant Engineer | ORD/000033/2022-2023 | 496/NKWSMD | 24/05/2022 | 60 | SUNIL SHARMA | 13.76 | 0 | 50
12 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000038/2022-2023 | 1265/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.14 | 0 | 0
13 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000126/2022-2023 | 1902/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.14 | 0 | 0
14 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000186/2022-2023 | 2576/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.14 | 0 | 0
15 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer II | Junior Engineer III | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
16 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SURFACE WATER BASED NABGAON KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KALIMPONG WITHIN KALIMPONG DISTRICT UNDER BLOCK UNDER NEORAKHOLA WATER SUPPLY AND MAINTENANCE DIVISION IN KALIMPONG DISTRICT. | Assistant Engineer II | Junior Engineer III | ORD/000122/2024-2025 | 2195/NKWSMD | 29/11/2024 | 60 | RAMESH AGARWAL | 46.56 | 0 | 0
17 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED NABGAON KHASMAHAL PWSS TO ACCOMMODATE FHTC IN KALIMPONG WITHIN KALIMPONG DISTRICT UNDER BLOCK UNDER NEORAKHOLA W/S & Mtc DIVISION IN KALIMPONG DISTRICT. | Assistant Engineer II | Junior Engineer III | ORD/000186/2022-2023 | 961/NKWSMD | 12/07/2022 | 300 | M/S KAMAK ENGINEERS AND CO. | 910.66 | 874.39 | 100
18 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer II | Junior Engineer III | ORD/000269/2023-2024 | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
19 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM DHOBI KHOLA TO LOWER DALEP UNDER BLOCK-II, KALIMPONG, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | ORD/000052/2022-2023 | 534/NKWSMD | 25/05/2022 | 1080 | GETEN NAMGYAL BHUTIA | 199.1 | 114.88 | 100
20 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating Gravity based piped water supply scheme for Chumang Forest under Gitdabling G.P kalimpong Block -II, Dist- Kalimpong in connection with JJM & Jal Swapna under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | Assistant Engineer II | Junior Engineer IV | ORD/000062/2022-2023 | 569/NKWSMD | 26/05/2022 | 90 | SITA SHARMA | 64.02 | 52.65 | 95
21 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source Dalapchand Slip reserve forest village under Dalapchand Gram Panchayat under Kalimpong Block - 1 in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte PART (A) | Assistant Engineer I | Junior Engineer IV | ORD/000070/2022-2023 | 577/NKWSMD | 26/05/2022 | 30 | SONAM TOPGAY BHUTIA | 4.7 | 3.91 | 95
22 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source Dalapchand Slip reserve forest village under Dalapchand Gram Panchayat under Kalimpong Block - 1 in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte (B) | Assistant Engineer I | Junior Engineer IV | ORD/000071/2022-2023 | 579/NKWSMD | 26/05/2022 | 30 | SONAM TOPGAY BHUTIA | 4.79 | 4.79 | 100
23 | Neorakhola W/S & Mtc.Div. |  | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0
24 | Neorakhola W/S & Mtc.Div. |  | Creating gravity based Provision Of Drinking water from spring water source Paren forest village under Paten Godak Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte |  |  | ORD/000064/2022-2023 | 571/NKWSMD | 26/05/2022 | 630 | SACHIN RAI | 47.13 | 0 | 100
25 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | new connection | Assistant Engineer II | Junior Engineer I | BILL/00021/2022-2023 | BP-2022-23-239 | 21/12/2022 | 0 | WBSEDCL | 0.26 | 0 | 0
26 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | new connection | Assistant Engineer II | Junior Engineer I | BILL/00022/2022-2023 | BP-2022-23-238 | 21/12/2022 | 0 | WBSEDCL | 0.26 | 0 | 0
27 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer II | Junior Engineer I | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0
28 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer II | Junior Engineer I | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
29 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR CHUNABHATTI BAZAR D.I.F & LISH FOREST UNDER KALIMPONG-I BLOCK, DISTRICT KALIMPONG, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PHE DTE. | Assistant Engineer II | Junior Engineer I | ORD/000074/2022-2023 | 590/NKWSMD | 26/05/2022 | 1080 | SRINIWAS AGARWAL | 112.55 | 86.71 | 100
30 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Supplementary Piped Water Supply Scheme for Chunabatti Bazar D.I.F & Lish Forest under Kalimpong-I Block District Kalimpong under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | Assistant Engineer II | Junior Engineer I | ORD/000279/2023-2024 | 156/NKWSMD | 30/01/2024 | 180 | SRINIWAS AGARWAL | 20.6 | 0 | 100
31 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer I | RTOR000098/2022-2023 | 1527/NKWSMD | 18/10/2022 | 0 | Resource Division | 1.21 | 0 | 0
32 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer I | RTOR000099/2022-2023 | 1552/NKWSMD | 19/10/2022 | 0 | Resource Division | 0.89 | 0 | 0
33 | Neorakhola W/S & Mtc.Div. |  | Creating gravity based Provision Of Drinking water from spring water source Icha forest village under Sangseer Gram Panchayat under Kalimpong Block - II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte |  |  | ORD/000051/2022-2023 | 533/NKWSMD | 25/05/2022 | 90 | SAINATH CONSTRUCTION COMPANY | 38.89 | 38.03 | 100
34 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at 3rd Mile Simkuna Gram GP - Rungbull, Block - Jorebungalow Sukhia. |  | Sub-Assistant Engineer | ORD/000165/2022-2023 | 941/NKWSMD | 12/07/2022 | 60 | BIMLA GURUNG | 9.29 | 9.11 | 0
35 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000195/2022-2023 | 2619/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.28 | 0 | 0
36 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Pokhriabong Turzum Panchyat - Pokhriabong-II Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000169/2022-2023 | 945/NKWSMD | 12/07/2022 | 60 | MOHAN MUKHIA | 67.07 | 25 | 100
37 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000081/2022-2023 | 1363/NKWSMD | 21/09/2022 | 0 | Resource Division | 3.2 | 0 | 0
38 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000131/2022-2023 | 1907/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.2 | 0 | 0
39 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000191/2022-2023 | 2617/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.2 | 0 | 0
40 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at New Fallodi Tea Garden GP - Soureni I, Block-Mirik. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000166/2022-2023 | 942/ NKWSMD | 12/07/2022 | 60 | ROHIT KUMAR DEWAN | 9.11 | 0 | 90
41 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Lower Mamring Khasmahal in Kurseong Block within Darjeeling District. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | ORD/000043/2023-2024 | 187/NKWSMD | 04/05/2023 | 690 | PREM CHANDRA RAI | 356.26 | 0 | 85
42 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | RTOR000044/2023-2024 | 321/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.69 | 0 | 0
43 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer II | Junior Engineer IV | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
44 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer II | Junior Engineer IV | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
45 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer IV | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
46 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Piped Water Supply Scheme at Nimbong Khasmahal Zone (VII) Under Fourteen Village, Under Kalimpong Block-I & Kalimpong Block -II In the District of Kalimpong Under Neorakhola Water Supply & Maintenance Division Public Health Engineering Directorate under 14 Village. (PART WORK ORDER) | Assistant Engineer II | Junior Engineer IV | ORD/000051/2025-2026 | 762/NKWSMD | 27/05/2025 | 90 | DHANJIT TAMANG | 35.94 | 0 | 100
47 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED NIMBONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE | Assistant Engineer II | Junior Engineer IV | ORD/000188/2022-2023 | 963/NKWSMD | 12/07/2022 | 860 | SRINIWAS AGARWAL | 677.16 | 455.89 | 85
48 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Visit of National Jal Jeevan Mission Team to hills and with an aim to arrange logistical support. | Assistant Engineer II | Junior Engineer IV | ORD/000223/2023-2024 | 1274/NKWSMD | 16/10/2023 | 30 | YAMA CONSTRUCTIONS LLP | 11.22 | 0 | 100
49 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer II | Junior Engineer IV | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
50 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SURFACE WATER BASED NAYA KAMAN PWSS TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE-GTA. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | ORD/000012/2025-2026 | 498/NKWSMD | 09/04/2025 | 60 | ABHINAY CHETTRI | 19.79 | 0 | 0
51 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED NAYA KAMAN PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | ORD/000261/2022-2023 | 1653/NKWSMD | 04/11/2022 | 1062 | ABHINAY CHETTRI | 86.11 | 0 | 80
52 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | RTOR000233/2022-2023 | 2587/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.81 | 0 | 0
53 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED TINDHURIA GOLIAPAKHA PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000220/2022-2023 | 1118/NKWSMD | 05/08/2022 | 270 | PREM CHANDRA RAI | 99.95 | 52.16 | 90
54 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000266/2022-2023 | 2838/NKWSMD | 17/03/2023 | 0 | Resource Division | 0.92 | 0 | 0
55 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Left out scheme for Piped Water Supply Scheme form Bulbuley Jhora to Suruk Block-Kalimpong I, District Kalimpong in connection with Jal Jeevan Mission, under PHED DD-II GTA. | Assistant Engineer-II | Junior Engineer-4 | ORD/000006/2025-2026 | 489/NKWSMD | 09/04/2025 | 60 | M/S. ASHOK KUMAR PERIWAL | 7.69 | 0 | 0
56 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM BULBULEY JHORA TO SURUK UNDER SAMTHAR G.P. BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-II | Junior Engineer-4 | ORD/000073/2022-2023 | 589/NKWSMD | 26/05/2022 | 300 | M/S. ASHOK KUMAR PERIWAL | 277.69 | 252.26 | 100
57 | Neorakhola W/S & Mtc.Div. |  | Creating gravity based Provision Of Drinking water from spring water source Mangber forest village under Teesta Gram Panchayat under Kalimpong Block - I in the District of Kalimpong Under Neorakhola water Supply Division, Kalimpong PHE Dte |  |  | ORD/000069/2022-2023 | 576/NKWSMD | 26/05/2022 | 30 | DORJEE SHERPA | 4.86 | 0 | 100
58 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
59 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
60 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM CHIP CHHIPEY JHORA TO CFC FOREST VILLAGE UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000075/2022-2023 | 591/NKWSMD | 26/05/2022 | 880 | MAHADEO PRASAD AGARWAL & CO | 82.95 | 60.3 | 100
61 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000269/2023-2024 | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
62 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM UTISHEY JHORA TO LOWER YOGDA UNDER SANGSEY G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-2,Junior Engineer-II | ORD/000039/2022-2023 | 521/NKWSMD | 25/05/2022 | 900 | ANAND MANI PRADHAN | 76.69 | 65.18 | 90
63 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM OKHERBOTEY TO DUN UNDER LOLAY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000093/2022-2023 | 616/NKWSMD | 26/05/2022 | 645 | DIL KUMAR RAI | 88.59 | 74.93 | 100
64 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare (Gorabari Margetshop GP) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1,Assistant Engineer4 | Sub-Assistant Engineer | ORD/000112/2022-2023 | 792/NKWSMD | 30/06/2022 | 1360 | SAMIR THAPA | 6.78 | 0 | 70
65 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer4 | Sub-Assistant Engineer | RTOR000048/2022-2023 | 1292/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.31 | 0 | 0
66 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Seepoydhura T.E. Mahanadi GP Block - Kurseong Block. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000133/2022-2023 | 813/NKWSMD | 30/06/2022 | 90 | HIMALI CONSTRUCTION COMPANY | 26.66 | 0 | 100
67 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000064/2022-2023 | 1308/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.51 | 0 | 0
68 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Additional work piped water supply scheme for Pokhriabong Busty No. 5 under Jal Jiwan Mission and Jal Swapno Programme. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000179/2023-2024 | 940/NKWSMD | 16/08/2023 | 510 | RISHI KESH THAKURI | 12.62 | 0 | 100
69 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR POKHRIBONG KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000256/2022-2023 | 1619/NKWSMD | 03/11/2022 | 180 | YAMA CONSTRUCTIONS LLP | 897.18 | 877.56 | 0
70 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Darjeeling Division-I, P.H.E.D., GTA |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000261/2023-2024 | 159/AE-II/NKWSMD | 10/01/2024 | 15 | MADAN KUMAR CHHETRI | 23.94 | 0 | 100
71 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000101/2023-2024 | 964/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.58 | 0 | 0
72 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LONGVIEW PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | ORD/000307/2022-2023 | 2471/NKWSMD | 06/02/2023 | 455 | SHAKTI CONSTRUCTION | 1742.62 | 1212.6 | 100
73 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | RTOR000213/2022-2023 | 2561/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.11 | 0 | 0
74 | Neorakhola W/S & Mtc.Div. | Kurseong Division | FOREST PAYMENT | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | BILL/00760/2023-2024 |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0
75 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest payment | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | BILL/01003/2023-2024 | BP-2023-24-601 | 18/03/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.28 | 0 | 0
76 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SURFACE WATER BASED BARASITTONG KHASMAHAL & SELPU KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000128/2024-2025 | 2205/NKWSMD | 02/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 246.9 | 0 | 80
77 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Barasitting Khasmahal & Selpu Khasmahal PWSS to accommodate FHTC in Kurseong Block within Darjeeling District | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000305/2022-2023 | 2362/NKWSMD | 01/02/2023 | 585 | YAMA CONSTRUCTIONS LLP | 1751.75 | 1690.05 | 100
78 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000150/2022-2023 | 2070/NKWSMD | 05/01/2023 | 0 | Resource Division | 10.71 | 0 | 0
79 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000198/2022-2023 | 2594/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.35 | 0 | 0
80 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | new connection | Assistant Engineer II | Junior Engineer IV | BILL/00010/2023-2024 | BP-2023-24-6 | 25/04/2023 | 0 | WBSEDCL | 0.26 | 0 | 0
81 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply and Maintenance Division Public Health Engineering Directorate for the period from July 2024 to December 2024. | Assistant Engineer II | Junior Engineer IV | ORD/000044/2024-2025 | 1205/NKWSMD | 10/07/2024 | 180 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 60
82 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR RIYONG FOREST & RIYANG RAILWAY STATION WATER SUPPLY SCHEME UNDER TISTA GRAM PANCHAYAT, KALIMPONG BLOCK-I, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG. | Assistant Engineer II | Junior Engineer IV | ORD/000183/2022-2023 | 927/NKWSMD | 12/07/2022 | 180 | GREEN VALLEY CONSTRUCTION | 185.43 | 72.63 | 85
83 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.02.2024 to 31.03.2024. | Assistant Engineer II | Junior Engineer IV | ORD/000319/2023-2024 | 168/NKWSMD | 31/01/2024 | 60 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 99
84 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.04.2024 to 31.05.2024. | Assistant Engineer II | Junior Engineer IV | ORD/000322/2023-2024 | 718/NKWSMD | 29/03/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 100
85 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer IV | RTOR000097/2022-2023 | 1371/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.91 | 0 | 0
86 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0
87 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
88 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR MONGPONG FOREST (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | ORD/000290/2022-2023 | 2147/NKWSMD | 20/01/2023 | 180 | SANTOSH TAMANG | 319.48 | 0 | 80
89 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | RTOR000223/2022-2023 | 2601/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.74 | 0 | 0
90 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | RTOR000236/2022-2023 | 2711/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.74 | 0 | 0
91 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Pokhari Tar with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 2,Assistant Engineer 4,Assistant Engineer2,Assistant Engineer4 |  | ORD/000181/2022-2023 | 957/NKWSMD | 12/07/2022 | 60 | PHURBA RUMBA | 25.37 | 25.18 | 0
92 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer 4,Assistant Engineer2,Assistant Engineer4 |  | RTOR000076/2022-2023 | 1320/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.22 | 0 | 0
93 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer 4,Assistant Engineer2,Assistant Engineer4 |  | RTOR000147/2022-2023 | 2067/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.22 | 0 | 0
94 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM HARESAY JHORA TO LOWER MUNSI DHURA AND KARBUTAR UNDER SANGSAY G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG. | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | ORD/000228/2022-2023 | 1357/NKWSMD | 21/09/2022 | 710 | DINESH SHERPA | 135.69 | 72.04 | 95
95 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Proposed Gravity Based Piped Water Supply Scheme For Lava Forest Under Lava Gitbeong G.P, Block : Kalimpong - II, District:Kalimpong | Assistant Engineer II | Junior Engineer III | ORD/000299/2022-2023 | 2350/NKWSMD | 01/02/2023 | 180 | BHUTIA AND SONS | 93.5 | 0 | 100
96 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer III | RTOR000206/2022-2023 | 2554/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.22 | 0 | 0
97 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Khalingdhura & Vahtukvar TG (Bhuttakheti) GP - Rangit-I, Block - Bijanbari Pullbazar |  | Sub-Assistant Engineer | ORD/000254/2022-2023 | 1617/NKWSMD | 03/11/2022 | 1060 | MANI KUMAR CHHETRI | 48.48 | 0 | 85
98 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme for Samarik Pani Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000265/2022-2023 | 1560/NKWSMD | 21/10/2022 | 965 | SRINIWAS AGARWAL | 1158.25 | 1060.28 | 95
99 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000122/2022-2023 | 1899/NKWSMD | 15/12/2022 | 0 | Resource Division | 5.24 | 0 | 0
100 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000181/2022-2023 | 2609/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.24 | 0 | 0
101 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT.(SM/13955) | Assistant Engineer 4 |  | BILL/00644/2024-2025 | BP-2024-25-450 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.58 | 0 | 0
102 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4 |  | ORD/000294/2022-2023 | 2152/NKWSMD | 20/01/2023 | 1065 | VINAYAK CONSTRUCTION | 229.98 | 0 | 80
103 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 |  | RTOR000207/2022-2023 | 2555/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.48 | 0 | 0
104 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
105 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Water Supply Scheme for Bamon Pokhari Forest Piped Water Supply Scheme in Kurseong Block Under Darjeeling District | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000278/2022-2023 | 1879/NKWSMD | 14/12/2022 | 980 | ROSHAN BISWAKARMA | 211.2 | 0 | 60
106 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000228/2022-2023 | 2583/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.02 | 0 | 0
107 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SAMABIYONG TEA GARDEN UNDER JAL JEEVAN MISSION PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000313/2022-2023 | 2493/NKWSMD | 09/02/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 640.39 | 0 | 90
108 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000205/2022-2023 | 2553/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.36 | 0 | 0
109 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000237/2022-2023 | 2712/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.36 | 0 | 0
110 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme For Ghoom Pahar Forest under JAL JEEWAN MISSION within Jorebunglow Sukhia Pokhri Block,District-Darjeeling Detail - (SW No. : SW/140971/2023) |  | Junior Engineer-IV,Sub-Assistant Engineer | BILL/00392/2024-2025 | BP-2024-25-291 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.45 | 0 | 0
111 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | External Water Supply Works at 10 Bedded Hospital, Ghoom, Darjeeling, GTA |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000241/2023-2024 | 1507/NKWSMD | 06/12/2023 | 210 | DHIRAJ TAMANG | 17.88 | 0 | 100
112 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000273/2023-2024 | 1591/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
113 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000315/2022-2023 | 2519/NKWSMD | 15/02/2023 | 815 | GARGO TRADERS | 1586.68 | 491.23 | 85
114 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
115 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 30/11/2023 (2 Months). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000325/2023-2024 | 1139/NKWSMD | 29/09/2023 | 61 | THE ELECTRIC SPHERE | 0.79 | 0 | 100
116 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000326/2023-2024 | 1457/NKWSMD | 30/11/2023 | 62 | THE ELECTRIC SPHERE | 0.79 | 0 | 100
117 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000209/2022-2023 | 2557/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.43 | 0 | 0
118 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000240/2022-2023 | 2714/NKWSMD | 03/03/2023 | 0 | Resource Division | 8.43 | 0 | 0
119 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
120 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Cost of Construction of 20 nos. of boundary pillers @ Rs. 3866 (Total no of executed is 5 nos including source tanks. Therefore one tank to be needs 4 nos. of pillers in four corners. | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | BILL/00594/2024-2025 |  | 20/11/2024 | 0 | WBSFDA | 0.77 | 0 | 0
121 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
122 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEMLING KHASMAHAL UNDER BLOCK: KALIMPONG - I, DISTRICT:KALIMPONG | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | ORD/000338/2022-2023 | 2735/NKWSMD | 03/03/2023 | 730 | ALLIED INSTRUMENTS | 785.88 | 0 | 100
123 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | RTOR000254/2022-2023 | 2747/NKWSMD | 06/03/2023 | 0 | Resource Division | 4.25 | 0 | 0
124 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR BHALUKHOP KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK-KALIMPONG-I, DISTRICT-KALIMPONG. | Assistant Engineer-II | Junior Engineer-2 | ORD/000054/2023-2024 | 672/NKWSMD | 12/07/2023 | 575 | SRINIWAS AGARWAL | 678.82 | 0 | 70
125 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Leftout Scheme Proposed Gravity Based Piped Water Supply Scheme for Bhalukhop Khasmahal under Kalimpong Block-I District-Kalimpong. | Assistant Engineer-II | Junior Engineer-2 | ORD/000132/2024-2025 | 2231/NKWSMD | 09/12/2024 | 90 | SRINIWAS AGARWAL | 53.33 | 0 | 0
126 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2 | RTOR000080/2023-2024 | 758/NKWSMD | 19/07/2023 | 0 | Resource Division | 7.79 | 0 | 0
127 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR YANGMAKUM KHASMAHAL (PART-2) UNDER BLOCK KALIMPONG-I DISTRICT KALIMPONG. |  |  | ORD/000060/2023-2024 | 414/NKWSMD | 05/06/2023 | 720 | EVERSHINE CONSTRUCTION | 376.97 | 0 | 60
128 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 447/NKWSMD | 07/06/2023 | 0 | Resource Division | 1.23 | 0 | 0
129 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000012/2023-2024 | 101/NKWSMD | 28/04/2023 | 999 | HARI PRASAD CHETTRI | 258.75 | 0 | 70
130 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/16161) |  | Sub-Assistant Engineer | ORD/000150/2024-2025 | 2353/NKWSMD | 19/12/2024 | 180 | HARI PRASAD CHETTRI | 53.29 | 0 | 0
131 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000011/2023-2024 | 208/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.42 | 0 | 0
132 | Neorakhola W/S & Mtc.Div. | Kurseong Division | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAMOHAN UNDER JAL JEEVAN MISSION. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00395/2024-2025 | BP-2024-25-287 | 25/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 2.7 | 0 | 0
133 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED RANGMOHAN PWSS TO ACCOMODATE FHTC IN MIRIK BLOCK | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000330/2022-2023 | 2669/NKWSMD | 01/03/2023 | 670 | MAHENDRA ADHIKARI | 304.14 | 0 | 85
134 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000257/2022-2023 | 2776/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.06 | 0 | 0
135 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
136 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TAKLING KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000031/2025-2026 | 631/NKWSMD | 05/05/2025 | 60 | SRINIWAS AGARWAL | 12.88 | 0 | 0
137 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000036/2023-2024 | 323/NKWSMD | 24/05/2023 | 0 | Resource Division | 2.37 | 0 | 0
138 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional estimate for water supply scheme for Bara Mungwa piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000016/2024-2025 | 980/NKWSMD | 18/06/2024 | 60 | GARGO TRADERS | 12.72 | 0 | 100
139 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BARA MUNGWA PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000064/2023-2024 | 438/NKWSMD | 07/06/2023 | 690 | GARGO TRADERS | 455.08 | 0 | 100
140 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
141 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
142 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Based Water Supply Scheme For Pubong Thulokhola under JAL JEEWAN MISSION under RR Block, District- Darjeeling Detail - (SW No. : SW/140500/2023) |  | Sub-Assistant Engineer | BILL/00394/2024-2025 | BP-2024-25-285 | 25/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.35 | 0 | 0
143 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Water supply Pubong Khasmahal Piped Water Supply Scheme Block Rangli-Rangliot District: Darjeeling. |  | Sub-Assistant Engineer | ORD/000003/2024-2025 | 967/NKWSMD | 14/06/2024 | 60 | RAMESH AGARWAL | 14.12 | 0 | 95
144 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme for Pubong Khasmahal Piped Water Supply Scheme In Rangli Rangliot Block Under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000056/2023-2024 | 411/NKWSMD | 05/06/2023 | 447 | RAMESH AGARWAL | 513.34 | 279.7 | 100
145 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000050/2023-2024 | 445/NKWSMD | 07/06/2023 | 0 | Resource Division | 3.46 | 0 | 0
146 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
147 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR LAMAGAON PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000038/2023-2024 | 221/NKWSMD | 10/05/2023 | 515 | TULSI NIROLA | 679.13 | 175 | 50
148 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Estimate for Construction of platform at Lamagaon Piped Water Supply Scheme under Pulbazar Bijanbari Block, PHED, Darjeeling Division, GTA. |  | Sub-Assistant Engineer | ORD/000099/2024-2025 | 976/NKWSMD | 18/06/2024 | 60 | TULSI NIROLA | 32.99 | 0 | 100
149 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household tap Connection under JJM & JSP Programme for Balance Household at Jhepi & Gurdung in Lamagaon under Darjeeling Division : PHED-GTA. |  | Sub-Assistant Engineer | ORD/000150/2023-2024 | 878/NKWSMD | 03/08/2023 | 350 | NARAYAN SUBBA | 33.7 | 0 | 100
150 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000023/2023-2024 | 242/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.87 | 0 | 0
151 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHEGRA KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-VI | ORD/000034/2023-2024 | 184/NKWSMD | 04/05/2023 | 540 | GREEN VALLEY CONSTRUCTION | 323.03 | 0 | 50
152 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2024 TO 31.10.2024. |  | Junior Engineer-VI | ORD/000103/2024-2025 | 1537/NKWSMD | 30/08/2024 | 61 | QRT SECURITY AND MANPOWER SERVICE | 0.39 | 0 | 80
153 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-VI | RTOR000010/2023-2024 | 202/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.46 | 0 | 0
154 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | KUMAI KHASMAHAL & KUMAI TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME (TSM/015530) | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000336/2022-2023 | 2732/NKWSMD | 03/03/2023 | 365 | RAMESH KUMAR AGARWAL & CO | 637.5 | 250 | 88
155 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000252/2022-2023 | 2748/NKWSMD | 06/03/2023 | 0 | Resource Division | 4.82 | 0 | 0
156 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RELLING PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000061/2023-2024 | 426/NKWSMD | 06/06/2023 | 365 | NIMA SHERPA | 857.26 | 0 | 55
157 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of additional pipeline for Augmentation scheme for Bijanbari Bazar under Darjeeling Division: PHED-GTA. |  | Sub-Assistant Engineer | ORD/000149/2023-2024 | 877/NKWSMD | 03/08/2023 | 60 | TULSI NIROLA | 40.01 | 0 | 50
158 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000051/2023-2024 | 446/NKWSMD | 07/06/2023 | 0 | Resource Division | 4.21 | 0 | 0
159 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW-SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00097/2024-2025 | BP-2024-25-87 | 08/07/2024 | 0 | WBSEDCL | 7.65 | 0 | 0
160 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW-SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000158/2023-2024 | 892/NKWSMD | 07/08/2023 | 545 | M/S BALAJI CONSTRUCTIONS | 1180.95 | 0 | 96
161 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000098/2023-2024 | 974/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.01 | 0 | 0
162 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | HATTA WATER SUPPLY SCHEME FROM PAL MAJUA KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT- DARJEELING. |  | Sub-Assistant Engineer | ORD/000106/2021-2022 | 621/NKWSMD | 21/02/2022 | 150 | HARI PRASAD CHETTRI | 303.02 | 299.91 | 100
163 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | Additional work for Hatta water supply scheme under Darjeeling Pulbazar Block, P.H.E. Dte. Darjeeling Division, G.T.A. |  | Sub-Assistant Engineer | ORD/000245/2023-2024 | 1530/NKWSMD | 14/12/2023 | 270 | MADAN KUMAR CHHETRI | 9.15 | 0 | 100
164 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000029/2021-2022 | 828/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.9 | 0 | 0
165 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000042/2022-2023 | 1266/NKWSMD | 05/09/2022 | 0 | Resource Division | 1.91 | 0 | 0
166 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR PUBUNG PIPED WATER SUPPLY SCHEME UNDER BLOCK- JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING |  |  | ORD/000044/2025-2026 | 630/NKWSMD | 05/05/2025 | 90 | MAHAKAL ENTERPRISES | 28.61 | 0 | 95
167 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR PUBONG PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DISTRICT DARJEELING. |  |  | ORD/000234/2023-2024 | 1372/NKWSMD | 22/11/2023 | 605 | SHAKTI CONSTRUCTION | 1221.09 | 0 | 100
168 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING, KURSEONG DIVISION PHED/GTA. |  |  | ORD/000038/2025-2026 | 653/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 263.39 | 0 | 0
169 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  |  | ORD/000201/2023-2024 | 1099/NKWSMD | 21/09/2023 | 455 | VINAYAK CONSTRUCTION | 3433.58 | 0 | 50
170 | Neorakhola W/S & Mtc.Div. |  | Preparation of draft proposal including preparation of maps in KML file , DGPS Map ,SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 02 (two) number of scheme under JJM (Jal Jeevan Mission). |  |  | ORD/000276/2023-2024 | 1596/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
171 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1172/NKWSMD | 05/10/2023 | 0 | Resource Division | 14.44 | 0 | 0
172 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme from Bhupaley Khola to Paren and and its surrounding area in Paren Godak G.P. Gorubathan Block Kalimpong, under Jal Swapno Programme within Kalimpong District | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000062/2021-2022 | 453/NKWSMD | 14/01/2022 | 90 | RAMESH KUMAR AGARWAL & CO | 105.63 | 58.01 | 85
173 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000022/2021-2022 | 656/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.14 | 0 | 0
174 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PEDONG KHASMAHAL (PART) ,work includes construvtion of Catchment chamber.Desilting tank. RCC Tank (Main Tank and Zonal Tank) ,Laying of gravity main HDPE PIPE, distribution HDPE pipe, and construction of Switch Room , boundary wall under 5 nos of zone inside the pedong Khasmahal under pedong Gram Panchayat , under Kalimpong Block -II , under Kalimpong district. | Assistant Engineer-I | Junior Engineer-4 | ORD/000237/2022-2023 | 1448/NKWSMD | 29/09/2022 | 300 | SRINIWAS AGARWAL | 713.75 | 425.76 | 70
175 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | ELECTRO-MECHANICAL WORK FOR GRAVITY BASED AND PUMPING BASED P.W.S SCHEME FOR PEDONG KHASMAHAL(PART) UNDER PEDONG G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG | Assistant Engineer-I | Junior Engineer-4 | ORD/000271/2022-2023 | 1779/NKWSMD | 28/11/2022 | 60 | THE ELECTRIC SPHERE | 19.28 | 0 | 0
176 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
177 | Neorakhola W/S & Mtc.Div. | Kurseong Division | FOREST PAYMENT | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00760/2023-2024 |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0
178 | Neorakhola W/S & Mtc.Div. | Kurseong Division | FOREST PAYMENT | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00905/2023-2024 | BP-2023-24-497 | 17/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0
179 | Neorakhola W/S & Mtc.Div. | Kurseong Division | LOHAGARH WATER SUPPLY SCHEME FROM MANAY KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DARJEELING | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000069/2021-2022 | 459/NKWSMD | 14/01/2022 | 2404 | SHREE VAISHNO ENTERPRISES | 153.57 | 0 | 80
180 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000003/2021-2022 | 637/NKWSMD | 23/02/2022 | 0 | Resource Division | 2.36 | 0 | 0
181 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S Scheme From Chagey Khola To Katarey Gaon And Its Adjoining Area Under Nimbong G.P. Block-I, Kalimpong Under Jal Jeevan Mission And Jal Swapno Programme. | Assistant Engineer-II | Junior Engineer-4 | ORD/000060/2021-2022 | 451/NKWSMD | 14/01/2022 | 90 | NIM TSHERING LEPCHA | 114.97 | 114.63 | 100
182 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer-II | Junior Engineer-4 | ORD/000150/2022-2023 | 680/NKWSMD | 31/05/2022 | 12 | THE ELECTRIC SPHERE | 4.98 | 2.36 | 95
183 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-4 | RTOR000014/2021-2022 | 648/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.3 | 0 | 0
184 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM KHANI KHOLA TO WEST SAMALBONG UNDER SAMALBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-I | ORD/000044/2021-2022 | 423/NKWSMD | 07/01/2022 | 915 | BASANT PRADHAN | 121.56 | 110.39 | 100
185 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-4,Junior Engineer-I | RTOR000009/2021-2022 | 643/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.31 | 0 | 0
186 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM OKHERBOTEY KHOLA TO UPPER PEDONG AND ITS ADJOINING AREA UNDER PEDONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | ORD/000054/2021-2022 | 445/NKWSMD | 14/01/2022 | 1335 | GETEN NAMGYAL BHUTIA | 230.25 | 119.6 | 85
187 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.05.2023 to 31.10.2023 (Assistant Engineer-I). | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | ORD/000204/2023-2024 | 111/NKWSMD | 28/04/2023 | 184 | DHURBA KUMAR PRADHAN | 1.01 | 0 | 100
188 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.02.2022 to 31.07.2022 (Assistant Engineer-I). | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | ORD/000239/2021-2022 | 578/NKWSMD | 31/01/2022 | 181 | DHURBA KUMAR PRADHAN | 1 | 0 | 100
189 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.08.2022 to 31.01.2023 (Assistant Engineer-I). | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | ORD/000400/2022-2023 | 1094/NKWSMD | 29/07/2022 | 184 | DHURBA KUMAR PRADHAN | 1.01 | 0 | 100
190 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | (Continuation) Hiring of Diesel run Maxi Cab (Non AC) on daily rate basis for official purpose for the Office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate from 01.02.2023 to 30.04.2023 (Assistant Engineer-I). | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | ORD/000401/2022-2023 | 2254/NKWSMD | 31/01/2023 | 89 | DHURBA KUMAR PRADHAN | 0.49 | 0 | 100
191 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-II | RTOR000001/2021-2022 | 630/NKWSMD | 21/02/2022 | 0 | Resource Division | 1.65 | 0 | 0
192 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-III | ORD/000107/2021-2022 | 626/NKWSMD | 21/02/2022 | 150 | GARGO TRADERS | 475.53 | 409.03 | 85
193 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | SUPPLEMENARY ESTIMATE OF PWS SCHEME FOR SAMPHONG KHOLA TO KAGEY BUSTY UNDER KAGEY G.P., BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT-KALIMPONG. | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-III | ORD/000262/2022-2023 | 1654/NKWSMD | 04/11/2022 | 90 | ALLIED INSTRUMENTS | 196.63 | 0 | 50
194 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-III | ORD/000269/2023-2024 | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
195 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-III | RTOR000034/2021-2022 | 837/NKWSMD | 21/03/2022 | 0 | Resource Division | 3.54 | 0 | 0
196 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM BARA SUKEY KHOLA TO CHOTTA MANZING IN POKHRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4 | ORD/000055/2021-2022 | 446/NKWSMD | 14/01/2022 | 1210 | PRAKASH TAMANG | 89.04 | 71.94 | 100
197 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4 | RTOR000028/2021-2022 | 662/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.33 | 0 | 0
198 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM GAIRIBAS KHOLA AND GEET KHOLA TO JHANDI AND ITS 20 ADJOINING VILLAGES COVERING 3 G.P (GORUBATHAN-II, NIM, POKHRAIBONG) IN GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO, DISTRICT-KALIMPONG. | Assistant Engineer I | Junior Engineer III | ORD/000002/2022-2023 | 9/NKWSMD | 04/04/2022 | 900 | M/S. ASHOK KUMAR PERIWAL | 551.65 | 303.78 | 100
199 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.05.2023 TO 31.08.2023. | Assistant Engineer I | Junior Engineer III | ORD/000219/2023-2024 | 126/NKWSMD | 28/04/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 100
200 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.01.2023 TO 30.04.2023. | Assistant Engineer I | Junior Engineer III | ORD/000402/2022-2023 | 2043/NKWSMD | 31/12/2022 | 120 | QRT SECURITY AND MANPOWER SERVICE | 0.85 | 0 | 100
201 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM CHINDAY JHORA TO YONZON, BOMZON, LAMA GAON AND ITS ADJOINING AREAS IN POKRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer I | Junior Engineer III | ORD/000160/2021-2022 | 889/NKWSMD | 28/03/2022 | 900 | MS. SURYA I PVT. LTD COMPANY | 96.11 | 76.6 | 100
202 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer III | RTOR000086/2022-2023 | 1377/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.54 | 0 | 0
203 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Soom 2nd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009296 SM Code-SM/08936 |  | Sub-Assistant Engineer | ORD/000059/2022-2023 | 555/NKWSMD | 26/05/2022 | 60 | NAVRATNA CONSTRUCTION CO | 16.91 | 0 | 100
204 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000034/2022-2023 | 1261/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.84 | 0 | 0
205 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000183/2022-2023 | 2575/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.84 | 0 | 0
206 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under JJM & JSP Programme including extension work for PWS Scheme for Dhupi gare, Bloomfield, Gram Panchyat -Rishihat Bloomfield, Block Bijanbari -PullBazar. TSM No. 009472 SM Code-SM/08930 |  | Sub-Assistant Engineer | ORD/000034/2022-2023 | 497/NKWSMD | 24/05/2022 | 222 | KIRAN SUBBA | 13.14 | 0 | 100
207 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000080/2022-2023 | 1362/NKWSMD | 21/09/2022 | 0 | Resource Division | 0.59 | 0 | 0
208 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000182/2022-2023 | 2614/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.59 | 0 | 0
209 | Neorakhola W/S & Mtc.Div. |  | P.W.S SCHEME FROM JHOLUNG KHOLA TO UPPER,MIDDLE AND LOWER DHAP IN RANGO G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. |  |  | ORD/000112/2021-2022 | 623/NKWSMD | 21/02/2022 | 150 | RAMESH KUMAR AGARWAL & CO | 462.38 | 460.69 | 100
210 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 834/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.93 | 0 | 0
211 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household Tap Connection under JJM & JSP Programme for 8th & 9th M ile , Peshoke Road GP Lamahatta under DARJEELING Division PHED, GTA |  | Sub-Assistant Engineer | VCH/000069/2022-2023 | BP-2022-23-50 | 20/05/2022 | 0 | KIRAN NIROLA | 5.7 | 0 | 0
212 | Neorakhola W/S & Mtc.Div. |  | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. |  |  | ORD/000273/2022-2023 | 1875/NKWSMD | 14/12/2022 | 60 | YAMA CONSTRUCTIONS LLP | 62.3 | 1.74 | 100
213 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000217/2022-2023 | 2597/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.87 | 0 | 0
214 | Neorakhola W/S & Mtc.Div. |  | Pro vidin g Functional household tap connection under JJM & JSP Prog ramm e for Dw s. scheme from Dabaipani Jh ora to Ran gpoo FV Sangsay GP |  |  | VCH/000005/2022-2023 | BP-2022-23-4 | 11/04/2022 | 0 | SANTOSH TAMANG | 13.5 | 0 | 0
215 | Neorakhola W/S & Mtc.Div. |  | Pr vidin g Functional household Tap connect ion und er JJ_M & J$P Programme for Pws scheme fro m Odam Khola to Sa nyasi Dara Nav gaon Pa bringtar GP |  |  | VCH/000013/2022-2023 | BP-2022-23-12 | 11/04/2022 | 0 | CHEMJONG ENTERPRISE | 17.69 | 0 | 0
216 | Neorakhola W/S & Mtc.Div. |  | Pro viding Functiona l household Tap connec tio n under JJM & JSP Pro gramme for Dw sche me from Tarchu Khola to Tarkhola FV 10mile Sangsey GP |  |  | VCH/000050/2022-2023 | BP-2022-23-43 | 06/05/2022 | 0 | ANAND MANI PRADHAN | 12.85 | 0 | 0
217 | Neorakhola W/S & Mtc.Div. |  | Pr oviding Functional household Tap connection under JJM & JSP Programme for Dws scheme from Dhaula Khola to Lava lava GP |  |  | VCH/000054/2022-2023 | BP-2022-23-38 | 06/05/2022 | 0 | NIMA TCHERING BHUTIA | 33.95 | 0 | 0
218 | Neorakhola W/S & Mtc.Div. |  | Pro vidin g Functional household Tap connection under JJM & JSP Programme for Dws scheme from Chamlakha Bhotia to Sangseer Mangal Dhura(Na rak) Sangsey GP |  |  | VCH/000060/2022-2023 | BP-2022-23-47 | 18/05/2022 | 0 | DINESH SHERPA | 13.62 | 0 | 0
219 | Neorakhola W/S & Mtc.Div. |  | Providing Functional household Tap connection under JJM & jSP Programme for Dws sche me from Narag Jhora to Munshi Dhura Gao n Sangsay Gp |  |  | VCH/000061/2022-2023 | BP-2022-23-48 | 18/05/2022 | 0 | DINESH SHERPA | 10.62 | 0 | 0
220 | Neorakhola W/S & Mtc.Div. |  | "Providing house connecti on for Dws scheme from salsalay Jhora to Bhutia Bust y and Lower Meerong(Bull Farm) Pedong gp" |  |  | VCH/000149/2022-2023 | BP-2022-23-103 | 04/08/2022 | 0 | GETEN NAMGYAL BHUTIA | 5.98 | 0 | 0
221 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer I,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | BILL/00174/2023-2024 | BP-2023-24-129 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
222 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TWO NOS OF VILLAGES UNDER BLOCK KURSEONG DISTRICT OF DARJEELING [TSM NO - 10476 / 10473] 1. Septiguri Khelaghar tea garden 2. Pairikumari | Assistant Engineer I,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000084/2022-2023 | 608/NKWSMD | 26/05/2022 | 240 | M/S KAMAK ENGINEERS AND CO. | 199.42 | 65.38 | 100
223 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000158/2022-2023 | 2374/NKWSMD | 03/02/2023 | 0 | Resource Division | 1.8 | 0 | 0
224 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED KANKE BONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | Assistant Engineer II | Junior Engineer IV | ORD/000136/2022-2023 | 816/NKWSMD | 30/06/2022 | 300 | GARGO TRADERS | 448.31 | 288.58 | 70
225 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source Rissium forest village under Santook Gram Panchayat under Kalimpong Block-II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer IV | ORD/000063/2022-2023 | 570/NKWSMD | 26/05/2022 | 90 | DAWA TANGEE SHERPA | 21.57 | 10.13 | 80
226 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM KHANI KHOLA TO CHUKIM UNDER KALIMPONG BLOCK-I, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | ORD/000047/2022-2023 | 529/NKWSMD | 25/05/2022 | 704 | PASANG LAMA | 134.25 | 104.57 | 100
227 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection by Strengthening mainline under Jal Jeevan Mission and Jal Swapno Programme for P.W.S Scheme at Sukhia Bazar, G.P - Sukhia Simana, Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000162/2022-2023 | 938/NKWSMD | 12/07/2022 | 60 | KAMAKHYA ENTERPRISES | 33.83 | 26.35 | 0
228 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000118/2022-2023 | 1895/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.4 | 0 | 0
229 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000177/2022-2023 | 2577/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.4 | 0 | 0
230 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Marybong GP - Lingia Marybong, Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000167/2022-2023 | 943/NKWSMD | 12/07/2022 | 903 | MANI KUMAR CHHETRI | 18.47 | 0 | 100
231 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000041/2022-2023 | 1268/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.48 | 0 | 0
232 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000130/2022-2023 | 1906/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.48 | 0 | 0
233 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000190/2022-2023 | 2590/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.48 | 0 | 0
234 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Bijuwa Gaon Pulundung GP - Pulundung, Block - Jorebungalow Sukhia |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000163/2022-2023 | 939/NKWSMD | 12/07/2022 | 60 | KIRAN NIROLA | 12.21 | 12.09 | 0
235 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000040/2022-2023 | 1267/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.39 | 0 | 0
236 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000132/2022-2023 | 1908/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.39 | 0 | 0
237 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000194/2022-2023 | 2591/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.39 | 0 | 0
238 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme from Reon Khola to Lower Pembling under Nimbong G.P. Block l, Kalimpong under Jal Swapno Programme within Kalimpong District | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | ORD/000052/2021-2022 | 431/NKWSMD | 07/01/2022 | 1250 | SANTOSH TAMANG | 95.07 | 63.07 | 100
239 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | RTOR000023/2021-2022 | 657/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.41 | 0 | 0
240 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
241 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface Water Based Upper Mamring Piped Water Supply Scheme to accmmodate FHTC in Kurseong Block within Darjeeling District under Kurseong Sub-Division, P.H.E.D-G.T.A | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000145/2022-2023 | 836/NKWSMD | 30/06/2022 | 90 | AJAY RAI | 89.52 | 35.7 | 85
242 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000141/2022-2023 | 2061/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.94 | 0 | 0
243 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Piped Water Supply Scheme from Bhadra Jhora to Chotta Suruk. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000143/2022-2023 | 834/NKWSMD | 30/06/2022 | 340 | ANAND KUMAR LAKHOTIA | 70.29 | 62.34 | 100
244 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PWSS Scheme for Lower Dara & Upper Dara and Lower Gari Gaon including construction of Catchment, desilting tank, rising main, distribution network including construction of RCC tank and protection work for the pipe under Kalimpong Block-I under Kalimpong District under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate. | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | ORD/000243/2022-2023 | 1497/NKWSMD | 14/10/2022 | 180 | M/S. ASHOK KUMAR PERIWAL | 306.11 | 160.74 | 100
245 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney (North Shibkhola habitation) under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000147/2022-2023 | 838/NKWSMD | 30/06/2022 | 60 | SONAM LAMA | 9.28 | 0 | 45
246 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000046/2022-2023 | 1290/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.77 | 0 | 0
247 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000117/2022-2023 | 797/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 9.35 | 9.08 | 100
248 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000056/2022-2023 | 1300/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.74 | 0 | 0
249 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Malotar T.E. Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000130/2022-2023 | 810/NKWSMD | 30/06/2022 | 60 | NARESH RAI | 17.84 | 17.75 | 0
250 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000059/2022-2023 | 1303/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.96 | 0 | 0
251 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for Piped Water Supply Scheme at Chandraman Gaon Gram Panchyat Paila Goan S D- 2 Block- Mirik TSM No. 009302 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000125/2022-2023 | 805/NKWSMD | 30/06/2022 | 915 | MS. SURYA I PVT. LTD COMPANY | 18.95 | 0 | 100
252 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000069/2022-2023 | 1313/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.34 | 0 | 0
253 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Krish Kunj: Gram Panchyat Duptin 10, Block - Mirik TSM No. 009481 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000127/2022-2023 | 807/NKWSMD | 30/06/2022 | 60 | BIKASH LAMA | 5.52 | 5.13 | 0
254 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Chotta Tingling: Gram Panchyat- Soureni-II , Block Mirik TSM No. 009480 | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000017/2022-2023 | 787/NKWSMD | 30/06/2022 | 60 | MAHENDRA ADHIKARI | 7.72 | 7.44 | 100
255 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Purba Kabi Gaon under Samthar G.P Kalimpong Block -I, Kalimpong Block-I, under Neorakhola W/S & Mtc Division, PHE Dte. | Assistant Engineer I | Junior Engineer IV | ORD/000135/2022-2023 | 815/NKWSMD | 30/06/2022 | 508 | DIPENDRA CHETTRI | 96.46 | 39.43 | 95
256 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SINGLA PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKHIAPOKRI DISTRICT-DARJEELING. |  | Sub-Assistant Engineer | ORD/000009/2025-2026 | 495/NKWSMD | 09/04/2025 | 180 | DAJUBHAI CONSTRUCTION | 88.19 | 0 | 0
257 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM SINGLA TEA GARDEN UNDER DARJEELING DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, G.T.A |  | Sub-Assistant Engineer | ORD/000226/2022-2023 | 1289/NKWSMD | 08/09/2022 | 995 | VINAYAK CONSTRUCTION | 280.33 | 140 | 100
258 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000109/2022-2023 | 1886/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.6 | 0 | 0
259 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000168/2022-2023 | 2605/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.6 | 0 | 0
260 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Rangaroong T.G water supply scheme Under Jal Jeewan Mission Detail - (SW No. : SW/111753/2022) |  | Sub-Assistant Engineer | BILL/00393/2024-2025 | "BP-2024-25-293 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.38 | 0 | 0
261 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Rageroong Tea Estate for water supply scheme under Darjeeling Division,PHED-GTA. |  | Sub-Assistant Engineer | ORD/000121/2023-2024 | 862/NKWSMD | 31/07/2023 | 790 | KUNCHAN JUNGA ENTERPRISES | 30.33 | 0 | 100
262 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING.(TSM/012508) |  | Sub-Assistant Engineer | ORD/000251/2022-2023 | 1529/NKWSMD | 18/10/2022 | 830 | KUNCHAN JUNGA ENTERPRISES | 272.77 | 212.34 | 100
263 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000115/2022-2023 | 1892/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.64 | 0 | 0
264 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000174/2022-2023 | 2611/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.64 | 0 | 0
265 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0
266 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
267 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000301/2022-2023 | 2352/NKWSMD | 01/02/2023 | 1025 | DIL KUMAR RAI | 326.83 | 0 | 80
268 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000214/2022-2023 | 2596/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.09 | 0 | 0
269 | Neorakhola W/S & Mtc.Div. |  | Creating Gravity Based Water Supply Scheme for Godak Busty, under Gorubathan Block, District:- Kalimpong, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000103/2023-2024 | 825/NKWSMD | 24/07/2023 | 600 | SANJAY BHUJEL | 350.72 | 0 | 85
270 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
271 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Proposed Pumping Based Piped Water Supply Scheme For Git Dubling Khasmahal (Part) (Pochak Habitation) Under Gitdabling G.P, Block : Kalimpong - II. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000272/2022-2023 | 1874/NKWSMD | 14/12/2022 | 240 | YAMA CONSTRUCTIONS LLP | 419.84 | 303.38 | 80
272 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000220/2022-2023 | 2564/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.48 | 0 | 0
273 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCEME FOR TAMSANG TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING (TSM/011759). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000043/2025-2026 | 648/NKWSMD | 05/05/2025 | 60 | DAJUBHAI HARDWARE | 23.02 | 0 | 0
274 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000052/2024-2025 | 386/NKWSMD | 31/05/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 100
275 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme for Tamsang Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000264/2022-2023 | 1562/NKWSMD | 21/10/2022 | 845 | VINAYAK CONSTRUCTION | 736.38 | 691.04 | 100
276 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000120/2022-2023 | 1897/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.25 | 0 | 0
277 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000179/2022-2023 | 2578/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.25 | 0 | 0
278 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM HIGHEST POINT JHORA TO UGEN MINDRU SAMTENLING GUMBA AND ITS ADJOINING AREA UNDER GITKOLBONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | ORD/000063/2021-2022 | 454/NKWSMD | 14/01/2022 | 90 | SANTOSH TAMANG | 192.88 | 171.97 | 100
279 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | RTOR000019/2021-2022 | 653/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.41 | 0 | 0
280 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Base Water Supply Scheme for Senchal-I under Jal Jeevan Mission Detail - (SW No. : SW/145710/2023) |  | Junior Engineer-V | BILL/00389/2024-2025 | BP-2024-25-452 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 5.7 | 0 | 0
281 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Based water supply scheme for Senchal-2 under JAl JEEWAN MISSION. Detail - (SW No. : SW/145709/2023) |  | Junior Engineer-V | BILL/00390/2024-2025 |  | 20/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0
282 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission Detail - (SW No. : SW/145713/2023) WEST BENGAL , DARJEELING |  | Junior Engineer-V | BILL/00391/2024-2025 |  | 20/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0
283 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission |  | Junior Engineer-V | BILL/00645/2024-2025 | BP-2024-25-454 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0
284 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity based water supply scheme for Senchal - 2 under JAL JEEWAN MISSION DETAILS (SW/145709/2023) |  | Junior Engineer-V | BILL/00646/2024-2025 | BP-2024-25-456 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0
285 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-V | ORD/000018/2023-2024 | 118/NKWSMD | 28/04/2023 | 974 | SUMAN THAKURI | 483 | 0 | 70
286 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-V | RTOR000006/2023-2024 | 153/NKWSMD | 03/05/2023 | 0 | Resource Division | 2.42 | 0 | 0
287 | Neorakhola W/S & Mtc.Div. |  | PAYMENT FOR WBSEDCL |  |  | BILL/00758/2023-2024 | BP-2023-24-503 | 17/02/2024 | 0 | WBSEDCL | 5.5 | 0 | 0
288 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR GOPALDHARA TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000040/2023-2024 | 223/NKWSMD | 10/05/2023 | 842 | GREENPRO ENGINEERING | 1051.51 | 300 | 100
289 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 326/NKWSMD | 24/05/2023 | 0 | Resource Division | 4.87 | 0 | 0
290 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
291 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Proposed Creating gravity based piped water supply scheme for Zone 3 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000020/2023-2024 | 102/NKWSMD | 28/04/2023 | 905 | MAHADEO PRASAD AGARWAL & CO | 493.17 | 0 | 60
292 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED Creating gravity based piped water supply scheme for Zone 1 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000302/2022-2023 | 2353/NKWSMD | 01/02/2023 | 970 | TASHI BHUTIA | 364.86 | 0 | 65
293 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED Creating gravity based piped water supply scheme for Zone 2 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000303/2022-2023 | 2354/NKWSMD | 01/02/2023 | 1085 | TASHI BHUTIA | 438.07 | 0 | 60
294 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED Creating gravity based piped water supply scheme for Zone 4 under Today Tangta Khasmahal under Gorubathan Block under Kalimpong District under PHE Dte | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000304/2022-2023 | 2361/NKWSMD | 01/02/2023 | 970 | MAHADEO PRASAD AGARWAL & CO | 298.82 | 0 | 70
295 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | RTOR000022/2023-2024 | 207/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.08 | 0 | 0
296 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | RTOR000215/2022-2023 | 2562/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.9 | 0 | 0
297 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme For Lower Bansbotay & Lower Lingsay Bong Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000057/2023-2024 | 415/NKWSMD | 05/06/2023 | 180 | HARI PRASAD CHETTRI | 287.97 | 0 | 80
298 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000048/2023-2024 | 443/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.38 | 0 | 0
299 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RIMBICK PIPED WATER SUPPLY SCHEME IN DARJEELING-PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000082/2023-2024 | 681/NKWSMD | 12/07/2023 | 781 | NIMA SHERPA | 699.58 | 0 | 90
300 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Piped water supply scheme for Rimbick & Namla under Darjeeling Pulbazar Block, Darjeeling Division, PHED, G.T.A. |  | Sub-Assistant Engineer | ORD/000247/2023-2024 | 87/NKWSMD | 11/01/2024 | 90 | NIMA SHERPA | 27.05 | 0 | 100
301 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000074/2023-2024 | 757/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.77 | 0 | 0
302 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHAINPURAY PIPED WATER SUPPLY SUPPLY IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000081/2023-2024 | 680/NKWSMD | 12/07/2023 | 797 | VAISHNO CONSTRUCTION | 80.25 | 0 | 100
303 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000068/2023-2024 | 755/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.86 | 0 | 0
304 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000025/2023-2024 | 124/NKWSMD | 28/04/2023 | 360 | DENDUP BHUTIA AND COMPANY | 255.41 | 0 | 100
305 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Strengthening of mainline of water supply scheme at Majua (Singhbumdera) under Darjeeling Division, PHED-GTA. |  | Sub-Assistant Engineer | ORD/000118/2023-2024 | 861/NKWSMD | 31/07/2023 | 60 | RISHI KESH THAKURI | 28.53 | 0 | 100
306 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000024/2023-2024 | 243/NKWSMD | 12/05/2023 | 0 | Resource Division | 1.08 | 0 | 0
307 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | ORD/000017/2023-2024 | 117/NKWSMD | 28/04/2023 | 815 | VINAYAK CONSTRUCTION | 1144.27 | 485.23 | 5
308 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | ORD/000036/2025-2026 | 652/NKWSMD | 05/05/2025 | 90 | MAGMA CONSORTIUM | 30.47 | 0 | 0
309 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | RTOR000008/2023-2024 | 155/NKWSMD | 03/05/2023 | 0 | Resource Division | 4.98 | 0 | 0
310 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED NAHORI TEA GARDEN (BALASOM) (PART) PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7 | ORD/000339/2022-2023 | 2736/NKWSMD | 03/03/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 659.52 | 306.11 | 85
311 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7 | RTOR000261/2022-2023 | 2772/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.03 | 0 | 0
312 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-IV | Junior Engineer-2 | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
313 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-IV | Junior Engineer-2 | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
314 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | WATER SUPPLY SCHEME FOR PAGRANG BONG KHASMAHAL PIPED WATER SUPPLY SCHEME GORUBATHAN BLOCK UNDER KALIMPONG DISTRICT. | Assistant Engineer-IV | Junior Engineer-2 | ORD/000085/2023-2024 | 684/NKWSMD | 12/07/2023 | 480 | MS. SURYA I PVT. LTD COMPANY | 388.09 | 80.35 | 80
315 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2 | RTOR000084/2023-2024 | 775/NKWSMD | 19/07/2023 | 0 | Resource Division | 1.15 | 0 | 0
316 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000055/2025-2026 | 820/NKWSMD | 09/06/2025 | 60 | M/S S S CONSTRUCTION | 14.61 | 0 | 0
317 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK KURSEONG UNDER DISTRICT DARJEELING. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000084/2023-2024 | 683/NKWSMD | 12/07/2023 | 420 | M/S S S CONSTRUCTION | 417.8 | 190 | 50
318 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000076/2023-2024 | 764/NKWSMD | 19/07/2023 | 0 | Resource Division | 1.84 | 0 | 0
319 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITBEONG KHASMAHAL UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT : KALIMPONG. | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000037/2023-2024 | 220/NKWSMD | 10/05/2023 | 545 | SRINIWAS AGARWAL | 940.34 | 0 | 85
320 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000030/2023-2024 | 250/NKWSMD | 12/05/2023 | 0 | Resource Division | 2.99 | 0 | 0
321 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA. SCHEME CODE - 15647 TSM/017747 | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00091/2024-2025 | "BP-2024-25-100 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0
322 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000377/2022-2023 | 2873/NKWSMD | 23/03/2023 | 695 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 488.43 | 0 | 52
323 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000269/2022-2023 | 2892/NKWSMD | 29/03/2023 | 0 | Resource Division | 6.38 | 0 | 0
324 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-III | Junior Engineer-3 | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
325 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-III | Junior Engineer-3 | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
326 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR DALAPCHAN KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG-II, DISTRICT:KALIMPONG. | Assistant Engineer-III | Junior Engineer-3 | ORD/000009/2023-2024 | 105/NKWSMD | 28/04/2023 | 240 | M/S. ASHOK KUMAR PERIWAL | 378.99 | 0 | 50
327 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-III | Junior Engineer-3 | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
328 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-3 | RTOR000033/2023-2024 | 277/NKWSMD | 17/05/2023 | 0 | Resource Division | 1.95 | 0 | 0
329 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer II | Junior Engineer III | BILL/00663/2023-2024 | BP-2023-24-421 | 16/01/2024 | 0 | WBSEDCL | 1.83 | 0 | 0
330 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Proposed Pumping Based Piped Water Supply Scheme For Maria Khasmahal (Part) (Upper Rabek) Under Kagay G.P, Block : Kalimpong - II, District:Kalimpong | Assistant Engineer II | Junior Engineer III | ORD/000292/2022-2023 | 2149/NKWSMD | 20/01/2023 | 1080 | THUPDEN BHUTIA | 251.88 | 0 | 100
331 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer III | RTOR000199/2022-2023 | 2549/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.76 | 0 | 0
332 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
333 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED NORTH & SOUTH SHIBKHOLA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000162/2023-2024 | 910/NKWSMD | 11/08/2023 | 570 | AROGYA ENTERPRISES | 1336.08 | 0 | 95
334 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000094/2023-2024 | 958/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.92 | 0 | 0
335 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR ICCHA KHASAMAHAL PIPED WATER SUPPLY SCHEME IN KALIMPONG-I BLOCK, UNDER KALIMPONG DISTRICT. |  |  | ORD/000095/2023-2024 | 722/NKWSMD | 18/07/2023 | 1095 | M/S. ASHOK KUMAR PERIWAL | 920.85 | 0 | 40
336 | Neorakhola W/S & Mtc.Div. |  | Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.02.2024 to 31.03.2024. |  |  | ORD/000318/2023-2024 | 167/NKWSMD | 31/01/2024 | 60 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 99
337 | Neorakhola W/S & Mtc.Div. |  | Continuation Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.04.2024 to 31.05.2024. |  |  | ORD/000321/2023-2024 | 717/NKWSMD | 29/03/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
338 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 771/NKWSMD | 19/07/2023 | 0 | Resource Division | 6.36 | 0 | 0
339 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-RANGLI RANGLIOT DISTRICT-DARJEELING. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000034/2025-2026 | 649/NKWSMD | 05/05/2025 | 180 | MAGMA CONSORTIUM | 74.02 | 0 | 0
340 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROVIDING FHTC UNDER JAL JEEVAN MISSION FOR BALANCE HOUSEHOLD AT 9TH MILE (MAMTA PARK LAMAHATTA) PESHOKE ROAD, LAMAHATTA UNDER DARJEELING DIVISION, P.H.E DEPTT, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000175/2023-2024 | 934/NKWSMD | 16/08/2023 | 60 | PUSHKAR GURUNG | 13.64 | 0 | 100
341 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000185/2023-2024 | 949/NKWSMD | 17/08/2023 | 1095 | VINAYAK CONSTRUCTION | 956.42 | 0 | 80
342 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000097/2023-2024 | 961/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.15 | 0 | 0
343 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection with retrofitting the existing distribution networks under Jal Swapno Programme for PWS scheme at Kataray forest Busty Gram Panchyat-Soureni-II, Block- Mirik TSM No. 009305 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000013/2022-2023 | 785/NKWSMD | 30/06/2022 | 60 | MAHENDRA ADHIKARI | 7.66 | 7.31 | 100
344 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR YANG MAKHUM KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | Assistant Engineer-III | Junior Engineer-3 | ORD/000050/2023-2024 | 359/NKWSMD | 26/05/2023 | 725 | M/S. ASHOK KUMAR PERIWAL | 644.99 | 0 | 61
345 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-3 | RTOR000085/2023-2024 | 777/NKWSMD | 19/07/2023 | 0 | Resource Division | 4.46 | 0 | 0
346 | Neorakhola W/S & Mtc.Div. |  | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical works like Intake, WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for Water Supply Scheme for Darjeeling Pulbazar Pumping - I Spring Water Supply Scheme followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000101/2024-2025 | 1567/NKWSMD | 03/09/2024 | 546 | DARA ENGINEERING & INFRASTRUCTURES PRIVATE LIMITED | 15881.1 | 0 | 5
347 | Neorakhola W/S & Mtc.Div. |  | (Continuation) Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate for the period from January 2025 to June 2025. |  |  | ORD/000217/2024-2025 | 2412/NKWSMD | 31/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 0
348 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 51/NKWSMD | 09/01/2024 | 0 | Resource Division | 22.53 | 0 | 0
349 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
350 | Neorakhola W/S & Mtc.Div. |  | Providing Piped Water Supply Scheme for 16th mile, Pagang Gumba area for left out households under Paiyong G.P under Kalimpong Block-II in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. |  |  | ORD/000008/2024-2025 | 972/NKWSMD | 18/06/2024 | 180 | EVERSHINE CONSTRUCTION | 231.87 | 0 | 0
351 | Neorakhola W/S & Mtc.Div. |  | Providing Piped Water Supply Scheme for Household in 29th mile & Galekhola under Teesta G.P under Kalimpong block-I in the district of Kalimpong connection with JJM, under Neorakhola W/S Mtc Division, P.H.E. Dte, Kalimpong. |  |  | ORD/000009/2024-2025 | 973/NKWSMD | 18/06/2024 | 330 | KAMAKHYA CONSTRUCTION | 172.8 | 0 | 70
352 | Neorakhola W/S & Mtc.Div. |  | Providing Piped Water Supply Scheme for Household in Samalbongay, Suntallay, Lepcha Gaon under Samthar G.P under Kalimpong Block-I in the district of Kalimpong in connection with JJM, Under Neorakhola W/S & Mtc Division, PHE Dte, Kalimpong. |  |  | ORD/000010/2024-2025 | 974/NKWSMD | 18/06/2024 | 360 | YADI LEPCHA | 117.35 | 0 | 80
353 | Neorakhola W/S & Mtc.Div. |  | Additional work for PWS Scheme from Dhobi Khola to Kashyone G.P., Block-II Kalimpong in connection with JJM, under Neorakhola W/S & Mtc Division, PHE, Dte. |  |  | ORD/000018/2024-2025 | 982/NKWSMD | 18/06/2024 | 180 | SAINATH CONSTRUCTION COMPANY | 19.83 | 0 | 100
354 | Neorakhola W/S & Mtc.Div. |  | Providing Piped Water Supply Scheme for Fourteen 14 Nos of Villages (Part) Under Kalimpong Block-I & Kalimpong Block-II in The District of Kalimpong under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Sillary Gaon Leftout. |  |  | ORD/000021/2025-2026 | 598/NKWSMD | 29/04/2025 | 120 | SUNIL BAJLA | 69.71 | 0 | 0
355 | Neorakhola W/S & Mtc.Div. |  | Additional Work for Proposed Surface Water Based Yakprintam Khasmahal (Part) Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kalimpong-I, Block within Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. |  |  | ORD/000061/2024-2025 | 1325/NKWSMD | 29/07/2024 | 180 | RELLI PALA CONSTRUCTION | 20.76 | 0 | 100
356 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in Nimbong Khasmahal (Part) under Nimbong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000100/2023-2024 | 1091/NKWSMD | 21/09/2023 | 230 | SANTOSH TAMANG | 166.29 | 0 | 80
357 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in Gairi Gaon, Barmiak Thingdara, Rubasta & 10th mile Mangchu forest village, Sangsey Khashamal (Part), Sangsey G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000101/2023-2024 | 817/NKWSMD | 24/07/2023 | 720 | M/S. ASHOK KUMAR PERIWAL | 360.01 | 0 | 56
358 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in Nechaligaon, Dangmmu Gaon & Sona Gaon, Paypang khasmahal, l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000102/2023-2024 | 818/NKWSMD | 24/07/2023 | 240 | SITA SHARMA | 142.71 | 0 | 70
359 | Neorakhola W/S & Mtc.Div. |  | Additional work for proposed Gravity based Piped Water Supply Scheme for Char Dhungey & Kela Busty under Pankasari Gram Panchayat under Gorubathan-II, block: Gorubathan, District: Kalimpong. |  |  | ORD/000102/2024-2025 | 1583/NKWSMD | 05/09/2024 | 240 | MS JAGANNATH PRASAD | 71.24 | 0 | 50
360 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in Lower Tunglabong, Lower Suntalay in Pokhrabong khasmahal, (Part), Pokhrabong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000105/2023-2024 | 819/NKWSMD | 24/07/2023 | 120 | PRAKASH TAMANG | 173 | 0 | 85
361 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in Middle & Lower Dabling, Gitdabling Khasmahal l (Part), Gitdabling G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000107/2023-2024 | 821/NKWSMD | 24/07/2023 | 780 | NIM TSHERING LEPCHA | 108.29 | 0 | 100
362 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in, SantookKhasmahal (Part) in Santook G.P, under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000108/2023-2024 | 822/NKWSMD | 24/07/2023 | 720 | JUSTINE BHUTIA | 240.27 | 0 | 70
363 | Neorakhola W/S & Mtc.Div. |  | Providing piped water SupplyScheme for Household in Jhandi Rai Goan, Chhetri Goan, Budrathoki Goan, Upper Suntalay, lower Suntalay, & Tunglabong in Pokhrabong khasmahal (Part), Pokhrabong G.P under Kalimpong Block-II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000109/2023-2024 | 823/NKWSMD | 24/07/2023 | 480 | MS. SURYA I PVT. LTD COMPANY | 282.37 | 0 | 65
364 | Neorakhola W/S & Mtc.Div. |  | Providing Piped Water Supply Scheme for Household in Sillery Gaon, in Paiengaon Forest village (Part), Santook G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000110/2023-2024 | 824/NKWSMD | 24/07/2023 | 720 | JUSTINE BHUTIA | 152.07 | 0 | 45
365 | Neorakhola W/S & Mtc.Div. |  | Providing Piped Water Supply Scheme for Household in Bomfoktar Gaon, Bhujel Goan, Sunwar Goan and sorrounding areas in Samthar G.P under Kalimpong Block -I in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000231/2023-2024 | 1307/NKWSMD | 31/10/2023 | 473 | D AND B GRACE | 39.16 | 0 | 70
366 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in Malthung Gaon, in Samthar G.P under Kalimpong Block -I in the district of Kalimpong in connection with JJM , under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000232/2023-2024 | 1308/NKWSMD | 31/10/2023 | 60 | BINOD CHANDRA BHUJEL | 23.81 | 0 | 95
367 | Neorakhola W/S & Mtc.Div. |  | Providing piped water Supply Scheme for Household in Manay Gumba, Cashier Gaon, MLA Gaon & Karbari Gaon, Sindibong Khasmahal (Part), Sindibong G.P under Kalimpong Block -II in the District of Kalimpong in connection with Jal Jeevan Mission, under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000277/2023-2024 | 119/NKWSMD | 16/01/2024 | 715 | SANTOSH TAMANG | 611.7 | 0 | 60
368 | Neorakhola W/S & Mtc.Div. |  | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
369 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 1284/NKWSMD | 17/10/2023 | 0 | Resource Division | 0.43 | 0 | 0
370 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1286/NKWSMD | 17/10/2023 | 0 | Resource Division | 1.14 | 0 | 0
371 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000123/2023-2024 | 1287/NKWSMD | 17/10/2023 | 0 | Resource Division | 1.9 | 0 | 0
372 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00096/2024-2025 | BP-2024-25-88 | 08/07/2024 | 0 | WBSEDCL | 17.08 | 0 | 0
373 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00280/2024-2025 | BP-2024-25-220 | 28/08/2024 | 0 | WBSEDCL | 5.43 | 0 | 0
374 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK P.H.E-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000030/2025-2026 | 639/NKWSMD | 05/05/2025 | 180 | SHAKTI CONSTRUCTION | 87.36 | 0 | 0
375 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000168/2023-2024 | 921/NKWSMD | 11/08/2023 | 365 | SHAKTI CONSTRUCTION | 1126.3 | 0 | 90
376 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000092/2023-2024 | 971/NKWSMD | 21/08/2023 | 0 | Resource Division | 7.21 | 0 | 0
377 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SINGEL TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000172/2023-2024 | 914/NKWSMD | 11/08/2023 | 815 | M/S. ASHOK KUMAR PERIWAL | 958.42 | 0 | 80
378 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000107/2023-2024 | 968/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.15 | 0 | 0
379 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR MALDIRAM FOREST PART, ST MARYS PART, UPPER LANKU & UPPER ROLAK PART, SIMRING TEA GARDEN PART, CHANDU BUSTY GIDHE PAHAR PART PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000108/2024-2025 | 1746/NKWSMD | 19/09/2024 | 365 | DAJUBHAI CONSTRUCTION | 861.59 | 0 | 80
380 | Neorakhola W/S & Mtc.Div. |  | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
381 | Neorakhola W/S & Mtc.Div. |  | Additional work for water supply scheme for Sangser Khasmahal Piped Water Supply Scheme (Zone - I, II, III, IV, V, VI, VII & VIII) in Kalimpong District. (TSM/013034) under Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate, Kalimpong. |  |  | ORD/000004/2025-2026 | 458/NKWSMD | 03/04/2025 | 180 | MS. SURYA I PVT. LTD COMPANY | 99.75 | 0 | 0
382 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE IV (KHARKA) (TSM/013034) |  |  | ORD/000280/2023-2024 | 255/NKWSMD | 20/02/2024 | 720 | SUNNY CONSTRUCTION | 418.78 | 0 | 40
383 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE I (BHANGAY, SANGSER KHASMAHAL (11,12)) (TSM/013034) |  |  | ORD/000281/2023-2024 | 256/NKWSMD | 20/02/2024 | 1095 | DINESH SHERPA | 732.17 | 0 | 50
384 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSER KHASMAHAL ZONE II (BHANGAY, BIMBONG) (TSM/013034) |  |  | ORD/000282/2023-2024 | 257/NKWSMD | 20/02/2024 | 540 | KHALING ENTERPRISES | 325.39 | 0 | 45
385 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE III (MALI BASSEY, KHAMDONG ) (TSM/013034) |  |  | ORD/000283/2023-2024 | 258/NKWSMD | 20/02/2024 | 360 | SANTOSH TAMANG | 365.87 | 0 | 45
386 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE V (SANGSER KHASMAHAL (11,12) (TSM/013034) |  |  | ORD/000284/2023-2024 | 259/NKWSMD | 20/02/2024 | 550 | DIPESH RAI | 170.34 | 0 | 100
387 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VI (KHARKA) (TSM/013034) |  |  | ORD/000285/2023-2024 | 260/NKWSMD | 20/02/2024 | 720 | SUNNY CONSTRUCTION | 96.88 | 0 | 35
388 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VII (TARA KHOLA FOREST VILLAGE), (TSM/013034) |  |  | ORD/000286/2023-2024 | 261/NKWSMD | 20/02/2024 | 540 | SANTOSH TAMANG | 236.31 | 0 | 50
389 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME TO SANGSEER KHASMAHAL ZONE VIII (MAN KHOLA FOREST VILLAGE), (TSM/013034) |  |  | ORD/000287/2023-2024 | 262/NKWSMD | 20/02/2024 | 540 | MS. SURYA I PVT. LTD COMPANY | 79.99 | 0 | 100
390 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S. Scheme from Uneak Khola to Dabling and its adjoining area under Gitdabling G.P. Block II under Kalimpong under Jal Swapno Programme within Darjeeling | Assistant Engineer-II | Junior Engineer-2 | ORD/000046/2021-2022 | 425/NKWSMD | 07/01/2022 | 90 | YAMA CONSTRUCTIONS LLP | 123.23 | 122.66 | 100
391 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2 | RTOR000024/2021-2022 | 658/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.52 | 0 | 0
392 | Neorakhola W/S & Mtc.Div. |  | P.W.S SCHEME FROM DHATURAY JHORA TO DEWRALI GAON, GUMBA GAON AND BICH GAON AREA UNDER KAFFER-KANKEBONG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. |  |  | ORD/000109/2021-2022 | 625/NKWSMD | 21/02/2022 | 150 | SANTOSH TAMANG | 305.11 | 303.46 | 100
393 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 836/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.76 | 0 | 0
394 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 1369/NKWSMD | 22/09/2022 | 0 | Resource Division | 1.76 | 0 | 0
395 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Retrofitting of Neorakhola piped water supply scheme to Provide Functional House Hold Tap connection to the en-route villages of the scheme in Kalimpong Block I in Kalimpong District under JJM & JAL SWAPNA Programme under Neorakhola Water Supply & Mtc Division under PHE Dte , Kalimpong | Assistant Engineer I | Junior Engineer I,Junior Engineer IV | ORD/000019/2021-2022 | 166/NKWSMD | 06/09/2021 | 30 | SONAM TOPGAY BHUTIA | 48.79 | 48.32 | 90
396 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Retrofitting of Neorakhola piped water supply scheme to Provide Functional House Hold Tap connection to the en-route villages of the scheme in Kalimpong Block I & II in Kalimpong District under JJM & JAL SWAPNA Programme under Neorakhola Water Supply & Mtc Division under PHE Dte , Kalimpong | Assistant Engineer I | Junior Engineer I,Junior Engineer IV | ORD/000020/2021-2022 | 167/NKWSMD | 06/09/2021 | 30 | SONAM TOPGAY BHUTIA | 49.43 | 49.08 | 90
397 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer I | Junior Engineer I,Junior Engineer IV | ORD/000150/2022-2023 | 680/NKWSMD | 31/05/2022 | 12 | THE ELECTRIC SPHERE | 4.98 | 0.79 | 95
398 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1(One) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the S.E. GTA, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer I | Junior Engineer I,Junior Engineer IV | ORD/000152/2022-2023 | 681/NKWSMD | 31/05/2022 | 365 | THE ELECTRIC SPHERE | 2.47 | 0.39 | 45
399 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Details of Additional Pipeline for the work Piped Water Supply Scheme from Nimbong Khola to Upper and Lower Gashok under Nimbong Gram Panchayat. | Assistant Engineer-II | Junior Engineer-4 | ORD/000114/2023-2024 | 852/NKWSMD | 28/07/2023 | 30 | SANTOSH TAMANG | 4.86 | 0 | 0
400 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-4 | RTOR000004/2021-2022 | 638/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.69 | 0 | 0
401 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-I,Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-III | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0
402 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM BURMAIK JHORA TO MAHAKAL DARA AND ADJOINING AREA UNDER BHALUKHOP G.P. BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-I,Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-III | ORD/000218/2022-2023 | 1112/NKWSMD | 05/08/2022 | 1691 | SUNNY CONSTRUCTION | 327.77 | 254.02 | 100
403 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer I | Junior Engineer I | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
404 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating gravity based Provision Of Drinking water from spring water source Paiengoan forest village under Santook Gram Panchayat under Kalimpong Block-II in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte | Assistant Engineer I | Junior Engineer I | ORD/000066/2022-2023 | 573/NKWSMD | 26/05/2022 | 90 | JUSTINE BHUTIA | 47.59 | 0 | 100
405 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer I | RTOR000096/2022-2023 | 1373/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.38 | 0 | 0
406 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SHIVKHOLA FOREST PAGLAJHORA PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000013/2025-2026 | 499/NKWSMD | 09/04/2025 | 90 | SWAD CONSTRUCTION | 55.85 | 0 | 0
407 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED SHIVAKHOLA FOREST PAGLA JHORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITH IN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000284/2022-2023 | 2082/NKWSMD | 10/01/2023 | 180 | SWAD CONSTRUCTION | 168.21 | 43.2 | 100
408 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000225/2022-2023 | 2566/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.65 | 0 | 0
409 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer IV | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
410 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SAMALBONG KHASMAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | Assistant Engineer II | Junior Engineer IV | ORD/000185/2022-2023 | 960/NKWSMD | 12/07/2022 | 300 | M/S. ASHOK KUMAR PERIWAL | 583.66 | 380.26 | 70
411 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MIDDLE MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT, UNDER KURSEONG DIVISION, P.H.E-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000223/2022-2023 | 1121/NKWSMD | 05/08/2022 | 1151 | PREM CHANDRA RAI | 96.87 | 40.81 | 100
412 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000267/2022-2023 | 2839/NKWSMD | 17/03/2023 | 0 | Resource Division | 1.03 | 0 | 0
413 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LOWER MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000090/2022-2023 | 609/NKWSMD | 26/05/2022 | 948 | NAVRATNA CONSTRUCTION CO | 125.37 | 25 | 80
414 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000140/2022-2023 | 2060/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.21 | 0 | 0
415 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR THULUNG GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000088/2022-2023 | 612/NKWSMD | 26/05/2022 | 60 | SEWARO CONSTRUCTION COMPANY | 75.88 | 55.29 | 95
416 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000077/2022-2023 | 1321/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.66 | 0 | 0
417 | Neorakhola W/S & Mtc.Div. |  | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. |  |  | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 100
418 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 2369/NKWSMD | 03/02/2023 | 0 | Resource Division | 2.13 | 0 | 0
419 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | PIPED WATER SUPPLY SCHEME FOR POKHRIABONG BUSTY NO. 5 UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000107/2022-2023 | 628/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 85.92 | 63.03 | 100
420 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000085/2022-2023 | 1367/NKWSMD | 21/09/2022 | 0 | Resource Division | 0.52 | 0 | 0
421 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000107/2022-2023 | 1884/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.52 | 0 | 0
422 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000166/2022-2023 | 2571/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.52 | 0 | 0
423 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM MANDIR KHOLA TO TANYANG UNDER KALIMPONG BLOCK-I, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | ORD/000055/2022-2023 | 551/NKWSMD | 26/05/2022 | 900 | AMIT KUMAR THAPA | 211.87 | 94.07 | 100
424 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURUK KHAS MAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTAHAR G.P, KALIMPONG BLOCK-I, UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE, KALIMPONG | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | BILL/00415/2024-2025 | BP-2024-25-341 | 01/10/2024 | 0 | WBSEDCL | 4.86 | 0 | 0
425 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURUK KHAS MAHAL (THREE HABITATION) PIPED WATER SUPPLY SCHEME (PWSS) UNDER SAMTAHAR G.P, KALIMPONG BLOCK-I, UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE, KALIMPONG | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | ORD/000242/2022-2023 | 1496/NKWSMD | 14/10/2022 | 180 | M/S. ASHOK KUMAR PERIWAL | 369.37 | 204.54 | 100
426 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000121/2022-2023 | 801/NKWSMD | 30/06/2022 | 60 | PRASANT NIROLA | 19.84 | 18.57 | 100
427 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000047/2022-2023 | 1323/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.66 | 0 | 0
428 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Rajbari Tindharay Gayabari-II GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000132/2022-2023 | 812/NKWSMD | 30/06/2022 | 60 | HIMALI CONSTRUCTION COMPANY | 22.13 | 21.45 | 100
429 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000058/2022-2023 | 1302/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.36 | 0 | 0
430 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SPRING SIDI PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Sub-Assistant Engineer | ORD/000053/2025-2026 | 776/NKWSMD | 28/05/2025 | 60 | HIMALAYAN CONSTRUCTION | 11.53 | 0 | 0
431 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Water Supply Scheme for Spring Sidi Tea Garden village Piped Water Supply Scheme In Kurseong Under Darjeeling District. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Sub-Assistant Engineer | ORD/000320/2022-2023 | 2644/NKWSMD | 24/02/2023 | 770 | HIMALAYAN CONSTRUCTION | 217.45 | 0 | 100
432 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Sub-Assistant Engineer | RTOR000134/2023-2024 | 700/NKWSMD | 22/03/2024 | 0 | Resource Division | 1.52 | 0 | 0
433 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer II | Junior Engineer III | BILL/00812/2023-2024 | BP-2023-24-525 | 21/02/2024 | 0 | WBSEDCL | 5.57 | 0 | 0
434 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR SUNTALAY KHASMAHAL UNDER TISTA G.P., KALIMPONG BLOCK-I, UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, P.H.E DIRECTORATE, KALIMPONG. | Assistant Engineer II | Junior Engineer III | ORD/000173/2022-2023 | 949/NKWSMD | 12/07/2022 | 1080 | M/S. ASHOK KUMAR PERIWAL | 86.51 | 17.16 | 56
435 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation of source and provding FHTC at Bijanbari Bazar under Jal Swapno Programme for Balance household at Bijanbari Bazar, Gram panchyat- Bijanabari, Block- Bijanbari-Pullbazaar TSM No. 009478 |  | Sub-Assistant Engineer | ORD/000124/2022-2023 | 804/NKWSMD | 30/06/2022 | 60 | PROSENJIT BASAK | 35.85 | 20.73 | 85
436 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Gothals Siding and Upper Kharay Busty with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000231/2022-2023 | 1445/NKWSMD | 28/09/2022 | 60 | NIPENDRA TAMANG | 31.04 | 0 | 30
437 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme from Thakalay Jhora to Vatty Dara 3rd Mile under Santook G.P. Block ll Kalimpong under Jal Swapno Programme within Kalimpong | Assistant Engineer-IV | Junior Engineer-II | ORD/000051/2021-2022 | 430/NKWSMD | 07/01/2022 | 90 | M/S. ASHOK KUMAR PERIWAL | 134.62 | 102.3 | 100
438 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-II | RTOR000025/2021-2022 | 659/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.77 | 0 | 0
439 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED SURFACE BASED PIPED WATER SUPPLY SCHEME FOR PUDDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | Assistant Engineer-IV | Junior Engineer-4 | ORD/000104/2023-2024 | 826/NKWSMD | 24/07/2023 | 785 | M/S. ASHOK KUMAR PERIWAL | 345.67 | 0 | 90
440 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAKAM FOREST UNDER BLOCK:- GORUBATHAN, DISTRICT:- KALIMPONG, P.H.E Dte. | Assistant Engineer-III | Junior Engineer-4 | ORD/000311/2022-2023 | 2491/NKWSMD | 09/02/2023 | 545 | M/S. ASHOK KUMAR PERIWAL | 874.4 | 0 | 65
441 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4 | RTOR000204/2022-2023 | 2552/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.08 | 0 | 0
442 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4 | RTOR000234/2022-2023 | 2716/NKWSMD | 03/03/2023 | 0 | Resource Division | 4.08 | 0 | 0
443 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000022/2025-2026 | 590/NKWSMD | 29/04/2025 | 90 | M/S BRM DEVELOPERS | 35.22 | 0 | 0
444 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000317/2022-2023 | 2521/NKWSMD | 15/02/2023 | 545 | GARGO TRADERS | 1596.98 | 1248.64 | 85
445 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
446 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000211/2022-2023 | 2559/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.78 | 0 | 0
447 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000241/2022-2023 | 2717/NKWSMD | 03/03/2023 | 0 | Resource Division | 6.78 | 0 | 0
448 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR PUSSINGBONG TEA GARDEN WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000045/2025-2026 | 632/NKWSMD | 05/05/2025 | 180 | VAJRA ENTERPRISES | 45.26 | 0 | 0
449 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR PUSSINGBONG PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000222/2023-2024 | 1279/NKWSMD | 17/10/2023 | 605 | SHAKTI CONSTRUCTION | 1586.35 | 0 | 95
450 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000271/2023-2024 | 1592/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
451 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000086/2023-2024 | 685/NKWSMD | 12/07/2023 | 605 | GARGO TRADERS | 2047.06 | 760.85 | 50
452 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000077/2023-2024 | 765/NKWSMD | 19/07/2023 | 0 | Resource Division | 5.61 | 0 | 0
453 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000269/2023-2024 | 1579/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
454 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | KUMAI FOREST(PART) & KUMAI TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME (TSM/016058) | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000335/2022-2023 | 2731/NKWSMD | 03/03/2023 | 180 | PUSHPA KUMAR RIZAL | 195.31 | 0 | 50
455 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000251/2022-2023 | 2749/NKWSMD | 06/03/2023 | 0 | Resource Division | 0.86 | 0 | 0
456 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0
457 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR KALIJHORA BAZAR PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000026/2023-2024 | 125/NKWSMD | 28/04/2023 | 810 | GREEN VALLEY CONSTRUCTION | 155.27 | 0 | 82
458 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000017/2023-2024 | 213/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.82 | 0 | 0
459 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer I,Assistant Engineer-III | Junior Engineer III,Junior Engineer-3 | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
460 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer I,Assistant Engineer-III | Junior Engineer III,Junior Engineer-3 | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
461 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR YOKPRINTAM KHASMAHAL (PART) UNDER SAMTHAR G.P, BLOCK : KALIMPONG-I, DISTRICT : KALIMPONG. | Assistant Engineer I,Assistant Engineer-III | Junior Engineer III,Junior Engineer-3 | ORD/000007/2023-2024 | 96/NKWSMD | 28/04/2023 | 700 | PASANG LAMA | 156.78 | 0 | 68
462 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission / Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024. | Assistant Engineer I,Assistant Engineer-III | Junior Engineer III,Junior Engineer-3 | ORD/000253/2023-2024 | 1468/NKWSMD | 01/12/2023 | 62 | THE ELECTRIC SPHERE | 0.81 | 0 | 0
463 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I,Assistant Engineer-III | Junior Engineer III,Junior Engineer-3 | ORD/000268/2023-2024 | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
464 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I,Assistant Engineer-III | Junior Engineer III,Junior Engineer-3 | RTOR000034/2023-2024 | 279/NKWSMD | 17/05/2023 | 0 | Resource Division | 0.84 | 0 | 0
465 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
466 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DANGIA PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000033/2023-2024 | 183/NKWSMD | 04/05/2023 | 240 | HARI PRASAD CHETTRI | 480.88 | 100 | 55
467 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission for Balance Household at upper Kolbong in connection with Dangia under Darjeeling Division, P.H.E-G.T.A. |  | Sub-Assistant Engineer | ORD/000246/2023-2024 | 164/NKWSMD | 30/01/2024 | 120 | TULSI NIROLA | 23.65 | 0 | 100
468 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.01.2024 TO 30.04.2024. |  | Sub-Assistant Engineer | ORD/000258/2023-2024 | 1576/NKWSMD | 29/12/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 100
469 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000012/2023-2024 | 209/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.98 | 0 | 0
470 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000130/2023-2024 | 163/NKWSMD | 30/01/2024 | 0 | Resource Division | 0.22 | 0 | 0
471 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0
472 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
473 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG DANSONG FOREST UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT: KALIMPONG | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000329/2022-2023 | 2668/NKWSMD | 28/02/2023 | 720 | DIPESH RAI | 202.99 | 0 | 90
474 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000249/2022-2023 | 2722/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.69 | 0 | 0
475 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000263/2022-2023 | 2777/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.44 | 0 | 0
476 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional estimate for water supply scheme for Pumong Tea Garden piped water supply scheme in rangli-rangliot Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000019/2024-2025 | 983/NKWSMD | 18/06/2024 | 60 | RAMESH AGARWAL | 48.79 | 0 | 100
477 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000083/2023-2024 | 682/NKWSMD | 12/07/2023 | 455 | RAMESH AGARWAL | 701.65 | 248 | 50
478 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000075/2023-2024 | 764/NKWSMD | 19/07/2023 | 0 | Resource Division | 7.38 | 0 | 0
479 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHEWARIBOTAY PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000048/2023-2024 | 261/NKWSMD | 15/05/2023 | 120 | NIMA SHERPA | 132.89 | 100 | 100
480 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024 |  | Sub-Assistant Engineer | ORD/000051/2024-2025 | 385/NKWSMD | 31/05/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
481 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000040/2023-2024 | 327/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.21 | 0 | 0
482 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BARBATIA KHASMAHAL PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000032/2023-2024 | 182/NKWSMD | 04/05/2023 | 330 | MS. SURYA I PVT. LTD COMPANY | 194.76 | 0 | 95
483 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000014/2023-2024 | 211/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.77 | 0 | 0
484 | Neorakhola W/S & Mtc.Div. |  | Surface water based Toryak Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kurseong Block within Darjeeling District |  |  | ORD/000233/2023-2024 | 1328/NKWSMD | 03/11/2023 | 365 | SHAKTI CONSTRUCTION | 1230.38 | 0 | 100
485 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Estimate for Water Supply Scheme for Ginglam & Gielle Tea Garden Piped Water Supply Scheme in Rangli-Rangliot Block under Darjeeling District. (SM/18721) | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000021/2024-2025 | 985/NKWSMD | 18/06/2024 | 60 | RAMESH AGARWAL | 32.15 | 0 | 100
486 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GINGLAM & GIELLE TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000182/2023-2024 | 907/NKWSMD | 11/08/2023 | 415 | RAMESH AGARWAL | 1031.49 | 0 | 100
487 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000103/2023-2024 | 976/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.58 | 0 | 0
488 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | BILL/00490/2023-2024 | BP-2023-24-294 | 02/11/2023 | 0 | WBSEDCL | 2.71 | 0 | 0
489 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | BILL/00491/2023-2024 | BP-2023-24-293 | 02/11/2023 | 0 | WBSEDCL | 5.02 | 0 | 0
490 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 65.83 | 100
491 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
492 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000156/2022-2023 | 2368/NKWSMD | 03/02/2023 | 0 | Resource Division | 6.09 | 0 | 0
493 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Rongchong and Labda under Kurseong Division. Scheme code - 18729 TSM/018103 | Assistant Engineer | Sub-Assistant Engineer | BILL/00090/2024-2025 | BP-2024-25-97 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 5.04 | 0 | 0
494 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR RONGCHONG AND LABDA IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION. PHED/GTA. | Assistant Engineer | Sub-Assistant Engineer | ORD/000040/2025-2026 | 655/NKWSMD | 05/05/2025 | 180 | DAJUBHAI CONSTRUCTION | 107.78 | 0 | 0
495 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RANGCHONG & LABDA PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT | Assistant Engineer | Sub-Assistant Engineer | ORD/000177/2023-2024 | 936/NKWSMD | 16/08/2023 | 605 | VINAYAK CONSTRUCTION | 1186.16 | 0 | 100
496 | Neorakhola W/S & Mtc.Div. |  | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-I) (MARGARET HOPE) |  |  | ORD/000218/2023-2024 | 1207/NKWSMD | 10/10/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1076.48 | 0 | 90
497 | Neorakhola W/S & Mtc.Div. |  | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-II) (MARGARET HOPE) |  |  | ORD/000224/2023-2024 | 1286/NKWSMD | 17/10/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1084.55 | 0 | 80
498 | Neorakhola W/S & Mtc.Div. |  | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-III) |  |  | ORD/000225/2023-2024 | 1287/NKWSMD | 17/10/2023 | 365 | TIKARAM SHARMA | 973.97 | 0 | 85
499 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1285/NKWSMD | 17/10/2023 | 0 | Resource Division | 6.92 | 0 | 0
500 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Home Dara(Tower Dara) Gram Panchyat -Relling , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009299 SM Code-SM/08927 GO2223000391PH |  | Sub-Assistant Engineer | ORD/000025/2022-2023 | 258/NKWSMD | 10/05/2022 | 60 | M/S DIVYA ENTERPRISES | 13.79 | 13.03 | 0
501 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000031/2022-2023 | 1258/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.68 | 0 | 0
502 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Sub-Assistant Engineer | ORD/000052/2025-2026 | 775/NKWSMD | 28/05/2025 | 180 | HIMALAYAN CONSTRUCTION | 122.95 | 0 | 0
503 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Sub-Assistant Engineer | ORD/000113/2023-2024 | 850/NKWSMD | 27/07/2023 | 715 | HIMALAYAN CONSTRUCTION | 921.25 | 0 | 85
504 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Gitangay T.E. Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000123/2022-2023 | 803/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 11.87 | 10.78 | 100
505 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000066/2022-2023 | 1310/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.44 | 0 | 0
506 | Neorakhola W/S & Mtc.Div. |  | Retrofitting for Functional Household Tap Connection (FHTC) of Piped Water Supply Scheme for Pedong Bazar and adjoining areas , Under Neorakhola W/S & Maintenance Division, P.H.Engineering Directorate, District- Kalimpong. |  |  | ORD/000050/2020-2021 | 187/NKWSMD | 12/10/2020 | 60 | LEGDEN PRADHAN | 21.21 | 42.12 | 100
507 | Neorakhola W/S & Mtc.Div. |  | Retrofitting in connection with improvement of piped water supply scheme for Pedong Bazar and adjoining areas under Neorakhola W/S & Mtc. Division, P.H.Engineering Directorate, District- Kalimpong. |  |  | ORD/000051/2020-2021 | 297/NKWSMD | 25/01/2021 | 60 | LEGDEN PRADHAN | 35.86 | 51.65 | 100
508 | Neorakhola W/S & Mtc.Div. |  | Laying of 65mm G.I. pipe from Upper Thukchu khola towards Pipli Dara under piped water supply scheme for Pedong Bazar and Adjoining Area in Dist-Kalimpong, Block-II, under Neorakhola W/S & Mtc Division under PHE Dte Kalimpong. |  |  | ORD/000102/2021-2022 | 269/NKWSMD | 23/11/2021 | 30 | LEGDEN PRADHAN | 4.08 | 3.41 | 100
509 | Neorakhola W/S & Mtc.Div. |  | Laying of 65mm G.I. pipe from Link road towards Pedong Bazar under piped water supply scheme for Pedong Bazar and Adjoining Area in Dist-Kalimpong, Block-II, under Neorakhola W/S & Mtc Division under PHE Dte Kalimpong. |  |  | ORD/000103/2021-2022 | 270/NKWSMD | 23/11/2021 | 30 | LEGDEN PRADHAN | 4.71 | 4.09 | 100
510 | Neorakhola W/S & Mtc.Div. |  | Restoration of pipeline of Piped Water Supply Scheme for Pedong Bazar adjoining areas damaged during this monsoon season. |  |  | ORD/000289/2023-2024 | 303/NKWSMD | 27/02/2024 | 60 | LEGDEN PRADHAN | 8.56 | 0 | 100
511 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM DHOBI KHOLA TO KASHYONE AND ITS ADJOINING AREA UNDER KASHYONE G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer I | Junior Engineer III | ORD/000110/2021-2022 | 627/NKWSMD | 21/02/2022 | 150 | DINESH SHERPA | 302.88 | 225.03 | 80
512 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer III | RTOR000035/2021-2022 | 838/NKWSMD | 21/03/2022 | 0 | Resource Division | 2.76 | 0 | 0
513 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer III | RTOR000092/2022-2023 | 1380/NKWSMD | 22/09/2022 | 0 | Resource Division | 2.76 | 0 | 0
514 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000015/2021-2022 | 649/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.88 | 0 | 0
515 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Piped Water Supply Scheme from Hari Khola to Upper and Lower Gumti in Samsing G.P. Gorubathan Block under Jal Swapno Programme within Kalimpong District | Assistant Engineer-I | Junior Engineer-4 | ORD/000065/2021-2022 | 456/NKWSMD | 14/01/2022 | 1088 | SUBAN RAI | 147.06 | 107.34 | 100
516 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000020/2021-2022 | 654/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.66 | 0 | 0
517 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Replacement of 3 nos Damaged Steel Bridge with 3 nos New Steel bridge of 20m Span in between Ch no 252-253, 35 m span steel bridge in between chain no.04 to 05 and new tubular steel bridge of 20m span at chain no 63, namly (bridge no-64, bridge no-55 and bridge no-57) resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000004/2022-2023 | 103/NKWSMD | 13/04/2022 | 180 | DHURBA KUMAR PRADHAN | 169.64 | 46.27 | 47
518 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Replacement of existing RCC bridge locally known as OLD English Bridge Bridge No 70 with New Steel bridge of 20m Span in between chain no-129 to 130 Span resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte, Kalimpong | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000005/2022-2023 | 104/NKWSMD | 13/04/2022 | 180 | JUSTINE BHUTIA | 50.25 | 0 | 99
519 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Replacement of 4 nos Damaged Steel Bridge with 3 nos New Steel bridge of 15m span in between ch no-119-120 (Bridge no-58), steel bridge 10m span chain no ¿ 144 (Bridge no-69) new tubular Steel bridge of 10m span in between ch no-95 (Bridge no-61) and construction of RCC bridge at ch no-92 in place of bridge no 15(Dhalua to Dolay), including resting over concrete abutment on both the sides including construction of slope protection works for abutments under Neorakhola Water Supply Scheme under PHE Dte. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000006/2022-2023 | 105/NKWSMD | 13/04/2022 | 360 | THUPDEN BHUTIA | 173.91 | 0 | 90
520 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from Off take structure to ch no 50 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000122/2021-2022 | 755/NKWSMD | 28/02/2022 | 180 | DHURBA KUMAR PRADHAN | 71.47 | 0 | 0
521 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 50 to ch no 100 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000123/2021-2022 | 756/NKWSMD | 28/02/2022 | 180 | DAWA LAMA | 71.25 | 0 | 0
522 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 100 to ch no 150 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000124/2021-2022 | 757/NKWSMD | 28/02/2022 | 180 | MOHAN KUMAR RAI | 71.21 | 0 | 0
523 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 150 to ch no 200 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000125/2021-2022 | 758/NKWSMD | 28/02/2022 | 180 | THUPDEN BHUTIA | 73.05 | 0 | 0
524 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 200 to ch no 250 (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000126/2021-2022 | 759/NKWSMD | 28/02/2022 | 180 | KUMAR THAPA | 73.24 | 0 | 0
525 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 250 to thukchu source (1500 meters) between lava to thockchu including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000127/2021-2022 | 760/NKWSMD | 28/02/2022 | 180 | BINOD TAMANG | 73.24 | 0 | 0
526 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from thukchu source to ch no 50 (1500 meters) between thockchu source to Alagarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000128/2021-2022 | 761/NKWSMD | 28/02/2022 | 180 | SONAM TOPGAY BHUTIA | 72.76 | 0 | 0
527 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 50 to 100 (1500 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000129/2021-2022 | 762/NKWSMD | 28/02/2022 | 180 | SANJAY GURUNG | 72.79 | 0 | 0
528 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 100 to 150 (1500 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000130/2021-2022 | 763/NKWSMD | 28/02/2022 | 180 | SONAM TOPGAY BHUTIA | 70.73 | 0 | 0
529 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 150 to 200 (1500 meters) between Thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface), construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000131/2021-2022 | 764/NKWSMD | 28/02/2022 | 180 | HEMANT MOKTAN | 70.72 | 0 | 0
530 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 200 to 262 (1860 meters) between thockchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch under Neorakhola water supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000132/2021-2022 | 765/NKWSMD | 28/02/2022 | 180 | JUSTINE BHUTIA | 91.64 | 0 | 0
531 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of 406.5 mm OD M.S pipe from ch no 262 to Algarah v notch (1890 meters) between thukchu source to Algarah V notch including the carriage of pipe, cleaning & painting of pipe surface (inner & outer surface) , construction of R.C.C thrust block along the stretch of Neorakhola water supply & Mtc Division, PHE Dte Kalimpong | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000133/2021-2022 | 766/NKWSMD | 28/02/2022 | 180 | JUSTINE BHUTIA | 92.4 | 0 | 0
532 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 1 to 9 from Neora source towards Dhalua source (ch no -29 to 219), under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000134/2021-2022 | 767/NKWSMD | 28/02/2022 | 180 | DHURBA KUMAR PRADHAN | 98.22 | 98.1 | 100
533 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 10 to 17 from Dhaula source towards lava (ch no 14 to 104) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000135/2021-2022 | 768/NKWSMD | 28/02/2022 | 180 | BHUTIA AND SONS | 86.41 | 74.84 | 85
534 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 18 to 24 from Dhaula source towards lava (ch no 104 to 194) ,under Neorakhola Water Supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000136/2021-2022 | 769/NKWSMD | 28/02/2022 | 180 | THUPDEN BHUTIA | 86.63 | 57.92 | 80
535 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 25 to 32 from Dhaula source towards lava (ch no 194 to 284) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000137/2021-2022 | 770/NKWSMD | 28/02/2022 | 180 | DAWA LAMA | 86.29 | 64.93 | 80
536 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 33 to 40 from dolay transit camp towards lava (ch no 303 to 395) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000138/2021-2022 | 771/NKWSMD | 28/02/2022 | 180 | JUSTINE BHUTIA | 74.38 | 74.04 | 75
537 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 41 to 47 from dolay transit camp towards lava (ch no 395 to 487) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000139/2021-2022 | 772/NKWSMD | 28/02/2022 | 180 | MOHAN KR. RAI | 74.69 | 56.73 | 80
538 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 48 to 54 from dolay transit camp towards lava (ch no 520 to 612) ,under Neorakhola Water Supply & Mtc Division ,PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000140/2021-2022 | 773/NKWSMD | 28/02/2022 | 180 | KUMAR THAPA | 82.45 | 59.93 | 71
539 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Protection & Restoration work of abutments including repair & maintenance of structural members of steel bridge no 59 & 66 from saddle back towards thokchu (ch no-183 -300) under Neorakhola Water Supply & Mtc Division, PHE Dte Kalimpong. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000141/2021-2022 | 774/NKWSMD | 28/02/2022 | 180 | BINOD TAMANG | 50.59 | 20.31 | 47
540 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000292/2023-2024 | 170/NKWSMD | 31/01/2024 | 180 | SUJIT DEB | 0.99 | 0 | 0
541 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months for G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. | Assistant Engineer I,Assistant Engineer II | Junior Engineer III,Junior Engineer IV | ORD/000330/2023-2024 | 169/NKWSMD | 31/01/2024 | 182 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 0
542 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating Gravity based piped water supply scheme for Bokhim Khasmaha & Paygang Khasmal (PC) under Gitdabling G.P kalimpong Block -II in the district of Kalimpong in connection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | Assistant Engineer I | Junior Engineer IV | ORD/000036/2022-2023 | 501/NKWSMD | 24/05/2022 | 180 | TIKARAM SHARMA | 126.49 | 106.04 | 85
543 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM PARANG KHOLA TO MUNSONG CINCHONA PLANTATION UNDER SANGSEY G.P. BLOCK-II, KALIMPONG, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-3,Junior Engineer-I | ORD/000049/2022-2023 | 531/NKWSMD | 25/05/2022 | 180 | YAMA CONSTRUCTIONS LLP | 222.09 | 218.46 | 100
544 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Balance work for water supply scheme for Murmudang, Kom Busty, & Lower Kolbong under Jal Jeevan Mission & JSP programme under Pull Bijanbari Block PHED-GTA. |  | Sub-Assistant Engineer | ORD/000152/2023-2024 | 880/NKWSMD | 03/08/2023 | 60 | AMRIT KUMAR SUBBA | 96.3 | 68.77 | 50
545 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR MURMIDANG, KOM BUSTY & LOWER KOLBONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  | Sub-Assistant Engineer | ORD/000221/2022-2023 | 1119/NKWSMD | 05/08/2022 | 180 | AMRIT KUMAR SUBBA | 107.92 | 82.37 | 50
546 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000084/2022-2023 | 1366/NKWSMD | 21/09/2022 | 0 | Resource Division | 1.49 | 0 | 0
547 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000106/2022-2023 | 1883/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.49 | 0 | 0
548 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000196/2022-2023 | 2592/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.49 | 0 | 0
549 | Neorakhola W/S & Mtc.Div. |  | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) |  |  | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
550 | Neorakhola W/S & Mtc.Div. |  | Creating gravity based Provision Of Drinking water from spring water source Noam forest village under Pokhriabong Gram Panchayat under Gorubathan Block in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte |  |  | ORD/000061/2022-2023 | 568/NKWSMD | 26/05/2022 | 90 | PRAKASH TAMANG | 44.19 | 37.19 | 100
551 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 1553/NKWSMD | 19/10/2022 | 0 | Resource Division | 0.34 | 0 | 0
552 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Relling-I & II, GP - Rungli, Block - Bijanbari Pullbazar |  | Sub-Assistant Engineer | ORD/000229/2022-2023 | 1443/NKWSMD | 28/09/2022 | 60 | SUMAN PRADHAN | 60.32 | 51.35 | 100
553 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000129/2022-2023 | 1905/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.94 | 0 | 0
554 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000189/2022-2023 | 2589/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.94 | 0 | 0
555 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Bhir Gaon & Dhar Gaon Gram, GP - Majua, Block - Bijanbari Pulbazar. |  | Sub-Assistant Engineer | ORD/000168/2022-2023 | 944/NKWSMD | 12/07/2022 | 120 | SUVASH RAI | 40.11 | 23.18 | 100
556 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000127/2022-2023 | 1903/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.05 | 0 | 0
557 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000187/2022-2023 | 2615/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.05 | 0 | 0
558 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme for balance household at Sumbuck & Kankeybong, GP - Jhepi, Block - Bijanbari Pulbazar. |  | Sub-Assistant Engineer | ORD/000175/2022-2023 | 951/NKWSMD | 12/07/2022 | 180 | SACHIN PRADHAN | 114.36 | 70.29 | 100
559 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000082/2022-2023 | 1364/NKWSMD | 21/09/2022 | 0 | Resource Division | 2.92 | 0 | 0
560 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000128/2022-2023 | 1904/NKWSMD | 15/12/2022 | 0 | Resource Division | 2.92 | 0 | 0
561 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000188/2022-2023 | 2616/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.92 | 0 | 0
562 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  | Sub-Assistant Engineer | BILL/00011/2023-2024 |  | 18/04/2023 | 0 | KASHYAP COMPUTERS | 0.85 | 0 | 0
563 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  | Sub-Assistant Engineer | BILL/00078/2023-2024 | BP-2023-24-40 | 11/05/2023 | 0 | KASHYAP COMPUTERS | 0.34 | 0 | 0
564 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | computer operator payment |  | Sub-Assistant Engineer | BILL/00484/2023-2024 | BP-2023-24-193 | 30/09/2023 | 0 | KASHYAP COMPUTERS | 0.51 | 0 | 0
565 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at 6th Mile Bazar Gram GP - Rampuria & Mineral Spring, Block - Pull Bijanbari |  | Sub-Assistant Engineer | ORD/000171/2022-2023 | 947/NKWSMD | 12/07/2022 | 60 | PUSHKAR GURUNG | 29.98 | 29.89 | 0
566 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
567 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED GHAYABARI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000080/2022-2023 | 605/NKWSMD | 26/05/2022 | 1010 | NAVRATNA CONSTRUCTION CO | 125.67 | 0 | 90
568 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
569 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM AGINGAREY KHOLCHA TO 12,8 NO. & KOTHIDARA UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000044/2022-2023 | 526/NKWSMD | 25/05/2022 | 180 | MAHADEO PRASAD AGARWAL & CO | 97.89 | 62.51 | 100
570 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by Public Health Engineering Directorate by engaging skilled artist and helper artist in different location within 332 Villages in Different Block under Darjeeling and Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate all complete as per direction of EIC. In Each Village in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by Public Health Engineering Directorate, Writing area should be Geo Tagged in appropriate portal as guided by Public Health Engineering Department. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000294/2023-2024 | 179/AE-II/NKWSMD | 05/03/2024 | 31 | RADIANT | 10 | 0 | 40
571 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM KATHAREY KHOLA TO BHUTIA BUSTY UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000058/2022-2023 | 1096/NKWSMD | 01/08/2022 | 910 | BRISTI CONSTRUCTION | 120.9 | 73.25 | 100
572 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation of Lolaygaon Bazar Water Supply Scheme (IMIS Code-0001723403) for providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna & Jal Jevan Mission(JJM) under Neorakhola W/S & Mtc. Division, P.H. E. Dte, Kalimpong | Assistant Engineer I | Junior Engineer III | ORD/000009/2022-2023 | 108/NKWSMD | 13/04/2022 | 450 | SANTOSH TAMANG | 95.54 | 49.43 | 100
573 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00492/2023-2024 | BP-2023-24-291 | 02/11/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
574 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00493/2023-2024 | BP-2023-24-292 | 02/11/2023 | 0 | WBSEDCL | 0.46 | 0 | 0
575 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00706/2023-2024 | BP-2023-24-475 | 28/01/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
576 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00707/2023-2024 | BP-2023-24-476 | 28/01/2024 | 0 | WBSEDCL | 5.49 | 0 | 0
577 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 45.54 | 100
578 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
579 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000010/2024-2025 | 1781/NKWSMD | 23/09/2024 | 0 | Resource Division | 0.54 | 0 | 0
580 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000155/2022-2023 | 2373/NKWSMD | 03/02/2023 | 0 | Resource Division | 4.21 | 0 | 0
581 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram TE (Dilaram Bazar habitation) under Kurseong Sub-Division PHED, GTA. |  |  | ORD/000111/2022-2023 | 791/NKWSMD | 30/06/2022 | 60 | JIWAN TAMANG | 5.96 | 5.94 | 0
582 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 1294/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.4 | 0 | 0
583 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | ORD/000113/2022-2023 | 793/NKWSMD | 30/06/2022 | 60 | NAVRATNA CONSTRUCTION CO | 14.52 | 12.11 | 98
584 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | RTOR000052/2022-2023 | 1296/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.19 | 0 | 0
585 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer 4,Assistant Engineer4 |  | ORD/000122/2022-2023 | 802/NKWSMD | 30/06/2022 | 60 | PHURBA RUMBA | 20.05 | 18.75 | 100
586 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer 4,Assistant Engineer4 |  | RTOR000054/2022-2023 | 1298/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.66 | 0 | 0
587 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under Jal Jeevan Mission & JSP Programme including Retrofitting work for PWS scheme for Cricket Bazar Tindharay Mahanadi GP Block - Kurseong Block. | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000115/2022-2023 | 795/NKWSMD | 30/06/2022 | 610 | BIKASH TAMANG | 12.59 | 0 | 1
588 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000057/2022-2023 | 1301/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.83 | 0 | 0
589 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Additional FHTC estimate for the work Piped Water Supply Scheme from Khani Khola to West Samalbong SM Code 09669 / IMIS ID 40012989 | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000217/2023-2024 | 1282/NKWSMD | 17/10/2023 | 30 | BASANT PRADHAN | 4.64 | 0 | 0
590 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | WATER SUPPLY SCHEME FOR SINGI KHASAMAHAL PIPED WATER SUPPLY SCHEME IN KALIMPONG-I BLOCK UNDER KALIMPONG DISTRICT. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000258/2022-2023 | 1621/NKWSMD | 03/11/2022 | 820 | SRINIWAS AGARWAL | 657.41 | 251.17 | 95
591 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Bagmara Mahanadi GP Block - Kurseong Block. | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000216/2022-2023 | 1110/NKWSMD | 05/08/2022 | 60 | MS. SURYA I PVT. LTD COMPANY | 9.17 | 9.16 | 0
592 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000070/2022-2023 | 1314/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.36 | 0 | 0
593 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for 14 Mile Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000120/2022-2023 | 800/NKWSMD | 30/06/2022 | 60 | PREM KUMAR PRADHAN | 10.87 | 10.55 | 100
594 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000065/2022-2023 | 1309/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.63 | 0 | 0
595 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000252/2022-2023 | 1530/NKWSMD | 18/10/2022 | 840 | VINAYAK CONSTRUCTION | 318.85 | 251.07 | 100
596 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000121/2022-2023 | 1898/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.32 | 0 | 0
597 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000180/2022-2023 | 2574/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.32 | 0 | 0
598 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at 3 Nos Montiviote TE with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer4,Sub-Assistant Engineer | ORD/000211/2022-2023 | 984/NKWSMD | 12/07/2022 | 60 | PRASANT NIROLA | 17.52 | 15.8 | 100
599 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer4,Sub-Assistant Engineer | RTOR000057/2023-2024 | 530/NKWSMD | 13/06/2023 | 0 | Resource Division | 2.05 | 0 | 0
600 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer4,Sub-Assistant Engineer | RTOR000149/2022-2023 | 2069/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.22 | 0 | 0
601 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | permission fro laying 80mm dia GI Pipeline along the hill side of Darjeeling Ghoom Bhanjang Bijanbari Road |  | Junior Engineer-IV,Sub-Assistant Engineer | BILL/00206/2022-2023 | BP-2022-23-426 | 30/03/2023 | 0 | NEORAKHOLA W/S & MTC. DIV. | 10.35 | 0 | 0
602 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Proposed Gravity Based Water Supply Scheme for Mariabong Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000236/2022-2023 | 1451/NKWSMD | 29/09/2022 | 1000 | GARGO TRADERS | 973.62 | 922.49 | 100
603 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000114/2022-2023 | 1891/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.68 | 0 | 0
604 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000173/2022-2023 | 2609/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.68 | 0 | 0
605 | Neorakhola W/S & Mtc.Div. |  | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
606 | Neorakhola W/S & Mtc.Div. |  | Piped Water Supply Scheme For Upper Fagu Tea Garden Under Jal Jeevan Mission. |  |  | ORD/000099/2023-2024 | 723/NKWSMD | 18/07/2023 | 715 | M/S R.S. CONSTRUCTION | 801.86 | 0 | 65
607 | Neorakhola W/S & Mtc.Div. |  | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). |  |  | ORD/000268/2023-2024 | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
608 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 814/NKWSMD | 24/07/2023 | 0 | Resource Division | 5.69 | 0 | 0
609 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000291/2022-2023 | 2148/NKWSMD | 20/01/2023 | 240 | M/S. ASHOK KUMAR PERIWAL | 390.86 | 0 | 50
610 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000202/2022-2023 | 2551/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.08 | 0 | 0
611 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000277/2022-2023 | 2004/NKWSMD | 23/12/2022 | 912 | ABHINAY CHETTRI | 306.39 | 72.02 | 100
612 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000229/2022-2023 | 2584/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.05 | 0 | 0
613 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST UNDER KURSEONG DIVISION. SCHEME CODE - 12983 TSM/012820 | Assistant Engineer 4 |  | BILL/00089/2024-2025 | BP-2024-25-96 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 8.41 | 0 | 0
614 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Continuation Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 | Assistant Engineer 4 |  | ORD/000252/2023-2024 | 1469/NKWSMD | 01/12/2023 | 62 | THE ELECTRIC SPHERE | 0.41 | 0 | 0
615 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4 |  | ORD/000308/2022-2023 | 2472/NKWSMD | 06/02/2023 | 1005 | M/S. ASHOK KUMAR PERIWAL | 1198.11 | 223.86 | 85
616 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 |  | RTOR000061/2023-2024 | 571/NKWSMD | 22/06/2023 | 0 | Resource Division | 7.02 | 0 | 0
617 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 |  | RTOR000203/2022-2023 | 2595/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.26 | 0 | 0
618 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LAVA FOREST (PART) UNDER LAVA GITBEONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | Assistant Engineer I | Junior Engineer IV | ORD/000309/2022-2023 | 2489/NKWSMD | 09/02/2023 | 960 | THUPDEN BHUTIA | 194.1 | 0 | 90
619 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer IV | RTOR000201/2022-2023 | 2550/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.99 | 0 | 0
620 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer IV | RTOR000235/2022-2023 | 2724/NKWSMD | 03/03/2023 | 0 | Resource Division | 0.99 | 0 | 0
621 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KALIMPONG G.P BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | Assistant Engineer-III | Junior Engineer-I | ORD/000053/2023-2024 | 360/NKWSMD | 26/05/2023 | 665 | RAMESH KUMAR AGARWAL & CO | 848.05 | 0 | 80
622 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-I | RTOR000046/2023-2024 | 366/NKWSMD | 29/05/2023 | 0 | Resource Division | 7.2 | 0 | 0
623 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | TAKDAH FOREST WATER SUPPLY SCHEME UNDER JAL JEEWAN MISSION |  | Sub-Assistant Engineer | BILL/00388/2024-2025 | BP-2024-25-283 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 7 | 0 | 0
624 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TUKDAH FOREST PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000030/2023-2024 | 108/NKWSMD | 28/04/2023 | 1347 | RAMESH AGARWAL | 108.34 | 0 | 95
625 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000025/2023-2024 | 244/NKWSMD | 12/05/2023 | 0 | Resource Division | 0.77 | 0 | 0
626 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR KOLBONG KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK : RANGLI RANGLIOT, DISTRICT: DARJEELING. |  | Sub-Assistant Engineer | ORD/000045/2023-2024 | 189/NKWSMD | 04/05/2023 | 772 | SRINIWAS AGARWAL | 212.21 | 75 | 100
627 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000037/2023-2024 | 324/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.88 | 0 | 0
628 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme For Upper & Lower Sumbuk Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000059/2023-2024 | 418/NKWSMD | 05/06/2023 | 360 | HARI PRASAD CHETTRI | 278.38 | 100 | 100
629 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000049/2023-2024 | 444/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.74 | 0 | 0
630 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAHARANI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000047/2025-2026 | 636/NKWSMD | 05/05/2025 | 120 | SURAJMULL PRABHUDAYAL | 16.26 | 0 | 100
631 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MAHARANI TEA GARDEN PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000340/2022-2023 | 2737/NKWSMD | 03/03/2023 | 805 | SRINIWAS AGARWAL | 440.47 | 103 | 65
632 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | RTOR000262/2022-2023 | 2773/NKWSMD | 10/03/2023 | 0 | Resource Division | 3.01 | 0 | 0
633 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR LINGSAYKHA KHASMAHAL UNDER LINGSEKHA G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | Assistant Engineer-I | Junior Engineer-3 | ORD/000051/2023-2024 | 417/NKWSMD | 05/06/2023 | 725 | THUPDEN BHUTIA | 875.98 | 0 | 60
634 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-3 | RTOR000055/2023-2024 | 449/NKWSMD | 07/06/2023 | 0 | Resource Division | 3.33 | 0 | 0
635 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
636 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BIJANBARI PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000006/2023-2024 | 89/NKWSMD | 27/04/2023 | 817 | VAISHNO CONSTRUCTION | 339.14 | 0 | 90
637 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000038/2023-2024 | 325/NKWSMD | 24/05/2023 | 0 | Resource Division | 1.84 | 0 | 0
638 | Neorakhola W/S & Mtc.Div. |  | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0
639 | Neorakhola W/S & Mtc.Div. |  | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00513/2023-2024 | BP-2023-24-319 | 17/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 4.74 | 0 | 0
640 | Neorakhola W/S & Mtc.Div. |  | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR MANGWA FOREST (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG-I, DISTRICT : KALIMPONG. |  |  | ORD/000080/2023-2024 | 679/NKWSMD | 12/07/2023 | 890 | DIPENDRA CHETTRI | 52.63 | 0 | 40
641 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 769/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.25 | 0 | 0
642 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR LADAM KHAS MAHAL UNDER KAGAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000323/2022-2023 | 2653/NKWSMD | 28/02/2023 | 180 | MS. SURYA I PVT. LTD COMPANY | 283.56 | 0 | 70
643 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000244/2022-2023 | 2719/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.04 | 0 | 0
644 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SINGALILA FOREST PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000003/2023-2024 | 87/NKWSMD | 27/04/2023 | 858 | NIMA SHERPA | 364.9 | 240 | 100
645 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SINGALILA UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PUL BIJANBARI BLOCK. |  | Sub-Assistant Engineer | ORD/000158/2024-2025 | 2368/NKWSMD | 20/12/2024 | 90 | RINZI SHERPA | 29 | 0 | 0
646 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000003/2023-2024 | 151/NKWSMD | 03/05/2023 | 0 | Resource Division | 0.47 | 0 | 0
647 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000015/2023-2024 | 212/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.47 | 0 | 0
648 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Proposed Gravity Based and Pumping Based PWSS for Palla Khasmahal (Mulpala part) under Lolay G.P Block: Kalimpong - II,District: Kalimpong. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00228/2024-2025 | "BP-2024-25-236 | 03/09/2024 | 0 | WBSEDCL | 11.27 | 0 | 0
649 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Darjeeling Division-II, P.H.E.D., GTA. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000260/2023-2024 | 158/AE-II/NKWSMD | 10/01/2024 | 195 | SANTOSH TAMANG | 18.72 | 0 | 100
650 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PALLA KHASMAHAL(MULPALA PART) UNDER LOLAY G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000328/2022-2023 | 2662/NKWSMD | 28/02/2023 | 240 | SRINIWAS AGARWAL | 197.88 | 0 | 50
651 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000248/2022-2023 | 2721/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.05 | 0 | 0
652 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
653 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme For St Marys and Geothals | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00647/2024-2025 | BP-2024-25-458 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 2.52 | 0 | 0
654 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED ST. MARYS AND GOETHALS PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000331/2022-2023 | 2670/NKWSMD | 01/03/2023 | 180 | SITA SHARMA | 300.54 | 0 | 60
655 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000258/2022-2023 | 2770/NKWSMD | 10/03/2023 | 0 | Resource Division | 4.4 | 0 | 0
656 | Neorakhola W/S & Mtc.Div. |  | DALINGKOT FOREST PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG. |  |  | ORD/000250/2023-2024 | 4/NKWSMD | 03/01/2024 | 365 | THUPDEN BHUTIA | 1388.85 | 0 | 15
657 | Neorakhola W/S & Mtc.Div. |  | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Neorakhola W/S & Mtc. Division, P.H.E. Dte. |  |  | ORD/000259/2023-2024 | 157/AE-II/NKWSMD | 10/01/2024 | 15 | SANTOSH TAMANG | 14.76 | 0 | 100
658 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000125/2023-2024 | 41/NKWSMD | 09/01/2024 | 0 | Resource Division | 4.82 | 0 | 0
659 | Neorakhola W/S & Mtc.Div. |  | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. |  |  | ORD/000014/2024-2025 | 979/NKWSMD | 18/06/2024 | 60 | SUNRISE ENTERPRISES | 24.35 | 0 | 100
660 | Neorakhola W/S & Mtc.Div. |  | Augmentation for ground water Reservoir of capacity 20 ML at Sepoydhura (Near Woodcut) Kurseong under PHED, Kusseong Sub- Division, GTA. |  |  | ORD/000056/2025-2026 | 824/NKWSMD | 09/06/2025 | 365 | INTERIOR'S NEST | 411.05 | 0 | 0
661 | Neorakhola W/S & Mtc.Div. |  | Ground Water Reservoir of 20 ML At Sepoydhura Near Woodcut Under Kurseong Division, P.H.E.D-GTA. |  |  | ORD/000227/2023-2024 | 1288/NKWSMD | 17/10/2023 | 928 | INTERIOR'S NEST | 2445.49 | 0 | 35
662 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1173/NKWSMD | 05/10/2023 | 0 | Resource Division | 11.65 | 0 | 0
663 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
664 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR HUM TUKDAH KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000076/2023-2024 | 674/NKWSMD | 12/07/2023 | 515 | RAMESH AGARWAL | 1210.81 | 0 | 100
665 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000275/2023-2024 | 1595/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
666 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000064/2023-2024 | 760/NKWSMD | 19/07/2023 | 0 | Resource Division | 9.95 | 0 | 0
667 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM KAMZER KHOLA TO LOWER LOLAY UNDER KALIMPONG BLOCK-I UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000056/2022-2023 | 552/NKWSMD | 26/05/2022 | 810 | SHASHI LEPCHA | 174.61 | 105.83 | 100
668 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | WATER SUPPLY SCHEME FOR LOLAY KHASMAHAL (Part-II) PIPED WATER SUPPLY SCHEME IN KALIMPONG-II BLOCK UNDER KALIMPONG DISTRICT. | Assistant Engineer-II | Junior Engineer-4 | ORD/000157/2023-2024 | 891/NKWSMD | 07/08/2023 | 635 | SRINIWAS AGARWAL | 1057.74 | 0 | 100
669 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Piped Water Supply Scheme from Kaijarbotay Jhora to Lower Poshyer Bhasmey under Tashiding G.P. Block l, Kalimpong under Jal Swapno Programme Kalimpong District | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000061/2021-2022 | 452/NKWSMD | 14/01/2022 | 90 | SUDEN TAMANG | 85.69 | 68.54 | 90
670 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000026/2021-2022 | 660/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.33 | 0 | 0
671 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | BILL/00011/2023-2024 |  | 18/04/2023 | 0 | KASHYAP COMPUTERS | 0.85 | 0 | 0
672 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | computer operator payment | Assistant Engineer-II | Junior Engineer-2 | BILL/00484/2023-2024 | BP-2023-24-193 | 30/09/2023 | 0 | KASHYAP COMPUTERS | 0.51 | 0 | 0
673 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM MAWATAR TO UPPER DABLING UNDER GITDABLING G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-II | Junior Engineer-2 | ORD/000042/2021-2022 | 419/NKWSMD | 07/01/2022 | 90 | TIKARAM SHARMA | 186.55 | 185.9 | 100
674 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2 | RTOR000018/2021-2022 | 652/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.27 | 0 | 0
675 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S. Scheme from Jholungay Khola (Bandukey) to Dokan dara in Rangpo G.P. Gorubathan Block, Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000058/2021-2022 | 449/NKWSMD | 14/01/2022 | 1000 | MAHADEO PRASAD AGARWAL & CO | 159.62 | 130.66 | 100
676 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000017/2021-2022 | 651/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.21 | 0 | 0
677 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM CHAR CHAREY JHORA TO PUBUNG BUSTY AND ITS ADJOINING AREAS IN POKRAIBONG G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer-I | Junior Engineer-4 | ORD/000104/2021-2022 | 628/NKWSMD | 21/02/2022 | 330 | SRINIWAS AGARWAL | 353.99 | 183.16 | 80
678 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000036/2021-2022 | 840/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.17 | 0 | 0
679 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009297 SM Code-SM/08931 |  | Sub-Assistant Engineer | ORD/000042/2022-2023 | 524/NKWSMD | 25/05/2022 | 60 | RAMESH PRADHAN AND CO. | 6.23 | 5.62 | 100
680 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000037/2022-2023 | 1264/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.22 | 0 | 0
681 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna , | Assistant Engineer | Sub-Assistant Engineer | BILL/00288/2023-2024 |  | 27/09/2023 | 0 | RAJ BUILDERS | 0.85 | 0 | 0
682 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | computer operator payment | Assistant Engineer | Sub-Assistant Engineer | BILL/00485/2023-2024 | BP-2023-24-192 | 30/09/2023 | 0 | RAJ BUILDERS | 0.85 | 0 | 0
683 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000216/2022-2023 | 2563/NKWSMD | 17/02/2023 | 0 | Resource Division | 12.04 | 0 | 0
684 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JaL Jeevan Mission and Jal Swapna Programme for Piped Wat¿r Supply Scheme for Ringtong godam dhura gorabari margret's hope GP under Kurseong Sub-Division P HED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000015/2022-2023 | BP-2022-23-14 | 11/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 5.35 | 0 | 0
685 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JaL Jeevan Mission and Jal Swapna Programme for Piped Water Supply Scheme for Upper Pachang lower Sonada GP-II under Kurseong Sub-Division P HED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000016/2022-2023 | BP-2022-23-15 | 11/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 4.67 | 0 | 0
686 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Pankhabari & sorroundingarea St Mary's GP-Ill under Kurseong Sub-Division PHED, GTA. | Assistant Engineer | Sub-Assistant Engineer | VCH/000019/2022-2023 | BP-2022-23-18 | 20/04/2022 | 0 | SURAJ LAMA | 9.17 | 0 | 0
687 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional House hold Tap Connection under Jal Jeev an Mission and Jal Swapna Programme for Piped water Supply Scheme for Longview Tarai 34 & satt Ghurnt, St Mary's GP-Ill under Kurseong Sub-Division PHED. GTA. | Assistant Engineer | Sub-Assistant Engineer | VCH/000021/2022-2023 | BP-2022-23-20 | 20/04/2022 | 0 | SURAJ LAMA | 6.21 | 0 | 0
688 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programe for Piped Water Supply Scheme for Upper Prashanti Gram & Chatakpur Upper Sonada GP under Kurseong Sub-Division PHED, | Assistant Engineer | Sub-Assistant Engineer | VCH/000025/2022-2023 | BP-2022-23-24 | 20/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 6.92 | 0 | 0
689 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission an.d Jal Swapno Programme for Piped Water Supply Scheme for D.B Road Ekta Valley Lowe r Sonada GP II under Kurseong Sub-Division PHED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000027/2022-2023 | BP-2022-23-26 | 20/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 6.46 | 0 | 0
690 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Longview T.E, St. Mary - Ill GP under Kurseong Sub-Divisi on PHED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000051/2022-2023 | BP-2022-23-39 | 06/05/2022 | 0 | SURAJ LAMA | 21.74 | 0 | 0
691 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for upper Sirubari, Ghyabari GP I under Kurseong Sub-Division PHED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000160/2022-2023 | BP-2022-23-123 | 23/08/2022 | 0 | NAVRATNA CONSTRUCTION CO | 14.53 | 0 | 0
692 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | Assistant Engineer | Sub-Assistant Engineer | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
693 | Neorakhola W/S & Mtc.Div. |  | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Simsaray Jhora t o Upper Ka mzer in Lolay GP |  |  | BILL/01006/2023-2024 | BP-2023-24-663 | 29/03/2024 | 0 | DIPESH RAI | 7.89 | 0 | 0
694 | Neorakhola W/S & Mtc.Div. |  | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. |  |  | ORD/000273/2022-2023 | 1875/NKWSMD | 14/12/2022 | 60 | YAMA CONSTRUCTIONS LLP | 62.3 | 34.3 | 100
695 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000218/2022-2023 | 2598/NKWSMD | 17/02/2023 | 0 | Resource Division | 10.9 | 0 | 0
696 | Neorakhola W/S & Mtc.Div. |  | "Providing Func tional household Tap connection under JJM & JSP Pro gram me for Pws sche me from Jhandi Jhora to Upper & lower Mangzing Pokhrebong GP" |  |  | VCH/000006/2022-2023 | BP-2022-23-5 | 11/04/2022 | 0 | ASHOK CHETTRI | 10.86 | 0 | 0
697 | Neorakhola W/S & Mtc.Div. |  | providing Functional household Tap connect ion under JJM & JSP Programme for Dws scheme from Jholung khola to Sangam Gaon under Rongo GP |  |  | VCH/000029/2022-2023 | BP-2022-23-28 | 20/04/2022 | 0 | PREM KUMAR GURUNG | 16.91 | 0 | 0
698 | Neorakhola W/S & Mtc.Div. |  | Providing Functional household Tap connection under JJM & JSP Pro grammme for Dws schem e from KAii KHola to Upper Fagu Fac tory line Nim GP |  |  | VCH/000030/2022-2023 | BP-2022-23-29 | 20/04/2022 | 0 | NEMESH LAMA | 8.59 | 0 | 0
699 | Neorakhola W/S & Mtc.Div. |  | Providin g Functional household Tap connection under JJM and JSP Programme for Dws scheme by Pumpin g fo r Malbusty Chettri Gaon Gorubathan GP |  |  | VCH/000031/2022-2023 | BP-2022-23-30 | 20/04/2022 | 0 | NEMESH LAMA | 9.28 | 0 | 0
700 | Neorakhola W/S & Mtc.Div. |  | Pr oviding house connection for Dws Scheme from Ambiok Khola to dalimtarr Busty Dalim GP |  |  | VCH/000070/2022-2023 | BP-2022-23-58 | 01/06/2022 | 0 | ASHOK SUNAM | 14.43 | 0 | 0
701 | Neorakhola W/S & Mtc.Div. |  | "Prov iding Function al household Tap connection under JJM & JSP Programme for Dws scheme from Dobaney Jhora to 2 no phase six bus stand Paten Godak Gp" |  |  | VCH/000282/2022-2023 | BP-2022-23-166 | 11/10/2022 | 0 | JOJO CONSTUCTION | 6 | 0 | 0
702 | Neorakhola W/S & Mtc.Div. |  | "Prov iding Function al household Tap connection under JJM & JSP Programme for Dws scheme from Dobaney Jhora to 2 no phase six bus stand Paten Godak Gp" |  |  | VCH/000289/2022-2023 | BP-2022-23-178 | 25/10/2022 | 0 | JOJO CONSTUCTION | 7.66 | 0 | 0
703 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Mini Piped Water Supply Scheme for South Sukna and Choklong under Kurseong Division. Scheme Code - 10788 TSM/010472 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00092/2024-2025 | "BP-2024-25-99 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.91 | 0 | 0
704 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00167/2023-2024 | BP-2023-24-123 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
705 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00168/2023-2024 | BP-2023-24-124 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
706 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00169/2023-2024 | BP-2023-24-125 | 28/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
707 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00170/2023-2024 | BP-2023-24-126 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
708 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00171/2023-2024 | BP-2023-24-122 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
709 | Neorakhola W/S & Mtc.Div. | Kurseong Division | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER KURSEONG, MIRIK BLOCK, DISTRICT OF DARJEELING. [TSM NO -10472] 1. Sukna Forest(Sukna Forest South). 2. Choklong Forest. 3. Panighata(panighata 14 number ward, 10 number line). 4. PanthabariForest(Naya Basti 1). 5. Panthabari Forest(Naya Basti 3). | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000085/2022-2023 | 607/NKWSMD | 26/05/2022 | 1203 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 242.87 | 143.47 | 100
710 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000079/2022-2023 | 1291/NKWSMD | 09/09/2022 | 0 | Resource Division | 2.35 | 0 | 0
711 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000154/2022-2023 | 2372/NKWSMD | 03/02/2023 | 0 | Resource Division | 2.35 | 0 | 0
712 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM GURUNG JHORA TO PACHIM KABI GAON UNDER BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III,Assistant Engineer-IV | Junior Engineer-3,Junior Engineer-II | ORD/000057/2022-2023 | 553/NKWSMD | 26/05/2022 | 180 | PASANG LAMA & SONS(HUF) | 133.86 | 85.71 | 100
713 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM DADALEY JHORA TOBURMAIK UNDER SANGSEY G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-2,Junior Engineer-II | ORD/000046/2022-2023 | 528/NKWSMD | 25/05/2022 | 180 | M/S. ASHOK KUMAR PERIWAL | 147.75 | 60 | 50
714 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Jhepi & Gurdung under Jal Jeevan Mission and Jal Swapno Programme. |  | Sub-Assistant Engineer | ORD/000138/2022-2023 | 818/NKWSMD | 30/06/2022 | 240 | VINAYAK CONSTRUCTION | 303.13 | 231.93 | 100
715 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000083/2022-2023 | 1365/NKWSMD | 21/09/2022 | 0 | Resource Division | 1.9 | 0 | 0
716 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000105/2022-2023 | 1882/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.9 | 0 | 0
717 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000165/2022-2023 | 2570/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.9 | 0 | 0
718 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Manebhanjyang Bazar, Panchyat - Sukhia Simana Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000170/2022-2023 | 946/NKWSMD | 12/07/2022 | 60 | MOHAN MUKHIA | 48.83 | 46.89 | 0
719 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000102/2022-2023 | 1911/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.54 | 0 | 0
720 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under JJM & JSP Programme including extension work for PWS Scheme for Upper & Lower Barbotia, Gram Panchyat -Rishihat Bloomfield, Block Bijanbari -PullBazar. TSM No. 009473 SM Code-SM/08932 |  | Sub-Assistant Engineer | ORD/000035/2022-2023 | 498/NKWSMD | 24/05/2022 | 60 | PROSENJIT BASAK | 18.21 | 16.93 | 100
721 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000125/2022-2023 | 1901/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.86 | 0 | 0
722 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000185/2022-2023 | 2580/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.86 | 0 | 0
723 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM HARISEY JHORA TO LOWER BHAGEY UNDER G.P. BLOCK-II KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. GO2223001538PH | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-II | ORD/000027/2022-2023 | 291/NKWSMD | 13/05/2022 | 180 | PEMA BHUTIA | 100.81 | 79.21 | 85
724 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED RONG TONG 12 MILE PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000077/2022-2023 | 600/NKWSMD | 26/05/2022 | 825 | NARAYAN THAPA | 83.04 | 39.5 | 51
725 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
726 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00488/2023-2024 | BP-2023-24-295 | 02/11/2023 | 0 | WBSEDCL | 6.14 | 0 | 0
727 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00489/2023-2024 | BP-2023-24-296 | 02/11/2023 | 0 | WBSEDCL | 4.87 | 0 | 0
728 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation Of ODEX Tube Well based 02(Two) number of pipe water supply Scheme having provision of 2(Two) number of RCC OHR viz 300 Cum & 200Cum and other related works for 6(Six) villages in GTA Area. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000094/2022-2023 | 825/NKWSMD | 30/06/2022 | 900 | M/S KAMAK ENGINEERS AND CO. | 783.01 | 230.38 | 100
729 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
730 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000161/2022-2023 | 2375/NKWSMD | 03/02/2023 | 0 | Resource Division | 9.18 | 0 | 0
731 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | :Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Linseybong, Gram Panchyat -Lodhuma-I, Block Bijanbari -PullBazar. TSM No. 009471 SM Code-SM/08926 |  | Sub-Assistant Engineer | ORD/000108/2022-2023 | 629/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 16.59 | 15.54 | 70
732 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000039/2022-2023 | 1269/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.17 | 0 | 0
733 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM SISNEY KHOLA TO NAJOK BUSTY UNDER KALIMPONG BLOCK-I UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000142/2022-2023 | 833/NKWSMD | 30/06/2022 | 360 | RABIN RAI | 73.59 | 48.56 | 100
734 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK: JORE BUNGALOW SUKHIAPOKHRI, DISTRICT: DARJEELING UNDER DARJEELING DIVISION, P.H.E-GTA. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000042/2025-2026 | 647/NKWSMD | 05/05/2025 | 60 | DAJUBHAI HARDWARE | 22.9 | 0 | 0
735 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000259/2022-2023 | 1622/NKWSMD | 03/11/2022 | 815 | VINAYAK CONSTRUCTION | 633.65 | 594.1 | 100
736 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000193/2022-2023 | 2581/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.75 | 0 | 0
737 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden (Khundrukey Busty, Lower Chimney, Majuwa Busty, Mohan Majuwa, Titney Busty habitation) under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000114/2022-2023 | 794/NKWSMD | 30/06/2022 | 960 | MS JAGANNATH PRASAD | 11.97 | 0 | 55
738 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000053/2022-2023 | 1297/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.07 | 0 | 0
739 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Kalimati Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000134/2022-2023 | 814/NKWSMD | 30/06/2022 | 60 | SWAD CONSTRUCTION | 12.14 | 12.09 | 0
740 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000060/2022-2023 | 1304/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.34 | 0 | 0
741 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS scheme fro Soureni Bazar: Gram Panchyat- Soureni-I, Block -Mirik TSM No. 009309 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000016/2022-2023 | 782/NKWSMD | 30/06/2022 | 60 | KAMAL PRADHAN | 22.21 | 17.24 | 100
742 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS scheme at Chowandhura Gram Panchyat Soureni-I Block Mirik TSM No. 009303 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000011/2022-2023 | 789/NKWSMD | 30/06/2022 | 915 | KAMAL PRADHAN | 11.04 | 0 | 100
743 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM SAWRENI KHOLA TO NIM BUSTY UNDER GORUBATHAN BLOCK, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000110/2022-2023 | 790/NKWSMD | 30/06/2022 | 180 | PRAKASH TAMANG | 174.02 | 111.36 | 85
744 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM DEORALI KHOLA TO PAKANG SONAGAON UNDER GITABLING G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000109/2022-2023 | 788/NKWSMD | 30/06/2022 | 1060 | TIKARAM SHARMA | 113.45 | 89.7 | 100
745 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PULUNGDONG TEA ESTATE VILLAGE WATER SUPPLY SCHEME UNDER JOREBUNGLOW SUKHIAPOKHARI BLOCK. |  | Junior Engineer-VI | ORD/000078/2023-2024 | 677/NKWSMD | 12/07/2023 | 180 | SATHI CONSTRUCTION COMPANY | 239.24 | 0 | 100
746 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PULUNGDUNG TEA ESTATE PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING. |  | Junior Engineer-VI | ORD/000146/2024-2025 | 2349/NKWSMD | 19/12/2024 | 90 | SATHI CONSTRUCTION COMPANY | 47.86 | 0 | 0
747 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-VI | RTOR000067/2023-2024 | 762/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.62 | 0 | 0
748 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.09.2024 to 31.10.2024. |  | Sub-Assistant Engineer | ORD/000105/2024-2025 | 1551/NKWSMD | 30/08/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 100
749 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation of source for lower takbia under Jal Swapno Programme for Goke-1, Block-Bijanbari-Pullbazar TSM No. 009479 |  | Sub-Assistant Engineer | ORD/000126/2022-2023 | 806/NKWSMD | 30/06/2022 | 60 | SAILESH RAI | 23.93 | 23.9 | 65
750 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000232/2022-2023 | 1146/NKWSMD | 29/09/2022 | 665 | GARGO TRADERS | 852.89 | 726.03 | 95
751 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000113/2022-2023 | 1890/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.04 | 0 | 0
752 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000172/2022-2023 | 2610/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.04 | 0 | 0
753 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Forest Busty, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000180/2022-2023 | 956/NKWSMD | 12/07/2022 | 970 | RAMESH THAPA | 23.61 | 0 | 100
754 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000074/2022-2023 | 1318/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.32 | 0 | 0
755 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating Gravity Based Piped Water Supply For Today Ambeok Tea Garden Under Gorubathan Block Under Kalimpong District Under P.H.E Dte. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000293/2022-2023 | 2151/NKWSMD | 20/01/2023 | 180 | M/S R.S. CONSTRUCTION | 255.72 | 100 | 85
756 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000222/2022-2023 | 2565/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.9 | 0 | 0
757 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Pumping based Piped water supply scheme for Turzum Forest under Teesta G.P. Kalimpong Block- I District Kalimpong. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00095/2024-2025 | BP-2024-25-446 | 28/11/2024 | 0 | WBSEDCL | 14.53 | 0 | 0
758 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Pumping Based Piped Water Supply Scheme for Turzum Forest under Teesta G.P. Block Kalimpong -I , District- Kalimpong. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00229/2024-2025 |  | 31/07/2024 | 0 | WBSEDCL | 14.53 | 0 | 0
759 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0
760 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00513/2023-2024 | BP-2023-24-319 | 17/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 4.74 | 0 | 0
761 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Pumping Based Piped Water Supply Scheme for Turzam Forest under Teesta G.P. Block Kalimpong-I, District: Kalimpong. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000279/2022-2023 | 2005/NKWSMD | 23/12/2022 | 180 | SANTOSH TAMANG | 221.13 | 40 | 50
762 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000227/2022-2023 | 2588/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.76 | 0 | 0
763 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer I | Junior Engineer III | BILL/00808/2023-2024 | BP-2023-24-520 | 21/02/2024 | 0 | WBSEDCL | 5.66 | 0 | 0
764 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer I | Junior Engineer III | BILL/00809/2023-2024 | BP-2023-24-521 | 21/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0
765 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Logistic arrangement and hand holding support to Jalpaiguri Government Engineering College for conducting Geo-Technical investigation at GLR sites in different locations of Darjeeling & Kalimpong District under Jal Jeevan Mission. | Assistant Engineer I | Junior Engineer III | ORD/000244/2023-2024 | 137/AE-II/NKWSMD | 08/12/2023 | 62 | YAMA CONSTRUCTIONS LLP | 6.99 | 0 | 100
766 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED BONG KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE | Assistant Engineer I | Junior Engineer III | ORD/000274/2022-2023 | 1876/NKWSMD | 14/12/2022 | 720 | SRINIWAS AGARWAL | 534.86 | 139.77 | 100
767 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer III | RTOR000135/2022-2023 | 2029/NKWSMD | 29/12/2022 | 0 | Resource Division | 6.25 | 0 | 0
768 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer III | RTOR000232/2022-2023 | 2586/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.25 | 0 | 0
769 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00194/2024-2025 | BP-2024-25-171 | 30/07/2024 | 0 | WBSEDCL | 0.95 | 0 | 0
770 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | payment for WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00767/2023-2024 | BP-2023-24-505 | 17/02/2024 | 0 | WBSEDCL | 4.8 | 0 | 0
771 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00768/2023-2024 | BP-2023-24-506 | 17/02/2024 | 0 | WBSEDCL | 10.62 | 0 | 0
772 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00769/2023-2024 | BP-2023-24-507 | 17/02/2024 | 0 | WBSEDCL | 0.96 | 0 | 0
773 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000074/2023-2024 | 675/NKWSMD | 12/07/2023 | 425 | YAMA CONSTRUCTIONS LLP | 2035.87 | 1350 | 75
774 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000065/2023-2024 | 770/NKWSMD | 19/07/2023 | 0 | Resource Division | 10.27 | 0 | 0
775 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
776 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000066/2023-2024 | 362/NKWSMD | 29/05/2023 | 365 | YAMA CONSTRUCTIONS LLP | 1365.56 | 1035.82 | 90
777 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000222/2024-2025 | 408/NKWSMD | 26/03/2025 | 90 | NIM TSHERING LEPCHA | 35.96 | 0 | 0
778 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | RTOR000059/2023-2024 | 532/NKWSMD | 13/06/2023 | 0 | Resource Division | 6.53 | 0 | 0
779 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR PANKHASARI KHASMAHAL PWSS (ZONE -1) to (ZONE-V) UNDER BLOCK:- GORUBATHAN, DISTRICT:- KALIMPONG, P.H.E Dte. | Assistant Engineer II | Junior Engineer III | ORD/000306/2022-2023 | 2470/NKWSMD | 06/02/2023 | 365 | THUPDEN BHUTIA | 1193.6 | 0 | 80
780 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer III | RTOR000200/2022-2023 | 2582/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.1 | 0 | 0
781 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME IN DARJEELING PHULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000022/2023-2024 | 121/NKWSMD | 28/04/2023 | 240 | MS. SURYA I PVT. LTD COMPANY | 196.43 | 0 | 70
782 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000013/2023-2024 | 210/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.21 | 0 | 0
783 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR JAMADARBHITTA KHASMAHAL (PART-1 & 2) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000024/2025-2026 | 592/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 45.62 | 0 | 0
784 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR JAMADAR BHITA KHASMAHAL (PART-1 & 2) PIPED WATER SUPPLY SCHEME IN KURSEONG, UNDER DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000094/2023-2024 | 718/NKWSMD | 18/07/2023 | 665 | GARGO TRADERS | 976.84 | 0 | 70
785 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000086/2023-2024 | 797/NKWSMD | 20/07/2023 | 0 | Resource Division | 3.43 | 0 | 0
786 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand note for proposal of Diversion of 0.03917 ha of forest land for Gravity based water supply scheme for Teesta DIF fund by West Bengal Public Health Engineering Directorate under Jal Jeevan mission. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00233/2024-2025 | BP-2024-25-222 | 28/08/2024 | 0 | WBSFDA | 2.6 | 0 | 0
787 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand note for Proposal of Diversion of 0.03917 ha of forest land for Gravity Based Water supply scheme for Teesta DIF fund by West Bengal Public Health Engineering Directorate under Jal Jeevan Mission. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00234/2024-2025 | BP-2024-25-221 | 28/08/2024 | 0 | WBSFDA | 1.76 | 0 | 0
788 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR TISTA BAZAR DIF (PART) UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000326/2022-2023 | 2659/NKWSMD | 28/02/2023 | 720 | M/S. ASHOK KUMAR PERIWAL | 474.98 | 0 | 90
789 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000246/2022-2023 | 2710/NKWSMD | 03/03/2023 | 0 | Resource Division | 4.22 | 0 | 0
790 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000255/2022-2023 | 2775/NKWSMD | 10/03/2023 | 0 | Resource Division | 4.22 | 0 | 0
791 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR GOKE UNDER PULL BIJANIARI BLOCK DARJEELING DIVISION, PHED TO ACCOMMODATE FHTC IN PULL BIJANBARI BLOCK |  | Sub-Assistant Engineer | ORD/000140/2024-2025 | 2331/NKWSMD | 17/12/2024 | 180 | MS. SURYA I PVT. LTD COMPANY | 66.7 | 0 | 0
792 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GOKE-I PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT |  | Sub-Assistant Engineer | ORD/000226/2023-2024 | 1293/NKWSMD | 17/10/2023 | 365 | VAISHNO CONSTRUCTION | 839.28 | 0 | 68
793 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000089/2023-2024 | 813/NKWSMD | 24/07/2023 | 0 | Resource Division | 6.67 | 0 | 0
794 | Neorakhola W/S & Mtc.Div. | Kurseong Division | AUGMENTATION OF LEFT OUT HABITATION OF CART ROAD GHAYABARI-II G.P. UNDER KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer5,Sub-Assistant Engineer | ORD/000008/2025-2026 | 494/NKWSMD | 09/04/2025 | 180 | SHAKTI CONSTRUCTION | 93.45 | 0 | 0
795 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR LIZZIPUR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer5,Sub-Assistant Engineer | ORD/000229/2023-2024 | 1291/NKWSMD | 17/10/2023 | 365 | SHAKTI CONSTRUCTION | 1461.53 | 0 | 100
796 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Preparation of Re-draft of proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 03 (three) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer5 | Junior Engineer5,Sub-Assistant Engineer | ORD/000274/2023-2024 | 1594/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.57 | 0 | 100
797 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer7,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
798 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAHANADI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer7,Sub-Assistant Engineer | ORD/000005/2023-2024 | 92/NKWSMD | 27/04/2023 | 605 | VINAYAK CONSTRUCTION | 1041.6 | 610.12 | 100
799 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer7,Sub-Assistant Engineer | RTOR000007/2023-2024 | 154/NKWSMD | 03/05/2023 | 0 | Resource Division | 6.37 | 0 | 0
800 | Neorakhola W/S & Mtc.Div. |  | GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KAGEY KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KAGEY G.P BLOCK : KALIMPONG-II, DISTRICT: KALIMPONG. |  |  | ORD/000079/2023-2024 | 678/NKWSMD | 12/07/2023 | 720 | NEOCON CONSTRUCTION CO | 208.69 | 0 | 75
801 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 774/NKWSMD | 19/07/2023 | 0 | Resource Division | 1.22 | 0 | 0
802 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR KARMAT BUSTY PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Sub-Assistant Engineer | ORD/000091/2023-2024 | 712/NKWSMD | 17/07/2023 | 300 | SRINIWAS AGARWAL | 128.73 | 0 | 100
803 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000062/2023-2024 | 776/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.26 | 0 | 0
804 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SAURINI BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK-MIRIK DISTRICT-DARJEELING, KURSEONG DIVISION PHE-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000026/2025-2026 | 594/NKWSMD | 29/04/2025 | 90 | ALLIED INSTRUMENTS | 22.62 | 0 | 0
805 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000035/2023-2024 | 278/NKWSMD | 17/05/2023 | 0 | Resource Division | 4.55 | 0 | 0
806 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Piped Water Supply Scheme for Mahanadi Forest under Kurseong Division. Scheme Code - 15648 TSM/017745 | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00094/2024-2025 | BP-2024-25-95 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 15.27 | 0 | 0
807 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
808 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR MAHANADI FOREST TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000065/2023-2024 | 439/NKWSMD | 07/06/2023 | 830 | RUKMANI ENGINEERING WORKS | 157.77 | 0 | 100
809 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00854/2023-2024 | BP-2024-25-56 | 07/06/2024 | 0 | WBSEDCL | 51.83 | 0 | 0
810 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION IN MIRIK BLOCK. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000016/2023-2024 | 116/NKWSMD | 28/04/2023 | 1193 | SRINIWAS AGARWAL | 677.35 | 290 | 90
811 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000020/2023-2024 | 205/NKWSMD | 10/05/2023 | 0 | Resource Division | 4.29 | 0 | 0
812 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Selim Hill T .E.under Kurseong Division PHED), GTA |  |  | VCH/000014/2022-2023 | BP-2022-23-13 | 11/04/2022 | 0 | SWAD CONSTRUCTION | 7.27 | 0 | 0
813 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection unde.r Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Makaibari Tea Estate under Kurseong Sub-DIvision PHED, GTA |  |  | VCH/000022/2022-2023 | BP-2022-23-21 | 20/04/2022 | 0 | NIPENDRA TAMANG | 10.07 | 0 | 0
814 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sittong-1 & Sittong-111 under Kurseong Sub-Division PHED, GTA. |  |  | VCH/000026/2022-2023 | BP-2022-23-25 | 20/04/2022 | 0 | BIKRAM RAI | 21.12 | 0 | 0
815 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Schem e for Dudhia Bazaar & its sorrounding area under Kurseong Sub-Division PHED, G1A |  |  | VCH/000037/2022-2023 | BP-2022-23-37 | 20/04/2022 | 0 | SUN SHINE GROUP | 19.39 | 0 | 0
816 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000143/2022-2023 |  | 26/08/2022 | 0 | SHREE VAISHNO ENTERPRISES | 14.73 | 0 | 0
817 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
818 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SAMALBONG PIPED WATER SUPPLY SCHEME UNDER BLOCK-PULBAZAR DISTRICT-DARJEELING. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000028/2025-2026 | 596/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 98.47 | 0 | 0
819 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SAMALBONG PIPED WATER SUPPLY SCHEME DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000178/2023-2024 | 937/NKWSMD | 16/08/2023 | 605 | GARGO TRADERS | 1200.76 | 0 | 80
820 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000100/2023-2024 | 963/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.35 | 0 | 0
821 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer I | Junior Engineer III | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
822 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer I | Junior Engineer III | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
823 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM 9th MILE JHORA TO 18th MILE AND ITS ADJOINING AREA UNDERPAIYONG G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer I | Junior Engineer III | ORD/000111/2021-2022 | 629/NKWSMD | 21/02/2022 | 750 | SUNIL BAJLA | 251.13 | 212.78 | 100
824 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer III | RTOR000037/2021-2022 | 839/NKWSMD | 21/03/2022 | 0 | Resource Division | 0.66 | 0 | 0
825 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer III | RTOR000089/2022-2023 | 1374/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.66 | 0 | 0
826 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR MOLATEY AND AVONGRAVE TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHRI UNDER DARJEELING DISTRICT |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000235/2022-2023 | 1452/NKWSMD | 29/09/2022 | 850 | SHAKTI CONSTRUCTION | 926.69 | 779.09 | 99
827 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000112/2022-2023 | 1889/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.41 | 0 | 0
828 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000171/2022-2023 | 2572/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.41 | 0 | 0
829 | Neorakhola W/S & Mtc.Div. |  | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
830 | Neorakhola W/S & Mtc.Div. |  | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER FOR PATEN GODAK KHASMAHAL, UNDER BLOCK: GORUBATHAN, DISTRICT KALIMPONG, UNDER PUBLIC HEALTH ENGINEERING DIRECTORATE. |  |  | ORD/000089/2023-2024 | 710/NKWSMD | 17/07/2023 | 730 | THUPDEN BHUTIA | 1116.3 | 0 | 45
831 | Neorakhola W/S & Mtc.Div. |  | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). |  |  | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
832 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 763/NKWSMD | 19/07/2023 | 0 | Resource Division | 5.38 | 0 | 0
833 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00957/2023-2024 | BP-2023-24-657 | 23/03/2024 | 0 | WBSEDCL | 11.34 | 0 | 0
834 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Balance work for Surface water based Purba & Paschim Phuguri Tea Garden Phuguri Forest and its Surrounding under Kurseong Division, P.H.E-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000057/2025-2026 | 874/NKWSMD | 16/06/2025 | 365 | INTERIOR'S NEST | 312.15 | 0 | 0
835 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST AND ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000059/2025-2026 | 829/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 93.84 | 0 | 0
836 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST & ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000169/2023-2024 | 913/NKWSMD | 11/08/2023 | 545 | INTERIOR'S NEST | 2568.72 | 0 | 75
837 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000110/2023-2024 | 970/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.04 | 0 | 0
838 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR ACHHALAL HATTA PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT DARJEELING. |  | Sub-Assistant Engineer | ORD/000126/2024-2025 | 2203/NKWSMD | 02/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 114.92 | 0 | 80
839 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR ACHHALAL HATTA PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000151/2023-2024 | 879/NKWSMD | 03/08/2023 | 365 | YAMA CONSTRUCTIONS LLP | 2563.35 | 850 | 50
840 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000132/2023-2024 | 174/NKWSMD | 08/02/2024 | 0 | Resource Division | 12.22 | 0 | 0
841 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4 | Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
842 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000095/2023-2024 | 959/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.46 | 0 | 0
843 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR DAWAIPANI & TUKDAH TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000037/2025-2026 | 650/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 130.55 | 0 | 0
844 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DAWAIPANI & TUKDAH TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000191/2023-2024 | 988/NKWSMD | 23/08/2023 | 815 | VINAYAK CONSTRUCTION | 992.81 | 0 | 100
845 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000113/2023-2024 | 999/NKWSMD | 24/08/2023 | 0 | Resource Division | 8.16 | 0 | 0
846 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
847 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Piped Water Supply Scheme from Chawa Khola to Relli and its adjoining area under Lolay G.P. Block II under Jal Swapno Programme within kalimpong District | Assistant Engineer-I | Junior Engineer-4 | ORD/000045/2021-2022 | 424/NKWSMD | 07/01/2022 | 90 | DIPESH RAI | 117.87 | 117.19 | 100
848 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000010/2021-2022 | 644/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.69 | 0 | 0
849 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme from Sisney Khola to Upper and Lower Kambal and Dingali Gaon in Yangmakum G.P. Block l, Kalimpong under Jal Swapno Programme within Kalimpong District | Assistant Engineer II | Junior Engineer IV | ORD/000143/2021-2022 | 754/NKWSMD | 28/02/2022 | 90 | MR. DAWA LAMA | 107.34 | 81.5 | 80
850 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer IV | RTOR000090/2022-2023 | 1378/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.54 | 0 | 0
851 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
852 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
853 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM ARDHALI JHORA TO TINKATAREY, CHAPLATEY, BARAL, GURDAY GAON KUMAI G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000064/2021-2022 | 455/NKWSMD | 14/01/2022 | 1210 | SAMSHER RAI | 177.01 | 96.44 | 100
854 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000268/2023-2024 | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
855 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000021/2021-2022 | 655/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.77 | 0 | 0
856 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S. Scheme from Bheri Posher Khola to Kothi Line via 6 nos. village in Nim G.P. Gorubathan Block under Lal Jeevan Mission and Jal Swapno Programme | Assistant Engineer-III | Junior Engineer-4 | ORD/000048/2021-2022 | 427/NKWSMD | 07/01/2022 | 980 | M/S R.S. CONSTRUCTION | 192.09 | 174.94 | 100
857 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4 | RTOR000011/2021-2022 | 645/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.26 | 0 | 0
858 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0
859 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
860 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM AMBOIK KHOLA (PARBALAKHA) TO GORUBATHAN TAR IN DALIM G.P. GORUBATHAN BLOCK UNDER JAL SWAPNO PROGRAMME WITHIN DISTRICT- KALIMPONG. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000105/2021-2022 | 624/NKWSMD | 21/02/2022 | 150 | M/S. ASHOK KUMAR PERIWAL | 356.75 | 202.42 | 85
861 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000032/2021-2022 | 835/NKWSMD | 21/03/2022 | 0 | Resource Division | 2.46 | 0 | 0
862 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under JJM & JSP Programme for PWS Scheme Raman Forest Village Source mahabir Jhora Gram Panchyat -Srikhola, Block Darjeeling - Pullbazaar. TSM No. 009295 SM Code-SM/08925 |  | Sub-Assistant Engineer | ORD/000029/2022-2023 | 492/NKWSMD | 24/05/2022 | 60 | NIMA SHERPA | 20.35 | 18.43 | 100
863 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000036/2022-2023 | 1263/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.37 | 0 | 0
864 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Gorkata Gram Panchyat -Goke-II , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009301 SM Code-SM/08933 |  | Sub-Assistant Engineer | ORD/000031/2022-2023 | 494/NKWSMD | 24/05/2022 | 60 | MS D.R ENTERPRISES | 24.24 | 23.54 | 100
865 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000032/2022-2023 | 1259/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.78 | 0 | 0
866 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Upper Lamagoan, Gram Panchyat -Kaijiliya, Block Bijanbari -PullBazar. TSM No. 009097 SM Code-SM/04601 |  | Sub-Assistant Engineer | ORD/000043/2022-2023 | 525/NKWSMD | 25/05/2022 | 60 | M/S DIVYA ENTERPRISES | 18.55 | 18.31 | 0
867 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000030/2022-2023 | 1272/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.47 | 0 | 0
868 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Gorkhey Forest Villa, Gram Panchyat -Sirkhola Danra Gaon, Block Bijanbari -PullBazar. TSM No. 009469 SM Code-SM/08929 |  | Sub-Assistant Engineer | ORD/000032/2022-2023 | 495/NKWSMD | 24/05/2022 | 60 | NIMA SHERPA | 16.74 | 15.75 | 100
869 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000035/2022-2023 | 1262/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.24 | 0 | 0
870 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection und er JJM & JSP Programme for PWS Schem e for Lama goan GP Jhepi Kaijiliya under Darjeeling Division PHED GTA |  | Sub-Assistant Engineer | VCH/000017/2022-2023 | BP-2022-23-16 | 11/04/2022 | 0 | HARI PRASAD CHETTRI | 9.27 | 0 | 0
871 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Relling Bhibaray & Lr Relling GP Relling under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000018/2022-2023 | BP-2022-23-17 | 11/04/2022 | 0 | HARI PRASAD CHETTRI | 8.03 | 0 | 0
872 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Singhbhumdera GP Mazua under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000023/2022-2023 | BP-2022-23-22 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 13.75 | 0 | 0
873 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Gairigoan Fatingtar GP Lodhoma II under Darjeeling Division PHED GTA |  | Sub-Assistant Engineer | VCH/000024/2022-2023 | BP-2022-23-23 | 20/04/2022 | 0 | BIRAJ RAI | 6.44 | 0 | 0
874 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap ·connection under JJM & JSP Programme for PWS Scheme for Samsu (Lower) Relling GP under Darjeeling Division PHED GTA |  | Sub-Assistant Engineer | VCH/000028/2022-2023 | BP-2022-23-27 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 4.03 | 0 | 0
875 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM &. .JSP Programme for PWSS Scheme for Dhotrey Forest fV GP Lodhoma 1 under DarJeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000033/2022-2023 | BP-2022-23-33 | 20/04/2022 | 0 | PASSANG TAMANG | 3.13 | 0 | 0
876 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Kankeybong GP Lodhoma under Darjeellng Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000034/2022-2023 | BP-2022-23-34 | 20/04/2022 | 0 | SACHIN PRADHAN | 13.66 | 0 | 0
877 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household d Tap Connection under JJM & JSP Programme for PWS Scheme for Lungtham Happy Valley under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000035/2022-2023 | BP-2022-23-35 | 20/04/2022 | 0 | SAMDEN DUKPA | 6.07 | 0 | 0
878 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional .Household Tap Connection under JJM & JSP Programme for PWS Scheme for Takbia (Lower ) GP Goke 1 under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000036/2022-2023 | BP-2022-23-36 | 20/04/2022 | 0 | SAILESH RAI | 7.3 | 0 | 0
879 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Tukvar TG GP Tukvar under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000066/2022-2023 | BP-2022-23-51 | 20/05/2022 | 0 | VINAYAK CONSTRUCTION | 47.99 | 0 | 0
880 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connecti on under JJM & JSP Pro gramme for PWS Scheme for Bijanbari Bazar GP Pull Bijnabari under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000067/2022-2023 | BP-2022-23-52 | 20/05/2022 | 0 | AROGYA ENTERPRISES | 24.75 | 0 | 0
881 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
882 | Neorakhola W/S & Mtc.Div. |  | Addition Estimate for the FHTC under JJM Programme 8 nos existing schemes to be provided with FHTC under Kalimpong Block-II in the district of Kalimpong, FHTC under JJM Programme 14 nos existing schemes to be provided with FHTC, FHTC under JJM Programme 10 nos existing schemes to be provided with FHTC under Block-III, Gorubathan. |  |  | ORD/000273/2022-2023 | 1875/NKWSMD | 14/12/2022 | 60 | YAMA CONSTRUCTIONS LLP | 62.3 | 25.97 | 100
883 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000219/2022-2023 | 2599/NKWSMD | 17/02/2023 | 0 | Resource Division | 9.09 | 0 | 0
884 | Neorakhola W/S & Mtc.Div. |  | Prnviding Functional house hold Tap connection under JJM & JSP Programmne Pws sc heme from Kafal dhara And aheri Jhora to SinJee Bazar } Samaibong GP |  |  | VCH/000003/2022-2023 | BP-2022-23-2 | 11/04/2022 | 0 | SANTOSH TAMANG | 18.15 | 0 | 0
885 | Neorakhola W/S & Mtc.Div. |  | "Providing Functional househol d Tap connection under JJM &JSP Programme for Dws scheme from Khani Khola to Baidar, Karki, Basnet, Lusuney& Sansari Dara Gaon" |  |  | VCH/000004/2022-2023 | BP-2022-23-3 | 11/04/2022 | 0 | SANTOSH TAMANG | 14.01 | 0 | 0
886 | Neorakhola W/S & Mtc.Div. |  | Providing Functional household Tap connectionunder JJM & JSP Prog ramme Pws sche me from Sarki dhara to Yok Primtam Acha rya Subba Gaon Seokbir GP |  |  | VCH/000007/2022-2023 | BP-2022-23-6 | 11/04/2022 | 0 | SUKRAJ SUBBA | 13.95 | 0 | 0
887 | Neorakhola W/S & Mtc.Div. |  | providin g Functional hou sehold Tap connection under J.JM &. JSP Pro gramme for Pws scheme from Kafleykhola to Gairigaon Bong GP |  |  | VCH/000008/2022-2023 | BP-2022-23-7 | 11/04/2022 | 0 | TEKENDRA ADHIKARI | 10.64 | 0 | 0
888 | Neorakhola W/S & Mtc.Div. |  | Providing Fun ct ional h ou sehold Tap connection under JJM & JSP Pro gramme for Dws scheme fr om Bhalu Khola to Lower New ar Gaon Bhalukhop GP |  |  | VCH/000009/2022-2023 | BP-2022-23-8 | 11/04/2022 | 0 | SUPER SAJAN CONSTRUCTION | 17.16 | 0 | 0
889 | Neorakhola W/S & Mtc.Div. |  | "Providing Functional househo ld Tap co nnection under JJM & JSP Pro gramm e for Dws scheme fr om Rabling Khola to Munt hung Busty Ka ffer Kankebong GP" |  |  | VCH/000010/2022-2023 | BP-2022-23-9 | 11/04/2022 | 0 | SANGAM GURUNG | 10.89 | 0 | 0
890 | Neorakhola W/S & Mtc.Div. |  | Providing Functional household Tap connection under JJM & JSP Programme for Pws scheme from Mai teraj Jhora to Upper Gairi gaon Bhalukhop GP |  |  | VCH/000011/2022-2023 | BP-2022-23-10 | 11/04/2022 | 0 | GABAC AND COMPANY | 11.97 | 0 | 0
891 | Neorakhola W/S & Mtc.Div. |  | Pro viding Functional househo ld Tap connection under JJM & JSP Prow amm e Dws sch eme from Reank Khola to Pembling Khare Gaon Nimbong GP |  |  | VCH/000012/2022-2023 | BP-2022-23-11 | 11/04/2022 | 0 | SANGAM GURUNG | 8.51 | 0 | 0
892 | Neorakhola W/S & Mtc.Div. |  | Pr oviding Fu n ctional h ousehold Tap connection und er JJM & JSP Programm e Dws sch eme from Sangbir Jhora to Barbot Pab ringt ar GP |  |  | VCH/000053/2022-2023 | BP-2022-23-42 | 06/05/2022 | 0 | SITA SHARMA | 18 | 0 | 0
893 | Neorakhola W/S & Mtc.Div. |  | Providing Functional. household Tap connection under JJM & JSP Programme for Dws scheme from Badiya Dhara to Dara Gaon Bhalukhop GP |  |  | VCH/000059/2022-2023 | BP-2022-23-55 | 18/05/2022 | 0 | GABAC AND COMPANY | 12.44 | 0 | 0
894 | Neorakhola W/S & Mtc.Div. |  | Providing Functional household Tap connection under JJM & JSP Programme for Dws scheme from Jurant , Khola to Middle& Lowe r Chuimkhim Pabringtar |  |  | VCH/000065/2022-2023 | BP-2022-23-56 | 20/05/2022 | 0 | DILIP CHHETRI ACHARYA | 13.44 | 0 | 0
895 | Neorakhola W/S & Mtc.Div. |  | "Pro vidin g Fun ctional household Tap connect ion under .IJM & JS P Pro gramm e for Dw s scheme by Pumping for Chaikaar, Bha nga and Mongpong Fv Pabringtar GP" |  |  | VCH/000094/2022-2023 | BP-2022-23-87 | 30/06/2022 | 0 | ANAND KUMAR LAKHOTIA | 14.91 | 0 | 0
896 | Neorakhola W/S & Mtc.Div. |  | PIPED WATER SUPPLY SCHEME FROM PAREN KHOLA TO RANGPO DIVISION UNDER SANGSEY G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000050/2022-2023 | 532/NKWSMD | 25/05/2022 | 180 | YAMA CONSTRUCTIONS LLP | 190.09 | 189.16 | 100
897 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 1376/NKWSMD | 22/09/2022 | 0 | Resource Division | 1.26 | 0 | 0
898 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer I,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | BILL/00175/2023-2024 | BP-2023-24-130 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
899 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000159/2022-2023 | 2370/NKWSMD | 03/02/2023 | 0 | Resource Division | 1.81 | 0 | 0
900 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM SIRISE KHOLA TO ROCKY ISLAND UNDER GORUBATHAN BLOCK UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000028/2022-2023 | 491/NKWSMD | 24/05/2022 | 180 | SRINIWAS AGARWAL | 164.25 | 75.53 | 80
901 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme from Sethi Khola to Upper Khani. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-III | ORD/000141/2022-2023 | 832/NKWSMD | 30/06/2022 | 820 | SANGAM GURUNG | 104.88 | 81.26 | 100
902 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR DARAGOAN UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PULL BIJANBARI BLOCK |  | Sub-Assistant Engineer | ORD/000077/2025-2026 | 967/NKWSMD | 03/07/2025 | 60 | SUNIL SHARMA | 6.93 | 0 | 0
903 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR DARAGOAN LEKHARGA UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  | Sub-Assistant Engineer | ORD/000086/2022-2023 | 613/NKWSMD | 26/05/2022 | 60 | SUNIL SHARMA | 58.05 | 0 | 100
904 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000104/2022-2023 | 1881/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.52 | 0 | 0
905 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000164/2022-2023 | 2569/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.52 | 0 | 0
906 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Fatinagar Gram, G.P. - Lodhama-I, Block - Bijanbari Pulbazar. |  | Sub-Assistant Engineer | ORD/000112/2023-2024 | 849/NKWSMD | 27/07/2023 | 60 | BIJAY CHETTRI | 25.37 | 0 | 100
907 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Takdah Bazar GP - Takdah Block - Rungli Rungliot. |  | Sub-Assistant Engineer | ORD/000174/2022-2023 | 950/NKWSMD | 12/07/2022 | 253 | NAVRATNA CONSTRUCTION CO | 150.61 | 0 | 100
908 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000134/2022-2023 | 1910/NKWSMD | 15/12/2022 | 0 | Resource Division | 5.85 | 0 | 0
909 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000192/2022-2023 | 2618/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.85 | 0 | 0
910 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Upper Mamring Khasmahal in Kurseong Block within Darjeeling District. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | ORD/000042/2023-2024 | 186/NKWSMD | 04/05/2023 | 870 | PREM CHANDRA RAI | 267.92 | 0 | 85
911 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | RTOR000042/2023-2024 | 328/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.74 | 0 | 0
912 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2023 TO 31.12.2023 |  | Sub-Assistant Engineer | ORD/000220/2023-2024 | 1023/NKWSMD | 31/08/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 100
913 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | CHOONGTOONG & LIZAHILL TEA GARDEN WATER SUPPLY SCHEME UNDER DARJEELING DIVISION I, PHED, GTA |  | Sub-Assistant Engineer | ORD/000239/2022-2023 | 1447/NKWSMD | 29/09/2022 | 300 | SUDESH RAYA MAJHI | 1203.75 | 819.09 | 80
914 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000108/2022-2023 | 1885/NKWSMD | 15/12/2022 | 0 | Resource Division | 16.58 | 0 | 0
915 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000167/2022-2023 | 2604/NKWSMD | 17/02/2023 | 0 | Resource Division | 16.58 | 0 | 0
916 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED RATNA DYANG PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA, DISTRICT DARJEELING. | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | ORD/000280/2022-2023 | 1988/NKWSMD | 23/12/2022 | 180 | KUMAR CHHETRI | 75.55 | 30.98 | 100
917 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | RTOR000226/2022-2023 | 2567/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.94 | 0 | 0
918 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED JOGMAYA TEA ESTATE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000285/2022-2023 | 2083/NKWSMD | 10/01/2023 | 180 | MS CHAMLING CONSTRUCTION | 66.72 | 0 | 80
919 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000224/2022-2023 | 2602/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.89 | 0 | 0
920 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SINGBULLI FACTORY GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000089/2022-2023 | 611/NKWSMD | 26/05/2022 | 60 | M/S JAI BHAWANI CONSTRUCTION CO | 63.19 | 44.66 | 97
921 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000078/2022-2023 | 1322/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.3 | 0 | 0
922 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | BILL/00172/2023-2024 | BP-2023-24-127 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
923 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | BILL/00173/2023-2024 | BP-2023-24-128 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
924 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | BILL/00494/2023-2024 | BP-2023-24-290 | 02/11/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
925 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 95 | 100
926 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Proposed Gravity Based Water Supply Scheme for Tumsung Khasmahal PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000240/2022-2023 | 1494/NKWSMD | 14/10/2022 | 1000 | ALLIED INSTRUMENTS | 587.51 | 574.91 | 100
927 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000110/2022-2023 | 1887/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.74 | 0 | 0
928 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000169/2022-2023 | 2606/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.74 | 0 | 0
929 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000116/2022-2023 | 796/NKWSMD | 30/06/2022 | 60 | PREM KUMAR PRADHAN | 27.69 | 26.69 | 100
930 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000055/2022-2023 | 1299/NKWSMD | 09/09/2022 | 0 | Resource Division | 2.61 | 0 | 0
931 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation for work for PWS Scheme for Dara Goan, Khoprail: Gram Panchyat -Soureni-II, Block Mirik TSM No. 009308 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000015/2022-2023 | 783/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 12.59 | 11.93 | 100
932 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Continuation Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for the period of 6 (Six) months. Note: With effect from date of issuing work order. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000248/2023-2024 | 1141/NKWSMD | 29/09/2023 | 182 | S S CONSTRUCTIONS | 0.99 | 0 | 100
933 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for bada Kothi: Gram Panchyat Soureni- II, Block - Mirik TSM No. 009482 SM Code-SM/08949 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000019/2022-2023 | 781/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 3.78 | 3.64 | 100
934 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap Connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Ghoomti T.E. Mahanadi GP Block Kurseong | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000131/2022-2023 | 811/NKWSMD | 30/06/2022 | 60 | MS CHAMLING CONSTRUCTION | 26.4 | 25.72 | 100
935 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000061/2022-2023 | 1305/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.91 | 0 | 0
936 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Sivitar T.E. Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000119/2022-2023 | 798/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 24.02 | 22.6 | 100
937 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000063/2022-2023 | 1307/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.68 | 0 | 0
938 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000079/2023-2024 | 767/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.82 | 0 | 0
939 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION P.H.E DTE. |  |  | ORD/000145/2024-2025 | 2347/NKWSMD | 19/12/2024 | 365 | YAMA CONSTRUCTIONS LLP | 1156.69 | 0 | 75
940 | Neorakhola W/S & Mtc.Div. |  | SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E. DTE. |  |  | ORD/000249/2023-2024 | 3/NKWSMD | 03/01/2024 | 455 | YAMA CONSTRUCTIONS LLP | 5612.47 | 0 | 95
941 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000221/2022-2023 | 2600/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.07 | 0 | 0
942 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme For Suruk Under Jal Jeevan Mission In Gorubathan Block Under Kalimpong District, Under P.H.E Dte. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000310/2022-2023 | 2490/NKWSMD | 09/02/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 636.52 | 0 | 60
943 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000162/2022-2023 | 2620/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.08 | 0 | 0
944 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000239/2022-2023 | 2713/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.08 | 0 | 0
945 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Milan Dhura, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000182/2022-2023 | 958/NKWSMD | 12/07/2022 | 970 | NABIN RAI | 20.04 | 0 | 100
946 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000143/2022-2023 | 2063/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.28 | 0 | 0
947 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Piped Water Supply Scheme at Chimney Simanatar with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED-GTA, Darjeeling. | Assistant Engineer 4,Assistant Engineer4 |  | ORD/000188/2023-2024 | 986/NKWSMD | 23/08/2023 | 60 | PHURBA RUMBA | 77.11 | 0 | 0
948 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 |  | RTOR000111/2023-2024 | 1000/NKWSMD | 24/08/2023 | 0 | Resource Division | 1.08 | 0 | 0
949 | Neorakhola W/S & Mtc.Div. |  | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  |  | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
950 | Neorakhola W/S & Mtc.Div. |  | CREATING GRAVITY BASED PIPED WATER SUPPLY SCHEME WITH SPRING WATER SOURCE FOR SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME, UNDER BLOCK:-GORUBATHAN. DISTRICT:-KALIMPONG, UNDER P.H.E Dte. |  |  | ORD/000044/2023-2024 | 358/NKWSMD | 26/05/2023 | 716 | THUPDEN BHUTIA | 348.89 | 0 | 50
951 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 367/NKWSMD | 29/05/2023 | 0 | Resource Division | 1.87 | 0 | 0
952 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000257/2022-2023 | 1620/NKWSMD | 03/11/2022 | 545 | GARGO TRADERS | 874.98 | 713.62 | 90
953 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000116/2022-2023 | 1893/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.72 | 0 | 0
954 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000175/2022-2023 | 2573/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.72 | 0 | 0
955 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme from Samthara Khola to Centre Gaon, Pintalay Gaon, Gudara Gaon, Bich Gaon and Chettri Gaon in Nimbong G.P. Block under Jal Swapno Programme within Kalimpong District | Assistant Engineer I | Junior Engineer III | ORD/000142/2021-2022 | 749/NKWSMD | 28/02/2022 | 90 | DINESH SHERPA | 154.6 | 90.46 | 100
956 | Neorakhola W/S & Mtc.Div. |  | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
957 | Neorakhola W/S & Mtc.Div. |  | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
958 | Neorakhola W/S & Mtc.Div. |  | Creating Gravity Based Water Supply Scheme for Kumai Forest Under Gorubathan Block Under Kalimpong District Under P.H.E Dte. |  |  | ORD/000055/2023-2024 | 416/NKWSMD | 05/06/2023 | 900 | SACHIN RAI | 279.21 | 0 | 65
959 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 450/NKWSMD | 07/06/2023 | 0 | Resource Division | 1.5 | 0 | 0
960 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED AND PUMPING BASED PIPED WATER SUPPLY SCHEME FOR PAIYONG KHASMAHAL (PART) UNDER PAIYONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | Assistant Engineer-IV | Junior Engineer-2 | ORD/000070/2023-2024 | 673/NKWSMD | 12/07/2023 | 1025 | EVERSHINE CONSTRUCTION | 878.08 | 0 | 70
961 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2 | RTOR000081/2023-2024 | 768/NKWSMD | 19/07/2023 | 0 | Resource Division | 3.98 | 0 | 0
962 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00614/2023-2024 | BP-2023-24-412 | 12/01/2024 | 0 | WBSEDCL | 0.82 | 0 | 0
963 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PANTHABARI PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000001/2023-2024 | 32/NKWSMD | 17/04/2023 | 90 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 91.41 | 0 | 100
964 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
965 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/01/2025 TO 31/03/2025 (3 MONTHS). | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000164/2024-2025 | 2411/NKWSMD | 31/12/2024 | 90 | NIM TSHERING LEPCHA | 1.45 | 0 | 0
966 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000002/2023-2024 | 58/NKWSMD | 24/04/2023 | 0 | Resource Division | 0.83 | 0 | 0
967 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme For Hatta Piped Water Supply Scheme in Darjeeling Pulbazar Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000058/2023-2024 | 413/NKWSMD | 05/06/2023 | 938 | SAGARMATHA CONSTRUCTION CO. | 278.82 | 0 | 80
968 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000047/2023-2024 | 442/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.83 | 0 | 0
969 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
970 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional estimate for water supply scheme for Manedara piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. (SM/15885) |  | Sub-Assistant Engineer | ORD/000017/2024-2025 | 981/NKWSMD | 18/06/2024 | 60 | ALLIED INSTRUMENTS | 13.06 | 0 | 100
971 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANEDARA PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000063/2023-2024 | 437/NKWSMD | 07/06/2023 | 690 | ALLIED INSTRUMENTS | 413.06 | 0 | 50
972 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
973 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation with new source with laying of HDPE pipes for Soring Khasmahal Piped Water Supply Scheme under Rangli Rangliot Block District Darjeeling. |  | Sub-Assistant Engineer | ORD/000323/2023-2024 | 720/NKWSMD | 29/03/2024 | 278 | SRINIWAS AGARWAL | 22.64 | 0 | 100
974 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
975 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SORIANG KHASMAHAL & TAKLING BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK- RANGLI RANGLIONT ; DISTRICT- DARJEELING. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000077/2023-2024 | 676/NKWSMD | 12/07/2023 | 515 | SRINIWAS AGARWAL | 531.05 | 0 | 100
976 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation with new source with laying of HDPE pipes for Soring Khasmahal Piped Water Supply Scheme under Rangli Rangliot Block District Darjeeling. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000323/2023-2024 | 720/NKWSMD | 29/03/2024 | 278 | SRINIWAS AGARWAL | 22.64 | 0 | 100
977 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000066/2023-2024 | 761/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.74 | 0 | 0
978 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00855/2023-2024 | BP-2023-24-656 | 23/03/2024 | 0 | WBSEDCL | 18.95 | 0 | 0
979 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR DUPTIN BUSTY PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000028/2023-2024 | 104/NKWSMD | 28/04/2023 | 758 | SHAKTI CONSTRUCTION | 830.5 | 0 | 100
980 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000026/2023-2024 | 251/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.42 | 0 | 0
981 | Neorakhola W/S & Mtc.Div. |  | SURFACE WATER BASED RINGTONG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000208/2023-2024 | 1289/NKWSMD | 17/10/2023 | 605 | SHAKTI CONSTRUCTION | 605.39 | 0 | 50
982 | Neorakhola W/S & Mtc.Div. | Kurseong Division | GRAVITY BASED WATER SUPPLYSCHEME FORUNDER SELIM HILL UNDER JAL JEEWAN MISSION | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00398/2024-2025 | "BP-2024-25-289 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.2 | 0 | 0
983 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED SELIM HILL TEA GARDEN TO ACCOMODATE FHTC IN KURSEONG BLOCK | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000341/2022-2023 | 2756/NKWSMD | 09/03/2023 | 365 | SHAKTI CONSTRUCTION | 910.25 | 0 | 85
984 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000259/2022-2023 | 2771/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.37 | 0 | 0
985 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | NIM & PHASINTING KHASMAHAL SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG | Assistant Engineer-IV | Junior Engineer-2 | ORD/000181/2023-2024 | 945/NKWSMD | 17/08/2023 | 730 | M/S. ASHOK KUMAR PERIWAL | 954.32 | 0 | 85
986 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2 | RTOR000093/2023-2024 | 957/NKWSMD | 21/08/2023 | 0 | Resource Division | 2.91 | 0 | 0
987 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR BADAMTAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK: DARJEELING PULBAZAR DISTRICT DARJEELNG UNDER DARJEELING DIVISION PHED GTA. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000054/2025-2026 | 817/NKWSMD | 05/06/2025 | 90 | ASHIRWAD CONSTRUCTION CO | 29.04 | 0 | 0
988 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BADAMTAM TEA GARDEN PWSS IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000184/2023-2024 | 947/NKWSMD | 17/08/2023 | 815 | ASHIRWAD CONSTRUCTION CO. | 1087.52 | 0 | 100
989 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000270/2023-2024 | 1590/NKWSMD | 29/12/2023 | 10 | MANOMITA CIVIL ENGINEERING CONSULTANCY PVT LTD | 0.95 | 0 | 100
990 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000104/2023-2024 | 966/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.07 | 0 | 0
991 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00818/2023-2024 | BP-2023-24-534 | 26/02/2024 | 0 | WBSEDCL | 6.22 | 0 | 0
992 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00819/2023-2024 | BP-2023-24-535 | 26/02/2024 | 0 | WBSEDCL | 4.83 | 0 | 0
993 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000075/2023-2024 | 671/NKWSMD | 12/07/2023 | 635 | YAMA CONSTRUCTIONS LLP | 1111.51 | 398.86 | 100
994 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000170/2024-2025 | 160/NKWSMD | 04/02/2025 | 180 | S S CONSTRUCTIONS | 98.42 | 0 | 100
995 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000118/2023-2024 | 1189/NKWSMD | 06/10/2023 | 0 | Resource Division | 5.08 | 0 | 0
996 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Piped Water Supply Scheme for Lebong & Mineral Tea Garden (SM/18726) under Darjeeling Division, PHED, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000020/2024-2025 | 984/NKWSMD | 18/06/2024 | 60 | KUNCHAN JUNGA ENTERPRISES | 49.4 | 0 | 0
997 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/18726) | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000149/2024-2025 | 2352/NKWSMD | 19/12/2024 | 60 | KUNCHAN JUNGA ENTERPRISES | 19.15 | 0 | 0
998 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000183/2023-2024 | 946/NKWSMD | 17/08/2023 | 866 | KUNCHAN JUNGA ENTERPRISES | 1046.33 | 0 | 85
999 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000102/2023-2024 | 965/NKWSMD | 21/08/2023 | 0 | Resource Division | 7.65 | 0 | 0
1000 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | RUNGBUL & HILL CART ROAD PIPED WATER SUPPLY SCHEME UNDER KURSEONG DIVISION. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000189/2023-2024 | 987/NKWSMD | 23/08/2023 | 755 | GARGO TRADERS | 1927.74 | 0 | 95
1001 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000112/2023-2024 | 998/NKWSMD | 24/08/2023 | 0 | Resource Division | 10.36 | 0 | 0
1002 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00759/2023-2024 | BP-2023-24-504 | 26/02/2024 | 0 | WBSEDCL | 7.09 | 0 | 0
1003 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | STRENGHTENING OF LAYING DISTRIBUTION SYSTEM FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION,PHE.DTE. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000060/2025-2026 | 831/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 253.18 | 0 | 0
1004 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADITIONAL WORK FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000061/2025-2026 | 830/NKWSMD | 09/06/2025 | 180 | MAA DURGA ENTERPRISE | 54.17 | 0 | 0
1005 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000163/2023-2024 | 911/NKWSMD | 11/08/2023 | 365 | INTERIOR'S NEST | 1516.55 | 125 | 65
1006 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000096/2023-2024 | 960/NKWSMD | 21/08/2023 | 0 | Resource Division | 11.68 | 0 | 0
1007 | Neorakhola W/S & Mtc.Div. |  | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake, WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR MANGARJUNG AND OTHER 3 VILLAGES followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000114/2024-2025 | 1612/NKWSMD | 09/09/2024 | 546 | GARGO TRADERS | 8505.63 | 0 | 25
1008 | Neorakhola W/S & Mtc.Div. |  | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1009 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM 7TH MILE TO ALGARAH BAZAR UNDER SANTOOK G.P. BLOCK-II, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME, DISTRICT- KALIMPONG. | Assistant Engineer I | Junior Engineer IV | ORD/000108/2021-2022 | 622/NKWSMD | 21/02/2022 | 1050 | JUSTINE BHUTIA | 297.77 | 235.28 | 80
1010 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer IV | RTOR000030/2021-2022 | 833/NKWSMD | 21/03/2022 | 0 | Resource Division | 2.48 | 0 | 0
1011 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I | Junior Engineer IV | RTOR000091/2022-2023 | 1375/NKWSMD | 22/09/2022 | 0 | Resource Division | 2.77 | 0 | 0
1012 | Neorakhola W/S & Mtc.Div. |  | P.W.S SCHEME FROM CHAGAY KHOLA TO SAURENI IN AHALAY G.P GORUBATHAN BLOCK, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000040/2021-2022 | 421/NKWSMD | 07/01/2022 | 180 | THUPDEN BHUTIA | 133.48 | 123.84 | 100
1013 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 641/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.33 | 0 | 0
1014 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Danra Goan, Soom 1st Division, Gram Panchyat -Soom Singtam, Block Bijanbari -PullBazar. TSM No. 009476 SM Code-SM/08937 |  | Sub-Assistant Engineer | ORD/000060/2022-2023 | 556/NKWSMD | 26/05/2022 | 60 | NAVRATNA CONSTRUCTION CO | 16.53 | 0 | 100
1015 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000124/2022-2023 | 1900/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.36 | 0 | 0
1016 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000184/2022-2023 | 2579/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.36 | 0 | 0
1017 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Sangsey V-Notch and Delo Middle Lake in Kalimpong Block I ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART -B) | Assistant Engineer I | Junior Engineer I,Junior Engineer III,Junior Engineer IV | ORD/000007/2022-2023 | 106/NKWSMD | 13/04/2022 | 180 | GETEN NAMGYAL BHUTIA | 80.78 | 80.04 | 100
1018 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Jhilkey Dhara and Sangsey V-Notch in Kalimpong Block I & ll ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART D) | Assistant Engineer I | Junior Engineer I,Junior Engineer III,Junior Engineer IV | ORD/000008/2022-2023 | 107/NKWSMD | 13/04/2022 | 180 | DHURBA KUMAR PRADHAN | 88.12 | 27.96 | 90
1019 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Jhilkey Dhara and Sangsey V-Notch in Kalimpong Block I & ll ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART C) | Assistant Engineer I | Junior Engineer I,Junior Engineer III,Junior Engineer IV | ORD/000020/2022-2023 | 139/NKWSMD | 20/04/2022 | 180 | SONAM TOPGAY BHUTIA | 162.35 | 162.49 | 100
1020 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Work for Extension of Pipeline by Way of Retrofitting of Neorakhola Piped Water Supply Scheme to Provide Functional Household Tap Connection to The Remain Household of En-Route Village Under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong. | Assistant Engineer I | Junior Engineer I,Junior Engineer III,Junior Engineer IV | ORD/000020/2025-2026 | 599/NKWSMD | 29/04/2025 | 120 | SONAM TOPGAY BHUTIA | 18.95 | 0 | 100
1021 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Extension of pipeline by Retrofitting of Neorakhola Piped water supply scheme for providing Functional Household Tap connection (FHTC) to the remaining en-route households (P.C) in between Sangsey V-Notch and Delo Middle Lake in Kalimpong Block I ,in the District of Kalimpong , under JJM and Jalswapna programme under Neorakhola w/s & Mtc. Division P.H.E. Dte (PART -A) | Assistant Engineer I | Junior Engineer I,Junior Engineer III,Junior Engineer IV | ORD/000026/2022-2023 | 290/NKWSMD | 13/05/2022 | 240 | DHURBA KUMAR PRADHAN | 152.1 | 0 | 100
1022 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of Presentation Slideof SAJAL GRAM Village i.c.w Jal Jeevan Mission(JJM)Programme and Video graph the Whole events of Successful Story of SAJAL GRAM at various Gram Panchayet (G.P) under Kalimpong District ; And involving of all Necessary equipments(Mike, External HDD,Projector with Screen , Flash Light for Camera along with Stands etc) and deployment of essential labour for the Work etc) for Integrated work up to the Completion of all activities in the name of IEC(Information, Education &Communication) for educate the rural inhabitants of the locality/command Area of Sajal Gram regarding importance of Potable Drinking Water & it¿s conservation in future ,Protection from theft etc in future as per Operational Guidelines of Jal Jeevan Mission (JJM) of Kalimpong District, covering tentatively39Villages at Present under Neorakhola W/S & Mtc Division, PHE Dte. | Assistant Engineer I | Junior Engineer I,Junior Engineer III,Junior Engineer IV | ORD/000385/2022-2023 | 78/AE-II /NKWSMD | 03/03/2023 | 5 | SAMRAT GHATAK | 0.98 | 0.2 | 50
1023 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan M is si on.an d Jal Swapno Programme for Pipe Water Supply Sche me Scheme for 5th mile upper Kotwali Gaon. from Boka Jhora Source under Jorebanglow- Sukhiapokhri Block Darj eeling" |  | Sub-Assistant Engineer | VCH/000055/2022-2023 | BP-2022-23-41 | 06/05/2022 | 0 | KAMAKHYA ENTERPRISES | 3.63 | 0 | 0
1024 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connect ion under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Sch eme for Pokhriabong Bazar from Nursery Fatak Source under Jorebanglow- Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000063/2022-2023 | BP-2022-23-54 | 20/05/2022 | 0 | RISHI KESH THAKURI | 7.36 | 0 | 0
1025 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Jai Jeevan Mi ssion and Jal Swapno Programme for Pipe Water Su pply Scheme for Minzu Pussimbing from Bethany Khop Source under Jorebanglow Sukhiapokhri Block Darjeeling ." |  | Sub-Assistant Engineer | VCH/000064/2022-2023 | BP-2022-23-53 | 20/05/2022 | 0 | KESHAR CHETTRI | 4.91 | 0 | 0
1026 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Scheme for Chotta Pubong ward No 3 & 4 from Singadevi Khela Source Under Jorebanglow - Su khiapokhri Block Dar je elin g under Darje eling Division PHED, GTA." |  | Sub-Assistant Engineer | VCH/000068/2022-2023 | BP-2022-23-49 | 20/05/2022 | 0 | KIRAN NIROLA | 3.11 | 0 | 0
1027 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Conne ct ion under Jal Jee van Missi on and Jal Swapno Programme for Prpe Water Supply Sch eme for Tar zum under Jorebanglow Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000112/2022-2023 | BP-2022-23-90 | 14/07/2022 | 0 | SONAM TAMANG | 4.1 | 0 | 0
1028 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Funct ional House hold Tap Connection under Jal Jeevan Mission an d Jal Swapno Programme for Pipe Water Supply Sc heme for Mazidhura Lower Parment Busty from Bhir Khola Sou rc e under Jorebanglow- Sukhiapokhri Block Darjeelin g under Darjeeling Division PH ED, GTA." |  | Sub-Assistant Engineer | VCH/000156/2022-2023 | BP-2022-23-111 | 12/08/2022 | 0 | KAMAKHYA ENTERPRISES | 3.68 | 0 | 0
1029 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JAL Jeeva n Mission and Jal Swapno Programme for Pipe Water Su pply Scheme for Chamong Maleteneya And Pari Gaon from Paa Khola and Kera Bari Source under Jorebangiow Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000161/2022-2023 | BP-2022-23-105 | 08/08/2022 | 0 | RISHI KESH THAKURI | 3.54 | 0 | 0
1030 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functionai Household Tap Connection under Jal Jeevan Mission and Jal Swapno Pro grarnme for Pipe Water Supply Sch eme for Pokhriabong Busty No 4. from Ghimiray Jhora an Thulung Pakha Source under Jorebanglow - Sukhiapokhi" |  | Sub-Assistant Engineer | VCH/000283/2022-2023 | BP-2022-23-170 | 20/10/2022 | 0 | RISHI KESH THAKURI | 2.56 | 0 | 0
1031 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jee van Mission and Jal Swapno Pro gramme for Pipe Water Supply Scheme for Lepcha Tribal Gaon Pokhriabong Busty from Gardinay Sim Source under Jorebanglow- Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000284/2022-2023 | BP-2022-23-171 | 20/10/2022 | 0 | RISHI KESH THAKURI | 3.13 | 0 | 0
1032 | Neorakhola W/S & Mtc.Div. |  | Providing Functional House hold Tap Connection under Jal Jeev an Mission and Jal Swapna Programme for Piped water Supply Scheme for Longview Tarai 34 & satt Ghurnt, St Mary's GP-Ill under Kurseong Sub-Division PHED. GTA. |  |  | VCH/000020/2022-2023 | BP-2022-23-19 | 20/04/2022 | 0 | SURAJ LAMA | 6.2 | 0 | 0
1033 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000144/2022-2023 |  | 26/08/2022 | 0 | SHREE VAISHNO ENTERPRISES | 14.05 | 0 | 0
1034 | Neorakhola W/S & Mtc.Div. |  | Providing Functional HouseholdTap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for for Hilay Jhora and Manju ak number Dara under Kurseong Sub-Division PHED, GTA |  |  | VCH/000154/2022-2023 | BP-2022-23-112 | 12/08/2022 | 0 | CHARDHAM CONSTRUCTION | 3.7 | 0 | 0
1035 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Khoprail sakha under Kurseong Sub-Division PHED. GTA |  |  | VCH/000155/2022-2023 | BP-2022-23-113 | 12/08/2022 | 0 | CHARDHAM CONSTRUCTION | 3.83 | 0 | 0
1036 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Conne ction under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Mandir Busty, Giddhapa har underKurseong Sub-Division PHED, GTA |  |  | VCH/000159/2022-2023 | BP-2022-23-122 | 23/08/2022 | 0 | NAVRATNA CONSTRUCTION CO | 6.08 | 0 | 0
1037 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
1038 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 02 (Two) nos. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2023 to 31.07.2023. |  | Sub-Assistant Engineer | ORD/000068/2023-2024 | 377/NKWSMD | 31/05/2023 | 61 | THE ELECTRIC SPHERE | 0.79 | 0.79 | 100
1039 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 01 (one) no. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Superintending Engineer, GTA, P.H.E. Dte from 01.06.2023 to 31.07.2023. |  | Sub-Assistant Engineer | ORD/000069/2023-2024 | 378/NKWSMD | 31/05/2023 | 61 | THE ELECTRIC SPHERE | 0.39 | 0.39 | 100
1040 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR KOLBONG UNDER JAL SWAPNO PROGRAMME. (BLOCK-DARJEELING-PULBAZAR) |  | Sub-Assistant Engineer | ORD/000091/2022-2023 | 610/NKWSMD | 26/05/2022 | 180 | HEMRAJ NIROLA | 80.89 | 80.56 | 0
1041 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 |  | Sub-Assistant Engineer | ORD/000150/2022-2023 | 680/NKWSMD | 31/05/2022 | 12 | THE ELECTRIC SPHERE | 4.98 | 1.57 | 95
1042 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1(One) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the S.E. GTA, P.H.E. Dte from 01.06.2022 to 31.05.2023 |  | Sub-Assistant Engineer | ORD/000152/2022-2023 | 681/NKWSMD | 31/05/2022 | 365 | THE ELECTRIC SPHERE | 2.47 | 1.97 | 45
1043 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/09/2023. |  | Sub-Assistant Engineer | ORD/000205/2023-2024 | 848/NKWSMD | 28/07/2023 | 62 | THE ELECTRIC SPHERE | 0.93 | 0.79 | 100
1044 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 |  | Sub-Assistant Engineer | ORD/000207/2023-2024 | 851/NKWSMD | 28/07/2023 | 123 | THE ELECTRIC SPHERE | 0.87 | 0.39 | 90
1045 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000044/2022-2023 | 1271/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.66 | 0 | 0
1046 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating Gravity based piped water supply scheme for Kolbong Forest village under lava Gitbeong G.P kalimpong Block -II,in the dist of Kalimpong in connection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | Assistant Engineer I | Junior Engineer III | ORD/000037/2022-2023 | 502/NKWSMD | 25/05/2022 | 90 | BHUTIA AND SONS | 38.82 | 21.67 | 60
1047 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Teesta Valley, GP - Rungli, Block - Rungli Rungliot. |  | Sub-Assistant Engineer | ORD/000176/2022-2023 | 952/NKWSMD | 12/07/2022 | 658 | NAVRATNA CONSTRUCTION CO | 167.77 | 47.34 | 92
1048 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000133/2022-2023 | 1909/NKWSMD | 15/12/2022 | 0 | Resource Division | 8.41 | 0 | 0
1049 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000197/2022-2023 | 2593/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.41 | 0 | 0
1050 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR ROLAK KHASMAHAL & LONKU KHASMAHAL UNDER KURSEONG BLOCK DISTRICT-DARJEELING UNDER KURSEONG DIVISION. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000041/2025-2026 | 656/NKWSMD | 05/05/2025 | 180 | DAJUBHAI CONSTRUCTION | 83.76 | 0 | 0
1051 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Rolak Khasmahal & Lonku Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kurseong Block within Darjeeling District. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000314/2022-2023 | 2494/NKWSMD | 09/02/2023 | 1405 | VINAYAK CONSTRUCTION | 1016.14 | 886.22 | 100
1052 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000151/2022-2023 | 2071/NKWSMD | 05/01/2023 | 0 | Resource Division | 8.37 | 0 | 0
1053 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000208/2022-2023 | 2556/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.37 | 0 | 0
1054 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000238/2022-2023 | 2723/NKWSMD | 03/03/2023 | 0 | Resource Division | 8.37 | 0 | 0
1055 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED SANTA BHAWAN & RAJBARI LOWER PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000219/2022-2023 | 1117/NKWSMD | 05/08/2022 | 1195 | BOBBY PRADHAN | 117.24 | 0 | 50
1056 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000148/2022-2023 | 2068/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.04 | 0 | 0
1057 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MANI KHOPE PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | ORD/000268/2022-2023 | 1749/NKWSMD | 25/11/2022 | 265 | ROSHAN BISWAKARMA | 78.65 | 34.79 | 100
1058 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | RTOR000114/2023-2024 | 1066/NKWSMD | 13/09/2023 | 0 | Resource Division | 0.42 | 0 | 0
1059 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LAPCHER (ROHINI) PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000082/2022-2023 | 603/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 63.44 | 53.24 | 100
1060 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000073/2022-2023 | 1317/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.52 | 0 | 0
1061 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000138/2022-2023 | 1258/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.52 | 0 | 0
1062 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MARCHEBUNG PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000079/2022-2023 | 602/NKWSMD | 26/05/2022 | 622 | ROSHAN BISWAKARMA | 60.38 | 22.6 | 100
1063 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000071/2022-2023 | 1315/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.57 | 0 | 0
1064 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000136/2022-2023 | 2056/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.57 | 0 | 0
1065 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Lower Lonku under Kurseong Sub-Division, P.H.E.D. GTA. | Assistant Engineer | Sub-Assistant Engineer | ORD/000140/2022-2023 | 831/NKWSMD | 30/06/2022 | 607 | BIKRAM RAI | 79.8 | 36.78 | 100
1066 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/01/2025 TO 31/03/2025 (3 MONTHS). | Assistant Engineer | Sub-Assistant Engineer | ORD/000163/2024-2025 | 2410/NKWSMD | 31/12/2024 | 90 | NIM TSHERING LEPCHA | 2.17 | 0 | 0
1067 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000142/2022-2023 | 2062/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.46 | 0 | 0
1068 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000264/2022-2023 | 2812 | 14/03/2023 | 0 | Resource Division | 0.46 | 0 | 0
1069 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM PHENTO SOURCE TO DUKA UNDER KALIMPONG BLOCK-II, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-I | Junior Engineer-3,Junior Engineer-III | ORD/000053/2022-2023 | 535/NKWSMD | 25/05/2022 | 1080 | SUNIL BAJLA | 155.54 | 115.72 | 100
1070 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM KHARKHOLA TO SADAR AND LOWER TOP LINE UNDER KALIMPONG GORUBATHAN BLOCK, UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000038/2022-2023 | 503/NKWSMD | 25/05/2022 | 810 | PRAYOG RAI | 102.55 | 97.81 | 100
1071 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull (Gorkha Busty habitation) under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000144/2022-2023 | 835/NKWSMD | 30/06/2022 | 1260 | SAMIR THAPA | 10.11 | 0 | 80
1072 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000049/2022-2023 | 1293/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.87 | 0 | 0
1073 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | WATER SUPPLY SCHEME FOR SEOKBIR KHASMAHAL PWSS IN KALIMPONG-I BLOCK, UNDER KALIMPONG DISTRICT (TSM/012581) | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000250/2022-2023 | 1528/NKWSMD | 18/10/2022 | 720 | SRINIWAS AGARWAL | 400.34 | 334.77 | 80
1074 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer I | Junior Engineer I | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0
1075 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer I | Junior Engineer I | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
1076 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer I | Junior Engineer I | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
1077 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED PARINGAR KHAS MAHAL PWS SCHEME TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOLA W/S & Mtc DIVISION, PHE DTE. | Assistant Engineer I | Junior Engineer I | ORD/000187/2022-2023 | 962/NKWSMD | 12/07/2022 | 590 | THUPDEN BHUTIA | 757.27 | 447.48 | 90
1078 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 | Assistant Engineer I | Junior Engineer I | ORD/000207/2023-2024 | 851/NKWSMD | 28/07/2023 | 123 | THE ELECTRIC SPHERE | 0.87 | 0 | 90
1079 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer I | Junior Engineer I | ORD/000268/2023-2024 | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1080 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months) | Assistant Engineer I | Junior Engineer I | ORD/000327/2023-2024 | 1458/NKWSMD | 30/11/2023 | 62 | THE ELECTRIC SPHERE | 0.39 | 0 | 100
1081 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Work for Providing FHTC under Jal Jeevan Mission for balance Household at Maneybhanjang Forest Village Gram Panchayat: Sukhia Simana Block: Jorebunglow Sukhiapokhri. |  | Sub-Assistant Engineer | ORD/000200/2023-2024 | 1082/NKWSMD | 19/09/2023 | 210 | MOHAN MUKHIA | 55.31 | 0 | 75
1082 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SUKHIA POKHARI PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000253/2022-2023 | 1525/NKWSMD | 17/10/2022 | 960 | SUMAN PRADHAN | 317.2 | 193.16 | 100
1083 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY Based & Pumping Based piped water supply scheme, work includes construction of Catchment chamber. Desilting tank. RCC Tank (Main Tank and Zonal Tank) ,Laying of gravity main HDPE PIPE, distribution HDPE pipe, and construction of Switch Room , boundary wall under 5 nos of zone inside the Kashone Khasmahal under Kashone Gram Panchayat , under Kalimpong Block -II , under Kalimpong District. | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | ORD/000234/2022-2023 | 1450/NKWSMD | 29/09/2022 | 1067 | GARGO TRADERS | 869.52 | 177.53 | 100
1084 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | ELECTRO-MECHANICAL WORK FOR GRAVITY BASED AND PUMPING BASED P.W.S SCHEME FOR KASHONE KHASMAHAL UNDER KASHONE G.P. UNDER KALIMPONG BLOCK-II, DIST. KALIMPONG. | Assistant Engineer-I | Junior Engineer-4,Junior Engineer-I | ORD/000270/2022-2023 | 1778/NKWSMD | 28/11/2022 | 60 | THE ELECTRIC SPHERE | 19.28 | 0 | 0
1085 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000014/2024-2025 | 979/NKWSMD | 18/06/2024 | 60 | SUNRISE ENTERPRISES | 24.35 | 0 | 100
1086 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Kurseong Division, P.H.E.D., GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000262/2023-2024 | 160/AE-II/NKWSMD | 10/01/2024 | 357 | MS JAGANNATH PRASAD | 12.44 | 0 | 100
1087 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme in Kurseong Under Darjeeling District. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000286/2022-2023 | 2081/NKWSMD | 10/01/2023 | 348 | SUNRISE ENTERPRISES | 185.86 | 117.28 | 100
1088 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Piped Water Supply Scheme (PWSS) under Dr. Graham's Home G.P, Kalimpong Block-I, Under Neorakhola Water Supply & Maintenance Division, PHE Dte, Kalimpong work includes construction of intake, sedimentation tank, RCC tanks of different sizes, laying of GI, HDPE pipes, boundary wall and providing FHTC. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000260/2022-2023 | 1652/NKWSMD | 04/11/2022 | 1813 | BASANT PRADHAN | 229.27 | 80.25 | 100
1089 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0
1090 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Aringalae with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000179/2022-2023 | 955/NKWSMD | 12/07/2022 | 790 | LAL BAHADUR THAPA | 27.77 | 0 | 75
1091 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000075/2022-2023 | 1319/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.74 | 0 | 0
1092 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000146/2022-2023 | 2066/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.74 | 0 | 0
1093 | Neorakhola W/S & Mtc.Div. |  | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
1094 | Neorakhola W/S & Mtc.Div. |  | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED |  |  | BILL/00502/2023-2024 | BP-2023-24-302 | 09/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.25 | 0 | 0
1095 | Neorakhola W/S & Mtc.Div. |  | FOREST PAYMENT |  |  | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
1096 | Neorakhola W/S & Mtc.Div. |  | CREATING GRAVITY BASED PROVISION OF DRINKING WATER FROM SPRING WATER SOURCE FOR PAREN FOREST VILLAGE, DHAULA (PART) UNDER PATEN GODAK GRAM PANCHAYAT UNDER GORUBATHAN BLOCK IN THE DISTRICT OF KALIMPONG UNDER NEORAKHOLA WATER SUPPLY AND MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG (SM/13609) |  |  | ORD/000090/2023-2024 | 711/NKWSMD | 17/07/2023 | 550 | SILAN GURUNG | 92.4 | 0 | 100
1097 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 756/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.31 | 0 | 0
1098 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED ROHINI TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | ORD/000011/2023-2024 | 100/NKWSMD | 28/04/2023 | 180 | RUKMANI ENGINEERING WORKS | 324.1 | 127.93 | 80
1099 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | RTOR000043/2023-2024 | 322/NKWSMD | 24/05/2023 | 0 | Resource Division | 1.69 | 0 | 0
1100 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | RTOR000152/2022-2023 | 2072/NKWSMD | 05/01/2023 | 0 | Resource Division | 8.37 | 0 | 0
1101 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00530/2023-2024 | BP-2023-24-321 | 25/12/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 5.47 | 0 | 0
1102 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
1103 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVETY BASED PIPED WATER SUPPLY SCHEME FOR SAKIYONG KHASMAHAL PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000031/2023-2024 | 181/NKWSMD | 04/05/2023 | 365 | MS. SURYA I PVT. LTD COMPANY | 393.31 | 0 | 70
1104 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000379/2022-2023 | 74/AE-II/NKWSMD | 28/02/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1105 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000380/2022-2023 | 75/AE-II/NKWSMD | 28/02/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1106 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Preparation of draft proposal including preparation of Maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH portal for forest land diversion in 05 (five) numbers of Scheme under Jal Jeevan Mission (JJM). | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000381/2022-2023 | 76/AE-II/NKWSMD | 28/02/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1107 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000032/2023-2024 | 249/NKWSMD | 12/05/2023 | 0 | Resource Division | 6.1 | 0 | 0
1108 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR KALIMPONG KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER TASHIDING G.P BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000067/2023-2024 | 363/NKWSMD | 29/05/2023 | 365 | YAMA CONSTRUCTIONS LLP | 896.8 | 125 | 80
1109 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR LEFT OUT HOUSEHOLD IN CONNECTION WITH TASHIDING KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER KALIMPONG BLOCK-I, DISTRICT-KALIMPONG IN CONNECTION WITH JAL JEEVAN MISSION, UNDER PHED DD-II, GTA. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000143/2024-2025 | 2334/NKWSMD | 17/12/2024 | 60 | YAMA CONSTRUCTIONS LLP | 16.08 | 0 | 0
1110 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000060/2023-2024 | 533/NKWSMD | 13/06/2023 | 0 | Resource Division | 6.58 | 0 | 0
1111 | Neorakhola W/S & Mtc.Div. | Kurseong Division | GRAVITY BASED WATER SUPPLY SCHEME FOR LATPANCHAR FOREST, UNDER JAL JEEVAN MISSION | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | BILL/00396/2024-2025 | BP-2024-25-281 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.3 | 0 | 0
1112 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR LATPANICHAR FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | ORD/000021/2023-2024 | 120/NKWSMD | 28/04/2023 | 905 | MS. SURYA I PVT. LTD COMPANY | 239.52 | 0 | 80
1113 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | RTOR000018/2023-2024 | 203/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.03 | 0 | 0
1114 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1115 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR LODHOMA PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000004/2023-2024 | 88/NKWSMD | 27/04/2023 | 600 | KAMAL AND COMPANY | 157.57 | 0 | 80
1116 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000041/2023-2024 | 329/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.28 | 0 | 0
1117 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR JAMADAR BHITA KHASMAHAL (PART-1 & 2) PIPED WATER SUPPLY SCHEME IN KURSEONG, UNDER DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000094/2023-2024 | 718/NKWSMD | 18/07/2023 | 665 | GARGO TRADERS | 976.84 | 0 | 70
1118 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000063/2023-2024 | 759/NKWSMD | 19/07/2023 | 0 | Resource Division | 4.38 | 0 | 0
1119 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00708/2023-2024 | BP-2023-24-477 | 28/01/2024 | 0 | WBSEDCL | 4.54 | 0 | 0
1120 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00709/2023-2024 | BP-2023-24-478 | 28/01/2024 | 0 | WBSEDCL | 6.1 | 0 | 0
1121 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR PANIGHATA PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000014/2023-2024 | 110/NKWSMD | 28/04/2023 | 900 | YAMA CONSTRUCTIONS LLP | 282.78 | 0 | 85
1122 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR PANIGHATA PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT DARJEELING, KURSEONG DIVISION PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000171/2024-2025 | 161/NKWSMD | 04/02/2025 | 180 | S S CONSTRUCTIONS | 52.49 | 0 | 80
1123 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000009/2023-2024 | 156/NKWSMD | 03/05/2023 | 0 | Resource Division | 7.53 | 0 | 0
1124 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000119/2023-2024 | 1188/NKWSMD | 06/10/2023 | 0 | Resource Division | 7.53 | 0 | 0
1125 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAHAL DHIRAM FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000023/2023-2024 | 122/NKWSMD | 28/04/2023 | 630 | MS. SURYA I PVT. LTD COMPANY | 250.28 | 0 | 85
1126 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000019/2023-2024 | 204/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.59 | 0 | 0
1127 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM - 15895] | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00231/2024-2025 | BP-2024-25-234 | 03/09/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
1128 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM NO - 15895] | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00232/2024-2025 | BP-2024-25-235 | 03/09/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
1129 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR SEVOK HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000062/2023-2024 | 434/NKWSMD | 06/06/2023 | 605 | SRINIWAS AGARWAL | 216.18 | 0 | 85
1130 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000056/2023-2024 | 441/NKWSMD | 07/06/2023 | 0 | Resource Division | 1.15 | 0 | 0
1131 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0
1132 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | ORD/000029/2023-2024 | 107/NKWSMD | 28/04/2023 | 605 | SRINIWAS AGARWAL | 690.58 | 0 | 100
1133 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | RTOR000027/2023-2024 | 247/NKWSMD | 12/05/2023 | 0 | Resource Division | 4.4 | 0 | 0
1134 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR ALOOBARI PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-VI | ORD/000015/2023-2024 | 115/NKWSMD | 28/04/2023 | 840 | P. D. COMPANY | 577.74 | 0 | 100
1135 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-VI | RTOR000004/2023-2024 | 156/NKWSMD | 03/05/2023 | 0 | Resource Division | 1.77 | 0 | 0
1136 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Proposed Pumping based Piped water supply scheme for Rambi Bazar DIF under Teesta G.P. Kalimpong Block I District Kalimpong. | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00423/2024-2025 |  | 26/09/2024 | 0 | WBSEDCL | 5.15 | 0 | 0
1137 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PAYMENT FOR WBSEDCL | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00958/2023-2024 | BP-2023-24-655 | 23/03/2024 | 0 | WBSEDCL | 5.15 | 0 | 0
1138 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1139 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000243/2022-2023 | 2718/NKWSMD | 03/03/2023 | 0 | Resource Division | 96.35 | 0 | 0
1140 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
1141 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR GITDUBLING KHASMAHAL (PART) PIPED WATER SUPPLY SCHEME, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000039/2023-2024 | 222/NKWSMD | 10/05/2023 | 1015 | SITA SHARMA | 625.46 | 0 | 50
1142 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | RTOR000031/2023-2024 | 246/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.31 | 0 | 0
1143 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Piped Water Supply Scheme for Sukna under Kurseong Division. Scheme Code - 15653 TSM/017746 | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00093/2024-2025 | BP-2024-25-98 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0
1144 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SUKNA PWSS TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000378/2022-2023 | 2874/NKWSMD | 23/03/2023 | 635 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 241.94 | 0 | 43
1145 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000268/2022-2023 | 2893/NKWSMD | 29/03/2023 | 0 | Resource Division | 2.48 | 0 | 0
1146 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1147 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR NAMLA TEA GARDEN PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000019/2023-2024 | 119/NKWSMD | 28/04/2023 | 728 | SAGARMATHA CONSTRUCTION CO. | 228.41 | 0 | 80
1148 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR NAMLA BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK-DARJEELING PULBAZAR DISTRICT-DARJEELING. |  | Sub-Assistant Engineer | ORD/000154/2024-2025 | 2357/NKWSMD | 19/12/2024 | 60 | SAGARMATHA CONSTRUCTION CO. | 10.39 | 0 | 0
1149 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Piped water supply scheme for Rimbick & Namla under Darjeeling Pulbazar Block, Darjeeling Division, PHED, G.T.A. |  | Sub-Assistant Engineer | ORD/000247/2023-2024 | 87/NKWSMD | 11/01/2024 | 90 | NIMA SHERPA | 27.05 | 0 | 100
1150 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000005/2023-2024 | 152/NKWSMD | 03/05/2023 | 0 | Resource Division | 2.37 | 0 | 0
1151 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000096/2023-2024 | 719/NKWSMD | 18/07/2023 | 1036 | SRINIWAS AGARWAL | 1473.72 | 0 | 65
1152 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | RTOR000087/2023-2024 | 815/NKWSMD | 24/07/2023 | 0 | Resource Division | 7.71 | 0 | 0
1153 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00815/2023-2024 | BP-2023-24-531 | 26/02/2024 | 0 | WBSEDCL | 6.19 | 0 | 0
1154 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00816/2023-2024 | BP-2023-24-532 | 26/02/2024 | 0 | WBSEDCL | 5.88 | 0 | 0
1155 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00817/2023-2024 | BP-2023-24-533 | 26/02/2024 | 0 | WBSEDCL | 6.18 | 0 | 0
1156 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000023/2025-2026 | 591/NKWSMD | 29/04/2025 | 180 | ALLIED INSTRUMENTS | 55.54 | 0 | 0
1157 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000155/2023-2024 | 883/NKWSMD | 03/08/2023 | 365 | GARGO TRADERS | 1359.83 | 480 | 80
1158 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00820/2023-2024 | BP-2023-24-536 | 26/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0
1159 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK: UNDER DARJEELING DISTRICT.UNDER KURSEONG DIVISION PHED-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000025/2025-2026 | 593/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 64.04 | 0 | 0
1160 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000156/2023-2024 | 884/NKWSMD | 03/08/2023 | 975 | GARGO TRADERS | 1832.72 | 0 | 75
1161 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 31/11/2023. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000206/2023-2024 | 1153/NKWSMD | 29/09/2023 | 61 | THE ELECTRIC SPHERE | 0.94 | 0 | 0
1162 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000148/2024-2025 | 2351/NKWSMD | 19/12/2024 | 180 | THUPDEN BHUTIA | 117.43 | 0 | 0
1163 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TUKDAH,LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000176/2023-2024 | 935/NKWSMD | 16/08/2023 | 365 | THUPDEN BHUTIA | 1654.3 | 0 | 80
1164 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000099/2023-2024 | 962/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.29 | 0 | 0
1165 | Neorakhola W/S & Mtc.Div. |  | PROPOSED GRAVITY PUMPING PIPED WATER SUPPLY SCHEME FOR DUNGRA KHASMAHAL G.P, UNDER BLOCK: KALIMPONG-I, DISTRICT: KALIMPONG. |  |  | ORD/000093/2023-2024 | 717/NKWSMD | 18/07/2023 | 1095 | SRINIWAS AGARWAL | 1228.4 | 0 | 60
1166 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 773/NKWSMD | 19/07/2023 | 0 | Resource Division | 4.38 | 0 | 0
1167 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAHAL DIRAM TEA GARDEN PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000324/2022-2023 | 2655/NKWSMD | 28/02/2023 | 630 | MS. SURYA I PVT. LTD COMPANY | 212.76 | 0 | 85
1168 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000133/2023-2024 | 263/NKWSMD | 20/02/2024 | 0 | Resource Division | 2.17 | 0 | 0
1169 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000245/2022-2023 | 2720/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.02 | 0 | 0
1170 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR KANKIBONG PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000228/2023-2024 | 1290/NKWSMD | 17/10/2023 | 365 | SAGARMATHA CONSTRUCTION CO. | 785.44 | 0 | 10
1171 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA. |  |  | ORD/000039/2025-2026 | 654/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 142.77 | 0 | 0
1172 | Neorakhola W/S & Mtc.Div. |  | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.08.2024 to 31.08.2024. |  |  | ORD/000096/2024-2025 | 1346/NKWSMD | 31/07/2024 | 31 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
1173 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000202/2023-2024 | 1100/NKWSMD | 21/09/2023 | 365 | VINAYAK CONSTRUCTION | 1970.49 | 0 | 50
1174 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1174/NKWSMD | 05/10/2023 | 0 | Resource Division | 3.2 | 0 | 0
1175 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | i)Hydrological study of Rungdong Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-I ii) Hydrological study of Jamboni River under Water Supply Scheme for Darjeeling Pulbazar Pumping-II iii) Hydrological study of Jhepi Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-III iv)Hydrological study of Balason Khola River (locally khown as Rangbhang Khola) under Water Supply Scheme for Mangarjung Tea Garden and other three villages (MVS), Block- Jorebunglow Sukhiapokhari. v) Hydrological study of Rangbhang River (Khola) Pumping water Supply Scheme for Mirik Municipal Town and EN-Route villages District- Darjeeling (under AMRUT) | Assistant Engineer 1 | Sub-Assistant Engineer | BILL/00218/2024-2025 | BP-2024-25-179 | 01/08/2024 | 0 | JADAVPUR UNIVERSITY | 17.51 | 0 | 0
1176 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000113/2025-2026 | 942/NKWSMD | 30/06/2025 | 92 | NIM TSHERING LEPCHA | 2.17 | 0 | 0
1177 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000114/2025-2026 | 943/NKWSMD | 30/06/2025 | 92 | NIM TSHERING LEPCHA | 3.61 | 0 | 0
1178 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - II SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000169/2024-2025 | 134/NKWSMD | 28/01/2025 | 546 | SSN DEVELOPERS | 8170.65 | 0 | 15
1179 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months for G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000218/2024-2025 | 146/NKWSMD | 31/01/2025 | 150 | YAMA CONSTRUCTIONS LLP | 0.83 | 0 | 0
1180 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000234/2024-2025 | 413/NKWSMD | 28/03/2025 | 92 | NIM TSHERING LEPCHA | 2.17 | 0 | 0
1181 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000235/2024-2025 | 414/NKWSMD | 28/03/2025 | 92 | NIM TSHERING LEPCHA | 3.61 | 0 | 0
1182 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000128/2023-2024 | 52/NKWSMD | 09/01/2024 | 0 | Resource Division | 13.36 | 0 | 0
1183 | Neorakhola W/S & Mtc.Div. |  | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites),GLRs,Chlorine cum switch room , Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - III SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000107/2024-2025 | 1653/NKWSMD | 11/09/2024 | 546 | YATERI CONSTRUCTIONS,JV OF YAMA CONSTRUCTIONS LLP(LEAD PARTNER),AROGYA ENT & BALAJI CONS. | 6744.68 | 0 | 40
1184 | Neorakhola W/S & Mtc.Div. |  | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/08/2024 to 31/01/2025. Note: With effect from the date of issuing work order. |  |  | ORD/000118/2024-2025 | 1349/NKWSMD | 31/07/2024 | 180 | SUJIT DEB | 0.99 | 0 | 100
1185 | Neorakhola W/S & Mtc.Div. |  | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months, other than G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. |  |  | ORD/000219/2024-2025 | 147/NKWSMD | 31/01/2025 | 150 | SUJIT DEB | 0.83 | 0 | 0
1186 | Neorakhola W/S & Mtc.Div. |  | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1187 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 53/NKWSMD | 09/01/2024 | 0 | Resource Division | 9.98 | 0 | 0
1188 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 1 - Sonada Khasmahal part 1] | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000171/2023-2024 | 915/NKWSMD | 11/08/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1177.68 | 200.66 | 80
1189 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 2 - Sonada Khasmahal part 2] | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000173/2023-2024 | 916/NKWSMD | 11/08/2023 | 605 | M/S. ASHOK KUMAR PERIWAL | 1167.7 | 200.74 | 80
1190 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 3 - Rongmook ceder (part), Oaks (part) & Ringtong tea garden (part)] | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000174/2023-2024 | 917/NKWSMD | 11/08/2023 | 365 | TIKARAM SHARMA | 1263.3 | 301.53 | 85
1191 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000106/2023-2024 | 972/NKWSMD | 21/08/2023 | 0 | Resource Division | 10.32 | 0 | 0
1192 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED RANGMOOK CEDER TEA GARDEN (PART) AND OAKS TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN JOREBUNGLOW SUKHIAPOKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.DTE. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000164/2023-2024 | 912/NKWSMD | 11/08/2023 | 1025 | M/S. ASHOK KUMAR PERIWAL | 2166.21 | 0 | 80
1193 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000109/2023-2024 | 975/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.24 | 0 | 0
1194 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00760/2023-2024 |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0
1195 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00905/2023-2024 | BP-2023-24-497 | 17/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0
1196 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR TINDHARIA & NORBUNG TEA GARDEN WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000010/2025-2026 | 496/NKWSMD | 09/04/2025 | 90 | SUNIT DEEP RAI | 17.57 | 0 | 0
1197 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED TINDHARIA & NARBUNG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSOENG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000166/2023-2024 | 919/NKWSMD | 11/08/2023 | 605 | SUNIT DEEP RAI | 1161.89 | 0 | 100
1198 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000105/2023-2024 | 967/NKWSMD | 21/08/2023 | 0 | Resource Division | 2.14 | 0 | 0
1199 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BHIRGAON DHARAGAON PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000159/2023-2024 | 893/NKWSMD | 07/08/2023 | 180 | RINZI SHERPA | 152.77 | 0 | 60
1200 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | RIMBICK WATER SUPPLY SCHEME FROM PARTHAM KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT-DARJEELING |  | Sub-Assistant Engineer | ORD/000001/2022-2023 | 8/NKWSMD | 04/04/2022 | 180 | NIMA SHERPA | 598.72 | 568.25 | 95
1201 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000043/2022-2023 | 1270/NKWSMD | 05/09/2022 | 0 | Resource Division | 10.06 | 0 | 0
1202 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000103/2022-2023 | 1880/NKWSMD | 15/12/2022 | 0 | Resource Division | 10.08 | 0 | 0
1203 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000163/2022-2023 | 2568/NKWSMD | 17/02/2023 | 0 | Resource Division | 10.08 | 0 | 0
1204 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S. Scheme from Okherbotay Jhora to Dara Gaon Lower Burmek under Munsung G.P. Block II Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | Assistant Engineer-I | Junior Engineer-3 | ORD/000047/2021-2022 | 426/NKWSMD | 07/01/2022 | 90 | DINESH SHERPA | 93.5 | 93.21 | 100
1205 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-3 | RTOR000005/2021-2022 | 639/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.31 | 0 | 0
1206 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
1207 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
1208 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Piped Water Supply Scheme from Sisney and Ankurey Jhora to Nokdara and its adjoining area under Lava- Gitbeong G.P. Block ll, Kalimpong under Jal Swapno Programme within Kalimpong District | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | ORD/000067/2021-2022 | 458/NKWSMD | 14/01/2022 | 90 | DIPESH RAI | 162.74 | 60 | 80
1209 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | RTOR000002/2021-2022 | 636/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.29 | 0 | 0
1210 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0
1211 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
1212 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme from Chamung Khola to Gitdabling Bazar and adjoining area under Gitdabling G.P. Block ll Kalimpong under Jal Swapno Programme within Kalimpong District | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | ORD/000050/2021-2022 | 429/NKWSMD | 07/01/2022 | 1228 | SITA SHARMA | 196.23 | 88.49 | 100
1213 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1214 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-I,Assistant Engineer-III | Junior Engineer-3,Junior Engineer-III | RTOR000013/2021-2022 | 647/NKWSMD | 23/02/2022 | 0 | Resource Division | 1.35 | 0 | 0
1215 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S SCHEME FROM BICHARI DHARA TO LOWER SUNDUNG UNDER PUDUNG G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-II | ORD/000043/2021-2022 | 422/NKWSMD | 07/01/2022 | 1050 | SUNNY CONSTRUCTION | 78.39 | 58.92 | 100
1216 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-II | RTOR000008/2021-2022 | 642/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.38 | 0 | 0
1217 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00496/2023-2024 | BP-2023-24-298 | 07/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 6.07 | 0 | 0
1218 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
1219 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
1220 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | P.W.S. Scheme from Mali khola to Kasmi Forest Village under Bong G.P. Block I, Kalimpong under Jal Jeevan Mission and Jal Swapno Programme | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000066/2021-2022 | 457/NKWSMD | 14/01/2022 | 90 | ANAND MANI PRADHAN | 90.35 | 32.28 | 100
1221 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | P.W.S SCHEME FROM CHISO PANI PEEPAL DHARA TO LAMINI, RAI, DHAJEY GAON UNDER BHALUKHOP G.P. BLOCK-I, KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-I | ORD/000057/2021-2022 | 448/NKWSMD | 14/01/2022 | 90 | SUNIL BAJLA | 192.85 | 185.65 | 100
1222 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-I | RTOR000016/2021-2022 | 650/NKWSMD | 23/02/2022 | 0 | Resource Division | 0.8 | 0 | 0
1223 | Neorakhola W/S & Mtc.Div. |  | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) |  |  | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
1224 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 1379/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.21 | 0 | 0
1225 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | RESTORATION OF ROAD SIDE DRAIN UNDER PWD |  | Sub-Assistant Engineer | BILL/00056/2022-2023 | BP-2022-23-234 | 20/12/2022 | 0 | PWD | 3.95 | 0 | 0
1226 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan M ission and Jal Swapno Pro gramme for Pip e Water Supply Scheme for Sukhia Pokhri Bajar and adjoining area (Augmentation, Extension and Reparing) Darjeeling Div ision.P HED.G .T.A" |  | Sub-Assistant Engineer | VCH/000032/2022-2023 | BP-2022-23-32 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 41.26 | 0 | 0
1227 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme for upper and lower Majuwa, Rangbhang from GairiBass and Gairi Jhora source under Jorebunglo w Su khiapo lhri Block under Darjeeling PHED" |  | Sub-Assistant Engineer | VCH/000111/2022-2023 | BP-2022-23-89 | 14/07/2022 | 0 | MOHAN MUKHIA | 4.34 | 0 | 0
1228 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Left out scheme from Nerola Jhora to Lower Ecchey Block- Kalimpong I, District Kalimpong in connection with Jal Jeevan Mission, under PHED Darjeeling Division-II GTA. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | ORD/000003/2025-2026 | 453/NKWSMD | 02/04/2025 | 60 | DIPENDRA CHETTRI | 8.12 | 0 | 0
1229 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PIPED WATER SUPPLY SCHEME FROM NEROLA JHORA TO LOWER ECHHEY UNDER BLOCK-1 KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-II | Junior Engineer-2,Junior Engineer-II | ORD/000040/2022-2023 | 522/NKWSMD | 25/05/2022 | 60 | SRINIWAS AGARWAL | 84.96 | 55.95 | 70
1230 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Upper Bansbotay, Gram Panchyat -Lodhuma-I, Block Bijanbari -PullBazar. TSM No. 009477 SM Code-SM/08923 |  | Sub-Assistant Engineer | ORD/000076/2022-2023 | 592/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 16.66 | 15.51 | 100
1231 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000029/2022-2023 | 1256/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.17 | 0 | 0
1232 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | The Supply, Installation, commissioning & Monitoring of "Non-Electrical Continuous Chlorinator" approved by Government of India & recommended by National Jal Jeevan Mission (NJJM) supplied through Piped Water Supply Schemes (PWSS) maintained by the Public Health Engineering Department (PHED) Government of West Bengal for a minimum period of 03 (Three) months in the District of Kalimpong under different Schemes (As per Schedule) Tentative number of units:6 Unit (Each Unit containing 2 no of Device) | Assistant Engineer II | Junior Engineer IV | ORD/000046/2023-2024 | 259/NKWSMD | 15/05/2023 | 92 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 31.66 | 0 | 0
1233 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Creating Gravity based piped water supply scheme for Birik Forest Village under Teesta G.P kalimpong Block -I,District- Kalimpong in Copnnection with JJM & Jal Swapna, under Neorakhola w/s & MtC Division , PHE Dte, Kalimpong | Assistant Engineer II | Junior Engineer IV | ORD/000067/2022-2023 | 574/NKWSMD | 26/05/2022 | 90 | HEMANT MOKTAN | 43.83 | 28.68 | 90
1234 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer IV | RTOR000095/2022-2023 | 1372/NKWSMD | 22/09/2022 | 0 | Resource Division | 0.26 | 0 | 0
1235 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WBSEDCL4003424527 |  | Sub-Assistant Engineer | BILL/00643/2024-2025 | BP-2024-25-447 | 28/11/2024 | 0 | WBSEDCL | 0 | 0 | 0
1236 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR 4th DIVISION: PHUBTSHERING TEA GARDEN UNDER JAL SWAPNO PROGRAMME. |  | Sub-Assistant Engineer | ORD/000087/2022-2023 | 614/NKWSMD | 26/05/2022 | 814 | KAMAKHYA ENTERPRISES | 92.66 | 36.34 | 100
1237 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000045/2022-2023 | 1257/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.98 | 0 | 0
1238 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Bungkulung G.P - Dhuptin, Block-Mirik. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000164/2022-2023 | 940 /NKWSMD | 12/07/2022 | 716 | KAMAL PRADHAN | 27.91 | 0 | 98
1239 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Glenburn Singritam, Gram Panchayat - Singritam, Block - Rangli Rangliot. |  | Sub-Assistant Engineer | ORD/000087/2023-2024 | 686/NKWSMD | 12/07/2023 | 269 | PUSHKAR GURUNG | 166.03 | 0 | 92
1240 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000078/2023-2024 | 766/NKWSMD | 19/07/2023 | 0 | Resource Division | 8.61 | 0 | 0
1241 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR GAYABARI BISHACRE (LOWER) UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000275/2022-2023 | 2002/NKWSMD | 23/12/2022 | 930 | KAMAL PRADHAN | 65.73 | 0 | 100
1242 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000153/2022-2023 | 2073/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.28 | 0 | 0
1243 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000231/2022-2023 | 2585/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.49 | 0 | 0
1244 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Augmentation of Surface Water Based Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kurseong Block in Functional Household Tap Connection in Kurseong Block within Darjeeling District under Kurseong Division, PHED-G.T.A. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | ORD/000030/2024-2025 | 1167/NKWSMD | 04/07/2024 | 210 | SHAKTI CONSTRUCTION | 36.03 | 0 | 100
1245 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED PUNKHABARI PWSS TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | ORD/000300/2022-2023 | 2351/NKWSMD | 01/02/2023 | 700 | SHAKTI CONSTRUCTION | 298.42 | 90.06 | 100
1246 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | RTOR000212/2022-2023 | 2560/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.39 | 0 | 0
1247 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED KOPCHI GAON PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer1,Assistant Engineer5 | Junior Engineer1 | ORD/000078/2022-2023 | 601/NKWSMD | 26/05/2022 | 778 | HIMALI CONSTRUCTION COMPANY | 47.25 | 21 | 100
1248 | Neorakhola W/S & Mtc.Div. | Kurseong Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.11.2024 to 31.12.2024. | Assistant Engineer1,Assistant Engineer5 | Junior Engineer1 | ORD/000116/2024-2025 | 2047/NKWSMD | 28/10/2024 | 65 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
1249 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LOWER CHISOPANI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000083/2022-2023 | 606/NKWSMD | 26/05/2022 | 930 | NARESH RAI | 69.92 | 46.79 | 100
1250 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000072/2022-2023 | 1316/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.52 | 0 | 0
1251 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000137/2022-2023 | 2057/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.52 | 0 | 0
1252 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR TINDHARIA TEA ESTATE WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000011/2025-2026 | 497/NKWSMD | 09/04/2025 | 180 | SUNIT DEEP RAI | 65.5 | 0 | 0
1253 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED TINDHARIA TEA ESTATE PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000081/2022-2023 | 604/NKWSMD | 26/05/2022 | 240 | KARUNAMAYA ENTERPRISES | 108.97 | 38.82 | 80
1254 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000139/2022-2023 | 1259/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.47 | 0 | 0
1255 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM DORKHOLA TO LUNGSEL UNDER KALIMPONG GORUBATHAN BLOCK UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000045/2022-2023 | 527/NKWSMD | 25/05/2022 | 180 | SRINIWAS AGARWAL | 197.08 | 149.04 | 98
1256 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00588/2023-2024 | BP-2023-24-381 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1257 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00589/2023-2024 | BP-2023-24-382 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1258 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00590/2023-2024 | BP-2023-24-383 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1259 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00591/2023-2024 | BP-2023-24-384 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1260 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00592/2023-2024 | BP-2023-24-385 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1261 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation Of ODEX Tube Well based 02(Two) number of pipe water supply Scheme having provision of 2(Two) number of RCC OHR viz 300 Cum & 200Cum and other related works for 6(Six) villages in GTA Area. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000094/2022-2023 | 825/NKWSMD | 30/06/2022 | 900 | M/S KAMAK ENGINEERS AND CO. | 783.01 | 100 | 100
1262 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
1263 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000160/2022-2023 | 2371/NKWSMD | 03/02/2023 | 0 | Resource Division | 3.6 | 0 | 0
1264 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SURFACE WATER BASED TOROYOK KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION ((FHTC) IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000049/2025-2026 | 638/NKWSMD | 05/05/2025 | 90 | SURAJMULL PRABHUDAYAL | 22.11 | 0 | 100
1265 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000001/2023-2024 | 59/NKWSMD | 24/04/2023 | 0 | Resource Division | 0.5 | 0 | 0
1266 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Leftout Scheme Proposed Pumping Based Water Supply Scheme for BANGLA JHORA TO JOGITAR, Gorubathan Block in the District of Kalimpong in connection with Jal Jeean Mission, under PHED Darjeeling Division-II GTA. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000005/2025-2026 | 459/NKWSMD | 03/04/2025 | 60 | SATEN LAMA | 12.78 | 0 | 0
1267 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM BANGLA JHORA TO JOGITAR UNDER GORUBATHAN BLOCK KALIMPONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer-III | Junior Engineer-4,Junior Engineer-I | ORD/000041/2022-2023 | 523/NKWSMD | 25/05/2022 | 810 | M/S R.S. CONSTRUCTION | 48.43 | 12.32 | 100
1268 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty (Lower kharaya and upper Kharaya Busty habitaion) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | ORD/000118/2022-2023 | 799/NKWSMD | 30/06/2022 | 60 | SAI ENTERPRISE | 16.5 | 16.03 | 100
1269 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | RTOR000051/2022-2023 | 1295/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.44 | 0 | 0
1270 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme for including augmentatin work for PWS scheme for okaity ward no. 03 Gram panchyat PGSD-I, Block-Mirik TSM No. 009304 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000012/2022-2023 | 784/NKWSMD | 30/06/2022 | 60 | ROSHAN BISWAKARMA | 7.58 | 7.55 | 0
1271 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000068/2022-2023 | 1312/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.28 | 0 | 0
1272 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Ektis Goan: Gram Panchyat-Paila Goan School Dara-I, Block- Mirik TSM No. 009307 SM Code-SM/08942 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000014/2022-2023 | 786/NKWSMD | 30/06/2022 | 60 | PUSHKAR GURUNG | 20.13 | 20.12 | 0
1273 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000067/2022-2023 | 1311/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.27 | 0 | 0
1274 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Manju Dara Gaon: Gram Panchyat- Soureni-II , Block Mirik TSM No. 009483 SM Code-SM/08950 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000018/2022-2023 | 780/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 5.33 | 5.11 | 100
1275 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000146/2022-2023 | 837/KWSMD | 30/06/2022 | 60 | MS JAGANNATH PRASAD | 23.75 | 22.99 | 100
1276 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000062/2022-2023 | 1306/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.5 | 0 | 0
1277 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Leftout Estimate for Piped Water Supply Scheme from under Mezeko Forest, Samthar G.P, Block:-Kalimpong-I P.S:- Kalimpong District:Kalimpong. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-II | ORD/000138/2024-2025 | 2329/NKWSMD | 17/12/2024 | 60 | D AND B GRACE | 5.88 | 0 | 0
1278 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SEPKHOLA PIPED WATER SUPPLY SCHEME UNDER MAZEOK FOREST VILLAGE, SAMTHAR G.P, Kalimpong Block-I, Under Neorakhola Water Supply & Maintainance Division, PHE Dte, Kalimpong. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-4,Junior Engineer-II | ORD/000230/2022-2023 | 1444/NKWSMD | 28/09/2022 | 270 | D AND B GRACE | 40.88 | 18.08 | 95
1279 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUN TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000233/2022-2023 | 1449/NKWSMD | 29/09/2022 | 850 | SRINIWAS AGARWAL | 748.35 | 655.64 | 99
1280 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000111/2022-2023 | 1888/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.24 | 0 | 0
1281 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000170/2022-2023 | 2607/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.24 | 0 | 0
1282 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme for MIM Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000255/2022-2023 | 1618/NKWSMD | 03/11/2022 | 360 | GARGO TRADERS | 1270.33 | 1164.42 | 95
1283 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000119/2022-2023 | 1896/NKWSMD | 15/12/2022 | 0 | Resource Division | 6.1 | 0 | 0
1284 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000178/2022-2023 | 2612/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.1 | 0 | 0
1285 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Musey Khola Gaon, Dokan Dhura. School Dhura Gram Panchayat - Maneydanra, Block - Rungli Rungliot. |  |  | ORD/000230/2023-2024 | 1306/NKWSMD | 31/10/2023 | 792 | JANG BAHADUR GURUNG | 46.23 | 0 | 100
1286 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Jholy Busty, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000178/2022-2023 | 954/NKWSMD | 12/07/2022 | 60 | BIRU KHAWAS | 38.21 | 36.13 | 100
1287 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000144/2022-2023 | 2064/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.59 | 0 | 0
1288 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Sittong - III Naspatti Gaon with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000177/2022-2023 | 953/NKWSMD | 12/07/2022 | 240 | MS. SURYA I PVT. LTD COMPANY | 62.8 | 0 | 82
1289 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000145/2022-2023 | 2065/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.23 | 0 | 0
1290 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | new connection | Assistant Engineer I | Junior Engineer III | BILL/00009/2023-2024 | BP-2023-24-5 | 25/04/2023 | 0 | WBSEDCL | 0.44 | 0 | 0
1291 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Mayrong Forest & Tendrabong Village (Partly) under Sakyong G.P, Block- Kalimpong-II, under Neorakhola Water Supply & Maintenence Division, P.H.Engineering Directorate, District-Kalimpong. | Assistant Engineer I | Junior Engineer III | ORD/000225/2022-2023 | 1155/NKWSMD | 12/08/2022 | 180 | JUSTINE BHUTIA | 186.36 | 79.31 | 75
1292 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR MOONDA KOTHI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING UNDER KURSEONG DIVISION PHED GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000033/2025-2026 | 635/NKWSMD | 05/05/2025 | 90 | SRINIWAS AGARWAL | 38.65 | 0 | 0
1293 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MOONDA KOTTE TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000337/2022-2023 | 2734/NKWSMD | 03/03/2023 | 545 | SRINIWAS AGARWAL | 1366.07 | 796.02 | 70
1294 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000253/2022-2023 | 2746/NKWSMD | 06/03/2023 | 0 | Resource Division | 7.15 | 0 | 0
1295 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.08.2024 to 31.08.2024 |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000097/2024-2025 | 1347/NKWSMD | 31/07/2024 | 31 | YAMA CONSTRUCTIONS LLP | 0.2 | 0 | 100
1296 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR PARMAGURI KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000238/2022-2023 | 1454/NKWSMD | 29/09/2022 | 300 | MADAN SHARMA | 1011.5 | 815.24 | 99
1297 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000117/2022-2023 | 1894/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.56 | 0 | 0
1298 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000176/2022-2023 | 2608/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.56 | 0 | 0
1299 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1300 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000276/2022-2023 | 2003/NKWSMD | 23/12/2022 | 180 | SRINIWAS AGARWAL | 280.33 | 141.65 | 80
1301 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000230/2022-2023 | 2603/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.22 | 0 | 0
1302 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR PANKHASARI KHASMAHAL (PART) UNDER GORUBATHAN II G.P, BLOCK : GORUBATHAN, DISTRICT:KALIMPONG | Assistant Engineer II | Junior Engineer III | ORD/000327/2022-2023 | 2660/NKWSMD | 28/02/2023 | 480 | THUPDEN BHUTIA | 200.56 | 0 | 97
1303 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer III | RTOR000247/2022-2023 | 2709/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.02 | 0 | 0
1304 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer II | Junior Engineer III | RTOR000256/2022-2023 | 2774/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.02 | 0 | 0
1305 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | GORUBATHAN KHASMAHAL PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME, UNDER BLOCK:- GORUBATHAN. DISTRICT:- KALIMPONG. | Assistant Engineer-I | Junior Engineer-4 | ORD/000092/2023-2024 | 716/NKWSMD | 18/07/2023 | 365 | M/S R.S. CONSTRUCTION | 1121.37 | 0 | 15
1306 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000073/2023-2024 | 772/NKWSMD | 19/07/2023 | 0 | Resource Division | 11.19 | 0 | 0
1307 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1308 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME UNDER BLOCK KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000035/2025-2026 | 651/NKWSMD | 05/05/2025 | 180 | MAGMA CONSORTIUM | 61.66 | 0 | 0
1309 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000316/2022-2023 | 2520/NKWSMD | 15/02/2023 | 1275 | VINAYAK CONSTRUCTION | 1768.52 | 1015.99 | 85
1310 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000210/2022-2023 | 2558/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.83 | 0 | 0
1311 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000242/2022-2023 | 2715/NKWSMD | 03/03/2023 | 0 | Resource Division | 5.83 | 0 | 0
1312 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
1313 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | BILL/00962/2023-2024 | BP-2023-24-650 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 5.55 | 0 | 0
1314 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | ORD/000268/2023-2024 | 1578/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1315 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED GRAVITY BASED & PUMPING BASED PIPED WATER SUPPLY SCHEME FOR SANTUK KHASMAHAL UNDER BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | Assistant Engineer-III | Junior Engineer-3,Junior Engineer-I | ORD/000312/2022-2023 | 2492/NKWSMD | 09/02/2023 | 665 | JUSTINE BHUTIA | 676.59 | 0 | 92
1316 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work of Piped Water Supply Scheme for Bloomfield Tea Garden Piped Water Supply Scheme in Pulbazar Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000002/2024-2025 | 966/NKWSMD | 14/06/2024 | 198 | HARI PRASAD CHETTRI | 59.7 | 0 | 100
1317 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BLOOMFIELD PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000097/2023-2024 | 720/NKWSMD | 18/07/2023 | 540 | HARI PRASAD CHETTRI | 369.22 | 0 | 100
1318 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.09.2024 to 31.10.2024. |  | Sub-Assistant Engineer | ORD/000104/2024-2025 | 1550/NKWSMD | 30/08/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
1319 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000088/2023-2024 | 812/NKWSMD | 24/07/2023 | 0 | Resource Division | 3.42 | 0 | 0
1320 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR RESHOP BAZAR PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Junior Engineer6,Sub-Assistant Engineer | ORD/000024/2023-2024 | 123/NKWSMD | 28/04/2023 | 605 | VAISHNO CONSTRUCTION | 416.96 | 0 | 100
1321 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer6,Sub-Assistant Engineer | RTOR000016/2023-2024 | 214/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.11 | 0 | 0
1322 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR OKAITY TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00216/2024-2025 | BP-2024-25-172 | 01/08/2024 | 0 | WBSEDCL | 50.95 | 0 | 0
1323 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000029/2023-2024 | 248/NKWSMD | 12/05/2023 | 0 | Resource Division | 7.85 | 0 | 0
1324 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED LINGSAY KHASMAHAL PIPED WATER SUPPLY SCHEME, UNDER KALIMPONG G.P, BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG. | Assistant Engineer-I | Junior Engineer-4 | ORD/000052/2023-2024 | 412/NKWSMD | 05/06/2023 | 910 | M/S. ASHOK KUMAR PERIWAL | 926.38 | 0 | 80
1325 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000053/2023-2024 | 448/NKWSMD | 07/06/2023 | 0 | Resource Division | 6.24 | 0 | 0
1326 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Demand raised for forest clearance of JJM scheme under Kalimpong Division PHED | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00456/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | WEST BENGAL PARIVESH CAMPA | 16.72 | 0 | 0
1327 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | FOREST PAYMENT | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | BILL/00961/2023-2024 | BP-2023-24-645 | 28/03/2024 | 0 | WEST BENGAL PARIVESH CAMPA | 11.59 | 0 | 0
1328 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | PROPOSED GRAVITY BASED PIPED WATER SUPPLY SCHEME FOR RANGPO FOREST PIPED WATER SUPPLY SCHEME, UNDER SANGASEY G.P BLOCK : KALIMPONG - II, DISTRICT:KALIMPONG | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000008/2023-2024 | 97/NKWSMD | 28/04/2023 | 752 | SANTOSH TAMANG | 259.19 | 0 | 90
1329 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05(five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | ORD/000272/2023-2024 | 1593/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1330 | Neorakhola W/S & Mtc.Div. | Kalimpong Division | Material Requisition To Resource Division | Assistant Engineer-IV | Junior Engineer-2,Junior Engineer-II | RTOR000021/2023-2024 | 206/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.27 | 0 | 0
1331 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOY DHURA TEA GARDEN IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000032/2025-2026 | 633/NKWSMD | 05/05/2025 | 180 | MS CHAMLING CONSTRUCTION | 66.89 | 0 | 0
1332 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SEPOYDHURA (ST MARYS -I) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000332/2022-2023 | 2706/NKWSMD | 02/03/2023 | 760 | SHAKTI CONSTRUCTION | 442.13 | 0 | 90
1333 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000250/2022-2023 | 2727/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.33 | 0 | 0
1334 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000260/2022-2023 | 2778/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.33 | 0 | 0
1335 | Neorakhola W/S & Mtc.Div. | Kurseong Division | MONGPOO CINKONA PLANTATION PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME. | Assistant Engineer1 | Junior Engineer4 | ORD/000010/2023-2024 | 98/NKWSMD | 28/04/2023 | 830 | VAISHNO CONSTRUCTION | 230.27 | 0 | 100
1336 | Neorakhola W/S & Mtc.Div. |  | Creating gravity based Provision Of Drinking water from spring water source Tashiding forest village under Tashiding Gram Panchayat under Kalimpong Block-I in the District of Kalimpong Under Neorakhola water Supply Division ,Kalimpong PHE Dte |  |  | ORD/000065/2022-2023 | 572/NKWSMD | 26/05/2022 | 267 | SONAM TSHERING LEPCHA | 10.2 | 0 | 75
1337 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 1554/NKWSMD | 19/10/2022 | 0 | Resource Division | 0.08 | 0 | 0
1338 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED EDENVALE TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000160/2023-2024 | 894/NKWSMD | 07/08/2023 | 180 | YAMA CONSTRUCTIONS LLP | 139.48 | 49.77 | 50
1339 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000124/2023-2024 | 1298/NKWSMD | 30/10/2023 | 0 | Resource Division | 0.67 | 0 | 0
1340 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME AT LOWER SIRUBARI WITH FUNCTIONAL HOUSEHOLD TAP CONNECTION UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME UNDER KURSEONG DIVISION PHED-GTA, DARJEELING. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000269/2022-2023 | 1748/NKWSMD | 25/11/2022 | 60 | BITIS PRADHAN AND BROTHERS | 24.69 | 0 | 100
1341 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000265/2022-2023 | 2813/NKWSMD | 14/03/2023 | 0 | Resource Division | 0.46 | 0 | 0
1342 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MALUTAR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000048/2025-2026 | 637/NKWSMD | 05/05/2025 | 60 | SURAJMULL PRABHUDAYAL | 13.02 | 0 | 100
1343 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000154/2023-2024 | 882/NKWSMD | 03/08/2023 | 365 | SHAKTI CONSTRUCTION | 1026.53 | 0 | 100
1344 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Work for Proposed Surface Water Based Yakprintam Khasmahal (Part) Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kalimpong-I, Block within Kalimpong District under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate. | Assistant Engineer I | Junior Engineer III | ORD/000061/2024-2025 | 1325/NKWSMD | 29/07/2024 | 180 | RELLI PALA CONSTRUCTION | 20.76 | 0 | 100
1345 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED SURFACE WATER BASED YAKPRINTAM KHASMAHAL (part) PWSS TO ACCOMMODATE FHTC IN KALIMPONG-I BLOCK WITHIN KALIMPONG DISTRICT UNDER NEORAKHOKA W/S & MTC. DIVISION, PHE DTE. | Assistant Engineer I | Junior Engineer III | ORD/000139/2022-2023 | 830/NKWSMD | 30/06/2022 | 810 | SANTOSH TAMANG | 127.14 | 109.46 | 95
1346 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1347 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOYDHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST UNDER KURSEONG DIVISION, PHED-GTA | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000046/2025-2026 | 634/NKWSMD | 05/05/2025 | 180 | VAJRA ENTERPRISES | 59.3 | 0 | 95
1348 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SEPOYDHURA (D.R.) TEA GARDEN, KHARIA BUSTY CHAITAPANI TEA GARDEN & BAMAN DHURA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000167/2023-2024 | 920/NKWSMD | 11/08/2023 | 645 | SHAKTI CONSTRUCTION | 1345.85 | 475 | 50
1349 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000108/2023-2024 | 969/NKWSMD | 21/08/2023 | 0 | Resource Division | 4.73 | 0 | 0
1350 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00821/2023-2024 | BP-2023-24-530 | 26/02/2024 | 0 | WBSEDCL | 6.32 | 0 | 0
1351 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MANJUA FOREST SOURINI-II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000027/2025-2026 | 595/NKWSMD | 29/04/2025 | 60 | ALLIED INSTRUMENTS | 13.7 | 0 | 0
1352 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MANJUA FOREST SOURENI -II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000035/2023-2024 | 109/NKWSMD | 28/04/2023 | 635 | MAA MANASA VYAPAAR | 1093.84 | 440 | 50
1353 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000028/2023-2024 | 245/NKWSMD | 12/05/2023 | 0 | Resource Division | 5.91 | 0 | 0
1354 | Neorakhola W/S & Mtc.Div. |  | Submission of Topo Survey report, Design and Drawing of all components of the whole project including final as built drawing after being vetted by the recognised Government Institute and getting necessary approval from the Expert Committee for Augmentation of source Cum creation of spring water storage of 80ml water for improvement of and upgradation of open ground Reservoir /Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I, & Kalimpong Block-II, under Neorakhola Water Supply Scheme. |  |  | ORD/000131/2024-2025 | 2230/NKWSMD | 09/12/2024 | 30 | THUPDEN BHUTIA | 28.69 | 0 | 100
1355 | Neorakhola W/S & Mtc.Div. |  | Augmentation of source cum creation of spring water storage of 80 ML water by improvement of and upgradation of Open Ground Reservoir / Lake at 3.2 Km from Algarah and other allied works to cover the uncovered areas of Kalimpong Block-I & Kalimpong Block-II under Neorakhola Water Supply Scheme. |  |  | ORD/000238/2023-2024 | 1501/NKWSMD | 06/12/2023 | 725 | TAJ CONSTRUCTION | 3802.55 | 0 | 25
1356 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00956/2023-2024 | BP-2023-24-658 | 23/03/2024 | 0 | WBSEDCL | 12.27 | 0 | 0
1357 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MIRIK KHASMAHAL (P) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000165/2023-2024 | 918/NKWSMD | 11/08/2023 | 365 | SHAKTI CONSTRUCTION | 1224.81 | 0 | 90
1358 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000091/2023-2024 | 973/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.04 | 0 | 0
1359 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
1360 | Neorakhola W/S & Mtc.Div. |  | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1361 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR GROUND WATER RESERVOIR HAVING CAPACITY OF 20 ML AT DURPIN LAKE TO ACCOMMODATE 5 MOUZAS IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. |  |  | ORD/000058/2025-2026 | 826/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 318.4 | 0 | 0
1362 | Neorakhola W/S & Mtc.Div. |  | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 5 Mouzas in Kurseong Block within Darjeeling District under Kurseong Division, P.H.E.D- GTA. |  |  | ORD/000267/2023-2024 | 100/NKWSMD | 15/01/2024 | 765 | INTERIOR'S NEST | 2672.64 | 0 | 35
Total | [10 empty] | 258716.94 | 48991.62