## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Malda Division | Chanchal Sub-Division | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Bakhra Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer |  | ORD/000231/2025-2026 | 4235/MD | 29/08/2025 | 60 | M/S N. N. ENTERPRISE | 32.31 | 0 | 0
2 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000568/2020-2021 | 2464/MD | 12/10/2020 | 30 | UTTAM KUMAR GHOSH | 57.92 | 7.52 | 0
3 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bakhra Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer |  | ORD/000739/2024-2025 | 58 | 08/01/2025 | 45 | M/S N. N. ENTERPRISE | 28.26 | 0 | 0
4 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000007/2024-2025 | 3919/MD | 06/08/2024 | 0 | Resource Division | 4 | 0 | 0
5 | Malda Division | Malda Sadar Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of GOBINDAPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000058/2020-2021 | 2262/MD | 29/09/2020 | 45 | UTTAM KUMAR DUTTA | 60.07 | 103.06 | 1
6 | Malda Division | Malda Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gobindapur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000278/2024-2025 | 3198/MD | 27/06/2024 | 476 | ANJIMA CONSTRUCTION CO. | 10.56 | 0 | 0
7 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Gourhanda Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000163/2025-2026 | 2876/MD | 17/06/2025 | 60 | M/S KUNDU CONSTRUCTION | 60.09 | 0 | 0
8 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOUR HANDA Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000168/2020-2021 | 2721/MD | 10/11/2020 | 45 | SUBHAS CHANDRA KESHARI | 74.49 | 45.41 | 0
9 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Gourhanda Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000850/2024-2025 | 1043/MD | 18/03/2025 | 75 | MATIUR RAHAMAN | 32.5 | 0 | 0
10 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Gourhanda & Jalalpur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Junior Engineer | ORD/000946/2024-2025 | 635/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.9 | 0 | 0
11 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Junior Engineer | RTOR000010/2024-2025 | 3922/MD | 06/08/2024 | 0 | Resource Division | 8.62 | 0 | 0
12 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. |  |  | ORD/000029/2020-2021 | 1964/MD | 31/08/2020 | 30 | M/S KUNDU CONSTRUCTION | 39.43 | 78 | 1
13 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000719/2023-2024 | 4768/MD | 05/12/2023 | 45 | M/S SINHA ENTERPRISE | 16.09 | 0 | 100
14 | Malda Division | Chanchal Sub-Division | Sinking of 01 (One) Nos. 250mm. Dia. x 200 mm. Big dia. Tube Well 131 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with 2nd Tube Well Site at Talbangura Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00673/2024-2025 | 464/DW | 25/09/2024 | 0 | A. L. ENGINEERING SOLUTION | 3.98 | 0 | 0
15 | Malda Division | Chanchal Sub-Division | Formal work order for Providing house connection under RANGHAT Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000015/2020-2021 | 2038/MD | 10/09/2020 | 120 | PROJECT INDIA | 94.64 | 8.18 | 100
16 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000558/2020-2021 | 2436/MD | 12/10/2020 | 120 | M/S TRILOCHAN CONSTRUCTION CO | 12 | 13.18 | 1
17 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000722/2021-2022 | 48/1/MD | 13/01/2022 | 30 | BIDYUT MAHALDAR | 0.39 | 0.39 | 100
18 | Malda Division | Chanchal Sub-Division | Testing of HDPE pipe 20 mm as per IS 4984:2016 reg. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | VCH/000108/2021-2022 | 44 | 07/05/2021 | 0 | CIPET EXTN CENTRE | 0.22 | 0 | 0
19 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000077/2020-2021 | 2465/MD | 12/10/2020 | 45 | UTTAM KUMAR GHOSH | 70.72 | 96.83 | 1
20 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer |  | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 0 | 1
21 | Malda Division | Malda Mechanical Division | Laying of Distribution Line, Providing FHTC, Construction of Pump House at Daudpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000143/2024-2025 | 2902/MD | 07/06/2024 | 420 | M/S MOON LIGHT CONSTRUCTION & CO. | 93.32 | 0 | 51
22 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of DAUDPUR & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000288/2022-2023 | 2234/MD | 16/09/2022 | 45 | M/S. TEWARI CONSTRUCTION | 6.19 | 0 | 0
23 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) Nos. 250mm. Dia. x 150mm. Big dia. Tube Well 160 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer at Daudpur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000289/2022-2023 | 2235/MD | 16/09/2022 | 15 | SNEHASISH GHOSH | 8.09 | 0 | 100
24 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Daudpur PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000303/2024-2025 | 4741/MD | 11/09/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 0
25 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DAUDPUR ZONE-I Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000388/2023-2024 | 3288/MD | 23/08/2023 | 952 | A. K. CONSTRUCTION | 151.6 | 0 | 60
26 | Malda Division | Malda Mechanical Division | Sinking of 200 mm (all through) Big dia. Tube Well of 160 m Deep by D.R Rig. Method using P.V.C. pipe & Filter including Supply of materials at head work site under DAUDPUR Water Supply Scheme of Chanchal-I Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000467/2024-2025 | 4822/MD | 13/09/2024 | 30 | SAUDAGAR INDIA | 10.21 | 0 | 0
27 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000762/2024-2025 | 71 | 13/01/2025 | 45 | THREE BROTHERS CONSTRUCTION & CO | 31.61 | 0 | 0
28 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000867/2024-2025 | 1223/MD | 26/03/2025 | 30 | M/S MADHU CONSTRUCTION | 19.79 | 0 | 0
29 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | RTOR000026/2022-2023 | 2756/MD | 22/11/2022 | 0 | Resource Division | 34.78 | 0 | 0
30 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | RTOR000129/2023-2024 | 99/MD | 05/01/2024 | 0 | Resource Division | 4.93 | 0 | 0
31 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000040/2023-2024 | 1947/MD | 16/05/2023 | 1136 | UTTAM KUMAR GHOSH | 399.3 | 177.48 | 75
32 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Kariali Zone-II PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000595/2024-2025 | 5599/MD | 05/11/2024 | 60 | DIPU DUTTA | 4.53 | 0 | 0
33 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000607/2024-2025 | 5603/MD | 05/11/2024 | 60 | GULJAR CONSTRUCTION | 6.93 | 0 | 0
34 | Malda Division | Malda Mechanical Division | Sinking of 200mm (all through) Big dia. Tube Well of 150m Deep at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000609/2024-2025 | 5605/MD | 05/11/2024 | 45 | SAUDAGAR INDIA | 9.82 | 0 | 0
35 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC Pipe line of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000612/2023-2024 | 4141/MD | 11/10/2023 | 30 | S.S.GHOSH ENTERPRISE & CO. | 2.13 | 0 | 80
36 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000635/2024-2025 | 5914/MD | 26/11/2024 | 521 | UTTAM KUMAR GHOSH | 27.23 | 0 | 0
37 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-II Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000692/2021-2022 | 657/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 2.76 | 2.73 | 1
38 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000954/2023-2024 | 699/MD | 09/02/2024 | 843 | UTTAM KUMAR GHOSH | 16.32 | 0 | 0
39 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Kandaran Zone-II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000955/2023-2024 | 700/MD | 09/02/2024 | 737 | UTTAM KUMAR GHOSH | 22.42 | 0 | 0
40 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000060/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 16.83 | 0 | 0
41 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000179/2023-2024 | 756/MD | 19/02/2024 | 0 | Resource Division | 4.31 | 0 | 0
42 | Malda Division | Malda Mechanical Division | Placement of fund against the work for road restoration for laying pipe line for Eklakhi to Rashikpur road from 2.400 KM to 7.900 Km under AKALPUR PWSS under Malda Division,PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | BILL/00515/2024-2025 | BP-2024-25-252 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 9.95 | 0 | 0
43 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Akalpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000209/2024-2025 | 3030/MD | 13/06/2024 | 30 | BENGAL ENGINEERING COMPANY | 15.69 | 0 | 0
44 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at AKALPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000309/2022-2023 | 2304/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9.04 | 9.03 | 1
45 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of AKALPUR Water Supply Scheme of Gazole Block. under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000345/2022-2023 | 3113/MD | 20/12/2022 | 45 | THREE BROTHERS CONSTRUCTION & CO | 6.69 | 6.67 | 0
46 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for AKALPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000359/2022-2023 | 2508/MD | 03/11/2022 | 45 | M/S. TEWARI CONSTRUCTION | 28.05 | 23.11 | 1
47 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Akalpur Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000598/2024-2025 | 5936/MD | 27/11/2024 | 90 | S. N. CONSTRUCTION | 42.82 | 0 | 0
48 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000016/2022-2023 | 2411/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
49 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of SWARUPGANJ Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000106/2023-2024 | 2333/MD | 08/06/2023 | 60 | ABANI BHUSAN GHOSH | 52.67 | 0 | 65
50 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube well site of Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000606/2024-2025 | 5602/MD | 05/11/2024 | 60 | BANIK BROTHERS | 6.93 | 0 | 0
51 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SWARUPGANJ Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000615/2022-2023 | 952/MD | 28/02/2023 | 1119 | BANIK BROTHERS | 469.75 | 91.75 | 75
52 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000756/2024-2025 | 74 | 13/01/2025 | 261 | BANIK BROTHERS | 83.72 | 0 | 0
53 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of SWARUPGANJ Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000917/2023-2024 | 379/MD | 17/01/2024 | 45 | BANIK BROTHERS | 21.73 | 0 | 0
54 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000076/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 23.46 | 0 | 0
55 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000178/2023-2024 | 755/MD | 19/02/2024 | 0 | Resource Division | 12.32 | 0 | 0
56 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DAKSHIN BHAKURIA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000234/2023-2024 | 2707/MD | 14/07/2023 | 270 | MOTI RAHAMAN | 202.31 | 0 | 42
57 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000366/2022-2023 | 2695/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 0 | 80
58 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Dakshin Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000490/2024-2025 | 5003/MD | 27/09/2024 | 45 | M/S TEWARI CONSTRUCTION | 32.97 | 0 | 0
59 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000078/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 9.78 | 0 | 0
60 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000135/2023-2024 | 114/MD | 05/01/2024 | 0 | Resource Division | 3.7 | 0 | 0
61 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of TALPUKUR Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000043/2023-2024 | 1899/MD | 10/05/2023 | 1025 | BANIK BROTHERS | 523.57 | 327.72 | 71
62 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well Site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000163/2024-2025 | 2938/MD | 10/06/2024 | 30 | BANIK BROTHERS | 8.99 | 0 | 100
63 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000662/2024-2025 | 6162/MD | 05/12/2024 | 45 | IDEAL CONSTRUCTION | 26.03 | 0 | 0
64 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000883/2023-2024 | 159/MD | 08/01/2024 | 45 | BANIK BROTHERS | 22.15 | 0 | 100
65 | Malda Division | RWS Malda Sub-Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Chaksukur, Dalla, Talpukur, Aiho PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000955/2024-2025 | 644/MD | 19/02/2025 | 7 | SADHANA CONSTRUCTION | 0.81 | 0 | 0
66 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000025/2023-2024 | 1605/MD | 11/04/2023 | 0 | Resource Division | 13.49 | 0 | 0
67 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000032/2022-2023 | 3044/MD | 12/12/2022 | 0 | Resource Division | 15.84 | 0 | 0
68 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of ARAZI JALSA Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000046/2023-2024 | 2008/MD | 17/05/2023 | 1108 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1160.94 | 248.24 | 65
69 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000265/2024-2025 | 3213/MD | 27/06/2024 | 461 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.89 | 0 | 70
70 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 10/05/2024 to 19/06/2024=41 Days). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000576/2024-2025 | 2421/MD | 09/05/2024 | 41 | TARUN KUMAR BHATTACHARYA | 0.19 | 0 | 0
71 | Malda Division | Malda Mechanical Division | Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 20/06/2024 to 16/12/2024=180 Days). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000577/2024-2025 | 3108/MD | 18/06/2024 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 0 | 0
72 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000634/2024-2025 | 5913/MD | 26/11/2024 | 354 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.74 | 0 | 0
73 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000054/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.31 | 0 | 0
74 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000096/2023-2024 | 29/MD | 04/01/2024 | 0 | Resource Division | 20.4 | 0 | 0
75 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SULTANNAGAR Water Supply Scheme at HARISHCHANDRAPUR-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000030/2023-2024 | 1845/MD | 02/05/2023 | 1065 | M/S ALISA CONSTRUCTIION | 289.64 | 0 | 89
76 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SULTANNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000370/2022-2023 | 2699/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 8.55 | 1
77 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SULTANNAGAR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000605/2022-2023 | 923/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.13 | 10.13 | 100
78 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000819/2022-2023 | 519/MSD | 30/12/2022 | 182 | ARUN KUMAR DAS | 0.86 | 0 | 71
79 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000013/2023-2024 | 1620/MD | 11/04/2023 | 0 | Resource Division | 10.22 | 0 | 0
80 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000037/2022-2023 | 3049/MD | 12/12/2022 | 0 | Resource Division | 25.94 | 0 | 0
81 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000054/2023-2024 | 1985/MD | 17/05/2023 | 45 | HIRAK ROY CHOUDHURY | 8.28 | 8.27 | 100
82 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 3 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000137/2025-2026 | 2615/MD | 02/06/2025 | 135 | M/S PARIMAL DAS | 17.27 | 0 | 0
83 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 4 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000138/2025-2026 | 2616/MD | 02/06/2025 | 135 | M/S PARIMAL DAS | 17.27 | 0 | 0
84 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000376/2022-2023 | 2702/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.42 | 8.42 | 1
85 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-4) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000377/2022-2023 | 2703/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.42 | 8.42 | 1
86 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-15 Samsabad, JL-20 Kadamtali, JL-21 Badanpur, JL-22 Chhotapara, JL-23 Lakshmi Kandar and JL-27 Rahutgaon) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000411/2022-2023 | 2985/MD | 07/12/2022 | 45 | MANIK CHOUDHURY | 55.22 | 51.22 | 100
87 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-11 Tutkhan, JL-12 Goalpara, and JL-14 Gotpara) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000412/2022-2023 | 2986/MD | 07/12/2022 | 45 | M/S PARIMAL DAS | 56.72 | 53.93 | 1
88 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Mekpur Water Supply scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000843/2024-2025 | 1068/MD | 19/03/2025 | 60 | S. R. ENTERPRISE | 8.04 | 0 | 0
89 | Malda Division | Malda Mechanical Division | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for MEKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000973/2023-2024 | 870/MD | 27/02/2024 | 45 | S. R. ENTERPRISE | 6.07 | 0 | 100
90 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Goalpara Mouza under Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001012/2023-2024 | 1514/MD | 16/03/2024 | 30 | S. N. CONSTRUCTION | 11.32 | 0 | 100
91 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SAIDPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000118/2023-2024 | 2320/MD | 08/06/2023 | 930 | NEOGI ENTERPRISE | 651.25 | 0 | 60
92 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000182/2024-2025 | 2957/MD | 10/06/2024 | 30 | SAYEM ENTERPRISE | 7.16 | 0 | 100
93 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000669/2024-2025 | 6168/MD | 05/12/2024 | 345 | ANJIMA CONSTRUCTION CO. | 22.39 | 0 | 0
94 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000048/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 20.1 | 0 | 0
95 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000158/2023-2024 | 240/MD | 10/01/2024 | 0 | Resource Division | 12.66 | 0 | 0
96 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of BIHARI ZONE-I Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. |  |  | ORD/000130/2020-2021 | 2440/MD | 12/10/2020 | 30 | BEE GEE CONSTRUCTION | 36.34 | 31.32 | 0
97 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI ZONE-II Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. |  |  | ORD/000135/2020-2021 | 2445/MD | 12/10/2020 | 30 | M/S SABANA CONSTRUCTION | 31.87 | 33.04 | 1
98 | Malda Division |  | Laying of Parallel/ Dedicated Pipeline for better Functionality at Bihari Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000230/2025-2026 | 4234/MD | 29/08/2025 | 60 | S. R. ENTERPRISE | 12.42 | 0 | 0
99 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BIHARI ZONE-II Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000725/2023-2024 | 4774/MD | 05/12/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.21 | 0 | 98
100 | Malda Division |  | Construction of Boundary Wall at 2nd Tube Well site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000126/2025-2026 | 2484/MD | 28/05/2025 | 60 | A. L. ENGINEERING SOLUTION | 6.45 | 0 | 0
101 | Malda Division |  | Construction of Boundary Wall at Head Work site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000246/2024-2025 | 3050/MD | 13/06/2024 | 654 | GOBINDA ENTERPRISE | 26.25 | 0 | 70
102 | Malda Division |  | Formal work order for the work of Implementation of DAHIL Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000357/2023-2024 | 3015/MD | 08/08/2023 | 967 | GHOSH BROTHERS | 1245.3 | 0 | 55
103 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Bhadar, Deotala, Mahil, Parail, Dahil & Moyna PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000951/2024-2025 | 640/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
104 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 199/MD | 09/01/2024 | 0 | Resource Division | 13.62 | 0 | 0
105 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 820/MD | 21/02/2024 | 0 | Resource Division | 51.73 | 0 | 0
106 | Malda Division |  | Laying of additional Distribution pipeline by different dia. UPVC pipe for GAZOLE ZONE-IV Piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, PHE Dte. |  |  | ORD/000057/2025-2026 | 2257/MD | 21/05/2025 | 406 | UTTAM KUMAR GHOSH | 21.83 | 0 | 0
107 | Malda Division |  | Dismentling & Restoration of Cement Concrete road and Construction of Thrust Block for protection of pipe line within the command area for Gazole Zone-III Water Supply Scheme at Gazole Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. |  |  | ORD/000104/2025-2026 | 2275/MD | 21/05/2025 | 336 | M/S DAS CONSTRUCTION | 55.73 | 0 | 0
108 | Malda Division |  | Augmentation of PH-2,PH-3,PH-4 &PH-6, at GAZOLE Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000186/2025-2026 | 2955/MD | 19/06/2025 | 60 | S. M. BUILDER | 5.21 | 0 | 0
109 | Malda Division |  | Construction of Boundary Wall at Head Work site of Gazole Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000271/2024-2025 | 3200/MD | 27/06/2024 | 30 | M/S TRILOCHAN CONSTRUCTION CO | 23.16 | 0 | 100
110 | Malda Division |  | Formal work order for the work of Augmentation of GAZOLE ZONE-III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000361/2023-2024 | 3032/MD | 09/08/2023 | 935 | M/S DAS CONSTRUCTION | 516.04 | 0 | 27
111 | Malda Division |  | Formal work order for the work of Augmentation of GAZOLE ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000373/2023-2024 | 3117/MD | 11/08/2023 | 991 | M/S TRILOCHAN CONSTRUCTION CO | 405.72 | 0 | 60
112 | Malda Division |  | Formal work order for the work of Augmentation of Gazole Zone-IV Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000598/2023-2024 | 4326/MD | 16/10/2023 | 989 | UTTAM KUMAR GHOSH | 243.55 | 0 | 30
113 | Malda Division |  | Formal work order for the work of Augmentation of Gazole Zone-II Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000599/2023-2024 | 4325/MD | 16/10/2023 | 898 | MILLENNIUM ENTERPRISR | 426.25 | 0 | 36
114 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000723/2024-2025 | 6414/MD | 19/12/2024 | 316 | MILLENNIUM ENTERPRISE | 73.8 | 0 | 0
115 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000724/2024-2025 | 6415/MD | 19/12/2024 | 423 | M/S DAS CONSTRUCTION | 71.69 | 0 | 0
116 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-IV Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000725/2024-2025 | 6416/MD | 19/12/2024 | 468 | UTTAM KUMAR GHOSH | 24.08 | 0 | 0
117 | Malda Division |  | Construction of Boundary Wall at Head Work Site of Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000728/2024-2025 | 6532/MD | 27/12/2024 | 447 | M/S DAS CONSTRUCTION | 19.38 | 0 | 0
118 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Jibjalsar, Bahirgachi, Hatnagar & Gazole PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000949/2024-2025 | 638/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
119 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 196.39 | 0 | 0
120 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 27/MD | 04/01/2024 | 0 | Resource Division | 56.25 | 0 | 0
121 | Malda Division | Malda Mechanical Division | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00530/2022-2023 | BP-2022-23-211 | 16/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 3.11 | 0 | 0
122 | Malda Division | Malda Mechanical Division | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall and Pump House (5.40x3.60 m) at Head work site of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000003/2025-2026 | 2413/MD | 27/05/2025 | 75 | MATIUR RAHAMAN | 38.45 | 0 | 0
123 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 No) at Mirzapur Water Supply Scheme under Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000017/2023-2024 | 1674/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 12.77 | 0 | 100
124 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for MIRZAPUR & its adjoining mouzas piped water supply at Bamongola Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000130/2022-2023 | 1747/MD | 27/07/2022 | 60 | UTTAM KUMAR DUTTA | 163.77 | 157.81 | 100
125 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Mirzapur Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000139/2025-2026 | 2617/MD | 02/06/2025 | 45 | ANJIMA CONSTRUCTION CO. | 13.72 | 0 | 0
126 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Mirzapur Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000146/2021-2022 | 1744/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 2.28 | 1
127 | Malda Division | Malda Mechanical Division | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of Augmentation of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000152/2024-2025 | 2921/MD | 10/06/2024 | 30 | UTTAM KUMAR DUTTA | 12.53 | 0 | 100
128 | Malda Division | Malda Mechanical Division | Emergent work for better functionally of existing FHTC connection on different diameter Pipeline for MIRZAPUR Piped Water Supply Scheme at Bamangola Dev. Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000194/2025-2026 | 3628/MD | 24/07/2025 | 60 | SAJEDUR RAHAMAN | 8.76 | 0 | 0
129 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) uPVC Pipeline under command area of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000224/2024-2025 | 3026/MD | 13/06/2024 | 261 | M/S KUNDU CONSTRUCTION | 89.01 | 0 | 90
130 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tubewell Site of Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000309/2024-2025 | 3949/MD | 07/08/2024 | 45 | HIRAK ROY CHOUDHURY | 7.45 | 0 | 0
131 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 600 M3 Capacity OHR with FHTC (Mouza- Jaitan, Mirzapur, Mukuli and Salalpur) of Mirzapur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000312/2023-2024 | 2917/MD | 31/07/2023 | 668 | MATIUR RAHAMAN | 281.67 | 0 | 89
132 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000461/2023-2024 | 3394/MD | 31/08/2023 | 45 | DIPU DUTTA | 4.16 | 0 | 0
133 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 4 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000462/2023-2024 | 3395/MD | 31/08/2023 | 45 | SARANGA SARKAR | 4.17 | 0 | 100
134 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000534/2021-2022 | 2687/MD | 09/09/2021 | 7 | HORIZEN | 1.25 | 1.25 | 1
135 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Head Work Site of Mirzapur Water Supply Scheme of Bamangola Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000601/2024-2025 | 5740/MD | 20/11/2024 | 120 | DEBAPRIYA SAHA | 45.31 | 0 | 0
136 | Malda Division | Malda Mechanical Division | Sinking of Tubewell No 3 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000864/2024-2025 | 1220/MD | 26/03/2025 | 45 | BABLU MANDAL | 12.17 | 0 | 0
137 | Malda Division | Malda Mechanical Division | Sinking of Tubewell No 4 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000865/2024-2025 | 1221/MD | 26/03/2025 | 45 | BABLU MANDAL | 12.04 | 0 | 0
138 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000014/2022-2023 | 1873/MD | 16/08/2022 | 0 | Resource Division | 132.02 | 0 | 0
139 | Malda Division |  | Construction of Boundary Wall at Head Work site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000138/2024-2025 | 2889/MD | 07/06/2024 | 177 | USHA ENTERPRISE | 19.58 | 0 | 100
140 | Malda Division |  | Laying of Distribution system of Kaluari Piped Water Supply Scheme at Old Malda Block for west part of rail line of mouza Adatpur & Jhanjra of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000254/2024-2025 | 3190/MD | 27/06/2024 | 45 | EVEREST INFRATECH INC | 85.91 | 0 | 0
141 | Malda Division |  | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Kaluari Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. |  |  | ORD/000316/2024-2025 | 3964/MD | 07/08/2024 | 632 | USHA ENTERPRISE | 45.21 | 0 | 60
142 | Malda Division |  | Formal work order for the work of Implementation of KALUARI Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000353/2023-2024 | 3017/MD | 08/08/2023 | 994 | USHA ENTERPRISE | 709.22 | 0 | 76
143 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000645/2024-2025 | 5922/MD | 26/11/2024 | 45 | USHA ENTERPRISE | 21.7 | 0 | 0
144 | Malda Division |  | Construction of Boundary Wall at 2nd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/001029/2023-2024 | 1255/MD | 15/03/2024 | 30 | CHARU CONSTRUCTION | 6.58 | 0 | 100
145 | Malda Division |  | Construction of Boundary Wall at 3rd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/001030/2023-2024 | 1256//MD | 15/03/2024 | 30 | GOUTAM SAHA | 7.48 | 0 | 0
146 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 357/MD | 16/01/2024 | 0 | Resource Division | 76.82 | 0 | 0
147 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 819/MD | 21/02/2024 | 0 | Resource Division | 75.05 | 0 | 0
148 | Malda Division |  | Construction of Boundary Wall at 2nd Tube Well site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000181/2024-2025 | 2956/MD | 10/06/2024 | 30 | HANNAN BUILDERS PVT. LTD. | 7.92 | 0 | 0
149 | Malda Division |  | Construction of Boundary Wall at Head Work site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000270/2024-2025 | 3228/MD | 28/06/2024 | 30 | HANNAN BUILDERS PVT. LTD. | 27.72 | 0 | 0
150 | Malda Division |  | Formal work order for the work of Implementation of PARAHAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000316/2023-2024 | 2951/MD | 02/08/2023 | 1115 | HANNAN BUILDERS PVT. LTD. | 1038.77 | 0 | 60
151 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000633/2024-2025 | 5912/MD | 26/11/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 71.72 | 0 | 0
152 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 239/MD | 10/01/2024 | 0 | Resource Division | 14.56 | 0 | 0
153 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 814/MD | 21/02/2024 | 0 | Resource Division | 47.82 | 0 | 0
154 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Hardamnagar Water Supply Scheme at Harishchandrapur-II under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000227/2021-2022 | 2380/MD | 13/08/2021 | 30 | PARIJAT RAY | 22.39 | 20.07 | 1
155 | Malda Division | Chanchal Sub-Division | Augmentation work of Pump House and Boundary Wall of Hardamnagar Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000808/2024-2025 | 1031/MD | 18/03/2025 | 303 | ASHIS CONSTRUCTION | 17.22 | 0 | 0
156 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ADHNA Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. |  |  | ORD/000055/2020-2021 | 2153/MD | 16/09/2020 | 30 | TARUN KUMAR DEY | 47.5 | 49.17 | 0
157 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Adhna Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000446/2023-2024 | 3363/MD | 29/08/2023 | 45 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 10.1 | 0 | 100
158 | Malda Division |  | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). |  |  | ORD/000559/2021-2022 | 522/MSD | 31/12/2021 | 2191 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0
159 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Adhna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000827/2024-2025 | 842/MD | 06/03/2025 | 346 | M/S /FAIZUL HAQUE BISWAS | 30.31 | 0 | 0
160 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of GOCHIYA Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000097/2023-2024 | 2319/MD | 08/06/2023 | 365 | M/S PARIMAL DAS | 508.24 | 0 | 35
161 | Malda Division | Malda Mechanical Division | Sinking of 200mm. (all through) Big dia. Tube Well of 180m Deep at Head Work Site by D.R. Rig Method using P.V.C. pipe including supply of materials at GOCHIYA Water Supply Scheme of Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000651/2024-2025 | 6044/MD | 02/12/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.84 | 0 | 0
162 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution pipeline in connection with Jal Jeevan Mission (JJM) at Gochiya Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000656/2024-2025 | 1259/MD | 28/03/2025 | 45 | M/S PARIMAL DAS | 48.34 | 0 | 0
163 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000023/2023-2024 | 1608/MD | 11/04/2023 | 0 | Resource Division | 15.61 | 0 | 0
164 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000030/2022-2023 | 3042/MD | 12/12/2022 | 0 | Resource Division | 26.32 | 0 | 0
165 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-3 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000337/2022-2023 | 2509/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 9.91 | 8.39 | 100
166 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000347/2022-2023 | 2550/MD | 03/11/2022 | 45 | SUDEB KARMAKAR | 6.69 | 6.67 | 100
167 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for ALTOR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000358/2022-2023 | 2507/MD | 03/11/2022 | 475 | M/S STAR INDIA CONSTRUTION | 40.04 | 35.34 | 1
168 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube well site of Altore Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000687/2024-2025 | 6204/MD | 09/12/2024 | 310 | MOSTAKIM ANSARI | 7.17 | 0 | 0
169 | Malda Division | Malda Mechanical Division | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of ALTOR Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000889/2024-2025 | 1128/MD | 21/03/2025 | 45 | GOBINDA ENTERPRISE | 8.15 | 0 | 0
170 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000017/2022-2023 | 2408/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
171 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000019/2022-2023 | 2404/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
172 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIBJALSAR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000480/2022-2023 | 1126/MD | 20/03/2023 | 45 | BANIK BROTHERS | 6.57 | 0 | 100
173 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of JIBJALSAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000487/2022-2023 | 195/MD | 19/01/2023 | 1166 | ACHARYYA CONSTRUCTION | 25 | 19.67 | 80
174 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at JIBJALSAR Water Supply Scheme under Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000609/2022-2023 | 927/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.71 | 9.54 | 100
175 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Jibjalsar Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000945/2023-2024 | 659/MD | 08/02/2024 | 631 | ACHARYYA CONSTRUCTION | 7.36 | 0 | 0
176 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000003/2023-2024 | 1580 | 10/04/2023 | 0 | Resource Division | 0.9 | 0 | 0
177 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000017/2023-2024 | 1614/MD | 11/04/2023 | 0 | Resource Division | 0.9 | 0 | 0
178 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000152/2023-2024 | 251/MD | 10/01/2024 | 0 | Resource Division | 1.03 | 0 | 0
179 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000298/2024-2025 | 3444/MD | 11/07/2024 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 18.55 | 0 | 0
180 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000313/2024-2025 | 3953/MD | 07/08/2024 | 45 | M/S ALISA CONSTRUCTIION | 7.26 | 0 | 0
181 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000373/2022-2023 | 2701/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 9.17 | 1
182 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sahara Bahara Mouza of Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000735/2024-2025 | 54 | 08/01/2025 | 45 | M I CONSTRUCTION | 7.44 | 0 | 0
183 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000928/2023-2024 | 545/MD | 31/01/2024 | 517 | FUTURE | 88.28 | 0 | 80
184 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000003/2024-2025 | 3916/MD | 06/08/2024 | 0 | Resource Division | 0.86 | 0 | 0
185 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000087/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 23.84 | 0 | 0
186 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000125/2023-2024 | 95/MD | 05/01/2024 | 0 | Resource Division | 7.39 | 0 | 0
187 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 Mtr. X 3.00 Mtr. Bore Hole Pump House for Tube Well No. 3 of JATRADANGA Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000241/2020-2021 | 3228MD | 28/12/2020 | 60 | M/S A. B. CONSTRUCTION | 4.74 | 4.74 | 1
188 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of JATRADANGA Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000293/2023-2024 | 2830/MD | 25/07/2023 | 270 | M/S KUNDU CONSTRUCTION | 171.22 | 0 | 53
189 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JATRADANGA Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000485/2022-2023 | 1133/MD | 20/03/2023 | 45 | M/S KAMALA ENTERPRISE | 4.16 | 0 | 0
190 | Malda Division | Malda Mechanical Division | Additional Laying, Road restroration and Providing Functional Household Tap Connection (FHTC) at Jatradanga Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000498/2024-2025 | 5271/MD | 01/10/2024 | 81 | M/S KUNDU CONSTRUCTION | 28.27 | 0 | 100
191 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of JATRADANGA Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000541/2021-2022 | 2695/MD | 09/09/2021 | 7 | RADIANT | 1.25 | 1.24 | 1
192 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000029/2023-2024 | 1809/MD | 27/04/2023 | 0 | Resource Division | 6.98 | 0 | 0
193 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000051/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 66.49 | 0 | 0
194 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000309/2023-2024 | 2873/MD | 26/07/2023 | 980 | VISCOUS ENGINEERS PVT. LTD. | 228.95 | 0 | 72
195 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000479/2024-2025 | 4994/MD | 27/09/2024 | 171 | S. R. CONSTRUCTION | 52.14 | 0 | 0
196 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000932/2023-2024 | 598/MD | 06/02/2024 | 60 | MD. TALEB ALI | 64.62 | 0 | 80
197 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000018/2024-2025 | 3994/MD | 08/08/2024 | 0 | Resource Division | 7.39 | 0 | 0
198 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000089/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 12.8 | 0 | 0
199 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000132/2023-2024 | 109/MD | 05/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
200 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MOBARAKPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000067/2023-2024 | 2035/MD | 19/05/2023 | 1048 | SUBHAS CHANDRA KESHARI | 501.69 | 0 | 64
201 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000168/2024-2025 | 2943/MD | 10/06/2024 | 30 | SUBHAS CHANDRA KESHARI | 8.39 | 0 | 0
202 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000215/2024-2025 | 3036/MD | 13/06/2024 | 30 | SUBHAS CHANDRA KESHARI | 25.86 | 0 | 0
203 | Malda Division | Malda Mechanical Division | Dedicated/Parallel Pipe Line for better functionality and road restoration and providing balance FHTC of Mobarakpur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000691/2025-2026 | 5920/MD | 26/11/2025 | 60 | SUBHAS CHANDRA KESHARI | 28.7 | 0 | 0
204 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000755/2024-2025 | 73 | 13/01/2025 | 45 | SUBHAS CHANDRA KESHARI | 38.17 | 0 | 0
205 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000011/2023-2024 | 1619/MD | 11/04/2023 | 0 | Resource Division | 16.07 | 0 | 0
206 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000033/2022-2023 | 3045/MD | 12/12/2022 | 0 | Resource Division | 24.43 | 0 | 0
207 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000181/2023-2024 | 774/MD | 20/02/2024 | 0 | Resource Division | 5.54 | 0 | 0
208 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of BAHARAL ZONE-I and II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000362/2023-2024 | 3067/MD | 09/08/2023 | 1075 | GHOSH BROTHERS | 1160.22 | 0 | 2
209 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Baharal Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000685/2021-2022 | 650/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 4.59 | 4.59 | 100
210 | Malda Division | Malda Mechanical Division | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Bharal, Bhado, Bilaimari and Chandmoni-I & II GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000970/2024-2025 | 659/MD | 19/02/2025 | 7 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0
211 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000071/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 90.88 | 0 | 0
212 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Rajaramchak Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000269/2024-2025 | 3227/MD | 28/06/2024 | 218 | MONDAL CONSTRUCTION | 20.25 | 0 | 0
213 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of RAJARAMCHAK Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000371/2023-2024 | 3087/MD | 10/08/2023 | 1053 | MONDAL CONSTRUCTION | 234.19 | 0 | 55
214 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000682/2022-2023 | 1131/MD | 20/03/2023 | 45 | ABHIJIT PAUL | 6.57 | 0 | 100
215 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000684/2022-2023 | 1136/MD | 20/03/2023 | 45 | RAJIB MANI | 4.17 | 0 | 100
216 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of RAJARAM CHAK Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000710/2023-2024 | 4640/MD | 24/11/2023 | 857 | M/S MOON LIGHT CONSTRUCTION & CO. | 51.23 | 0 | 25
217 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000042/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 27.36 | 0 | 0
218 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000162/2023-2024 | 253/MD | 10/01/2024 | 0 | Resource Division | 7.85 | 0 | 0
219 | Malda Division | Malda Mechanical Division | Laying of Pipeline work for facilitating FHTC at Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000145/2024-2025 | 3223/MD | 27/06/2024 | 226 | M/S NARESH KUMAR JAIN | 4.95 | 0 | 100
220 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Pump House No.-3, Earth filling and 3 Nos. Boundary wall at Bahirgachhi Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000184/2025-2026 | 2954/MD | 19/06/2025 | 60 | ABHIJIT PAUL | 12.95 | 0 | 0
221 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-23) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000697/2022-2023 | 1154/MD | 20/03/2023 | 613 | M/S KUNDU CONSTRUCTION | 46.45 | 43.89 | 80
222 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-24) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000704/2022-2023 | 1162/MD | 20/03/2023 | 45 | UTTAM KUMAR GHOSH | 54.79 | 46.47 | 100
223 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000718/2022-2023 | 1176/MD | 20/03/2023 | 30 | M/S DYNAMIC CONSTRUCTION | 10.03 | 8.79 | 100
224 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 5 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000719/2022-2023 | 1177/MD | 20/03/2023 | 30 | M/S DYNAMIC CONSTRUCTION | 10.03 | 8.05 | 100
225 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bahirgachhi Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000729/2022-2023 | 1203/MD | 21/03/2023 | 45 | M/S. TEWARI CONSTRUCTION | 8.33 | 0 | 100
226 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 5th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000998/2023-2024 | 1177/MD | 14/03/2024 | 30 | M/S MANDAL & SONS | 12.5 | 0 | 100
227 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000999/2023-2024 | 1178/MD | 14/03/2024 | 180 | A. K. CONSTRUCTION | 17.97 | 0 | 0
228 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 5 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001000/2023-2024 | 1179/MD | 14/03/2024 | 180 | UTTAM KUMAR GHOSH | 18 | 0 | 0
229 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001023/2023-2024 | 1249/MD | 15/03/2024 | 200 | A. L. ENGINEERING SOLUTION | 9.45 | 0 | 100
230 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000175/2024-2025 | 2950/MD | 10/06/2024 | 30 | RAHANUL ALAM | 7.23 | 0 | 0
231 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000220/2024-2025 | 3203/MD | 27/06/2024 | 30 | M/S EHAN ENTERPRISE | 11.45 | 0 | 0
232 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000560/2022-2023 | 751/MD | 17/02/2023 | 30 | RAHANUL ALAM | 11.27 | 11.22 | 100
233 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000567/2022-2023 | 758/MD | 17/02/2023 | 30 | M/S FOUR STAR CONSTRUCTION | 14.57 | 13.36 | 0
234 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-III) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000576/2022-2023 | 767/MD | 17/02/2023 | 30 | RAHANUL ALAM | 11.31 | 11.29 | 100
235 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000584/2024-2025 | 5618/MD | 06/11/2024 | 30 | RUQAIYA ENTERPRISE | 1.82 | 0 | 0
236 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 140 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAKSHIN MAHENDRAPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000780/2022-2023 | 1438/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.45 | 0 | 95
237 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Dakhin Mahendrapur PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000905/2023-2024 | 278/MD | 11/01/2024 | 45 | S N CONSTRUCTION | 4.18 | 0 | 99
238 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000039/2023-2024 | 1932/MD | 12/05/2023 | 1020 | A. D. ENTERPRISE | 310.11 | 0 | 66
239 | Malda Division | Chanchal Sub-Division | Sinking of Tube Well, Providing FHTC, Construction of Pump House & Boundary Wall at Matiharpur Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000109/2025-2026 | 2280/MD | 21/05/2025 | 225 | M/S /FAIZUL HAQUE BISWAS | 52.25 | 0 | 0
240 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mathurapur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000514/2024-2025 | 5338/MD | 03/10/2024 | 45 | SAHA CONSTRUCTION | 63.03 | 0 | 0
241 | Malda Division | Chanchal Sub-Division | Laying of Distribution of UPVC Pipeline of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000563/2023-2024 | 2331/MD | 08/06/2023 | 60 | SAHA CONSTRUCTION | 42.05 | 0 | 100
242 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Mathurapur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000866/2024-2025 | 1222/MD | 26/03/2025 | 30 | M/S MADHU CONSTRUCTION | 22.79 | 0 | 0
243 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000065/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 12.83 | 0 | 0
244 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000120/2023-2024 | 90/MD | 05/01/2024 | 0 | Resource Division | 7.39 | 0 | 0
245 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Moua-Aragacchhi, JL-No. 57) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000736/2022-2023 | 1208/MD | 21/03/2023 | 377 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.03 | 0 | 100
246 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Mouza-Dalla, JL No. 54) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000738/2022-2023 | 1210/MD | 21/03/2023 | 361 | TARUN KUMAR DEY | 28.46 | 0 | 100
247 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dalla Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000755/2022-2023 | 1303/MD | 23/03/2023 | 45 | M/S BHARATI CONSTRUCTION | 8.34 | 0 | 100
248 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000770/2022-2023 | 1428/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 6.86 | 5.98 | 100
249 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000771/2022-2023 | 1429/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 6.86 | 6.17 | 100
250 | Malda Division | Malda Mechanical Division | Replacement of ( 200 mm Dia. All through) Tubewell No.-1 (75 M deep) at Head Work Site by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000974/2023-2024 | 871/MD | 27/02/2024 | 347 | A. L. ENGINEERING SOLUTION | 7 | 0 | 100
251 | Malda Division | Malda Mechanical Division | Devlopment of 200 mm dia. (90 Mtr. Deep) Big dia. Tube Well at Head Work Site by using suitable Air compressor at DALLA Piped Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000977/2023-2024 | 456/MD | 19/01/2024 | 7 | ABHIJIT PAUL | 0.68 | 0 | 100
252 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant for providing FHTC with Construction of Blower room & backwash water disposal at Tubewell no. 3 site of Dalla Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001008/2023-2024 | 1184/MD | 14/03/2024 | 413 | MERCURY ENGINEERING COMPANY | 16.64 | 0 | 30
253 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant for providing FHTC with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Dalla Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001009/2023-2024 | 1185/MD | 14/03/2024 | 413 | MERCURY ENGINEERING COMPANY | 16.64 | 0 | 50
254 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Tubewell site at Dalla Mouza of Dalla Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/001018/2023-2024 | 1186/MD | 14/03/2024 | 30 | J. M. CONSTRUCTION | 11.89 | 0 | 75
255 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000021/2024-2025 | 3997/MD | 08/08/2024 | 0 | Resource Division | 7.39 | 0 | 0
256 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Talsur Piped Water Supply scheme under Malda Division, P.H.E.Dte. (Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000562/2022-2023 | 753/MD | 17/02/2023 | 45 | M/S. TEWARI CONSTRUCTION | 48.93 | 30.27 | 98
257 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Talsur Piped Water Supply scheme under Malda Division PHE. Dte. (Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000571/2022-2023 | 762/MD | 17/02/2023 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 93.98 | 84.48 | 98
258 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Talsur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000722/2022-2023 | 1196/MD | 21/03/2023 | 45 | M/S RAKHI ENTERPRISE | 4.18 | 0 | 96
259 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 150 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of TALSUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000779/2022-2023 | 1437/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 9.92 | 9.4 | 100
260 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-I) | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000559/2022-2023 | 750/MD | 17/02/2023 | 30 | M/S FOUR STAR CONSTRUCTION | 14.54 | 14.37 | 100
261 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline Gannadia Piped Water Supply Scheme in Harischandrapur I & II Block for Installation of FHTC under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000561/2022-2023 | 752/MD | 17/02/2023 | 45 | PARIJAT RAY | 31.32 | 23.98 | 77
262 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-II) | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000566/2022-2023 | 757/MD | 17/02/2023 | 30 | M/S SABANA CONSTRUCTION | 18.76 | 0 | 70
263 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline for Talbangura Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000570/2022-2023 | 761/MD | 17/02/2023 | 30 | M/S N. N. ENTERPRISE | 19.12 | 19.05 | 100
264 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipeline Konar Piped Water Supply Scheme in Harischandrapur I Block for Installation of FHTC under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000735/2022-2023 | 1214/MD | 21/03/2023 | 45 | M/S. TEWARI CONSTRUCTION | 21.7 | 0 | 90
265 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-IVB Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000079/2023-2024 | 2094/MD | 02/06/2023 | 1153 | M/S N. C. SARKAR | 392.9 | 0 | 31
266 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-1 Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000368/2023-2024 | 3057/MD | 09/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.17 | 0 | 100
267 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-2 of Manikchak Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000369/2023-2024 | 3058/MD | 09/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.16 | 0 | 100
268 | Malda Division | Malda Mechanical Division | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 82.40M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVB Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000964/2023-2024 | 826/MD | 28/02/2024 | 480 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 197.84 | 0 | 0
269 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tubewell Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/001028/2023-2024 | 1254/MD | 15/03/2024 | 473 | A.K. AGENCY | 7.58 | 0 | 0
270 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000092/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 84.6 | 0 | 0
271 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ADINA ZONE-II Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000028/2023-2024 | 1839/MD | 02/05/2023 | 791 | M/S PARIMAL DAS | 275.44 | 140.03 | 50
272 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000684/2021-2022 | 649/MD | 22/03/2022 | 15 | TECHVISION | 3.11 | 0 | 100
273 | Malda Division | Malda Mechanical Division | Augmentation of Pump House No.-2 at Adina Zone-II Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000840/2024-2025 | 1070/MD | 19/03/2025 | 60 | MAHA MAYA CONSTRUCTION | 1.81 | 0 | 0
274 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000022/2023-2024 | 1611/MD | 11/04/2023 | 0 | Resource Division | 4.15 | 0 | 0
275 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000077/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 2.97 | 0 | 0
276 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-65C/6570 for the Month of JUNE 2023 under Malda Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/00296/2023-2024 | BP-2023-24-159 | 18/08/2023 | 0 | UTTAM KUMAR GHOSH | 0.39 | 0 | 0
277 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of RATUA ZONE-II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000053/2023-2024 | 1999/MD | 17/05/2023 | 270 | NIRMAN | 550.19 | 0 | 30
278 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 3 of Ratua Zone-II Piped Water Supply Scheme under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000134/2025-2026 | 2508/MD | 29/05/2025 | 45 | M/S NAMITA CONSTRUCTION | 4.18 | 0 | 0
279 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-II Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000600/2024-2025 | 5739/MD | 20/11/2024 | 180 | M/S TEWARI CONSTRUCTION | 72.46 | 0 | 0
280 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-II Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000681/2021-2022 | 647/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 3.67 | 3.42 | 1
281 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/01/2025 to 30/06/2025). | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000871/2024-2025 | 6634/MD | 31/12/2024 | 181 | AMIN ENTERPRISE | 0.86 | 0 | 0
282 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Sambalpur, Gobarjona, Kadamtali & Magura PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000971/2024-2025 | 660/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.73 | 0 | 0
283 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000144/2023-2024 | 121/MD | 06/01/2024 | 0 | Resource Division | 54.12 | 0 | 0
284 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000247/2024-2025 | 3052/MD | 13/06/2024 | 391 | J. M. CONSTRUCTION | 23.32 | 0 | 60
285 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000647/2024-2025 | 439/MD | 06/02/2025 | 45 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 53.22 | 0 | 0
286 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MAHIL Piped Water Supply at Gazole Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000663/2022-2023 | 1038/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 1500.23 | 373.57 | 40
287 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000004/2023-2024 | 1583/MD | 10/04/2023 | 0 | Resource Division | 29.33 | 0 | 0
288 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000032/2023-2024 | 1804/MD | 27/04/2023 | 0 | Resource Division | 69.4 | 0 | 0
289 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000150/2023-2024 | 244/MD | 10/01/2024 | 0 | Resource Division | 23.41 | 0 | 0
290 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 Nos.) at SANJAIL Water Supply Scheme under Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000019/2023-2024 | 1676/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.83 | 9.83 | 100
291 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) and Construction of Pump House in 2nd Tubewell site in connection with Jal Jeevan Mission (JJM) at Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000174/2025-2026 | 2890/MD | 17/06/2025 | 60 | MADHUMITA ENTERPRISE | 19.36 | 0 | 0
292 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANJAIL & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000290/2022-2023 | 2236/MD | 16/09/2022 | 45 | SARIF BUILDERS | 6.14 | 0 | 98
293 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150mm. dia., 140 Mtr. deep Big dia Tube Well at Head Work Site by D.R. Rig method using PVC pipe & Gravel Filter including supply of Materials at Sanjail Water Supply Scheme of Old Malda Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000291/2022-2023 | 2237/MD | 16/09/2022 | 15 | M/S DEBASISH GHOSH | 8.81 | 0 | 100
294 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line SANJAIL its adjoining mouzas Pipe Water Supply Scheme at Old Malda Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000302/2022-2023 | 2170/MD | 21/09/2022 | 558 | M/S PARIMAL DAS | 124.75 | 123.89 | 100
295 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 100 M³ Capacity 20 mtr. staging height RCC Elevated service reservoir as per Departmental Design & drawing ( Ref FRG No-PC/-I/OHR/3/2012) including pipe connection and cost of pipes, specials delivery inlet, washout & overflow pipe etc, all complete with Geotechnical Investigation for SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000436/2022-2023 | 44/MD | 16/01/2023 | 180 | M/S PARIMAL DAS | 55.12 | 43.53 | 99
296 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Bamboo Pile Walling and Horizontal Road Crossing for piped water supply scheme of SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000789/2022-2023 | 1447/MD | 29/03/2023 | 30 | M/S PARIMAL DAS | 3.44 | 3.44 | 0
297 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000886/2023-2024 | 270/MD | 11/01/2024 | 45 | M/S BHARATI CONSTRUCTION | 18.49 | 0 | 95
298 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SANJAIL Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000923/2023-2024 | 455/MD | 19/01/2024 | 45 | M/S SHREE CONSORTIUM | 20.24 | 0 | 99
299 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Sanjail Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000957/2023-2024 | 705/MD | 09/02/2024 | 45 | SADHANA CONSTRUCTION | 5.8 | 0 | 65
300 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | RTOR000025/2022-2023 | 2752/MD | 22/11/2022 | 0 | Resource Division | 17.38 | 0 | 0
301 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Gun Sankrul Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000058/2023-2024 | 2003/MD | 17/05/2023 | 45 | M/S. CHATTERJEE ENTERPRISE | 8.3 | 0 | 100
302 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at GUN SANKARUL Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000378/2022-2023 | 2704/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.52 | 8.44 | 1
303 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Pashim Banjapara-, JL- 32, Chirakuti, JL-39, Hatidubi JL-40, Bag Malancha JL-41) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000405/2022-2023 | 2988/MD | 07/12/2022 | 816 | MANAS KUMAR SAHA | 65.41 | 60.28 | 90
304 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Kuripara-, JL- 36, Bhabuk, JL-37, Paramanika JL-38) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000406/2022-2023 | 2989/MD | 07/12/2022 | 45 | KRISHNENDU DUTTA | 59.95 | 52.25 | 100
305 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at GUN SANKRUL Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000716/2022-2023 | 1174/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 8.52 | 7.66 | 100
306 | Malda Division | Malda Mechanical Division | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Jadupur JL- 28, Kamaldighi JL-29, Dhumadighi JL-30, Gungaon JL-31, Fatepur JL-34) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000981/2023-2024 | 976/MD | 04/03/2024 | 211 | M/S AMIT KUMAR GUPTA | 45.81 | 0 | 71
307 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000021/2022-2023 | 2407/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
308 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000048/2023-2024 | 1994/MD | 17/05/2023 | 991 | UTTAM KUMAR DUTTA | 417.89 | 61.27 | 40
309 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000100/2023-2024 | 2327/MD | 08/06/2023 | 60 | MD. TALEB ALI | 70.61 | 0 | 40
310 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Alal zone-l Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000245/2024-2025 | 3051/MD | 13/06/2024 | 413 | SAHA CONSTRUCTION | 50.08 | 0 | 40
311 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000262/2024-2025 | 3210/MD | 27/06/2024 | 506 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.15 | 0 | 0
312 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000686/2021-2022 | 651/MD | 22/03/2022 | 15 | TECHVISION | 3.42 | 3.36 | 1
313 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000715/2024-2025 | 6406/MD | 19/12/2024 | 332 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 16.46 | 0 | 0
314 | Malda Division | Malda Mechanical Division | Augmentation of Pump House-1 & Pump House-2, at ALAL Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000890/2024-2025 | 1129/MD | 21/03/2025 | 45 | ARUN MUKHERJEE | 2.42 | 0 | 0
315 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000063/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 40.31 | 0 | 0
316 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000154/2023-2024 | 246/MD | 10/01/2024 | 0 | Resource Division | 9.71 | 0 | 0
317 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Barkol Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000128/2025-2026 | 2485/MD | 28/05/2025 | 60 | SURAJIT MONDAL | 9.44 | 0 | 0
318 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 11.4 | 1
319 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000167/2020-2021 | 2720/MD | 10/11/2020 | 45 | M/S JHA CONSTRUCTION | 71.77 | 102.84 | 1
320 | Malda Division | RWS Malda Sub-Division | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (130 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at BORKOL Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000454/2024-2025 | 4813/MD | 13/09/2024 | 30 | M/S DAS CONSTRUCTION | 9.07 | 0 | 100
321 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | ORD/000165/2020-2021 | 2718/MD | 10/11/2020 | 30 | NIRENDRA NATH KUNDU | 58.72 | 82.4 | 1
322 | Malda Division | Chanchal Sub-Division | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dhanjana Madhaypara command area of Dhanjana Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | ORD/000611/2023-2024 | 4139/MD | 11/10/2023 | 30 | M/S BANERJEE CONSTRUCTION | 3.7 | 0 | 100
323 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DHANJANA Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | ORD/000726/2023-2024 | 4775/MD | 05/12/2023 | 45 | ANUKUL CHANDRA DAS | 7.04 | 0 | 100
324 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Rajarshi Sinha, Junior Engineer | RTOR000109/2023-2024 | 39/MD | 04/01/2024 | 0 | Resource Division | 1.08 | 0 | 0
325 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIAGHAT Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000213/2020-2021 | 3001/MD | 10/12/2020 | 30 | A. K. CONSTRUCTION | 49.81 | 44.5 | 1
326 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000005/2024-2025 | 3917/MD | 06/08/2024 | 0 | Resource Division | 3.76 | 0 | 0
327 | Malda Division | Chanchal Sub-Division | Restoration of Road of KHARANGAPUR JABRA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000210/2025-2026 | 3725/MD | 30/07/2025 | 30 | GOBINDA ENTERPRISE | 29.03 | 0 | 0
328 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000232/2023-2024 | 2709/MD | 14/07/2023 | 720 | GOBINDA ENTERPRISE | 168.68 | 0 | 84
329 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Kharangapur Jabra Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000301/2024-2025 | 3447/MD | 11/07/2024 | 417 | GOBINDA ENTERPRISE | 29.37 | 0 | 70
330 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000374/2022-2023 | 779/MD | 17/02/2023 | 30 | MERCURY ENGINEERING COMPANY | 9.2 | 0 | 98
331 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000074/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.42 | 0 | 0
332 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000133/2023-2024 | 110/MD | 05/01/2024 | 0 | Resource Division | 4.81 | 0 | 0
333 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000096/2025-2026 | 2338/MD | 22/05/2025 | 313 | M/S DAS CONSTRUCTION | 31.48 | 0 | 0
334 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000184/2024-2025 | 2959/MD | 10/06/2024 | 416 | M/S DAS CONSTRUCTION | 9.32 | 0 | 0
335 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000297/2024-2025 | 3443/MD | 11/07/2024 | 598 | M/S DAS CONSTRUCTION | 22.19 | 0 | 70
336 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SHARANPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000368/2022-2023 | 2697/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 8.85 | 0
337 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000578/2024-2025 | 5550/MD | 29/10/2024 | 519 | M/S DAS CONSTRUCTION | 31.36 | 0 | 70
338 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SHARANPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000587/2022-2023 | 825/MD | 21/02/2023 | 1043 | M/S DAS CONSTRUCTION | 189.29 | 41.02 | 85
339 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SAHARANPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | ORD/000607/2022-2023 | 925/MD | 27/02/2023 | 166 | DUTTA ENTERPRISE | 10.13 | 0 | 100
340 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | RTOR000001/2023-2024 | 1581 | 10/04/2023 | 0 | Resource Division | 6.65 | 0 | 0
341 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | RTOR000015/2023-2024 | 1617/MD | 11/04/2023 | 0 | Resource Division | 6.65 | 0 | 0
342 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-06,Mr. Susanta Pal, JE_Deputation | RTOR000036/2022-2023 | 3048/MD | 12/12/2022 | 0 | Resource Division | 17.95 | 0 | 0
343 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Chhatrak Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000212/2024-2025 | 3033/MD | 13/06/2024 | 536 | M/S TRILOCHAN CONSTRUCTION CO | 26.65 | 0 | 75
344 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tubewell site of Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000213/2024-2025 | 3034/MD | 13/06/2024 | 30 | BIDYUT MAHALDAR | 10.41 | 0 | 0
345 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHHATRAK Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000369/2022-2023 | 2698/MD | 17/11/2022 | 30 | MERCURY ENGINEERING COMPANY | 9.2 | 8.82 | 0
346 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000480/2024-2025 | 4995/MD | 27/09/2024 | 45 | BIDYUT MAHALDAR | 14.99 | 0 | 0
347 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of CHHATRAK Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000594/2022-2023 | 875/MD | 22/02/2023 | 1317 | M/S TRILOCHAN CONSTRUCTION CO | 150.77 | 50.56 | 90
348 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at CHHATRAK Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000606/2022-2023 | 924/MD | 27/02/2023 | 30 | SAUDAGAR INDIA | 10.13 | 9.66 | 0
349 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000002/2023-2024 | 1584/MD | 10/04/2023 | 0 | Resource Division | 4.3 | 0 | 0
350 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000016/2023-2024 | 1613/MD | 11/04/2023 | 0 | Resource Division | 4.3 | 0 | 0
351 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000019/2024-2025 | 3995/MD | 08/08/2024 | 0 | Resource Division | 2.22 | 0 | 0
352 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000035/2022-2023 | 3047/MD | 12/12/2022 | 0 | Resource Division | 19.68 | 0 | 0
353 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00841/2023-2024 | BP-2023-24-461 | 02/02/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0
354 | Malda Division | Malda Mechanical Division | Laying of 200 mm dia HDPE water carrying pipe of chainage 327.800 of the NH-34 of Sahapur GhoshparaBypass More of Saha & Adjoining Mouza water supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00880/2023-2024 | BP-2023-24-478 | 15/02/2024 | 0 | NATIONAL HIGHWAYS AUTHORITY OF INDIA PAYABLE AT MALDA | 0.56 | 0 | 0
355 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/01127/2023-2024 | BP-2023-24-602 | 28/03/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.41 | 0 | 0
356 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of SAHAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000080/2023-2024 | 2093/MD | 02/06/2023 | 1145 | S DUTTA | 785.2 | 0 | 45
357 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sahapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000136/2025-2026 | 2534/MD | 30/05/2025 | 120 | M/S DAS CONSTRUCTION | 123.11 | 0 | 0
358 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Sahapur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000203/2024-2025 | 2990/MD | 11/06/2024 | 315 | S. N. CONSTRUCTION | 24.73 | 0 | 0
359 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of SAHAPUR Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000538/2021-2022 | 2692/MD | 09/09/2021 | 7 | RADIANT | 1.72 | 1.7 | 1
360 | Malda Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000607/2023-2024 | 4111/MD | 10/10/2023 | 181 | M/S TRILOCHAN CONSTRUCTION CO | 22.05 | 0 | 0
361 | Malda Division | Malda Mechanical Division | Augmentation work of Construction of Boundary Wall at Head Work site of Sahapur Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000894/2024-2025 | 1224/MD | 26/03/2025 | 75 | SHREE BISHNU CONSTRUCTION | 25.15 | 0 | 0
362 | Malda Division | Malda Mechanical Division | Augmentation work of Pump House and Construction of Toilet at Head Work site Site of Sahapur Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000895/2024-2025 | 1225/MD | 26/03/2025 | 75 | M/S S. S. CONSTRUCTION | 3.73 | 0 | 0
363 | Malda Division | Malda Mechanical Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 1st Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000896/2024-2025 | 1226/MD | 26/03/2025 | 75 | M/S AMIT KUMAR GUPTA | 11.48 | 0 | 0
364 | Malda Division | Malda Mechanical Division | Augmentation of Boundary wall, Pump House and Construction of Toilet at 3rdd Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000897/2024-2025 | 1227/MD | 26/03/2025 | 75 | M/S AMIT KUMAR GUPTA | 5.02 | 0 | 0
365 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000055/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 104.87 | 0 | 0
366 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000186/2023-2024 | 821/MD | 21/02/2024 | 0 | Resource Division | 23.62 | 0 | 0
367 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of BAIRAT Piped Water Supply Scheme at Harishchandrapur-I Dev. Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000534/2022-2023 | 581/MD | 09/02/2023 | 1295 | USHA ENTERPRISE | 732.14 | 300.97 | 79
368 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Bairat Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000884/2023-2024 | 160/MD | 08/01/2024 | 494 | USHA ENTERPRISE | 21.58 | 0 | 70
369 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000058/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 27.83 | 0 | 0
370 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000107/2023-2024 | 37/MD | 04/01/2024 | 0 | Resource Division | 16.2 | 0 | 0
371 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of BANGURA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000207/2025-2026 | 3704/MD | 29/07/2025 | 60 | M/S GHOSH CONSTRUCTION | 22.26 | 0 | 0
372 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000371/2022-2023 | 778/MD | 17/02/2023 | 30 | SAUDAGAR (INDIA) | 9.2 | 8.87 | 100
373 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000389/2023-2024 | 3289/MD | 23/08/2023 | 678 | KUNDU CONSTRUCTION | 148.48 | 0 | 65
374 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bangrua Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000573/2024-2025 | 1150/MD | 21/03/2025 | 225 | A. B. CONSTRUCTION | 26.08 | 0 | 60
375 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000017/2024-2025 | 3993/MD | 08/08/2024 | 0 | Resource Division | 3.7 | 0 | 0
376 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000088/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 6.97 | 0 | 0
377 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000124/2023-2024 | 94/MD | 05/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
378 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Matiharpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000154/2025-2026 | 2692/MD | 04/06/2025 | 45 | M/S ROY CONSTRUCTION | 29.35 | 0 | 0
379 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of MATIHARPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000656/2022-2023 | 1010/MD | 10/03/2023 | 60 | M/S DAS CONSTRUCTION | 84.75 | 0 | 0
380 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000056/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.44 | 0 | 0
381 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000118/2023-2024 | 88/MD | 05/01/2024 | 0 | Resource Division | 15.4 | 0 | 0
382 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of EMAMNAGAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000662/2022-2023 | 1039/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 1113.74 | 0 | 50
383 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000719/2024-2025 | 6410/MD | 19/12/2024 | 466 | ABANI BHUSAN GHOSH | 52.11 | 0 | 0
384 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000009/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 113.13 | 0 | 0
385 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000151/2023-2024 | 250/MD | 10/01/2024 | 0 | Resource Division | 16.78 | 0 | 0
386 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-04-H-8254 for the Month of MAY, JUNE and JULY 2023 under Malda Division PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | BILL/00295/2023-2024 |  | 10/08/2023 | 0 | SHABNAM ARA | 1.18 | 0 | 0
387 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of RATUA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000069/2023-2024 | 2042/MD | 19/05/2023 | 1074 | STARCO CONSTRUCTIONS | 853.24 | 124.2 | 60
388 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000675/2024-2025 | 6200/MD | 09/12/2024 | 45 | UTTAM KUMAR GHOSH | 7.56 | 0 | 100
389 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-I Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000680/2021-2022 | 646/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 4.4 | 4.17 | 1
390 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Ratua Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000689/2024-2025 | 6206/MD | 09/12/2024 | 45 | RAJA CONSTRUCTION | 4.51 | 0 | 0
391 | Malda Division | Malda Mechanical Division | Dismantling of abandoned room at Head work site of Ratua-I PWSS under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/000951/2023-2024 | 654/MD | 08/02/2024 | 30 | M/S. TEWARI CONSTRUCTION | 1.93 | 0 | 100
392 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | ORD/001015/2023-2024 | 1517/MD | 16/03/2024 | 715 | UTTAM KUMAR GHOSH | 79.16 | 0 | 0
393 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Mr. Sujit Sarkar, Junior Engineer | RTOR000067/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 80.51 | 0 | 0
394 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Augmentation of PUKHURIA Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000062/2023-2024 | 2022/MD | 18/05/2023 | 1137 | DUTTA ENTERPRISE | 957.93 | 0 | 60
395 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000167/2025-2026 | 5794/MD | 13/11/2025 | 60 | DUTTA ENTERPRISE | 117.25 | 0 | 0
396 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at 4th Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000315/2024-2025 | 3955/MD | 07/08/2024 | 45 | MAHA MAYA CONSTRUCTION | 7.12 | 0 | 100
397 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000694/2021-2022 | 659/MD | 22/03/2022 | 15 | ECO CARE | 3.71 | 3.71 | 1
398 | Malda Division | Chanchal Sub-Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 2 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000942/2023-2024 | 651/MD | 08/02/2024 | 45 | CHAKRABORTY & MANDAL ENTERPRISE | 4.76 | 0 | 100
399 | Malda Division | Chanchal Sub-Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 1 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000950/2023-2024 | 652/MD | 08/02/2024 | 45 | J. M. CONSTRUCTION | 4.76 | 0 | 0
400 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Paharpur, Sultanpur, Pukuria PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000972/2024-2025 | 661/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.73 | 0 | 0
401 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000068/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 120.24 | 0 | 0
402 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jigin Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000127/2025-2026 | 2509/MD | 29/05/2025 | 60 | ARKADEEP ENTERPRISE | 7.24 | 0 | 0
403 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000483/2022-2023 | 1129/MD | 20/03/2023 | 45 | JOYDEB SENGUPTA | 6.58 | 0 | 100
404 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000685/2022-2023 | 1134/MD | 20/03/2023 | 45 | M/S ROY CONSTRUCTION | 4.21 | 0 | 100
405 | Malda Division | Malda Mechanical Division | Formal work order for Implementation of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000741/2022-2023 | 1251/MD | 22/03/2023 | 590 | GOBINDA ENTERPRISE | 88.5 | 60.98 | 100
406 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000050/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 34.75 | 0 | 0
407 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Kankot Water Supply Scheme in Ratua I Block for Installation of FHTC under Malda Division PHE. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000563/2022-2023 | 754/MD | 17/02/2023 | 30 | PRITAM ENTERPRISE | 4.76 | 4.63 | 0
408 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kankot Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000724/2022-2023 | 1198/MD | 21/03/2023 | 45 | PRITAM ENTERPRISE | 4.16 | 0 | 0
409 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of KANKOT Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000777/2022-2023 | 1435/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 0 | 0
410 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Arjuna Piped Water Supply scheme at Harishchandrapur-II under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000564/2022-2023 | 755/MD | 17/02/2023 | 30 | GHOSH CONSTRUCTION | 15.53 | 15.5 | 0
411 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arjuna Mouza of Arjuna Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000734/2024-2025 | 10 | 03/01/2025 | 45 | TWO BROTHERS CONSTRUCTION | 10.01 | 0 | 0
412 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Arjuna Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000749/2022-2023 | 1297/MD | 23/03/2023 | 45 | SAYEM ENTERPRISE | 4.2 | 0 | 100
413 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of ARJUNA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000775/2022-2023 | 1433/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 8.68 | 100
414 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Arjuna Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000860/2024-2025 | 1053/MD | 18/03/2025 | 75 | M/S KUNDU CONSTRUCTION | 28.76 | 0 | 0
415 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000029/2023-2024 | 1840/MD | 02/05/2023 | 45 | SARIF BUILDERS | 12.75 | 0 | 100
416 | Malda Division | RWS Malda Sub-Division | Dismantling of concrete for the laying of Distribution system through the concrete roads within Aiho Zone-I Piped Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000491/2024-2025 | 5004/MD | 27/09/2024 | 45 | M/S FRIENDS CONSTRUCTION & CO. | 19.96 | 0 | 90
417 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000554/2022-2023 | 1179/MD | 21/03/2023 | 710 | M/S STAR INDIA CONSTRUTION | 85.22 | 38 | 100
418 | Malda Division | RWS Malda Sub-Division | Construction of R.C.C. Culvert (Approach) infront of Head Works Site of AIHO ZONE-I Piped Water Supply Scheme under Malda Division PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000613/2023-2024 | 4142/MD | 11/10/2023 | 30 | M/S STAR INDIA CONSTRUTION | 1.12 | 0 | 100
419 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aiho Zone-I Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000659/2024-2025 | 1260/MD | 28/03/2025 | 134 | SIVRAM ENTERPRISE | 17.36 | 0 | 0
420 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000672/2022-2023 | 1211/MD | 22/03/2023 | 710 | M/S FRIENDS CONSTRUCTION & CO. | 91.59 | 44.92 | 65
421 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-1 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000984/2023-2024 | 979/MD | 04/03/2024 | 45 | S. R. CONSTRUCTION | 28.24 | 0 | 100
422 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000080/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 8.74 | 0 | 0
423 | Malda Division | Malda Sadar Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-I Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000588/2022-2023 | 828/MD | 21/02/2023 | 45 | M/S PARIMAL DAS | 82.32 | 74.78 | 98
424 | Malda Division | Malda Sadar Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-II Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000589/2022-2023 | 1159/MD | 20/03/2023 | 45 | KRISHNENDU DUTTA | 59.38 | 0 | 85
425 | Malda Division | Malda Sadar Sub-Division | Augmentation of Boundary Walls and Construction of Switch Room of size 3.60 x 3.0 M of BAHERPUR ( ZONE I & II) Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000707/2024-2025 | 6389/MD | 18/12/2024 | 45 | PABITRA MANDAL | 21.71 | 0 | 0
426 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000150/2024-2025 | 2919/MD | 10/06/2024 | 386 | M/S N. C. SARKAR | 34.1 | 0 | 0
427 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-II Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000382/2023-2024 | 3238/MD | 22/08/2023 | 1042 | M/S N. C. SARKAR | 442.76 | 0 | 25
428 | Malda Division | Malda Mechanical Division | Construction of Approach Road at Head Work site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000893/2023-2024 | 272/MD | 11/01/2024 | 264 | M/S N. C. SARKAR | 3.91 | 0 | 100
429 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 92.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-II Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000994/2023-2024 | 1278/MD | 15/03/2024 | 240 | DEBAPRIYA SAHA | 210.87 | 0 | 0
430 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000094/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 144.69 | 0 | 0
431 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000300/2024-2025 | 3446/MD | 11/07/2024 | 30 | M/S TEWARI CONSTRUCTION | 37.37 | 0 | 0
432 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000500/2024-2025 | 5404/MD | 21/10/2024 | 45 | MAHA MAYA CONSTRUCTION | 21.72 | 0 | 0
433 | Malda Division | Chanchal Sub-Division | Augmentation work of Pump House and Boundary Wall of Bhingole Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000847/2024-2025 | 1033/MD | 18/03/2025 | 75 | BINA CONSTRUCTION | 10.95 | 0 | 0
434 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000021/2023-2024 | 1610/MD | 11/04/2023 | 0 | Resource Division | 4.52 | 0 | 0
435 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000083/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 8.78 | 0 | 0
436 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ADINA ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000119/2023-2024 | 2322/MD | 08/06/2023 | 840 | M/S TRILOCHAN CONSTRUCTION CO | 348.95 | 0 | 35
437 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000683/2021-2022 | 648/MD | 22/03/2022 | 15 | TECHVISION | 3.04 | 3.01 | 1
438 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Adina Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000888/2023-2024 | 162/MD | 08/01/2024 | 219 | M/S PARIMAL DAS | 21.89 | 0 | 85
439 | Malda Division | Malda Mechanical Division | Continuation work order Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/12/2024 to 31/12/2024). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001032/2024-2025 | 6291/MD | 11/12/2024 | 17 | RUQAIYA ENTERPRISE | 0.08 | 0 | 0
440 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000075/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 34.17 | 0 | 0
441 | Malda Division |  | Formal work order for the work of Augmentation of SAMSI (Zone-I & II) Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000356/2023-2024 | 3014/MD | 08/08/2023 | 995 | DUTTA ENTERPRISE | 1066.35 | 0 | 38
442 | Malda Division |  | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-1of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000455/2024-2025 | 4809/MD | 13/09/2024 | 30 | ASHIS CONSTRUCTION | 8.5 | 0 | 0
443 | Malda Division |  | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-2 of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000456/2024-2025 | 4810/MD | 13/09/2024 | 30 | ASHIS CONSTRUCTION | 8.5 | 0 | 100
444 | Malda Division |  | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Samsi Hospital of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. |  |  | ORD/000457/2024-2025 | 4811/MD | 13/09/2024 | 30 | ABHIJIT PAUL | 8.5 | 0 | 100
445 | Malda Division |  | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2023 to 30/04/2024). |  |  | ORD/000716/2023-2024 | 4428/MD | 30/10/2023 | 183 | SHABNAM ARA | 0.86 | 0 | 56
446 | Malda Division |  | 1st layer Land Development Work at Head Work site of Samsi Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000764/2024-2025 | 6622 | 31/12/2024 | 30 | M/S FOUR STAR CONSTRUCTION | 0.95 | 0 | 100
447 | Malda Division |  | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Debipur, Kahala, Mahanandatola, Ratua & Samsi GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000969/2024-2025 | 658/MD | 19/02/2025 | 7 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0
448 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 358/MD | 16/01/2024 | 0 | Resource Division | 30.48 | 0 | 0
449 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 818/MD | 21/02/2024 | 0 | Resource Division | 98.17 | 0 | 0
450 | Malda Division |  | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for HATNAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. |  |  | ORD/000214/2025-2026 | 3771/MD | 04/08/2025 | 60 | M/S GUPTA ENTERPRISE | 91.12 | 0 | 0
451 | Malda Division |  | Formal work order for the work of Implementation of HATNAGAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000372/2023-2024 | 3104/MD | 10/08/2023 | 876 | M/S GUPTA ENTERPRISE | 628.84 | 0 | 70
452 | Malda Division |  | Formal work order for the work of Providing Functional Household Tap Connection (FHTC), Laying of Distribution Pipeline and allied works in connection with Jal Jeevan Mission (JJM) at Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000770/2024-2025 | 66/MD | 13/01/2025 | 443 | M/S GUPTA ENTERPRISE | 241.12 | 0 | 20
453 | Malda Division |  | Construction of Boundary Wall at Head Work site of Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000845/2024-2025 | 832/MD | 06/03/2025 | 209 | M/S GUPTA ENTERPRISE | 30.13 | 0 | 0
454 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 247/MD | 10/01/2024 | 0 | Resource Division | 8.25 | 0 | 0
455 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 817/MD | 21/02/2024 | 0 | Resource Division | 32.68 | 0 | 0
456 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of Rahimpur Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II | Junior Engineer-07 | ORD/000006/2023-2024 | 1571/MD | 10/04/2023 | 992 | M/S GUPTA ENTERPRISE | 841.12 | 338.43 | 90
457 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II | Junior Engineer-07 | ORD/000179/2024-2025 | 2954/MD | 10/06/2024 | 236 | M/S AMIT KUMAR GUPTA | 7.17 | 0 | 50
458 | Malda Division | Malda Mechanical Division | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for RAHIMPUR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II | Junior Engineer-07 | ORD/000213/2025-2026 | 3770/MD | 04/08/2025 | 150 | M/S GUPTA ENTERPRISE | 11.35 | 0 | 0
459 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II | Junior Engineer-07 | ORD/000632/2024-2025 | 5911/MD | 26/11/2024 | 309 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 48.65 | 0 | 20
460 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II | Junior Engineer-07 | ORD/000844/2024-2025 | 831/MD | 06/03/2025 | 209 | M/S GUPTA ENTERPRISE | 28.39 | 0 | 60
461 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II | Junior Engineer-07 | RTOR000052/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 14.65 | 0 | 0
462 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II | Junior Engineer-07 | RTOR000099/2023-2024 | 28/MD | 04/01/2024 | 0 | Resource Division | 16.25 | 0 | 0
463 | Malda Division |  | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Altor Water Supply Scheme of Gazole Dev. Block under Malda Division P.H.E Dte in the District of Malda. |  |  | ORD/000141/2025-2026 | 2619/MD | 02/06/2025 | 135 | M/S AMIT KUMAR GUPTA | 18.01 | 0 | 0
464 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. |  |  | ORD/000160/2020-2021 | 2713/MAAD | 10/11/2020 | 45 | MANIK CHANDRA SAHA | 68.5 | 54.67 | 0
465 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bibijhuti, JL. No. 58, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. |  |  | ORD/000303/2020-2021 | 283/MD | 28/01/2021 | 30 | ANUKUL CHANDRA DAS | 9.41 | 0.19 | 1
466 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Altor Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000447/2023-2024 | 3364/MD | 29/08/2023 | 45 | M/S BABLU ENTERPRISE | 18.17 | 0 | 80
467 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Altore Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000597/2024-2025 | 5738/MD | 20/11/2024 | 346 | SAMBHU NATH SARKAR | 42.53 | 0 | 0
468 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000150/2025-2026 | 2688/MD | 04/06/2025 | 45 | MODERN CO-OPERATIVE LABOUR CONTRCT & CONSTRUCTION SOCIETY LIMITED. | 34.99 | 0 | 0
469 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000158/2024-2025 | 2933/MD | 10/06/2024 | 30 | M/S BHARATI CONSTRUCTION | 7.23 | 0 | 80
470 | Malda Division | Malda Mechanical Division | Restoration of Road at Bhagabatipur Mouza of Nabagram Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000198/2025-2026 | 3632/MD | 24/07/2025 | 45 | M/S FOUR STAR CONSTRUCTION | 12.6 | 0 | 0
471 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Nabagram PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000304/2024-2025 | 3450/MD | 10/07/2024 | 73 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 95
472 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC pipe line of NABAGRAM Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000959/2023-2024 | 710/MD | 09/02/2024 | 143 | RATAN KARMAKAR | 4.11 | 0 | 90
473 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000044/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 21.33 | 0 | 0
474 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000119/2023-2024 | 89/MD | 05/01/2024 | 0 | Resource Division | 18.48 | 0 | 0
475 | Malda Division |  | Formal work order for the work of Implementation of PARAIL Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000261/2023-2024 | 3008/MD | 07/08/2023 | 1025 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1011.34 | 0 | 55
476 | Malda Division |  | Construction of Boundary Wall at Head Work site of Parail Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000264/2024-2025 | 3212/MD | 27/06/2024 | 641 | M/S JHA CONSTRUCTION | 26.23 | 0 | 70
477 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 235/MD | 10/01/2024 | 0 | Resource Division | 7.35 | 0 | 0
478 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 813/MD | 21/02/2024 | 0 | Resource Division | 39.07 | 0 | 0
479 | Malda Division |  | The payment to WBSRDA against the repair of damaged roads. |  |  | BILL/00732/2024-2025 |  | 11/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 6 | 0 | 0
480 | Malda Division |  | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design (Ref :- DRG.No. PC/-I/OHR/11/2012) including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme of BEJPURA PWSS at Harishchandrapur-II Block in the District of Malda, under Malda Division, PHE Dte. |  |  | ORD/000388/2024-2025 | 4556/MD | 30/08/2024 | 669 | NILMANI BASAK | 131.79 | 0 | 25
481 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of UTTAR CHANDIPUR ZONE-IV A Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000034/2023-2024 | 1850/MD | 03/05/2023 | 975 | BANIK BROTHERS | 341.23 | 0 | 22
482 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-IV B Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000170/2025-2026 | 7812/MD | 11/06/2025 | 60 | BEE GEE CONSTRUCTION | 121.68 | 0 | 0
483 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Uttar Chandipur Zone-IV A Piped Water Supply Scheme at Manikchak Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000890/2023-2024 | 164/MD | 08/01/2024 | 45 | J. M. CONSTRUCTION | 10.08 | 0 | 95
484 | Malda Division | Malda Mechanical Division | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 75M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVA Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000988/2023-2024 | 1079/MD | 13/03/2024 | 624 | DUTTA ENTERPRISE | 188.41 | 0 | 0
485 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-A Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/001013/2023-2024 | 1515/MD | 16/03/2024 | 657 | BANIK BROTHERS | 28.69 | 0 | 0
486 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/001014/2023-2024 | 1516/MD | 16/03/2024 | 472 | M/S N. C. SARKAR | 26.44 | 0 | 0
487 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000091/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 72.43 | 0 | 0
488 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150mm. Dia) Tube Well no-3 ( 70 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000304/2022-2023 | 2299/MD | 28/09/2022 | 30 | MECHANO TRADING CO. | 5.25 | 0 | 0
489 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000340/2022-2023 | 3112/MD | 20/12/2022 | 45 | HIRAK ROY CHOUDHURY | 6.69 | 0 | 0
490 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damage A.C pipe lineby different dia UPVC pipe for PANNAPUR Piped Water Supply Scheme ( Nimnail, Jahanabad) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000364/2022-2023 | 2605/MD | 10/11/2022 | 45 | MANIK CHANDRA SAHA | 69.14 | 66.54 | 88
491 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Pannapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000621/2024-2025 | 5791/MD | 21/11/2024 | 45 | DEY CONSTRUCTION | 36.95 | 0 | 0
492 | Malda Division | Malda Mechanical Division | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (250 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000976/2023-2024 | 885/MD | 27/02/2024 | 347 | A. L. ENGINEERING SOLUTION | 14.82 | 0 | 100
493 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | RTOR000020/2022-2023 | 2405/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
494 | Malda Division | Chanchal Sub-Division | Bill for car hiring no. WB/51C/7999 for office of the Superintending Enginner, North Bengal Circle-II, PHE Dte. For the period from (01/02/2023 to 15/05/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00228/2023-2024 | BP-2023-24-108 | 13/07/2023 | 0 | TARUN KUMAR BHATTACHARYA | 1.05 | 0 | 0
495 | Malda Division | Chanchal Sub-Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB65C/6570, For the month of MAY, 2023. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00289/2023-2024 | BP-2023-24-143 | 09/08/2023 | 0 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0
496 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supply & delivery of Steel Table with Locker and Wooden Top, Office Visitors Chair and High back mesh Executive Chair for the Conference Room of District Laboratory 1st Floor and office of the Superintending Engineer, North Bengal Circle - Il under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000021/2023-2024 | 1712/MD | 20/04/2023 | 15 | M/S PARIMAL DAS | 2.42 | 2.42 | 0
497 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SADLICHAK Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000027/2020-2021 | 1962/MD | 31/08/2020 | 30 | BEE GEE CONSTRUCTION | 43.35 | 21.01 | 1
498 | Malda Division | Chanchal Sub-Division | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Dalla JL.-54, Aragachi JL-57) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000046/2025-2026 | 2252/MD | 21/05/2025 | 243 | ACHARYYA CONSTRUCTION | 25.17 | 0 | 0
499 | Malda Division | Chanchal Sub-Division | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for GUNSANKRUL Piped Water Supply Scheme (Jadupur JL.-28, Paschim Banjhapara JL32) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000047/2025-2026 | 2253/MD | 21/05/2025 | 90 | RABIUL ISLAM | 22.84 | 0 | 0
500 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bejpura Piped Water Supply Scheme (Phase-II) at Harischandrapur - II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000055/2022-2023 | 1487/MD | 23/06/2022 | 30 | CHARU CONSTRUCTION | 6.53 | 6.53 | 1
501 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BEJPURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000056/2020-2021 | 2152/MD | 16/09/2020 | 45 | NEOGI ENTERPRISE | 68.33 | 36.27 | 1
502 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BHAIRABPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000057/2020-2021 | 2142/MD | 16/09/2020 | 60 | SUBHAS CHANDRA KESHARI | 92.31 | 48.11 | 1
503 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of GUN SANKRUL Water Supply Scheme at Malda Old Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000059/2020-2021 | 2261/MD | 29/09/2020 | 45 | MILLENNIUM ENTERPRISR | 74.5 | 21.23 | 0
504 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JAGANNATHPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000060/2020-2021 | 2141/MD | 16/09/2020 | 45 | DEBAPRIYA SAHA | 77.59 | 32.71 | 0
505 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000065/2020-2021 | 2139/MD | 16/09/2020 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 65.52 | 16.95 | 0
506 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JALALPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000067/2020-2021 | 2140/MD | 16/09/2020 | 60 | FUTURE | 116.65 | 86.06 | 0
507 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000070/2020-2021 | 2135/MD | 16/09/2020 | 90 | HANNAN BUILDERS PVT. LTD. | 145.2 | 20.4 | 1
508 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Repairing of existing FHTC connection for Talsur Water Supply Scheme under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000074/2022-2023 | 330/CSD | 22/06/2022 | 30 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 1.06 | 1.06 | 1
509 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN MAHENDRAPUR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000079/2020-2021 | 2683/MD | 06/11/2020 | 45 | MADE & TRADE CO. | 85.01 | 112.26 | 0
510 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000080/2020-2021 | 2684/MD | 06/11/2020 | 60 | MADE & TRADE CO. | 132.4 | 29.22 | 100
511 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAMBALPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000082/2020-2021 | 2437/MD | 12/10/2020 | 60 | HANNAN BUILDERS PVT. LTD. | 156.77 | 138.24 | 1
512 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bejpura Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000084/2025-2026 | 2282/MD | 21/05/2025 | 45 | M I CONSTRUCTION | 30.42 | 0 | 0
513 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of TALSUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000085/2020-2021 | 2255/MD | 29/09/2020 | 90 | TARUN KUMAR BHATTACHARYA | 135.29 | 30 | 0
514 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000085/2025-2026 | 2313/MD | 22/05/2025 | 60 | M/S JHA CONSTRUCTION | 52.11 | 0 | 0
515 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000086/2025-2026 | 2329/MD | 22/05/2025 | 60 | SAHA CONSTRUCTION | 43.45 | 0 | 0
516 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of RAJARAMPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000087/2020-2021 | 2263/MD | 29/09/2020 | 45 | UTTAM KUMAR DUTTA | 59.93 | 48.18 | 0
517 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-III Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000087/2025-2026 | 2330/MD | 22/05/2025 | 60 | BEE GEE CONSTRUCTION | 43.45 | 0 | 0
518 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-IV Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000088/2025-2026 | 2331/MD | 22/05/2025 | 60 | M/S SRINJOYEE | 8.7 | 0 | 0
519 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Birjabhita Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000091/2025-2026 | 2333/MD | 22/05/2025 | 60 | ACHARYYA CONSTRUCTION | 52.11 | 0 | 0
520 | Malda Division | Chanchal Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Piped Water Supply Scheme under Harishchandrapur-I & II, Chanchal-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000098/2025-2026 | 2340/MD | 22/05/2025 | 365 | M/S SABANA CONSTRUCTION | 65.08 | 0 | 0
521 | Malda Division | Chanchal Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Ratua-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000099/2025-2026 | 2341/MD | 22/05/2025 | 365 | M/S TEWARI CONSTRUCTION | 32.63 | 0 | 0
522 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000122/2022-2023 | 1640/MD | 19/07/2022 | 30 | KRISHNENDU DUTTA | 26.59 | 26.43 | 1
523 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000123/2022-2023 | 1641/MD | 19/07/2022 | 30 | UTTAM KUMAR GHOSH | 23.82 | 22.75 | 1
524 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000124/2022-2023 | 1642/MD | 19/07/2022 | 30 | M/S AMIT KUMAR GUPTA | 16.26 | 15.32 | 1
525 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/04/2022 to 27/09/2022) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000127/2022-2023 | 797/MD | 01/04/2022 | 180 | USHA ENTERPRISE | 0.86 | 0.45 | 1
526 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000137/2022-2023 | 213/MSD | 30/06/2022 | 184 | UTTAM KUMAR GHOSH | 0.86 | 2.07 | 1
527 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000141/2022-2023 | 215/MSD | 30/06/2022 | 6 | SHYAMAL KUMAR MAITRA | 0.86 | 1.6 | 1
528 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BHADO Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000155/2020-2021 | 2704/MD | 10/11/2020 | 60 | GHOSH BROTHERS | 148.17 | 148.15 | 100
529 | Malda Division | Chanchal Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Habibpur & Gazole Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000160/2025-2026 | 2880/MD | 17/06/2025 | 365 | SAMBHU NATH SARKAR | 52.09 | 0 | 0
530 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Khanpur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000165/2025-2026 | 2878/MD | 17/06/2025 | 60 | BINA CONSTRUCTION | 61.93 | 0 | 0
531 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 46.89 | 1
532 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jagannathpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000171/2025-2026 | 2888/MD | 17/06/2025 | 255 | M/S SABANA CONSTRUCTION | 90.55 | 0 | 0
533 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-I Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000172/2025-2026 | 2889/MD | 17/06/2025 | 60 | M/S SINHA ENTERPRISE | 43.12 | 0 | 0
534 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gobarjana Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000177/2025-2026 | 2893/MD | 17/06/2025 | 60 | J. M. CONSTRUCTION | 26 | 0 | 0
535 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Khanpur-Hulaspur Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000182/2025-2026 | 2897/MD | 17/06/2025 | 60 | M/S ROY CONSTRUCTION | 31.51 | 0 | 0
536 | Malda Division | Chanchal Sub-Division | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Gunkrul JL-34) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000199/2024-2025 | 2931/MD | 10/06/2024 | 45 | RABIUL ISLAM | 17.29 | 0 | 100
537 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000225/2021-2022 | 2378/MD | 13/08/2021 | 30 | ACHARYYA CONSTRUCTION | 13.48 | 12.47 | 1
538 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-III Water Supply Scheme at Ratua-I under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000226/2021-2022 | 2379/MD | 13/08/2021 | 30 | FUTURE | 13.48 | 0 | 0
539 | Malda Division | Chanchal Sub-Division | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Magura Zone-I Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000228/2025-2026 | 4233/MD | 29/08/2025 | 60 | BEE GEE CONSTRUCTION | 51.17 | 0 | 0
540 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000230/2023-2024 | 504/MSD | 30/06/2023 | 184 | UTTAM KUMAR GHOSH | 0.86 | 0.4 | 26
541 | Malda Division | Chanchal Sub-Division | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold, Land Development & providing Balance FHTC for better Functionality at Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000232/2025-2026 | 4236/MD | 29/08/2025 | 60 | MANIK CHOUDHURY | 91.14 | 0 | 0
542 | Malda Division | Chanchal Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by UPVC pipe line and Construction of Boundary wall ,Aproach Raod at HW & 2nd TW site in for PERAPUR Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000237/2025-2026 | 4520/MD | 12/09/2025 | 292 | BANIK BROTHERS | 90.01 | 0 | 0
543 | Malda Division | Chanchal Sub-Division | Car hiring No. WB 65 A/4911 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000258/2022-2023 | 312/NBC-II | 01/04/2022 | 365 | USHA ENTERPRISE | 3.59 | 1.09 | 0
544 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000258/2024-2025 | 3206/MD | 27/06/2024 | 45 | M/S AMIT KUMAR GUPTA | 69.58 | 0 | 0
545 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Talsur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000259/2024-2025 | 3207/MD | 27/06/2024 | 443 | BEE GEE CONSTRUCTION | 88.37 | 0 | 65
546 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Magura Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000276/2024-2025 | 3196/MD | 27/06/2024 | 45 | NATIONAL CONSTRUCTION | 26.03 | 0 | 0
547 | Malda Division | Chanchal Sub-Division | Extension of UPVC pipe line for Providing Functional Household Tap Connection with Jal Jeevan Mission (JJM) command area of Khanpur Hulashpur Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000281/2024-2025 | 3232/MD | 28/06/2024 | 45 | BIDYUT MAHALDAR | 9.98 | 0 | 0
548 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000305/2020-2021 | 285/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.56 | 17.95 | 1
549 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000321/2024-2025 | 3252/MD | 28/06/2024 | 180 | ARUN KUMAR DAS | 0.86 | 0 | 0
550 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-1) (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000322/2024-2025 | 3253/MD | 28/06/2024 | 180 | SHYAMAL KUMAR MAITRA | 0.86 | 0 | 0
551 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000324/2024-2025 | 3255/MD | 28/06/2024 | 180 | AMIN ENTERPRISE | 0.86 | 0 | 60
552 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1) (Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000325/2024-2025 | 3256/MD | 28/06/2024 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 100
553 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1)(Period from 01/07/2024 to 31/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000326/2024-2025 | 3257/MD | 28/06/2024 | 180 | M/S TEWARI CONSTRUCTION | 0.86 | 0 | 100
554 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/06/2024 to 14/12/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000327/2024-2025 | 3054/MD | 14/06/2024 | 180 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0
555 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000334/2022-2023 | 215/1/MSD | 30/06/2022 | 184 | ARUN KUMAR DAS | 4.5 | 2.17 | 0
556 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000338/2020-2021 | 447/MD | 08/02/2021 | 30 | MANIK CHOUDHURY | 37.13 | 22.88 | 0
557 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under BALUPUR ZONE-II Piped Water Supply Scheme at Ratua-I Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000346/2020-2021 | 512/MD | 09/02/2021 | 60 | JAL PRAVAHIKA PVT. LTD. | 104.87 | 5.04 | 0
558 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of UPVC distribution pipe line for JALALPUR Water Supply Scheme at CHANCHAL- II Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000352/2020-2021 | 552/MD | 12/02/2021 | 30 | FUTURE | 3.33 | 5.86 | 0
559 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000356/2020-2021 | 554/MD | 12/02/2021 | 30 | RAY CONSTRUCTION CO. | 57.64 | 80.35 | 1
560 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under DAULATNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000357/2020-2021 | 553/MD | 12/02/2021 | 60 | NEOGI ENTERPRISE | 120.32 | 119.96 | 1
561 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM) under command area of Bhado of BHADO Water Supply Scheme under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000381/2022-2023 | 2735/MD | 18/11/2022 | 30 | M/S MANDAL & SONS | 6.77 | 6.11 | 0
562 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASHPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000395/2022-2023 | 2955/MD | 07/12/2022 | 30 | BIDYUT MAHALDAR | 5.17 | 0 | 100
563 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Khanpur-Hulaspur W/S Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000403/2022-2023 | 2963/MD | 07/12/2022 | 30 | BIDYUT MAHALDAR | 7.04 | 0 | 100
564 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000408/2022-2023 | 2991/MD | 07/12/2022 | 45 | S. R. CONSTRUCTION | 25.41 | 21.2 | 0
565 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for hiring of inspection vehicle (Motor Cab or Maruti Omni Category (Standard), Non-Air Condition, Bharat Stage-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine) in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, P.H.E. Dte. (Period from 06/01/2023 to 05/07/2023) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000437/2022-2023 | 193/RWS | 05/01/2023 | 181 | SHYAMAL KUMAR MAITRA | 0.86 | 0.93 | 15
566 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/09/2024 to 28/02/2025). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000444/2024-2025 | 4590/MD | 30/08/2024 | 180 | RAJENDRA PRASAD SINGH | 0.86 | 0 | 0
567 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mekpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000449/2023-2024 | 3366/MD | 29/08/2023 | 45 | MANIK CHOUDHURY | 16.14 | 0 | 90
568 | Malda Division | Chanchal Sub-Division | Replacement of 200 mm dia. X 150 mm Dia.) Tubewell No:-2 (130 M Deep) by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MAHAMMADPUR Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000451/2024-2025 | 4807/MD | 13/09/2024 | 78 | GOBINDA ENTERPRISE | 8.29 | 0 | 100
569 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Rajarampur Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000452/2023-2024 | 3369/MD | 29/08/2023 | 45 | M/S PRATIMA CONSTRUCTION | 16.13 | 0 | 100
570 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Saiyedpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000454/2023-2024 | 3371/MD | 29/08/2023 | 45 | S. R. CONSTRUCTION | 20.14 | 0 | 100
571 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under BEHERPUR ZONE-I Pipe Water Supply Scheme at Bamangola Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000481/2020-2021 | 435/MD | 08/02/2021 | 60 | PROJECT INDIA | 126.35 | 16.31 | 100
572 | Malda Division | Chanchal Sub-Division | Providing car on daily hirer basis @ Rs. 12.00/km for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000503/2022-2023 | 653/CSD | 07/11/2022 | 365 | SAUDIPTA KUMAR DAS | 4.56 | 0.33 | 0
573 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000510/2022-2023 | 520/MSD | 30/12/2022 | 182 | UTTAM KUMAR GHOSH | 0.86 | 1.51 | 15
574 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Bejpura Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000513/2021-2022 | 542/CSD | 27/10/2021 | 30 | NEOGI ENTERPRISE | 4.26 | 4.24 | 1
575 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000514/2021-2022 | 545/CSD | 01/11/2021 | 30 | FUTURE | 4.72 | 4.6 | 1
576 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000515/2021-2022 | 546/CSD | 01/11/2021 | 30 | FUTURE | 2.66 | 2.66 | 1
577 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000518/2022-2023 | 2474/MD | 21/10/2022 | 365 | SHABNAM ARA | 4.5 | 2.33 | 21
578 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000529/2021-2022 | 3573/MD | 20/12/2021 | 30 | M/S JHA CONSTRUCTION | 39.81 | 36.95 | 1
579 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000530/2021-2022 | 3574/MD | 20/12/2021 | 30 | GOBINDA ENTERPRISE | 19.97 | 19.47 | 1
580 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000531/2021-2022 | 3575/MD | 20/12/2021 | 30 | PABITRA MANDAL | 19.48 | 17.34 | 1
581 | Malda Division | Chanchal Sub-Division | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 28/09/2022 to 26/03/2023) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000533/2022-2023 | 1108/MD | 20/09/2022 | 180 | USHA ENTERPRISE | 4.5 | 1.02 | 0
582 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Different dia. Damaged pipe line repair on emergency basis (damage due to widening of road) in connection with annual operation maintenance and providing FHTC to villagers under MEKPUR Piped Water Supply Scheme at Old Malda Dev. block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000549/2021-2022 | 513/MSD | 31/12/2021 | 1 | A. K. CONSTRUCTION | 2.06 | 0 | 0
583 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000552/2020-2021 | 2684/MD | 03/12/2020 | 1 | MADE & TRADE CO. | 0 | 23.94 | 1
584 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000557/2021-2022 | 520/MSD | 31/12/2021 | 181 | SHYAMAL KUMAR MAITRA | 0.86 | 1.2 | 1
585 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAGURA ZONE-I Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000559/2020-2021 | 2551/MD | 15/10/2020 | 30 | MILLENNIUM ENTERPRISR | 1 | 13.37 | 1
586 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DALLA Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000560/2020-2021 | 2438/MD | 12/10/2020 | 120 | M/S JHA CONSTRUCTION | 10 | 11.19 | 1
587 | Malda Division | Chanchal Sub-Division | Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 26/06/2023 to 22/12/2023) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000562/2023-2024 | 1452/NBC-II | 21/06/2023 | 181 | USHA ENTERPRISE | 2.19 | 0.94 | 42
588 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000563/2021-2022 | 49/MD | 13/01/2022 | 60 | S. R. CONSTRUCTION | 40.3 | 39.7 | 1
589 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000564/2021-2022 | 48/MD | 13/01/2022 | 21 | BIDYUT MAHALDAR | 7.56 | 6.11 | 0
590 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/01/2021 to 31/12/2021). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000573/2020-2021 | 3280/MD | 30/12/2020 | 365 | SHYAMAL KUMAR MAITRA | 1.73 | 1.29 | 1
591 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malsa Mouza of KhanpurHulaspur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000574/2024-2025 | 5485/MD | 24/10/2024 | 361 | M/S /FAIZUL HAQUE BISWAS | 26.08 | 0 | 40
592 | Malda Division | Chanchal Sub-Division | Continuation work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/02/2021 to 30/09/2021). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000579/2020-2021 | 276/MD | 28/01/2021 | 365 | RANJIT ADHIKARY | 2.66 | 1.26 | 0
593 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000604/2023-2024 | 3810/MD | 16/10/2023 | 30 | RABIUL ISLAM | 8.8 | 0 | 90
594 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khopakati Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000625/2024-2025 | 5832/MD | 22/11/2024 | 450 | M/S SABANA CONSTRUCTION | 55.74 | 0 | 0
595 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Emergent installation of Sulice Valve & Construction of Sluice Valve & Repairing of FHTC for Khanpur Hulashpur Water Supply Scheme under Malda division, P.H.E. Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000631/2021-2022 | 31/CSD | 05/01/2022 | 15 | BIDYUT MAHALDAR | 1.27 | 1.27 | 1
596 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 3.9 | 1
597 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) under commend area of Kutubsahar Water Supply Scheme of Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000658/2021-2022 | 1899/MD | 30/06/2021 | 120 | RABIUL ISLAM | 10 | 0.63 | 0
598 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) including upvc laying in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda (Phase - II). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000663/2021-2022 | 742/MD | 28/03/2022 | 30 | FUTURE | 22.06 | 21.09 | 1
599 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-II Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000668/2024-2025 | 6167/MD | 05/12/2024 | 45 | S. R. CONSTRUCTION | 63.36 | 0 | 0
600 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Replacement of different dia A.C pipe line (damage due to widening of road) by laying of different dia UPVC pipe in connection with annual operation maintenance and providing FHTC to Villagers under RAJARAMPUR Piped Water Supply Scheme of Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000672/2021-2022 | 142/MSD | 31/03/2022 | 2 | SSD CONSTRUCTION | 4.84 | 4.35 | 1
601 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/02/2022 to 31/03/2022) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000703/2021-2022 | 232/MD | 27/01/2022 | 59 | USHA ENTERPRISE | 0.28 | 0.33 | 1
602 | Malda Division | Chanchal Sub-Division | Car hiring No. 51C/7999 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/03/2022 to 30/06/2022) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000704/2021-2022 | 473/MD | 25/02/2022 | 120 | TARUN KUMAR BHATTACHARYA | 0.58 | 1.04 | 1
603 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000705/2021-2022 | 522/MSD | 31/12/2021 | 181 | UTTAM KUMAR GHOSH | 0.86 | 2.38 | 1
604 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000706/2021-2022 | 521/MSD | 31/12/2021 | 365 | ARUN KUMAR DAS | 0.86 | 1.76 | 1
605 | Malda Division | Chanchal Sub-Division | Supply of Forms & Stationary articles for the use of this office. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000707/2021-2022 | 3456/MD | 06/12/2021 | 1 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.28 | 1.28 | 1
606 | Malda Division | Chanchal Sub-Division | Supply of Stationary articles for the use of Malda District Laboratory. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000708/2021-2022 | 367/MD | 10/02/2022 | 1 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.35 | 0.35 | 1
607 | Malda Division | Chanchal Sub-Division | Supply of Stationary articles for the use of Malda District Laboratory. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000709/2021-2022 | 368/MD | 10/02/2022 | 1 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.1 | 0.46 | 0
608 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000717/2021-2022 | 520/MSD | 31/12/2021 | 6 | SHYAMAL KUMAR MAITRA | 2.16 | 0.67 | 0
609 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000718/2021-2022 | 521/MSD | 31/12/2021 | 181 | ARUN KUMAR DAS | 2.16 | 0.9 | 0
610 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DALLA Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000718/2023-2024 | 4767/MD | 05/12/2023 | 45 | A. B. CONSTRUCTION | 14.09 | 0 | 100
611 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000720/2023-2024 | 4769/MD | 05/12/2023 | 45 | ACHARYYA CONSTRUCTION | 12.14 | 0 | 100
612 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000721/2024-2025 | 6412/MD | 19/12/2024 | 194 | PABITRA MANDAL | 40.29 | 0 | 0
613 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mihaghat Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000737/2024-2025 | 56 | 08/01/2025 | 311 | ASHIS CONSTRUCTION | 26.57 | 0 | 0
614 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BALUPUR ZONE-II & III Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000742/2023-2024 | 5247/MD | 22/12/2023 | 45 | M/S. TEWARI CONSTRUCTION | 56.74 | 0 | 40
615 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHOPAKATI Water Supply Scheme at Harishchandrapuir-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000743/2023-2024 | 5245/MD | 22/12/2023 | 45 | M/S FOUR STAR CONSTRUCTION | 38.41 | 0 | 98
616 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/02/2023 to 19/08/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000760/2022-2023 | 809/MD | 17/02/2023 | 180 | M/S. TEWARI CONSTRUCTION | 0.86 | 2.22 | 100
617 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/03/2023 to 09/08/2023). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000761/2022-2023 | 1020/MD | 10/03/2023 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 1.83 | 100
618 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000761/2024-2025 | 80 | 13/01/2025 | 45 | M/S AMIT KUMAR GUPTA | 65.21 | 0 | 1
619 | Malda Division | Chanchal Sub-Division | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000771/2024-2025 | 271/MD | 28/01/2025 | 15 | FUTURE | 0.84 | 0 | 100
620 | Malda Division | Chanchal Sub-Division | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-II Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000772/2024-2025 | 272/MD | 28/01/2025 | 15 | FUTURE | 0.84 | 0 | 100
621 | Malda Division | Chanchal Sub-Division | Placing of Diesel Driven Bolero Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/02/2020 to 31/01/2021) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000778/2019-2020 | 349/MD | 28/01/2020 | 0 | RANJIT ADHIKARY | 1.51 | 1.51 | 1
622 | Malda Division | Chanchal Sub-Division | Augmentation of work to ensure proper functioning of 250 M³ Capacity 20 Mtr. Staging height RCC Over Head Reservoir of Dalla Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000832/2024-2025 | 1060/MD | 19/03/2025 | 60 | BENGAL ENGINEERING COMPANY | 8.47 | 0 | 0
623 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Daulatnagar Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000854/2024-2025 | 1047/MD | 18/03/2025 | 75 | M/S PARIMAL DAS | 30.45 | 0 | 0
624 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Jalalpur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000861/2024-2025 | 1054/MD | 18/03/2025 | 75 | M/S MOON LIGHT CONSTRUCTION & CO. | 28.53 | 0 | 0
625 | Malda Division | Chanchal Sub-Division | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DALLA Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000884/2024-2025 | 1123/MD | 21/03/2025 | 45 | M/S GHOSH CONSTRUCTION | 9.58 | 0 | 0
626 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000894/2023-2024 | 1010/MSD | 29/12/2023 | 183 | UTTAM KUMAR GHOSH | 0.86 | 0 | 25
627 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nikhrail command area of MAHANADAPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000907/2023-2024 | 285/MD | 11/01/2024 | 45 | M/S AYUSH BUILDERS | 6.37 | 0 | 100
628 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000913/2023-2024 | 386/MD | 17/01/2024 | 45 | PARIJAT RAY | 58.89 | 0 | 70
629 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000922/2023-2024 | 1011/MSD | 29/12/2023 | 183 | ARUN KUMAR DAS | 0.86 | 0 | 67
630 | Malda Division | Chanchal Sub-Division | Continuation of work order for hiring of inspection vehicle(Motor Cab or Maruti Omni Category(Standard,Non-Air Condition, Bharat Stage-III purchase on or after 01.05.2008 with Diesel/LPG/CNG Engine)in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, PHE Dte.(Period from 01.01.2024 to 30.06.2024) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000930/2023-2024 | 431/RWS | 29/12/2023 | 182 | SHYAMAL KUMAR MAITRA | 0.86 | 0 | 70
631 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/08/2023 to 15/02/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000938/2023-2024 | 3225/MD | 18/08/2023 | 180 | M/S. TEWARI CONSTRUCTION | 0.86 | 0 | 90
632 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/08/2023 to 06/02/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000939/2023-2024 | 3029/MD | 08/08/2023 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 99
633 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hazzabari Village of Khord Babupur Mouza under KUTUB SAHAR Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000983/2023-2024 | 978/MD | 04/03/2024 | 45 | DHRITIPALI | 12.79 | 0 | 100
634 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/03/2024 to 31/08/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000993/2023-2024 | 843/MD | 22/02/2024 | 180 | RAJENDRA PRASAD SINGH | 0.86 | 0 | 17
635 | Malda Division | Chanchal Sub-Division | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 23/12/2023 to 19/06/2024) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001010/2023-2024 | 2089/NBC-II | 20/12/2023 | 180 | USHA ENTERPRISE | 0.86 | 0 | 26
636 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001011/2023-2024 | 1513/MD | 16/03/2024 | 45 | A. B. CONSTRUCTION | 26.41 | 0 | 0
637 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gun Sankrul Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001021/2023-2024 | 1189/MD | 14/03/2024 | 383 | TARUN KUMAR DEY | 26.39 | 0 | 0
638 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Chanchal-I & Harishchandrapur-I Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001039/2023-2024 | 892/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.85 | 0 | 100
639 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001040/2023-2024 | 893/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.85 | 0 | 100
640 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001041/2023-2024 | 894/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 100
641 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001042/2023-2024 | 895/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 100
642 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001043/2023-2024 | 896/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 100
643 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation, Retrofitting Schemes and different CWPP site of Chanchal-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001044/2023-2024 | 897/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 100
644 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes and different CWPP site of Old Malda Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001045/2023-2024 | 898/MD | 28/02/2024 | 7 | PRITAM ENTERPRISE | 0.85 | 0 | 100
645 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation and Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001046/2023-2024 | 899/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.85 | 0 | 100
646 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different CWPP site of Gazole & Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001047/2023-2024 | 900/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.85 | 0 | 100
647 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001048/2023-2024 | 901/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.97 | 0 | 100
648 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Bamongola Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001049/2023-2024 | 902/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 100
649 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Gazole & Old Malda Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001050/2023-2024 | 903/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 100
650 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001051/2023-2024 | 904/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 100
651 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Gazole Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001052/2023-2024 | 905/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 100
652 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at different CWPP sites of Chanchal-I, Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001053/2023-2024 | 906/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.73 | 0 | 100
653 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes and different CWPP sites of Chanchal-I, Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001054/2023-2024 | 907/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.6 | 0 | 100
654 | Malda Division | Chanchal Sub-Division | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Englishbazar & Manikchak Block under RWS Malda Sub-Division in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001055/2023-2024 | 908/MD | 28/02/2024 | 7 | PRITAM ENTERPRISE | 0.36 | 0 | 100
655 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000003/2021-2022 | 3552/MD | 26/11/2021 | 0 | Resource Division | 8.78 | 0 | 0
656 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000004/2021-2022 | 3585/MD | 21/12/2021 | 0 | Resource Division | 6.45 | 0 | 0
657 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000006/2021-2022 | 456/MD | 22/02/2022 | 0 | Resource Division | 3.29 | 0 | 0
658 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000008/2022-2023 | 1258/MD | 27/05/2022 | 0 | Resource Division | 8.01 | 0 | 0
659 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000011/2024-2025 | 3923/MD | 06/08/2024 | 0 | Resource Division | 4.31 | 0 | 0
660 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000013/2024-2025 | 3926/MD | 06/08/2024 | 0 | Resource Division | 5.13 | 0 | 0
661 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000023/2024-2025 | 5970/MD | 28/11/2024 | 0 | Resource Division | 154 | 0 | 0
662 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000025/2024-2025 | 5973/MD | 28/11/2024 | 0 | Resource Division | 154 | 0 | 0
663 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000100/2023-2024 | 30/MD | 04/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
664 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000102/2023-2024 | 32/MD | 04/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
665 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000110/2023-2024 | 40/MD | 04/01/2024 | 0 | Resource Division | 5.85 | 0 | 0
666 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000111/2023-2024 | 52/MD | 04/01/2024 | 0 | Resource Division | 1.93 | 0 | 0
667 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000113/2023-2024 | 56/MD | 04/01/2024 | 0 | Resource Division | 0.31 | 0 | 0
668 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000176/2023-2024 | 533/MD | 30/01/2024 | 0 | Resource Division | 12.94 | 0 | 0
669 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000029/2020-2021 | 1964/MD | 31/08/2020 | 30 | M/S KUNDU CONSTRUCTION | 39.43 | 0.01 | 1
670 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing FHTC (Functional House hold Tap Connection) of Ranghat Piped Water Supply Scheme at Chanchal-II Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000056/2023-2024 | 1991/MD | 17/05/2023 | 15 | M/S FOUR STAR CONSTRUCTION | 9.06 | 0 | 100
671 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of different dia sluice valve chambers with other allied work to proper functioning of FHTC work within the command area of JAGJIBANPUR Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000400/2022-2023 | 2960/MD | 07/12/2022 | 30 | M/S AYUSH BUILDERS | 3.64 | 3.64 | 1
672 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme at Habibpu Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000554/2020-2021 | 2447/MD | 12/10/2020 | 120 | MANIK CHOUDHURY | 12 | 12 | 1
673 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandapur-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00486/2022-2023 | BP-2022-23-192 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
674 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at BHALUKA FATEPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000016/2023-2024 | 1673/MD | 18/04/2023 | 449 | MERCURY ENGINEERING COMPANY | 10.71 | 0 | 95
675 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000025/2022-2023 | 1192/MD | 24/05/2022 | 31 | M/S GULFAM CONSTRUCTION. | 4.78 | 0 | 0
676 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000026/2022-2023 | 1193/MD | 24/05/2022 | 31 | M/S SRINJOYEE | 4.78 | 0 | 0
677 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 02 (Two) Nos. 150mm. Dia. x 100mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Bhaluka Fatepur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000046/2022-2023 | 1395/MD | 14/06/2022 | 30 | A. L. ENGINEERING SOLUTION | 10 | 0 | 0
678 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000083/2023-2024 | 2173/MD | 07/06/2023 | 30 | M/S EHAN ENTERPRISE | 11.04 | 0 | 0
679 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Bhaluka Fatepur Pipe Water Supply Scheme at Harishchandrapur-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000136/2022-2023 | 1828/MD | 04/08/2022 | 90 | GHOSH BROTHERS | 348.1 | 290.89 | 68
680 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000152/2021-2022 | 1750/MD | 15/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 2.86 | 1
681 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Bhaluka Fatepur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000177/2024-2025 | 2952/MD | 10/06/2024 | 30 | SARIF BUILDERS | 9.93 | 0 | 0
682 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 700 M3 Capacity OHR with FHTC (Mouza-Bhaluka) of Bhaluka Fatepur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000354/2023-2024 | 3020/MD | 08/08/2023 | 711 | GHOSH BROTHERS | 283.26 | 0 | 0
683 | Malda Division | Malda Mechanical Division | Continuation work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000695/2021-2022 | 1840/MD | 30/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 1.45 | 0 | 0
684 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000962/2023-2024 | 715/MD | 09/02/2024 | 45 | J. M. CONSTRUCTION | 14.06 | 0 | 80
685 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at BHALUKA FATEPUR Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000971/2023-2024 | 830/MD | 21/02/2024 | 45 | OLI CONSTRUCTION | 4.17 | 0 | 0
686 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000012/2022-2023 | 1871/MD | 16/08/2022 | 0 | Resource Division | 65.9 | 0 | 0
687 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000026/2023-2024 | 1607/MD | 11/04/2023 | 0 | Resource Division | 29.16 | 0 | 0
688 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000037/2023-2024 | 1801 | 27/04/2023 | 0 | Resource Division | 59.54 | 0 | 0
689 | Malda Division | Malda Mechanical Division | Formal work order for Augmentation of DEOTALA Piped water supply scheme for the work of Geotechnical Study,construction of 500 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Gazole Dev Block under Malda Division PH Engg Dte. In the District of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000003/2022-2023 | 868/MD | 08/04/2022 | 1208 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 460.03 | 120.32 | 50
690 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Rising main with connection between 1st Tube well and 3 rd Tube well and condtructtion of standpost for DEOTALA Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000031/2022-2023 | 1308/MD | 01/06/2022 | 30 | JIBON GHOSH | 4.43 | 2.05 | 0
691 | Malda Division | Malda Mechanical Division | Augmentation of Head Work Site pump House at DEOTALA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000117/2025-2026 | 2468/MD | 28/05/2025 | 45 | S. R. ENTERPRISE | 2.06 | 0 | 100
692 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Deotala Water Supply Scheme in Gazole block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000148/2021-2022 | 1746/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 1.78 | 1
693 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Deotala Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000718/2024-2025 | 6409/MD | 19/12/2024 | 331 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 26.07 | 0 | 0
694 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Deotala Piped Water Supply Scheme at Deotala Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000889/2023-2024 | 163/MD | 08/01/2024 | 449 | M I CONSTRUCTION | 14.99 | 0 | 100
695 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Car-2) (Period from 01/03/2025 to 31/08/2025). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/001038/2024-2025 | 752/MD | 27/02/2025 | 181 | SINGH BROTHERS | 0.86 | 0 | 0
696 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000004/2022-2023 | 1106/MD | 17/05/2022 | 0 | Resource Division | 37.39 | 0 | 0
697 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000042/2022-2023 | 1585/MD | 28/03/2023 | 0 | Resource Division | 2.3 | 0 | 0
698 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000194/2023-2024 | 816/MD | 21/02/2024 | 0 | Resource Division | 45.08 | 0 | 0
699 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SAHAPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000375/2022-2023 | 780/MD | 17/02/2023 | 30 | SAUDAGAR (INDIA) | 9.2 | 9.18 | 0
700 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of SAHAPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000490/2022-2023 | 594/MD | 09/02/2023 | 570 | M/S /FAIZUL HAQUE BISWAS | 57.62 | 29.26 | 90
701 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000020/2023-2024 | 1616/MD | 11/04/2023 | 0 | Resource Division | 2.45 | 0 | 0
702 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000020/2024-2025 | 3996/MD | 08/08/2024 | 0 | Resource Division | 2.34 | 0 | 0
703 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000081/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 1.2 | 0 | 0
704 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000310/2022-2023 | 2305/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9.06 | 9.02 | 1
705 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000346/2022-2023 | 2801/MD | 24/11/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.69 | 6.53 | 0
706 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for PURBA BINODPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000357/2022-2023 | 2506/MD | 03/11/2022 | 530 | TARUN KUMAR DEY | 41.23 | 38.6 | 1
707 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Purba Binodpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000996/2023-2024 | 1511/MD | 16/03/2024 | 230 | SARAJ TRADERS | 26.4 | 0 | 100
708 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-4 & 5 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block. under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000338/2022-2023 | 2510/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 10.01 | 8.57 | 100
709 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of KUTUB SAHAR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000348/2022-2023 | 2802/MD | 24/11/2022 | 45 | MARSS INTERNATIONAL | 6.69 | 0 | 100
710 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line (damage due to widening of road) by different dia UPVC pipe for KUTUB SAHAR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000361/2022-2023 | 2604/MD | 10/11/2022 | 690 | BEE GEE CONSTRUCTION | 55.12 | 0 | 65
711 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Tube Well No.-5 site in connection with Source Augmentation of KUTUB SAHAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000366/2023-2024 | 3055/MD | 09/08/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.15 | 0 | 100
712 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well No. - 5 (160 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000445/2023-2024 | 3352/MD | 29/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 11.88 | 0 | 100
713 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at 5th Tube Well Site of Kutub Sahar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000720/2024-2025 | 6411/MD | 19/12/2024 | 45 | ZEOLITE FRESH INDIA | 17.27 | 0 | 0
714 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Kutubshar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001005/2023-2024 | 1183/MD | 14/03/2024 | 180 | M/S JHA CONSTRUCTION | 17.28 | 0 | 0
715 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Tubewell site at Khord Babupur Mouza of Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001006/2023-2024 | 1193/MD | 14/03/2024 | 293 | AHONA ENTERPRISE | 10.71 | 0 | 100
716 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Tubewell site at Misipur Mouza of Kutubsahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001024/2023-2024 | 1250/MD | 15/03/2024 | 382 | SATELLITE CONSTRUCTION | 9.6 | 0 | 100
717 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000022/2022-2023 | 2409/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
718 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000001/2025-2026 | 1298/MD | 04/04/2025 | 272 | UTTAM KUMAR GHOSH | 96.59 | 0 | 0
719 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000008/2023-2024 | 1570/MD | 10/04/2023 | 933 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 735.7 | 0 | 30
720 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head work site of Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000488/2024-2025 | 5001/MD | 27/09/2024 | 45 | PABITRA MANDAL | 23.69 | 0 | 0
721 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000667/2022-2023 | 1061/MD | 15/03/2023 | 60 | BINA CONSTRUCTION | 51.95 | 0 | 100
722 | Malda Division | RWS Malda Sub-Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Krishnapur, Horgoa, Perapur, Jamalpur & Rajarampur PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000953/2024-2025 | 642/MD | 19/02/2025 | 7 | SADHANA CONSTRUCTION | 0.8 | 0 | 0
723 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tubewell site of Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001033/2023-2024 | 1259/MD | 15/03/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.5 | 0 | 0
724 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000146/2023-2024 | 123/MD | 06/01/2024 | 0 | Resource Division | 46.72 | 0 | 0
725 | Malda Division | RWS Malda Sub-Division | Laying of Pipeline work at Mianagar Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000277/2024-2025 | 3197/MD | 27/06/2024 | 45 | CHARU CONSTRUCTION | 18.22 | 0 | 100
726 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia) Tube Well no-3 (100 Mtr. deep )by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000305/2022-2023 | 2300/MD | 28/09/2022 | 30 | MECHANO TRADING CO. | 7.59 | 0 | 100
727 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000341/2022-2023 | 2548/MD | 03/11/2022 | 45 | ANJIMA CONSTRUCTION CO. | 6.69 | 0 | 100
728 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MIANAGAR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000355/2022-2023 | 2504/MD | 03/11/2022 | 45 | DEBAPRIYA SAHA | 76.83 | 52.55 | 100
729 | Malda Division | RWS Malda Sub-Division | Replacement of 200 mm (all through)Big Dia. Tubewell No:-1 (130MDeep) at Headwork site by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte,in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000449/2024-2025 | 4806/MD | 13/09/2024 | 152 | JOY GURU ENTERPRISE | 9.56 | 0 | 100
730 | Malda Division | RWS Malda Sub-Division | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at MIANAGAR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000880/2024-2025 | 1119/MD | 21/03/2025 | 45 | CHARU CONSTRUCTION | 9.63 | 0 | 0
731 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Mianagar Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001027/2023-2024 | 1253/MD | 15/03/2024 | 30 | CHARU CONSTRUCTION | 9.61 | 0 | 0
732 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DUBA KHOSKON Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000374/2023-2024 | 3118/MD | 11/08/2023 | 509 | M/S NANDY ENTERPRISES | 904.54 | 0 | 0
733 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at DubaKhaskon Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000726/2024-2025 | 6417/MD | 19/12/2024 | 286 | M/S MANDAL & SONS | 36.96 | 0 | 0
734 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000038/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 15.2 | 0 | 0
735 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000168/2023-2024 | 249/MD | 10/01/2024 | 0 | Resource Division | 14.04 | 0 | 0
736 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of BISHANPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000042/2023-2024 | 1911/MD | 11/05/2023 | 270 | A. K. CONSTRUCTION | 349.38 | 0 | 25
737 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Bhakri, Chandrapara & Dhangra Bishanpur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000945/2024-2025 | 634/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.9 | 0 | 0
738 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Choupaldanga, Wari, Gochiya, Bangrua, Kharangapur Jabra, Bishanpur PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000957/2024-2025 | 646/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 100
739 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000034/2023-2024 | 1803/MD | 27/04/2023 | 0 | Resource Division | 38.38 | 0 | 0
740 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000123/2023-2024 | 93/MD | 05/01/2024 | 0 | Resource Division | 8.31 | 0 | 0
741 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of NEMUA Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000006/2025-2026 | 2393/MD | 26/05/2025 | 75 | SURAJIT MONDAL | 5.98 | 0 | 0
742 | Malda Division | RWS Malda Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 40 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of NEMUA Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000609/2023-2024 | 4113/MD | 10/10/2023 | 120 | DEBAPRIYA SAHA | 17.17 | 0 | 90
743 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (102.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at NEMUA Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000710/2022-2023 | 1168/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.8 | 6.43 | 100
744 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Nemua Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000731/2022-2023 | 1205/MD | 21/03/2023 | 45 | BINA CONSTRUCTION | 4.15 | 3.47 | 100
745 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall and Pathway at 3rd Tube Well Site of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000965/2023-2024 | 804/MD | 21/02/2024 | 273 | GOUTAM SAHA | 8.77 | 0 | 60
746 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000184/2023-2024 | 776/MD | 20/02/2024 | 0 | Resource Division | 6.16 | 0 | 0
747 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 20m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Sailpur Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. (3rd Call). | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000013/2025-2026 | 2421/MD | 27/05/2025 | 180 | M/S KUNDU CONSTRUCTION | 14.62 | 0 | 0
748 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for SAILPUR Piped Water Supply Scheme at Englishbazar Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000700/2022-2023 | 1157/MD | 20/03/2023 | 45 | S. R. CONSTRUCTION | 18.8 | 15.2 | 79
749 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 96.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAILPUR Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000709/2022-2023 | 1167/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.21 | 6.04 | 100
750 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sailpur Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000759/2022-2023 | 1306/MD | 23/03/2023 | 45 | M/S A. B. CONSTRUCTION | 4.14 | 0 | 95
751 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sailpur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000826/2024-2025 | 703/MD | 21/02/2025 | 45 | CHARU CONSTRUCTION | 27.37 | 0 | 0
752 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000182/2023-2024 | 775/MD | 20/02/2024 | 0 | Resource Division | 1.85 | 0 | 0
753 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Fatepur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000272/2024-2025 | 3229/MD | 28/06/2024 | 637 | THREE BROTHERS CONSTRUCTION & CO | 26.65 | 0 | 60
754 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of FATEPUR and its adjoinining mouzas Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000642/2022-2023 | 1028/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 1157.58 | 0 | 50
755 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000147/2023-2024 | 124/MD | 06/01/2024 | 0 | Resource Division | 121.21 | 0 | 0
756 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000153/2023-2024 | 243/MD | 10/01/2024 | 0 | Resource Division | 13.18 | 0 | 0
757 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dilalbati Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000125/2025-2026 | 2483/MD | 28/05/2025 | 126 | M/S GLOBAL ENTERPRISE | 4.85 | 0 | 0
758 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of DILALBATI Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000387/2023-2024 | 3285/MD | 23/08/2023 | 1010 | ZEST INFRACON | 155.98 | 0 | 50
759 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000681/2022-2023 | 1130/MD | 20/03/2023 | 45 | SOFIKUL ISLAM | 6.54 | 0 | 100
760 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000683/2022-2023 | 1135/MD | 20/03/2023 | 45 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 4.15 | 0 | 100
761 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Saidpur, Alal Zone-I, II, III, Rahimpur, Dilalbati & Altor PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000952/2024-2025 | 641/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
762 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000064/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 7.53 | 0 | 0
763 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000166/2023-2024 | 242/MD | 10/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
764 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of ALAL ZONE- III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000096/2023-2024 | 2324/MD | 08/06/2023 | 1152 | SAMBHU NATH SARKAR | 283.63 | 0 | 85
765 | Malda Division | Malda Mechanical Division | Dedicated Pipe laying for better Functionality and Providing Balance FHTC, Construction of Approach Road, Land development and allied work for ALAL Zone-III Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000215/2025-2026 | 3776/MD | 04/08/2025 | 60 | SAMBHU NATH SARKAR | 11.17 | 0 | 0
766 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000267/2024-2025 | 3214/MD | 27/06/2024 | 247 | SAMBHU NATH SARKAR | 28.48 | 0 | 100
767 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000638/2024-2025 | 5917/MD | 26/11/2024 | 176 | ABHIJIT CONSTRUCTION | 14.16 | 0 | 100
768 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-III Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000688/2021-2022 | 653/MD | 22/03/2022 | 15 | TECHVISION | 2.95 | 2.94 | 1
769 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at ALAL ZONE-III Piped Water Supply Scheme under Gazole Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000972/2023-2024 | 831/MD | 21/02/2024 | 45 | SADHANA CONSTRUCTION | 4.16 | 0 | 100
770 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000072/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 19.37 | 0 | 0
771 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000157/2023-2024 | 245/MD | 10/01/2024 | 0 | Resource Division | 4.42 | 0 | 0
772 | Malda Division |  | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MAHAMMADPUR Water Supply Scheme at Malda Old Block under Malda Division, PHE Dte. |  |  | ORD/000028/2020-2021 | 1963/MD | 31/08/2020 | 30 | A. K. CONSTRUCTION | 25.17 | 44.97 | 0
773 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. |  |  | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 12 | 1
774 | Malda Division |  | Replacement of 200 mm dia. X 150 mm Dia.) Tubewell No:-2 (130 M Deep) by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MAHAMMADPUR Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte. |  |  | ORD/000451/2024-2025 | 4807/MD | 13/09/2024 | 78 | GOBINDA ENTERPRISE | 8.29 | 0 | 100
775 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MAHAMMADPUR Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000721/2023-2024 | 4770/MD | 05/12/2023 | 45 | M/S EHAN ENTERPRISE | 8.07 | 0 | 100
776 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of SERBABAR BALARAMPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000065/2023-2024 | 2019/MD | 18/05/2023 | 594 | JAHANGIR ALAM | 596.09 | 0 | 75
777 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at Head Work site of Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000153/2025-2026 | 2691/MD | 04/06/2025 | 45 | JAHANGIR ALAM | 28.62 | 0 | 0
778 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000654/2024-2025 | 6364/MD | 17/12/2024 | 45 | JAHANGIR ALAM | 58.94 | 0 | 0
779 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000024/2023-2024 | 1809/MD | 27/04/2023 | 0 | Resource Division | 18.28 | 0 | 0
780 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000031/2022-2023 | 3043/MD | 12/12/2022 | 0 | Resource Division | 25.7 | 0 | 0
781 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme at Harshchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000162/2020-2021 | 3046/MD | 11/12/2020 | 30 | S DUTTA | 44.04 | 78.69 | 1
782 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000165/2020-2021 | 2718/MD | 10/11/2020 | 30 | NIRENDRA NATH KUNDU | 58.72 | 0.33 | 1
783 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mouza- Dakshin Gouripur, Village-Baghuya, JL No. 167 GP-Malior-II of DAKSHIN GOURIPUR Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000382/2022-2023 | 2736/MD | 18/11/2022 | 30 | M/S SABANA CONSTRUCTION | 3.28 | 2.07 | 100
784 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000655/2021-2022 | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 0 | 1
785 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Bodrail, JL. No. 167, G.P.-Kanturka of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000102/2020-2021 | 2298/MD | 30/09/2020 | 31 | BAKUL CHANDRA HALDAR | 2.82 | 5.03 | 0
786 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000136/2020-2021 | 2446/MD | 12/10/2020 | 30 | KRISHNENDU DUTTA | 43.4 | 31.8 | 1
787 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chatra, JL. No. 29, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000143/2020-2021 | 2453/MD | 12/10/2020 | 30 | BENGAL ENGINEERING COMPANY | 6.92 | 11.35 | 0
788 | Malda Division | RWS Malda Sub-Division | Stationary Bill under Malda Division, PHE Dte. n the district of Malda | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000259/2022-2023 | 1969/MD | 26/08/2022 | 1 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.26 | 1.26 | 1
789 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Detail route survey and design & drawing of distribution network, for providing FHTC in Uttar Chandipur Zone-I Water Supply scheme of Manikchak Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000429/2022-2023 | 478/MSD | 09/12/2022 | 15 | FUTURE | 0.84 | 0.01 | 1
790 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sailpur Water Supply Scheme at Englishbazar Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000453/2023-2024 | 3370/MD | 29/08/2023 | 45 | BENGAL ENGINEERING COMPANY | 11.91 | 0 | 95
791 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for ................ at Bamangola Dev. Block in Malda District. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00280/2022-2023 |  | 31/01/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
792 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for Bamangram Piped Water Supply Scheme at Bamaongola Dev. Block in Malda district. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00463/2022-2023 | BP-2022-23-188 | 02/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
793 | Malda Division | Malda Mechanical Division | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Bamongram Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | BILL/00531/2022-2023 | BP-2022-23-210 | 16/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 12.47 | 0 | 0
794 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of BAMANGRAM Piped water supply scheme for the work of Geotechnical Study, construction of 500 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Bamongola Dev. Block under Malda Division PH Engg.Dte. In the District of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000007/2022-2023 | 1132/MD | 20/05/2022 | 365 | M/S S. DAS & ENTERPRISE | 571.92 | 394.19 | 90
795 | Malda Division | Malda Mechanical Division | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall at Head work site of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000009/2025-2026 | 2412/MD | 27/05/2025 | 150 | M/S BHARATI CONSTRUCTION | 33.45 | 0 | 0
796 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200mm. Big dia. Tube Well 125 Mtr. deep by Direct Rotary method using PVC pipe & Gravel Filter including supply of Materials at Bamangram Piped Water Supply Scheme of Bamangola Dev. Block under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000048/2022-2023 | 1397/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 9.71 | 0 | 100
797 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bamangram Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000145/2021-2022 | 1743/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 2.45 | 1
798 | Malda Division | Malda Mechanical Division | Laying of dedicated /Parallel pipe line for better functionality and providing balance FHTC of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000195/2025-2026 | 3629/MD | 24/07/2025 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 87.27 | 0 | 0
799 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with 2nd Tube Well Site of Bamangram Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000223/2023-2024 | 2673/MD | 13/07/2023 | 45 | DEB CONSTRUCTION | 4.17 | 0 | 100
800 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tube Well Site of Bamongram Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000310/2024-2025 | 3950/MD | 07/08/2024 | 45 | SWASTIK UDYOG | 8.01 | 0 | 0
801 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Excess laying of HDPE (PE-80) pipe for distribution system for the Augmentation of BAMANGRAM & its adjoining mouzas piped water supply at Bamongola Dev. Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000407/2022-2023 | 2990/MD | 07/12/2022 | 45 | BINA CONSTRUCTION | 22.62 | 22.62 | 0
802 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House of Bamangram Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000777/2024-2025 | 294/MD | 29/01/2025 | 60 | M/S EHAN ENTERPRISE | 4.36 | 0 | 0
803 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for Bamangram Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000958/2023-2024 | 706/MD | 09/02/2024 | 45 | M/S GHOSH CONSTRUCTION | 8.85 | 0 | 100
804 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000002/2022-2023 | 1104/MD | 17/05/2022 | 0 | Resource Division | 77.51 | 0 | 0
805 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | RTOR000039/2022-2023 | 1248/MD | 22/03/2023 | 0 | Resource Division | 79.81 | 0 | 0
806 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000035/2023-2024 | 1849/MD | 03/05/2023 | 820 | SOVON KUMAR DAS | 322.9 | 115.35 | 100
807 | Malda Division | RWS Malda Sub-Division | Laying of Distribution of UPVC Pipeline of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000564/2023-2024 | 2328/MD | 08/06/2023 | 60 | UTTAM KUMAR GHOSH | 64.73 | 0 | 80
808 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000620/2024-2025 | 5790/MD | 21/11/2024 | 45 | DHRITIPALI | 60.57 | 0 | 0
809 | Malda Division | RWS Malda Sub-Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Oltara, Mianagar, Kadirpur, Bhabuk, Kanthalanpur PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000954/2024-2025 | 643/MD | 19/02/2025 | 7 | DHRITIPALI | 0.88 | 0 | 0
810 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000043/2023-2024 | 1809/MD | 27/04/2023 | 0 | Resource Division | 14.46 | 0 | 0
811 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House, Blower Room, RCC Over Head Reservior and Construction Pathway & Approch Road at Head Work Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000004/2025-2026 | 2376/MD | 26/05/2025 | 75 | M/S T. K. CONSTRUCTION | 21.59 | 0 | 0
812 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000005/2025-2026 | 2288/MD | 21/05/2025 | 75 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.42 | 0 | 0
813 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply scheme ( Kutubpur JL-79, Basudevpur JL-80,Ijjatpur ,JL-81 & Minapara JL-92 ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000013/2023-2024 | 1638/MD | 12/04/2023 | 45 | SHREE BISHNU CONSTRUCTION | 56.31 | 27.91 | 90
814 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000308/2022-2023 | 2303/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9 | 8.58 | 1
815 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000344/2022-2023 | 2549/MD | 03/11/2022 | 45 | J. M. CONSTRUCTION | 6.69 | 6.52 | 90
816 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply Scheme (Dhalsana JL-48, Horkhorka JL-49, & Saiyadpur ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000363/2022-2023 | 2603/MD | 10/11/2022 | 45 | A. K. CONSTRUCTION | 46.61 | 41.9 | 80
817 | Malda Division | RWS Malda Sub-Division | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Saiyadpur Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000643/2024-2025 | 5919/MD | 26/11/2024 | 45 | SHREE BISHNU CONSTRUCTION | 88.25 | 0 | 0
818 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 132.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at SAIYADPUR Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000717/2022-2023 | 1175/MD | 20/03/2023 | 30 | A. D. D. ASSOCIATES | 9.15 | 9.13 | 100
819 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Saiyadpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000733/2022-2023 | 1207/MD | 21/03/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 4.15 | 4.14 | 100
820 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall and pathway at 3rd Tube well Site of SAIYADPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000909/2023-2024 | 287/MD | 11/01/2024 | 45 | KANAN CONSTRUCTION ENTERPRISE | 6.32 | 0 | 0
821 | Malda Division | RWS Malda Sub-Division | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for SAIYEDPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000975/2023-2024 | 884/MD | 27/02/2024 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 12.59 | 0 | 100
822 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000023/2022-2023 | 2410/MD | 17/10/2022 | 0 | Resource Division | 10.98 | 0 | 0
823 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000183/2023-2024 | 777/MD | 20/02/2024 | 0 | Resource Division | 3.08 | 0 | 0
824 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for TULSHIHATA (ZONE-I) & its adjoining mouzas Piped Water Supply at Harishchandrapur-I Block in the District Malda under Malda Division, PHE Dte. (2nd Call). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000271/2022-2023 | 2129/MD | 16/09/2022 | 472 | BANIK BROTHERS | 168.65 | 101.34 | 100
825 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Tulshihatta Zone-I Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000455/2023-2024 | 3372/MD | 29/08/2023 | 278 | M/S SABANA CONSTRUCTION | 80.46 | 0 | 100
826 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-I Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000689/2021-2022 | 654/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.42 | 3.42 | 1
827 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihata Zone-I Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000740/2024-2025 | 60 | 08/01/2025 | 311 | M/S BABLU ENTERPRISE | 30.36 | 0 | 30
828 | Malda Division | Malda Mechanical Division | Laying of additional at Tulshihatta Zone-I Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000758/2024-2025 | 76 | 13/01/2025 | 251 | M/S GHOSH CONSTRUCTION | 12.42 | 0 | 100
829 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Bbairat, Paro, Mabarakpur, Sri Chandrapur, Tulshihatta Zone-I & II, Kismat Barol PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000958/2024-2025 | 647/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 100
830 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000009/2024-2025 | 3921/MD | 06/08/2024 | 0 | Resource Division | 4.31 | 0 | 0
831 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000015/2022-2023 | 1874/MD | 16/08/2022 | 0 | Resource Division | 18.81 | 0 | 0
832 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000057/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 17.88 | 0 | 0
833 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000103/2023-2024 | 33/MD | 04/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
834 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobil in respect of hired Vehicle Car No. WB61A/3084, For the month of June and July 2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00330/2023-2024 | BP-2023-24-192 | 07/09/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0
835 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 500 M3 Capacity OHR with Soil Investigation and FHTC of CHOUPALDANGA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000044/2023-2024 | 2007/MD | 17/05/2023 | 865 | NIRMAN | 243.67 | 0 | 65
836 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Choupaldanga Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000063/2025-2026 | 1911/MD | 14/05/2025 | 60 | NEOGI ENTERPRISE | 104.36 | 0 | 0
837 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000146/2025-2026 | 2684/MD | 04/06/2025 | 150 | GIRIDHARI CONSTRUCTION | 25.91 | 0 | 0
838 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tubewell site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000147/2025-2026 | 2685/MD | 04/06/2025 | 211 | HARUN ALL RASHID & BROTHERS | 17.12 | 0 | 0
839 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of CHOUPALDANGA & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000298/2022-2023 | 2194/MD | 22/09/2022 | 45 | M/S EHAN ENTERPRISE | 6.67 | 0 | 95
840 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHOUPALDANGA Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000326/2022-2023 | 2348/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.65 | 8.71 | 100
841 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line of CHOUPALDANGA and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000335/2022-2023 | 2384/MD | 13/10/2022 | 811 | NEOGI ENTERPRISE | 275.7 | 217.53 | 100
842 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at CHOUPALDANGA Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000677/2022-2023 | 1139/MD | 20/03/2023 | 30 | DUTTA ENTERPRISE | 20.31 | 0 | 95
843 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for CHOUPALDANGA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000924/2023-2024 | 511/MD | 29/01/2024 | 383 | AHONA ENTERPRISE | 14.91 | 0 | 99
844 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000934/2023-2024 | 579/MD | 02/02/2024 | 45 | GULJAR CONSTRUCTION | 4.19 | 0 | 100
845 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000935/2023-2024 | 580/MD | 02/02/2024 | 45 | GULJAR CONSTRUCTION | 4.19 | 0 | 100
846 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000024/2022-2023 | 2755/MD | 22/11/2022 | 0 | Resource Division | 53 | 0 | 0
847 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000121/2023-2024 | 91/MD | 05/01/2024 | 0 | Resource Division | 10.44 | 0 | 0
848 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANKAIL Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000343/2022-2023 | 2800/MD | 24/11/2022 | 679 | M/S N. N. ENTERPRISE | 6.68 | 0 | 100
849 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for SANKAIL Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000365/2022-2023 | 2606/MD | 10/11/2022 | 1087 | M/S KUNDU CONSTRUCTION | 71.98 | 66.44 | 0
850 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall of Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000485/2024-2025 | 4998/MD | 27/09/2024 | 45 | BALAJI ENGINEERS CO OPERATIVE SOCIETY LT | 10.15 | 0 | 0
851 | Malda Division | RWS Malda Sub-Division | Replacement of (200 mm Dia. All through) Tubewell No:-1 (130 m deep) at Headwork Site by D.R Rig Method using P.V.C. pipe & Filter including Supply of materials at SANKAIL water supply scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000785/2024-2025 | 350/MD | 30/01/2025 | 30 | A. L. ENGINEERING SOLUTION | 9.06 | 0 | 0
852 | Malda Division | RWS Malda Sub-Division | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (130 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at SANKAIL Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000920/2023-2024 | 381/MD | 17/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 11.77 | 0 | 100
853 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000012/2025-2026 | 2420/MD | 27/05/2025 | 45 | JAHANGIR ALAM | 27.3 | 0 | 0
854 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MALIOR Water Supply Scheme at HarishchandrapurII Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000066/2023-2024 | 2021/MD | 18/05/2023 | 958 | JAHANGIR ALAM | 509.49 | 0 | 95
855 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Malior Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000319/2024-2025 | 3967/MD | 07/08/2024 | 180 | SUBHAS CHANDRA KESHARI | 30.15 | 0 | 0
856 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of MALIOR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000372/2022-2023 | 2700/MD | 17/11/2022 | 30 | SAUDAGAR (INDIA) | 9.2 | 9.2 | 100
857 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at MALIOR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000604/2022-2023 | 922/MD | 27/02/2023 | 30 | MERCURY ENGINEERING COMPANY | 10.13 | 10.01 | 100
858 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000736/2024-2025 | 55 | 08/01/2025 | 311 | ABHIJIT PAUL | 28.77 | 0 | 70
859 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000004/2024-2025 | 3924/MD | 06/08/2024 | 0 | Resource Division | 4.07 | 0 | 0
860 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000014/2023-2024 | 1618/MD | 11/04/2023 | 0 | Resource Division | 17.18 | 0 | 0
861 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000038/2022-2023 | 3050/MD | 12/12/2022 | 0 | Resource Division | 25.1 | 0 | 0
862 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000557/2022-2023 | 748/MD | 17/02/2023 | 30 | M/S AMIT KUMAR GUPTA | 46.66 | 0 | 95
863 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000565/2022-2023 | 756/MD | 17/02/2023 | 45 | SUBHAS CHANDRA KESHARI | 85.86 | 85.79 | 0
864 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000579/2024-2025 | 5596/MD | 05/11/2024 | 30 | M/S AMIT KUMAR GUPTA | 1.71 | 0 | 10
865 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dahara Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000750/2022-2023 | 1298/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.19 | 0 | 97
866 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000759/2024-2025 | 77 | 13/01/2025 | 45 | RAJIB MANI | 10.09 | 0 | 0
867 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 200mm. Big dia Tube Well 150 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000782/2022-2023 | 1440/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 11.02 | 0 | 100
868 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Gouripur Piped Water Supply scheme in Harischandrapur II Block under Malda Division PHE. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000577/2022-2023 | 768/MD | 17/02/2023 | 45 | SUDIPTA GHOSH | 29.67 | 0 | 0
869 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of DAKSHIN GOURIPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000581/2024-2025 | 5615/MD | 06/11/2024 | 30 | A. H. ENTERPRISE | 1.7 | 0 | 100
870 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dakshin Gouripur Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000747/2022-2023 | 1295/MD | 23/03/2023 | 45 | SAYEM ENTERPRISE | 4.18 | 0 | 97
871 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 140 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAKSHIN GOURIPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000778/2022-2023 | 1436/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 9.62 | 9.3 | 100
872 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000022/2025-2026 | 1740/MD | 08/05/2025 | 222 | M/S DEY ENTERPRISE | 5.78 | 0 | 0
873 | Malda Division | RWS Malda Sub-Division | Augmentation work of Boundary wall, Pump House, Blower Room RCC Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000156/2025-2026 | 2707/MD | 04/06/2025 | 75 | SAHA CONSTRUCTION | 19.71 | 0 | 0
874 | Malda Division | RWS Malda Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 25 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000608/2023-2024 | 4112/MD | 10/10/2023 | 120 | M/S AMIT KUMAR GUPTA | 14.74 | 0 | 90
875 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Moua Mabrakpur, JL No.- 123 & Mouza-Muchia, JL No. 124) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000699/2022-2023 | 1156/MD | 20/03/2023 | 45 | TARUN KUMAR DEY | 41.74 | 39.04 | 100
876 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Mouza- Jalkar Bithan, JL No. 115) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000706/2022-2023 | 1164/MD | 20/03/2023 | 45 | AVIK KUMAR GHOSH | 27.37 | 13.46 | 85
877 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000707/2022-2023 | 1165/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.79 | 7.03 | 100
878 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000708/2022-2023 | 1166/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.79 | 6.2 | 100
879 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mobarakpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000730/2022-2023 | 1204/MD | 21/03/2023 | 45 | M. S. AGENCY | 8.3 | 0 | 100
880 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall and pathway at 3rd Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000908/2023-2024 | 286/MD | 11/01/2024 | 45 | M. S. AGENCY | 7.66 | 0 | 100
881 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 4th Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000961/2023-2024 | 712/MD | 09/02/2024 | 45 | S. R. ENTERPRISE | 6.71 | 0 | 100
882 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of KANDARAN ZONE-I Piped Water Supply Scheme at Chanchal-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000041/2023-2024 | 1910/MD | 11/05/2023 | 966 | M/S SINHA CONSTRUCTION CO. | 1071.52 | 169.74 | 93
883 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Kandaran Zone-I Water Supply Scheme in Chanchol- II block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000147/2021-2022 | 1745/MD | 15/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 2.86 | 0
884 | Malda Division | Malda Mechanical Division | Sinking of Tube Well No -I & Replacement of Existing Tube Well at Site No- II each of 200mm Dia all through and 180 Mtr. Deep Big Dia Tube Well at Kandaran Zone-I Piped Water Supply Scheme at Chanchal -II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000193/2025-2026 | 3692/MD | 29/07/2025 | 216 | ASHIS CONSTRUCTION | 21.23 | 0 | 50
885 | Malda Division | Malda Mechanical Division | Restoration of pipe line by concreting of Kandaran Zone -II Water Supply Scheme under Chanchal -II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000202/2025-2026 | 3694/MD | 29/07/2025 | 155 | UTTAM KUMAR GHOSH | 41.82 | 0 | 0
886 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for KANDARON (ZONE-II) & its adjoining mouzas piped water supply at Chanchal-II Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000585/2022-2023 | 818/MD | 20/02/2023 | 681 | UTTAM KUMAR GHOSH | 175.28 | 102.83 | 95
887 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of OHR and providing Functional Household Tap Connection for Augmentation of Kandaran Zone -II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000600/2023-2024 | 4321/MD | 16/10/2023 | 533 | WELFARE ENGINEERING CO-OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 187.94 | 0 | 75
888 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kandaran Zone-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000828/2024-2025 | 701/MD | 21/02/2025 | 45 | M/S SINHA CONSTRUCTION CO. | 33.12 | 0 | 0
889 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd TW site of KANDARAN ZONE-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/001037/2023-2024 | 1520/MD | 16/03/2024 | 406 | JUPITAR LABOUR CO-OPERATIVE CONTRACT AND CONSTRUCTION SOCIETY LTD. | 31.42 | 0 | 80
890 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000061/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 157.32 | 0 | 0
891 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000126/2023-2024 | 96/MD | 05/01/2024 | 0 | Resource Division | 38.49 | 0 | 0
892 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-I Piped Water Supply Scheme at Manikchak Dev. Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000025/2023-2024 | 1752/MD | 26/04/2023 | 921 | M/S PARIMAL DAS | 154.83 | 51.36 | 85
893 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-I Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000149/2024-2025 | 2918/MD | 10/06/2024 | 30 | M/S PARIMAL DAS | 26.22 | 0 | 0
894 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-I Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000655/2024-2025 | 6402/MD | 19/12/2024 | 45 | M/S PARIMAL DAS | 12.41 | 0 | 0
895 | Malda Division | Malda Mechanical Division | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000965/2024-2025 | 654/MD | 19/02/2025 | 7 | DHRITIPALI | 0.55 | 0 | 0
896 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 30.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-I Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000991/2023-2024 | 1276/MD | 15/03/2024 | 728 | GIYASUDDIN SEKH | 133.01 | 0 | 35
897 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000095/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 82.44 | 0 | 0
898 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SUJAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000095/2023-2024 | 2168/MD | 07/06/2023 | 1025 | NEOGI ENTERPRISE | 395.25 | 0 | 50
899 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tubewell Site of Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000151/2024-2025 | 2920/MD | 10/06/2024 | 509 | NEOGI ENTERPRISE | 21.09 | 0 | 95
900 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Sujapur Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000317/2024-2025 | 3965/MD | 07/08/2024 | 180 | NEOGI ENTERPRISE | 30.19 | 0 | 0
901 | Malda Division | Malda Mechanical Division | Sinking of 200 mm (all through) Big Dia. Tube-Well of 130 M Deep at Rahutgaon (JL No-27) mouza under Sujapur PWSS of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000452/2024-2025 | 4808/MD | 13/09/2024 | 152 | NEOGI ENTERPRISE | 9.07 | 0 | 0
902 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/001022/2023-2024 | 1191/MD | 14/03/2024 | 45 | NEOGI ENTERPRISE | 26.42 | 0 | 0
903 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000173/2023-2024 | 406/MD | 18/01/2024 | 0 | Resource Division | 2.22 | 0 | 0
904 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000189/2023-2024 | 811/MD | 21/02/2024 | 0 | Resource Division | 31.08 | 0 | 0
905 | Malda Division |  | Formal work order for the work of Implementation of BABUPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000360/2023-2024 | 3033/MD | 09/08/2023 | 1023 | M/S UDYOG & CO. | 1331.07 | 0 | 65
906 | Malda Division |  | Construction of Boundary Wall at 2nd Tube well site of Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000676/2024-2025 | 6201/MD | 09/12/2024 | 45 | M/S GHOSH CONSTRUCTION | 7.15 | 0 | 0
907 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000717/2024-2025 | 6408/MD | 19/12/2024 | 423 | MANIK CHOUDHURY | 50.96 | 0 | 0
908 | Malda Division |  | Erection of Property board related to Jal Jeevan Mission works of Fatepur, Paharpur, Uttar Mahinagar, Arazi Jalsa, Babupur, Rajaramchak & Emamnagar PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000950/2024-2025 | 639/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0
909 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 6156/MD | 05/12/2024 | 0 | Resource Division | 12.16 | 0 | 0
910 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 236/MD | 10/01/2024 | 0 | Resource Division | 19.1 | 0 | 0
911 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 815/MD | 21/02/2024 | 0 | Resource Division | 49.72 | 0 | 0
912 | Malda Division | RWS Malda Sub-Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00189/2024-2025 | BP-2024-25-91 | 13/06/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.11 | 0 | 0
913 | Malda Division | RWS Malda Sub-Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00347/2024-2025 | BP-2024-25-194 | 06/08/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 6.2 | 0 | 0
914 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000037/2023-2024 | 1887/MD | 08/05/2023 | 694 | M/S PARIMAL DAS | 418.92 | 0 | 45
915 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000098/2023-2024 | 2325/MD | 08/06/2023 | 60 | M/S S. S. ENTERPRISE | 75.74 | 0 | 40
916 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000124/2025-2026 | 2482/MD | 28/05/2025 | 60 | SAYEM ENTERPRISE | 6.89 | 0 | 0
917 | Malda Division | RWS Malda Sub-Division | Sinking of Tubewell, Providing FHTC, Construction of Pump House & Boundary wall at Horgoa Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000483/2024-2025 | 5083/MD | 27/09/2024 | 60 | M/S TECHNICO & CO | 44.88 | 0 | 0
918 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000628/2024-2025 | 5835/MD | 22/11/2024 | 313 | RABIUL ISLAM | 15.25 | 0 | 0
919 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work Site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000629/2024-2025 | 5836/MD | 22/11/2024 | 281 | M/S ANKUSH ENTERPRISE | 22.71 | 0 | 90
920 | Malda Division | RWS Malda Sub-Division | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 18/9-19/0 betweenBulbulchandi (BBC) to Shingabad Station(SQB) Station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000911/2023-2024 | 384/MD | 17/01/2024 | 440 | GHOSH CONSTRUCTION | 28.86 | 0 | 100
921 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000039/2023-2024 | 1810/MD | 27/04/2023 | 0 | Resource Division | 20.8 | 0 | 0
922 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at HATINDA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000110/2025-2026 | 2410/MD | 27/05/2025 | 45 | MONDAL CONSTRUCTION | 10.65 | 0 | 0
923 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of HATINDA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000297/2022-2023 | 2193/MD | 22/09/2022 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 6.66 | 0 | 1
924 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at HATINDA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000675/2022-2023 | 1138/MD | 20/03/2023 | 671 | DUTTA ENTERPRISE | 21.12 | 0 | 100
925 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hatinda Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000863/2024-2025 | 1102/MD | 20/03/2025 | 60 | USHA ENTERPRISE | 119.77 | 0 | 0
926 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000969/2023-2024 | 828/MD | 21/02/2024 | 388 | MD. MANSUR ALI | 4.14 | 0 | 100
927 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000970/2023-2024 | 829/MD | 21/02/2024 | 45 | MD. MANSUR ALI | 4.14 | 0 | 0
928 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000005/2023-2024 | 1815/MD | 27/04/2023 | 0 | Resource Division | 29.46 | 0 | 0
929 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000029/2022-2023 | 2754/MD | 22/11/2022 | 0 | Resource Division | 25.94 | 0 | 0
930 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000115/2023-2024 | 85/MD | 05/01/2024 | 0 | Resource Division | 13.89 | 0 | 0
931 | Malda Division | RWS Malda Sub-Division | Replacement of 200 mm dia. all through Tube Well at Head Work site (75m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000080/2025-2026 | 2274/MD | 21/05/2025 | 30 | A. L. ENGINEERING SOLUTION | 6.9 | 0 | 0
932 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000134/2021-2022 | 1525/MD | 05/05/2021 | 30 | M/S DAS CONSTRUCTION | 57.24 | 71 | 1
933 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000072/2020-2021 | 2439/MD | 12/10/2020 | 45 | M/S AMIT KUMAR GUPTA | 72.29 | 57.28 | 66
934 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000124/2022-2023 | 1642/MD | 19/07/2022 | 30 | M/S AMIT KUMAR GUPTA | 16.26 | 0.04 | 1
935 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of MAHESHPUR Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000132/2020-2021 | 2442/MD | 12/10/2020 | 30 | M/S PRATIMA CONSTRUCTION | 14.91 | 0.06 | 1
936 | Malda Division | RWS Malda Sub-Division | Design , Supplying, Fabrication, Erection, & Commissioning including 3 (three) months Trial Run of 25 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Mianagar Water Supply Scheme of Habibpur Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000161/2025-2026 | 2760/MD | 09/06/2025 | 296 | UTTAM KUMAR GHOSH | 15.57 | 0 | 0
937 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000551/2020-2021 | 2439/MD | 12/10/2020 | 120 | M/S AMIT KUMAR GUPTA | 20 | 7.03 | 0
938 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of UPVC pipe line in place of damaged portion due to the construction of PMGSY road at KANDARAN ZONE-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (Part-III) | Sri Biswadip Sengupta, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000576/2021-2022 | 36/CSD | 07/01/2022 | 20 | M/S FOUR STAR CONSTRUCTION | 4.84 | 0.22 | 1
939 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of GOURIA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000296/2022-2023 | 2192/MD | 22/09/2022 | 279 | RAJIB MANI | 6.69 | 4.82 | 100
940 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 160 Mtr. deepTube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of GOURIA Water Supply Scheme at Chanchal I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000324/2022-2023 | 2346/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.96 | 8.77 | 100
941 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line of GAURIA and its adjoining mouzas Pipe Water Supply Scheme at Chanchal-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000353/2022-2023 | 2412/MD | 17/10/2022 | 473 | S DUTTA | 374.04 | 105.46 | 92
942 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000661/2024-2025 | 6196/MD | 09/12/2024 | 45 | M/S GHOSH ENTERPRISE | 7.23 | 0 | 0
943 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 600 M3 Capacity Over Head Reservoir with Soil Investigation and FHTC of GAURIA Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000665/2022-2023 | 1036/MD | 13/03/2023 | 750 | SOVAN KUMAR ROY | 293.21 | 0 | 78
944 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000672/2024-2025 | 6197/MD | 09/12/2024 | 45 | M/S DYNAMIC CONSTRUCTION | 7.23 | 0 | 0
945 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at GAURIA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000674/2022-2023 | 1137/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 21.11 | 0 | 50
946 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 2 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000891/2023-2024 | 165/MD | 08/01/2024 | 45 | SK ENTERPRISE | 4.17 | 0 | 100
947 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 3 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | ORD/000892/2023-2024 | 271/MD | 11/01/2024 | 45 | S. M. BUILDER | 4.18 | 0 | 100
948 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | RTOR000027/2022-2023 | 2757/MD | 22/11/2022 | 0 | Resource Division | 45.2 | 0 | 0
949 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Nur Alam, Junior Engineer | RTOR000114/2023-2024 | 84/MD | 05/01/2024 | 0 | Resource Division | 13.46 | 0 | 0
950 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 600 M3 Capacity OHR with soil Investigation and FHTC of WARI Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000007/2023-2024 | 1567/MD | 10/04/2023 | 270 | SAMBHU NATH SARKAR | 288.41 | 0 | 42
951 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at WARI Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000018/2023-2024 | 1675/MD | 18/04/2023 | 30 | SAUDAGAR INDIA | 20.31 | 0 | 100
952 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000169/2024-2025 | 2944/MD | 10/06/2024 | 30 | MS ENTERPRISE | 9.33 | 0 | 5
953 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000170/2024-2025 | 2945/MD | 10/06/2024 | 30 | MS ENTERPRISE | 9.33 | 0 | 90
954 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000218/2024-2025 | 3039/MD | 13/06/2024 | 567 | SAMBHU NATH SARKAR | 36.41 | 0 | 90
955 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of WARI & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000299/2022-2023 | 2195/MD | 22/09/2022 | 45 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 6.67 | 0 | 97
956 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of WARI Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000327/2022-2023 | 2349/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.65 | 8.06 | 100
957 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line of WARI and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000336/2022-2023 | 2396/MD | 14/10/2022 | 90 | GHOSH BROTHERS | 379.96 | 243.79 | 85
958 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) & Laying of additional Pipeline in connection with Jal Jeevan Mission (JJM) at Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000801/2024-2025 | 344/MD | 30/01/2025 | 426 | GOBINDA ENTERPRISE | 107.02 | 0 | 0
959 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 2 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000899/2023-2024 | 166/MD | 08/01/2024 | 45 | M/S SAI RAM ENTERPRISE | 4.19 | 0 | 98
960 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000900/2023-2024 | 273/MD | 11/01/2024 | 45 | LOKNATH ENTERPRISE | 4.19 | 0 | 97
961 | Malda Division | Malda Mechanical Division | Laying of Rising Main including Specials and Valves for WARI Piped Water Supply Scheme at Harischandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000921/2023-2024 | 382/MD | 17/01/2024 | 271 | MAHA MAYA CONSTRUCTION | 15.4 | 0 | 72
962 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000028/2022-2023 | 2753/MD | 22/11/2022 | 0 | Resource Division | 42.01 | 0 | 0
963 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000131/2023-2024 | 108/MD | 05/01/2024 | 0 | Resource Division | 13 | 0 | 0
964 | Malda Division | RWS Malda Sub-Division | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 0552 KM to 9.943 Km under Talpukur and Krishnapur PWSS under Malda Division,PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00513/2024-2025 | BP-2024-25-260 | 13/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 30.66 | 0 | 0
965 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000010/2023-2024 | 1573/MD | 10/04/2023 | 932 | M/S MAA TARA CONSTRUCTION | 570.36 | 202.62 | 80
966 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000107/2023-2024 | 2334/MD | 08/06/2023 | 60 | GOBINDA ENTERPRISE | 90.08 | 66.52 | 85
967 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well Site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000164/2024-2025 | 2939/MD | 10/06/2024 | 30 | PRITAM ENTERPRISE | 7.16 | 0 | 0
968 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Krishnapur Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000630/2024-2025 | 5837/MD | 22/11/2024 | 266 | VISCOUS ENGINEERS PVT. LTD. | 30.14 | 0 | 0
969 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000631/2024-2025 | 5838/MD | 22/11/2024 | 175 | M/S MAA TARA CONSTRUCTION | 60.55 | 0 | 0
970 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000781/2024-2025 | 347/MD | 30/01/2025 | 90 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.18 | 0 | 0
971 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000887/2023-2024 | 161/MD | 08/01/2024 | 45 | GOBINDA ENTERPRISE | 18.55 | 0 | 100
972 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000041/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 13.07 | 0 | 0
973 | Malda Division | Malda Mechanical Division | Service Connection charge at P/H No. II of Bhadar Water Supply Scheme under Gazole C.C.C. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | BILL/00748/2023-2024 | BP-2023-24-404 | 26/12/2023 | 0 | WBSEDCL | 11.36 | 0 | 0
974 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of BHADAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000049/2023-2024 | 1996/MD | 17/05/2023 | 715 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 336.77 | 225.14 | 85
975 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of BHADAR Piped Water Supply Scheme at Gaole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000105/2023-2024 | 2332/MD | 08/06/2023 | 571 | M/S KUNDU CONSTRUCTION | 87.98 | 80.55 | 90
976 | Malda Division | Malda Mechanical Division | Laying of Distribution Sysytem and Providing Functional Household Tap Connection (FHTC) of BHADAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000200/2024-2025 | 2928/MD | 10/06/2024 | 386 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 55.17 | 0 | 50
977 | Malda Division | Malda Mechanical Division | Placing of diesel driven Car on hire basis for official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/07/2023 to 30/09/2023). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000596/2023-2024 | 487/MD | 21/06/2023 | 92 | SUBHANKAR SINGH | 0.31 | 0.31 | 100
978 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Bhadar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000885/2023-2024 | 269/MD | 11/01/2024 | 182 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 22.49 | 0 | 80
979 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000040/2023-2024 | 1810/MD | 27/04/2023 | 0 | Resource Division | 20.43 | 0 | 0
980 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000098/2023-2024 | 26/MD | 04/01/2024 | 0 | Resource Division | 12.71 | 0 | 0
981 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000011/2025-2026 | 2419/MD | 27/05/2025 | 45 | SAHA CONSTRUCTION | 27.27 | 0 | 0
982 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of SRI CHANDRAPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000031/2023-2024 | 1851/MD | 02/05/2023 | 700 | M/S ALISA CONSTRUCTIION | 389.77 | 0 | 65
983 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000311/2024-2025 | 3951/MD | 07/08/2024 | 45 | M/S ALISA CONSTRUCTIION | 8.68 | 0 | 0
984 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000646/2024-2025 | 5923/MD | 26/11/2024 | 45 | M/S ALISA CONSTRUCTIION | 65.18 | 0 | 0
985 | Malda Division | Malda Mechanical Division | Road Restoration and Laying of parallel/ dedicated pipe line for better functionality of Srichandrapur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000694/2025-2026 | 5921/MD | 26/11/2025 | 60 | KAUSHIK MAJUMDAR | 10.02 | 0 | 0
986 | Malda Division | Malda Mechanical Division | Laying of Distribution of UPVC Pipeline of SRI CHANDRAPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000705/2023-2024 | 4634/MD | 23/11/2023 | 686 | M/S TRILOCHAN CONSTRUCTION CO | 80.4 | 0 | 100
987 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000036/2023-2024 | 1799/MD | 27/04/2023 | 0 | Resource Division | 42.87 | 0 | 0
988 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000122/2023-2024 | 92/MD | 05/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
989 | Malda Division | Malda Mechanical Division | Providing Balance Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000175/2025-2026 | 2891/MD | 17/06/2025 | 60 | M/S AMIT KUMAR GUPTA | 23.59 | 0 | 0
990 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000263/2024-2025 | 3211/MD | 27/06/2024 | 551 | M/S DAS CONSTRUCTION | 33.31 | 0 | 20
991 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000268/2024-2025 | 3226/MD | 28/06/2024 | 552 | M/S DAS CONSTRUCTION | 36.14 | 0 | 40
992 | Malda Division | Malda Mechanical Division | Road cutting and road restoration at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000690/2024-2025 | 6207/MD | 09/12/2024 | 388 | M/S DAS CONSTRUCTION | 5.06 | 0 | 0
993 | Malda Division | Malda Mechanical Division | Formal work order for Implementation of Uttar Mahinagar Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | ORD/000740/2022-2023 | 1252/MD | 22/03/2023 | 1249 | M/S DAS CONSTRUCTION | 239.41 | 0 | 70
994 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000045/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 21.65 | 0 | 0
995 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07 | RTOR000164/2023-2024 | 241/MD | 10/01/2024 | 0 | Resource Division | 4.53 | 0 | 0
996 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 90m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Oltara Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000204/2024-2025 | 2991/MD | 11/06/2024 | 180 | M/S JHA CONSTRUCTION | 32.88 | 0 | 0
997 | Malda Division | RWS Malda Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000714/2024-2025 | 6405/MD | 19/12/2024 | 45 | M/S JHA CONSTRUCTION | 65.17 | 0 | 0
998 | Malda Division | RWS Malda Sub-Division | Formal work order for Implementation of OLTARA Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000742/2022-2023 | 1253/MD | 22/03/2023 | 943 | DUTTA ENTERPRISE | 919.78 | 340.7 | 85
999 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000082/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.37 | 0 | 0
1000 | Malda Division | Malda Mechanical Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 25 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Bhabuk Water Supply Scheme of Habibpur Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000142/2025-2026 | 2620/MD | 02/06/2025 | 135 | M/S AMIT KUMAR GUPTA | 15.55 | 0 | 0
1001 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (135 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BHABUK Piped Water Supply Scheme (Tube Well No-3) of Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000379/2022-2023 | 2705/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 9.14 | 6.4 | 100
1002 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BHABUK Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000410/2022-2023 | 2984/MD | 07/12/2022 | 45 | SOVON KUMAR DAS | 43.65 | 40.92 | 1
1003 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Bhabuk Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000487/2024-2025 | 5000/MD | 27/09/2024 | 385 | M/S KUNDU CONSTRUCTION | 18.34 | 0 | 0
1004 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000518/2022-2023 | 2474/MD | 21/10/2022 | 365 | SHABNAM ARA | 4.5 | 0 | 21
1005 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bhabuk Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000727/2022-2023 | 1201/MD | 21/03/2023 | 45 | M.S. ENTERPRISE | 4.17 | 0 | 100
1006 | Malda Division | Malda Mechanical Division | Augmentation of work to ensure proper functioning of 250 M³ Capacity 20 Mtr. Staging height RCC Over Head Reservoir of Bhabuk Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000835/2024-2025 | 1061/MD | 19/03/2025 | 60 | SADHANA CONSTRUCTION | 9.21 | 0 | 0
1007 | Malda Division | Malda Mechanical Division | Emergent Laying of different diameter UPVC Pipeline and others allied work for Gap negotiatiomn for BHABUK its adjoining mouzas Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000966/2023-2024 | 805/MD | 21/02/2024 | 663 | GOBINDA ENTERPRISE | 12.33 | 0 | 0
1008 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Uttar Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000273/2024-2025 | 3202/MD | 27/06/2024 | 30 | M/S SABANA CONSTRUCTION | 10.34 | 0 | 100
1009 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000488/2022-2023 | 196/MD | 19/01/2023 | 591 | M/S SABANA CONSTRUCTION | 39.58 | 28.08 | 90
1010 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000018/2023-2024 | 1615/MD | 11/04/2023 | 0 | Resource Division | 1.32 | 0 | 0
1011 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Sadlichalk Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000196/2024-2025 | 2900/MD | 07/06/2024 | 30 | SAYEM ENTERPRISE | 2.12 | 0 | 0
1012 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000574/2022-2023 | 765/MD | 17/02/2023 | 30 | RABIUL ISLAM | 6.89 | 6.87 | 0
1013 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of SADLICHAK Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000720/2022-2023 | 1178/MD | 20/03/2023 | 686 | JAYA ENTERPRISE | 12.03 | 0 | 95
1014 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000754/2022-2023 | 1302/MD | 23/03/2023 | 45 | SOFIKUL ISLAM | 4.19 | 0 | 0
1015 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Sadlichak Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000807/2024-2025 | 999/MD | 12/03/2025 | 75 | SUBHAS CHANDRA KESHARI | 28.01 | 0 | 0
1016 | Malda Division | Malda Sadar Sub-Division | Augmentation work of Boundary wall, Pump House, Blower Room,Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of ANANDIPUR Water Supply Scheme of Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000111/2025-2026 | 2414/MD | 27/05/2025 | 75 | M/S GHOSH CONSTRUCTION | 20.21 | 0 | 0
1017 | Malda Division | Malda Sadar Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000166/2020-2021 | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 8.75 | 1
1018 | Malda Division | Malda Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Anandipur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000825/2024-2025 | 702/MD | 21/02/2025 | 320 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.05 | 0 | 0
1019 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Rampur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000179/2025-2026 | 2894/MD | 17/06/2025 | 60 | S. N. CONSTRUCTION | 29.67 | 0 | 0
1020 | Malda Division | Chanchal Sub-Division | Replacement of existing tube well by 200x200 mm dia. and 250 M Deep by Big Dia Tube Well at 2nd Tube Well site of Rampur Piped Water Supply Scheme at Chanchal-II block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000463/2024-2025 | 4820/MD | 13/09/2024 | 92 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 13.75 | 0 | 100
1021 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme, Chanchal II Block under Malda Division, P.H.E. Dte. in the District of Malda | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000573/2022-2023 | 764/MD | 17/02/2023 | 30 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 18.18 | 18.15 | 100
1022 | Malda Division | Chanchal Sub-Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000585/2024-2025 | 5619/MD | 06/11/2024 | 30 | M/S JHA CONSTRUCTION | 2.88 | 0 | 0
1023 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000753/2022-2023 | 1301/MD | 23/03/2023 | 45 | SUBINDU PRAMANIK | 4.19 | 0 | 0
1024 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Rampur Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000769/2022-2023 | 1397/MD | 28/03/2023 | 30 | A. L. ENGINEERING SOLUTION | 13.37 | 12.62 | 100
1025 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bihari Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000089/2025-2026 | 2422/MD | 27/05/2025 | 60 | PRADIP KUMAR BANIK | 15.71 | 0 | 0
1026 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Bihari Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000090/2025-2026 | 2332/MD | 22/05/2025 | 60 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 29.11 | 0 | 0
1027 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of Distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Rampur village of Bihari Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000558/2022-2023 | 749/MD | 17/02/2023 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.67 | 5.35 | 100
1028 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bihari Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000721/2022-2023 | 1195/MD | 21/03/2023 | 45 | M/S MAJAF CONSTRUCTION | 4.17 | 0 | 0
1029 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of BIHARI Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000776/2022-2023 | 1434/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 0 | 0
1030 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at head work site of Jotgopal Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000201/2024-2025 | 2988/MD | 11/06/2024 | 30 | SHREE BISHNU CONSTRUCTION | 24.3 | 0 | 0
1031 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of JOTGOPAL Piped Water Supply Scheme at Englishbazar Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000235/2023-2024 | 2710/MD | 14/07/2023 | 270 | SHREE BISHNU CONSTRUCTION | 192.85 | 0 | 32
1032 | Malda Division | RWS Malda Sub-Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 95m Deep at Jotegopal PWSS under Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000255/2024-2025 | 3199/MD | 27/06/2024 | 45 | ABHIJIT PAUL | 8.36 | 0 | 100
1033 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JOTGOPAL Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000484/2022-2023 | 1132/MD | 20/03/2023 | 45 | S. R. ENTERPRISE | 4.14 | 0 | 100
1034 | Malda Division | RWS Malda Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 01/01/2025 to 30/06/2025). | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000874/2024-2025 | 6637/MD | 31/12/2024 | 181 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0
1035 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000030/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 9.73 | 0 | 0
1036 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000053/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.86 | 0 | 0
1037 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000187/2023-2024 | 822/MD | 21/02/2024 | 0 | Resource Division | 7.67 | 0 | 0
1038 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of Tubewell, Laying of Distribution System and Providing Functional Household Tap connection (FHTC) of Mahishbathani Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000052/2023-2024 | 2005/MD | 17/05/2023 | 565 | M/S DAS CONSTRUCTION | 92.6 | 0 | 50
1039 | Malda Division | Malda Mechanical Division | Road restoration in connection with dismantling of road and renovation the same with balanced allied work to provide FHTC at Maheshbathani Piped Water Supply Scheme under Old Malda Dev Block under Malda Division, P.H.E Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000119/2025-2026 | 2471/MD | 28/05/2025 | 45 | M/S DAS CONSTRUCTION | 11.92 | 0 | 100
1040 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000314/2023-2024 | 503/MSD | 30/06/2023 | 180 | ARUN KUMAR DAS | 0.86 | 0 | 100
1041 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Head Work Site of Mahishbathani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | ORD/000952/2023-2024 | 653/MD | 08/02/2024 | 45 | M/S DAS CONSTRUCTION | 4.15 | 0 | 100
1042 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-07 | RTOR000079/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.94 | 0 | 0
1043 | Malda Division | Chanchal Sub-Division | Surveying, Planning, Design, Engineering, Supplying, Construction, Erection, Testing and Commissioning of Raw water Intake and Raw Water Pumping Main, WTP , Primary and Secondary Clear Water Transmission main, Boosting stations and other allied works including all Civil , Electro-Mechanical and IOT based Supervisory monitoring system for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District followed by 3(Three) months Trial Run and Subsequent Operation & Maintenance for 5(five) years | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00442/2024-2025 | BP-2024-25-223 | 28/08/2024 | 0 | EXECUTIVE ENGINEER | 1.35 | 0 | 0
1044 | Malda Division | Chanchal Sub-Division | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00527/2024-2025 | BP-2024-25-253 | 11/09/2024 | 0 | EXECUTIVE ENGINEER | 1.29 | 0 | 0
1045 | Malda Division | Chanchal Sub-Division | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | BILL/00745/2024-2025 | BP-2024-25-386 | 19/11/2024 | 0 | EXECUTIVE ENGINEER | 1.29 | 0 | 0
1046 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Construction of Overhead Reservoir on pile or raft foundation based on soil test report, laying of Distribution system, FHTC including pump house, boundary wall, internal road with RCC Culvert, internal pipe connection of Surface Water Based Piped Water Supply Scheme for Chanchal-II, Ratua-I & Ratua-II Block in the district of Malda Under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000380/2023-2024 | 3155/MD | 16/08/2023 | 960 | REAN WATER TECH PRIVATE LIMITED. | 10818.5 | 0 | 5
1047 | Malda Division | Chanchal Sub-Division | Construction of Flexible Bitumen Roads from Nakkatti Bridge to Y Junction of Irrigation Embankment by Bituminous work under Malda Division PHE Dte, in the District of Malda during the year 2024 - 2025. | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | ORD/000671/2024-2025 | 6161/MD | 05/12/2024 | 220 | M/S ANKUSH ENTERPRISE | 64.08 | 0 | 65
1048 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | RTOR000001/2024-2025 | 3836/MD | 30/07/2024 | 0 | Resource Division | 7172.16 | 0 | 0
1049 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | RTOR000024/2024-2025 | 5971/MD | 28/11/2024 | 0 | Resource Division | 345.26 | 0 | 0
1050 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Subhajit Kumar Paul, Junior Engineer,Mr. Susanta Pal, JE_Deputation | RTOR000040/2022-2023 | 1811/MD | 27/04/2023 | 0 | Resource Division | 12067.76 | 0 | 0
1051 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arbara Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000092/2025-2026 | 2334/MD | 22/05/2025 | 60 | S & G CONSTRUCTION | 28.65 | 0 | 0
1052 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Chandipur, JL. No. 40, G.P.-Bhagabanpur of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000105/2020-2021 | 2301/MD | 30/09/2020 | 31 | BIDYUT MAHALDAR | 4.45 | 7.63 | 0
1053 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Mahupaul, JL. No. 100, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000110/2020-2021 | 2306/MD | 30/09/2020 | 31 | RABIUL ISLAM | 2.82 | 3.43 | 0
1054 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Sadhail, JL. No. 116, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000116/2020-2021 | 2312/MD | 30/09/2020 | 31 | DEVI ENTERPRISE | 2.07 | 2.07 | 1
1055 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Dubol, JL. No. 93, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000118/2020-2021 | 2314/MD | 30/09/2020 | 31 | PRITAM ENTERPRISE | 3.31 | 3.02 | 0
1056 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Basantapur, JL. No. 82, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000119/2020-2021 | 2315/MD | 30/09/2020 | 31 | M/S RADHA KRISHNA ENTERPRISE | 2.64 | 2.52 | 0
1057 | Malda Division | Chanchal Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 50 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Malipakar Water Supply Scheme of Harishchandrapur-II Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000135/2025-2026 | 2510/MD | 29/05/2025 | 135 | BANIK BROTHERS | 20.04 | 0 | 0
1058 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Barijpur, JL. No. 43, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000138/2020-2021 | 2448/MD | 12/10/2020 | 30 | PARIJAT RAY | 41.39 | 56.13 | 0
1059 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sankail, JL. No. 166, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000142/2020-2021 | 2452/MD | 12/10/2020 | 30 | M/S BABLU ENTERPRISE | 20.5 | 30.73 | 0
1060 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daksin Sahar, JL. No. 133, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000146/2020-2021 | 2456/MD | 12/10/2020 | 30 | M/S BANERJEE CONSTRUCTION | 19.18 | 13.41 | 0
1061 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sanjib, JL. No. 136, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000147/2020-2021 | 2457/MD | 12/10/2020 | 30 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.51 | 15.08 | 0
1062 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Birasthali, JL. No. 137, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000148/2020-2021 | 2458/MD | 12/10/2020 | 30 | M/S. TEWARI CONSTRUCTION | 28.57 | 0 | 66
1063 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Arbara, JL. No. 57, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000149/2020-2021 | 2459/MD | 12/10/2020 | 30 | TARUN KUMAR DEY | 31.69 | 23.11 | 0
1064 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bagunja, JL. No. 38, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000150/2020-2021 | 2460/MD | 12/10/2020 | 30 | M/S N. N. ENTERPRISE | 5.71 | 9.49 | 0
1065 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Haripur, JL. No. 20, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000151/2020-2021 | 2461/MD | 12/10/2020 | 30 | M/S STAR INDIA CONSTRUTION | 17.3 | 22.14 | 0
1066 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khadiarpur, JL. No. 21, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000152/2020-2021 | 2462/MD | 12/10/2020 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.85 | 23.43 | 0
1067 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khosalpur, JL. No. 56, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000153/2020-2021 | 2463/MD | 12/10/2020 | 30 | IDEAL CONSTRUCTION | 9.01 | 11.83 | 0
1068 | Malda Division | Chanchal Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & FHTC for BASARA piped Water Supply Scheme at Bamongola Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000205/2025-2026 | 3693/MD | 29/07/2025 | 156 | MANIK CHOUDHURY | 60.11 | 0 | 0
1069 | Malda Division | Chanchal Sub-Division | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & providing FHTC for PURBA BINODPUR piped Water Supply Scheme at Gazole Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000206/2025-2026 | 3722/MD | 30/07/2025 | 60 | ABHIJIT CONSTRUCTION | 17.47 | 0 | 0
1070 | Malda Division | Chanchal Sub-Division | Sinking of 200mm (all through) Big Dia Tube Well of 180m Deep at 3rd Tube Well Site and Construction of Pump House at 3rd Tube Well site Laying of dedicated/Parallel pipe line and Providing balanced FHTC under GANNADIA Piped Water Supply Scheme under at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000208/2025-2026 | 3723/MD | 30/07/2025 | 245 | HARUN ALL RASHID & BROTHERS | 39.34 | 0 | 0
1071 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gangnadia, JL. No. 114, G.P.-Mahendrapur of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000291/2020-2021 | 265/MD | 28/01/2021 | 30 | MANIK CHOUDHURY | 38.45 | 45.42 | 1
1072 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bansdol, JL. No. 94, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000292/2020-2021 | 266/MD | 28/01/2021 | 30 | M/S. TEWARI CONSTRUCTION | 21.96 | 21.41 | 1
1073 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bampal Charkhi, JL. No. 51, G.P.- Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000293/2020-2021 | 267/MD | 28/01/2021 | 30 | MANIK CHOUDHURY | 35.11 | 16.94 | 0
1074 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Adampur, JL. No. 121, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000294/2020-2021 | 268/MD | 28/01/2021 | 30 | BEE GEE CONSTRUCTION | 29.13 | 53.15 | 1
1075 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Memua, JL. No. 122, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000295/2020-2021 | 269/MD | 28/01/2021 | 30 | GOBINDA ENTERPRISE | 23.19 | 45.81 | 1
1076 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Raykhandighi, JL. No. 23, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000296/2020-2021 | 270/MD | 28/01/2021 | 1381 | M/S KUNDU CONSTRUCTION | 25.44 | 0 | 100
1077 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Gaushpur, JL. No. 90, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000297/2020-2021 | 271/MD | 28/01/2021 | 30 | GOBINDA ENTERPRISE | 14.36 | 25.01 | 1
1078 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Latasi, JL. No. 89, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000298/2020-2021 | 272/MD | 28/01/2021 | 30 | M/S SABANA CONSTRUCTION | 35.86 | 34.96 | 1
1079 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Basudebpur, JL. No. 150, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000299/2020-2021 | 273/MD | 28/01/2021 | 30 | MD WARESH ALI | 14.72 | 14.66 | 1
1080 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Surjyapura Tengurpura, JL. No. 151, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000300/2020-2021 | 274/MD | 28/01/2021 | 30 | A. K. CONSTRUCTION | 29.56 | 19.74 | 100
1081 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sahabajpur, JL. No. 55, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000301/2020-2021 | 281/MD | 28/01/2021 | 30 | M/S. TEWARI CONSTRUCTION | 20.81 | 31.12 | 1
1082 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Naikanda, JL. No. 39, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000302/2020-2021 | 282/MD | 28/01/2021 | 30 | FAIZUL HAQUE BISWAS | 16.18 | 14.76 | 1
1083 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bibijhuti, JL. No. 58, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000303/2020-2021 | 283/MD | 28/01/2021 | 30 | ANUKUL CHANDRA DAS | 9.41 | 15.9 | 1
1084 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARBARA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000303/2022-2023 | 2196/MD | 22/09/2022 | 30 | S & G CONSTRUCTION | 7.96 | 7.2 | 1
1085 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Rasulpur, JL. No. 71, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000304/2020-2021 | 284/MD | 28/01/2021 | 30 | A. K. SIKDAR | 8.24 | 7.88 | 1
1086 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000305/2020-2021 | 285/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.56 | 0.58 | 1
1087 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Rampur, JL. No. 74, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000306/2020-2021 | 286/MD | 28/01/2021 | 30 | S. N. CONSTRUCTION | 16.86 | 15.79 | 1
1088 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Elam, JL. No. 75, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000307/2020-2021 | 287/MD | 28/01/2021 | 30 | ACHARYYA CONSTRUCTION | 12.36 | 0 | 1
1089 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Isadpur, JL. No. 77, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000308/2020-2021 | 288/MD | 28/01/2021 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.42 | 24.36 | 1
1090 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Kanua Bhabanipur, JL. No. 78, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000309/2020-2021 | 289/MD | 28/01/2021 | 30 | JOYDEB SENGUPTA | 6.64 | 0 | 0
1091 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Lakshmanpur, JL. No. 74, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000310/2020-2021 | 290/MD | 28/01/2021 | 30 | M/S SABANA CONSTRUCTION | 27.25 | 25.76 | 1
1092 | Malda Division | Chanchal Sub-Division | Continuation of work order for hiring of inspection vehicle (motor cab or Maruti omni category non air condition Bharat stage III purchase on or after 1.05.2008 with deiseal/LPG/CNG Engine ) in perfectly good condition of performing along journey and should cover anywhere without any trouble on monthly heir basis for official use of the office of the Assistant Engineer ,RWS Malda sub division ,PHE Dte.( Period from 06/07/2023 to 31/12/2023 ) | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000310/2023-2024 | 199/RWS | 06/06/2023 | 178 | SHYAMAL KUMAR MAITRA | 0.85 | 0.96 | 55
1093 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Alampur, JL. No. 107, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000311/2020-2021 | 291/MD | 28/01/2021 | 30 | RANJIT ADHIKARY | 5.68 | 4.84 | 1
1094 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Barinda, JL. No. 95, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000312/2020-2021 | 292/MD | 28/01/2021 | 30 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.85 | 9.98 | 1
1095 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Harinandanbati, JL. No. 109, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000313/2020-2021 | 293/MD | 28/01/2021 | 30 | S. R. CONSTRUCTION | 15.52 | 13.97 | 1
1096 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bujurkhali, JL. No. 110, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000314/2020-2021 | 294/MD | 28/01/2021 | 1799 | GOBINDA ENTERPRISE | 14.53 | 0 | 0
1097 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Jalakar Bithan, JL. No. 115, G.P.- Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000315/2020-2021 | 295/MD | 28/01/2021 | 30 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 7.78 | 0 | 100
1098 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Teliapara, JL. No. 74, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000316/2020-2021 | 296/MD | 28/01/2021 | 30 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.53 | 0 | 0
1099 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Ashrafpur, JL. No. 132, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000317/2020-2021 | 297/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.91 | 0 | 0
1100 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chhatia, JL. No. 133, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000318/2020-2021 | 298/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 17.51 | 0 | 0
1101 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gopalnagar, JL. No. 80, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000319/2020-2021 | 299/MD | 28/01/2021 | 30 | S. N. CONSTRUCTION | 18.77 | 18.77 | 1
1102 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jagdala, JL. No. 77, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000320/2020-2021 | 300/MD | 28/01/2021 | 30 | PABITRA MONDAL | 9.57 | 17.56 | 1
1103 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Parameswarpur, JL. No. 81, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000321/2020-2021 | 301/MD | 28/01/2021 | 30 | A. K. SIKDAR | 7.04 | 5.7 | 1
1104 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhabanipur, JL. No. 75, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000322/2020-2021 | 302/MD | 28/01/2021 | 489 | MARSS INTERNATIONAL | 7.25 | 0 | 100
1105 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhadreshwar, JL. No. 78, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000323/2020-2021 | 303/MD | 28/01/2021 | 30 | ACHARYYA CONSTRUCTION | 13.25 | 10.79 | 1
1106 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dihatti, JL. No. 79, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000324/2020-2021 | 304/MD | 28/01/2021 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.93 | 2.9 | 0
1107 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Harischandrapur, JL. No. 83, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000325/2020-2021 | 305/MD | 28/01/2021 | 30 | KRISHNENDU DUTTA | 25.76 | 24.94 | 1
1108 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabanipur, JL. No. 85, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000326/2020-2021 | 306/MD | 28/01/2021 | 30 | RANJIT ADHIKARY | 8.8 | 0 | 0
1109 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabuk, JL. No. 89, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000327/2020-2021 | 307/MD | 28/01/2021 | 30 | S. R. CONSTRUCTION | 14.93 | 28.86 | 1
1110 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhairabpur, JL. No. 86, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000328/2020-2021 | 308/MD | 28/01/2021 | 30 | CHARU CONSTRUCTION | 5.85 | 0 | 0
1111 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jot Haricharan, JL. No. 43, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000330/2020-2021 | 310/MD | 28/01/2021 | 30 | JOY ENTERPRISE | 6.77 | 5.81 | 1
1112 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dharmma Danga, JL. No. 44, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000331/2020-2021 | 311/MD | 28/01/2021 | 30 | MANAS KUMAR SAHA | 18.67 | 16.39 | 1
1113 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kasba, JL. No. 45, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000332/2020-2021 | 312/MD | 28/01/2021 | 30 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 15.48 | 9.46 | 1
1114 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000338/2020-2021 | 447/MD | 08/02/2021 | 30 | MANIK CHOUDHURY | 37.13 | 4.9 | 0
1115 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kendua, JL. No. 54, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000339/2020-2021 | 448/MD | 08/02/2021 | 30 | FAIZUL HAQUE BISWAS | 25.78 | 24.34 | 1
1116 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gorakhpur, JL. No. 76, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000340/2020-2021 | 449/MD | 08/02/2021 | 30 | TARUN KUMAR DEY | 27.04 | 23.08 | 1
1117 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Konar, JL. No. 73, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000341/2020-2021 | 450/MD | 08/02/2021 | 30 | M/S. TEWARI CONSTRUCTION | 25.97 | 20.69 | 0
1118 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Agra, JL. No. 84, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000342/2020-2021 | 451/MD | 08/02/2021 | 30 | M/S. TEWARI CONSTRUCTION | 25.53 | 15.46 | 1
1119 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Khatil, JL. No. 42, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000343/2020-2021 | 452/MD | 08/02/2021 | 30 | GOBINDA ENTERPRISE | 22.15 | 35.24 | 1
1120 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Muchia, JL. No. 124, G.P.-Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000344/2020-2021 | 509/MD | 09/02/2021 | 30 | M/S KUNDU CONSTRUCTION | 46.63 | 93.25 | 1
1121 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying of additional pipe line and Providing FHTC connection at Uttar Rasulpur village of Rampur water supply scheme, Chanchal-II Dev. Block , Chanchal Sub-Division of PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000351/2022-2023 | 2546/MD | 03/11/2022 | 30 | ANUKUL CHANDRA DAS | 6.35 | 6.19 | 100
1122 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Restoration pipe line for Providing FHTC in connection with JJM at Birasthal along NH-81 under command area of Dakshin Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000352/2022-2023 | 2547/MD | 03/11/2022 | 30 | M/S. TEWARI CONSTRUCTION | 1.15 | 0 | 0
1123 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kankot, JL. No. 50, G.P.-Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000353/2020-2021 | 557/MD | 12/02/2021 | 30 | RAY CONSTRUCTION CO. | 57.6 | 29.11 | 1
1124 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bahirgachhi, JL. No. 24, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000354/2020-2021 | 556/MD | 12/02/2021 | 45 | UTTAM KUMAR GHOSH | 71.29 | 12.54 | 0
1125 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Arazi Deharul, JL. No. 21, G.P.-Bahirgachhi-II of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000355/2020-2021 | 555/MD | 12/02/2021 | 30 | BEE GEE CONSTRUCTION | 52.81 | 47.96 | 1
1126 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection under MOBARAKPUR Piped Water Supply Scheme at Old Malda Block in the district of Malda under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000358/2020-2021 | 591/MD | 18/02/2021 | 60 | NIRENDRA NATH KUNDU | 125 | 30.6 | 0
1127 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daulatpur, JL. No. 92, G.P.-Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000360/2020-2021 | 569/MD | 15/02/2021 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 84.94 | 83.13 | 1
1128 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Malipakar, JL. No. 91, G.P.-Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000361/2020-2021 | 568/MD | 15/02/2021 | 45 | NEOGI ENTERPRISE | 78.3 | 66.23 | 46
1129 | Malda Division | Chanchal Sub-Division | Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Uttar Arbara under command area of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000364/2023-2024 | 3053/MD | 09/08/2023 | 30 | SOFIKUL ISLAM | 3.09 | 3.08 | 100
1130 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of SSP with other allied work to proper functioning of FHTC work within the command area of NEMUA Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000401/2022-2023 | 2961/MD | 07/12/2022 | 30 | SUDEB KARMAKAR | 2.09 | 0 | 0
1131 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Kumedpur, JL. No. 142, G.P.-Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000431/2021-2022 | 3004/MD | 07/10/2021 | 30 | FUTURE | 49.95 | 45.14 | 1
1132 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mabrakpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000448/2023-2024 | 3365/MD | 29/08/2023 | 45 | GOBINDA ENTERPRISE | 36.28 | 0 | 100
1133 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Nemua Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000450/2023-2024 | 3367/MD | 29/08/2023 | 45 | MOMTAJ ALI | 40.32 | 0 | 74
1134 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Purba Binodpur Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000451/2023-2024 | 3368/MD | 29/08/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.11 | 0 | 100
1135 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) At -Bibijhuti (JL. No. 58), Naikanda (JL. No. 39) & Chandipur (JL. No. 40) G.P.-Kharba In connection of Source Augmentation of Kendua PWSS at Chanchal-I Block under Malda Division. PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000468/2023-2024 | 3458/MD | 07/09/2023 | 328 | M/S /FAIZUL HAQUE BISWAS | 33.7 | 0 | 100
1136 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dakhin Sahar Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000499/2024-2025 | 5403/MD | 21/10/2024 | 340 | GOBINDA ENTERPRISE | 65.18 | 0 | 0
1137 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Lalpur Bodra, JL. No. 31, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000550/2020-2021 | 3102/MD | 15/12/2020 | 30 | M/S SINHA ENTERPRISE | 0 | 5.61 | 1
1138 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Collection of household tap connection details through baseline household mobile's App (Jal Swapna) under commend area of Rajarampur, Mekpur, Purba Binodpur, Mianagar & Basora Piped Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000551/2021-2022 | 515/MSD | 31/12/2021 | 1 | DHRITIPALI | 0.96 | 0.96 | 1
1139 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Rampur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000571/2024-2025 | 5484/MD | 24/10/2024 | 45 | M/S JHA CONSTRUCTION | 57.8 | 0 | 0
1140 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Kankot Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000605/2023-2024 | 3811/MD | 29/09/2023 | 30 | PRITAM ENTERPRISE | 7.66 | 0 | 100
1141 | Malda Division | Chanchal Sub-Division | Acceptance cum formal work order for Laying and extension of uPVC Pipe Line of different diameter at Dihotti & Bhadreswar Mouza of PARAMESHWARPUR Water Supply Scheme at BAMONGOLA Block under Malda Division P.H.E. Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000659/2021-2022 | 3413/MD | 02/12/2021 | 1 | ACHARYYA CONSTRUCTION | 1.25 | 2.09 | 1
1142 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000663/2024-2025 | 6163/MD | 05/12/2024 | 300 | M/S N. N. ENTERPRISE | 38.42 | 0 | 0
1143 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kankot Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000664/2024-2025 | 6164/MD | 05/12/2024 | 45 | MD WARESH ALI | 30.59 | 0 | 0
1144 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BAHIRGACHHI Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000717/2023-2024 | 4766/MD | 05/12/2023 | 229 | IDEAL CONSTRUCTION | 12.1 | 0 | 80
1145 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000722/2023-2024 | 4771/MD | 05/12/2023 | 45 | MD WARESH ALI | 19.7 | 0 | 80
1146 | Malda Division | Chanchal Sub-Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Raikhadighi Mouza under BAHIRGACHHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000727/2024-2025 | 6418/MD | 19/12/2024 | 45 | ANUKUL CHANDRA DAS | 18.48 | 0 | 0
1147 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000743/2024-2025 | 6585/MD | 31/12/2024 | 289 | M/S BABLU ENTERPRISE | 44.5 | 0 | 50
1148 | Malda Division | Chanchal Sub-Division | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000787/2024-2025 | 352/MD | 30/01/2025 | 180 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 89.7 | 0 | 34
1149 | Malda Division | Chanchal Sub-Division | Augmentation work of OHR, Pump House and Boundary Wall of Arbara Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000858/2024-2025 | 1051/MD | 18/03/2025 | 75 | M/S ANKUSH ENTERPRISE | 32.37 | 0 | 0
1150 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/08/2023 to 31/01/2024). | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000987/2023-2024 | 2023/NBC-II | 30/08/2023 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 0 | 76
1151 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at RAIKHADIGHI Mouza under BAHIRGACHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000997/2023-2024 | 1176/MD | 14/03/2024 | 293 | ABHIJIT ENTERPRISE | 13.25 | 0 | 100
1152 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001004/2023-2024 | 1512/MD | 16/03/2024 | 168 | MANIK CHOUDHURY | 21.17 | 0 | 100
1153 | Malda Division | Chanchal Sub-Division | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 23/12/2023 to 19/06/2024=180 Days). Vehicle no. WB 65A/4911. | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | ORD/001161/2023-2024 | 5151/MD | 21/12/2023 | 180 | USHA ENTERPRISE | 0.86 | 0 | 0
1154 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000014/2024-2025 | 3993/MD | 08/08/2024 | 0 | Resource Division | 6.16 | 0 | 0
1155 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000101/2023-2024 | 31/MD | 04/01/2024 | 0 | Resource Division | 5.85 | 0 | 0
1156 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000104/2023-2024 | 34/MD | 04/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
1157 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000112/2023-2024 | 55/MD | 04/01/2024 | 0 | Resource Division | 0.62 | 0 | 0
1158 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer | Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000137/2023-2024 | 112/MD | 05/01/2024 | 0 | Resource Division | 1.23 | 0 | 0
1159 | Malda Division | RWS Malda Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000163/2020-2021 | 2716/MD | 10/11/2020 | 45 | M/S AMIT KUMAR GUPTA | 73.35 | 47.09 | 40
1160 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Akalpur Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000598/2024-2025 | 5936/MD | 27/11/2024 | 90 | S. N. CONSTRUCTION | 42.82 | 0 | 0
1161 | Malda Division | Chanchal Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | Sri Susanta Saha, Assistant Engineer |  | ORD/000164/2020-2021 | 2717/MD | 10/11/2020 | 45 | UNIVERSAL ENTERPRIESES | 70.14 | 124.54 | 1
1162 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Sri Susanta Saha, Assistant Engineer |  | RTOR000002/2024-2025 | 3915/MD | 06/08/2024 | 0 | Resource Division | 1.42 | 0 | 0
1163 | Malda Division | Malda Mechanical Division | Formal work order for Augmentation of TILASAN Piped water supply scheme for the work of Geotechnical Study,construction of 200 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block under Malda Division PH Engg.Dte. In the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000004/2022-2023 | 996/MD | 22/04/2022 | 365 | UTTAM KUMAR GHOSH | 180.23 | 137.44 | 100
1164 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Rising Main including connection of Pump No-1 & Pump No 2 and by pass arrangement for TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000030/2022-2023 | 1307/MD | 01/06/2022 | 30 | M/S EHAN ENTERPRISE | 4.44 | 4.43 | 1
1165 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Dismantling of concrete road and Construction the same at different places of road connecting to LDS of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000081/2023-2024 | 2177/MD | 07/06/2023 | 30 | UTTAM KUMAR GHOSH | 21.68 | 21.68 | 100
1166 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional House hold Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under Command area of Augmentation of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000082/2023-2024 | 2178//MD | 07/06/2023 | 30 | UTTAM KUMAR GHOSH | 13.35 | 12.19 | 100
1167 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of TILASAN Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000539/2021-2022 | 2693/MD | 09/09/2021 | 7 | RADIANT | 1.25 | 1.25 | 1
1168 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Dismentling of Concrete road and Construction the same from Head Work site to 2nd Tube Well Site of TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, P.H.E. Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | ORD/000785/2022-2023 | 1443/MD | 29/03/2023 | 30 | M/S EHAN ENTERPRISE | 3.15 | 3.15 | 100
1169 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | RTOR000005/2022-2023 | 1107/MD | 17/05/2022 | 0 | Resource Division | 16.55 | 0 | 0
1170 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | RTOR000010/2022-2023 | 1461/MD | 22/06/2022 | 0 | Resource Division | 6.78 | 0 | 0
1171 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Shreya Das, Junior Engineer | RTOR000043/2022-2023 | 1587/MD | 28/03/2023 | 0 | Resource Division | 0.41 | 0 | 0
1172 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65A/4911 for the month of May & June 2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00370/2023-2024 |  | 04/09/2023 | 0 | USHA ENTERPRISE | 0.41 | 0 | 0
1173 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for UTTAR HARISHCHANDRAPUR ZONE-I Piped Water Supply Scheme at Harishchandapur-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00487/2022-2023 | BP-2022-23-196 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
1174 | Malda Division | Malda Mechanical Division | Placement of fund against the work for road restoration work for laying of pipe line for NH-81 to Harishchandarapur Railway Station Road under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00495/2022-2023 | BP-2022-23-213 | 17/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 1.4 | 0 | 0
1175 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-I) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000044/2022-2023 | 1393/MD | 14/06/2022 | 21 | M/S DEBASISH GHOSH | 10.83 | 0 | 96
1176 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-II) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000045/2022-2023 | 1394/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 10.82 | 0 | 95
1177 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at Head Work site of UTTAR HARISHCHANDRAPUR ZONE-II & its adjoining mouza Water Supply Scheme under Malda Division,PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000054/2022-2023 | 1486/MD | 23/06/2022 | 60 | S. N. CONSTRUCTION | 6.18 | 0 | 0
1178 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 4 of Uttar Harishchandrapur Zone-I PWSS under Harishchandrapur-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000107/2025-2026 | 2278/MD | 21/05/2025 | 45 | MASUMA ENTERPRISE | 4.28 | 0 | 100
1179 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2ND Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000134/2022-2023 | 1791/MD | 01/08/2022 | 1035 | PRADIP KUMAR DAS | 369.64 | 216.23 | 100
1180 | Malda Division | Malda Mechanical Division | Construction of 5.40 mtr.X 3.60 mtr Switch Room cum chlorine room at UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Head Work Site under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000140/2024-2025 | 2891/MD | 07/06/2024 | 45 | KANAN CONSTRUCTION ENTERPRISE | 6.6 | 0 | 100
1181 | Malda Division | Malda Mechanical Division | Road restoration work related to laying of Pipeleine at Uttar Harishchandrapur Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000159/2025-2026 | 2881/MD | 17/06/2025 | 45 | PRADIP KUMAR DAS | 56.21 | 0 | 0
1182 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000210/2024-2025 | 3031/MD | 13/06/2024 | 657 | M/S GHOSH CONSTRUCTION | 10.19 | 0 | 0
1183 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-II Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000211/2024-2025 | 3032/MD | 13/06/2024 | 153 | M/S. B. PAUL & COMPANY | 25.13 | 0 | 82
1184 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 400 M3 Capacity OHR with Soil Investigation and FHTC of UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Harishchandrapur-I and II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000227/2023-2024 | 2682/MD | 13/07/2023 | 988 | KANAN CONSTRUCTION ENTERPRISE | 229.11 | 0 | 65
1185 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 900 M3 Capacity OHR with FHTC (Mouza- Uttar Harishchandrapur 50% area covered) of Uttar Harishchandrapur Zone-I Piped Water Supply Scheme at Harishchandrapur-I & II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000476/2023-2024 | 3615/MD | 21/09/2023 | 468 | MAHAMAYA BURIMA ENTERPRISE | 340.61 | 0 | 65
1186 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000489/2024-2025 | 5002/MD | 27/09/2024 | 270 | SAJEDUR RAHAMAN | 34.41 | 0 | 80
1187 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-II Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000509/2022-2023 | 377/MD | 31/01/2023 | 1034 | KUNDU CONSTRUCTION | 227.6 | 93.51 | 41
1188 | Malda Division | Malda Mechanical Division | Laying of Additional Pipeline HDPE in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000624/2024-2025 | 5831/MD | 22/11/2024 | 317 | KUNDU CONSTRUCTION | 95.04 | 0 | 0
1189 | Malda Division | Malda Mechanical Division | Laying Emergent repairing of distribution pipe line & laying of UPVC pipe line of UTTAR HARISHCHANDRAPUR water supply scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000783/2019-2020 | 856/MD | 20/03/2020 | 0 | PARIJAT RAY | 4.57 | 0 | 1
1190 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Uttar Harishchandrapur Zone-I PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000903/2023-2024 | 276/MD | 11/01/2024 | 45 | M/S DUTTA ENTERPRISE | 4.18 | 0 | 0
1191 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000006/2022-2023 | 1206/MD | 24/05/2022 | 0 | Resource Division | 53.31 | 0 | 0
1192 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000105/2023-2024 | 35/MD | 04/01/2024 | 0 | Resource Division | 17.33 | 0 | 0
1193 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000127/2023-2024 | 97/MD | 05/01/2024 | 0 | Resource Division | 11.4 | 0 | 0
1194 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of KARIALI ZONE-I Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000226/2023-2024 | 2681/MD | 13/07/2023 | 1019 | KANAN CONSTRUCTION ENTERPRISE | 437.7 | 0 | 75
1195 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-I Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | ORD/000691/2021-2022 | 656/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.23 | 3.23 | 1
1196 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | RTOR000059/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 56.72 | 0 | 0
1197 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05 | RTOR000130/2023-2024 | 100/MD | 05/01/2024 | 0 | Resource Division | 25.06 | 0 | 0
1198 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well no-3 ( 115 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at RAJARAMPUR Water Supply Scheme of Habibpur Block .under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000306/2022-2023 | 2301/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 8.24 | 8.2 | 1
1199 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of RAJARAMPUR Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000342/2022-2023 | 3109/MD | 20/12/2022 | 45 | M/S SRINJOYEE | 6.68 | 6.49 | 1
1200 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for RAJARAMPUR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000356/2022-2023 | 2505//MD | 03/11/2022 | 45 | GOBINDA ENTERPRISE | 43.92 | 41.3 | 100
1201 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at RAJARAMPUR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000883/2024-2025 | 1122/MD | 21/03/2025 | 369 | THREE BROTHERS CONSTRUCTION & CO | 9.43 | 0 | 0
1202 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | RTOR000018/2022-2023 | 2406/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0
1203 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of KISMAT BAROL Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000094/2023-2024 | 2115/MD | 06/06/2023 | 602 | MILLENNIUM ENTERPRISR | 463.93 | 0 | 52
1204 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000167/2024-2025 | 2942/MD | 10/06/2024 | 30 | S & G CONSTRUCTION | 8.41 | 0 | 0
1205 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000214/2024-2025 | 3035/MD | 13/06/2024 | 567 | MILLENNIUM ENTERPRISE | 28.66 | 0 | 80
1206 | Malda Division | Malda Mechanical Division | Dedicated/Parallel Pipe Line for better functionality and road restoration of Kismat Baral Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000690/2025-2026 | 5919/MD | 26/11/2025 | 60 | MILLENNIUM ENTERPRISE | 44.43 | 0 | 0
1207 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000012/2023-2024 | 1612/MD | 11/04/2023 | 0 | Resource Division | 14.33 | 0 | 0
1208 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000034/2022-2023 | 3046/MD | 12/12/2022 | 0 | Resource Division | 22.91 | 0 | 0
1209 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of ALAL ZONE-II Piped Water Supply Scheme at Gajol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000050/2023-2024 | 2000/MD | 17/05/2023 | 944 | KRISHNENDU DUTTA | 357.66 | 0 | 50
1210 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000266/2024-2025 | 3415/MD | 09/07/2024 | 571 | KRISHNENDU DUTTA | 33.49 | 0 | 0
1211 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube Well site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000312/2024-2025 | 3952/MD | 07/08/2024 | 557 | KRISHNENDU DUTTA | 8.71 | 0 | 0
1212 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000687/2021-2022 | 652/MD | 22/03/2022 | 15 | TECHVISION | 3.33 | 3.32 | 0
1213 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000716/2024-2025 | 6407/MD | 19/12/2024 | 407 | KRISHNENDU DUTTA | 28.08 | 0 | 0
1214 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000066/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.65 | 0 | 0
1215 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000156/2023-2024 | 252/MD | 10/01/2024 | 0 | Resource Division | 8.7 | 0 | 0
1216 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BASARA Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000413/2022-2023 | 2987/MD | 07/12/2022 | 936 | M/S JHA CONSTRUCTION | 81.06 | 0 | 100
1217 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Basara Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000728/2022-2023 | 1202/MD | 21/03/2023 | 45 | M.S. ENTERPRISE | 4.17 | 0 | 0
1218 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bujurkhali, Harinandanbati & Chandipur Mouza of Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000783/2024-2025 | 349/MD | 30/01/2025 | 92 | DHRITIPALI | 21.06 | 0 | 0
1219 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BASARA Piped Water Supply Scheme (Tube Well No-3) of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000835/2022-2023 | 2706/MD | 17/11/2022 | 30 | RATAN CHANDRA SARKAR | 6.81 | 0 | 0
1220 | Malda Division | Malda Mechanical Division | Sinking of ( 200 mm Dia. X 150 mm Dia.) Tube well No.-4 (250 M deep) by D.R Rig. Method using P.V.C. Pipe & Gravel Filter including Supply of materials at BASARA Water Supply Scheme of Bamongola Block under Malda Division, P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000919/2023-2024 | 380/MD | 17/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 12.74 | 0 | 100
1221 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Augmentation of CHANCHAL ZONE-I, ZONE-II AND ZONE-III Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000658/2022-2023 | 1026/MD | 13/03/2023 | 1111 | GHOSH BROTHERS | 1318.2 | 0 | 15
1222 | Malda Division | Chanchal Sub-Division | Emergent Interconnection between Existing Tube Well and Bolck office building water tank in connection of CHANCHAL Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000763/2024-2025 | 6621/MD | 31/12/2024 | 180 | BIDYUT MAHALDAR | 0.86 | 0 | 100
1223 | Malda Division | Chanchal Sub-Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-2) (Period from 01/01/2025 to 30/06/2025). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000873/2024-2025 | 6636/MD | 31/12/2024 | 181 | M/S TEWARI CONSTRUCTION | 0.86 | 0 | 0
1224 | Malda Division | Chanchal Sub-Division | Laying of Distribution Sysytem of Chanchal Zone -I, II & III Piped Water Supply Scheme at Chanchal -I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000926/2023-2024 | 535/MD | 30/01/2024 | 548 | GHOSH BROTHERS | 56.98 | 0 | 35
1225 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000069/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 186.59 | 0 | 0
1226 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000134/2023-2024 | 111/MD | 05/01/2024 | 0 | Resource Division | 34.35 | 0 | 0
1227 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Moyna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000677/2024-2025 | 6202/MD | 09/12/2024 | 45 | M/S /FAIZUL HAQUE BISWAS | 7.17 | 0 | 100
1228 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Moua- Bade Myna, JL No. 117) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000698/2022-2023 | 1155/MD | 20/03/2023 | 879 | M/S BABLU ENTERPRISE | 22.65 | 20.58 | 37
1229 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Mouza- Moyna, JL No. 119 & Mouza- Anantarapur, JL No. 120) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000705/2022-2023 | 1163/MD | 20/03/2023 | 45 | MOMTAJ ALI | 24.65 | 0 | 0
1230 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000711/2022-2023 | 1169/MD | 20/03/2023 | 30 | M/S SAHA CONSTRUCTION | 9.8 | 7.83 | 100
1231 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000712/2022-2023 | 1170/MD | 20/03/2023 | 30 | A. D. D. ASSOCIATES | 10.56 | 0 | 0
1232 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Moyna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000732/2022-2023 | 1206/MD | 21/03/2023 | 45 | M/S /FAIZUL HAQUE BISWAS | 8.33 | 0 | 50
1233 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Moyna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000774/2024-2025 | 297/MD | 29/01/2025 | 45 | MOMTAJ ALI | 52.13 | 0 | 0
1234 | Malda Division | Malda Mechanical Division | Augmentation of Head Work site Pump House at MOYNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000885/2024-2025 | 1124/MD | 21/03/2025 | 45 | M/S /FAIZUL HAQUE BISWAS | 2.06 | 0 | 100
1235 | Malda Division | Malda Mechanical Division | Augmentation of Pump House-2 at MOYNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000886/2024-2025 | 1125/MD | 21/03/2025 | 45 | M/S /FAIZUL HAQUE BISWAS | 2.02 | 0 | 100
1236 | Malda Division | Malda Mechanical Division | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of MOYNA Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | ORD/000888/2024-2025 | 1127/MD | 21/03/2025 | 45 | HIND CO-OPERATIVA LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.24 | 0 | 0
1237 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-07,Mukaddar Parvage, Junior Engineer | RTOR000167/2023-2024 | 248/MD | 10/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
1238 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000176/2024-2025 | 2951/MD | 10/06/2024 | 30 | BINA CONSTRUCTION | 9.07 | 0 | 0
1239 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000569/2022-2023 | 760/MD | 17/02/2023 | 30 | J. M. CONSTRUCTION | 5.95 | 5.58 | 100
1240 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-III) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000572/2022-2023 | 763/MD | 17/02/2023 | 30 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 8.87 | 8.46 | 100
1241 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000734/2022-2023 | 1213/MD | 21/03/2023 | 45 | S & G CONSTRUCTION | 20.67 | 20.32 | 100
1242 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000752/2022-2023 | 1300/MD | 23/03/2023 | 45 | A.K. AGENCY | 4.18 | 0 | 98
1243 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 200mm. Dia. x 150mm. Big dia Tube Well 143 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of MALIPAKAR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000781/2022-2023 | 1439/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.2 | 7.64 | 100
1244 | Malda Division | Malda Mechanical Division | Replacement of 200 mm dia. (all through)Tubewell No:-2 (75 M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at DAKSHIN BRINDABANBATI Water Supply Scheme of Habibpur Malda Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000461/2024-2025 | 4816/MD | 13/09/2024 | 30 | JOY GURU ENTERPRISE | 6.9 | 0 | 0
1245 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000703/2022-2023 | 1161/MD | 20/03/2023 | 555 | M/S JHA CONSTRUCTION | 77.26 | 0 | 100
1246 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000726/2022-2023 | 1200/MD | 21/03/2023 | 45 | SURAJIT MONDAL | 4.16 | 0 | 100
1247 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. All through) Tube Well No - 3 (75.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at DAKSHIN BRINDABANBATI Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000773/2022-2023 | 1431/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 6.72 | 0 | 100
1248 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DAKSHIN BRINDABANBATI Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000879/2024-2025 | 1118/MD | 21/03/2025 | 178 | ACHARYYA CONSTRUCTION | 9.3 | 0 | 0
1249 | Malda Division | Malda Mechanical Division | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000982/2023-2024 | 977/MD | 04/03/2024 | 45 | M/S JHA CONSTRUCTION | 44.56 | 0 | 85
1250 | Malda Division |  | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/00851/2023-2024 | BP-2023-24-461 | 02/02/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0
1251 | Malda Division |  | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/01128/2023-2024 | BP-2023-24-603 | 28/03/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.28 | 0 | 0
1252 | Malda Division |  | Construction of Boundary Wall at head work site of Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000202/2024-2025 | 2989/MD | 11/06/2024 | 416 | NEOGI ENTERPRISE | 25.32 | 0 | 67
1253 | Malda Division |  | Design, Fabrication, Supplying, Installing, Commissioning and 3 (three) months Trial Run of 100 m³/hr. capacity of Iron Elimination Plant (Pressure Type) with provision of polishing unit and Construction of 3.60 mtr. X 3.00 mtr. Blower room of Head Work Site of MORGRAM Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. |  |  | ORD/000227/2025-2026 | 4232/MD | 29/08/2025 | 60 | NEOGI ENTERPRISE | 34.98 | 0 | 0
1254 | Malda Division |  | Formal work order for the work of Implementation of MORGRAM Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000370/2023-2024 | 3107/MD | 10/08/2023 | 900 | NEOGI ENTERPRISE | 664.04 | 0 | 70
1255 | Malda Division |  | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000606/2023-2024 | 4110/MD | 10/10/2023 | 397 | RAY CONSTRUCTION CO. | 20.07 | 0 | 100
1256 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000639/2024-2025 | 5918/MD | 26/11/2024 | 45 | NEOGI ENTERPRISE | 81.8 | 0 | 0
1257 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 238/MD | 10/01/2024 | 0 | Resource Division | 16.12 | 0 | 0
1258 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 810/MD | 21/02/2024 | 0 | Resource Division | 66.34 | 0 | 0
1259 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of TULSHIHATTA ZONE-II Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000038/2023-2024 | 1885/MD | 08/05/2023 | 962 | MANIK CHANDRA SAHA | 276.32 | 0 | 71
1260 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 2 of Tulshihatta Zone-II Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000073/2025-2026 | 2266/MD | 21/05/2025 | 45 | M/S GLOBAL ENTERPRISE | 4.34 | 0 | 100
1261 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 1 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000456/2023-2024 | 3397/MD | 31/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 10.81 | 0 | 96
1262 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 2 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000457/2023-2024 | 3398/MD | 31/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 10.81 | 0 | 95
1263 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Tulshihata Zone-II Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000618/2024-2025 | 5742/MD | 20/11/2024 | 452 | M/S BABLU ENTERPRISE | 25.14 | 0 | 75
1264 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-II Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000690/2021-2022 | 655/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.27 | 3.24 | 1
1265 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihatta Zone-II Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000757/2024-2025 | 75 | 13/01/2025 | 45 | M/S BABLU ENTERPRISE | 24.37 | 0 | 0
1266 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000033/2023-2024 | 1806/MD | 27/04/2023 | 0 | Resource Division | 17.43 | 0 | 0
1267 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000128/2023-2024 | 98/MD | 05/01/2024 | 0 | Resource Division | 6.9 | 0 | 0
1268 | Malda Division | Chanchal Sub-Division | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB61A/3084 for the month of April 2023 | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00234/2023-2024 | BP-2023-24-115 | 20/07/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.31 | 0 | 0
1269 | Malda Division | Chanchal Sub-Division | Submission of bill for hire charges & HSD & Mobil charges of vehicle No. WB61A/3084 for the month of May-2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00294/2023-2024 | BP-2023-24-147 | 10/08/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0
1270 | Malda Division | Chanchal Sub-Division | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65C/6570 for the month of July2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00369/2023-2024 | BP-2023-24-195 | 07/09/2023 | 0 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0
1271 | Malda Division | Chanchal Sub-Division | Soil Investigation and design of substructure for Over Head Reservoirs for MALATIPUR Piped Water Supply Scheme at Chanchal-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | BILL/00489/2022-2023 | BP-2022-23-198 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
1272 | Malda Division | Chanchal Sub-Division | Augmentation Pump House and Boundary Wall of Malatipur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000130/2025-2026 | 2492/MD | 28/05/2025 | 75 | CHARU CONSTRUCTION | 16.65 | 0 | 0
1273 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Malatipur Pipe Water Supply Scheme at Chanchal-II Block in the District of Malda under Malda Division P.H.E. Dte. (2ND Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000132/2022-2023 | 1788/MD | 01/08/2022 | 823 | M/S MAA TARA CONSTRUCTION | 300.02 | 181.24 | 85
1274 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malatipur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000166/2025-2026 | 2879/MD | 17/06/2025 | 60 | SAHA CONSTRUCTION | 56.44 | 0 | 0
1275 | Malda Division | Chanchal Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000169/2025-2026 | 7811/MD | 11/06/2025 | 60 | HANNAN BUILDERS PVT. LTD. | 130.04 | 0 | 0
1276 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Construction of 400 M3 Capacity OHR with FHTC (Mouza-Harishpara, Kashipara and Gobindapara) of MALATIPUR Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000311/2023-2024 | 2914/MD | 31/07/2023 | 180 | DEEP CONSTRUCTION | 183.27 | 0 | 100
1277 | Malda Division | Chanchal Sub-Division | Erection of Property board related to Jal Jeevan Mission works of Kshempur & Malatipur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000947/2024-2025 | 636/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.82 | 0 | 0
1278 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000007/2022-2023 | 1207/MD | 24/05/2022 | 0 | Resource Division | 0.61 | 0 | 0
1279 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000012/2024-2025 | 3925/MD | 06/08/2024 | 0 | Resource Division | 8.01 | 0 | 0
1280 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000035/2023-2024 | 1801/MD | 27/04/2023 | 0 | Resource Division | 0.59 | 0 | 0
1281 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000138/2023-2024 | 113/MD | 05/01/2024 | 0 | Resource Division | 8.6 | 0 | 0
1282 | Malda Division |  | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Perapur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000020/2025-2026 | 1612/MD | 30/04/2025 | 120 | MANIK CHANDRA SAHA | 97.83 | 0 | 0
1283 | Malda Division |  | Construction of Boundary Wall at Head Work site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/000154/2024-2025 | 2923/MD | 10/06/2024 | 600 | GHOSH CONSTRUCTION | 23.72 | 0 | 70
1284 | Malda Division |  | Formal work order for the work of Implementation of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000358/2023-2024 | 3016/MD | 08/08/2023 | 813 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 838.31 | 0 | 10
1285 | Malda Division |  | Laying of Distribution of UPVC Pipeline of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. |  |  | ORD/000898/2024-2025 | 1214/MD | 25/03/2025 | 310 | BANIK BROTHERS | 66.48 | 0 | 0
1286 | Malda Division |  | Construction of Boundary Wall at 2nd Tubewell site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. |  |  | ORD/001034/2023-2024 | 1260/MD | 15/03/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 7.65 | 0 | 0
1287 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 234/MD | 10/01/2024 | 0 | Resource Division | 17.65 | 0 | 0
1288 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 812/MD | 21/02/2024 | 0 | Resource Division | 54.03 | 0 | 0
1289 | Malda Division | Malda Mechanical Division | Bill for reimbursement of cost of Diesel and mobil in respect of hired vehicle Ambassador Car No.- WB-65/D2727 For the month of January, February and March 2023. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | BILL/00336/2023-2024 |  | 22/08/2023 | 0 | ARUN KUMAR DAS | 0.96 | 0 | 0
1290 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 750 M3 Capacity OHR with Soil Investigation and FHTC of KHARBA Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000063/2023-2024 | 2020/MD | 18/05/2023 | 954 | SOVAN KUMAR ROY | 355.8 | 0 | 40
1291 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying distribution pipe line of KHARBA and it's adjoining mouzas Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte. Govt of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000068/2023-2024 | 2033/MD | 19/05/2023 | 90 | HANNAN BUILDERS PVT. LTD. | 430.15 | 0 | 80
1292 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube Well site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000172/2024-2025 | 2947/MD | 10/06/2024 | 30 | M/S GHOSH ENTERPRISE | 8.66 | 0 | 0
1293 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000219/2024-2025 | 3040/MD | 13/06/2024 | 30 | SOVAN KUMAR ROY | 24.8 | 0 | 0
1294 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of KHARBA Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000482/2022-2023 | 1128/MD | 20/03/2023 | 45 | M/S FOUR STAR CONSTRUCTION | 4.2 | 0 | 100
1295 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at KHARBA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000676/2022-2023 | 1140/MD | 20/03/2023 | 30 | DUTTA ENTERPRISE | 21.12 | 0 | 95
1296 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Kharba PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000901/2023-2024 | 274/MD | 11/01/2024 | 45 | SABITA CONSTRUCTION COMPANY | 4.17 | 0 | 98
1297 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at Kharba under Chanchal-I under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | ORD/000902/2023-2024 | 275/MD | 11/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.64 | 0 | 95
1298 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000070/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 88.29 | 0 | 0
1299 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Sanjit Sarkar, Junior Engineer | RTOR000116/2023-2024 | 86/MD | 05/01/2024 | 0 | Resource Division | 16.23 | 0 | 0
1300 | Malda Division |  | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. |  |  | ORD/000161/2020-2021 | 2714/MD | 10/11/2020 | 30 | NEOGI ENTERPRISE | 66.16 | 81.97 | 100
1301 | Malda Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. |  |  | ORD/000363/2023-2024 | 3052/MD | 09/08/2023 | 30 | M/S AYUSH BUILDERS | 7.85 | 0 | 100
1302 | Malda Division |  | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. |  |  | ORD/000365/2023-2024 | 3054MD | 09/08/2023 | 30 | M/S SRINJOYEE | 4.65 | 4.63 | 100
1303 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 36/MD | 04/01/2024 | 0 | Resource Division | 1.58 | 0 | 0
1304 | Malda Division | Malda Sadar Sub-Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Purba Binodpur, JL. No. 44, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer |  | ORD/000139/2020-2021 | 2449/MD | 12/10/2020 | 30 | A. B. CONSTRUCTION | 11.75 | 21.72 | 0
1305 | Malda Division | Malda Sadar Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | Sri Biswadip Sengupta, Assistant Engineer |  | ORD/000159/2020-2021 | 2712/MD | 10/11/2020 | 45 | NIRENDRA NATH KUNDU | 77.09 | 70.11 | 0
1306 | Malda Division | RWS Malda Sub-Division | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB 04-H-8254 for the month of MAY, JUNE, JULY 2023 under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | BILL/00314/2023-2024 | BP-2023-24-157 | 18/08/2023 | 0 | SHABNAM ARA | 1.18 | 0 | 0
1307 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of Bulbulchandi Piped water supply scheme for the work of Geotechnical Study,construction of 700 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block in the District of Malda under Malda Division, PH Engg Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000006/2022-2023 | 1125/MD | 19/05/2022 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 551.54 | 388.46 | 85
1308 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 110 Mtr. Deep Big dia Tube well (1 Nos.) at BULBULCHANDI Water Supply Scheme under Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000015/2023-2024 | 1672/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 8.95 | 8.64 | 100
1309 | Malda Division | RWS Malda Sub-Division | Shifting of existing water pipeline of different dia (OD) HDPE Pipeline in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) due to New Culvert Construction along the road under command area of AUGMENTATION of BULBULCHANDI Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000144/2025-2026 | 2682/MD | 04/06/2025 | 45 | ACQUA CONSTRUCTION CONSORTIUM | 5.61 | 0 | 0
1310 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection, Dismentling of Concrete road & Restoration and Laying of Rising Main including Specials & Valves for Bulbulchandi Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000162/2025-2026 | 2761/MD | 09/06/2025 | 60 | ACQUA CONSTRUCTION CONSORTIUM | 86.98 | 0 | 0
1311 | Malda Division | RWS Malda Sub-Division | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of BULBULCHANDI Water Supply Scheme ( Mouza - Bulbulchandi, Soladanga) at Habibpur Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000302/2024-2025 | 3448/MD | 11/07/2024 | 45 | ACQUA CONSTRUCTION CONSORTIUM | 47.09 | 0 | 90
1312 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) HDPE Pipeline under command area of AUGMENTATION of BULBULCHANDI Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000617/2024-2025 | 5741/MD | 20/11/2024 | 45 | MILLENNIUM ENTERPRISE | 86.38 | 0 | 0
1313 | Malda Division | RWS Malda Sub-Division | Repairing of boundary wall and Land Development work corresponding to Tube Well No. 3 at BULBULCHANDI Piped Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | ORD/000947/2023-2024 | 657/MD | 08/02/2024 | 45 | M/S GHOSH CONSTRUCTION | 2.5 | 0 | 100
1314 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000003/2022-2023 | 1105/MD | 17/05/2022 | 0 | Resource Division | 81.12 | 0 | 0
1315 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Sumit Kumar Ganguly, Junior Engineer | RTOR000041/2022-2023 | 1586/MD | 28/03/2023 | 0 | Resource Division | 6.43 | 0 | 0
1316 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/00488/2022-2023 | BP-2022-23-197 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
1317 | Malda Division | Malda Mechanical Division | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | BILL/00490/2022-2023 | BP-2022-23-199 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0
1318 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 900 M³ Capacity OHR with FHTC of Aridanga Zone-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000005/2023-2024 | 1572/MD | 10/04/2023 | 365 | USHA ENTERPRISE | 338.37 | 54.91 | 92
1319 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 400 M³ Capacity OHR with FHTC of ARIDANGA ZON-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000014/2023-2024 | 1649/MD | 13/04/2023 | 628 | UTTAM KUMAR GHOSH | 173.92 | 19.27 | 93
1320 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Araidanga Zone-I Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000027/2022-2023 | 1306/MD | 01/06/2022 | 30 | J. M. CONSTRUCTION | 4.76 | 0 | 0
1321 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01 (One) No. 250mm. Dia. x 150mm. Big dia. Tube Well 120 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Araidanga (Zone-I)Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000047/2022-2023 | 1396/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 6.91 | 0 | 0
1322 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Araidanga (Zone-I) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000131/2022-2023 | 1784/MD | 01/08/2022 | 60 | USHA ENTERPRISE | 282.55 | 280.52 | 100
1323 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of ARAIDANGA (Zone-II) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000133/2022-2023 | 1789/MD | 01/08/2022 | 60 | SUBHAS CHANDRA KESHARI | 163.59 | 137.51 | 1
1324 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of Distribution pipe line in connection with Augmentation of Araidanga Zone-I ( node from J-69 to J-172, J-73 to 240, J-81 to 331, J-172 to J-73, 240 to J-191, 331 to J-69) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000144/2022-2023 | 1932/MD | 23/08/2022 | 15 | SUBRATA SAHA | 6.17 | 6.17 | 1
1325 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Araidanga Zone-I Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000168/2025-2026 | 5795/MD | 13/11/2025 | 60 | M/S JHA CONSTRUCTION | 110.7 | 0 | 0
1326 | Malda Division | Malda Mechanical Division | Continuation work order for the work of Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Revisional Transport authority for office of the SE/NBC-II under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000590/2022-2023 | 1248/NBC-II | 14/11/2022 | 180 | TARUN KUMAR BHATTACHARYA | 3.79 | 2.59 | 78
1327 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of NIJGANPARANPUR under Araidanga Zone-II Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000723/2023-2024 | 4772/MD | 05/12/2023 | 45 | J. M. CONSTRUCTION | 12.15 | 0 | 70
1328 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000745/2023-2024 | 5248/MD | 22/12/2023 | 45 | M/S JHA CONSTRUCTION | 31.99 | 0 | 80
1329 | Malda Division | Malda Mechanical Division | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000746/2023-2024 | 5250/MD | 22/12/2023 | 45 | M/S KUNDU CONSTRUCTION | 25.79 | 0 | 80
1330 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARAIDANGA ZONE-I Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000747/2023-2024 | 5249/MD | 22/12/2023 | 45 | CHARU CONSTRUCTION | 20.19 | 0 | 75
1331 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000792/2022-2023 | 1476/MD | 30/03/2023 | 30 | UTTAM KUMAR GHOSH | 11.04 | 7.47 | 75
1332 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000793/2022-2023 | 1477/MD | 30/03/2023 | 30 | CHARU CONSTRUCTION | 11.09 | 10.18 | 0
1333 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Village Uportola, Namotola, Radhanagar, Chunakhali and Paranpur under Aridanga Zone-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000880/2023-2024 | 155/MD | 08/01/2024 | 45 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 12.15 | 0 | 70
1334 | Malda Division | Malda Mechanical Division | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Car-2) (Period from 01/02/2025 to 31/07/2025). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001037/2024-2025 | 377/MD | 31/01/2025 | 181 | SUBRATA SAHA | 0.86 | 0 | 0
1335 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000013/2022-2023 | 1872/MD | 16/08/2022 | 0 | Resource Division | 88.26 | 0 | 0
1336 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000027/2023-2024 | 1606/MD | 11/04/2023 | 0 | Resource Division | 31.54 | 0 | 0
1337 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000046/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 124.23 | 0 | 0
1338 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000108/2023-2024 | 38/MD | 04/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
1339 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000180/2023-2024 | 778/MD | 20/02/2024 | 0 | Resource Division | 1.23 | 0 | 0
1340 | Malda Division | Malda Mechanical Division | Placement of fund against the work for road restoration work for laying of pipe line for Aridanga Piped Water Supply Scheme under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | VCH/001010/2022-2023 | BP-2022-23-98 | 23/11/2022 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.67 | 0 | 0
1341 | Malda Division | RWS Malda Sub-Division | Augmentation work of Construction of Boundary Wall at Head Work site of MAHISHBATHANI Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000008/2025-2026 | 2411/MD | 27/05/2025 | 75 | M/S EHAN ENTERPRISE | 10.94 | 0 | 0
1342 | Malda Division | RWS Malda Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 135m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Maheshpur Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000157/2024-2025 | 2926/MD | 10/06/2024 | 295 | MERCURY ENGINEERING COMPANY | 47.11 | 0 | 18
1343 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and laying of 90 mm OD diameter UPVC Pipeline under command area of Augmentation of Maheshpur Piped Water Supply Scheme at Englishbazar Dev. Block in the District Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000196/2025-2026 | 3630/MD | 24/07/2025 | 60 | M/S STAR INDIA CONSTRUTION | 70.86 | 0 | 0
1344 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Augmentation of MAHESHPUR Piped water supply scheme for the work of Geotechnical Study,construction of 600 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within English Bazar Block under Malda Division PH Engg.Dte. In the District of Malda . | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000421/2022-2023 | 3179/MD | 23/12/2022 | 1121 | M/S NIRAPADA BHATTACHARJEE | 631.46 | 325.77 | 95
1345 | Malda Division | RWS Malda Sub-Division | Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site at Maheshpur PWSS of Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000463/2023-2024 | 3396/MD | 31/08/2023 | 45 | SADHANA CONSTRUCTION | 6.52 | 0 | 100
1346 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Sinking of 300 mm. Dia. x 200 mm. dia. and 95 Mtr. Deep Big dia Tube well (2 No) at MAHESHPUR Water Supply Scheme under English Bazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000603/2022-2023 | 921/MD | 27/02/2023 | 555 | ASHIS CONSTRUCTION | 21.48 | 8.9 | 100
1347 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Maheshpur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000741/2024-2025 | 25/MD | 06/01/2025 | 360 | M/S STAR INDIA CONSTRUTION | 60.76 | 0 | 85
1348 | Malda Division | RWS Malda Sub-Division | Laying of Rising Main including Specials and Valves for MAHESHPUR Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000914/2023-2024 | 387/MD | 17/01/2024 | 450 | S. N. CONSTRUCTION | 19.15 | 0 | 35
1349 | Malda Division | RWS Malda Sub-Division | Additional Laying of Distribution pipe line of MAHESHPUR Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000915/2023-2024 | 388/MD | 17/01/2024 | 313 | DEBAPRIYA SAHA | 37.78 | 0 | 100
1350 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work Site of MAHESHPUR Piped Water Supply Scheme at Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda. | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | ORD/000916/2023-2024 | 378/MD | 17/01/2024 | 288 | M/S SRINJOYEE | 15.94 | 0 | 100
1351 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000028/2023-2024 | 1810/MD | 27/04/2023 | 0 | Resource Division | 28.61 | 0 | 0
1352 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000049/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 28.61 | 0 | 0
1353 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer-06 | RTOR000188/2023-2024 | 823/MD | 21/02/2024 | 0 | Resource Division | 17.76 | 0 | 0
1354 | Malda Division | Malda Mechanical Division | Formal work order for the work of Construction of 700 M3 Capacity OHR with Soil Investigation and FHTC of Kushida Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000009/2023-2024 | 1569/MD | 10/04/2023 | 982 | SUBHAS CHANDRA KESHARI | 333.31 | 0 | 65
1355 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Kushida Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000011/2023-2024 | 1568/MD | 10/04/2023 | 1087 | SUBHAS CHANDRA KESHARI | 434.18 | 147.44 | 87
1356 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000028/2022-2023 | 1195/MD | 24/05/2022 | 31 | RANJIT ADHIKARY | 4.8 | 0 | 0
1357 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000029/2022-2023 | 1196/MD | 24/05/2022 | 31 | RAHANUL ALAM | 4.8 | 0 | 1
1358 | Malda Division | Malda Mechanical Division | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 150m Deep at 3rd Tubewell site of Kushida PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000305/2024-2025 | 3451/MD | 11/07/2024 | 227 | SAUDAGAR INDIA | 10.14 | 0 | 90
1359 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kushida Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000760/2024-2025 | 81 | 13/01/2025 | 45 | SUBHAS CHANDRA KESHARI | 78.22 | 0 | 0
1360 | Malda Division | Malda Mechanical Division | Laying of Distribution pipe line in connection with Augmentation of Uttar Rampur Mouza (JL-36) under KUSHIDA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000763/2023-2024 | 5324/MD | 27/12/2023 | 60 | SUBHAS CHANDRA KESHARI | 91.57 | 0 | 50
1361 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000936/2023-2024 | 581/MD | 02/02/2024 | 417 | RAHANUL ALAM | 4.19 | 0 | 95
1362 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 4 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000937/2023-2024 | 582/MD | 02/02/2024 | 273 | SR ENTERPRISE | 4.19 | 0 | 95
1363 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Khusida, Bhingol, Uttar Harishandrapur, Dakshin Mahendrapur, Konar, Rangaipur PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000956/2024-2025 | 645/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 100
1364 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 06/02/2024 to 30/06/2024). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/001221/2023-2024 | 589/MD | 02/02/2024 | 146 | M/S FOUR STAR CONSTRUCTION | 0.71 | 0 | 0
1365 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000047/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 51.58 | 0 | 0
1366 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000136/2023-2024 | 115/MD | 05/01/2024 | 0 | Resource Division | 13.49 | 0 | 0
1367 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of PUTIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000489/2022-2023 | 593/MD | 09/02/2023 | 90 | PARIJAT RAY | 41.34 | 26.52 | 95
1368 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at PUTIA Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000608/2022-2023 | 926/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.13 | 9.49 | 100
1369 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Putia Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000738/2024-2025 | 57 | 08/01/2025 | 45 | CHOWDHURY CONSTRUCTION | 1.61 | 0 | 0
1370 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000006/2024-2025 | 3918/MD | 06/08/2024 | 0 | Resource Division | 0.22 | 0 | 0
1371 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | RTOR000019/2023-2024 | 1609/MD | 11/04/2023 | 0 | Resource Division | 0.81 | 0 | 0
1372 | Malda Division | RWS Malda Sub-Division | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 11.645 KM to 13.904 Km and Nimbari to Harishchandrapur road from 0.00 KM to 0.889 KM under Kadirpur and Chaksukur PWSS under Malda Division,PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | BILL/00514/2024-2025 | BP-2024-25-251 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 14.42 | 0 | 0
1373 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at Head Work Site of Chaksukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000626/2024-2025 | 5833/MD | 22/11/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 19.53 | 0 | 0
1374 | Malda Division | RWS Malda Sub-Division | Formal work order for the work of Implementation of CHAKSUKUR Piped Water Supply at Habibpur Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000661/2022-2023 | 1035/MD | 13/03/2023 | 897 | HANNAN BUILDERS PVT. LTD. | 880.48 | 0 | 40
1375 | Malda Division | RWS Malda Sub-Division | Construction of Boundary Wall at 2nd Tube well site of Chaksukur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000678/2024-2025 | 6203/MD | 09/12/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 8.68 | 0 | 0
1376 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000006/2023-2024 | 1582/MD | 10/04/2023 | 0 | Resource Division | 17.4 | 0 | 0
1377 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000086/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 25.7 | 0 | 0
1378 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for KHATIL Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000511/2022-2023 | 414/MD | 02/02/2023 | 758 | M/S AMIT KUMAR GUPTA | 74.79 | 0 | 100
1379 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Khatil Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000756/2022-2023 | 1304/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.18 | 0 | 0
1380 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KHATIL Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000774/2022-2023 | 1432/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 7.56 | 7.48 | 100
1381 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Khatil Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/000778/2024-2025 | 296/MD | 29/01/2025 | 401 | M/S ROY CONSTRUCTION | 8.52 | 0 | 0
1382 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/001002/2023-2024 | 1181/MD | 14/03/2024 | 30 | M/S EHAN ENTERPRISE | 10.2 | 0 | 0
1383 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer | ORD/001003/2023-2024 | 1182/MD | 14/03/2024 | 45 | S. N. CONSTRUCTION | 21.18 | 0 | 0
1384 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kadirpur Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000024/2023-2024 | 1714/MD | 20/04/2023 | 45 | SHANKAR PRASAD BHAGAT | 8.32 | 0 | 100
1385 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kadirpur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000642/2024-2025 | 5945/MD | 28/11/2024 | 277 | M/S SINHA ENTERPRISE | 26.03 | 0 | 0
1386 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for KADIRPUR Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000702/2022-2023 | 1160/MD | 20/03/2023 | 45 | M/S AMIT KUMAR GUPTA | 73.06 | 64.94 | 90
1387 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000713/2022-2023 | 1171/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.23 | 6.23 | 100
1388 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 4 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Biswajit Ghosh, Junior Engineer,Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000714/2022-2023 | 1172/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.23 | 6.23 | 100
1389 | Malda Division | Malda Mechanical Division | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000195/2024-2025 | 2899/MD | 07/06/2024 | 30 | A. L. ENGINEERING SOLUTION | 2.11 | 0 | 0
1390 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000575/2022-2023 | 766/MD | 17/02/2023 | 30 | CHARU CONSTRUCTION | 11.7 | 11.7 | 100
1391 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000751/2022-2023 | 1299/MD | 23/03/2023 | 45 | SOFIKUL ISLAM | 4.19 | 0 | 95
1392 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of UTTAR KUMEDPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000783/2022-2023 | 1441/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 12.03 | 0 | 60
1393 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Uttar Kumedpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Susanta Pal, JE_Deputation | ORD/000806/2024-2025 | 438/MD | 06/02/2025 | 75 | M/S T. K. CONSTRUCTION | 32.5 | 0 | 0
1394 | Malda Division | Malda Mechanical Division | Interconnection between new Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000280/2024-2025 | 3231/MD | 28/06/2024 | 521 | M/S /FAIZUL HAQUE BISWAS | 12.28 | 0 | 100
1395 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of UPVC pipe line laying with Withdrawing and relaying of DI pipe line for Providing Functional Household Tap Connection (FHTC) in connection to Source Augmentation of Kendua PWSS, Chanchal I Block Malda Division PHE. Dte in The District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000568/2022-2023 | 759/MD | 17/02/2023 | 30 | M/S /FAIZUL HAQUE BISWAS | 15.08 | 12.02 | 100
1396 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000723/2022-2023 | 1197/MD | 21/03/2023 | 45 | RABIUL ISLAM | 4.18 | 0 | 100
1397 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Kendua Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000768/2022-2023 | 1398/MD | 28/03/2023 | 30 | A. L. ENGINEERING SOLUTION | 12.62 | 0 | 100
1398 | Malda Division | Malda Mechanical Division | Augmentation work of OHR, Pump House and Boundary Wall of Kendua Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Rajarshi Sinha, Junior Engineer | ORD/000857/2024-2025 | 1050/MD | 18/03/2025 | 75 | M/S DAS CONSTRUCTION | 31.92 | 0 | 0
1399 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for PARAMESWARPUR Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000737/2022-2023 | 1209/MD | 21/03/2023 | 45 | SOVON KUMAR DAS | 29.32 | 25.32 | 80
1400 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Parameswarpur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000757/2022-2023 | 1305/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.17 | 0 | 99
1401 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PARAMESWARPUR Water Supply Scheme of Bamongola Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Mukaddar Parvage, Junior Engineer | ORD/000772/2022-2023 | 1430/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 8.85 | 8.05 | 100
1402 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall of Adhna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000082/2025-2026 | 2267/MD | 21/05/2025 | 45 | M/S. B. K. ASSOCIATES | 10.13 | 0 | 0
1403 | Malda Division | Malda Mechanical Division | Replacement of 200 mm dia. all through Big Dia. Tube Well at Head Work site (150m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of ADHNA Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000115/2025-2026 | 2466/MD | 28/05/2025 | 60 | GOBINDA ENTERPRISE | 9.82 | 0 | 0
1404 | Malda Division | Malda Mechanical Division | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (170 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at ADHNA Water Supply Scheme of Gazol Block under Malda Division, PHE Dte, Govt. of West Bengal | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000458/2024-2025 | 4812/MD | 13/09/2024 | 156 | A. D. D. ASSOCIATES | 10.6 | 0 | 100
1405 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for ADHNA Piped Water Supply Scheme at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000556/2022-2023 | 1181/MD | 21/03/2023 | 30 | GOBINDA ENTERPRISE | 40.5 | 36.95 | 90
1406 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at ADHNA Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000715/2022-2023 | 1173/MD | 20/03/2023 | 30 | JAYA ENTERPRISE | 7.56 | 7.05 | 100
1407 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Adhna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000725/2022-2023 | 1199/MD | 21/03/2023 | 45 | M/S GHOSH ENTERPRISE | 4.17 | 0 | 100
1408 | Malda Division | Malda Mechanical Division | Augmentation of Head work site Pump House,Pump House No.-2 ,Earth filling and 2 Nos. Boundary wall at ADHNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000876/2024-2025 | 1115/MD | 21/03/2025 | 194 | GOBINDA ENTERPRISE | 7.83 | 0 | 0
1409 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at Meherpur Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000137/2024-2025 | 2888/MD | 07/06/2024 | 45 | MAA MANASA CONSTRUCTION | 4.15 | 0 | 0
1410 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of MEHERPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000219/2023-2024 | 2683/MD | 13/07/2023 | 1051 | M/S S. D. ENTERPRISE | 307.58 | 0 | 75
1411 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 140 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of aterials at Heads Work Site of MEHERPUR Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000339/2022-2023 | 2511/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 9.34 | 0 | 100
1412 | Malda Division | Malda Mechanical Division | Formal work order for the work of Laying Distribution pipe line for MEHERPUR and its adjoining mouzas Piped Water Supply at Old Malda Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000660/2022-2023 | 1040/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 529.66 | 369.92 | 100
1413 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000673/2024-2025 | 6198/MD | 09/12/2024 | 90 | RAJIB MANI | 7.52 | 0 | 0
1414 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 3rd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000674/2024-2025 | 6199/MD | 09/12/2024 | 45 | J. M. CONSTRUCTION | 7.52 | 0 | 0
1415 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000062/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 4.83 | 0 | 0
1416 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-III Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000233/2023-2024 | 2708/MD | 14/07/2023 | 1175 | SOVON KUMAR DAS | 355.42 | 0 | 18
1417 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-III Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000253/2024-2025 | 3189/MD | 27/06/2024 | 584 | SOVON KUMAR DAS | 27.49 | 0 | 0
1418 | Malda Division | Malda Mechanical Division | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000367/2023-2024 | 3056/MD | 09/08/2023 | 480 | A. L. ENGINEERING SOLUTION | 9.16 | 0 | 100
1419 | Malda Division | Malda Mechanical Division | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) & rectification work in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-III Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | ORD/000875/2024-2025 | 1104/MD | 20/03/2025 | 225 | SOVON KUMAR DAS | 93.26 | 0 | 0
1420 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-05,Rahul Das Biswas, Junior Engineer | RTOR000093/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 60.79 | 0 | 0
1421 | Malda Division | RWS Malda Sub-Division | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for Aiho Zone-II piped Water Supply scheme of Habibpur Block in the District of Malda under Malda Division, P.H.E.Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000466/2024-2025 | 4821/MD | 13/09/2024 | 45 | FUTURE | 10.04 | 0 | 100
1422 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000555/2022-2023 | 1180/MD | 21/03/2023 | 45 | FUTURE | 81.51 | 44.55 | 34
1423 | Malda Division | RWS Malda Sub-Division | Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000703/2023-2024 | 4589/MD | 22/11/2023 | 465 | FUTURE | 90.61 | 0 | 60
1424 | Malda Division | RWS Malda Sub-Division | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000767/2022-2023 | 1396/MD | 28/03/2023 | 704 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 13.01 | 0 | 100
1425 | Malda Division | RWS Malda Sub-Division | Augmentation of 3 Nos. Pump House at AIHO ZONE-2 Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000878/2024-2025 | 1117/MD | 21/03/2025 | 45 | RATAN KARMAKAR | 5.36 | 0 | 0
1426 | Malda Division | RWS Malda Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-2 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000985/2023-2024 | 980/MD | 04/03/2024 | 298 | FUTURE | 32.22 | 0 | 100
1427 | Malda Division | RWS Malda Sub-Division | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/05/2024 to 30/06/2024). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/001218/2023-2024 | 1440/MD | 15/03/2024 | 61 | SHABNAM ARA | 0.29 | 0 | 100
1428 | Malda Division | RWS Malda Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-03,Ramen Karmakar, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | RTOR000084/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.34 | 0 | 0
1429 | Malda Division | Malda Mechanical Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000081/2025-2026 | 2251/MD | 21/05/2025 | 45 | MANAS KUMAR SAHA | 53.59 | 0 | 0
1430 | Malda Division | Malda Mechanical Division | Formal work order for the work of Augmentation of NASHIPUR Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000236/2023-2024 | 2711/MD | 14/07/2023 | 806 | MANAS KUMAR SAHA | 452.36 | 0 | 70
1431 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 4th Tube Well site of Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000314/2024-2025 | 3954/MD | 07/08/2024 | 45 | RATAN KARMAKAR | 7.1 | 0 | 0
1432 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 3 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000948/2023-2024 | 656/MD | 08/02/2024 | 45 | RATAN KARMAKAR | 4.76 | 0 | 0
1433 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 4 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000949/2023-2024 | 655/MD | 08/02/2024 | 45 | ISMAIL ENTERPRISE | 4.76 | 0 | 0
1434 | Malda Division | Malda Mechanical Division | Erection of Property board related to Jal Jeevan Mission works of Nasipur, Ariadanga Zone-I & II, Pirpur PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/000973/2024-2025 | 662/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.8 | 0 | 0
1435 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 16/02/2024 to 30/06/2024). | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | ORD/001222/2023-2024 | 717/MD | 09/02/2024 | 136 | M/S TEWARI CONSTRUCTION | 0.64 | 0 | 95
1436 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | RTOR000016/2024-2025 | 3992/MD | 08/08/2024 | 0 | Resource Division | 6.16 | 0 | 0
1437 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | RTOR000073/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.88 | 0 | 0
1438 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Sudip Kumar Mahata, Junior Engineer | RTOR000199/2023-2024 | 833/MD | 21/02/2024 | 0 | Resource Division | 12.62 | 0 | 0
1439 | Malda Division | Malda Mechanical Division | Acceptance cum formal work order for Implementation of AIHORANI Piped Water Supply Scheme at Old Malda Dev. Block of Malda district under Malda Division, PHE Dte. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000834/2022-2023 | 1500/MD | 30/03/2023 | 552 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 37.17 | 0 | 90
1440 | Malda Division | Malda Mechanical Division | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Aihorani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | ORD/000953/2023-2024 | 650/MD | 08/02/2024 | 45 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.3 | 0 | 100
1441 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Mr. Prosanta Mandal, Assistant Engineer | Junior Engineer-07,Mr. Sujit Sarkar, Junior Engineer | RTOR000172/2023-2024 | 405/MD | 18/01/2024 | 0 | Resource Division | 0.65 | 0 | 0
1442 | Malda Division | Malda Mechanical Division | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House & Boundary wall at Alinagar Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000144/2024-2025 | 2901/MD | 07/06/2024 | 353 | SUDIP DEY | 83.78 | 0 | 85
1443 | Malda Division | Malda Mechanical Division | Laying of Parallel/ Dedicated Pipeline for better Functionality at Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000246/2025-2026 | 4348/MD | 10/09/2025 | 440 | BANIK BROTHERS | 26.97 | 0 | 0
1444 | Malda Division | Malda Mechanical Division | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000505/2024-2025 | 5408/MD | 21/10/2024 | 130 | BANIK BROTHERS | 36.94 | 0 | 0
1445 | Malda Division | Malda Mechanical Division | Bamboo piing, earth filing for protection of pipe line at different places for Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000590/2024-2025 | 5624/MD | 06/11/2024 | 30 | BANIK BROTHERS | 8.66 | 0 | 100
1446 | Malda Division | Malda Mechanical Division | Formal work order for the work of Implementation of ALINAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000614/2022-2023 | 940/MD | 27/02/2023 | 1220 | BANIK BROTHERS | 458.54 | 166.86 | 75
1447 | Malda Division | Malda Mechanical Division | Placing of diesel driven vehicle on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000831/2022-2023 | 667/CSD | 29/12/2022 | 365 | SUDIPTA GHOSH | 0.85 | 0.33 | 37
1448 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at Head Work site of Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000882/2023-2024 | 158/MD | 08/01/2024 | 45 | M/S N. N. ENTERPRISE | 14.51 | 0 | 100
1449 | Malda Division | Malda Mechanical Division | Construction of Boundary Wall at 2nd Tube Well Site of ALINAGAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/000980/2023-2024 | 975/MD | 04/03/2024 | 45 | BANIK BROTHERS | 9.13 | 0 | 100
1450 | Malda Division | Malda Mechanical Division | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 12/11/2023 to 09/05/2024=180 Days). | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | ORD/001231/2023-2024 | 4566/MD | 10/11/2023 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 0 | 0
1451 | Malda Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Biswadip Sengupta, Assistant Engineer | Junior Engineer-07,Ramen Karmakar, Junior Engineer | RTOR000145/2023-2024 | 122/MD | 06/01/2024 | 0 | Resource Division | 28.48 | 0 | 0
1452 | Malda Division | Chanchal Sub-Division | Formal work order for the work of Implementation of PASCHIM BHAGABANPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000045/2023-2024 | 1995/MD | 17/05/2023 | 960 | M/S TECHNICO & CO | 568.26 | 105.95 | 90
1453 | Malda Division | Chanchal Sub-Division | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Paschim Bhagabanpur Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000318/2024-2025 | 3966/MD | 07/08/2024 | 180 | SHREE BISHNU CONSTRUCTION | 30.26 | 0 | 0
1454 | Malda Division | Chanchal Sub-Division | Construction of Boundary Wall at 2nd Tube Well site of Paschim Bhagabanpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000446/2024-2025 | 4735/MD | 11/09/2024 | 30 | M/S MADHU CONSTRUCTION | 10.76 | 0 | 15
1455 | Malda Division | Chanchal Sub-Division | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House at Paschim Bhagabanpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000484/2024-2025 | 5084/MD | 27/09/2024 | 60 | M/S TEWARI CONSTRUCTION | 92.44 | 0 | 20
1456 | Malda Division | Chanchal Sub-Division | Additional Laying Distribution of UPVC pipe line of PASCHIM BHAGABANPUR Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | ORD/000960/2023-2024 | 711/MD | 09/02/2024 | 45 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 2.15 | 0 | 90
1457 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000085/2023-2024 | 1811/MD | 27/04/2023 | 0 | Resource Division | 22.21 | 0 | 0
1458 | Malda Division | Chanchal Sub-Division | Material Requisition To Resource Division | Assistant Engineer - II,Sri Susanta Saha, Assistant Engineer | Junior Engineer-05,Mr. Subhajit Kumar Paul, Junior Engineer | RTOR000117/2023-2024 | 87/MD | 05/01/2024 | 0 | Resource Division | 11.09 | 0 | 0
1459 | Malda Division |  | Quotation for feasibility study report on possibility of setting up a 5.97-MLD capacity, radial collector well on Sub Surface Water based Piped Water Supply Scheme from Tangon River for Fluoride affected areas of Bamangola Block (Mouza- Berul, Jl-63, Near Bamongola Kathuadanga Primary School) towards implementation of water supply project based on Sub surface water of River Tangon. |  |  | BILL/00564/2024-2025 | BP-2024-25-284 | 23/09/2024 | 0 | INDUSTRY INSTITUTE PARTNERSHIP CELL JADAVPUR UNIVERSITY | 30.95 | 0 | 0
1460 | Malda Division |  | Formal work order for the work of Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion of all civil, electrical and mechanical works including all allied and related works of Sub- Surface Water Based Piped Water Supply Scheme in Bamangola block of Malda district followed by three (3) months trial run and five (05) year operation and maintenance. |  |  | ORD/000584/2023-2024 | 3993/MD | 06/10/2023 | 908 | ENGINEERING PROJECTS (INDIA) LIMITED (A GOVERNMENT OF INDIA ENTERPRISE) | 12347.61 | 0 | 7
1461 | Malda Division |  | Sinking of 200mm (all through) Big dia. Tube Well of 30.0 m Deep and RCC Structure for hoisting of MS Pipe for Tube well and Platform at Tangon river bed of bamongola Sub Surface Water based PWSS for Fluride affected areas of Bamongola Block under Malda Division, P.H.E Dte in the district of Malda. (10 Nos Tube Well & 20 Nos RCC Structure) |  |  | ORD/000692/2025-2026 | 5922/MD | 26/11/2025 | 120 | ASHIS CONSTRUCTION | 68.99 | 0 | 0
1462 | Malda Division |  | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 834/MD | 21/02/2024 | 0 | Resource Division | 3626.73 | 0 | 0
Total | [10 empty] | 132023.16 | 14711.89