## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Aug. of Rajbalhat W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00015/2022-2023 | BP-2022-23-114 | 14/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.48 | 0 | 0
2 | Electrical | Srirampur Sub-Division | Quoation bill for new service connection at Rajbalhat | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00775/2022-2023 | 151 | 08/02/2023 | 0 | WBSEDCL | 3.85 | 0 | 0
3 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 5004123576 Reference ID- 503622497 SM Code- 09694 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01402/2024-2025 | 345 | 31/07/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
4 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 100000118583 Reference ID- 860312463 SM Code- 09694 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01992/2024-2025 | 480 | 01/10/2024 | 0 | WBSEDCL | 1.63 | 0 | 0
5 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. IV, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000061/2023-2024 | 1640/ED | 11/04/2023 | 90 | SUDIKSHA CONSTRUCTION | 10.68 | 0 | 0
6 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000168/2022-2023 | 3501/ED | 30/12/2022 | 90 | MAA KALI ENTERPRISE | 10.68 | 0 | 100
7 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJBALHAT PIPED W/S SCHEME, T.W. No. V, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002580/2023-2024 | 456/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 65
8 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for New Connection of Choutara T/W-I W/S scheme under ED PHE Dte. (SM/12252) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06544/2023-2024 | 909 | 21/03/2024 | 0 | WBSEDCL | 3.43 | 0 | 0
9 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for New Connection of Choutara T/W-II W/S scheme under ED PHE Dte. (SM/12252) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06548/2023-2024 | 908 | 21/03/2024 | 0 | WBSEDCL | 3.41 | 0 | 0
10 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chautara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000080/2022-2023 | 3462/ED | 30/12/2022 | 90 | DAS ENTERPRISE | 20.46 | 0 | 35
11 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at KAMRAI water supply scheme (SM/12258), T/W No. - I, Vill. & P.O. - KAMRAI, Dist. - Hooghly. Ref. Id. - 503562461, Dated - 16-02-2024, Application No. - 5004013365, | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06156/2023-2024 | 795 | 22/02/2024 | 0 | WBSEDCL | 9.09 | 0 | 0
12 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at KAMRAI water supply scheme (SM/12258), T/W No. - II, Vill. & P.O. - KAMRAI, Dist. - Hooghly. Ref. Id. - 503562460, Dated - 16-02-2024, Application No. - 5004013396 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06157/2023-2024 | 796 | 22/02/2024 | 0 | WBSEDCL | 0.35 | 0 | 0
13 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kamrai water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000085/2022-2023 | 3467/ED | 30/12/2022 | 630 | DEBJYOTI BASU | 22.37 | 0 | 95
14 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/001055/2023-2024 | 4027/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 30.05 | 0 | 10
15 | Electrical | RWS Howrah Sub-Division | QUOTATION OF NEW SERVICE CONNECTION FOR KHILA W/S SCHEME, PH NO-III | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/02133/2023-2024 | 124 | 20/07/2023 | 0 | WBSEDCL | 6.1 | 0 | 0
16 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khila water supply scheme, T.W. No.- I, II & III, Block: Udaynaraynpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000116/2022-2023 | 3554/ED | 30/12/2022 | 1037 | M/S P.P. ELECTRICALS | 30.54 | 0 | 50
17 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, C (Dariapur) in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001427/2023-2024 | 4888/ED | 27/12/2023 | 183 | SUNRISE ENGINEERING CORPORATION | 61.12 | 0 | 0
18 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, B (Rautara) in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001059/2023-2024 | 4030/ED | 17/10/2023 | 810 | DEY ENTERPRISE | 57.7 | 0 | 25
19 | Electrical | Chinsuria Sub-Division | Additional Quotation for new service connection at Kuchpala W/S Sch. , T/W No. - I [SM/12238] , Block - Polba-Dadpur, under Dadpur CCC, WBSEDCL, Ref Id. - 860296974, dt. - 15/04/2024, Application No. - 100000105244 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00189/2024-2025 | 74 | 18/04/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
20 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kuchpala W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04323/2023-2024 | 434 | 21/11/2023 | 0 | WBSEDCL | 5.39 | 0 | 0
21 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kuchpala W/S Sch., T/W No. - I, Block - Polba-Dadpur under Dadpur CCC, WBSEDCL, Ref. Id. - 503553646,dt. - 11-03-2024, Application No. - 5003998904 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06460/2023-2024 | 887 | 15/03/2024 | 0 | WBSEDCL | 12.43 | 0 | 0
22 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kuchpala water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000161/2022-2023 | 3496/ED | 30/12/2022 | 90 | M/S DILIP MITRA | 21.59 | 0 | 90
23 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | BILL/04445/2023-2024 | 506 | 08/12/2023 | 0 | WBSEDCL | 0.4 | 0 | 0
24 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Bandhpur W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | BILL/04446/2023-2024 | 507 | 08/12/2023 | 0 | WBSEDCL | 12.9 | 0 | 0
25 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandhpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | ORD/000128/2022-2023 | 3482/ED | 30/12/2022 | 90 | ASHUTOSH DAS & CO. | 21.38 | 0 | 90
26 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BANDHPUR water supply scheme, TW No. III, Block: Chanditala-I, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Chandital-II Block Junior Engineer (Civill),Junior Engineer2 | ORD/003084/2024-2025 | 479/ED | 18/03/2025 | 90 | S.K. ENTERPRISE | 11.3 | 0 | 0
27 | Electrical | RWS Howrah Sub-Division | Quotation bill for new service connection of Kharda Itarai PWSS, P.H-II | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | BILL/00721/2023-2024 | 17 | 02/05/2023 | 0 | WBSEDCL | 7.81 | 0 | 0
28 | Electrical | RWS Howrah Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION OF KHORDA ETARAI W/S SCHEME PH NO-I, ELECTRICAL DIVISION, PHE DTE | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | BILL/00751/2023-2024 | 39 | 15/05/2023 | 0 | WBSEDCL | 7.36 | 0 | 0
29 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khorda Etarai water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000137/2022-2023 | 3513/ED | 30/12/2022 | 611 | MAHAMAYA ENTERPRISE | 20.36 | 0 | 90
30 | Electrical | Howrah Sadar Sub-Division | Quotation money deposit for Domjur (Zone-III) Khasmara W/S ,P.H No.-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00732/2023-2024 | 21 | 04/05/2023 | 0 | WBSEDCL | 0.69 | 0 | 0
31 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Domjur, Khasmara W/S. Sch. Z-III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00841/2023-2024 | 65 | 08/06/2023 | 0 | WBSEDCL | 2.34 | 0 | 0
32 | Electrical | Howrah Sadar Sub-Division | Deposition of additional quotation money for domjur zone-III ( KHASMARA) w/s scheme P.H No.-I ,Dist- Howrah under ED PHED. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00967/2023-2024 |  | 07/06/2023 | 0 | WBSEDCL | 2.34 | 0 | 0
33 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Khasmara W/S. Sch. Howrah | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02723/2023-2024 | 167 | 04/08/2023 | 0 | WBSEDCL | 0.22 | 0 | 0
34 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Khasmara W/S. Sch. PWSS-II | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04130/2023-2024 | 377 | 25/10/2023 | 0 | WBSEDCL | 15.25 | 0 | 0
35 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Khasmara (Domjur Zone-III) Pwss P.H No-III , Dist-Howrah under ED, PHED. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/06055/2023-2024 | 752 | 16/02/2024 | 0 | WBSEDCL | 12.75 | 0 | 0
36 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khasmara Domjur (Zone-III) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000155/2022-2023 | 3512/ED | 30/12/2022 | 90 | H.K.DAS & CO. | 34.31 | 0 | 65
37 | Electrical | Ulberia Sub-Division | Supply of Fuel for 1(One) no Diesel Luxury taxi on contract Carriage for the Office of the Assistant Engineer,Howrah Mechanical Sub Division PHE Dte.(JJM Work for Hooghly District) for the Month of March 2024. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | BILL/00263/2024-2025 | 106 | 07/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
38 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Tulsiberia Kalimandir W/S. Sch. PH-I & II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | BILL/00718/2023-2024 | 18 | 02/05/2023 | 0 | WBSEDCL | 11.36 | 0 | 0
39 | Electrical | Ulberia Sub-Division | Deposition of Quotation money for Tulshiberia w/s scheme, P.H No-I ,Dist-howrah under ED PHED. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | BILL/01065/2023-2024 | 76 | 15/06/2023 | 0 | WBSEDCL | 4.24 | 0 | 0
40 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tulsiberia water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000133/2022-2023 | 3525/ED | 30/12/2022 | 663 | TAMAL ENTERPRISE | 20.35 | 0 | 30
41 | Electrical | Ulberia Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/001104/2023-2024 | 2830/HMSD | 30/10/2023 | 182 | SANJIB PRADHAN | 0.86 | 0 | 42
42 | Electrical | Srirampur Sub-Division | payment of quotation of wbsedcl bill Begampur w/s scheme z II PH NO III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00744/2023-2024 | 33 | 12/05/2023 | 0 | WBSEDCL | 0.58 | 0 | 0
43 | Electrical | Srirampur Sub-Division | Payment of Wbsedcl Quotation for Begampur W/S Scheme Zone-I, PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00745/2023-2024 | 32 | 12/05/2023 | 0 | WBSEDCL | 0.58 | 0 | 0
44 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection of WBSEDCL for Begampur Kharsari P-II W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | BILL/00773/2022-2023 | 145 | 30/01/2023 | 0 | WBSEDCL | 0.68 | 0 | 0
45 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur Kharsarai water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000053/2022-2023 | 2043/ED | 01/12/2022 | 90 | BARISAL TRADING CO. | 10.61 | 0 | 50
46 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Begampur water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/000199/2022-2023 | 826/ED | 14/02/2023 | 90 | CINZANO | 21.49 | 0 | 99
47 | Electrical | Srirampur Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Begampur Purba Tajpur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/001127/2022-2023 | 726/HMSD | 24/03/2023 | 30 | ART CONSORTIUM | 3.24 | 0 | 0
48 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Begampur water supply scheme, T.W. No. II, Block: Chanditala-II, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | ORD/001176/2022-2023 | 2043 /ED | 01/12/2022 | 90 | BARISAL TRADING CO. | 10.61 | 0 | 0
49 | Electrical | Srirampur Sub-Division | Quotation bill payment for Begampur w/s scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2,Junior Engineer4 | VCH/002688/2022-2023 |  | 04/11/2022 | 0 | WBSEDCL | 0.68 | 0 | 0
50 | Electrical | Howrah Sadar Sub-Division | Quotation Money deposition for new service connection at Ichapur pwss, P.H No.-I , Dist-Howrah under ED PHED. Application No.- 1007513772 Ref. ID- 106460039 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/06102/2023-2024 | 761 | 16/02/2024 | 0 | WBSEDCL | 17.39 | 0 | 0
51 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Ichhapur pwss , P.H No.-II, Dist-Howrah under PHED. App. No.-1007566560 Ref.ID: 106496241 SM/13629 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/06259/2023-2024 | 859 | 11/03/2024 | 0 | WBSEDCL | 17.26 | 0 | 0
52 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ichapur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000127/2022-2023 | 3541/ED | 30/12/2022 | 1080 | KASHINATH PAL & CO. | 21.15 | 0 | 60
53 | Electrical | Howrah Sadar Sub-Division | Shifting of 1 (No.) 25kva DISTRIBUTION SUB-STATATION at Dakshin Jhapordah (Zone-I) PWSS, P.H No.-I under ED, PHED. Ref. ID.-860318414 SM/13751 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02300/2024-2025 | BP-24-25-595 | 21/11/2024 | 0 | WBSEDCL | 1.71 | 0 | 0
54 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. Z-i | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04500/2023-2024 | 546 | 19/12/2023 | 0 | WBSEDCL | 9.63 | 0 | 0
55 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-I) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000251/2022-2023 | 918/ED | 22/02/2023 | 90 | D. K. ELECTRIC | 32.22 | 0 | 30
56 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
57 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
58 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03829/2023-2024 | 287 | 20/09/2023 | 0 | WBSEDCL | 5.55 | 0 | 0
59 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sahapur W/S. Sch. TW-II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03830/2023-2024 | 288 | 20/09/2023 | 0 | WBSEDCL | 7.41 | 0 | 0
60 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sahapur water supply scheme TW No I and II Block Pursurah, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000233/2022-2023 | 864/ED | 14/02/2023 | 90 | TRIO CONCERN | 20.77 | 0 | 45
61 | Electrical | Chandannagar Sub-Division | Purba Ramnagar w/s scheme,P H No . 3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | BILL/03771/2023-2024 |  | 05/09/2023 | 0 | WBSEDCL | 4.62 | 0 | 0
62 | Electrical | Chandannagar Sub-Division | Purba Ramnagar w/s scheme,P H No 3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | BILL/03772/2023-2024 | 275 | 08/09/2023 | 0 | WBSEDCL | 4.62 | 0 | 0
63 | Electrical | Chandannagar Sub-Division | Purba Ramnagar w/s scheme,P H NO 4 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | BILL/03773/2023-2024 | 274 | 08/09/2023 | 0 | WBSEDCL | 5.06 | 0 | 0
64 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Purba Ramnagar water supply scheme TW No I and II Block Tarakeswar, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Tarakeswar Block Junior Engineer | ORD/000222/2022-2023 | 853/ED | 14/02/2023 | 90 | C.M. ENTERPRISE | 21.49 | 0 | 85
65 | Electrical | Chinsuria Sub-Division | Quotation money deposition for new service connection at Sripur w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004132708 Reference ID- 503625865 SM Code- 13411 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00326/2024-2025 | 104 | 06/05/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
66 | Electrical | Chinsuria Sub-Division | Supply Xerox Paper ofice of the EE PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/01915/2022-2023 | 253 | 31/03/2023 | 0 | BARRACKPORE CENTRAL ZONE | 0.09 | 0 | 0
67 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pandua, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000170/2024-2025 | 1193/ED | 14/06/2024 | 90 | SUBHRA ENTERPRISE | 10.75 | 0 | 60
68 | Electrical | Chinsuria Sub-Division | "Supply, Delivery & Installation of S/P/M & other E/M equipments etc. for Sripur W/S. Sch. TW-III RA-I" | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001034/2022-2023 | 1320/ED | 17/08/2022 | 90 | SWAPAN ENTERPRISE | 7.37 | 0 | 0
69 | Electrical | Chinsuria Sub-Division | Withdrawing of 10 HP submersible pumping machinery and installation of standby pumping machinery and allied electrical/mechanical works at Sripur w/s scheme, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001135/2022-2023 | 1991/HMSD | 10/11/2022 | 21 | KUSHANI ENTERPRISE | 2.45 | 0 | 0
70 | Electrical | Chinsuria Sub-Division | Quatation bill for Sripur W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | VCH/002739/2022-2023 |  | 10/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.96 | 0 | 0
71 | Electrical | Chinsuria Sub-Division | Quotation bill for Sripur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | VCH/002751/2022-2023 | 108 | 18/11/2022 | 0 | WBSEDCL | 2.96 | 0 | 0
72 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gabberia Mallik Bagan water supply scheme, T.W. No.- I, II & III, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000152/2022-2023 | 3538/ED | 30/12/2022 | 90 | INDIA ENTERPRISE | 30.58 | 0 | 0
73 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Paschim Panchla W/S. Sch. PH-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/04335/2023-2024 | 445 | 28/11/2023 | 0 | WBSEDCL | 23.36 | 0 | 0
74 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Paschim Panchla W/S. Sch. PH-II | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/04336/2023-2024 | 446 | 28/11/2023 | 0 | WBSEDCL | 22.73 | 0 | 0
75 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Panchla water supply scheme, T.W. No. I, II & III, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000037/2023-2024 | 1714/ED | 18/04/2023 | 90 | S.P. CONSTRUCTION | 30.56 | 0 | 40
76 | Electrical | North 24 Pgs W/S Division I | Chak Kanthalia | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | BILL/01115/2023-2024 |  | 27/06/2023 | 0 | WBSEDCL | 1.66 | 0 | 0
77 | Electrical | North 24 Pgs W/S Division I | Supplimentary quotation for Patulia PH No 3 ( Near Ruiya Verir Gate ) | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | BILL/02396/2023-2024 |  | 27/07/2023 | 0 | WBSEDCL | 5.04 | 0 | 0
78 | Electrical | North 24 Pgs W/S Division I | Quotation for service connection for OHR site at Zone IA-II ( Chalk Kanthalia ) in Barrackpore-II block | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | BILL/02595/2023-2024 | 162 | 03/08/2023 | 0 | WBSEDCL | 5.04 | 0 | 0
79 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/001428/2023-2024 | 4889/ED | 27/12/2023 | 183 | BENGAL CONSTRUCTION | 59.48 | 0 | 0
80 | Electrical | Srirampur Sub-Division | Madhavpur w/s scheme,P H No 1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/03774/2023-2024 | 273 | 08/09/2023 | 0 | WBSEDCL | 3.71 | 0 | 0
81 | Electrical | Srirampur Sub-Division | Madhavpur w/s scheme,P H No 2 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04511/2023-2024 | 554 | 21/12/2023 | 0 | WBSEDCL | 6.73 | 0 | 0
82 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Madhabpur water supply scheme TW No I and II Block Chanditala II District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000231/2022-2023 | 862/ED | 14/02/2023 | 899 | NEW RANBEE ENGINEERING | 20.36 | 0 | 40
83 | Electrical | Srirampur Sub-Division | Rectification & overhualing of VCB Panel, LT Panel, ATS Panel, AVR and transformer at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001207/2021-2022 | 145/AE-I/ED | 18/02/2022 | 90 | ORIENTAL ENGINEERING CO. | 1.9 | 0 | 0
84 | Electrical | Srirampur Sub-Division | Supply & Installation of NRV and other allied works at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001208/2021-2022 | 1009/AE-I/ED | 13/08/2021 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0
85 | Electrical | Srirampur Sub-Division | Supply & Installation of Butterfly valve for pump set no-2 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001210/2021-2022 | 42/AE-I/ED | 14/01/2022 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0
86 | Electrical | Srirampur Sub-Division | Supply & Installation of Butterfly valve & Check valve for pump set no-3 at BS-I, Madhabpur under (N) 24 Pgs. Arsenic Area W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001211/2021-2022 | 43/AE-I/ED | 14/01/2022 | 90 | ORIENTAL ENGINEERING CO. | 4.56 | 0 | 0
87 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 9, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007604360 Reference ID- 106521117 SM Code- 14095 | AE/SADAR | JE Sadar | BILL/00434/2024-2025 | 114 | 13/05/2024 | 0 | WBSEDCL | 10.29 | 0 | 0
88 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 4b, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007682963 Reference ID- 106564006 SM Code- 14095 | AE/SADAR | JE Sadar | BILL/00454/2024-2025 | 130 | 17/05/2024 | 0 | WBSEDCL | 17.99 | 0 | 0
89 | Electrical | Howrah Sadar Sub-Division | Deposition of quotation money for Aug.of Baragachia w/s scheme , zone-vi, P.H No-II Dist-Howrah under ED/PHED. | AE/SADAR | JE Sadar | BILL/00740/2023-2024 | 24 | 11/05/2023 | 0 | WBSEDCL | 11.06 | 0 | 0
90 | Electrical | Howrah Sadar Sub-Division | Quatation for shifting of H.T.O.H. Line DP to the PHE No- I, Zone- VI, Hantal sashan , Howrah under Bargachia CCC. Application No- 100000113194 Reference ID- 860304044 SM Code- 14095 | AE/SADAR | JE Sadar | BILL/01269/2024-2025 | 331 | 30/07/2024 | 0 | WBSEDCL | 5.83 | 0 | 0
91 | Electrical | Howrah Sadar Sub-Division | New service connection | AE/SADAR | JE Sadar | BILL/02059/2023-2024 | 106 | 19/07/2023 | 0 | WBSEDCL | 7.45 | 0 | 0
92 | Electrical | Howrah Sadar Sub-Division | New service connection | AE/SADAR | JE Sadar | BILL/02060/2023-2024 | 107 | 19/07/2023 | 0 | WBSEDCL | 3.43 | 0 | 0
93 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Bargachia PH-I, Z-VI W/S. Sch. | AE/SADAR | JE Sadar | BILL/02327/2023-2024 | 146 | 26/07/2023 | 0 | WBSEDCL | 4.96 | 0 | 0
94 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- II, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008229574 Reference ID- 106837719 SM Code- 14095 | AE/SADAR | JE Sadar | BILL/02606/2024-2025 | 627 | 18/12/2024 | 0 | WBSEDCL | 16.23 | 0 | 0
95 | Electrical | Howrah Sadar Sub-Division | new service connection | AE/SADAR | JE Sadar | BILL/03696/2023-2024 | 243 | 01/09/2023 | 0 | WBSEDCL | 5.82 | 0 | 0
96 | Electrical | Howrah Sadar Sub-Division | new service connection | AE/SADAR | JE Sadar | BILL/03698/2023-2024 | 244 | 01/09/2023 | 0 | WBSEDCL | 5.93 | 0 | 0
97 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Bargachi W/S. Sch. Z-X, PH-I | AE/SADAR | JE Sadar | BILL/04324/2023-2024 | 435 | 23/11/2023 | 0 | WBSEDCL | 1.81 | 0 | 0
98 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Bargachia W/S. Sch. Z-V | AE/SADAR | JE Sadar | BILL/04567/2023-2024 | 570 | 27/12/2023 | 0 | WBSEDCL | 4.23 | 0 | 0
99 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Bargachia W/S. Sch. Z-I | AE/SADAR | JE Sadar | BILL/04568/2023-2024 | 571 | 27/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0
100 | Electrical | Howrah Sadar Sub-Division | Quotation for New Service Connection at Bargachia W/S. Sch. Z=IX | AE/SADAR | JE Sadar | BILL/04610/2023-2024 | 609 | 04/01/2024 | 0 | WBSEDCL | 13.16 | 0 | 0
101 | Electrical | Howrah Sadar Sub-Division | Quotation Money deposition for new service connection at Bargachia water supply scheme, Zone-8 ,P.H No.-I , Dist- Howrah under ED , PHED. | AE/SADAR | JE Sadar | BILL/06035/2023-2024 | 736 | 07/02/2024 | 0 | WBSEDCL | 10.61 | 0 | 0
102 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- III, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007550896 Reference ID- 106484781 SM Code- 14095 | AE/SADAR | JE Sadar | BILL/06320/2023-2024 | 880 | 13/03/2024 | 0 | WBSEDCL | 25.65 | 0 | 0
103 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Bargachia w/s scheme, Zone- 8, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007566516 Reference ID- 106496242 SM Code- 14095 | AE/SADAR | JE Sadar | BILL/06321/2023-2024 | 881 | 13/03/2024 | 0 | WBSEDCL | 15.65 | 0 | 0
104 | Electrical | Howrah Sadar Sub-Division | Supply, delivery of clamp on type portable Flowmeter set for different OHR site of Bargachia water supply scheme, Howrah under Electrical Division, PHE Dte. | AE/SADAR | JE Sadar | ORD/000083/2023-2024 | 2157/ED | 16/06/2023 | 60 | SHANTA COLIBRI (INDIA) PVT. LTD | 17.68 | 0 | 100
105 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of BARGACHIA Water Supply Scheme, Zone-I, II, III, IV(A), IV(B), V, VI, VII, VIII, IX, X. T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR | JE Sadar | ORD/000768/2023-2024 | 2185/ED | 22/06/2023 | 731 | J.D.J ENTERPRISE | 250.01 | 0 | 35
106 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-I,TW No-II Block-Arambag,Dist-Hooghly under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03883/2023-2024 | 312 | 27/09/2023 | 0 | WBSEDCL | 8.01 | 0 | 0
107 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Daharkundu W/S. Sch. Z-I. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04085/2023-2024 | 354 | 12/10/2023 | 0 | WBSEDCL | 4.97 | 0 | 0
108 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-I, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000172/2022-2023 | 765/ED | 09/02/2023 | 90 | POLYCON ENGINEERS | 20.39 | 0 | 30
109 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttarbabnan W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04641/2023-2024 | 631 | 08/01/2024 | 0 | WBSEDCL | 0.35 | 0 | 0
110 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttarbabnan W/S. Sch. TW-II, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04642/2023-2024 | 630 | 08/01/2024 | 0 | WBSEDCL | 24.56 | 0 | 0
111 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Babnan water supply scheme, Zone-I, T.W. No.- I, II & III and Zone-II, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000282/2022-2023 | 932/ED | 22/02/2023 | 900 | DEY ENTERPRISE | 50.9 | 0 | 90
112 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mahisgot w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/14116) Application No-5004015913 Reference Id-503563370 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06067/2023-2024 | 755 | 16/02/2024 | 0 | WBSEDCL | 5.89 | 0 | 0
113 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mahisgot w/S Scheme,Zone-II,PH No-II Block-Khanakul-I Dist-Hooghly under ED,PHE Dte. (SM/14116) Application No-5004068599 Reference Id-503594190 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06468/2023-2024 | 892 | 18/03/2024 | 0 | WBSEDCL | 4.28 | 0 | 0
114 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisgot water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000176/2022-2023 | 769/ED | 09/02/2023 | 90 | M/S S R ENTERPRISE | 20.27 | 0 | 0
115 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
116 | Electrical | Chinsuria Sub-Division | Quotation of New Service Connection for Bhandarhati w/s Scheme,PH No-V, Block-Dhaniakhali Dist-Hooghly under electrical division,PHE Dte.(SM/14040)Application No-5004059159 Reference Id-503589837. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00325/2024-2025 | 97 | 06/05/2024 | 0 | WBSEDCL | 10.74 | 0 | 0
117 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for Bhanderhati T/W-V W/S scheme under ED PHE Dte. (SM/14040) | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01163/2024-2025 | 291 | 15/07/2024 | 0 | WBSEDCL | 1.77 | 0 | 0
118 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Bhandarhati W/S. Sch. TW-III" | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03757/2023-2024 | 253 | 05/09/2023 | 0 | WBSEDCL | 6.25 | 0 | 0
119 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bhandarhati TW-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03789/2023-2024 |  | 11/09/2023 | 0 | WBSEDCL | 6.36 | 0 | 0
120 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Bhandarhati TW-III" | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03791/2023-2024 | 311 | 29/09/2023 | 0 | WBSEDCL | 0.11 | 0 | 0
121 | Electrical | Chinsuria Sub-Division | Quotation for new service connection charge at Bhanderhati PWSS, TW - IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04368/2023-2024 | 453 | 01/12/2023 | 0 | WBSEDCL | 4.22 | 0 | 0
122 | Electrical | Chinsuria Sub-Division | Quotation for New Service Connection at Bhandarhati W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04659/2023-2024 | 667 | 15/01/2024 | 0 | WBSEDCL | 8.52 | 0 | 0
123 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhandarhati water supply scheme, T.W. No.- I, II, III & IV, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000201/2022-2023 | 828/ED | 14/02/2023 | 760 | EASTERN INDIA SALES & SERVICE | 42.97 | 0 | 25
124 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mostafapur w/s Scheme,PH No-I Block-Khanakul-II District-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004136071 Reference Id-503627505. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00709/2024-2025 | 211 | 11/06/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
125 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Mostafapur w/s scheme,TW No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13333) Application No-5004151915 Reference Id-503634018 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01590/2024-2025 | 357 | 07/08/2024 | 0 | WBSEDCL | 8.49 | 0 | 0
126 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mostafapur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002465/2023-2024 | 326/ED | 21/02/2024 | 90 | M.S ENTERPRISE | 21.9 | 0 | 0
127 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MOSTAFAPUR water supply scheme, TW No. III, Block: Khanakul-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/003097/2024-2025 | 483/ED | 18/03/2025 | 90 | SUDIP PRADHAN | 11.3 | 0 | 0
128 | Electrical | Arambug Sub-Division | quotation of New Service Connection for Nakunda W/S Scheme, TW No-I Block-Goghat-I, Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02478/2023-2024 | 151 | 01/08/2023 | 0 | WBSEDCL | 5.07 | 0 | 0
129 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Nakunda W/s Scheme,TW No-2, Block-Goghat-II, Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02479/2023-2024 | 152 | 01/08/2023 | 0 | WBSEDCL | 5.56 | 0 | 0
130 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nakunda water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000177/2022-2023 | 770/ED | 09/02/2023 | 90 | R.M.D TRADING. | 20.61 | 0 | 40
131 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Ghoshpur W/S. Sch.PH-V | Assistant Engineer | Junior Engineer (Civill) | BILL/04584/2023-2024 | 585 | 28/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
132 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000208/2024-2025 | 1176/ED | 14/06/2024 | 90 | P.K. ENTERPRISE | 10.72 | 0 | 0
133 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghoshpur water supply scheme, T.W. No. I, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002474/2023-2024 | 335/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
134 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service Connection of Paschim Joykrishnapur w/s scheme,Zone-2,PH No-3 Distric- Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02004/2023-2024 | 105 | 19/07/2023 | 0 | WBSEDCL | 3.19 | 0 | 0
135 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection for Paschim Joykrishnapur W/S Scheme,Zone-I,TW No-III Block-Haripal Dist-hooghly under ED,PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/03853/2023-2024 | 304 | 26/09/2023 | 0 | WBSEDCL | 10.44 | 0 | 0
136 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Paschim Joykrishnapur water supply scheme, Zone-I, T.W. No. I & Zone-II, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000003/2023-2024 | 1619/ED | 11/04/2023 | 897 | STANDARD ELECTRICALS | 21.81 | 0 | 40
137 | Electrical | Howrah Mechanical Sub-Division | Car Hire Charges Bill for official use office of the Executive Engineer Howrah Mechanical Sub-Division PHED | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000985/2023-2024 | 959/HMSD | 20/04/2023 | 365 | SANJIB PRADHAN | 5 | 0 | 1
138 | Electrical | Howrah Mechanical Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001104/2023-2024 | 2830/HMSD | 30/10/2023 | 182 | SANJIB PRADHAN | 0.86 | 0 | 42
139 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Joykrishnapur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001128/2022-2023 | 727/HMSD | 24/03/2023 | 30 | KUNAL ENTERPRISE | 3.01 | 0 | 0
140 | Electrical | Howrah Mechanical Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001901/2023-2024 | 3112/HMSD | 22/11/2023 | 196 | SIDDHARTHA CHATTERJEE. | 0.93 | 0 | 60
141 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Atghara water supply scheme TW No I Block Khanakul I District Hooghly under ED PHED. | Assistant Engineer | Junior Engineer (Civill) | ORD/000286/2022-2023 | 936/ED | 22/02/2023 | 922 | OSMAN SEKH | 10.75 | 0 | 40
142 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-II | Assistant Engineer | Junior Engineer (Civill) | BILL/04592/2023-2024 | 593 | 29/12/2023 | 0 | WBSEDCL | 3.51 | 0 | 0
143 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Patul water supply scheme, T.W. No.-V, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001385/2023-2024 | 4735/ED | 15/12/2023 | 90 | MAA KALI ENTERPRISE | 10.74 | 0 | 30
144 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Purba Raypur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000005/2023-2024 | 1621/ED | 11/04/2023 | 90 | ESENCE ENGINEERING CONCERN | 10.75 | 0 | 0
145 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jaykrishnapur w/s Scheme,TW no-3 Block-Goghat-I Dist-Hooghly under ED,PHE Dte(SM/15808) Application No-5004009573 Reference Id-503561825 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06051/2023-2024 | 748 | 16/02/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
146 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001150/2022-2023 | 1502/ED | 28/03/2023 | 90 | M/S DILIP MITRA | 10.75 | 0 | 0
147 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Shibrai W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02905/2023-2024 | 202 | 21/08/2023 | 0 | WBSEDCL | 3.84 | 0 | 0
148 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Shibrai W/S. Sch. PH-IV Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05979/2023-2024 | 734 | 05/02/2024 | 0 | WBSEDCL | 7.63 | 0 | 0
149 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shibrai water supply scheme, T.W. No. I & II, Block: Pandua, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000023/2023-2024 | 1700/ED | 18/04/2023 | 90 | A.G. ENTERPRISE | 22.81 | 0 | 50
150 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Basta W/S. Sch.TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04580/2023-2024 | 578 | 27/12/2023 | 0 | WBSEDCL | 3.06 | 0 | 0
151 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Basta W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05115/2023-2024 | 686 | 19/01/2024 | 0 | WBSEDCL | 3.61 | 0 | 0
152 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basta water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001215/2023-2024 | 4541/ED | 23/11/2023 | 552 | SHIVAM ENTERPRISE | 20.25 | 0 | 95
153 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DIHI BAGNAN PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000368/2024-2025 | 1452/ED | 25/07/2024 | 90 | BARMAN ROY TRADERS | 11.09 | 0 | 0
154 | Electrical | Arambug Sub-Division | Hiring of diesel driven contract carriage along with driver for the official use of the SEMC-I PHED | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000962/2023-2024 | 933_HMSD | 18/04/2023 | 365 | S.P. CONSTRUCTION | 5 | 0 | 30
155 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dihi Bagnan water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001476/2021-2022 | 552/ED | 22/03/2022 | 90 | BISALAXMI ENTERPRISE | 6.59 | 0 | 30
156 | Electrical | Arambug Sub-Division | Supply, delivery & installation of automatic Chlorinator for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002115/2022-2023 | 70/HMSD | 10/01/2023 | 7 | BISALAXMI ENTERPRISE | 0.8 | 0 | 100
157 | Electrical | Arambug Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Dihi Bagnan water supply scheme, T.W. No.-III, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002116/2022-2023 | 657/HMSD | 04/04/2022 | 15 | BOSE & CHATTERJEE INDUSTRIES | 2.37 | 0 | 30
158 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Kamina W/S. Sch. TW-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | BILL/04247/2023-2024 | 422 | 10/11/2023 | 0 | WBSEDCL | 18 | 0 | 0
159 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamina water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000081/2023-2024 | 1998/ED | 19/05/2023 | 90 | MENAKA ENTERPRISE | 22.87 | 0 | 40
160 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Sibgachia W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/04504/2023-2024 | 550 | 21/12/2023 | 0 | WBSEDCL | 5.62 | 0 | 0
161 | Electrical | Ulberia Sub-Division | Quotation for new service connection for Shibgachchia water supply scheme, Tubewell No. II, Block: Amta-II, Howrah SM/18193 Application No. 1007523518 Reference id: 106465462 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/06054/2023-2024 | 756 | 16/02/2024 | 0 | WBSEDCL | 7.89 | 0 | 0
162 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shibgachhia water supply scheme, T.W. No. I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/003466/2023-2024 | 1909/ED | 12/05/2023 | 90 | A.G. ENTERPRISE | 20.49 | 0 | 50
163 | Electrical | Arambug Sub-Division | Quotation of New Service Connection For Dharmmapur w/s scheme,PH No-II Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte(SM/17716) Application no-5004012404 Reference Id-503561209 | Assistant Engineer | Junior Engineer (Civill) | BILL/06049/2023-2024 | 740 | 08/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
164 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Dharmmapur w/s Scheme,PH No-I Block-Khanakul-I Dist-Hooghly under ED,PHE Dte(SM/17716) Application No-5004012408 Reference Id-503561211 | Assistant Engineer | Junior Engineer (Civill) | BILL/06050/2023-2024 | 741 | 08/02/2024 | 0 | WBSEDCL | 5.64 | 0 | 0
165 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dharmmapur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000050/2023-2024 | 1794/ED | 24/04/2023 | 830 | M/S, GHOSH ENTERPRISE | 20.35 | 0 | 30
166 | Electrical | Chinsuria Sub-Division | Quotation for new service connection charge at Bhatua PWSS, TW - I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04370/2023-2024 | 455 | 01/12/2023 | 0 | WBSEDCL | 15.6 | 0 | 0
167 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhatua water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000078/2023-2024 | 1924/ED | 15/05/2023 | 90 | UNITED ENTERPRISE | 23.21 | 0 | 50
168 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04635/2023-2024 | 635 | 08/01/2024 | 0 | WBSEDCL | 4.83 | 0 | 0
169 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Nilarpur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04638/2023-2024 | 634 | 08/01/2024 | 0 | WBSEDCL | 8.22 | 0 | 0
170 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nilarpur water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000073/2023-2024 | 1929/ED | 15/05/2023 | 90 | SWAPAN ENTERPRISE | 23.08 | 0 | 90
171 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhur Kunda w/s Scheme,Zone-II,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17719) Application No-5004320081 Reference Id- 503705387 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01374/2024-2025 | 339 | 30/07/2024 | 0 | WBSEDCL | 4.47 | 0 | 0
172 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhurkunda w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/17719) Application No-5004034182 Reference Id-503574967 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06200/2023-2024 | 811 | 28/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
173 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhurkunda water supply scheme, Zone - II, T.W. No. I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000076/2023-2024 | 1932/ED | 15/05/2023 | 676 | BISALAXMI ENTERPRISE | 22.61 | 0 | 30
174 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Maheshpur (Zone - I) W/S Sch., [SM/10451] T/W No. - IV, Nr. Sugandhya Panchyate, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594865, Dt. - 02-04-2024, Application No. - 5004069700 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00075/2024-2025 | 41 | 09/04/2024 | 0 | WBSEDCL | 4.4 | 0 | 0
175 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT MAHESHPUR (AUG.) W/S SCH., ZONE - II, P.H. NO. - III, dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00758/2023-2024 | 43 | 19/05/2023 | 0 | WBSEDCL | 2.71 | 0 | 0
176 | Electrical | Chinsuria Sub-Division | Quotation for new service connection charge at Maheshpur PWSS, Zone-I, TW - III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04369/2023-2024 | 456 | 01/12/2023 | 0 | WBSEDCL | 3.32 | 0 | 0
177 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Maheshpur water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000220/2022-2023 | 851/ED | 14/02/2023 | 472 | P.K. ENGINEERING | 21.49 | 0 | 95
178 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAHESHPUR PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Polba Dadpur, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000377/2024-2025 | 1464/ED | 25/07/2024 | 90 | MAA TARA ENTERPRISE. | 11.1 | 0 | 30
179 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002330/2022-2023 | 2385//HMSD | 27/12/2022 | 30 | DEBASHISH GHOSH | 0.29 | 0 | 30
180 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Sunia w/S Scheme,PH No-II, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18593) Application No-5004479490 Reference Id-503802380 | Assistant Engineer | Junior Engineer (Civill) | BILL/02308/2024-2025 | 607 | 05/12/2024 | 0 | WBSEDCL | 7.79 | 0 | 0
181 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Sunia w/s Scheme,PH No-IV,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18593) Application No-5004475105 Reference Id-503799038 | Assistant Engineer | Junior Engineer (Civill) | BILL/02473/2024-2025 | 616 | 05/12/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
182 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sunia PWSS W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | BILL/05994/2023-2024 | 747 | 08/02/2024 | 0 | WBSEDCL | 4.51 | 0 | 0
183 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No. III & IV, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000885/2023-2024 | 3458/ED | 11/08/2023 | 629 | DIPALI CONSTRUCTION | 21.49 | 0 | 20
184 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000917/2023-2024 | 3588/ED | 28/08/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 15
185 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bengai w/s Scheme, PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004190291 Reference Id-503647427. | Assistant Engineer |  | BILL/00482/2024-2025 | 150 | 22/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
186 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bengai w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004215163 Reference Id-503657720 | Assistant Engineer |  | BILL/00624/2024-2025 | 186 | 03/06/2024 | 0 | WBSEDCL | 5.66 | 0 | 0
187 | Electrical | Arambug Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2023 WB-15C-5554 | Assistant Engineer |  | BILL/00625/2024-2025 | 187 | 03/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
188 | Electrical | Arambug Sub-Division | Supply of Fuel for 1(One) no Diesel luxury Taxi on contract Carriage for the office of the Assistant Engineer Howrah mechanical Sub Division PHE Dte(JJM Work for Hooghly District) for the Month of April 2024. | Assistant Engineer |  | BILL/00626/2024-2025 | 191 | 10/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
189 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bengai w/s Scheme, PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/18597) Application No-5004034165 Reference Id-503574963 | Assistant Engineer |  | BILL/06198/2023-2024 | 812 | 28/02/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
190 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BENGAI PIPED W/S SCHEME, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer |  | ORD/000135/2024-2025 | 1161/ED | 14/06/2024 | 291 | M.S. ENTERPRISE | 10.95 | 0 | 30
191 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BENGAI PIPED W/S SCHEME, T.W. No. IV, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer |  | ORD/000136/2024-2025 | 1162/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0
192 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bengai water supply scheme, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer |  | ORD/000913/2023-2024 | 3584/ED | 28/08/2023 | 495 | M.S. ENTERPRISE | 23.69 | 0 | 40
193 | Electrical | Chinsuria Sub-Division | Electric quot. of WBSEDCL for New service Connection of Bagnan T/W-V W/S scheme under Electrical Division PHE Dte. (SM/11867) | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02294/2024-2025 | BP-24-25-599 | 21/11/2024 | 0 | WBSEDCL | 5.92 | 0 | 0
194 | Electrical | Chinsuria Sub-Division | Quotation Bill foe New Service Connection at Bagnan W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02587/2023-2024 | 158 | 03/08/2023 | 0 | WBSEDCL | 3.74 | 0 | 0
195 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bagnan W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02590/2023-2024 |  | 01/08/2023 | 0 | WBSEDCL | 10.74 | 0 | 0
196 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection charge at Bagnan w/s scheme, Zone-II, T.W. No.-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02725/2023-2024 | 182 | 11/08/2023 | 0 | WBSEDCL | 10.74 | 0 | 0
197 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bagnan water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000195/2022-2023 | 822/ED | 14/02/2023 | 90 | A.S. ENTERPRISE | 21.45 | 0 | 30
198 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Pukuria w/s Scheme,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004151686 Reference Id-503633620 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00413/2024-2025 | 101 | 05/05/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
199 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Pukhuria w/s Scheme,PH No-I,Block-Goghat-II,Dist-Hooghly under Electrical Division,PHE Dte.(SM/17626) Application No-5004294636 Reference Id-503691998 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01173/2024-2025 | 313 | 23/07/2024 | 0 | WBSEDCL | 4.01 | 0 | 0
200 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pukhuria water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000047/2023-2024 | 1733/ED | 19/04/2023 | 988 | B.T. PROJECT PVT. LTD. | 41.11 | 0 | 10
201 | Electrical |  | Quotation Bill for New Service Connection at Bandipur W/S. Sch |  |  | BILL/06036/2023-2024 | 738 | 07/02/2024 | 0 | WBSEDCL | 18.99 | 0 | 0
202 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. V, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001530/2021-2022 | 174_ED | 01/02/2022 | 90 | M/S DILIP MITRA | 6.74 | 0 | 50
203 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bandipur water supply scheme, T.W. No. VI, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002574/2022-2023 | 3483/ED | 30/12/2022 | 90 | M/S S.R. ENTERPRISE | 10.82 | 0 | 30
204 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No.- IV, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001280/2023-2024 | 2442_ED | 13/10/2023 | 45 | R.N.S. TRADING | 6.14 | 0 | 50
205 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VII, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001521/2021-2022 | 172/ED | 01/02/2022 | 90 | RAJIB COMPANY | 6.59 | 0 | 100
206 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. VI, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001522/2021-2022 | 171/ED | 01/02/2022 | 90 | ESENCE ENGINEERING CONCERN | 6.58 | 0 | 100
207 | Electrical |  | Supply delivery and installation of Chlorinator for BARUIPARA w/s scheme PH No. VI District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001523/2021-2022 | 103/HMSD | 18/01/2022 | 7 | STANDARD ELECTRICALS | 0.76 | 0 | 100
208 | Electrical |  | Supply delivery and installation of Chlorinator for Baruipara w/s scheme PH No. VII District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001528/2021-2022 | 83/HMSD | 14/01/2022 | 30 | M/S CHANDIMATA ELECTRICALS | 0.76 | 0 | 100
209 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baruipara water supply scheme, T.W. No. V, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001533/2021-2022 | 170/ED | 01/02/2022 | 90 | BIJAN ENTERPRISE | 6.63 | 0 | 100
210 | Electrical |  | Quotation money deposition for new service connection at Sahapur w/s scheme, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008116886 Reference ID- 106763473 SM Code- 18844 |  |  | BILL/02025/2024-2025 | 474 | 01/10/2024 | 0 | WBSEDCL | 5.78 | 0 | 0
211 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Sahapur Piped Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001303/2023-2024 | 4536/ED | 23/11/2023 | 90 | MUKHERJEE ART CENTRE | 10.68 | 0 | 0
212 | Electrical | Chinsuria Sub-Division | Supply of diesel and mobile for inspection car of AE-I under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00258/2024-2025 | 90 | 26/04/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
213 | Electrical | Chinsuria Sub-Division | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2024 WB-04G-2822 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00460/2024-2025 | 145 | 22/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
214 | Electrical | Chinsuria Sub-Division | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 From 01/06/2024 to 30/06/2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01368/2024-2025 | 330 | 30/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
215 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05126/2023-2024 | 699 | 22/01/2024 | 0 | WBSEDCL | 5.76 | 0 | 0
216 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kumrul W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05128/2023-2024 | 698 | 22/01/2024 | 0 | WBSEDCL | 5.23 | 0 | 0
217 | Electrical | Chinsuria Sub-Division | Supply of diesel & mobile oil for inspection car of AE-I under ED , PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06465/2023-2024 | 891 | 18/03/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
218 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kumrul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000086/2022-2023 | 3468/ED | 30/12/2022 | 90 | DEY ENTERPRISE | 23.33 | 0 | 0
219 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002502/2023-2024 | 139/AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0 | 5
220 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003308/2023-2024 | 139_/AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0 | 0
221 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. CAR NO.- WB-04G-2822 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003411/2023-2024 | 139_AE-I/ED | 29/01/2024 | 151 | DASHRATH KUMAR PRAJAPATI | 0.72 | 0 | 0
222 | Electrical |  | Quotation money deposition for new service connection at Balichak w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1007772492 Reference ID- 106595796 SM Code- 18885 |  |  | BILL/00491/2024-2025 | 164 | 28/05/2024 | 0 | WBSEDCL | 5.63 | 0 | 0
223 | Electrical |  | Quotation money deposition for new service connection at Ballychak(Khalrah High School) w/s scheme, T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1008185087 Reference ID- 106811234 SM Code- 18885 |  |  | BILL/02274/2024-2025 | BP-24-25-580 | 19/11/2024 | 0 | WBSEDCL | 25.61 | 0 | 0
224 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Balichak Water Supply Scheme Block- Amta-I District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001300/2023-2024 | 4533/ED | 23/11/2023 | 571 | GHOSE ENGINEERING SYNDICATE | 21.91 | 0 | 50
225 | Electrical |  | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- IV in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814868 Application no- 5004498035 |  |  | BILL/02601/2024-2025 | 630 | 18/12/2024 | 0 | WBSEDCL | 8.62 | 0 | 0
226 | Electrical |  | Quotation for new service connection for source Augmentation of SOMRA Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHE Dte. ( SM/18969), Reference Id- 503814816 Application no- 5004497772 |  |  | BILL/02602/2024-2025 | 629 | 18/12/2024 | 0 | WBSEDCL | 8.47 | 0 | 0
227 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SOMRA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001214/2023-2024 | 4492/ED | 23/11/2023 | 1074 | MAA TARA CONSTRUCTION | 21.47 | 0 | 50
228 | Electrical |  | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18971), Reference Id- 503733787 Application no- 5004386169 |  |  | BILL/01969/2024-2025 | 479 | 01/10/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
229 | Electrical |  | Quotation for new service connection for source Augmentation of Rameswarpur Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. (SM/18971), Reference Id- 503726898 Application no- 5004370950 |  |  | BILL/01970/2024-2025 | 481 | 01/10/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
230 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF RAMESWARPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001244/2023-2024 | 4494/ED | 23/11/2023 | 90 | R.K.ENTERPRISE | 21.48 | 0 | 0
231 | Electrical |  | Quotation for new service connection for source Augmentation of KAMARPARA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18972), Reference Id-503777915 Application no- 5004449275 |  |  | BILL/02271/2024-2025 | BP-24-25-585 | 19/11/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
232 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF KAMARPARA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001245/2023-2024 | 4495/ED | 23/11/2023 | 90 | PADMA ENGINEERING CO. | 21.49 | 0 | 0
233 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEPARA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001258/2023-2024 | 4504/ED | 23/11/2023 | 90 | GOENKA ENTERPRISE | 10.75 | 0 | 0
234 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04133/2023-2024 | 386 | 01/11/2023 | 0 | WBSEDCL | 5.36 | 0 | 0
235 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04201/2023-2024 | 402 | 09/11/2023 | 0 | WBSEDCL | 7.87 | 0 | 0
236 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Patul water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000091/2022-2023 | 3473/ED | 30/12/2022 | 901 | CINZANO | 20.51 | 0 | 90
237 | Electrical |  | Quotation for new service connection at Goswamimalipara (Aug.)[SM/18953] W/S Sch., T/W No. - III, Block - Polba-dadpur, under Dadpur CCC, WBSEDCL, Ref Id. - 503619160, dt. - 25-06-2024, Application No. - 5004116875. |  |  | BILL/01141/2024-2025 | 263 | 03/07/2024 | 0 | WBSEDCL | 9.13 | 0 | 0
238 | Electrical |  | Quotation for new service connection at Goswamimalipara (Aug.) [SM/18953] W/s Sch., T/W No. - IV, Village & P. O. - Shenet, Dt. - Hooghly under Dadpur CCC, WBSEDCL, Ref. Id. - 503669411, Dt. - 11-07-2024, Application No. - 5004243696 |  |  | BILL/01190/2024-2025 | 311 | 22/07/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
239 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of GOSWAMI MALIPARA Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001277/2023-2024 | 4517/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 90
240 | Electrical | Arambug Sub-Division | Additional Quotation of New Service Connection for Raghubati w/S Scheme,PH No-I, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18672) Application No-100000123537 Reference Id-860318457 | Assistant Engineer | Junior Engineer (Civill) | BILL/02307/2024-2025 | 606 | 05/12/2024 | 0 | WBSEDCL | 0.96 | 0 | 0
241 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Raghubati W/S. Sch.TW-I | Assistant Engineer | Junior Engineer (Civill) | BILL/04150/2023-2024 | 392 | 03/11/2023 | 0 | WBSEDCL | 5.08 | 0 | 0
242 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Raghubati W/S. Sch | Assistant Engineer | Junior Engineer (Civill) | BILL/06037/2023-2024 | 737 | 07/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
243 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Raghubati water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000844/2023-2024 | 3412/ED | 10/08/2023 | 541 | M/S NABIN GOPAL SENGUPTA | 20.36 | 0 | 50
244 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of BAIKUNTHAPUR piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001290/2023-2024 | 4522/ED | 23/11/2023 | 90 | TRIDENT ENTERPRISE | 22.03 | 0 | 0
245 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paba water supply scheme, T.W. No. III, Block: Goghat-II, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002575/2022-2023 | 2046/ED | 01/12/2022 | 90 | M/S G P ENTERPRISE | 11.11 | 0 | 30
246 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HARADITYA Piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001292/2023-2024 | 4524/ED | 23/11/2023 | 90 | WIZARDTECH SOLUTION | 21.49 | 0 | 0
247 | Electrical |  | Additional quotation for Baksa w/s scheme against application no.- 5003987334 Ref ID: 860295228 |  |  | BILL/06497/2023-2024 | 13 | 04/04/2024 | 0 | WBSEDCL | 0.93 | 0 | 0
248 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baksa water supply scheme, T.W. No. I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001985/2023-2024 | 117/ED | 15/01/2024 | 90 | M.S.C. ENTERPRISE | 10.24 | 0 | 80
249 | Electrical | Chinsuria Sub-Division | Lokabati PH__II Water supply Scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05987/2023-2024 | 724 | 05/02/2024 | 0 | WBSEDCL | 17.53 | 0 | 0
250 | Electrical | Chinsuria Sub-Division | Lokabati PH__I Water supply Scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05988/2023-2024 | 725 | 05/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
251 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Lokabati water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2022-2023 | 3469/ED | 30/12/2022 | 945 | INDRANI ENTERPRISE | 22.4 | 0 | 75
252 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Basubati W/S Sch, TW-I (Head Work site), Dist. Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01916/2023-2024 | 90 | 13/07/2023 | 0 | WBSEDCL | 3.85 | 0 | 0
253 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Basubati W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04512/2023-2024 | 553 | 21/12/2023 | 0 | WBSEDCL | 2.59 | 0 | 0
254 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000130/2022-2023 | 3484/ED | 30/12/2022 | 90 | ASHUTOSH DAS & CO. | 23.01 | 0 | 90
255 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Basubati water supply scheme, T.W. No. III, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000873/2023-2024 | 3446/ED | 11/08/2023 | 90 | BISALAXMI ENTERPRISE | 11.5 | 0 | 0
256 | Electrical | RWS Howrah Sub-Division | Shifting of LT OH Line | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | BILL/00212/2022-2023 | 144 | 30/01/2023 | 0 | WBSEDCL | 0.27 | 0 | 0
257 | Electrical | RWS Howrah Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works for Kalyanpur Birampur W/S. Sch.PH-II | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000048/2022-2023 | 2101/HMSD | 24/11/2022 | 30 | DIPA CHHETRI | 4.25 | 0 | 0
258 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalyanpur Birampur water supply scheme, P.H. No. - I (Replacement Tubewell), Block Bagnan-I District - Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000064/2022-2023 | 2100/HMSD | 24/11/2022 | 30 | OSMAN SEKH | 4.12 | 0 | 0
259 | Electrical | RWS Howrah Sub-Division | Supply, delivery of electro mechanical equipments for Kalyanpur Birampur water supply scheme, P.H. No. I (Replacement tubewell), District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000068/2022-2023 | 35/HMSD | 05/01/2023 | 30 | J.K. ENGINEERING CO. | 2.87 | 0 | 0
260 | Electrical | RWS Howrah Sub-Division | Supply, delivery of electro mechanical equipments for Kalyanpur Birampur water supply scheme, P.H. No. II (Replacement tubewell), District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000069/2022-2023 | 36/HMSD | 05/01/2023 | 30 | P.K. ENTERPRISE | 3.55 | 0 | 0
261 | Electrical | RWS Howrah Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Kalyanpur Birampur water supply scheme, P.H. No.-II, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/001426/2021-2022 | 1245/HMSD | 14/07/2021 | 21 | A.G. ENTERPRISE | 2.74 | 0 | 0
262 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05129/2023-2024 | 693 | 22/01/2024 | 0 | WBSEDCL | 11.8 | 0 | 0
263 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05131/2023-2024 | 694 | 22/01/2024 | 0 | WBSEDCL | 5.69 | 0 | 0
264 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Durgapur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000146/2022-2023 | 3489/ED | 30/12/2022 | 90 | M/S CHANDIMATA ELECTRICALS | 20.38 | 0 | 35
265 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service connection of Bhagabatipur W/s Scheme, PH No-I Dist-Hooghly under Electrical Division ,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02003/2023-2024 | 103 | 19/07/2023 | 0 | WBSEDCL | 2.6 | 0 | 0
266 | Electrical | Howrah Mechanical Sub-Division | Additional Quotation of New Service Connection for Bhagabatipur w/s Scheme,Tw no-I,Block-Haripal,Dist-Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/03884/2023-2024 | 296 | 21/09/2023 | 0 | WBSEDCL | 0.48 | 0 | 0
267 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Bhagabatipur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/06152/2023-2024 | 793 | 22/02/2024 | 0 | WBSEDCL | 12.75 | 0 | 0
268 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhagabatipur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000077/2022-2023 | 3459/ED | 30/12/2022 | 90 | NITESH MANAGEMENT | 10.16 | 0 | 40
269 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme, PH No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03686/2023-2024 | 227 | 01/09/2023 | 0 | WBSEDCL | 4.93 | 0 | 0
270 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Bhanjipur w/s scheme PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03689/2023-2024 | 228 | 01/09/2023 | 0 | WBSEDCL | 4.65 | 0 | 0
271 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Bhanjipur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04415/2023-2024 | 493 | 07/12/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
272 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhanjipur water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000078/2022-2023 | 3460/ED | 30/12/2022 | 90 | M.S. ENTERPRISE | 22.27 | 0 | 100
273 | Electrical | Howrah Mechanical Sub-Division | New Service Connection at Harat Piped W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02741/2023-2024 | 170 | 09/08/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
274 | Electrical | Howrah Mechanical Sub-Division | NEW SERVICE CONNECTION | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02746/2023-2024 |  | 08/08/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
275 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection for Harat Water Supply Scheme,TW No-II,Block-Haripal, Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/03621/2023-2024 | 224 | 28/08/2023 | 0 | WBSEDCL | 5.57 | 0 | 0
276 | Electrical | Howrah Mechanical Sub-Division | Additional Quotation Of New Service Connection for Harat w/s Scheme,PH No-I,Block-Haripal,Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/04079/2023-2024 | 349 | 11/10/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
277 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection for Harat w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/11290) Application No-5003979859 Reference Id-503541273 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/06474/2023-2024 | 902 | 19/03/2024 | 0 | WBSEDCL | 3.73 | 0 | 0
278 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Harat water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000083/2022-2023 | 3465/ED | 30/12/2022 | 90 | M/S A.K BANERJEE | 21.49 | 0 | 30
279 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at DhaniakhaliZ-II, PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00805/2023-2024 | 57 | 02/06/2023 | 0 | WBSEDCL | 5.86 | 0 | 0
280 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dhaniakhali W/S. Sch. W/S. Sch. Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02592/2023-2024 | 155 | 03/08/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
281 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000206/2022-2023 | 833/ED | 14/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 59
282 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Anandapur W/S. Sch. TW-III & IV, Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01816/2022-2023 | 205 | 21/03/2023 | 0 | WBSEDCL | 1.46 | 0 | 0
283 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anandapur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000048/2023-2024 | 1734/ED | 19/04/2023 | 90 | P.K. ENGINEERING | 21.49 | 0 | 70
284 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Soaluk T/W-IV W/S scheme under Electrical Division PHE Dte. (SM/11467) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01614/2024-2025 | 376 | 12/08/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
285 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Aug. of Soaluk W/S. Sch. PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01873/2022-2023 | 208 | 22/03/2023 | 0 | WBSEDCL | 3 | 0 | 0
286 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Soaluk water supply scheme, T.W. No.- I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000114/2022-2023 | 668/ED | 02/02/2023 | 90 | M/S BIPUL BANERJEE | 10.96 | 0 | 100
287 | Electrical | Arambug Sub-Division | Replacement of some electrical devices, equipments and items, outdoor lighting, voltage corrector etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000316/2022-2023 | 492/HMSD | 02/03/2023 | 30 | RADHARANI ENTERPRISE | 2.99 | 0 | 100
288 | Electrical | Arambug Sub-Division | Replacement of some electrical devices and equipments like mcc cum pdb etc. including allied works for Soaluk water supply scheme, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000318/2022-2023 | 494/HMSD | 02/03/2023 | 30 | N.S. TRADING | 4.21 | 0 | 0
289 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002473/2023-2024 | 334/ED | 21/02/2024 | 435 | DEY ENTERPRISE | 10.43 | 0 | 35
290 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Atisara W/s Sch.,T/W - I, Block - Singur | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02063/2023-2024 | 115 | 20/07/2023 | 0 | WBSEDCL | 5.59 | 0 | 0
291 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Atisara W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04502/2023-2024 | 543 | 19/12/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
292 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Atisara water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000123/2022-2023 | 3479/ED | 30/12/2022 | 90 | R.N.S. TRADING | 23.26 | 0 | 49
293 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
294 | Electrical | Arambug Sub-Division | Supply & Delivery of standby submersible pumping machinery for Kapsit & others W/S. Sch. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | ORD/001120/2021-2022 | 556/HMSD | 17/03/2022 | 90 | DITHI ENTERPRISE | 0.79 | 0 | 0
295 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
296 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
297 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04365/2023-2024 | 459 | 01/12/2023 | 0 | WBSEDCL | 6.9 | 0 | 0
298 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Radhaballavpur PWSS, Zone-II, TW - II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04484/2023-2024 | 530 | 15/12/2023 | 0 | WBSEDCL | 13 | 0 | 0
299 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Radhaballavpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000180/2022-2023 | 773/ED | 09/02/2023 | 812 | KARTICK BAL | 20.62 | 0 | 30
300 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttar Babnan W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05980/2023-2024 | 732 | 05/02/2024 | 0 | WBSEDCL | 10.71 | 0 | 0
301 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Uttar Babnan W/S. Sch. TW-I,Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05981/2023-2024 | 731 | 05/02/2024 | 0 | WBSEDCL | 0.35 | 0 | 0
302 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Babnan water supply scheme, Zone-I, T.W. No.- I, II & III and Zone-II, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000282/2022-2023 | 932/ED | 22/02/2023 | 900 | DEY ENTERPRISE | 50.9 | 0 | 90
303 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Haripur W/S Sch.[SM/14122], Block - Polba-Dadpur, WBSEDCL, Ref. Id. - 503619164, Dt. - 25/04/2024, Application No. - 5004117110 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00475/2024-2025 | 135 | 17/05/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
304 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Haripur W/S Sch., T/W No. - II, Block - Polba-dadpur, Dist. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02328/2023-2024 | 147 | 26/07/2023 | 0 | WBSEDCL | 2.9 | 0 | 0
305 | Electrical | Chinsuria Sub-Division | Quotation for new service Connection at Haripur W/S Sch., T/W No. - I, Block - Polba-Dadpur, District - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03711/2023-2024 | 252 | 05/09/2023 | 0 | WBSEDCL | 5.79 | 0 | 0
306 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001215/2022-2023 | 3490 / ED | 30/12/2022 | 90 | P.K. ENGINEERING | 20.24 | 0 | 98
307 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kota w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under ED,PHE Dte (SM/13320) Application No-5004009660 Reference Id-503561831 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06048/2023-2024 | 742 | 08/02/2024 | 0 | WBSEDCL | 3.97 | 0 | 0
308 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for KOTA w/s scheme PH No-2 Block-Goghat-I Dist-Hooghly under ED,PHE Dte. (SM/13320) Application No-5004018773 Reference Id-503565232 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06101/2023-2024 | 765 | 16/02/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
309 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kota water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000174/2022-2023 | 767/ED | 09/02/2023 | 919 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 21.06 | 0 | 40
310 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KOTA PIPED W/S SCHEME, T.W. No. III & IV, Block: Goghat-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002505/2023-2024 | 421/ED | 29/02/2024 | 550 | BISALAXMI ENTERPRISE | 21.48 | 0 | 30
311 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Shyam Chak Mini PWSS | AE/SADAR |  | BILL/05016/2023-2024 | 687 | 19/01/2024 | 0 | WBSEDCL | 0.09 | 0 | 0
312 | Electrical | Howrah Mechanical Sub-Division | NEW SERVICE CONNECTION AT SANKHALI PWSS P.H No.-I | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02907/2023-2024 | 205 | 24/08/2023 | 0 | WBSEDCL | 3.2 | 0 | 0
313 | Electrical | Howrah Mechanical Sub-Division | NEW SERVICE CONNECTION AT SANKHALI PWSS P.H No.-II | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02908/2023-2024 | 207 | 24/08/2023 | 0 | WBSEDCL | 3.51 | 0 | 0
314 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sankhali water supply scheme, T.W. No.- I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000260/2022-2023 | 927/ED | 22/02/2023 | 45 | SRI KRISHNA NIRMAN | 20.35 | 0 | 90
315 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Sankhanagar Chakbansberia W/S Sch. , T/W No. - I(Aug.), Block - Chinsurah- Mogra, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04082/2023-2024 |  | 10/10/2023 | 0 | WBSEDCL | 6.63 | 0 | 0
316 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Sankhanagar Chak Bansberia W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04090/2023-2024 | 355 | 12/10/2023 | 0 | WBSEDCL | 6.63 | 0 | 0
317 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sankhanagar & Chakbasnberia water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000022/2023-2024 | 1699/ED | 18/04/2023 | 90 | EMCON | 11.4 | 0 | 80
318 | Electrical | Chinsuria Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Sankhanagar Chawk Bansberia w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000315/2022-2023 | 491/HMSD | 02/03/2023 | 30 | S.B.ENTERPRISE | 2.49 | 0 | 1
319 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001388/2023-2024 | 4738/ED | 15/12/2023 | 90 | S. DUTTA | 10.74 | 0 | 90
320 | Electrical | Chinsuria Sub-Division | New Service connection quotation charges for ph-4 Gurap pwss | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04473/2023-2024 | 523 | 12/12/2023 | 0 | WBSEDCL | 10.02 | 0 | 0
321 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gurap water supply scheme, T.W. No. I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000017/2023-2024 | 1633/ED | 11/04/2023 | 90 | DITHI ENTERPRISE | 11.4 | 0 | 70
322 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
323 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Senpur Dwitiya W/S. Sch. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | BILL/05982/2023-2024 | 729 | 05/02/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
324 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Borhal W/S. Sch. PH-2 & 3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00001/2023-2024 | 26 | 11/05/2023 | 0 | WBSEDCL | 11.8 | 0 | 0
325 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-II) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000983/2023-2024 | 1632/ED | 11/04/2023 | 90 | INDTECH ASSOCIATES. | 22.81 | 0 | 85
326 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- II, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038623 Ref. ID- 503577402 SM Code- 15886 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06230/2023-2024 | 831 | 04/03/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
327 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- I, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038621 Ref. ID- 503577388 SM Code- 15886 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06231/2023-2024 | 832 | 04/03/2024 | 0 | WBSEDCL | 6 | 0 | 0
328 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.( SM/158668) Application No-5004061104 Reference Id-503590562 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06457/2023-2024 | 886 | 15/03/2024 | 0 | WBSEDCL | 4.62 | 0 | 0
329 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tirol (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000031/2023-2024 | 1708/ED | 18/04/2023 | 90 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 0 | 40
330 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for TIROL PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000166/2024-2025 | 1189/ED | 14/06/2024 | 271 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 10.73 | 0 | 0
331 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Gar Mandaran w/s Scheme,Zone-II,PH no-III Block-Goghat-II Dist-Hooghly under Electrical division,PHe Dte.(SM/15887) Application No-5004498949 Reference Id-503815611 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02604/2024-2025 | 638 | 18/12/2024 | 0 | WBSEDCL | 9.44 | 0 | 0
332 | Electrical | Arambug Sub-Division | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-I,Block-Goghat-I Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03700/2023-2024 | 241 | 01/09/2023 | 0 | WBSEDCL | 4.17 | 0 | 0
333 | Electrical | Arambug Sub-Division | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-II Block-Goghat-II, Dist-Hooghly under Electrical Division ,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03701/2023-2024 | 242 | 01/09/2023 | 0 | WBSEDCL | 5.35 | 0 | 0
334 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000029/2023-2024 | 1706/ED | 18/04/2023 | 805 | UNITED TRADERS | 21.47 | 0 | 30
335 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000877/2023-2024 | 3450/ED | 11/08/2023 | 874 | M.D ENTERPRISE | 21.44 | 0 | 20
336 | Electrical | RWS Howrah Sub-Division | Quotation for Pole Shifting of Jhikira w/s Scheme,PH No-I under Electrical Division,PHE Dte(SM/11719) Application Id-100000105833. Reference Id-860297815. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | BILL/00234/2024-2025 | 84 | 22/04/2024 | 0 | WBSEDCL | 0.36 | 0 | 0
337 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | BILL/04630/2023-2024 | 619 | 08/01/2024 | 0 | WBSEDCL | 3.86 | 0 | 0
338 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Jhikira W/S. Sch. PH-III | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | BILL/05720/2023-2024 | 709 | 25/01/2024 | 0 | WBSEDCL | 12.37 | 0 | 0
339 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jhikira water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000256/2022-2023 | 923/ED | 22/02/2023 | 584 | STANDARD ELECTRICALS | 22.61 | 0 | 70
340 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JHIKIRA water supply scheme, TW No. III, Block: Amta-II, District - Howrah under Electrical Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/003101/2024-2025 | 486/ED | 18/03/2025 | 90 | STANDARD ELECTRICALS | 11.3 | 0 | 0
341 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bali w/s Scheme, PH No-3 Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15803) Application No-5004191492 Reference Id-503647819. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00537/2024-2025 |  | 29/05/2024 | 0 | WBSEDCL | 7.09 | 0 | 0
342 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bali water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001144/2022-2023 | 1496/ED | 28/03/2023 | 795 | RUBY ENTERPRISE. | 10.75 | 0 | 30
343 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04593/2023-2024 | 594 | 29/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0
344 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patul water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000004/2023-2024 | 1620/ED | 11/04/2023 | 720 | NITESH MANAGEMENT | 10.74 | 0 | 50
345 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Radhaballavpur w/s Scheme, TW No-3 Dist- Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02131/2023-2024 | 117 | 20/07/2023 | 0 | WBSEDCL | 2.82 | 0 | 0
346 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Radhaballabpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000006/2023-2024 | 1622/ED | 11/04/2023 | 90 | M/S, GHOSH ENTERPRISE | 10.74 | 0 | 40
347 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Kola W/S. Sch. " | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04320/2023-2024 | 440 | 23/11/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
348 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kola water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000018/2023-2024 | 1634/ED | 11/04/2023 | 90 | BIJAN ENTERPRISE | 11.4 | 0 | 95
349 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kapsit w/s Scheme, PH No-3 Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004276344 Reference Id-503683335. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01142/2024-2025 | 264 | 03/07/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
350 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kapsit w/s Scheme,PH No-IV Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004320167 Reference Id- 503705436 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01375/2024-2025 | 335 | 30/07/2024 | 0 | WBSEDCL | 11.46 | 0 | 0
351 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kapsit water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001152/2022-2023 | 1504/ED | 28/03/2023 | 888 | A.K. ENTERPRISE | 21.93 | 0 | 100
352 | Electrical | Arambug Sub-Division | Quotaion of New Service Connection for Mayapur w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15791) Application No-5004314243 Reference Id-503702554 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01355/2024-2025 | 334 | 30/07/2024 | 0 | WBSEDCL | 7.67 | 0 | 0
353 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Mayapur PWSS, Zone-I, TW - I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04372/2023-2024 | 462 | 01/12/2023 | 0 | WBSEDCL | 4.9 | 0 | 0
354 | Electrical | Arambug Sub-Division | Quotation for New Service Connection at Mayapur W/S. Sch. Z=I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04612/2023-2024 | 611 | 04/01/2024 | 0 | WBSEDCL | 5.8 | 0 | 0
355 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-I) water supply scheme, T.W. No. I, II, III & IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000034/2023-2024 | 1711/ED | 18/04/2023 | 90 | D. K. ELECTRIC | 40.97 | 0 | 0
356 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jagatpur w/s Scheme,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/16122) Application No-5004134007 Reference Id-503627506 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01002/2024-2025 | 262 | 03/07/2024 | 0 | WBSEDCL | 12.35 | 0 | 0
357 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jagatpur w/s Scheme, TW No-4 Block-Khanakul-II,Dist-Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03860/2023-2024 | 308 | 27/09/2023 | 0 | WBSEDCL | 7.56 | 0 | 0
358 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Jagatpur w/s Scheme, TW no-5 Block-Khanakul-II,Dist-Hooghly under Electrical division,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03861/2023-2024 | 289 | 20/09/2023 | 0 | WBSEDCL | 6.65 | 0 | 0
359 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jagatpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000030/2023-2024 | 1707/ED | 18/04/2023 | 90 | GHOSE ENGINEERING SYNDICATE | 21.93 | 0 | 40
360 | Electrical | Arambug Sub-Division | Hire Charges Bill of V.No.- WB-04G-2822 for official use of Electrical Division PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001029/2023-2024 | 591_AE-1_ED | 21/08/2023 | 7 | DASHRATH KUMAR PRAJAPATI | 5 | 0 | 10
361 | Electrical | Arambug Sub-Division | Hire Charges Bill for official use office of the Assistant Engineer -I PHED | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002498/2022-2023 | 203_ae1 | 27/03/2023 | 365 | DASHRATH KUMAR PRAJAPATI | 5 | 0 | 1
362 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Rajballavbati W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04221/2023-2024 | 412 | 09/11/2023 | 0 | WBSEDCL | 6.55 | 0 | 0
363 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Rajballabhbati PWSS, TW - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04485/2023-2024 | 528 | 15/12/2023 | 0 | WBSEDCL | 1.71 | 0 | 0
364 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajaballabhbati water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000033/2023-2024 | 1710/ED | 18/04/2023 | 714 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 20.5 | 0 | 20
365 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Ramnagar W/s scheme, PH No-I, District-Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01919/2023-2024 | 93 | 13/07/2023 | 0 | WBSEDCL | 11.28 | 0 | 0
366 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Ramnagar W/s Scheme, PH No-II, District-Hooghly Under Electrical Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01920/2023-2024 | 94 | 13/07/2023 | 0 | WBSEDCL | 10.9 | 0 | 0
367 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Ramnagar w/s Scheme,PH No-3,Block-Arambag,Dist-Hooghly under Electrical Division, PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04078/2023-2024 | 346 | 11/10/2023 | 0 | WBSEDCL | 12.88 | 0 | 0
368 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Salepue Paschimpara Ramnagar W/S. Sch. TW-3 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04316/2023-2024 | 428 | 17/11/2023 | 0 | WBSEDCL | 1.21 | 0 | 0
369 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ramnagar water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000054/2023-2024 | 1798/ED | 24/04/2023 | 90 | C.M. ENTERPRISE | 21.38 | 0 | 50
370 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ramnagar water supply scheme, T.W. No. III, Block: Arambag, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001384/2023-2024 | 4734/ED | 15/12/2023 | 144 | H.K.DAS & CO. | 10.76 | 0 | 30
371 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sinhal Patan water supply Scheme [SM/18103], T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. No. - 503588851, Dt. - 07-03-2024, Application No. - 5004057413 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06279/2023-2024 | 877 | 13/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0
372 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sinhal Patnan water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000075/2023-2024 | 1931/ED | 15/05/2023 | 691 | H.K.DAS & CO. | 22.34 | 0 | 99
373 | Electrical | Chandannagar Sub-Division | Quotation money deposition for new service connection at Kamarkundu w/s scheme, Zone- VI, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004229746 Reference ID- 503663995 SM Code- 18397 | Assistant Engineer (Civil) |  | BILL/00822/2024-2025 | 218 | 18/06/2024 | 0 | WBSEDCL | 4.94 | 0 | 0
374 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Kamarkundu W/S Sch., Zone - V, T/W No. - I,[SM/18397], under Singur CCC, WBSEDCL, Ref. Id. - 503706067, Dt. - 30-07-2024, Application No. - 5004320836 | Assistant Engineer (Civil) |  | BILL/01591/2024-2025 | 356 | 07/08/2024 | 0 | WBSEDCL | 7.25 | 0 | 0
375 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-VI, TW-III | Assistant Engineer (Civil) |  | BILL/04570/2023-2024 | 576 | 27/12/2023 | 0 | WBSEDCL | 3.64 | 0 | 0
376 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-I | Assistant Engineer (Civil) |  | BILL/04571/2023-2024 | 575 | 27/12/2023 | 0 | WBSEDCL | 4.52 | 0 | 0
377 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch.TW-II | Assistant Engineer (Civil) |  | BILL/04585/2023-2024 | 596A | 29/12/2023 | 0 | WBSEDCL | 3.79 | 0 | 0
378 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Kamarkundu PWSS, Zone-VI, TW - II | Assistant Engineer (Civil) |  | BILL/04586/2023-2024 | 589 | 28/12/2023 | 0 | WBSEDCL | 3.79 | 0 | 0
379 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-II | Assistant Engineer (Civil) |  | BILL/04854/2023-2024 | 673 | 17/01/2024 | 0 | WBSEDCL | 6.51 | 0 | 0
380 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I | Assistant Engineer (Civil) |  | BILL/05906/2023-2024 | 720 | 31/01/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
381 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-IV | Assistant Engineer (Civil) |  | BILL/05910/2023-2024 | 716 | 29/01/2024 | 0 | WBSEDCL | 4.87 | 0 | 0
382 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-III | Assistant Engineer (Civil) |  | BILL/05911/2023-2024 | 719 | 29/01/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
383 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I | Assistant Engineer (Civil) |  | BILL/05913/2023-2024 | 718 | 29/01/2024 | 0 | WBSEDCL | 3.02 | 0 | 0
384 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-VI | Assistant Engineer (Civil) |  | BILL/05915/2023-2024 | 717 | 29/01/2024 | 0 | WBSEDCL | 4.81 | 0 | 0
385 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-III | Assistant Engineer (Civil) |  | BILL/05985/2023-2024 | 730 | 05/02/2024 | 0 | CESC LIMITED. | 5.17 | 0 | 0
386 | Electrical | Chandannagar Sub-Division | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-VII | Assistant Engineer (Civil) |  | BILL/06106/2023-2024 | 771 | 19/02/2024 | 0 | WBSEDCL | 4.87 | 0 | 0
387 | Electrical | Chandannagar Sub-Division | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-I, Z-VII | Assistant Engineer (Civil) |  | BILL/06107/2023-2024 | 773 | 19/02/2024 | 0 | WBSEDCL | 4.67 | 0 | 0
388 | Electrical | Chandannagar Sub-Division | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-IV | Assistant Engineer (Civil) |  | BILL/06108/2023-2024 | 772 | 19/02/2024 | 0 | WBSEDCL | 7.2 | 0 | 0
389 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamarkundu water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/001864/2023-2024 | 50/ED | 05/01/2024 | 731 | DAS ENTERPRISE | 172.16 | 0 | 55
390 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Kapasaria w/s scheme, Zone- I, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 100000120622 Reference ID- 860314252 SM Code- 18624 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02124/2024-2025 | 559 | 11/11/2024 | 0 | WBSEDCL | 0.19 | 0 | 0
391 | Electrical | Srirampur Sub-Division | "Quotation Bill for New Service Connection at Kapasaria W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02923/2023-2024 | 211 | 24/08/2023 | 0 | WBSEDCL | 17.21 | 0 | 0
392 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. PH-III & IV, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04024/2023-2024 | 317 & 318 | 03/10/2023 | 0 | WBSEDCL | 6.88 | 0 | 0
393 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. Z-II, TW-IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04608/2023-2024 | 608 | 04/01/2024 | 0 | WBSEDCL | 4.82 | 0 | 0
394 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No. V & VI, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000881/2023-2024 | 3454/ED | 11/08/2023 | 90 | R.N.S. TRADING | 20.83 | 0 | 0
395 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No.- I, II, III & IV, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000918/2023-2024 | 3589/ED | 28/08/2023 | 90 | R.N.S. TRADING | 41.38 | 0 | 90
396 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. IX, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003086/2024-2025 | 480/ED | 18/03/2025 | 90 | SWAPAN ENTERPRISE | 11.3 | 0 | 0
397 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VIII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003090/2024-2025 | 481/ED | 18/03/2025 | 90 | ANUPAMA ENGINEERING WORKS | 11.3 | 0 | 0
398 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003095/2024-2025 | 482/ED | 18/03/2025 | 90 | S.P. CONSTRUCTION | 11.42 | 0 | 0
399 | Electrical | Srirampur Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003739/2024-2025 | 331_AE-I/ED | 05/02/2025 | 176 | SWARUP LAL SARKAR | 0.84 | 0 | 0
400 | Electrical | Howrah Mechanical Sub-Division | Quotation for New Service Connection of Haripal W/S scheme(Aug),Zone-II,PH No-II Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00730/2023-2024 | 16 | 02/05/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
401 | Electrical | Howrah Mechanical Sub-Division | "Quotation Bill for New Service Connection at of Haripal W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/01913/2022-2023 | 01 | 11/04/2023 | 0 | WBSEDCL | 5.42 | 0 | 0
402 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Haripal water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000213/2022-2023 | 840/ED | 14/02/2023 | 90 | DAS ENTERPRISE | 32.23 | 0 | 50
403 | Electrical | Howrah Mechanical Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer Mechanical Circle-II, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000946/2023-2024 | 1381/HMSD | 14/06/2023 | 184 | DEBASHISH GHOSH | 0.87 | 0 | 20
404 | Electrical |  | Quotation money deposition for new service connection at Nakubar 3 w/s scheme, Dist.-Howrah under PHE Dte. Application No- 1007699722 Reference ID- 106569868 SM Code- 18847 |  |  | BILL/00513/2024-2025 | 176 | 30/05/2024 | 0 | WBSEDCL | 9.56 | 0 | 0
405 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Nakubar Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001306/2023-2024 | 4539/ED | 23/11/2023 | 494 | DEY ENTERPRISE | 21.5 | 0 | 40
406 | Electrical |  | Additional Quotation money for new service connection of Ajangachi w/s scheme, PH No. 2, Block- Amta-II, Howrah Application ID: 100000103588 Reference ID: 860295388 SM/18561 |  |  | BILL/00033/2024-2025 | 25 | 05/04/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
407 | Electrical |  | Quotation Bill for New Service Connection at Ajangachi W/S. Sch.PH-I |  |  | BILL/05722/2023-2024 | 707 | 25/01/2024 | 0 | WBSEDCL | 10.69 | 0 | 0
408 | Electrical |  | Quotation for new service connection at TW no. 2 of Ajangachi w/s scheme, Amta-II, Howrah Application No. 1007513650 Ref id:106459509 SM/18561 |  |  | BILL/06074/2023-2024 | 749 | 16/02/2024 | 0 | WBSEDCL | 4.16 | 0 | 0
409 | Electrical |  | Quotation for new service connection at TW no. 2 of Ajangachi w/s scheme, Amta-II, Howrah |  |  | BILL/06076/2023-2024 | 750 | 16/02/2024 | 0 | WBSEDCL | 4.33 | 0 | 0
410 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ajangachhi water supply scheme, T.W. No.- I, II & III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000924/2023-2024 | 3595/ED | 28/08/2023 | 581 | P.K. ENGINEERING | 32.24 | 0 | 60
411 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for AJANGACHI water supply scheme, TW No. IV, Block: Amta-II, District - Howrah under Electrical Division PHE Dte. |  |  | ORD/003105/2024-2025 | 488/ED | 18/03/2025 | 90 | MAA KALI ENTERPRISE | 11.29 | 0 | 0
412 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-I, Z-II | Assistant Engineer | Junior Engineer (Civill) | BILL/04317/2023-2024 | 426 | 17/11/2023 | 0 | WBSEDCL | 5.3 | 0 | 0
413 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-II, Z-II, | Assistant Engineer | Junior Engineer (Civill) | BILL/04318/2023-2024 | 425 | 17/11/2023 | 0 | WBSEDCL | 3.94 | 0 | 0
414 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000190/2024-2025 | 1205/ED | 14/06/2024 | 90 | SWAPAN ENTERPRISE | 10.75 | 0 | 0
415 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. V, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000193/2024-2025 | 1207/ED | 14/06/2024 | 90 | D.S. ENTERPRISE | 10.74 | 0 | 0
416 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnanagar water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000992/2023-2024 | 3788/ED | 26/09/2023 | 90 | GLACIER ENGINEERING CO. | 21.75 | 0 | 40
417 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-II | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | BILL/04581/2023-2024 | 586 | 28/12/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
418 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-I | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | BILL/04582/2023-2024 | 587 | 28/12/2023 | 0 | WBSEDCL | 3.95 | 0 | 0
419 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Narayanpur water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | ORD/000819/2023-2024 | 3175/ED | 28/07/2023 | 704 | M/S A.K BANERJEE | 20.35 | 0 | 30
420 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Sarda Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001299/2023-2024 | 4532/ED | 23/11/2023 | 90 | S.B.ENTERPRISE | 10.74 | 0 | 0
421 | Electrical |  | Supply delivery and installation of Chlorinator for Sarda w/s scheme PH No. IV District Howrah under Electrical Division, PHE dte. |  |  | ORD/002568/2022-2023 | 721/HMSD | 23/03/2023 | 7 | TRIO CONCERN | 0.8 | 0 | 100
422 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Islampur (Replacement) water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/000109/2022-2023 | 711/ED | 03/02/2023 | 90 | T.N. BANERJEE | 21.42 | 0 | 1
423 | Electrical | Howrah Sadar Sub-Division | Car hiring & fuel bill for the month of July 2023 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/000828/2023-2024 | 0444_0445_0447 | 31/07/2023 | 31 | JAMECO AGENCIES PRIVATE LIMITED. | 0.73 | 0 | 5
424 | Electrical | Howrah Sadar Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/000829/2023-2024 | 958/HMSD | 20/04/2023 | 184 | ARINDAM AUDDY | 0.15 | 0 | 5
425 | Electrical | Howrah Sadar Sub-Division | Hire charges bill of vehicle no. WB04G2822 for the month of july 2023 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/002117/2022-2023 | 203_AE_I_ED | 23/03/2023 | 31 | DASHRATH KUMAR PRAJAPATI | 0.15 | 0 | 5
426 | Electrical | Howrah Sadar Sub-Division | Car hiring bill for Car No. WB15C5554 for the month of July 2023 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/002118/2022-2023 | 215_AE_II_ED | 24/03/2023 | 31 | DILIP KUMAR GHOSH | 0.15 | 0 | 5
427 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer |  | ORD/000863/2023-2024 | 3435/ED | 11/08/2023 | 90 | ANJAN ENTERPRISE | 21.5 | 0 | 0
428 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer |  | ORD/000925/2023-2024 | 3596/ED | 28/08/2023 | 90 | ANJAN ENTERPRISE | 21.5 | 0 | 0
429 | Electrical |  | Quotation for New Service Connection at Sherpur W/S. Sch. PH-I, Amta-I |  |  | BILL/04662/2023-2024 | 643 | 09/01/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
430 | Electrical |  | Quotation for New Service Connection at Sherpur W/S. Sch. PH-II, Amta-I |  |  | BILL/04663/2023-2024 | 640 | 09/01/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
431 | Electrical |  | Quotation for New Service Connection at Sherpur W/S. Sch. PH-III, Amta-I |  |  | BILL/04664/2023-2024 | 641 | 09/01/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
432 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sherpur water supply scheme, T.W. No. I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001888/2023-2024 | 63/ED | 08/01/2024 | 720 | MAA KALI ENTERPRISE | 34.21 | 0 | 60
433 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF CHOPA PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001210/2023-2024 | 4488/ED | 23/11/2023 | 90 | H.K.DAS & CO. | 21.88 | 0 | 0
434 | Electrical |  | Quotation for new service connection at Pownan W/S Sch. , (S. Aug.),[SM/18951] T/W No. - IV, Bihari Pally, Block - Polba-Dadpur, Dist. Hooghly, under SM/Polba, WBSEDCL, Ref. Id. - 503594866, Dt. - 02-04-2024, Application No. - 5004069653 |  |  | BILL/00077/2024-2025 | 39 | 09/04/2024 | 0 | WBSEDCL | 4.2 | 0 | 0
435 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04447/2023-2024 | 505 | 08/12/2023 | 0 | WBSEDCL | 3.8 | 0 | 0
436 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04448/2023-2024 | 503 | 08/12/2023 | 0 | WBSEDCL | 3.63 | 0 | 0
437 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04449/2023-2024 | 502 | 08/12/2023 | 0 | WBSEDCL | 6.86 | 0 | 0
438 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04450/2023-2024 | 504 | 08/12/2023 | 0 | WBSEDCL | 3.55 | 0 | 0
439 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000845/2023-2024 | 3413/ED | 10/08/2023 | 90 | MENAKA ENTERPRISE | 20.36 | 0 | 30
440 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000846/2023-2024 | 3414/ED | 10/08/2023 | 90 | S.P. CONSTRUCTION | 22.37 | 0 | 70
441 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HARISH CHAK piped Water Supply Scheme Block- Khanakul-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001289/2023-2024 | 4521/ED | 23/11/2023 | 90 | T S CONSTRUCTION | 21.47 | 0 | 0
442 | Electrical |  | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004377254 Reference ID- 503729858 SM Code- 18966 |  |  | BILL/02275/2024-2025 | BP-24-25-584 | 19/11/2024 | 0 | WBSEDCL | 5.2 | 0 | 0
443 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND PIPED W/S SCHEME, Zone - I, T.W. No. IV, Block: Chanditala - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000176/2024-2025 | 1200/ED | 14/06/2024 | 90 | NITESH MANAGEMENT | 10.72 | 0 | 0
444 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHIKRAND MINI PIPED W/S SCHEME, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000395/2024-2025 | 1479/ED | 25/07/2024 | 90 | SHIVAM ENTERPRISE | 7.58 | 0 | 0
445 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of CHIKRAND ZONE-I Piped Water Supply Scheme Block- Chanditala-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001294/2023-2024 | 4526/ED | 23/11/2023 | 90 | DEBJYOTI BASU | 10.75 | 0 | 90
446 | Electrical |  | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone- I, T.W. NO- I, Dist.-Hooghly under PHE Dte. Application No- 5004091751 Reference ID- 503606734 SM Code- 18778 |  |  | BILL/00160/2024-2025 | 69 | 16/04/2024 | 0 | WBSEDCL | 4.86 | 0 | 0
447 | Electrical |  | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004303896 Reference ID- 503696996 SM Code- 18778 |  |  | BILL/01404/2024-2025 | 348 | 31/07/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
448 | Electrical |  | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004303977 Reference ID- 503697862 SM Code- 18778 |  |  | BILL/01405/2024-2025 | 346 | 31/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
449 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000935/2023-2024 | 3614/ED | 29/08/2023 | 90 | M/S P.P. ELECTRICALS | 20.34 | 0 | 40
450 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000936/2023-2024 | 3615/ED | 29/08/2023 | 90 | INDRANI ENTERPRISE | 20.27 | 0 | 40
451 | Electrical | Ulberia Sub-Division | Quotation for new service connection for Hijlak Piped Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. (SM/13747), Reference Id- 106636949, Application no- 1007864377 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00918/2024-2025 | 257 | 03/07/2024 | 0 | WBSEDCL | 5.55 | 0 | 0
452 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hijlak water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000257/2022-2023 | 924/ED | 22/02/2023 | 922 | MENAKA ENTERPRISE | 20.27 | 0 | 40
453 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
454 | Electrical |  | Electric quot. of WBSEDCL for New service Connection of Bahadurpur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18944) |  |  | BILL/01966/2024-2025 | 477 | 01/10/2024 | 0 | WBSEDCL | 5.51 | 0 | 0
455 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BAHADURPUR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001263/2023-2024 | 4508/ED | 23/11/2023 | 90 | GLACIER ENGINEERING CO. | 21.74 | 0 | 35
456 | Electrical |  | Quotation of New Service Connection for Rajhato w/s Scheme, PH No-I,Block-Khanakul-II, Dist-Hooghly under Electrical Division,PHE Dte.(SM/18947) Application No-5003994230 Reference Id-503551061. |  |  | BILL/00673/2024-2025 | 200 | 10/06/2024 | 0 | WBSEDCL | 10.68 | 0 | 0
457 | Electrical |  | Quotation of New Service Connection for Rajhato w/s Scheme, PH No-II,Block-Khanakul-II, Dist-Hooghly under Electrical Division,PHE Dte.(SM/18947) Application No-5003994235 Reference Id-503551060. |  |  | BILL/00674/2024-2025 | 201 | 10/06/2024 | 0 | WBSEDCL | 10.3 | 0 | 0
458 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of RAJHATO Piped Water Supply Scheme Block- Khanakul-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001266/2023-2024 | 4511/ED | 23/11/2023 | 90 | PURUSHOTTAM ENTERPRISE | 21.47 | 0 | 30
459 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kanupat water supply scheme, T.W. No. II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/001125/2022-2023 | 1404/ED | 22/03/2023 | 90 | MAA KALI ENTERPRISE | 8.27 | 0 | 0
460 | Electrical | Ulberia Sub-Division | Hiring of diesel car | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | BILL/00005/2023-2024 | 05 | 13/04/2023 | 0 | TRIDIP SARKAR | 0.4 | 0 | 0
461 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000105/2022-2023 | 604/ED | 02/02/2023 | 90 | D. K. ELECTRIC | 10.99 | 0 | 0
462 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000243/2022-2023 | 2104/HMSD | 24/11/2022 | 30 | M.G. CONSTRUCTIONS & CO. | 4.94 | 0 | 0
463 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. III & IV, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000870/2023-2024 | 3443/ED | 11/08/2023 | 90 | D. K. ELECTRIC | 21.98 | 0 | 0
464 | Electrical | Ulberia Sub-Division | Hire Charges Bill of V.No.- WB-15C-5554 for office of the E/E. PHED | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/001027/2023-2024 | 591*AE-II/ED | 18/08/2023 | 365 | DILIP KUMAR GHOSH | 5 | 0 | 30
465 | Electrical | Ulberia Sub-Division | Supply, Delivery of actuator operated butterfly valvefor Augmentation of Surikhali W/S. Sch. Z-I, PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/002321/2022-2023 | 2156//HMSD | 30/11/2022 | 90 | M.G. CONSTRUCTIONS & CO. | 0.99 | 0 | 100
466 | Electrical | Ulberia Sub-Division | Hiring of 1 (One) Diesel Luxury Taxi on contract carriage for office of the Assistant Engineer-II, ED, PHED | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/002538/2022-2023 | 215_ae_ed | 24/03/2023 | 365 | DILIP KUMAR GHOSH | 5 | 0 | 20
467 | Electrical | Ulberia Sub-Division | Quotation for new service connection for Augmentation of Mankur Deulgram Water Supply Scheme, PH NO- II in the district Howrah under Electrical Division, PHE Dte. ( SM/09349), Reference Id- 106530323, Application no- 1007620510 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | BILL/00085/2024-2025 | 38 | 09/04/2024 | 0 | WBSEDCL | 10.4 | 0 | 0
468 | Electrical | Ulberia Sub-Division | Quotation for new service connection of Mankur Deulgram W/S. Sch. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | BILL/06047/2023-2024 | 745 | 08/02/2024 | 0 | WBSEDCL | 6.67 | 0 | 0
469 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mankur Deulgram water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000247/2022-2023 | 914/ ED | 22/02/2023 | 90 | A.G. ENTERPRISE | 23.02 | 0 | 50
470 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mankur Deulgram water supply scheme, T.W. No. III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000868/2023-2024 | 3441/ED | 11/08/2023 | 90 | M.S.C. ENTERPRISE | 11.5 | 0 | 0
471 | Electrical | Chinsuria Sub-Division | Fuel Charges Bil | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00736/2022-2023 | 147 | 31/01/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0
472 | Electrical | Chinsuria Sub-Division | Hiring Charges Bill | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00737/2022-2023 | 146 | 31/01/2023 | 0 | SUNIL RAJAK | 0.26 | 0 | 0
473 | Electrical | Chinsuria Sub-Division | Hire Charges Bill | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00738/2022-2023 | 138 | 20/01/2023 | 0 | DILIP KUMAR GHOSH | 0.15 | 0 | 0
474 | Electrical | Chinsuria Sub-Division | Fuel Charges Bill | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00739/2022-2023 | 137 | 20/01/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
475 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of S/P/M & other allied works for Rajhat W/S. Sch. Z-I, TW-III Dist-Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000063/2022-2023 | 1035/ED | 28/06/2022 | 90 | C.M. ENTERPRISE | 9.45 | 0 | 100
476 | Electrical | Chinsuria Sub-Division | Supply & installation of Automatic Chlorinator at Rajhat water supply scheme, Zone-I, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000597/2022-2023 | 1770/HMSD | 28/09/2022 | 7 | GANGULY ENGINEERING CO. | 0.8 | 0 | 100
477 | Electrical | Chinsuria Sub-Division | Supply & installation of LED board and outside display board for depicting details of Pump/Valve operators at Zone-I & II, P.H. No.-III of Rajhat w/s scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000598/2022-2023 | 2349/HMSD | 20/12/2022 | 10 | INDTECH ASSOCIATES. | 0.84 | 0 | 0
478 | Electrical | Chinsuria Sub-Division | Electric Supply | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001970/2022-2023 | 12 | 08/06/2022 | 0 | WBSEDCL | 7.29 | 0 | 0
479 | Electrical | Howrah Sadar Sub-Division | Quotation bill for new service connection at Aug. of Maju Khetra W/S. Sch. TW-III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00845/2022-2023 | 172 | 28/02/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
480 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Maju W/S. Sch. TW-IV | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00909/2022-2023 | 187 | 13/03/2023 | 0 | WBSEDCL | 3.06 | 0 | 0
481 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Maju water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000246/2022-2023 | 913/ED | 22/02/2023 | 90 | POLYCON ENGINEERS | 21.5 | 0 | 30
482 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAJU PIPED W/S SCHEME, T.W. No. I (Replacement), Block: Jagatballavpur, District - Howrah under JJM Program under Electrical Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000374/2024-2025 | 1461/ED | 25/07/2024 | 90 | BISALAXMI ENTERPRISE | 11.31 | 0 | 30
483 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Maju water supply scheme, T.W. No. III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000867/2023-2024 | 3440/ED | 11/08/2023 | 90 | POLYCON ENGINEERS | 10.75 | 0 | 40
484 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Janai w/s scheme, Zone- II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004099413 Reference ID- 503611354 SM Code- 09695 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00159/2024-2025 | 71 | 16/04/2024 | 0 | WBSEDCL | 4.56 | 0 | 0
485 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Janai W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00537/2022-2023 | 131 | 16/01/2023 | 0 | WBSEDCL | 0.68 | 0 | 0
486 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Janai water supply scheme, T.W. No.- I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000102/2022-2023 | 648/ED | 02/02/2023 | 90 | M/S BABUSONA ENTERPRISE | 10.74 | 0 | 100
487 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANAI PIPED W/S SCHEME, Zone - II, T.W. No. II, Block: Chanditala - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000171/2024-2025 | 1194/ED | 14/06/2024 | 413 | DAS ENTERPRISE | 10.73 | 0 | 30
488 | Electrical | Ulberia Sub-Division | Quotation bill for New Service connection at Aug. of Kanpur W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | BILL/00789/2022-2023 | 159 | 10/02/2023 | 0 | WBSEDCL | 6.45 | 0 | 0
489 | Electrical | Ulberia Sub-Division | Hire & Fuel Charges Bills | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | BILL/01890/2022-2023 | 230 | 29/03/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 1.72 | 0 | 0
490 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Kanpur W/S. Sch. TW-VI | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | BILL/04172/2023-2024 | 405 | 09/11/2023 | 0 | WBSEDCL | 3.34 | 0 | 0
491 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipment's etc. including allied works for Kanpur water supply scheme, T.W. No. I (Replacement tubewell), Block - Amta - I District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000062/2022-2023 | 2105/HMSD | 24/11/2022 | 30 | MOITRA ENGINEERING CO. | 4.82 | 0 | 0
492 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kanpur water supply scheme, T.W. No.-II, Block: Amta-I, District - Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/001387/2023-2024 | 4737/ED | 15/12/2023 | 90 | D. K. ELECTRIC | 10.74 | 0 | 100
493 | Electrical | Ulberia Sub-Division | Supply, Delivery & Installation of S/M/P & other E/M equipments etc. Including allied works for Kanpur W/S. Sch. Z-II, TW-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/002088/2022-2023 | 1549/ED | 20/09/2022 | 90 | D. K. ELECTRIC | 10.14 | 0 | 1
494 | Electrical | Ulberia Sub-Division | "Supply, Delivery & Installation of S/M/P & other E/M equipments etc. Including allied works for Kanpur W/S. Sch. Z-II, TW-II Howarah" | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/002114/2022-2023 | 1549//ED | 20/09/2022 | 7 | D. K. ELECTRIC | 10.13 | 0 | 1
495 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Haripur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 100000123497 Reference ID- 860318447 SM Code- 12250 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/02303/2024-2025 | BP-24-25-597 | 21/11/2024 | 0 | WBSEDCL | 2.22 | 0 | 0
496 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04443/2023-2024 | 501 | 08/12/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
497 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Haripur W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04444/2023-2024 | 508 | 08/12/2023 | 0 | WBSEDCL | 9.7 | 0 | 0
498 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000147/2022-2023 | 3490/ED | 30/12/2022 | 90 | P.K. ENGINEERING | 20.24 | 0 | 49
499 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haripur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000192/2022-2023 | 785/ED | 09/02/2023 | 90 | SRI KRISHNA NIRMAN | 20.26 | 0 | 65
500 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Hasnan W/S Sch., T/W No. - I, Block - Polba-Dadpur, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03712/2023-2024 | 255 | 05/09/2023 | 0 | WBSEDCL | 12.17 | 0 | 0
501 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Hasnan W/S Sch. , T/W No - II, Block- Polba-Dadpur, Dist - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03713/2023-2024 | 254 | 05/09/2023 | 0 | WBSEDCL | 4.01 | 0 | 0
502 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba-Dadpur, District Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000084/2022-2023 | 3466/ED | 30/12/2022 | 90 | T.N. BANERJEE | 21.6 | 0 | 0
503 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hasnan water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002464/2023-2024 | 325/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0
504 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05321/2023-2024 | 696 | 22/01/2024 | 0 | WBSEDCL | 6.37 | 0 | 0
505 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Simla W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05334/2023-2024 | 697 | 22/01/2024 | 0 | WBSEDCL | 5.91 | 0 | 0
506 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Simla water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000120/2022-2023 | 3476/ED | 30/12/2022 | 1678 | A.S. ENTERPRISE | 21.42 | 0 | 45
507 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Gopalnagar W/S sch. , T/W - II, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00736/2023-2024 | 23 | 11/05/2023 | 0 | WBSEDCL | 2.53 | 0 | 0
508 | Electrical | Chandannagar Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT GOPALNAGAR W/S SCH. , T/W NO. - IV, DIST. - HOOGHLY | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00737/2023-2024 | 25 | 11/05/2023 | 0 | WBSEDCL | 4.09 | 0 | 0
509 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01453/2022-2023 | 211 | 24/03/2023 | 0 | WBSEDCL | 0.7 | 0 | 0
510 | Electrical | Chandannagar Sub-Division | Revised Quotation New service connection at Gopalnagar W/S Sch. , T/W No. - IV, Block - Singur, due to non payment of previous quotation for online banking transaction error. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04056/2023-2024 |  | 06/10/2023 | 0 | WBSEDCL | 4.09 | 0 | 0
511 | Electrical | Chandannagar Sub-Division | Revised Quotation Bill for New Service Connection at Gopal Nagar W/S. Sch. TW-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04070/2023-2024 | 338 | 10/10/2023 | 0 | WBSEDCL | 0 | 0 | 0
512 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gopalnagar water supply scheme, T.W. No.- I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000211/2022-2023 | 838/ED | 14/02/2023 | 791 | WEST BENGAL ENGINEERING CO. | 32.24 | 0 | 90
513 | Electrical | Chinsuria Sub-Division | Bishnupur PH__I Water supply Scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05986/2023-2024 | 723 | 05/02/2024 | 0 | WBSEDCL | 7.9 | 0 | 0
514 | Electrical | Chinsuria Sub-Division | Quotation of New service Connection Charge for Bishnupur w/s Scheme,TW No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12263) Application no-5003995286 Reference Id-503552526 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06105/2023-2024 | 762 | 16/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
515 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987362 Reference Id-503547192 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06057/2023-2024 | 760 | 16/02/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
516 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Routhkhana w/s Scheme,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/12233) Application No-5003987354 Reference Id-503547191 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06058/2023-2024 | 758 | 16/02/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
517 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ROUTHKHANA PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000149/2024-2025 | 1172/ED | 14/06/2024 | 90 | BINAPANI ENTERPRISE | 10.64 | 0 | 0
518 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Routhkhana water supply scheme, T.W. No.- I & II, Block: Khanakul-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000169/2022-2023 | 3502/ED | 30/12/2022 | 90 | BINAPANI ENTERPRISE | 21.48 | 0 | 0
519 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Nababpur PWSS P.H. No.-I, Hooghly. Application No. 5004064466 Ref ID: 503597309 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/00035/2024-2025 | 21 | 05/04/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
520 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Nababpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004064410 Reference ID- 503597307 SM Code- 12239 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/02122/2024-2025 | 560 | 11/11/2024 | 0 | WBSEDCL | 4.18 | 0 | 0
521 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000164/2022-2023 | 3498/ED | 30/12/2022 | 90 | ANJAN ENTERPRISE | 21.33 | 0 | 30
522 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nababpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000193/2022-2023 | 786/ED | 09/02/2023 | 727 | M/S P.P. ELECTRICALS | 22.36 | 0 | 50
523 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at P.H No.-II of Bipra Noapara pwss, Dist- Howrah under ED PHED. App. No.-1007764053 SM/11711 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00457/2024-2025 | 134 | 17/05/2024 | 0 | WBSEDCL | 7.48 | 0 | 0
524 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bipra Noapara water supply scheme, T.W. No.- I & II, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000117/2022-2023 | 3507/ED | 30/12/2022 | 90 | MAA KALI ENTERPRISE | 22.83 | 0 | 40
525 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bipra Noapara water supply scheme, T.W. No.- III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000861/2023-2024 | 3433/ED | 11/08/2023 | 90 | MAA KALI ENTERPRISE | 21.49 | 0 | 30
526 | Electrical | Chandannagar Sub-Division | Astara w/s scheme,P H No-1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03938/2023-2024 | 313 | 27/09/2023 | 0 | WBSEDCL | 5.81 | 0 | 0
527 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for ASTARA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004031983 Ref. ID- 503573554 SM/11286 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06196/2023-2024 | 804 | 27/02/2024 | 0 | WBSEDCL | 6.23 | 0 | 0
528 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Astara water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000075/2022-2023 | 3457/ED | 30/12/2022 | 90 | S S ENTERPRISES | 23.02 | 0 | 95
529 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection Charge for Pannra w/S Scheme,TW No-II, Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03766/2023-2024 | 258 | 05/09/2023 | 0 | WBSEDCL | 3.16 | 0 | 0
530 | Electrical | Chandannagar Sub-Division | Quotation for New Service Connection at Pantra W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04613/2023-2024 | 612 | 14/03/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
531 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Panrra water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000090/2022-2023 | 3472/ED | 30/12/2022 | 90 | SANKAR PRASAD DUTTA & CO. | 23 | 0 | 30
532 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Sauria W/S. Sch. TW-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | BILL/04513/2023-2024 | 558 | 21/12/2023 | 0 | WBSEDCL | 3.59 | 0 | 0
533 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Sauria W/S. Sch. TW-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | BILL/04514/2023-2024 | 557 | 21/12/2023 | 0 | WBSEDCL | 7.61 | 0 | 0
534 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Saoria water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000136/2022-2023 | 3521/ED | 30/12/2022 | 702 | GLACIER ENGINEERING CO. | 20.25 | 0 | 90
535 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nayachak water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000150/2022-2023 | 3518/ED | 30/12/2022 | 90 | JAGANNATH ENTERPRISE | 21.36 | 0 | 0
536 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nayachak water supply scheme, T.W. No. III, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000882/2023-2024 | 3455/ED | 11/08/2023 | 90 | TAMAL ENTERPRISE | 10.76 | 0 | 0
537 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
538 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
539 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
540 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
541 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
542 | Electrical | Chinsuria Sub-Division | New Connection of Digsui Heora W/S. Sch. Z-I, PH-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00002/2022-2023 | BP-2022-23-110 | 01/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.91 | 0 | 0
543 | Electrical | Chinsuria Sub-Division | Quotation bill for New Connection of WBSEDCL at Digsui Heora W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00774/2022-2023 | 127 | 17/01/2023 | 0 | WBSEDCL | 3.83 | 0 | 0
544 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical Mechanical equipments etc. with allied works for Digsui- Heora W/S. Sch. TW-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000241/2022-2023 | 1538/ED | 19/09/2022 | 90 | SRI KRISHNA NIRMAN | 8.93 | 0 | 100
545 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Digsui Heora water supply scheme, Zone-II, T.W. No.- III, Block: Chinsurah Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001366/2022-2023 | 1917/ED | 21/11/2022 | 90 | M/S S.R. ENTERPRISE | 9.41 | 0 | 100
546 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. with effect from 01.04.2023 to 31.08.2023. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001367/2022-2023 | 203/AE-I/ED | 27/03/2023 | 153 | DASHRATH KUMAR PRAJAPATI | 0.73 | 0 | 5
547 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of sautomatic chlorinatorfor Digsui Heora W/S. Sch. Z-I, TW-III Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002560/2022-2023 | 69/HMSD | 10/01/2023 | 7 | SRI KRISHNA NIRMAN | 0.8 | 0 | 100
548 | Electrical | Chinsuria Sub-Division | Digsui Heora W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002738/2022-2023 |  | 10/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 21.72 | 0 | 0
549 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004026546 Reference Id-503570690 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/00429/2024-2025 | 110 | 09/05/2024 | 0 | WBSEDCL | 5.15 | 0 | 0
550 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13324) Application no-5004073228 Reference Id-503597246 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/00441/2024-2025 | 125 | 17/05/2024 | 0 | WBSEDCL | 8.29 | 0 | 0
551 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Marakhana water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/000188/2022-2023 | 781 /ED | 09/02/2023 | 843 | S.G.-ENTERPRISE | 20.5 | 0 | 30
552 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dubir Bheri W/S Sch.(Aug.) , T/W no. - I, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02846/2023-2024 | 193 | 17/08/2023 | 0 | WBSEDCL | 10.34 | 0 | 0
553 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dubir Bheri W/S Sch(Aug.)., T/W No. - II, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02847/2023-2024 | 194 | 17/08/2023 | 0 | WBSEDCL | 8.98 | 0 | 0
554 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dubir Bheri water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000207/2022-2023 | 834/ED | 14/02/2023 | 450 | BARISAL TRADING CO. | 21.49 | 0 | 90
555 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-V | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/04498/2023-2024 | 544 | 19/12/2023 | 0 | WBSEDCL | 36.89 | 0 | 0
556 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Bainchi W/S. Sch. PH-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/04499/2023-2024 | 545 | 19/12/2023 | 0 | WBSEDCL | 3.53 | 0 | 0
557 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baichi water supply scheme, T.W. No.- I & II, Block: Pandua, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000196/2022-2023 | 823/ED | 14/02/2023 | 90 | SRI KRISHNA NIRMAN | 21.49 | 0 | 90
558 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jaynagar water supply scheme, T.W. No. I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000027/2023-2024 | 1704/ED | 18/04/2023 | 90 | DIPALI CONSTRUCTION | 22.8 | 0 | 30
559 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JAYNAGAR water supply scheme, TW No. III, Block: Panchla, District - Howrah under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003106/2024-2025 | 489/ED | 18/03/2025 | 90 | DIPALI CONSTRUCTION | 11.3 | 0 | 0
560 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
561 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
562 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
563 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service connection of Mollarchak Mini water supply scheme, Amta- I , Howrah | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/06038/2023-2024 | 735 | 07/02/2024 | 0 | WBSEDCL | 0.09 | 0 | 0
564 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chiladangi water supply scheme, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001146/2022-2023 | 1498/ED | 28/03/2023 | 90 | DAS ENTERPRISE | 10.73 | 0 | 0
565 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chiladangi water supply scheme, T.W. No. II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001531/2021-2022 | 3004_ED | 29/12/2021 | 90 | A.G. ENTERPRISE | 10.52 | 0 | 0
566 | Electrical | Chinsuria Sub-Division | New Service connection quotation charges for ph-4 Bhastara pwss | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04471/2023-2024 | 522 | 12/12/2023 | 0 | WBSEDCL | 3.73 | 0 | 0
567 | Electrical | Chinsuria Sub-Division | New Service connection quotation charges for ph-3 Bhastara pwss | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04472/2023-2024 | 521 | 12/12/2023 | 0 | WBSEDCL | 3.8 | 0 | 0
568 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhastara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000014/2023-2024 | 1630/ED | 11/04/2023 | 90 | M.S ENTERPRISE | 22.83 | 0 | 50
569 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000206/2022-2023 | 833/ED | 14/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 59
570 | Electrical |  | Quotation for New Service Connection at Shankardari Mini W/S. Sch. |  |  | BILL/04665/2023-2024 | 651 | 10/01/2024 | 0 | WBSEDCL | 0.08 | 0 | 0
571 | Electrical | Hooghly Division | Quotation of New Service Connection for Samanta Khanda w/s Scheme, PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/16127) Application No-5004034170 Reference Id-503574968 | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | BILL/06199/2023-2024 | 814 | 28/02/2024 | 0 | WBSEDCL | 4.75 | 0 | 0
572 | Electrical | Hooghly Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAMANTA KHANDA PIPED W/S SCHEME, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/000137/2024-2025 | 1163/ED | 14/06/2024 | 90 | PADMA ENGINEERING CO. | 10.74 | 0 | 0
573 | Electrical | Hooghly Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Samanta Khanda water supply scheme, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer (Civill),Junior Engineer4 | ORD/000311/2022-2023 | 1241/ED | 06/03/2023 | 90 | R.M.D TRADING. | 22.84 | 0 | 0
574 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sibrambati W/s Sch. Zone - II, T/W No. - III,[SM/15888], under Singur CCC, WBSEDCL, Ref. Id. - 503666629, Dt. - 18-06-2024, Application No. - 5004236084 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00851/2024-2025 | 247 | 24/06/2024 | 0 | WBSEDCL | 9.51 | 0 | 0
575 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Sibrambati W/S. Sch.TW-I, Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04132/2023-2024 | 378 | 25/10/2023 | 0 | WBSEDCL | 5.8 | 0 | 0
576 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Shibrambati W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04457/2023-2024 | 520 | 11/12/2023 | 0 | WBSEDCL | 4.42 | 0 | 0
577 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sibrambati (Zone-II) water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000032/2023-2024 | 1709/ED | 18/04/2023 | 410 | GLACIER ENGINEERING CO. | 21.1 | 0 | 50
578 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shibrambati water supply scheme, Zone-II, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002479/2023-2024 | 339/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.36 | 0 | 90
579 | Electrical | Ulberia Sub-Division | Quotation bill for new service connection of WBSEDC at Chakur w/s scheme, T.W. No.-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00779/2022-2023 | 150 | 08/02/2023 | 0 | WBSEDCL | 2.74 | 0 | 0
580 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at of Chakur W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/01914/2022-2023 | 02 | 11/04/2023 | 0 | WBSEDCL | 0.69 | 0 | 0
581 | Electrical | Ulberia Sub-Division | Supply, Delivery & Installation of S/P/M & other Electrical/Mechanical equipments etc. including allied works for Chakur W/S. Sch. Howrah | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000005/2022-2023 | 781/ED | 05/05/2022 | 365 | D. K. ELECTRIC | 10.41 | 0 | 0
582 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chakur water supply scheme, T.W. No. I, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000145/2022-2023 | 3528/ED | 30/12/2022 | 90 | DAS ENTERPRISE | 10.66 | 0 | 0
583 | Electrical | Ulberia Sub-Division | Chakur water supply scheme. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/002477/2021-2022 | 21-22/134 | 22/03/2022 | 0 | WBSEDCL | 7.32 | 0 | 0
584 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Kishorepur W/S. Sch. PH-III | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04922/2023-2024 | 675 | 18/01/2024 | 0 | WBSEDCL | 4.48 | 0 | 0
585 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kishorpur water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000001/2023-2024 | 1617/ED | 11/04/2023 | 751 | M/S G P ENTERPRISE | 10.74 | 0 | 20
586 | Electrical | Arambug Sub-Division | Emergency replacement of burnt submersible pump-motor set by newly supplied pump-motor set, rewinding of the burnt submersible motor, replacement of voltage corrector and related works at Kishorpur w/s scheme, P.H No-I, Dist- Hooghly. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000319/2022-2023 | 495/HMSD | 02/03/2023 | 30 | SOMNATH ENTERPRISE | 3.58 | 0 | 100
587 | Electrical | Arambug Sub-Division | Quotation Bill for for New Service Connection at Gobindopur W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | BILL/04319/2023-2024 | 427 | 17/11/2023 | 0 | WBSEDCL | 4.41 | 0 | 0
588 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000055/2023-2024 | 1799/ED | 24/04/2023 | 862 | OSMAN SEKH | 10.75 | 0 | 50
589 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No. II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002487/2023-2024 | 138/ED | 16/01/2024 | 90 | MUKHERJEE ART CENTRE | 10.7 | 0 | 0
590 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connectio at Bhalia W/S. Sch. Z-I, TW-IV | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04161/2023-2024 | 396 | 06/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0
591 | Electrical | Arambug Sub-Division | "Quotation Bill for New Service Connection at Bhalia W/S. Sch. Z-I" | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04164/2023-2024 | 401 | 09/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0
592 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-I) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000009/2023-2024 | 1625/ED | 11/04/2023 | 90 | C.M.S. ENGINEERING CONCERN | 22.04 | 0 | 30
593 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHALIA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000188/2024-2025 | 1204/ED | 14/06/2024 | 90 | C.M.S. ENGINEERING CONCERN | 10.95 | 0 | 0
594 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARANDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000366/2024-2025 | 1450/ED | 25/07/2024 | 90 | MOITRA ENGINEERING CO. | 11.08 | 0 | 0
595 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Arandi water supply scheme, T.W. No. III, Block: Arambag, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002101/2022-2023 | 1919/ED | 21/11/2022 | 859 | INDTECH ASSOCIATES. | 10.67 | 0 | 30
596 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Rajhat(Uncovered)[Rajhat Uttar] W/S Sch.[SM/18095], T/W No. - I, Mahashay Para, Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599474, Dt. - 22-03-2024, Application No. - 5004078306 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00013/2024-2025 | 16 | 04/04/2024 | 0 | WBSEDCL | 11.27 | 0 | 0
597 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Rajhat Dakshinpara W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04458/2023-2024 | 519 | 11/12/2023 | 0 | WBSEDCL | 10.03 | 0 | 0
598 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJHAT UTTAR PROPOSED TW Site under Chirnurah Sub Division, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002584/2023-2024 | 459/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 90
599 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Keshabpur water supply scheme, T.W. No. I, II & III, Block: Domjur, District - Howrah under Electrical Division, PHE Dte. | AE/SADAR |  | ORD/001358/2023-2024 | 4694/ED | 08/12/2023 | 571 | DAS ENTERPRISE | 32.91 | 0 | 40
600 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Ganderpukur W/S Sch., T/W No. - I, Block - Singur, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04074/2023-2024 | 339 | 10/10/2023 | 0 | WBSEDCL | 0.64 | 0 | 0
601 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Ganderpukur W/S Sch. , T/W No. - II, Block- Singur, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04075/2023-2024 | 347 | 11/10/2023 | 0 | WBSEDCL | 2.39 | 0 | 0
602 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ganderpukur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000041/2023-2024 | 1727/ED | 19/04/2023 | 90 | M/S DAS ENTERPRISE | 21.05 | 0 | 49
603 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - I, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589159, Dt. - 07-03-2024, Application No. - 5004058510 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06275/2023-2024 | 875 | 13/03/2024 | 0 | WBSEDCL | 9.63 | 0 | 0
604 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bainchipota(Zone- II) water supply Scheme [SM/17629], T/W No. - II, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. No. - 503589664, Dt. - 07-03-2024, Application No. - 5004059136 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06280/2023-2024 | 874 | 13/03/2024 | 0 | WBSEDCL | 0.64 | 0 | 0
605 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota (Zone-II) water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000046/2023-2024 | 1732/ED | 19/04/2023 | 90 | BINAPANI ENTERPRISE | 20.52 | 0 | 30
606 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Lakshmipur w/s scheme,TW No-3 District-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02128/2023-2024 | 118 | 20/07/2023 | 0 | WBSEDCL | 3.52 | 0 | 0
607 | Electrical | Arambug Sub-Division | Quotation of New service Connection for Lakshmipur W/s Scheme, TW No-4, Block-Goghat-I, Dist-hooghly Under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02477/2023-2024 | 150 | 01/08/2023 | 0 | WBSEDCL | 2.69 | 0 | 0
608 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Lakshmipur water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000215/2022-2023 | 849/ED | 14/02/2023 | 90 | PRADIP KUMAR DHABAL | 21.51 | 0 | 40
609 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhurkunda w/s Scheme, Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/17721) Application No-5004190543 Reference Id-503647430. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00483/2024-2025 | 149 | 22/05/2024 | 0 | WBSEDCL | 3.63 | 0 | 0
610 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhurkunda w/s scheme, Zone-I,PH No-I Block-Goghat-II,under Electrical Division,PHE Dte.(SM/17721) Application No-5004243748 Reference Id-503669340. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00831/2024-2025 | 230 | 20/06/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
611 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhurkunda water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000049/2023-2024 | 1793/ED | 24/04/2023 | 668 | H.K.DAS & CO. | 22.39 | 0 | 40
612 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHURKUNDA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000138/2024-2025 | 1164/ED | 14/06/2024 | 90 | H.K.DAS & CO. | 10.89 | 0 | 0
613 | Electrical |  | Quotation of New Service Connection for Mainan w/s Scheme,PH No-4 Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004288912 Reference Id-503688427. |  |  | BILL/01158/2024-2025 | 293 | 15/07/2024 | 0 | WBSEDCL | 7.06 | 0 | 0
614 | Electrical |  | Quotation of New Service Connection for Mainan w/s Scheme,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004320142 Reference Id- 503705441 |  |  | BILL/01376/2024-2025 | 336 | 30/07/2024 | 0 | WBSEDCL | 8.26 | 0 | 0
615 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAINAN PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000370/2024-2025 | 1454/ED | 25/07/2024 | 90 | SUDIKSHA CONSTRUCTION | 22.11 | 0 | 0
616 | Electrical |  | Quotation of New Service Connection for Bhalia w/s Scheme,Zone-II,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/19014) Application No-5004416386 Reference Id-503753715 |  |  | BILL/01983/2024-2025 | 478 | 01/10/2024 | 0 | WBSEDCL | 6.49 | 0 | 0
617 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001983/2023-2024 | 115/ED | 15/01/2024 | 502 | A.G. ENTERPRISE | 20.49 | 0 | 20
618 | Electrical |  | Quotation for new service connection of Harop W/S. Sch. PH-II |  |  | BILL/06046/2023-2024 | 746 | 08/02/2024 | 0 | WBSEDCL | 6.37 | 0 | 0
619 | Electrical |  | Quotation for new service connection of Harop W/S. Sch. PH-I |  |  | BILL/06053/2023-2024 | 753 | 16/02/2024 | 0 | WBSEDCL | 4.08 | 0 | 0
620 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Harop (Zone-I & II) water supply scheme, T.W. No. I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000922/2023-2024 | 3593/ED | 28/08/2023 | 612 | SUBHRA ENTERPRISE | 32.24 | 0 | 50
621 | Electrical |  | Quotation money deposition for new service connection at Udang w/s scheme, Zone- I, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1007772514 Reference ID- 106595797 SM Code- 18567 |  |  | BILL/00492/2024-2025 | 165 | 28/05/2024 | 0 | WBSEDCL | 5.3 | 0 | 0
622 | Electrical |  | Quotation money deposition for new service connection at Udang w/s scheme, Zone- II, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1008049557 Reference ID- 106726236 SM Code- 18567 |  |  | BILL/02113/2024-2025 | 557 | 05/11/2024 | 0 | WBSEDCL | 25.4 | 0 | 0
623 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Udang water supply scheme, T.W. No. I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000923/2023-2024 | 3594/ED | 28/08/2023 | 90 | EMCON | 21.49 | 0 | 0
624 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000154/2024-2025 | 1177/ED | 14/06/2024 | 90 | M/S G P ENTERPRISE | 10.74 | 0 | 0
625 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000155/2024-2025 | 1178/ED | 14/06/2024 | 90 | M/S. UTTAM KUMAR CHATTERJEE. | 10.74 | 0 | 0
626 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000816/2023-2024 | 3161/ED | 27/07/2023 | 614 | GLACIER ENGINEERING CO. | 21.83 | 0 | 50
627 | Electrical |  | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008024177 Reference ID- 106715773 SM Code- 18883 |  |  | BILL/02125/2024-2025 | 565 | 13/11/2024 | 0 | WBSEDCL | 11.33 | 0 | 0
628 | Electrical |  | Quotation money deposition for new service connection at Amoragori w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1008024188 Reference ID- 106715771 SM Code- 18883 |  |  | BILL/02129/2024-2025 | 566 | 13/11/2024 | 0 | WBSEDCL | 10.4 | 0 | 0
629 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Amragari Water Supply Scheme Block- Amta-II District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001298/2023-2024 | 4531/ED | 23/11/2023 | 596 | DAS ENTERPRISE | 21.49 | 0 | 40
630 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amragori water supply scheme, T.W. No. III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/002780/2022-2023 | 1796/ED | 02/11/2022 | 90 | MENAKA ENTERPRISE | 10.84 | 0 | 100
631 | Electrical |  | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-III under Electrical Division,PHE Dte.(SM/18644). Application No-5004112076. Reference Id-503617154. |  |  | BILL/00190/2024-2025 | 78 | 19/04/2024 | 0 | WBSEDCL | 19.66 | 0 | 0
632 | Electrical |  | Quotation of New Service Connection for Bakulia w/s Scheme,PH No-IV under Electrical Division,PHE Dte.(SM/18644). Application No-5004111585. Reference Id-503617124. |  |  | BILL/00191/2024-2025 | 79 | 19/04/2024 | 0 | WBSEDCL | 7.52 | 0 | 0
633 | Electrical |  | Supply of Fuel of 1(One) no Diesel luxury Taxi on contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of April 2024. |  |  | BILL/00501/2024-2025 | 154 | 28/05/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
634 | Electrical |  | Supply of Fuel for 1(One) no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division PHE DTe. for the Month of May 2024. Car No-WB 04H 0517 |  |  | BILL/00715/2024-2025 | 226 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
635 | Electrical |  | Supply of Fuel for 1(one) no Diesel Luxury taxi on Contract Carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte for the Month of June 2024. |  |  | BILL/01151/2024-2025 | 283 | 09/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
636 | Electrical |  | Supply of Fuel for 1(One) no. Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer,Howrah mechanical Sub Division,PHE Dte for the Month of July 2024. |  |  | BILL/01636/2024-2025 | 413 | 22/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
637 | Electrical |  | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte for the Month of August 2024. Car No. WB-04H-0517 From 01.08.2024 to 31.08.2024 |  |  | BILL/01975/2024-2025 | 467 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
638 | Electrical |  | Fuel Bill for Hiring of 1no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division,PHE Dte for the Month of September 2024 |  |  | BILL/02075/2024-2025 | 532 | 28/10/2024 | 0 | ARINDAM AUDDY | 0.07 | 0 | 0
639 | Electrical |  | Fuel Bill for Hiring of 1no Diesel Luxury Taxi on Contract Carriage for the Office of the Assistant Engineer Howrah Mechanical Sub Division,PHE Dte for the Month of September 2024. |  |  | BILL/02076/2024-2025 | 534 | 28/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.18 | 0 | 0
640 | Electrical |  | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of SEPTEMBER,2024 |  |  | BILL/02095/2024-2025 | 546 | 30/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.12 | 0 | 0
641 | Electrical |  | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/000002/2024-2025 | 2404/HMSD | 26/04/2024 | 153 | ARINDAM AUDDY | 0.73 | 0 | 0
642 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bakulia water supply scheme, T.W. No. I & II, Block: Balagarh, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000926/2023-2024 | 3597/ED | 28/08/2023 | 90 | R.M.D TRADING. | 21.89 | 0 | 0
643 | Electrical |  | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/001103/2023-2024 | 2829/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 0 | 15
644 | Electrical |  | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/002957/2023-2024 | 2829_/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 0 | 0
645 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004191479 Reference Id-503647821. | Assistant Engineer | Junior Engineer (Civill) | BILL/00536/2024-2025 | 179 | 30/05/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
646 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004423599 Reference Id-503761602 | Assistant Engineer | Junior Engineer (Civill) | BILL/02033/2024-2025 | 508 | 21/10/2024 | 0 | WBSEDCL | 4.87 | 0 | 0
647 | Electrical | Arambug Sub-Division | Quotation of New Service Connection For Garmandaran w/s Scheme,Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/18646) Application No-5004431289 Reference Id-503764743 | Assistant Engineer | Junior Engineer (Civill) | BILL/02059/2024-2025 | 516 | 21/10/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
648 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000876/2023-2024 | 3449/ED | 11/08/2023 | 90 | AMIT DAS | 21.46 | 0 | 0
649 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000928/2023-2024 | 3599/ED | 28/08/2023 | 673 | UNITED TRADERS | 21.47 | 0 | 40
650 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DHAMAITIKAR PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001252/2023-2024 | 4501/ED | 23/11/2023 | 678 | S.G.-ENTERPRISE | 21.5 | 0 | 45
651 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BACHHANARI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000367/2024-2025 | 1451/ED | 25/07/2024 | 90 | DAS ENTERPRISE | 11.08 | 0 | 0
652 | Electrical |  | Supply delivery and installation of Chlorinator for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001526/2021-2022 | 316/HMSD | 18/02/2022 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 0.76 | 0 | 100
653 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bachhanari water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001529/2021-2022 | 553_ED | 22/03/2022 | 90 | S.M. ELECTRICALS | 6.05 | 0 | 50
654 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Bachhanari w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002572/2022-2023 | 659/HMSD | 04/04/2022 | 30 | NITESH MANAGEMENT | 2.74 | 0 | 100
655 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. III, Block: Arambag , District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001520/2021-2022 | 472/ED | 10/03/2022 | 90 | DAS ENTERPRISE | 6.89 | 0 | 100
656 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001524/2021-2022 | 540/HMSD | 17/03/2022 | 21 | MOITRA ENGINEERING CO. | 2.74 | 0 | 100
657 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001525/2021-2022 | 542/HMSD | 17/03/2022 | 30 | KASHINATH PAL & CO. | 2.74 | 0 | 100
658 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No. IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001534/2021-2022 | 473/ED | 10/03/2022 | 90 | S.P. ENTERPRISE | 6.92 | 0 | 50
659 | Electrical |  | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. IV District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002569/2022-2023 | 71/HMSD | 10/01/2023 | 7 | S P ENTERPRISE | 0.8 | 0 | 100
660 | Electrical |  | Supply and installation of short MS casing pipe making TW foundation and S&F submersible AL. Ar. cable at Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002570/2022-2023 | 1928/HMSD | 03/11/2022 | 7 | DAS ENTERPRISE | 0.9 | 0 | 100
661 | Electrical |  | Supply delivery and installation of Chlorinator for Hayatpur w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/002571/2022-2023 | 1878/HMSD | 20/10/2022 | 7 | DAS ENTERPRISE | 0.8 | 0 | 100
662 | Electrical | Arambug Sub-Division | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004136337 Reference Id-503627274. | Assistant Engineer |  | BILL/00328/2024-2025 | 102 | 06/05/2024 | 0 | WBSEDCL | 10.8 | 0 | 0
663 | Electrical | Arambug Sub-Division | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-I Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004135566 Reference Id-503626938. | Assistant Engineer |  | BILL/00329/2024-2025 | 103 | 06/05/2024 | 0 | WBSEDCL | 10.73 | 0 | 0
664 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Shantipur w/s Scheme, Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18592) Application No-5004190445 Reference Id-503647425. | Assistant Engineer |  | BILL/00481/2024-2025 | 151 | 22/05/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
665 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHANTIPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer |  | ORD/000141/2024-2025 | 1167/ED | 14/06/2024 | 90 | SRI KRISHNA NIRMAN | 10.54 | 0 | 30
666 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer |  | ORD/000916/2023-2024 | 3587/ED | 28/08/2023 | 642 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.26 | 0 | 30
667 | Electrical | North 24 Pgs W/S Division I | Payment to WBSEDCL of Malikapur | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | BILL/01116/2023-2024 |  | 27/06/2023 | 0 | WBSEDCL | 1.66 | 0 | 0
668 | Electrical | North 24 Pgs W/S Division I | Quotation for New Connection at Malikapur OHR site. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | BILL/02478/2024-2025 | 609 | 05/12/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
669 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, B (Malikapur) in Barasat-I Block of North 24 Parganas District. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/001058/2023-2024 | 4029/ED | 17/10/2023 | 183 | A.G. ENTERPRISE | 55.55 | 0 | 0
670 | Electrical |  | Quotation for new service connection at Akna(S. Aug.) W/S Sch.[SM/18943], T/W No. - III, Barol Chowmatha, Block - Polba-Dadpur, Dist. - Hooghly under Mogra CCC, WBSEDCL, Ref. Id. - 503586679, Dt. - 27-03-2024, Application No. - 5004053218 |  |  | BILL/00015/2024-2025 | 14 | 04/04/2024 | 0 | WBSEDCL | 7.46 | 0 | 0
671 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AKNA PIPED W/S SCHEME Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001262/2023-2024 | 4507/ED | 23/11/2023 | 90 | KARUNAMOY ENGINEERING | 10.74 | 0 | 90
672 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amra water supply scheme, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000032/2022-2023 | 1914/ED | 21/11/2022 | 90 | M/S MANABESH ROY | 9.39 | 0 | 98
673 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of AMRA Piped W/S Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001274/2023-2024 | 4514/ED | 23/11/2023 | 90 | SRI KRISHNA NIRMAN | 21.5 | 0 | 0
674 | Electrical | Ulberia Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Mellock Brahmandakuria P-III W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00741/2022-2023 | 141 | 20/01/2023 | 0 | WBSEDCL | 2.6 | 0 | 0
675 | Electrical | Ulberia Sub-Division | NEW SERVICE CONNECTION FOR AUGMENTATION OF MELLOK BRAHMANDAKURIA PH NO-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00756/2023-2024 | 41 | 17/05/2023 | 0 | WBSEDCL | 2.74 | 0 | 0
676 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mellok Brahmandakuria water supply scheme, Head work site, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000190/2022-2023 | 783/ED | 09/02/2023 | 90 | DIPALI CONSTRUCTION | 10.79 | 0 | 1
677 | Electrical | Ulberia Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000617/2023-2024 | 933/HMSD | 18/04/2023 | 153 | S.P. CONSTRUCTION | 0.4 | 0 | 40
678 | Electrical | Ulberia Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000618/2023-2024 | 959/HMSD | 20/04/2023 | 184 | SANJIB PRADHAN | 0.38 | 0 | 40
679 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mellok Brahmandakuria water supply scheme, T.W. No.- II, Block: Bagnan, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000862/2023-2024 | 3434/ED | 11/08/2023 | 90 | DIPALI CONSTRUCTION | 10.74 | 0 | 50
680 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nischintapur water supply scheme T.W. No. New, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000036/2023-2024 | 1713/ED | 18/04/2023 | 90 | PADMA ENGINEERING CO. | 10.74 | 0 | 80
681 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Enayetpur water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000209/2022-2023 | 836/ED | 14/02/2023 | 90 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0
682 | Electrical | Chandannagar Sub-Division | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00904/2022-2023 | 183 | 10/03/2023 | 0 | WBSEDCL | 0.65 | 0 | 0
683 | Electrical | Chandannagar Sub-Division | Quotation Bill for New service connection at (Aug.) of Dwipa W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00905/2022-2023 | 183 | 10/03/2023 | 0 | WBSEDCL | 3.08 | 0 | 0
684 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dwipa water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000208/2022-2023 | 835/ED | 14/02/2023 | 90 | M/S PS & ASSOCIATES | 21.49 | 0 | 0
685 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Paschim Bainan W/S. Sch. PH-V | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/03699/2023-2024 | 231 | 01/09/2023 | 0 | WBSEDCL | 4.96 | 0 | 0
686 | Electrical | Ulberia Sub-Division | Quotation bill for service connection P.H. No.-III at Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000010/2022-2023 | 1046/ED | 21/08/2022 | 365 | WBSEDCL | 0.68 | 0 | 0
687 | Electrical | Ulberia Sub-Division | Service connection for P.H. No.-III of Ground Based Piped Water Supply Scheme for Paschim Bainan | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000011/2022-2023 | 1006615110/Quot/03 | 10/08/2022 | 365 | WBSEDCL | 0.68 | 0 | 0
688 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paschim Bainan water supply scheme, T.W. No. III, Block: Bagnan-I, District - Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000031/2022-2023 | 1915/ED | 21/11/2022 | 90 | MAA KALI ENTERPRISE | 10.01 | 0 | 97
689 | Electrical | Ulberia Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works fo Paschim Bainan W/S. Sch. RW-IV | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000047/2022-2023 | 1793/ED | 02/11/2022 | 90 | HINDUSTAN ENGINEERING CORPORATION ( E & M ) | 10.84 | 0 | 0
690 | Electrical | Ulberia Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works fo Paschim Bainan W/S. Sch. TW-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000049/2022-2023 | 2103/HMSD | 24/11/2022 | 30 | KARUNAMOY ENGINEERING | 4.87 | 0 | 0
691 | Electrical | Ulberia Sub-Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000308/2021-2022 | GO2122007937PH | 05/01/2022 | 365 | WBSEDCL | 0.68 | 0 | 0
692 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Bainan water supply scheme, T.W. No. V, VI & VII, Block: Bagnan-I, District - Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000883/2023-2024 | 3456/ED | 11/08/2023 | 90 | SANKAR PRASAD DUTTA & CO. | 33.21 | 0 | 35
693 | Electrical | Ulberia Sub-Division | Electric Supply at Bagnan | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/002238/2022-2023 | 46 | 22/08/2022 | 0 | WBSEDCL | 0.68 | 0 | 0
694 | Electrical | Ulberia Sub-Division | Electric Supply at Paschim Bainan | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/002245/2022-2023 | 53 | 23/08/2022 | 0 | WBSEDCL | 0.68 | 0 | 0
695 | Electrical | Ulberia Sub-Division | New Connection at Paschim Bainan W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/002587/2022-2023 |  | 17/10/2022 | 0 | WBSEDCL | 4.12 | 0 | 0
696 | Electrical | Ulberia Sub-Division | New Connection in for Paschim Bainan W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/002696/2022-2023 | 94 | 20/10/2022 | 0 | WBSEDCL | 4.12 | 0 | 0
697 | Electrical | Chandannagar Sub-Division | Quotation bill for New Connection at Beraberi W/S. Sch. PH-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00012/2022-2023 | BP-2022-23-111 | 14/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.54 | 0 | 0
698 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Beraberi W/S Sch. , T/W No. - V [SM/09984] , Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503614887, dt. - 12/04/2024, Application No. - 5004104119 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00188/2024-2025 | 75 | 18/04/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
699 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000035/2022-2023 | 1918/ED | 21/11/2022 | 90 | GLACIER ENGINEERING CO. | 10.67 | 0 | 0
700 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001275/2022-2023 | 1792/ED | 02/11/2022 | 90 | ALPHA ENTERPRISE | 10.67 | 0 | 99
701 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001361/2022-2023 | 1548/ED | 20/09/2022 | 649 | PERFECT AIRCONDITION | 9.66 | 0 | 99
702 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Beraberi water supply scheme, T.W. No. V, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002478/2023-2024 | 338/ED | 21/02/2024 | 540 | DEY ENTERPRISE | 10.41 | 0 | 90
703 | Electrical | Chandannagar Sub-Division | Electricity Bill New Connection | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002508/2022-2023 |  | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.03 | 0 | 0
704 | Electrical | Chandannagar Sub-Division | New Connection of Electricity | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002509/2022-2023 |  | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0
705 | Electrical | Chandannagar Sub-Division | New Connection | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/002536/2022-2023 | 80 | 16/09/2022 | 0 | WBSEDCL | 6.36 | 0 | 0
706 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ulanpara water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000132/2022-2023 | 3526/ED | 30/12/2022 | 90 | M/S, GHOSH ENTERPRISE | 21.37 | 0 | 0
707 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Banharishpur W/S. Sch. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/02466/2023-2024 | 148 | 28/07/2023 | 0 | WBSEDCL | 6.77 | 0 | 0
708 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Banharishpur pwss, P.H No.-I Dist-Howrah under ED PHED. App. No.-1007561303 Ref. ID.- 106491239 SM/11723 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/06247/2023-2024 | 851 | 07/03/2024 | 0 | WBSEDCL | 25.8 | 0 | 0
709 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Banharishpur water supply scheme, T.W. No. III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000283/2022-2023 | 933/ED | 22/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 50
710 | Electrical | Chinsuria Sub-Division | Add. Electric quot. of WBSEDCL for New service Connection of Barul T/W-I W/S scheme under Electrical Division PHE Dte. (SM/12246) App. No- 5003997215 Ref. Id- 503556940 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02093/2024-2025 | 539 | 29/10/2024 | 0 | WBSEDCL | 1.34 | 0 | 0
711 | Electrical | Chinsuria Sub-Division | Barul PH__II Water supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05989/2023-2024 | 726 | 05/02/2024 | 0 | WBSEDCL | 4.11 | 0 | 0
712 | Electrical | Chinsuria Sub-Division | Barul PH__I Water supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05990/2023-2024 | 727 | 05/02/2024 | 0 | WBSEDCL | 3.04 | 0 | 0
713 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Barul water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000076/2022-2023 | 3458/ED | 30/12/2022 | 1095 | T S CONSTRUCTION | 20.35 | 0 | 65
714 | Electrical | Ulberia Sub-Division | Quotation for new service connection for Mato w/s scheme, P/H No. 5, near Ghoradaha Primary School Block- Amta- I, Dist. - Howrah. Application No. 1007444170 Ref. id: 106409240 SM/09930 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/06163/2023-2024 | 798 | 23/02/2024 | 0 | WBSEDCL | 14.15 | 0 | 0
715 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MATO PIPED W/S SCHEME, T.W. No. V, Block: Amta-I, District - Howrah under JJM Program under Electrical Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/002507/2023-2024 | 423/ED | 29/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 85
716 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme, PH No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03687/2023-2024 | 229 | 01/09/2023 | 0 | WBSEDCL | 6.25 | 0 | 0
717 | Electrical | Chandannagar Sub-Division | Quotation bill for WBSEDCL security deposit for Rambati w/s scheme PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03688/2023-2024 | 230 | 01/09/2023 | 0 | WBSEDCL | 9.37 | 0 | 0
718 | Electrical | Chandannagar Sub-Division | Revised Quotation Bill for New Service Connection at Rambati W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04076/2023-2024 | 345 | 11/10/2023 | 0 | WBSEDCL | 0 | 0 | 0
719 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rambati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000092/2022-2023 | 3474/ED | 30/12/2022 | 90 | S.G. TECHNICAL SERVICES | 20.35 | 0 | 90
720 | Electrical | Chandannagar Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle - II, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000285/2024-2025 | 2871/HMSD | 04/06/2024 | 182 | DEBASHISH GHOSH | 0.86 | 0 | 0
721 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
722 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection at Rajhat w/s scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00841/2022-2023 | 173 | 28/02/2023 | 0 | WBSEDCL | 7.44 | 0 | 0
723 | Electrical | Chinsuria Sub-Division | Quotation bill for New service connection at Rajhat W/S. Sch Z-I, PH-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00851/2022-2023 | 173 | 28/02/2023 | 0 | WBSEDCL | 19.98 | 0 | 0
724 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-I, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000234/2022-2023 | 865/ED | 14/02/2023 | 90 | DIPA CHHETRI | 10.17 | 0 | 100
725 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000835/2023-2024 | 959/HMSD | 20/04/2023 | 30 | SANJIB PRADHAN | 0.39 | 0 | 1
726 | Electrical | Chinsuria Sub-Division | Car hiring and fuel bill for car no. WB02AB3954 from 01.07.2023 to 31.07.2023. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000836/2023-2024 | 363//AE-I/ED | 29/05/2023 | 31 | TRIDIP SARKAR | 0.38 | 0 | 1
727 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
728 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
729 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Nowpara W/S. Sch. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/04628/2023-2024 | 617 | 08/01/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
730 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Nowpara W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/04629/2023-2024 | 618 | 08/01/2024 | 0 | WBSEDCL | 7.8 | 0 | 0
731 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Uttar Khariop water supply scheme, T.W. No. III, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000095/2023-2024 | 2076/ED | 31/05/2023 | 90 | D. K. ELECTRIC | 10.72 | 0 | 100
732 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nawapara water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000167/2022-2023 | 3517/ED | 30/12/2022 | 90 | T S CONSTRUCTION | 22.49 | 0 | 80
733 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Sripatipur W/S Scheme,Zone-I,TW No-I Block-Haripal,Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03763/2023-2024 | 262 | 05/09/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
734 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for sripatipur W/S Scheme,Zone-I,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03764/2023-2024 | 261 | 05/09/2023 | 0 | WBSEDCL | 3.16 | 0 | 0
735 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Sripatipur w/s scheme,Zone-II,TW No-II Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03765/2023-2024 | 260 | 05/09/2023 | 0 | WBSEDCL | 6.19 | 0 | 0
736 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Sripatipur w/s Scheme,Z-I,TW No-3 Block-Haripal,District-Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03886/2023-2024 | 299 | 22/09/2023 | 0 | WBSEDCL | 2.5 | 0 | 0
737 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Sripatipur PWSS, Zone-II, TW - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04486/2023-2024 | 531 | 15/12/2023 | 0 | WBSEDCL | 3.22 | 0 | 0
738 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sripatipur water supply scheme TW No I II III IV and V, Block Haripal, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000230/2022-2023 | 861/ED | 14/02/2023 | 884 | DEY ENTERPRISE | 53.74 | 0 | 65
739 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
740 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
741 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - I (Dingalghat, bansberia),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643287, dt. - 10-05-2024, Application No. - 5004179261 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00455/2024-2025 | 123 | 17/05/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
742 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Saptagram (S.Aug.) W/S Sch. [SM/13409], T/W No. - II (Chotokhejuria),Block -Chinsurah- Mogra under Saptagram CCC, WBSDCL. Ref. Id - 503643407, dt. - 10-05-2024, Application No. - 5004179275 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00458/2024-2025 | 126 | 17/05/2024 | 0 | WBSEDCL | 5.49 | 0 | 0
743 | Electrical | Chinsuria Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Saptagram w/s scheme, P.H No.- IV, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000314/2022-2023 | 490/HMSD | 02/03/2023 | 30 | M.S.C. ENTERPRISE | 2.49 | 0 | 0
744 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAPTAGRAM PIPED W/S SCHEME, T.W. No. V & VI, Block: Chinsurah Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000352/2024-2025 | 1457/ED | 25/07/2024 | 90 | D. K. ELECTRIC | 22.19 | 0 | 70
745 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Saptagram water supply scheme, T.W. No. IV, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001248/2022-2023 | 1318/ED | 17/08/2022 | 90 | M.S.C. ENTERPRISE | 7.28 | 0 | 0
746 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
747 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kulihanda[SM/13345] W/S Sch., T/W No. - VII, Sukantanagar, Dt. - Hooghly, Ref. Id. - 503611685, Dt. - 8/04/2024, Application No. - 5004102924 under Pipulpati CCC, WBSEDCL | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00137/2024-2025 | 55 | 12/04/2024 | 0 | WBSEDCL | 8.56 | 0 | 0
748 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kulihanda W/S (Aug.)[SM/13345] Scheme, T/W No. - VIII,(Adarsha Nagar, Panditjir Dokan) under Bandel CCC, WBSEDCL, Ref. Id. - 503647843, Dt. - 17-05-2024, Application No. - 5004191804 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00514/2024-2025 | 177 | 30/05/2024 | 0 | WBSEDCL | 6.18 | 0 | 0
749 | Electrical | Chinsuria Sub-Division | Quotation bill for New Service Connection Kulihanda W/S. Sch. pH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00855/2022-2023 | 175 | 28/02/2023 | 0 | WBSEDCL | 4.33 | 0 | 0
750 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kulihanda W/S. Sch. TW-VI | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04243/2023-2024 | 420 | 10/11/2023 | 0 | WBSEDCL | 5.1 | 0 | 0
751 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000162/2022-2023 | 3497/ED | 30/12/2022 | 90 | H.K.DAS & CO. | 10.82 | 0 | 100
752 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kulihanda W/S. Sch. TW-IV, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001136/2022-2023 | 1037/ED | 28/06/2022 | 90 | STANDARD ELECTRICALS | 10.23 | 0 | 0
753 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car/Ambassador (BS-IV) for official use of the Chief Engineer (Electrical/Mechanical) Southern Zone, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001170/2023-2024 | 1072/HMSD | 11/05/2023 | 365 | ORIENTAL ENGINEERING CO. | 0.95 | 0 | 80
754 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery to be installed at Zone-VII, C (Dariapur) for Augmentation of Zone-VIII, A/B/C in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001060/2023-2024 | 4031/ED | 17/10/2023 | 749 | M/S P.P. ELECTRICALS | 109.28 | 0 | 20
755 | Electrical | Arambug Sub-Division | Quotation of new Service Connection for Gobindanagar Water supply Scheme,Zone-II,PH No-I Block-Arambag Dist-hooghly under Electrical Division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04022/2023-2024 | 314 | 03/10/2023 | 0 | WBSEDCL | 4.73 | 0 | 0
756 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000173/2022-2023 | 766/ED | 09/02/2023 | 90 | BARISAL TRADING CO. | 20.5 | 0 | 0
757 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-II, T.W. No. III, Block: Goghat-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002472/2023-2024 | 333/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
758 | Electrical | Arambug Sub-Division | Quotation of New service Connection at Shantipur w/s Scheme,Zone-II,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/14684) Application No-5004136393 Reference Id-503627261. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00327/2024-2025 | 96 | 06/05/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
759 | Electrical | Arambug Sub-Division | Quotation App. No.-5004182874 SM/14684 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00466/2024-2025 | 117 | 17/05/2024 | 0 | WBSEDCL | 13.85 | 0 | 0
760 | Electrical | Arambug Sub-Division | Additional Quotation for Shantipur w/s Scheme,Zone-II,PH no-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte,(SM/14684) Application No-100000124534 Reference Id-860319604 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02603/2024-2025 | 636 | 18/12/2024 | 0 | WBSEDCL | 0.91 | 0 | 0
761 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-II, T.W. No.- I & II, Block: Goghat-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000182/2022-2023 | 775/ED | 09/02/2023 | 996 | A.G. ENTERPRISE | 20.26 | 0 | 40
762 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Radhaballavpur W/S. Sch. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04564/2023-2024 | 573 | 27/12/2023 | 0 | WBSEDCL | 11.45 | 0 | 0
763 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Radhaballavpur W/S. Sch. TW-II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04565/2023-2024 | 572 | 27/12/2023 | 0 | WBSEDCL | 6.9 | 0 | 0
764 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RADHABALLAVPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000156/2024-2025 | 1179/ED | 14/06/2024 | 90 | BIJAN ENTERPRISE | 10.7 | 0 | 0
765 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Radhaballavpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000179/2022-2023 | 772/ED | 09/02/2023 | 90 | BIJAN ENTERPRISE | 20.26 | 0 | 0
766 | Electrical | RWS Howrah Sub-Division | QUOTATION OF NEW SERVICE CONNECTION FOR SONATALA W/S SCHEME, PH NO-I | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/02134/2023-2024 | 125 | 20/07/2023 | 0 | WBSEDCL | 2.58 | 0 | 0
767 | Electrical | RWS Howrah Sub-Division | QUOTATION OF NEW SERVICE CONNECTION FOR SONATALA W/S SCHEME, PH-II | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/02135/2023-2024 | 126 | 20/07/2023 | 0 | WBSEDCL | 4.2 | 0 | 0
768 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sonatala water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000262/2022-2023 | 929/ED | 22/02/2023 | 90 | TRIO CONCERN | 20.88 | 0 | 80
769 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dhasghara W/S. Sch. Z-I, TW-II & Z-ii, TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04947/2023-2024 | 676 & 677 | 18/01/2024 | 0 | WBSEDCL | 12.17 | 0 | 0
770 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05345/2023-2024 | 701 | 22/01/2024 | 0 | WBSEDCL | 12.21 | 0 | 0
771 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Dashghara W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05358/2023-2024 | 700 | 22/01/2024 | 0 | WBSEDCL | 9.7 | 0 | 0
772 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dashghara water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000252/2022-2023 | 919/ED | 22/02/2023 | 90 | H.K.DAS & CO. | 43.01 | 0 | 35
773 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection at Jangalpara W/S. Sch. PH-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00727/2023-2024 | 34 | 12/05/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
774 | Electrical | Srirampur Sub-Division | New service connection charges for Jangalpara w/s scheme, PH No.-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01159/2023-2024 | 87 | 12/07/2023 | 0 | WBSEDCL | 0.53 | 0 | 0
775 | Electrical | Srirampur Sub-Division | New service connection charges for Jangalpara w/s scheme, PH No.-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01160/2023-2024 | 85 | 12/07/2023 | 0 | WBSEDCL | 2.95 | 0 | 0
776 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangalpara water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001149/2022-2023 | 1501/ED | 28/03/2023 | 338 | INDRANI ENTERPRISE | 10.75 | 0 | 75
777 | Electrical | North 24 Pgs W/S Division I | Aug of Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas at Kharki OHR site.[SM/15816] | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/01824/2024-2025 | 444 | 05/09/2024 | 0 | WBSEDCL | 0.46 | 0 | 0
778 | Electrical | North 24 Pgs W/S Division I | Tentulia Existing OHR site quotation received for Load Enhancement Application No. 1007958975 Consumer Id 153161466 SM Code : 15816 | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/02121/2024-2025 | 562 | 11/11/2024 | 0 | WBSEDCL | 0.35 | 0 | 0
779 | Electrical | North 24 Pgs W/S Division I | Quotation for New Service Connection at Khilkapur OHR site SM Code: 15816 | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/02609/2024-2025 | 634 | 18/12/2024 | 0 | WBSEDCL | 6.96 | 0 | 0
780 | Electrical | North 24 Pgs W/S Division I | Quotation Bill for New Service Connection at Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/04594/2023-2024 | 592 | 29/12/2023 | 0 | WBSEDCL | 1.08 | 0 | 0
781 | Electrical | North 24 Pgs W/S Division I | Quotation Bill for New Service Connection at Berunanpukuria W/S. Sch. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/04650/2023-2024 | 620 | 08/01/2024 | 0 | WBSEDCL | 1.21 | 0 | 0
782 | Electrical | North 24 Pgs W/S Division I | Quotation Bill for New Service Connection at Kharu OHE Site | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/06153/2023-2024 | 785 | 20/02/2024 | 0 | WBSEDCL | 1.41 | 0 | 0
783 | Electrical | North 24 Pgs W/S Division I | Quotation Bill for New Service Connection at Beraberia OHR Site | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/06154/2023-2024 | 786 | 21/02/2024 | 0 | WBSEDCL | 0.97 | 0 | 0
784 | Electrical | North 24 Pgs W/S Division I | Quotation for Sarberia OHR site Application no: 1007488840 SM 15816 | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/06219/2023-2024 | 852 | 07/03/2024 | 0 | WBSEDCL | 2.05 | 0 | 0
785 | Electrical | North 24 Pgs W/S Division I | Surjapur OHR Site Customer ID: 152146528 SM 15816 | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/06501/2023-2024 | 903 | 19/03/2024 | 0 | WBSEDCL | 1.12 | 0 | 0
786 | Electrical | North 24 Pgs W/S Division I | Supplimentory Quotation for Load enhancement of Telenipara OHR site for Mangal Pandey Augmentation SM Code: 15816 | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/06532/2023-2024 | 905 | 21/03/2024 | 0 | WBSEDCL | 7.17 | 0 | 0
787 | Electrical | North 24 Pgs W/S Division I | Quotation for Load enhancement of Telenipara OHR site for Mangal Pandey Augmentation SM Code: 15816 | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/06533/2023-2024 | 906 | 21/03/2024 | 0 | WBSEDCL | 1.72 | 0 | 0
788 | Electrical | North 24 Pgs W/S Division I | Supplimentory Quotation for Load enhancement of Surjapur OHR site for Mangal Pandey Augmentation SM Code: 15816 | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | BILL/06534/2023-2024 | 907 | 21/03/2024 | 0 | WBSEDCL | 2.82 | 0 | 0
789 | Electrical | North 24 Pgs W/S Division I | Renovation of High Lift Pumping Machinery, MCC panel, Sub-station equipments along with SCADA system at Water Treatment Plant of Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001048/2023-2024 | 4020/ED | 17/10/2023 | 549 | B.T. PROJECT PVT. LTD. | 392.78 | 0 | 5
790 | Electrical | North 24 Pgs W/S Division I | Providing Electro Mechanical equipments for Augmentation of Intake of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001049/2023-2024 | 4021/ED | 17/10/2023 | 822 | ORIENTAL ENGINEERING CO. | 143.79 | 0 | 0
791 | Electrical | North 24 Pgs W/S Division I | Augmentation of Centrifugal Pumping Machinery at Boosting Station - I along with disinfection arrangement at different zones under Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001050/2023-2024 | 4022/ED | 17/10/2023 | 593 | ORIENTAL ENGINEERING CO. | 323.41 | 0 | 5
792 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, A (Kharu) in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001054/2023-2024 | 4026/ED | 17/10/2023 | 822 | ORIENTAL ENGINEERING CO. | 29.74 | 0 | 5
793 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001055/2023-2024 | 4027/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 30.05 | 0 | 10
794 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001056/2023-2024 | 4028/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 33.17 | 0 | 10
795 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, B (Malikapur) in Barasat-I Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001058/2023-2024 | 4029/ED | 17/10/2023 | 183 | A.G. ENTERPRISE | 55.55 | 0 | 0
796 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, B (Rautara) in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001059/2023-2024 | 4030/ED | 17/10/2023 | 810 | DEY ENTERPRISE | 57.7 | 0 | 25
797 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery to be installed at Zone-VII, C (Dariapur) for Augmentation of Zone-VIII, A/B/C in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001060/2023-2024 | 4031/ED | 17/10/2023 | 749 | M/S P.P. ELECTRICALS | 109.28 | 0 | 20
798 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, B (Tapanpur) in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001061/2023-2024 | 4032/ED | 17/10/2023 | 183 | ALPHA ENTERPRISE | 58.67 | 0 | 0
799 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, B (Telinipara) in Barrackpore-II Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001062/2023-2024 | 4033/ED | 17/10/2023 | 183 | S.P. CONSTRUCTION | 34.15 | 0 | 0
800 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001428/2023-2024 | 4889/ED | 27/12/2023 | 183 | BENGAL CONSTRUCTION | 59.48 | 0 | 0
801 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas at Zone- XIV A, (Dangadihila) in Barrackpore-II Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/001051/2023-2024 | 4023/ED | 17/10/2023 | 183 | R.N.S. TRADING | 57.03 | 0 | 0
802 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV, B (Ruiya) in Barrackpore-II Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/001053/2023-2024 | 4025/ED | 17/10/2023 | 183 | AHALYA ENGINEERING WORKS | 62.2 | 0 | 0
803 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Augmentation of Dharampur W/S Sch.[SM/15891], T/W No. - II, South Simla, Block - Chinsurah-Mogra Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599481, Dt. - 22-03-2024, Application No. - 5004078318 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00014/2024-2025 | 15 | 04/04/2024 | 0 | WBSEDCL | 7.75 | 0 | 0
804 | Electrical | Chinsuria Sub-Division | Supply of Fuel for 1(one) no Diesel Luxury Taxi on contract Carriage for the Office of the assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of March 2024. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00164/2024-2025 |  | 12/04/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
805 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of Submersible Pumping machinery and other Electrical/mechanical equipments etc. including allied works for Dharampur w/s scheme | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00872/2022-2023 | 178 | 02/03/2023 | 0 | H.K.DAS & CO. | 4.32 | 0 | 0
806 | Electrical | Chinsuria Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for DHARAMPUR w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00874/2022-2023 | 177 | 02/03/2023 | 0 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 2.72 | 0 | 0
807 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of Automatic Chlorinator for Dharampur water supply scheme, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00876/2022-2023 | 177 | 02/03/2023 | 0 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 0.76 | 0 | 0
808 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dharampur W/S Sch. , T/W No. -I (Aug.), Block - Chinsurah-Mogra, Dist. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03784/2023-2024 | 282 | 13/09/2023 | 0 | WBSEDCL | 0.64 | 0 | 0
809 | Electrical | Chinsuria Sub-Division | Hire Charges Bill for official use office of the Howrah Mechanical Sub-Division PHED | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000987/2023-2024 | 958/HmSD | 20/04/2023 | 365 | ARINDAM AUDDY | 5 | 0 | 1
810 | Electrical | Chinsuria Sub-Division | Car Hire Charges Bill for official use of the Howrah Mechanical Sub-Division PHED | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001026/2023-2024 | 958,HMSD | 20/04/2023 | 365 | ARINDAM AUDDY | 5 | 0 | 50
811 | Electrical | Chinsuria Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001103/2023-2024 | 2829/HMSD | 30/10/2023 | 182 | ARINDAM AUDDY | 0.86 | 0 | 15
812 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Dharampur water supply scheme, T.W. No. I & II, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001357/2023-2024 | 4693/ED | 08/12/2023 | 90 | BISALAXMI ENTERPRISE | 21.99 | 0 | 49
813 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kanpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001151/2022-2023 | 1503/ED | 28/03/2023 | 90 | BISALAXMI ENTERPRISE | 10.73 | 0 | 0
814 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dakshin Rasulpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001147/2022-2023 | 1499/ED | 28/03/2023 | 90 | KARUNAMOY ENGINEERING | 10.74 | 0 | 0
815 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Bhangamora W/S. Sch. TW-III | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03828/2023-2024 | 391 | 03/11/2023 | 0 | WBSEDCL | 7.9 | 0 | 0
816 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhangamora water supply scheme, T.W. No. I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001145/2022-2023 | 1497/ED | 28/03/2023 | 90 | KAMAKHYA ENTERPRISE | 10.69 | 0 | 0
817 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bighati w/s sch. (Zone - I), T/W -II, dt. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03626/2023-2024 | 223 | 28/08/2023 | 0 | WBSEDCL | 5.21 | 0 | 0
818 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bighati W/s Scheme, Zone - I, T/W - I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04124/2023-2024 | 380 | 25/10/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
819 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Bighati W/S. Sch. TW-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04242/2023-2024 | 423 | 10/11/2023 | 0 | WBSEDCL | 5.25 | 0 | 0
820 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000312/2022-2023 | 1242/ED | 06/03/2023 | 630 | ORIENTAL ENGINEERING CO. | 40.49 | 0 | 80
821 | Electrical | Arambug Sub-Division | Quotation of new service Connection for Naopara w/s Scheme,PH No-I Block-Khanakul-II, Dist-Hooghly under ED,PHE Dte(SM/16237) Application No-5004015680 Reference Id-503563156 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/06072/2023-2024 | 751 | 16/02/2024 | 0 | WBSEDCL | 0.2 | 0 | 0
822 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NAOPARA MINI W/S SCHEME, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000168/2024-2025 | 1191/ED | 14/06/2024 | 90 | MAA TARA CONSTRUCTION | 7.52 | 0 | 30
823 | Electrical | Arambug Sub-Division | Supply, Delivery & Installation of submersible Pumping Machinery & other allied electrical/mechanical equipments etc. incliding allied works for Hazipur W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | ORD/000522/2021-2022 | 555/ED | 23/03/2022 | 90 | GLACIER ENGINEERING CO. | 6.62 | 0 | 60
824 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Balidaha W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05064/2023-2024 | 682 | 19/01/2024 | 0 | WBSEDCL | 3.71 | 0 | 0
825 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balidaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000067/2023-2024 | 1922/ED | 15/05/2023 | 90 | D. K. ELECTRIC | 22.6 | 0 | 50
826 | Electrical | Howrah Sadar Sub-Division | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dakshin Panchla water supply scheme, T.W. No. I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000045/2023-2024 | 1731/ED | 19/04/2023 | 90 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0
827 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dakshin Panchla water supply scheme, T.W. No. II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000874/2023-2024 | 3447/ED | 11/08/2023 | 90 | BARISAL TRADING CO. | 10.74 | 0 | 0
828 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Mahisgot W/S. Sch. PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06151/2023-2024 | 794 | 22/02/2024 | 0 | WBSEDCL | 20.71 | 0 | 0
829 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Mahishgot water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000082/2023-2024 | 1999/ED | 19/05/2023 | 958 | AMITAVA CHAKRABORTY | 20.29 | 0 | 30
830 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037073/Quot/03 Reference ID- 503576717 SM Code- 18310 | Assistant Engineer | Junior Engineer (Civill) | BILL/06217/2023-2024 | 820 | 01/03/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
831 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036811/Quot/03 Reference ID- 503576702 SM Code- 18310 | Assistant Engineer | Junior Engineer (Civill) | BILL/06218/2023-2024 | 821 | 01/03/2024 | 0 | WBSEDCL | 3.87 | 0 | 0
832 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for POL water supply scheme, T.W. No.- I, II & III, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000813/2023-2024 | 3158/ED | 27/07/2023 | 90 | DAS ENTERPRISE | 30.48 | 0 | 0
833 | Electrical |  | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of February,2024 |  |  | BILL/00826/2024-2025 | 224 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0
834 | Electrical |  | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of MARCH,2024 |  |  | BILL/00827/2024-2025 | 225 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.16 | 0 | 0
835 | Electrical |  | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of April,2024 |  |  | BILL/00828/2024-2025 | 227 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0
836 | Electrical |  | Quotation for new service connection for source Augmentation of Udaynarayanpur Water Supply Scheme, Zone- I & II, TW NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18398), Reference Id- 106743785 Application no- 1008083381 |  |  | BILL/02060/2024-2025 |  | 03/10/2024 | 0 | WBSEDCL | 7.68 | 0 | 0
837 | Electrical |  | Quotation for new service connection for source Augmentation of Udaynarayanpur Water Supply Scheme, Zone- I & II, TW NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18398), Reference Id- 106743785 Application no- 1008083381 |  |  | BILL/02834/2024-2025 | 498 | 21/10/2024 | 0 | WBSEDCL | 6.9 | 0 | 0
838 | Electrical |  | Quotation for new service connection for Augmentation of Udaynaraynpur Zone-I & II Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. ( SM/18398), Reference Id- 106420083, Application no- 1007452782 |  |  | BILL/06587/2023-2024 | 912 | 21/03/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
839 | Electrical |  | Quotation for new service connection for Augmentation of Udaynaraynpur Zone-I & II Water Supply Scheme, PH NO- II in the district Howrah under Electrical Division, PHE Dte. ( SM/18398), Reference Id- 106420105, Application no- 1007452865 |  |  | BILL/06588/2023-2024 | 910 | 21/03/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
840 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Udaynarayanpur (Zone-I & II) water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000991/2023-2024 | 3845/ED | 04/10/2023 | 606 | M/S, GHOSH ENTERPRISE | 23.17 | 0 | 80
841 | Electrical |  | Supply, delivery and installation of voltage correcting device and other allied works for Udaynarayanpur water supply scheme, Zone- I, T.W. No. III, Dist.- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001624/2021-2022 | 539/HMSD | 17/03/2022 | 21 | C.M. ENTERPRISE | 2.74 | 0 | 90
842 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF UDAYNARAYANPUR PIPED W/S SCHEME, Zone - I & II, T.W. No. III, District - Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/002509/2023-2024 | 425/ED | 29/02/2024 | 90 | PERFECT AIRCONDITION | 10.75 | 0 | 0
843 | Electrical | Chinsuria Sub-Division | Supply, delivery, installation & Commissioning of Electro Mechanical machinery for Intermediate Pumping Station (IPS-I) to be installed at Boinchi Gram and Intermediate Pumping Station (IPS-2) to be installed at Damdama Gram under Balagarh-Pandua Surface Based Pipe Water Supply Scheme, in the Dist. of Hooghly under Electrical Division, P.H.E, Dte. | Assistant Engineer (Civil) |  | ORD/000007/2025-2026 | 660/ED | 24/04/2025 | 30 | M/S S.S. ENTERPRISE | 234.37 | 0 | 0
844 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182766 Reference Id-503644453. | Assistant Engineer | Junior Engineer (Civill) | BILL/00447/2024-2025 | 121 | 17/05/2024 | 0 | WBSEDCL | 4.54 | 0 | 0
845 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme, PH No-III Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182716 Reference Id-503644451. | Assistant Engineer | Junior Engineer (Civill) | BILL/00448/2024-2025 | 119 | 17/05/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
846 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme,PH No-IV Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004416593 Reference Id-503753758 | Assistant Engineer | Junior Engineer (Civill) | BILL/01984/2024-2025 | 475 | 01/10/2024 | 0 | WBSEDCL | 7.6 | 0 | 0
847 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Balundi w/s Scheme,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004415806 Reference Id-503753690 | Assistant Engineer | Junior Engineer (Civill) | BILL/01985/2024-2025 | 476 | 01/10/2024 | 0 | WBSEDCL | 8.08 | 0 | 0
848 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000130/2024-2025 | 1155/ED | 14/06/2024 | 90 | DEY ENTERPRISE | 10.75 | 0 | 0
849 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000131/2024-2025 | 1156/ED | 14/06/2024 | 90 | DEY ENTERPRISE | 10.75 | 0 | 0
850 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balundi water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000912/2023-2024 | 3583/ED | 28/08/2023 | 90 | M/S G P ENTERPRISE | 21.47 | 0 | 0
851 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bilaspur PWSS Zone-II, P.H. No.-III, Hooghly. Application No. 5004065667 Ref ID: 503592945 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00111/2024-2025 | 45 | 09/04/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
852 | Electrical | Srirampur Sub-Division | Fuel Charge | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00783/2022-2023 | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.17 | 0 | 0
853 | Electrical | Srirampur Sub-Division | Fuel Charge | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00784/2022-2023 | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0
854 | Electrical | Srirampur Sub-Division | car hire charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00785/2022-2023 | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.15 | 0 | 0
855 | Electrical | Srirampur Sub-Division | fuel charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00786/2022-2023 | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.07 | 0 | 0
856 | Electrical | Srirampur Sub-Division | Hire Charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00787/2022-2023 | 157 | 10/02/2023 | 0 | DEBASHISH GHOSH | 0.18 | 0 | 0
857 | Electrical | Srirampur Sub-Division | Fuel Charges | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00788/2022-2023 | 158 | 10/02/2023 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0
858 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bilaspur water supply scheme Zone-I, T.W. No. II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00856/2022-2023 |  | 27/02/2023 | 0 | A.S. ENTERPRISE | 10.23 | 0 | 0
859 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-II, TW-I, Dist- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000096/2022-2023 | 779/ED | 05/05/2022 | 90 | H.K.DAS & CO. | 10.5 | 0 | 0
860 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of S/P/M & other E/M allied works for Bilaspur W/S. Sch. Hooghly Z-II, TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000361/2022-2023 | 780/,ED | 05/05/2022 | 90 | TAMAL ENTERPRISE | 10.55 | 0 | 5
861 | Electrical | Srirampur Sub-Division | Supply & installation of LED board and outside display board for depicting details of pump/valve operators at Zone-I, P.H. No.I & II of Bilashpur w/s scheme, Dist.-Hooghly under ED, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000362/2022-2023 | 2410/HMSD | 30/12/2022 | 10 | DIPA CHHETRI | 0.84 | 0 | 0
862 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. with allied works for Bilaspur W/S. Sch. TW- II, Z-I, Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000862/2022-2023 | 913 /ED | 07/06/2022 | 90 | A.S. ENTERPRISE | 10.48 | 0 | 0
863 | Electrical | Srirampur Sub-Division | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipment etc, including allied works for Bilaspur W/S. Sch. Z-I, TW-I, Dist- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001165/2021-2022 | 778/ED | 05/02/2022 | 90 | M/S DAS ENTERPRISE | 10.52 | 0 | 0
864 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone-II, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002578/2023-2024 | 454/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 65
865 | Electrical | Srirampur Sub-Division | Electric Supply | Assistant Engineer (Civil) | Junior Engineer (Civill) | VCH/001992/2022-2023 | 13 | 04/07/2022 | 0 | WBSEDCL | 19.89 | 0 | 0
866 | Electrical | Chandannagar Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Auf. of Paschim Gopinathpur W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00059/2022-2023 | 121 | 28/12/2022 | 0 | WBSEDCL | 2.54 | 0 | 0
867 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Aug. of Paschin Gopinathpur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00906/2022-2023 | 184 | 10/03/2023 | 0 | WBSEDCL | 2.95 | 0 | 0
868 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. III, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000056/2022-2023 | 2047/ED | 01/12/2022 | 90 | MAHADEV ENTERPRISE | 10.17 | 0 | 30
869 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Gopinathpur water supply scheme T.W. No. IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000254/2022-2023 | 921/ED | 22/02/2023 | 90 | MOITRA ENGINEERING CO. | 10.68 | 0 | 0
870 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PURBA THAKURANICHAK PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000372/2024-2025 | 1455/ED | 25/07/2024 | 90 | M.S. ENTERPRISE | 22.21 | 0 | 0
871 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-II, Hooghly. Application No. 5004042700 Ref ID: 503581618 | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/00119/2024-2025 | 44 | 09/04/2024 | 0 | WBSEDCL | 10.61 | 0 | 0
872 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004066730 Ref ID: 503597305 | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/00236/2024-2025 | 87 | 23/04/2024 | 0 | WBSEDCL | 4.55 | 0 | 0
873 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-I, Hooghly. Application No. 5004034017 Ref ID: 503576013 | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/00237/2024-2025 | 86 | 23/04/2024 | 0 | WBSEDCL | 5.36 | 0 | 0
874 | Electrical | Srirampur Sub-Division | Quotation for new service connection of Bhogatipur W/S. Sch. PH-I | Assistant Engineer (Civil) | chanditala-I block Junior Engineer (Civill) | BILL/06052/2023-2024 | 739 | 08/02/2024 | 0 | WBSEDCL | 6.31 | 0 | 0
875 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of MajhuKhetra Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001296/2023-2024 | 4529/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0
876 | Electrical |  | Quotation money deposition for new service connection at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008188704 Reference ID- 106812203 SM Code- 18845 |  |  | BILL/02272/2024-2025 | BP-24-25-583 | 19/11/2024 | 0 | WBSEDCL | 4.19 | 0 | 0
877 | Electrical |  | Quotation money deposition for additional work at Beldubi w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 100000124155 Reference ID- 860319335 SM Code- 18845 |  |  | BILL/02531/2024-2025 | 610 | 05/12/2024 | 0 | WBSEDCL | 0.02 | 0 | 0
878 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Beldubi Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001304/2023-2024 | 4537/ED | 23/11/2023 | 554 | D. K. ELECTRIC | 10.74 | 0 | 95
879 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bauria water supply scheme, T.W. No. III, Block: Uluberia-I, District - Howrah under Electrical Division, PHE Dte. |  |  | ORD/001017/2023-2024 | 3878/ED | 06/10/2023 | 209 | MAA KALI ENTERPRISE | 10.74 | 0 | 70
880 | Electrical |  | Quotation of New Service Connection for Gopaldaha w/s Scheme,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/19015) Application No-5004148688, Reference Id-503632547 |  |  | BILL/00414/2024-2025 | 100 | 06/05/2024 | 0 | WBSEDCL | 12.59 | 0 | 0
881 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopaldaha water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001654/2023-2024 | 05/ED | 02/01/2024 | 90 | M/S CHANDIMATA ELECTRICALS | 20.49 | 0 | 20
882 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-I) water supply scheme, T.W. No.- I, II, III & IV, Block: Uluberia-II District- Howrah under Electrical Division, PHE Dte. | AE/Ulu | JE-USD | ORD/000911/2023-2024 | 3582/ED | 28/08/2023 | 90 | D. K. ELECTRIC | 42.71 | 0 | 0
883 | Electrical |  | Quotation money deposition for new service connection at Khanakul W/S Zone- I ,T.W No.-I , Hooghly APP. No.- 5004036875 SM/18645 |  |  | BILL/06213/2023-2024 | 824 | 01/03/2024 | 0 | WBSEDCL | 4.35 | 0 | 0
884 | Electrical |  | Quotation money deposition for new service connection at khanakul w/s scheme, zone-II, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036737/Quot/03 Reference ID- 503576720 SM Code- 18645 |  |  | BILL/06214/2023-2024 | 823 | 01/03/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
885 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000157/2024-2025 | 1180/ED | 14/06/2024 | 382 | M/S A.K BANERJEE | 10.73 | 0 | 50
886 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KHANAKUL PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000158/2024-2025 | 1181/ED | 14/06/2024 | 630 | M/S A.K BANERJEE | 10.74 | 0 | 10
887 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Khanakul water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000929/2023-2024 | 3600/ED | 28/08/2023 | 90 | M/S S.R. ENTERPRISE | 21.49 | 0 | 0
888 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAYRAMBATI PIPED W/S SCHEME Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001247/2023-2024 | 4497/ED | 23/11/2023 | 90 | BISALAXMI ENTERPRISE | 21.48 | 0 | 0
889 | Electrical |  | Quotation for new service connection for source Augmentation of EKTARPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18935), Reference Id- 503777877 Application no- 5004449206 |  |  | BILL/02273/2024-2025 | BP-24-25-581 | 19/11/2024 | 0 | WBSEDCL | 11.08 | 0 | 0
890 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001208/2023-2024 | 4486/ED | 23/11/2023 | 90 | CINZANO | 21.5 | 0 | 0
891 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DWARBASINI PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001212/2023-2024 | 4490/ED | 23/11/2023 | 647 | M/S S.R. ENTERPRISE | 21.81 | 0 | 90
892 | Electrical |  | Quotation for new service connection for source Augmentation of CHAPTA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18940), Reference Id- 503729663 Application no- 5004376500 |  |  | BILL/01968/2024-2025 | 473 | 01/10/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
893 | Electrical |  | Quotation for new service connection for source Augmentation of Chapta Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division,PHE Dte. ( SM/18940), Reference Id- 503751380 Application no- 5004412432 |  |  | BILL/02292/2024-2025 | BP-24-25-593 | 21/11/2024 | 0 | WBSEDCL | 8.08 | 0 | 0
894 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF CHAPTA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001213/2023-2024 | 4491/ED | 23/11/2023 | 770 | MAA KALI ENTERPRISE | 21.49 | 0 | 50
895 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Dihibatpur T/W-VI W/S scheme under Electrical Division PHE Dte. (SM/18670) | Assistant Engineer | Junior Engineer (Civill) | BILL/01615/2024-2025 | 373 | 12/08/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
896 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VI, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000159/2024-2025 | 1182/ED | 14/06/2024 | 90 | M/S CHANDIMATA ELECTRICALS | 10.73 | 0 | 0
897 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VII, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000160/2024-2025 | 1183/ED | 14/06/2024 | 90 | STANDARD ELECTRICALS | 10.75 | 0 | 0
898 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dihibatpur water supply scheme, T.W. No.- I, II & III, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000843/2023-2024 | 3411/ED | 10/08/2023 | 90 | B.T. PROJECT PVT. LTD. | 32.89 | 0 | 0
899 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibatpur water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002469/2023-2024 | 330/ED | 21/02/2024 | 90 | AMIT DAS | 10.72 | 0 | 0
900 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of KEOTA Piped Water Supply Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001279/2023-2024 | 4519/ED | 23/11/2023 | 90 | SUJOY RANJAN BHOWMICK | 10.74 | 0 | 0
901 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HASAMPUR Piped Water Supply Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001288/2023-2024 | 4520/ED | 23/11/2023 | 90 | APEX ENGINEERING & PROJECT CO. | 10.74 | 0 | 0
902 | Electrical |  | Quotation Bill for New Service Connection at Uttar Manashree W/S. Sch. |  |  | BILL/05563/2023-2024 | 703 | 24/01/2024 | 0 | WBSEDCL | 14.99 | 0 | 0
903 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Uttar Manasri water supply scheme, T.W. No. I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001219/2023-2024 | 4542/ED | 23/11/2023 | 586 | M/S DAS ENTERPRISE | 22.04 | 0 | 50
904 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF JAMGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001264/2023-2024 | 4509/ED | 23/11/2023 | 90 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 0 | 0
905 | Electrical |  | Quotation for new service connection for Hanral (S.Aug) T.W. - I [SM/18948] (Sekendarpur), Block - Polba-Dadpur, Dt. - Hooghly under WBSEDCL, Dadpur CCC, Ref. Id. -503739105, Dt. - 21-11-2024, Application No. - 5004394547 |  |  | BILL/02479/2024-2025 | 617 | 05/12/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
906 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of HANRAL Piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001267/2023-2024 | 4512/ED | 23/11/2023 | 630 | KUSHANI ENTERPRISE | 10.74 | 0 | 30
907 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-II, T.W. No. III, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001951/2023-2024 | 90/ED | 10/01/2024 | 540 | WIZARDTECH SOLUTION | 10.68 | 0 | 90
908 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Antpur PWSS P.H. No.-IV, Hooghly. Application No. 5004065652 Ref ID: 503592944 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00120/2024-2025 | 42 | 09/04/2024 | 0 | WBSEDCL | 5.37 | 0 | 0
909 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Antpur (Aug) water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002564/2022-2023 | 1321/ED | 17/08/2022 | 90 | M/S, GHOSH ENTERPRISE | 10.28 | 0 | 75
910 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ANTPUR PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002583/2023-2024 | 458/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 65
911 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00801/2022-2023 | 164 | 21/02/2023 | 0 | WBSEDCL | 7.85 | 0 | 0
912 | Electrical | Srirampur Sub-Division | Quatation Bill for New Service Connection of WBSEDCL at Jangipara W/S. Sch. PH-IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00802/2022-2023 | 164 | 21/02/2023 | 0 | WBSEDCL | 2.77 | 0 | 0
913 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jangipara water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000217/2022-2023 | 843/ED | 14/02/2023 | 90 | R.M.D TRADING. | 21.82 | 0 | 30
914 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000390/2024-2025 | 1474/ED | 25/07/2024 | 90 | SARVATAH PROJECTS PRIVATE LIMITED | 11.1 | 0 | 0
915 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANGIPARA PIPED W/S SCHEME, Zone-I, T.W. No. III, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002579/2023-2024 | 455/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 60
916 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Aug. of Kaknan W/S. Sch. TW-III Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00938/2022-2023 |  | 13/03/2023 | 0 | WBSEDCL | 3.65 | 0 | 0
917 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kaknan water supply scheme, T.W. No.- I, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000287/2022-2023 | 937/ED | 22/02/2023 | 922 | OSMAN SEKH | 10.75 | 0 | 83
918 | Electrical | North 24 Pgs W/S Division I | Quotation for New service connection at Mohanpur PWSS Head Works Site SM/10579 | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | BILL/06220/2023-2024 | 822 | 01/03/2024 | 0 | WBSEDCL | 5.43 | 0 | 0
919 | Electrical | North 24 Pgs W/S Division I | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MOHANPUR PIPED W/S SCHEME, T.W. No. IV, Block: Barrackpore-II, District - North 24 Pgs. under JJM Program under Electrical Division PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/002510/2023-2024 | 426/ED | 29/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 100
920 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05066/2023-2024 | 680 | 19/01/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
921 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Khajurdaha W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05713/2023-2024 | 706 | 25/01/2024 | 0 | WBSEDCL | 4.32 | 0 | 0
922 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khajurdaha water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000159/2022-2023 | 3495/ED | 30/12/2022 | 1555 | AHALYA ENGINEERING WORKS | 20.35 | 0 | 40
923 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001056/2023-2024 | 4028/ED | 17/10/2023 | 183 | WEST BENGAL ENGINEERING CO. | 33.17 | 0 | 10
924 | Electrical | Ulberia Sub-Division | QUOTATION FOR NEW POWER CONNECTION FOR CHANDRAPUR PWSS PH NO-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/02977/2023-2024 | 216 | 24/08/2023 | 0 | WBSEDCL | 7.33 | 0 | 0
925 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chandrapur water supply scheme, T.W. No. I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000284/2022-2023 | 934/ED | 22/02/2023 | 90 | KARUNAMOY ENGINEERING | 21.49 | 0 | 0
926 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Ghoraberia W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | BILL/04515/2023-2024 | 556 | 21/12/2023 | 0 | WBSEDCL | 6.69 | 0 | 0
927 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Ghoraberia W/S. Sch. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | BILL/04516/2023-2024 | 555 | 21/12/2023 | 0 | WBSEDCL | 4.24 | 0 | 0
928 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghoraberia water supply scheme, T.W. No.- I & II, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000141/2022-2023 | 3509/ED | 30/12/2022 | 90 | NUPUR CHANDRA HALDER | 21.45 | 0 | 80
929 | Electrical | RWS Howrah Sub-Division | Making of T.W. Foundation at Ghoberia water supply scheme, P.H No.- I, Dist-Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/002048/2024-2025 | 3976/HMSD | 21/08/2024 | 7 | NUPUR CHANDRA HALDER | 0.97 | 0 | 0
930 | Electrical | RWS Howrah Sub-Division | Additional works for Making of T.W. Foundation at Ghoraberia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/002059/2024-2025 | 5014/HMSD | 30/08/2024 | 7 | NUPUR CHANDRA HALDER | 0.68 | 0 | 0
931 | Electrical | RWS Howrah Sub-Division | Making of T.W. Foundation at Ghoraberia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/002060/2024-2025 | 5015/HMSD | 30/08/2024 | 7 | NUPUR CHANDRA HALDER | 0.94 | 0 | 0
932 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Natibpur w/s scheme, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004216541 Reference ID- 503658560 SM Code-12235 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01652/2024-2025 | 410 | 21/08/2024 | 0 | WBSEDCL | 7.79 | 0 | 0
933 | Electrical | Arambug Sub-Division | Quotation Money depostion for new service connection at Natibpur pwss, P.H No-I, Dist- Hooghly uned ED, PHED. App. No.-5004020953 SM/12235 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02301/2024-2025 | BP-24-25-598 | 21/11/2024 | 0 | WBSEDCL | 8.56 | 0 | 0
934 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Natibpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000089/2022-2023 | 3471/ED | 30/12/2022 | 913 | BARMAN ROY TRADERS | 21.9 | 0 | 40
935 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NATIBPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000167/2024-2025 | 1190/ED | 14/06/2024 | 90 | BARMAN ROY TRADERS | 10.47 | 0 | 0
936 | Electrical | Chinsuria Sub-Division | Durgapur PH__II Water supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/00456/2024-2025 |  | 14/05/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
937 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06044/2023-2024 | 743 | 08/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
938 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kamalpur W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/06045/2023-2024 | 744 | 08/02/2024 | 0 | WBSEDCL | 14.44 | 0 | 0
939 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamalpur water supply scheme, T.W. No.- I & II, Block: Dhaniakhali District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000149/2022-2023 | 3492/ED | 30/12/2022 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.6 | 0 | 0
940 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Madhusudanpur(S.Aug.) W/S Sch. , T/W No. -III (Nr. Tissu Bus stand) [SM/11167] under Mogra CCC, WBSEDCL, Ref Id. - 503586680, Dt. - 16/04/2024, Application No. - 5004053256, | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00192/2024-2025 | 80 | 19/04/2024 | 0 | WBSEDCL | 4.7 | 0 | 0
941 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Madhusudanpur water supply scheme TW No I Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000218/2022-2023 | 850/ED | 14/02/2023 | 567 | AMIT DAS | 10.75 | 0 | 90
942 | Electrical | Arambug Sub-Division | Additional Quotation of Bhadur w/s Scheme,Zone-I,PH No-3 Block-Goghat-I Dist-Hooghly under Electrical division,PHE Dte.(SM/11463) Reference Id-860301435 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00622/2024-2025 | 183 | 03/06/2024 | 0 | WBSEDCL | 1.61 | 0 | 0
943 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhadur w/s scheme,zone-II,TW No-II Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02129/2023-2024 | 119 | 20/07/2023 | 0 | WBSEDCL | 2.8 | 0 | 0
944 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Bhadur w/s Scheme,Zone-I,TW No-III Dist-Hooghly Under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02130/2023-2024 | 116 | 20/07/2023 | 0 | WBSEDCL | 6.86 | 0 | 0
945 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhadur water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000200/2022-2023 | 827/ED | 14/02/2023 | 90 | C.M.S. ENGINEERING CONCERN | 21.95 | 0 | 20
946 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
947 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
948 | Electrical | Howrah Sadar Sub-Division | Deposition of quotation money for domjur(zone-iv) dakshin jhapardaha( zone-ii) water supply scheme , P.H No.-I,Dist-Howrah umder ED, PHED. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00752/2023-2024 |  | 12/05/2023 | 0 | WBSEDCL | 0.73 | 0 | 0
949 | Electrical | Howrah Sadar Sub-Division | New service connection | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02058/2023-2024 | 108 | 19/07/2023 | 0 | WBSEDCL | 4.03 | 0 | 0
950 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Domjur(Zone-IV) w/s scheme, Dakshin Jhapordaha(Zone-II), Pwss, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1008185043 Reference ID- 106810747 SM Code- 13752 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02127/2024-2025 | 571 | 13/11/2024 | 0 | WBSEDCL | 5.47 | 0 | 0
951 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Dakshin Jhapardaha W/S. Sch. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04634/2023-2024 | 629 | 08/01/2024 | 0 | WBSEDCL | 3.61 | 0 | 0
952 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-IV) Dakshin Jhapardaha(Z-II) water supply scheme, T.W. No. I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000249/2022-2023 | 916/ED | 22/02/2023 | 820 | M.S. ENTERPRISE | 32.73 | 0 | 40
953 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, A (Kharu) in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001054/2023-2024 | 4026/ED | 17/10/2023 | 822 | ORIENTAL ENGINEERING CO. | 29.74 | 0 | 5
954 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
955 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
956 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, B (Telinipara) in Barrackpore-II Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/001062/2023-2024 | 4033/ED | 17/10/2023 | 183 | S.P. CONSTRUCTION | 34.15 | 0 | 0
957 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection at Amodghata w/s scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00840/2022-2023 | 174 | 28/02/2023 | 0 | WBSEDCL | 7.19 | 0 | 0
958 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000236/2022-2023 | 867/ED | 14/02/2023 | 90 | JOYSHREE CONCERN | 10.83 | 0 | 100
959 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Amodghata water supply scheme, T.W. No.- V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000278/2022-2023 | 945/ED | 22/02/2023 | 90 | JOYSHREE CONCERN | 10.83 | 0 | 0
960 | Electrical | Chandannagar Sub-Division | new service connection | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02600/2023-2024 | 164 | 03/08/2023 | 0 | WBSEDCL | 1.7 | 0 | 0
961 | Electrical | Chandannagar Sub-Division | new service connection | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02602/2023-2024 | 165 | 03/08/2023 | 0 | WBSEDCL | 3.25 | 0 | 0
962 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Bahir Khanda w/S Scheme,TW No-3 Block-Haripal Dist-Hooghly under ED,PHE Dte. (SM/13404) Application No-5003976156 Reference Id-503538913 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06473/2023-2024 | 900 | 19/03/2024 | 0 | WBSEDCL | 3.58 | 0 | 0
963 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bahirkhanda water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000126/2022-2023 | 3481/ED | 30/12/2022 | 60 | S.M. ELECTRICALS | 21.48 | 0 | 60
964 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bahir Khanda water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002482/2023-2024 | 342/ED | 21/02/2024 | 90 | JOYSHREE CONCERN | 10.58 | 0 | 20
965 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Patinan W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/04030/2023-2024 | 316 | 03/10/2023 | 0 | WBSEDCL | 8.55 | 0 | 0
966 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Patinan W/S. Sch. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/04569/2023-2024 | 574 | 27/12/2023 | 0 | WBSEDCL | 4.2 | 0 | 0
967 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Patinan water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000163/2022-2023 | 3546/ED | 30/12/2022 | 90 | M/S CHANDIMATA ELECTRICALS | 20.27 | 0 | 40
968 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
969 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/04599/2023-2024 | 605 | 03/01/2024 | 0 | WBSEDCL | 20.72 | 0 | 0
970 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Binogram W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/04607/2023-2024 | 606 | 03/01/2024 | 0 | WBSEDCL | 7.72 | 0 | 0
971 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Binagram water supply scheme, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000183/2022-2023 | 776/ED | 09/02/2023 | 90 | STANDARD ELECTRICALS | 22.4 | 0 | 50
972 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Ghatampur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04322/2023-2024 | 430,431,432,433 | 21/11/2023 | 0 | WBSEDCL | 15.55 | 0 | 0
973 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No.- I & II, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000185/2022-2023 | 778/ED | 09/02/2023 | 90 | C.M.S. ENGINEERING CONCERN | 23.74 | 0 | 97
974 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghatampur water supply scheme, T.W. No. III & IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000878/2023-2024 | 3451/ED | 11/08/2023 | 90 | C.M.S. ENGINEERING CONCERN | 23.25 | 0 | 97
975 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Bighati W/S Sch., Zone- II, T/W No. - III, Block - Singur, [SM/15249], under WBSEDCL, Khalisani CCC, Ref ID- 503803673, Dt. - 26-11-2024, Application No. - 5004481450, | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02526/2024-2025 | 608 | 05/12/2024 | 0 | WBSEDCL | 5.32 | 0 | 0
976 | Electrical | Chandannagar Sub-Division | Quotation bill of WBSEDCL security deposit for Bighati PWSS, TW No.- II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04478/2023-2024 | 524 | 13/12/2023 | 0 | WBSEDCL | 4.06 | 0 | 0
977 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bighati water supply scheme, Zone-I, T.W. No.- I & II and Zone-II, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000312/2022-2023 | 1242/ED | 06/03/2023 | 630 | ORIENTAL ENGINEERING CO. | 40.49 | 0 | 80
978 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Purba Gazipur W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/05721/2023-2024 | 708 | 25/01/2024 | 0 | WBSEDCL | 0.08 | 0 | 0
979 | Electrical | Ulberia Sub-Division | Quotation money deposition for new service connection at Joargarh pwss ,T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007613302 Reference ID- 106525750 SM Code- 15186 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,JE/USD,Junior Engineer5 | BILL/06654/2023-2024 | 23 | 05/04/2024 | 0 | WBSEDCL | 5.13 | 0 | 0
980 | Electrical | Ulberia Sub-Division | Quotation money deposition for new service connection at Joargarh pwss ,T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007614302 Reference ID- 106526159 SM Code- 15186 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,JE/USD,Junior Engineer5 | BILL/06655/2023-2024 |  | 28/03/2024 | 0 | WBSEDCL | 4.9 | 0 | 0
981 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Joargarh water supply scheme, T.W. No. I, II & III, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,JE/USD,Junior Engineer5 | ORD/000026/2023-2024 | 1703/ED | 18/04/2023 | 90 | H.K.DAS & CO. | 32.55 | 0 | 0
982 | Electrical | Howrah Mechanical Sub-Division | Quotation for New Service Connection at Manirampur Mini W/S. Sch. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04666/2023-2024 | 650 | 10/01/2024 | 0 | WBSEDCL | 0.08 | 0 | 0
983 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Borhal w/s scheme, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004065635 Reference ID- 503592946 SM Code- 16449 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00487/2024-2025 | 146 | 22/05/2024 | 0 | WBSEDCL | 4.57 | 0 | 0
984 | Electrical | Srirampur Sub-Division | Borhal Z-I P H NO-3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/02294/2023-2024 | 145 | 26/07/2023 | 0 | WBSEDCL | 4.55 | 0 | 0
985 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Borhal (Zone-I) water supply scheme, T.W. No. I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000015/2023-2024 | 1631/ED | 11/04/2023 | 90 | S.S. ENTERPRISES | 23.3 | 0 | 85
986 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002466/2023-2024 | 327/ED | 21/02/2024 | 842 | DEY ENTERPRISE | 20.85 | 0 | 45
987 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MORHAL PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002882/2023-2024 | 457/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 65
988 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-II, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04451/2023-2024 | 509 | 08/12/2023 | 0 | WBSEDCL | 10.63 | 0 | 0
989 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-I, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04452/2023-2024 | 510 | 08/12/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
990 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Gopalpur Piped W/S. Sch. Z-II, PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04579/2023-2024 | 577 | 27/12/2023 | 0 | WBSEDCL | 7.27 | 0 | 0
991 | Electrical | Srirampur Sub-Division | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. I & II Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000010/2023-2024 | 1626/ED | 11/04/2023 | 810 | UNITED ENTERPRISE | 21.83 | 0 | 80
992 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. III & IV, Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000880/2023-2024 | 3453/ED | 11/08/2023 | 90 | DAS ENTERPRISE | 21.49 | 0 | 50
993 | Electrical | Howrah Sadar Sub-Division | Power connection of reorganization at Polgustia w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 100000104716 Reference ID- 860294676 SM Code- 10143 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00079/2024-2025 | 36 | 09/04/2024 | 0 | WBSEDCL | 0.5 | 0 | 0
994 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Polgustia w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1007622375 Reference ID- 106532179 SM Code- 00343 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00151/2024-2025 | 56 | 12/04/2024 | 0 | WBSEDCL | 10.94 | 0 | 0
995 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Poulgusthia (Replacement) water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000110/2022-2023 | 719/ED | 03/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 0
996 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Poulgusthia (Replacement) water supply scheme, T.W. No. III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000884/2023-2024 | 3457/ED | 11/08/2023 | 90 | M/S G P ENTERPRISE | 10.76 | 0 | 90
997 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Malaypur water supply scheme TW No I and II Block Arambag, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000288/2022-2023 | 938/ED | 22/02/2023 | 875 | MAHADEV ENTERPRISE | 21.42 | 0 | 40
998 | Electrical | Chandannagar Sub-Division | Quotation money deposition for new service connection at Kulteghori w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004314314 Reference ID- 503702908 SM Code- 16564 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01407/2024-2025 | 349 | 31/07/2024 | 0 | WBSEDCL | 24.36 | 0 | 0
999 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kulteghori (Aug.) water supply scheme, T.W. No. I, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000077/2023-2024 | 1933/ED | 15/05/2023 | 90 | DAS ENTERPRISE | 11.48 | 0 | 30
1000 | Electrical | Chinsuria Sub-Division | Additional Quotation for new service connection at Badinan w/s sch. , P.H. No. III, Dist -Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00750/2023-2024 | 37 | 15/05/2023 | 0 | WBSEDCL | 0.48 | 0 | 0
1001 | Electrical | Chinsuria Sub-Division | Quatation bill for New service connection at Aug. of Badinan w/s scheme, P.H No.-3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00871/2022-2023 | 176 | 02/03/2023 | 0 | WBSEDCL | 4.74 | 0 | 0
1002 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Badinan W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04640/2023-2024 | 632 | 08/01/2024 | 0 | WBSEDCL | 5.16 | 0 | 0
1003 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000012/2023-2024 | 1628/ED | 11/04/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 11.41 | 0 | 99
1004 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Badinan water supply scheme, T.W. No. III, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000124/2022-2023 | 3480/ED | 30/12/2022 | 90 | INDIA ENTERPRISE | 10.64 | 0 | 90
1005 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000864/2023-2024 | 3436/ED | 11/08/2023 | 90 | BIDYUT KUMAR MUKHERJEE | 11.41 | 0 | 0
1006 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service connection for Bangalpur w/s scheme, Ph No-I, in the district Howrah under Electrical Division, PHE Dte. ( SM/16760 ) Reference Id- 106680402, Application no- 1007951594 | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | BILL/01369/2024-2025 | 333 | 30/07/2024 | 0 | WBSEDCL | 6.26 | 0 | 0
1007 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bangalpur water supply scheme, T.W. No.- I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000080/2023-2024 | 1997/ED | 19/05/2023 | 958 | C.M.S. ENGINEERING CONCERN | 35.16 | 0 | 35
1008 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - II, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503678884, dt. - 26-06-2024, Application No. - 5004264232. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00977/2024-2025 | 260 | 03/07/2024 | 0 | WBSEDCL | 13.18 | 0 | 0
1009 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Khorda Apurbapur [SM/18097] W/S Sch., T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref Id. - 503675586, dt. - 26-06-2024, Application No. - 5004257575. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00978/2024-2025 | 261 | 03/07/2024 | 0 | WBSEDCL | 14.47 | 0 | 0
1010 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Khordaa purbapur water supply scheme, T.W. No. I, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000072/2023-2024 | 1928/ED | 15/05/2023 | 655 | TAMAL ENTERPRISE | 11.65 | 0 | 50
1011 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Hijali W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/04588/2023-2024 | 595 | 29/12/2023 | 0 | WBSEDCL | 6.03 | 0 | 0
1012 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Hijali W/S. Sch. PH-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/04648/2023-2024 | 633 | 08/01/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
1013 | Electrical | Srirampur Sub-Division | Shifting of 11KV HTOH line at Hijali pump house No.-1 Application ID: 100000103017 Ref ID: 860295257 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/06502/2023-2024 | 899 | 19/03/2024 | 0 | WBSEDCL | 6.79 | 0 | 0
1014 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hijali water supply scheme, T.W. No. I & II, Block: Jangipara, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000069/2023-2024 | 1925/ED | 15/05/2023 | 90 | GLACIER ENGINEERING CO. | 23.4 | 0 | 25
1015 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037021/Quot/03 Reference ID- 503576711 SM Code- 18308 | Assistant Engineer | Junior Engineer (Civill) | BILL/06215/2023-2024 | 818 | 03/03/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
1016 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036968/Quot/03 Reference ID- 503576706 SM Code- 18308 | Assistant Engineer | Junior Engineer (Civill) | BILL/06216/2023-2024 | 819 | 01/03/2024 | 0 | WBSEDCL | 11.54 | 0 | 0
1017 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Udaypur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000817/2023-2024 | 3162/ED | 27/07/2023 | 90 | DEBJYOTI BASU | 21.36 | 0 | 0
1018 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for UDNA w/s Scheme, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18309) Application No-5004114171 Reference Id-503617472 | Assistant Engineer | Junior Engineer (Civill) | BILL/00233/2024-2025 | 83 | 22/04/2024 | 0 | WBSEDCL | 3.38 | 0 | 0
1019 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for UDNA water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000814/2023-2024 | 3159/ED | 27/07/2023 | 90 | MAA KALI ENTERPRISE | 20.23 | 0 | 100
1020 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Udna water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002471/2023-2024 | 332/ED | 21/02/2024 | 90 | MAA KALI ENTERPRISE | 21.44 | 0 | 20
1021 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004146914 Reference ID- 503632742 SM Code- 17176 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00437/2024-2025 | 128 | 17/05/2024 | 0 | WBSEDCL | 3.91 | 0 | 0
1022 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Jagannathbati w/s scheme, P.H. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004146792 Reference ID- 503632743 SM Code- 17176 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00444/2024-2025 | 133 | 17/05/2024 | 0 | WBSEDCL | 9.39 | 0 | 0
1023 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathbati water supply scheme, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000051/2023-2024 | 1795/ED | 24/04/2023 | 799 | AHALYA ENGINEERING WORKS | 20.26 | 0 | 60
1024 | Electrical | Chandannagar Sub-Division | Quation Money for Gauribati w/s scheme P.H.No-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02005/2023-2024 | 104 | 19/07/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
1025 | Electrical | Chandannagar Sub-Division | Gauribati water supply scheme,PHNo-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02305/2023-2024 | 140 | 25/07/2023 | 0 | WBSEDCL | 3.83 | 0 | 0
1026 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Gouribati W/S. Sch. TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/05984/2023-2024 | 733 | 05/02/2024 | 0 | WBSEDCL | 6.9 | 0 | 0
1027 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gauribati water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000081/2022-2023 | 3463/ED | 30/12/2022 | 90 | POLYCON ENGINEERS | 22.28 | 0 | 100
1028 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gouribati water supply scheme, T.W. No. III, Block: Tarakeswar, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002481/2023-2024 | 341/ED | 21/02/2024 | 90 | J.K. ENGINEERING CO. | 10.74 | 0 | 40
1029 | Electrical | Ulberia Sub-Division | Quotation Bill For New Service Connection at Rej. Amta. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/00795/2022-2023 | 160 | 15/02/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
1030 | Electrical | Ulberia Sub-Division | Quotation bill for New Service Connection at Rej. of Amta W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/00796/2022-2023 | 160 | 15/02/2023 | 0 | WBSEDCL | 11.41 | 0 | 0
1031 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Rej. of Amta W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/01566/2022-2023 | 200 | 17/03/2023 | 0 | WBSEDCL | 2.7 | 0 | 0
1032 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Rej. of Amta W/S. Sch. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/01568/2022-2023 | 200 | 17/03/2023 | 0 | WBSEDCL | 2.48 | 0 | 0
1033 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Ranapara W/S. Sch. Amta-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/03888/2023-2024 | 298 | 21/09/2023 | 0 | WBSEDCL | 5.12 | 0 | 0
1034 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, T.W. No.- III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000060/2023-2024 | 1612/ED | 10/04/2023 | 90 | D. K. ELECTRIC | 11.18 | 0 | 1
1035 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rejuvenation of AMTA water supply scheme, T.W. No. II (Replacement tubwell at PWD premises), Block: Amta-I, District - Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000064/2023-2024 | 1837/ED | 28/04/2023 | 90 | D. K. ELECTRIC | 8.36 | 0 | 25
1036 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, Zone - I, T.W. No. II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000106/2022-2023 | 587/ED | 02/02/2023 | 90 | D. K. ELECTRIC | 11.25 | 0 | 30
1037 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, Zone - I, T.W. No. I, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000107/2022-2023 | 588/ED | 02/02/2023 | 90 | D. K. ELECTRIC | 11.25 | 0 | 30
1038 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amta (Ranapara) water supply scheme, T.W. No.-II, Block: Amta-II, District - Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/001386/2023-2024 | 4736/ED | 15/12/2023 | 90 | D. K. ELECTRIC | 10.74 | 0 | 100
1039 | Electrical |  | Quotation Bill for New Service Connection at Chitnan W/S. Sch. TW-III |  |  | BILL/04517/2023-2024 | 562 | 22/12/2023 | 0 | WBSEDCL | 4.85 | 0 | 0
1040 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chitnan water supply scheme, T.W. No. III, Block: Amta-II, District: Howrah under Electrical Division, PHE Dte. |  |  | ORD/002475/2023-2024 | 336/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
1041 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New Connection of Shyampur T/W-IV W/S scheme under ED PHE Dte (SM/18347) | Assistant Engineer | Junior Engineer (Civill) | BILL/01356/2024-2025 | 338 | 30/07/2024 | 0 | WBSEDCL | 4.57 | 0 | 0
1042 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Shyampur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18347) | Assistant Engineer | Junior Engineer (Civill) | BILL/01613/2024-2025 | 372 | 12/08/2024 | 0 | WBSEDCL | 26.41 | 0 | 0
1043 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, T.W. No. V, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000165/2024-2025 | 1187/ED | 14/06/2024 | 90 | COOLING CARE CENTER | 10.74 | 0 | 0
1044 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyampur water supply scheme, T.W. No.- I, II, III & IV, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000820/2023-2024 | 3174/ED | 28/07/2023 | 644 | H.K.DAS & CO. | 43.01 | 0 | 25
1045 | Electrical |  | Quotation bill for new service connection charges at Panchghara PWSS P.H. No.-IV, Hooghly. Application No. 5004090927 Ref ID: 503606723 |  |  | BILL/00486/2024-2025 | 148 | 22/05/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
1046 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Panchghora water supply scheme, T.W. No. I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000993/2023-2024 | 3789/ED | 26/09/2023 | 90 | SRI KRISHNA NIRMAN | 10.74 | 0 | 80
1047 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PANCHGHORA PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/002577/2023-2024 | 453/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 65
1048 | Electrical |  | Quotation of New Service Connection for Mayapur w/s Scheme, PH No-II Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte. |  |  | BILL/00428/2024-2025 | 131 | 17/05/2024 | 0 | WBSEDCL | 4.32 | 0 | 0
1049 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. I, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000177/2024-2025 | 1201/ED | 14/06/2024 | 90 | WIZARDTECH SOLUTION | 10.75 | 0 | 0
1050 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. II, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000185/2024-2025 | 1202/ED | 14/06/2024 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0
1051 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAYAPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000186/2024-2025 | 1203/ED | 14/06/2024 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0
1052 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Par-Radhanagar | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/01884/2022-2023 | 228 | 29/03/2023 | 0 | WBSEDCL | 8.72 | 0 | 0
1053 | Electrical | RWS Howrah Sub-Division | Quotation bill for New Service Connection at Par-Radhanagar Water Supply Scheme. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/04051/2023-2024 | 331 | 06/10/2023 | 0 | WBSEDCL | 2.67 | 0 | 0
1054 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Per Radhanagr water supply scheme, T.W. No. III & IV, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000255/2022-2023 | 922/ED | 22/02/2023 | 404 | GLACIER ENGINEERING CO. | 21.83 | 0 | 80
1055 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF MANDARAN PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001251/2023-2024 | 4500/ED | 23/11/2023 | 90 | SANKAR PRASAD DUTTA & CO. | 21.71 | 0 | 0
1056 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme,Z-I,PH No-III Block-Arambag Dist-Hooghly under Electrical Division, PHE Dte.(SM/18668) Application No-5004097240 Reference Id-503608902 | Assistant Engineer | Junior Engineer (Civill) | BILL/00082/2024-2025 | 37 | 09/04/2024 | 0 | WBSEDCL | 3.72 | 0 | 0
1057 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18668) Application No-5004138271, Reference Id-503628273 | Assistant Engineer | Junior Engineer (Civill) | BILL/00416/2024-2025 | 94 | 06/05/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
1058 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I, PH No-4 Block-Arambag, Dist-Hooghly Under Electrical division, PHE Dte.(SM/18668) Application No-5004256486, Reference Id-503674894. | Assistant Engineer | Junior Engineer (Civill) | BILL/00976/2024-2025 | 255 | 03/07/2024 | 0 | WBSEDCL | 5.29 | 0 | 0
1059 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tirol (Zone-I) water supply scheme, T.W. No. I, II & III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000841/2023-2024 | 3409/ED | 10/08/2023 | 784 | WEST BENGAL ENGINEERING CO. | 32.24 | 0 | 60
1060 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04416/2023-2024 | 494 | 07/12/2023 | 0 | WBSEDCL | 12.83 | 0 | 0
1061 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04643/2023-2024 | 627 | 08/01/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
1062 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04644/2023-2024 | 626 | 08/01/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
1063 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Baligori W/S. Sch. PH-I, Z-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04646/2023-2024 | 628 | 08/01/2024 | 0 | WBSEDCL | 9.44 | 0 | 0
1064 | Electrical | Chandannagar Sub-Division | Additional Quotation Charge for Effecting New PHE Connection at PHE-2, Baligori, Monoharpur | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04853/2023-2024 | 674 | 17/01/2024 | 0 | WBSEDCL | 1.12 | 0 | 0
1065 | Electrical | Chandannagar Sub-Division | Quotation bill for new service connection at Baligori water supply scheme, Zone-I, P.H. No.-I, Hooghly Application No.- 100000101765 Referance ID: 860294205 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06261/2023-2024 | 860 | 11/03/2024 | 0 | WBSEDCL | 0.47 | 0 | 0
1066 | Electrical | Chandannagar Sub-Division | Additional quotation for effecting new service connection of Baligori Zone-II, P.H. No.-I Ref ID: 860293430 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06485/2023-2024 | 898 | 19/03/2024 | 0 | WBSEDCL | 0.12 | 0 | 0
1067 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-II, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000849/2023-2024 | 3417/ED | 10/08/2023 | 90 | ASHUTOSH DAS & CO. | 20.35 | 0 | 90
1068 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000850/2023-2024 | 3418/ED | 10/08/2023 | 90 | BINAPANI ENTERPRISE | 21.36 | 0 | 30
1069 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000871/2023-2024 | 3444/ED | 11/08/2023 | 90 | BINAPANI ENTERPRISE | 21.38 | 0 | 0
1070 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-II, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000872/2023-2024 | 3445/ED | 11/08/2023 | 90 | ASHUTOSH DAS & CO. | 20.35 | 0 | 0
1071 | Electrical |  | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, P.H No.-IV of Amritsal. App. No.-1007859284 Ref. ID.-106635058 SM/19186 |  |  | BILL/00958/2024-2025 | 259 | 03/07/2024 | 0 | WBSEDCL | 4.5 | 0 | 0
1072 | Electrical |  | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, P.H No.-III of Amritsal. App. No.-1007867663 SM/19186 |  |  | BILL/00965/2024-2025 | 258 | 03/07/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
1073 | Electrical |  | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 01/07/2024 to 31/07/2024 |  |  | BILL/01628/2024-2025 | 364 | 12/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1074 | Electrical |  | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.06.2024 to 30.06.2024 |  |  | BILL/01821/2024-2025 | 450 | 10/09/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0
1075 | Electrical |  | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.07.2024 to 31.07.2024 |  |  | BILL/01822/2024-2025 | BP-24-25-588 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0
1076 | Electrical |  | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. WB-04G-2822 01.08.2024 to 31.08.2024 |  |  | BILL/01994/2024-2025 | 470 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.21 | 0 | 0
1077 | Electrical |  | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.07.2024 to 31.07.2024 |  |  | BILL/02055/2024-2025 | 515 | 21/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1078 | Electrical |  | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.06.2024 to 30.06.2024 |  |  | BILL/02056/2024-2025 | 514 | 21/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0
1079 | Electrical |  | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. Car No. WB-19J-7094 From 01.08.2024 to 31.08.2024 |  |  | BILL/02057/2024-2025 | 512 | 21/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1080 | Electrical |  | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No.- WB-04G-2822 From - 01.09.2024 to 30.09.2024 |  |  | BILL/02082/2024-2025 | 528 | 28/10/2024 | 0 | DASHRATH KUMAR PRAJAPATI | 0.07 | 0 | 0
1081 | Electrical |  | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 From 01.09.2024 to 30.09.2024 |  |  | BILL/02083/2024-2025 | 530 | 28/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.17 | 0 | 0
1082 | Electrical |  | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1008027768 Reference ID- 106717102 SM Code- 19186 |  |  | BILL/02114/2024-2025 | 554 | 05/11/2024 | 0 | WBSEDCL | 14.39 | 0 | 0
1083 | Electrical |  | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1008027751 Reference ID- 106717103 SM Code- 19186 |  |  | BILL/02115/2024-2025 | 555 | 05/11/2024 | 0 | WBSEDCL | 14.39 | 0 | 0
1084 | Electrical |  | Quotation money deposition for new service connection Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks, Dist.-Howrah under PHE Dte. Application No- 1007786607 Reference ID- 106603564 SM Code- 19186 |  |  | BILL/02119/2024-2025 | 553 | 05/11/2024 | 0 | WBSEDCL | 9.85 | 0 | 0
1085 | Electrical |  | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks . App. No.-1007900847 Ref. ID.-106654842 SM/19186 |  |  | BILL/02130/2024-2025 | 569 | 13/11/2024 | 0 | WBSEDCL | 24.34 | 0 | 0
1086 | Electrical |  | Augmentation Of Surface Water Based Water Supply Scheme For Shyampur-I & Ii And Part Of Bagnan-I, Bagnan-Ii And Uluberia-I Blocks . App. No.-1008024203 Ref. ID.-106715772 SM/19186 |  |  | BILL/02131/2024-2025 | 568 | 13/11/2024 | 0 | WBSEDCL | 10.03 | 0 | 0
1087 | Electrical |  | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/04/2024 to 30/04/2024 Bill No.- 0107 |  |  | BILL/02268/2024-2025 | BP-24-25-586 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0
1088 | Electrical |  | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/05/2024 to 31/05/2024 Bill No.- 0246 |  |  | BILL/02269/2024-2025 | BP-24-25-587 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1089 | Electrical |  | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No.- WB-02AT-8617 01.08.2024 to 31.08.2024 |  |  | BILL/02270/2024-2025 | BP-24-25-589 | 19/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.14 | 0 | 0
1090 | Electrical |  | Quotation for new service connection in the district Howrah under Electrical Division, PHE Dte. ( SM/19186), Reference Id- 106776950 Application no- 1008136524 |  |  | BILL/02295/2024-2025 | BP-24-25-592 | 21/11/2024 | 0 | WBSEDCL | 17.75 | 0 | 0
1091 | Electrical |  | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. Car No. WB-04G-2822 From 01/10/2024 to 31/10/2024 |  |  | BILL/02332/2024-2025 | 622 | 06/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1092 | Electrical |  | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.06.2024 to 30.11.2024. VEHICLE No. WB-02AB-3954 |  |  | ORD/000055/2024-2025 | 999/AE-I/ED | 16/05/2024 | 183 | TRIDIP SARKAR | 0.87 | 0 | 0
1093 | Electrical |  | Hiring of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. |  |  | ORD/000283/2024-2025 | 1359/AE-I/ED | 21/06/2024 | 184 | DASHRATH KUMAR PRAJAPATI | 0.87 | 0 | 0
1094 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, Zone-I, T.W. No. I (Replacement), Block: Shyampur-I, District - Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000376/2024-2025 | 1463/ED | 25/07/2024 | 90 | DIPALI CONSTRUCTION | 11.1 | 0 | 90
1095 | Electrical |  | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-II, PHE Dte. |  |  | ORD/002386/2023-2024 | 3300/HMSD | 11/12/2023 | 182 | DEBASHISH GHOSH | 0.86 | 0 | 0
1096 | Electrical |  | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- 2, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004136093 Reference ID- 503627504 SM Code- 18772 |  |  | BILL/00530/2024-2025 | 180 | 30/05/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
1097 | Electrical |  | Quotation of New Service Connection for Chinra w/s Scheme, Zone-II,TW No-III Block-Khanakul-II Dist-Hooghly under Electrical Division Phe Dte.(SM/18772) Application No-5004383077 Reference Id-503732160 |  |  | BILL/01928/2024-2025 | 454 | 10/09/2024 | 0 | WBSEDCL | 3.57 | 0 | 0
1098 | Electrical |  | Quotation of New Service Connection for Chinra w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/18772) Application No-5003988265 Reference Id-503547190 |  |  | BILL/06060/2023-2024 | 759 | 16/02/2024 | 0 | WBSEDCL | 6.73 | 0 | 0
1099 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000147/2024-2025 | 1170/ED | 14/06/2024 | 90 | ANJAN ENTERPRISE | 10.71 | 0 | 0
1100 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000148/2024-2025 | 1171/ED | 14/06/2024 | 90 | R.K.ENTERPRISE | 10.74 | 0 | 0
1101 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000932/2023-2024 | 3611/ED | 29/08/2023 | 682 | MAHADEV ENTERPRISE | 22.26 | 0 | 30
1102 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Bhursit Bamunpara, TW-III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00908/2022-2023 |  | 09/03/2023 | 0 | WBSEDCL | 11.77 | 0 | 0
1103 | Electrical | Howrah Sadar Sub-Division |  | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/01996/2023-2024 |  | 14/07/2023 | 0 | WBSEDCL | 5 | 0 | 0
1104 | Electrical | Howrah Sadar Sub-Division | Additional Quotation money deposition for Bhurshit Bamunpara PWSS, P.H No.-III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/02864/2023-2024 |  | 17/08/2023 | 0 | WBSEDCL | 21.59 | 0 | 0
1105 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme T.W. No. New, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000250/2022-2023 | 917/ED | 22/02/2023 | 90 | ANIK & CO. | 10.69 | 0 | 70
1106 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme, T.W. No. IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000825/2023-2024 | 3221/ED | 03/08/2023 | 90 | ALAK KUMAR CHAKRABORTY | 10.85 | 0 | 70
1107 | Electrical | Chinsuria Sub-Division | Replacement of some electrical accessories, voltage correcting device and other allied works for Pandua water supply scheme, Zone-III, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000317/2022-2023 | 493/HMSD | 02/03/2023 | 30 | KARUNAMOY ENGINEERING | 3.06 | 0 | 0
1108 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Sekrahati W/S. Sch. TW-III, Howrah | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/01880/2022-2023 | 213 | 24/03/2023 | 0 | WBSEDCL | 2.98 | 0 | 0
1109 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shekrahati water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000248/2022-2023 | 915/ED | 22/02/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 65
1110 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT CHANPARAI W/S SCH., P.H. NO. - III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00782/2023-2024 | 53 | 31/05/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
1111 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanparai water supply scheme, T.W. No.- I, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000203/2022-2023 | 830/ED | 14/02/2023 | 259 | NITESH MANAGEMENT | 10.73 | 0 | 97
1112 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Polba[SM/10468] W/S Sch. , Zone - I, T/W No. - IV, (Nr. Kasundipara primary school), Block - Polba-Dadpur, under Polba CCC, WBSEDCL, Ref. Id. - 503595736, Dt. - 05/04/2024, Application No. - 5004071216, | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00121/2024-2025 | 35 | 09/04/2024 | 0 | WBSEDCL | 7.13 | 0 | 0
1113 | Electrical | Chinsuria Sub-Division | Quotation bill for security money of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00799/2022-2023 | 163 | 20/02/2023 | 0 | WBSEDCL | 2.81 | 0 | 0
1114 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection charges of WBSEDCL at Polba w/s scheme, Zone-II, P.H. No.-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00800/2022-2023 | 163 | 20/02/2023 | 0 | WBSEDCL | 12.44 | 0 | 0
1115 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Polba water supply scheme TW No I and II Block Polba Dadpur, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000221/2022-2023 | 852/ED | 14/02/2023 | 90 | S.P. CONSTRUCTION | 21.49 | 0 | 98
1116 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for POLBA PIPED W/S SCHEME, Zone-I, T.W. No. IV, Block: Polba Dadpur, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000379/2024-2025 | 1465/ED | 25/07/2024 | 90 | COOLING CARE CENTER | 11.1 | 0 | 95
1117 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kamarpukur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000219/2022-2023 | 844/ED | 14/02/2023 | 90 | SUTRADHAR TRADERS | 10.78 | 0 | 35
1118 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Chanditala PWSS Zone-II, P.H. No.-IV, Hooghly. Application No. 5004085812 Ref ID: 503603818 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00031/2024-2025 | 19 | 05/04/2024 | 0 | WBSEDCL | 6.27 | 0 | 0
1119 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Chanditala PWSS Zone-I, P.H. No.-V, Hooghly. Application No. 5004085765 Ref ID: 503603819 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00032/2024-2025 | 20 | 05/04/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
1120 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- III, T.W. NO- III, Dist.-Hooghly under PHE Dte. Application No- 5004091705 Reference ID- 503606735 SM Code- 10338 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00161/2024-2025 | 70 | 16/04/2024 | 0 | WBSEDCL | 8.21 | 0 | 0
1121 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Chanditala w/s scheme, Zone- I, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004099440 Reference ID- 503611397 SM Code- 18966 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00485/2024-2025 | 152 | 22/05/2024 | 0 | WBSEDCL | 3.84 | 0 | 0
1122 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection of WBSEDC at Chanditalaw/s scheme, T.W. No.-XII | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00777/2022-2023 | 149 | 08/02/2023 | 0 | WBSEDCL | 0.54 | 0 | 0
1123 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection of WBSEDC at Chanditala w/s scheme, T.W. No.-XI | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00778/2022-2023 | 149 | 08/02/2023 | 0 | WBSEDCL | 0.54 | 0 | 0
1124 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chanditala water supply scheme, T.W. No. X, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000101/2022-2023 | 3529/ED | 30/12/2022 | 90 | BISALAXMI ENTERPRISE | 10.66 | 0 | 0
1125 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chanditala water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000202/2022-2023 | 829/ED | 14/02/2023 | 687 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 0 | 95
1126 | Electrical | Srirampur Sub-Division | Augumention of Electro Mechanical Equipments and other electro mechanical accessories at Pump House under Barijhati GP and Garalgacha Gram Panchayet of Chanditala - II Block, Dist-Hooghly under Electrical Divisio, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001480/2023-2024 | 4892/ED | 27/12/2023 | 90 | D. K. ELECTRIC | 31.09 | 0 | 100
1127 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XII & XIII, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002504/2023-2024 | 420/ED | 29/02/2024 | 564 | DEY ENTERPRISE | 20.85 | 0 | 40
1128 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHANDITALA PIPED W/S SCHEME, T.W. No. XIV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/002576/2023-2024 | 452/ED | 05/03/2024 | 90 | D. K. ELECTRIC | 9.7 | 0 | 65
1129 | Electrical | Srirampur Sub-Division | Quatation Bill for Chanditala W/S. Sch. PH-X | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | VCH/002744/2022-2023 |  | 16/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0
1130 | Electrical | Srirampur Sub-Division | Quotation bill for Chanditala W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | VCH/002752/2022-2023 | 109 | 18/11/2022 | 0 | WBSEDCL | 0.66 | 0 | 0
1131 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Murgaberia W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | BILL/00848/2022-2023 | 170 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0
1132 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New service connection at Murgaberia W/S. Sch. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | BILL/00849/2022-2023 | 170 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0
1133 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Murgaberia water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000139/2022-2023 | 3516/ED | 30/12/2022 | 90 | BIJAN ENTERPRISE | 20.25 | 0 | 70
1134 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05715/2023-2024 | 704 | 25/01/2024 | 0 | WBSEDCL | 5.78 | 0 | 0
1135 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Rudrarani W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05718/2023-2024 | 705 | 25/01/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1136 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Gurbari W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05065/2023-2024 | 681 | 19/01/2024 | 0 | WBSEDCL | 3.25 | 0 | 0
1137 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gurbari water supply scheme, T.W. No. I & II, Block: Dhaniakhali District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000082/2022-2023 | 3464/ED | 30/12/2022 | 90 | A.G. ENTERPRISE | 21.58 | 0 | 0
1138 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Samanti PWSS P.H No- III , Dist-Howrah under ED PHED. Application No.-1007542321 dated- 17/02/2024 Ref. ID.- 106478203 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/06164/2023-2024 | 797 | 23/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
1139 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Samanti water supply scheme, T.W. No.- I, II, III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000153/2022-2023 | 3520/ED | 30/12/2022 | 90 | R.N.S. TRADING | 43.41 | 0 | 0
1140 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Baniara w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008236708 Reference ID- 106843119 SM Code- 11722 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/02596/2024-2025 | 632 | 18/12/2024 | 0 | WBSEDCL | 19.17 | 0 | 0
1141 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Baniyara W/S. Sch. TW-I & II | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/03760/2023-2024 | 256,257 | 05/09/2023 | 0 | WBSEDCL | 23.59 | 0 | 0
1142 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Baniyara W/S. Sch. TW-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/04128/2023-2024 | 383 | 25/10/2023 | 0 | WBSEDCL | 3.52 | 0 | 0
1143 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for for New Service Connection at Baniyara Porel W/S. Sch. TW-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/04315/2023-2024 | 429 | 17/11/2023 | 0 | WBSEDCL | 0.73 | 0 | 0
1144 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniara water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000079/2023-2024 | 1996/ED | 19/05/2023 | 1170 | SANKAR PRASAD DUTTA & CO. | 35.9 | 0 | 60
1145 | Electrical | Arambug Sub-Division | New Service Connection at Mandara W/S. Sch. PH-III | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00725/2023-2024 | 15 | 24/04/2023 | 0 | WBSEDCL | 9.72 | 0 | 0
1146 | Electrical | Arambug Sub-Division | New service connection of WBSEDCL for Mandra w/s scheme | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00798/2022-2023 | 161 | 16/02/2023 | 0 | WBSEDCL | 0.31 | 0 | 0
1147 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Mandara W/S. Sch. PH-IV | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01284/2022-2023 | 190 | 16/03/2023 | 0 | WBSEDCL | 2.76 | 0 | 0
1148 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mandra water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000038/2023-2024 | 1715/ED | 18/04/2023 | 90 | M/S A.K BANERJEE | 21.89 | 0 | 75
1149 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. V, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000128/2024-2025 | 1153/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0
1150 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MALAYPUR PIPED W/S SCHEME, T.W. No. VI, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000129/2024-2025 | 1154/ED | 14/06/2024 | 90 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0
1151 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ATGHARA PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000175/2024-2025 | 1199/ED | 14/06/2024 | 90 | EMCON | 10.74 | 0 | 0
1152 | Electrical | Howrah Mechanical Sub-Division | Quotation for new service connection at Purushottampur W/S Sch. , T/W No. - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/04126/2023-2024 | 381 | 25/10/2023 | 0 | WBSEDCL | 2.72 | 0 | 0
1153 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Purushattampur W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/04244/2023-2024 | 413 | 10/11/2023 | 0 | WBSEDCL | 3.4 | 0 | 0
1154 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purushottampur water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000166/2022-2023 | 3500/ED | 30/12/2022 | 90 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 21.49 | 0 | 80
1155 | Electrical | Hooghly Division | Mini Piped water Supply Scheme | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1156 | Electrical | Hooghly Division | Mini piped Water Supply scheme | Assistant Engineer Howrah mechanical Sub Division,Assistant Engineer(HQ) | Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1157 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Sitapur W/S. Sch. PH-II | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/04590/2023-2024 | 590 | 29/12/2023 | 0 | WBSEDCL | 7.22 | 0 | 0
1158 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Sitapur W/S. Sch. PH-I | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/04591/2023-2024 | 591 | 29/12/2023 | 0 | WBSEDCL | 6.37 | 0 | 0
1159 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sitapur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000160/2022-2023 | 3523/ED | 30/12/2022 | 1006 | DIPALI CONSTRUCTION | 21.37 | 0 | 60
1160 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-I Dist-Hooghly under ED, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01917/2023-2024 | 91 | 13/07/2023 | 0 | WBSEDCL | 5.05 | 0 | 0
1161 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Baradangal w/s Scheme,Zone-II,PH No-II District-Hooghly Under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01918/2023-2024 | 92 | 13/07/2023 | 0 | WBSEDCL | 4.6 | 0 | 0
1162 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Baradangal water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000198/2022-2023 | 825/ED | 14/02/2023 | 926 | OSMAN SEKH | 21.5 | 0 | 70
1163 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/sScheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical division,PHE Dte.(SM/13322). Application No-5004325249, Reference Id-503707789 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/01406/2024-2025 | 350 | 31/07/2024 | 0 | WBSEDCL | 7.6 | 0 | 0
1164 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Marakhana w/s Scheme,Zone-II,Ph No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13322) Application No-5004011194 Reference Id-503561404 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | BILL/06480/2023-2024 | 901 | 19/03/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
1165 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Marakhana water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3,Khanakul 2 Block Junior Engineer | ORD/000189/2022-2023 | 782/ED | 09/02/2023 | 90 | S.G. TECHNICAL SERVICES | 20.49 | 0 | 0
1166 | Electrical | Arambug Sub-Division | Quotation of New Service Connection For Selampur w/s Scheme,Zone-II,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/14685) Application No-5004431262 Reference Id-503764740 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02058/2024-2025 | 537 | 28/10/2024 | 0 | WBSEDCL | 4.39 | 0 | 0
1167 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034192 Reference Id-503574969. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06201/2023-2024 | 810 | 28/02/2024 | 0 | WBSEDCL | 4.41 | 0 | 0
1168 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme, Z-II,PH No-I Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/14685) Application No-5004034199 Reference Id-503574970 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06202/2023-2024 | 809 | 28/02/2024 | 0 | WBSEDCL | 4.48 | 0 | 0
1169 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000140/2024-2025 | 1166/ED | 14/06/2024 | 809 | S.S. ENTERPRISES | 10.95 | 0 | 0
1170 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sealdanga water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000028/2023-2024 | 1705/ED | 18/04/2023 | 90 | PADMA ENGINEERING CO. | 21.49 | 0 | 0
1171 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1172 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Harit water supply scheme, T.W. No.- I & II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000214/2022-2023 | 841/ED | 14/02/2023 | 90 | DEBJYOTI BASU | 21.49 | 0 | 50
1173 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Gobindanagar W/S. Sch. Z-I, PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04149/2023-2024 | 393 | 03/11/2023 | 0 | WBSEDCL | 3.97 | 0 | 0
1174 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Gobindanagar w/s scheme,Zone-I,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/15247) Application No-5004049800, Reference Id-503584072 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06239/2023-2024 | 839 | 01/03/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
1175 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gobindanagar water supply scheme, Zone-I, T.W. No. III & IV, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000879/2023-2024 | 3452/ED | 11/08/2023 | 90 | PERFECT AIRCONDITION | 20.49 | 0 | 0
1176 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme,Zone-I, PH No-I Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/15252) Application No-5004151889 Reference Id-503633694 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00412/2024-2025 | 95 | 06/05/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
1177 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selampur w/s Scheme,Zone-I,PH No-II,Block-Goghat-II,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15252) Application No-5004294581 Reference Id-503691996 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01172/2024-2025 | 312 | 22/07/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
1178 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELAMPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000139/2024-2025 | 1165/ED | 14/06/2024 | 90 | ANUPAMA ENGINEERING WORKS | 10.75 | 0 | 0
1179 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selampur water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000281/2022-2023 | 931/ED | 22/02/2023 | 769 | GHOSE ENGINEERING SYNDICATE | 22.1 | 0 | 30
1180 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at P.H No.-III of Bhandardah Pwss , Dist- howrah under ED PHED. App. No.-1007763810 SM/14197 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00468/2024-2025 | 120 | 17/05/2024 | 0 | WBSEDCL | 6.68 | 0 | 0
1181 | Electrical | Howrah Sadar Sub-Division | new service connection | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02065/2023-2024 | 127 | 20/07/2023 | 0 | WBSEDCL | 2.85 | 0 | 0
1182 | Electrical | Arambug Sub-Division | Quotation for New Service Connection at Mayapur W/S. Sch. Z=II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04611/2023-2024 | 610 | 04/01/2024 | 0 | WBSEDCL | 6.44 | 0 | 0
1183 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000025/2023-2024 | 1702/ED | 18/04/2023 | 90 | NUPUR CHANDRA HALDER | 20.8 | 0 | 0
1184 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sibrambati water supply Scheme [SM/15889],Zone - I, T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503588850, Dt. - 11-03-2024, Application No. - 5004057590 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06274/2023-2024 | 882 | 13/03/2024 | 0 | WBSEDCL | 5.7 | 0 | 0
1185 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Sibrambati W/S Sch., (Zone - I), T/W No. - II,[SM/15889] Block - Singur under Singur CCC, WBSEDCL, Ref. Id. - 503591781, Dt. - 12-03-2024, Application No. - 5004061900 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06469/2023-2024 | 893 | 18/03/2024 | 0 | WBSEDCL | 6.69 | 0 | 0
1186 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sibrambati water supply scheme, Zone-I, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001359/2023-2024 | 4695/ED | 08/12/2023 | 540 | A.K. ENTERPRISE | 22.43 | 0 | 70
1187 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Pratapnagar w/s Scheme,PH No-3, Block-Arambag, Dist-Hooghly under Electrical division,PHE Dte.(SM/15807) Application No-5004254598 Reference Id-503673919 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00850/2024-2025 | 248 | 24/06/2024 | 0 | WBSEDCL | 7.9 | 0 | 0
1188 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Pratapnagar water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000021/2023-2024 | 1698/ED | 18/04/2023 | 989 | GOENKA ENTERPRISE | 20.5 | 0 | 10
1189 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-III Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460458 Reference Id-503787369 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02276/2024-2025 | BP-24-25-579 | 19/11/2024 | 0 | WBSEDCL | 4.06 | 0 | 0
1190 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460466 Reference Id-503787366 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02592/2024-2025 | 628 | 18/12/2024 | 0 | WBSEDCL | 5.68 | 0 | 0
1191 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000151/2024-2025 | 1174/ED | 14/06/2024 | 90 | BARISAL TRADING CO. | 10.74 | 0 | 0
1192 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000152/2024-2025 | 1175/ED | 14/06/2024 | 90 | S.M. ELECTRICALS | 10.74 | 0 | 0
1193 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000208/2024-2025 | 1176/ED | 14/06/2024 | 90 | P.K. ENTERPRISE | 10.72 | 0 | 0
1194 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-II) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001143/2022-2023 | 1495/ED | 28/03/2023 | 90 | BARISAL TRADING CO. | 21.49 | 0 | 0
1195 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Bhandardaha W/S. Sch. TW-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04169/2023-2024 | 408 | 09/11/2023 | 0 | WBSEDCL | 2.37 | 0 | 0
1196 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhandardaha water supply scheme, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000068/2023-2024 | 1923/ED | 15/05/2023 | 360 | ANIK & CO. | 23.07 | 0 | 90
1197 | Electrical | Chandannagar Sub-Division | Quotation for New Service Connection at Kalachara W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04668/2023-2024 | 649 | 10/01/2024 | 0 | WBSEDCL | 1.47 | 0 | 0
1198 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalachhara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000070/2023-2024 | 1926/ED | 15/05/2023 | 90 | S.G. TECHNICAL SERVICES | 22.6 | 0 | 25
1199 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002470/2023-2024 | 331/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0
1200 | Electrical | Chandannagar Sub-Division | Quotation for service connection for Nawpara W/S Sch. , T/W -I, Block - Singur | Assistant Engineer (Civil) |  | BILL/02064/2023-2024 | 111 | 19/07/2023 | 0 | WBSEDCL | 2.63 | 0 | 0
1201 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Nawpara W/S. Sch. TW-II | Assistant Engineer (Civil) |  | BILL/04503/2023-2024 | 547 | 19/12/2023 | 0 | WBSEDCL | 15.9 | 0 | 0
1202 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nawpara water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000810/2023-2024 | 3063/ED | 12/07/2023 | 90 | POLYCON ENGINEERS | 21.71 | 0 | 92
1203 | Electrical | Chandannagar Sub-Division | Additional Quotation for new service connection at Bainchipota[SM/17289] W/S Sch., Zone - I, T/W No. - II under Nasibpur CCC, WBSEDCL, Ref. Id. - 860298080, Dt. - 23/04/2024, Application ID. - 100000106100 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00330/2024-2025 | 98 | 06/05/2024 | 0 | WBSEDCL | 0.25 | 0 | 0
1204 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Boinchipota W/s sch. , T/W - I, Block- Singur, Dist. -hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02062/2023-2024 | 110 | 19/07/2023 | 0 | WBSEDCL | 3.99 | 0 | 0
1205 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Boinchipota W/S Sch,, Zone - I. T/W No. - II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04125/2023-2024 | 382 | 25/10/2023 | 0 | WBSEDCL | 2.44 | 0 | 0
1206 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bainchipota water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000053/2023-2024 | 1797/ED | 24/04/2023 | 360 | MITRA ASSOCIATES | 20.2 | 0 | 97
1207 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Uttar Jhapordah W/S. Sch. Z-II, PH-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04325/2023-2024 | 438 | 23/11/2023 | 0 | WBSEDCL | 3.72 | 0 | 0
1208 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Uttar Jhapordah pwss, T.W No.-I , Dist-Howrah under ED PHED. App. No.-1007533769 Ref. ID.: 106472906 SM/17175 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/06203/2023-2024 | 813 | 28/02/2024 | 0 | WBSEDCL | 6.94 | 0 | 0
1209 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at UTTAR JHAPORDAH pwss, T.W No.-III Dist-Howrah, under PHED. App. No.-1007553536 Ref. ID.-106486515 SM/17175 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/06211/2023-2024 | 816 | 01/03/2024 | 0 | WBSEDCL | 15.45 | 0 | 0
1210 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-II) Uttar Jhapardaha water supply scheme, T.W. No. I, II, III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000057/2023-2024 | 1801/ED | 24/04/2023 | 90 | DEY ENTERPRISE | 42.99 | 0 | 0
1211 | Electrical |  | Quotation for new service connection charge at Mohisgot PWSS, Zone-I, TW - I |  |  | BILL/04366/2023-2024 | 457 | 01/12/2023 | 0 | WBSEDCL | 5.39 | 0 | 0
1212 | Electrical |  | Quotation for new service connection charge at Mohisgot PWSS, Zone-I, TW - II |  |  | BILL/04367/2023-2024 | 458 | 01/12/2023 | 0 | WBSEDCL | 6.15 | 0 | 0
1213 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisgot water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000914/2023-2024 | 3585/ED | 28/08/2023 | 672 | GLACIER ENGINEERING CO. | 20.6 | 0 | 10
1214 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001205/2023-2024 | 4483/ED | 23/11/2023 | 90 | M/S A.K BANERJEE | 21.49 | 0 | 0
1215 | Electrical |  | Quotation money deposition for new service connection at Laskarpur w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1007772477 Reference ID- 106595815 SM Code- 18842 |  |  | BILL/01147/2024-2025 | 269 | 08/07/2024 | 0 | WBSEDCL | 19.44 | 0 | 0
1216 | Electrical |  | Quotation money deposition for new service connection at Laskarpur w/s scheme, Zone- T.W. No.-VI, Dist.-Howrah under PHE Dte. Application No- 1007900745 Reference ID- 106654843 SM Code- 18842 |  |  | BILL/01273/2024-2025 | 332 | 30/07/2024 | 0 | WBSEDCL | 23.11 | 0 | 0
1217 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Laskarpur water supply scheme, T.W. No.- IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001018/2023-2024 | 3879/ED | 06/10/2023 | 90 | GHOSH AND GHOSH | 10.74 | 0 | 0
1218 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Laskarpur Piped Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001301/2023-2024 | 4534/ED | 23/11/2023 | 540 | DIPALI CONSTRUCTION | 21.49 | 0 | 30
1219 | Electrical |  | Quotation money deposition for new service connection at Gobindapur w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1007622411 Reference ID- 106532178 SM Code- 18843 |  |  | BILL/00149/2024-2025 | 54 | 12/04/2024 | 0 | WBSEDCL | 10.89 | 0 | 0
1220 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001019/2023-2024 | 3880/ED | 06/10/2023 | 90 | ANIK & CO. | 10.75 | 0 | 40
1221 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gobindapur water supply scheme, T.W. No.- I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001020/2023-2024 | 3881/ED | 06/10/2023 | 90 | OSMAN SEKH | 10.75 | 0 | 60
1222 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Gobindapur Piped Water Supply Scheme Block- Jagatballavpur District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001302/2023-2024 | 4535/ED | 23/11/2023 | 90 | P.K. ENGINEERING | 10.74 | 0 | 30
1223 | Electrical |  | Quotation of New Service Connection for Balipur w/s Scheme, Zone-I,TW No-III Block-Khanakul-I,Dist-Hooghly under Electrical Division PHE Dte. |  |  | BILL/03702/2023-2024 | 232 | 01/09/2023 | 0 | WBSEDCL | 3.1 | 0 | 0
1224 | Electrical |  | Quotation of New Service Connection for Balipur w/s scheme,zone-I,TW no-3, Block-khanakul-I,Dist-Hooghly under Electrical Division PHE Dte |  |  | BILL/03885/2023-2024 | 297 | 21/09/2023 | 0 | WBSEDCL | 10.61 | 0 | 0
1225 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Balipur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000934/2023-2024 | 3613/ED | 29/08/2023 | 90 | PURUSHOTTAM ENTERPRISE | 21.72 | 0 | 30
1226 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002470/2023-2024 | 331/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 0
1227 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-II,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208366 Reference Id-503655425. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00671/2024-2025 | 203 | 10/06/2024 | 0 | WBSEDCL | 3.71 | 0 | 0
1228 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Purba Krishnapur w/s Scheme, PH No-I,Block-Arambag, Dist-Hooghly under Electrical Division,PHE Dte.(SM/17625) Application No-5004208398 Reference Id-503655423. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00672/2024-2025 | 202 | 10/06/2024 | 0 | WBSEDCL | 4.86 | 0 | 0
1229 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Purbba Krishnapur water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000044/2023-2024 | 1730/ED | 19/04/2023 | 804 | CINZANO | 20.96 | 0 | 50
1230 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Nasibpur W/s Sch.,H/W Site(T/W No. - I), Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01922/2023-2024 | 89 | 12/07/2023 | 0 | WBSEDCL | 3.56 | 0 | 0
1231 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Nasibpur PWSS, TW - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04482/2023-2024 | 527 | 14/12/2023 | 0 | WBSEDCL | 0.73 | 0 | 0
1232 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Nasibpur water supply Scheme [SM/17627], T/W No. - III, Block - Singur, under Nasibpur CCC, WBSEDCL, Ref. Id. - 503584530, Dt. - 07-03-2024, Application No. - 5004050532 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06277/2023-2024 | 872 | 13/03/2024 | 0 | WBSEDCL | 2.63 | 0 | 0
1233 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000043/2023-2024 | 1729/ED | 19/04/2023 | 90 | ANIK & CO. | 20.5 | 0 | 45
1234 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Nasibpur water supply scheme, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002477/2023-2024 | 337/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.36 | 0 | 100
1235 | Electrical |  | Quotation Bill for New Service Connection at Kulgachia W/S. Sch. TW-IV |  |  | BILL/04120/2023-2024 | 409 | 09/11/2023 | 0 | WBSEDCL | 4.35 | 0 | 0
1236 | Electrical |  | Quotation Bill for New Service Connection at Kulgachia W/S. Sch. TW-III |  |  | BILL/04248/2023-2024 | 421 | 10/11/2023 | 0 | WBSEDCL | 29.37 | 0 | 0
1237 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentaion of Kulgacchi Water Supply Scheme Block- Uluberia - I District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001297/2023-2024 | 4530/ED | 23/11/2023 | 90 | D. K. ELECTRIC | 32.23 | 0 | 35
1238 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of BORHAL Piped Water Supply Scheme Block- Jangipara District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/002466/2023-2024 | 327/ED | 21/02/2024 | 842 | DEY ENTERPRISE | 20.85 | 0 | 45
1239 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF ABDULPUR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001255/2023-2024 | 4503/ED | 23/11/2023 | 90 | ESENCE ENGINEERING CONCERN | 10.72 | 0 | 0
1240 | Electrical |  | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- IV, T.W. No.-II, Dist.-Howrah under PHE Dte. Application No- 1007629084 Reference ID- 106535440 SM Code- 18747 |  |  | BILL/00324/2024-2025 | 109 | 09/05/2024 | 0 | WBSEDCL | 3.93 | 0 | 0
1241 | Electrical |  | Deposition of quotation money for new service connection at P.H No.-I of Baniban W/S scheme, Zone-IV, Dist- Howrah under ED PHED. App. No.-1007628595 SM/18747 |  |  | BILL/00453/2024-2025 | 132 | 17/05/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
1242 | Electrical |  | Quotation money deposition for new service connection at Baniban w/s scheme, Zone- IV, T.W. No.-03, Dist.-Howrah under PHE Dte. Application No- 1007829643 Reference ID- 106621794 SM Code- 18747 |  |  | BILL/01178/2024-2025 | 314 | 22/07/2024 | 0 | WBSEDCL | 8.04 | 0 | 0
1243 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-IV) water supply scheme, New Tubewell, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000937/2023-2024 | 3616/ED | 29/08/2023 | 90 | MAA TARA ENTERPRISE. | 10.17 | 0 | 0
1244 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban (Zone-II) water supply scheme, T.W. No.- I, II, III & IV, Block: Uluberia-II District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000938/2023-2024 | 3617/ED | 29/08/2023 | 90 | DEY ENTERPRISE | 45.74 | 0 | 0
1245 | Electrical |  | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- II in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503697548, Application no- 5004304981 |  |  | BILL/01373/2024-2025 | 337 | 30/07/2024 | 0 | WBSEDCL | 3.93 | 0 | 0
1246 | Electrical |  | Quotation for new service connection for source Augmentation of HARAL Water Supply Scheme, Zone-III, TW NO- I in the district Hooghly under Electrical Division, PHE Dte. (SM/18938), Reference Id- 503705756, Application no- 5004321019 |  |  | BILL/01632/2024-2025 | 374 | 12/08/2024 | 0 | WBSEDCL | 23.02 | 0 | 0
1247 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF HARAL PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001211/2023-2024 | 4489/ED | 23/11/2023 | 495 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.49 | 0 | 80
1248 | Electrical |  | Supply delivery and installation of voltage correcting device and other allied works for Dihibayra w/s scheme PH No. III District Hooghly under Electrical Division, PHE dte. |  |  | ORD/001527/2021-2022 | 544/HMSD | 17/03/2022 | 30 | WIZARDTECH SOLUTION | 2.36 | 0 | 100
1249 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibayra water supply scheme, T.W. No. III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001532/2021-2022 | 471_ED | 10/03/2022 | 90 | T S CONSTRUCTION | 6.4 | 0 | 50
1250 | Electrical |  | Quotation for new service connection for source Augmentation of DUMURDHA Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. (SM/18942), Reference Id- 503718763 Application no- 5004350181 |  |  | BILL/01798/2024-2025 | 425 | 01/10/2024 | 0 | WBSEDCL | 8.83 | 0 | 0
1251 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DUMURDHA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001261/2023-2024 | 4506/ED | 23/11/2023 | 495 | INDTECH ASSOCIATES. | 10.76 | 0 | 80
1252 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Gholdhuguri W/S. Sch. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02139/2023-2024 | 123 | 20/07/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
1253 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Gholedigrui w/s scheme, Zone- I, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004475357 Reference ID- 503799179 SM Code- 13334 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02304/2024-2025 | BP-24-25-596 | 21/11/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
1254 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Zone-I PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02733/2023-2024 | 171 | 10/08/2023 | 0 | WBSEDCL | 5.99 | 0 | 0
1255 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000186/2022-2023 | 779/ED | 09/02/2023 | 90 | TRIO CONCERN | 22.03 | 0 | 75
1256 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-I, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/002467/2023-2024 | 328/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
1257 | Electrical | Ulberia Sub-Division | New service connection at Haturie Kandarpur W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00846/2022-2023 | 171 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0
1258 | Electrical | Ulberia Sub-Division | New service connection at Haturie Kandarpur W/S. Sch. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00847/2022-2023 | 171 | 28/02/2023 | 0 | WBSEDCL | 0.55 | 0 | 0
1259 | Electrical | Ulberia Sub-Division | Quotation for new service connection for Haturie Kandarpur w/s scheme in the district Howrah under Electrical Division, PHE Dte. Reference Id- 106616939, Application no- 1007818619 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00848/2024-2025 | 249 | 24/06/2024 | 0 | WBSEDCL | 16.08 | 0 | 0
1260 | Electrical | Ulberia Sub-Division | Quotation for new service connection for Ground Water Based Pwss Haturie Kandarpur, in the district Howrah under Electrical Division, PHE Dte. Reference Id- 106616946, Application no- 1007818648 ( SM/11000) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/00849/2024-2025 | 246 | 24/06/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
1261 | Electrical | Ulberia Sub-Division | NEW SERVICE CONNECTION FOR HATURIA KANDARPUR PWSS, PUMP HOUSE-III | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/02061/2023-2024 | 109 | 19/07/2023 | 0 | WBSEDCL | 0.76 | 0 | 0
1262 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haturie-Kandarpur water supply scheme, T.W. No.- I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000157/2022-2023 | 3510/ED | 30/12/2022 | 90 | MAHADEV ENTERPRISE | 32.2 | 0 | 40
1263 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Makardah water supply scheme , P.H No-III, Dist- Howrah under ED PHED. App. No.-1007939058 SM/11159 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/01647/2024-2025 | 409 | 21/08/2024 | 0 | WBSEDCL | 13.4 | 0 | 0
1264 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for for New Service Connection at Makardaha W/S. Sch. PH-II | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04314/2023-2024 | 424 | 17/11/2023 | 0 | WBSEDCL | 9.12 | 0 | 0
1265 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Makardaha water supply scheme, T.W. No. III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000285/2022-2023 | 935/ED | 22/02/2023 | 90 | GLACIER ENGINEERING CO. | 21.83 | 0 | 30
1266 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Makardaha water supply scheme, T.W. No.- New, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000860/2023-2024 | 3432/ED | 11/08/2023 | 690 | GLACIER ENGINEERING CO. | 10.75 | 0 | 50
1267 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Oilipur W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/00055/2023-2024 | 03 | 13/04/2023 | 0 | WBSEDCL | 0.96 | 0 | 0
1268 | Electrical | Howrah Mechanical Sub-Division | Quotation Bill for New Service Connection at Aug. of Olipur W/S. Sch. Z-I & II, PH-III & I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/01882/2022-2023 | 220 | 27/03/2023 | 0 | WBSEDCL | 4.54 | 0 | 0
1269 | Electrical | Howrah Mechanical Sub-Division | QUOTATION for new Service Connection of Olipur W/S Scheme ,Zone-I,PH No-I, Block-Haripal,Dist-Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02000/2023-2024 | 101 | 19/07/2023 | 0 | WBSEDCL | 3.26 | 0 | 0
1270 | Electrical | Howrah Mechanical Sub-Division | Quotation for New Service Connection of Olipur W/S Scheme ,Zone-I,PH No-II District-Hooghly under ED,PHE DTe | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02001/2023-2024 | 100 | 19/07/2023 | 0 | WBSEDCL | 1.93 | 0 | 0
1271 | Electrical | Howrah Mechanical Sub-Division | New service connection | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/02598/2023-2024 | 163 | 03/08/2023 | 0 | WBSEDCL | 11.4 | 0 | 0
1272 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Olipur water supply scheme, T.W. No.- I, II, III & IV, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000039/2023-2024 | 1716/ED | 18/04/2023 | 90 | D. K. ELECTRIC | 42.97 | 0 | 45
1273 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for OLIPUR water supply scheme, Zone-II, TW No. IV, Block: Haripal, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/003079/2024-2025 | 477/ED | 18/03/2025 | 90 | SUBHRA ENTERPRISE | 11.3 | 0 | 0
1274 | Electrical | Chandannagar Sub-Division | Augmentation Of Solepur-Duttapur Water Supply Scheme. TW-3, Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01909/2022-2023 | 248 | 30/03/2023 | 0 | WBSEDCL | 2.82 | 0 | 0
1275 | Electrical | Chandannagar Sub-Division | Quation Money for Salepur Duttapur PH No-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02007/2023-2024 | 102 | 19/07/2023 | 0 | WBSEDCL | 3.35 | 0 | 0
1276 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Salepur Duttapur water supply scheme TW No I and II Block Tarakeswar, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000226/2022-2023 | 857/ED | 14/02/2023 | 90 | ALPHA ENTERPRISE | 21.49 | 0 | 45
1277 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05060/2023-2024 | 685 | 19/01/2024 | 0 | WBSEDCL | 11.72 | 0 | 0
1278 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Kanajoli W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05061/2023-2024 | 684 | 19/01/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
1279 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kanajoli water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000156/2022-2023 | 3493/ED | 30/12/2022 | 90 | CHATTERJEE BROTHERS | 20.25 | 0 | 35
1280 | Electrical | Chinsuria Sub-Division | Quotation of New Service Connection for Chalua w/s Scheme,PH No-II Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte(SM/12257) Application No-5003977943 Reference Id-503540606 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06103/2023-2024 | 763 | 16/02/2024 | 0 | WBSEDCL | 6.68 | 0 | 0
1281 | Electrical | Chinsuria Sub-Division | Quotation of New Service Connection for Chalua w/s Scheme,TW No-I,Block-Dhaniakhali Dist-Hooghly under ED,PHE Dte.(SM/12257) Application No-5003977900 Reference Id-503540601 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06104/2023-2024 | 764 | 16/02/2024 | 0 | WBSEDCL | 4.74 | 0 | 0
1282 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chalua water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000079/2022-2023 | 3461/ED | 30/12/2022 | 90 | M/S P.P. ELECTRICALS | 22.94 | 0 | 0
1283 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Dudhkalmi PWSS P.H. No.-II, Hooghly. Application No. 5004031077 Ref ID: 503576014 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/00039/2024-2025 | 24 | 05/04/2024 | 0 | WBSEDCL | 5.3 | 0 | 0
1284 | Electrical | Srirampur Sub-Division | Dudhkalmi w/s scheme,P H No 1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | BILL/04509/2023-2024 | 559 | 21/12/2023 | 0 | WBSEDCL | 5.64 | 0 | 0
1285 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dudhkalmi water supply scheme, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | chanditala-I block Junior Engineer (Civill),Junior Engineer2 | ORD/000144/2022-2023 | 3488/ED | 30/12/2022 | 90 | S.P. CONSTRUCTION | 21.37 | 0 | 0
1286 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dalimba W/S Sch., T/W No. - I, Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03783/2023-2024 | 283 | 13/09/2023 | 0 | WBSEDCL | 4.85 | 0 | 0
1287 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Dalimba W/S Sch., T/W No. - II, Block - Polba-Dadpur, Dist. - Hooghly. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04077/2023-2024 | 350 | 11/10/2023 | 0 | WBSEDCL | 3.11 | 0 | 0
1288 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dalimba water supply scheme, T.W. No.- I & II, Block: Polba - Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000142/2022-2023 | 3487/ED | 30/12/2022 | 810 | A.K. ENTERPRISE | 20.38 | 0 | 90
1289 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I & PH-II Howrah | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/01879/2022-2023 | 212 | 24/03/2023 | 0 | WBSEDCL | 15.82 | 0 | 0
1290 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000140/2022-2023 | 3514/ED | 30/12/2022 | 549 | M/S S R ENTERPRISE | 20.38 | 0 | 90
1291 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxuary Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00957/2024-2025 | 266 | 03/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1292 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte Car No.- WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01156/2024-2025 | 281 | 09/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1293 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte 01/07/2024 to 31/07/2024 WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01639/2024-2025 | 412 | 22/08/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1294 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.- WB-15C-5554 From 01.08.2024 to 31.08.2024 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01995/2024-2025 | 468 | 01/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1295 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No.WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02106/2024-2025 | 549 | 30/10/2024 | 0 | DILIP KUMAR GHOSH | 0.08 | 0 | 0
1296 | Electrical | Chandannagar Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01.09.2024 to 30.09.2024 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02107/2024-2025 | 550 | 30/10/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.16 | 0 | 0
1297 | Electrical | Chandannagar Sub-Division | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02471/2024-2025 | 623 | 18/12/2024 | 0 | DILIP KUMAR GHOSH | 0.02 | 0 | 0
1298 | Electrical | Chandannagar Sub-Division | Fuel consumption bill 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. Car No. WB-15C-5554 From 01/10/2024 to 31/10/2024 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02472/2024-2025 | 619 | 05/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
1299 | Electrical | Chandannagar Sub-Division | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04474/2023-2024 | 526 | 14/12/2023 | 0 | WBSEDCL | 8.35 | 0 | 0
1300 | Electrical | Chandannagar Sub-Division | Quotation bill of WBSEDCL new service connection charges at Aima Chapsara PWSS, TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04475/2023-2024 | 525 | 14/12/2023 | 0 | WBSEDCL | 2.72 | 0 | 0
1301 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Aima Chapsara water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000074/2022-2023 | 3456/ED | 30/12/2022 | 90 | TAMAL ENTERPRISE | 21.5 | 0 | 30
1302 | Electrical | Chandannagar Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer-II, Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000515/2024-2025 | 1645/AE-II/ED | 29/07/2024 | 184 | DILIP KUMAR GHOSH | 0.87 | 0 | 0
1303 | Electrical | Chandannagar Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer - II, Electrical Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/003371/2023-2024 | 218_AE-II_ED | 20/02/2024 | 182 | DILIP KUMAR GHOSH | 0.86 | 0 | 0
1304 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Gourangachak Pwss I & II | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/01885/2022-2023 | 227 | 29/03/2023 | 0 | WBSEDCL | 11.63 | 0 | 0
1305 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gauranga Chak water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000143/2022-2023 | 3508/ED | 30/12/2022 | 427 | P.P. CONCERN | 20.36 | 0 | 30
1306 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte.(SM/13762). Application No-5004034769 Reference Id-503576011 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00150/2024-2025 | 53 | 12/04/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
1307 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Hirapur w/s Scheme,Zone-II,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13762) Application no-5004034787 Reference Id-503576010 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00440/2024-2025 | 127 | 17/05/2024 | 0 | WBSEDCL | 6.13 | 0 | 0
1308 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Hirapur w/s scheme, Zone- II, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004210670 Reference ID- 503656455 SM Code- 13762 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00820/2024-2025 | 222 | 18/06/2024 | 0 | WBSEDCL | 3.09 | 0 | 0
1309 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000150/2024-2025 | 1173/ED | 14/06/2024 | 90 | PS & ASSOCIATES | 10.75 | 0 | 50
1310 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000187/2022-2023 | 780/ED | 09/02/2023 | 873 | M.D ENTERPRISE | 20.49 | 0 | 10
1311 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Barramnagar W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | BILL/05983/2023-2024 | 728 | 05/02/2024 | 0 | WBSEDCL | 8.74 | 0 | 0
1312 | Electrical | Ulberia Sub-Division | Quotation money deposition for new service connection at Barramnagar pwss , P.H No.-II, Dist-Howrah under PHED. App. No.-1007576971 Ref.ID: 106502484 SM/13750 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | BILL/06262/2023-2024 | 865 | 12/03/2024 | 0 | WBSEDCL | 27.26 | 0 | 0
1313 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Barramnagar water supply scheme, T.W. No.- I & II, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000122/2022-2023 | 3534/ED | 30/12/2022 | 805 | M/S S R ENTERPRISE | 20.38 | 0 | 60
1314 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1315 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
1316 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1317 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1318 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1319 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
1320 | Electrical | Arambug Sub-Division | Mini Piped Water Supply Scheme. | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01595/2024-2025 | BILL/01595/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 93.44 | 0 | 0
1321 | Electrical | RWS Howrah Sub-Division | Quotation bill for new service connection charge for Shibpur PWSS TW - I | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/04436/2023-2024 | 496 | 07/12/2023 | 0 | WBSEDCL | 12.3 | 0 | 0
1322 | Electrical | RWS Howrah Sub-Division | Quotation Bill for New Service Connection at Sibpur W/S. Sch. PH-II | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/04438/2023-2024 | 511 | 08/12/2023 | 0 | WBSEDCL | 10.12 | 0 | 0
1323 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sibpur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000258/2022-2023 | 925/ED | 22/02/2023 | 587 | ESENCE ENGINEERING CONCERN | 21.35 | 0 | 90
1324 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-2 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00020/2023-2024 | 04 | 13/04/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
1325 | Electrical | Howrah Sadar Sub-Division | Additional quotation money deposit for Nimabalia w/s scheme. P.H-I, dist-howrah under ED/PHED. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00747/2023-2024 | 35 | 12/05/2023 | 0 | WBSEDCL | 3.97 | 0 | 0
1326 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Nimabalia W/S. Sch. PH-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/01298/2022-2023 | 189 | 16/03/2023 | 0 | WBSEDCL | 7.62 | 0 | 0
1327 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for shifting of L.T O.H along with service cable at Nimabalia P.H No-I , Dist-Howrah under ED PHED. App. No.-100000101729 Ref I.D : 860293289 SM/13770 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/06282/2023-2024 | 879 | 13/03/2024 | 0 | WBSEDCL | 0.63 | 0 | 0
1328 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nimabalia water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000119/2022-2023 | 3544/ED | 30/12/2022 | 90 | GHOSE ENGINEERING SYNDICATE | 22.59 | 0 | 75
1329 | Electrical | Howrah Sadar Sub-Division | Making of T.W. Foundation at Nimabalia water supply scheme, P.H No.- II, Dist-Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/003571/2023-2024 | 3455/HMSD | 20/12/2023 | 7 | GHOSE ENGINEERING SYNDICATE | 0.96 | 0 | 0
1330 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05964/2023-2024 | 721 | 31/01/2024 | 0 | WBSEDCL | 8.41 | 0 | 0
1331 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Parjana W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05965/2023-2024 | 722 | 31/01/2024 | 0 | WBSEDCL | 7.3 | 0 | 0
1332 | Electrical | Chandannagar Sub-Division | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Parjana water supply scheme, T.W. No.- I, II & III, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000178/2022-2023 | 771/ED | 09/02/2023 | 90 | WEST BENGAL ENGINEERING CO. | 32.05 | 0 | 30
1333 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Khadinan water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000118/2022-2023 | 3543/ED | 30/12/2022 | 792 | ANJAN ENTERPRISE | 22.15 | 0 | 50
1334 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Refaitpur W/S Sch., Zone - I, T/w No. - I, Dist. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03782/2023-2024 | 305 | 26/09/2023 | 0 | WBSEDCL | 6.1 | 0 | 0
1335 | Electrical | Chinsuria Sub-Division | Quotattion for new service connection at Refaitpur W/S Sch., Zon - I, T/W -II, Block - Chinsurah-Mogra, Dt. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03980/2023-2024 | 315 | 03/10/2023 | 0 | WBSEDCL | 13.11 | 0 | 0
1336 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Refaitpur W/S. Sch. TW- I & II, & Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04136/2023-2024 | 388&389 | 02/11/2023 | 0 | WBSEDCL | 11.2 | 0 | 0
1337 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Refaitpur water supply scheme Zone I TW No I and II and Zone II TW No I and II Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000232/2022-2023 | 863/ED | 14/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 40.5 | 0 | 90
1338 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Refaitpur water supply scheme Zone I TW No I and II and Zone II TW No I and II Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000232/2022-2023 | 863/ED | 14/02/2023 | 90 | ORIENTAL ENGINEERING CO. | 40.5 | 0 | 90
1339 | Electrical | Ulberia Sub-Division | Quotation for new service connection for Matinala Water Supply Scheme, PH NO- II, in the district Howrah under Electrical Division, PHE Dte. ( SM/15285), Reference Id- 106538620 , Application no- 1007634961 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | BILL/00087/2024-2025 | 40 | 09/04/2024 | 0 | WBSEDCL | 4.07 | 0 | 0
1340 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Matinala water supply scheme, T.W. No.- I & II, Block: Bagnan-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000261/2022-2023 | 928/ED | 22/02/2023 | 90 | R.M.D TRADING. | 20.38 | 0 | 0
1341 | Electrical | Howrah Mechanical Sub-Division | Quotation money deposition for new service connection at Santoshpur w/s scheme, P.H. No.-3, Dist.-Hooghly under PHE Dte. Application No- 5004085290 Reference ID- 503609191 SM Code- 15793 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | BILL/00439/2024-2025 | 129 | 17/05/2024 | 0 | WBSEDCL | 6.12 | 0 | 0
1342 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Santoshpur water supply scheme, T.W. No. I, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000007/2023-2024 | 1623/ED | 11/04/2023 | 720 | UNIVERSAL ENTERPRISES | 10.75 | 0 | 100
1343 | Electrical | Howrah Mechanical Sub-Division | Quotation of New Service Connection of Bamonjol W/S Scheme(Aug) TW No-3 District-Hooghly under Electrical Division, PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | BILL/01998/2023-2024 | 113 | 19/07/2023 | 0 | WBSEDCL | 0.79 | 0 | 0
1344 | Electrical | Howrah Mechanical Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamonjol water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000013/2023-2024 | 1629/ED | 11/04/2023 | 90 | ANIK & CO. | 11.41 | 0 | 40
1345 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Krishnarampur PWSS P.H. No.-IV, Hooghly. Application No. 5004062824 Ref ID: 503597308 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00117/2024-2025 | 43 | 09/04/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
1346 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection at Krishnarampur W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00726/2023-2024 | 31 | 12/05/2023 | 0 | WBSEDCL | 2.37 | 0 | 0
1347 | Electrical | Srirampur Sub-Division | New service connection charges for Krishnarampur w/s scheme, PH No.-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01161/2023-2024 | 86 | 12/07/2023 | 0 | WBSEDCL | 2.37 | 0 | 0
1348 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnarampur water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000019/2023-2024 | 1635/ED | 11/04/2023 | 90 | D.S. ENTERPRISE | 11.41 | 0 | 70
1349 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNARAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000174/2024-2025 | 1198/ED | 14/06/2024 | 322 | P.P. CONCERN | 10.75 | 0 | 75
1350 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-IV, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235292 Reference ID- 503666262 SM Code- 16121 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00817/2024-2025 | 221 | 18/06/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
1351 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-III, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235310 Reference ID- 5004235310 SM Code- 16121 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00818/2024-2025 | 220 | 18/06/2024 | 0 | WBSEDCL | 5.73 | 0 | 0
1352 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-II, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004234490 Reference ID- 503666255 SM Code- 16121 | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00819/2024-2025 | 219 | 18/06/2024 | 0 | WBSEDCL | 7.27 | 0 | 0
1353 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-III | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00893/2022-2023 | 180 | 09/03/2023 | 0 | WBSEDCL | 2.81 | 0 | 0
1354 | Electrical | Arambug Sub-Division | "Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-IV Hooghly" | Assistant Engineer | Khanakul 2 Block Junior Engineer | BILL/00895/2022-2023 | 180 | 09/03/2023 | 0 | WBSEDCL | 2.75 | 0 | 0
1355 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sabalsinghapur water supply scheme, T.W. No. III, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/000869/2023-2024 | 3442/ED | 11/08/2023 | 90 | BISALAXMI ENTERPRISE | 10.74 | 0 | 25
1356 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/001074/2023-2024 | 4190/ED | 01/11/2023 | 90 | D. K. ELECTRIC | 10.83 | 0 | 40
1357 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Khanakul 2 Block Junior Engineer | ORD/002102/2022-2023 | 2048/ED | 01/12/2022 | 90 | BOSE & CHATTERJEE INDUSTRIES | 10.57 | 0 | 0
1358 | Electrical | Srirampur Sub-Division | Aniya water supply scheme,P H No-3 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/02293/2023-2024 | 142 | 25/07/2023 | 0 | WBSEDCL | 3.2 | 0 | 0
1359 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Aniya water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000011/2023-2024 | 1627/ED | 11/04/2023 | 90 | ANIK & CO. | 11.41 | 0 | 85
1360 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Patna Bhirabpur W/S Sch. T/W - I (Aug.), Dist. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03755/2023-2024 | 259 | 05/09/2023 | 0 | WBSEDCL | 5.61 | 0 | 0
1361 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patna Bhairavpur water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000020/2023-2024 | 1636/ED | 11/04/2023 | 90 | DIPA CHHETRI | 11.5 | 0 | 90
1362 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Dahar Kundu W/S. Sch.TW-I, Z-II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04583/2023-2024 | 588 | 28/12/2023 | 0 | WBSEDCL | 6.53 | 0 | 0
1363 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-II,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/15913) Application No-5004015927 Reference Id-503563368 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/06064/2023-2024 | 754 | 16/02/2024 | 0 | WBSEDCL | 16.1 | 0 | 0
1364 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DAHARKUNDU PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000204/2024-2025 | 1160/ED | 14/06/2024 | 90 | B.P. TRADING CORPORATION | 10.75 | 0 | 0
1365 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-II, T.W. No.- I & II, Block: Armbag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000310/2022-2023 | 1240/ED | 06/03/2023 | 787 | ALPHA ENTERPRISE | 20.47 | 0 | 30
1366 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT HANRAL W/S SCHEME, T/W NO. - III, DIST. - HOOGHLY | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00762/2023-2024 | 45 | 23/05/2023 | 0 | WBSEDCL | 10.88 | 0 | 0
1367 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Hanral W/S. Sch. PH-III, Z-I Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00894/2022-2023 | 179 | 09/03/2023 | 0 | WBSEDCL | 2.86 | 0 | 0
1368 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Hanral W/S Sch., Zone -I, T/W No. - III [SM/16119] under SM/Dadpur, WBSEDCL, Ref Id. - 503657583, dt. - 25-06-2024, Application No. - 5004214131 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00969/2024-2025 | 256 | 03/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
1369 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-I, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001374/2022-2023 | 969/ED | 25/02/2023 | 90 | TRIDENT ENTERPRISE | 11.08 | 0 | 90
1370 | Electrical | Chinsuria Sub-Division | Quotation for new service connection at Kalora W/S Sch.,Near Majhar, [SM/18099], T/W No. - I, Block - Polba-Dadpur under Bandel CCC, WBSEDCL | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06246/2023-2024 | 850 | 07/03/2024 | 0 | WBSEDCL | 10.7 | 0 | 0
1371 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalora water supply scheme, T.W. No. I & II, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000071/2023-2024 | 1927/ED | 15/05/2023 | 90 | MAA KALI ENTERPRISE | 22.96 | 0 | 50
1372 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Basa Mallikpur mini piped W/S. Sch. | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | BILL/04337/2023-2024 | 452 | 29/11/2023 | 0 | WBSEDCL | 0.32 | 0 | 0
1373 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bara Mallikpur Mini Piped W/S Scheme Block- Dhaniakhali District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil) | Dhaniakhali Block Junior Engineer (Civill) | ORD/001696/2023-2024 | 5175/ED | 28/12/2023 | 90 | RISHAV ENTERPRISE | 7.25 | 0 | 55
1374 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-II, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04645/2023-2024 | 622 | 08/01/2024 | 0 | WBSEDCL | 12.14 | 0 | 0
1375 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-I, Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04647/2023-2024 | 623 | 08/01/2024 | 0 | WBSEDCL | 8.9 | 0 | 0
1376 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Mundalika W/S. Sch. Z-I, PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04688/2023-2024 | 664 | 11/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
1377 | Electrical | Srirampur Sub-Division | Quotation for New service connection at Mundalika W/S. Sch.Z-I, PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06222/2023-2024 | 826 | 01/03/2024 | 0 | WBSEDCL | 5.4 | 0 | 0
1378 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mundalika water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000821/2023-2024 | 3176/ED | 28/07/2023 | 613 | R.N.S. TRADING | 43.65 | 0 | 10
1379 | Electrical | Chandannagar Sub-Division | Naita w/s scheme,P H No -I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03902/2023-2024 | 307 | 26/09/2023 | 0 | WBSEDCL | 4.39 | 0 | 0
1380 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for NAITA water supply scheme PH NO-II , Dist- Hooghly Application NO.-5004032139 Ref. ID- 503573584 SM/11291 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/06195/2023-2024 | 803 | 27/02/2024 | 0 | WBSEDCL | 6.57 | 0 | 0
1381 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Naita water supply scheme, T.W. No. I & II, Block: Tarakeswar, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000088/2022-2023 | 3470/ED | 30/12/2022 | 810 | GOENKA ENTERPRISE | 21.49 | 0 | 70
1382 | Electrical | Chandannagar Sub-Division | Quotation New Service Connection for Diara Water Supply Scheme, Block - Singur, Dist - hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02761/2023-2024 | 172 | 10/08/2023 | 0 | WBSEDCL | 3.96 | 0 | 0
1383 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Diara W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/05922/2023-2024 | 714 | 29/01/2024 | 0 | WBSEDCL | 8.07 | 0 | 0
1384 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Diara water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002462/2023-2024 | 324/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 20.85 | 0 | 90
1385 | Electrical | Ulberia Sub-Division | Quotation for new connection of Ghuteghari water supply scheme (Mini), Amta-I, Howrah Application No. 5004019125 Reference id: 503565825 SM/17198 UNDER JANGIPARA CCC, HOOGHLY | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/06260/2023-2024 | 858 | 11/03/2024 | 0 | WBSEDCL | 0.3 | 0 | 0
1386 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Madhabpur W/S. Sch. TW-I | Assistant Engineer | Junior Engineer (Civill) | BILL/04165/2023-2024 | 399 | 09/11/2023 | 0 | WBSEDCL | 3.86 | 0 | 0
1387 | Electrical | Arambug Sub-Division | Quotation for new service connection charge at Madhabpur PWSS, TW - II | Assistant Engineer | Junior Engineer (Civill) | BILL/04371/2023-2024 | 463 | 01/12/2023 | 0 | WBSEDCL | 8.57 | 0 | 0
1388 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MADHABPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000134/2024-2025 | 1159/ED | 14/06/2024 | 90 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0
1389 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Madhabpur water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000812/2023-2024 | 3157/ED | 27/07/2023 | 614 | RAJIB COMPANY | 21.49 | 0 | 30
1390 | Electrical | Arambug Sub-Division | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.12.2023 to 31.05.2024. | Assistant Engineer | Junior Engineer (Civill) | ORD/001947/2023-2024 | 876/AE-I/ED | 23/11/2023 | 182 | TRIDIP SARKAR | 0.87 | 0 | 10
1391 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Kumursa w/s Scheme,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18307) Application No-5004423612 Reference Id-503761600 | Assistant Engineer | Junior Engineer (Civill) | BILL/02034/2024-2025 | 513 | 21/10/2024 | 0 | WBSEDCL | 6.05 | 0 | 0
1392 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Kumursha W/S. Sch. | Assistant Engineer | Junior Engineer (Civill) | BILL/04410/2023-2024 | 488 | 06/12/2023 | 0 | WBSEDCL | 4.16 | 0 | 0
1393 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumursa water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000811/2023-2024 | 3156/ED | 27/07/2023 | 583 | ANJAN ENTERPRISE | 21.46 | 0 | 50
1394 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Selalpur w/s Scheme,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18596) Application No-5004135212, Reference Id-503626837 | Assistant Engineer | Junior Engineer (Civill) | BILL/00415/2024-2025 | 99 | 06/05/2024 | 0 | WBSEDCL | 7.66 | 0 | 0
1395 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Selalpur W/S. Sch. TW-I | Assistant Engineer | Junior Engineer (Civill) | BILL/04166/2023-2024 | 400 | 09/11/2023 | 0 | WBSEDCL | 3.98 | 0 | 0
1396 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELALPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000132/2024-2025 | 1157/ED | 14/06/2024 | 90 | M/S DILIP MITRA | 10.74 | 0 | 0
1397 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selalpur water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000915/2023-2024 | 3586/ED | 28/08/2023 | 551 | M/S DILIP MITRA | 21.5 | 0 | 30
1398 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Gangadharpur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004064346 Ref ID: 503597306 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00036/2024-2025 | 22 | 05/04/2024 | 0 | WBSEDCL | 5.4 | 0 | 0
1399 | Electrical | Srirampur Sub-Division | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of November, 2023. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00836/2024-2025 | 237 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0
1400 | Electrical | Srirampur Sub-Division | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of December, 2023. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00837/2024-2025 | 238 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
1401 | Electrical | Srirampur Sub-Division | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of January,2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00838/2024-2025 | 233 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
1402 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.05.2024 to 31.05.2024 WB-02AT-8617 Bill No : 0239 Bill Date : 31/05/2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00852/2024-2025 | 253 | 24/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0
1403 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.04.2024 to 30.04.2024 WB-02AT-8617 Bill No : 0100 Bill Date : 30/04/2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00853/2024-2025 | 250 | 24/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0
1404 | Electrical | Srirampur Sub-Division | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/03/2024 to 31/03/2024 Bill No.- 1469 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01398/2024-2025 | 353 | 31/07/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1405 | Electrical | Srirampur Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.07.2024 to 31.07.2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/01962/2024-2025 | 463 | 13/09/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
1406 | Electrical | Srirampur Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No. WB-11C-1616 01.08.2024 to 31.08.2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02101/2024-2025 | 563 | 11/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0
1407 | Electrical | Srirampur Sub-Division | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.09.2024 to 30.09.2024 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02102/2024-2025 | 564 | 11/11/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.15 | 0 | 0
1408 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No. WB-02AT-8617 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02302/2024-2025 | 605 | 05/12/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.06 | 0 | 0
1409 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charge at Gangadharpur, Zone-II, P.H. No.-II, District-Hooghly Application No.- 5004481099 Ref No.: 503803227 Scheme Code: SM/18623 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02309/2024-2025 | 611 | 05/12/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
1410 | Electrical | Srirampur Sub-Division | Gangadharpur w/s scheme,P H No 1 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04510/2023-2024 | 560 | 21/12/2023 | 0 | WBSEDCL | 3.67 | 0 | 0
1411 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Gangadharpur w/s scheme, Zone-II, PH No.-I, Hooghly. Application No.- 5004040971 Ref ID: 503579949 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06456/2023-2024 | 885 | 15/03/2024 | 0 | WBSEDCL | 5.59 | 0 | 0
1412 | Electrical | Srirampur Sub-Division | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000229/2024-2025 | 3054/HMSD | 20/06/2024 | 184 | SIDDHARTHA CHATTERJEE. | 0.87 | 0 | 0
1413 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gangadharpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000919/2023-2024 | 3590/ED | 28/08/2023 | 916 | GOENKA ENTERPRISE | 21.37 | 0 | 60
1414 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gangadharpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000920/2023-2024 | 3591/ED | 28/08/2023 | 826 | M/S PS & ASSOCIATES | 20.26 | 0 | 60
1415 | Electrical | Srirampur Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/003200/2023-2024 | 2502_/HMSD | 26/09/2023 | 152 | S.P. CONSTRUCTION | 0.72 | 0 | 0
1416 | Electrical |  | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008503 Reference Id-503559062 |  |  | BILL/06458/2023-2024 | 884 | 15/03/2024 | 0 | WBSEDCL | 8.68 | 0 | 0
1417 | Electrical |  | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008491 Reference Id-503559063 |  |  | BILL/06459/2023-2024 | 883 | 15/03/2024 | 0 | WBSEDCL | 4.21 | 0 | 0
1418 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000142/2024-2025 | 1168/ED | 14/06/2024 | 90 | SRI KRISHNA NIRMAN | 10.54 | 0 | 0
1419 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000933/2023-2024 | 3612/ED | 29/08/2023 | 642 | TRIO CONCERN | 17.37 | 0 | 15
1420 | Electrical | Srirampur Sub-Division | Quotation money deposition for new service connection at Jogmohanpur w/s scheme, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5003805642 Reference ID- 503409286 SM Code- 17632 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/01403/2024-2025 | 347 | 31/07/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
1421 | Electrical | Srirampur Sub-Division | Quotation bill for new service connection charges at Jagmohanpur w/s scheme, P.H. No.-I, Dist: Hooghly. Application No.-5004024656 Ref ID: 503569651 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/06264/2023-2024 | 863 | 12/03/2024 | 0 | WBSEDCL | 7.56 | 0 | 0
1422 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagmohanpur water supply scheme, T.W. No.- I & II, Block: Chanditala-I District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000052/2023-2024 | 1796/ED | 24/04/2023 | 648 | MASSK ENGINEERING WORKS. | 20.35 | 0 | 75
1423 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NATUNCHAR KRISHNABATI PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001206/2023-2024 | 4484/ED | 23/11/2023 | 90 | A.S. ENTERPRISE | 21.82 | 0 | 0
1424 | Electrical |  | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-I |  |  | BILL/04439/2023-2024 | 514 | 08/12/2023 | 0 | WBSEDCL | 3.75 | 0 | 0
1425 | Electrical |  | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-II |  |  | BILL/04440/2023-2024 | 513 | 08/12/2023 | 0 | WBSEDCL | 4.08 | 0 | 0
1426 | Electrical |  | Quotation Bill for New Service Connection at Debandi W/S. Sch. PH-III |  |  | BILL/04441/2023-2024 | 512 | 08/12/2023 | 0 | WBSEDCL | 4.27 | 0 | 0
1427 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Debandi water supply scheme, T.W. No.- I, II & III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000909/2023-2024 | 3580/ED | 28/08/2023 | 672 | S.S. ENTERPRISES | 34.16 | 0 | 60
1428 | Electrical | Arambug Sub-Division | Electric quot for Ghol Digrui Zone-II T/W-I W/S scheme | Assistant Engineer | Junior Engineer (Civill) | BILL/02719/2023-2024 | 166 | 04/08/2023 | 0 | WBSEDCL | 3.16 | 0 | 0
1429 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Z-II, TW-II | Assistant Engineer | Junior Engineer (Civill) | BILL/03827/2023-2024 | 285 | 18/09/2023 | 0 | WBSEDCL | 3.29 | 0 | 0
1430 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000815/2023-2024 | 3160/ED | 27/07/2023 | 90 | DIPALI CONSTRUCTION | 21.49 | 0 | 30
1431 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002468/2023-2024 | 329/ED | 21/02/2024 | 90 | DEY ENTERPRISE | 10.43 | 0 | 0
1432 | Electrical |  | Quotation money deposition for new service connection at Chikrand w/s scheme, Dist.-Hooghly under PHE Dte. Application No- 5004485180 Reference ID- 503806101 SM Code- 18967 v |  |  | BILL/02480/2024-2025 | 615 | 04/12/2024 | 0 | WBSEDCL | 10.74 | 0 | 0
1433 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of CHIKRAND ZONE-II Piped Water Supply Scheme Block- Chanditala-II District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001295/2023-2024 | 4527/ED | 23/11/2023 | 525 | DEBJYOTI BASU | 10.75 | 0 | 75
1434 | Electrical |  | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802582 Application no- 5004479726 |  |  | BILL/02527/2024-2025 | 602 | 05/12/2024 | 0 | WBSEDCL | 19.9 | 0 | 0
1435 | Electrical |  | Quotation for new service connection for source Augmentation of NAMAJGRAM Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18970), Reference Id- 503802583 Application no- 5004479665 |  |  | BILL/02528/2024-2025 | 612 | 05/12/2024 | 0 | WBSEDCL | 4.24 | 0 | 0
1436 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NAMAJGRAM PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001243/2023-2024 | 4493/ED | 23/11/2023 | 90 | M.S. ENTERPRISE | 21.51 | 0 | 0
1437 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF GUPTIPARA PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001253/2023-2024 | 4502/ED | 23/11/2023 | 90 | DIPA CHHETRI | 11.05 | 0 | 0
1438 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Srirampur T/W-II W/S scheme under Electrical Division PHE Dte. (SM/18643) | Assistant Engineer | Junior Engineer (Civill) | BILL/02653/2024-2025 | 637 | 18/12/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
1439 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIRAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000163/2024-2025 | 1186/ED | 14/06/2024 | 90 | SOMNATH ENTERPRISE | 10.66 | 0 | 0
1440 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Srirampur water supply scheme, Zone-I, T.W. No. I and Zone-II, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001990/2023-2024 | 118/ED | 15/01/2024 | 90 | PRADIP KUMAR DHABAL | 21.51 | 0 | 0
1441 | Electrical |  | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - I, (Near Sarat Library ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045949, Reference No. - 503581960 |  |  | BILL/06237/2023-2024 | 836 | 04/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
1442 | Electrical |  | Quotation for the new service connection at Debanandapur (Source Aug.) [SM/18975] W/S Sch. T/W No. - II, (Manaspur near Lalbaba Ashram ) Block- - Chinsura-Mogra, Hooghly under BANDEL CCC, WBSEDCL, Application No. - 5004045960, Reference No. - 503581923 |  |  | BILL/06238/2023-2024 | 840 | 04/03/2024 | 0 | WBSEDCL | 20.45 | 0 | 0
1443 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF DEBANANDAPUR PIPED W/S SCHEME Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001249/2023-2024 | 4498/ED | 23/11/2023 | 90 | R.N.S. TRADING | 22.03 | 0 | 40
1444 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF NATAGARI PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001250/2023-2024 | 4499/ED | 23/11/2023 | 90 | R.M.D TRADING. | 22.05 | 0 | 0
1445 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000161/2024-2025 | 1184/ED | 14/06/2024 | 90 | RISHAV ENTERPRISE | 10.75 | 0 | 0
1446 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000162/2024-2025 | 1185/ED | 14/06/2024 | 90 | M/S, GHOSH ENTERPRISE | 10.73 | 0 | 0
1447 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Pursurah Block Junior Engineer | ORD/002473/2023-2024 | 334/ED | 21/02/2024 | 435 | DEY ENTERPRISE | 10.43 | 0 | 35
1448 | Electrical |  | Quotation for new service connection for source Augmentation of BELUN Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18936 ), Reference Id- 503802585 Application no- 5004479701 |  |  | BILL/02529/2024-2025 | 613 | 05/12/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
1449 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001209/2023-2024 | 4487/ED | 23/11/2023 | 709 | C.M.S. ENGINEERING CONCERN | 21.64 | 0 | 50
1450 | Electrical |  | Quotation for new service connection at Naldanga(S.Aug.) [SM/18954], T/W NO. - I, under Pipulpati CCC, WBSEDCL, Ref. Id. - 503644538, dt.- 14-05-2024, Application No. - 5004183039 |  |  | BILL/00539/2024-2025 | 181 | 30/05/2024 | 0 | WBSEDCL | 8.65 | 0 | 0
1451 | Electrical |  | Quotation for additional quotation for Naldanga(S.Aug.) W/s Sch., T.W. No. - VII [SM/18954], Ref Id- 860316928, Application Id. - 100000122348, dt. - 30-10-2024 |  |  | BILL/02128/2024-2025 | 567 | 13/11/2024 | 0 | WBSEDCL | 0.81 | 0 | 0
1452 | Electrical |  | Quotation for new service connection at Naldanga (Source Aug.) water supply Scheme [SM/18954], T/W No. - VI(Mini), Block - Chinsurah-Mogra, under Bandel CCC, WBSEDCL, Ref. Id. - 503582004, Dt. - 29-02-2024, Application No. - 5004045934 |  |  | BILL/06281/2023-2024 | 878 | 13/03/2024 | 0 | WBSEDCL | 4.35 | 0 | 0
1453 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for NALDANGA MINI W/S SCHEME, Block: Chinsura Mogra, District - Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/000169/2024-2025 | 1192/ED | 14/06/2024 | 90 | TULIP ENTERPRISE | 7.53 | 0 | 95
1454 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Naldanga w/s scheme, T.W No. V, Block: Chinsurah Mogra, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001171/2023-2024 | 4444/ED | 17/11/2023 | 90 | MOITRA ENGINEERING CO. | 10.92 | 0 | 90
1455 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of NALDANGA piped W/S Scheme Block- ChinsurahMogra District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001278/2023-2024 | 4518/ED | 23/11/2023 | 90 | SUBHRA ENTERPRISE | 21.49 | 0 | 70
1456 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Ganeshbati W/S Scheme(Aug) TW No-4 District-Hooghly under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00754/2023-2024 | 42 | 17/05/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
1457 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Ganeshbati water supply scheme, T.W. No. I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001148/2022-2023 | 1500/ED | 28/03/2023 | 826 | ASHUTOSH DAS & CO. | 21.49 | 0 | 30
1458 | Electrical | RWS Howrah Sub-Division | Quotation bill for new service connection charge for Bedhi Chandrapur PWSS TW - I | AE/RWS | JE/BLK/amta2 | BILL/04434/2023-2024 | 498 | 07/12/2023 | 0 | WBSEDCL | 3.4 | 0 | 0
1459 | Electrical | RWS Howrah Sub-Division | Quotation bill for new service connection charge for Bedhi Chandrapur PWSS TW - II | AE/RWS | JE/BLK/amta2 | BILL/04435/2023-2024 | 497 | 07/12/2023 | 0 | WBSEDCL | 10.33 | 0 | 0
1460 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bedhi Chandrapur water supply scheme, T.W. No.- I & II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS | JE/BLK/amta2 | ORD/000822/2023-2024 | 3177/ED | 28/07/2023 | 431 | NEW RANBEE ENGINEERING | 21.38 | 0 | 85
1461 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, B (Tapanpur) in Amdanga Block of North 24 Parganas District. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/001061/2023-2024 | 4032/ED | 17/10/2023 | 183 | ALPHA ENTERPRISE | 58.67 | 0 | 0
1462 | Electrical |  | Quotation for new service connection for source Augmentation of AYMA NABABPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18941), Reference Id- 503802584 Application no- 5004479744 |  |  | BILL/02530/2024-2025 | 603 | 05/12/2024 | 0 | WBSEDCL | 4.01 | 0 | 0
1463 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF AYMANABABPUR PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001259/2023-2024 | 4505/ED | 23/11/2023 | 90 | A.G. ENTERPRISE | 21.49 | 0 | 0
1464 | Electrical |  | Quotation for new service connection at Sudarshan Water Supply Scheme [SM/18949](S.Aug.),T.W. No. - III, sarangpur, Block - Polba-Dadpur, Dt. - Hooghly, under Polba CCC, Ref. Id. - 503787954, Application No. - 5004461023, Dt.-11-11-2024 |  |  | BILL/02277/2024-2025 | BP-24-25-582 | 19/11/2024 | 0 | WBSEDCL | 6.27 | 0 | 0
1465 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of SUDARSHAN Piped W/S Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001273/2023-2024 | 4513/ED | 23/11/2023 | 533 | M/S, GHOSH ENTERPRISE | 21.49 | 0 | 99
1466 | Electrical | RWS Howrah Sub-Division | Supply, delivery and installation of voltage correcting device and other allied works for Pancharul water supply scheme, T.W. No. II (Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/001031/2022-2023 | 496/HMSD | 02/03/2023 | 30 | SUDIKSHA CONSTRUCTION | 3.95 | 0 | 100
1467 | Electrical | RWS Howrah Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pancharul water supply scheme, T.W. No.- II (Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/001033/2022-2023 | 2106/HMSD | 24/11/2022 | 30 | WIZARDTECH SOLUTION | 4.67 | 0 | 0
1468 | Electrical | RWS Howrah Sub-Division | Installation of departmentally supplied submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/001162/2022-2023 | 2147/HMSD | 29/11/2022 | 7 | DAS ENTERPRISE | 0.63 | 0 | 0
1469 | Electrical | RWS Howrah Sub-Division | Supply, delivery of submersible pumping machinery and other electrical/ mechanical equipments etc. for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/001163/2022-2023 | 2064/HMSD | 22/11/2022 | 7 | DAS ENTERPRISE | 0.97 | 0 | 0
1470 | Electrical | RWS Howrah Sub-Division | Supply, delivery of electrical/ mechanical equipments for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/001164/2022-2023 | 2063/HMSD | 22/11/2022 | 7 | DAS ENTERPRISE | 0.96 | 0 | 0
1471 | Electrical | Chinsuria Sub-Division | Supply, Delivery & Installation of S/P/M & other Electrical/Mechanical equipment etc. including allied works for Rajhat W/S. Sch. Z-II, TW-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000026/2022-2023 | 1036/ED | 28/06/2022 | 99 | INDIA ENTERPRISE | 9.21 | 0 | 100
1472 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-II, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000235/2022-2023 | 866/ED | 14/02/2023 | 90 | KUSHANI ENTERPRISE | 10.17 | 0 | 100
1473 | Electrical | Chinsuria Sub-Division | Supply & installation of LED board at Zone-II, P.H. No.-I & II of Rajhat water supply scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000600/2022-2023 | 2348/HMSD | 20/12/2022 | 10 | SUDHIKSHA CONSTRUCTION | 0.79 | 0 | 0
1474 | Electrical | Chinsuria Sub-Division | "Hire Charges Bill of V.No.- WB07J-3173 01.03.23 to 14.05.23" with fuel bill | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002170/2022-2023 | 215//AE-II/ED | 24/03/2023 | 30 | INDRANI ENTERPRISE | 0.62 | 0 | 1
1475 | Electrical | Chinsuria Sub-Division | 'Hire Charges Bill of V.No.- WB07J-317301.03.23 to 14.05.23' with fuel bill | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002176/2022-2023 | 215//AE-II/ED | 24/03/2023 | 30 | INDRANI ENTERPRISE | 0.63 | 0 | 1
1476 | Electrical | Chinsuria Sub-Division | Electric Supply | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | VCH/001993/2022-2023 | 14 | 07/07/2022 | 0 | WBSEDCL | 4.53 | 0 | 0
1477 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000242/2022-2023 | 2044/ED | 01/12/2022 | 90 | R.N.S. TRADING | 10.29 | 0 | 0
1478 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001223/2022-2023 | 1319/ED | 17/08/2022 | 90 | ANJAN ENTERPRISE | 9.78 | 0 | 100
1479 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Aug. of Saidpur W/S. Sch. Z-II, PH-III & II | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01883/2022-2023 | 218 | 27/03/2023 | 0 | WBSEDCL | 15.33 | 0 | 0
1480 | Electrical | Arambug Sub-Division | Power Connection for Saidpur W/S. Sch. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000002/2022-2023 | 5003400960/Quot/03 | 11/07/2022 | 365 | WBSEDCL | 13.34 | 0 | 0
1481 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Saidpur water supply scheme Zone I TW No I and Zone II TW No I Block Pursurah, District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000225/2022-2023 | 856/ED | 14/02/2023 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.48 | 0 | 65
1482 | Electrical | Arambug Sub-Division | Supply, Delivery & Installation of S/P/M & other E/M equipments etc. including allied works for Saidpur W/S. Sch. Z-I, TW-III. Hooghly | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/001142/2022-2023 | 1038/ED | 28/06/2022 | 90 | P.K. ENGINEERING | 10.19 | 0 | 0
1483 | Electrical | Arambug Sub-Division | Electric Supply | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | VCH/001994/2022-2023 | 15 | 15/07/2022 | 0 | WBSEDCL | 13.34 | 0 | 0
1484 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Tantisal W/S Sch. TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01894/2022-2023 | 226 | 29/03/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
1485 | Electrical | Arambug Sub-Division | Quotation for New Service Connection for Tantisal water Supply Scheme,TW No-II, Block-Khanakul-I,Dist-Hooghly under ED PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03620/2023-2024 | 221 | 25/08/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
1486 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Tantisal water supply scheme, T.W. No. I & II, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000103/2022-2023 | 3478/ED | 30/12/2022 | 90 | GHOSE ENGINEERING SYNDICATE | 22.37 | 0 | 60
1487 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at kamarpukur,Anur w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004182874 Reference ID- 503645387 SM Code- 09698 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00484/2024-2025 | 147 | 22/05/2024 | 0 | WBSEDCL | 5.57 | 0 | 0
1488 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Annur W/S. Sch. Z-II, PH-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00912/2022-2023 | 186 | 13/03/2023 | 0 | WBSEDCL | 4.44 | 0 | 0
1489 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000194/2022-2023 | 820/ED | 14/02/2023 | 90 | SUTRADHAR TRADERS | 10.78 | 0 | 0
1490 | Electrical | North 24 Pgs W/S Division I | Payment to WBSEDCL | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | BILL/01113/2023-2024 |  | 27/06/2023 | 0 | WBSEDCL | 1.66 | 0 | 0
1491 | Electrical | North 24 Pgs W/S Division I | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, A (Berunanpukuria) in Barasat-I Block of North 24 Parganas District. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/001052/2023-2024 | 4024/ED | 17/10/2023 | 748 | DIPALI CONSTRUCTION | 24.95 | 0 | 10
1492 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for Rudrapur W/S , P.H No-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00733/2023-2024 | 22 | 04/05/2023 | 0 | WBSEDCL | 0.69 | 0 | 0
1493 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Domjur, Rudrapur W/S. Sch. PH-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00840/2023-2024 | 64 | 08/06/2023 | 0 | WBSEDCL | 1.86 | 0 | 0
1494 | Electrical | Howrah Sadar Sub-Division | Deposition of additional quotation money for Rudrapur w/s scheme P.H No.-I ,Dist- Howrah under ED PHED. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00968/2023-2024 |  | 07/06/2023 | 0 | WBSEDCL | 1.86 | 0 | 0
1495 | Electrical | Howrah Sadar Sub-Division | New service connection for Rudrapur pwss P.H No.-II | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02569/2023-2024 | 159 | 03/08/2023 | 0 | WBSEDCL | 3.44 | 0 | 0
1496 | Electrical | Howrah Sadar Sub-Division | new service connection for Rudrapur pwss , P.H No.-III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02570/2023-2024 | 157 | 03/08/2023 | 0 | WBSEDCL | 14.97 | 0 | 0
1497 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Rudrapur W/S. Sch. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/02724/2023-2024 | 168 | 04/08/2023 | 0 | WBSEDCL | 0.33 | 0 | 0
1498 | Electrical | Howrah Sadar Sub-Division | Quotation bill for service connection charge for Rudrapur w/s scheme, TW III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04433/2023-2024 | 500 | 07/12/2023 | 0 | WBSEDCL | 11.71 | 0 | 0
1499 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rudrapur water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000154/2022-2023 | 3519/ED | 30/12/2022 | 450 | ORIENTAL ENGINEERING CO. | 34.24 | 0 | 98
1500 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Barakamalpur W/S Sch.[SM/12369], Zone - IV, T/W No. - I, (Gobindapur Dulepara), Block - Singur, Dt. - Hooghly under Nasibpur CCC, WBSEDCL, Ref. Id. - 503600456, Dated - 22-03-2024, Application No. - 5004079502 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/00012/2024-2025 | 12 | 04/04/2024 | 0 | WBSEDCL | 2.81 | 0 | 0
1501 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for Barakamalpur , Zone - III, T/W - I, Block Singur, Dist - hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/02760/2023-2024 | 173 | 10/08/2023 | 0 | WBSEDCL | 3.52 | 0 | 0
1502 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Barakamalpur W/S Sch., Zone - II, T/W - III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04127/2023-2024 | 385 | 25/10/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
1503 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-II, TW-IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04131/2023-2024 | 384 | 25/10/2023 | 0 | WBSEDCL | 5.89 | 0 | 0
1504 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04170/2023-2024 | 404 | 09/11/2023 | 0 | WBSEDCL | 3.23 | 0 | 0
1505 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Aug. of Bora Kamalpur W/S. Sch. Z-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04171/2023-2024 | 403 | 09/11/2023 | 0 | WBSEDCL | 3.93 | 0 | 0
1506 | Electrical | Chandannagar Sub-Division | Quotation for new service connection charge at Bora Kamalpur PWSS, Zone-II, TW - VI | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04483/2023-2024 | 532 | 15/12/2023 | 0 | WBSEDCL | 3.43 | 0 | 0
1507 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-I, TW-I & TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04690/2023-2024 | 665 & 666 | 11/01/2024 | 0 | WBSEDCL | 10.85 | 0 | 0
1508 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-IV | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04855/2023-2024 | 766 | 16/02/2024 | 0 | WBSEDCL | 3.94 | 0 | 0
1509 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Barakamalpur W/S. Sch. Z-III, TW-III | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05993/2023-2024 | 805 | 27/02/2024 | 0 | WBSEDCL | 5.78 | 0 | 0
1510 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for BARAKAMALPUR water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001365/2022-2023 | 1371/ED | 14/03/2023 | 365 | M/S S.S. ENTERPRISE | 130.31 | 0 | 70
1511 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00777/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 6.07 | 0 | 0
1512 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - IV | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00778/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 5.95 | 0 | 0
1513 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00780/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 8.32 | 0 | 0
1514 | Electrical | Chinsuria Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT RAGHUNATHPUR, P.H. NO. - II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00781/2023-2024 | 52 | 31/05/2023 | 0 | WBSEDCL | 2.64 | 0 | 0
1515 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Raghunathpur water supply scheme TW No I II III and IV, Block Chinsurah Mogra, District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000224/2022-2023 | 855/ED | 14/02/2023 | 90 | D. K. ELECTRIC | 42.97 | 0 | 95
1516 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001388/2023-2024 | 4738/ED | 15/12/2023 | 90 | S. DUTTA | 10.74 | 0 | 90
1517 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Assistant Chief Engineer (M/E), PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/002165/2022-2023 | 2382/HMSD | 27/12/2022 | 121 | BHOLA DEY | 1.11 | 0 | 1
1518 | Electrical | Chandannagar Sub-Division | Quotation for new service connection for Nanda W/s Sch., H/W Site(T/W No.- I), Dist - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01921/2023-2024 | 88 | 12/07/2023 | 0 | WBSEDCL | 7.92 | 0 | 0
1519 | Electrical | Chandannagar Sub-Division | Additional Quotation for Nanda W/S Sch., T/W no. - I, Block - Singur, Dt. - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02869/2023-2024 | 196 | 17/08/2023 | 0 | WBSEDCL | 0.43 | 0 | 0
1520 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Nanda W/S Sch., T/W No. - II, District - Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03889/2023-2024 | 301 | 22/09/2023 | 0 | WBSEDCL | 0.64 | 0 | 0
1521 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nanda water supply scheme, T.W. No.- I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000165/2022-2023 | 3499/ED | 30/12/2022 | 90 | RAJIB COMPANY | 21.48 | 0 | 95
1522 | Electrical | Arambug Sub-Division | Electric quot. of WBSEDCL for New service Connection of Kelepara T/W-II W/S scheme under Electrical Division PHE Dte. (SM/12232) | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01616/2024-2025 | 375 | 12/08/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
1523 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kelepara water supply scheme, T.W. No.- I & II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000158/2022-2023 | 3494/ED | 30/12/2022 | 900 | PADMA ENGINEERING CO. | 20.47 | 0 | 30
1524 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KELEPARA PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000164/2024-2025 | 1188/ED | 14/06/2024 | 90 | PADMA ENGINEERING CO. | 10.74 | 0 | 0
1525 | Electrical | Srirampur Sub-Division | Bishnupur water supply scheme, P H No -I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/02286/2023-2024 | 141 | 25/07/2023 | 0 | WBSEDCL | 3.39 | 0 | 0
1526 | Electrical | Srirampur Sub-Division | Bishnupur water supply scheme,PH No-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | BILL/02310/2023-2024 | 144 | 26/07/2023 | 0 | WBSEDCL | 2.89 | 0 | 0
1527 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bishnupur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000138/2022-2023 | 3486/ED | 30/12/2022 | 90 | BARMAN ROY TRADERS | 20.46 | 0 | 85
1528 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BILASPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Jangipara, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Jangipara Block Junior Engineer (Civill),Junior Engineer2 | ORD/000172/2024-2025 | 1195/ED | 14/06/2024 | 706 | MAA KALI ENTERPRISE | 10.7 | 0 | 40
1529 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Jagannathpur W/S. Sch.PH-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04609/2023-2024 | 607 | 04/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
1530 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Jagganathpur W/S. Sch. PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04639/2023-2024 | 621 | 08/01/2024 | 0 | WBSEDCL | 6.73 | 0 | 0
1531 | Electrical | Srirampur Sub-Division | Quotation Bill for Suplimentary Quotation for NSC Jagannathpur W/S. Sch PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05298/2023-2024 | 695 | 22/01/2024 | 0 | WBSEDCL | 0.06 | 0 | 0
1532 | Electrical | Srirampur Sub-Division | Quotation for New service connection at Jagannathpur W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06221/2023-2024 | 825 | 01/03/2024 | 0 | WBSEDCL | 10.23 | 0 | 0
1533 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Jagannathpur water supply scheme, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000148/2022-2023 | 3491/ED | 30/12/2022 | 848 | BISALAXMI ENTERPRISE | 20.31 | 0 | 50
1534 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Goradaha w/s Scheme,TW No-3 Block-Khanakul-I,Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/03627/2023-2024 | 220 | 25/08/2023 | 0 | WBSEDCL | 6.53 | 0 | 0
1535 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/04140/2023-2024 | 390 | 02/11/2023 | 0 | WBSEDCL | 8.75 | 0 | 0
1536 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Goradaha water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000212/2022-2023 | 839/ED | 14/02/2023 | 838 | M/S S R ENTERPRISE | 21.49 | 0 | 15
1537 | Electrical | Chandannagar Sub-Division | Quotation for new service connection of Sirazpur w/s scheme,PH No-I Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02002/2023-2024 | 112 | 19/07/2023 | 0 | WBSEDCL | 5.08 | 0 | 0
1538 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Uttar Sirazpur W/S. Sch. TW-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04327/2023-2024 | 443 | 24/11/2023 | 0 | WBSEDCL | 5.56 | 0 | 0
1539 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sirazpur water supply scheme, T.W. No. I & II, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000121/2022-2023 | 3477/ED | 30/12/2022 | 90 | DIPALI CONSTRUCTION | 21.47 | 0 | 30
1540 | Electrical | Ulberia Sub-Division | New Service Connection at Sonamui W/S. SCh. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/00774/2023-2024 | 47 | 24/05/2023 | 0 | WBSEDCL | 17.81 | 0 | 0
1541 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Sonamui W/S. Sch. PH-II | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/00775/2023-2024 | 47 | 24/05/2023 | 0 | WBSEDCL | 10.43 | 0 | 0
1542 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Sonamui W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/00835/2023-2024 | 59 | 05/06/2023 | 0 | WBSEDCL | 0.21 | 0 | 0
1543 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sonamui water supply scheme, T.W. No.- I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000134/2022-2023 | 3524/ED | 30/12/2022 | 90 | SANKAR PRASAD DUTTA & CO. | 22.35 | 0 | 100
1544 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at Cheragram W/S. Sch. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/05063/2023-2024 | 683 | 19/01/2024 | 0 | WBSEDCL | 13.03 | 0 | 0
1545 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Cheragram water supply scheme, T.W. No.- I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000204/2022-2023 | 831/ED | 14/02/2023 | 90 | INDRAJIT MITRA | 10.98 | 0 | 57
1546 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Mohisnala w/s scheme, T.W. No.-I, Dist.-Howrah under PHE Dte. Application No- 1007840878 Reference ID- 106627061 SM Code- 11894 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00832/2024-2025 | 231 | 20/06/2024 | 0 | WBSEDCL | 13.93 | 0 | 0
1547 | Electrical | Howrah Sadar Sub-Division | Fuel consumption bill of 1 (one) no. diesel driven motor car on contract carriage for the Official use of the Assistant Engineer-I, Electrical Division, PHE Dte. From 01.05.2024 to 31.05.2024 WB-04G-2822 Bill No : 0240 Bill Date : 31/05/2024 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00833/2024-2025 | 241 | 20/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0
1548 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Mahishnala W/S. Sch. PWSS-II | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/04129/2023-2024 | 379 | 25/10/2023 | 0 | WBSEDCL | 9.03 | 0 | 0
1549 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Mahisnala (Domjur Zone-I) Pwss P.H No-III , Dist-Howrah under ED, PHED. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/06056/2023-2024 | 757 | 16/02/2024 | 0 | WBSEDCL | 7.55 | 0 | 0
1550 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahisnala Domjur (Zone-I) water supply scheme, T.W. No.- I, II & III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000151/2022-2023 | 3515/ED | 30/12/2022 | 990 | DAS ENTERPRISE | 34.26 | 0 | 75
1551 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. TW-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/04134/2023-2024 | 387 | 01/11/2023 | 0 | WBSEDCL | 4.27 | 0 | 0
1552 | Electrical | Ulberia Sub-Division | Quotation Bill for New Service Connection at Uttar Gpalpur W/S. Sch. PH-I | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/04328/2023-2024 | 441 | 24/11/2023 | 0 | WBSEDCL | 3.46 | 0 | 0
1553 | Electrical | Ulberia Sub-Division | Quotation bill for service connection charges at Gopalpur w/s scheme, Zone-II, P.H. No.-II, Dist: Hooghly Application No.- 5004035005 Ref Id: 503576015 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | BILL/06263/2023-2024 | 864 | 12/03/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
1554 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000125/2022-2023 | 3539/ED | 30/12/2022 | 1037 | KARTICK BAL | 20.35 | 0 | 60
1555 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Sibaichandi W/S. Sch. TW-I & II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/03758/2023-2024 | 250, 251 | 05/09/2023 | 0 | WBSEDCL | 27.99 | 0 | 0
1556 | Electrical | Chinsuria Sub-Division | "Quotation Bill for New Service Connection at Sibaichandi TW-I & II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/03788/2023-2024 | 309 & 310 | 27/09/2023 | 0 | WBSEDCL | 4.03 | 0 | 0
1557 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Sibaichandi water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000227/2022-2023 | 858/ED | 14/02/2023 | 90 | ANJAN ENTERPRISE | 21.45 | 0 | 45
1558 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02593/2023-2024 | 156 | 03/08/2023 | 0 | WBSEDCL | 3.84 | 0 | 0
1559 | Electrical | Chinsuria Sub-Division | Quotation Bill for New Service Connection at SRIKRISHNAPUR W/S. Sch. Z-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02594/2023-2024 |  | 01/08/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
1560 | Electrical | Chinsuria Sub-Division | Quotation bill for new service connection charge at Srikrishnapur w/s scheme, T.W. No.-II | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | BILL/02726/2023-2024 | 181 | 11/08/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
1561 | Electrical | Chinsuria Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Srikrishnapur water supply scheme TW No I and II Block DhaniakhalI District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/000229/2022-2023 | 860/ED | 14/02/2023 | 90 | ASHUTOSH DAS & CO. | 21.49 | 0 | 50
1562 | Electrical | Chinsuria Sub-Division | Hiring of Luxury Car (BS-IV) for the Official us of the Executive Engineer, Electrical Division PHED wef 01.06.23 to 30.11.23 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer1 | ORD/001022/2023-2024 | 363_AE-I_ED | 29/05/2023 | 365 | TRIDIP SARKAR | 5 | 0 | 40
1563 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil) | Chinsurah Block Junior Engineer (Civill) | BILL/01594/2024-2025 | 377 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 8.49 | 0 | 0
1564 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Shyampur PH-I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | BILL/00907/2022-2023 | 188 | 13/03/2023 | 0 | WBSEDCL | 2.57 | 0 | 0
1565 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Shyampur W/S. Sch. PH-II | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | BILL/01891/2022-2023 | 229 | 29/03/2023 | 0 | WBSEDCL | 2.69 | 0 | 0
1566 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, Zone-I, P.H. No. II (Replaced tubewell), District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/001159/2022-2023 | 2099/HMSD | 24/11/2022 | 30 | D. K. ELECTRIC | 4.3 | 0 | 0
1567 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shyampur water supply scheme, T.W. No.- I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/001364/2022-2023 | 3522/ED | 30/12/2022 | 90 | S P ENTERPRISE | 20.28 | 0 | 11
1568 | Electrical | Arambug Sub-Division | Mini Piped water Supply Scheme | Assistant Engineer | Goghat-I & Goghat-II Block Junior Engineer (Civill) | BILL/01596/2024-2025 | BILL/01596/2024 | 16/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1569 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No.- I, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000244/2022-2023 | 911/ED | 22/02/2023 | 45 | SAIKAT ENTERPRISE | 11.51 | 0 | 0
1570 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Bamunhati water supply scheme, T.W. No. III & IV, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/003615/2023-2024 | 3465/ED | 11/08/2023 | 90 | B.T. PROJECT PVT. LTD. | 23.5 | 0 | 0
1571 | Electrical | Arambug Sub-Division | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- I, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004201533 Reference ID- 503652893 SM Code- 13325 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00821/2024-2025 | 223 | 18/06/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
1572 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Chinra w/s Scheme,Zone-I,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325) Application No-5004308863 Reference Id-503700260 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02035/2024-2025 | 510 | 21/10/2024 | 0 | WBSEDCL | 3.75 | 0 | 0
1573 | Electrical | Arambug Sub-Division | Quotation for Shifting Existing LT Structure at Chinra w/s Scheme,Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/13325).Application No-100000121107 Reference Id-860315657 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/02094/2024-2025 | 548 | 30/10/2024 | 0 | WBSEDCL | 0.63 | 0 | 0
1574 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000146/2024-2025 | 1169/ED | 14/06/2024 | 90 | GOENKA ENTERPRISE | 10.74 | 0 | 0
1575 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000184/2022-2023 | 777/ED | 09/02/2023 | 898 | GOENKA ENTERPRISE | 20.48 | 0 | 10
1576 | Electrical | Chandannagar Sub-Division | Quotation for New Service Connection of Bade Digaria W/S scheme,TW No-I, Block-Haripal, District- Hooghly under ED ,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01982/2023-2024 | 98 | 17/07/2023 | 0 | WBSEDCL | 3.05 | 0 | 0
1577 | Electrical | Chandannagar Sub-Division | Quotation for new Service Connection of Bade Digaria w/s Scheme, TW No-II, Block- Haripal, District- Hooghly under ED ,PHE DTE | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01983/2023-2024 | 99 | 17/07/2023 | 0 | WBSEDCL | 2.3 | 0 | 0
1578 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000170/2022-2023 | 559/ED | 02/02/2023 | 90 | M/S A.K BANERJEE | 21.37 | 0 | 0
1579 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bade Digaria water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000171/2022-2023 | 764/ED | 09/02/2023 | 90 | M/S A.K BANERJEE | 21.37 | 0 | 40
1580 | Electrical | Howrah Sadar Sub-Division | new service connetion | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/02066/2023-2024 | 129 | 20/07/2023 | 0 | WBSEDCL | 4.04 | 0 | 0
1581 | Electrical | Howrah Sadar Sub-Division | Quotation money deposition for new service connection at Domjur(Zone-VIII) w/s scheme, Domjur(CT),Pwss, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1008185198 Reference ID- 106810746 SM Code- 14155 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/02126/2024-2025 | 570 | 13/11/2024 | 0 | WBSEDCL | 9.33 | 0 | 0
1582 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-VIII) Domjur (CT) water supply scheme, T.W. No. I & II, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000253/2022-2023 | 920/ED | 22/02/2023 | 860 | A.G. ENTERPRISE | 21.49 | 0 | 40
1583 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Domjur (Zone-VIII) Domjur (CT) water supply scheme, T.W. No.- III, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000857/2023-2024 | 3429/ED | 11/08/2023 | 90 | D. K. ELECTRIC | 10.74 | 0 | 100
1584 | Electrical | North 24 Pgs W/S Division I | Quotation for Balibhara w/s scheme TW no.- I | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | BILL/00449/2024-2025 | 116 | 17/05/2024 | 0 | WBSEDCL | 4.33 | 0 | 0
1585 | Electrical | North 24 Pgs W/S Division I | Quotation for new service connection at Bidyadharpur W/S Scheme PH No 1 ( SM/14501 ) | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | BILL/00110/2024-2025 | 34 | 09/04/2024 | 0 | WBSEDCL | 0.79 | 0 | 0
1586 | Electrical | Howrah Sadar Sub-Division | Quotation for new service connection charge at Gangadharpur Deulpur PWSS, Zone-II, TW - I | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/04487/2023-2024 | 529 | 15/12/2023 | 0 | WBSEDCL | 0.32 | 0 | 0
1587 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. III and Zone-II, T.W. No. III Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000875/2023-2024 | 3448/ED | 11/08/2023 | 90 | R.M.D TRADING. | 21.99 | 0 | 0
1588 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000921/2023-2024 | 3592/ED | 28/08/2023 | 90 | R.N.S. TRADING | 43.65 | 0 | 0
1589 | Electrical | Chandannagar Sub-Division | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00870/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.51 | 0 | 0
1590 | Electrical | Chandannagar Sub-Division | Supply & delivery of submersible pumping machinery for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00873/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.51 | 0 | 0
1591 | Electrical | Chandannagar Sub-Division | Supply & installation of MCC Panel & allied works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00875/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 2.7 | 0 | 0
1592 | Electrical | Chandannagar Sub-Division | Supply & delivery of electro-mechanical equipments and installation of submersible pumping machinery & other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00877/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.72 | 0 | 0
1593 | Electrical | Chandannagar Sub-Division | Supply ,delivery & installation of Actuator operated butterfly valve for for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00878/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 1 | 0 | 0
1594 | Electrical | Chandannagar Sub-Division | Supply ,delivery & installation of Voltage correcting device and other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00879/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 1.7 | 0 | 0
1595 | Electrical | Chandannagar Sub-Division | Supply & installation of Automatic Chlorinator at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00880/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.71 | 0 | 0
1596 | Electrical | Chandannagar Sub-Division | Internal electrification and works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/00881/2022-2023 |  | 28/02/2023 | 0 | DEY ENTERPRISE | 0.59 | 0 | 0
1597 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection of Malia W/S Scheme(Aug) T.W No-4 District-Hooghly under Electrical Division PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/01997/2023-2024 | 114 | 19/07/2023 | 0 | WBSEDCL | 2.28 | 0 | 0
1598 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Malia water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000002/2023-2024 | 1618/ED | 11/04/2023 | 90 | A.S. ENTERPRISE | 10.71 | 0 | 50
1599 | Electrical | Chandannagar Sub-Division | Supply, Installation of MCC panel & allied works at Malia W/S. Sch. PH-III Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000187/2020-2021 | 503/HMSD | 12/03/2021 | 90 | DEY ENTERPRISE | 2.7 | 0 | 0
1600 | Electrical | Chandannagar Sub-Division | Supply, Delivery & Installation of voltage correcting device & other allied works for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000188/2020-2021 | 322/HMSD | 15/02/2021 | 90 | DEY ENTERPRISE | 1.7 | 0 | 0
1601 | Electrical | Chandannagar Sub-Division | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001224/2021-2022 | 863/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.51 | 0 | 0
1602 | Electrical | Chandannagar Sub-Division | Supply & Delivery of electro-mechanical equipments & Installation of S/P/M & other allied works for Malia W/S. Sch. PH-III, Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001225/2021-2022 | 864/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.72 | 0 | 0
1603 | Electrical | Chandannagar Sub-Division | Supply, Delivery & Installation of actuor operated butterfly valve for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001226/2021-2022 | 865/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 1 | 0 | 0
1604 | Electrical | Chandannagar Sub-Division | Supply, Delivery & Installation of automatic chlorinator for Malia W/S. Sch. PH-III | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001227/2021-2022 | 862/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.71 | 0 | 0
1605 | Electrical | Chandannagar Sub-Division | Internal Electrification & allied works at Malia W/S. Sch. PH-III Hooghly | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/001228/2021-2022 | 861/HMSD | 13/05/2021 | 90 | DEY ENTERPRISE | 0.59 | 0 | 0
1606 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Shyamballavpur w/s Scheme,TW No-3,Dist-Hooghly under ED,PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02132/2023-2024 | 122 | 20/07/2023 | 0 | WBSEDCL | 4.38 | 0 | 0
1607 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyamballavpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000008/2023-2024 | 1624/ED | 11/04/2023 | 90 | S.G.-ENTERPRISE | 10.73 | 0 | 40
1608 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Mahishtikari W/S. Sch. TW-II, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04167/2023-2024 | 406 | 09/11/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
1609 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Mahishtikri W/S. Sch. TW-I, Z-I | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04168/2023-2024 | 407 | 09/11/2023 | 0 | WBSEDCL | 3.04 | 0 | 0
1610 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-I) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000042/2023-2024 | 1728/ED | 19/04/2023 | 866 | MENAKA ENTERPRISE | 20.26 | 0 | 30
1611 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection Charge for Mahishtikri w/s Scheme,Zone-2,TW No-I Block-Haripal Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03761/2023-2024 | 264 | 07/09/2023 | 0 | WBSEDCL | 9.89 | 0 | 0
1612 | Electrical | Chandannagar Sub-Division | Quotation of New Service Connection for Mahistikri w/s Scheme,Zone-2,TW No-2 Block-Haripal,Dist-Hooghly under ED,PHE Dte | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/03762/2023-2024 | 263 | 07/09/2023 | 0 | WBSEDCL | 3.24 | 0 | 0
1613 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mahishtikri (Zone-II) water supply scheme, T.W. No. I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000024/2023-2024 | 1701/ED | 18/04/2023 | 90 | DEBJYOTI BASU | 20.5 | 0 | 60
1614 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Gopalbati w/s Scheme,PH No-II,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/16756) Application No-5004475080 Reference Id-503799042 | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/02474/2024-2025 | 618 | 05/12/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
1615 | Electrical | Arambug Sub-Division | Quotation Bill for New Service Connection at Gopalbati W/S. Sch. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | BILL/04409/2023-2024 | 487 | 06/12/2023 | 0 | WBSEDCL | 3.95 | 0 | 0
1616 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Gopalbati water supply scheme TW No I and II Block Goghat I District Hooghly under ED PHED. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer4 | ORD/000056/2023-2024 | 1800/ED | 24/04/2023 | 708 | KAMAKHYA ENTERPRISE | 20.26 | 0 | 30
1617 | Electrical |  | Quotation for New Service Connection at Rashpur W/S. Sch. PH-I, Amta-I |  |  | BILL/04660/2023-2024 | 644 | 09/01/2024 | 0 | WBSEDCL | 13.7 | 0 | 0
1618 | Electrical |  | Quotation for New Service Connection at Rashpur W/S. Sch. PH-II, Amta-I |  |  | BILL/04661/2023-2024 | 642 | 09/01/2024 | 0 | WBSEDCL | 11.6 | 0 | 0
1619 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Raspur water supply scheme, T.W. No.- I & II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000939/2023-2024 | 3618/ED | 29/08/2023 | 630 | SWAPAN ENTERPRISE | 20.37 | 0 | 80
1620 | Electrical |  | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18934), Reference Id- 503795724 Application no- 5004470487 |  |  | BILL/02293/2024-2025 | BP-24-25-594 | 21/11/2024 | 0 | WBSEDCL | 7.02 | 0 | 0
1621 | Electrical |  | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHEDte. ( SM/18934), Reference Id- 503814971 Application no- 5004498167 |  |  | BILL/02600/2024-2025 | 631 | 18/12/2024 | 0 | WBSEDCL | 6.54 | 0 | 0
1622 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME Block- Balagarh, District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001207/2023-2024 | 4485/ED | 23/11/2023 | 770 | BARISAL TRADING CO. | 21.49 | 0 | 25
1623 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.02.2024 to 29.02.2024 WB19J-7094 SM Code- 11465 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00717/2024-2025 | 229 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.26 | 0 | 0
1624 | Electrical | Srirampur Sub-Division | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From 01.01.2024 to 31.01.2024 WB19J-7094 SM Code- 11465 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/00719/2024-2025 | 228 | 18/06/2024 | 0 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0
1625 | Electrical | Srirampur Sub-Division | Purba Tajpur w/s scheme, P H No 1 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | BILL/04329/2023-2024 | 442 | 24/11/2023 | 0 | WBSEDCL | 5.52 | 0 | 0
1626 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Purba Tajpur water supply scheme TW No I Block Chanditala II District Hooghly under ED PHED. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/000223/2022-2023 | 854/ED | 14/02/2023 | 90 | A.K. SIKDAR | 10.72 | 0 | 99
1627 | Electrical | Srirampur Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer2 | ORD/001009/2023-2024 | 2502/HMSD | 26/09/2023 | 152 | S.P. CONSTRUCTION | 0.72 | 0 | 15
1628 | Electrical | Arambug Sub-Division | Quotation bill for New Service connection of Rajhato w/s scheme,TW-I | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/00731/2023-2024 | 20 | 04/05/2023 | 0 | WBSEDCL | 2.22 | 0 | 0
1629 | Electrical | Arambug Sub-Division | Quotation for New Service Connection of Rajhato(Aug) w/s Scheme, PH No-2 District-Hooghly Under Electrical division PHE Dte | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01162/2023-2024 | 84 | 10/07/2023 | 0 | WBSEDCL | 2.57 | 0 | 0
1630 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Rajhato water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000289/2022-2023 | 939/ED | 22/02/2023 | 90 | MAA KALI ENTERPRISE | 21.48 | 0 | 60
1631 | Electrical | Chandannagar Sub-Division | Augmentation Of Champadanga Water Supply Scheme TW-4 | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | BILL/01908/2022-2023 | 250, 251 | 31/03/2023 | 0 | WBSEDCL | 6.95 | 0 | 0
1632 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000237/2022-2023 | 868/ED | 14/02/2023 | 745 | STANDARD ELECTRICALS | 21.96 | 0 | 95
1633 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chapadanga water supply scheme, T.W. No.- IV & V, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Junior Engineer (Civill),Junior Engineer3 | ORD/000279/2022-2023 | 946/ED | 22/02/2023 | 90 | STANDARD ELECTRICALS | 21.96 | 0 | 0
1634 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of Bikihakola Water Supply Scheme Block- Panchla District- Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001305/2023-2024 | 4538/ED | 23/11/2023 | 90 | D. K. ELECTRIC | 10.74 | 0 | 0
1635 | Electrical |  | Quotation for new service connection for source Augmentation of Garbhabanipur Water Supply Scheme, PH NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18849), Reference Id- 106616115, Application no- 1007816541 |  |  | BILL/00710/2024-2025 | 212 | 11/06/2024 | 0 | WBSEDCL | 11.44 | 0 | 0
1636 | Electrical |  | Additional Quotation for new service connection for source Augmentation of Garbhabanipur Water Supply Scheme, PH NO- III in the district Howrah under Electrical Division, PHE Dte. (SM/18849), Reference Id- 860319020, Application no- 100000123590 |  |  | BILL/02475/2024-2025 | 614 | 05/12/2024 | 0 | WBSEDCL | 0.74 | 0 | 0
1637 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF GARBHABANIPUR PIPED W/S SCHEME, T.W. No. III, Block: Udaynarayanpur, District - Howrah under JJM Program under Electrical Division PHE Dte. |  |  | ORD/002508/2023-2024 | 424/ED | 29/02/2024 | 519 | SMILE | 10.74 | 0 | 90
1638 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-I Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282705 Reference Id-503686110 | Assistant Engineer | Junior Engineer (Civill) | BILL/01152/2024-2025 | 285 | 09/07/2024 | 0 | WBSEDCL | 5.39 | 0 | 0
1639 | Electrical | Arambug Sub-Division | Quotation of New Service Connection for Ghar Gohal w/s scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/19013) Application No-5004282784 Reference Id-503686105 | Assistant Engineer | Junior Engineer (Civill) | BILL/01153/2024-2025 | 286 | 09/07/2024 | 0 | WBSEDCL | 6.42 | 0 | 0
1640 | Electrical | Arambug Sub-Division | Hiring of Luxury Car / Ambassadar (BS-IV) for Officical use of the Assistant Chief Engineer (M/E), PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000284/2024-2025 | 2870/HMSD | 04/06/2024 | 182 | BHOLA DEY | 0.86 | 0 | 0
1641 | Electrical | Arambug Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghar Gohal water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001984/2023-2024 | 116/ED | 15/01/2024 | 531 | GLACIER ENGINEERING CO. | 21.1 | 0 | 30
1642 | Electrical |  | Quotation App. No.-1007748306 SM/18560 |  |  | BILL/00467/2024-2025 | 118 | 17/05/2024 | 0 | WBSEDCL | 6.52 | 0 | 0
1643 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. III and Zone-II, T.W. No. III Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000875/2023-2024 | 3448/ED | 11/08/2023 | 90 | R.M.D TRADING. | 21.99 | 0 | 0
1644 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Deulpur & Gangadharpur water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000921/2023-2024 | 3592/ED | 28/08/2023 | 90 | R.N.S. TRADING | 43.65 | 0 | 0
1645 | Electrical |  | Quotation money deposition for new service connection at Panchla w/s scheme, T.W. No.-III, Dist.-Howrah under PHE Dte. Application No- 1007951166 Reference ID- 106680336 SM Code- 18563 |  |  | BILL/01982/2024-2025 | 489 | 01/10/2024 | 0 | WBSEDCL | 3.43 | 0 | 0
1646 | Electrical |  | Quotation money deposition for shifting of 1 mtr. pcc pole and others allied works at panchla pwss. near P.H No.-I under ED PHED. Ref. NO.-860314452 SM/18563 |  |  | BILL/02032/2024-2025 | BP-24-25-591 | 20/11/2024 | 0 | WBSEDCL | 0.45 | 0 | 0
1647 | Electrical |  | Quotation money deposition for new service connection at PANCHLA pwss, T.W No.-I , Dist-Howrah under ED PHED. App. No.-1007505290 Ref. ID.: 106463795 SM/18563 |  |  | BILL/06204/2023-2024 | 815 | 28/02/2024 | 0 | WBSEDCL | 4.43 | 0 | 0
1648 | Electrical |  | Quotation money deposition for new service connection at Panchla pwss, Dist-Howrah, under PHED. App. No.-1007554361 Ref. No.-106486310 SM/18563 |  |  | BILL/06212/2023-2024 | 817 | 01/03/2024 | 0 | WBSEDCL | 5.05 | 0 | 0
1649 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Panchla water supply scheme, T.W. No.- I, II, III & IV, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000910/2023-2024 | 3581/ED | 28/08/2023 | 705 | WEST BENGAL ENGINEERING CO. | 46.35 | 0 | 30
1650 | Electrical | Ulberia Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baniban water supply scheme, Zone-III, T.W. No. I, II, III & IV, Block: Uluberia-II, District- Howrah under Electrical Division, PHE Dte. | AE/Ulu | JE-USD | ORD/000927/2023-2024 | 3598/ED | 28/08/2023 | 90 | DEY ENTERPRISE | 42.99 | 0 | 0
1651 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BHABANIPUR CHAR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001246/2023-2024 | 4496/ED | 23/11/2023 | 90 | PERPETUAL ENTERPRISE | 21.7 | 0 | 0
1652 | Electrical | Howrah Sadar Sub-Division | Quotation Bill for New Service Connection at Jujarsah W/S. Sch.PH-III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/04080/2023-2024 | 348 | 11/10/2023 | 0 | WBSEDCL | 3.71 | 0 | 0
1653 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jujarsah water supply scheme, T.W. No.- I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000245/2022-2023 | 912/ED | 22/02/2023 | 846 | MAA KALI ENTERPRISE | 23.16 | 0 | 50
1654 | Electrical | Howrah Sadar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jujarsah water supply scheme, T.W. No. III, IV & V, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000866/2023-2024 | 3439/ED | 11/08/2023 | 90 | H.K.DAS & CO. | 35.18 | 0 | 0
1655 | Electrical | Howrah Sadar Sub-Division | Supply, Delivery & Installation of voltage correcting device & other allied works for Jujursha W/S. Sch. PH-I Howrah | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/001160/2022-2023 | 1372/HMSD | 27/07/2022 | 7 | MAA KALI ENTERPRISE | 2.85 | 0 | 0
1656 | Electrical | Chinsuria Sub-Division | Mini piped Water Supply scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/01597/2024-2025 |  | 05/08/2024 | 0 | ZILLA PARISHAD HOOGHLY | 288.8 | 0 | 0
1657 | Electrical | Chinsuria Sub-Division | Mini Piped Water Supply Scheme | Assistant Engineer (Civil),Assistant Engineer Howrah mechanical Sub Division | Balagarh Block Junior Engineer (Civill),Junior Engineer1 | BILL/02038/2024-2025 | BILL/01597/2024 | 01/10/2024 | 0 | ZILLA PARISHAD HOOGHLY | 76.45 | 0 | 0
1658 | Electrical |  | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - III, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619158, Dt. - 13-05-2024, Application No. - 5004116682 |  |  | BILL/00450/2024-2025 | 124 | 17/05/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
1659 | Electrical |  | Quotation for new servce connection at Puinan (S.Aug.) [SM/18952] , T/W No. - IV, Block - Polba-Dadpur, Dist. - Hooghly under Dadpur CCC, WBSEDCL, Ref, Id. - 503619159, Dt. - 13-05-2024, Application No. - 5004116723 |  |  | BILL/00451/2024-2025 | 122 | 17/05/2024 | 0 | WBSEDCL | 6.36 | 0 | 0
1660 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation Of PUINAN piped Water Supply Scheme Block- Polba-Dadpur District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001276/2023-2024 | 4516/ED | 23/11/2023 | 90 | SUTRADHAR TRADERS | 21.47 | 0 | 30
1661 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-II, PH-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04442/2023-2024 | 519A | 11/12/2023 | 0 | WBSEDCL | 6.86 | 0 | 0
1662 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-I, PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04587/2023-2024 | 596 | 29/12/2023 | 0 | WBSEDCL | 0.74 | 0 | 0
1663 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04589/2023-2024 | 597 | 29/12/2023 | 0 | WBSEDCL | 5.03 | 0 | 0
1664 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04636/2023-2024 | 625 | 08/01/2024 | 0 | WBSEDCL | 5.57 | 0 | 0
1665 | Electrical | Srirampur Sub-Division | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-I | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/04637/2023-2024 | 624 | 08/01/2024 | 0 | WBSEDCL | 7.5 | 0 | 0
1666 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000847/2023-2024 | 3415/ED | 10/08/2023 | 90 | A.S. ENTERPRISE | 20.34 | 0 | 60
1667 | Electrical | Srirampur Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000848/2023-2024 | 3416/ED | 10/08/2023 | 90 | P.K. ENGINEERING | 22.13 | 0 | 0
1668 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of SAOTA Piped Water Supply Scheme Block- Pursura District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001291/2023-2024 | 4523/ED | 23/11/2023 | 90 | TRIO CONCERN | 21.48 | 0 | 0
1669 | Electrical | Chandannagar Sub-Division | Qoutation for new service connection at Balarambati W/S Sch., Head works Site, (T/W No - I), Dt. - Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/03703/2023-2024 | 233 | 01/09/2023 | 0 | WBSEDCL | 3.21 | 0 | 0
1670 | Electrical | Chandannagar Sub-Division | Quotation Bill for New Service Connection at Balarambati W/S. Sch. TW-II | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/05924/2023-2024 | 715 | 29/01/2024 | 0 | WBSEDCL | 6.84 | 0 | 0
1671 | Electrical | Chandannagar Sub-Division | Quotation for new service connection at Balarambati W/S Sch., T/W No. - III, [SM/18657], Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503584700, Dt. - 12-03-2024, Application No. - 5004050064 | Assistant Engineer (Civil) | Junior Engineer (Civill) | BILL/06470/2023-2024 | 894 | 18/03/2024 | 0 | WBSEDCL | 5.07 | 0 | 0
1672 | Electrical | Chandannagar Sub-Division | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balarambati water supply scheme, T.W. No. I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000842/2023-2024 | 3410/ED | 10/08/2023 | 90 | ORIENTAL ENGINEERING CO. | 32.24 | 0 | 80
1673 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Source Augmentation of GOURHATI piped Water Supply Scheme Block- Arambag District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001293/2023-2024 | 4525/ED | 23/11/2023 | 90 | UNIVERSAL ENTERPRISES | 21.49 | 0 | 0
1674 | Electrical |  | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF PANDUA PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001265/2023-2024 | 4510/ED | 23/11/2023 | 90 | INDIA ENTERPRISE | 21.48 | 0 | 0
Total | [10 empty] | 26213.14 | 0