## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Enhancement of contractual demand from 71 KVA to 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o The Ex.Engg PMD PHE Dte.(Consumer ID : 950006038) to their premises at Balitora Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00042/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 6.74 | 0 | 0
2 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Payment for New Electric connection charge at Madhukunda O.H.R. Site , Mouja : Madhukunda under Augmentation of Balitora Water Supply to Santuri CCC of WBSEDCL . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00147/2024-2025 | BP-24-25-26 | 11/06/2024 | 0 | SANTURI CCC | 0.94 | 0 | 0
3 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Payment of new Electric service connection charge to WBSEDCL ,Santuri CCC at Santuri Mouja ( O.H.R. No.2 under Balitora W.S.Scheme ) ,application no.- 2004753984 , Ref. Id.- 204318171 , Contact Demand - 1330 watt . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00173/2024-2025 | BP-24-25-41 | 02/07/2024 | 0 | SANTURI CCC | 0.05 | 0 | 0
4 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Payment for New Service Connection charge at Manpur , JL - 31 , Plot - 479 under Purulia Mechanical Division P.H.E. Dte. to WBSEDCL , Purulia , Santuri CCC . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00177/2024-2025 | BP-24-25-42 | 02/07/2024 | 0 | SANTURI CCC | 3.6 | 0 | 0
5 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Enhancement of the contract demand from 71 KVA at 0.4 KV to 120/120/120/120/120 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Balitora Water Supply | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00867/2023-2024 | BP-23-24-310 | 21/03/2024 | 0 | WBSEDCL PURULIA | 11.11 | 0 | 0
6 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, MCC panel Flowmeter and other allied works for augmentation of Balitora water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000033/2023-2024 | 438/PMD | 19/04/2023 | 60 | PREMNATH MITRA | 46.28 | 0 | 90
7 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Balitora w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000133/2023-2024 | 648/PMD | 08/06/2023 | 60 | PREMNATH MITRA | 12.15 | 0 | 91
8 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of Balitora water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000404/2022-2023 | 232/PMD | 03/03/2023 | 60 | ASHOKE ADHIKARY | 12.85 | 12.85 | 80
9 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Enhancement of the contract demand from 80 KVA at 0.4 KV to 105/105//105//105//105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE SINDRI CHASMORE Water Supply, (Consumer ID -942413800) | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00865/2023-2024 | BP-23-24-308 | 19/03/2024 | 0 | WBSEDCL PURULIA | 1.44 | 0 | 0
10 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of 2 M.T capacity single girder H.O.T crane with gantry girder and square rail for Sindrichasmore w/s scheme new CWR Pump house under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000049/2024-2025 | 968/PMD | 20/06/2024 | 60 | RABINDRA NATH KHAN | 8.09 | 0 | 100
11 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and external illumination with other allied works for augmentation of existing pump house & new CWR pump house of Sindrichasmore water supply scheme under Purulia Mechanical Division , PHE Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000054/2024-2025 | 972/PMD | 20/06/2024 | 226 | COMBINE ENTERPRISES | 18.83 | 0 | 20
12 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply of valves, pipes and miscellaneous works for new proposed CWR & existing P.H of Sindrichasmore w/s scheme under PMD, PHE Dte. in the district Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 995/PMD | 21/06/2024 | 60 | RABINDRA NATH KHAN | 1.61 | 0 | 0
13 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing internal and external illumination arrangement at proposed CWR of Sindrichasmore W/S under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000153/2023-2024 | 649/PMD | 08/06/2023 | 60 | MAHIPAL MAJHI | 6.13 | 0 | 5
14 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, flowmeter with necessary substitutes and allied electrical panel at existing pump house at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000365/2022-2023 | 207/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 66.49 | 30.88 | 60
15 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tubewell with supply of necessary substitutes at Augmentation of Sindri chasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000366/2022-2023 | 208/PMD | 28/02/2023 | 704 | RABINDRA NATH KHAN | 17.88 | 4.98 | 85
16 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, Voltage Stabilizer with necessary substitutes and allied electrical panel at for Proposed CWR at intake side of Sindrichasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000376/2022-2023 | 206/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 31.34 | 0 | 15
17 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Sindrichasmore Water Supply scheme Block Purulia-II under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000382/2022-2023 | 213/PMD | 28/02/2023 | 30 | TAPAN KUMAR DEY | 21.61 | 12.88 | 60
18 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000441/2023-2024 | 421/PMD | 11/03/2024 | 30 | TAPAN KUMAR DEY | 5.21 | 0 | 30
19 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and laying of cables for taking power & Misc. works for Pump house of Sindrichasmore w/s scheme under PMD, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000593/2024-2025 | 1451/PMD | 01/10/2024 | 30 | RABINDRA NATH KHAN | 6.21 | 0 | 0
20 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery & installation of Glow Sign board & Lighting conductor under Sindri Chas more Water Supply Scheme under Purulia Mechanical Division P.H.E Dte.in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000596/2024-2025 | 350/PMSD(W/S) | 04/09/2024 | 15 | PINTU DEY | 0.48 | 0 | 100
21 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of Indoor type Vacuum Circuit breaker and allied works for Sindrichasmore w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000620/2024-2025 | 1542/PMD | 11/11/2024 | 385 | RABINDRA NATH KHAN | 12.07 | 0 | 100
22 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of automatically controlled diaphragm type Chlorinator dosing pump with Piping & structural works in connection with Disinfection arrangement System & Miscellaneous works at Pump House under Sindrichasmore W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000621/2024-2025 | 1543/PMD | 11/11/2024 | 60 | MAHIPAL MAJHI | 3.63 | 0 | 100
23 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Manguria lalpur Water Supply scheme Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000081/2021-2022 | 166/PMD | 07/03/2022 | 30 | JAL PRAVAHIKA PVT. LTD | 20.5 | 11.71 | 100
24 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well and existing one no tube well with allied cable line and other allied works for augmentation of Manguria Lalpur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000289/2022-2023 | 80/PMD | 01/02/2023 | 60 | RAJIB COMPANY | 24.65 | 22.9 | 100
25 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Manguria Lalpur water supply scheme under PMD PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000290/2022-2023 | 82/PMD | 01/02/2023 | 60 | SWAPAN ENTERPRISE | 13.25 | 0 | 100
26 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Manguria Lalpur water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000294/2022-2023 | 81/PMD | 01/02/2023 | 60 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 49.6 | 0 | 100
27 | Purulia Mechanical | Raghunathpur Sub-Division | SUPPLY DELIVERY & INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM OF AUGMENTATION OF MANGURIA LALPUR W/S SCHEME, HURA BLOCK UNDER PMD PHE DTE.(TR.NO 371 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000081/2022-2023 | C042211603113 | 08/04/2022 | 0 | JAL PRAVAHIKA PVT. LTD | 8.78 | 0 | 0
28 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 110 KVA AT 0.4 KV TO 160/160/160/160/160 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , THE EX ENGG PMD PHE DTE(CONSUMER ID : 950009505) TO THEIR PREMISES AT MANGURIA LALPUR WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000427/2022-2023 |  | 03/11/2022 | 0 | WBSEDCL PURULIA | 9.17 | 0 | 0
29 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation for new connection | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00453/2023-2024 | BP-23-24-220 | 05/12/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0
30 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000052/2024-2025 | 970/PMD | 20/06/2024 | 60 | M/S D. PALIT & CO. | 11.74 | 0 | 0
31 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of internal and external illumination arrangement at existing at Intake pump house, clear water, chemical house buiding, substation building,OHR site Chorination room at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000181/2023-2024 | 1171/PMD | 03/11/2023 | 456 | RABINDRA NATH KHAN | 34.4 | 0 | 35
32 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000428/2022-2023 | 246/PMD | 03/03/2023 | 788 | NUPUR CHANDRA HALDER | 69.09 | 0 | 65
33 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Manbazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000432/2022-2023 | 251PMD | 06/03/2023 | 60 | MOON LIGHT HOUSE | 12.08 | 0 | 80
34 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell at Manbazar w/s(zone-1) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000433/2022-2023 | 252/PMD | 06/03/2023 | 60 | SANTANU BANERJEE | 48.12 | 0 | 57
35 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 175kva voltage stabilizer for Augmentation of Manbazar w/s(Zone-1) scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000434/2022-2023 | 253/PMD | 06/03/2023 | 703 | SANTU MITRA | 18.25 | 0 | 59
36 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000003/2023-2024 | 612/PMD | 01/06/2023 | 0 | Resource Division | 3.1 | 0 | 0
37 | Purulia Mechanical | Purulia Sadar Sub-Division | Priming arrangement for two nos centrifugal pump and two back wash pump and other allied works at Hutmura (OHR) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | Assistant Engineer |  | ORD/000065/2024-2025 | 994/PMD | 21/06/2024 | 60 | SUBRATA DUTTA | 1.06 | 0 | 100
38 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply, Delivery and installation of submersible pumping machineries, flowmeter, backwash pump, chlorination system, external lighting arrangement with other allied works in connection with new WTP for augmentation of Hutmura(Intake side & new CWR Zone ) w/s scheme under PMD, PHE Dte. in the District of Purulia. | Assistant Engineer |  | ORD/000682/2024-2025 | 1694/PMD | 06/12/2024 | 90 | DEY ENTERPRISE, HOWRAH | 55.15 | 0 | 0
39 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | For new connection of Augmentation of Raghunathpur zone VII B | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | BILL/00776/2023-2024 | BP-23-24-278 | 01/02/2024 | 0 | WBSEDCL PURULIA | 0.26 | 0 | 0
40 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-IV) under Raghunathpur water supply project, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000009/2025-2026 | 620/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.88 | 0 | 0
41 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VII B under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000044/2023-2024 | 450/PMD | 20/04/2023 | 30 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 21.59 | 0 | 65
42 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone VII B under Purulia Mechanical Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000584/2024-2025 | 1443/PMD | 01/10/2024 | 60 | M/S A.D. CONCERN | 3.87 | 0 | 0
43 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and laying of cable and other works, at OHR site Ketlapur of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000609/2024-2025 | 857/PMD | 03/06/2024 | 10 | ANUP KUMAR SAHA | 0.64 | 0 | 95
44 | Purulia Mechanical | Raghunathpur Sub-Division | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE IIB | Assistant Engineer |  | BILL/00478/2023-2024 | BP-23-24-248 | 04/01/2024 | 0 | WBSEDCL PURULIA | 2.87 | 0 | 0
45 | Purulia Mechanical | Raghunathpur Sub-Division | Addition of column pipe including supply along with allied works, at OHR site-II B, Khajura under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000016/2025-2026 | 635/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.37 | 0 | 0
46 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone II B under PMD PHE Dte. District Purulia. | Assistant Engineer |  | ORD/000121/2023-2024 | 802/PMD | 12/07/2023 | 30 | A G ENTERPRISE | 21.84 | 0 | 85
47 | Purulia Mechanical | Raghunathpur Sub-Division | Earthing arrangement and other works, at OHR site Uporkhajura of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000605/2024-2025 | 899/PMD | 10/06/2024 | 15 | ANUP KUMAR SAHA | 0.5 | 0 | 90
48 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000655/2024-2025 | 1027/PMD | 25/06/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 95
49 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Executive Engineer, Purulia Mechanical Division PHE, Dte. (01/10/24 to 31/03/25) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000615/2024-2025 | 400/PMSD(W/S) | 23/09/2024 | 182 | TAPAN KUMAR DEY | 0.86 | 0 | 0
50 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000028/2024-2025 | 941/PMD | 19/06/2024 | 365 | WEST BENGAL ENGINEERING CO | 568.2 | 0 | 0
51 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000029/2024-2025 | 942/PMD | 19/06/2024 | 365 | CONCORD ENGINEERING | 516.53 | 0 | 0
52 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000030/2024-2025 | 943/PMD | 19/06/2024 | 365 | ORIENTAL ENGINEERING CO. | 723.12 | 0 | 0
53 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000031/2024-2025 | 944/PMD | 19/06/2024 | 365 | MAHADEV ENTERPRISE | 561.07 | 0 | 0
54 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000032/2024-2025 | 945/PMD | 19/06/2024 | 365 | ASHOKE ADHIKARY | 39.78 | 0 | 0
55 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000082/2024-2025 | 1018/PMD | 25/06/2024 | 365 | TAPAN KUMAR DEY | 53.82 | 0 | 0
56 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Jhalda II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000083/2024-2025 | 1019/PMD | 25/06/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 41.16 | 0 | 0
57 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Joypur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000084/2024-2025 | 1020/PMD | 25/06/2024 | 365 | A G ENTERPRISE | 34.82 | 0 | 0
58 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Kashipur Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000085/2024-2025 | 1021/PMD | 25/06/2024 | 365 | DEBJYOTI BASU | 53.82 | 0 | 0
59 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000086/2024-2025 | 1022/PMD | 25/06/2024 | 365 | SANTU MITRA | 12.66 | 0 | 0
60 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Neturia Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000087/2024-2025 | 1023/PMD | 25/06/2024 | 365 | SEN BROTHERS | 6.33 | 0 | 0
61 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Para Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000088/2024-2025 | 1024/PMD | 25/06/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 56.98 | 0 | 0
62 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Puncha Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000089/2024-2025 | 1025/PMD | 25/06/2024 | 365 | SUBRATA DUTTA | 22.15 | 0 | 0
63 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000090/2024-2025 | 1048/PMD | 28/06/2024 | 365 | ASHOKE ADHIKARY | 25.32 | 0 | 0
64 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Purulia II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000091/2024-2025 | 1049/PMD | 28/06/2024 | 365 | SAIBAL SARKAR | 47.49 | 0 | 0
65 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur I Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000092/2024-2025 | 1050/PMD | 28/06/2024 | 365 | BISHWANATH NANDI | 22.86 | 0 | 0
66 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Raghunathpur II Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000093/2024-2025 | 1051/PMD | 28/06/2024 | 365 | S. PATHAK & CO. | 15.82 | 0 | 0
67 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Santuri Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000094/2024-2025 | 1052/PMD | 28/06/2024 | 365 | NUPUR CHANDRA HALDER | 22.16 | 0 | 0
68 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Hura Block for Surface water based piped water supply scheme, (Northern Sector) Districts Purulia under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000328/2024-2025 | 1253/PMD | 22/08/2024 | 365 | KAMAKHYA ENTERPRISE | 45.76 | 0 | 0
69 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000461/2023-2024 | 466/PMD | 14/03/2024 | 365 | DEBJYOTI BASU | 59.65 | 0 | 0
70 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000462/2023-2024 | 467/PMD | 14/03/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 59.66 | 0 | 0
71 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000463/2023-2024 | 468/PMD | 14/03/2024 | 365 | DAS ENTERPRISE | 49.68 | 0 | 0
72 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000464/2023-2024 | 469/PMD | 14/03/2024 | 365 | SEN BROTHERS | 19.88 | 0 | 0
73 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000465/2023-2024 | 470/PMD | 14/03/2024 | 365 | NUPUR CHANDRA HALDER | 69.62 | 0 | 0
74 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000466/2023-2024 | 471/PMD | 14/03/2024 | 365 | SUNRISE ENGINEERING CORPORATION | 19.89 | 0 | 0
75 | Purulia Mechanical | Purulia Sadar Sub-Division | Internal illumination and outdoor lighting arrangement and other allied works for Augmentation of Balitora Water Supply Scheme under Purulia Mechanical Division. PHE. Dte. | Assistant Engineer |  | ORD/000466/2024-2025 | 1292/PMD | 30/08/2024 | 60 | PREMNATH MITRA | 7.83 | 0 | 2
76 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000467/2023-2024 | 493/PMD | 15/03/2024 | 365 | A G ENTERPRISE | 413.21 | 0 | 0
77 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | Assistant Engineer |  | ORD/000467/2024-2025 | 1293/PMD | 30/08/2024 | 182 | AVISHEK ENTERPRISE | 5.97 | 0 | 100
78 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000469/2023-2024 | 495/PMD | 15/03/2024 | 365 | EASTERN INDIA SALES AND SERVICE | 413.27 | 0 | 0
79 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000470/2023-2024 | 496/PMD | 15/03/2024 | 365 | DEY ENTERPRISE, HOWRAH | 474.14 | 0 | 0
80 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000472/2023-2024 | 498/PMD | 15/03/2024 | 365 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 103.28 | 0 | 0
81 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000473/2023-2024 | 499/PMD | 15/03/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 51.65 | 0 | 0
82 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000475/2023-2024 | 501/PMD | 15/03/2024 | 365 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 309.93 | 0 | 0
83 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000476/2023-2024 | 502/PMD | 15/03/2024 | 365 | AHALYA ENGINEERING WORKS | 206.45 | 0 | 0
84 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000478/2023-2024 | 504/PMD | 15/03/2024 | 365 | TAPAN KUMAR DEY | 257.9 | 0 | 0
85 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000479/2023-2024 | 505/PMD | 15/03/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 154.78 | 0 | 0
86 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery & Installation of Disinfection Arrangement & Illumination arrangement for OHR sites, at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000480/2023-2024 | 506/PMD | 15/03/2024 | 365 | PREMNATH MITRA | 206.89 | 0 | 0
87 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000483/2023-2024 | 472/PMD | 14/03/2024 | 365 | M/S A.D. CONCERN | 9.94 | 0 | 0
88 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Para Block at PWSS SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000484/2023-2024 | 473/PMD | 14/03/2024 | 365 | SAIBAL SARKAR | 39.78 | 0 | 0
89 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000485/2023-2024 | 474/PMD | 14/03/2024 | 365 | SANTU MITRA | 9.94 | 0 | 0
90 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Purulia I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000487/2023-2024 | 475/PMD | 14/03/2024 | 365 | JAL PRAVAHIKA PVT. LTD | 39.76 | 0 | 0
91 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000488/2023-2024 | 476/PMD | 14/03/2024 | 365 | M/S D. PALIT & CO. | 19.89 | 0 | 0
92 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000489/2023-2024 | 477/PMD | 14/03/2024 | 365 | PINTU DEY | 19.89 | 0 | 0
93 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000490/2023-2024 | 478/PMD | 14/03/2024 | 365 | COMBINE ENTERPRISES | 29.84 | 0 | 0
94 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Hura Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000662/2024-2025 | 1668/PMD | 05/12/2024 | 365 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0
95 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000663/2024-2025 | 1669/PMD | 05/12/2024 | 365 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 3.32 | 0 | 0
96 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Jhalda II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000664/2024-2025 | 1670/PMD | 05/12/2024 | 365 | SEN BROTHERS | 2.77 | 0 | 0
97 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Joypur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000665/2024-2025 | 1671/PMD | 05/12/2024 | 365 | SEN BROTHERS | 1.11 | 0 | 0
98 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Kashipur Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000666/2024-2025 | 1672/PMD | 05/12/2024 | 365 | NUPUR CHANDRA HALDER | 3.88 | 0 | 0
99 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000667/2024-2025 | 1673/PMD | 05/12/2024 | 365 | S. PATHAK & CO. | 1.11 | 0 | 0
100 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Para and Neturia Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000668/2024-2025 | 1674/PMD | 05/12/2024 | 365 | M/S A.D. CONCERN | 2.77 | 0 | 0
101 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia I and Puncha Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000669/2024-2025 | 1675/PMD | 05/12/2024 | 365 | SANTU MITRA | 2.77 | 0 | 0
102 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Purulia II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000670/2024-2025 | 1676/PMD | 05/12/2024 | 365 | ASHOKE ADHIKARY | 2.22 | 0 | 0
103 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur I Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000671/2024-2025 | 1677/PMD | 05/12/2024 | 365 | M/S D. PALIT & CO. | 1.11 | 0 | 0
104 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Raghunathpur II Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000672/2024-2025 | 1678/PPMD | 05/12/2024 | 365 | PINTU DEY | 1.11 | 0 | 0
105 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Santuri Block at PWSS for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR PURULIA DISTRICT (NORTHERN SECTOR) PHASE-II under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000673/2024-2025 | 1679/PMD | 05/12/2024 | 365 | COMBINE ENTERPRISES | 1.66 | 0 | 0
106 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation at Begunkodar O.H.R near H.S School, Po begunkadar Ps Kotshila. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00849/2023-2024 | BILL/00849/2023 | 01/03/2024 | 0 | WBSEDCL PURULIA | 0.41 | 0 | 0
107 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2021-2022 | 113/PMD | 28/02/2022 | 30 | ANUP KUMAR SAHA | 20.47 | 8.21 | 100
108 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of essential item on the intake Burge of Jhalda Augmentation W/S Scheme under P.M.D., P.H.E.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000183/2023-2024 | 1173/PMD | 03/11/2023 | 425 | ANUP KUMAR SAHA | 6.21 | 0 | 50
109 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing external illumination arrangement at WTP area of Jhalda Aug WTP under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000230/2023-2024 | 1206/PMD | 03/11/2023 | 60 | ANUP KUMAR SAHA | 2.74 | 0 | 100
110 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, MCC panel and with necessary substitutes and allied works at the intake of the Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000254/2022-2023 | 44/PMD | 19/01/2023 | 714 | ANUP KR. SAHA | 43.88 | 37.65 | 70
111 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of centrifugal pumping machineries, MCC panel, Flowmeter With necessary substitutes and allied works at WTP area of Jhalda Augmentation w/s project under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000270/2022-2023 | 45/PMD | 19/01/2023 | 60 | SUNRISE ENGINEERING CORPORATION | 49.44 | 0 | 60
112 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at OHR site for Augmentation of Jhalda Water Supply scheme Block Jhalda under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000291/2022-2023 | 83/PMD | 01/02/2023 | 670 | ANUP KR. SAHA | 21.57 | 11.02 | 100
113 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000009/2023-2024 | 618/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
114 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF JHALDA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 343 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000084/2022-2023 | C042211566405 | 08/04/2022 | 0 | ANUP KR. SAHA | 12.25 | 0 | 0
115 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 1 Site) Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000006/2022-2023 | 309/PMD | 11/05/2022 | 30 | ANUP KR. SAHA | 20.47 | 19.57 | 96
116 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sutabai Water Supply scheme (OHR no 2 Site ) Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000007/2022-2023 | 310/PMD | 11/05/2022 | 30 | COMBINE ENTERPRISE | 20.48 | 19.57 | 96
117 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery & installation of flow meter and with others allied works for Augmentation Sutaboi w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. (w.e.f 01.11.23 to 31.12.23) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000019/2023-2024 | 390/PMD | 06/04/2023 | 60 | S. PATHAK & CO. | 4.85 | 0 | 100
118 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal lighting arrangement at Sutaboi pump house, Chlorination room at OHR site 1&2 with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE, Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000020/2023-2024 | 391/PMD | 06/04/2023 | 60 | S. PATHAK & CO. | 2.74 | 0 | 100
119 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied works at OHR-1 for Augmentation of sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000021/2023-2024 | 392/PMD | 06/04/2023 | 60 | MOUSUMI BENERJEE | 5.88 | 0 | 100
120 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Riverbed illumination arrangement with others allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000022/2023-2024 | 393/PMD | 06/04/2023 | 60 | MAHIPAL MAJHI | 5.95 | 0 | 100
121 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machinery with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000046/2024-2025 | 965/PMD | 20/06/2024 | 469 | NUPUR CHANDRA HALDER | 20.18 | 0 | 20
122 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied works at OHR-2 under sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000131/2023-2024 | 869/PMD | 21/07/2023 | 60 | M/S UJJAL DIESEL SERVICE | 5.81 | 0 | 100
123 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000438/2023-2024 | 418/PMD | 11/03/2024 | 60 | ASHOKE ADHIKARY | 8.07 | 0 | 0
124 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery, Storage, Installation and Commissioning of Chlorination Arrangement at Head work site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000460/2023-2024 | 440/PMD | 11/03/2024 | 570 | M/S D.G.B.ENTERPRISE | 25 | 0 | 97
125 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation submersible pumping machineries at new deep tube well, MCC panel and laying of cable line, with others allied works for augmentation of Sutaboi water supply scheme under Purulia Mechanical Division, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000477/2022-2023 | 324/PMD | 22/03/2023 | 60 | COMBINE ENTERPRISES | 71.28 | 38.44 | 100
126 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of MCC panel at Sutaboi Water Supply Scheme under Purulia Mechanical Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000486/2023-2024 | 193/PMD | 16/02/2024 | 15 | SUJIT MUKHERJEE | 0.64 | 0 | 100
127 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of 150KVA oil cooled voltage stabilizer and supply cable and making cable trench with allied works for Augmentation of Sutaboi w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000487/2022-2023 | 353/PMD | 27/03/2023 | 60 | SWAPAN ENTERPRISE | 18.17 | 0 | 100
128 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of Booster pumping machinery for gaseous chlorination system at OHR-I site of Sutaboi W/S scheme under PMD P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000494/2023-2024 | 218/PMD | 20/02/2024 | 15 | S. PATHAK & CO. | 0.96 | 0 | 100
129 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal Pump set with other allied work at River site of Augmentation of Sutaboi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | ORD/000582/2024-2025 | 1473/PMD | 21/10/2024 | 120 | COMBINE ENTERPRISES | 5.61 | 0 | 0
130 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION AT OHR 2 SITE OF SUTABAI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000327/2022-2023 | BP-2022-23-33 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0
131 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR OHR SITE AT SUTABOI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL),Junior Engineer-3 | VCH/000328/2022-2023 | BP-2022-23-32 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0
132 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for OHR 1 at Augmentation of Arrha Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00026/2022-2023 | BP-22-23-83 | 24/02/2023 | 0 | WBSEDCL PURULIA | 1.16 | 0 | 0
133 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for OHR 2(Manpura) under Augmentation of Arrha Water Supply Scheme under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00027/2022-2023 | BP-23-24-271 | 22/01/2024 | 0 | WBSEDCL PURULIA | 0.31 | 0 | 0
134 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000063/2024-2025 | 992/PMD | 21/06/2024 | 60 | M/S R.K. ENTERPRISE | 4.6 | 0 | 100
135 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Arrah Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000069/2021-2022 | 114/PMD | 28/02/2022 | 30 | TAPAN KUMAR DEY | 20.47 | 11.71 | 100
136 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Augmentation of existing old LBSF unit by the new one VCB (one incoming two outgoing) at Arrah W/S scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000119/2023-2024 | 800/PMD | 12/07/2023 | 782 | COMBINE ENTERPRISES | 29.23 | 0 | 81
137 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Internal lighting and external lighting for Arrah w/s scheme(Zone-1and Zone-II) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000123/2023-2024 | 819/PMD | 14/07/2023 | 262 | M/S A.D. CONCERN | 5.9 | 0 | 100
138 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting fixing of ST pole and laying of cable line for lighting arrangement at(Z-I, Z-II and pump house) with other allied works under Arrah Water Supply Scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000216/2023-2024 | 1202/PMD | 03/11/2023 | 395 | TAPAN KUMAR DEY | 6.6 | 0 | 70
139 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Submersible pumping machineries for Direct pumping with other allied works for Augmentation at arrah w/s (zone-l) scheme under PMD, PHE, Dte. in the District of Puurlia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000298/2022-2023 | 89/PMD | 02/02/2023 | 60 | SAMAN KUMAR MAHATO | 14.03 | 9.72 | 100
140 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of submersible pumping machinery at newly constructed River Bed Tubewell for Augmentation of Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000369/2022-2023 | 199/PMD | 28/02/2023 | 954 | JAL PRAVAHIKA PVT. LTD | 22.65 | 0 | 75
141 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Centrifugal pumping machinery with MCC panel, Flow meter and other allied works for Augmentation at Arrah w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000370/2022-2023 | 200/PMD | 28/02/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 71.89 | 12.98 | 100
142 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-1for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000383/2022-2023 | 214/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.62 | 12.91 | 100
143 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Arrah OHR-2 for Augmentation of Arrah Water Supply scheme Block Raghunathpur-I under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000384/2022-2023 | 215/PMD | 28/02/2023 | 30 | TAPAN KUMAR DEY | 21.61 | 12.88 | 80
144 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 50 KVA voltage stabilizer at Arrah OHR site(Z-I) for Augmentation of Arrah water supply scheme under PMD PHE Dte. in the district of purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000390/2023-2024 | 375/PMD | 04/03/2024 | 60 | BISHWANATH NANDI | 7.09 | 0 | 100
145 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF ARRAH WATER SUPPLY SCHEME UNDER KASHIPUR BLOCK (TR.NO 373 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | VCH/000095/2022-2023 | C042228557261 | 13/04/2022 | 0 | TAPAN KUMAR DEY | 8.76 | 0 | 0
146 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Puncha W/S Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00251/2023-2024 | BP-2023-24-155 | 14/09/2023 | 0 | WBSEDCL PURULIA | 2.8 | 0 | 0
147 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Puncha. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00487/2023-2024 | BP-23-24-247 | 28/12/2023 | 0 | WBSEDCL PURULIA | 11.46 | 0 | 0
148 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000047/2023-2024 | 516/PMD | 05/05/2023 | 981 | EASTERN INDIA SALES AND SERVICE | 65.68 | 0 | 36
149 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Puncha w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000048/2023-2024 | 517/PMD | 05/05/2023 | 644 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 50.41 | 0 | 80
150 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Augmentation of Puncha w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000130/2023-2024 | 868/PMD | 21/07/2023 | 60 | SOUVIK MANDAL | 2.83 | 0 | 100
151 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing and installation of HOT Crane, Electro magnetic Flow meter and other allied woks for Augmentation of Puncha Water Supply Scheme (River Site) under purilia Mechanical Division, P.H.E. Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000206/2023-2024 | 1196/PMD | 03/11/2023 | 180 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 10.26 | 0 | 80
152 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Puncha w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000438/2022-2023 | 257/PMD | 06/03/2023 | 894 | SWAPAN MANDAL | 3.01 | 0 | 90
153 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Puncha w/s scheme(OHR Site) for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000439/2022-2023 | 258/PMD | 06/03/2023 | 894 | SWAPAN MANDAL | 7.71 | 4.29 | 60
154 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of submersible pumping machinery at with MCC panel newly constructed River Bed Tubewell for Augmentation of Puncha w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000440/2022-2023 | 259/PMD | 06/03/2023 | 1062 | ANUP KR. SAHA | 36.41 | 6.72 | 66
155 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 125kva voltage stabilizer for Augmentation of Puncha(River Site) w/s scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000441/2022-2023 | 260/PMD | 06/03/2023 | 907 | SEN BROTHERS | 13.61 | 10.04 | 100
156 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Open well Submersible pumping machinery with others electro-mechanical work at Puncha River site for Augmentation of Puncha PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000756/2024-2025 | 40/PMD | 10/01/2025 | 325 | S. PATHAK & CO. | 9.44 | 0 | 100
157 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000006/2023-2024 | 615/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
158 | Purulia Mechanical | Raghunathpur Sub-Division | New service connection at Saltore Hijuli OHR site | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00111/2024-2025 | BP-24-25-15 | 24/05/2024 | 0 | WBSEDCL SALTORE CCC | 0.11 | 0 | 0
159 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for removal of one 63 KVA DTR along with one span HT & one span LT line at the premises of Saltore Hijuli PHE | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00435/2023-2024 | BP-23-24-222 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.09 | 0 | 0
160 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Saltore Hijuli Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000040/2023-2024 | 446/PMD | 20/04/2023 | 30 | T.N.BANERJEE | 21.56 | 0 | 50
161 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 8 nos. River bed submersible pumps motor sets with other allied works for SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000058/2023-2024 | 527/PMD | 05/05/2023 | 60 | INDRAJIT MITRA | 23.5 | 0 | 8
162 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and Installation of Submersible pumping machineries for newly constructed tube wells and other allied works for Augmentation of Saltore hijuli W/S scheme under PMD Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000058/2024-2025 | 976/PMD | 20/06/2024 | 60 | BISHWANATH NANDI | 8.76 | 0 | 70
163 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and delivery of Free chlorine test kit at different Pumping water supply scheme under Purulia Mechanical Division, PHE Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000321/2023-2024 | 46/PMSD(W/S) | 08/02/2024 | 15 | M/S R.K. ENTERPRISE | 0.94 | 0 | 100
164 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of CWR Submersible pumping machineries, MCC Panels, flow meter with others allied works for Augmentation at SALTORE HIJULI ( ZONE-3) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000347/2022-2023 | 132/PMD | 20/02/2023 | 60 | M/S D. PALIT & CO. | 27.01 | 0 | 35
165 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels, flow meter, HOT crane with others allied works for Augmentation at SALTORE HIJULI (ZONE-1 and 2) w/s scheme under PMD, PHE Dte. in the District of Purulia . | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000349/2022-2023 | 134/PMD | 20/02/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 70.46 | 9.06 | 100
166 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works at SALTORE HIJULI w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000350/2022-2023 | 135/PMD | 20/02/2023 | 60 | BISHWANATH NANDI | 7.64 | 7.63 | 0
167 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and fitting fixing of Mainswitch and cable for Pumphouse and internal and external illumination of OHR site for Augmentation at Saltore Hijuli(Zone-1 & 2) w/s supply scheme under PMD,PHE Dte .in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000391/2023-2024 | 376/PMD | 04/03/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 10.49 | 0 | 100
168 | Purulia Mechanical | Raghunathpur Sub-Division | Testing commissioning of Gaseous chlorination system and extension of solution line upto OLD CWR for Augmentation at Saltore Hijuli (Zone-1 & 2) under PMD, PHE Dte in the district of Purulia. (2ND Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000566/2024-2025 | 353/PMSD(W/S) | 04/09/2024 | 392 | BISHWANATH NANDI | 0.81 | 0 | 100
169 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of automatically controlled diaphragm type Chlorinator dosing pump with Piping & structural works in connection with Disinfection arrangement System for zone-III & Miscellaneous works at Pump House under Saltore-Hijuli W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000642/2024-2025 | 1574/PMD | 14/11/2024 | 107 | BISHWANATH NANDI | 4.42 | 0 | 100
170 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FOR AUGMENTATION OF SALTORE HIJULI WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000425/2022-2023 | BP-22-23-85 | 28/02/2023 | 0 | WBSEDCL PURULIA | 4.68 | 0 | 0
171 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Joypur (River Side) W/S Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00245/2023-2024 | BP-2023-24-150 | 14/09/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0
172 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection For Augmentation of Joypur | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00246/2023-2024 | BP-2023-24-149 | 14/09/2023 | 0 | WBSEDCL PURULIA | 4.45 | 0 | 0
173 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Joypur (OHR side) water supply scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000031/2023-2024 | 421/PMD | 13/04/2023 | 60 | MERCURY ENGINEERING COMPANY | 36.21 | 0 | 30
174 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Joypur(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000120/2023-2024 | 801/PMD | 12/07/2023 | 664 | M/S P.P.ELECTRICALS | 15.63 | 0 | 96
175 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied work at Joypur water Supply Scheme (River Site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000203/2023-2024 | 1193/PMD | 03/11/2023 | 60 | S. PATHAK & CO. | 10.83 | 0 | 56
176 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Joypur OHR for Augmentation of Joypur Water supply scheme block Joypur under PMD PHE Dte. district Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000381/2022-2023 | 212/PMD | 28/02/2023 | 30 | ANUP KR. SAHA | 21.6 | 12.92 | 93
177 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement of internal lighting with other allied works for augmentation of Joypur (River side & OHR side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000424/2022-2023 | 242/PMD | 03/03/2023 | 60 | MD. ASLAM | 1.21 | 0 | 60
178 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Joypur(riverside) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000425/2022-2023 | 243/PMD | 03/03/2023 | 367 | ANUP KR. SAHA | 70.91 | 33.7 | 66
179 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Joypur(Riverside) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000426/2022-2023 | 244/PMD | 03/03/2023 | 790 | COMBINE ENTERPRISES | 58.94 | 38.28 | 35
180 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Joypur(OHR Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000427/2022-2023 | 245/PMD | 03/03/2023 | 60 | ANUP KR. SAHA | 10.76 | 6.2 | 96
181 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Yard lighting arrangement with others allied work at Joypur water supply scheme (OHR site) for Augmentation of Joypur PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000438/2023-2024 | 418/PMD | 11/03/2024 | 60 | ASHOKE ADHIKARY | 8.07 | 0 | 0
182 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | RTOR000004/2023-2024 | 613/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
183 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Dubra (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000039/2023-2024 | 445/PMD | 20/04/2023 | 30 | DEY ENTERPRISE,MALDAH | 21.63 | 0 | 70
184 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Dubra water supply scheme under PMD PHE Dte. In the district of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000182/2023-2024 | 1172/PMD | 03/11/2023 | 60 | SWAPAN ENTERPRISE | 7.21 | 0 | 75
185 | Purulia Mechanical | Raghunathpur Sub-Division | Internal and external illumination with other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000184/2023-2024 | 1174/PMD | 03/11/2023 | 60 | PINTU DEY | 5.37 | 0 | 25
186 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, HOT, Flowmeter and other allied works for augmentation of Dubra water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000456/2022-2023 | 296/PMD | 16/03/2023 | 60 | TAPAN KUMAR DEY | 42.49 | 0 | 40
187 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Satra Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000078/2021-2022 | 163/PMD | 07/03/2022 | 30 | DEY ENTERPRISE | 20.5 | 12.28 | 85
188 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of two nos. submersible pumping machineries in newly constructed river bed tube well, voltage stabilizer with allied cable line and other allied works for augmentation of Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000095/2022-2023 | 521/PMD | 05/08/2022 | 30 | NUPUR CHANDRA HALDER | 22.86 | 21 | 92
189 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Centrifugal pumping machineries, floor mounted MCC panel, HOT Crane, Flow meter and other allied works at Satra high Lift (Boosting Station) for Augmentation of Satra Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000200/2023-2024 | 1190/PMD | 03/11/2023 | 90 | NUPUR CHANDRA HALDER | 43.54 | 0 | 85
190 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of headwork site centrifugal pumping machineries, augmentation of MCC panel, Flow meter and other allied works for augmentation of Satra (River side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000344/2022-2023 | 129/PMD | 20/02/2023 | 60 | NUPUR CHANDRA HALDER | 36.75 | 36.26 | 51
191 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries for river bed tube well with allied cable line and other allied works for Satra w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000687/2024-2025 | 1699/PMD | 06/12/2024 | 30 | NUPUR CHANDRA HALDER | 3.31 | 0 | 0
192 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000010/2023-2024 | 620/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
193 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | SUPPLY DELIVERY & INSTT OF TWO NOS SUBMERSIBLE PUMP MOTOR SETS IN NEW CONSTRUCTED RIVERBED TUBE WELL AND LAYING OF DEPARTMENTALLY SUPPLIED CABLE LINE WITH OTHER ALLIED WORKS FOR SATRA W/S SCHEME UNDER PMD PHE DTE.(TR.NO 326/21-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000113/2022-2023 | C052221499438 | 11/05/2022 | 0 | NUPUR CHANDRA HALDER | 2.4 | 0 | 0
194 | Purulia Mechanical | Raghunathpur Sub-Division | New Connection for Augmentation of para W/S | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | BILL/00247/2023-2024 | BP-23-24-151 | 14/09/2023 | 0 | WBSEDCL PURULIA | 7.5 | 0 | 0
195 | Purulia Mechanical | Raghunathpur Sub-Division | Internal and external illumination with other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000017/2023-2024 | 388/PMD | 06/04/2023 | 802 | M/S KARUNAMOYEE CONSTRUCTION | 5.33 | 0 | 40
196 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Para (Pump house site) Water Supply scheme Block Para under PMD PHE Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000038/2023-2024 | 444/PMD | 20/04/2023 | 30 | MS SAJAHAN CHOWDHURY | 21.63 | 0 | 100
197 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of headwork site centrifugal pumping machineries, backwash pumping machineries, MCC panel, H.O.T., Flowmwter and other allied works for augmentation of Para water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000373/2022-2023 | 203/PMD | 28/02/2023 | 60 | RABINDRA NATH KHAN | 76.22 | 13.88 | 100
198 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of submersible pumping machineries into the intake well with allied cable line and other allied works for augmentation of Para w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000374/2022-2023 | 204/PMD | 28/02/2023 | 60 | PINTU DEY | 10.13 | 4.41 | 100
199 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 150 KVA voltage stabilizer for Augmentation of Para water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000375/2022-2023 | 205/PMD | 28/02/2023 | 60 | M/S D. PALIT & CO. | 15.06 | 0 | 100
200 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and laying of 185 sq mm XLPE cable at para water supply scheme under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000592/2024-2025 | 1450/PMD | 01/10/2024 | 30 | SUMIT KUMAR CHAKRABORTY | 4.24 | 0 | 100
201 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and Delivery and installation intake well cover & allied work at para water supply scheme under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000679/2024-2025 | 1691/PMD | 06/12/2024 | 30 | PINTU DEY | 2.04 | 0 | 100
202 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at para water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-4 | ORD/000686/2024-2025 | 1698/PMD | 06/12/2024 | 90 | KAMAKHYA ENTERPRISE | 15.46 | 0 | 0
203 | Purulia Mechanical | Purulia Sadar Sub-Division | Different Electro-Mechanical works at Sub-Station at Bundwan under Augmentation of Bundwan Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | Assistant Engineer |  | ORD/000041/2024-2025 | 954/PMD | 19/06/2024 | 90 | M S ENTERPRISE | 30.22 | 0 | 100
204 | Purulia Mechanical | Purulia Sadar Sub-Division | Arrangement for high pressure testing of SubStation equipment for 250 KVA Sub - Station at Bundwan w/s Scheme under Purulia Mechanical Division,PHE,Dte. | Assistant Engineer |  | ORD/000079/2024-2025 | 1016/PMD | 25/06/2024 | 30 | M S ENTERPRISE | 1.19 | 0 | 100
205 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & fitting fixing of Main switch, valve and other electro-mechanical accessories at WTP site for Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000057/2024-2025 | 975/PMD | 20/06/2024 | 60 | SUBRATA DUTTA | 3.98 | 0 | 100
206 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machinery, Voltage stabilizer with other allied work for direct pumping at OHR site of Augmentation of Bagmundi water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000109/2024-2025 | 1173/PMD | 31/07/2024 | 478 | PINTU DEY | 29.04 | 0 | 25
207 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation 60kva voltage stabilizer for Augmentation of Bagmundi w/s scheme for under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000227/2023-2024 | 1205/PMD | 03/11/2023 | 120 | BISHWANATH NANDI | 7.74 | 0 | 100
208 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & delivery of electric cable at Bagmundi water supply scheme for Augmentation of Bagmundi PWSS under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000303/2023-2024 | 385/PMSD(W/S) | 17/10/2023 | 15 | SEN BROTHERS | 0.92 | 0 | 100
209 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bathanbari Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000075/2021-2022 | 160/PMD | 07/03/2022 | 30 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 20.5 | 4.38 | 100
210 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply Delivery and installation of Submersible pumping machinery, MCC Panel, Voltage stabilizer, flow meter, ilumination arrangement with allied works for augmentation of Bathanbari PWSS under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000092/2022-2023 | 518/PMD | 05/08/2022 | 60 | COMBINE ENTERPRISES | 46.66 | 40.38 | 82
211 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of fabricated M.S. structure barge with others allied works at Augmentation of Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000210/2022-2023 | 192/PMSD (W/S) | 22/06/2022 | 21 | COMBINE ENTERPRISES | 4.27 | 3.29 | 80
212 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & delivery of submersible pumping machinery at Bathanbari w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000263/2023-2024 | 1234/PMD | 08/11/2023 | 15 | COMBINE ENTERPRISES | 0.68 | 0 | 100
213 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Lagda, Dimdiha, Sonaijuri GP in Purulia-I Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000324/2022-2023 | 23/PMSD (Drilling) | 01/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
214 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Udyeshpur GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000325/2022-2023 | 24/PMSD (Drilling) | 01/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
215 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Dubra, Para GP in Para Block within the district of Purulia under code SM10285 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000327/2022-2023 | 19/PMSD (Drilling) | 31/01/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
216 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Execution of the yield test at Joradih GP in Raghunathpur-II Block within the district of Purulia under code SM10250 under PMD, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000330/2022-2023 | 26/PMSD (Drilling) | 02/02/2023 | 15 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 0.98 | 0 | 0
217 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000459/2023-2024 | 439/PMD | 11/03/2024 | 60 | PINTU DEY | 25.09 | 0 | 50
218 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and delivery of submersible pump motor sets at Bathanbari W/S scheme under PMD P.H.E Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000481/2023-2024 | 197/PMD | 16/02/2024 | 15 | PINTU DEY | 0.6 | 0 | 100
219 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and delivery of submersible pump motor sets at Bathanbari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000495/2023-2024 | 343/PMD | 28/02/2024 | 15 | S PATHAK AND CO | 0.6 | 0 | 100
220 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Hose pipes and other works at Bathanbari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000531/2023-2024 | 436/PMD | 11/03/2024 | 60 | ANUP KUMAR SAHA | 15.88 | 0 | 50
221 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTT OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BATHANBARI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 347 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000087/2022-2023 | C042211590242 | 08/04/2022 | 0 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 12.27 | 0 | 0
222 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 1kg/hr gaseous chlorination system of Aug. of Bathanbari water supply scheme.(Tr.no 347 of 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000512/2022-2023 | C112206903482 | 10/11/2022 | 0 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 3.84 | 0 | 0
223 | Purulia Mechanical | Purulia Sadar Sub-Division | Continuation Work Order for "Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/05/25 to 28/10/25)" | Assistant Engineer |  | ORD/000021/2025-2026 | 76/PMSD(Drilling) | 28/04/2025 | 181 | NUPUR CHANDRA HALDER | 0.86 | 0 | 0
224 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000095/2024-2025 | 1053/PMD | 28/06/2024 | 365 | DAS ENTERPRISE | 50.63 | 0 | 0
225 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000096/2024-2025 | 1054/PMD | 28/06/2024 | 365 | M/S S.G.ENTERPRISE | 31.65 | 0 | 0
226 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000097/2024-2025 | 1055/PMD | 28/06/2024 | 365 | ANUP KUMAR SAHA | 50.65 | 0 | 0
227 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Voltage Stabilizer and allied works for different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000098/2024-2025 | 1056/PMD | 28/06/2024 | 365 | RABINDRA NATH KHAN | 25.32 | 0 | 0
228 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000513/2023-2024 | 515/PMD | 15/03/2024 | 365 | COMBINE ENTERPRISES | 154.79 | 0 | 0
229 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000514/2023-2024 | 516/PMD | 15/03/2024 | 365 | GOENKA ENTERPRISE | 258.09 | 0 | 0
230 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection arrangement and Illumination arrangement for OHR sites, at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000515/2023-2024 | 517/PMD | 15/03/2024 | 365 | SINHA ELECTRICALS | 206.55 | 0 | 0
231 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000518/2023-2024 | 479/PMD | 14/03/2024 | 365 | SUBRATA DUTTA | 69.61 | 0 | 0
232 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000519/2023-2024 | 480/PMD | 14/03/2024 | 365 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 69.58 | 0 | 0
233 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000520/2023-2024 | 481/PMD | 14/03/2024 | 365 | RABINDRA NATH KHAN | 109.36 | 0 | 0
234 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Diaphragm type Automatic Chlorinator and Illumination arrangement for OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000521/2023-2024 | 482/PMD | 14/03/2024 | 365 | M/S D.G.B.ENTERPRISE | 39.77 | 0 | 0
235 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000674/2024-2025 | 1680/PMD | 05/12/2024 | 365 | SUBRATA DUTTA | 3.88 | 0 | 0
236 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Balarampur Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000675/2024-2025 | 1681/PMD | 05/12/2024 | 365 | S. PATHAK & CO. | 3.88 | 0 | 0
237 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Bandwan Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000676/2024-2025 | 1682/PMD | 05/12/2024 | 365 | RABINDRA NATH KHAN | 6.1 | 0 | 0
238 | Purulia Mechanical | Purulia Sadar Sub-Division | Piping and structural works in connection with Disinfection arrangement System at different OHR sites at Manbazar-II Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000677/2024-2025 | 1683/PMD | 05/12/2024 | 365 | PINTU DEY | 2.22 | 0 | 0
239 | Purulia Mechanical | Purulia Sadar Sub-Division | Supply Delivery and Installation of Disinfection Arrangement and Illumination arrangement for OHR sites, at Bagmundi Block for PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR PHASE-II for Purulia District under Purulia Mechanical Division, P.H.E. Dte.(2nd Call) | Assistant Engineer |  | ORD/000701/2024-2025 | 1740/PMD | 16/12/2024 | 365 | R.N.S. TRADING | 470.76 | 0 | 0
240 | Purulia Mechanical | Purulia Sadar Sub-Division | Hiring of One no. inspection vehicle for Office of the Driller-in-Charge, PMSD (Drilling) under Purulia Mechanical Division PHE Dte. (w.e.f 01/11/24 to 30/04/25) | Assistant Engineer |  | ORD/000779/2024-2025 | 473/PMSD(Drilling) | 24/09/2024 | 181 | NUPUR CHANDRA HALDER | 0.86 | 0 | 0
241 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | NEW CONNECTION FOR AUGMENTATION OF SIRKABAD | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00477/2023-2024 | BP-23-24-249 | 04/01/2024 | 0 | WBSEDCL PURULIA | 7.42 | 0 | 0
242 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and lowering of submersible pump motor sets at newly constructed River Bed Tubewell with supply of necessary substitute at Sirkabad water supply scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000025/2023-2024 | 410/PMD | 10/04/2023 | 632 | M/S S.G.ENTERPRISE | 26.76 | 10.41 | 40
243 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Flowmeter at Sirkabad water supply scheme under , PMD, PHE;Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000035/2023-2024 | 440/PMD | 19/04/2023 | 623 | BISHWANATH NANDI | 4.67 | 0 | 80
244 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Submersible Pump motor and other related works at Sirkabad w/s scheme under Purulia Mechanical Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000043/2024-2025 | 956/PMD | 19/06/2024 | 90 | RABINDRA NATH KHAN | 3.88 | 0 | 70
245 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Yard lighting arrangement with others allied work at Sirkabad water supply scheme (Pump house & OHR site) for Augmentation of Sirkabad PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000062/2024-2025 | 991/PMD | 21/06/2024 | 178 | ASISH KR. SEN | 11.2 | 0 | 80
246 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sirkabad Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000082/2021-2022 | 167/PMD | 07/03/2022 | 30 | MAHADEV ENTERPRISE | 20.89 | 20.58 | 100
247 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Centrifugal pumping machineries with necessary substitutes and allied works at Augmentation of SIRKABAD W/S scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000444/2022-2023 | 263/PMD | 06/03/2023 | 60 | RABINDRA NATH KHAN | 56.33 | 34.99 | 70
248 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of voltage stabilizer at Sirkabad W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000446/2022-2023 | 265/PMD | 06/03/2023 | 60 | GOUTAM CHAKRABORTY | 12.75 | 9.4 | 75
249 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and laying of Cable of river bed tube well with other allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000580/2024-2025 | 1438/PMD | 01/10/2024 | 30 | M/S S.G.ENTERPRISE | 2.91 | 0 | 50
250 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of Submersible Pump of river bed tube well, Flowmeter & Water level transmiter with others allied works at Sirkabad w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000640/2024-2025 | 1572/PMD | 14/11/2024 | 90 | M/S D. PALIT & CO. | 22.94 | 0 | 0
251 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | BILL/00454/2023-2024 | BP-23-24-223 | 05/12/2023 | 0 | WBSEDCL PURULIA | 1.87 | 0 | 0
252 | Purulia Mechanical | Raghunathpur Sub-Division | Supply,delivery and installation of Submersible pumping machineries and Al. Armoured cables for Augmentation of Lachhiyar W/S scheme under PMD Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000069/2024-2025 | 997/PMD | 21/06/2024 | 60 | M/S UJJAL DIESEL SERVICE | 2.83 | 0 | 74
253 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lachayara Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000091/2021-2022 | 189/PMD | 14/03/2022 | 1022 | M/S ESTERN INDIA SALES AND SERVICE | 20.62 | 13.93 | 80
254 | Purulia Mechanical | Raghunathpur Sub-Division | Yard lighting arrangement with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000186/2023-2024 | 1176/PMD | 03/11/2023 | 60 | MOUSUMI BENERJEE | 5.02 | 0 | 76
255 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation submersible pumping machineries at new deep tube well and laying of cable line, with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000301/2022-2023 | 90/PMD | 03/02/2023 | 708 | KOUSHIK CHATTERJEE | 32.79 | 15.21 | 50
256 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000302/2022-2023 | 91/PMD | 03/02/2023 | 60 | MAHADEV ENTERPRISE | 51.57 | 0 | 35
257 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 60KVA oil cooled voltage stabilizer and allied works for Augmentation of Lachiyara w/s scheme under PMD, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000304/2022-2023 | 92/PMD | 03/02/2023 | 60 | EMCON | 6.79 | 0 | 75
258 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of 30KVA oil cooled voltage stabilizer(at OLD Pump house) and Double tank dosing system Miscellaneous works at under Lachhiyara W/S Scheme, Purulia Mechanical Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000639/2024-2025 | 1571/PMD | 14/11/2024 | 60 | TAPAN KUMAR DEY | 6.97 | 0 | 0
259 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Full deposit scheme for Chitmu water pump under Jhalda CCC | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00253/2023-2024 | BP-2023-24-147 | 15/09/2023 | 0 | WBSEDCL PURULIA | 2.45 | 0 | 0
260 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Chitmu W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000016/2021-2022 | 20/PMD | 19/01/2022 | 45 | M/S D. PALIT & CO. | 30.6 | 27.21 | 0
261 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Flowmeter & 50KVA voltage stabilizer and with others allied works at Chitmu water supply scheme under , PMD, PHE;Dte.in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000016/2023-2024 | 387/PMD | 06/04/2023 | 60 | M/S UJJAL DIESEL SERVICE | 7.49 | 0 | 100
262 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of pumping machineries with Allied works at Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000022/2022-2023 | 306/PMD | 06/05/2022 | 30 | RABINDRA NATH KHAN | 35.6 | 29.77 | 85
263 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Centrifugal pumping machineries,, with all ancillaries & auxiliaries including allied works at CWR side pump house at Chitmu Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000023/2023-2024 | 394/PMD | 06/04/2023 | 60 | M S ENTERPRISE | 33.26 | 0 | 100
264 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Chitmu Water Supply scheme Block Jhalda-II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000083/2021-2022 | 168/PMD | 07/03/2022 | 30 | CINZANO | 20.5 | 13.97 | 100
265 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of lighting arrangement at pump house with other allied works for Augmentation of Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000179/2023-2024 | 1150/PMD | 17/10/2023 | 30 | M/S UJJAL DIESEL SERVICE | 4.75 | 0 | 100
266 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 2 MT capacity HOT Crane with other allied works for Augmentation of Chitmu Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000204/2023-2024 | 1194/PMD | 03/11/2023 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 8.27 | 0 | 100
267 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at pumphouse site with other allied works under Chitmu w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000551/2023-2024 | 377/PMD | 04/03/2024 | 212 | M/S UJJAL DIESEL SERVICE | 5.56 | 0 | 100
268 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting-fixing of MS pipe, valves and dismantling joint at Chitmu W/S scheme under P.M.D. P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000559/2023-2024 | 72/PMSD(W/S) | 23/02/2024 | 15 | M S ENTERPRISE | 0.94 | 0 | 100
269 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Sinking of 200mmX165mm tubewell with installation of submersible pumping machinery, Cable and other works for Augmentation of Chitmu w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000617/2024-2025 | 1537/PMD | 11/11/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 8.74 | 0 | 40
270 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000007/2023-2024 | 616/PMD | 01/06/2023 | 0 | Resource Division | 0.34 | 0 | 0
271 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | LOAD ENHANCEMENT APPLICATION FOR CHITMU WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000325/2022-2023 | BP-2022-23-39 | 08/09/2022 | 0 | WBSEDCL PURULIA | 1.7 | 0 | 0
272 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ajodhya Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000021/2022-2023 | 320/PMD | 17/05/2022 | 30 | ALPHA ENTERPRISES | 20.5 | 20.49 | 100
273 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Open well Submersible pumping machinery, MCC Panel with others electro-mechanical work at Manbazar Baludih for Augmentation of Manbazar PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000052/2024-2025 | 970/PMD | 20/06/2024 | 60 | M/S D. PALIT & CO. | 11.74 | 0 | 0
274 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Ajodhya W/S Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000061/2021-2022 | 107/PMD | 28/02/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 20.4 | 20.37 | 100
275 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Submersible pumping machineries with all ancillaries & auxiliaries for augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000094/2022-2023 | 520/PMD | 05/08/2022 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 31.83 | 31.18 | 100
276 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machineries,with all ancillaries & auxiliaries including allied works for augmentation of Ajodhya Water Supply Scheme,under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000100/2022-2023 | 527/PMD | 05/08/2022 | 30 | SWAPAN ENTERPRISE | 9.45 | 8.8 | 100
277 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of submersible pumping machinery for Direct Pumping with Flow meter for Augmentation of Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000136/2023-2024 | 903/PMD | 04/08/2023 | 30 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 7.54 | 0 | 90
278 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Indoor & outdoor illumination arrangement with others electro-mechanical work at Ajodhya water supply scheme (Low lift) for Augmentation of Ajodhya PWSS under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000230/2024-2025 | 1224/PMD | 13/08/2024 | 264 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 6.95 | 0 | 30
279 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Electrification and Rectification of lighting arrangement at pump house with other allied works for Augmentation at Ajodhya w/s scheme under PMD, PHE Dte. in the District of Purulia . | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000285/2022-2023 | 76/PMD | 01/02/2023 | 60 | BISHWANATH NANDI | 5.77 | 5.66 | 100
280 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Construction of Big Dia R.B.T.W (200 mm × 165 mm) at Ajodhya Hill top of Bagmundi block in Purulia district under Purulia Mechanical Division PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000457/2023-2024 | 437/PMD | 11/03/2024 | 30 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 14.57 | 0 | 90
281 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Submersible pumping machinery with other allied work at Newly sunk T/W of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000579/2024-2025 | 1437/PMD | 01/10/2024 | 214 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 11.87 | 0 | 90
282 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Voltage stabilizer with other allied work at low lift P/H no. 3 & 4 of Augmentation of Ajodhya water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000618/2024-2025 | 1540/PMD | 11/11/2024 | 176 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 5.42 | 0 | 80
283 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Construction of Rig Bore tubewell (200mm x 165 mm) by DTH method at Ajodhya for Ajodhya PWSS under Purulia Mechanical Division, P.H.Engineering Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000680/2024-2025 | 1692/PMD | 06/12/2024 | 30 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.94 | 0 | 90
284 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | NEW CONNECTION FOR AUGMENTATION OF RANGAMATI WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00041/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 4.21 | 0 | 0
285 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New Connection for Augmentation of Rangamati water supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00248/2023-2024 | BP-23-24-203 | 17/10/2023 | 0 | WBSEDCL PURULIA | 4.21 | 0 | 0
286 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Rangamatia Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000054/2022-2023 | 395/PMD | 16/06/2022 | 30 | MS EMMESS | 20.5 | 20.49 | 100
287 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Internal external illumination with other allied works for Augmentation of Rangamati Water Supply Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000205/2023-2024 | 1195/PMD | 03/11/2023 | 60 | SANTU MITRA | 6.37 | 0 | 100
288 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Additional work for supply delivery and laying of submersible cable with jointing kit for newly constructed river bed tube well for augmentation of Rangamati water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000239/2023-2024 | 335/PMSD(W/S) | 11/09/2023 | 15 | NUPUR CHANDRA HALDER | 0.89 | 0 | 100
289 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmwter and other allied works for augmentation of Rangamati water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000442/2022-2023 | 261/PMD | 06/03/2023 | 60 | NUPUR CHANDRA HALDER | 46.44 | 0 | 72
290 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000443/2022-2023 | 262/PMD | 06/03/2023 | 60 | NUPUR CHANDRA HALDER | 8.54 | 0 | 0
291 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries into the existing CWR and in River bed Tube Well with allied cable line and other allied works for augmentation of Rangamati w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000468/2024-2025 | 1294/PMD | 30/08/2024 | 397 | M/S A.D. CONCERN | 10 | 0 | 50
292 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 100KVA voltage stabilizer for Augmentation of Rangamati water supply scheme under Purulia Mechanical Division PHE, Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000480/2022-2023 | 339/PMD | 24/03/2023 | 60 | SANTU MITRA | 10.39 | 6.08 | 100
293 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and laying of cable line at Rangamati water supply scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000553/2023-2024 | 106/PMSD(W/S) | 05/03/2024 | 7 | SANTU MITRA | 0.74 | 0 | 100
294 | Purulia Mechanical | Raghunathpur Sub-Division | New power connection at Parbeliya PWSS OHR Campus(Reference M.B.NO MB/0000210/2023-2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00870/2023-2024 | BP-23-24-300 | 05/03/2024 | 0 | WBSEDCL PURULIA | 0.11 | 0 | 0
295 | Purulia Mechanical | Raghunathpur Sub-Division | Sub: Enhancement of the contract demand from 85 KVA at 0.4 KV to 119/119/119/119/119 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o-THE EXE. ENGG, PMD, P.H.E DTE., PURULIA, SITE- PHE PERBELIA W/S under Purulia Regional Office. (1) Application No.- L000005249. (2) Consumer Id.- 932416100 | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00892/2023-2024 | BP-23-24-339 | 27/03/2024 | 0 | WBSEDCL PURULIA | 6.85 | 0 | 0
296 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of submersible pumps motor sets with other allied works for Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000032/2023-2024 | 437/PMD | 19/04/2023 | 60 | KOUSHIK CHATTERJEE | 12.04 | 0 | 100
297 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Parbeliya Water Supply scheme Block Neturia under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000040/2022-2023 | 321/PMD | 17/05/2022 | 30 | MS SAJAHAN CHOWDHURY | 20.49 | 13.97 | 100
298 | Purulia Mechanical | Raghunathpur Sub-Division | External and internal illumination of OHR site,High lift and low lift site of Parbeliya water supply scheme and Flood light at Low lift site for Augmentation work under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000044/2024-2025 | 962/PMD | 20/06/2024 | 90 | MOON LIGHT HOUSE | 8.27 | 0 | 100
299 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 50KVA oil cooled voltage stabilizer and allied works for Augmentation of Parbeliya w/s scheme (Low lift) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000079/2023-2024 | 588/PMD | 23/05/2023 | 60 | M/S A.D. CONCERN | 5.88 | 0 | 100
300 | Purulia Mechanical | Raghunathpur Sub-Division | Internal illumination of pump house room with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000132/2023-2024 | 647/PMD | 08/06/2023 | 60 | GOLAP KR. GHOSH | 1.46 | 0 | 100
301 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery & installation of Electromagnetic flow meter and with others allied works for Augmentation of Parbeliya w/s scheme (Low lift & High lift) under Purulia Mechanical Division, PHE, Dte. in the Purulia District. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000435/2022-2023 | 254/PMD | 06/03/2023 | 60 | BISHWANATH NANDI | 6.91 | 0 | 100
302 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 40 KVA voltage stabilizer for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division ,PHE Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000467/2024-2025 | 1293/PMD | 30/08/2024 | 182 | AVISHEK ENTERPRISE | 5.97 | 0 | 100
303 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery of Submersible pumping machineries for Parbeliya W/S scheme under PMD P.H.E Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000501/2023-2024 | 196/PMD | 16/02/2024 | 15 | M/S A.D. CONCERN | 0.59 | 0 | 100
304 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Dewatering submersible pump set at Parbelia w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000510/2023-2024 | 344/PMD | 28/02/2024 | 15 | M/S R.K. ENTERPRISE | 0.55 | 0 | 100
305 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of MCC Panel at Parbelia w/s scheme under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000532/2023-2024 | 354/PMD | 29/02/2024 | 300 | SUBAL SARKAR | 0.64 | 0 | 100
306 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 500 ltr UPVC tank and pipe line for eye shower for augmentation of Parbeliya High lift water supply scheme under Purulia Mechanical Division, P.H.E Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000556/2023-2024 | 195/PMD | 16/02/2024 | 10 | MS SAJAHAN CHOWDHURY | 0.37 | 0 | 100
307 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 119/119/119/119/119 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 932416100) TO THEIR PREMISES AT PARBELIYA WATER SUPPLY SARBARI NETURIA DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000423/2022-2023 | BP-22-23-86 | 28/02/2023 | 0 | WBSEDCL PURULIA | 1.98 | 0 | 0
308 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | FOR NEW SERVICE CONNECTION OF AUGMENTATION OF BUNDWAN WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00043/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 0.71 | 0 | 0
309 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER METER ROOM AT AUG OF BUNDWAN WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00099/2023-2024 | C072325293658 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.26 | 0 | 0
310 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Additional Quotation for PHE Connection at Chilla. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00501/2023-2024 | BP-23-24-270 | 22/01/2024 | 0 | WBSEDCL PURULIA | 4.02 | 0 | 0
311 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | LOAD ENHANCEMENT FOR AUG OF BUNDWAN WS SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00604/2023-2024 | BP-2023-24-201 | 17/10/2023 | 0 | WBSEDCL PURULIA | 0.71 | 0 | 0
312 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bandwan Water Supply scheme (OHR site) Block Bandwan under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2022-2023 | 394/PMD | 16/06/2022 | 1020 | S P CONSTRUCTION | 20.5 | 0 | 100
313 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of H.L. Centrifugal pump with allied motor as needed at 950 KLD water treatment plant, Bundwan under PMD,PHE, Dte, in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000061/2022-2023 | 403/PMD | 17/06/2022 | 30 | RABINDRA NATH KHAN | 9.19 | 9.19 | 100
314 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Flowmeter for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000091/2022-2023 | 526/PMD | 05/08/2022 | 911 | SUBRATA DUTTA | 8.02 | 4.67 | 100
315 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries with necessary allied works at intake for augmentation of Bandwan w/s project under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000096/2022-2023 | 522/PMD | 05/08/2022 | 1214 | TAPAN KUMAR DEY | 27.3 | 17.41 | 65
316 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries with necessary substitutes with allied works for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000097/2022-2023 | 523/PMD | 05/08/2022 | 60 | RABINDRA NATH KHAN | 88.94 | 53.46 | 65
317 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer for augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000118/2022-2023 | 537/pmd | 17/08/2022 | 60 | M/S M S ENTERPRISE | 66.56 | 40.82 | 100
318 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing internal and external illumination arrangement at existing at Intake pump house, clear water, chemical house building, substation building, OHR site Chorination room for Augmentation of Bandwan PWSS under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000119/2022-2023 | 547/PMD | 18/08/2022 | 30 | ASHOKE ADHIKARY | 8.91 | 7.26 | 90
319 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Sinking of 200mmX165mm tubewell and other allied works at Bandwan spot water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000189/2023-2024 | 1179/PMD | 03/11/2023 | 15 | SAIBAL SARKAR | 7.13 | 0 | 100
320 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and Delivery of different gaseous chlorine spare parts for Bandwan and other water supply schemes under PMD PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000343/2022-2023 | 125/PMD | 16/02/2023 | 30 | RABINDRA NATH KHAN | 10.82 | 10.82 | 100
321 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 85 KVA AT 0.4 KV TO 245/245/245/245/245 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 942408200) TO THEIR PREMISES AT BUNDWAN WATER SUPPLY DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000422/2022-2023 | BP-22-23-84 | 28/02/2023 | 0 | WBSEDCL PURULIA | 9.31 | 0 | 0
322 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Payment of WBSEDCL quotation for new power connection at Bongabari W/S Scheme (Zone-II), Mahara, under PMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00342/2024-2025 | BP-24-25-112 | 23/08/2024 | 0 | WBSEDCL PURULIA | 8.05 | 0 | 0
323 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Proposed pump house Bongabari w/s(Zone-II) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000055/2023-2024 | 524/PMD | 05/05/2023 | 60 | DEY ENTERPRISE, HOWRAH | 37.81 | 0 | 20
324 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Centrifugal pumping machinery with other allied work for direct pumping at Mahara (Zone - III) of Augmentation of Bongabari water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2024-2025 | 1017/PMD | 25/06/2024 | 463 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 49.03 | 0 | 25
325 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Internal lighting and external lighting at Proposed Pump House for Augmentation of Bongabari w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000129/2023-2024 | 867/PMD | 21/07/2023 | 60 | KANTILAL SAO | 2.84 | 0 | 0
326 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Bongabari(Zone-III) Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000386/2022-2023 | 217/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.61 | 12.91 | 0
327 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bongabari w/s scheme(River Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000410/2022-2023 | 238/PMD | 03/03/2023 | 60 | COMBINE ENTERPRISES | 77.44 | 0 | 15
328 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation 75kva voltage stabilizer for Augmentation of Bongabari w/s scheme(Zone-II) for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000429/2022-2023 | 239/PMD | 03/03/2023 | 60 | MOUSUMI BENERJEE | 8.01 | 0 | 15
329 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply & installation of submersible pumping machinery at River Bed Tubewell for Augmentation of Bongabari w/s(River site) scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000431/2022-2023 | 250/PMD | 06/03/2023 | 60 | SEN BROTHERS | 8.99 | 3.09 | 90
330 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation at Bongabari w/s scheme(Zone-II) under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000469/2022-2023 | 309/PMD | 16/03/2023 | 30 | TAPAN KUMAR DEY | 21.6 | 12.87 | 0
331 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and fitting-fixing of ST pole and laying of cable line for Illumination arrangement at Proposed pump house (Zone-II) site with other allied works under Bongabari w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000543/2023-2024 | 374/PMD | 04/03/2024 | 60 | TAPAN KUMAR DEY | 5.82 | 0 | 0
332 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and Installation of Openwell submersible pumping machinery with other allied works at Bongabari w/s scheme (Pindra) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000622/2024-2025 | 1544/PMD | 11/11/2024 | 324 | M/S A.D. CONCERN | 3.09 | 0 | 30
333 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000002/2023-2024 | 611/PMD | 01/06/2023 | 0 | Resource Division | 1.03 | 0 | 0
334 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-III), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000002/2025-2026 | 563/PMD | 07/04/2025 | 20 | SANTU MITRA | 0.94 | 0 | 0
335 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-Babugram, Zone-VI (T/W-II), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000003/2025-2026 | 562/PMD | 07/04/2025 | 20 | S. PATHAK & CO. | 0.96 | 0 | 0
336 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of earthing arrangement and other works at OHR site- Babugram (Zone-VI) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | Assistant Engineer |  | ORD/000004/2025-2026 | 561/PMD | 07/04/2025 | 20 | ANUP KUMAR SAHA | 0.96 | 0 | 0
337 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-IV), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000010/2025-2026 | 621/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.94 | 0 | 0
338 | Purulia Mechanical | Raghunathpur Sub-Division | Addition of column pipe including supply along with other works at OHR site-IA/II , Gobag (T/W no- 1,2,3 & 4 ) under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000015/2025-2026 | 633/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.75 | 0 | 0
339 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone IV B under PMD PHE Dte. District Purulia. | Assistant Engineer |  | ORD/000125/2023-2024 | 861/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 75
340 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000648/2024-2025 | 1108/PMD | 11/07/2024 | 82 | ANUP KUMAR SAHA | 0.81 | 0 | 90
341 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site -Salata (I-B) (Tube Well -IV) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000651/2024-2025 | 1257/PMD | 22/08/2024 | 40 | ANUP KUMAR SAHA | 0.81 | 0 | 95
342 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and delivery of Submersible pumping machineries at Augmentation of Ramchandrapur Water Supply Scheme, under Purulia Mechanical Division, PHE. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000050/2024-2025 | 969/PMD | 20/06/2024 | 30 | COMBINE ENTERPRISES | 1.69 | 0 | 0
343 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery, Storage, Installation and Commissioning of Chlorination Arrangement at New pump house under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000051/2024-2025 | 964/PMD | 20/06/2024 | 90 | S S ENTERPRISE | 25.29 | 0 | 80
344 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Submersible pump, MS pipe, specials including allied works in connection with direct pumping under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | Assistant Engineer | Junior Engineer-1 | ORD/000631/2024-2025 | 1549/PMD | 11/11/2024 | 60 | EASTERN INDIA SALES AND SERVICE | 2.58 | 0 | 100
345 | Purulia Mechanical | Raghunathpur Sub-Division | Providing indoor and outdoor lighting, making double tank system and other allied works at OHR site at Rangadanga under Augmentation of Ramchandrapur Water supply scheme under Purulia Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000632/2024-2025 | 1552/PMD | 11/11/2024 | 60 | SEN BROTHERS | 5.73 | 0 | 0
346 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Voltage stabilizer at New Pump house for Augmentation of Ramchandrapur water supply scheme under PMD PHE Dte. in the district of Purulia. | Assistant Engineer | Junior Engineer-1 | ORD/000633/2024-2025 | 1553/PMD | 11/11/2024 | 90 | KOUSHIK CHATTERJEE | 5.99 | 0 | 0
347 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery, Storage, Installation and Commissioning of Pre Chlorination Arrangement at WTP and High Lift site under Augmentation of Ramchandrapur water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000643/2024-2025 | 1575/PMD | 14/11/2024 | 90 | PREMNATH MITRA | 24.94 | 0 | 0
348 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation for new connection at Rangadanga OHR site under Ramchandrapur water supply scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00089/2024-2025 | BP-24-25-11 | 10/05/2024 | 0 | SANTURI CCC | 2.88 | 0 | 0
349 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation for New Connection at New Pump House at Ramchandrapur | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00112/2024-2025 | BP-24-25-14 | 24/05/2024 | 0 | SANTURI CCC | 1.29 | 0 | 0
350 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Quotation money payment for new connection near baranti Dam | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00168/2024-2025 | BP-2024-25-32 | 21/06/2024 | 0 | SANTURI CCC | 6.19 | 0 | 0
351 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Bill for Load Enhancement for Aug of Ramchandrapur W/S Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | BILL/00433/2023-2024 | BP-23-24-226 | 05/12/2023 | 0 | WBSEDCL PURULIA | 1.41 | 0 | 0
352 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Ramchandrapur Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000076/2021-2022 | 161/PMD | 07/03/2022 | 30 | MERCURY ENGINEERING COMPANY | 20.5 | 20.5 | 100
353 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and External illumination work for Augmentation Ramchandrapur Water supply scheme at Existing WTP and Intake pump house , Block: santuri , Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000099/2022-2023 | 525/PMD | 05/08/2022 | 30 | MOON LIGHT HOUSE | 9.48 | 9.13 | 55
354 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of VT pump motor , MCC Panel and other electromechanical equipment's for Raw water intake pump house at Augmentation of Ramchandrapur PWSS, Block: Santuri, Under Purulia Mechanical Division PHE Dte Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000255/2022-2023 | 46/PMD | 19/01/2023 | 803 | EASTERN INDIA SALES AND SERVICE | 65.49 | 11.04 | 100
355 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Centrifugal pump motor sets MCC, Flowmeter to supply Zone I & II OHR with allied works at New pump house of Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000305/2022-2023 | 93/PMD | 03/02/2023 | 60 | MAHADEV ENTERPRISE | 36.04 | 0 | 20
356 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of automatically controlled Chlorinator having flow rate of 100 LPH and maximum pressure of 10 kg/cm2. at Augmentation of Ramchandrapur water supply scheme OHR/pump house block Santuri, under Purulia Mechanical Division PHE, Dte. district-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000306/2022-2023 | 94/PMD | 03/02/2023 | 30 | GOLAP KR. GHOSH | 1.92 | 1.27 | 0
357 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of voltage stabilizer at WTP site and allied works for Augmentation of Ramchandrapur water supply scheme District- Purulia, under Purulia Mechanical Division PHE, Dte. Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000307/2022-2023 | 95/PMD | 03/02/2023 | 60 | MOON LIGHT HOUSE | 6.31 | 0 | 40
358 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Vertical multistage centrifugal pump motor sets , Panel , Flow meter and all electro mechanical equipments at Augmentation of Ramchandrapur water supply scheme for direct pumping Block- Santuri, under Purulia Mechanical Division PHE Dte. Dist- Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000308/2022-2023 | 96/PMD | 03/02/2023 | 788 | EASTERN INDIA SALES AND SERVICE | 51.14 | 0 | 100
359 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Centrifugal pump motor sets, MCC, with allied works at WTP site for Augmentation of Ramchandrapur water supply scheme Block: Santuri, Under Purulia Mechanical Division PHE Dte. Dist-Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000348/2022-2023 | 133/PMD | 20/02/2023 | 60 | DEBJYOTI BASU | 34.04 | 9.53 | 100
360 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing And Installation of H.O.T. Crane at newly constructed Pump House and old pump house under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000385/2023-2024 | 371/PMD | 04/03/2024 | 60 | EASTERN INDIA SALES AND SERVICE | 16.98 | 0 | 100
361 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal Illumination and Yard lighting arrangement at newly Constructed Pump House under under Augmentation of Ramchandrapur Water Supply Scheme, Block: Santuri, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000386/2023-2024 | 372/PMD | 04/03/2024 | 60 | SEN BROTHERS | 11.66 | 0 | 0
362 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-1 | ORD/000546/2023-2024 | 379/PMD | 04/03/2024 | 348 | S. PATHAK & CO. | 10.22 | 0 | 100
363 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New service connection for khariduara OHR campus for Aug of Manbazar (part-II) W/S scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00090/2023-2024 | BP-2023-2024-73 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
364 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New service connection for Kutni OHR campus for Aug of Manbazar -II (part II) W/S scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00091/2023-2024 |  | 22/06/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
365 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR HENSLA UNDER AUGMENTATION OF MANBAZAR-II (PART) WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00096/2023-2024 | BP-2023-2024-72 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
366 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR DANGORDI FOR AUG OF MANBAZAR -II(PART) WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00097/2023-2024 | BP-2023-2024-71 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
367 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | NEW SERVICE CONNECTION FOR KUTNI UNDER AUG OF MANBAZAR-II(PART) WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00098/2023-2024 | BP-2023-2024-74 | 14/07/2023 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
368 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement for high pressure testing of Sub -Station equipment for 500 KVA Sub - Station at Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE,Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2024-2025 | 971/PMD | 20/06/2024 | 30 | TAPAN KUMAR DEY | 1.19 | 0 | 100
369 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of old centrifugal pump motor sets by the new pump motor set with supply and installation of Scada compatible MCC panel at clear water pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000066/2023-2024 | 553/PMD | 16/05/2023 | 60 | RABINDRA NATH KHAN | 110.31 | 0 | 100
370 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Replacement of Rupture & multiple jointed LT Cable line from clear water pump house to Intake pump house at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2023-2024 | 554/PMD | 16/05/2023 | 60 | ANUP KR. SAHA | 42.18 | 0 | 100
371 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of existing old VCB by the new one(one incoming two outgoing) and installation of one new transformer at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2023-2024 | 555/PMD | 16/05/2023 | 60 | TAPAN KUMAR DEY | 61.95 | 0 | 95
372 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-1) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000069/2023-2024 | 556/PMD | 16/05/2023 | 60 | SWAPAN ENTERPRISE | 21.65 | 0 | 10
373 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-2) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000070/2023-2024 | 557/PMD | 16/05/2023 | 60 | NUPUR CHANDRA HALDER | 21.66 | 0 | 65
374 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-3) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000071/2023-2024 | 558/PMD | 16/05/2023 | 60 | GOENKA ENTERPRISE | 21.65 | 0 | 100
375 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system,MCC,all electro mechanical equipments at OHR( Zone-4) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2023-2024 | 559/PMD | 16/05/2023 | 60 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 21.65 | 0 | 100
376 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of existing gaseous chlorination system at Manbazar-2(Part) w/s Scheme under Purulia mechanical Division, PHE, Dte. in the purulia district. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000073/2023-2024 | 561/PMD | 16/05/2023 | 60 | ASHOKE ADHIKARY | 15.5 | 0 | 100
377 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of gaseous chlorination system, MCC, all electro mechanical equipment's at OHR( Zone-5) at Manbazar-II(part) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000074/2023-2024 | 560/PMD | 16/05/2023 | 60 | H K DAS AND CO | 21.65 | 0 | 100
378 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Rectification of internal & external lighting arrangement at conference hall & allied premises of awareness generation cum water sample collection centre at Mouza-ghat Block - Manbazar-2 under Purulia Mechanical Division under PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000077/2023-2024 | 581/PMD | 19/05/2023 | 30 | PREMNATH MITRA | 11.92 | 0 | 70
379 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Installation of One no submersible pumping machinery at intake pump house with supply and installation of Scada compatible MCC panel at Manbazar-II (part) w/s scheme under PMD, PHE, Dte. in the district of purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000078/2023-2024 | 582/PMD | 19/05/2023 | 60 | TAPAN KUMAR DEY | 26.38 | 0 | 60
380 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Manbazar Water Supply scheme Block Manbazar-I under PMD PHE Dte. District Purulia. (2nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000218/2023-2024 | 1203/PMD | 03/11/2023 | 90 | PRINCE INDUSTRIES (INDIA) | 21.5 | 0 | 0
381 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing and Installation of Electro-Mechanical Equipment¿s at Intake, Clear water Pump House and 5 nos. OHRs in Manbazar-II (Part) water supply scheme under Purulia Mechanical Division, PHE, Dte., District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000637/2024-2025 | 1569/PMD | 14/11/2024 | 90 | EASTERN INDIA SALES AND SERVICE | 80.69 | 0 | 0
382 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Making fencing boundry at Transformer Yard of Manbazar - II Water Supply Scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000690/2024-2025 | 1702/PMD | 06/12/2024 | 360 | TAPAN KUMAR DEY | 1.53 | 0 | 100
383 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new service connection at Zone-VI OHR(Babugram) site under Raghunathpur Aug. water supply scheme. | Assistant Engineer |  | BILL/00288/2024-2025 | BP-24-25-75 | 02/08/2024 | 0 | WBSEDCL PURULIA | 6.21 | 0 | 0
384 | Purulia Mechanical | Raghunathpur Sub-Division | Addition of column pipe including supply along with allied works at OHR site-VII B, Ketlapur under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000014/2025-2026 | 634/PMD | 24/04/2025 | 15 | ANUP KUMAR SAHA | 0.49 | 0 | 0
385 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone VI B under PMD PHE Dte. District Purulia. | Assistant Engineer |  | ORD/000122/2023-2024 | 803/PMD | 12/07/2023 | 30 | MERCURY ENGINEERING COMPANY | 21.6 | 0 | 0
386 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & Installation of Submersible Pumping Machinery along with allied works, at OHR site- Babugram, Zone-VI (T/W-I), under Raghunathpur water supply project, PHE Dte. | Assistant Engineer |  | ORD/000965/2024-2025 | 517/PMD | 28/03/2025 | 20 | SUJIT MUKHERJEE | 0.99 | 0 | 0
387 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for Augmentation of River site of Lagda W/S, block- Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00863/2023-2024 | BP-23-24-298 | 05/03/2024 | 0 | WBSEDCL PURULIA | 7.63 | 0 | 0
388 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for Augmentation OHR site of Lagda W/S | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00866/2023-2024 | BP-23-24-301 | 05/03/2024 | 0 | WBSEDCL PURULIA | 7.04 | 0 | 0
389 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Lagda Water Supply scheme Block Purulia-I under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000079/2021-2022 | 164/PMD | 07/03/2022 | 30 | ASHUTOSH DAS AND CO. | 20.5 | 8.8 | 90
390 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Providing internal and external illumination arrangement at existing at OHR site of Lagda W/S under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000154/2023-2024 | 650/PMD | 08/06/2023 | 60 | TUSHAR GHOSH | 6.13 | 0 | 90
391 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and lowering of submersible pump motor sets at at newly constructed River Bed Tube well with supply of necessary substitutes at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000345/2022-2023 | 130/PMD | 20/02/2023 | 1046 | SANTANU BANERJEE | 26.09 | 6.24 | 40
392 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of centrifugal pumping machineries, Flowmeter with necessary substitutes and allied electrical panel at Lagda w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000346/2022-2023 | 131/PMD | 20/02/2023 | 701 | PROGRESIVE ENGINEERS CO-OPERATIVE SOCITY LTD. | 69.89 | 20.5 | 70
393 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of voltage stabilizer at OHR site of Lagda W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000368/2022-2023 | 210/PMD | 28/02/2023 | 672 | TUSHAR GHOSH | 7.07 | 0 | 90
394 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Submersible Pump motor and other related works for Augmentation work of Lagda w/s scheme (OHR Site) under Purulia Mechanical Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000387/2023-2024 | 373/PMD | 04/03/2024 | 515 | GOUTAM CHAKRABORTY | 4.73 | 0 | 50
395 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of voltage stabilizer at Augmentation of Lagda W/S under PMD PHE dte in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000468/2022-2023 | 308/PMD | 16/03/2023 | 30 | GOUTAM CHAKRABORTY | 11.85 | 8.05 | 70
396 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000001/2023-2024 | 610/PMD | 01/06/2023 | 0 | Resource Division | 0.86 | 0 | 0
397 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 125 KVA AT 0.4 KV TO 281/281/281/281/281 KVA RESPECTIVELY AT 11 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o EX ENGG PMD PHE DTE. (CONSUMER ID : 942406300) TO THEIR PREMISES AT KOTSHILA WATER SUPPLY SCHEME (AUGMENTATION) | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00044/2022-2023 |  | 28/02/2023 | 0 | WBSEDCL PURULIA | 10.37 | 0 | 0
398 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Bill for earnest money for the proposed Enhancement of the load at your premises at Kotshila W/S Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00434/2023-2024 | BP-23-24-219 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0
399 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | SHIFTING OF ENERGY METER FROM EXISTING METER ROOM TO ANOTHER ROOM AT KOTHSILA WS SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00508/2023-2024 | BP-23-24-269 | 22/01/2024 | 0 | WBSEDCL PURULIA | 0.28 | 0 | 0
400 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Enhancement of the contract demand from 125KVA at 0.4 KV to 281/281//281//281//281 KVA respectively at 11 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kotshila Water Supply, (Consumer ID -942406300) | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00860/2023-2024 | BP-24-25-1 | 19/04/2024 | 0 | WBSEDCL PURULIA | 10.24 | 0 | 0
401 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and delivery of essential Electromechanical items for Augmentation of Kotshila w/s Scheme in PMD store under Purulia Mechanical Division PHE, Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000188/2023-2024 | 1178/PMD | 03/11/2023 | 60 | SAIBAL SARKAR | 5.15 | 0 | 100
402 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KOTSHILA w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000253/2022-2023 | 43/PMD | 19/01/2023 | 60 | TAPAN KUMAR DEY | 78.43 | 17.89 | 65
403 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of 400KVA 11/.433 KV substation with 11 KV 800A VCB Panel with others allied works for Augmentation of Kotshila w/s scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000269/2022-2023 | 42/PMD | 19/01/2023 | 60 | CHAKRABORTY ENTERPRISE | 48.1 | 0 | 60
404 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation 12kg/cm2 chlorine machine with others works for Augmentation of Kotshila w/s scheme under Purulia Mechanical Division, PHE, Dte. in purulia district. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000296/2022-2023 | 77/PMD | 01/02/2023 | 30 | R K ENTERPRISES | 3.6 | 0 | 91
405 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation submersible pumping machineries & 3 core 10 Sq. mm Al Ar. cable line , with others allied works for Augmentation of Kotshila W/S scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000490/2022-2023 | 154/PMD | 24/02/2023 | 60 | M/S S.G.ENTERPRISE | 31.8 | 17.85 | 75
406 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | DEPOSITION OF THE EARNEST MONEY FOR THE PORPOSED ENHANCEMENT OF THE LOAD AT KOTHSILA WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000326/2022-2023 | 780/PMD | 23/11/2022 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0
407 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Baram(River Side) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2023-2024 | 522/PMD | 05/05/2023 | 607 | P K ENGINEERING | 39.21 | 0 | 100
408 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baram Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2021-2022 | 112/PMD | 28/02/2022 | 30 | A G ENTERPRISE | 20.48 | 20.17 | 99
409 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of submersible pumping machineries in newly constructed river bed tube well with allied cable line and other allied works for augmentation of Baram(River Side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000408/2022-2023 | 236/PMD | 03/03/2023 | 60 | SUMIT KR. CHAKRABORTY | 11.33 | 0 | 20
410 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 100 KVA voltage stabilizer for Augmentation of Baram(River Side) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000409/2022-2023 | 237/PMD | 03/03/2023 | 60 | S. PATHAK & CO. | 10.86 | 6.3 | 65
411 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of 1 kg/hr gaseous chlorination system at Baram High lift for augmentation of Baram Water supply scheme under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000459/2023-2024 | 439/PMD | 11/03/2024 | 60 | PINTU DEY | 25.09 | 0 | 50
412 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER | RTOR000011/2023-2024 | 619/PMD | 01/06/2023 | 0 | Resource Division | 1.55 | 0 | 0
413 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Raghunathpur Pipe Water Supply scheme for Zone-VIII under Purulia Mechanical Division PHE. Dte. District Purulia | Assistant Engineer |  | ORD/000387/2022-2023 | 218/PMD | 28/02/2023 | 30 | JAL PRAVAHIKA PVT. LTD | 21.57 | 0 | 100
414 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New Connection for Augmentation of Santuri | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | BILL/00252/2023-2024 | BP-2023-24-148 | 14/09/2023 | 0 | WBSEDCL PURULIA | 4.95 | 0 | 0
415 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Santuri Water Supply scheme Block Santuri under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000041/2023-2024 | 447/PMD | 20/04/2023 | 30 | DAS ENTERPRISE | 21.57 | 0 | 25
416 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Submersible pumping machineries ,Al. Armoured cables and laying of Al. armoured cables for Augmentation of Santuri W/S scheme under PMD Dte .in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000068/2024-2025 | 996/PMD | 21/06/2024 | 60 | SEN BROTHERS | 4.25 | 0 | 70
417 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of Centrifugal pumping machineries, MCC panel with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000457/2022-2023 | 297/PMD | 16/03/2023 | 60 | GOENKA ENTERPRISE | 33.83 | 0 | 20
418 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of 30KVA oil cooled voltage stabilizer and allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000458/2022-2023 | 298/PMD | 16/03/2023 | 60 | BISHWANATH NANDI | 4.13 | 3.13 | 80
419 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Yard lighting arrangement with others allied works for Augmentation of Santuri w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-2 | ORD/000459/2022-2023 | 299/PMD | 16/03/2023 | 60 | S. PATHAK & CO. | 5.02 | 0 | 20
420 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New connection for Hutmura high lift Water supply scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00822/2023-2024 | BP-23-24-282 | 16/02/2024 | 0 | WBSEDCL PURULIA | 7.07 | 0 | 0
421 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Hutmura(OHR site) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000024/2023-2024 | 395/PMD | 06/04/2023 | 60 | MOON LIGHT HOUSE | 7.36 | 0 | 100
422 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Internal and external illumination with other allied works for augmentation of Hutmura W/S scheme(both intake & OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000056/2023-2024 | 525/PMD | 05/05/2023 | 60 | ASISH KR. SEN | 5.12 | 0 | 100
423 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, delivery and installation of Open well Submersuble pumping machinery for direct pumping with others electro-mechanical work at Hutmura W/S (OHR Site) under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000064/2024-2025 | 993/PMD | 21/06/2024 | 406 | SUBRATA DUTTA | 15.59 | 0 | 55
424 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Hutmura Water Supply scheme Block Purulia-II under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000065/2022-2023 | 397/PMD | 16/06/2022 | 30 | SUBRATA DUTTA | 20.51 | 20.45 | 100
425 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Repairing, overhauling thorough repairing of floating walkway with required MS work by necessary supply of materials and other allied works at Hutmura (Low Lift) w/s scheme under PMD PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000168/2021-2022 | 78/PMSD (W/S) | 08/03/2022 | 7 | SUBRATA DUTTA | 4.6 | 3.6 | 80
426 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Augmentation of floating walkway lowering and anchoring of existing repaired floating barge with required ms work by necessary supply of materials and other allied works at Hutmura(Low Lift) W/S scheme under PMD PHE Dte in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000342/2022-2023 | 124/PMD | 15/02/2023 | 60 | ASHOKE ADHIKARY | 7.85 | 0 | 0
427 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries with flexible hose pipe, MCC panel, flowmeter with other allied works for augmentation of Hutmura(Intake side) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000422/2022-2023 | 240/PMD | 03/03/2023 | 60 | KHITISH CH. PATHAK | 18.86 | 0 | 100
428 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of centrifugal pumping machineries, MCC panel, flowmeter and other allied works at Hutmura(OHR site) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000423/2022-2023 | 241/PMD | 03/03/2023 | 60 | SUBRATA DUTTA | 50.17 | 14.51 | 100
429 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, fixing of PVC pipe,cable,valve etc and other allied works at Hutmura (low lift) Site water supply scheme under Purulia Mechanical Division, PHE, Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000502/2024-2025 | 1305/PMD | 03/09/2024 | 20 | KHITISH CH. PATHAK | 3.39 | 0 | 100
430 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Continuation Work Order for "Hiring of One no. inspection vehicle for Office of the Driller-In-Charge, PMSD (Drilling) under Purulia Mechanical Division P.H.E Dte." (W.e.f- 01.05.2024 to 31.10.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000523/2023-2024 | 49/PMSD(Drilling) | 12/03/2024 | 184 | NUPUR CHANDRA HALDER | 0.9 | 0 | 100
431 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 50 KVA voltage stabilizer for Augmentation of Hutmura(low lift site) water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000590/2024-2025 | 1448/PMD | 01/10/2024 | 90 | ASHOKE ADHIKARY | 7.37 | 0 | 0
432 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at Hutmura water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000683/2024-2025 | 1695/PMD | 06/12/2024 | 90 | SUBRATA DUTTA | 9.99 | 0 | 0
433 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Enhancement of contract demand load for Augmentation of Hutmura Water Supply Scheme | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000429/2022-2023 |  | 03/11/2022 | 0 | WBSEDCL PURULIA | 3.08 | 0 | 0
434 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 2 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000041/2022-2023 | 322/PMD | 17/05/2022 | 30 | AHALYA ENGINEERING WORKS | 20.57 | 20.56 | 98
435 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 3 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000042/2022-2023 | 323/PMD | 17/05/2022 | 30 | S.P. ENTERPRISE | 20.48 | 0 | 100
436 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme (OHR no 4 site) Block Hura under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000043/2022-2023 | 324/PMD | 17/05/2022 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGY PVT LTD. | 20.51 | 19.02 | 100
437 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kalabani Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000066/2021-2022 | 111/PMD | 28/02/2022 | 1038 | ORIENTAL ENGINEERING CO. | 20.43 | 13.93 | 100
438 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of submersible pump-motor set instead of existing submersible pump-motor set at Kalabani w/s scheme under Purulia Mechanical Division , PHE, Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000080/2023-2024 | 592/PMD | 24/05/2023 | 30 | SUBRATA DUTTA | 9.05 | 0 | 100
439 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Tialabani OHR site (Zone-IV) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000112/2023-2024 | 640/PMD | 08/06/2023 | 30 | MOON LIGHT HOUSE | 2.5 | 0 | 100
440 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Kalabani OHR site (Zone-I) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000113/2023-2024 | 641/PMD | 08/06/2023 | 30 | MD. ASLAM | 2.56 | 0 | 100
441 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Deshra OHR site (Zone-III) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000114/2023-2024 | 642/PMD | 08/06/2023 | 30 | MD. ASLAM | 2.45 | 0 | 100
442 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery and installation of lighting arrangement at Ladhurka OHR site (Zone-II) with other allied works under Kalabani w/s scheme under Purulia Mechanical Division, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000115/2023-2024 | 643/PMD | 08/06/2023 | 30 | KOUSHIK CHATTERJEE | 2.46 | 0 | 100
443 | Purulia Mechanical | Raghunathpur Sub-Division | Sinking of 200mmX165mm tubewell and other allied works for Kalabani water supply scheme Purulia,under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | ORD/000215/2023-2024 | 1201/PMD | 03/11/2023 | 15 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 7.12 | 0 | 100
444 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION FOR KALABANI WATER SUPPLY SCHEME | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000321/2022-2023 | BP-22-23-34 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0
445 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION AT PHE LADHURKA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000322/2022-2023 | BP-2022-23-35 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0
446 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION FOR DESHRA OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000323/2022-2023 | BP-2022-23-36 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.29 | 0 | 0
447 | Purulia Mechanical | Raghunathpur Sub-Division | NEW SERVICE CONNECTION FOR TILABANI OHR SITE UNDER KALABANI WATER SUPPLY SCHEME UNDER PMD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-4 | VCH/000324/2022-2023 | BP-2022-23-37 | 08/09/2022 | 0 | WBSEDCL PURULIA | 0.48 | 0 | 0
448 | Purulia Mechanical | Raghunathpur Sub-Division | Enhancement of the contract demand from 60 KVA at 0.4 KV to 105/105//105/105/105 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Kashipur Water Supply, (Consumer ID -950023805) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00893/2023-2024 | BP-23-24-311 | 21/03/2024 | 0 | WBSEDCL KASHIPUR CCC | 4.47 | 0 | 0
449 | Purulia Mechanical | Raghunathpur Sub-Division | Cable laying from river bed site to pump house at kashipur water supply scheme of augumentation and other allied works under PMD, PHE Dte in the district of purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000045/2024-2025 | 963/PMD | 20/06/2024 | 30 | PINTU DEY | 1.71 | 0 | 100
450 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Kashipur Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000087/2022-2023 | 430/PMD | 23/06/2022 | 30 | PREMNATH MITRA | 20.49 | 13.97 | 100
451 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for augmentation of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000093/2022-2023 | 519/PMD | 05/08/2022 | 30 | DEY ENTERPRISE, HOWRAH | 10.24 | 10.23 | 80
452 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of submersible pumping machinery at River Bed Tubewell and changing cable line, clamping and other allied works at Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000242/2024-2025 | 1230/PMD | 13/08/2024 | 20 | PINTU DEY | 1.62 | 0 | 100
453 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000251/2022-2023 | 40/PMD | 19/01/2023 | 60 | PINTU DEY | 7.98 | 4.15 | 0
454 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and fitting of 3 Ton capacity triple spur gear type chain pulley Block Mono rail with others allied works for Augmentation at KASHIPUR w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000252/2022-2023 | 41/PMD | 19/01/2023 | 60 | RABINDRA NATH KHAN | 9.64 | 9.64 | 0
455 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Centrifugal pumping machineries, MCC Panel with others allied works for Augmentation of KASHIPUR Water supply Scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000267/2022-2023 | 39/PMD | 19/01/2023 | 60 | WEST BENGAL ENGINEERING CO | 67.56 | 0 | 43
456 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of 125 KVA voltage stabilizer for Augmentation of KASHIPUR water supply scheme under PMD PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000284/2022-2023 | 75/PMD | 01/02/2023 | 60 | PINTU DEY | 11.26 | 7.88 | 100
457 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery & installation of flow meter and with others allied works for Augmentation at KASHIPUR w/s scheme under Purulia Mechanical Division, PHE, Dte. in the Purulia District. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000341/2022-2023 | 123/PMD | 15/02/2023 | 60 | SANTU MITRA | 3.92 | 0 | 30
458 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation of 4 nos. submersible pumps motor sets with other allied works for Augmentation work of Kashipur w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000624/2024-2025 | 1546/PMD | 11/11/2024 | 460 | PINTU DEY | 12.16 | 0 | 45
459 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of PLC panel, Level transmitter, Solar light(OHR Site) with other allied work at Kashipur water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000684/2024-2025 | 1696/PMD | 06/12/2024 | 360 | PINTU DEY | 13.57 | 0 | 100
460 | Purulia Mechanical | Raghunathpur Sub-Division | ENHANCEMENT OF CONTRACTUAL DEMAND FROM 60 KVA AT 0.4 KV TO 105/105/105/105/105 KVA RESPECTIVELY AT 0.4 KV FOR NEXT CONSECUTIVE FIVE YEARS PERIOD OF OPERATION i.r.o , EX ENGG PMD PHE DTE(CONSUMER ID : 950023805) TO THEIR PREMISES AT KASHIPUR WATER SUPPLY KASHIPUR DIST PURULIA UNDER REGIONAL OFFICE PURULIA | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | VCH/000424/2022-2023 | BP-22-23-87 | 28/02/2023 | 0 | WBSEDCL PURULIA | 3.71 | 0 | 0
461 | Purulia Mechanical | Raghunathpur Sub-Division | Enhancement of contractual demand from 90 KVA at 0.4 KV to their premises at PALASHKHOLA WATER SUPPLY, Dist- Purulia under Regional Office Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00113/2023-2024 |  | 20/07/2023 | 0 | WBSEDCL PURULIA | 6.55 | 0 | 0
462 | Purulia Mechanical | Raghunathpur Sub-Division | Enhancement of the contract demand from 90 KVA at 0.4 KV to 180/180/180/180/180 KVA respectively at 0.4 KV for next consecutive five years period of operation i.r.o to Executive Engineer, Site- PHE Palashkhola Water Supply, (Consumer ID -942406300) | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | BILL/00862/2023-2024 | BP-23-24-340 | 21/03/2024 | 0 | WBSEDCL PURULIA | 16.57 | 0 | 0
463 | Purulia Mechanical | Raghunathpur Sub-Division | Rectification of Internal lighting and external lighting for Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000049/2023-2024 | 518/PMD | 05/05/2023 | 60 | RAKSHIT ENTERPRISE | 9.24 | 0 | 100
464 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, Delivery and installation 200 kva voltage stabilizer for Augmentation of Palashkhola Keliyathol w/s scheme for under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000050/2023-2024 | 519/PMD | 05/05/2023 | 60 | ALPHA ENTERPRISES | 26.97 | 0 | 100
465 | Purulia Mechanical | Raghunathpur Sub-Division | Supply & installation of Horizontal Multistage Centrifugal pumping machinery with other allied works for Augmentation at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000118/2023-2024 | 646/PMD | 08/06/2023 | 662 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 77.49 | 0 | 100
466 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Palashkhola Keliyathol Water Supply scheme Block Kashipur under Purulia Mechanical Division PHE. Dte. District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000385/2022-2023 | 216/PMD | 28/02/2023 | 30 | COMBINE ENTERPRISES | 21.61 | 12.91 | 100
467 | Purulia Mechanical | Raghunathpur Sub-Division | Supply & installation of submersible pumping machinery at River Bed Tubewell at Palashkhola Keliyathol w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER je1_drill_pur_mesdd@wbphed.gov.in,Junior Engineer-3 | ORD/000448/2022-2023 | 267/PMD | 06/03/2023 | 60 | SAIBAL SARKAR | 47.89 | 13.06 | 50
468 | Purulia Mechanical | Purulia Sadar Sub-Division | Hiring of maxi cab (non air conditioned) Bharat Stage-III Diesel/LPG/CNG driver engine including driver for official use of the Assistant Engineer, Purulia Mechanical Sub-Division (W/S) PHE, Dte. (01/10/24 to 31/03/25) | Assistant Engineer |  | ORD/000614/2024-2025 | 399/PMSD(W/S) | 23/09/2024 | 182 | PINTU DEY | 0.86 | 0 | 0
469 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of electro mechanical equipments submersible pump motor sets of Raw water pump house , centrifugal pump motor sets for Clear water pump house at Marble Lake piped water supply scheme , Block : Baghmundi under Purulia Mechanical Division PHE Dte. Dist : Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000173/2021-2022 | 471/PMD | 28/07/2021 | 150 | COMBINE ENTERPRISES | 43.7 | 5.09 | 100
470 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Voltage stabilizer ,valves, external illumination arrangement with allied works at Marble lake PWSS Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000467/2022-2023 | 307/PMD | 16/03/2023 | 30 | COMBINE ENTERPRISES | 13.17 | 0 | 60
471 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement of Pandel & other Miscellaneous works for infield training at Pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000567/2023-2024 | 23/PMSD(Drilling) | 16/02/2024 | 15 | AMIT PATHAK | 0.54 | 0 | 100
472 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Arrangement of refreshment for infield training of pump operator & valve operator of different water supply scheme under Purulia Mechanical Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000568/2023-2024 | 24/PMSD(Drilling) | 16/02/2024 | 15 | AMIT PATHAK | 0.43 | 0 | 100
473 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of PLC panel, Level transmitter with other allied work at Marble Lake water supply scheme under Purulia Mechanical Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000645/2024-2025 | 1577/PMD | 14/11/2024 | 90 | SUBRATA DUTTA | 14.57 | 0 | 0
474 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY AND INSTALLATION OF ELECTRO MECHANICAL EQUIPMENTS SUBMERSIBLE PUMP MOTOR SETS FOR RAW WATER PUMP HOUSE , CENTRIFUGAL PUMP MOTOR SETS FOR CLEAR WATER PUMP HOUSE AT MARBLE LAKE PIPED WATER SUPPLY SCHEME (TR.NO 179 OF 21-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000562/2021-2022 | C022228319640 | 09/02/2022 | 0 | COMBINE ENTERPRISE | 37.42 | 0 | 0
475 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Beldi Water Supply scheme Block Arsha under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000080/2021-2022 | 165/PMD | 07/03/2022 | 30 | DEBJYOTI BASU | 20.5 | 20.19 | 100
476 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, voltage stabilizer, Flowmeter with necessary substitutes and allied works at BELDI w/s scheme under PMD, PHE Dte. in the District of Purulia.. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000371/2022-2023 | 201/PMD | 28/02/2023 | 60 | TAPAN KUMAR DEY | 34.55 | 13.19 | 60
477 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Rectification of different feeders of Beldi W/S scheme(Low lift) for Augmentation of Beldi W/S Scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000441/2023-2024 | 421/PMD | 11/03/2024 | 30 | TAPAN KUMAR DEY | 5.21 | 0 | 30
478 | Purulia Mechanical | Raghunathpur Sub-Division | WBSEDCL for Sohardi Mouza, Babugram, P.O-Sanka, Raghunathpur Water Supply Scheme | Assistant Engineer |  | BILL/00146/2024-2025 | BP-24-25-28 | 11/06/2024 | 0 | WBSEDCL PURULIA | 2.32 | 0 | 0
479 | Purulia Mechanical | Raghunathpur Sub-Division | Modification of existing filter bed control system with allied works at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000005/2025-2026 | 568/PMD | 07/04/2025 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 101.61 | 0 | 0
480 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Chemical house panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | Assistant Engineer |  | ORD/000035/2024-2025 | 948/PMD | 19/06/2024 | 90 | M/S UJJAL DIESEL SERVICE | 5.66 | 0 | 100
481 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Filter house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE DTE. | Assistant Engineer |  | ORD/000036/2024-2025 | 949/PMD | 19/06/2024 | 90 | MOUSUMI BENERJEE | 10.45 | 0 | 100
482 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of existing old Recirculation Sump Pump motor set at Lakshmanpur WTP of Raghunathpur W/S project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000037/2024-2025 | 950/PMD | 19/06/2024 | 90 | SAIBAL SARKAR | 22.94 | 0 | 0
483 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of existing one number old VT pump with new one at intake of Lakshmanpur WTP of Raghunathpur W/S Project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000038/2024-2025 | 951/PMD | 19/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 20.75 | 0 | 0
484 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of internal and External illuminations arrangements at existing Pump house-2 nos, PDB room Transformer room-2 nos , DG room, VCB room-2nos, AVR room, chlorine room, filter house(first floor and ground floor), chemical house (first floor and ground floor), Administrative building and Nine nos of OHR with supply luminaires and under Raghunathpur water supply project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000039/2024-2025 | 952/PMD | 19/06/2024 | 227 | SUBRATA DUTTA | 28.81 | 0 | 100
485 | Purulia Mechanical | Raghunathpur Sub-Division | Defixing the existing idle unit and supply delivery and installation of Electro-Magnetic Flow Meter with cable and remote display unit at different site of WTP. Intake OHR inlet and Outlet pipeline at Forest premises at Garpanchakot, WBSEDCL office premises under Raghunathpur water supply project under PMD. PHE. Dte. | Assistant Engineer |  | ORD/000040/2024-2025 | 953/PMD | 19/06/2024 | 408 | EASTERN INDIA SALES AND SERVICE | 83.58 | 0 | 65
486 | Purulia Mechanical | Raghunathpur Sub-Division | Supply of Safety items of Gaseous Chlorination system at Lakshmanpur WTP and OHR no 5 ,6 ,7 under Raghunathpur W/S project under PMD, PHE, Dte | Assistant Engineer |  | ORD/000042/2024-2025 | 955/PMD | 19/06/2024 | 90 | TUSHAR GHOSH | 9.75 | 0 | 100
487 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Raw water Intke pump house panel at Lakshmanpur WTP under Raghunathpur water supply project under PMD PHE DTE . | Assistant Engineer |  | ORD/000077/2024-2025 | 998/PMD | 21/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 26.2 | 0 | 0
488 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing of Clear water pump house Panel at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD PHE Dte. | Assistant Engineer |  | ORD/000078/2024-2025 | 999/PMD | 21/06/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 57.19 | 0 | 0
489 | Purulia Mechanical | Raghunathpur Sub-Division | Repairing and rectification of Gaseous Chlorination system at OHR no. 5,6 & 7 of Raghunathpur Water Supply Project under P.M.D., P.H.E. Dte. | Assistant Engineer |  | ORD/000210/2023-2024 | 1182/PMD | 03/11/2023 | 15 | EASTERN INDIA SALES AND SERVICE | 15.26 | 0 | 100
490 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-1 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000223/2023-2024 | 1253/PMD | 17/11/2023 | 90 | TAPAN KUMAR DEY | 21.67 | 0 | 100
491 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-2 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000224/2023-2024 | 1254/PMD | 17/11/2023 | 90 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 21.66 | 0 | 100
492 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-3 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000225/2023-2024 | 1255/PMD | 17/11/2023 | 90 | SAIBAL SARKAR | 21.67 | 0 | 70
493 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of Gaseous Chlorination System, MCC, all electro mechanical equipments at OHR No.-4 under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE Dte. Dist.- Purulia. | Assistant Engineer |  | ORD/000226/2023-2024 | 1256/PMD | 17/11/2023 | 90 | RABINDRA NATH KHAN | 21.67 | 0 | 50
494 | Purulia Mechanical | Raghunathpur Sub-Division | Street light illumination arrangement at Lakshmanpur WTP East side of Recirculation System under Raghunathpur Water Supply Project underPurulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000238/2024-2025 | 1227/PMD | 13/08/2024 | 20 | M/S R.K. ENTERPRISE | 0.98 | 0 | 100
495 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of 14 Ring Current Collector at Lakshmanpur WTP Clariflocculator under Raghunathpur water supply project under Purulia Mechanical Division , P.H.E. Dte. | Assistant Engineer |  | ORD/000440/2023-2024 | 420/PMD | 11/03/2024 | 296 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 1.48 | 0 | 100
496 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & fitting of Fire Extinguisher with refilling of Fire Extinguisher at different sections of Raghunathpur Water Supply Project under Purulia Mechanical Division PHE, Dte. | Assistant Engineer |  | ORD/000454/2023-2024 | 434/PMD | 11/03/2024 | 30 | M/S R.K. ENTERPRISE | 2.16 | 0 | 10
497 | Purulia Mechanical | Raghunathpur Sub-Division | Street light illumination arrangement at Lakshmanpur WTP West Side of Recirculation System under Raghunathpur Water Supply Project under Purulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000583/2024-2025 | 1441/PMD | 01/10/2024 | 30 | MD. ASLAM | 0.99 | 0 | 0
498 | Purulia Mechanical | Raghunathpur Sub-Division | Street light illumination arrangement at Lakshmanpur WTP MiddleSide of Recirculation System under Raghunathpur Water Supply Project underPurulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000623/2024-2025 | 1545/PMD | 11/11/2024 | 60 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 1 | 0 | 0
499 | Purulia Mechanical | Raghunathpur Sub-Division | Supply & fixing of display board for depicting details of Pump and others at Pump House/Other location of Raghunathpur and other blocks in the Dist-Purulia under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000657/2024-2025 | 1260/PMD | 22/08/2024 | 131 | SUJIT MUKHERJEE | 0.85 | 0 | 100
500 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery, laying and connection of cable for high lift pump house power connection and other works under Raghunathpur water supply project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000688/2024-2025 | 1700/PMD | 06/12/2024 | 90 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 68.36 | 0 | 100
501 | Purulia Mechanical | Raghunathpur Sub-Division | Additional work related to Defixing the existing old unit and installation of new Electro Magnetic Flow meter with cable and remote display unit at different site under Raghunathpur w/s project under PMD, PHE Dte. | Assistant Engineer |  | ORD/000969/2024-2025 | 529/PMD | 28/03/2025 | 60 | EASTERN INDIA SALES AND SERVICE | 5.48 | 0 | 0
502 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | New Connection for Augmentation of Barabazar W/S Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00244/2023-2024 | BP-23-24-154 | 14/09/2023 | 0 | WBSEDCL PURULIA | 3.74 | 0 | 0
503 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Construction of Rigbored Tubewell (200mm x 165mm) by DTH method for Barabazar and other Schemes under Purulia Mechanical Division PHE.Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000010/2021-2022 | 19/PMD | 19/01/2022 | 30 | RABINDRA NATH KHAN | 13.59 | 2.57 | 79
504 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of headwork site centrifugal pumping machineries, floor mounted MCC panel, Flowmeter and other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000052/2023-2024 | 521/PMD | 05/05/2023 | 60 | GOENKA ENTERPRISE | 36.99 | 0 | 100
505 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Barabazar Water Supply scheme Block Barabazar under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000063/2021-2022 | 108/PMD | 28/02/2022 | 30 | M/S M S ENTERPRISE | 20.48 | 20.24 | 100
506 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and Installation & Commissioning of Chlorination Arrangement at Barabazar OHR for Augmentation of Barabazar water supply scheme under Purulia Mechanical Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 1090/PMD | 08/07/2024 | 60 | MOUSUMI BENERJEE | 10.14 | 0 | 70
507 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of Submersible pumping machinery with all ancillaries & auxiliaries works for Augmentation of Barabazar Water Supply Scheme under PMD PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000189/2022-2023 | 766/PMD | 14/11/2022 | 7 | MOUSUMI BENERJEE | 3.24 | 2.91 | 90
508 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Internal and external illumination with other allied works for augmentation of Barabazar water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000405/2022-2023 | 233/PMD | 03/03/2023 | 795 | AVISHEK ENTERPRISE | 4.86 | 0 | 100
509 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply, Delivery and installation of submersible pumping machineries in newly constructed tube well with allied cable line and other allied works for augmentation of Barabazar w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000406/2022-2023 | 234/PMD | 03/03/2023 | 700 | MOUSUMI BENERJEE | 9.65 | 0 | 70
510 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply delivery and installation of 75 KVA voltage stabilizer for Augmentation of Barabazar water supply scheme under PMD PHE Dte. In the district of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000407/2022-2023 | 235/PMD | 03/03/2023 | 60 | MOUSUMI BENERJEE | 7.6 | 0 | 35
511 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | External illumination of OHR site barabazar water supply scheme for Augmentation work under Purulia Mechanical Division, P.H.E. Dte. In district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000439/2023-2024 | 419/PMD | 11/03/2024 | 570 | BISHWANATH NANDI | 7.55 | 0 | 100
512 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and laying of 1.1 KV grade 3.5 core 95 sq. mm XLPE insulated Al. armoured cable for Augmentation at Barabazar W/S Scheme under PMD, PHE Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000537/2023-2024 | 499/PMSD(W/S) | 21/12/2023 | 15 | MOUSUMI BENERJEE | 0.62 | 0 | 100
513 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply and fitting fixing of loop box for outdoor lighting for Augmentation at Barabazar Water Supply Scheme under PMD, PHE Dte.in the district of Purulia. (2ND Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000588/2024-2025 | 349/PMSD(W/S) | 04/09/2024 | 10 | AVISHEK ENTERPRISE | 0.17 | 0 | 100
514 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | Supply,delivery and Installation of Level Transmitter ,Submersible pumping machineries and other allied works for Augmentation of Barabazar W/S scheme under PMD Dte .in the District Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000681/2024-2025 | 1693/PMD | 06/12/2024 | 111 | MOUSUMI BENERJEE | 7.51 | 0 | 50
515 | Purulia Mechanical | Purulia Mechanical Sub-Division (Drilling) | CONSTRUCTION OF RIG BORE TUBE WELL (200 x165) MM DIA BY DTH METHOD FOR BARABAZAR AND OTHER SCHEMES UNDER PMD PHE DTE.(TR.NO 60 OF 2022-23) | ASSISTANT ENGINEER | JUNIOR ENGINEER | VCH/000230/2022-2023 | C072218251845 | 18/07/2022 | 0 | RABINDRA NATH KHAN | 8.16 | 0 | 0
516 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sonathol Water Supply scheme Block Kashipur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000064/2021-2022 | 109/PMD | 28/02/2022 | 30 | R.N.S. TRADING | 20.48 | 0 | 100
517 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Submersible pump motor ,cable line,Kiosk , MCC allied electro mechanical equipments at Augmentation of sonatholi Water supply scheme Block: kashipur, Under Purulia Mechanical Division PHE Dte. Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000286/2022-2023 | 78/PMD | 01/02/2023 | 60 | SUMIT KR. CHAKRABORTY | 25.34 | 0 | 20
518 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Horizontal split casing centrifugal pump motor, MCC , Flow meter and All electro mechanical equipments , with allied works for Augmentation Sonathali low lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000287/2022-2023 | 79/PMD | 01/02/2023 | 60 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 37.16 | 0 | 50
519 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and external illumination arrangement at Augmentation Sonathali low lift and High lift Water supply scheme Block: Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000472/2022-2023 | 312/PMD | 16/03/2023 | 30 | NUPUR CHANDRA HALDER | 5.13 | 0 | 45
520 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Vertical multistage centrifugal pump motor sets ,Pannel , Flow meter and all electro mechanical equipment's at Augmentation of Sonathali High Lift Water supply scheme for direct pumping Block :Kashipur, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000513/2022-2023 | 100/PMD | 09/02/2023 | 60 | R.N.S. TRADING | 45.25 | 0 | 68
521 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Providing And Installation of 2 M.T. capacity manually operated curved monorail for Low Lift Pump House and High Lift Pump House under Augmentation of Sonathali Water Supply Scheme, Block: Kashipur, under Purulia Mechanical Division, PHE, Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000546/2023-2024 | 379/PMD | 04/03/2024 | 348 | S. PATHAK & CO. | 10.22 | 0 | 100
522 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTT. OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF SNATHOL W/S SCHEME KASHIPUR BLOCK UNDER PMD PHE DTE.(TR.NO 342 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | VCH/000586/2021-2022 | C032262583160 | 28/03/2022 | 0 | R.N.S. TRADING | 13.71 | 0 | 0
523 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Baghmundi | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00249/2023-2024 | BP-2023-24-153 | 14/09/2023 | 0 | WBSEDCL PURULIA | 6.08 | 0 | 0
524 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Load Enhancement for Augmentation of Baghmundi | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | BILL/00250/2023-2024 | BP-2023-24-152 | 14/09/2023 | 0 | WBSEDCL PURULIA | 3.86 | 0 | 0
525 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Augmentation of Barge and floating walkway with required MS work by necessary supply of materials and other allied works for Augmentation of Bagmundi W/S scheme under PMD PHE Dte in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000051/2023-2024 | 520/PMD | 05/05/2023 | 60 | ASHOKE ADHIKARY | 19.46 | 0 | 21
526 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Baghmundi Water Supply scheme Block Baghmundi under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000065/2021-2022 | 110/PMD | 28/02/2022 | 30 | COMBINE ENTERPRISE | 20.48 | 4.69 | 100
527 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(Intake Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000075/2023-2024 | 562/PMD | 16/05/2023 | 60 | H K DAS AND CO | 16.75 | 0 | 100
528 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of Internal lighting and external lighting for Bagmundi w/s scheme( WTP and OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000128/2023-2024 | 866/PMD | 21/07/2023 | 60 | ASHOKE ADHIKARY | 3.05 | 0 | 100
529 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of external lighting and other allied works for Baghmundi (High Lift) water supply scheme under PMD PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000185/2022-2023 | 755/PMD | 07/11/2022 | 30 | SUBRATA DUTTA | 4.01 | 3.9 | 100
530 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(OHR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000401/2022-2023 | 229/PMD | 03/03/2023 | 60 | PINTU DEY | 22.94 | 7.82 | 70
531 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply & installation of Centrifugal pumping machinery with other allied works for Augmentation at Bagmundi w/s scheme(CWR Site) under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | ORD/000402/2022-2023 | 230/PMD | 03/03/2023 | 60 | SUBRATA DUTTA | 40.32 | 8.79 | 75
532 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY AND INSTALLATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAGHMUNDI WATER SUPPLY SCHEME UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000083/2022-2023 | C042211560768 | 08/04/2022 | 0 | COMBINE ENTERPRISE | 12.25 | 0 | 0
533 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | SUPPLY DELIVERY & INSTTALATION OF 1KG/HR GASEOUS CHLORINATION SYSTEM AT AUGMENTATION OF BAHGMUNDI W/S SCHEME , BAGHMUNDI BLOCK UNDER PMD PHE DTE.(TR.NO 344 OF 2021-22) | ASSISTANT ENGINEER | JUNIOR ENGINEER (MECHANICAL) | VCH/000100/2022-2023 | C042249065860 | 29/04/2022 | 0 | COMBINE ENTERPRISE | 3.54 | 0 | 0
534 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Balarampur. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00485/2023-2024 | BP-23-24-246 | 28/12/2023 | 0 | WBSEDCL PURULIA | 6.55 | 0 | 0
535 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | New Connection for Augmentation of Balarampur. | ASSISTANT ENGINEER | JUNIOR ENGINEER | BILL/00486/2023-2024 | BP-23-24-245 | 28/12/2023 | 0 | WBSEDCL PURULIA | 4.7 | 0 | 0
536 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Balarampur OHR side zone-2 for Augmentation of Balarampur Water Supply scheme Block Balarampur under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000037/2023-2024 | 443/PMD | 20/04/2023 | 30 | ASHUTOSH DAS AND CO. | 21.56 | 0 | 0
537 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Internal and external illumination with other allied works for augmentation of Balarampur OHR site(Z-1 & Z-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000211/2023-2024 | 1197/PMD | 03/11/2023 | 60 | MOON LIGHT HOUSE | 8.85 | 0 | 0
538 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-1) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000212/2023-2024 | 1198/PMD | 03/11/2023 | 120 | COMBINE ENTERPRISES | 33.66 | 0 | 55
539 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, floor mounted MCC panel, Voltage stabilizer, Flowmeter and other allied works for augmentation of Balarampur OHR site(Zone-2) water supply scheme under PMD, PHE Dte. In the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000213/2023-2024 | 1199/PMD | 03/11/2023 | 120 | COMBINE ENTERPRISES | 34.58 | 0 | 60
540 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of centrifugal pumping machineries, flowmeter, MCC panel and other allied works at intake side pump house for augmentation of Balarampur water supply scheme under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000256/2022-2023 | 47/PMD | 19/01/2023 | 60 | COMBINE ENTERPRISES | 74.71 | 13.61 | 100
541 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of headwork site centrifugal pumping machineries, Flowmeter, MCC Panel and other allied works for augmentation of Balarampur WTP under PMD, PHE Dte. in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000455/2022-2023 | 197/PMD | 24/02/2023 | 60 | ORIENTAL ENGINEERING CO. | 147.95 | 0 | 55
542 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and installation of MS pipe, specials including supply and laying of different size cables including allied works at WTP site under Augmentation of Balarampur Water supply scheme under Purulia Mechanical Division, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000626/2024-2025 | 1548/PMD | 11/11/2024 | 60 | ORIENTAL ENGINEERING CO. | 15.53 | 0 | 0
543 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | QUATATION FOR SHIFTING OF TRANSFORMER | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | BILL/00476/2023-2024 | BP-23-24-238 | 13/12/2023 | 0 | WBSEDCL PURULIA | 2.36 | 0 | 0
544 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Augmentation at SARBARI (Phase-1) w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000116/2023-2024 | 644/PMD | 08/06/2023 | 30 | AVISHEK ENTERPRISE | 6.27 | 0 | 100
545 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery and fitting fixing of the luminaries external and internal lighting with others allied works for Rejuvenation at SARBARI (Phase-2) w/s scheme under PMD, PHE Dte. in the District of Purulia.. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000117/2023-2024 | 645/PMD | 08/06/2023 | 30 | SANTU MITRA | 4.4 | 0 | 50
546 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, Delivery and installation of Centrifugal pumping machineries, MCC Panels with others allied works for rejuvenation at SARBARI PHASE-2 w/s scheme under PMD, PHE Dte. in the District of Purulia. (2 nd Call) | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000185/2023-2024 | 1175/PMD | 03/11/2023 | 120 | R.N.S. TRADING | 41.91 | 0 | 0
547 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-1 Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000201/2023-2024 | 1191/PMD | 03/11/2023 | 60 | SEN BROTHERS | 9.71 | 0 | 100
548 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of 2 MT Capacity single girder H.O.T Crane with gantry girder and square rail for Sarbori Phase-2 Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000202/2023-2024 | 1192/PMD | 03/11/2023 | 60 | P K ENGINEERING | 11.49 | 0 | 100
549 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply delivery installation of 1kg/hr gaseous chlorination system at Augmentation of Sarbari Water Supply scheme Neturia Block under PMD PHE Dte. District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000292/2022-2023 | 84/PMD | 01/02/2023 | 60 | GHOSE ENGINEERING SYNDICATE | 21.61 | 0 | 100
550 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of Centrifugal pumping machineries, MCC Panel, Flowmeter with others allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE, Dte. in the District of Purulia | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000309/2022-2023 | 97/PMD | 03/02/2023 | 60 | GOENKA ENTERPRISE | 49.77 | 0 | 100
551 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery and installation of 4 nos. submersible pumps motor sets at newly constructed riverbed tubewell with other allied works for Augmentation at SARBARI PHASE-1 w/s scheme under PMD, PHE Dte. in the District of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000310/2022-2023 | 98/PMD | 03/02/2023 | 698 | AVISHEK ENTERPRISE | 12.13 | 9.86 | 100
552 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply and installation of valves, pipes & Misc. works for Pump house of Sarbori w/s scheme under PMD, PHE Dte. in the District Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000594/2024-2025 | 1452/PMD | 01/10/2024 | 30 | R.N.S. TRADING | 1.73 | 0 | 0
553 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Supply, delivery & installation of Lighting conductor under Sarbori Water Supply Scheme under Purulia Mechanical Division P.H.E Dte.in the district of Purulia. | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | ORD/000604/2024-2025 | 351/PMSD(W/S) | 04/09/2024 | 15 | BISWAJIT MAJI | 0.61 | 0 | 0
554 | Purulia Mechanical | Purulia Mechanical Sub-Division(W/S) | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER,Junior Engineer-3 | RTOR000008/2023-2024 | 617/PMD | 01/06/2023 | 0 | Resource Division | 3.1 | 0 | 0
555 | Purulia Mechanical | Purulia Division | For new connection at Gobag near uposasthya kendra under augmentation of Raghunathpur zone 1A/1 & zone 1A/II | Assistant Engineer(HQ) |  | BILL/00777/2023-2024 | BP-23-24-277 | 01/02/2024 | 0 | WBSEDCL PURULIA | 2.81 | 0 | 0
556 | Purulia Mechanical | Purulia Division | Supply, delivery & Installation of Submersible Pumping Machinery and other works, at OHR site- Ketlapur, Zone-VII B (T/W-III) under Raghunathpur water supply project, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000008/2025-2026 | 619/PMD | 22/04/2025 | 20 | ANUP KUMAR SAHA | 0.88 | 0 | 0
557 | Purulia Mechanical | Purulia Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone 1A/II under PMD PHE Dte. District Purulia. | Assistant Engineer(HQ) |  | ORD/000124/2023-2024 | 860/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 75
558 | Purulia Mechanical | Purulia Division | Supply, delivery and laying of cable and other works, at OHR site Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000610/2024-2025 | 858/PMD | 03/06/2024 | 10 | ANUP KUMAR SAHA | 0.94 | 0 | 95
559 | Purulia Mechanical | Purulia Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site - I (Tube Well -Il), of Gobag of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer(HQ) |  | ORD/000646/2024-2025 | 1010/PMD | 24/06/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 95
560 | Purulia Mechanical | Raghunathpur Sub-Division | NEW CONNECTION FOR AUGMENTATION OF RAGHUNATHPUR ZONE VB | Assistant Engineer | Junior Engineer-1 | BILL/00479/2023-2024 | BP-23-24-250 | 04/01/2024 | 0 | WBSEDCL PURULIA | 1.18 | 0 | 0
561 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery installation of 1kg/hr gaseous chlorination system for Augmentation of Rathunathpur Pipe Water Supply scheme for Zone V B under PMD PHE Dte. District Purulia. | Assistant Engineer | Junior Engineer-1 | ORD/000126/2023-2024 | 862/PMD | 20/07/2023 | 30 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 21.6 | 0 | 75
562 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Nanduka-V(B) of Raghunathpur water supply project under Purulia Mechanical Division,PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000564/2023-2024 | 367/PMD. | 01/03/2024 | 10 | ASHOKE ADHIKARY | 0.98 | 0 | 80
563 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of kiosk box comprising of motor startering arrangement (DOL), at OHR site V(B) (T/W-1) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000565/2023-2024 | 445/PMD | 11/03/2024 | 10 | TAPAN KUMAR DEY | 1 | 0 | 60
564 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & laying of cable and other works at OHR site- V(B) of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000566/2023-2024 | 443/PMD | 11/03/2024 | 10 | TAPAN KUMAR DEY | 0.84 | 0 | 60
565 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site-V (Tube well-II), Nanduka under Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000598/2024-2025 | 1028/PMD | 25/06/2024 | 15 | S. PATHAK & CO. | 0.95 | 0 | 90
566 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of earthing arrangement and other works at OHR site-V, Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-1 | ORD/000599/2024-2025 | 1041/PMD | 26/06/2024 | 15 | S. PATHAK & CO. | 0.71 | 0 | 70
567 | Purulia Mechanical | Raghunathpur Sub-Division | Payment of New Electric Connection charge at Salata mouza ,Babugram site , Zone - IV B Raghunathpur - 1 under Augmentation of Raghunathpur W.S. Project and payment to WBSEDCL Raghunathpur CCC . Referance Id - 204346008 | Assistant Engineer |  | BILL/00191/2024-2025 | BP-24-25-48 | 16/07/2024 | 0 | ASSISTANT ENGINEER & IN CHARGE, RAGHUNATHPUR 132 KV SUB STATION (WBSETCL) | 3.11 | 0 | 0
568 | Purulia Mechanical | Raghunathpur Sub-Division | Supply of Diesel & Mobil for vehicle WB56V-4010 for the month of March-2024 under PMD, PHE Dte. | Assistant Engineer |  | BILL/00227/2024-2025 | BP-24-25-80 | 02/08/2024 | 0 | M/S SANKAR AUTO SERVICE | 0.22 | 0 | 0
569 | Purulia Mechanical | Raghunathpur Sub-Division | Payment to WBSEDCL , Chelyama CCC for new connection at Vill. + P.O. - Chelyama , Rghunathpur , application no,- 2004770178 , reference Id.- 204327440 . | Assistant Engineer |  | BILL/00289/2024-2025 | BP-24-25-76 | 02/08/2024 | 0 | WBSEDCL PURULIA | 5.36 | 0 | 0
570 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | Assistant Engineer |  | BILL/00456/2023-2024 | BP-23-24-221 | 05/12/2023 | 0 | WBSEDCL PURULIA | 0.05 | 0 | 0
571 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | Assistant Engineer |  | BILL/00457/2023-2024 | BP-23-24-281 | 16/02/2024 | 0 | WBSEDCL PURULIA | 1.63 | 0 | 0
572 | Purulia Mechanical | Raghunathpur Sub-Division | Quotation for new connection | Assistant Engineer |  | BILL/00458/2023-2024 | BP-23-24-280 | 16/02/2024 | 0 | WBSEDCL PURULIA | 0.61 | 0 | 0
573 | Purulia Mechanical | Raghunathpur Sub-Division | New Connection for Augmentation of Raghunathpur ZOne- I B (Nanduara) | Assistant Engineer |  | BILL/00821/2023-2024 | BP-24-25-27 | 11/06/2024 | 0 | WBSEDCL PURULIA | 0.25 | 0 | 0
574 | Purulia Mechanical | Raghunathpur Sub-Division | New Connection for Augmentation of Raghunathpur ZOne-I B (Sohardi Mouza Babugram, Sanka) | Assistant Engineer |  | BILL/00823/2023-2024 |  | 08/02/2024 | 0 | WBSEDCL PURULIA | 2.32 | 0 | 0
575 | Purulia Mechanical | Raghunathpur Sub-Division | Bulk power supply at 11 KV, Purulia for a contractual demand of 400/400/400/400/400 KVA respectively for next consecutive five years, Mouza-Salata, Block-Raghunathpur -I , Purulia | Assistant Engineer |  | BILL/00864/2023-2024 | BP-23-24-299 | 05/03/2024 | 0 | WBSEDCL PURULIA | 38.16 | 0 | 0
576 | Purulia Mechanical | Raghunathpur Sub-Division | Modification of existing filter bed control system with allied works at Lakshmanpur WTP under Raghunathpur Water Supply Project under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000005/2025-2026 | 568/PMD | 07/04/2025 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD. | 101.61 | 0 | 0
577 | Purulia Mechanical | Raghunathpur Sub-Division | Yard lighting arrangement at different OHR site and other works under Augmentation of Raghunathpur Pipe Water Supply Project under PMD, PHE. Dte. | Assistant Engineer |  | ORD/000006/2025-2026 | 569/PMD | 07/04/2025 | 269 | BISHWANATH NANDI | 24.28 | 0 | 80
578 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and Installation of 4KG/HR Gaseous Chlorination system and Chlorine leak absorption system at Lakshmanpur WTP under Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000174/2023-2024 | 1126PMD | 11/10/2023 | 120 | ELECTRICAL AND MECHANICAL ENGINEERING CORPORATION | 80.55 | 0 | 0
579 | Purulia Mechanical | Raghunathpur Sub-Division | Replacement of existing two number old VT pumps with new pumps at intake pump house of Lakshmanpur WTP for Augmentation of Raghunarhpur W/S project with allied works, under PMD, PHE, Dte. | Assistant Engineer |  | ORD/000175/2023-2024 | 1127/PMD | 11/10/2023 | 599 | COMBINE ENTERPRISES | 31.33 | 0 | 91
580 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of electro mechanical equipment's, HSC pump motor sets, MCC, HOT, Valves, Flowmeter at Proposed Clear water pump house in Lakshmanpur WTP Under Augmentation of Raghunathpur water supply project Bolck : Neturia, Under Purulia Mechanical Division PHE Dte Dist-Purulia. | Assistant Engineer |  | ORD/000177/2023-2024 | 458/PMD | 14/03/2024 | 120 | NEW ALIGNMENT | 192.41 | 0 | 0
581 | Purulia Mechanical | Raghunathpur Sub-Division | Supply delivery and installation of electro mechanical equipments, HSC pump motor sets, MCC, HOT, Valves, Flowmeter ,400 KVA electrical substation, Gaseous chlorination system at Clear water Boosting pump house Under Augmentation of Raghunathpur water supply project Under Purulia Mechanical Division PHE Dte Dist-Purulia. | Assistant Engineer |  | ORD/000178/2023-2024 | 1147/PMD | 16/10/2023 | 120 | MAHADEV ENTERPRISE | 331.9 | 0 | 0
582 | Purulia Mechanical | Raghunathpur Sub-Division | Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte. | Assistant Engineer |  | ORD/000207/2023-2024 | 1086/PMD | 29/09/2023 | 183 | PINTU DEY | 0.89 | 0 | 84
583 | Purulia Mechanical | Raghunathpur Sub-Division | Installation of Ongrid solar system and Fabrication structure on ground floor Solarisation of WBSEDCL energised pumping machinery at Existing 8 nos OHR and Proposed 6nos OHR site under Augmentation of Raghunathpur water supply project under PMD, PHE, Dte. District Purulia. | Assistant Engineer |  | ORD/000231/2023-2024 | 1125/PMD | 11/10/2023 | 538 | PROGRESSIVE ENGINEERS CO. OPERATIVE SOCIETY LTD. | 44.79 | 0 | 50
584 | Purulia Mechanical | Raghunathpur Sub-Division | Strengthen the existing monorail at Chlorination Building of Lakshmanpur WTP and other allied works under Raghunathpur Water Supply Project under under Purulia Mechanical Division P.H.E. Dte. | Assistant Engineer |  | ORD/000444/2023-2024 | 424/PMD | 11/03/2024 | 386 | RABINDRA NATH KHAN | 7.76 | 0 | 100
585 | Purulia Mechanical | Raghunathpur Sub-Division | Continuation Work Order for "Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.04.2024 to 30.09.2024 | Assistant Engineer |  | ORD/000499/2023-2024 | 525/PMD | 18/03/2024 | 183 | PINTU DEY | 0.89 | 0 | 55
586 | Purulia Mechanical | Raghunathpur Sub-Division | Continuation Work Order for"Hiring charges of 1(one) no. Car.(Diesel driven) along with driver for use of the Office of the Assistant Engineer(H.Q) for augmentation of different water supply scheme in Raghunathpur Block, under Purulia Mechanical Division P.H.E Dte." With effect from :01.10.2024 to 31.03.2025 | Assistant Engineer |  | ORD/000570/2024-2025 | 1375/PMD | 19/09/2024 | 182 | PINTU DEY | 0.89 | 0 | 0
587 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-II), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000576/2024-2025 | 1009/PMD | 24/06/2024 | 15 | SUJIT MUKHERJEE | 0.95 | 0 | 80
588 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Salata (Z-IB) (Tube well-I), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000577/2024-2025 | 906/PMD | 10/06/2024 | 15 | M/S A.D. CONCERN | 0.95 | 0 | 80
589 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of 1 Ton A.C machine at Lakshmanpur Bungalow of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000578/2024-2025 | 1116/PMD | 12/07/2024 | 15 | TAPAN KUMAR DEY | 0.62 | 0 | 100
590 | Purulia Mechanical | Raghunathpur Sub-Division | Yard lighting and internal illumination arrangement at Augmentation of Raghunathpur Pipe Water Supply Scheme for Zone IV - B under Purulia Mechanical Division, PHE. Dte. | Assistant Engineer |  | ORD/000589/2024-2025 | 1447/PMD | 01/10/2024 | 151 | BISHWANATH NANDI | 13.34 | 0 | 65
591 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of A.C Machine at Ground floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000606/2023-2024 | 446/PMD | 11/03/2024 | 10 | S PATHAK AND CO | 0.79 | 0 | 99
592 | Purulia Mechanical | Raghunathpur Sub-Division | Supply and installation of A.C Machine at first floor of Shimul Annex Building at Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000608/2023-2024 | 385/PMD | 04/03/2024 | 10 | S PATHAK AND CO | 0.79 | 0 | 99
593 | Purulia Mechanical | Raghunathpur Sub-Division | Providing Mechanical / Electrical Works with all accessories for High Lift Pumping Machinary at Booster Pumping Station - Zone VIII, Augmentation of Raghunathpur Water Supply Project under PMD PHE Dte. in the District of Purulia. | Assistant Engineer |  | ORD/000638/2024-2025 | 1570/PMD | 14/11/2024 | 180 | COMBINE ENTERPRISES | 47.9 | 0 | 0
594 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery, installation and commissioning of chlorine leak absorption System at different OHR sites of Raghunathpur Water Supply Project under PMD PHE Dte. | Assistant Engineer |  | ORD/000644/2024-2025 | 1576/PMD | 14/11/2024 | 90 | TAPAN KUMAR DEY | 90.02 | 0 | 0
595 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube well-3), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000647/2024-2025 | 1259/PMD | 22/08/2024 | 15 | M/S UJJAL DIESEL SERVICE | 0.96 | 0 | 90
596 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- Uporkhajura (Tube well-III), of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000650/2024-2025 | 1115/PMD | 12/07/2024 | 15 | ANUP KUMAR SAHA | 0.81 | 0 | 0
597 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-IV), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000652/2024-2025 | 1323/PMD | 04/09/2024 | 103 | M/S A.D. CONCERN | 0.96 | 0 | 90
598 | Purulia Mechanical | Raghunathpur Sub-Division | Supply, delivery & installation of Submersible Pumping Machinery along with allied works, at OHR site- VB (Tube Wel-V), Nanduka of Raghunathpur water supply project under Purulia Mechanical Division, PHE Dte. | Assistant Engineer |  | ORD/000653/2024-2025 | 1324/PMD | 04/09/2024 | 15 | PINTU DEY | 0.96 | 0 | 90
Total | [10 empty] | 16211.49 | 1467.77