## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Midnapore Mechanical | Digha Sub-Division | Electric Quotiaton for Kasbagola Water Supply Scheme T/W-III (Ref. ID-204005246) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00380/2023-2024 | BP-2023-24-66 | 06/06/2023 | 0 | WBSEDCL | 0.61 | 0 | 0
2 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-4 of Kasbagola ws scheme under MMD, PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004773721 Con ID-204332518 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01328/2024-2025 | BP-2024-25-359 | 01/07/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
3 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Kasbagola PWSS to Accommodate FHTC in EGRA-I Block under Digha Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001925/2022-2023 | 844/W/MMD | 24/03/2023 | 840 | ECO ENTERPRISE | 35.55 | 13.97 | 25
4 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000172/2022-2023 | 2003984006/QUOT/1017 | 05/07/2022 | 365 | WBSEDCL | 0.56 | 0 | 0
5 | Midnapore Mechanical |  | New Service Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000173/2022-2023 | MNA/QUT/22-23/NSC/PHE/201 | 08/07/2022 | 365 | WBSEDCL | 1.86 | 0 | 0
6 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000174/2022-2023 | 2003984015/QUOT/1016 | 05/07/2022 | 365 | WBSEDCL | 0.56 | 0 | 0
7 | Midnapore Mechanical |  | New service connection PHE Full deposite scheme for T/W -II of Shyampur Water supply scheme under MMD PHE Dte. |  |  | ORD/000176/2022-2023 | MNA/QUT/22-23/NSC/PHE/101 | 08/07/2022 | 365 | WBSEDCL | 1.42 | 0 | 0
8 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. |  |  | ORD/001014/2022-2023 | 1863/W/MMD | 22/09/2022 | 120 | PRANAB KUMAR DAS | 12.66 | 11.9 | 100
9 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Shyampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. |  |  | ORD/001130/2022-2023 | 2111/W/MMD | 28/11/2022 | 120 | ECO ENTERPRISE | 12.68 | 12.42 | 100
10 | Midnapore Mechanical |  | New Servic Connection Full Deposit Scheme, T/W-I of Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001775/2022-2023 | BP-2022-23-29 | 10/08/2022 | 0 | WBSEDCL | 1.86 | 0 | 0
11 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001776/2022-2023 | BP-2022-23-32 | 11/08/2022 | 0 | WBSEDCL | 1.42 | 0 | 0
12 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -II Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001777/2022-2023 | BP-2022-23-30 | 10/08/2022 | 0 | WBSEDCL | 0.56 | 0 | 0
13 | Midnapore Mechanical |  | Electic quotation bill at Moyna CCC for T/W -I Shyampur Water supply scheme under MMD PHE Dte. |  |  | VCH/001778/2022-2023 | BP-2022-23-28 | 10/08/2022 | 0 | WBSEDCL | 0.56 | 0 | 0
14 | Midnapore Mechanical |  | Electric quotation for Baharampur PWSS Tube Well- I in connection Madhakhali CCC (2004185409) |  |  | BILL/00062/2022-2023 | BP-2022-23-105 | 27/02/2023 | 0 | WBSEDCL | 0.47 | 0 | 0
15 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-2 under Baharampur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. |  |  | ORD/001131/2022-2023 | 2112/W/MMD | 28/11/2022 | 120 | ALPHA ENTERPRISE | 10.92 | 8.34 | 100
16 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Baharampur Piped Water Supply Scheme., Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. |  |  | ORD/001342/2022-2023 | 35/W/MMD | 04/01/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.58 | 11.58 | 100
17 | Midnapore Mechanical |  | Supply delivery of Voltage Stabilizer and submersible pump motor set at PH No. II of Baharampur Water Supply Scheme under H.E.S.D. under Midnapore Mechanical Division, P.H.E. Dte. |  |  | ORD/002188/2022-2023 | 291/MMSD-I | 23/03/2023 | 10 | ALPHA ENTERPRISE | 3.06 | 3.06 | 100
18 | Midnapore Mechanical |  | Electric quotation MADHAKHALI CCC at Baharampur T/W-II Pin-721444 |  |  | VCH/002772/2022-2023 | BP-2022-23-60 | 23/11/2022 | 0 | WBSEDCL | 0.61 | 0 | 0
19 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Basudebberya in Block - Deshopran under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001449/2022-2023 | 159/W/MMD | 02/02/2023 | 180 | MUKHERJEE ART CENTRE | 25.26 | 12.02 | 54
20 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. |  |  | ORD/001258/2022-2023 | 2188/W/MMD | 12/12/2022 | 120 | S.S.GHORAI | 13.09 | 12.3 | 75
21 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Narikelda water supply scheme under Midnapore Mechanical Division, PHE Dte. |  |  | ORD/001259/2022-2023 | 2189/W/MMD | 12/12/2022 | 120 | MENAKA ENTERPRISE | 13.09 | 12.32 | 100
22 | Midnapore Mechanical | Kharagpur Sub-Division | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Lachmi Chak water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001136/2021-2022 | 2512/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 0 | 100
23 | Midnapore Mechanical | Kharagpur Sub-Division | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Lachmi Chak water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001142/2021-2022 | 2514/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 3.95 | 0
24 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001188/2021-2022 | 147/W/MMD | 31/01/2022 | 120 | P.P.CONCERN | 6.5 | 2.09 | 0
25 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001189/2021-2022 | 148/W/MMD | 31/01/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.51 | 4.32 | 0
26 | Midnapore Mechanical | Kharagpur Sub-Division | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Lachmi Chak water supply scheme , tube well no. 2 of Sabang Block of Paschim Midnapur Dist. under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001557/2021-2022 | 43/MMSD-I | 19/01/2022 | 7 | DEBJYOTI BASU | 0.19 | 0.19 | 0
27 | Midnapore Mechanical | Kharagpur Sub-Division | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Lachmi Chak water supply scheme , tube well no. I of Sabang Block of Paschim Midnapur Dist. under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001558/2021-2022 | 44/MMSD-I | 19/01/2022 | 7 | DEBJYOTI BASU | 0.19 | 0.19 | 0
28 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Lachhmi Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-147/W/MMD, DT-31/01/2022) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/005602/2021-2022 | BP-2021-22-120 | 17/03/2022 | 0 | P.P.CONCERN | 3.68 | 0 | 0
29 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charges of WBSEDCL at TW-III (Additional) of Barasahara Water Supply Scheme (Ref. ID - 20395154) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00408/2022-2023 | BP-2022-23-152 | 28/03/2023 | 0 | WBSEDCL | 3.4 | 0 | 0
30 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charges of WBSEDCL at TW-IV (Additional) of Barasahara Water Supply Scheme (Ref. ID - 203934601) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00409/2022-2023 |  | 22/03/2023 | 0 | WBSEDCL | 2.55 | 0 | 0
31 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Barsahara PWSS Tube Well-IV WS Scheme (Ref. ID 203934601) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00413/2022-2023 | BP-2002-23-153 | 28/03/2023 | 0 | WBSEDCL | 2.55 | 0 | 0
32 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Barsahara PWSS Tube Well-III WS Scheme (Ref. ID 203935154) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00414/2022-2023 |  | 25/03/2023 | 0 | WBSEDCL | 3.4 | 0 | 0
33 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring at Tube Well no 4 of Barshahara Water Supply Scheme (Block- Sabang) under MMD, PHE Dte., Dist. Paschim Medinipur. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000492/2023-2024 | 1850/W/MMD | 22/08/2023 | 677 | MANORANJAN DEY | 12.51 | 11.77 | 100
34 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and Installation of Voltage Stabilizer for Tube well No.-3 of Barshahara Water Supply Scheme [ Block-Sabang] under MMD, PHE Dte., Dist.- Paschim Medinipur. (JJM Work) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001252/2023-2024 | 1112/MMSD-I | 14/09/2023 | 30 | RITESH ENTERPRISE | 2.83 | 2.83 | 100
35 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001306/2022-2023 | 2308/W/MMD | 29/12/2022 | 180 | RITESH ENTERPRISE | 10.79 | 0 | 85
36 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
37 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0.2 | 100
38 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.09 | 100
39 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SHANKARPUR Water Supply Scheme T/W-III, (Ref. ID-204049544) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01682/2023-2024 | BP-2023-24-168 | 04/08/2023 | 0 | WBSEDCL | 4.93 | 0 | 0
40 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03723/2023-2024 | BP-2023-24-675 | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0
41 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Shankarpur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000064/2023-2024 | 1223/W/MMD | 25/04/2023 | 180 | THE GODFATHER TRADING COMPANY | 11.96 | 11.75 | 100
42 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000053/2023-2024 | 1218/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 40.43 | 23.84 | 60
43 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation bill of Sapai T/W-III ,P.O.-Bahitrakunda under Marishda CCC (Memo No. 2004155106) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00050/2022-2023 | BP-2022-23-100 | 10/01/2023 | 0 | WBSEDCL | 0.47 | 0 | 0
44 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000159/2023-2024 | 1394/W/MMD | 01/06/2023 | 180 | BHABANI PRASAD MANNA | 11.59 | 0 | 80
45 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well I under Sapai water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001143/2022-2023 | 2124/W/MMD | 28/11/2022 | 120 | DEBKUMAR BASU | 11.15 | 10.8 | 0
46 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service Connection charges of WBSEDL at Sartla Additional TW-III W/S Scheme (Consumer No. 2004156120) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00043/2022-2023 | BP-2022-23-91 | 04/01/2023 | 0 | WBSEDCL | 3.81 | 0 | 0
47 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION MONEY FOR ADDITIONAL TUBEWELL NO 3 OF SARTLA WATER SUPPLY SCHEME [ REFERENCE ID 860268179, APLLICATION ID 100000077609 , CHANDKURI CCC, WBSEDCL ] | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00120/2023-2024 | BP-2023-24-44 | 19/05/2023 | 0 | WBSEDCL | 0.78 | 0 | 0
48 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No III of Sartla Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE.TSM009946 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000240/2023-2024 | 605/MMSD-I | 06/06/2023 | 15 | EMCON | 5.76 | 5.76 | 100
49 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Sartla (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002043/2022-2023 | 951/W/MMD | 28/03/2023 | 180 | EMCON | 10.78 | 5.66 | 98
50 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004945784/QUOT/03 DT. 05-11-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204429932 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03007/2024-2025 | C112423558564 | 19/11/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
51 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHALTI and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001411/2022-2023 | 2422/W/MMD | 31/12/2022 | 882 | P.K.ENGINEERING | 22.8 | 17.61 | 90
52 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at CONTAI SALINE AREA ZONE-III, T/W NO-I, PHASE-B W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004696671/QUOT/03 DT. 24-04-2024 Application NO- 2004696671 Application type-New connection Consumer Id- 204284086 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00705/2024-2025 | BP-2024-25-146 | 09/05/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
53 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-A) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001909/2022-2023 | 810/W/MMD | 24/03/2023 | 180 | SUBHAM ENTERPRISE | 13.59 | 6.32 | 47
54 | Midnapore Mechanical | Contai Sub-Division | Electric quotation bill for WBSEDCL at TW III of Argoal WS Scheme (Ref. ID - 203932077) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00060/2023-2024 | BP-2023-24-7 | 18/04/2023 | 0 | WBSEDCL | 0.74 | 0 | 0
55 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sinking of Boosting Tube Well and Allied Works for Argoal PWSS under Contai Sub-Division of Tamluk Division, PHE Dte. Block ¿ Potashpur II within the Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001738/2022-2023 | 640/W/MMD | 20/03/2023 | 180 | PURUSHOTTAM ENTERPRISE | 13.57 | 13.27 | 100
56 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill for the Service connection at T/W NO-I , ZONE-II Of BAJKUL W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: KHEJURI C.C.C. Ref. Memo No-KJR/QTN/200 DT. 25-06-2024 Application NO- 100000111551 DT. 25-06-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860303091 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01400/2024-2025 | BP-2024-25-379 | 08/07/2024 | 0 | WBSEDCL | 0.53 | 0 | 0
57 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BAJKUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204114262) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03058/2023-2024 | BP-2023-24-374 | 01/12/2023 | 0 | WBSEDCL | 3.48 | 0 | 0
58 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BAJKUL Water Supply Scheme T/W-II, Zone- II, (Ref. ID-204114267) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03059/2023-2024 | BP-2023-24-375 | 02/12/2023 | 0 | WBSEDCL | 4.77 | 0 | 0
59 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001980/2022-2023 | 819/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 23.7 | 21.81 | 85
60 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BHAJACHAULI Water Supply Scheme T/W-III, (Ref. ID-204050249) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01683/2023-2024 | BP-2023-24-167 | 04/08/2023 | 0 | WBSEDCL | 1.74 | 0 | 0
61 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bhajachauli, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001905/2022-2023 | 806/W/MMD | 24/03/2023 | 536 | DEBKUMAR BASU | 13.58 | 12.76 | 100
62 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00102/2023-2024 | BP-2023-24-26 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
63 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Suadighi Water Supply Scheme Zone-I, TW-III (Ref. Id-203950247) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00107/2023-2024 | BP-2023-24-38 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
64 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Suadighi Water Supply Scheme TW-I , zone-II (Ref. ID -203932077) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00111/2023-2024 |  | 28/04/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
65 | Midnapore Mechanical | Contai Sub-Division | quotation for new power connection at newly sunk t/w at Madhakhali w/s scheme zone -II , T/W - I | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00270/2023-2024 |  | 23/05/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
66 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of SUADIGHI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004740459/QUOT/03 DT. 17-05-2024 Application NO- 2004740459 Application type-New connection Consumer Id- 204309985 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01130/2024-2025 | BP-2024-25-246 | 06/06/2024 | 0 | WBSEDCL | 7.11 | 0 | 0
67 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SUADIGHI Water Supply Scheme T/W-II, Zone-II (Ref. ID-204020001) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01825/2023-2024 | BP-2023-24-201 | 24/08/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
68 | Midnapore Mechanical | Contai Sub-Division | Suadighi W/S scheme TW no.-III, Z-I Ref.-860286948 ID-100000094898 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03153/2023-2024 | BP-2023-24-449 | 19/12/2023 | 0 | WBSEDCL | 3.64 | 0 | 0
69 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone II), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001467/2022-2023 | 205/W/MMD | 10/02/2023 | 180 | BALAJI CONSTRUCTION | 40.78 | 34.24 | 70
70 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Suadighi piped water supply scheme (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001470/2022-2023 | 208/W/MMD | 10/02/2023 | 180 | NIRMAN | 27.16 | 25.53 | 75
71 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
72 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amlagora to Accommodate FHTC, Block - Garbeta-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001290/2022-2023 | 2293/W/MMD | 29/12/2022 | 180 | DEBJYOTI BASU | 23 | 0 | 0
73 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BIRAMPUT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, CONTAI C.C.C. Ref. Memo No-2004614786/QUOT/03 DT. 23-02-2024 Application NO- 2004614786 Application type-New connection Reference Id- 204225082 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04264/2023-2024 | BP-2023-24-792 | 06/03/2024 | 0 | WBSEDCL | 3.83 | 0 | 0
74 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NARAYAN DANRI and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001585/2022-2023 | 468/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 23.68 | 16.85 | 30
75 | Midnapore Mechanical | Haldia Sub-Division | Quotation for Kanchanpur w/s scheme PH II in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216165, App No 2004599558) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04142/2023-2024 | BP-2023-24-756 | 01/03/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
76 | Midnapore Mechanical | Haldia Sub-Division | Quotation for Kanchanpur w/s scheme PH I in the Purba Medinipur under MMD PHE Dte.(Ref ID 204216166, App No 2004599555) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04143/2023-2024 | BP-2023-24-755 | 01/03/2024 | 0 | WBSEDCL | 5.06 | 0 | 0
77 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANCHANPUR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001583/2022-2023 | 466/W/MMD | 20/03/2023 | 914 | DEY ENTERPRISE | 23.7 | 11.15 | 45
78 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KADUA and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002033/2022-2023 | 941/W/MMD | 28/03/2023 | 180 | S.G.ENTERPRISE | 21.6 | 0 | 0
79 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PANUSI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004615668/QUOT/03 DT. 23-02-2024 Application NO- 2004615668 Application type-New connection Consumer Id- 204225684 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02553/2024-2025 | C102412615985 | 04/10/2024 | 0 | WBSEDCL | 11.08 | 0 | 0
80 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PANSUI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601802/QUOT/03 DT. 15-02-2024 Application NO- 2004601802 Application type-New connection Reference Id- 204217830 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04342/2023-2024 | BP-2023-24-811 | 11/03/2024 | 0 | WBSEDCL | 6.85 | 0 | 0
81 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
82 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALCHITKINI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001643/2022-2023 | 520/W/MMD | 20/03/2023 | 180 | BIJAN ENTERPRISE | 22.72 | 0 | 0
83 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
84 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well for Paschimbetya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001907/2022-2023 | 808/W/MMD | 24/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.58 | 8.29 | 60
85 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-I Of RAMNAGAR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004957544/QUOT/03 DT. 06-11-2024 Application NO- 2004957544 Application type-New connection Consumer Id- 204440003 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03008/2024-2025 | C112423558120 | 19/11/2024 | 0 | WBSEDCL | 2.66 | 0 | 0
86 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-I) PWSS, Block Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001916/2022-2023 | 820/W/MMD | 24/03/2023 | 860 | M/S SWAPAN BANERJEE | 27.17 | 0 | 52
87 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Markunda PWSS T/W - II | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03221/2023-2024 | BP-2023-24-465 | 27/12/2023 | 0 | WBSEDCL | 4.07 | 0 | 0
88 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation of new power connection at Markunda PWSS T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03222/2023-2024 | BP-2023-24-466 | 27/12/2023 | 0 | WBSEDCL | 3.54 | 0 | 0
89 | Midnapore Mechanical | Kharagpur Sub-Division | electric quotation for T/W - II of Markunda water supply Scheme | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001553/2023-2024 | Elce/quot/2004530133 | 14/12/2023 | 30 | WBSEDCL | 4.07 | 0 | 0
90 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOHALDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001663/2022-2023 | 577/W/MMD | 20/03/2023 | 834 | R.S. ENTERPRISE | 12.62 | 8.87 | 60
91 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Trikalpur PWSS T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03573/2023-2024 | BP-2023-24-602 | 07/02/2024 | 0 | WBSEDCL | 2.74 | 0 | 0
92 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Trikalpur PWSS T/W - II | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03574/2023-2024 | BP-2023-24-601 | 07/02/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
93 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of ANTRI PWSS. REF CONSUMER ID-204212535, APPLICATION NO-2004593704, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03738/2023-2024 | BP-2023-24-695 | 16/02/2024 | 0 | WBSEDCL | 8.6 | 0 | 0
94 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANTRI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001644/2022-2023 | 578/W/MMD | 20/03/2023 | 834 | ALPHA ENTERPRISE | 25.24 | 18.17 | 20
95 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
96 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Chawrakalganda W/S scheme T/W-I Application No.-2004520328 Ref:-204154822 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03168/2023-2024 | BP-2023-24-438 | 18/12/2023 | 0 | WBSEDCL | 8.99 | 0 | 0
97 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAWRAKALGANDA AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001710/2022-2023 | 627/W/MMD | 20/03/2023 | 957 | P.K.ENGINEERING | 23.7 | 18.1 | 35
98 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BETULIACHAKLALPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818516/QUOT/03 DT. 12-07-2024 Application NO- 2004818516 Application type-New connection Consumer Id- 204355509 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01891/2024-2025 | C082410083941 | 08/08/2024 | 0 | WBSEDCL | 13.02 | 0 | 0
99 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BETULYA CHAKLALPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001323/2022-2023 | 2325/W/MMD | 29/12/2022 | 180 | S.S.GHORAI | 23.7 | 14.81 | 55
100 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation of New service connection at Chongra w/s scheme PH I at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653990 Con ID 204255037) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00235/2024-2025 | BP-2024-25-32 | 15/04/2024 | 0 | WBSEDCL | 15.26 | 0 | 0
101 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation of New service connection at Chongra w/s scheme PH II at Moyna Block in the District of Purba Medinipur under MMD PHE Dte. (App ID 2004653966 Con ID 204255035) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00240/2024-2025 | BP-2024-25-33 | 15/04/2024 | 0 | WBSEDCL | 8.93 | 0 | 0
102 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHONGRA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001362/2022-2023 | 2373/W/MMD | 31/12/2022 | 720 | DIPALI CONSTRUCTION | 23.68 | 13.53 | 50
103 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Bikrampur pwss (Ref Consumar ID-204197919),Application No-2004569264,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03556/2023-2024 | BP-2023-24-611 | 07/02/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
104 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of BIKRAMPUR pwss (Ref Consumar ID-204198610),Application No-2004571249,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03569/2023-2024 | BP-2023-24-605 | 07/02/2024 | 0 | WBSEDCL | 5.54 | 0 | 0
105 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BIKRAMPUR PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001297/2022-2023 | 2300/W/MMD | 29/12/2022 | 1037 | P.K.ENGINEERING | 22.8 | 21.11 | 50
106 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quatation bill for Swadighi H/W Site W/S SCHEME under MMD,PHE,Dte. BLOCK- Sahid Matangini WBSEDCL SUPPLY OFFICE: Matangini C.C.C Ref. Memo No- 2004992438/Quot/03/1203 DT. 05-12-2024 APPLICATION NO: 2004992438 Consumer Id- 204463808 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03680/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 8.06 | 0 | 0
107 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SOYA DIGHI and ADJOINING MOUJAS, Block - Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002035/2022-2023 | 943/W/MMD | 28/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.79 | 0 | 0
108 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for New connection GULARI water supply scheme Head Work Site. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662586 Ref no.-204260849 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00257/2024-2025 | BP-2024-25-28 | 15/04/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
109 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New electric Quotation as per bill for Guluri water supply scheme, T/W-II Matangini CCC Block- Sahid Matangini Application No.-2004770105 Consumer ID.-204328454 Date.-12/06/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01283/2024-2025 | BP-2024-25-340 | 25/06/2024 | 0 | WBSEDCL | 3.61 | 0 | 0
110 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GULURI and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001680/2022-2023 | 557/W/MMD | 20/03/2023 | 720 | SHIVAM ENTERPRISE | 22.78 | 10.61 | 75
111 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-II of Kanpur PWSS.(ref Consumer ID-204136082) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02994/2023-2024 | BP-2023-24-382 | 02/12/2023 | 0 | WBSEDCL | 3.01 | 0 | 0
112 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw no-I Of Kanpur PWSS.(Ref consumer ID-204136075) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03019/2023-2024 | BP-2023-24-380 | 02/12/2023 | 0 | WBSEDCL | 3.93 | 0 | 0
113 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANPUR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001678/2023-2024 | 56/W/MMD | 15/01/2024 | 441 | ORIENTAL ENGINEERING CO. | 22.86 | 5.16 | 20
114 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II of KIA W/S Scheme under MMD, PHE, Dte. Block- Egra-I, Egra CCC Ref. Memo no- 2004607232/QUOT/03/3197 Dt. 20-Feb-2024 Application NO- 2004607232 Application type-New connection Reference Id- 204221796 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04144/2023-2024 | bp-2023-24-759 | 01/03/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
115 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-1 of KIA ws scheme under MMD, PHE DTE, Block-Egra-1, under EGRA CCC. Application no-2004607227, CON ID-204221794. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04145/2023-2024 | BP-2023-24-758 | 01/03/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
116 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002034/2022-2023 | 942/W/MMD | 28/03/2023 | 709 | ORIENTAL ENGINEERING CO. | 22.79 | 7.34 | 90
117 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SHANRPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER DEBRA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001597/2022-2023 | 480/W/MMD | 20/03/2023 | 180 | PURUSHOTTAM ENTERPRISE | 10.98 | 0 | 0
118 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Lowada pwss (Ref Consumar ID-204395093),Application No-2004893015,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02976/2024-2025 | C112417246901 | 12/11/2024 | 0 | WBSEDCL | 4.82 | 0 | 0
119 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Lowada pwss (Ref Consumar ID-204197979),Application No-2004569198,Application Type-New Connection,Name of ccc- Lowada ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03555/2023-2024 | BP-2023-24-661 | 12/02/2024 | 0 | WBSEDCL | 3.25 | 0 | 0
120 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for LOYADA AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001940/2022-2023 | 825/W/MMD | 24/03/2023 | 180 | P.K.ENGINEERING | 22.65 | 17.56 | 50
121 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BULANPUR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001959/2022-2023 | 871/W/MMD | 27/03/2023 | 180 | KUSHANI ENTERPRISE | 5.98 | 0 | 0
122 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-I of Ghritagram PWSS. Ref Consumer ID-204175253) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03332/2023-2024 | BP-2023-24-552 | 17/01/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
123 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-II of Ghritagram PWSS .(Ref Consumer ID-204175255) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03333/2023-2024 | BP-2023-24-553 | 16/01/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
124 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GHRITAGRAM AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001433/2023-2024 | 3087/W/MMD | 29/11/2023 | 540 | PADMA ENGINEERING CO. | 10.99 | 7.56 | 25
125 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at GRITHAGRAM Water supply scheme, Keshiary block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002720/2023-2024 | 1065/W/MMD | 14/03/2024 | 360 | M/S EMMESS | 12.39 | 7.44 | 30
126 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BASANTIA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877659/QUOT/03 DT. 12-09-2024 Application NO- 2004877659 Application type-New connection Consumer Id- 204397982 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02496/2024-2025 | C092445108283 | 30/09/2024 | 0 | WBSEDCL | 7.85 | 0 | 0
127 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTIA AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001725/2022-2023 | 597/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 22.8 | 0 | 0
128 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Kasba water supply scheme T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | BILL/03557/2023-2024 | BP-2023-24-641 | 08/02/2024 | 0 | WBSEDCL | 4.6 | 0 | 0
129 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at kasba water supply scheme T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | BILL/03583/2023-2024 | BP-2023-24-640 | 08/02/2024 | 0 | WBSEDCL | 0.51 | 0 | 0
130 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KASHBA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/000147/2023-2024 | 1378/W/MMD | 30/05/2023 | 180 | THE BUSINESS ENGINEERING INDIA | 11.98 | 0 | 15
131 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR KUSHMAN WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/14656, APPLICATION NO 2004816276, REFERENCE ID 204354169, BIRSHINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01731/2024-2025 | C072445025889 | 30/07/2024 | 0 | WBSEDCL | 5.09 | 0 | 0
132 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR KUSHMAN WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14656, APPLICATION NO 2004816294, REFERENCE ID 204354171, BIRSHINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01732/2024-2025 | C072445022964 | 30/07/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
133 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001635/2022-2023 | 540/W/MMD | 20/03/2023 | 939 | M/S. S.R. ENTERPRISE | 22.75 | 6.25 | 40
134 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-III of Digha Central zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812635 CON ID-204351924 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01584/2024-2025 | C072438487551 | 23/07/2024 | 0 | WBSEDCL | 0.43 | 0 | 0
135 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of Digha Central zone under MMD, PHE Dte, Block-Ramnagar-I, DIGHA CCC Application no-2004812648 CON ID-204351925 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01585/2024-2025 | C072438486724 | 23/07/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
136 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Central) Water Supply Scheme in Block Ramnagar I under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000071/2023-2024 | 1241/W/MMD | 28/04/2023 | 180 | SOUMEN ELECTRIC | 33.56 | 33.15 | 100
137 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
138 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-III of Digha Eastern zone under MMD, PHE Dte, Block-Ramnagar-I,DIGHA CCC Application no-2004812582 CON ID-204351921 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01586/2024-2025 | C072438488216 | 23/07/2024 | 0 | WBSEDCL | 0.88 | 0 | 0
139 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Digha (Eastern) Water Supply Scheme within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001996/2022-2023 | 900/W/MMD | 27/03/2023 | 765 | S.S.GHORAI | 25.26 | 14.86 | 100
140 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR CHAULISINGPUR WATER SUPPLY SCHEME, T W NO I, [ BAHIRSINGPUR ] JJM WORKS, SCHEME CODE SM/14998, APPLICATION NO 2004995144, REFERENCE ID 204465793, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03679/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 5.23 | 0 | 0
141 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001991/2022-2023 | 803/W/MMD | 24/03/2023 | 180 | SHREE BISHNU CONSTRUCTION | 10.79 | 0 | 0
142 | Midnapore Mechanical | Ghatal Subdivision | DANDIPUR WATER SUPPLY SCHEME, PH - I, BLOCK - GHATAL , SCHEME - SM/14999, REF. ID - 2004496533, GHATAL CCC, | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03011/2023-2024 | BP-2023-24-393 | 02/12/2023 | 0 | WBSEDCL | 3.86 | 0 | 0
143 | Midnapore Mechanical | Ghatal Subdivision | DANDIPUR WATER SUPPLY SCHEME, PH - II, BLOCK - GHATAL , SCHEME - SM/14999, REF. ID - 2004496518, GHATAL CCC | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03012/2023-2024 | BP-2023-24-394 | 02/12/2023 | 0 | WBSEDCL | 7.2 | 0 | 0
144 | Midnapore Mechanical | Ghatal Subdivision | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 40
145 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
146 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KASHI BHUINABAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004804684/QUOT/03 DT. 03-07-2024 Application NO- 2004804684 Application type-New connection Consumer Id- 204347452 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01468/2024-2025 | BP-2024-25-417 | 15/07/2024 | 0 | WBSEDCL | 0.51 | 0 | 0
147 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASHI BHUIANBAR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001702/2022-2023 | 591/W/MMD | 20/03/2023 | 180 | S.S.GHORAI | 21.58 | 13.15 | 62
148 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of PALASIA PWSS. REF CONSUMER ID-204302056, APPLICATION NO-2004723600, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01020/2024-2025 | BP-2024-25-227 | 31/05/2024 | 0 | WBSEDCL | 2.89 | 0 | 0
149 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-I of PALASIA PWSS. (Ref Consumer ID-204205809), APPLICATION NO-2004580481, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03572/2023-2024 | BP-2023-24-606 | 07/02/2024 | 0 | WBSEDCL | 0.64 | 0 | 0
150 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PALASIA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001383/2022-2023 | 2394/W/MMD | 31/12/2022 | 975 | DAS ENTERPRISE | 22.83 | 17.93 | 30
151 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF SAORAPIR PWSS. REF CONSUMER ID-204424028, APPLICATION NO-2004937486, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02969/2024-2025 | C102455575467 | 30/10/2024 | 0 | WBSEDCL | 4.52 | 0 | 0
152 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SAORAPIR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001903/2022-2023 | 802/W/MMD | 24/03/2023 | 180 | RSA ENTERPRISE | 21.59 | 0 | 0
153 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF AMDA PWSS. REF CONSUMER ID-204283803, APPLICATION NO-2004695702, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01152/2024-2025 | BP-2024-25-270 | 12/06/2024 | 0 | WBSEDCL | 4.88 | 0 | 0
154 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKSHI CHAK, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001671/2022-2023 | 571/W/MMD | 20/03/2023 | 895 | DEY ENTERPRISE | 5.99 | 0 | 95
155 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001593/2022-2023 | 475/W/MMD | 20/03/2023 | 180 | S.B.ENTERPRISE | 10.98 | 10.39 | 100
156 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I under Baita water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001015/2022-2023 | 1864/W/MMD | 22/09/2022 | 30 | DEY ENTERPRISE | 11.17 | 9.58 | 0
157 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAITA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002014/2022-2023 | 912/W/MMD | 27/03/2023 | 180 | M/S EMMESS | 11.88 | 7.79 | 40
158 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of MARKHA PWSS. REF CONSUMER ID-204291858, APPLICATION NO-2004701565, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00696/2024-2025 | BP-2024-25-145 | 09/05/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
159 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II OF MARKHA PWSS. REF CONSUMER ID-204383573, APPLICATION NO-2004868760, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02130/2024-2025 | C082449441995 | 02/09/2024 | 0 | WBSEDCL | 6.9 | 0 | 0
160 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MARKHA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002010/2022-2023 | 909/W/MMD | 27/03/2023 | 919 | ORIENTAL ENGINEERING CO. | 27.37 | 0 | 30
161 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Gholshai water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000093/2023-2024 | 1299/W/MMD | 12/05/2023 | 120 | KAMAKSHYA ENTERPRISE | 5.93 | 5.36 | 80
162 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Gholshai water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000094/2023-2024 | 1300/W/MMD | 12/05/2023 | 120 | SUBHRA ENTERPRISE | 5.91 | 5.36 | 100
163 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II , zone-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927974/QUOT/03 DT. 04-10-2024 Application NO- 2004927974 Application type-New connection Consumer Id- 204417444 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02973/2024-2025 | BP-2024-25-779 | 05/11/2024 | 0 | WBSEDCL | 4.94 | 0 | 0
164 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I, ZONE-III Of KANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004927967/QUOT/03 DT. 04-10-2024 Application NO- 2004927967 Application type-New connection Consumer Id- 204417441 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02988/2024-2025 | C112422744521 | 18/11/2024 | 0 | WBSEDCL | 4.99 | 0 | 0
165 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
166 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR BACHRA KUNDU WATER SUPPLY SCHEME, T W NO4, [ AUGMENTATION ] , JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/15572, APPLICATION NO 2004849416, REFERENCE ID 204373204, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02046/2024-2025 | C082441572310 | 29/08/2024 | 0 | WBSEDCL | 3.66 | 0 | 0
167 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BACHHRA KUNDU TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002016/2022-2023 | 914/W/MMD | 27/03/2023 | 549 | GLACIER ENGINEERING CO. | 25.26 | 17.68 | 60
168 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001962/2022-2023 | 861/W/MMD | 27/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 13.43 | 0 | 95
169 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN MANDARMANI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001999/2022-2023 | 901/W/MMD | 27/03/2023 | 1336 | S.S.GHORAI | 12.63 | 0 | 100
170 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PALDUHI PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001992/2022-2023 | 898/W/MMD | 27/03/2023 | 180 | A.S.ENTERPRISE | 12.62 | 0 | 0
171 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN LAKSHYA PWSS WITHIN MAHISHADAL BLOCK UNDER HALDIA SUB-DIVISION OF TAMLUK DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002001/2022-2023 | 903/W/MMD | 27/03/2023 | 180 | RITESH ENTERPRISE | 13.59 | 0 | 0
172 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme TW no.-I, Z-V Ref.-204156069 Application ID-2004521724 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03157/2023-2024 | BP-2023-24-443 | 19/12/2023 | 0 | WBSEDCL | 3.08 | 0 | 0
173 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme T/W-II, Z-V Application-no.-2004522973 Ref.-204157003 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03166/2023-2024 | BP-2023-24-444 | 19/12/2023 | 0 | WBSEDCL | 3 | 0 | 0
174 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-V in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000042/2023-2024 | 1213/W/MMD | 25/04/2023 | 180 | SUBHASIS ROY | 21.6 | 19.98 | 90
175 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I, Zone-II Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732398/QUOT/03/213 DT. 15-05-2024 Application NO- 2004732398 Application type-New connection Consumer Id- 204305458 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01131/2024-2025 | BP-2024-25-247 | 06/06/2024 | 0 | WBSEDCL | 6.88 | 0 | 0
176 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
177 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-IV of Digha western zone under MMD,PHE DTE, Block-Ramnagar-I, DIGHA CCC Application no-2004812623 CON ID-204351922 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01583/2024-2025 | BP-2024-25-457 | 23/07/2024 | 0 | WBSEDCL | 0.92 | 0 | 0
178 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 60
179 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bagmari Water Supply Scheme, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001753/2022-2023 | 632/W/MMD | 20/03/2023 | 180 | JOYSHREE CONCERN | 13.56 | 0.64 | 90
180 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BAGMARI Water Supply Scheme T/W-III, (Ref. ID-204067663) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01870/2023-2024 | W/23-24/223 | 01/09/2023 | 0 | WBSEDCL | 3.34 | 0 | 0
181 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bagmari Accommodate FHTC under Potashpur-II Block within Purba Medinipur District. Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000062/2023-2024 | 1221/W/MMD | 25/04/2023 | 180 | RISHAV ENTERPRISE | 11.94 | 11.49 | 100
182 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at KALINDI and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000268/2024-2025 | 738/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 6.87 | 0.18 | 100
183 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Kasbagola PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001840/2022-2023 | 756/W/MMD | 23/03/2023 | 720 | UNITED TRADERS | 11.34 | 6.7 | 100
184 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MALIHATI AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000078/2023-2024 | 1278/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.54 | 17.39 | 50
185 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BAGCHHARI Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000751/2023-2024 | 2281/W/MMD | 29/08/2023 | 180 | DEBJYOTI BASU | 30.12 | 15.79 | 100
186 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHESHPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002205/2022-2023 | 581/W/MMD | 20/03/2023 | 180 | B.P.TRADING CORPORATION | 25.26 | 16.4 | 90
187 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SHAL DAHARA AND ADJOINING MOUJAS PWWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002208/2022-2023 | 619/W/MMD | 20/03/2023 | 347 | SUJOY RANJAN BHOWMICK | 21.58 | 14.72 | 56
188 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Nilda pwss (Zone-I) (Ref Consumar ID-204312296),Application No-2004743827,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01065/2024-2025 | BP-2024-25-196 | 24/05/2024 | 0 | WBSEDCL | 5.52 | 0 | 0
189 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Nilda pwss (Zone-I) (Ref Consumar ID-204312269),Application No-2004743789,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01066/2024-2025 | BP-2024-25-195 | 24/05/2024 | 0 | WBSEDCL | 3.66 | 0 | 0
190 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipment¿s for NILDA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK Dist Paschim Medinipur UNDER MIDNAPUR DIVISION under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000248/2023-2024 | 1570/W/MMD | 13/07/2023 | 641 | DEBJYOTI BASU | 20.97 | 13.16 | 40
191 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Nilda pwss (Zone-II) (Ref Consumar ID-204310727),Application No-2004741416,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01067/2024-2025 | BP-2024-25-197 | 24/05/2024 | 0 | WBSEDCL | 7.26 | 0 | 0
192 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Nilda pwss (Zone-II) (Ref Consumar ID-204310685),Application No-2004741431,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01068/2024-2025 | BP-2024-25-198 | 24/05/2024 | 0 | WBSEDCL | 9.92 | 0 | 0
193 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NILDA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000031/2023-2024 | 1195/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.64 | 14.12 | 40
194 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Lutunia TW-IV WS Scheme(Ref. ID 2004233628) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00059/2023-2024 | BP-2023-24-6 | 18/04/2023 | 0 | WBSEDCL | 0.46 | 0 | 0
195 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Rejuvenation of Electro-Mechanical components of Chakismilepur PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002125/2022-2023 | 1063/W/MMD | 29/03/2023 | 180 | M/S EMMESS | 11.01 | 8.89 | 55
196 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Srikanta w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707397, Ref ID 204292174) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01073/2024-2025 | BP-2024-25-192 | 24/05/2024 | 0 | WBSEDCL | 8.38 | 0 | 0
197 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SRIKANTHA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001588/2022-2023 | 471/W/MMD | 20/03/2023 | 955 | SOUMEN ELECTRIC | 25.24 | 19.29 | 60
198 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670691/QUOT/03 DT. 05-04-2024 Application NO- 2004670691 Application type-New connection Consumer Id- 204266384 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00298/2024-2025 | BP-2024-25-44 | 18/04/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
199 | Midnapore Mechanical | Digha Sub-Division | ADDITIONAL Quotation Bill for DEULI W/S SCHEME T/W NO- I , RAMNAGRA -II BLOCK . Ref. MEMO No- PBN/NS/36 Dt. 25.04.2024 Application NO- 100000106413 Dt. 25.04.2024 Reference Id- 860299003 REF CONSUMER ID: 204244736 WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00708/2024-2025 | BP-2024-25-147 | 09/05/2024 | 0 | WBSEDCL | 0.84 | 0 | 0
200 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DEULI W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004641295/QUOT/03 DT. 12-03-2024 Application NO- 2004641295 Application type-New connection Consumer Id- 204244736 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04495/2023-2024 | BP-2023-24-863 | 16/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
201 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEULI and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001683/2022-2023 | 564/W/MMD | 20/03/2023 | 1487 | DEY ENTERPRISE | 22.8 | 10.63 | 85
202 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of Dakshin Parshura PWSS. (Ref Consumer ID-204182272) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03339/2023-2024 | BP-2023-24-557 | 16/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
203 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of Daksin parshura PWSS. (Ref Consumer ID-204182381) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03340/2023-2024 | BP-2023-24-558 | 16/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
204 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHIN PARSHURA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000023/2023-2024 | 1186/W/MMD | 25/04/2023 | 643 | RSA ENTERPRISE | 22.89 | 9.97 | 25
205 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Jaganathchak T/W - II Within Khargpur - II Block, Application No - 2004975111 , Ref ID - 204452538 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03156/2024-2025 | C122403006019 | 03/12/2024 | 0 | WBSEDCL | 3.56 | 0 | 0
206 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Jaganathchak T/W - I Within Khargpur - II Block, Application No - 2004975165 , Ref ID - 204452539 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03157/2024-2025 | C122403005259 | 03/12/2024 | 0 | WBSEDCL | 5.31 | 0 | 0
207 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for JAGANATH CHAK AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000384/2023-2024 | 1723/W/MMD | 09/08/2023 | 180 | S.K.ENTERPRISE | 25.26 | 19.8 | 50
208 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Uttar Chandrachak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707437, Ref ID 204292173) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01076/2024-2025 | BP-2024-25-190 | 24/05/2024 | 0 | WBSEDCL | 4.89 | 0 | 0
209 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Uttar chandrachak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004756265, Ref ID 204319510) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01696/2024-2025 | BP-2024-25-485 | 30/07/2024 | 0 | WBSEDCL | 4.37 | 0 | 0
210 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR CHANDRA CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001337/2022-2023 | 2342/W/MMD | 29/12/2022 | 823 | SOUMEN ELECTRIC | 23.68 | 18.26 | 60
211 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-II, T W NO 2, [ SOBHAPUR ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004792617, REFERENCE ID 204341188, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01462/2024-2025 | BP-2024-25-428 | 16/07/2024 | 0 | WBSEDCL | 3.51 | 0 | 0
212 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-I, T W NO 1, [ SUNDRABANDHA ] JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004776663, REFERENCE ID 204331299, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01463/2024-2025 | BP-2024-25-429 | 16/07/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
213 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR AMBA WATER SUPPLY SCHEME, ZONE-III, T W NO I [ SADATPUR ] , JJM WORKS, SCHEME CODE SM/19049, APPLICATION NO 2004887943, REFERENCE ID 204392629, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/02446/2024-2025 | C092445635685 | 30/09/2024 | 0 | WBSEDCL | 6.69 | 0 | 0
214 | Midnapore Mechanical | Kharagpur Sub-Division | Withdrawing the pumping machinaries and installation of Submersible Pump motor set for further extra lowering ( 20 ft ) for each tube well and other works at P H No. 2 of Amba ( Shobhapur ) Water Supply Scheme [ Block Kharagpur-I ] under MMD, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000610/2025-2026 | 1150/MMSD-I | 14/08/2025 | 7 | DEBJYOTI BASU | 0.18 | 0 | 0
215 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Amba (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/001441/2023-2024 | 3097/W/MMD | 29/11/2023 | 906 | DEBJYOTI BASU | 43.72 | 33.57 | 65
216 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Rejuvenation of Electro-Mechanical components of Chotokalshibhanga PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002124/2022-2023 | 1062/W/MMD | 29/03/2023 | 180 | THE GODFATHER TRADING COMPANY | 5.07 | 5.07 | 60
217 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SHILARAJNAGAR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/18585, APPLICATION NO 2004628032, REFERENCE ID 204234631, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04401/2023-2024 | BP-2023-24-840 | 14/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
218 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SHILARAJNAGAR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/18585, APPLICATION NO 2004627434, REFERENCE ID 204234630, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04402/2023-2024 | BP-2023-24-841 | 14/03/2024 | 0 | WBSEDCL | 4.46 | 0 | 0
219 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Shilarajnagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000391/2023-2024 | 1730/W/MMD | 09/08/2023 | 570 | ORIENTAL ENGINEERING CO. | 27.35 | 16.21 | 55
220 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0
221 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BATIPUR AND ITS ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002039/2022-2023 | 947/W/MMD | 28/03/2023 | 180 | A.S.ENTERPRISE | 21.57 | 0 | 0
222 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of ERENDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792956/QUOT/03/379 DT. 02-07-2024 Application NO- 2004792956 Application type-New connection Consumer Id- 204345868 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01701/2024-2025 | BP-2024-25-494 | 29/07/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
223 | Midnapore Mechanical | Digha Sub-Division | Erenda W/S scheme PH-I Application no.-2004523042 ref.-204156895 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03192/2023-2024 | BP-2023-24-482 | 27/12/2023 | 0 | WBSEDCL | 4.3 | 0 | 0
224 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ERENDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001356/2022-2023 | 2367/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 10.96 | 45
225 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626691/QUOT/03/1613 DT. 01/03/2024 Application NO- 2004626691 Application type-New connection Consumer Id- 204233925 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04504/2023-2024 | BP-2023-24-857 | 16/03/2024 | 0 | WBSEDCL | 4.05 | 0 | 0
226 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TAJPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, BALIGHAI C.C.C. Ref. Memo No- 2004626737/QUOT/03/1611 DT. 01-03-2024 Application NO- 2004626737 Application type-New connection Consumer Id- 204233924 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04505/2023-2024 | BP-2023-24-856 | 16/03/2024 | 0 | WBSEDCL | 4.66 | 0 | 0
227 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAJPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001587/2022-2023 | 470/W/MMD | 20/03/2023 | 744 | SOUMEN ELECTRIC | 25.24 | 23.66 | 100
228 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashinathpur & its adjoining mouzas under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000744/2023-2024 | 2288/W/MMD | 29/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0
229 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Bhagabanpur PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001295/2022-2023 | 2298/W/MMD | 29/12/2022 | 1094 | SUBHAM ENTERPRISE | 22.79 | 10.73 | 40
230 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000389/2023-2024 | 1728/W/MMD | 09/08/2023 | 180 | SUBODH KUMAR BANIK | 27.3 | 4.88 | 51
231 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-II) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000392/2023-2024 | 1731/W/MMD | 09/08/2023 | 180 | M/S B.M. ELECTRICAL | 22.89 | 0 | 50
232 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Goura (Zone-I, II, III & IV) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-III) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000395/2023-2024 | 1734/W/MMD | 09/08/2023 | 180 | KAMAKSHYA ENTERPRISE | 11.98 | 0 | 0
233 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0
234 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
235 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Harasankarpur Khamarchak W/S scheme T/W-II Application No.-2004586186, Ref ID.-204209423 Date of quotation .-06/02/2024 New connection. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03701/2023-2024 | BP-2023-24-683 | 15/02/2024 | 0 | WBSEDCL | 4.35 | 0 | 0
236 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Harasankar Khamarchak H/W Site Block=Sahid Matangini Application No=2004626478 Reference ID=204233282 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04340/2023-2024 | BP-2023-24-803 | 11/03/2024 | 0 | WBSEDCL | 4.36 | 0 | 0
237 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR KHAMARCHAK AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001693/2022-2023 | 621/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.81 | 21.15 | 35
238 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Kiarana w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004686357, Con ID 204277586) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00645/2024-2025 | BP-2024-25-110 | 06/05/2024 | 0 | WBSEDCL | 13.89 | 0 | 0
239 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Kiarana w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.(App No.- 2004620100, Ref ID 204229479) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04503/2023-2024 | BP-2023-24-860 | 16/03/2024 | 0 | WBSEDCL | 4.37 | 0 | 0
240 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIARANA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001415/2022-2023 | 2426/W/MMD | 31/12/2022 | 670 | DEY ENTERPRISE | 23.7 | 19.45 | 100
241 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER CHANDRAKONA - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICTunder JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000367/2023-2024 | 1693/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 49.92 | 0 | 80
242 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of GOPALBANDH PWSS. REF CONSUMER ID-204269014, APPLICATION NO-2004675316 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00313/2024-2025 | BP-2024-25-72 | 24/04/2024 | 0 | WBSEDCL | 9.56 | 0 | 0
243 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of GOPALBANDH PWSS. REF CONSUMER ID-204269029, APPLICATION NO-2004675306 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00318/2024-2025 | BP-2024-25-71 | 24/04/2024 | 0 | WBSEDCL | 0.29 | 0 | 0
244 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOPAL BANDH AND ITS ADJOINING MOUZAS WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000343/2023-2024 | 1683/W/MMD | 04/08/2023 | 636 | ALPHA ENTERPRISE | 25.24 | 18.17 | 20
245 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of KHARIGERIA PWSS. REF CONSUMER ID-204211927, APPLICATION NO-2004590188 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/03744/2023-2024 | BP-2023-24-686 | 16/02/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
246 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of KHARIGERIA PWSS. REF CONSUMER ID-204212338, APPLICATION NO-2004593715, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/03745/2023-2024 | BP-2023-24-685 | 16/02/2024 | 0 | WBSEDCL | 4.92 | 0 | 0
247 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARI GERYA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000361/2023-2024 | 1689/W/MMD | 04/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 25.25 | 0 | 0
248 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 181 | M/S BIKASH DE | 3.69 | 0 | 0
249 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.14 | 50
250 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Zone-II Pump House-II under Bhemwa water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001477/2022-2023 | 215/W/MMD | 10/02/2023 | 180 | DEBJYOTI BASU | 11.23 | 10.45 | 100
251 | Midnapore Mechanical | Kharagpur Sub-Division | Service connection charge of WBSEDCL at Talda, Sabang | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001028/2021-2022 | 2003774985/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
252 | Midnapore Mechanical | Kharagpur Sub-Division | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Talda water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001137/2021-2022 | 2511/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 0 | 100
253 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Talda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001176/2021-2022 | 122/W/MMD | 24/01/2022 | 120 | S.S.GHORAI | 6.55 | 5.4 | 0
254 | Midnapore Mechanical | Kharagpur Sub-Division | Service connection charges of WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001118/2022-2023 | BP-2021-22-57 | 22/04/2022 | 0 | WBSEDCL | 1.15 | 0 | 0
255 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Talda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte.(w/O No. 122/W/MMD dt. 24-01-2022) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001764/2022-2023 | BP-2022-23-42 | 12/08/2022 | 0 | S.S.GHORAI | 0.71 | 0 | 0
256 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of Pumping Machinery and other electromechanical equipment at newly sunk T/W at Talda, Block- Sabang under Ground bored Mini Piped W/S Scheme Dist- Paschim Medinipur under MMD,P.H.E.Dte.(W/O No. 122/W/MMD dt. 24-01-2022)(T.No. 1206 of 21-22) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001769/2022-2023 | BP-2022-23-36 | 12/08/2022 | 0 | S.S.GHORAI | 0.44 | 0 | 0
257 | Midnapore Mechanical | Kharagpur Sub-Division | Service connection charge of WBSEDCL at Dantarda, Batitaki, Chandkuri | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001029/2021-2022 | 2003774979/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
258 | Midnapore Mechanical | Kharagpur Sub-Division | Service connection charge of WBSEDCL at Nowgan, Sabang | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001031/2021-2022 | 2003774953/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
259 | Midnapore Mechanical | Kharagpur Sub-Division | Service connection charge of WBSEDCL at Now gan, Sabang | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001035/2021-2022 | 2003774945/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
260 | Midnapore Mechanical | Kharagpur Sub-Division | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Dantardabatitaki water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001130/2021-2022 | 2505/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 100
261 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Dantardabatitaki, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001174/2021-2022 | 120/W/MMD | 24/01/2022 | 120 | ECO ENTERPRISE | 6.51 | 3.87 | 0
262 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for service connection charges of WBSEDCL at Nilot Bhemua | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001520/2021-2022 | 2003855203/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0.13 | 0
263 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well of Paschim Pathari to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | ORD/000131/2023-2024 | 1351/W/MMD | 24/05/2023 | 782 | DEBJYOTI BASU | 8.07 | 7.35 | 92
264 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 4 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001128/2021-2022 | 2510/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 100
265 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 3 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001129/2021-2022 | 2508/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 100
266 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001131/2021-2022 | 2506/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 100
267 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Chaulkuri water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001134/2021-2022 | 2504/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 100
268 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001190/2021-2022 | 149/W/MMD | 31/01/2022 | 120 | BUSR ENGINEERING | 6.54 | 6.54 | 0
269 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001191/2021-2022 | 150/W/MMD | 31/01/2022 | 120 | KAMAKSHYA ENTERPRISE | 6.59 | 6.48 | 0
270 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -III at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001192/2021-2022 | 151/W/MMD | 31/01/2022 | 120 | MANORANJAN DEY | 6.55 | 6.42 | 0
271 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -IV at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001193/2021-2022 | 152/W/MMD | 31/01/2022 | 120 | JAGANNATH ENTERPRISE | 6.51 | 2.63 | 0
272 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -IV at Chaulkuri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-152/W/MMD, DT.-31/01/2022) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/005603/2021-2022 | BP-2021-22-119 | 17/03/2022 | 0 | JAGANNATH ENTERPRISE | 3.87 | 0 | 0
273 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation bill of WBSEDCL for application no 2003798482/2003798478/2003798131/2003798158/2003798182/2003798165 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/005612/2021-2022 | BP-2021-22-72 | 07/03/2022 | 0 | WBSEDCL | 0.76 | 0 | 0
274 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation for Amjore PWSS Tube Well-II WS Scheme (Ref. ID 203928706) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00399/2022-2023 | Bp-2022-23-148 | 24/03/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
275 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation for Amjore PWSS Tube Well-I WS Scheme (Ref. ID 203928705) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00401/2022-2023 | BP-2022-23-149 | 24/03/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
276 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Amjor Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001374/2022-2023 | 2385/W/MMD | 31/12/2022 | 180 | ABHIJIT BASU | 22.88 | 22.68 | 100
277 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS under Contai-II Block (Phase-II) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002025/2022-2023 | 884/W/MMD | 27/03/2023 | 180 | UTTAM KUMAR CHATTERJEE | 12.39 | 0 | 0
278 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Baichberya PWSS Tube Well- III (Ref. ID - 203911567) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00159/2022-2023 | BP-2022-23-129 | 13/03/2023 | 0 | WBSEDCL | 8.28 | 0 | 0
279 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Qoutation bill for T/W -IV of Baichberia water supply scheme | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/03565/2023-2024 | BP-2023-24-608 | 07/02/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
280 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baichberia Water Supply Scheme in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000046/2023-2024 | 1219/W/MMD | 25/04/2023 | 860 | BHABANI PRASAD MANNA | 27.19 | 12.79 | 50
281 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well - II of Baichberiya water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001137/2022-2023 | 2118/W/MMD | 28/11/2022 | 458 | RITESH ENTERPRISE | 12.17 | 11.3 | 90
282 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation for New Service connection at Additional TW - III of Kapasda Water Supply Scheme (Ref. Id-203959877) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00073/2023-2024 | BP-2023-24-39 | 04/05/2023 | 0 | WBSEDCL | 4.45 | 0 | 0
283 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation for New Service connection charges of Additional TW IV of Kapasda WS Scheme (Ref. ID - 203959882) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00074/2023-2024 | BP-2023-24-32 | 04/05/2023 | 0 | WBSEDCL | 2.08 | 0 | 0
284 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments Rejuvenation of Ground water based piped water supply scheme for P/H-IV of Kapasda (Part) to accommodate FHTC under JJM under Sabang Block in Paschim Medinipur District under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000125/2023-2024 | 1345/W/MMD | 24/05/2023 | 180 | M/S EMMESS | 11.88 | 11.13 | 100
285 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped water supply scheme for PH No III of Kapasda Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE. TSM009952 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000234/2023-2024 | 600/MMSD-I | 05/06/2023 | 15 | DEBKUMAR BASU | 5.76 | 0 | 0
286 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001305/2022-2023 | 2307/W/MMD | 29/12/2022 | 180 | DEBKUMAR BASU | 10.78 | 9.07 | 100
287 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
288 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0.2 | 100
289 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.09 | 100
290 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Gourangapur/Chapbasan PWSS Tube Well-I in connection Tamluk CCC (2004170186) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00054/2022-2023 |  | 09/02/2023 | 0 | WBSEDCL | 4.58 | 0 | 0
291 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Chapbasan PWSS Tube Well-II in connection Tamluk CCC (2004150121) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00055/2022-2023 |  | 09/02/2023 | 0 | WBSEDCL | 4.16 | 0 | 0
292 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme Block - Tamluk under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001468/2022-2023 | 206/W/MMD | 10/02/2023 | 180 | UNITED TRADERS | 27.3 | 26.8 | 60
293 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-III of Keshpur water supply scheme.( Consumer ID-204052921.) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01866/2023-2024 | BP-2023-24-232 | 07/09/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
294 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No- IV of Keshpur water supply scheme.(Conumer ID-204057049) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01867/2023-2024 | BP-2023-24-230 | 07/09/2023 | 0 | WBSEDCL | 2.76 | 0 | 0
295 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw no-V of Keshpur water supply scheme.(Consumer ID-204051457) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01868/2023-2024 | BP-2023-24-231 | 07/09/2023 | 0 | WBSEDCL | 2.67 | 0 | 0
296 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Additional quotation for effective new service connection at KESHPUR(Near Auditorium) in modified route. ( Augmentation of Keshpur PWSS) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03225/2023-2024 | BP-2023-24-480 | 27/12/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
297 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECRTIC QUOTATION BILL FOR TW NO-IV OF KESHPUR PWSS. (Ref Consumer ID-204189500) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03444/2023-2024 |  | 15/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0
298 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0
299 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001293/2022-2023 | 2296/W/MMD | 29/12/2022 | 180 | P.K.ENGINEERING | 22.88 | 18.2 | 20
300 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 100
301 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 181 | M/S BIKASH DE | 3.69 | 0 | 0
302 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.14 | 50
303 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 100
304 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-I, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000077/2023-2024 | 1279/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 25.14 | 0 | 0
305 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Khasbazar (Part) to accommodate FHTC under Jal Sapno Mission under Debra block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002004/2022-2023 | 875/W/MMD | 27/03/2023 | 180 | RADHARANI ENTERPRISE | 5.98 | 5.87 | 100
306 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme Block - Nandakumar under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001964/2022-2023 | 863/W/MMD | 27/03/2023 | 180 | PRANAB KUMAR DAS | 13.47 | 0 | 70
307 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920/QUOT/03 DT. 17-05-2024 Application NO- LY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738920 Application type-New connection Consumer Id- 204309716 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01096/2024-2025 | BP-2024-25-225 | 31/05/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
308 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MUKUNDAPUR and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001638/2022-2023 | 518/W/MMD | 20/03/2023 | 180 | RMD TRADING | 22.76 | 8.42 | 85
309 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-II of Joynagar w/s scheme,Block-Sutahata under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application No.-2004818887 Application type-new connection Reference ID-204355766 Quotation Date-12/7/2024 Quotation Due Date-14/7/2025 Contract Demand-8344 W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01695/2024-2025 | BP-2024-25-495 | 29/07/2024 | 0 | WBSEDCL | 4.61 | 0 | 0
310 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-I of Joynagar w/s scheme Block-sutahata in the Dist. of Purba Medinipur under MMD ,PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004839280 Application type-new connection Reference ID-204366525 Quotation Date-26/07/2024 Quotation due Date-28/07/2025 Contract Demand-8344W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01858/2024-2025 | C082408702219 | 07/08/2024 | 0 | WBSEDCL | 7.89 | 0 | 0
311 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAYNAGAR and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001586/2022-2023 | 469/W/MMD | 20/03/2023 | 742 | BHABANI PRASAD MANNA | 23.7 | 0 | 0
312 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-I, Part-A, Zone-I (Ref. ID-204050258) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01686/2023-2024 | BP-2023-24-164 | 04/08/2023 | 0 | WBSEDCL | 2.34 | 0 | 0
313 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for CONTAI S.A.Rej. Water Supply Scheme T/W-II, Part-A, Zone-I (Ref. ID-204050190) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01687/2023-2024 | BP-2023-24-163 | 04/08/2023 | 0 | WBSEDCL | 2.48 | 0 | 0
314 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-A),under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000158/2023-2024 | 1393/W/MMD | 01/06/2023 | 180 | P.K.ENGINEERING | 27.18 | 10.43 | 30
315 | Midnapore Mechanical | Contai Sub-Division | Electric Quotiaton for Madhakhali Water Supply Scheme Zone-II, T/W-I (Ref. ID-204004293) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00381/2023-2024 | BP-2023-24-67 | 06/06/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
316 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MADHAKHALI Water Supply Scheme Z-II, T/W-II (Ref. ID-204049127 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01632/2023-2024 | BP-2023-24-138 | 27/07/2023 | 0 | WBSEDCL | 2.39 | 0 | 0
317 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of MADHAKHALI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004826940/QUOT/03 DT. 25-07-2024 Application NO- 2004826940 Application type-New connection Consumer Id- 204360840 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01887/2024-2025 | BP-2024-25-551 | 08/08/2024 | 0 | WBSEDCL | 3.35 | 0 | 0
318 | Midnapore Mechanical | Contai Sub-Division | Madhakhali W/S scheme PH-III, Zone-I Application no-2004427213 Ref.-204078346 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03236/2023-2024 | BP-2023-24-501 | 05/01/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
319 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I of Zone - I Madhakhali water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001013/2022-2023 | 1862/W/MMD | 22/09/2022 | 120 | M/S B.M. ELECTRICAL | 11.68 | 10.76 | 70
320 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Madhakhali piped water supply scheme, (Zone I), Block ¿ Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001515/2022-2023 | 359/W/MMD | 09/03/2023 | 180 | AHALYA ENGINEERING WORKS | 27.16 | 25.59 | 20
321 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
322 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service Connection charges of WBSEDCL for Additional T/W-III of Zone-II of Chandkuri W/S Scheme (Consumer No. 2004156140) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00047/2022-2023 | BP-2022-23-92 | 04/01/2023 | 0 | WBSEDCL | 2.41 | 0 | 0
323 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service Connection charges of WBSEDCL for T/W-III of Zone-I of Chandkuri W/S Scheme (Consumer No. 2004156096) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00048/2022-2023 | BP-2022-23-93 | 10/01/2023 | 0 | WBSEDCL | 2.2 | 0 | 0
324 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well-III, Zone-I of Chandkuri to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000129/2023-2024 | 1349/W/MMD | 24/05/2023 | 180 | M/S EMMESS | 11.88 | 11.67 | 100
325 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Replacement and upgradation work of Voltage Stabilizer for Tube well No. III of Chandkuri Zone I Water Supply Scheme Block Sabang under MMD, PHE Dte. Dist.- Paschim Medinipur. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001301/2023-2024 | 1226/MMSD-I | 03/10/2023 | 30 | BALAJI CONSTRUCTION | 3.6 | 3.6 | 100
326 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001307/2022-2023 | 2309/W/MMD | 29/12/2022 | 180 | BALAJI CONSTRUCTION | 10.79 | 7.88 | 100
327 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
328 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0.31 | 100
329 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.09 | 100
330 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for New connection Jamitya water supply scheme Tube Well-II. Quotation Bill Date.-01/04/2024 Block-Kolaghat. Kolaghat CCC Application No.-2004662461 Ref no.-204260852 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00254/2024-2025 | BP-2024-25-27 | 15/04/2024 | 0 | WBSEDCL | 10.19 | 0 | 0
331 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New service connection at Jamitya water supply scheme H/W site Kolaghat CCC Block- Kolaghat Application No.-2004803550 Consumer ID.-204346513 Date.-02-07-2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01469/2024-2025 | BP-2024-25-416 | 15/07/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
332 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004812325/QUOT/03/814 DT. 09-07-2024 Application NO- 2004812325 Application type-New connection Consumer Id- 204352202 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01587/2024-2025 | BP-2024-25-450 | 23/07/2024 | 0 | WBSEDCL | 6.77 | 0 | 0
333 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of JERTHAN W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847107/QUOT/03/1183 DT. 13-08-2024 Application NO- 2004847107 Application type-New connection Consumer Id- 204372867 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02121/2024-2025 | C082448274884 | 02/09/2024 | 0 | WBSEDCL | 10.86 | 0 | 0
334 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JERTHAN and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001371/2022-2023 | 2382/W/MMD | 31/12/2022 | 180 | ECO ENTERPRISE | 25.26 | 13.35 | 40
335 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MALIKPUR and ADJOINING MOUJAS, Block Potashpur II District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001327/2022-2023 | 2329/W/MMD | 29/12/2022 | 180 | DAS ENTERPRISE | 23.64 | 0 | 0
336 | Midnapore Mechanical | Haldia Sub-Division | Quotation Bill for new service connection at TW-I & II of Hariballavpur w/s scheme under MMD,PHE, Dte. Block-Sutahata,Chaitanyapur C.C.C Memo No.-2004632082/Quot/03 Date-05/03/2024 Application No.-2004632082 Application Type-New Connection Reference ID-204237950 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04382/2023-2024 | BP-2023-24-826 | 13/03/2024 | 0 | WBSEDCL | 13.11 | 0 | 0
337 | Midnapore Mechanical | Haldia Sub-Division | Quotation Bill for New Service Connection at PH-II of Hariballavpur pwss,Block-Sutahata, under MMD,PHE Dte. Name of C.C.C.- Chaitanyapur Application no.-2004644794 Application Type-New Connection Quotation Date-15/03/2024 Quotation Due Date-17/03/2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04750/2023-2024 | BP-2023-24-920 | 28/03/2024 | 0 | WBSEDCL | 0.28 | 0 | 0
338 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARIBALLABHPUR and ADJOINING MOUJAS, Block Sutahata District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001328/2022-2023 | 2330/W/MMD | 29/12/2022 | 180 | MAHADEV ENTERPRISE | 23.65 | 0 | 80
339 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835493 Application type-New connection Consumer Id- 204365530 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02118/2024-2025 | C082448216760 | 02/09/2024 | 0 | WBSEDCL | 7.35 | 0 | 0
340 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PURBA RADHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Application NO- 2004835536 Application type-New connection Consumer Id- 204365524 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02120/2024-2025 | C082448207124 | 02/09/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
341 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA RADHAPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001334/2022-2023 | 2339/W/MMD | 29/12/2022 | 180 | MAHADEV ENTERPRISE | 23.63 | 0 | 0
342 | Midnapore Mechanical | Contai Sub-Division | Goyalda W/S scheme, TW-II, site tarat(near Tower) application no-2004515995 id-204153075 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03148/2023-2024 | BP-2023-24-456 | 21/12/2023 | 0 | WBSEDCL | 3.23 | 0 | 0
343 | Midnapore Mechanical | Contai Sub-Division | Goyalda W/S scheme, TW-I, site tarat(near swasan) application no-2004515964 id-204153046 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03149/2023-2024 | BP-2023-24-457 | 21/12/2023 | 0 | WBSEDCL | 3.74 | 0 | 0
344 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOYALDA and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001319/2022-2023 | 2321/W/MMD | 29/12/2022 | 824 | S.S.GHORAI | 22.81 | 17.99 | 100
345 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818449/QUOT/03 DT. 12-07-2024 Application NO- 2004818449 Application type-New connection Consumer Id- 204355505 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01889/2024-2025 | BP-2024-25-552 | 08/08/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
346 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of ABASBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004940081/QUOT/03 DT. 24-10-2024 Application NO- 2004940081 Application type-New connection CONSUMER ID: 204426079 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03001/2024-2025 | C112423541900 | 19/11/2024 | 0 | WBSEDCL | 14.89 | 0 | 0
347 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ABAS BERYA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001341/2022-2023 | 2346/W/MMD | 29/12/2022 | 180 | EASTERN INDIA SALES & SERVICE | 25.25 | 0 | 0
348 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation for Natshallakhya PWSS Tube Well- III, Zone-I in connection Mukundapur CCC (2004197468) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00160/2022-2023 | BP-2022-23-128 | 13/03/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
349 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001473/2022-2023 | 211/W/MMD | 10/02/2023 | 180 | S.B.ENTERPRISE | 13.65 | 13.41 | 75
350 | Midnapore Mechanical | Haldia Sub-Division | Replacement of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Tube Well-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur Districtunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002727/2023-2024 | 1072/W/MMD | 14/03/2024 | 180 | ECO ENTERPRISE | 10.85 | 10.61 | 90
351 | Midnapore Mechanical | Haldia Sub-Division | Quotation for net billing meter at Betkundu w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (Con ID - 222016853 & Application No.- 2004450537) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03722/2023-2024 | BP-2023-24-674 | 15/02/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
352 | Midnapore Mechanical | Haldia Sub-Division | QUATATION BILL FOR BETKUNDU Water Supply scheme Tube Well no.-III Mahishadal CCC Application No.-2004625358 Ref ID.-204232822 Block-Mahishadal | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04573/2023-2024 | BP-2023-24-889 | 22/03/2024 | 0 | WBSEDCL | 4.84 | 0 | 0
353 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground water Based Betkundu Water Supply Scheme, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001928/2022-2023 | 847/W/MMD | 24/03/2023 | 896 | MAA BHABOTARINE ENTERPRISE | 27.18 | 0 | 60
354 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769741/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769741 Application type-New connection Consumer Id- 204327215 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01281/2024-2025 | BP-2024-25-336 | 25/06/2024 | 0 | WBSEDCL | 5 | 0 | 0
355 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARAHAT W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769769/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/170 DT. 10-06-2024 Application NO- 2004769769 Application type-New connection Consumer Id- 204327222 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01282/2024-2025 | BP-2024-25-335 | 25/06/2024 | 0 | WBSEDCL | 1.2 | 0 | 0
356 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAHAT and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001414/2022-2023 | 2425/W/MMD | 31/12/2022 | 882 | DEY ENTERPRISE | 22.8 | 0 | 85
357 | Midnapore Mechanical | Digha Sub-Division | PADIMA W/S SCHEME T/W-I Application No.-2004566513 Ref.-204194520 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03532/2023-2024 | BP-2023-24-613 | 07/02/2024 | 0 | WBSEDCL | 6.31 | 0 | 0
358 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PADIMA W/S Scheme under MMD, PHE, Dte. Block- Ramnagar-I, DIGHA C.C.C. Ref. Memo No- 2004626606/QUOT/03 DT. 04-03-2024 Application NO- 2004626606 Application type-New connection CONSUMMER ID- 204233354 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04338/2023-2024 | BP-2023-24-804 | 11/03/2024 | 0 | WBSEDCL | 7.74 | 0 | 0
359 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PADIMA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001665/2022-2023 | 548/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.62 | 19.87 | 100
360 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
361 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOTHRA Water Supply Scheme , (Ref. ID-204075850) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02187/2023-2024 | BP-2023-24-238 | 12/09/2023 | 0 | WBSEDCL | 3.98 | 0 | 0
362 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Gathra W/S scheme H/W site. Application No.-100000094421 Ref.-860286461 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03303/2023-2024 | BP-2023-24-544 | 15/01/2024 | 0 | WBSEDCL | 0.34 | 0 | 0
363 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Gathra W/S Scheme T/W-II Application No=2005003708 Reference ID=204470377 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03670/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
364 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GATHRA and ADJOINING MOUJAS, Block Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001355/2022-2023 | 2366/W/MMD | 31/12/2022 | 180 | ABHIJIT BASU | 23.69 | 11.08 | 35
365 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotiaton for New S.C. Sabra Water Supply Scheme PH-I (Ref. ID-203964025) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00066/2023-2024 | BP-2023-24-8 | 27/04/2023 | 0 | WBSEDCL | 0.58 | 0 | 0
366 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-I (Ref. ID-860267633) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00067/2023-2024 | BP-2023-24-9 | 27/04/2023 | 0 | WBSEDCL | 2.19 | 0 | 0
367 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotiaton for New S.C.Sabra Water Supply Scheme PH-II (Ref. ID-203964023) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00068/2023-2024 | BP-2023-24-10 | 27/04/2023 | 0 | WBSEDCL | 0.58 | 0 | 0
368 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-II (Ref. ID-860267634) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00069/2023-2024 | BP-2023-24-11 | 27/04/2023 | 0 | WBSEDCL | 2.23 | 0 | 0
369 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotiaton for New S.C. Sabra Water Supply Scheme PH-III (Ref. ID-203964024) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00070/2023-2024 | BP-2023-24-12 | 27/04/2023 | 0 | WBSEDCL | 0.58 | 0 | 0
370 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotiaton for New S.C (Infra. Cost.). Sabra Water Supply Scheme PH-III (Ref. ID-860267635) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00071/2023-2024 | BP-2023-24-13 | 27/04/2023 | 0 | WBSEDCL | 3.51 | 0 | 0
371 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Extra work due to way leave at Sabra T.W.No-III | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00579/2023-2024 | BP-2023-24-131 | 19/07/2023 | 0 | WBSEDCL | 0.95 | 0 | 0
372 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SABRA AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000002/2023-2024 | 1104/W/MMD | 05/04/2023 | 180 | P.K.ENGINEERING | 27.37 | 27.02 | 100
373 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sabra Piped Water Supply Scheme.under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000019/2023-2024 | 1157/W/MMD | 17/04/2023 | 180 | PS & ASSOCIATES | 27.3 | 13.37 | 60
374 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and delivery LED Smart Bright street light fixture and other related works at P H of Sabra and other water supply scheme under Midnapur Mechanical Division , P.H.E.Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000060/2025-2026 | 663/MMSD-I | 13/05/2025 | 10 | P.K.ENGINEERING | 3 | 0 | 0
375 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
376 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001915/2022-2023 | 818/W/MMD | 24/03/2023 | 180 | EMCON | 11.83 | 11 | 100
377 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone I Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002728/2023-2024 | 1077/W/MMD | 15/03/2024 | 180 | SOUMEN ELECTRIC | 24.86 | 8.41 | 35
378 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for URDHABMAL Water Supply Scheme T/W-I, (Ref. ID-204076039) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02197/2023-2024 | BP-2023-24-244 | 12/09/2023 | 0 | WBSEDCL | 15.45 | 0 | 0
379 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for URDHABMAL Water Supply Scheme T/W-II, (Ref. ID-204076027) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02199/2023-2024 | BP-2023-24-243 | 12/09/2023 | 0 | WBSEDCL | 3.36 | 0 | 0
380 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for URDDHABMAL and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001686/2022-2023 | 562/W/MMD | 20/03/2023 | 895 | M/S B.M. ELECTRICAL | 22.81 | 16.19 | 70
381 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
382 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
383 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of Panchbajari W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601878/QUOT/03 DT. 15-02-2024 Quotation due date-14.02.2025 Application NO- 2004601878 Application type-New connection Reference Id- 204217833 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04263/2023-2024 | BP-2023-24-793 | 06/03/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
384 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
385 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Tlkhoja w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004685657, Con ID 204277587) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00646/2024-2025 | BP-2024-25-123 | 05/05/2024 | 0 | WBSEDCL | 9.91 | 0 | 0
386 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Tilkhoja w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608980, Ref ID-204222618) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04498/2023-2024 | BP-2023-24-852 | 16/03/2024 | 0 | WBSEDCL | 2.97 | 0 | 0
387 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Tilkhoja and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001322/2022-2023 | 2324/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 0 | 60
388 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new application at Natshallakhya Zone I PH IV in the district of Purba Medinipur under MMD PHE Dte. ( App No. 20046922155, Ref ID 204281189) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01077/2024-2025 | BP-2024-25-191 | 24/05/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
389 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-I Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001935/2022-2023 | 854/W/MMD | 24/03/2023 | 180 | SUBHASIS ROY | 27.33 | 0 | 0
390 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAKALSABAKARAM PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001298/2022-2023 | 2301/W/MMD | 29/12/2022 | 972 | ECO ENTERPRISE | 23.01 | 14.89 | 50
391 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Baraghar pwss (Ref Consumar ID-204444966),Application No-2004963063,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03032/2024-2025 | C112429694917 | 25/11/2024 | 0 | WBSEDCL | 5.52 | 0 | 0
392 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Baraghar PWSS, BLOCK - DEBRA Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001301/2022-2023 | 2303/W/MMD | 29/12/2022 | 855 | DEBJYOTI BASU | 22.79 | 14.23 | 40
393 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Gobindapur PWSS TW - II Under Narayangarh Block Application No - 2004845772 , Ref ID - 204370310 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02442/2024-2025 | C092443180598 | 27/09/2024 | 0 | WBSEDCL | 4.92 | 0 | 0
394 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Gobindapur PWSS TW - I Under Narayangarh Block Application No - 2004845774 , Ref ID - 204370304 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02447/2024-2025 | C092443178985 | 27/09/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
395 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
396 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at gama PWSS T/W - II under Narayangarh block , application no - 2004739453 , ref no - 204309708 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01078/2024-2025 | BP-2024-25-231 | 04/06/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
397 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at gama PWSS T/W - I under Narayangarh block , application no - 2004739405 , ref no - 204309707 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01123/2024-2025 | BP-2024-25-232 | 04/06/2024 | 0 | WBSEDCL | 3.32 | 0 | 0
398 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
399 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Jalimanda pwss (Ref Consumar ID-204444967),Application No-2004963152,Application Type-New Connection,Name of ccc-Balaichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03029/2024-2025 | C112429710144 | 25/11/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
400 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for JALIMANDA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001655/2022-2023 | 576/W/MMD | 20/03/2023 | 926 | ABHIJIT MUKHERJEE | 25.24 | 18.15 | 46
401 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation bill for Tw no-III of Gobardhanpur water supply scheme.(Ref consumer ID-204049772) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02683/2023-2024 | BP-2023-24-274 | 12/10/2023 | 0 | WBSEDCL | 4.65 | 0 | 0
402 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation bill for Tw No-IV of Gobardhanpur water supply scheme (Ref Consumer ID-204049773) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02685/2023-2024 | BP-2023-24-273 | 12/10/2023 | 0 | WBSEDCL | 2.71 | 0 | 0
403 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GOBARDHANPUR TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER PINGLA BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001595/2022-2023 | 478/W/MMD | 20/03/2023 | 721 | DIPALI CONSTRUCTION | 22.98 | 10.65 | 35
404 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of Submersible pumping machineries and other allied electromechanical works at Newly sunk Tube well (Relacement) at Pump House-2 under Gobardhanpur water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001865/2024-2025 | 788/W/MMD | 24/02/2025 | 180 | M/S. SAJAHAN CHOWDHURY | 14.21 | 0 | 0
405 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | New PHE connection at Tw No-III of Palashi PWSS. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03228/2023-2024 | BP-2023-24-543 | 11/01/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
406 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring at Tube Well-III of Palashi Water Supply Scheme (Block- Debra) under MMD, PHE Dte., Dist. Paschim Medinipur. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000495/2023-2024 | 1851/W/MMD | 22/08/2023 | 180 | RELIABLE CONSTRUCTIONS | 12.83 | 12.28 | 100
407 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF BELDA PWSS. REF CONSUMER ID-204412272, APPLICATION NO-2004920291, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02970/2024-2025 | C102455561727 | 30/10/2024 | 0 | WBSEDCL | 6.26 | 0 | 0
408 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TRILOCHANPUR PWSS Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001296/2022-2023 | 2299/W/MMD | 29/12/2022 | 180 | RITESH ENTERPRISE | 23.01 | 15.96 | 55
409 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II OF JHETAJAMBONI PWSS. REF CONSUMER ID-204383571, APPLICATION NO-2004868778, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02116/2024-2025 | C082449438485 | 02/09/2024 | 0 | WBSEDCL | 6.32 | 0 | 0
410 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of JHETA JAMBONI PWSS. REF CONSUMER ID-204240654, APPLICATION NO-2004634470, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04479/2023-2024 | BP-2023-24-849 | 14/03/2024 | 0 | WBSEDCL | 2.9 | 0 | 0
411 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for JHETA JAMBONI PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000012/2023-2024 | 1128/W/MMD | 12/04/2023 | 731 | A-NIK & CO. | 27.37 | 6.12 | 20
412 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-I, Irhpala water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000156/2022-2023 | 2003978653 | 06/07/2022 | 365 | WBSEDCL | 0.46 | 0 | 0
413 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-II, Irhpala water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000157/2022-2023 | 2003978660 | 06/07/2022 | 365 | WBSEDCL | 0.46 | 0 | 0
414 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-I under Irpala water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000222/2022-2023 | 1651/W/MMD | 12/08/2022 | 120 | DEBJYOTI BASU | 11.77 | 8.58 | 100
415 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-II under Irpala water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000223/2022-2023 | 1652/W/MMD | 12/08/2022 | 120 | M/S. SAJAHAN CHOWDHURY | 11.79 | 11.58 | 100
416 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-II, Irhpala water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001781/2022-2023 | BP-2022-23-25 | 08/08/2022 | 0 | WBSEDCL | 0.46 | 0 | 0
417 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-I, Irhpala water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001782/2022-2023 | BP-2022-23-24 | 08/08/2022 | 0 | WBSEDCL | 0.46 | 0 | 0
418 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARBHUNA BASAN STAND ALONE PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002006/2022-2023 | 879/W/MMD | 27/03/2023 | 180 | DEBSANKER BHATTACHARYA | 5.98 | 4.35 | 40
419 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments at newly sunk replacement tube well-I under Asadtaliya w/s scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000415/2023-2024 | 579/HESD | 04/08/2023 | 7 | BALAJI CONSTRUCTION | 0.19 | 0 | 0
420 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments at newly sunk replacement tube well-II under Asadtaliya w/s scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000416/2023-2024 | 578/HESD | 04/08/2023 | 7 | SHOVAN KUMAR DAS | 0.13 | 0 | 0
421 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well I under Asadtaliya water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001135/2022-2023 | 2116/W/MMD | 28/11/2022 | 120 | BALAJI CONSTRUCTION | 11.24 | 10.54 | 100
422 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well II under Asadtaliya water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001136/2022-2023 | 2117/W/MMD | 28/11/2022 | 120 | SHOVAN KUMAR DAS | 11.37 | 10.65 | 100
423 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF AMRA TARYA PWSS. REF CONSUMER ID-204283796, APPLICATION NO-2004695723, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01157/2024-2025 | BP-2024-25-272 | 12/06/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
424 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF AMRA TARYA PWSS. REF CONSUMER ID-204283802, APPLICATION NO-2004695729, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01158/2024-2025 | BP-2024-25-271 | 12/06/2024 | 0 | WBSEDCL | 3.51 | 0 | 0
425 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Gopinathpur pwss (Ref Consumar ID-204252433),Application No-2004648562,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00284/2024-2025 | BP-2024-25-40 | 18/04/2024 | 0 | WBSEDCL | 4.27 | 0 | 0
426 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Gopinathpur pwss (Ref Consumar ID-204251445),Application No-2004648522,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00286/2024-2025 | BP-2024-25-39 | 18/04/2024 | 0 | WBSEDCL | 3.81 | 0 | 0
427 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOPINATHPUR AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000079/2023-2024 | 1277/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.54 | 0 | 80
428 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of ANGUA PWSS. REF CONSUMER ID-204310283 APPLICATION NO-2004740900, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01024/2024-2025 | BP-2024-25-210 | 28/05/2024 | 0 | WBSEDCL | 6.04 | 0 | 0
429 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of ANGUA PWSS. REF CONSUMER ID-204310356 APPLICATION NO-2004739370 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01031/2024-2025 | BP-2024-25-211 | 28/05/2024 | 0 | WBSEDCL | 4.55 | 0 | 0
430 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANGUA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001902/2022-2023 | 801/W/MMD | 24/03/2023 | 768 | RSA ENTERPRISE | 21.59 | 0 | 35
431 | Midnapore Mechanical | Digha Sub-Division | Fatepur W/S scheme PH-I Application no.-2004511512 ref.-204147631 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03193/2023-2024 | BP-2023-24-468 | 27/12/2023 | 0 | WBSEDCL | 0.86 | 0 | 0
432 | Midnapore Mechanical | Digha Sub-Division | Fatepur W/S scheme TW-II Application No.-2004521 Ref.-204156067 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03363/2023-2024 | BP-2023-24-574 | 18/01/2024 | 0 | WBSEDCL | 0.26 | 0 | 0
433 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FATEPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001673/2022-2023 | 570/W/MMD | 20/03/2023 | 539 | DEY ENTERPRISE | 11.98 | 10.88 | 100
434 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Gokulpur PWSS T/W - I , Application no- 2004790935, Ref no : 204339890 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01582/2024-2025 | BP-2024-25-453 | 23/07/2024 | 0 | WBSEDCL | 3.12 | 0 | 0
435 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
436 | Midnapore Mechanical | Digha Sub-Division | Chirulia Chatla W/S scheme Zone-III, T/W-I Application.-2004553660 Ref.-204183515 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03362/2023-2024 | BP-2023-24-575 | 18/01/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
437 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at Zone-III,TW-II of Chirulia Chatla ws scheme under MMD, PHE Dte. Block-Egra-I, Chopalia CCC. App. no-2004635402, Con ID-204242995 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04742/2023-2024 | Bp-2023-24-915 | 28/03/2024 | 0 | WBSEDCL | 3.69 | 0 | 0
438 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Chirulia-Chatla Zone-3 Egra I Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001984/2022-2023 | 892/W/MMD | 27/03/2023 | 888 | SHREE BISHNU CONSTRUCTION | 23.68 | 0 | 52
439 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00106/2023-2024 | BP-2023-24-25 | 04/05/2023 | 0 | WBSEDCL | 0.37 | 0 | 0
440 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Mukutshila PWSS Zone-II, Tube Well-II WS Scheme (Ref. ID 203933340) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00418/2022-2023 |  | 25/03/2023 | 0 | WBSEDCL | 0.37 | 0 | 0
441 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Mukutshila Zone-II Water Supply Scheme with Allied Works & 1 No. Boosting Tube Well to Accommodate FHTC within Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001471/2022-2023 | 209/W/MMD | 10/02/2023 | 180 | SUBHASIS ROY | 11.84 | 9.44 | 70
442 | Midnapore Mechanical | Contai Sub-Division | Biswanathpur W/S scheme TW-I Application no.-2004496775 Ref no.-204135775 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03194/2023-2024 | BP-2023-24-469 | 27/12/2023 | 0 | WBSEDCL | 1.54 | 0 | 0
443 | Midnapore Mechanical | Contai Sub-Division | Biswanathpur W/S scheme PH no.-II Application No.-2004521756 Ref.-204156072 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03244/2023-2024 | BP-2023-24-498 | 05/01/2024 | 0 | WBSEDCL | 2.56 | 0 | 0
444 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BISWANATHPUR PWSS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001728/2022-2023 | 600/W/MMD | 20/03/2023 | 499 | M/S S M ELECTRICAL | 5.98 | 5.42 | 100
445 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PASCHIM RASULPUR AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001711/2022-2023 | 594/W/MMD | 20/03/2023 | 180 | INDIA ENTERPRISE | 21.62 | 0 | 0
446 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF SOLEMANPUR PWSS. REF CONSUMER ID-204393519, APPLICATION NO-2004889549, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02461/2024-2025 | C102401981777 | 03/10/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
447 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric Quotation bill for Tw no-I of Gamaria PWSS. (ref Consumer ID-204109025). | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02901/2023-2024 | BP-2023-24-326 | 03/11/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
448 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw no-II of Gamaria PWSS (Ref Consumer ID-204109023) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02903/2023-2024 | BP-2023-24-327 | 03/11/2023 | 0 | WBSEDCL | 2.73 | 0 | 0
449 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GAMARIA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001380/2022-2023 | 2391/W/MMD | 31/12/2022 | 180 | SUBHASIS ROY | 22.89 | 13.26 | 25
450 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of ASTICHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671988/QUOT/03/47 DT. 05-04-2024 Application NO- 2004671988 Application type-New connection Consumer Id- 204266732 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00502/2024-2025 | BP-2024-25-91 | 24/04/2024 | 0 | WBSEDCL | 7.72 | 0 | 0
451 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-I) PWSS Egra II Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001981/2022-2023 | 889/W/MMD | 27/03/2023 | 180 | M.D.ENTERPRISE | 23.65 | 0 | 0
452 | Midnapore Mechanical | Kharagpur Sub-Division | ELECTRIC QUOTATION BILL FOR AD TW NO-III OF RAGPUR PWSS. REF CONSUMER ID-204391667, APPLICATION NO-2004886583, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02427/2024-2025 | BP-2024-25-680 | 27/09/2024 | 0 | WBSEDCL | 6.23 | 0 | 0
453 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001943/2022-2023 | 829/W/MMD | 24/03/2023 | 720 | M/S EMMESS | 11.33 | 9.71 | 20
454 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHISHAGOT AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001730/2022-2023 | 602/W/MMD | 20/03/2023 | 712 | BHABANI PRASAD MANNA | 11.98 | 0 | 40
455 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
456 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Narasinghapur water supply scheme T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03560/2023-2024 | BP-2023-24-620 | 07/02/2024 | 0 | WBSEDCL | 0.51 | 0 | 0
457 | Midnapore Mechanical | Kharagpur Sub-Division | Additional Quotation for LT network connection at Narasinghapur PWSS P/H- I , application no - 100000101096 , Ref id - 860293136 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04197/2023-2024 | BP-2023-24-781 | 06/03/2024 | 0 | WBSEDCL | 3.12 | 0 | 0
458 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NARASINGHAPUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001717/2022-2023 | 616/W/MMD | 20/03/2023 | 732 | JAGANNATH ENTERPRISE | 21.58 | 0 | 40
459 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of Dosatina PWSS.(ref Consumer ID-204182345) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03337/2023-2024 | BP-2023-24-554 | 16/01/2024 | 0 | WBSEDCL | 3.93 | 0 | 0
460 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of Dosatina PWSS.(Ref Consumer ID-204182357) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03338/2023-2024 | BP-2023-24-555 | 16/01/2024 | 0 | WBSEDCL | 5.43 | 0 | 0
461 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DOSATINA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002009/2022-2023 | 908/W/MMD | 27/03/2023 | 666 | SUJOY RANJAN BHOWMICK | 27.37 | 20.83 | 15
462 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Augmentation of Adasimla Water Supply Scheme [ Block- Sabang ] under MMD, PHE Dte., Dist.- Paschim Medinipur. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000132/2023-2024 | 1352/W/MMD | 24/05/2023 | 180 | SUJOY RANJAN BHOWMICK | 14.23 | 7.25 | 83
463 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001967/2022-2023 | 878/W/MMD | 27/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 5.99 | 0 | 0
464 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DUBDA and ADJOINING MOUJAS, Block Egra II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000087/2023-2024 | 1269/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 0 | 0
465 | Midnapore Mechanical | Digha Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
466 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Kaktia PWSS Tube Well--III WS Scheme (Ref. ID - 203931856) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00319/2022-2023 | BP-2022-23-138 | 20/03/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
467 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Kaktia PWSS Tube Well--IV WS Scheme (Ref. ID - 203931902) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00320/2022-2023 | BP-2022-23-139 | 20/03/2023 | 0 | WBSEDCL | 2.94 | 0 | 0
468 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Electric Quotiaton for KAKTIA Water Supply Scheme T/W-III (Ref. ID-860272167) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01616/2023-2024 | BP-2023-24-134 | 27/07/2023 | 0 | WBSEDCL | 0.28 | 0 | 0
469 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different woks for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001474/2022-2023 | 212/W/MMD | 10/02/2023 | 180 | WEST BENGAL ENGINEERING CO. | 40.35 | 25.37 | 35
470 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR ANANDAPUR WATER SUPPLY SCHEME, T W NO IV, [ AUGMENTATION ] , JJM WORKS, SCHEME CODE SM/15570, APPLICATION NO 2004815766, REFERENCE ID 204354166, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01677/2024-2025 | C072443787374 | 30/07/2024 | 0 | WBSEDCL | 6.86 | 0 | 0
471 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR ANANDAPUR- SUNDARPUR WATER SUPPLY SCHEME, T W NO IIII, [JOYNAGAR], AUGMENTATION, JJM WORKS, SCHEME CODE SM/15570, APPLICATION NO 2004815790, REFERENCE ID 204354167, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01678/2024-2025 | C072443785883 | 30/07/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
472 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANADAPUR SUNDARPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002015/2022-2023 | 913/W/MMD | 27/03/2023 | 797 | GLACIER ENGINEERING CO. | 25.26 | 17.68 | 85
473 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for Banpatna w/s mini scheme(Consumer ID-203877125) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00089/2023-2024 |  | 19/04/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
474 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for kankuria mini w/s.(consumer ID-203877119) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00092/2023-2024 |  | 19/04/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
475 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for Jotekanuramgarh pwss (Ref Consumar ID-203856003),Application No-2004144274,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-II. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03700/2023-2024 |  | 09/02/2024 | 0 | WBSEDCL | 0.13 | 0 | 0
476 | Midnapore Mechanical | Ghatal Subdivision | Additional Electric quotation bill of Jotekanuramgarh pwss (Ref Consumer ID-203856003),Application No-2004144274,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-I. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03731/2023-2024 |  | 12/02/2024 | 0 | WBSEDCL | 0 | 0 | 0
477 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Construction & Commissioning including FHTC with 3 (three) months trial run including electro-mechanical part for proposed 26 nos. Mini Pipe W/S Scheme within blocks Chandrakona-I (4 Nos.), Chandrakona-II (8 Nos.), Daspur-I (3 Nos.), Daspur-II (9 Nos.) & Kharagpur-I (2 Nos.) in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001858/2022-2023 | 773/W/MMD | 23/03/2023 | 180 | BHABANI PRASAD MANNA | 68.08 | 67.01 | 97
478 | Midnapore Mechanical | Digha Sub-Division | Kanpur W/S scheme T/W-I, Zone-IV Application No.-2004536085 Ref.-204168169 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03290/2023-2024 | BP-2023-24-542 | 11/01/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
479 | Midnapore Mechanical | Digha Sub-Division | Kanpur W/S scheme PH-II, Zone-IV Application No.-2004565701 Ref no.-204193734 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03521/2023-2024 | BP-2023-24-587 | 02/02/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
480 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
481 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HABICHAK Water Supply SchemeT/W-III (Ref. ID-204049767) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01633/2023-2024 | BP-2023-24-142 | 27/07/2023 | 0 | WBSEDCL | 3.76 | 0 | 0
482 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HABICHAK Water Supply SchemeT/W-IV (Ref. ID-204049766) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01634/2023-2024 | BP-2023-24-141 | 27/07/2023 | 0 | WBSEDCL | 3.4 | 0 | 0
483 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Electric Quotiaton for HABICHAK Water Supply Scheme, T/W- II, (Ref. ID-860281634) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02879/2023-2024 | BP-2023-24-322 | 01/11/2023 | 0 | WBSEDCL | 2.27 | 0 | 0
484 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 25.33 | 55
485 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for MAHISHADAL BETKUNDU Water Supply Scheme T/W-, (Ref. ID-222016853) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02680/2023-2024 | BP-2023-24-268 | 10/10/2023 | 0 | WBSEDCL | 0.01 | 0 | 0
486 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Betkundu PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001849/2022-2023 | 766/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.24 | 0 | 0
487 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvination of Electro-Mechanical components of Pratapdighi PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001850/2022-2023 | 768/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.65 | 10.44 | 75
488 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004698092/QUOT/03 DT. 23-04-2024 Application NO- 2004698092 Application type-New connection Consumer Id- 204285056 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00706/2024-2025 | BP-2024-25-139 | 09/05/2024 | 0 | WBSEDCL | 10.71 | 0 | 0
489 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638854/QUOT/03 DT. 13-03-2024 Application NO- 2004638854 Application type-New connection CONSUMER ID: 204243849 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04739/2023-2024 | BP-2023-24-911 | 28/03/2024 | 0 | WBSEDCL | 2.77 | 0 | 0
490 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of NUNHANDA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, BHAGWANPUR C.C.C. Ref. Memo No- 2004638811/QUOT/03 DT. 13-03-2024 Application NO- 2004638811 Application type-New connection CONSUMER ID: 204243848 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04748/2023-2024 | BP-2023-24-912 | 28/03/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
491 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
492 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Khukur Daha & its adjoining mouzas.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/001556/2023-2024 | 3171/W/MMD | 18/12/2023 | 180 | NIRMAN | 27.34 | 0 | 0
493 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
494 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uchitpur water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001141/2021-2022 | 2530/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 100
495 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uchitpur water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001185/2021-2022 | 2532/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.48 | 0 | 100
496 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Uchitpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001197/2021-2022 | 156/W/MMD | 31/01/2022 | 120 | MENAKA ENTERPRISE | 6.52 | 6.52 | 0
497 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Uchitpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001198/2021-2022 | 157/W/MMD | 31/01/2022 | 120 | P.K.ENGINEERING | 6.52 | 6.4 | 70
498 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Dhuipara pwss (Ref Consumar ID-204310840),Application No-2004741253,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01070/2024-2025 | BP-2024-25-194 | 24/05/2024 | 0 | WBSEDCL | 4.55 | 0 | 0
499 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Dhuipara pwss (Ref Consumar ID-204310843),Application No-2004741201,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01071/2024-2025 | BP-2024-25-193 | 24/05/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
500 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHUIPARA PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK,UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000026/2023-2024 | 1190/W/MMD | 25/04/2023 | 706 | RSA ENTERPRISE | 22.79 | 0.58 | 60
501 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Operation and Guarding of Pumping machinery at Pump House No. TW-I, II of Dhuipara water supply scheme Block- Mohanpur Dist.- Paschim Medinipur under Midnapore Mechanical Division, P.H.E. Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000074/2025-2026 | 1146/W/MMD | 13/05/2025 | 245 | RAJIB GHOSH | 4.61 | 0 | 0
502 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAGUYAN AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002199/2022-2023 | 456/W/MMD | 20/03/2023 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 0
503 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation for new service connection at Monoharpur T.W.no-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00117/2023-2024 |  | 08/05/2023 | 0 | WBSEDCL | 0.78 | 0 | 0
504 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | New service connection at Monoharpur T.W.No-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00118/2023-2024 |  | 08/05/2023 | 0 | WBSEDCL | 2.5 | 0 | 0
505 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KAKRAJIT AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001922/2022-2023 | 841/W/MMD | 24/03/2023 | 180 | P.K.ENGINEERING | 54.76 | 25.68 | 30
506 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of BAGRUI PWSS. REF CONSUMER ID-204211962, APPLICATION NO-2004590203, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/03742/2023-2024 | BP-2023-24-688 | 16/02/2024 | 0 | WBSEDCL | 3.51 | 0 | 0
507 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of BAGRUI PWSS. REF CONSUMER ID-204211970, APPLICATION NO-2004590212, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/03743/2023-2024 | BP-2023-24-687 | 16/02/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
508 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 181 | M/S BIKASH DE | 3.69 | 0 | 0
509 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.13 | 50
510 | Midnapore Mechanical | Tamluk Sadar Sub-Division | AJANGECHIA w/s SCHEME Application No.-2004568912 Ref.-204196601 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03528/2023-2024 | BP-2023-24-586 | 02/02/2024 | 0 | WBSEDCL | 5.6 | 0 | 0
511 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJANGECHHYA, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001661/2022-2023 | 545/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.58 | 9.75 | 45
512 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation Sabang CCC at Daspur, Bankibheri Pin-721434 ( 2003870026) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00158/2022-2023 | BP-2022-23-123 | 09/03/2023 | 0 | WBSEDCL | 0.12 | 0 | 0
513 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION FOR NEW POWER CONNECTION OF DASPUR MINI WATER SUPPLY ASCHEME [ APPLICATION --2004478402, REFERENCE ID ----204120945, SABONG CCC, QUOTATION NO ---2004478402/QUOT/03 DATED 26/10/2023, SCHEME NAME --- DASPUR MINI. , SCHEME CODE ---SM/10658 , MB NO--3580 ] | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02891/2023-2024 | BP-2023-24-344 | 10/11/2023 | 0 | WBSEDCL | 3.98 | 0 | 0
514 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-I at Daspur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000016/2022-2023 | 557/W/MMD | 12/04/2022 | 120 | RITESH ENTERPRISE | 6.49 | 0 | 100
515 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-II at Daspur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000017/2022-2023 | 558/W/MMD | 12/04/2022 | 1032 | SUBHAM ENTERPRISE | 6.44 | 4.95 | 100
516 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at DASPUR water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001282/2021-2022 | 76/W/MMD | 17/01/2022 | 5 | DEBJYOTI BASU | 4.47 | 4.22 | 100
517 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100 mmX 150mtr) RBTW by Rotary Method at Daspur water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur District under Midnapur Mechanical Division P.H.E Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001285/2021-2022 | 75/W/MMD | 17/01/2022 | 5 | DEBJYOTI BASU | 4.47 | 4.21 | 100
518 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Additional work in connection with sinking of (150mmX100mmX150mtr) RBTW by Rotary method at Daspur water supply scheme, tube well no.-1 of Sabang Block of PaschimMidnapur Dist. under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001556/2021-2022 | 175/MMSD-I | 17/02/2022 | 7 | DEBJYOTI BASU | 0.35 | 0.35 | 80
519 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation Sabang CCC at Daspur, Bankibheri Pin-721434 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001590/2021-2022 | 2003870026 | 23/03/2022 | 365 | WBSEDCL | 0.13 | 0 | 0
520 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotation bill Sabang CCC at Daspur, Bankibheri, Pin-721434 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002768/2022-2023 |  | 17/11/2022 | 0 | WBSEDCL | 0.13 | 0 | 0
521 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for PUTPUTIA Water Supply Scheme , T/W-II (Ref. ID-204075888) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02182/2023-2024 | BP-2023-24-240 | 12/09/2023 | 0 | WBSEDCL | 4.59 | 0 | 0
522 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for PUTPUTIA Head Work Water Supply Scheme T/W-I, (Ref. ID-204094476) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02679/2023-2024 | BP-2023-24-270 | 10/10/2023 | 0 | WBSEDCL | 5.52 | 0 | 0
523 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PUTPUTIA PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001691/2022-2023 | 620/W/MMD | 20/03/2023 | 896 | M/S B.M. ELECTRICAL | 22.81 | 19.81 | 35
524 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II OF TORIA PWSS. REF CONSUMER ID-204370272, APPLICATION NO-2004843239 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/01875/2024-2025 | C082421721033 | 16/08/2024 | 0 | WBSEDCL | 5.29 | 0 | 0
525 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of TORIA PWSS. REF CONSUMER ID-204248200, APPLICATION NO-2004645189, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/04584/2023-2024 | BP-2023-24-893 | 22/03/2024 | 0 | WBSEDCL | 7.19 | 0 | 0
526 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TORIA PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000362/2023-2024 | 1690/W/MMD | 04/08/2023 | 180 | UTTAM KUMAR CHATTERJEE | 25.25 | 17.54 | 30
527 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Dubraji PWSS P/H- I , application no - 2004608941 , Ref id - 204222615 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04196/2023-2024 | BP-2023-24-777 | 06/03/2024 | 0 | WBSEDCL | 1.81 | 0 | 0
528 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Dubraji PWSS P/H- II , application no - 2004609001 , Ref id - 204222611 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04198/2023-2024 | BP-2023-24-778 | 06/03/2024 | 0 | WBSEDCL | 6.46 | 0 | 0
529 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUBRAJI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000364/2023-2024 | 1692/W/MMD | 04/08/2023 | 180 | A.S.ENTERPRISE | 27.34 | 18.45 | 40
530 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Tube Well-IV of Lutunia to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000160/2023-2024 | 1348/W/MMD | 24/05/2023 | 180 | SUJOY RANJAN BHOWMICK | 11.88 | 11.65 | 100
531 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Pump House-III under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001076/2022-2023 | 1968/W/MMD | 20/10/2022 | 120 | BUSR ENGINEERING | 10.79 | 10.51 | 99
532 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-II under Ranirbazar water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist - Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001133/2022-2023 | 2114/W/MMD | 28/11/2022 | 120 | M/S EMMESS | 11.37 | 10.1 | 0
533 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation Ghatal CCC at Ranisimulia, Ranirbazar Water supply scheme under MMD PHE Dte | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002770/2022-2023 | BP-2022-23-58 | 23/11/2022 | 0 | WBSEDCL | 0.3 | 0 | 0
534 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric quotation for Bishnubar PWSS Tube Well-III WS Scheme Additional TW (Ref. ID - 203930212) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00321/2022-2023 | BP-2022-23-140 | 20/03/2023 | 0 | WBSEDCL | 3.23 | 0 | 0
535 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001547/2022-2023 | 405/W/MMD | 16/03/2023 | 180 | DAS ENTERPRISE | 35.46 | 11.06 | 61
536 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Bhagwanpur Zone-II, TW - III (Ref. ID - 203964030) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00108/2023-2024 | BP-2023-24-30 | 04/05/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
537 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for BHAGWANPUR Water Supply Scheme Z-I, T/W-III (Ref. ID-204049532 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01631/2023-2024 | BP-2023-24-137 | 27/07/2023 | 0 | WBSEDCL | 3.34 | 0 | 0
538 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bhagwanpur PWSS to Accommodate FHTC in Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (Zone-I & Zone-II) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001929/2022-2023 | 848/W/MMD | 24/03/2023 | 180 | BHABANI PRASAD MANNA | 59.25 | 18.74 | 35
539 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict Quotation Bill for mohanpur water supply scheme (consumer ID-203995501) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00339/2023-2024 | BP-2023-24-228 | 05/09/2023 | 0 | WBSEDCL | 2.3 | 0 | 0
540 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Mohanpur to Accommodate FHTC under Jal Sapno Mission under Mohanpur Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001966/2022-2023 | 877/W/MMD | 27/03/2023 | 180 | JOYSHREE CONCERN | 11.85 | 8.66 | 51
541 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Kapaseria Water Supply Scheme, Block Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001908/2022-2023 | 809/W/MMD | 24/03/2023 | 180 | RITESH ENTERPRISE | 13.59 | 12.86 | 90
542 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MUKUTSHILA, Water Supply Scheme T/W-V, Zone-II (Ref. ID-204049558) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01672/2023-2024 | BP-2023-24-162 | 04/08/2023 | 0 | WBSEDCL | 2.26 | 0 | 0
543 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, MUKUTSHILA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049562) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01680/2023-2024 | BP-2023-24-160 | 04/08/2023 | 0 | WBSEDCL | 1.51 | 0 | 0
544 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-2)under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000149/2023-2024 | 1377/W/MMD | 30/05/2023 | 180 | MENAKA ENTERPRISE | 35.5 | 31.24 | 75
545 | Midnapore Mechanical | Ghatal Subdivision | Service Connection charges of WBSEDCL at Krishnaballavpur P/H-I | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00036/2022-2023 | BP-2022-23-95 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
546 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Krishnaballabhpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001313/2022-2023 | 2315/W/MMD | 29/12/2022 | 180 | M/S EMMESS | 6.01 | 5.97 | 80
547 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sinking of Boosting Tube Well and Allied Works to Accommodate FHTC under JJM in Kanaidighi PWSS under Contai-III Block, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001759/2022-2023 | 639/W/MMD | 20/03/2023 | 180 | A.M.S. ENTERPRISE | 13.59 | 0 | 0
548 | Midnapore Mechanical | Contai Sub-Division | Contai S.A Zone -III W/S scheme PH-II Application no.-2004474775 ref.-204117777 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03195/2023-2024 |  | 15/12/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
549 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area (Zone-III) (Phase-B) PWSS to Accommodate FHTC in Contai-I and III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001918/2022-2023 | 822/W/MMD | 24/03/2023 | 720 | P.K.ENGINEERING | 40.78 | 28.91 | 80
550 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-I (Ref. ID-204049557) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01674/2023-2024 | BP-2023-24-154 | 04/08/2023 | 0 | WBSEDCL | 2.55 | 0 | 0
551 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-I (Phase-1) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001911/2022-2023 | 812/W/MMD | 24/03/2023 | 714 | DEBJYOTI BASU | 54.33 | 28.88 | 25
552 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for TIKASHI, Water Supply Scheme T/W-II, (Ref. ID-204049560) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01681/2023-2024 | BP-2023-24-161 | 04/08/2023 | 0 | WBSEDCL | 2.41 | 0 | 0
553 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for TIKASHI Water Supply Scheme T/W-I, (Ref. ID-204134790) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03185/2023-2024 | BP-2023-24-440 | 19/12/2023 | 0 | WBSEDCL | 5.13 | 0 | 0
554 | Midnapore Mechanical | Contai Sub-Division | Additional quotation for Tkashi w/s swcheme PH I at Khejuri I Block in the District of Purba Medinipur under MMD PHE Dte. (Application ID 100000100192 Dated 12.02.2024 Ref ID 860292212) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03783/2023-2024 | BP-2023-24-715 | 20/02/2024 | 0 | WBSEDCL | 0.84 | 0 | 0
555 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TIKASHI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000090/2023-2024 | 1266/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 25.14 | 22.33 | 88
556 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686956/QUOT/03 DT. 19-04-2024 Application NO- 2004686956 Application type-New connection Consumer Id- 204277583 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00703/2024-2025 | BP-2024-25-143 | 09/05/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
557 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004691120/QUOT/03 DT. 19-04-2024 Application NO- 2004691120 Application type-New connection Consumer Id- 204280540 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00704/2024-2025 | BP-2024-25-142 | 09/05/2024 | 0 | WBSEDCL | 11.94 | 0 | 0
558 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULYA and ADJOINING MOUJAS, Block - Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001653/2022-2023 | 525/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 19.94 | 80
559 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Ramchandrapur W/S scheme PH No.-I Application No.-2004543119 Ref.-204175235 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03266/2023-2024 | BP-2023-24-512 | 09/01/2024 | 0 | WBSEDCL | 2.95 | 0 | 0
560 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipment¿s at TW II for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000074/2023-2024 | 1243/W/MMD | 28/04/2023 | 644 | M/S EMMESS | 13.59 | 6.63 | 60
561 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Solat PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001517/2022-2023 | 361/W/MMD | 09/03/2023 | 180 | AMIT DAS | 13.56 | 12.85 | 0
562 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-20048335913/QUOT/03 DT. 26-07-2024 Application NO- 20048335913 MEMO NO: AMR/PHE/282 DT.26/7/2024 Application type-New connection Consumer Id- 204365755 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01857/2024-2025 | BP-2024-25-539 | 07/08/2024 | 0 | WBSEDCL | 4.45 | 0 | 0
563 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835826/QUOT/03 DT. 26-07-2024 Application NO- 2004835826 MEMO NO: AMR/PHE/288 DT.26/7/2024 Application type-New connection Consumer Id- 204365757 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01863/2024-2025 | BP-2024-25-538 | 07/08/2024 | 0 | WBSEDCL | 4.24 | 0 | 0
564 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SELMABAD and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001650/2022-2023 | 522/W/MMD | 20/03/2023 | 1317 | S.S.ENTERPRISES | 23.7 | 2.91 | 51
565 | Midnapore Mechanical | Digha Sub-Division | Nij-Maitana W/S scheme T/W-I Application No.-2004550686 Ref.-204181243 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03291/2023-2024 | BP-2023-24-540 | 11/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0
566 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of Nijmaitana ws scheme under MMD,PHE, Dte. Ref. Application no-2004579831. Con ID-204204430. PICHABONI CCC, BLOCK-RAMNAGAR-II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03654/2023-2024 | BP-2023-24-680 | 15/02/2024 | 0 | WBSEDCL | 3.07 | 0 | 0
567 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835399/QUOT/03 DT. 26-07-2024 Application NO- 2004835399 MEMO NO: AMR/PHE/281 DT.26/7/2024 Application type-New connection Consumer Id- 204365758 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01860/2024-2025 | BP-2024-25-541 | 07/08/2024 | 0 | WBSEDCL | 4.98 | 0 | 0
568 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004895165/QUOT/03 DT. 10-09-2024 MEMO NO: AMR/PHE/377 DT. 10-09-2024 Application NO- 2004895165 Application type-New connection Consumer Id- 204395918 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02451/2024-2025 | BP-2024-25-718 | 30/09/2024 | 0 | WBSEDCL | 3.34 | 0 | 0
569 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PALPARA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001589/2022-2023 | 472/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 25.24 | 17.6 | 53
570 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MAHABISHRA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004667051/QUOT/03 DT. 15-04-2024 Application NO- 2004667051 Application type-New connection Consumer Id- 204275715 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00577/2024-2025 | BP-2024-25-101 | 26/04/2024 | 0 | WBSEDCL | 6.36 | 0 | 0
571 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHABISHRA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001582/2022-2023 | 465/W/MMD | 20/03/2023 | 803 | DEY ENTERPRISE | 23.7 | 0 | 90
572 | Midnapore Mechanical | Ghatal Subdivision | Electric quotaion for tw-I of Ranichak w/s scheme(consumar ID-203974580) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00097/2023-2024 | BP-2023-24-20 | 28/04/2023 | 0 | WBSEDCL | 3 | 0 | 0
573 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for tw-II of Ranichak w/s scheme(consumar ID-203974585) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00099/2023-2024 | BP-2023-24-19 | 28/04/2023 | 0 | WBSEDCL | 2.15 | 0 | 0
574 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Ranichak & its adjoining mouzas. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001310/2022-2023 | 2312/W/MMD | 29/12/2022 | 180 | ECO ENTERPRISE | 25.26 | 25.11 | 100
575 | Midnapore Mechanical | Ghatal Subdivision | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001562/2023-2024 | 1211/MMSD-I | 29/09/2023 | 92 | SUBHASIS ROY | 0.45 | 0 | 0
576 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-III of Baharchandberia ws scheme under MMD, PHE Dte, Block-Conai-II, MARISHDA CCC Application no-2004763702 Con ID-204323627 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01232/2024-2025 | BP-2024-25-286 | 18/06/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
577 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
578 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well for 2nd Tube Well for Baharchandberya Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block ¿ Deshopran under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001747/2022-2023 | 643/W/MMD | 20/03/2023 | 180 | K.S.P. ENTERPRISE | 13.57 | 11.31 | 85
579 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHAGDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852019/QUOT/03/563 DT. 07-08-2024 Application NO- 2004852019 Application type-New connection Consumer Id- 204373372 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02124/2024-2025 | C082449401206 | 02/09/2024 | 0 | WBSEDCL | 5.03 | 0 | 0
580 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGDA and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001398/2022-2023 | 2409/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 45
581 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Murakata PWSS , Application no - 2004644754 , Ref ID - 204248051 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00319/2024-2025 | BP-2024-25-81 | 24/04/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
582 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Murakata PWSS tw- II within Narayangarh block Application No- 2004844779 Ref No - 204369553 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02445/2024-2025 | C092443182572 | 27/09/2024 | 0 | WBSEDCL | 4.16 | 0 | 0
583 | Midnapore Mechanical | Kharagpur Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of MURAKATA PWSS. REF CONSUMER ID-204204417, APPLICATION NO-2004578935, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03576/2023-2024 | BP-2023-24-637 | 08/02/2024 | 0 | WBSEDCL | 4.64 | 0 | 0
584 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Pakurseni PWSS T/W - II under Narayangarh block , application no - 2004739517 , ref no - 204309706 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01079/2024-2025 | BP-2024-25-233 | 04/06/2024 | 0 | WBSEDCL | 4.43 | 0 | 0
585 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Pakurseni PWSS , Application no - 2004644720 , Ref ID - 204248038 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04637/2023-2024 | BP-2023-24-896 | 28/03/2024 | 0 | WBSEDCL | 3.38 | 0 | 0
586 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Babalpur PWSS T/W - II , Application no- 2004790929, Ref no : 204339891 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01580/2024-2025 | C072438248345 | 23/07/2024 | 0 | WBSEDCL | 2.91 | 0 | 0
587 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Babalpur PWSS T/W - I , Application no- 2004790923, Ref no : 204339889 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01581/2024-2025 | C072438232052 | 23/07/2024 | 0 | WBSEDCL | 3.57 | 0 | 0
588 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
589 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Serkhanchak Zone I w/s scheme PH IV Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004675042, Ref ID 204268872) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00291/2024-2025 | BP-2024-25-50 | 18/04/2024 | 0 | WBSEDCL | 8.33 | 0 | 0
590 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SHERKHANCHAK Water Supply Scheme Z-I, T/W-III (Ref. ID-204040417 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01637/2023-2024 | BP-2023-24-139 | 27/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
591 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-I) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001514/2022-2023 | 358/W/MMD | 09/03/2023 | 180 | S.K.ENTERPRISE | 35.55 | 29.45 | 70
592 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657831/QUOT/03/1513 DT. 28-03-2024 Application NO- 2004657831 Application type-New connection Consumer Id- 204257680 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00260/2024-2025 | BP-2024-25-30 | 15/04/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
593 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KEKAI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760163/QUOT/03 DT. 04-06-2024 Application NO- 2004760163 Application type-New connection Consumer Id- 204322029 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01231/2024-2025 | BP-2024-25-287 | 18/06/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
594 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KEKAI and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001366/2022-2023 | 2377/W/MMD | 31/12/2022 | 900 | GHOSH ENGINEERING SYNDICATE | 25.24 | 5.85 | 51
595 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF BHANSRA PWSS. REF CONSUMER ID-204370484, APPLICATION NO-2004846729, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02125/2024-2025 | C082448282150 | 02/09/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
596 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHANSRA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000162/2023-2024 | 1404/W/MMD | 02/06/2023 | 720 | DEBJYOTI BASU | 22.78 | 14.24 | 20
597 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004701293/QUOT/03/98 DT. 25-04-2024 Application NO- 2004701293 Application type-New connection Consumer Id- 204287569 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00856/2024-2025 | BP-2024-25-162 | 15/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0
598 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of RUKMINIPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004792717/QUOT/03/381 DT. 02/07/2024 Application NO- 2004792717 Application type-New connection Consumer Id- 204345882 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01699/2024-2025 | BP-2024-25-493 | 29/07/2024 | 0 | WBSEDCL | 4.04 | 0 | 0
599 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RUKMINIPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001354/2022-2023 | 2365/W/MMD | 31/12/2022 | 974 | ABHIJIT BASU | 23.69 | 14.81 | 80
600 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BHUIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004950601/QUOT/03 DT. 30-10-2024 Application NO- 2004950601 Application type-New connection Consumer Id- 204434656 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03006/2024-2025 | C112423559210 | 20/11/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
601 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BHUNIAJIBAR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- 2004620665/QUOT/03 DT. 27-02-2024 Application NO- 2004620665 Application type-New connection Reference Id- 204229268 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04331/2023-2024 | BP-2023-24-807 | 11/03/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
602 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BHUIANJIBAR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001685/2022-2023 | 563/W/MMD | 20/03/2023 | 803 | SUBHRA ENTERPRISE | 22.78 | 16.52 | 100
603 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-I of Kusumpur PWSS. Ref Consumer ID-204136077. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02990/2023-2024 | BP-2023-24-385 | 02/12/2023 | 0 | WBSEDCL | 3.66 | 0 | 0
604 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-II of Kusumpur PWSS.(Ref Consumer ID-204136080). | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02991/2023-2024 | BP-2023-24-386 | 02/12/2023 | 0 | WBSEDCL | 1.84 | 0 | 0
605 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUSUMPUR AND ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001427/2023-2024 | 3079/W/MMD | 29/11/2023 | 180 | BINAPANI ENTERPRISE | 23.01 | 0 | 0
606 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Kasba Asanda PWSS T/W - I Within Narayangarh Block Application No - 2004987922, Ref ID- 204460782 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03871/2024-2025 |  | 24/12/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
607 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAR JHIKURIA AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001893/2022-2023 | 792/W/MMD | 24/03/2023 | 892 | M/S B.M. ELECTRICAL | 21.56 | 13.57 | 40
608 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for new connection at Tw-I of Radhaballabhpur water supply scheme. Consumer ID-204030193. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00580/2023-2024 | BP-2023-24-127 | 13/07/2023 | 0 | WBSEDCL | 0.28 | 0 | 0
609 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for new connection at Tw No-II of Radhaballabhpur water supply scheme. Consumer ID-204018509. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00582/2023-2024 | BP-2023-24-126 | 13/07/2023 | 0 | WBSEDCL | 0.28 | 0 | 0
610 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Additional quatation for service connection charge for effecting NSC at Radhaballavpur PWSS vide Application 2004305845. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01864/2023-2024 | BP-2023-24-234 | 07/09/2023 | 0 | WBSEDCL | 1.91 | 0 | 0
611 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Additional quotation for service connection charge for effecting NSC vide Application No-2004305839. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01865/2023-2024 | BP-2023-24-233 | 07/09/2023 | 0 | WBSEDCL | 2.14 | 0 | 0
612 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Supply and delivery LED Smart Bright street light fixture and other related works at P H of Radhaballavpur and other water supply scheme under Midnapur Mechanical Division , P.H.E.Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000062/2025-2026 | 660/MMSD-I | 13/05/2025 | 10 | ASHUTOSH DAS & CO. | 1.62 | 0 | 0
613 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0
614 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHABALLABHPUR PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001950/2022-2023 | 833/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 22.12 | 50
615 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of DAKSHIN AMRIA PWSS. REF CONSUMER ID-204310379 APPLICATION NO-2004739365 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01026/2024-2025 | BP-2024-25-205 | 28/05/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
616 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF DAKSHIN AMRIA PWSS. REF CONSUMER ID-204389348, APPLICATION NO-2004882536, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02411/2024-2025 | C092442004530 | 27/09/2024 | 0 | WBSEDCL | 9.74 | 0 | 0
617 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHIN AMRIA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001758/2022-2023 | 648/W/MMD | 20/03/2023 | 180 | MANIK CHANDRA SAHA | 21.56 | 16.28 | 25
618 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for utta Bar water supply scheme zone-I Pump house no-I(consumar Id-204139570) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03016/2023-2024 | BP-2023-24-378 | 02/12/2023 | 0 | WBSEDCL | 4.3 | 0 | 0
619 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for uttar Bar Zone-I Pump house NO-II (Consumar Id-204139580) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03017/2023-2024 | BP-2023-24-377 | 02/12/2023 | 0 | WBSEDCL | 2.7 | 0 | 0
620 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001641/2022-2023 | 573/W/MMD | 20/03/2023 | 820 | DEY ENTERPRISE | 25.26 | 0 | 90
621 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Uttar Bar (Zone-I & II) & its adjoining mouzas. under JJM Program under MMD PHE Dte. (Part-II) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001955/2022-2023 | 868/W/MMD | 27/03/2023 | 889 | M/S B.M. ELECTRICAL | 23.01 | 21.35 | 65
622 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0
623 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF KARANJIMURA PWSS. REF CONSUMER ID-204283801, APPLICATION NO-2004695741, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01153/2024-2025 | BP-2024-25-269 | 12/06/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
624 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF KARANJIMURA PWSS. REF CONSUMER ID-204283800, APPLICATION NO-2004695735 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01154/2024-2025 | BP-2024-25-268 | 12/06/2024 | 0 | WBSEDCL | 7.94 | 0 | 0
625 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KARANJIMURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001430/2023-2024 | 3084/W/MMD | 29/11/2023 | 672 | SUJOY RANJAN BHOWMICK | 21.58 | 14.66 | 20
626 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Khurshi PWSS T/W no - II of Narayangarh block Application no - 2004754862 , Ref ID - 204323387 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01304/2024-2025 | BP-2024-25-343 | 25/06/2024 | 0 | WBSEDCL | 5.95 | 0 | 0
627 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Khurshi PWSS P/H- I , application no - 2004609043 , Ref id - 204223722 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04204/2023-2024 | bp-2023-24-783 | 06/03/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
628 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Gojina w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619845, Ref ID-204229480) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04499/2023-2024 | BP-2023-24-862 | 16/03/2024 | 0 | WBSEDCL | 5.65 | 0 | 0
629 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Gojina w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619919, Ref ID-204229478) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04500/2023-2024 | BP-2023-24-861 | 16/03/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
630 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOJINA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001654/2022-2023 | 526/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 5.65 | 60
631 | Midnapore Mechanical | Contai Sub-Division | Katari W/S scheme PH.-I Application No.-2004565589 Ref No.-204193626 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03478/2023-2024 | BP-2023-24-590 | 02/02/2024 | 0 | WBSEDCL | 5.84 | 0 | 0
632 | Midnapore Mechanical | Contai Sub-Division | Katari W/S scheme PH.-II Application No.-2004565602 Ref No.-204193624 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03479/2023-2024 | BP-2023-24-591 | 02/02/2024 | 0 | WBSEDCL | 5.2 | 0 | 0
633 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KATARI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001612/2022-2023 | 505/W/MMD | 20/03/2023 | 180 | AMIT DAS | 21.57 | 20.26 | 50
634 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Malighati pwss (Ref Consumar ID-204391665),Application No-2004886446,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02422/2024-2025 | C092443140214 | 27/09/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
635 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Malighati (Ref Consumar ID-204391662),Application No-2004886364, Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02423/2024-2025 | C092443138989 | 27/09/2024 | 0 | WBSEDCL | 1.19 | 0 | 0
636 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MALIGHATI AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001376/2022-2023 | 2387/W/MMD | 31/12/2022 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 0
637 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHA KANTAPUR AND IT'S ADJOINING MOUJAS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001901/2022-2023 | 800/W/MMD | 24/03/2023 | 1013 | KAMAKSHYA ENTERPRISE | 21.57 | 0 | 15
638 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Ramchandrapur pwss (Ref Consumar ID-204369740),Application No-2004844151,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02010/2024-2025 | C082430134176 | 20/08/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
639 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Ramchandrapur pwss (Ref Consumar ID-204369742),Application No-2004844160,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02011/2024-2025 | C082430133485 | 20/08/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
640 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RAMCHANDRAPUR AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001603/2022-2023 | 482/W/MMD | 20/03/2023 | 873 | SAIKAT SINHA | 23.01 | 16.78 | 50
641 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Chakabdullah PWSS t/w - II , khargpur - II block , Madpur CCC , Application No - 2004799237, Ref ID : 204344491 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01635/2024-2025 | BP-2024-25-482 | 30/07/2024 | 0 | WBSEDCL | 3.8 | 0 | 0
642 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Chak Abdulla PWSS P/H- I , application no - 2004608932 , Ref id - 204222608 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04194/2023-2024 | BP-2023-24-769 | 04/03/2024 | 0 | WBSEDCL | 2.79 | 0 | 0
643 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001617/2022-2023 | 498/W/MMD | 20/03/2023 | 623 | GOENKA ENTERPRISE | 23.01 | 21.45 | 100
644 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of Kalagram PWSS (Ref Consumer Id-204128489) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02995/2023-2024 | BP-2023-24-387 | 02/12/2023 | 0 | WBSEDCL | 3.43 | 0 | 0
645 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric Quotation bill for Tw No-II of kalagram PWSS. (ref Consumer ID-204128480) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02996/2023-2024 | BP-2023-24-388 | 02/12/2023 | 0 | WBSEDCL | 3.05 | 0 | 0
646 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 100
647 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KALAGRAM AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001919/2022-2023 | 838/W/MMD | 24/03/2023 | 669 | SUJOY RANJAN BHOWMICK | 27.36 | 21.95 | 20
648 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 181 | M/S BIKASH DE | 3.69 | 0 | 0
649 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.54 | 50
650 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 100
651 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of Kharika PWSS. (Ref Conumer ID-204182369) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03342/2023-2024 | BP-2023-24-563 | 16/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
652 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of KHARIKA PWSS. (Ref Consumer ID-204195441), APPLICATION NO-2004564930, APPLICATION TYPE-NEW CONNECTION,NAME OF CCC-ANANDAPUR CCC, BLOCK-KESHPUR. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03575/2023-2024 | BP-2023-24-642 | 08/02/2024 | 0 | WBSEDCL | 4.79 | 0 | 0
653 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARIKA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001923/2022-2023 | 842/W/MMD | 24/03/2023 | 708 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 30
654 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Kutki PWSS T/W- I ,Narayangarh Block , Application no- 2004677554 , ref. Id - 204270807 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00702/2024-2025 | BP2024-25-152 | 09/05/2024 | 0 | WBSEDCL | 3.97 | 0 | 0
655 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Kutki Pwss T/W - II within Narayangarh Block Application No- 2004857382 , Ref No - 204376545 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02117/2024-2025 | BP-2024-25-628 | 02/09/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
656 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUTKI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001956/2022-2023 | 869/W/MMD | 27/03/2023 | 180 | JAL PRAVAHIKA PVT. LTD. | 11.95 | 0 | 0
657 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of SOLPOTA PWSS. REF CONSUMER ID-204310319 APPLICATION NO-2004739410, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01021/2024-2025 | BP-2024-25-203 | 28/05/2024 | 0 | WBSEDCL | 6.75 | 0 | 0
658 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of SOLPOTA PWSS. REF CONSUMER ID-204310435 APPLICATION NO-2004739612, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01022/2024-2025 | BP-2024-25-204 | 28/05/2024 | 0 | WBSEDCL | 6.41 | 0 | 0
659 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SOLPOTA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001756/2022-2023 | 647/W/MMD | 20/03/2023 | 892 | DEY ENTERPRISE | 21.57 | 14.66 | 20
660 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for Addl. TW-IV of Maligram W/S Scheme (Consumer ID 203971943) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00076/2023-2024 | BP-2023-24-35 | 04/05/2023 | 0 | WBSEDCL | 4.08 | 0 | 0
661 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Maligram & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001607/2022-2023 | 487/W/MMD | 20/03/2023 | 1032 | M/S MANABESH ROY | 22.93 | 10.66 | 40
662 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of POTA PUKURIA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670768/QUOT/03 DT. 05-04-2024 Application NO- 2004670768 Application type-New connection Consumer Id- 204266388 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00295/2024-2025 | BP-2024-25-45 | 18/04/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
663 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for POTA PAKURIA and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001668/2022-2023 | 551/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 9.99 | 80
664 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for BADALPUR Water Supply Scheme T/W-I, (Ref. ID-204134593) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02999/2023-2024 | BP-2023-24-360 | 24/11/2023 | 0 | WBSEDCL | 3.28 | 0 | 0
665 | Midnapore Mechanical | Digha Sub-Division | Badalpur W/S scheme PH-II Application no.-2004522472 ref.-204156771 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03196/2023-2024 | BP-2023-24-470 | 27/12/2023 | 0 | WBSEDCL | 4.53 | 0 | 0
666 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BADALPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001662/2022-2023 | 546/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.58 | 19.98 | 100
667 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-I of Sarang water supply scheme.(ref consumer ID-204121968) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03122/2023-2024 | BP-2023-24-413 | 09/12/2023 | 0 | WBSEDCL | 4.75 | 0 | 0
668 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-II of Sarang PWSS .(Ref Conumer ID-204122250). | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03226/2023-2024 | BP-2023-24-481 | 27/12/2023 | 0 | WBSEDCL | 5.73 | 0 | 0
669 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SARANG AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001630/2022-2023 | 490/W/MMD | 20/03/2023 | 895 | INDTECH ASSOCIATES | 23 | 0 | 20
670 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charges of WBSEDCL at TW-III (Additional) of Kolanda Water Supply Scheme (Ref. ID - 203935156) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00406/2022-2023 |  | 22/03/2023 | 0 | WBSEDCL | 1.78 | 0 | 0
671 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charges of WBSEDCL at TW-IV (Additional) of Kolanda Water Supply Scheme (Ref. ID - 203935153) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00407/2022-2023 |  | 22/03/2023 | 0 | WBSEDCL | 0.46 | 0 | 0
672 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Kolanda PWSS Tube Well-III WS Scheme (Ref. ID 203935156) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00415/2022-2023 | BP-2023-24-24 | 04/05/2023 | 0 | WBSEDCL | 1.78 | 0 | 0
673 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Kolanda PWSS Tube Well-IV WS Scheme (Ref. ID 203935153) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00416/2022-2023 |  | 25/03/2023 | 0 | WBSEDCL | 0.46 | 0 | 0
674 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
675 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0.2 | 100
676 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.09 | 100
677 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Installation of Dept. Submersible Pump motor set and with other acessories and other allied works at Tubewell no 3 ( newly sunk ) of Kolanda Water Supply Scheme [ Block Sabong ] under MMD, PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002418/2023-2024 | 41/MMSD-I | 16/01/2024 | 7 | SHOVAN KUMAR DAS | 0.3 | 0 | 100
678 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw no-I of Piasala PWSS. (Ref ID- 204061141) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01764/2023-2024 | BP-2023-24-183 | 11/08/2023 | 0 | WBSEDCL | 2.75 | 0 | 0
679 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of Piasala water supply scheme. (ref Id-204061139) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01765/2023-2024 | BP-2023-24-184 | 11/08/2023 | 0 | WBSEDCL | 2.82 | 0 | 0
680 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF RAGHUNATHPUR [ BONPATNA-I] WATER SUPPLY ASCHEME [ APPLICATION --2004479616, REFERENCE ID ----204122242, NIMPURA CCC, QUOTATION NO ---2004479616/QUOT/03 DATED 26/10/2023, SCHEME NAME --- RAGHUNATHPUR [ BONPATNA -I] . , SCHEME CODE ---SM/15257 , MB NO--3580 ] | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02918/2023-2024 | BP-2023-24-349 | 10/11/2023 | 0 | WBSEDCL | 3.73 | 0 | 0
681 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF RAGHUNATHPUR [ BONPATNA-II] WATER SUPPLY ASCHEME [ APPLICATION --2004479629, REFERENCE ID ----204122243, NIMPURA CCC, QUOTATION NO ---2004479629/QUOT/03 DATED 26/10/2023, SCHEME NAME --- RAGHUNATHPUR [ BONPATNA -II] . , SCHEME CODE ---SM/15257 , MB NO--3580 ] | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02919/2023-2024 | BP-2023-24-348 | 10/11/2023 | 0 | WBSEDCL | 3.64 | 0 | 0
682 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Raghunathpur & its adjoining mouzas, Block - Kharagpur-I, Dist-Paschim Medinipurunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002196/2022-2023 | 450/W/MMD | 20/03/2023 | 959 | J K ENGINEERING CO | 22.94 | 14.1 | 100
683 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation bill for Tw no-III of Chhotokhelna water supply scheme.Ref Consumer ID-204084641. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02517/2023-2024 | BP-2023-24-248 | 14/09/2023 | 0 | WBSEDCL | 5.48 | 0 | 0
684 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001609/2022-2023 | 488/W/MMD | 20/03/2023 | 180 | KUSHANI ENTERPRISE | 10.98 | 10.71 | 50
685 | Midnapore Mechanical | Kharagpur Sub-Division | ELECTRIC QUOTATION BILL FOR AD TW NO-III OF KARKAI PWSS. REF CONSUMER ID-204350044, APPLICATION NO-2004810203, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01472/2024-2025 | C072443773813 | 30/07/2024 | 0 | WBSEDCL | 3.17 | 0 | 0
686 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001613/2022-2023 | 534/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 11.39 | 7.12 | 20
687 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Contai Saline Area Zone-IV Part-I Piped Water Supply Scheme Deshopran Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001983/2022-2023 | 891/W/MMD | 27/03/2023 | 180 | GANGULY ENGINEERING CO. | 23.69 | 0 | 0
688 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Additional Electrict quotation bill for TW-II of Radhamohanpur pwss (Ref Consumar ID-860303412),Application No-100000110832,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01364/2024-2025 | BP-2024-25-378 | 08/07/2024 | 0 | WBSEDCL | 0.43 | 0 | 0
689 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Radhamohanpur pwss (Ref Consumar ID-204439150),Application No-2004955822,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03035/2024-2025 | C112429737180 | 25/11/2024 | 0 | WBSEDCL | 3.57 | 0 | 0
690 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Radhamohanpur pwss (Ref Consumar ID-204210515),Application No-2004585811,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03735/2023-2024 | BP-2023-24-704 | 16/02/2024 | 0 | WBSEDCL | 5.95 | 0 | 0
691 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001942/2022-2023 | 827/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.65 | 10.5 | 45
692 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PRATAPPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002019/2022-2023 | 917/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 12.62 | 0 | 0
693 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR MANSUKA WATER SUPPLY SCHEME, T W NO 4 JJM WORKS, SCHEME CODE SM/15084, APPLICATION NO 2004759850, REFERENCE ID 204321898, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01170/2024-2025 | BP-2024-25-295 | 18/06/2024 | 0 | WBSEDCL | 2.71 | 0 | 0
694 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANSUKA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002017/2022-2023 | 915/W/MMD | 27/03/2023 | 180 | M/S. A.D. CONCERN | 13.68 | 12.82 | 80
695 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR RUPNARAYANPUR [ ZONE-III/ T W NO I ] WATER SUPPLY SCHEME, MINI- JINSAHAR , JJM WORKS, SCHEME CODE 16262, APPLICATION NO 2004652971, REFERENCE ID 204253744, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00312/2024-2025 | BP-2024-25-80 | 24/04/2024 | 0 | WBSEDCL | 1.47 | 0 | 0
696 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME ( JINSAR ), MINI, ZONE-III JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582814, REFERENCE ID 204206254, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00596/2024-2025 |  | 24/04/2024 | 0 | WBSEDCL | 0.12 | 0 | 0
697 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR RUPNARAYANPUR WATER SUPPLY SCHEME ( SOVANIPUR ), ZONE-III JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582809, REFERENCE ID 204206252, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03660/2023-2024 | BP-2023-24-703 | 16/02/2024 | 0 | WBSEDCL | 0.12 | 0 | 0
698 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR RUPNARAYANPUR WATER SUPPLY SCHEME [ JINSAR ] , ZONE-III/I, T W NO I, JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004582814, REFERENCE ID 204206254, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03778/2023-2024 | BP-2023-24-714 | 20/02/2024 | 0 | WBSEDCL | 0.12 | 0 | 0
699 | Midnapore Mechanical | Kharagpur Sub-Division | RUPNARAYANPUR WATER SUPPLY SCHEME,ZONE-III, T W - I , JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004606325, REFERENCE ID 204221223, KHARAGPUR CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04201/2023-2024 | BP-2023-24-780 | 06/03/2024 | 0 | WBSEDCL | 0.54 | 0 | 0
700 | Midnapore Mechanical | Kharagpur Sub-Division | RUPNARAYANPUR WATER SUPPLY SCHEME, MINI , ZONE - I , T W NO 1 , JJM WORKS, SCHEME CODE SM/16262, APPLICATION NO 2004614456, REFERENCE ID 204224878, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04202/2023-2024 | BP-2023-24-779 | 06/03/2024 | 0 | WBSEDCL | 0.11 | 0 | 0
701 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001968/2022-2023 | 880/W/MMD | 27/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 45.55 | 0 | 0
702 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Rupnarayanpur (Zone-I, II & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte.(Part-II) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002011/2022-2023 | 881/W/MMD | 27/03/2023 | 889 | M/S B ENTERPRISE | 17.88 | 7.95 | 80
703 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
704 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SRINAGAR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER CHANDRAKONA-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002021/2022-2023 | 919/W/MMD | 27/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 25.26 | 21.86 | 100
705 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURSHURI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000059/2023-2024 | 1231/W/MMD | 25/04/2023 | 676 | PRADIP KUMAR DHABAL | 25.24 | 0 | 80
706 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-I, (Ref. ID-204072720) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02536/2023-2024 | BP-2023-24-308 | 01/11/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
707 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for PURBA TEGHARI, Water Supply Scheme , T/W-II, (Ref. ID-204072721) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02537/2023-2024 | BP-2023-24-307 | 01/11/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
708 | Midnapore Mechanical | Contai Sub-Division | Additional Electric Quotiaton for PURBA TEGHARI Water Supply Scheme, T/W- I, (Ref. ID-860281573) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02878/2023-2024 | BP-2023-24-339 | 10/11/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
709 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Deshopran in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000049/2023-2024 | 1206/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 34.45 | 0 | 53
710 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601950/QUOT/03 DT. 15-02-2024 Application NO- 2004601950 Application type-New connection Reference Id- 204217839 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04265/2023-2024 |  | 01/03/2024 | 0 | WBSEDCL | 6.61 | 0 | 0
711 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of GARABAR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, MADHAKHALI C.C.C. Ref. Memo No- 2004625653/QUOT/03 DT. 01-03-2024 Application NO- 2004625653 Application type-New connection Consumer Id- 204232821 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04339/2023-2024 |  | 06/03/2024 | 0 | WBSEDCL | 5.56 | 0 | 0
712 | Midnapore Mechanical | Digha Sub-Division | Quotation For New Service Connections at Tube Well-I of Chirulia Chalta, Zone-I W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746276 Consumer ID.-204313776 Application Date.-29/05/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01137/2024-2025 | BP-2024-25-254 | 06/06/2024 | 0 | WBSEDCL | 13.67 | 0 | 0
713 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 20
714 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I OF THAUR PWSS. REF CONSUMER ID-204342953, APPLICATION NO-2004797675, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01471/2024-2025 | BP-2024-25-415 | 15/07/2024 | 0 | WBSEDCL | 3.08 | 0 | 0
715 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of Thaur PWSS. (Ref Consumer ID-204182374) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03343/2023-2024 | BP-2023-24-561 | 16/01/2024 | 0 | WBSEDCL | 3.12 | 0 | 0
716 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THAUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002003/2022-2023 | 905/W/MMD | 27/03/2023 | 950 | SUJOY RANJAN BHOWMICK | 27.37 | 18.46 | 25
717 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) at different villages (2 Nos.) under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur District Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000055/2023-2024 | 1227/W/MMD | 25/04/2023 | 180 | SOUMEN ELECTRIC | 12.14 | 0 | 0
718 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pratapdighi Accommodate FHTC under Potashpur-II Block within Purba Medinipur District in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000063/2023-2024 | 1222/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 11.76 | 0 | 0
719 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Contai Saline Area, Zone-IV PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001852/2022-2023 | 770/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 12.67 | 0 | 0
720 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Kanpur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001851/2022-2023 | 769/W/MMD | 23/03/2023 | 180 | SUBHASIS ROY | 12.67 | 0 | 0
721 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for load enhacement at Tw no-I of Ukhla water supply scheme. Consumer ID-200331903. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00267/2023-2024 |  | 22/05/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
722 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Rejuvenation of Electro-Mechanical components of Ukhla PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002123/2022-2023 | 1061/W/MMD | 29/03/2023 | 180 | ABHIJIT MUKHERJEE | 21.09 | 8.46 | 55
723 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BASANCHHARA Water supply scheme, Chandrakona -II block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000754/2023-2024 | 2284/W/MMD | 29/08/2023 | 180 | RSA ENTERPRISE | 30.18 | 24.19 | 100
724 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHUNRABILA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002206/2022-2023 | 587/W/MMD | 20/03/2023 | 180 | M/S NABIN GOPAL SENGUPTA | 25.24 | 24.78 | 100
725 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Rejuvenation of Electro-Mechanical components of Hatimasan PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002121/2022-2023 | 1059/W/MMD | 29/03/2023 | 180 | THE GODFATHER TRADING COMPANY | 5.07 | 5.07 | 60
726 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SAMSARA ZONE 2 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000033/2023-2024 | 1197/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.64 | 14.12 | 40
727 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670651/QUOT/03 DT. 05-04-2024 Application NO- 2004670651 Application type-New connection Consumer Id- 204266386 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00296/2024-2025 | BP-2024-25-49 | 18/04/2024 | 0 | WBSEDCL | 7.85 | 0 | 0
728 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DAKSHIN SHITALA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004905806/QUOT/03 DT. 18-09-2024 Application NO- 2004905806 Application type-New connection Consumer Id- 204402411 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02498/2024-2025 | C102415718521 | 05/10/2024 | 0 | WBSEDCL | 7.48 | 0 | 0
729 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-I of Nilkanthapur ws scheme under MMD,PHE Dte , Block-Ramnagar-I, DIGHA CCC Application no-2004764563 Con ID-204324292 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01233/2024-2025 | BP-2024-25-289 | 18/06/2024 | 0 | WBSEDCL | 5.95 | 0 | 0
730 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000165/2023-2024 | 1407/W/MMD | 02/06/2023 | 700 | SOUMEN ELECTRIC | 21.56 | 0 | 55
731 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF SALBANI AND IT'S ADJOINING MOUJAS PWSS, BLOCK - SALBONI, DIST.- PASCHIM MEDINIPUR. under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000036/2023-2024 | 1200/W/MMD | 25/04/2023 | 180 | MANORANJAN DEY | 25.26 | 0 | 0
732 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Shyampur pwss (Ref Consumar ID-204391666),Application No-2004886437,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02425/2024-2025 | BP-2024-25-682 | 27/09/2024 | 0 | WBSEDCL | 5.56 | 0 | 0
733 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SHYAMPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001894/2022-2023 | 793/W/MMD | 24/03/2023 | 903 | M/S B.M. ELECTRICAL | 21.56 | 13.57 | 40
734 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR KALARA WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/18502, APPLICATION NO 2004809520, REFERENCE ID 204352787, DASPUR CCC, WBSEDCL. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/01638/2024-2025 | BP-2024-25-487 | 30/07/2024 | 0 | WBSEDCL | 6.53 | 0 | 0
735 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR KALARA WATER SUPPLY SCHEME, T W NO II, JJM WORKS, SCHEME CODE SM/18502, APPLICATION NO 2004829551, REFERENCE ID 204362487,BLOCK- DASPUR-I, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/01851/2024-2025 | BP-2024-25-543 | 07/08/2024 | 0 | WBSEDCL | 3.01 | 0 | 0
736 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kalara Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000345/2023-2024 | 1684/W/MMD | 04/08/2023 | 905 | ALPHA ENTERPRISE | 37.86 | 27.25 | 60
737 | Midnapore Mechanical | Ghatal Subdivision | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
738 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HARIDHARPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000310/2023-2024 | 1629/W/MMD | 25/07/2023 | 180 | BHABANI PRASAD MANNA | 27.39 | 0 | 60
739 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-II, T W NO 1, JJM WORKS, SCHEME CODE SM/19053, APPLICATION NO 2004776674, REFERENCE ID 204331298, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01456/2024-2025 | BP-2024-25-419 | 15/07/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
740 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-I, T W NO 1, JJM WORKS, SCHEME CODE SM/19053, APPLICATION NO 2004796950, REFERENCE ID 204343402, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01457/2024-2025 | BP-2024-25-420 | 15/07/2024 | 0 | WBSEDCL | 4.86 | 0 | 0
741 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR BHETIA WATER SUPPLY SCHEME, ZONE-I, T W NO II, [ PURBA BHURKUNDI ], KGP-I, JJM WORKS, SCHEME CODE SM/19053, , APPLICATION NO 2004890152, REFERENCE ID 204393530, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/02977/2024-2025 | C112417250894 | 12/11/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
742 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Bhetia (Zone-I, II, III, and IV) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. .(Part-II) | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/001443/2023-2024 | 3099/W/MMD | 29/11/2023 | 180 | SUBHASIS ROY | 11.97 | 0 | 0
743 | Midnapore Mechanical | Contai Sub-Division | Satsatamal W/S scheme PH-I Application.-2004536916 Ref.-204169242 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03296/2023-2024 | BP-2023-24-533 | 11/01/2024 | 0 | WBSEDCL | 4.14 | 0 | 0
744 | Midnapore Mechanical | Contai Sub-Division | Satsatamal W/S scheme PH-II Application no.-2004544493 Ref.-204176804 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03456/2023-2024 | BP-2023-24-578 | 18/01/2024 | 0 | WBSEDCL | 9.26 | 0 | 0
745 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATSATMAL and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001364/2022-2023 | 2375/W/MMD | 31/12/2022 | 882 | AHALYA ENGINEERING WORKS | 25.25 | 18.31 | 90
746 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANAKPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001594/2022-2023 | 476/W/MMD | 20/03/2023 | 180 | M/S. SAJAHAN CHOWDHURY | 23 | 18.08 | 60
747 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Bhuta (Zone-I and II) and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000365/2023-2024 | 1695/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 45.31 | 35.64 | 50
748 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0
749 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
750 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for Gopinathpur PWSS Tube Well-I WS Scheme (Ref. ID 203917726) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00395/2022-2023 | BP-2022-23-143 | 24/03/2023 | 0 | WBSEDCL | 0.49 | 0 | 0
751 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for Gopinathpur PWSS Tube Well-II WS Scheme (Ref. ID 203917725) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00396/2022-2023 | BP-2022-23-144 | 24/03/2023 | 0 | WBSEDCL | 0.49 | 0 | 0
752 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopinathpur Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001605/2022-2023 | 530/W/MMD | 20/03/2023 | 180 | P.K.ENGINEERING | 22.78 | 21.15 | 50
753 | Midnapore Mechanical | Kharagpur Sub-Division | Service connection charge of WBSEDCL at Dantarda, Chandkuri | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001027/2021-2022 | 2003775012/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
754 | Midnapore Mechanical | Kharagpur Sub-Division | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Dontarda water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001135/2021-2022 | 2507/W/MMD | 30/11/2021 | 4 | DEBJYOTI BASU | 4.47 | 0 | 100
755 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Dontarda, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001173/2021-2022 | 119/W/MMD | 24/01/2022 | 120 | DEBKUMAR BASU | 6.52 | 3.87 | 0
756 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of GOLARANIJ W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609771/QUOT/03 DT. 21-02-2024 Application NO- 2004609771 Application type-New connection Reference Id- 204223235 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04385/2023-2024 | BP-2023-24-823 | 13/03/2024 | 0 | WBSEDCL | 5.82 | 0 | 0
757 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Golaranji, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001914/2022-2023 | 816/W/MMD | 24/03/2023 | 180 | MEGA SOLAR ENERGY | 11.79 | 0 | 85
758 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Dasagram PWSS Tube Well-II in connection Chandkuri CCC ( Consumer No. 2004164613) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00051/2022-2023 | BP-2022-23-101 | 18/01/2023 | 0 | WBSEDCL | 2.47 | 0 | 0
759 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Dasagram PWSS Tube Well-I near Hospital in connection Chandkuri CCC (Consumer No. 2004164602) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00052/2022-2023 | BP-2022-23-102 | 30/01/2023 | 0 | WBSEDCL | 2.41 | 0 | 0
760 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Dasha Gram & its adj. mouzas, Block - Sabang, Dist. - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001309/2022-2023 | 2311/W/MMD | 29/12/2022 | 180 | KAMAKSHYA ENTERPRISE | 25.14 | 22.55 | 0
761 | Midnapore Mechanical | Ghatal Subdivision | Installation of Dept. Submersible Pump motor set and with other supplied items and other allied works at Tubewell no 1 of Panna Water Supply Scheme Block Ghatal under MMD, PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001605/2023-2024 | 1546/MMSD-I | 12/12/2023 | 15 | SHOVAN KUMAR DAS | 1.29 | 0 | 100
762 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Panna Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001891/2022-2023 | 789/W/MMD | 24/03/2023 | 923 | A G ENTERPRISE | 22.77 | 9.34 | 80
763 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for Tube Well-III, Z-II of Thenkuachak W/S Scheme at Nandakumar CCC (2004173196) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00060/2022-2023 | BP-2022-23-110 | 01/03/2023 | 0 | WBSEDCL | 8.3 | 0 | 0
764 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for Tube Well-III, Z-I of Thenkuachak W/S Scheme at Nandakumar CCC (2004172999) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00061/2022-2023 | BP-2022-23-111 | 01/03/2023 | 0 | WBSEDCL | 1.11 | 0 | 0
765 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Thenkuachak PWSS to Accommodate FHTC in Nandakumar & Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District., under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001475/2022-2023 | 213/W/MMD | 10/02/2023 | 180 | DAS ENTERPRISE | 40.3 | 37.84 | 60
766 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Net-Metering Solar Power Plant quotation at Mohisda water supply scheme Zone-I, Tube Well-I Matangini CCC Block-Sahid Matangini Application No.-2004795833 Consumer ID.-222091158 Quotation Date.-26/06/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01450/2024-2025 | BP-2024-25-446 | 16/07/2024 | 0 | WBSEDCL | 0.01 | 0 | 0
767 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotiaton for Mahisda Water Supply Scheme zone-I, T/W-III (Ref. ID-204015583) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01669/2023-2024 | BP-2023-24-173 | 04/08/2023 | 0 | WBSEDCL | 8.05 | 0 | 0
768 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Net Billing Mahisda Zone-I,T/W-I Matangini CCC Application No=2004795833 Consumer ID=222091158 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02430/2024-2025 | BP-2024-25-773 | 28/10/2024 | 0 | WBSEDCL | 0.22 | 0 | 0
769 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Electric Quotation for MAHISDA Water Supply Scheme, T/W- III, Zone- I (Ref. ID-860281848) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02908/2023-2024 | BP-2023-24-320 | 01/11/2023 | 0 | WBSEDCL | 4.8 | 0 | 0
770 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) Zone-I Water Supply Scheme, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001931/2022-2023 | 850/W/MMD | 24/03/2023 | 180 | MUKHERJEE ART CENTRE | 12.37 | 11.32 | 65
771 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-I) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001957/2022-2023 | 860/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 23.7 | 0 | 0
772 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charges of WBSEDCL for Bikini Nischintapur, Badalpur, Sabang additional T/W-III of Bikini Nischintapur W/S Scheme(Consumer No. 2004156126) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00049/2022-2023 | BP-2022-23-90 | 04/01/2023 | 0 | WBSEDCL | 2.2 | 0 | 0
773 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No III of Bhikini Nischintapur Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE.TSM009947 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000236/2023-2024 | 602/MMSD-I | 05/06/2023 | 15 | SRI KRISHNA NIRMAN | 5.76 | 5.76 | 100
774 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Continuation work order for hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001225/2023-2024 | 922/MMSD-I | 08/08/2023 | 30 | M/S BIKASH DE | 0.15 | 0.15 | 100
775 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Continuation work order for hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001245/2023-2024 | 894/MMSD-I | 04/08/2023 | 30 | SUBHASIS ROY | 0.15 | 0 | 0
776 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Bhikini Nischintapur water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001537/2022-2023 | 1336/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 3.74 | 50
777 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001696/2022-2023 | 610/W/MMD | 20/03/2023 | 180 | SRI KRISHNA NIRMAN | 10.79 | 5.85 | 48
778 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
779 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.06 | 100
780 | Midnapore Mechanical | Ghatal Subdivision | KOTULPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/09988, APPLICATION NO 2004606465, REFERENCE ID 204221239, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04221/2023-2024 | BP-2023-24-768 | 04/03/2024 | 0 | WBSEDCL | 2.67 | 0 | 0
781 | Midnapore Mechanical | Ghatal Subdivision | KOTULPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/09988, APPLICATION NO 2004606516, REFERENCE ID 204221238, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04223/2023-2024 | BP-2023-24-767 | 04/03/2024 | 0 | WBSEDCL | 4.14 | 0 | 0
782 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Kutulpur Water supply scheme,Ghatal block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000391/2024-2025 | 2007/W/MMD | 30/08/2024 | 180 | M/S S M ELECTRICAL | 27 | 4.5 | 80
783 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
784 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Eletrict quotation bill for Atla water supply scheme at PH-II(Consumar Id-860286126) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03070/2023-2024 |  | 28/11/2023 | 0 | WBSEDCL | 2.88 | 0 | 0
785 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Antla Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000001/2023-2024 | 1103/W/MMD | 05/04/2023 | 180 | WEST BENGAL ENGINEERING CO. | 23.74 | 22.68 | 87
786 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new connection at Bamanpur w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004732591, Ref ID 204305895) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01366/2024-2025 | BP-2024-25-376 | 08/07/2024 | 0 | WBSEDCL | 10.38 | 0 | 0
787 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAMANPUR and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001600/2022-2023 | 504/W/MMD | 20/03/2023 | 895 | SUJOY RANJAN BHOWMICK | 21.62 | 10.07 | 50
788 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for MOYNA Water Supply Scheme T/W-III, Zone-I, (Ref. ID-204143546) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03134/2023-2024 | BP-2023-24-408 | 09/12/2023 | 0 | WBSEDCL | 4.7 | 0 | 0
789 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for MOYNA Water Supply Scheme T/W-IV, Zone-I, (Ref. ID-204136064) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03186/2023-2024 | BP-2023-24-437 | 18/12/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
790 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Augmentation of Moyna (Zone-I) PWSS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001752/2022-2023 | 645/W/MMD | 20/03/2023 | 529 | SOUMEN ELECTRIC | 27.17 | 26.82 | 60
791 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004686002/QUOT/03 DT. 16-04-2024 Application NO- 2004686002 Application type-New connection Consumer Id- 204277214 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00574/2024-2025 | BP-2024-25-104 | 26/04/2024 | 0 | WBSEDCL | 5.44 | 0 | 0
792 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004685984/QUOT/03 DT. 16-04-2024 Application NO- 2004685984 Application type-New connection Consumer Id- 204277213 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00575/2024-2025 | BP-2024-25-103 | 26/04/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
793 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
794 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KSHETRAPAL and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001637/2022-2023 | 517/W/MMD | 20/03/2023 | 804 | KARUNAMOY ENGINEERING | 22.75 | 0 | 70
795 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - IV at GOBINDAPUR Zone-II Water supply scheme,Block : Shahid Matangini, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001176/2023-2024 | 2612/W/MMD | 19/09/2023 | 180 | PURUSHOTTAM ENTERPRISE | 13.17 | 0 | 0
796 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOBINDAPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002197/2022-2023 | 454/W/MMD | 20/03/2023 | 540 | S.S.ENTERPRISES | 21.62 | 0 | 20
797 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HARINAN Water Supply Scheme , (Ref. ID-204069690) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01871/2023-2024 | W/23-24/224 | 01/09/2023 | 0 | WBSEDCL | 3.04 | 0 | 0
798 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for HARINAN, Water Supply Scheme T/W-II , (Ref. ID-204069696) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01872/2023-2024 | W/23-24/225 | 01/09/2023 | 0 | WBSEDCL | 3.25 | 0 | 0
799 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
800 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARINAN PWSS and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001333/2022-2023 | 2338/W/MMD | 29/12/2022 | 180 | DEY ENTERPRISE | 23.7 | 22.63 | 85
801 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
802 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARADA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004847092/QUOT/03/1184 DT. 13-08-2024 Application NO- 2004847092 Application type-New connection Consumer Id- 204372857 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02122/2024-2025 | C082448216760 | 02/09/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
803 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARDA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001402/2022-2023 | 2413/W/MMD | 31/12/2022 | 180 | ECO ENTERPRISE | 22.8 | 9.45 | 35
804 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004781161/QUOT/03 DT. 19-06-2024 Application NO- 2004781161 Application type-New connection Consumer Id- 204333913 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01330/2024-2025 | BP-2024-25-358 | 01/07/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
805 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886291/QUOT/03/582 DT. 06-09-2024 Application NO- 2004886291 Application type-New connection Consumer Id- 204391659 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02450/2024-2025 | C092443181197 | 27/09/2024 | 0 | WBSEDCL | 3.46 | 0 | 0
806 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALYANPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001348/2022-2023 | 2359/W/MMD | 31/12/2022 | 912 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 80
807 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Basantachak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004756260, Ref ID 204319518) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01700/2024-2025 | BP-2024-25-492 | 29/07/2024 | 0 | WBSEDCL | 5.19 | 0 | 0
808 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Basantachak w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608977, Ref ID-204222619) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04497/2023-2024 | BP-2023-24-853 | 16/03/2024 | 0 | WBSEDCL | 2.96 | 0 | 0
809 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BASANTA CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001330/2022-2023 | 2335/W/MMD | 29/12/2022 | 180 | ORIENTAL ENGINEERING CO. | 23.68 | 21.94 | 80
810 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Radhaballavchak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631522, Ref ID 204237226) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04736/2023-2024 | BP-2023-24-907 | 28/03/2024 | 0 | WBSEDCL | 7.1 | 0 | 0
811 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Radhaballavchak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631928, Ref ID 204238450) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04746/2023-2024 | BP-2023-24-908 | 28/03/2024 | 0 | WBSEDCL | 11.33 | 0 | 0
812 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RADHABALLAV CHAK and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001335/2022-2023 | 2340/W/MMD | 29/12/2022 | 914 | S.G.TECHNICAL SERVICE | 23.58 | 0 | 80
813 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Belda to Accommodate FHTC under Narayangarh Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001608/2022-2023 | 531/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.79 | 21.52 | 80
814 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674624/QUOT/03 DT. 09-04-2024 Application NO- 2004674624 Application type-New connection Consumer Id- 204269445 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00506/2024-2025 | BP-2024-25-88 | 24/04/2024 | 0 | WBSEDCL | 7.55 | 0 | 0
815 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TELAMI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674680/QUOT/03 DT. 09-04-2024 Application NO- 2004674680 Application type-New connection Consumer Id- 204269489 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00508/2024-2025 | BP-2024-25-89 | 24/04/2024 | 0 | WBSEDCL | 5.15 | 0 | 0
816 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TELAMI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001344/2022-2023 | 2355/W/MMD | 31/12/2022 | 180 | SOUMEN ELECTRIC | 21.56 | 15.29 | 70
817 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-IV, Zone-II (Ref. ID-204049361) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01675/2023-2024 | BP-2023-24-155 | 04/08/2023 | 0 | WBSEDCL | 2.97 | 0 | 0
818 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-I, Zone-II (Ref. ID-204049345) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01676/2023-2024 | BP-2023-24-156 | 04/08/2023 | 0 | WBSEDCL | 0.97 | 0 | 0
819 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-II, Zone-II (Ref. ID-204049556) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01677/2023-2024 | BP-2023-24-157 | 04/08/2023 | 0 | WBSEDCL | 2.4 | 0 | 0
820 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049047) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01678/2023-2024 | BP-2023-24-158 | 04/08/2023 | 0 | WBSEDCL | 2.3 | 0 | 0
821 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for Chargeable Head, SHILLABERIA JANKA, Water Supply Scheme T/W-IV, Zone-I (Ref. ID-204049555) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01679/2023-2024 | BP-2023-24-159 | 04/08/2023 | 0 | WBSEDCL | 2.8 | 0 | 0
822 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Shillaberia Jhanka PWSS to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District Zone-II,under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000082/2023-2024 | 1274/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 50.28 | 34.45 | 70
823 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Khejuri Zone II w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640039, Ref ID - 204244094) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04493/2023-2024 | BP-2023-24-850 | 16/03/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
824 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Khejuri Zone II w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004639938, Ref ID - 204243679) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04494/2023-2024 | BP-2023-24-851 | 16/03/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
825 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-II (Phase-II)under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000091/2023-2024 | 1280/W/MMD | 04/05/2023 | 719 | DEBJYOTI BASU | 40.2 | 25.05 | 25
826 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769073/QUOT/03/443 DT. 11-06-2024 Application NO- 2004769073 Application type-New connection Consumer Id- 204327178 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01277/2024-2025 | BP-2024-25-334 | 25/06/2024 | 0 | WBSEDCL | 4.79 | 0 | 0
827 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SAHARA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004769176/QUOT/03/442 DT. 11-06-2024 Application NO- 2004769176 Application type-New connection Consumer Id- 204327965 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01279/2024-2025 | BP-2024-25-333 | 25/06/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
828 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHARA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002032/2022-2023 | 940/W/MMD | 28/03/2023 | 856 | SUJOY RANJAN BHOWMICK | 27.69 | 16.57 | 60
829 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Barasubarnanagar PWSS Tube Well- III in connection Mukundapur CCC (2004188348) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00059/2022-2023 | BP-2022-23-109 | 01/03/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
830 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Boosting Tube Well No. III for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District.under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000133/2023-2024 | 1354/W/MMD | 24/05/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 12.5 | 40
831 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well (Head Work) & 1 (One) No. Boosting Tube Well for Barasubarnanagar Water Supply Scheme for Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001343/2022-2023 | 36/W/MMD | 04/01/2023 | 360 | SOUMEN ELECTRIC | 13.57 | 12.8 | 80
832 | Midnapore Mechanical | Digha Sub-Division | Ramnagar W/S scheme T/W-I, Zone-II Application-2004536109 Ref.-204168170 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03289/2023-2024 | BP-2023-24-541 | 11/01/2024 | 0 | WBSEDCL | 5.06 | 0 | 0
833 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ramnagar (Zone-II) PWSS, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001917/2022-2023 | 821/W/MMD | 24/03/2023 | 180 | M/S SWAPAN BANERJEE | 27.17 | 12.76 | 45
834 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation bill for Tw no-I of Kelegoda water supply scheme. Ref Consumer ID-204087644. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02665/2023-2024 | BP-2023-24-264 | 26/09/2023 | 0 | WBSEDCL | 3.99 | 0 | 0
835 | Midnapore Mechanical | Ghatal Subdivision | Electric Quotation bill for Tw No-II of Kelegoda water supply scheme. Ref Consumer ID-204087648. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02666/2023-2024 | BP-2023-24-263 | 26/09/2023 | 0 | WBSEDCL | 2.87 | 0 | 0
836 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based PWSS for Kelegoda & its adjoining mouzas Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001300/2022-2023 | 2302/W/MMD | 29/12/2022 | 720 | DEBJYOTI BASU | 22.87 | 14.31 | 50
837 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ADDITIONAL ELECTRIC QUOTATION BILL FOR TW NO-II OF MAHISHAMURA PWSS DUE TO WAY LEAVE PROBLEM I.R.O APPLICATION NO-2004578943, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, REFERENCE ID-860304242, APPLICATION ID-100000111812, NAME OF CCC- KESHIARY CCC, BLOCK-KESHIARY. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01852/2024-2025 | BP-2024-25-544 | 07/08/2024 | 0 | WBSEDCL | 0.81 | 0 | 0
838 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ADDITIONAL ELECTRIC QUOTATION BILL FOR TW NO-I OF MAHISHAMURA PWSS DUE TO WAY LEAVE DISPUTE. REF ID-860310382, APPLICATION NO-2004543905, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION., NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02112/2024-2025 | BP-2024-25-624 | 02/09/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
839 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-I of Mahisamura PWSS.(Ref Consumer ID-204175254) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03331/2023-2024 | BP-2023-24-556 | 16/01/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
840 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of MAHISHAMURAPWSS. REF CONSUMER ID-204204415, APPLICATION NO-2004578943, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03577/2023-2024 | BP-2023-24-634 | 08/02/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
841 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MAHISAMURA PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001425/2023-2024 | 3077/W/MMD | 29/11/2023 | 489 | DAS ENTERPRISE | 22.6 | 14.53 | 20
842 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Haludbari w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004785778, Ref ID 204336496) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01365/2024-2025 | BP-2024-25-377 | 08/07/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
843 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for Haludbari Water Supply scheme Tube well no.-I Khejuri CCC Block-Khejuri Application No.-2004645013 Ref ID.-204247115 Quatation Bill Date.-14/03/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04572/2023-2024 | BP-2023-24-888 | 22/03/2024 | 0 | WBSEDCL | 4.93 | 0 | 0
844 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HALUD BARI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001652/2022-2023 | 524/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 15.86 | 48
845 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of AYMABAR BERYA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004775224/QUOT/03 DT. 14-06-2024 Application NO- 2004775224 Application type-New connection Consumer Id- 204330602 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01331/2024-2025 | BP-2024-25-355 | 01/07/2024 | 0 | WBSEDCL | 10.56 | 0 | 0
846 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of AYMABAR BARIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878127/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/350 DT. 30/08/2024 Application NO- 2004878127 Application type-New connection Consumer Id- 204387570 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02448/2024-2025 | C102415716055 | 05/10/2024 | 0 | WBSEDCL | 3.99 | 0 | 0
847 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AYMABAR BARYA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001649/2022-2023 | 542/W/MMD | 20/03/2023 | 1017 | SOUMEN ELECTRIC | 21.56 | 15.29 | 60
848 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for PASCHIMBAR Water Supply Scheme T/W-I, (Ref. ID-204104644) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03057/2023-2024 | BP-2023-24-390 | 02/12/2023 | 0 | WBSEDCL | 1.05 | 0 | 0
849 | Midnapore Mechanical | Contai Sub-Division | Paschimbarh W/S scheme T/W No.-II (Laxmi Mandir) Applicatiot No.-2004522520 Ref.-204156806 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03179/2023-2024 | BP-2023-24-479 | 27/12/2023 | 0 | WBSEDCL | 4.86 | 0 | 0
850 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-I of Dudhebudhe PWSS. (Ref Consumer ID-204136081) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02992/2023-2024 | BP-2023-24-384 | 02/12/2023 | 0 | WBSEDCL | 4.06 | 0 | 0
851 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-II of Dudhebudhe PWSS. (Ref Consumer ID-204136079) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02993/2023-2024 | BP-2023-24-383 | 02/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
852 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUDHE BUDE AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001448/2023-2024 | 3081/W/MMD | 29/11/2023 | 180 | SANKAR PRASAD DUTTA AND CO | 22.99 | 8.81 | 30
853 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Bahurupa PWSS tw- II within Narayangarh block Application No- 2004845777 Ref No - 204370313 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02443/2024-2025 | C092443173799 | 27/09/2024 | 0 | WBSEDCL | 4.41 | 0 | 0
854 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
855 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KASBAPATASHPUR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001353/2022-2023 | 2364/W/MMD | 31/12/2022 | 180 | JAL PRAVAHIKA PVT. LTD. | 23.44 | 0 | 0
856 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743549/QUOT/03 DT. 25-05-2024 Application NO- 2004743549 Application type-New connection Consumer Id- 204312620 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01202/2024-2025 | BP-2024-25-318 | 24/06/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
857 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of AMARPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004793608/QUOT/03 DT. 25-06-2024 MEMO NO: AMR/PHE/223 DT. 25-06-2024 Application NO- 2004793608 Application type-New connection Consumer Id- 204340910 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01369/2024-2025 | BP-2024-25-373 | 08/07/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
858 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMARPUR and ADJOINING MOUJAS, Block potaspur- I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002029/2022-2023 | 937/W/MMD | 28/03/2023 | 710 | MENAKA ENTERPRISE | 22.77 | 13.33 | 50
859 | Midnapore Mechanical | Ghatal Subdivision | Service connection charge of WBSEDCL at Bhagirathpur Zone-I | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00038/2022-2023 | BP-2022-23-96 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
860 | Midnapore Mechanical | Ghatal Subdivision | Service Connection charges of WBSEDCL at Bhagirathpur TW -II Water Supply Scheme Chowka | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00040/2022-2023 | BP-2022-23-97 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
861 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001315/2022-2023 | 2317/W/MMD | 29/12/2022 | 180 | M/S EMMESS | 6.01 | 6.01 | 90
862 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Bhagirathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Zone-II) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001973/2022-2023 | 883/W/MMD | 27/03/2023 | 180 | RISHAV ENTERPRISE | 6 | 5.45 | 100
863 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well No I of Zone II under Sherkhan Chack water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001134/2022-2023 | 2115/W/MMD | 28/11/2022 | 120 | BHABANI PRASAD MANNA | 11.56 | 0 | 0
864 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Sherkhanchak PWSS (Zone-II) to Accommodate FHTC in Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001476/2022-2023 | 214/W/MMD | 10/02/2023 | 445 | EMCON | 11.83 | 10.96 | 85
865 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of BARANGI PWSS. REF CONSUMER ID-204310410 APPLICATION NO-2004739361 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01032/2024-2025 | BP-2024-25-213 | 28/05/2024 | 0 | WBSEDCL | 4.88 | 0 | 0
866 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARANGI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001946/2022-2023 | 834/W/MMD | 24/03/2023 | 180 | BHAGIRATHI JUTH AND HOLDINGS PVT LTD | 23.76 | 0 | 0
867 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of GOBARDHANPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004595917/QUOT/03 DT. 12-02-2024 Application NO- 2004595917 Application type-New connection Consumer Id- 204213656 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01134/2024-2025 | BP-2024-25-250 | 06/06/2024 | 0 | WBSEDCL | 3.79 | 0 | 0
868 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of Gabardhanpur W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004595896/QUOT/03 DT. 12-03-2024 Application NO- 2004595896 Application type-New connection CONSUMER ID: 204213657 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04738/2023-2024 | BP-2023-24-921 | 28/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
869 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GABARDHANPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001639/2022-2023 | 519/W/MMD | 20/03/2023 | 180 | RMD TRADING | 22.76 | 0 | 0
870 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF SOHAGPUR PWSS. REF CONSUMER ID-204373750, APPLICATION NO-2004853006, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02013/2024-2025 | BP-2024-25-583 | 20/08/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
871 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF SOHAGPUR PWSS. REF CONSUMER ID-204373749, APPLICATION NO-2004852981, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02018/2024-2025 | BP-2024-25-582 | 20/08/2024 | 0 | WBSEDCL | 3.21 | 0 | 0
872 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of UTTAR PIASALA PWSS. REF CONSUMER ID-204188705, APPLICATION NO-2004550684, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03732/2023-2024 | BP-2023-24-693 | 16/02/2024 | 0 | WBSEDCL | 2.92 | 0 | 0
873 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of UTTAR PIASALA PWSS. REF CONSUMER ID-204200349, APPLICATION NO-2004571244 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03733/2023-2024 | BP-2023-24-694 | 16/02/2024 | 0 | WBSEDCL | 4.26 | 0 | 0
874 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0
875 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for UTTAR PIASHALA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001895/2022-2023 | 794/W/MMD | 24/03/2023 | 180 | PADMA ENGINEERING CO. | 21.55 | 12.5 | 20
876 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for khamra pwss at TW-I (Ref Id-204169703) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03243/2023-2024 | BP-2023-24-490 | 29/12/2023 | 0 | WBSEDCL | 6.37 | 0 | 0
877 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | lectrict quotation bill for TW-II of KHAMRA pwss (Ref Consumar ID-204235950),Application No-2004627275,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/04395/2023-2024 | BP-2023-24-814 | 13/03/2024 | 0 | WBSEDCL | 3.17 | 0 | 0
878 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Khamra PWSS, Block-Debra, Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001294/2022-2023 | 2297/W/MMD | 29/12/2022 | 914 | ABHIJIT BASU | 22.87 | 12.1 | 45
879 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of PANCHYAR PWSS. REF CONSUMER ID-204234627, APPLICATION NO-2004627392, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04582/2023-2024 | BP-2023-24-892 | 21/03/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
880 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of PANCHYAR PWSS. REF CONSUMER ID-204234628, APPLICATION NO-2004627380 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04586/2023-2024 | BP-2023-24-891 | 22/03/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
881 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PANCHYAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001422/2023-2024 | 3073/W/MMD | 29/11/2023 | 180 | CONCORD ENGINEERING | 21.56 | 0 | 0
882 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of BAMANBIRUAN PWSS. REF CONSUMER ID-204244321, APPLICATION NO-2004640141, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02388/2024-2025 | C092403245767 | 04/09/2024 | 0 | WBSEDCL | 6.16 | 0 | 0
883 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of BAMANBIRUAN PWSS. REF CONSUMER ID-204183585, APPLICATION NO-2004552319, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04059/2023-2024 | BP-2023-24-747 | 27/02/2024 | 0 | WBSEDCL | 4.81 | 0 | 0
884 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAMANBIRUA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001385/2022-2023 | 2396/W/MMD | 31/12/2022 | 899 | M/S EMMESS | 22.89 | 14.77 | 20
885 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of BAMANDA PWSS. REF CONSUMER ID-204302072, APPLICATION NO-2004723744, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01023/2024-2025 | BP-2024-25-212 | 28/05/2024 | 0 | WBSEDCL | 2.35 | 0 | 0
886 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of BAMANDA PWSS. REF CONSUMER ID-204212537, APPLICATION NO-2004593868, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03739/2023-2024 | BP-2023-24-691 | 16/02/2024 | 0 | WBSEDCL | 4.5 | 0 | 0
887 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAMANDA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001606/2022-2023 | 486/W/MMD | 20/03/2023 | 652 | DIPALI CONSTRUCTION | 22.98 | 10.62 | 20
888 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KULDIHA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/001576/2022-2023 | 460/W/MMD | 20/03/2023 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 50
889 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
890 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Piped Water Supply Scheme for Sankarpur Zone-II Ramnagar I Blockunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/002046/2022-2023 | 887/W/MMD | 27/03/2023 | 180 | R.S. ENTERPRISE | 11.4 | 0 | 0
891 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001988/2022-2023 | 895/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 11.84 | 0 | 0
892 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SILAMPUR Water Supply Scheme T/W-III, (Ref. ID-204134606) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02997/2023-2024 | BP-2023-24-361 | 24/11/2023 | 0 | WBSEDCL | 3.71 | 0 | 0
893 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001986/2022-2023 | 894/W/MMD | 27/03/2023 | 180 | SUBHASIS ROY | 11.84 | 11.09 | 85
894 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAINCHA W/S Scheme under MMD, PHE, Dte. Block- Egra-II, BALIGHAI C.C.C. Ref. Memo No- 2004626460/QUOT/03 DT. 01-03-2024 Application NO- 2004626460 Application type-New connection Consumer Id- 204233927 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04507/2023-2024 | BP-2023-24-864 | 16/03/2024 | 0 | WBSEDCL | 5.54 | 0 | 0
895 | Midnapore Mechanical | Digha Sub-Division | "Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAINCHA AND ITS ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. ¿" | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002040/2022-2023 | 948/W/MMD | 28/03/2023 | 887 | A.S.ENTERPRISE | 21.57 | 9.57 | 90
896 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KATNADIGHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760145/QUOT/03 DT. 04-06-2024 Application NO- 2004760145 Application type-New connection Consumer Id- 204322030 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01237/2024-2025 | BP-2024-25-296 | 18/06/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
897 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR KURAN WATER SCHEME , T W NO NO 2 , APLLICATION 2004345710, REFERENCE ID 204027343, BIRSINGHA CCCC WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00587/2023-2024 | BP-2023-24-125 | 13/07/2023 | 0 | WBSEDCL | 0.51 | 0 | 0
898 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR KURAN WATER SCHEME , T W NO NO 1 , APLLICATION 2004345690, REFERENCE ID 204027368, BIRSINGHA CCCC WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00588/2023-2024 | BP-2023-24-124 | 13/07/2023 | 0 | WBSEDCL | 0.51 | 0 | 0
899 | Midnapore Mechanical | Ghatal Subdivision | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 40
900 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kuran & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001945/2022-2023 | 831/W/MMD | 24/03/2023 | 895 | WEST BENGAL ENGINEERING CO. | 22.63 | 15.52 | 80
901 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
902 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SHRIRAMPUR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/15120, APPLICATION NO 2004760170, REFERENCE ID 204322019, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01218/2024-2025 | BP-2024-25-294 | 18/06/2024 | 0 | WBSEDCL | 3.63 | 0 | 0
903 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Shrirampur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001748/2022-2023 | 651/W/MMD | 20/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 10.77 | 9.88 | 80
904 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIRCHAK TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001645/2022-2023 | 586/W/MMD | 20/03/2023 | 717 | M.DHARA & BROTHERS | 25.14 | 0 | 90
905 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of ELUNI PWSS. (Ref Consumer ID-204200310), Application No-2004571268, Application Type-New Connection, Name of CCC-Upperkuai. Block-Keshpur | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03542/2023-2024 | BP-2023-24-617 | 07/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
906 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of ELUNI PWSS. (Ref Consumer ID-204188708), APPLICATION NO-2004550744, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03550/2023-2024 | BP-2023-24-616 | 07/02/2024 | 0 | WBSEDCL | 2.88 | 0 | 0
907 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0
908 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ELUNI PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001618/2022-2023 | 535/W/MMD | 20/03/2023 | 803 | DEBJYOTI BASU | 22.78 | 14.24 | 25
909 | Midnapore Mechanical | Kharagpur Sub-Division | Electric Quotation for ADD Tw No-III of Raghunathchak w/s scheme.(Consumer ID-203972934) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00081/2023-2024 | BP-2023-24-27 | 04/05/2023 | 0 | WBSEDCL | 2.53 | 0 | 0
910 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001713/2022-2023 | 615/W/MMD | 20/03/2023 | 180 | CHAKRABORTY MINING & ENGINEERING | 10.78 | 10.56 | 80
911 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOBINDANAGAR, Water Supply Scheme T/W-I, Zone-I (Ref. ID-204056032) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01754/2023-2024 | BP-2023-24-177 | 08/08/2023 | 0 | WBSEDCL | 2.92 | 0 | 0
912 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOBINDANAGAR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048353) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01814/2023-2024 | BP-2023-24-197 | 18/08/2023 | 0 | WBSEDCL | 12.55 | 0 | 0
913 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for GOBINDANAGAR (ALALPARA)Water Supply Scheme Z-II, T/W-II (Ref. ID-204048367) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01815/2023-2024 | BP-2023-24-198 | 18/08/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
914 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional service connection charge at Gobindanagar, Zone-II, TW-IV Chiara, Chiara, Gobindanagar, Golghat Panskura Ref ID-860294542 Application ID-100000102262 Panskura CCC | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04383/2023-2024 | BP-2023-24-827 | 13/03/2024 | 0 | WBSEDCL | 1.83 | 0 | 0
915 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
916 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1(One)) No. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001395/2023-2024 | 3042/W/MMD | 17/11/2023 | 501 | SHIVAM ENTERPRISE | 13.68 | 2.95 | 80
917 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 3 (Three) Nos. Boosting Tube Well for Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002000/2022-2023 | 902/W/MMD | 27/03/2023 | 180 | M/S EMMESS | 40.78 | 40.07 | 70
918 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Tulia W/S scheme Application no.-2004555235 Ref.-204184819 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03534/2023-2024 | BP-2023-24-621 | 07/02/2024 | 0 | WBSEDCL | 16.04 | 0 | 0
919 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TULIA AND ADJOINING MOUJAS PWSS Tamluk Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001977/2022-2023 | 888/W/MMD | 27/03/2023 | 180 | M.D.ENTERPRISE | 23.65 | 11.02 | 35
920 | Midnapore Mechanical | Haldia Electrical Sub-Division | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT BHERI BHARANGA AND OTHER 20 PWSS IN PURBA MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001487/2022-2023 | 266/W/MMD | 20/02/2023 | 180 | SOUMEN ELECTRIC | 41.28 | 0 | 0
921 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Nahapar PWSS T/W- I , Application no- 2004677546 , ref. Id - 204270806 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00695/2024-2025 | BP-2024-25-141 | 09/05/2024 | 0 | WBSEDCL | 2.96 | 0 | 0
922 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
923 | Midnapore Mechanical | Kharagpur Sub-Division | Electric Quotation for Add Tw no-IV of Beluria w/s scheme. (Consumer ID-203972925) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00079/2023-2024 | BP-2023-24-29 | 04/05/2023 | 0 | WBSEDCL | 2.32 | 0 | 0
924 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for Add Tw no-III of Beluria w/s scheme. (Consumer ID-203972911) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00080/2023-2024 | BP-2023-24-28 | 04/05/2023 | 0 | WBSEDCL | 2.31 | 0 | 0
925 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well-IV of Beluria to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000173/2023-2024 | 1415/W/MMD | 02/06/2023 | 180 | AMIT DAS | 11.85 | 11.58 | 10
926 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Beluria (Part) to Accommodate FHTC under Jal Sapno Mission under Pingla Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001698/2022-2023 | 611/W/MMD | 20/03/2023 | 180 | MAA TARA ENTERPRISE | 10.76 | 10.33 | 25
927 | Midnapore Mechanical | Kharagpur Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
928 | Midnapore Mechanical | Kharagpur Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.09 | 100
929 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 20
930 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004714304/QUOT/03/142 DT. 03-05-2024 Application NO- 2004714304 Application type-New connection Consumer Id- 204294967 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01278/2024-2025 | BP-2024-25-337 | 25/06/2024 | 0 | WBSEDCL | 4.73 | 0 | 0
931 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-IV Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004941929/QUOT/03/769 DT. 25-10-2024 Application NO- 2004941929 Application type-New connection Consumer Id- 204428742 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03020/2024-2025 | C112429746394 | 25/11/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
932 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
933 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Dekhali w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640113, Ref ID - 204244140) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04492/2023-2024 | BP-2023-24-865 | 16/03/2024 | 0 | WBSEDCL | 8.79 | 0 | 0
934 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEKHALI and ADJOINING MOUJAS, Block ¿ Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001590/2022-2023 | 474/W/MMD | 20/03/2023 | 180 | KAMAKSHYA ENTERPRISE | 27.04 | 23.1 | 60
935 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for TAJPUR Boosting, Water Supply Scheme T/W (Ref. ID-204063651) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01823/2023-2024 | BP-2023-24-202 | 24/08/2023 | 0 | WBSEDCL | 3.86 | 0 | 0
936 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.71 | 35
937 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw no-I of Langamara PWSS.(Ref Consumer ID-204136076 | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03020/2023-2024 | BP-2023-24-381 | 02/12/2023 | 0 | WBSEDCL | 6.74 | 0 | 0
938 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-II of Lengamara PWSS.(Ref Conumer ID-204136078) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03021/2023-2024 | BP-2023-24-379 | 02/12/2023 | 0 | WBSEDCL | 4.36 | 0 | 0
939 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION IRO APPLICATION NO-2004495588, FOR TW NO-II of LANGAMARA PWSS. REF ID-860293842 , APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION., NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04332/2023-2024 | BP-2023-24-810 | 11/03/2024 | 0 | WBSEDCL | 1.44 | 0 | 0
940 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for LENGA MARA AND IT'S ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001426/2023-2024 | 3078/W/MMD | 29/11/2023 | 672 | S.P. ENTERPRISE | 22.65 | 15.73 | 20
941 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-1 of Badalpur ws scheme under MMD,PHE Dte. Block-Contai-I, Pichaboni CCC. Application no-2004641194. Con ID-204244743. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00009/2024-2025 | BP-2024-25-1 | 04/04/2024 | 0 | WBSEDCL | 0.86 | 0 | 0
942 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 60
943 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for JALPAI PART-II, Water Supply Scheme , T/W-III, (Ref. ID-204076620) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02190/2023-2024 | BP-2023-24-257 | 26/09/2023 | 0 | WBSEDCL | 5.72 | 0 | 0
944 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.64 | 35
945 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for SARIPUR Water Supply Scheme T/W-I, (Ref. ID-204064849) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02888/2023-2024 | BP-2023-24-309 | 01/11/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
946 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 8.1 | 55
947 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Deshopran in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000049/2023-2024 | 1206/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 34.45 | 0 | 53
948 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Sonachura PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001856/2022-2023 | 767/W/MMD | 23/03/2023 | 1 | M/S SWAPAN BANERJEE | 12.24 | 0 | 0
949 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Rajarampur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001854/2022-2023 | 772/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.65 | 10.53 | 82
950 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Bhagabanpur, Zone-I PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001844/2022-2023 | 761/W/MMD | 23/03/2023 | 180 | SOUMEN ELECTRIC | 12.22 | 9.89 | 60
951 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Madhabpur (Balighai) PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001843/2022-2023 | 760/W/MMD | 23/03/2023 | 180 | RAJIB COMPANY | 12.24 | 7.15 | 35
952 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Silampur PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001853/2022-2023 | 771/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.66 | 6.77 | 30
953 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KENCHKAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002013/2022-2023 | 911/W/MMD | 27/03/2023 | 886 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 14.69 | 95
954 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHANYAGACHHI TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002036/2022-2023 | 944/W/MMD | 28/03/2023 | 180 | DEBJYOTI BASU | 25.25 | 24.62 | 100
955 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Dwariberia PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001855/2022-2023 | 757/W/MMD | 23/03/2023 | 180 | M/S SWAPAN BANERJEE | 11.35 | 0 | 0
956 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Nijpapan pwss (Ref Consumar ID-204439149),Application No-2004955912,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03036/2024-2025 | C112429784294 | 25/11/2024 | 0 | WBSEDCL | 7.13 | 0 | 0
957 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Nijpapan pwss (Ref Consumar ID-204439153),Application No-2004955897,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03037/2024-2025 | C112429781413 | 25/11/2024 | 0 | WBSEDCL | 8.48 | 0 | 0
958 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NIJPAPAN AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001939/2022-2023 | 824/W/MMD | 24/03/2023 | 952 | P.K.ENGINEERING | 22.65 | 15.64 | 45
959 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MADHABPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001900/2022-2023 | 799/W/MMD | 24/03/2023 | 180 | BHABANI PRASAD MANNA | 21.62 | 0 | 0
960 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF KESHURIA [ ZONE-II/ T W -I] WATER SUPPLY ASCHEME [ APPLICATION --2004479640, REFERENCE ID ----204122245, NIMPURA CCC, QUOTATION NO ---2004479640/QUOT/03 DATED 26/10/2023, SCHEME NAME --- KESHURIA [ ZONE-II/ TW -I] . , SCHEME CODE ---SM/18192 , MB NO--3580 ] | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02916/2023-2024 | BP-2023-24-345 | 10/11/2023 | 0 | WBSEDCL | 0.51 | 0 | 0
961 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF KESHURIA [ ZONE-II/ T W -II] WATER SUPPLY ASCHEME [ APPLICATION --2004479660, REFERENCE ID ----204122246, NIMPURA CCC, QUOTATION NO ---2004479660/QUOT/03 DATED 26/10/2023, SCHEME NAME --- KESHURIA [ ZONE-II/ TW -II] . , SCHEME CODE ---SM/18192 , MB NO--3580 ] | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02917/2023-2024 | BP-2023-24-346 | 10/11/2023 | 0 | WBSEDCL | 4.04 | 0 | 0
962 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR KESHURIA WATER SUPPLY SCHEME, ZONE- I , T W NO I , [ DARKHOLA ] , JJM WORKS, SCHEME CODE SM/18192, APPLICATION NO 2004890131, REFERENCE ID 204393531, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02979/2024-2025 | C112417260038 | 12/11/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
963 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER Kharagpur - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000038/2023-2024 | 1187/W/MMD | 25/04/2023 | 180 | A G ENTERPRISE | 40.67 | 20.73 | 40
964 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
965 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Jarisai pwss (Zone-II) (Ref Consumar ID-204310810),Application No-2004741371,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01063/2024-2025 | BP-2024-25-199 | 24/05/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
966 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Jarisai pwss (Zone-II) (Ref Consumar ID-204310795),Application No-2004741390,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01072/2024-2025 | BP-2024-25-200 | 24/05/2024 | 0 | WBSEDCL | 5.43 | 0 | 0
967 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Jarisai (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000028/2023-2024 | 1192/W/MMD | 25/04/2023 | 712 | GOENKA ENTERPRISE | 22.76 | 17.36 | 50
968 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Kashida pwss (Zone-II) (Ref Consumar ID-204434298),Application No-2004944507,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03025/2024-2025 | C112429747814 | 25/11/2024 | 0 | WBSEDCL | 3.97 | 0 | 0
969 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Kashida (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000029/2023-2024 | 1193/W/MMD | 25/04/2023 | 716 | GOENKA ENTERPRISE | 22.63 | 17.25 | 50
970 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of ASTICHAK ZII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004749715/QUOT/03 DT. 05-06-2024 Application NO- 2004749715 Application type-New connection Consumer Id- 204317619 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01229/2024-2025 | BP-2024-25-299 | 18/06/2024 | 0 | WBSEDCL | 5.53 | 0 | 0
971 | Midnapore Mechanical | Digha Sub-Division | Supply delivery & laying of 25sq mm AL. armored cable at Pump House No-I of Astichak Zone-II water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000256/2025-2026 | 586/HESD | 19/06/2025 | 7 | SOUMEN ELECTRIC | 0.19 | 0 | 0
972 | Midnapore Mechanical | Digha Sub-Division | Making of Tube Well Foundation & others at Pump House no. III & IV of Astichak, Zone-II piped water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000265/2025-2026 | 603/HESD | 19/06/2025 | 7 | M/S B.M. ELECTRICAL | 0.57 | 0 | 0
973 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Astichak (Zone-II) PWSS Egra II Block under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001982/2022-2023 | 890/W/MMD | 27/03/2023 | 857 | M/S B.M. ELECTRICAL | 23.7 | 15.94 | 40
974 | Midnapore Mechanical | Contai Sub-Division | Quotation bill for Kanthi Bari Water supply scheme PH-I, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711599 Reference ID.-204294533 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00857/2024-2025 | BP-2024-25-161 | 15/05/2024 | 0 | WBSEDCL | 15.76 | 0 | 0
975 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KANTHI BARI and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001347/2022-2023 | 2358/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0
976 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MUKUNDAPUR and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001409/2022-2023 | 2420/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 14.3 | 51
977 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHISHAGOT AND IT'S ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001737/2022-2023 | 601/W/MMD | 20/03/2023 | 180 | SHAKEEL KHAN | 11.98 | 0 | 0
978 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service Connection charges of WBSEDCL for Additional T/W-III of Julkapur W/S Scheme (Consumer No. 2004156146) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00046/2022-2023 | BP-2022-23-89 | 04/01/2023 | 0 | WBSEDCL | 2.41 | 0 | 0
979 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Julkapur PWSS Tube Well-IV WS Scheme (Ref. ID 203938905) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00417/2022-2023 | BP-2022-23-154 | 29/03/2023 | 0 | WBSEDCL | 1.85 | 0 | 0
980 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Additional Tube Well-IV of Julkapur to Accommodate FHTC, Block - Sabang, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000130/2023-2024 | 1350/W/MMD | 24/05/2023 | 180 | SUBHASIS ROY | 11.88 | 11.1 | 93
981 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH NoIII of Julkapur Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE.TSM009944 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000238/2023-2024 | 606/MMSD-I | 06/06/2023 | 15 | EMCON | 5.76 | 5.76 | 100
982 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Julkapur water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001447/2022-2023 | 1335/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 4.13 | 50
983 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002042/2022-2023 | 950/W/MMD | 28/03/2023 | 180 | EMCON | 10.78 | 1.61 | 90
984 | Midnapore Mechanical | RWS Midnapur Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of JANKAPUR PWSS. REF CONSUMER ID-204298990, APPLICATION NO-2004720643, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | BILL/00880/2024-2025 | BP-2024-25-181 | 20/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0
985 | Midnapore Mechanical | RWS Midnapur Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of JANKAPUR PWSS. REF CONSUMER ID-204298988, APPLICATION NO-2004720671, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | BILL/00881/2024-2025 | BP-2024-25-180 | 20/05/2024 | 0 | WBSEDCL | 2.99 | 0 | 0
986 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gobradan w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No. 2004631559, Ref ID 204237227) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04737/2023-2024 | BP-2023-24-905 | 28/03/2024 | 0 | WBSEDCL | 9.24 | 0 | 0
987 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gobradan w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No 2004631550, 204237224) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04743/2023-2024 | BP-2024-25-16 | 08/04/2024 | 0 | WBSEDCL | 10.25 | 0 | 0
988 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II OF GHOSHPUR PWSS. REF CONSUMER ID-204294953, APPLICATION NO-2004713752, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01789/2024-2025 | C072449541730 | 02/08/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
989 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of GHOSHPUR PWSS. REF CONSUMER ID-204218492, APPLICATION NO-2004603166, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03779/2023-2024 | BP-2023-24-713 | 20/02/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
990 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GHOSHPUR PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000351/2023-2024 | 1686/W/MMD | 04/08/2023 | 678 | SHOVAN KUMAR DAS | 27.39 | 19.55 | 20
991 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0
992 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipment's at Newly sunk Tube well within NANDAKUMAR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001559/2023-2024 | 3174/W/MMD | 18/12/2023 | 180 | SOUMEN ELECTRIC | 96.15 | 55.59 | 20
993 | Midnapore Mechanical | Haldia Electrical Sub-Division | 11/0.433 KV, 1600 KVA Electrical Substation allied Electrical works at Chandipur GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001636/2023-2024 | 41/W/MMD | 10/01/2024 | 540 | THE MARKET ELECTRICAL ENGINEERING WORKS | 532.18 | 97.17 | 20
994 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electro-mechanical works for Nandakumar and Chandipur WTP SITE under Midnapore Mechanical Division, PHE Dte. under JJM in Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001638/2023-2024 | 42/W/MMD | 10/01/2024 | 733 | MACHINE SUPPLIERS SYNDICATE (P) LTD | 734.46 | 0 | 10
995 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electro-Mechanical works for Chandipur GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001641/2023-2024 | 43/W/MMD | 10/01/2024 | 528 | WEST BENGAL ENGINEERING CO. | 1578.72 | 0 | 20
996 | Midnapore Mechanical | Haldia Electrical Sub-Division | 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Nandakumar GLR Boosting station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001642/2023-2024 | 44/W/MMD | 10/01/2024 | 540 | APEX ENGINEERING & PROJECT CO | 533.06 | 115.61 | 20
997 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electro-Mechanical works for Nandakumar GLR Boosting Station under water supply scheme for Nandakumar and Chandipur Block in Purba Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001718/2023-2024 | 92/W/MMD | 24/01/2024 | 540 | ORIENTAL ENGINEERING CO. | 1405.35 | 0 | 20
998 | Midnapore Mechanical | Haldia Electrical Sub-Division | Hiring Vehicle for Site inspection of Nandakumar Chnadipur Surface based Project and Pingla Panskura Surface based Project under Midnapore Mechanical Division , P.H.E.Dte (Vehical No. WB-31A-3738) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001868/2024-2025 | 781//WMMD | 24/02/2025 | 365 | SUDIP KUMAR ROY | 7.78 | 0 | 70
999 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well within CHANDIPUR block, District - PURBA Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001875/2023-2024 | 903/W/MMD | 21/02/2024 | 180 | DEBJYOTI BASU | 192.31 | 102.72 | 20
1000 | Midnapore Mechanical | Haldia Electrical Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1001 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Augumentation of ground water based Barbasudebpur PWSS to accommodate FHTC in Haldia block under Haldia Sub Division of Tamluk Division in purba medinipur district under JJM program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000426/2023-2024 | 623/HESD | 17/08/2023 | 15 | SHIVAM ENTERPRISE | 3.5 | 3.24 | 75
1002 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well II under Barbasudebpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001138/2022-2023 | 2119/W/MMD | 28/11/2022 | 120 | M/S B.M. ELECTRICAL | 11.26 | 10.32 | 100
1003 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Barbasudevpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001518/2022-2023 | 362/W/MMD | 09/03/2023 | 180 | SHIVAM ENTERPRISE | 12.63 | 11.88 | 0
1004 | Midnapore Mechanical | Ghatal Subdivision | Laying of 25sq.mm armoured cable and electromechanical equipment at pump house no II of Jotghanashyam water supply scheme under Panschim Medinipur District under Midnapore Mechanical Division, P.H.E. Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002151/2022-2023 | 196/MMSD-I | 28/02/2023 | 7 | DIPALI CONSTRUCTION | 4.42 | 0 | 0
1005 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quatation for New service connection at Sijua T.W.No-II (Ref Id-203987545) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00113/2023-2024 | BP-2023-24-40 | 15/05/2023 | 0 | WBSEDCL | 4.17 | 0 | 0
1006 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001291/2022-2023 | 2294/W/MMD | 29/12/2022 | 520 | P.K.ENGINEERING | 11.44 | 10.64 | 20
1007 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for Gobindanagar PWSS T/W-I at under Daspur CCC | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00032/2022-2023 | BP-2022-23-82 | 27/12/2022 | 0 | WBSEDCL | 0.46 | 0 | 0
1008 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for Gobindanagar PWSS Tube Well-II at under Daspur Customer Care Centre | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00034/2022-2023 | BP-2022-23-83 | 27/12/2022 | 0 | WBSEDCL | 0.46 | 0 | 0
1009 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for Gobindanagar PWSS Tube Well-III (Ref. ID-203924590) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00162/2022-2023 | BP-2022-23-130 | 14/03/2023 | 0 | WBSEDCL | 0.47 | 0 | 0
1010 | Midnapore Mechanical | Ghatal Subdivision | Replacement and upgradation work of Voltage Stabilizer for Tube well No. 1 and 2 of Gobindanagar Water Supply Scheme Block Daspur I under MMD, PHE Dte., Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001303/2023-2024 | 1227/MMSD-I | 03/10/2023 | 30 | BALAJI CONSTRUCTION | 5.17 | 5.17 | 100
1011 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gobindanagar Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001375/2022-2023 | 2386/W/MMD | 31/12/2022 | 852 | BALAJI CONSTRUCTION | 22.89 | 17.48 | 100
1012 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gobindanagar(Add. Tube Well No.-III) Piped Water Supply Scheme under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001880/2022-2023 | 778/W/MMD | 24/03/2023 | 180 | S.S.GHORAI | 8.17 | 6.35 | 100
1013 | Midnapore Mechanical | Ghatal Subdivision | Supply and installation of chlorination and fenching and civil works for protection of pumping machinaries at Tube Well no III of Gobindanagar Water Supply Scheme [ Block- Daspur-I] under MMD, PHE Dte., Dist.- Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002710/2023-2024 | 318/MMSD-I | 04/03/2024 | 10 | S.S.GHORAI | 1.72 | 0 | 0
1014 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Baghaput in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000066/2023-2024 | 1225/W/MMD | 25/04/2023 | 180 | M/S. JIT ENTERPRISE | 26.93 | 0 | 0
1015 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply & delivery of submersible pump motor set & other electromechanical accessories at P/H No-I, under DURMUT Water Supply Scheme under MMD , P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000174/2023-2024 | 462/HESD | 13/06/2023 | 15 | DEBJYOTI BASU | 7.25 | 7.25 | 60
1016 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under durmut water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001220/2022-2023 | 2162/W/MMD | 08/12/2022 | 120 | DEBJYOTI BASU | 11.13 | 4.81 | 70
1017 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000180/2022-2023 | 2003987573/QUOT/03 | 11/07/2022 | 365 | WBSEDCL | 0.7 | 0 | 0
1018 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No III under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001141/2022-2023 | 2122/W/MMD | 28/11/2022 | 120 | SOUMEN ELECTRIC | 13.1 | 0.55 | 100
1019 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well No IV under Gopalpur water supply scheme under Midnapore Mechanical Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001142/2022-2023 | 2123/W/MMD | 28/11/2022 | 120 | MANORANJAN DEY | 13.12 | 12.89 | 75
1020 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation bill at Mahishadal CCC for T/W-II Gopalpur water supply scheme under MMD PHE Dte | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | VCH/001780/2022-2023 | BP-2022-23-26 | 10/08/2022 | 0 | WBSEDCL | 0.7 | 0 | 0
1021 | Midnapore Mechanical | Haldia Sub-Division | Electric quotation MAHISHADAL CCC at Gopalpur, Manashathan Water supply scheme under MMD PHE Dte | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | VCH/002769/2022-2023 | BP-2022-23-61 | 23/11/2022 | 0 | WBSEDCL | 0.5 | 0 | 0
1022 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for DHANGHARA Water Supply Scheme T/W-III, (Ref. ID-204049566) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01685/2023-2024 | BP-2023-24-165 | 04/08/2023 | 0 | WBSEDCL | 1.35 | 0 | 0
1023 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at DHANYAGARAHA Water supply scheme, contai - III block, District -Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000968/2024-2025 | 2338/W/MMD | 16/12/2024 | 180 | P.K.ENGINEERING | 24.97 | 0 | 65
1024 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Dhanghara, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001466/2022-2023 | 204/W/MMD | 10/02/2023 | 180 | M/S SREEJIT ENTERPRISE | 13.52 | 13.29 | 55
1025 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION FOR NEW POWER CONNECTION OF NARAYANBARH [AUG.] WATER SUPPLY ASCHEME [ APPLICATION --2004480446, REFERENCE ID ----204122723, SABONG CCC, QUOTATION NO ---2004480446/QUOT/03 DATED 26/10/2023, SCHEME NAME --- NARAYANBARH AUG. , SCHEME CODE ---SM/10779 , MB NO--3580 ] | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02885/2023-2024 | BP-2023-24-342 | 10/11/2023 | 0 | WBSEDCL | 7.58 | 0 | 0
1026 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001304/2022-2023 | 2306/W/MMD | 29/12/2022 | 180 | DEBKUMAR BASU | 10.79 | 6.79 | 70
1027 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
1028 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0.1 | 100
1029 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.09 | 100
1030 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at Z-I of TW-III of Chaitanyapur w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695240 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-11900W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00650/2024-2025 | BP-2024-25-114 | 06/05/2024 | 0 | WBSEDCL | 7.14 | 0 | 0
1031 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-IV, zone- I, (Ref. ID-204078116) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02605/2023-2024 | BP-2023-24-249 | 19/09/2023 | 0 | WBSEDCL | 10.52 | 0 | 0
1032 | Midnapore Mechanical | Haldia Sub-Division | Replacement of valves,re-new of rising line & others pumping arrangement works at Tube Well no. II, Zone-I of Chaitanyapur water supply scheme under Midnapore Mechanical Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000131/2025-2026 | 429/HESD | 23/04/2025 | 7 | S.B.ENTERPRISE | 0.42 | 0 | 0
1033 | Midnapore Mechanical | Haldia Sub-Division | Withdrawing & Lowering of defective submersible pumping machinery set at Zone-I, Pump House no. II of Chaitanyapur water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000178/2025-2026 | 525/HESD | 30/05/2025 | 7 | M/S B.M. ELECTRICAL | 0.09 | 0 | 0
1034 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - III at CHAITANYAPUR Zone-I Water supply scheme, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001174/2023-2024 | 2611/W/MMD | 19/09/2023 | 439 | THE GODFATHER TRADING COMPANY | 14.94 | 10.16 | 40
1035 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based CHAITANYAPUR Zone-I PWSS to Accommodate FHTC in Sutahata Block Under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001932/2022-2023 | 851/W/MMD | 24/03/2023 | 180 | ECO ENTERPRISE | 13.46 | 13.19 | 40
1036 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE- I Of AMARSHI KASBA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775131/QUOT/03 DT. 14-06-2024 Application NO- 2004775131 MEMO NO: AMR/PHE/175 DT.14/06/2024 Application type-New connection Consumer Id- 204330575 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01335/2024-2025 | BP-2024-25-361 | 01/07/2024 | 0 | WBSEDCL | 4.79 | 0 | 0
1037 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-I, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001904/2022-2023 | 805/W/MMD | 24/03/2023 | 880 | RITESH AGARWALL | 12.63 | 0 | 45
1038 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Zone- II of Tube well-I and II at Dakshin Chak Water supply scheme, Haldia block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001684/2023-2024 | 63/W/MMD | 15/01/2024 | 180 | SUJOY RANJAN BHOWMICK | 28.21 | 16.58 | 30
1039 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001723/2022-2023 | 635/W/MMD | 20/03/2023 | 799 | P.K.ENGINEERING | 27.18 | 19.11 | 30
1040 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household Tap Connection (FHTC) by Augmentation of T/W- III, Zone-I for Dakshin Chak Water Supply Scheme, Block - Haldia under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002726/2023-2024 | 1071/W/MMD | 14/03/2024 | 180 | DEBSANKER BHATTACHARYA | 13.59 | 0 | 0
1041 | Midnapore Mechanical | Contai Sub-Division | BRINDABANPUR w/s SCHEME PH.-I APPLICATION NO.-2004567517 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03536/2023-2024 | BP-2023-24-610 | 07/02/2024 | 0 | WBSEDCL | 5.95 | 0 | 0
1042 | Midnapore Mechanical | Contai Sub-Division | BRINDABANPUR w/s SCHEME PH.-II APPLICATION NO.-2004570658 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03537/2023-2024 | BP-2023-24-609 | 07/02/2024 | 0 | WBSEDCL | 4.06 | 0 | 0
1043 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BRINDABANPUR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001316/2022-2023 | 2318/W/MMD | 29/12/2022 | 180 | AHALYA ENGINEERING WORKS | 21.61 | 19.67 | 75
1044 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for RAMCHANDRAPUR Water Supply Scheme , (Ref. ID-204075844) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02185/2023-2024 | BP-2023-24-239 | 12/09/2023 | 0 | WBSEDCL | 3.95 | 0 | 0
1045 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAMCHANDRAPUR and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001332/2022-2023 | 2337/W/MMD | 29/12/2022 | 1068 | DEY ENTERPRISE | 23.7 | 11.09 | 65
1046 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Mayachar w/s scheme PH II in the district of Purba Medinipur (Application no 1007525986, Ref ID 106467535) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03780/2023-2024 | BP-2023-24-712 | 20/02/2024 | 0 | WBSEDCL | 6.18 | 0 | 0
1047 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Mayachar w/s scheme PH I in the district of Purba Medinipur (Application no 1007526112, Ref ID 106467554) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03781/2023-2024 | BP-2023-24-711 | 20/02/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
1048 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAYACHAR and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001397/2022-2023 | 2408/W/MMD | 31/12/2022 | 721 | S.G.ENTERPRISE | 21.6 | 21.27 | 100
1049 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DANGARTULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004706844/QUOT/03 DT. 29-04-2024 Application NO- 2004706844 MEMO NO: AMR/PHE/91 DT.29/04/2024 Application type-New connection Consumer Id- 204291543 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00854/2024-2025 | BP-2024-25-164 | 15/05/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
1050 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DANGAR TULSHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004862083/QUOT/03 DT. 16-08-2024 MEMO NO: AMR/PHE/330 DT. 16-08-2024 Application NO- 2004862083 Application type-New connection Consumer Id- 204378443 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02119/2024-2025 | C082448267203 | 02/09/2024 | 0 | WBSEDCL | 4.66 | 0 | 0
1051 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DANGAR TULSI and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001401/2022-2023 | 2412/W/MMD | 31/12/2022 | 882 | SUJOY RANJAN BHOWMICK | 22.8 | 9.04 | 35
1052 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 2nd Tube Well & 1 (One) No. Boosting Tube Well for Sofiabad Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001731/2022-2023 | 637/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 9.66 | 60
1053 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for CONTAI S.A. RAJ (PHASE-B) Water Supply Scheme T/W-II,Zone-III, (Ref. ID-204114270) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02907/2023-2024 | BP-2023-24-321 | 01/11/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
1054 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Zone-II), under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001513/2022-2023 | 357/W/MMD | 09/03/2023 | 180 | K.S.P. ENTERPRISE | 13.57 | 0 | 60
1055 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Contai Saline Area Zone-I PWSS to Accommodate FHTC in Contai-I & III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District (Phase-B), under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001744/2022-2023 | 642/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 13.58 | 0 | 0
1056 | Midnapore Mechanical | Contai Sub-Division | Pachahari W/S scheme PH-I Application.-2004537390 Ref.-204168886 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03297/2023-2024 | BP-2023-24-531 | 11/01/2024 | 0 | WBSEDCL | 4.08 | 0 | 0
1057 | Midnapore Mechanical | Contai Sub-Division | Pachahari W/S scheme PH-II Application.-2004537398 Ref.-204168891 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03298/2023-2024 | BP-2023-24-532 | 11/01/2024 | 0 | WBSEDCL | 3.16 | 0 | 0
1058 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1059 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Naichanpur W/S scheme Ph-I Application No.-204543058 Ref.-204175259 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03267/2023-2024 | BP-2023-24-514 | 09/01/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
1060 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Naichanpur W/S scheme PH-II Application No.-2004543088 Ref.-204175260 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03268/2023-2024 | BP-2023-24-513 | 09/01/2024 | 0 | WBSEDCL | 4.51 | 0 | 0
1061 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for NAICHHANPUR AND ADJOINING MOUJAS PWSS, Block Moyna, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000168/2023-2024 | 1411/W/MMD | 02/06/2023 | 180 | P.K.ENGINEERING | 27.53 | 0 | 0
1062 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Kunarpur PWSS PH - II within Narayangarh Block Application No - 2004909199, Ref ID - 204404484 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02967/2024-2025 | C102455618296 | 30/10/2024 | 0 | WBSEDCL | 4.96 | 0 | 0
1063 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Kunarpur PWSS PH - I within Narayangarh Block Application No - 2004909181, Ref ID - 204404487 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02968/2024-2025 | C102455616858 | 30/10/2024 | 0 | WBSEDCL | 3.69 | 0 | 0
1064 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
1065 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Dingal pwss (Ref Consumar ID-204198617),Application No-2004571068,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03553/2023-2024 | BP-2023-24-600 | 07/02/2024 | 0 | WBSEDCL | 0.51 | 0 | 0
1066 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Dingal pwss (Ref Consumar ID-204199250),Application No-2004571039,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03554/2023-2024 | BP-2023-24-599 | 07/02/2024 | 0 | WBSEDCL | 6.95 | 0 | 0
1067 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DINGAL AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001941/2022-2023 | 826/W/MMD | 24/03/2023 | 952 | P.K.ENGINEERING | 22.65 | 15.64 | 50
1068 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-I of Sahajadapur ws scheme under MMD,PHE Dte. Ref. Application no-2004579826, CON ID-204204429, under PICHABONI CCC, Block-CONTAI-I | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03655/2023-2024 | BP-2023-24-679 | 15/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
1069 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAHAJADAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001657/2022-2023 | 543/W/MMD | 20/03/2023 | 772 | SOUMEN ELECTRIC | 21.56 | 16.07 | 100
1070 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ADDITIONAL QUOTATION FOR TW NO-I OF CHANDANA PWSS DUE TO SITE CHANGE. APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION. NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY, REFERENCE ID-860308277, APPLICATION ID-100000116147. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02045/2024-2025 | BP-2024-25-606 | 29/08/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
1071 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of CHANDANA PWSS. (Ref Consumer ID-204175251) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03445/2023-2024 | BP-2023-24-585 | 25/01/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
1072 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF CHANDANA PWSS. (Ref Consumer ID-204175252) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03446/2023-2024 | BP-2023-24-584 | 25/01/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
1073 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHANDANA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001429/2023-2024 | 3083/W/MMD | 29/11/2023 | 641 | DIPALI CONSTRUCTION | 21.53 | 2.9 | 20
1074 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF GAZIPUR PATNA PWSS. REF CONSUMER ID-204362824, APPLICATION NO-2004829676, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01730/2024-2025 | BP-2024-25-498 | 30/07/2024 | 0 | WBSEDCL | 2.98 | 0 | 0
1075 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-II of GAZIPUR PATNA PWSS (REf CONSUMER ID-204183572) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03498/2023-2024 | BP-2023-24-583 | 25/01/2024 | 0 | WBSEDCL | 0.72 | 0 | 0
1076 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GAZIPUR PATNA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001947/2022-2023 | 835/W/MMD | 24/03/2023 | 737 | BHAGIRATHI JUTH AND HOLDINGS PVT LTD | 23.74 | 2.91 | 5
1077 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Amtalia Water Supply Scheme of Deshapran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001729/2022-2023 | 636/W/MMD | 20/03/2023 | 180 | SOUMEN ELECTRIC | 13.57 | 9.66 | 60
1078 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Dakshin Usutpur Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004690463 Reference ID=204279652 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00665/2024-2025 | BP-2024-25-166 | 15/05/2024 | 0 | WBSEDCL | 4.65 | 0 | 0
1079 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Dakshin Usutpur Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004690460 Reference ID=204279646 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00667/2024-2025 | BP-2024-25-167 | 15/05/2024 | 0 | WBSEDCL | 3.52 | 0 | 0
1080 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN UTASPUR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000084/2023-2024 | 1272/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.69 | 0 | 25
1081 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
1082 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
1083 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KALABERIA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001338/2022-2023 | 2343/W/MMD | 29/12/2022 | 180 | ORIENTAL ENGINEERING CO. | 25.24 | 0 | 0
1084 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ASHARI AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001899/2022-2023 | 798/W/MMD | 24/03/2023 | 1013 | BHABANI PRASAD MANNA | 21.62 | 0 | 80
1085 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HARI PURA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001431/2023-2024 | 3085/W/MMD | 29/11/2023 | 180 | M/S EMMESS | 22.79 | 14.69 | 20
1086 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER SUPPLY FOR SAKUI W/S SCHEME , T W NO 02, CONSUMER ID 204030395, SCHEME CODE SM/12826 , NIMPURA CCC WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01613/2023-2024 | BP-2023-24-130 | 19/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
1087 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SATKUI TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- I BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001610/2022-2023 | 533/W/MMD | 20/03/2023 | 180 | P.K.ENGINEERING | 22.78 | 10.6 | 45
1088 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF KHANDRUI PWSS. REF CONSUMER ID-204393520, APPLICATION NO-2004889527, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02454/2024-2025 | C102401983645 | 03/10/2024 | 0 | WBSEDCL | 6.62 | 0 | 0
1089 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF KHANDRUI PWSS. REF CONSUMER ID-204393518, APPLICATION NO-2004889496, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02459/2024-2025 | C102401983017 | 03/10/2024 | 0 | WBSEDCL | 5.19 | 0 | 0
1090 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Patna pwss (Ref Consumar ID-204251327),Application No-2004648431,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00285/2024-2025 | BP-2024-25-42 | 18/04/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
1091 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Patna pwss (Ref Consumar ID-204252309),Application No-2004648500,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00287/2024-2025 | BP-2024-25-41 | 18/04/2024 | 0 | WBSEDCL | 5.21 | 0 | 0
1092 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Patna PWSS, BLOCK - DEBRA Dist-Paschim Medinipur under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001302/2022-2023 | 2304/W/MMD | 29/12/2022 | 1274 | DEBJYOTI BASU | 22.87 | 14.31 | 50
1093 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of RANIOR PWSS.(Ref Consumer ID-204200356), APPLICATION NO-2004571235, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC- UPPERKUAI CCC. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03549/2023-2024 | BP-2023-24-614 | 07/02/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
1094 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of RANIOR PWSS.(Ref Consumer ID-204200319), APPLICATION NO-2004571260, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC- UPPERKUAI CCC, BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03551/2023-2024 | BP-2023-24-615 | 07/02/2024 | 0 | WBSEDCL | 4.85 | 0 | 0
1095 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PIPED WATER SUPPLY SCHEME FOR RANIAR AND IT'S ADJOINING MOUZASunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001432/2023-2024 | 3086/W/MMD | 29/11/2023 | 457 | M/S BARMAN ROY TRADERS | 25.52 | 6.28 | 20
1096 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURBA MAHAMMADPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877670/QUOT/03 DT. 12-09-2024 Application NO- 2004877670 Application type-New connection Consumer Id- 204397980 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02497/2024-2025 | C092445105167 | 30/09/2024 | 0 | WBSEDCL | 12.11 | 0 | 0
1097 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MAHAMMADPUR and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001667/2022-2023 | 550/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 11.03 | 55
1098 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Kukrada PWSS TW - II with in Narayangarh Block Application No - 2005005228 Ref ID - 204471132 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | BILL/03674/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 6.21 | 0 | 0
1099 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUKRADA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/001623/2022-2023 | 500/W/MMD | 20/03/2023 | 819 | PADMA ENGINEERING CO. | 23 | 0 | 80
1100 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
1101 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RANJAPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/15118, APPLICATION NO 2004816268, REFERENCE ID 204354168, BIRSHINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01735/2024-2025 | BP-2024-25-500 | 30/07/2024 | 0 | WBSEDCL | 3.09 | 0 | 0
1102 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RANJAPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15118, APPLICATION NO 2004816291, REFERENCE ID 204354170, BIRSHINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01736/2024-2025 | BP-2024-25-505 | 30/07/2024 | 0 | WBSEDCL | 6.72 | 0 | 0
1103 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ranjapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000194/2023-2024 | 1461/W/MMD | 13/06/2023 | 180 | TAPAN KUMAR SARKAR | 22.99 | 0 | 40
1104 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SAGARPUR WATER SUPPLY SCHEME, T W NO I, JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004809605, REFERENCE ID 204352801, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01629/2024-2025 | C072443748308 | 29/07/2024 | 0 | WBSEDCL | 10.81 | 0 | 0
1105 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SAGARPUR WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15119, [ NABODAY SANGHA ] APPLICATION NO 2004809587, REFERENCE ID 204352800, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01631/2024-2025 | C072443762107 | 29/07/2024 | 0 | WBSEDCL | 9.98 | 0 | 0
1106 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sagarpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001633/2022-2023 | 491/W/MMD | 20/03/2023 | 845 | INDTECH ASSOCIATES | 23 | 0 | 85
1107 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HRISINGPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Assistant Engineer,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Junior Engineer,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002037/2022-2023 | 945/W/MMD | 28/03/2023 | 180 | DEBJYOTI BASU | 25.25 | 24.68 | 5
1108 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BELDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607449/QUOT/03 DT. 21-02-2024 Application NO- 2004607449 Application type-New connection Consumer Id- 204223207 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04386/2023-2024 | BP-2023-24-824 | 13/03/2024 | 0 | WBSEDCL | 3.03 | 0 | 0
1109 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BELDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001349/2022-2023 | 2360/W/MMD | 31/12/2022 | 912 | WEST BENGAL ENGINEERING CO. | 23.67 | 0 | 50
1110 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of GAGANESHWAR PWSS. REF CONSUMER ID-204208789, APPLICATION NO-2004586829, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03578/2023-2024 | BP-2023-24-636 | 08/02/2024 | 0 | WBSEDCL | 4.03 | 0 | 0
1111 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of GAGANESHWAR PWSS. REF CONSUMER ID-204204420, APPLICATION NO-2004578826, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03579/2023-2024 | BP-2023-24-635 | 08/02/2024 | 0 | WBSEDCL | 7.11 | 0 | 0
1112 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GAGANESHWAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000679/2024-2025 | 2120/W/MMD | 01/10/2024 | 180 | ORIENTAL ENGINEERING CO. | 32.75 | 10 | 20
1113 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quatation for New service connection at Chakismilpur(Ref no-203987606) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00114/2023-2024 | BP-2023-24-65 | 06/06/2023 | 0 | WBSEDCL | 5.42 | 0 | 0
1114 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001511/2022-2023 | 355/W/MMD | 09/03/2023 | 180 | MANORANJAN DEY | 11.44 | 8.34 | 20
1115 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Benia pwss (Ref Consumar ID-204439151),Application No-2004955856,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03030/2024-2025 | C112429735070 | 25/11/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
1116 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Benia pwss (Ref Consumar ID-204439152),Application No-2004955874,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03031/2024-2025 | C112429730333 | 25/11/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
1117 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BENYA AND IT'S ADJOINING MOUJAS PWSS. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001601/2022-2023 | 484/W/MMD | 20/03/2023 | 1290 | SHOVAN KUMAR DAS | 23.01 | 17.35 | 65
1118 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ADDITIONAL QUOTATION FEE FOR EFFECTING NSC AT HATKATA PWSS. REF ID-860299035, APPLICATION ID-100000106465, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00688/2024-2025 | BP-2024-25-127 | 06/05/2024 | 0 | WBSEDCL | 0.01 | 0 | 0
1119 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II OF HATKATA PWSS. REF CONSUMER ID-204325523, APPLICATION NO-2004767096, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01212/2024-2025 | BP-2024-25-293 | 18/06/2024 | 0 | WBSEDCL | 5.49 | 0 | 0
1120 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ADDITIONAL QUOTATION FOR EFFECTING NSC IRO ASSISTANT ENGINEER PHE DTE FOR EFFECTING NSC IN REVISED ROUTE AT TW-I OF HATKATA PWSS, REFERENCE ID-860305080, APPLICATION ID-100000112900. APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01733/2024-2025 | C072445050786 | 30/07/2024 | 0 | WBSEDCL | 2.46 | 0 | 0
1121 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of HATKATA PWSS. REF CONSUMER ID-204210559, APPLICATION NO-2004589087, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03736/2023-2024 | BP-2023-24-699 | 16/02/2024 | 0 | WBSEDCL | 6.35 | 0 | 0
1122 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for HATKATA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002007/2022-2023 | 906/W/MMD | 27/03/2023 | 719 | JYOTY SOLAR POWER | 27.36 | 25.66 | 30
1123 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ MULBANDH] WATER SUPPLY ASCHEME [ APPLICATION --2004479472, REFERENCE ID ----204122244, NIMPURA CCC, QUOTATION NO ---2004479472/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ MULBANDH ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02911/2023-2024 | BP-2023-24-347 | 10/11/2023 | 0 | WBSEDCL | 0.51 | 0 | 0
1124 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GERIASULI-II] WATER SUPPLY ASCHEME [ APPLICATION --2004479502, REFERENCE ID ----204122241, NIMPURA CCC, QUOTATION NO ---2004479502/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GERIASULI-II ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02912/2023-2024 | BP-2023-24-354 | 13/11/2023 | 0 | WBSEDCL | 0.51 | 0 | 0
1125 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GURIAMARI] WATER SUPPLY ASCHEME [ APPLICATION --2004479524, REFERENCE ID ----204122240, NIMPURA CCC, QUOTATION NO ---2004479524/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GURIAMARI ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ], | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02913/2023-2024 | BP-2023-24-353 | 13/11/2023 | 0 | WBSEDCL | 3.5 | 0 | 0
1126 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GERIASULI-I] WATER SUPPLY ASCHEME [ APPLICATION --2004479494, REFERENCE ID ----204122247, NIMPURA CCC, QUOTATION NO ---2004479494/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GERIASULI-I] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02914/2023-2024 | BP-2023-24-350 | 10/11/2023 | 0 | WBSEDCL | 4.75 | 0 | 0
1127 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR HARIATARA WATER SUPPLY SCHEME (PORADIHA), JJM WORKS, SCHEME CODE SM/14483, APPLICATION NO 2004576970, REFERENCE ID 204203221, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03730/2023-2024 | BP-2023-24-701 | 16/02/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
1128 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR HARIATARA WATER SUPPLY SCHEME, ZONE-I, T W NO II, JJM WORKS, SCHEME CODE SM/14483, APPLICATION NO 2004576786, REFERENCE ID 204203220, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04703/2023-2024 | BP-2023-24-917 | 28/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
1129 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001745/2022-2023 | 650/W/MMD | 20/03/2023 | 180 | M/S. SAJAHAN CHOWDHURY | 43.15 | 27.18 | 63
1130 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte.(Part-II) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002026/2022-2023 | 934/W/MMD | 28/03/2023 | 180 | SUBHASIS ROY | 11.97 | 0 | 90
1131 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT DEBHOG AND OTHER 26 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001520/2022-2023 | 364/W/MMD | 09/03/2023 | 180 | P.K.ENGINEERING | 53.06 | 0 | 0
1132 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAMUASHANKARPUR PWSS, Block ¿ Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001743/2022-2023 | 603/W/MMD | 20/03/2023 | 180 | KRISHNA ENGINEERING | 11.94 | 0 | 0
1133 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Satkalua W/S scheme H/W site. Application No.-2004547137 Ref.-204177910 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03302/2023-2024 | BP-2023-24-548 | 15/01/2024 | 0 | WBSEDCL | 4.11 | 0 | 0
1134 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SATKALUA AND IT'S ADJOINING MOUJAS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001716/2022-2023 | 595/W/MMD | 20/03/2023 | 180 | INDIA ENTERPRISE | 21.62 | 10.61 | 35
1135 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME ( SANKARCHAK ), MINI, ZONE-I JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582819, REFERENCE ID 204206253, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00595/2024-2025 |  | 24/04/2024 | 0 | WBSEDCL | 0.12 | 0 | 0
1136 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME,ZONE-II/I, T W - I ,[ RAMNAGAR ] JJM WORKS, SCHEME CODE SM/14492, KGP-I, APPLICATION NO 2004696766, REFERENCE ID 204284088, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00635/2024-2025 | BP-2024-25-120 | 06/05/2024 | 0 | WBSEDCL | 0.11 | 0 | 0
1137 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR KASHIJORA, ZONE-II/I, T W NO II [ BENAPURUR CHAITA ] WATER SUPPLY SCHEME, JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004890141, REFERENCE ID 204393532, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03033/2024-2025 | C112429713000 | 25/11/2024 | 0 | WBSEDCL | 4.28 | 0 | 0
1138 | Midnapore Mechanical | Kharagpur Sub-Division | CERTIFIED THAT IT IS QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME (SANKARACHAK) , MINI, ZONE-I , JJM WORKS, SCHEME CODE SM/14492, , APPLICATION NO 2004582819, REFERENCE ID 204206253, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03699/2023-2024 | BP-2023-24-702 | 16/02/2024 | 0 | WBSEDCL | 0.12 | 0 | 0
1139 | Midnapore Mechanical | Kharagpur Sub-Division | KASHIJORA WATER SUPPLY SCHEME, ZONE I , T W NO 1 , JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582753, REFERENCE ID 204224605, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04189/2023-2024 | BP-2023-24-770 | 04/03/2024 | 0 | WBSEDCL | 3.25 | 0 | 0
1140 | Midnapore Mechanical | Kharagpur Sub-Division | KASHIJORA WATER SUPPLY SCHEME, ZONE I , T W NO 2 , JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582759, REFERENCE ID 204223621, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04203/2023-2024 | BP-2023-24-771 | 05/03/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
1141 | Midnapore Mechanical | Kharagpur Sub-Division | Supply and Installation of ( Dept. ) Submersible Pumping Machinery, Voltage Stabilizer ( Dept. ) , Chlorination System ( Dept. ) and Internal House Wiring and other allied works at Tube Well no 2 of Kashijora Mini Water Supply Scheme , Zone -II [ Block- Kharagpur-I ] under MMD, PHE Dte., Dist.- Paschim Medinipur. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000053/2024-2025 | 730/MMSD-I | 07/06/2024 | 365 | PURUSHOTTAM ENTERPRISE | 2.86 | 1.46 | 87
1142 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001631/2022-2023 | 538/W/MMD | 20/03/2023 | 710 | SOUMEN ELECTRIC | 34.15 | 23.62 | 55
1143 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I and II) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. .(Part-II) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002027/2022-2023 | 935/W/MMD | 28/03/2023 | 900 | RISHAV ENTERPRISE | 5.98 | 5.26 | 80
1144 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill of Erection for the Service connection at T/W NO-II Of CHAKBHABANI W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-PTP/QOT/HT/151 DT. 14-05-2024 Application NO- 100000107893 DT. 14-05-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860299943 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01129/2024-2025 | BP-2024-25-245 | 06/06/2024 | 0 | WBSEDCL | 0.37 | 0 | 0
1145 | Midnapore Mechanical | Contai Sub-Division | Chakbhabani W/S scheme PH-I Application no.-2004520839 ref.-204155241 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03190/2023-2024 | BP-2023-24-484 | 27/12/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
1146 | Midnapore Mechanical | Contai Sub-Division | Chakbhabani W/S scheme PH-II Application no.-2004520828 ref.-204155254 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03191/2023-2024 | BP-2023-24-483 | 27/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
1147 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of CHIRULIA W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004692025/QUOT/03/97 DT. 25-04-2024 Application NO- 2004692025 Application type-New connection Consumer Id- 204287568 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00853/2024-2025 | BP-2024-25-165 | 15/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
1148 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
1149 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Chirulia PWSS under Egra-II Block (Phase-III) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001989/2022-2023 | 896/W/MMD | 27/03/2023 | 837 | ECO ENTERPRISE | 12.63 | 8.53 | 85
1150 | Midnapore Mechanical | Contai Sub-Division | Deshduttabar W/S scheme T/W-I Application-no.-2004523550 Ref.-204157344 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03167/2023-2024 | BP-2023-24-446 | 19/12/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
1151 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Contai - I and III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000048/2023-2024 | 1205/W/MMD | 25/04/2023 | 859 | BHABANI PRASAD MANNA | 57.85 | 0 | 60
1152 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for MANIKPUR Boosting, Water Supply Scheme T/W (Ref. ID-204063673) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01822/2023-2024 | BP-2023-24-203 | 24/08/2023 | 0 | WBSEDCL | 4.87 | 0 | 0
1153 | Midnapore Mechanical | Haldia Sub-Division | Additional Quotation of Manikpur Boosting Tube Well Application ID-100000095367 Referance ID- 860287817 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/03181/2023-2024 | BP-2023-24-467 | 27/12/2023 | 0 | WBSEDCL | 0.29 | 0 | 0
1154 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.51 | 35
1155 | Midnapore Mechanical | Haldia Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
1156 | Midnapore Mechanical | Haldia Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
1157 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation for new service connection at Kotbar w/s scheme Boosting T/W I in the district of Purba Medinipur under MMD PHE Dte. (App No 2004689061, Ref ID 204279764) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01165/2024-2025 | BP-2024-25-275 | 12/06/2024 | 0 | WBSEDCL | 6.09 | 0 | 0
1158 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 5.95 | 55
1159 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Dhitpur water supply scheme T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03558/2023-2024 | BP-2023-24-623 | 07/02/2024 | 0 | WBSEDCL | 1.28 | 0 | 0
1160 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Dhitpur PWSS P/H- II , application no - 2004609048 , Ref id - 204222614 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04193/2023-2024 | BP-2023-24-776 | 06/03/2024 | 0 | WBSEDCL | 4.62 | 0 | 0
1161 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHITPUR AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001987/2022-2023 | 837/W/MMD | 24/03/2023 | 180 | HARA PROSAD DAS | 23.73 | 13.12 | 70
1162 | Midnapore Mechanical | RWS Midnapur Sub-Division | QUOTATION MONEY FOR T W NO 3 OF ABASHGARH WATER SUPPLY SCHEME [ REF- CONSUMER ID 203990474, UNDER RAJABAZAR CCC, WBSEDCL ] | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00156/2023-2024 | BP-2023-24-43 | 19/05/2023 | 0 | WBSEDCL | 0.31 | 0 | 0
1163 | Midnapore Mechanical | RWS Midnapur Sub-Division | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Abasgarh water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000110/2023-2024 | 428/MMSD-I | 24/04/2023 | 15 | SUJOY RANJAN BHOWMICK | 4.37 | 4.37 | 100
1164 | Midnapore Mechanical | RWS Midnapur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Abasgarh mouza. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002002/2022-2023 | 904/W/MMD | 27/03/2023 | 900 | ECO ENTERPRISE | 10.78 | 6.25 | 40
1165 | Midnapore Mechanical | Haldia Electrical Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1166 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Mukutshila, Zone-II PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001848/2022-2023 | 765/W/MMD | 23/03/2023 | 720 | M/S EMMESS | 12.24 | 9.08 | 70
1167 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000273/2024-2025 | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 100
1168 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Narandia PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001845/2022-2023 | 762/W/MMD | 23/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 12.24 | 0 | 90
1169 | Midnapore Mechanical | Haldia Electrical Sub-Division | Supply and installation of Sign Board for depicting the scheme details of different ongoing Solarisation/ Rejuvenation/ Other JJM works for the purpose of Geotagging at RAMNAGAR and Adjacent under MMD, P.H.E. Dte.Dist.- Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000273/2024-2025 | 739/HESD | 01/08/2024 | 15 | THE GODFATHER TRADING COMPANY | 8.1 | 0.18 | 100
1170 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Ramnagar PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001846/2022-2023 | 763/W/MMD | 23/03/2023 | 718 | UNITED TRADERS | 12.24 | 7.15 | 45
1171 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Chaupenia PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002119/2022-2023 | 1057/W/MMD | 29/03/2023 | 180 | M/S EMMESS | 11.28 | 11.28 | 100
1172 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Khejuri PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001847/2022-2023 | 764/W/MMD | 23/03/2023 | 1678 | ORIENTAL ENGINEERING CO. | 12.24 | 0 | 60
1173 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for tw no-I of Sashabedia PWSS . (Ref ID-204061143). | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01763/2023-2024 | BP-2023-24-182 | 11/08/2023 | 0 | WBSEDCL | 3.09 | 0 | 0
1174 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANDIPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000214/2023-2024 | 1495/W/MMD | 22/06/2023 | 180 | DEBJYOTI BASU | 25.25 | 15.48 | 80
1175 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Golegram pwss (Ref Consumar ID-204391663),Application No-2004886425,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02426/2024-2025 | C092442840754 | 27/09/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
1176 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOLEGRAM AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000014/2023-2024 | 1130/W/MMD | 12/04/2023 | 720 | P.K.ENGINEERING | 25.25 | 12.32 | 50
1177 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Samsara pwss (Ref Consumar ID-204431250),Application No-2004944502,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03002/2024-2025 | C112423562756 | 19/11/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1178 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Samsara pwss (Ref Consumar ID-204434263),Application No-2004944497,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03003/2024-2025 | C112423562182 | 19/11/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
1179 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SAMSARA ZONE 1 PIPED WATER SUPPLY SCHEME OF MOHANPUR BLOCK UNDER MEDINIPUR DIVISION under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000032/2023-2024 | 1196/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.64 | 14.12 | 40
1180 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Sautia pwss (Zone-I) (Ref Consumar ID-204310821),Application No-2004741353,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01069/2024-2025 | BP-2024-25-202 | 24/05/2024 | 0 | WBSEDCL | 4.52 | 0 | 0
1181 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sautia (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000034/2023-2024 | 1198/W/MMD | 25/04/2023 | 720 | DEBJYOTI BASU | 22.77 | 14.23 | 40
1182 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR ADDITIONAL TW NO-III of AMRAKUCHI PWSS. REF CONSUMER ID-204269829, APPLICATION NO-2004675304, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00317/2024-2025 | BP-2024-25-73 | 24/04/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
1183 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshpur to Accommodate FHTC, Block - Keshpur, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000005/2023-2024 | 1121/W/MMD | 12/04/2023 | 696 | S.S.GHORAI | 22.89 | 12.33 | 20
1184 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Amrakuchi to accommodate FHTC in Keshpur block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002207/2022-2023 | 617/W/MMD | 20/03/2023 | 180 | JAGANNATH ENTERPRISE | 21.58 | 0 | 0
1185 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Borai Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000025/2023-2024 | 1189/W/MMD | 25/04/2023 | 180 | RSA ENTERPRISE | 23.01 | 0 | 0
1186 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Chakmakrampur PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002130/2022-2023 | 1068/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 11.02 | 0 | 70
1187 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KAINARA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738882/QUOT/03 DT. 17-05-2024 Application NO-2004738882 Application type-New connection Consumer Id- 204309127 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01097/2024-2025 | BP-2024-25-226 | 31/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0
1188 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for Shifting of LT POLE AT KAINARA T/W NO-I , BLOCK: RAMNAGRA -I WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. MEMO No- DGA/QT/1042 Dt. 17.09.2024 Application NO- 100000119117 Dt. 17/09/2024 Reference Id- 860313097 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02500/2024-2025 | C102415728122 | 05/10/2024 | 0 | WBSEDCL | 0.33 | 0 | 0
1189 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-I of KAINARA WS SCHEME under MMD,PHE Dte, Block-Ramnagar-I, DIGHA CCC, Application no-2004644445, CON ID-204246842 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04740/2023-2024 | BP-2023-24-914 | 28/03/2024 | 0 | WBSEDCL | 6.46 | 0 | 0
1190 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAINARA and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001656/2022-2023 | 527/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 75
1191 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at TW-I of Simulberia w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695156 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-6000W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00648/2024-2025 | BP-2024-25-109 | 06/05/2024 | 0 | WBSEDCL | 8.39 | 0 | 0
1192 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULBERYA and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001670/2022-2023 | 553/W/MMD | 20/03/2023 | 684 | DEBJYOTI BASU | 21.62 | 8.99 | 46
1193 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Akramarkandapur PWSS P/H- I , application no - 2004609042 , Ref id - 204222613 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04191/2023-2024 | BP-2023-24-775 | 06/03/2024 | 0 | WBSEDCL | 4.16 | 0 | 0
1194 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER Kharagpur - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000038/2023-2024 | 1187/W/MMD | 25/04/2023 | 180 | A G ENTERPRISE | 40.67 | 0 | 40
1195 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Chak Prayag pwss (Ref Consumar ID-204391664),Application No-2004886442,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02424/2024-2025 | C092443136780 | 27/09/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
1196 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK PRAYAG AND ITS ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002203/2022-2023 | 532/W/MMD | 20/03/2023 | 180 | P.K.ENGINEERING | 22.78 | 15.76 | 40
1197 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quation bill for gobindapur pwss at pump house no-I (Consumar Id-204182978) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03325/2023-2024 | BP-2023-24-536 | 11/01/2024 | 0 | WBSEDCL | 3.28 | 0 | 0
1198 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Gobindapur pwss at pump house no-II (Consumar Id-204182972) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03326/2023-2024 | BP-2023-24-537 | 11/01/2024 | 0 | WBSEDCL | 3 | 0 | 0
1199 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002202/2022-2023 | 483/W/MMD | 20/03/2023 | 864 | M/S. P.P.ELECTRICALS | 22.95 | 21.4 | 90
1200 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004660093/QUOT/03 DT. 01-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204261081 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00521/2024-2025 | BP-2024-25-96 | 24/04/2024 | 0 | WBSEDCL | 5.33 | 0 | 0
1201 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTANA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001681/2022-2023 | 565/W/MMD | 20/03/2023 | 864 | DEY ENTERPRISE | 22.8 | 0 | 55
1202 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674845/QUOT/03 DT. 09-04-2024 Application NO- 2004674845 Application type-New connection Consumer Id- 204269900 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00500/2024-2025 | BP-2024-25-83 | 24/04/2024 | 0 | WBSEDCL | 3.69 | 0 | 0
1203 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674832/QUOT/03 DT. 09-04-2024 Application NO- 2004674832 Application type-New connection Consumer Id- 204269889 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00510/2024-2025 | BP-2024-25-82 | 24/04/2024 | 0 | WBSEDCL | 6.05 | 0 | 0
1204 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURANDA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001627/2022-2023 | 512/W/MMD | 20/03/2023 | 925 | GLACIER ENGINEERING CO. | 22.8 | 16.25 | 100
1205 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II OF SINNIBAR PWSS. REF CONSUMER ID-204211984, APPLICATION NO-2004590238, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01455/2024-2025 | BP-2024-25-418 | 15/07/2024 | 0 | WBSEDCL | 4.67 | 0 | 0
1206 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for TW No-I of SINNIBAR PWSS (Ref Consumer ID-204182338) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03341/2023-2024 | BP-2023-24-562 | 16/01/2024 | 0 | WBSEDCL | 3.23 | 0 | 0
1207 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SINNIBAR PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000360/2023-2024 | 1688/W/MMD | 04/08/2023 | 804 | SOUMEN ELECTRIC | 27.37 | 19.54 | 20
1208 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Making of T.W Foundation at PH-I of Sinnibar and Salikotha piped water supply scheme under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000834/2025-2026 | 1117/MMSD-I | 14/08/2025 | 7 | SOUMEN ELECTRIC | 0.81 | 0 | 0
1209 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JHAKRA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division |  | ORD/001453/2023-2024 | 3096/W/MMD | 29/11/2023 | 180 | SHREE BISHNU CONSTRUCTION | 25.25 | 20.79 | 80
1210 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KUAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division |  | ORD/001452/2023-2024 | 3095/W/MMD | 29/11/2023 | 550 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 0 | 90
1211 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR MAKARAMPUR WATER SUPPLY SCHEME , T W - I , JJM WORKS, SCHEME CODE SM/18586, APPLICATION NO 2004696153, REFERENCE ID 204284318, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00636/2024-2025 | BP-2024-25-119 | 06/05/2024 | 0 | WBSEDCL | 5.84 | 0 | 0
1212 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR MAKARAMPUR WATER SUPPLY SCHEME , T W - II , JJM WORKS, SCHEME CODE SM/18586, APPLICATION NO 2004696147, REFERENCE ID 204284316, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00637/2024-2025 | BP-2024-25-118 | 06/05/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1213 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Makarampur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000382/2023-2024 | 1721/W/MMD | 09/08/2023 | 754 | S.G.TECHNICAL SERVICE | 23 | 0 | 85
1214 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric Quotation bill for Tw No-I of Khasjangal water supply scheme. (ref Consumer ID-204109026) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02899/2023-2024 | BP-2023-24-330 | 03/11/2023 | 0 | WBSEDCL | 2.83 | 0 | 0
1215 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric Quotation bill for Tw no-II of Khasjangal water supply scheme.(Ref Consumer ID-204109024) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02900/2023-2024 | BP-2023-24-331 | 03/11/2023 | 0 | WBSEDCL | 3.58 | 0 | 0
1216 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHAS JANGAL PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001616/2022-2023 | 495/W/MMD | 20/03/2023 | 1019 | M/S MANABESH ROY | 22.91 | 15.95 | 25
1217 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - II, JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004696073, REFERENCE ID 204284332, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00642/2024-2025 | BP-2024-25-122 | 06/05/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
1218 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004696081, REFERENCE ID 2204284306, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00644/2024-2025 | BP-2024-25-121 | 06/05/2024 | 0 | WBSEDCL | 4.33 | 0 | 0
1219 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR TATARPUR WATER SUPPLY SCHEME, T W - I, JJM WORKS, SCHEME CODE SM/18540, APPLICATION NO 2004700117, REFERENCE ID 204286354, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00828/2024-2025 | BP-2024-25-159 | 13/05/2024 | 0 | WBSEDCL | 7.37 | 0 | 0
1220 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000368/2023-2024 | 1694/W/MMD | 04/08/2023 | 759 | A G ENTERPRISE | 78.38 | 0 | 20
1221 | Midnapore Mechanical | Ghatal Subdivision | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
1222 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of DHARMAPUR PWSS. REF CONSUMER ID-204188704, APPLICATION NO-2004559827, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/03734/2023-2024 | BP-2023-24-700 | 16/02/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
1223 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of DHARMAPUR PWSS. REF CONSUMER ID-204240653, APPLICATION NO-2004634438, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPEERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | BILL/04477/2023-2024 | BP-2023-24-847 | 14/03/2024 | 0 | WBSEDCL | 7.59 | 0 | 0
1224 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DHARMA PUR AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000339/2023-2024 | 1680/W/MMD | 04/08/2023 | 180 | SUBHASIS ROY | 27.34 | 0 | 0
1225 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.14 | 50
1226 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Reripur PWSS P/H- I , application no - 2004590029 , Ref id - 204211394 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04205/2023-2024 | BP-2023-24-784 | 06/03/2024 | 0 | WBSEDCL | 2.61 | 0 | 0
1227 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Reripur PWSS P/H- II , application no - 2004590055 , Ref id - 204211393 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04207/2023-2024 | BP-2023-24-785 | 06/03/2024 | 0 | WBSEDCL | 3.81 | 0 | 0
1228 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of KUSUMDAHARI PWSS. REF CONSUMER ID-204269092, APPLICATION NO-2004675269, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00310/2024-2025 | BP-2024-25-76 | 24/04/2024 | 0 | WBSEDCL | 3.88 | 0 | 0
1229 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of KUSUMDAHARI PWSS. REF CONSUMER ID-204269085, APPLICATION NO-2004675279, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00314/2024-2025 | BP-2024-25-77 | 24/04/2024 | 0 | WBSEDCL | 4.8 | 0 | 0
1230 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUSUMDAHARI PIPED WATER SUPPLY SCHEMEunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000340/2023-2024 | 1681/W/MMD | 04/08/2023 | 679 | INDTECH ASSOCIATES | 23 | 9.67 | 25
1231 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Barbasi T/W - I Within Khargpur - II Block, Application No - 2004975141 , Ref ID - 204452540 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03155/2024-2025 | C122403004364 | 04/12/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1232 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Barbasi T/W - II Within Khargpur - II Block, Application No - 2004970379 , Ref ID - 204449425 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03158/2024-2025 | C122403004056 | 04/12/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
1233 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BARBASI & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME.under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000350/2023-2024 | 1685/W/MMD | 04/08/2023 | 180 | S.K.ENTERPRISE | 25.26 | 19.8 | 50
1234 | Midnapore Mechanical | Contai Sub-Division | Barttan W/S scheme T/W no.-II(Tower) Application-2004521219 Ref.-204156075 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03177/2023-2024 | BP-2023-24-477 | 27/12/2023 | 0 | WBSEDCL | 3.01 | 0 | 0
1235 | Midnapore Mechanical | Contai Sub-Division | Barttan W/S scheme T/W no.-I(Tower) Application-2004521240 Ref.-204156076 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03178/2023-2024 | BP-2023-24-478 | 27/12/2023 | 0 | WBSEDCL | 2.93 | 0 | 0
1236 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTAN and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001578/2022-2023 | 473/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 25.26 | 18.96 | 100
1237 | Midnapore Mechanical | RWS Midnapur Sub-Division | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Maliara water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002150/2022-2023 | 1345/MMSD-I | 30/12/2022 | 15 | P.K.ENGINEERING | 4.37 | 4.37 | 100
1238 | Midnapore Mechanical | RWS Midnapur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC, Block - Midnapore, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000020/2023-2024 | 1135/W/MMD | 12/04/2023 | 180 | SUBHASIS ROY | 11.32 | 10.5 | 100
1239 | Midnapore Mechanical | Kharagpur Sub-Division | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Nilhat water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001184/2021-2022 | 2524/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.48 | 0 | 100
1240 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Nilhat, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001196/2021-2022 | 155/W/MMD | 31/01/2022 | 120 | DEY ENTERPRISE | 6.81 | 4 | 0
1241 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Lejibheri, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001194/2021-2022 | 153/W/MMD | 31/01/2022 | 120 | DEBJYOTI BASU | 6.51 | 6.39 | 0
1242 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at LEJIBHERI water supply scheme, of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001291/2021-2022 | 2516/W/MMD | 30/11/2021 | 4 | OSMAN SEKH | 4.47 | 3.52 | 0
1243 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation for service connection charges of WBSEDCL at Neziveri | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001523/2021-2022 | 2003855194/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0.13 | 0
1244 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Naoyagan water supply scheme, tube well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001138/2021-2022 | 2528/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 100
1245 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Naoyagan water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001140/2021-2022 | 2526/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 100
1246 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001186/2021-2022 | 145/W/MMD | 31/01/2022 | 120 | PRANAB KUMAR DAS | 6.51 | 2.26 | 0
1247 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -II at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001187/2021-2022 | 146/W/MMD | 31/01/2022 | 120 | BHABANI PRASAD MANNA | 6.56 | 6.56 | 0
1248 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well -I at Naoyagan, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. (W/O-145/W/MMD, DT.-31/01/2022) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/005604/2021-2022 | BP-2021-22-118 | 17/03/2022 | 0 | PRANAB KUMAR DAS | 4.13 | 0 | 0
1249 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at TW-III of Murisai w/s scheme under MMD, PHE Dte. Block-Contai-III, MARISHDA CCC Application n0-2004764433 Con ID-204324522 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01234/2024-2025 | BP-2024-25-285 | 18/06/2024 | 0 | WBSEDCL | 5.67 | 0 | 0
1250 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at Murisai Water supply scheme, Contai - III block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001859/2024-2025 | 782/W/MMD | 24/02/2025 | 180 | PADMA ENGINEERING CO. | 14.81 | 0 | 0
1251 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Murisai, Block Contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001910/2022-2023 | 811/W/MMD | 24/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 13.75 | 8.29 | 60
1252 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation for New Service Connection charges of Additional TW-III of Panapara WS Scheme (Ref. Id-203959888) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00075/2023-2024 | BP-2023-24-31 | 04/05/2023 | 0 | WBSEDCL | 3.31 | 0 | 0
1253 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Panpara (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001694/2022-2023 | 609/W/MMD | 20/03/2023 | 180 | M/S EMMESS | 10.79 | 10.52 | 85
1254 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
1255 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0 | 100
1256 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.09 | 100
1257 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Jamira, chowka, Ghatal, T/W-I Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00029/2022-2023 | BP-2022-23-70 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1258 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Masharpur, chowka, Ghatal, P/H-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00030/2022-2023 | BP-2022-23-71 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1259 | Midnapore Mechanical | Ghatal Subdivision | Service Connection charges of WBSEDCL at P/H-II of Jamira W/S Scheme | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00035/2022-2023 | BP-2022-23-99 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
1260 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001314/2022-2023 | 2316/W/MMD | 29/12/2022 | 180 | M/S EMMESS | 6.01 | 5.6 | 100
1261 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Jamira mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Zone-II) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001479/2022-2023 | 229/W/MMD | 13/02/2023 | 180 | RISHAV ENTERPRISE | 6 | 5.98 | 100
1262 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Jamira, chowka, Ghatal, T/W-I P/H-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | VCH/002775/2022-2023 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1263 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Masharpur, chowka, Ghatal, T/W-I P/H-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | VCH/002776/2022-2023 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1264 | Midnapore Mechanical | Ghatal Subdivision | Service Connection Charges of WBSEDCL at T/W-I of Raghunathpur W/S Scheme | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00037/2022-2023 | BP-2022-23-98 | 11/01/2023 | 0 | WBSEDCL | 0.13 | 0 | 0
1265 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Raghunathpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001244/2022-2023 | 2175/W/MMD | 12/12/2022 | 120 | A.S.ENTERPRISE | 5.92 | 5.37 | 0
1266 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-III under Raghunathpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001245/2022-2023 | 2176/W/MMD | 12/12/2022 | 120 | M.D.ENTERPRISE | 5.97 | 5.97 | 100
1267 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Mini Piped Water Supply Scheme for Raghunathpur mouza under SAGY, Block - Ghatal, G.P. - Dewanchak-II, P.S. - Ghatal, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001692/2022-2023 | 608/W/MMD | 20/03/2023 | 180 | M/S S M ELECTRICAL | 6 | 0 | 0
1268 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Raghunathpur, monoharpur, Ghatal, T/W-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002777/2022-2023 | BP-2022-23-62 | 23/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1269 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Raghunathpur, monoharpur, Ghatal, T/W-III P/H-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002778/2022-2023 | BP-2022-23-63 | 23/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1270 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for WBSEDCL at TW-III of Bishnupur Water Supply Scheme (Ref. ID-203959904) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00072/2023-2024 | BP-2023-24-42 | 19/05/2023 | 0 | WBSEDCL | 2.18 | 0 | 0
1271 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to accommodate FHTC under Jal Sapno Mission under Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002005/2022-2023 | 876/W/MMD | 27/03/2023 | 180 | RADHARANI ENTERPRISE | 5.98 | 4.44 | 100
1272 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for KUMIRDA Water Supply Scheme T/W-IV, (Ref. ID-204050266) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01684/2023-2024 | BP-2023-24-166 | 04/08/2023 | 0 | WBSEDCL | 5.19 | 0 | 0
1273 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Mukutshila Zone I w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671631, Ref ID 204266595) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03075/2024-2025 | C112443271348 | 02/12/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
1274 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Mukutshila PWSS to accommodate FHTC within Khejuri-I Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001926/2022-2023 | 845/W/MMD | 24/03/2023 | 180 | DEBJYOTI BASU | 35.54 | 24.61 | 50
1275 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Khejurberia PWSS to accommodate FHTC in Nandakumar Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001519/2022-2023 | 363/W/MMD | 09/03/2023 | 180 | UNITED TRADERS | 23.68 | 22.93 | 60
1276 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of Mosharpur water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000160/2022-2023 | 2003978639 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0
1277 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Masharpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000224/2022-2023 | 1653/W/MMD | 12/08/2022 | 120 | BHABANI PRASAD MANNA | 5.64 | 5.64 | 100
1278 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Masharpur water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001243/2022-2023 | 2174/W/MMD | 12/12/2022 | 120 | SUBHASIS ROY | 5.92 | 5.38 | 91
1279 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of Mosharpur water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001774/2022-2023 | BP-2022-23-45 | 23/08/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1280 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional quotation for Dakhin Anukha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 100000112312, Ref ID 860303992) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01721/2024-2025 | BP-2024-25-496 | 30/07/2024 | 0 | WBSEDCL | 0.99 | 0 | 0
1281 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation for Dakhin Ankha w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608987, Ref ID-204222617) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04496/2023-2024 | BP-2023-24-859 | 16/03/2024 | 0 | WBSEDCL | 3.58 | 0 | 0
1282 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation for Dakhin Ankha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608983, Ref ID-204222616) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04501/2023-2024 | BP-2023-24-858 | 16/03/2024 | 0 | WBSEDCL | 3.47 | 0 | 0
1283 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
1284 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DKSHIM ANKHA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001636/2022-2023 | 516/W/MMD | 20/03/2023 | 683 | KARUNAMOY ENGINEERING | 22.75 | 15.69 | 100
1285 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MIRJAPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671915/QUOT/03/50 DT. 05-04-2024 Application NO- 2004671915 Application type-New connection Consumer Id- 204266735 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00514/2024-2025 | BP-2024-25-92 | 24/04/2024 | 0 | WBSEDCL | 4.49 | 0 | 0
1286 | Midnapore Mechanical | Digha Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1287 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block - Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001615/2022-2023 | 506/W/MMD | 20/03/2023 | 180 | M/S DILIP MITRA | 21.59 | 0 | 0
1288 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for tw-I of Jotekanuramgarh w/s scheme (consumar ID-203974593) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00100/2023-2024 | BP-2023-24-18 | 28/04/2023 | 0 | WBSEDCL | 7.05 | 0 | 0
1289 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for tw-II of Jote kanuramgarh w/s scheme(consumar ID-203974597) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00101/2023-2024 | BP-2023-24-17 | 28/04/2023 | 0 | WBSEDCL | 4.14 | 0 | 0
1290 | Midnapore Mechanical | Ghatal Subdivision | Some repairing works of Voltage Stabiliser at pump house no-I&IIof Jote Kanuramgarh water Supply Scheme under MMD PHE Dte, Dist-Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000294/2025-2026 | 780/MMSD-I | 30/05/2025 | 7 | P.K.ENGINEERING | 0.49 | 0 | 0
1291 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Jote Kanuramgar & its adjoining mouzas. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001311/2022-2023 | 2313/W/MMD | 29/12/2022 | 720 | DEBJYOTI BASU | 25.25 | 12.6 | 100
1292 | Midnapore Mechanical | Ghatal Subdivision | Electric Quotation for TW-I of Ramkrishapur W/S Scheme (ID-203973517) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00095/2023-2024 | BP-2023-24-22 | 28/04/2023 | 0 | WBSEDCL | 5.24 | 0 | 0
1293 | Midnapore Mechanical | Ghatal Subdivision | Electric Quotation for TW-II of Ramkrishnapur W/S Scheme (ID-203974545) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00096/2023-2024 | BP-2023-24-21 | 28/04/2023 | 0 | WBSEDCL | 3.11 | 0 | 0
1294 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Ramkrishnapur & its adjoining mouzas. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001312/2022-2023 | 2314/W/MMD | 29/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 27.35 | 27.01 | 80
1295 | Midnapore Mechanical | Ghatal Subdivision | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001562/2023-2024 | 1211/MMSD-I | 29/09/2023 | 92 | SUBHASIS ROY | 0.45 | 0 | 0
1296 | Midnapore Mechanical | Ghatal Subdivision | Additional work for increasing of hight of tube well and other allied work ar tube well no. I & II of Ramkrishnapur and Kanchangeria (Tube well no. I) water supply scheme [Block-Daspur-II and Debra] under MMD, PHE Dte., Dist.- Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002709/2023-2024 | 338/MMSD-I | 05/03/2024 | 10 | SUJOY RANJAN BHOWMICK | 1.33 | 0 | 100
1297 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for MADHYA HINGLI Water Supply Scheme T/W-I, (Ref. ID-204136074) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03184/2023-2024 | BP-2023-24-441 | 19/12/2023 | 0 | WBSEDCL | 5.95 | 0 | 0
1298 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Madhya Hingli w/s scheme PH II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03665/2023-2024 | BP-2023-24-682 | 15/02/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
1299 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for Bakcha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004620130, Ref ID-204229481) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04502/2023-2024 | BP-2023-24-854 | 16/03/2024 | 0 | WBSEDCL | 2.97 | 0 | 0
1300 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Bakcha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.2004631507, Ref ID 204237228) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04744/2023-2024 | BP-2023-24-906 | 28/03/2024 | 0 | WBSEDCL | 6.12 | 0 | 0
1301 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAKCHA and ADJOINING MOUJAS, Block Moyna, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001331/2022-2023 | 2336/W/MMD | 29/12/2022 | 180 | PRANAB KUMAR DAS | 23.69 | 22.11 | 90
1302 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-I, (Ref. ID-204086227) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02892/2023-2024 | BP-2023-24-313 | 01/11/2023 | 0 | WBSEDCL | 3.78 | 0 | 0
1303 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MIRJAPUR Water Supply Scheme T/W-II, (Ref. ID-204090824) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02893/2023-2024 | BP-2023-24-316 | 01/11/2023 | 0 | WBSEDCL | 1.14 | 0 | 0
1304 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001350/2022-2023 | 2361/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 23.67 | 23.13 | 100
1305 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BALGOBINDAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004675882/QUOT/03 DT. 12-04-2024 Application NO- 2004675882 Application type-New connection Consumer Id- 204270815 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00578/2024-2025 | BP-2024-25-100 | 26/04/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
1306 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BALGOBINDAPUR and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001329/2022-2023 | 2334/W/MMD | 29/12/2022 | 180 | S.S.GHORAI | 23.7 | 14.81 | 55
1307 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TANIA BILA and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001318/2022-2023 | 2320/W/MMD | 29/12/2022 | 180 | M/S. SAJAHAN CHOWDHURY | 22.79 | 16.65 | 65
1308 | Midnapore Mechanical | Contai Sub-Division | Bijoynagar W/S scheme T/W-II Application.-2004537378 Ref.-204168879 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03294/2023-2024 | BP-2023-24-529 | 11/01/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
1309 | Midnapore Mechanical | Contai Sub-Division | Bijoynagar W/S scheme T/W-I Application.-2004537086 Ref.-204168733 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03295/2023-2024 | BP-2023-24-530 | 11/01/2024 | 0 | WBSEDCL | 4.08 | 0 | 0
1310 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BIJAYNAGAR and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001320/2022-2023 | 2322/W/MMD | 29/12/2022 | 723 | GOENKA ENTERPRISE | 22.8 | 21.04 | 100
1311 | Midnapore Mechanical | Contai Sub-Division | Gar Bhera W/S scheme T/W-V Application No.-2004553977 Ref.-204184071 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03358/2023-2024 | BP-2023-24-573 | 18/01/2024 | 0 | WBSEDCL | 5.53 | 0 | 0
1312 | Midnapore Mechanical | Contai Sub-Division | Garbhera W/S scheme T/W-II Application No.-2004554001 Ref.-204184072 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03359/2023-2024 | BP-2023-24-580 | 18/01/2024 | 0 | WBSEDCL | 7.59 | 0 | 0
1313 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GAR BHERA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001336/2022-2023 | 2341/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 22.14 | 85
1314 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004870409/QUOT/03 DT. 23-08-2024 MEMO NO: AMR/PHE/338 DT. 23-08-2024 Application NO- 2004870409 Application type-New connection Consumer Id- 204383603 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02398/2024-2025 | BP-2024-25-648 | 06/09/2024 | 0 | WBSEDCL | 5.91 | 0 | 0
1315 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878231/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/351 DT. 30-08-2024 Application NO- 2004878231 Application type-New connection Consumer Id- 204387577 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02453/2024-2025 | C102415714404 | 05/10/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
1316 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARA BHAGIA and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001626/2022-2023 | 511/W/MMD | 20/03/2023 | 925 | GLACIER ENGINEERING CO. | 22.8 | 16.26 | 60
1317 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818541/QUOT/03 DT. 12-07-2024 Application NO- 2004818541 Application type-New connection Consumer Id- 204355510 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01890/2024-2025 | BP-2024-25-555 | 08/08/2024 | 0 | WBSEDCL | 12.51 | 0 | 0
1318 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of NILKANTHAPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE : BHAGWANPUR C.C.C. Ref. Memo No- 2004942161/QUOT/03 DT. 24-10-2024 Application NO- 2004942161 Application type-New connection CONSUMER ID: 204427729 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03004/2024-2025 | C112423542425 | 20/11/2024 | 0 | WBSEDCL | 2.78 | 0 | 0
1319 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001412/2022-2023 | 2423/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 17.44 | 62
1320 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHIPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001413/2022-2023 | 2424/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 22.8 | 14.3 | 51
1321 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-1 of Amdai w/s scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia CCC,Application no-2004635540.Con ID-204242882 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04574/2023-2024 | BP-2023-24-886 | 22/03/2024 | 0 | WBSEDCL | 5.55 | 0 | 0
1322 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of AMDAI WS Scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia ccc . Application no-2004635643. CON ID-204240383. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04576/2023-2024 | BP-2023-24-887 | 22/03/2024 | 0 | WBSEDCL | 4.92 | 0 | 0
1323 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMDAI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001405/2022-2023 | 2416/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.81 | 0 | 80
1324 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BRINDABANPUR AND ITS ADJOINING MOJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000009/2023-2024 | 1125/W/MMD | 12/04/2023 | 180 | S.P. ENTERPRISE | 22.65 | 8.21 | 50
1325 | Midnapore Mechanical | Digha Sub-Division | Paniparul W/S scheme TW-2 Memo No.-2004516165/Quot/03/1650 application no-2004516165 ref. id-204151594 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03146/2023-2024 | BP-2023-24-447 | 19/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
1326 | Midnapore Mechanical | Digha Sub-Division | Paniparul W/S scheme TW-2 Memo No.-2004516174/Quot/03/1649 application no-2004516174 ref. id-204151561 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03147/2023-2024 | BP-2023-24-448 | 19/12/2023 | 0 | WBSEDCL | 4.39 | 0 | 0
1327 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-I, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001933/2022-2023 | 852/W/MMD | 24/03/2023 | 180 | ECO ENTERPRISE | 13.47 | 13.3 | 100
1328 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill cost due to Modification for NSC of PHE AT Site- BASUDEVBERIA W/S SCHEME, T/W NO-I Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/253 DT. 16-05-2024 Application NO- 100000108115 DT. 16-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300165 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01128/2024-2025 | BP-2024-25-241 | 06/06/2024 | 0 | WBSEDCL | 0.59 | 0 | 0
1329 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558723/QUOT/03 DT. 10-01-2024 Application NO- 2004558723 Application type-New connection Consumer Id- 204187848 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04388/2023-2024 | BP-2023-24-829 | 13/03/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
1330 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BASUDEVBERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558731/QUOT/03 DT. 27-02-2024 Application NO- 2004558731 Application type-New connection Consumer Id- 204187847 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04390/2023-2024 | BP-2023-24-828 | 13/03/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
1331 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1332 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1333 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Damodarpur PWSS Tube Well-III WS Scheme (Ref. ID - 203911304) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00317/2022-2023 | BP-2022-23-136 | 20/03/2023 | 0 | WBSEDCL | 0.37 | 0 | 0
1334 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Replacement Tube Well of 1st Tube Well and 1 (One) No. Boosting Tube Well for Damudarpur Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District, Block Contai I,under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000170/2023-2024 | 1413/W/MMD | 02/06/2023 | 180 | RUBY ENTERPRISE | 27.17 | 13.44 | 80
1335 | Midnapore Mechanical | Contai Sub-Division | Quotation for New service connection at TW-I of Raghu Sardarbar Jalpai ws scheme under MMD,PHE ,Dte. Ref Application no-2004579837, CON ID-204204431, under PICHABONI CCC, Block-Contai-I | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03659/2023-2024 | BP-2023-24-662 | 12/02/2024 | 0 | WBSEDCL | 4.25 | 0 | 0
1336 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAGHUSARDAR BAR JALPAI and ADJOINING MOUJAS, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001666/2022-2023 | 549/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 21.62 | 10.04 | 80
1337 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHANDPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001679/2022-2023 | 566/W/MMD | 20/03/2023 | 180 | DEY ENTERPRISE | 22.8 | 0 | 0
1338 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004670828/QUOT/03 DT. 05-04-2024 Application NO- 2004670828 Application type-New connection Consumer Id- 204266383 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00301/2024-2025 | BP-2024-25-43 | 18/04/2024 | 0 | WBSEDCL | 8.56 | 0 | 0
1339 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KALAPUNJA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749309/QUOT/03 DT. 28-05-2024 Application NO- 2004749309 Application type-New connection Consumer Id- 204316972 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01146/2024-2025 | BP-2024-25-258 | 06/06/2024 | 0 | WBSEDCL | 3.89 | 0 | 0
1340 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of BHIKUBAR PWSS. REF CONSUMER ID-204310348 APPLICATION NO-2004739394 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01025/2024-2025 | BP-2024-25-207 | 28/05/2024 | 0 | WBSEDCL | 1.23 | 0 | 0
1341 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of BHIKUBAR PWSS. REF CONSUMER ID-204310423 APPLICATION NO-2004739593 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01027/2024-2025 | BP-2024-25-206 | 28/05/2024 | 0 | WBSEDCL | 0.84 | 0 | 0
1342 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHIKUBAR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001735/2022-2023 | 649/W/MMD | 20/03/2023 | 744 | M/S. S.R. ENTERPRISE | 32.33 | 22.1 | 30
1343 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at tw-III of Ranisai ws scheme under MMD PHE Dte,Block-Ramnagar-I, Digha CCC Application no-2004764426 Con ID-204324285 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01226/2024-2025 | C062416826632 | 18/06/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
1344 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001997/2022-2023 | 885/W/MMD | 27/03/2023 | 1259 | SUDIKSHA CONSTRUCTION | 12.37 | 3.05 | 10
1345 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Patna w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004640160, Ref ID - 204244152) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04491/2023-2024 | BP-2023-24-855 | 16/03/2024 | 0 | WBSEDCL | 7.46 | 0 | 0
1346 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PATNA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001372/2022-2023 | 2383/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 27.7 | 19.5 | 60
1347 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Duria PWSS P/H- I , application no - 2004609049 , Ref id - 204223727 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04206/2023-2024 | BP-2023-24-786 | 06/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
1348 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill cost for Diversion of route due to RAW at the PHE Site-BAHADURPUR W/S SCHEME,T/W NO-II, MADHABPUR Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-MDK/QOUT/260 DT. 17-05-2024 Application NO- 100000108126 DT. 17-05-2024 Application type-ADDITIONAL QUOTATION REF. Id- 860300546 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01144/2024-2025 | BP-2024-25-242 | 06/06/2024 | 0 | WBSEDCL | 1.41 | 0 | 0
1349 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004601928/QUOT/03 DT. 15-02-2024 Application NO- 2004601928 Application type-New connection Reference Id- 204217837 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04266/2023-2024 | BP-2023-24-794 | 06/03/2024 | 0 | WBSEDCL | 4 | 0 | 0
1350 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1351 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649232/QUOT/03 DT. 20-03-2024 Application NO- 2004649232 Application type-New connection Consumer Id- 204250589 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00007/2024-2025 | BP-2024-25-3 | 04/04/2024 | 0 | WBSEDCL | 6.98 | 0 | 0
1352 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PANCHET W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004626644/QUOT/03 DT. 01-03-2024 Application NO- 2004626644 Application type-New connection Consumer Id- 204234144 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04391/2023-2024 | BP-2023-24-820 | 13/03/2024 | 0 | WBSEDCL | 3.99 | 0 | 0
1353 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PANCHET and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001367/2022-2023 | 2378/W/MMD | 31/12/2022 | 900 | GHOSH ENGINEERING SYNDICATE | 25.24 | 0 | 45
1354 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004775287/QUOT/03 DT. 14-06-2024 Application NO- 2004775287 MEMO NO: AMR/PHE/176 DT.14/06/2024 Application type-New connection Consumer Id- 204330587 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01332/2024-2025 | BP-2024-25-354 | 01/07/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
1355 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of NAIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004609871/QUOT/03 DT. 21-02-2024 Application NO- 2004609871 Application type-New connection Reference Id- 204223251 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04392/2023-2024 | BP-2023-24-821 | 13/03/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
1356 | Midnapore Mechanical | Contai Sub-Division | Making of Tube Well Foundation & others at Pump House no. I & II of Naipur piped water supply scheme under Medinipur Mechanical Division P.H.E Dte. in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000255/2025-2026 | 585/HESD | 19/06/2025 | 7 | SOUMEN ELECTRIC | 0.66 | 0 | 0
1357 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAIPUR and ADJOINING MOUJAS, Block Potashpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001317/2022-2023 | 2319/W/MMD | 29/12/2022 | 824 | SOUMEN ELECTRIC | 22.78 | 16.14 | 90
1358 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill For New Service Connection at TW-IV of Jalpai PWSS under MMD PHE Dte.,Block-Nandakumar C.C.C.-Na Contract Demand-12000Wndakumar Application no.-2004653153 Application Type-New Connection Quotation Date-28/03/2024 Quotation Due Date-28/03/2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00252/2024-2025 | BP-2024-25-26 | 15/04/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
1359 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Jalpai W/S scheme TW-III Application No.-2004554813 Ref.-204184634 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/03346/2023-2024 | BP-2023-24-576 | 18/01/2024 | 0 | WBSEDCL | 3.46 | 0 | 0
1360 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at JALPAI Water supply scheme,T/W - V, NANDAKUMAR block, District ¿ Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000390/2024-2025 | 2006/W/MMD | 30/08/2024 | 180 | M/S EMMESS | 14.12 | 0 | 0
1361 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipment's for augmentation of ground water based Jaipai w/s scheme under JJM Program under Medinipur Mechanical Division P.H.E Dte. In the dist of PurbaMedinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000427/2023-2024 | 580/HESD | 04/08/2023 | 7 | BHABANI PRASAD MANNA | 0.39 | 0 | 0
1362 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water based Jalpai Water Supply Scheme, Block ¿ Nanda Kumar, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001512/2022-2023 | 356/W/MMD | 09/03/2023 | 180 | BHABANI PRASAD MANNA | 40.78 | 25.4 | 60
1363 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Asti PWSS T/W - II Within Narayangarh Block Application No - 2004987869, Ref ID- 204460781 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03867/2024-2025 |  | 24/12/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
1364 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Asti PWSS T/W - I Within Narayangarh Block Application No - 2004987846, Ref ID- 204460783 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03868/2024-2025 |  | 24/12/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
1365 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
1366 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Nilkunthia W/S Scheme T/W-I Application No=2004684512 Reference ID=204275851 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00576/2024-2025 | BP-2024-25-102 | 26/04/2024 | 0 | WBSEDCL | 4.02 | 0 | 0
1367 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NILKANTHIA AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001695/2022-2023 | 622/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 22.81 | 0 | 0
1368 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of BHETIA MALA PWSS. REF CONSUMER ID-204310335, APPLICATION NO-2004739400, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01029/2024-2025 | BP-2024-25-208 | 28/05/2024 | 0 | WBSEDCL | 5.73 | 0 | 0
1369 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of BHETIA MALA PWSS. REF CONSUMER ID-204310299 APPLICATION NO-2004739419, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01030/2024-2025 | BP-2024-25-209 | 28/05/2024 | 0 | WBSEDCL | 6.22 | 0 | 0
1370 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHETIAMLA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001604/2022-2023 | 485/W/MMD | 20/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 22.95 | 15.98 | 10
1371 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Barakalankai PWSS T/W no - II of Narayangarh block Applocation no - 2004754804 , Ref ID - 204323283 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01305/2024-2025 | BP-2024-25-342 | 25/06/2024 | 0 | WBSEDCL | 4.75 | 0 | 0
1372 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Barakalankai PWSS T/W no - I of Narayangarh block Applocation no - 2004752560 , Ref ID - 204317453 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01306/2024-2025 | BP-2024-25-341 | 25/06/2024 | 0 | WBSEDCL | 6.29 | 0 | 0
1373 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MATHURA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004811805/QUOT/03 DT. 11-07-2024 Application NO- 2004811805 Application type-New connection Consumer Id- 204351926 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01978/2024-2025 | C082420136916 | 14/08/2024 | 0 | WBSEDCL | 4.18 | 0 | 0
1374 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MATHURA and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001688/2022-2023 | 561/W/MMD | 20/03/2023 | 180 | M/S B.M. ELECTRICAL | 22.81 | 3.13 | 62
1375 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Satyapur pwss (Ref Consumar ID-204369741),Application No-2004844164,Application Type-New Connection,Name of ccc-Lowada ccc, block-debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02009/2024-2025 | BP-2024-25-579 | 20/08/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
1376 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SATYAPUR AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001602/2022-2023 | 481/W/MMD | 20/03/2023 | 897 | SAIKAT SINHA | 23.01 | 16.47 | 52
1377 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for TW-I of Chaipat(Zone-II)(Nischintapur) pwss ,(Ref Consumar ID-204219008),Application No-2004604095,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00600/2024-2025 |  | 24/04/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
1378 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for TW-I,ZONE-I for chaipat water supply scheme.Ref consumer Id-204087542 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02667/2023-2024 | BP-2023-24-262 | 26/09/2023 | 0 | WBSEDCL | 4.7 | 0 | 0
1379 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for TW-I of chaipat , Zone-II pwss (Ref Consumar ID-204219008),Application No-2004604095,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03932/2023-2024 | BP-2023-24-726 | 23/02/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
1380 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for TW-II of CHAIPAT,ZONE-II pwss (Ref Consumar ID-204239049),Application No-2004633954,Application Type-New Connection,Name of ccc-Sonakhali ccc, block-Daspur-II. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/04394/2023-2024 | BP-2023-24-817 | 13/03/2024 | 0 | WBSEDCL | 13.12 | 0 | 0
1381 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Chaipat (Zone-I & II) & its adjoining mouzas. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001938/2022-2023 | 823/W/MMD | 24/03/2023 | 892 | M/S. SAJAHAN CHOWDHURY | 47.51 | 34.42 | 80
1382 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0
1383 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF BRAHMAN KHALISA PWSS. REF CONSUMER ID-204373748, APPLICATION NO-2004853061, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02014/2024-2025 | C082430150750 | 20/08/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
1384 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF BRAHMAN KHALISA PWSS. REF CONSUMER ID-204373752, APPLICATION NO-2004853092, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02015/2024-2025 | C082430136142 | 20/08/2024 | 0 | WBSEDCL | 3.87 | 0 | 0
1385 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL TW NO-I of ANAR PWSS. REF CONSUMER ID-204204419, APPLICATION NO-2004578966, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03580/2023-2024 | BP-2023-24-638 | 07/02/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
1386 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL TW NO-II of ANAR PWSS. REF CONSUMER ID-204204416, APPLICATION NO-2004578958, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03584/2023-2024 | BP-2023-24-639 | 08/02/2024 | 0 | WBSEDCL | 4.1 | 0 | 0
1387 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ANAR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001447/2023-2024 | 3074/W/MMD | 29/11/2023 | 180 | SANKAR PRASAD DUTTA AND CO | 22.99 | 21.17 | 60
1388 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF KESHARAMBHA PWSS. REF CONSUMER ID-204391647, APPLICATION NO-2004886652, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02457/2024-2025 | C102401980457 | 03/10/2024 | 0 | WBSEDCL | 3.23 | 0 | 0
1389 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF KESHARAMBHA PWSS. REF CONSUMER ID-204391649, APPLICATION NO-2004886653, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02462/2024-2025 | C102401979918 | 03/10/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
1390 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Radhanagar PWSS T/W- I ,Narayangarh Block , Application no- 2004680777 , ref. Id - 204273485 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00697/2024-2025 | BP-2024-25-148 | 09/05/2024 | 0 | WBSEDCL | 4.23 | 0 | 0
1391 | Midnapore Mechanical | Digha Sub-Division | Kadua W/S scheme PH-I Application No.-2004550666 Ref.-204181244 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03292/2023-2024 | BP-2023-24-539 | 11/01/2024 | 0 | WBSEDCL | 2.97 | 0 | 0
1392 | Midnapore Mechanical | Digha Sub-Division | Kadua W/S scheme PH-II Application No.-2004550634 Ref.-204181242 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03293/2023-2024 | BP-2023-24-538 | 11/01/2024 | 0 | WBSEDCL | 2.76 | 0 | 0
1393 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Dontiara and its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000060/2023-2024 | 1232/W/MMD | 25/04/2023 | 180 | PRADIP KUMAR DHABAL | 21.56 | 0 | 0
1394 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at different PWSS of Block Egra - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000050/2023-2024 | 1207/W/MMD | 25/04/2023 | 981 | BHABANI PRASAD MANNA | 59.85 | 0 | 20
1395 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Benadiha water supply scheme T/W no I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03287/2023-2024 | BP-2023-24-500 | 05/01/2024 | 0 | WBSEDCL | 4.63 | 0 | 0
1396 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for New power connection at Benadiha water supply Scheme T/W no - II | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03288/2023-2024 | BP-2023-24-499 | 05/01/2024 | 0 | WBSEDCL | 3.08 | 0 | 0
1397 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
1398 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743601/QUOT/03 DT. 20-05-2024 Application NO- 2004743601 Application type-New connection Consumer Id- 204312616 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01204/2024-2025 | BP-2024-25-322 | 24/06/2024 | 0 | WBSEDCL | 5.12 | 0 | 0
1399 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KULRAKHI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004769788/QUOT/03 DT. 10-06-2024 MEMO NO: AMR/PHE/171 DT. 10-06-2024 Application NO- 2004769788 Application type-New connection Consumer Id- 204327232 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01280/2024-2025 | BP-2024-25-339 | 25/06/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
1400 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KULRAKHI AND IT'S ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001706/2022-2023 | 592/W/MMD | 20/03/2023 | 180 | ASHUTOSH DAS & CO. | 21.53 | 0 | 0
1401 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for TW-I of Kashipur Water Supply Scheme | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03360/2023-2024 | BP-2023-24-534 | 11/01/2024 | 0 | WBSEDCL | 4.56 | 0 | 0
1402 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for TW-II of Kashipur Water Supply Scheme | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03361/2023-2024 | BP-2023-24-535 | 11/01/2024 | 0 | WBSEDCL | 7.91 | 0 | 0
1403 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF SALIKOTHA PWSS. REF CONSUMER ID-204355062, APPLICATION NO-2004817398, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01639/2024-2025 | BP-2024-25-480 | 30/07/2024 | 0 | WBSEDCL | 0.82 | 0 | 0
1404 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of SALIKOTHA PWSS. REF CONSUMER ID-204212538, APPLICATION NO-2004593803, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, NAME OF BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03737/2023-2024 | BP-2023-24-692 | 16/02/2024 | 0 | WBSEDCL | 7.51 | 0 | 0
1405 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SALIKOTHA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001924/2022-2023 | 843/W/MMD | 24/03/2023 | 861 | SOUMEN ELECTRIC | 27.37 | 22.62 | 20
1406 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
1407 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF KHARIPARA PWSS. REFERENCE CONSUMER ID NO-204408593, APPLICATION NO-2004913778, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02980/2024-2025 | C112417261960 | 12/11/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
1408 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF KHARIPARA PWSS. REFERENCE CONSUMER ID NO-204408594, APPLICATION NO-2004913789, APPLICATION TYPE- NEW CONNECTION, NAME OF CCC- KESHIARY CCC, NAME OF BLOCK- KESHIARY. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02981/2024-2025 | C112417261030 | 12/11/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
1409 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHARIPARA AND IT'S ADJOINING MOUJASunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001423/2023-2024 | 3075/W/MMD | 29/11/2023 | 489 | DAS ENTERPRISE | 22.6 | 14.53 | 25
1410 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for shifting of PHE meter room with allied works at PH-I of Barsundra w/s scheme under MMD PHE Dte. Name of C.C.C.-Brajalalchak Reference ID-860311526 Application ID-100000117246 Quotation Date-27/08/2024 Quotation Due Date-25/11/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02393/2024-2025 | C092404597616 | 05/09/2024 | 0 | WBSEDCL | 1.38 | 0 | 0
1411 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Barsundra PWSS in the District of Purba Medinipur under JJM programme, Block ¿ Haldia, District - Purba Medinipur under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001545/2022-2023 | 396/W/MMD | 15/03/2023 | 180 | BALAJI CONSTRUCTION | 12.4 | 11.59 | 60
1412 | Midnapore Mechanical | Haldia Sub-Division | Additional works for providing and installation of submersible pumping machineries and other electromechanical equipments for Rejuvenation of elctro-mechanical components of Barsundra PWSS in the district of purba medinipur district under JJM program,Block-Haldia,under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001560/2023-2024 | 951/HESD | 30/11/2023 | 7 | BALAJI CONSTRUCTION | 0.69 | 0.54 | 100
1413 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR MULGRAM WATER SUPPLY SCHEME, T W NO 3 JJM WORKS, SCHEME CODE SM/15578, APPLICATION NO 2004759871, REFERENCE ID 204321899, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01171/2024-2025 | C082421719721 | 16/08/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
1414 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MULGRAM TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER GHATAL BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002018/2022-2023 | 916/W/MMD | 27/03/2023 | 180 | BALAJI CONSTRUCTION | 12.63 | 0 | 0
1415 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of BHATUIGERIA PWSS. REF CONSUMER ID-204269804, APPLICATION NO-2004675318, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00309/2024-2025 | BP-2024-25-78 | 24/04/2024 | 0 | WBSEDCL | 4.27 | 0 | 0
1416 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of BHATUIGERIA PWSS. REF CONSUMER ID-204269077, APPLICATION NO-2004675295, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00315/2024-2025 | BP-2024-25-79 | 24/04/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
1417 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BHATUIGERYA PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001642/2022-2023 | 574/W/MMD | 20/03/2023 | 180 | DEY ENTERPRISE | 25.26 | 0 | 0
1418 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-IV, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606750/QUOT/03/424 DT. 19-02-2024 Application NO- 2004606750 Application type-New connection Reference Id- 204221087 | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04140/2023-2024 | BP-2023-24-761 | 01/03/2024 | 0 | WBSEDCL | 2.62 | 0 | 0
1419 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-III Of BAJKUL W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II Ref. Memo No- 2004606772/QUOT/03/426 DT. 19-02-2024 Application NO- 2004606772 Application type-New connection Reference Id- 204221105 | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/04141/2023-2024 | BP-2023-24-760 | 01/03/2024 | 0 | WBSEDCL | 2.86 | 0 | 0
1420 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-III, Block Bhagawanpur II, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000081/2023-2024 | 1275/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 37.71 | 22.94 | 76
1421 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone III Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002722/2023-2024 | 1067/W/MMD | 14/03/2024 | 360 | DEBJYOTI BASU | 25.9 | 0 | 55
1422 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR ARJUNI , ZONE-III, TW-I, WATER SUPPLY SCHEME, T W NO I , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004793768, REFERENCE ID 204340976, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01461/2024-2025 | BP-2024-25-425 | 16/07/2024 | 0 | WBSEDCL | 0.11 | 0 | 0
1423 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-I, T W NO I , [ RADHANAGAR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004722207, REFERENCE ID 204303570, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01464/2024-2025 | BP-2024-25-426 | 16/07/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
1424 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ BALARAMPUR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004734869, REFERENCE ID 204308441, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01734/2024-2025 | BP-2024-25-503 | 30/07/2024 | 0 | WBSEDCL | 7.56 | 0 | 0
1425 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE-II, T W NO 2, [PATHRI ], JJM WORKS, BLOCK- KHARAGPUR-I, SCHEME CODE SM/15533, APPLICATION NO 2004834083, REFERENCE ID 204364748, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02041/2024-2025 | BP-2024-25-602 | 29/08/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
1426 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, Z-V, T W NO I , [ HARIHARPUR ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004800012, REFERENCE ID 204344344, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02359/2024-2025 | C092403086596 | 04/09/2024 | 0 | WBSEDCL | 1.52 | 0 | 0
1427 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR ARJUNI WATER SUPPLY SCHEME, ZONE IV , T W NO I , MINI , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004601377, REFERENCE ID 204217215, MANIKPARA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04208/2023-2024 | BP-2023-24-789 | 06/03/2024 | 0 | WBSEDCL | 0.11 | 0 | 0
1428 | Midnapore Mechanical | Kharagpur Sub-Division | ARJUNI WATER SUPPLY SCHEME, ZONE- III, T W - I ,[ SHUSHNIA ] , JJM WORKS, SCHEME CODE SM/15533, APPLICATION NO 2004614503, REFERENCE ID 204224894, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04209/2023-2024 | BP-2023-24-788 | 06/03/2024 | 0 | WBSEDCL | 0.11 | 0 | 0
1429 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001621/2022-2023 | 536/W/MMD | 20/03/2023 | 180 | AHALYA ENGINEERING WORKS | 45.54 | 29.36 | 60
1430 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Arjuni (Zone-I, II, III, IV, V & VI) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001958/2022-2023 | 870/W/MMD | 27/03/2023 | 180 | AHALYA ENGINEERING WORKS | 35.94 | 22.11 | 35
1431 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ADDITIONAL QUOTATION FEE FOR EFFECTING NSC AT TW-I & II of TEGHORI PWSS. REF ID-860299039, APPLICATION ID-100000106469, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00689/2024-2025 | BP-2024-25-126 | 06/05/2024 | 0 | WBSEDCL | 0.24 | 0 | 0
1432 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ADDITIONAL QUOTATION (2) FEE FOR EFFECTING NSC AT TW-I & II of TEGHORI PWSS. REF ID-860298907, APPLICATION ID-100000106407, APPLICATION TYPE-DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00690/2024-2025 | BP-2024-25-125 | 06/05/2024 | 0 | WBSEDCL | 1.49 | 0 | 0
1433 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of TAGHORI PWSS. REF CONSUMER ID-204211957, APPLICATION NO-2004590158, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03740/2023-2024 | BP-2023-24-690 | 16/02/2024 | 0 | WBSEDCL | 8.97 | 0 | 0
1434 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of TAGHORI PWSS. REF CONSUMER ID-204212284, APPLICATION NO-2004590144, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03741/2023-2024 | BP-2023-24-689 | 16/02/2024 | 0 | WBSEDCL | 0.29 | 0 | 0
1435 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TEGHARI AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002008/2022-2023 | 907/W/MMD | 27/03/2023 | 180 | JYOTY SOLAR POWER | 21.98 | 13.99 | 30
1436 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 181 | M/S BIKASH DE | 3.69 | 0 | 0
1437 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.14 | 50
1438 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAGDOBA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001960/2022-2023 | 872/W/MMD | 27/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 5.99 | 0 | 0
1439 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of BARCHUNFALI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004877553/QUOT/03 DT. 29-08-2024 Application NO- 2004877553 Application type-New connection Consumer Id- 204387021 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02397/2024-2025 | C092406568982 | 06/09/2024 | 0 | WBSEDCL | 6.02 | 0 | 0
1440 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Augmentation of Barchunfali Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001998/2022-2023 | 893/W/MMD | 27/03/2023 | 180 | SUDIKSHA CONSTRUCTION | 11.83 | 0 | 0
1441 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Manibpur water supply scheme T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03564/2023-2024 | BP-2023-24-619 | 07/02/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
1442 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Manibpur PWSS , T/W - II , Application no - 2004582208 , Ref ID - 204206278 , Madpur CCC | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03747/2023-2024 | BP-2023-24-708 | 16/02/2024 | 0 | WBSEDCL | 4.14 | 0 | 0
1443 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001575/2022-2023 | 459/W/MMD | 20/03/2023 | 180 | BALAJI CONSTRUCTION | 22.89 | 0 | 60
1444 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DAKSHIN KALYANPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004671005/QUOT/03 DT. 05-04-2024 Application NO- 2004671005 Application type-New connection Consumer Id- 204268105 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00297/2024-2025 | BP-2024-25-47 | 18/04/2024 | 0 | WBSEDCL | 2.16 | 0 | 0
1445 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DAKSHIN KALYANPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001749/2022-2023 | 604/W/MMD | 20/03/2023 | 180 | KRISHNA ENGINEERING | 11.95 | 5.39 | 45
1446 | Midnapore Mechanical | Kharagpur Sub-Division | KHEMASOLI WATER SUPPLY SCHEME , TUBE WELL NO II, SCHEME CODE - SM/15590, BLOCK KHARAGPUR - I, MB NO 3580, PAGE 30-31, and ORIGINAL QUOTATION | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02668/2023-2024 | BP-2023-24-261 | 26/09/2023 | 0 | WBSEDCL | 0.54 | 0 | 0
1447 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Khemasoli (Zone-I, II and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002022/2022-2023 | 920/W/MMD | 27/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 31.54 | 8.06 | 43
1448 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION MONEY FOR BHEWMA WATER SUPPLY SCHEME,ZONE-II, T W - III , JJM WORKS, SCHEME CODE SM/15219, PARENT CODE SM/03856 , APPLICATION NO 2004571035, REFERENCE ID 204198622, SABONG CCC, WBSEDCL | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03552/2023-2024 | BP-2023-24-607 | 07/02/2024 | 0 | WBSEDCL | 4 | 0 | 0
1449 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
1450 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.06 | 100
1451 | Midnapore Mechanical | Digha Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-3, TW-II OF SHANKARPUR WS SCHEME UNDER MMD, PHE DTE, BLOCK-RAMNAGAR -1, DIGHA CCC APP. NO-2004746394 CON ID-204313991 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01143/2024-2025 | BP-2024-25-257 | 06/06/2024 | 0 | WBSEDCL | 0.71 | 0 | 0
1452 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I , ZONE-III Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-I, DIGHA C.C.C. Ref. Memo No- 2004626526/QUOT/03 DT. 04-03-2024 Application NO- 2004626526 Application type-New connection Consumer Id- 204233340 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04341/2023-2024 | BP-2023-24-809 | 11/03/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
1453 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-III in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000040/2023-2024 | 1211/W/MMD | 25/04/2023 | 859 | S.S.GHORAI | 23.52 | 14.1 | 75
1454 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
1455 | Midnapore Mechanical | Digha Sub-Division | Quotation For New Service Connections at Tube Well-III of Panchrol W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746343 Consumer ID.-204313789 Application Date.-29/05/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01140/2024-2025 | BP-2024-25-251 | 06/06/2024 | 0 | WBSEDCL | 4.71 | 0 | 0
1456 | Midnapore Mechanical | Digha Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
1457 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN PANCHROL PWSS UNDER EGRA-I BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001994/2022-2023 | 899/W/MMD | 27/03/2023 | 720 | M/S EMMESS | 12.63 | 8.28 | 90
1458 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at tw-III of Bheribaranga ws under MMD,PHE Dte ,Block-Ramnagar-II. Digha CCC Application no-2004764489 CON ID-204324289 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01225/2024-2025 | BP-2024-25-290 | 18/06/2024 | 0 | WBSEDCL | 4.32 | 0 | 0
1459 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN BHERIBARANGA PWSS UNDER RAMNAGAR-II BLOCK (PHASE-II) within Purba Medinipur District under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001990/2022-2023 | 897/W/MMD | 27/03/2023 | 720 | A.S.ENTERPRISE | 12.62 | 0 | 75
1460 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at ckakkesi PWSS , T/W - I , Application no - 2004582548 , Ref ID - 204206277 , Madpur CCC | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03750/2023-2024 | BP-2023-24-707 | 16/02/2024 | 0 | WBSEDCL | 3.51 | 0 | 0
1461 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Chak keshi PWSS P/H- II , application no - 2004609056 , Ref id - 204222612 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04188/2023-2024 | BP-2023-24-772 | 06/03/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
1462 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKKESHI AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001944/2022-2023 | 830/W/MMD | 24/03/2023 | 739 | WEST BENGAL ENGINEERING CO. | 22.63 | 0 | 80
1463 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BARHUARY ZIII W/S Scheme under MMD, PHE, Dte. Block- EGRA II, WBSEDCL SUPPLY OFFICE: BALIGHAIC.C.C. Ref. Memo No- 2004737554/QUOT/03 DT. 16-05-2024 Application NO- 2004737554 Application type-New connection Consumer Id- 204309058 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01227/2024-2025 | BP-2024-25-292 | 18/06/2024 | 0 | WBSEDCL | 3.27 | 0 | 0
1464 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, Zone-III Of BATHUARY W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004793307/QUOT/03/380 DT. 02-07-2024 Application NO- 2004793307 Application type-New connection Consumer Id- 204346846 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01698/2024-2025 | BP-2024-25-497 | 31/07/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
1465 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
1466 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme TW no.-I, Z-IV Ref.-204156071 Application ID-2004521698 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03156/2023-2024 | BP-2023-24-442 | 19/12/2023 | 0 | WBSEDCL | 2.63 | 0 | 0
1467 | Midnapore Mechanical | Digha Sub-Division | Sankarpur W/S scheme PH.-II, zone-IV Application No.-2004565718 Ref.-204193727 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03540/2023-2024 | BP-2023-24-622 | 07/02/2024 | 0 | WBSEDCL | 7.26 | 0 | 0
1468 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-IV in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000041/2023-2024 | 1212/W/MMD | 25/04/2023 | 180 | SUBHASIS ROY | 23.93 | 22.24 | 90
1469 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Argoal PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001842/2022-2023 | 759/W/MMD | 23/03/2023 | 180 | MENAKA ENTERPRISE | 12.23 | 5.82 | 35
1470 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION FOR NEW POWER CONNECTION OF SHYAMSUNDAR [AUG.] WATER SUPPLY ASCHEME [ APPLICATION --2004480397 REFERENCE ID ----204122721 SABONG CCC, QUOTATION NO ---2004480397/QUOT/03 DATED 26/10/2023, SCHEME NAME --- SHYAMSUNDAR AUG. , SCHEME CODE ---SM/17949 , MB NO--3580 ] | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02884/2023-2024 | BP-2023-24-343 | 10/11/2023 | 0 | WBSEDCL | 3.49 | 0 | 0
1471 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Shyamsundarpur & its adj. mouzas, Block - Sabang, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002200/2022-2023 | 458/W/MMD | 20/03/2023 | 180 | S.B.ENTERPRISE | 10.91 | 10.01 | 100
1472 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Keshpur PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002129/2022-2023 | 1067/W/MMD | 29/03/2023 | 180 | BHABANI PRASAD MANNA | 11.39 | 0 | 0
1473 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Dhaneswarpur (Block Dantan-II) PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002128/2022-2023 | 1066/W/MMD | 29/03/2023 | 308 | BHABANI PRASAD MANNA | 11.39 | 9.92 | 100
1474 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAMKRISHNAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000206/2023-2024 | 1491/W/MMD | 22/06/2023 | 715 | SUJOY RANJAN BHOWMICK | 23.69 | 14.1 | 100
1475 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) Nos. Boosting Tube Well for Paramanandapur Water Supply Scheme of Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. within the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000039/2023-2024 | 1208/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 11.44 | 7.08 | 50
1476 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MANIKKUNDA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000208/2023-2024 | 1492/W/MMD | 22/06/2023 | 180 | S.K.ENTERPRISE | 25.26 | 0 | 0
1477 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of DUAN-II pwss (Ref Consumar ID-204235945),Application No-2004627252,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/04396/2023-2024 | BP-2023-24-816 | 13/03/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
1478 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of DUAN-II pwss (Ref Consumar ID-204235948),Application No-2004627235,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/04397/2023-2024 | BP-2023-24-815 | 13/03/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1479 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DUAN-II AND ITS ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002201/2022-2023 | 477/W/MMD | 20/03/2023 | 716 | M/S. SAJAHAN CHOWDHURY | 23 | 18.08 | 60
1480 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHASKENDU BAGICHA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001949/2022-2023 | 832/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 0 | 0
1481 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Sautia (Zone-II) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000035/2023-2024 | 1199/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 22.62 | 12.77 | 50
1482 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KADABANI AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000006/2023-2024 | 1122/W/MMD | 12/04/2023 | 180 | ABHIJIT MUKHERJEE | 21.56 | 13.58 | 40
1483 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000212/2023-2024 | 1494/W/MMD | 22/06/2023 | 180 | DEBJYOTI BASU | 27.38 | 17.2 | 80
1484 | Midnapore Mechanical | Contai Sub-Division | Gurgram W/S scheme PH-II,(River Side) Application No.-2004523993 Ref.-204157866 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03175/2023-2024 | BP-2023-24-475 | 27/12/2023 | 0 | WBSEDCL | 9.17 | 0 | 0
1485 | Midnapore Mechanical | Contai Sub-Division | Gurgram W/S scheme PH-I,(Primary School) Application No.-2004523960 Ref.-204157826 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03176/2023-2024 | BP-2023-24-476 | 27/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
1486 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GURGRAM & ADJOINING MOUZAS, Block- Bhagwanpur I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000309/2023-2024 | 1628/W/MMD | 25/07/2023 | 180 | ALPHA ENTERPRISE | 23.68 | 23.17 | 80
1487 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of URURI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No- 2004570649/QUOT/03 DT. 22-01-2024 Application NO- 2004570649 Application type-New connection Consumer Id- 204198017 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01133/2024-2025 | BP-2024-25-249 | 06/06/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
1488 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Under URURI W/S Scheme under MMD,PHE,Dte. Ref. Quotation no- 2004558742/Quot/03 dt. 10- Jan-24 quotation Due date- 09-Jan-25 Application NO- 2004558742 Application type-New connection Reference Id- 204188975 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03657/2023-2024 | BP-2023-24-676 | 15/02/2024 | 0 | WBSEDCL | 3.62 | 0 | 0
1489 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1490 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at MANGRUL Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000753/2023-2024 | 2283/W/MMD | 29/08/2023 | 180 | S.B.ENTERPRISE | 30.52 | 22.69 | 90
1491 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TALADIHA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004969351/QUOT/03 DT. 18-11-2024 MEMO NO: AMR/PHE/512 DT. 18-11-2024 Application NO- 2004969351 Application type-New connection Consumer Id- 204448691 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03064/2024-2025 | C112433888301 | 27/11/2024 | 0 | WBSEDCL | 6.1 | 0 | 0
1492 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TALADIHA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001403/2022-2023 | 2414/W/MMD | 31/12/2022 | 857 | ECO ENTERPRISE | 22.8 | 11.71 | 40
1493 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONAKANIA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DANTAN- I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000022/2023-2024 | 1184/W/MMD | 25/04/2023 | 180 | AMUSAR IMPEX PVT. LTD | 23.77 | 18.83 | 15
1494 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Additional Tw No-II (Boosting) of SONAKANIA water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist.:- Paschim Medinipur | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002721/2023-2024 | 1066/W/MMD | 14/03/2024 | 180 | MANORANJAN DEY | 6.72 | 0 | 0
1495 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER CHANDRAKONA - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICTunder JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000367/2023-2024 | 1693/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 49.92 | 0 | 80
1496 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR GOPALNAGAR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/19044, APPLICATION NO 2004696196, REFERENCE ID 204284323, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00639/2024-2025 | BP-2024-25-113 | 06/05/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1497 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR GOPALNAGAR WATER SUPPLY SCHEME, T W - II , JJM WORKS, SCHEME CODE SM/19044, APPLICATION NO 2004702574, REFERENCE ID 204287860, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00829/2024-2025 | BP-2024-25-160 | 13/05/2024 | 0 | WBSEDCL | 7.03 | 0 | 0
1498 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopalnagar Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/001434/2023-2024 | 3088/W/MMD | 29/11/2023 | 495 | S.P. ENTERPRISE | 22.95 | 0 | 80
1499 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric Quotation for MAGRAJPUR (MINIPIPED) Water Supply Scheme, (Ref. ID-203942445) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02230/2023-2024 | BP-2023-24-237 | 12/09/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
1500 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Magrajpur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000018/2022-2023 | 559/W/MMD | 12/04/2022 | 120 | M/S NABIN GOPAL SENGUPTA | 6.46 | 0 | 100
1501 | Midnapore Mechanical | Kharagpur Sub-Division | ELECTRIC QUOTATION BILL FOR ZONE-I , TW NO-III OF BARISHA PWSS. REF CONSUMER ID-204351761, APPLICATION NO-2004812598, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01578/2024-2025 | BP-2024-25-459 | 23/07/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
1502 | Midnapore Mechanical | Kharagpur Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-III, Zone -I OF BARISHA PWSS (NARANGADIHI). REF CONSUMER ID-204376280, APPLICATION NO-2004857600, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02399/2024-2025 | BP-2024-25-650 | 06/09/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
1503 | Midnapore Mechanical | Kharagpur Sub-Division | ELECTRIC QUOTATION BILL FOR ZONE-II, TW NO-III OF BARISHA PWSS. REF CONSUMER ID-204391668, APPLICATION NO-2004886574, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02428/2024-2025 | C102415730586 | 05/10/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
1504 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Barisha {Zone-I, II of (II/I and II/II)} and its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001442/2023-2024 | 3098/W/MMD | 29/11/2023 | 540 | DEBJYOTI BASU | 34.18 | 24.73 | 25
1505 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Melerachak water supply scheme T/W - I | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03559/2023-2024 | BP-2023-24-630 | 08/02/2024 | 0 | WBSEDCL | 4.37 | 0 | 0
1506 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Melerachak PWSS , T/W - I , Application no - 2004582161 , Ref ID - 204206275 , Madpur CCC | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03748/2023-2024 | BP-2023-24-706 | 16/02/2024 | 0 | WBSEDCL | 4.25 | 0 | 0
1507 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MELERACHAK AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000390/2023-2024 | 1729/W/MMD | 09/08/2023 | 180 | SUJOY RANJAN BHOWMICK | 27.36 | 18 | 60
1508 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of DAKHINDIHA PWSS. REF CONSUMER ID-204204414, APPLICATION NO-2004578903, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03581/2023-2024 | BP-2023-24-632 | 08/02/2024 | 0 | WBSEDCL | 3.04 | 0 | 0
1509 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL TW NO-I of DAKHINDIHA PWSS. REF CONSUMER ID-204204413, APPLICATION NO-2004578886, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03582/2023-2024 | BP-2023-24-633 | 08/02/2024 | 0 | WBSEDCL | 2.9 | 0 | 0
1510 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DAKSHINDIHA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001428/2023-2024 | 3082/W/MMD | 29/11/2023 | 180 | CONCORD ENGINEERING | 21.56 | 19.3 | 30
1511 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR TANGASOL WATER SUPPLY SCHEME ( NEAR ICDS ) , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580955, REFERENCE ID 204205371, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/03725/2023-2024 | BP-2023-24-698 | 16/02/2024 | 0 | WBSEDCL | 4.09 | 0 | 0
1512 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR TANGASOL WATER SUPPLY SCHEME ( GALUKSAL ) JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004581010, REFERENCE ID 204205373, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/03726/2023-2024 | BP-2023-24-697 | 16/02/2024 | 0 | WBSEDCL | 3.99 | 0 | 0
1513 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR TUNGASOLE WATER SUPPLY SCHEME, ZONE-II , T W NO I ,MINI [ NEAR PRIMARY SCHOOL ] , KGP-I , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580975, REFERENCE ID 204205372, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/04268/2023-2024 | BP-2023-24-791 | 06/03/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
1514 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR TUNGASOLE WATER SUPPLY SCHEME, ZONE-I , T W NO II [ NEAR AMGACHIYA ] , KGP-I , JJM WORKS, SCHEME CODE SM/18696, APPLICATION NO 2004580997, REFERENCE ID 204205374, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/04269/2023-2024 | BP-2023-24-790 | 06/03/2024 | 0 | WBSEDCL | 5.81 | 0 | 0
1515 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000388/2023-2024 | 1727/W/MMD | 09/08/2023 | 180 | HARA PROSAD DAS | 23.73 | 15.56 | 40
1516 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Tangasol (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. (Part-II) | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000394/2023-2024 | 1733/W/MMD | 09/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 21.57 | 12.46 | 45
1517 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for GOPINATHPUR Water Supply Scheme T/W-I, (Ref. ID-204089465) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02886/2023-2024 | BP-2023-24-310 | 01/11/2023 | 0 | WBSEDCL | 3.57 | 0 | 0
1518 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for GOPINATHPUR Water Supply Scheme T/W-II, (Ref. ID-204089466) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02887/2023-2024 | BP-2023-24-319 | 01/11/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
1519 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOPINATHPUR and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002031/2022-2023 | 939/W/MMD | 28/03/2023 | 180 | MENAKA ENTERPRISE | 23.67 | 21.89 | 100
1520 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DWARIKAPUR and ADJOINING MOUJAS, Block ¿ Bhagwanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001408/2022-2023 | 2419/W/MMD | 31/12/2022 | 180 | BOSE & CHATTERJEE INDUSTRIES | 22.76 | 0 | 0
1521 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
1522 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Routhmoni PWSS T/W - I , Application no- 2004812911, Ref no : 204353062 | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | BILL/01579/2024-2025 | BP-2024-25-458 | 23/07/2024 | 0 | WBSEDCL | 5.12 | 0 | 0
1523 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Routhmoni PWSS T/W - II Khargpur - II Block, Application No - 2004799376 , Ref ID : 204344493 | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | BILL/02017/2024-2025 | C082430203830 | 20/08/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
1524 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RAUTMANI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/001436/2023-2024 | 3090/W/MMD | 29/11/2023 | 180 | AMITAVA CHAKRABORTY | 25.24 | 0 | 0
1525 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Radhakishore PWSS T/W - II under KGP - II block , Application No- 2004799279, Ref No- 204344494 | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | BILL/01807/2024-2025 | BP-2024-25-525 | 06/08/2024 | 0 | WBSEDCL | 6.95 | 0 | 0
1526 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Radhakishore PWSS T/W - I Khargpur - II Block, Application No - 2004799343 , Ref ID : 204344492 | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | BILL/02016/2024-2025 | BP-2024-25-585 | 20/08/2024 | 0 | WBSEDCL | 4.95 | 0 | 0
1527 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHAKISHOR AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000359/2023-2024 | 1687/W/MMD | 04/08/2023 | 696 | ORIENTAL ENGINEERING CO. | 27.35 | 0 | 80
1528 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of 33/0.433 KV, 3000 KVA Electrical Substation with allied Electrical works at WTP at Panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/000163/2024-2025 | 1659/W/MMD | 29/07/2024 | 180 | THE MARKET ELECTRICAL ENGINEERING WORKS | 747.99 | 0 | 0
1529 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of 11/0.433 KV, 800 KVA Electrical Substation with allied Electrical works at Pingla Boosting at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/002705/2023-2024 | 1057/W/MMD | 13/03/2024 | 180 | APEX ENGINEERING & PROJECT CO | 338.92 | 0 | 0
1530 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of 11/0.433 KV, 1600 KVA Electrical Substation with allied Electrical works at Intake point (River bank) at panskura under surface water based water supply scheme for Pingla, Panskura and Khargpur-II Block in Purba & Paschim Medinipur District under JJM under Midnapore Mechanical Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/002717/2023-2024 | 1058/W/MMD | 13/03/2024 | 180 | THE MARKET ELECTRICAL ENGINEERING WORKS | 485.76 | 0 | 0
1531 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004570684/QUOT/03 DT. 22-01-2024 Application NO- 2004570684 Application type-New connection Consumer Id- 204198020 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04389/2023-2024 | BP-2023-24-819 | 13/03/2024 | 0 | WBSEDCL | 4.4 | 0 | 0
1532 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KAYEMGERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004558744/QUOT/03 DT. 10-01-2024 Application NO- 2004558744 Application type-New connection Consumer Id- 204188974 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04393/2023-2024 | BP-2023-24-818 | 13/03/2024 | 0 | WBSEDCL | 4.19 | 0 | 0
1533 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAYEMGERYA and ADJOINING MOUJAS, Block Bhagawanpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001321/2022-2023 | 2323/W/MMD | 29/12/2022 | 1077 | MAA TARA ENTERPRISE | 22.75 | 9.67 | 45
1534 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Palashpai (Zone-I and II) and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000366/2023-2024 | 1696/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 46.02 | 35.66 | 50
1535 | Midnapore Mechanical | Ghatal Subdivision | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 40
1536 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
1537 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for MAJNA Water Supply Scheme T/W-III, (Ref. ID-204068438) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01930/2023-2024 | BP-2023-24-235 | 08/09/2023 | 0 | WBSEDCL | 3.52 | 0 | 0
1538 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Supply Scheme for Majna, Block Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001912/2022-2023 | 813/W/MMD | 24/03/2023 | 180 | MEGA SOLAR ENERGY | 11.34 | 4.67 | 58
1539 | Midnapore Mechanical | Kharagpur Sub-Division | Service connection charge of WBSEDCL at Nankar Nila, Chandkuri | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001030/2021-2022 | 2003774962/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
1540 | Midnapore Mechanical | Kharagpur Sub-Division | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Nankarnila water supply scheme, tube well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001127/2021-2022 | 2509/W/MMD | 30/11/2021 | 4 | SUJOY RANJAN BHOWMICK | 4.47 | 0 | 100
1541 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Nankarnila, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001175/2021-2022 | 121/W/MMD | 24/01/2022 | 120 | SHOVAN KUMAR DAS | 6.51 | 6.39 | 0
1542 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dwariberia water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001140/2022-2023 | 2121/W/MMD | 28/11/2022 | 120 | PRANAB KUMAR DAS | 11.12 | 9.38 | 100
1543 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric quotation for Chandiveti PWSS Tube Well- III in connection Mukundapur CCC (2004186280) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00163/2022-2023 | BP-2022-23-131 | 14/03/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
1544 | Midnapore Mechanical | Contai Sub-Division | Electric quotation for Junboni PWSS Tube Well-IV WS Scheme (Ref. ID-203911303) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00318/2022-2023 | BP-2022-23-137 | 20/03/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
1545 | Midnapore Mechanical | Contai Sub-Division | Additional Quotation Bill for T/W NO-IV Of JUNBONI W/S Scheme under MMD, PHE, Dte. Block- Contai-I, PICHABANI C.C.C. Ref. Memo No- 2004620649/QUOT/03 DT. 27-02-2024 Application NO- 2004620649 Reference Id- 204229267 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04304/2023-2024 | BP-2023-24-798 | 07/03/2024 | 0 | WBSEDCL | 6.88 | 0 | 0
1546 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Junbani, Block ¿ Contai I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000202/2023-2024 | 1482/W/MMD | 21/06/2023 | 467 | MAA KALI ENTERPRISE | 11.4 | 9.96 | 25
1547 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Chandrakona Road Rly. Station to Accommodate FHTC, Block - Garhbeta-III, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001963/2022-2023 | 874/W/MMD | 27/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 23.76 | 11.13 | 95
1548 | Midnapore Mechanical | Ghatal Subdivision | Electric Quotation ID No. 204047232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01614/2023-2024 | BP-2023-24-132 | 20/07/2023 | 0 | WBSEDCL | 3.07 | 0 | 0
1549 | Midnapore Mechanical | Ghatal Subdivision | Electric Quotation for SONAKHALI Water Supply Scheme T/W-II (Ref. ID-204046818 ) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01615/2023-2024 | BP-2023-24-133 | 20/07/2023 | 0 | WBSEDCL | 5.24 | 0 | 0
1550 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Sonakhali to Accommodate FHTC, Block - Daspur-II, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001592/2022-2023 | 452/W/MMD | 20/03/2023 | 864 | SAIKAT SINHA | 27.36 | 22.99 | 71
1551 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Khejuri PWSS to accommodate FHTC within Khejuri-II Block under Contai Sub-Division of Tamluk Division in Purba Meinipur District Zone-I (Phase-2) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001962/2022-2023 | 861/W/MMD | 27/03/2023 | 180 | DIAMOND ELECTRICAL WORKS | 13.43 | 12.63 | 95
1552 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000018/2023-2024 | 1134/W/MMD | 12/04/2023 | 180 | ORIENTAL ENGINEERING CO. | 89.14 | 35.3 | 20
1553 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Simulia PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001965/2022-2023 | 864/W/MMD | 27/03/2023 | 180 | SWAPAN ENTERPRISE | 13.66 | 12.85 | 35
1554 | Midnapore Mechanical | Kharagpur Sub-Division | Electric Quotation for Add tw no- IV of Pingla w/s scheme.(Consumer ID-203970943) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00082/2023-2024 | BP-2023-24-23 | 28/04/2023 | 0 | WBSEDCL | 2.83 | 0 | 0
1555 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for Pingla PWSS Tube Well-III WS Scheme (Ref. ID 203917728) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00398/2022-2023 | BP-2022-23-146 | 27/03/2023 | 0 | WBSEDCL | 0.49 | 0 | 0
1556 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000148/2023-2024 | 1375/W/MMD | 30/05/2023 | 680 | SHOVAN KUMAR DAS | 25.24 | 23.41 | 20
1557 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Pingla to Accommodate FHTC, Block - Pingla, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001308/2022-2023 | 2310/W/MMD | 29/12/2022 | 180 | SHOVAN KUMAR DAS | 25.52 | 0 | 0
1558 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service Connection charges of WBSEDCL for Additional T/W-IV of Debhog Water Supply Scheme (Consumer No. 2004156795) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00044/2022-2023 | Bp-2022-23-87 | 10/01/2023 | 0 | WBSEDCL | 0.19 | 0 | 0
1559 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service Connection charges of WBSEDCL for Additional T/W-III of Debhog Water Supply Scheme (Consumer No. 2004156111) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00045/2022-2023 | BP-2022-23-88 | 04/01/2023 | 0 | WBSEDCL | 2.2 | 0 | 0
1560 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments 250 X 150 mm dia. Deep tube well with (A.S.T.M.D. Schedule-80) Medium Duty P.V.C. Pipe and 150 mm dia. Fiberglass strainer sunk AS ADDITIONAL T.W. (T/W No.- III) of Debhog W/S Scheme Within Sabang Block Under Midnapore Division PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000126/2023-2024 | 1346/W/MMD | 24/05/2023 | 180 | S.S.GHORAI | 11.88 | 10.55 | 100
1561 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Supply and delivery at site Submersible pumping machinery and other electro-mechanical equipment in connection with Rejuvenation of Ground water based piped piped water supply scheme for PH No IV of Debhog Part to accommodate FHTC under Sabang Block in Paschim Medinipur District under M.M.D,.PH.E. DTE. TSM009949 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000235/2023-2024 | 601/MMSD-I | 05/06/2023 | 15 | SUBHASIS ROY | 5.76 | 0 | 0
1562 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001303/2022-2023 | 2305/W/MMD | 29/12/2022 | 180 | SUBHASIS ROY | 10.78 | 0 | 0
1563 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Debhog water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001446/2022-2023 | 1334/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 3.68 | 50
1564 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW IV of Debhog water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001482/2022-2023 | 1333/MMSD-I | 26/12/2022 | 15 | DEBJYOTI BASU | 4.37 | 3.76 | 50
1565 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 0.9 | 0.06 | 25
1566 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 184 | M/S BIKASH DE | 3 | 0.2 | 100
1567 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 184 | SUBHASIS ROY | 0.9 | 0.07 | 100
1568 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Monoharpur PWSS to Accommodate FHTC in Haldia Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000065/2023-2024 | 1224/W/MMD | 25/04/2023 | 180 | TAPAN KUMAR SARKAR | 24.79 | 0 | 0
1569 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK BAJIT AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001897/2022-2023 | 796/W/MMD | 24/03/2023 | 180 | CHAKRABORTY MINING & ENGINEERING | 21.58 | 12.91 | 38
1570 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for NARANDIHA Water Supply Scheme T/W-III, (Ref. ID-204068440) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01931/2023-2024 | BP-2023-24-236 | 08/09/2023 | 0 | WBSEDCL | 3.76 | 0 | 0
1571 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001978/2022-2023 | 817/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 35.55 | 22.74 | 40
1572 | Midnapore Mechanical | Digha Sub-Division | Quotation For New Service Connections at Tube Well-I of Shwina W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746256 Consumer ID.-204316922 Application Date.-29/05/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01138/2024-2025 | BP-2024-25-253 | 06/06/2024 | 0 | WBSEDCL | 3.74 | 0 | 0
1573 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHWNIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001598/2022-2023 | 502/W/MMD | 20/03/2023 | 864 | SRI KRISHNA NIRMAN | 21.57 | 0 | 53
1574 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAUDDHA CHULI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001629/2022-2023 | 513/W/MMD | 20/03/2023 | 180 | GLACIER ENGINEERING CO. | 22.79 | 17.58 | 50
1575 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-I of Eriakhali w/s scheme,Block-Sutahata under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695183 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-8500W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00649/2024-2025 | BP-2024-25-108 | 06/05/2024 | 0 | WBSEDCL | 6.26 | 0 | 0
1576 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-II Of Erekhali w/s scheme, Block-Sutahata in the Dist. of purba medinipur under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004923436 Application Type-New Connection Reference ID-204414482 Quotation Date-01/10/2024 Quotation Due Date-01/10/2025 Contract Demand-8344W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02676/2024-2025 | C102415718521 | 05/10/2024 | 0 | WBSEDCL | 6.17 | 0 | 0
1577 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for EREKHALI and ADJOINING MOUJAS, Block Sutahata, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001325/2022-2023 | 2327/W/MMD | 29/12/2022 | 976 | M/S. SAJAHAN CHOWDHURY | 23.69 | 15.21 | 60
1578 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-II PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001472/2022-2023 | 210/W/MMD | 10/02/2023 | 180 | M/S S.G. ENTERPRISE | 27.26 | 0 | 0
1579 | Midnapore Mechanical | Haldia Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001951/2022-2023 | 101/HESD | 27/02/2023 | 184 | S.S.GHORAI | 0.9 | 0 | 53
1580 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SARBERIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004818488/QUOT/03 DT. 12-07-2024 Application NO- 2004818488 Application type-New connection Consumer Id- 204355506 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01888/2024-2025 | BP-2024-25-553 | 08/08/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
1581 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SARBERYA Water Supply Scheme T/W-I, (Ref. ID-204090827) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02894/2023-2024 | BP-2023-24-315 | 01/11/2023 | 0 | WBSEDCL | 3.24 | 0 | 0
1582 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SARBERIYA Water Supply Scheme T/W-I, (Ref. ID-204147803) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03135/2023-2024 | BP-2023-24-411 | 09/12/2023 | 0 | WBSEDCL | 3.32 | 0 | 0
1583 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for SARBERIYA Water Supply Scheme T/W-II, (Ref. ID-204147802) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03136/2023-2024 | BP-2023-24-410 | 09/12/2023 | 0 | WBSEDCL | 3.12 | 0 | 0
1584 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SARBERYA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001361/2022-2023 | 2372/W/MMD | 31/12/2022 | 974 | DIPALI CONSTRUCTION | 23.68 | 13.17 | 85
1585 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-III, Zone-II, (Ref. ID-204076090) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02203/2023-2024 | BP-2023-24-242 | 12/09/2023 | 0 | WBSEDCL | 9.52 | 0 | 0
1586 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for CHAITANYAPUR Water Supply Scheme T/W-I, Zone-II, (Ref. ID-204076083) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/02204/2023-2024 | BP-2023-24-241 | 12/09/2023 | 0 | WBSEDCL | 3.63 | 0 | 0
1587 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based CHAITANYAPUR Zone-II PWSS to Accommodate FHTC in Sutahata Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District Block ¿Sutahata, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001718/2022-2023 | 631/W/MMD | 20/03/2023 | 180 | M/S. SAJAHAN CHOWDHURY | 37.88 | 36.99 | 60
1588 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Harasankar W/S scheme H/W site Application No.-2004562746 Ref.-204191037 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03465/2023-2024 | BP-2023-24-588 | 02/02/2024 | 0 | WBSEDCL | 5.1 | 0 | 0
1589 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HARASHANKAR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001705/2022-2023 | 626/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 23.7 | 11.01 | 35
1590 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of PAHARPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743736/QUOT/03 DT. 20-05-2024 Application NO- 2004743736 Application type-New connection Consumer Id- 204312608 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01203/2024-2025 | BP-2024-25-320 | 24/06/2024 | 0 | WBSEDCL | 6.24 | 0 | 0
1591 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PAHARPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001400/2022-2023 | 2411/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 13.57 | 45
1592 | Midnapore Mechanical | Contai Sub-Division | Dakshin Kalamadan W/S scheme Application No.-2004527976 Ref.-204160990 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03265/2023-2024 | BP-2023-24-515 | 09/01/2024 | 0 | WBSEDCL | 13.12 | 0 | 0
1593 | Midnapore Mechanical | Contai Sub-Division | Quotation for Dakhin Kalamdan w/s scheme PH II under MMD PHE Dte in the district of Purba Medinipur. (Ref 204221089 App No. 2004606720) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04146/2023-2024 | BP-2023-24-757 | 01/03/2024 | 0 | WBSEDCL | 2.81 | 0 | 0
1594 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686929/QUOT/03 DT. 19-04-2024 Application NO- 2004686929 Application type-New connection Consumer Id- 204277584 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00707/2024-2025 | BP-2024-25-140 | 09/05/2024 | 0 | WBSEDCL | 2.87 | 0 | 0
1595 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004739171/QUOT/03 DT. 16-05-2024 Application NO- 2004739171 Application type-New connection Consumer Id- 204309281 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01135/2024-2025 | BP-2024-25-244 | 06/06/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
1596 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001584/2022-2023 | 467/W/MMD | 20/03/2023 | 180 | BHABANI PRASAD MANNA | 23.7 | 0 | 85
1597 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732464/QUOT/03/212 DT. 13-05-2024 Application NO- 2004732464 Application type-New connection Consumer Id- 204305461 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01132/2024-2025 | BP-2024-25-248 | 06/06/2024 | 0 | WBSEDCL | 3.9 | 0 | 0
1598 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004940316/QUOT/03/770 DT. 25-10-2024 Application NO- 2004940316 Application type-New connection Consumer Id- 204428743 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03021/2024-2025 | C112429700471 | 25/11/2024 | 0 | WBSEDCL | 6.29 | 0 | 0
1599 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAJENDRA CHAK and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001407/2022-2023 | 2418/W/MMD | 31/12/2022 | 180 | BOSE & CHATTERJEE INDUSTRIES | 22.73 | 0 | 0
1600 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657850/QUOT/03/1514 DT. 28-03-2024 Application NO- 2004657850 Application type-New connection Consumer Id- 204257679 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00259/2024-2025 | BP-2024-25-31 | 15/04/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
1601 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004889798/QUOT/03 DT. 12-09-2024 Application NO- 2004889798 Application type-New connection Consumer Id- 204393534 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02499/2024-2025 | C092445096068 | 30/09/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
1602 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TUPCHIBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001581/2022-2023 | 464/W/MMD | 20/03/2023 | 713 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 0 | 80
1603 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Mirikpur W/S scheme H/W site Tw-I Application.-2004547150 Ref.-204177955 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03299/2023-2024 | BP-2023-24-545 | 15/01/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
1604 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Mirikpur W/S scheme H/W site Tw-II Application.-2004547153 Ref.-204177965 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03300/2023-2024 | BP-2023-24-546 | 15/01/2024 | 0 | WBSEDCL | 4.21 | 0 | 0
1605 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRIKPUR AND ITS ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001750/2022-2023 | 644/W/MMD | 20/03/2023 | 749 | SOUMEN ELECTRIC | 27.17 | 23.4 | 80
1606 | Midnapore Mechanical | Haldia Electrical Sub-Division | Additional quatation for Tulia Anantapur Zone-I, TW-III , Tamluk Block Application ID.-100000099975 Reference ID.-860292305 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03782/2023-2024 | BP-2023-24-716 | 20/02/2024 | 0 | WBSEDCL | 0.23 | 0 | 0
1607 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Anantapur Zone-I PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001722/2022-2023 | 633/W/MMD | 20/03/2023 | 180 | DEBJYOTI BASU | 40.78 | 25.63 | 50
1608 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for ILASHPUR Water Supply Scheme T/W-I, (Ref. ID-204086226) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02895/2023-2024 | BP-2023-24-314 | 01/11/2023 | 0 | WBSEDCL | 3.01 | 0 | 0
1609 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ILASHPUR and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001357/2022-2023 | 2368/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 19.18 | 50
1610 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for MOYNA Water Supply Scheme T/W-I,Zone-II, (Ref. ID-204143547) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03133/2023-2024 | BP-2023-24-409 | 09/12/2023 | 0 | WBSEDCL | 5.37 | 0 | 0
1611 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Moyna W/S scheme T/W-III, Z-II Ref.-204143545 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03164/2023-2024 | BP-2023-24-436 | 18/12/2023 | 0 | WBSEDCL | 2.74 | 0 | 0
1612 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Moyna W/S scheme PH.-II, Zone-II Application No.-2004557342 Ref.-204187844 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03367/2023-2024 | BP-2023-24-577 | 18/01/2024 | 0 | WBSEDCL | 8.84 | 0 | 0
1613 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Moyna (Zone-II) PWSS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001715/2022-2023 | 630/W/MMD | 20/03/2023 | 530 | ALPHA ENTERPRISE | 37.86 | 35.46 | 70
1614 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672028/QUOT/03/45 DT. 05-04-2024 Application NO- 2004672028 Application type-New connection Consumer Id- 204266730 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00503/2024-2025 | BP-2024-25-94 | 24/04/2024 | 0 | WBSEDCL | 5.1 | 0 | 0
1615 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of UTTAR SILAMPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004672007/QUOT/03/46 DT. 05-04-2024 Application NO- 2004672007 Application type-New connection Consumer Id- 204266731 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00511/2024-2025 | BP-2024-25-93 | 24/04/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
1616 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SILAMPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001579/2022-2023 | 462/W/MMD | 20/03/2023 | 713 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 20.72 | 80
1617 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSI C.C.C. Ref. Memo No- 2004743815/QUOT/03 DT. 20-05-2024 Application NO- 2004743815 Application type-New connection Consumer Id- 204312604 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01205/2024-2025 | BP-2024-25-321 | 24/06/2024 | 0 | WBSEDCL | 3.12 | 0 | 0
1618 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of DHANKAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607668/QUOT/03 DT. 21-02-2024 Application NO- 2004607668 Application type-New connection Consumer Id- 204222374 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04387/2023-2024 | BP-2023-24-825 | 13/03/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
1619 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DHANKAR and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001634/2022-2023 | 515/W/MMD | 20/03/2023 | 804 | KARUNAMOY ENGINEERING | 22.75 | 10.38 | 51
1620 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Shuja Pwss T/W - II within Narayangarh Block Application No- 2004857400 , Ref No - 204376544 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02114/2024-2025 | BP-2024-25-626 | 02/09/2024 | 0 | WBSEDCL | 3.74 | 0 | 0
1621 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Shuja Pwss T/W - I within Narayangarh Block Application No- 2004857391 , Ref No - 204376543 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02115/2024-2025 | BP-2024-25-625 | 02/09/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
1622 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Tutranga PWSS T/W- II ,Narayangarh Block , Application no- 2004680728 , ref. Id - 204273486 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00699/2024-2025 | BP-2024-25-150 | 09/05/2024 | 0 | WBSEDCL | 2.84 | 0 | 0
1623 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Tutranga PWSS T/W- I ,Narayangarh Block , Application no- 2004680694 , ref. Id - 204273484 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00701/2024-2025 | BP-2024-25-149 | 09/05/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
1624 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DURMUT AND ADJOINING MOUJAS PWSS, Block Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001913/2022-2023 | 815/W/MMD | 24/03/2023 | 180 | TAPAN KUMAR DEY | 22.78 | 9.45 | 35
1625 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for Belun PWSS Tube Well-III WS Scheme (Ref. ID 203917727) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00397/2022-2023 | BP-2022-23-147 | 27/03/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
1626 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gokulnagar w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No 2004631965, Ref ID 204238451) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04745/2023-2024 | BP-2023-24-909 | 28/03/2024 | 0 | WBSEDCL | 7.06 | 0 | 0
1627 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gokulnagar w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No 2004635309, Ref ID 204240956) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04747/2023-2024 | BP-2023-24-910 | 28/03/2024 | 0 | WBSEDCL | 5.65 | 0 | 0
1628 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOKULNAGAR and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001365/2022-2023 | 2376/W/MMD | 31/12/2022 | 882 | AHALYA ENGINEERING WORKS | 25.25 | 20.03 | 50
1629 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional Quotation for Kharui Water Supply Scheme T/W-I Kolaghat CCC, Block-Sahaid Matangini Reference ID=860298136 Application ID=100000106136 Quotation Date=23.04.2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00694/2024-2025 | BP-2024-25-144 | 09/05/2024 | 0 | WBSEDCL | 0.62 | 0 | 0
1630 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Kharui W/S Scheme T/W-II Application No=2004614098 Reference ID=204225097 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04335/2023-2024 | BP-2023-24-802 | 11/03/2024 | 0 | WBSEDCL | 3.72 | 0 | 0
1631 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Kharui W/S Scheme H/W Site Application No=2004624417 Reference ID=204231697 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04336/2023-2024 | BP-2023-24-801 | 11/03/2024 | 0 | WBSEDCL | 4.66 | 0 | 0
1632 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARUI AND ADJOINING MOUZAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001703/2022-2023 | 625/W/MMD | 20/03/2023 | 721 | DEBJYOTI BASU | 23.7 | 15.07 | 90
1633 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004834992/QUOT/03 DT. 26-07-2024 Application NO- 2004834992 MEMO NO: AMR/PHE/284 DT.26/7/2024 Application type-New connection Consumer Id- 204365754 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01861/2024-2025 | BP-2024-25-537 | 07/08/2024 | 0 | WBSEDCL | 6.84 | 0 | 0
1634 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of TAPINDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835302/QUOT/03 DT. 26-07-2024 Application NO- 2004835302 MEMO NO: AMR/PHE/285 DT.26/7/2024 Application type-New connection Consumer Id- 204365759 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01862/2024-2025 | BP-2024-25-536 | 07/08/2024 | 0 | WBSEDCL | 1.98 | 0 | 0
1635 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TAPINDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001345/2022-2023 | 2356/W/MMD | 31/12/2022 | 974 | SOUMEN ELECTRIC | 21.61 | 15.29 | 61
1636 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674870/QUOT/03 DT. 09-04-2024 Application NO- 2004674870 Application type-New connection Consumer Id- 204269908 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00507/2024-2025 | BP-2024-25-84 | 24/04/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
1637 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of ALANGIRI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674883/QUOT/03 DT. 09-04-2024 Application NO- 2004674883 Application type-New connection Consumer Id- 204269736 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00509/2024-2025 | BP-2024-25-85 | 24/04/2024 | 0 | WBSEDCL | 6.04 | 0 | 0
1638 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for ALANGIRI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001406/2022-2023 | 2417/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.81 | 10.72 | 80
1639 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Barnan Water supply Scheme Tubewell No-II Application No=2004756795 Reference ID=204319871 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01163/2024-2025 | BP-2024-25-267 | 12/06/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
1640 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Barnan Water supply Scheme Tubewell No-I Application No=2004754441 Reference ID=204318380 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01164/2024-2025 | BP-2024-25-266 | 12/06/2024 | 0 | WBSEDCL | 8.5 | 0 | 0
1641 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARNAN AND ITS ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001699/2022-2023 | 624/W/MMD | 20/03/2023 | 896 | DEBJYOTI BASU | 23.7 | 15.07 | 50
1642 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gouranga chak w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709475, Ref ID 204293707) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01074/2024-2025 | BP-2024-25-189 | 24/05/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
1643 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation for new service connection at Gouranga chak w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004709436, Ref ID 204293706) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01075/2024-2025 | BP-2024-25-188 | 24/05/2024 | 0 | WBSEDCL | 7.81 | 0 | 0
1644 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of KATAI pwss (Ref Consumar ID-204251279),Application No-2004649169,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/04704/2023-2024 | BP-2023-24-916 | 28/03/2024 | 0 | WBSEDCL | 3.51 | 0 | 0
1645 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KATAI AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001757/2022-2023 | 646/W/MMD | 20/03/2023 | 874 | PINTU DEY | 21.56 | 13.58 | 90
1646 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF SANTRAPUR PWSS. REF CONSUMER ID-204283799, APPLICATION NO-2004695693, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01155/2024-2025 | BP-2024-25-274 | 12/06/2024 | 0 | WBSEDCL | 9.04 | 0 | 0
1647 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF SANTRAPUR PWSS. REF CONSUMER ID-204283797, APPLICATION NO-2004695677, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01156/2024-2025 | BP-2024-25-273 | 12/06/2024 | 0 | WBSEDCL | 9.04 | 0 | 0
1648 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for SANTRAPUR AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001446/2023-2024 | 3072/W/MMD | 29/11/2023 | 520 | SANKAR PRASAD DUTTA AND CO | 22.99 | 2.81 | 25
1649 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SYAMRAIBAR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001399/2022-2023 | 2410/W/MMD | 31/12/2022 | 180 | SUJOY RANJAN BHOWMICK | 21.62 | 7.35 | 35
1650 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF PUNYA PWSS. REF CONSUMER ID-204412273, APPLICATION NO-2004920306, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02971/2024-2025 | C102455560774 | 30/10/2024 | 0 | WBSEDCL | 8.8 | 0 | 0
1651 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674807/QUOT/03 DT. 09-04-2024 Application NO- 2004674807 Application type-New connection Consumer Id- 204269878 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00504/2024-2025 | BP-2024-25-87 | 24/04/2024 | 0 | WBSEDCL | 4.9 | 0 | 0
1652 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674743/QUOT/03 DT. 09-04-2024 Application NO- 2004674743 Application type-New connection Consumer Id- 204269918 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00505/2024-2025 | BP-2024-25-86 | 24/04/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1653 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JUMKI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001360/2022-2023 | 2371/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 17.21 | 85
1654 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SAR BERYA and ADJOINING MOUJAS, Block ¿ Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001659/2022-2023 | 544/W/MMD | 20/03/2023 | 529 | SOUMEN ELECTRIC | 21.56 | 21.13 | 100
1655 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAPASDA and ADJOINING MOUJAS, Block ¿ contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001677/2022-2023 | 556/W/MMD | 20/03/2023 | 180 | SHIVAM ENTERPRISE | 22.78 | 0 | 0
1656 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1657 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for GHATASHALA Water Supply Scheme T/W-I, (Ref. ID-204135822) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03002/2023-2024 | BP-2023-24-359 | 24/11/2023 | 0 | WBSEDCL | 4.07 | 0 | 0
1658 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at T/W-2 of Ghantashala ws scheme under MMD PHE DTE, Ref Application no-2004577503, Con ID-204203251 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03568/2023-2024 | BP-2023-24-651 | 09/02/2024 | 0 | WBSEDCL | 8.39 | 0 | 0
1659 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GHANTA SHALA AND IT'S ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001708/2022-2023 | 593/W/MMD | 20/03/2023 | 713 | ASHUTOSH DAS & CO. | 21.53 | 0 | 80
1660 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of CHISTIPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835430/QUOT/03 DT. 26-07-2024 Application NO- 2004835430 MEMO NO: AMR/PHE/280 DT.26/7/2024 Application type-New connection Consumer Id- 204365756 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01859/2024-2025 | BP-2024-25-540 | 07/08/2024 | 0 | WBSEDCL | 5.03 | 0 | 0
1661 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHISTIPUR AND ITS ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002041/2022-2023 | 949/W/MMD | 28/03/2023 | 887 | M/S B.M. ELECTRICAL | 22.78 | 0 | 62
1662 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KHANDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001920/2022-2023 | 839/W/MMD | 24/03/2023 | 180 | SHOVAN KUMAR DAS | 27.39 | 19.55 | 90
1663 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAGURANJALPAI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2004689899/QUOT/03 DT. 19-04-2024 Application NO- 2004689899 Application type-New connection Consumer Id- 204279763 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00664/2024-2025 | BP-2024-25-111 | 06/05/2024 | 0 | WBSEDCL | 3.63 | 0 | 0
1664 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAGURAN JALPAI AND IT'S ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001721/2022-2023 | 596/W/MMD | 20/03/2023 | 712 | T.S.CONSTRUCTION | 22.75 | 0 | 51
1665 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of Nonakourda W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760157/QUOT/03 DT. 04-06-2024 Application NO- 2004760157 Application type-New connection Consumer Id- 204322028 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01238/2024-2025 | BP-2024-25-288 | 18/06/2024 | 0 | WBSEDCL | 3.23 | 0 | 0
1666 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NONAKOURDA and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001669/2022-2023 | 552/W/MMD | 20/03/2023 | 720 | DEBJYOTI BASU | 21.62 | 0 | 55
1667 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of Chotanakdana water supply scheme.(Ref Id-204061140) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01766/2023-2024 | BP-2023-24-185 | 11/08/2023 | 0 | WBSEDCL | 3.42 | 0 | 0
1668 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of Chhotanakdana water supply scheme.(Ref Id-204061142). | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01767/2023-2024 | BP-2023-24-186 | 11/08/2023 | 0 | WBSEDCL | 5.41 | 0 | 0
1669 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAGECHA and ADJOINING MOUJAS, Block ¿ Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001664/2022-2023 | 547/W/MMD | 20/03/2023 | 896 | DEBJYOTI BASU | 21.58 | 6.57 | 40
1670 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Uttar Karkara PWSS T/W- I ,Narayangarh Block , Application no- 2004683009 , ref. Id - 204276095 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00698/2024-2025 | BP-2024-25-151 | 09/05/2024 | 0 | WBSEDCL | 7.19 | 0 | 0
1671 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RADHANAGAR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/14131, APPLICATION NO 2004759827, REFERENCE ID 204321839, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01168/2024-2025 | BP-2024-25-303 | 18/06/2024 | 0 | WBSEDCL | 5.19 | 0 | 0
1672 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RADHANAGAR WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14131, APPLICATION NO 2004759835, REFERENCE ID 204321895, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01169/2024-2025 | BP-2024-25-302 | 18/06/2024 | 0 | WBSEDCL | 6.7 | 0 | 0
1673 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001646/2022-2023 | 589/W/MMD | 20/03/2023 | 748 | K.S.P. ENTERPRISE | 25.24 | 0 | 80
1674 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0
1675 | Midnapore Mechanical | Kharagpur Sub-Division | Electric Quotation for KALAIKUNDA Water Supply Scheme T/W-I (Ref. ID-212248275) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01688/2023-2024 | BP-2023-24-174 | 04/08/2023 | 0 | WBSEDCL | 0.95 | 0 | 0
1676 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000013/2023-2024 | 1129/W/MMD | 12/04/2023 | 180 | P.K.ENGINEERING | 23.75 | 19.42 | 70
1677 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of KUBIR CHAK PWSS. REF CONSUMER ID-204266459, APPLICATION NO-2004670480, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00290/2024-2025 | BP-2024-25-46 | 18/04/2024 | 0 | WBSEDCL | 4.92 | 0 | 0
1678 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of KUBIR CHAK PWSS. REF CONSUMER ID-204240650, APPLICATION NO-2004634372, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04478/2023-2024 | BP-2023-24-848 | 14/03/2024 | 0 | WBSEDCL | 4.34 | 0 | 0
1679 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Making of T.W Foundation at PH-I of Kubirchak piped water supply scheme under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000839/2025-2026 | 1128/MMSD-I | 14/08/2025 | 7 | KAMAKSHYA ENTERPRISE | 0.7 | 0 | 0
1680 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUBIR CHAK PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001591/2022-2023 | 457/W/MMD | 20/03/2023 | 805 | KAMAKSHYA ENTERPRISE | 22.77 | 17.63 | 25
1681 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for kumarsanda pwss at pump house NO-I (Ref Id-204159129) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03183/2023-2024 | BP-2023-24-458 | 21/12/2023 | 0 | WBSEDCL | 5.97 | 0 | 0
1682 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for KUMARSANDA pwss at TW-II (Ref Id-204158498) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03242/2023-2024 | BP-2023-24-491 | 29/12/2023 | 0 | WBSEDCL | 3.17 | 0 | 0
1683 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUMARSANDA AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000080/2023-2024 | 1276/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.54 | 20.89 | 90
1684 | Midnapore Mechanical | Tamluk Sadar Sub-Division | New service connection at Uttar Sautanchak water supply scheme tube well no.-II Tamluk CCC Block-Tamluk Application No.-2004785533 Consumer ID.-204336033 Date.-21-06-2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01329/2024-2025 | BP-2024-25-356 | 01/07/2024 | 0 | WBSEDCL | 2.93 | 0 | 0
1685 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for Uttat Sautanchak Water Supply scheme H/W site. Quotation Bill Date.-20/03/2024 Tamluk Block Tamluk CCC Application No.-2004648593 Ref. ID-204250592 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04735/2023-2024 | BP-2023-24-919 | 28/03/2024 | 0 | WBSEDCL | 0.87 | 0 | 0
1686 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR SAUTANCHAK PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002038/2022-2023 | 946/W/MMD | 28/03/2023 | 719 | M/S. S.R. ENTERPRISE | 21.55 | 12.49 | 75
1687 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Purbaanukha W/S scheme H/W site Application No.-2004603682 Ref.-204218679 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/04060/2023-2024 | BP-2023-24-748 | 27/02/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
1688 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA NUKHA AND IT'S ADJOINING MOUJAS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001726/2022-2023 | 598/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 23.7 | 11.62 | 35
1689 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-I Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00025/2022-2023 | BP-2022-23-74 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1690 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00026/2022-2023 | BP-2022-23-75 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1691 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-I Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00027/2022-2023 | BP-2022-23-72 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1692 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00028/2022-2023 | BP-2022-23-73 | 14/12/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1693 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-I, Dewanchak water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000158/2022-2023 | 2003978666 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0
1694 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Chowka water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001239/2022-2023 | 2170/W/MMD | 12/12/2022 | 120 | BHABANI PRASAD MANNA | 5.93 | 5.36 | 0
1695 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Chowka water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001240/2022-2023 | 2171/W/MMD | 12/12/2022 | 120 | M/S BARMAN ROY TRADERS | 5.93 | 5.37 | 0
1696 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-I Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002779/2022-2023 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1697 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Chowka, chowka, Ghatal, T/W-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002780/2022-2023 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1698 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-I Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002781/2022-2023 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1699 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation BIRSINGHA CCC at Gholsai, Chowka, a, Ghatal, T/W-II Pin-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002782/2022-2023 |  | 17/11/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1700 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at JHAUGERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000044/2023-2024 | 1215/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 12.05 | 0 | 0
1701 | Midnapore Mechanical | Digha Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT ZONE-2, TW-2 OF KANPUR WS SCHEME UNDER MMD PHE DTE,BLOCK-RAMNAGAR-II, DIGHA CCC APPLCATION NO-2004746438, CON ID-204313992 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01139/2024-2025 | BP-2024-25-252 | 06/06/2024 | 0 | WBSEDCL | 6.19 | 0 | 0
1702 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
1703 | Midnapore Mechanical | Haldia Sub-Division | Quotation of new service connection at Amritberiya w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004714253, Ref ID 204295221) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01142/2024-2025 | BP-2024-25-243 | 06/06/2024 | 0 | WBSEDCL | 4.8 | 0 | 0
1704 | Midnapore Mechanical | Haldia Sub-Division | Quotation for new service connection at Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No. 2004760250, Ref ID 204322037) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01334/2024-2025 | BP-2024-25-362 | 01/07/2024 | 0 | WBSEDCL | 5.48 | 0 | 0
1705 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMRITBERYA and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000086/2023-2024 | 1270/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 21.2 | 60
1706 | Midnapore Mechanical | Haldia Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1707 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W NO III [ BAIDYAPUR ] , JJM WORKS, SCHEME CODE SM/15567, [ PARENT CODE - SM/04578 ] APPLICATION NO 2004648343, REFERENCE ID 204250593, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00308/2024-2025 | BP-2024-25-70 | 24/04/2024 | 0 | WBSEDCL | 10.58 | 0 | 0
1708 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15567, APPLICATION NO 2004697947, REFERENCE ID 204284912, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00640/2024-2025 |  | 29/04/2024 | 0 | WBSEDCL | 3.09 | 0 | 0
1709 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RANAPUR WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15567, APPLICATION NO 2004697947, REFERENCE ID 204284912, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00641/2024-2025 | BP-2024-25-117 | 06/05/2024 | 0 | WBSEDCL | 3.09 | 0 | 0
1710 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RANAPUR TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER DASPUR-I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/002020/2022-2023 | 918/W/MMD | 27/03/2023 | 180 | MAA TARA ENTERPRISE | 25.2 | 9.61 | 85
1711 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Pelageriya PWSS P/H- I , application no - 2004609021 , Ref id - 204222609 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04190/2023-2024 | BP-2023-24-773 | 06/03/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
1712 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Pelageriya PWSS P/H- II , application no - 2004608985 , Ref id - 204222610 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04192/2023-2024 | BP-2023-24-774 | 06/03/2024 | 0 | WBSEDCL | 3.33 | 0 | 0
1713 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PELAGERYA & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001985/2022-2023 | 836/W/MMD | 24/03/2023 | 180 | HARA PROSAD DAS | 23.73 | 15.56 | 20
1714 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SUPAPURSURI WATER SUPPLY SCHEME, T W NO 2 , [ AUGMENTATION ] , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004809558, REFERENCE ID 204352004, DASPUR CCC, WBSEDCL. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01632/2024-2025 | C072443865657 | 29/07/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
1715 | Midnapore Mechanical | Ghatal Subdivision | SUPAPURSURI WATER SUPPLY SCHEME, T W - III , JJM WORKS, SCHEME CODE SM/15905, APPLICATION NO 2004588382, REFERENCE ID 204209925, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04200/2023-2024 | BP-2023-24-787 | 06/03/2024 | 0 | WBSEDCL | 3.08 | 0 | 0
1716 | Midnapore Mechanical | Digha Sub-Division | Kanpur W/S scheme TW no.-II, Z-V Ref.-204156068 Application ID-2004521673 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03154/2023-2024 | BP-2023-24-445 | 19/12/2023 | 0 | WBSEDCL | 2.57 | 0 | 0
1717 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-I,ZONE-V of KANPUR WS SCHEME under MMD,PHE Dte, Block-Ramnagar-II, DIGHA CCC, Application no-2004644488, CON ID-204246837 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04741/2023-2024 | BP-2023-24-913 | 28/03/2024 | 0 | WBSEDCL | 4.81 | 0 | 0
1718 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Ramnagar - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000052/2023-2024 | 1216/W/MMD | 25/04/2023 | 889 | BHABANI PRASAD MANNA | 83.38 | 0 | 34
1719 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RAMCHANDRAPUR WATER SUPPLY SCHEME, T W - II , JJM WORKS, SCHEME CODE SM/16632, APPLICATION NO 2004696180, REFERENCE ID 204284327, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00638/2024-2025 | BP-2024-25-116 | 06/05/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
1720 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR RAMCHANDRAPUR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/16632, APPLICATION NO 2004696177, REFERENCE ID 204284325, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00643/2024-2025 | BP-2024-25-115 | 06/05/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
1721 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ramchandrapur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001628/2022-2023 | 537/W/MMD | 20/03/2023 | 1108 | BALAJI CONSTRUCTION | 22.79 | 0 | 80
1722 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Kapasharia PWSS in the District of Purba Medinipur under JJM programme. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002149/2022-2023 | 1083/W/MMD | 30/03/2023 | 180 | S.S.GHORAI | 11.86 | 0 | 0
1723 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PIARDANGA TO ACCOMMODATE FHTC UNDER CHANDRAKONA - II BLOCK IN PASCHIM MEDINIPUR DISTRICT UNDER MEDINIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000007/2023-2024 | 1123/W/MMD | 12/04/2023 | 811 | R.S. ENTERPRISE | 25.24 | 11.81 | 60
1724 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Rejuvenation of Electro-Mechanical components of Dhamsai PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002122/2022-2023 | 1060/W/MMD | 29/03/2023 | 180 | PADMA ENGINEERING CO. | 11.37 | 8.01 | 40
1725 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Chakmakrampur & its adj. mouzas, Block - Kharagpur-II, Dist.- Paschim Medinipur.under JJM Program under MMD. PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002204/2022-2023 | 539/W/MMD | 20/03/2023 | 900 | M/S. S.R. ENTERPRISE | 22.75 | 10.57 | 65
1726 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2023-2024 | 1694/W/MMD | 04/08/2023 | 759 | A G ENTERPRISE | 78.38 | 0 | 20
1727 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER CHANDRAKONA - I and II BLOCK IN PASCHIM MIDNAPORE DISTRICTunder JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000367/2023-2024 | 1693/W/MMD | 04/08/2023 | 180 | AMUSAR IMPEX PVT. LTD | 49.92 | 0 | 80
1728 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR TIORBERYA WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/17575, APPLICATION NO 2004723249, REFERENCE ID 204300057, SONAKHALI CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00879/2024-2025 | BP-2024-25-182 | 20/05/2024 | 0 | WBSEDCL | 5.68 | 0 | 0
1729 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR TIORBERYA WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/17575, APPLICATION NO 2004826966, REFERENCE ID 204360838, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02043/2024-2025 | C082441589956 | 29/08/2024 | 0 | WBSEDCL | 6.75 | 0 | 0
1730 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PWSS UNDER DASPUR - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTEunder JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2023-2024 | 1694/W/MMD | 04/08/2023 | 759 | A G ENTERPRISE | 78.38 | 0 | 20
1731 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | AUGMENTATION OF DISINFECTION ARRANGEMENT FOR EASING OF OPERATION OF CHLORINATION AT PIRAKATA AND OTHER 35 PWSS IN PASCHIM MEDINIPUR DISTRICT UNDER JJM PROGRAM UNDER MIDNAPORE MECHANICAL DIVISION P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002148/2022-2023 | 1080/W/MMD | 30/03/2023 | 720 | DEBJYOTI BASU | 70.43 | 30.32 | 35
1732 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for THE PROPOSED GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JADABPUR TO ACCOMMODATE FHTC UNDER CHANDRAKONA - I BLOCK IN PASCHIM MIDNAPORE DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000210/2023-2024 | 1493/W/MMD | 22/06/2023 | 694 | SUJOY RANJAN BHOWMICK | 37.89 | 25.35 | 100
1733 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for TW-II of Dubrajpur pwss (Ref Consumar ID-204362492),Application No-2004829564,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspur-II. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01806/2024-2025 | BP-2024-25-527 | 06/08/2024 | 0 | WBSEDCL | 4.42 | 0 | 0
1734 | Midnapore Mechanical | Ghatal Subdivision | Electrict quotation bill for TW-I of Dubrajpur pwss (Ref Consumar ID-204373188),Application No-2004849368,Application Type-New Connection,Name of ccc-Daspur ccc, block-Daspue-II | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02012/2024-2025 | C082430177901 | 20/08/2024 | 0 | WBSEDCL | 15.54 | 0 | 0
1735 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Dubrajpur and its adjoining mouzas, Block - Daspur-II, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000037/2023-2024 | 1202/W/MMD | 25/04/2023 | 1075 | TAPAN KUMAR SARKAR | 23.77 | 0 | 45
1736 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
1737 | Midnapore Mechanical | Kharagpur Sub-Division | Electrict quotation bill for TW-II of Islampur pwss (Ref Consumar ID-204444970),Application No-2004963217,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | BILL/03038/2024-2025 | C112429786723 | 25/11/2024 | 0 | WBSEDCL | 6.59 | 0 | 0
1738 | Midnapore Mechanical | Kharagpur Sub-Division | Electrict quotation bill for TW-I of Islampur pwss (Ref Consumar ID-204444968),Application No-2004963184,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra | AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | BILL/03039/2024-2025 | C112429789179 | 25/11/2024 | 0 | WBSEDCL | 6.34 | 0 | 0
1739 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for ISLAMPUR AND IT'S ADJOINING MOUJAS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/001896/2022-2023 | 795/W/MMD | 24/03/2023 | 799 | CHAKRABORTY MINING & ENGINEERING | 21.58 | 13.24 | 38
1740 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Talbandi pwss (Ref Consumar ID-204314575),Application No-2004747841,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01121/2024-2025 | BP-2024-25-234 | 04/06/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
1741 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for TALBANDI AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002044/2022-2023 | 952/W/MMD | 28/03/2023 | 180 | MASSK ENGINEERING WORKS | 21.58 | 0 | 0
1742 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF KEDAR PWSS. REF CONSUMER ID-204393521, APPLICATION NO-2004889559, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02460/2024-2025 | C102401978777 | 03/10/2024 | 0 | WBSEDCL | 6.65 | 0 | 0
1743 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF KEDAR PWSS. REF CONSUMER ID-204391651, APPLICATION NO-2004886654, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02463/2024-2025 | C102401977236 | 03/10/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
1744 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ADDITIONAL QUOTATION FOR SHIFTING OF 11 KV LINE & DTR AT TW NO-I OF KEDAR PWSS.(APPLICATION NO-2004886654), REFERENCE ID-860319778, APPLICATION ID-100000125268, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC- KHAKURDA CCC, NAME OF BLOCK-DANTAN-II. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03673/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 2.05 | 0 | 0
1745 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of FULESWAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767027/QUOT/03 DT. 07-06-2024 Application NO- 2004767027 Application type-New connection Consumer Id- 204325420 | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01222/2024-2025 | BP-2024-25-301 | 18/06/2024 | 0 | WBSEDCL | 12.7 | 0 | 0
1746 | Midnapore Mechanical | Contai Sub-Division | Quotation bill for Fuleswar W/S scheme T/W. No.-I, P.S- Contai, Block.-Contai-II Application No.-2004626938 Ref ID.-204233452 Date.-01/03/2024 Quotation Date.-01-03-2024 Mukundapur CCC | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04337/2023-2024 | BP-2023-24-808 | 11/03/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
1747 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FULESHWAR and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001622/2022-2023 | 508/W/MMD | 20/03/2023 | 180 | M/S DILIP MITRA | 22.77 | 9.98 | 60
1748 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790353/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/211 DT. 24-06-2024 Application NO- 2004790353 Application type-New connection Consumer Id- 204339004 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01367/2024-2025 | BP-2024-25-375 | 08/07/2024 | 0 | WBSEDCL | 5.65 | 0 | 0
1749 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790382/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/212 DT. 24-06-2024 Application NO- 2004790382 Application type-New connection Consumer Id- 204339027 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01368/2024-2025 | BP-2024-25-374 | 08/07/2024 | 0 | WBSEDCL | 2.17 | 0 | 0
1750 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHOULA BHERI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001660/2022-2023 | 529/W/MMD | 20/03/2023 | 889 | BHABANI PRASAD MANNA | 25.26 | 0 | 50
1751 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE- I, T W NO II, [ GOPALI ] JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004741941, REFERENCE ID 204310971, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01460/2024-2025 | BP-2024-25-423 | 15/07/2024 | 0 | WBSEDCL | 4.31 | 0 | 0
1752 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE- I ,T W NO I [ RANGAMATIA ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 20047411952, REFERENCE ID 204310973, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01467/2024-2025 | BP-2024-25-424 | 15/07/2024 | 0 | WBSEDCL | 5.89 | 0 | 0
1753 | Midnapore Mechanical | Kharagpur Sub-Division | THE QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ GHOLGHARIA ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004726863, REFERENCE ID 204303571, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01737/2024-2025 | C072445370570 | 30/07/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1754 | Midnapore Mechanical | Kharagpur Sub-Division | THE QUOTATION MONEY FOR GOPALI WATER SUPPLY SCHEME, ZONE-II, T W NO I, [ GHOLGHARIA FREE PRIMARY SCHOOL ] , JJM WORKS, SCHEME CODE SM/19048, APPLICATION NO 2004726901, REFERENCE ID 204303571, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01738/2024-2025 | C072445369106 | 30/07/2024 | 0 | WBSEDCL | 2.98 | 0 | 0
1755 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gopali (Zone-I and II) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/001438/2023-2024 | 3092/W/MMD | 29/11/2023 | 540 | M.S.ENTERPRISE | 47.53 | 0 | 85
1756 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAHANABAD and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000089/2023-2024 | 1267/W/MMD | 04/05/2023 | 697 | MENAKA ENTERPRISE | 25.14 | 0 | 0
1757 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000383/2023-2024 | 1722/W/MMD | 09/08/2023 | 180 | DEY ENTERPRISE | 25.26 | 0 | 0
1758 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Benai (Zone-I & II) & its adjoining mouzas.under JJM Program under MMD PHE Dte. (Part-II) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000393/2023-2024 | 1732/W/MMD | 09/08/2023 | 180 | M/S. JIT ENTERPRISE | 22.78 | 0 | 0
1759 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 181 | S.K.ENTERPRISE | 4.11 | 0 | 0
1760 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
1761 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I of KHIRISHMUL PWSS. REF CONSUMER ID-204269078, APPLICATION NO-2004675326, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00311/2024-2025 | BP-2024-25-74 | 24/04/2024 | 0 | WBSEDCL | 6.61 | 0 | 0
1762 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-II of KHIRISHMUL PWSS. REF CONSUMER ID-204269069, APPLICATION NO-2004675308 APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00316/2024-2025 | BP-2024-25-75 | 24/04/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1763 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHIRISH MUL AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000341/2023-2024 | 1682/W/MMD | 04/08/2023 | 678 | PADMA ENGINEERING CO. | 23 | 16.01 | 30
1764 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different ongoing piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.- w.e.f.-01-07-2025 to 28-02-2026 (Vehicle No. WB33C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000513/2025-2026 | 842/MMSD-I | 11/06/2025 | 243 | M/S BIKASH DE | 3.66 | 0 | 0
1765 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.14 | 50
1766 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR DASPUR AUGMENTATION, DIHIBALIHARPUR WATER SUPPLY SCHEME, T W NO IV , JJM WORKS, SCHEME CODE SM/18506, APPLICATION NO 2004809572, REFERENCE ID 204352799, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01636/2024-2025 | BP-2024-25-488 | 30/07/2024 | 0 | WBSEDCL | 6.23 | 0 | 0
1767 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR DASPUR WATER SUPPLY SCHEME, T W NO 3, [ AUGMENTATION ] , JJM WORKS, BLOCK- DASPUR-I, SCHEME CODE SM/18506, APPLICATION NO 2004849405, REFERENCE ID 204373191, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02042/2024-2025 | C082441593739 | 29/08/2024 | 0 | WBSEDCL | 5.2 | 0 | 0
1768 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Daspur to Accommodate FHTC, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000363/2023-2024 | 1691/W/MMD | 04/08/2023 | 702 | P.K.ENGINEERING | 37.87 | 26.42 | 100
1769 | Midnapore Mechanical | Kharagpur Sub-Division | Electric Quotation for TW-II of Khirinda W/S Scheme (Consumer ID 203971015) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00077/2023-2024 | BP-2023-24-33 | 04/05/2023 | 0 | WBSEDCL | 2.69 | 0 | 0
1770 | Midnapore Mechanical | Kharagpur Sub-Division | Electric quotation for Tw no-I of Khirinda w/s scheme ( Consumer ID-203972928) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00078/2023-2024 | BP-2023-24-34 | 04/05/2023 | 0 | WBSEDCL | 2.63 | 0 | 0
1771 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Khirinda Piped Water Supply Scheme. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001640/2022-2023 | 572/W/MMD | 20/03/2023 | 180 | DEY ENTERPRISE | 25.26 | 0 | 0
1772 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
1773 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | wbsedcl Quotation bill of Debra water supply scheme at pump house no-III | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00584/2023-2024 |  | 23/06/2023 | 0 | WBSEDCL | 2.87 | 0 | 0
1774 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of ground based piped water Supply scheme for DEBRA to accommodate FHTC under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001423/2022-2023 | 94/W/MMD | 17/01/2023 | 180 | M/S. S.R. ENTERPRISE | 25.23 | 24.78 | 80
1775 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of ground based piped water Supply scheme for DEBRA to accommodate FHTC under JJM Program under MMD PHE Dte. (Part-II) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001961/2022-2023 | 873/W/MMD | 27/03/2023 | 180 | MASSK ENGINEERING WORKS | 8.35 | 0 | 0
1776 | Midnapore Mechanical | Contai Sub-Division | Electric quotation Bill of T/W-III of Anurai water suplly scheme under MMD PHE Dte. under Marishda CCC | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000228/2022-2023 | 2004006184/QUOT/03 | 30/07/2022 | 365 | WBSEDCL | 0.7 | 0.7 | 0
1777 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well at Pump House-I under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001012/2022-2023 | 1861/W/MMD | 22/09/2022 | 120 | SUBHAM ENTERPRISE | 11.67 | 8.29 | 20
1778 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional 3rd Tube well under Anurai water supply scheme under Midnapore Mechanical Division, PHE Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001272/2022-2023 | 2201/W/MMD | 14/12/2022 | 837 | A G ENTERPRISE | 12.25 | 11.41 | 100
1779 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Mirjapur, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001195/2021-2022 | 154/W/MMD | 31/01/2022 | 120 | DIPALI CONSTRUCTION | 6.49 | 3.87 | 0
1780 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Mirjapur water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001292/2021-2022 | 2518/W/MMD | 30/11/2021 | 4 | OSMAN SEKH | 4.47 | 3.84 | 60
1781 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation for service connection charges of WBSEDCL at Lakshmichak,Andulia T/W-I | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001522/2021-2022 | 2003855188/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0.13 | 0
1782 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation Sabang CCC at Mirjapur Mini piped Water supply scheme under MMD PHE Dte | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002771/2022-2023 | BP-2022-23-59 | 23/11/2022 | 0 | WBSEDCL | 0.1 | 0 | 0
1783 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charge of WBSEDCL at Haripura, Bonai | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001034/2021-2022 | 2003774906/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
1784 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Haripura water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001133/2021-2022 | 2522/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 100
1785 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Haripura, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001178/2021-2022 | 124/W/MMD | 24/01/2022 | 120 | M/S B.M. ELECTRICAL | 6.54 | 6.41 | 0
1786 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Quotation for service connection charges of WBSEDCL at Lakshmichak,Andulia T/W-II | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001521/2021-2022 | 2003855176/Quot/03 | 10/03/2022 | 365 | WBSEDCL | 0.13 | 0.13 | 0
1787 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charge of WBSEDCL at Fatechak, Sabang | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001033/2021-2022 | 2003774921/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
1788 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Fate Chak water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001132/2021-2022 | 2520/W/MMD | 30/11/2021 | 4 | P.K.ENGINEERING | 4.47 | 0 | 100
1789 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Fate Chak, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001177/2021-2022 | 123/W/MMD | 24/01/2022 | 120 | SOUMEN ELECTRIC | 6.55 | 6.55 | 0
1790 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | LOAD ENHANCEMENT OF KHUNKHUNYA MINI WATER SUPPLY SCHEME , SCHEME CODE SM/09684, COSUMER ID 20350372, CHANDKURI CCC [ ENTERED MB NO 3580, PAGE 13-14 ] | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00857/2023-2024 | BP-2023-24-128 | 13/07/2023 | 0 | WBSEDCL | 0.37 | 0 | 0
1791 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Service connection charge of WBSEDCL at Khunkhunia, Sabang | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001032/2021-2022 | 2003774931/Quot/03 | 16/12/2021 | 365 | WBSEDCL | 0.13 | 0.13 | 0
1792 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Khunkhunya water supply scheme of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001139/2021-2022 | 2534/W/MMD | 30/11/2021 | 4 | MENAKA ENTERPRISE | 4.47 | 0 | 100
1793 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well at Khunkhunya, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001179/2021-2022 | 125/W/MMD | 24/01/2022 | 120 | M.S.ENTERPRISE | 6.52 | 6.42 | 0
1794 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-III Of TALDA W/S Scheme under MMD, PHE, Dte. Block- CONTAI-III, WBSEDCL SUPPLY OFFICE: MARISHDA C.C.C. Ref. Memo No- 2004815942/QUOT/03 DT. 10-07-2024 Application NO-2004815942 Application type-New connection Consumer Id- 204353932 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01697/2024-2025 | C072443922958 | 29/07/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
1795 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Talda, Block Contai III, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000169/2023-2024 | 1412/W/MMD | 02/06/2023 | 718 | SHIVAM ENTERPRISE | 12.63 | 0 | 90
1796 | Midnapore Mechanical | Contai Sub-Division | Quotation for new service connection at Kamarda w/s scheme PH III Additional TW in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004671499, Ref ID 204266596) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00288/2024-2025 | BP-2024-25-48 | 18/04/2024 | 0 | WBSEDCL | 3.07 | 0 | 0
1797 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well no - III at Kamarda Water supply scheme, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001187/2023-2024 | 2610/W/MMD | 19/09/2023 | 712 | M/S SREEJIT ENTERPRISE | 14.77 | 10.79 | 50
1798 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-I at Uttar Eral, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001199/2021-2022 | 158/W/MMD | 31/01/2022 | 120 | TAPAN KUMAR SARKAR | 6.47 | 6 | 0
1799 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and installation of pumping machinery and other electromechanical equipment at newly sunk Tube well-II at Uttar Eral, Block- Sabang under ground water based mini piped water supply scheme Dist. Paschim Medinipur under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001200/2021-2022 | 159/W/MMD | 31/01/2022 | 120 | RAJIB COMPANY | 6.46 | 5.99 | 0
1800 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uttar Eral water supply scheme, Tube Well no. 1 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte.. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001205/2021-2022 | 73/W/MMD | 17/01/2022 | 5 | SUJOY RANJAN BHOWMICK | 4.48 | 0 | 100
1801 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Sinking of (150 mmX 100mmX 150 mtr) RBTW by Rotary Method at Uttar Eral water supply scheme, Tube Well no. 2 of Sabang Block of Paschim Midnapur Dist under MMD. P.H.E. Dte.. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001206/2021-2022 | 74/W/MMD | 17/01/2022 | 5 | SUJOY RANJAN BHOWMICK | 4.48 | 0 | 100
1802 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different Works for Providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000054/2023-2024 | 1220/W/MMD | 25/04/2023 | 360 | S.G.TECHNICAL SERVICE | 11.96 | 0 | 100
1803 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotiaton for Erashal Water Supply Scheme TW-IV (Ref. ID-203949710) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00109/2023-2024 | BP-2023-24-36 | 04/05/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
1804 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotiaton for Erashal Water Supply Scheme TW-III (Ref. ID-203949718) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00110/2023-2024 | BP-2023-24-37 | 04/05/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
1805 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for Providing Functional Household TAP Connection (FHTC) by Augmentation of Erasole Water Supply Scheme. in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000061/2023-2024 | 1226/W/MMD | 25/04/2023 | 180 | SOUMEN ELECTRIC | 26.95 | 26.58 | 100
1806 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for Denkua Water Supply SchemeT/W-I (Ref. ID-224005066 ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01617/2023-2024 | BP-2023-24-135 | 20/07/2023 | 0 | WBSEDCL | 0.11 | 0 | 0
1807 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Dhenkua Water supply scheme, Sutahata block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000389/2024-2025 | 2005/W/MMD | 30/08/2024 | 180 | P.K.ENGINEERING | 9.29 | 0 | 80
1808 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Replacement Tube well No I under Dhenkua water supply scheme under Midnapore Mechanical Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001139/2022-2023 | 2120/W/MMD | 28/11/2022 | 120 | DIPALI CONSTRUCTION | 11.1 | 10.95 | 100
1809 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Sutahata and Tamluk in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000053/2023-2024 | 1218/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 40.43 | 12.76 | 60
1810 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme Block - Sutahata under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/002024/2022-2023 | 862/W/MMD | 27/03/2023 | 180 | M/S B ENTERPRISE | 13.41 | 0 | 70
1811 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of MADHABPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671978/QUOT/03/48 DT. 05-04-2024 Application NO- 2004671978 Application type-New connection Consumer Id- 204266733 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00537/2024-2025 | BP-2024-25-90 | 24/04/2024 | 0 | WBSEDCL | 1 | 0 | 0
1812 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for MADHABPUR Water Supply Scheme T/W-I, Zone-II (Ref. ID-204047955) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01869/2023-2024 | W/23-24/222 | 01/09/2023 | 0 | WBSEDCL | 4.9 | 0 | 0
1813 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for Madhabpur Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001927/2022-2023 | 846/W/MMD | 24/03/2023 | 180 | AHALYA ENGINEERING WORKS | 37.88 | 28.29 | 60
1814 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-II, Dewanchak water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000159/2022-2023 | 2003978672 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0
1815 | Midnapore Mechanical | Ghatal Subdivision | Service Connection charges of WBSEDCL at Dewanchak, Chowka, Dewanchak P/H-I | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000168/2022-2023 | 2003978666 | 28/06/2022 | 365 | WBSEDCL | 0.11 | 0 | 0
1816 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-III under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000220/2022-2023 | 1649/W/MMD | 12/08/2022 | 120 | KAMAKSHYA ENTERPRISE | 5.6 | 5.58 | 98
1817 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-IV under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist Paschim Medinipur | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000221/2022-2023 | 1650/W/MMD | 12/08/2022 | 120 | SHOVAN KUMAR DAS | 5.75 | 5.74 | 100
1818 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for Birsingha CCC, Dewanchak water supply scheme Zone-II, Pin no-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001072/2022-2023 | 2003788821../Quot/03 | 06/08/2022 | 365 | WBSEDCL | 0.11 | 0 | 0
1819 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-I under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001241/2022-2023 | 2172/W/MMD | 12/12/2022 | 880 | P.K.ENGINEERING | 5.91 | 4.18 | 100
1820 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at Zone-II under Dewanchak water supply scheme of SAGY programme under Midnapore Mechanical Division, PHE Dte. Dist. Paschim Medinipur. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001242/2022-2023 | 2173/W/MMD | 12/12/2022 | 120 | PADMA ENGINEERING CO. | 5.93 | 5.36 | 0
1821 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-II, Dewanchak water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001773/2022-2023 | BP-2022-23-46 | 23/08/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1822 | Midnapore Mechanical | Ghatal Subdivision | Quotation Bill of PH-I, Dewanchak water supply scheme under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001783/2022-2023 | BP-2022-23-23 | 08/08/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1823 | Midnapore Mechanical | Ghatal Subdivision | Electric quotation for Birsingha CCC, Zone-II, Dewanchak water supply scheme under MMD PHE Dte, Pin no.-14/10/2022 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002565/2022-2023 | 2004068300 | 17/10/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1824 | Midnapore Mechanical | Ghatal Subdivision | electric quotation for Birsingha CCC, Zone-I Dewanchak water supply scheme undre MMD PHE Dte. Pin No.-721232 | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/002566/2022-2023 | 2004068257 | 17/10/2022 | 0 | WBSEDCL | 0.11 | 0 | 0
1825 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for Chargeable Head, KHEJURI, Water Supply Scheme T/W-III, Zone-II (Ref. ID-204049542) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01673/2023-2024 |  | 01/08/2023 | 0 | WBSEDCL | 1.41 | 0 | 0
1826 | Midnapore Mechanical | Digha Sub-Division | Purushottampur W/S scheme PH-I Application no.-2004522734 ref.-204156888 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03197/2023-2024 | BP-2023-24-472 | 27/12/2023 | 0 | WBSEDCL | 2.75 | 0 | 0
1827 | Midnapore Mechanical | Digha Sub-Division | Purushottampur W/S scheme PH-II Application no.-2004522748 ref.-204156889 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03198/2023-2024 | BP-2023-24-471 | 27/12/2023 | 0 | WBSEDCL | 2.78 | 0 | 0
1828 | Midnapore Mechanical | Digha Sub-Division | Additional Quotation Bill for New Service connection at T/W NO-I & II Of PURBA PURUSHOTTAMPUR W/S Scheme under MMD, PHE, Dte. Block- RAMNAGAR-II, PICHABANI C.C.C. Ref. Memo No- PBN/SM/958 DT. 28-02-2024 Application NO- T/W NO-I: 2004522734 Con. Id- 204156888 ( T/W NO-I) Application NO- T/W NO-II: 2004522748 Con. Id- 204156889 ( T/W NO-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/04267/2023-2024 | BP-2023-24-795 | 06/03/2024 | 0 | WBSEDCL | 3.26 | 0 | 0
1829 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBO PURUSHOTTAMPUR and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001647/2022-2023 | 541/W/MMD | 20/03/2023 | 530 | SOUMEN ELECTRIC | 21.56 | 19.72 | 80
1830 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KAJIBASAN W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767101/QUOT/03 DT. 07-06-2024 Application NO- 2004767101 Application type-New connection Consumer Id- 204325527 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01221/2024-2025 | BP-2024-25-300 | 18/06/2024 | 0 | WBSEDCL | 16.47 | 0 | 0
1831 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAJI BASAN and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001624/2022-2023 | 509/W/MMD | 20/03/2023 | 180 | SANJIB SAHA | 22.79 | 0 | 0
1832 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for AMARSIKASBA Water Supply Scheme T/W-I, Zone -II, (Ref. ID-204098661) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02897/2023-2024 | BP-2023-24-311 | 01/11/2023 | 0 | WBSEDCL | 3.28 | 0 | 0
1833 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-II Of AMARSI KASBA W/S Scheme under MMD, PHE, Dte. Block- Potashpur-I, AMARSI C.C.C. Ref. Memo No- 2004607907/QUOT/03 DT. 21-02-2024 Application NO- 2004607907 Application type-New connection Reference Id- 204223198 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04384/2023-2024 | BP-2023-24-822 | 13/03/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
1834 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Amarshi Kasba Zone-II, Block Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001971/2022-2023 | 814/W/MMD | 24/03/2023 | 180 | S.K.ENTERPRISE | 22.8 | 19.87 | 10
1835 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Ad Tw no -III of Dantan PWSS (Ref Consumer ID-204122249) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02906/2023-2024 | BP-2023-24-325 | 03/11/2023 | 0 | WBSEDCL | 3.33 | 0 | 0
1836 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-IV of Dantan PWSS (UTTAR RAY BAR).(Ref Consumer ID-204205780), APPLICATION NO-2004580499, APPLICATION TYPE-NEW CONNECTION, BLOCK-DANTAN-I, NAME OF CCC-DANTAN CCC. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03570/2023-2024 | BP-2023-24-603 | 07/02/2024 | 0 | WBSEDCL | 9.63 | 0 | 0
1837 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-V of Dantan PWSS .(Krishnapur), Ref Consumer ID-204205815, APPLICATION NO-2004580504, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-DANTAN CCC, BLOCK-DANTAN-I | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03571/2023-2024 | BP-2023-24-604 | 07/02/2024 | 0 | WBSEDCL | 3.78 | 0 | 0
1838 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Dantan to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur.under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000171/2023-2024 | 1414/W/MMD | 02/06/2023 | 180 | DEY ENTERPRISE | 54.73 | 0 | 0
1839 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Bargodagodar PWSS to Accommodate FHTC in Nandakumar Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001469/2022-2023 | 207/W/MMD | 10/02/2023 | 180 | SOUMEN ELECTRIC | 40.4 | 37.91 | 100
1840 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03933/2023-2024 | BP-2023-24-724 | 23/02/2024 | 0 | WBSEDCL | 10.34 | 0 | 0
1841 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03934/2023-2024 | BP-2023-24-725 | 23/02/2024 | 0 | WBSEDCL | 11.01 | 0 | 0
1842 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-I, (Ref. ID-204134070) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03001/2023-2024 | BP-2023-24-358 | 24/11/2023 | 0 | WBSEDCL | 4.02 | 0 | 0
1843 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for BAGMARI (RAMNAGAR-I) Water Supply Scheme T/W-II, (Ref. ID-204143154) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03055/2023-2024 | BP-2023-24-376 | 02/12/2023 | 0 | WBSEDCL | 4.91 | 0 | 0
1844 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for KAKRA Water Supply Scheme T/W-I, (Ref. ID-204090826) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02889/2023-2024 | BP-2023-24-318 | 01/11/2023 | 0 | WBSEDCL | 3.34 | 0 | 0
1845 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for KAKRA Water Supply Scheme T/W-II, (Ref. ID-204090825) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02890/2023-2024 | BP-2023-24-317 | 01/11/2023 | 0 | WBSEDCL | 2.85 | 0 | 0
1846 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAKRA and ADJOINING MOUJAS, Block Bhagawanpur I, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001324/2022-2023 | 2326/W/MMD | 29/12/2022 | 180 | EASTERN INDIA SALES & SERVICE | 23.69 | 23.22 | 95
1847 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Santipur W/S scheme H/W Site Application No.-2004562690 Ref.-204191008 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03464/2023-2024 | BP-2023-24-589 | 02/02/2024 | 0 | WBSEDCL | 10.61 | 0 | 0
1848 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
1849 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTIPUR and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001340/2022-2023 | 2345/W/MMD | 29/12/2022 | 895 | GOENKA ENTERPRISE | 25.26 | 0 | 30
1850 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
1851 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for ANANTAPUR Water Supply Scheme Z-II, T/W-III (Ref. ID-204048948) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01775/2023-2024 | BP-2023-24-188 | 11/08/2023 | 0 | WBSEDCL | 9.99 | 0 | 0
1852 | Midnapore Mechanical | Haldia Electrical Sub-Division | Electric Quotation for ANANTAPUR, Water Supply Scheme ,Zone-I, T/W-III, (Ref. ID-204060666) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01816/2023-2024 | BP-2023-24-189 | 14/08/2023 | 0 | WBSEDCL | 6.18 | 0 | 0
1853 | Midnapore Mechanical | Haldia Electrical Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Anantapur Zone-II PWSS to Accommodate FHTC in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001740/2022-2023 | 641/W/MMD | 20/03/2023 | 180 | M/S. JIT ENTERPRISE | 13.59 | 9.63 | 35
1854 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MUSTAFAPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004649225/QUOT/03 DT. 20-03-2024 Application NO- 2004649225 Application type-New connection Consumer Id- 204250590 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00008/2024-2025 | BP-2024-25-2 | 04/04/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
1855 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of MUSTAPHAPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886313/QUOT/03/583 DT. 06-09-2024 Application NO- 2004886313 Application type-New connection Consumer Id- 204391660 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02452/2024-2025 | C092443181607 | 27/09/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
1856 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUSTAPHAPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001620/2022-2023 | 507/W/MMD | 20/03/2023 | 742 | M/S DILIP MITRA | 22.77 | 0 | 85
1857 | Midnapore Mechanical | Kharagpur Sub-Division | New Service connection charge at Kuliara under Choupenia W/S scheme, ID-2004294643 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00139/2023-2024 | BP-2023-24-69 | 07/06/2023 | 0 | WBSEDCL | 3.05 | 0 | 0
1858 | Midnapore Mechanical | Kharagpur Sub-Division | New service connection charges for the pump house at Maheshpur under Choupenia W/S Scheme, ID-2004294624 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00140/2023-2024 | BP-2023-24-68 | 07/06/2023 | 0 | WBSEDCL | 3.42 | 0 | 0
1859 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE.under JJM Program under MMD PHE Dte. (Phase-II) | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000249/2023-2024 | 1571/W/MMD | 13/07/2023 | 180 | M/S EMMESS | 11.81 | 11.01 | 90
1860 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAUPANYA TO ACCOMMODATE FHTC UNDER JAL SAPNO MISSION UNDER KHARAGPUR- II BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MEDNIPUR DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001596/2022-2023 | 479/W/MMD | 20/03/2023 | 180 | PURUSHOTTAM ENTERPRISE | 10.98 | 10.66 | 100
1861 | Midnapore Mechanical | Contai Sub-Division | Nayaput W/S scheme PH-I Application no.-2004522692 ref.-204156883 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03199/2023-2024 | BP-2023-24-473 | 27/12/2023 | 0 | WBSEDCL | 4.81 | 0 | 0
1862 | Midnapore Mechanical | Contai Sub-Division | Nayaput W/S scheme PH-II Application no.-2004522675 ref.-204156884 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03201/2023-2024 | BP-2023-24-474 | 27/12/2023 | 0 | WBSEDCL | 4.44 | 0 | 0
1863 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAYAPUT and ADJOINING MOUJAS, Block - Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001651/2022-2023 | 523/W/MMD | 20/03/2023 | 180 | S.G.TECHNICAL SERVICE | 23.69 | 16.85 | 55
1864 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK NARSINGHA AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001704/2022-2023 | 613/W/MMD | 20/03/2023 | 1095 | BHABANI PRASAD MANNA | 21.58 | 0 | 85
1865 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for Chaksulpan water supply scheme pump house NO-I(Consumar Id-204134472) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/02962/2023-2024 | BP-2023-24-362 | 24/11/2023 | 0 | WBSEDCL | 4.7 | 0 | 0
1866 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAK SULPAN AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001948/2022-2023 | 828/W/MMD | 24/03/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.65 | 10.53 | 50
1867 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Kurpai W/S scheme H/W site. Application.-2004547144 Ref.-204177947 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03301/2023-2024 | BP-2023-24-547 | 15/01/2024 | 0 | WBSEDCL | 8.64 | 0 | 0
1868 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Kurpai T/W-II Tamluk CCC Application No=2005004861 Reference ID=204470853 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/03678/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 5.23 | 0 | 0
1869 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KURPAI AND ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000085/2023-2024 | 1271/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 22.69 | 0 | 35
1870 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004707237/QUOT/03 DT. 29-04-2024 Application NO- 2004707237 MEMO NO: AMR/PHE/90 DT.29/04/2024 Application type-New connection Consumer Id- 204291521 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00855/2024-2025 | BP-2024-25-163 | 15/05/2024 | 0 | WBSEDCL | 5.32 | 0 | 0
1871 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of MAKRAMPUR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004944304/QUOT/03 DT. 25-10-2024 Application NO- 2004944304 Application type-New connection Consumer Id- 204428639 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03005/2024-2025 | C112423561463 | 19/11/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
1872 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAKRAMPUR and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001404/2022-2023 | 2415/W/MMD | 31/12/2022 | 882 | RITESH ENTERPRISE | 22.79 | 0 | 50
1873 | Midnapore Mechanical | Digha Sub-Division | Depal W/S scheme TW no.-I Ref.-204156070 Application ID-2004521731 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03155/2023-2024 | BP-2023-24-439 | 19/12/2023 | 0 | WBSEDCL | 5.4 | 0 | 0
1874 | Midnapore Mechanical | Digha Sub-Division | DEPAL w/s SCHEME PH -II APPLICATION nO.-2004566534 REF.-204194525 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03535/2023-2024 | BP-2023-24-612 | 07/02/2024 | 0 | WBSEDCL | 24.63 | 0 | 0
1875 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DEPAL and ADJOINING MOUJAS, Block ¿ Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001359/2022-2023 | 2370/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 85
1876 | Midnapore Mechanical | Contai Sub-Division | Chingurdania W/S scheme PH No.-I Application No.-2004565714 Ref.-204193544 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03477/2023-2024 | BP-2023-24-594 | 02/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
1877 | Midnapore Mechanical | Contai Sub-Division | Quotation for New service connection at Chingurdaniya w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. (App No.- 2004620601 , Ref ID 204229471) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04330/2023-2024 | BP-2023-24-812 | 11/03/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
1878 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAISPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001346/2022-2023 | 2357/W/MMD | 31/12/2022 | 180 | WEST BENGAL ENGINEERING CO. | 22.78 | 0 | 0
1879 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of UTTAR DAUDPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004852092/QUOT/03/562 DT. 07-08-2024 Application NO- 2004852092 Application type-New connection Consumer Id- 204373375 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02123/2024-2025 | C092403062421 | 04/09/2024 | 0 | WBSEDCL | 6.07 | 0 | 0
1880 | Midnapore Mechanical | Digha Sub-Division | Uttar Daudpur W/S scheme PH-I Application no.-2004523051 ref.-204157004 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03189/2023-2024 | BP-2023-24-485 | 27/12/2023 | 0 | WBSEDCL | 3.69 | 0 | 0
1881 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for UTTAR DAIDPUR and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001358/2022-2023 | 2369/W/MMD | 31/12/2022 | 180 | BHABANI PRASAD MANNA | 23.7 | 11.06 | 85
1882 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SANTRA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004746350/QUOT/03 DT. 22-05-2024 Application NO- 2004746350 Application type-New connection Consumer Id- 204313989 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01136/2024-2025 | BP-2024-25-256 | 06/06/2024 | 0 | WBSEDCL | 6.93 | 0 | 0
1883 | Midnapore Mechanical | Digha Sub-Division | QUOTATION FOR NEW SERVICE CONNECTION AT TW-1 OF SANTRA WS SCHEME UNDER MMD PHE DTE , BLOCK-RAMNAGAR-1, DIGHA CCC APPLICATION NO-2004746369 CON ID-204313990 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01141/2024-2025 | BP-2024-25-255 | 06/06/2024 | 0 | WBSEDCL | 6.93 | 0 | 0
1884 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SANTRA and ADJOINING MOUJAS, Block ¿ Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001580/2022-2023 | 463/W/MMD | 20/03/2023 | 712 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 12.6 | 90
1885 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for UTTAR KHASDA Water Supply SchemeT/W-III (Ref. ID-204049279) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01636/2023-2024 | BP-2023-24-136 | 27/07/2023 | 0 | WBSEDCL | 2.59 | 0 | 0
1886 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Uttar Khasda Water Supply Scheme of Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. within with in the Purba Medinipur District. under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001736/2022-2023 | 638/W/MMD | 20/03/2023 | 772 | SOUMEN ELECTRIC | 13.57 | 9.66 | 100
1887 | Midnapore Mechanical | Haldia Sub-Division | Quotation bill for new service connection at TW-I of Mohanpur w/s scheme,Block-Sutahata,under MMD,PHE Dte. C.C.C-Chaitanyapur Application no.-2004695195 Application type-new connection Quotation Date-24/04/2024 Quotation Due Date-24/04/2025 Contract Demand-6800W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00647/2024-2025 | BP-2024-25-112 | 06/05/2024 | 0 | WBSEDCL | 16.83 | 0 | 0
1888 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MOHANPUR and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001678/2022-2023 | 567/W/MMD | 20/03/2023 | 925 | M/S B.M. ELECTRICAL | 22.81 | 16.19 | 70
1889 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at TW-I of Mamudpur W/S scheme under MMD PHE Dte. Block-Tamluk Tamluk CCC Application No.-2004916353 Consumer ID.-204409669 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/02974/2024-2025 | C112402770847 | 05/11/2024 | 0 | WBSEDCL | 3.64 | 0 | 0
1890 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAMUDPUR AND IT'S ADJOINING MOUJAS PWSS, Block ¿ Tamluk, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001697/2022-2023 | 623/W/MMD | 20/03/2023 | 1198 | BHABANI PRASAD MANNA | 23.7 | 0 | 40
1891 | Midnapore Mechanical | Contai Sub-Division | Ajaya W/S scheme T/W -I Application No.-2004565721 Ref.-204193605 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03475/2023-2024 | BP-2023-24-593 | 02/02/2024 | 0 | WBSEDCL | 3.19 | 0 | 0
1892 | Midnapore Mechanical | Contai Sub-Division | Ajaya W/S scheme T/W -II Application No.-2004565730 Ref.-204193622 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03476/2023-2024 | BP-2023-24-592 | 02/02/2024 | 0 | WBSEDCL | 8.24 | 0 | 0
1893 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AJAYA and ADJOINING MOUJAS, Block ¿ Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/002290/2022-2023 | 2384/W/MMD | 31/12/2022 | 180 | P.K.ENGINEERING | 27.7 | 12.66 | 45
1894 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHARAT KOTBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: Patashpur ccc Ref. Memo No- 2004760152/QUOT/03 DT. 04-06-2024 Application NO- 2004760152 Application type-New connection Consumer Id- 204322027 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01276/2024-2025 | BP-2024-25-319 | 24/06/2024 | 0 | WBSEDCL | 3.85 | 0 | 0
1895 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KHARATKOTBAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASHPUR C.C.C. Ref. Memo No-2004811790/QUOT/03 DT. 11-07-2024 Application NO- 2004811790 Application type-New connection Consumer Id- 204351927 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01977/2024-2025 | BP-2024-25-565 | 14/08/2024 | 0 | WBSEDCL | 5.76 | 0 | 0
1896 | Midnapore Mechanical | Contai Sub-Division | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 366 | S.S.GHORAI | 2.12 | 0 | 50
1897 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHARAT KATBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001370/2022-2023 | 2381/W/MMD | 31/12/2022 | 857 | ECO ENTERPRISE | 25.26 | 15.54 | 85
1898 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
1899 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Agar Water Supply Scheme T/W-II Matangini CCC,Block=Sahid Matangini Application No=2004676891 Reference ID=204270379 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00668/2024-2025 | BP-2024-25-168 | 15/05/2024 | 0 | WBSEDCL | 0.29 | 0 | 0
1900 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation Bill for Agar Water Supply Scheme H/W Site Matangini CCC,Block=Sahid Matangini Application No=2004699675 Reference ID=204286135 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00669/2024-2025 | BP-2024-25-169 | 15/05/2024 | 0 | WBSEDCL | 5.63 | 0 | 0
1901 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AGAR & ADJOINING MOUJAS PWSS, Block ¿ Shahid Matangini, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000167/2023-2024 | 1409/W/MMD | 02/06/2023 | 180 | M/S B.M. ELECTRICAL | 21.62 | 0 | 0
1902 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of KHAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004671992/QUOT/03/40 DT. 08-04-2024 Application NO- 2004671992 Application type-New connection Consumer Id- 204266827 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00501/2024-2025 | BP-2024-25-95 | 24/04/2024 | 0 | WBSEDCL | 5.83 | 0 | 0
1903 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of KHAR W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, WBSEDCL SUPPLY OFFICE: PATSHPUR C.C.C. Ref. Memo No-2004886304/QUOT/03/581 DT. 06-09-2024 Application NO- 2004886304 Application type-New connection Consumer Id- 204391661 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02449/2024-2025 | C092443182184 | 27/09/2024 | 0 | WBSEDCL | 3.56 | 0 | 0
1904 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001674/2022-2023 | 569/W/MMD | 20/03/2023 | 864 | DEY ENTERPRISE | 27.17 | 0 | 52
1905 | Midnapore Mechanical | Haldia Sub-Division | Quotation Bill for Baramritberia Water Supply scheme Tube well no.-I Mahishadal CCC Block-Mahishadal Application No.-2004603891 Ref ID.-204219157 Quatation Bill Date.-15/03/2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/04575/2023-2024 | BP-2023-24-890 | 22/03/2024 | 0 | WBSEDCL | 14.61 | 0 | 0
1906 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARAMRIT BERE and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001632/2022-2023 | 514/W/MMD | 20/03/2023 | 180 | GLACIER ENGINEERING CO. | 22.79 | 20.88 | 100
1907 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAMUNDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657865/QUOT/03 DT. 28-03-2024 Application NO- 2004657865 Application type-New connection Consumer Id- 204257681 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00258/2024-2025 | BP-2024-25-29 | 15/04/2024 | 0 | WBSEDCL | 4.23 | 0 | 0
1908 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BAMUNDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004889786/QUOT/03 DT. 12-09-2024 Application NO- 2004889786 Application type-New connection Consumer Id- 204393533 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02501/2024-2025 | C092445097329 | 30/09/2024 | 0 | WBSEDCL | 4.5 | 0 | 0
1909 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARMUNDA and ADJOINING MOUJAS, Block Potashpur II, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002030/2022-2023 | 938/W/MMD | 28/03/2023 | 180 | MENAKA ENTERPRISE | 22.77 | 17.51 | 65
1910 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-II of Kanakpur pwss (Ref Consumar ID-204314650),Application No-2004748062,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01120/2024-2025 | BP-2024-25-279 | 12/06/2024 | 0 | WBSEDCL | 3.21 | 0 | 0
1911 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Kanakpur pwss (Ref Consumar ID-204314629),Application No-2004748015,Application Type-New Connection,Name of ccc-Lowada ccc, block-Debra | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01122/2024-2025 | BP-2024-25-278 | 12/06/2024 | 0 | WBSEDCL | 4.62 | 0 | 0
1912 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KANKRA SIBRAM AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002045/2022-2023 | 953/W/MMD | 28/03/2023 | 180 | MASSK ENGINEERING WORKS | 21.58 | 0 | 0
1913 | Midnapore Mechanical | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-III, ZONE-II Of PANIPARUL W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004773750/QUOT/03/483 DT. 18-06-2024 Application NO- 2004773750 Application type-New connection Consumer Id- 204332477 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01327/2024-2025 | BP-2024-25-360 | 01/07/2024 | 0 | WBSEDCL | 3.41 | 0 | 0
1914 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for PANIPARUL Water Supply Scheme T/W-II, Zone -II, (Ref. ID-204087320) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02896/2023-2024 | BP-2023-24-312 | 01/11/2023 | 0 | WBSEDCL | 2.76 | 0 | 0
1915 | Midnapore Mechanical | Digha Sub-Division | Electric Quotation for PANIPARUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204128964) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/03056/2023-2024 | BP-2023-24-389 | 02/12/2023 | 0 | WBSEDCL | 4.9 | 0 | 0
1916 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Paniparul Zone-II, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001934/2022-2023 | 853/W/MMD | 24/03/2023 | 799 | M/S S.G. ENTERPRISE | 26.86 | 24.84 | 80
1917 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Additional Tube well at PANIPARUL ZONE - II Water supply scheme, Egra -II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002702/2023-2024 | 1051/W/MMD | 13/03/2024 | 385 | GLACIER ENGINEERING CO. | 14 | 9.07 | 54
1918 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-II, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004749319/QUOT/03 DT. 28-05-2024 Application NO- 2004749319 Application type-New connection Consumer Id- 204315788 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01145/2024-2025 | BP-2024-25-259 | 06/06/2024 | 0 | WBSEDCL | 2.83 | 0 | 0
1919 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MUKUNDAPUR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001672/2022-2023 | 554/W/MMD | 20/03/2023 | 712 | DEBJYOTI BASU | 22.8 | 0 | 55
1920 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF TURKA KASHBA PWSS. REF CONSUMER ID-204391650, APPLICATION NO-2004886647, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02455/2024-2025 | C102401986837 | 03/10/2024 | 0 | WBSEDCL | 3.46 | 0 | 0
1921 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF TURKA KASHBA PWSS. REF CONSUMER ID-204391652, APPLICATION NO-2004886649, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02456/2024-2025 | C102401985532 | 03/10/2024 | 0 | WBSEDCL | 7.1 | 0 | 0
1922 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric qutation bill for khanamohan water supply scheme at pump house NO-I | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02921/2023-2024 | BP-2023-24-341 | 10/11/2023 | 0 | WBSEDCL | 3.06 | 0 | 0
1923 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for khanamohan water supply scheme at pump house N0-II | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02922/2023-2024 | BP-2023-24-340 | 10/11/2023 | 0 | WBSEDCL | 3.61 | 0 | 0
1924 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHANAMOHAN AND IT'S ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001898/2022-2023 | 797/W/MMD | 24/03/2023 | 860 | BHABANI PRASAD MANNA | 21.62 | 20.07 | 80
1925 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF RELA PWSS. REF CONSUMER ID-204391648, APPLICATION NO-2004886689, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02458/2024-2025 | C102401976404 | 03/10/2024 | 0 | WBSEDCL | 5.33 | 0 | 0
1926 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF RELA PWSS. REF CONSUMER ID-204391646, APPLICATION NO-2004886695, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02464/2024-2025 | C102401976054 | 03/10/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
1927 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SHIFTING OF HT LINE ALONG WITH DTR OF GOPMAHAL URF MONAHARPUR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/14651, APPLICATION NO 100000109467, REFERENCE ID 860301697, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01333/2024-2025 | BP-2024-25-357 | 01/07/2024 | 0 | WBSEDCL | 2.02 | 0 | 0
1928 | Midnapore Mechanical | Ghatal Subdivision | GOPMAHAL WATER SUPPLY SCHEME, PH - I, BLOCK - GHATAL , SCHEME - SM/14651, REF. ID - 204135807, GHATAL CCC, | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03009/2023-2024 | BP-2023-24-391 | 02/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0
1929 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001577/2022-2023 | 461/W/MMD | 20/03/2023 | 180 | M/S B.M. ELECTRICAL | 22.89 | 14.77 | 40
1930 | Midnapore Mechanical | Ghatal Subdivision | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 40
1931 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
1932 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at at different PWSS of Block Egra - II in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000073/2023-2024 | 1242/W/MMD | 28/04/2023 | 764 | BHABANI PRASAD MANNA | 84.29 | 0 | 70
1933 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Chakmaoa water supply scheme T/W - II | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03562/2023-2024 | BP-2023-24-618 | 07/02/2024 | 0 | WBSEDCL | 1.99 | 0 | 0
1934 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Chakmawa PWSS , T/W - I , Application no - 2004582518 , Ref ID - 204206276 , Madpur CCC | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03746/2023-2024 | BP-2023-24-705 | 16/02/2024 | 0 | WBSEDCL | 3.78 | 0 | 0
1935 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKMAOA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001720/2022-2023 | 618/W/MMD | 20/03/2023 | 180 | SUJOY RANJAN BHOWMICK | 21.58 | 12.51 | 50
1936 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR CHAKSADI WATER SUPPLY SCHEME, T W NO 1 JJM WORKS, SCHEME CODE SM/14997, APPLICATION NO 2004759795, REFERENCE ID 204321902, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01172/2024-2025 | BP-2024-25-297 | 18/06/2024 | 0 | WBSEDCL | 4.43 | 0 | 0
1937 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR CHAKSADI WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14997, APPLICATION NO 2004759781, REFERENCE ID 204321817, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01173/2024-2025 | BP-2024-25-298 | 18/06/2024 | 0 | WBSEDCL | 5.1 | 0 | 0
1938 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001921/2022-2023 | 840/W/MMD | 24/03/2023 | 180 | RITESH ENTERPRISE | 27.39 | 19.55 | 40
1939 | Midnapore Mechanical | Ghatal Subdivision | ADDITIONAL QUOTATION MONEY FOR HEMANTAPUR WATER SUPPLY SCHEME, T W NO I, ADDITIONAL QUOTATION, JJM WORKS, SCHEME CODE SM/15011, APPLICATION NO 100000114253, REFERENCE ID 860308903, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01853/2024-2025 | BP-2024-25-545 | 07/08/2024 | 0 | WBSEDCL | 0.73 | 0 | 0
1940 | Midnapore Mechanical | Ghatal Subdivision | CERTIFIED THAT IT IS THE QUOTATION MONEY FOR HEMANTAPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/15011, APPLICATION NO 2004627986, REFERENCE ID 204234632, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04400/2023-2024 | BP-2023-24-842 | 14/03/2024 | 0 | WBSEDCL | 3.35 | 0 | 0
1941 | Midnapore Mechanical | Ghatal Subdivision | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 60 | SUBHASIS ROY | 0.29 | 0 | 40
1942 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001993/2022-2023 | 804/W/MMD | 24/03/2023 | 180 | SHREE BISHNU CONSTRUCTION | 10.79 | 10 | 80
1943 | Midnapore Mechanical | Ghatal Subdivision | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 306 | SUBHASIS ROY | 6.3 | 0 | 0
1944 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw No-I of Pundra PWSS (ref Consumer ID-204121973) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03123/2023-2024 | BP-2023-24-412 | 09/12/2023 | 0 | WBSEDCL | 5.37 | 0 | 0
1945 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Tw no-II of PUNDRA PWSS.(Ref Consumer ID-204183610) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03344/2023-2024 | BP-2023-24-564 | 16/01/2024 | 0 | WBSEDCL | 4.78 | 0 | 0
1946 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for PUNDRA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001384/2022-2023 | 2395/W/MMD | 31/12/2022 | 819 | DAS ENTERPRISE | 22.83 | 14.05 | 30
1947 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of ITABERIA W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601903/QUOT/03 DT. 15-02-2024 Application NO- 2004601903 Application type-New connection Reference Id- 204217836 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00599/2024-2025 |  | 24/04/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
1948 | Midnapore Mechanical | Contai Sub-Division | Quotation Bill for Shifting of 33 KV FEEDER HT LINE AT SABITRAPUR( KANPUR W/S SCHEME ZONE-V, T/W NO-I) , RAMNAGRA -II BLOCK , DIGHA CCC, DIST.-PURBA MEDINIPUR. Ref. MEMO No- CD/1971 Dt. 22.02.2024 Application NO- 100000101137 Dt. 22/02/2024 Reference Id- 860292957 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04262/2023-2024 | BP-2023-24-813 | 13/03/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
1949 | Midnapore Mechanical | Contai Sub-Division | Electric Quotation for ITABERIA Water Supply Scheme, T/W-I, (Ref. ID-204217836) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/04345/2023-2024 | BP-2023-24-813 | 13/03/2024 | 0 | WBSEDCL | 0.49 | 0 | 0
1950 | Midnapore Mechanical | Contai Sub-Division | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 227 | SOUMEN ELECTRIC | 2.2 | 0 | 70
1951 | Midnapore Mechanical | Contai Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1952 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-II of Uttar Gopalpur ws scheme under MMD,PHE Dte. Ref Application no-2004579836, CON ID-204204432, PICABONI CCC,Block-Ramnagar II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03653/2023-2024 | BP-2023-24-677 | 15/02/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
1953 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at TW-1 of Uttar Gopalpur ws scheme under MMD, PHE Dte. Ref. Application no-2004579816, Ref Con ID-204204428. PICHABONI CCC, Block-Ramnagar-II | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03656/2023-2024 | BP-2023-24-677 | 15/02/2024 | 0 | WBSEDCL | 4.27 | 0 | 0
1954 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I of KULBONI PWSS. REF CONSUMER ID-204226372, APPLICATION NO-2004615833, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04333/2023-2024 | BP-2023-24-806 | 11/03/2024 | 0 | WBSEDCL | 6.53 | 0 | 0
1955 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II of KULBONI PWSS. REF CONSUMER ID-204226373, APPLICATION NO-2004615869, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/04334/2023-2024 | BP-2023-24-805 | 11/03/2024 | 0 | WBSEDCL | 6.65 | 0 | 0
1956 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KULBANI AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001424/2023-2024 | 3076/W/MMD | 29/11/2023 | 180 | M/S EMMESS | 34.18 | 22.03 | 20
1957 | Midnapore Mechanical | Contai Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MASHAGON and ADJOINING MOUJAS, Block ¿ contai III, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001684/2022-2023 | 559/W/MMD | 20/03/2023 | 180 | DIPALI CONSTRUCTION | 22.6 | 0 | 0
1958 | Midnapore Mechanical | RWS Midnapur Sub-Division | Electric quotation for Nayagram PWSS Tube Well- III in connection Barua CCC ( | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00066/2022-2023 |  | 21/02/2023 | 0 | WBSEDCL | 0.19 | 0 | 0
1959 | Midnapore Mechanical | RWS Midnapur Sub-Division | Electric quotation for Nayagram PWSS Tube Well- IV in connection Barua CCC (2004189731) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00067/2022-2023 |  | 21/02/2023 | 0 | WBSEDCL | 0.19 | 0 | 0
1960 | Midnapore Mechanical | RWS Midnapur Sub-Division | Electric quotation for Nayagram PWSS Tube Well- III in connection Barua CCC | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00411/2022-2023 | BP-2022-23-159 | 31/03/2023 | 0 | WBSEDCL | 0.19 | 0 | 0
1961 | Midnapore Mechanical | RWS Midnapur Sub-Division | Electric quotation for Nayagram PWSS Tube Well- IV in connection Barua CCC (2004189731) | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00412/2022-2023 | BP-2022-23-160 | 31/03/2023 | 0 | WBSEDCL | 0.19 | 0 | 0
1962 | Midnapore Mechanical | RWS Midnapur Sub-Division | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW IV of Nayagram water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000111/2023-2024 | 424/MMSD-I | 20/04/2023 | 15 | SUJOY RANJAN BHOWMICK | 4.37 | 4.37 | 60
1963 | Midnapore Mechanical | RWS Midnapur Sub-Division | Providing and installation of submersible pumping machineries and other electromechanical equipment at newly sunk tube well at Additional TW III of Nayagram water supply scheme under Midnapore Mechanical Division, P.H.E. DTE. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000112/2023-2024 | 423/MMSD-I | 20/04/2023 | 15 | DEBJYOTI BASU | 4.37 | 4.37 | 100
1964 | Midnapore Mechanical | RWS Midnapur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Nayagram and its adj. mouzas, Block - Midnapore Sadar, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001892/2022-2023 | 791/W/MMD | 24/03/2023 | 180 | SHOVAN KUMAR DAS | 22.79 | 15.81 | 68
1965 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR RISA WATER SUPPLY SCHEME, T W NO 2, JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004636219, REFERENCE ID 204240939, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | BILL/01465/2024-2025 | BP-2024-25-427 | 16/07/2024 | 0 | WBSEDCL | 4.64 | 0 | 0
1966 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR RISA WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/15591, APPLICATION NO 2004582784, REFERENCE ID 204211198, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | BILL/03724/2023-2024 | BP-2023-24-696 | 16/02/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
1967 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Risa & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | ORD/002012/2022-2023 | 910/W/MMD | 27/03/2023 | 894 | JAL PRAVAHIKA PVT. LTD. | 25.24 | 15.78 | 95
1968 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Bara Mohanpur PWSS T/W- I ,Narayangarh Block , Application no- 2004641957 , ref. Id - 404244873 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00700/2024-2025 | BP-2024-25-153 | 09/05/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
1969 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Baramohanpur PWSS T/W - II under Narayangarh Block , Application no - 2004852851 , Ref No - 204373751. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/02113/2024-2025 | C092402013162 | 04/09/2024 | 0 | WBSEDCL | 4.02 | 0 | 0
1970 | Midnapore Mechanical | Kharagpur Sub-Division | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 15 | SOUMEN ELECTRIC | 6.62 | 0 | 50
1971 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR MAHARJPUR WATER SUPPLY SCHEME, T W NO I, JJM WORKS, SCHEME CODE SM/15325, APPLICATION NO 2004857637, REFERENCE ID 204376542, BIRSINGHA CCC, WBSEDCL | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/03034/2024-2025 | C112429741036 | 25/11/2024 | 0 | WBSEDCL | 3.31 | 0 | 0
1972 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Maharajpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/001611/2022-2023 | 493/W/MMD | 20/03/2023 | 180 | S.P. ENTERPRISE | 22.95 | 0 | 0
1973 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AILAN and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000088/2023-2024 | 1268/W/MMD | 04/05/2023 | 180 | MENAKA ENTERPRISE | 27.04 | 0 | 0
1974 | Midnapore Mechanical | Digha Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under HESD, PHE Dte., Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/002725/2023-2024 | 1070/W/MMD | 14/03/2024 | 180 | THE GODFATHER TRADING COMPANY | 10.42 | 0 | 100
1975 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at PANCHBERYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000045/2023-2024 | 1217/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 11.87 | 0 | 40
1976 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Additional quatation bill for application no-2004172244 for Tw No-II of Tanuya PWSS. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/03227/2023-2024 | BP-2023-24-464 | 27/12/2023 | 0 | WBSEDCL | 3.2 | 0 | 0
1977 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Tanuya Piped Water Supply Scheme.under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000128/2023-2024 | 1358/W/MMD | 24/05/2023 | 180 | PS & ASSOCIATES | 27.3 | 18.41 | 60
1978 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at DAHA DAYA PIPED WATER SUPPLY SCHEME in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000043/2023-2024 | 1214/W/MMD | 25/04/2023 | 889 | THE GODFATHER TRADING COMPANY | 12.14 | 5.32 | 65
1979 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MURAKATA AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002291/2022-2023 | 499/W/MMD | 20/03/2023 | 804 | PADMA ENGINEERING CO. | 32.97 | 22.68 | 25
1980 | Midnapore Mechanical | Haldia Electrical Sub-Division | Quotation Bill for new service connection at TW-III of Barsundra w/s scheme,under MMD,PHE,Dte.,Purba Medinipur Block-Haldia, C.C.C.-Brajalalchak Application no.-2004651015 Application Type-New connection Quotation Date-22/03/2024 Quotation Due Date-24/03/2025 Contract Demand-10209 W | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00018/2024-2025 | BP-2024-25-17 | 08/04/2024 | 0 | WBSEDCL | 4.22 | 0 | 0
1981 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Electro-Mechanical components of Chatra PWSS in the District of Paschim Medinipur under JJM programme. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002120/2022-2023 | 1058/W/MMD | 29/03/2023 | 180 | S.S.GHORAI | 5.07 | 5.07 | 95
1982 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at LAKSHIPUR Water supply scheme, Chandrakona -I block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000752/2023-2024 | 2282/W/MMD | 29/08/2023 | 306 | SUJOY RANJAN BHOWMICK | 30.18 | 25.07 | 95
1983 | Midnapore Mechanical | Haldia Electrical Sub-Division | Rejuvenation of Electro-Mechanical components of Bajkul, Zone-I PWSS in the District of Purba Medinipur under JJM programme under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001841/2022-2023 | 758/W/MMD | 23/03/2023 | 1269 | SOUMEN ELECTRIC | 11.85 | 5.47 | 40
1984 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Electric Quotation for DAKSHIN MECHOGRAM Water Supply Scheme T/W- III, (Ref. ID-204066734) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01829/2023-2024 | BP-2023-24-205 | 24/08/2023 | 0 | WBSEDCL | 3.77 | 0 | 0
1985 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Nandigram I & II and Panskura - I in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000051/2023-2024 | 1209/W/MMD | 25/04/2023 | 180 | BHABANI PRASAD MANNA | 53.9 | 12.51 | 35
1986 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Continuation order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 484/HESD | 28/05/2024 | 91 | S.S.GHORAI | 0.45 | 0 | 100
1987 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Tamluk Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001532/2023-2024 | 949/HESD | 30/11/2023 | 91 | S.S.GHORAI | 0.45 | 0.05 | 100
1988 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Additional quotation for Kulbari w/s scheme PH III in the district of Purba Medinipur under MMD PHE Dte. (App ID 100000118086, Con ID 860311696) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/02429/2024-2025 | C102415733205 | 05/10/2024 | 0 | WBSEDCL | 0.38 | 0 | 0
1989 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at Kulbari w/s scheme boosting TW III Application No.-2004567719, Ref.-204195754 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03933/2023-2024 | BP-2023-24-724 | 23/02/2024 | 0 | WBSEDCL | 10.34 | 0 | 0
1990 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Quotation bill for new service connection at Kulbari Boosting TW IV Application No.-2004567339, Ref ID.-204195755 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/03934/2023-2024 | BP-2023-24-725 | 23/02/2024 | 0 | WBSEDCL | 11.01 | 0 | 0
1991 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Boosting tubewells at different PWSS of Block Chandipur in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000047/2023-2024 | 1204/W/MMD | 25/04/2023 | 740 | BHABANI PRASAD MANNA | 77.91 | 0 | 55
1992 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Narma PWSS T/W no - II of Narayangarh block Application no - 2004754830 , Ref ID - 204323480 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/01303/2024-2025 | BP-2024-25-338 | 25/06/2024 | 0 | WBSEDCL | 8.18 | 0 | 0
1993 | Midnapore Mechanical | Kharagpur Sub-Division | Quotation for new power connection at Narma PWSS P/H- I , application no - 2004609088 , Ref id - 204223723 | AE Kharagpur Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/04199/2023-2024 | BP-2023-24-782 | 06/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
1994 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KEOT KHALISA TO ACCOMMODATE FHTC UNDER JAL JEEVAN MISSION UNDER MOHANPUR BLOCK IN PASCHIM MEDNIPUR DISTRICT UNDER MIDNAPORE DIVISION, PHE DTE. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000024/2023-2024 | 1188/W/MMD | 25/04/2023 | 180 | M/S EMMESS | 23.77 | 13.95 | 52
1995 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electrict quotation bill for TW-I of Jarisai pwss (Zone-I) (Ref Consumar ID-204310834),Application No-2004741317,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01064/2024-2025 | BP-2024-25-201 | 24/05/2024 | 0 | WBSEDCL | 4.08 | 0 | 0
1996 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Jarisai (Zone-I) Water Supply Scheme, Block - Mohanpur, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000027/2023-2024 | 1191/W/MMD | 25/04/2023 | 712 | GOENKA ENTERPRISE | 22.63 | 17.25 | 50
1997 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation for Load enhancement at Tw no-I of Suktajuri water supply scheme. Consumer ID-200331905. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00268/2023-2024 |  | 22/05/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
1998 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Rejuvenation of Electro-Mechanical components of Suktajuri PWSS in the District of Paschim Medinipur under JJM programme under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002126/2022-2023 | 1064/W/MMD | 29/03/2023 | 180 | TAPAN KUMAR SARKAR | 21.01 | 8.24 | 52
1999 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR GOKULPUR MINI WATER SUPPLY SCHEME,ZONE-III, T W NO I [ LELUAKOLA ] ,JJM WORKS, SCHEME CODE SM/19102, APPLICATION NO 2004793778, REFERENCE ID 204340985, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01466/2024-2025 | BP-2024-25-430 | 16/07/2024 | 0 | WBSEDCL | 0.11 | 0 | 0
2000 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR GOKULPUR WATER SUPPLY SCHEME, ZONE-III, T W NO II [ WALIPUR] , JJM WORKS, SCHEME CODE SM/19102, BLOCK- KHARAGPUR-I, APPLICATION NO 2004831803, REFERENCE ID 204363828, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01854/2024-2025 | C082408995334 | 07/08/2024 | 0 | WBSEDCL | 3.81 | 0 | 0
2001 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR GOKULPUR WATER SUPPLY SCHEME, ZONE-II, T W NO I [ KESHPAL] , JJM WORKS, SCHEME CODE SM/19102, APPLICATION NO 2004825721, REFERENCE ID 204360221, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | BILL/01855/2024-2025 | C082408994649 | 07/08/2024 | 0 | WBSEDCL | 4.01 | 0 | 0
2002 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte. (Zone-III) | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/001558/2023-2024 | 3173/W/MMD | 18/12/2023 | 836 | RISHAV ENTERPRISE | 5.98 | 0 | 85
2003 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Gokulpur (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-Iunder JJM Program under MMD PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/001667/2023-2024 | 54/W/MMD | 15/01/2024 | 807 | M/S BARMAN ROY TRADERS | 25.52 | 0 | 75
2004 | Midnapore Mechanical | Haldia Sub-Division | Electric Quotation for NATSHALLAKHYA Water Supply Scheme Z-II, T/W-III (Ref. ID-204048971) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01635/2023-2024 | BP-2023-24-140 | 27/07/2023 | 0 | WBSEDCL | 4.26 | 0 | 0
2005 | Midnapore Mechanical | Haldia Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Natshal Lakshya Zone-II Phase-I PWSS to Accommodate FHTC in Mahishadal Block under Haldia Sub-Division of Tamluk Division in Purba Medinipur District, under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001755/2022-2023 | 634/W/MMD | 20/03/2023 | 180 | JOYSHREE CONCERN | 13.56 | 13.46 | 90
2006 | Midnapore Mechanical | Tamluk Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HOGALBERYA and ADJOINING MOUJAS, Block Shahid Matangini, District Purba Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001339/2022-2023 | 2344/W/MMD | 29/12/2022 | 180 | BHABANI PRASAD MANNA | 25.26 | 0 | 40
2007 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SURATPUR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/19043, APPLICATION NO 2004809647, REFERENCE ID 20352804, DASPUR CCC, WBSEDCL | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/01633/2024-2025 | BP-2024-25-490 | 30/07/2024 | 0 | WBSEDCL | 11.24 | 0 | 0
2008 | Midnapore Mechanical | Ghatal Subdivision | QUOTATION MONEY FOR SURATPUR WATER SUPPLY SCHEME, T W NO II, JJM WORKS, SCHEME CODE SM/19043, APPLICATION NO 2004809619, REFERENCE ID 204352803, DASPUR CCC, WBSEDCL. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/01634/2024-2025 | BP-2024-25-489 | 30/07/2024 | 0 | WBSEDCL | 4.78 | 0 | 0
2009 | Midnapore Mechanical | Ghatal Subdivision | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Suratpur Piped Water Supply Scheme, Block - Daspur-I, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/001435/2023-2024 | 3089/W/MMD | 29/11/2023 | 525 | GOENKA ENTERPRISE | 23.01 | 0 | 100
2010 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-I of Amla Bani PWSS (Ref Consumer ID-204182336) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03335/2023-2024 | BP-2023-24-560 | 16/01/2024 | 0 | WBSEDCL | 5.76 | 0 | 0
2011 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Electric quotation bill for Tw No-II of Amla Bani PWSS. (Ref Consumer ID-204182328) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03336/2023-2024 | BP-2023-24-559 | 16/01/2024 | 0 | WBSEDCL | 2.93 | 0 | 0
2012 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for AMLA BANI AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000385/2023-2024 | 1724/W/MMD | 09/08/2023 | 600 | K.S.P. ENTERPRISE | 25.24 | 18.02 | 20
2013 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 100
2014 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 181 | M/S BIKASH DE | 3.69 | 0 | 0
2015 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.54 | 50
2016 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 100
2017 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Ad Tw no-III of Keshaiary PWSS . Ref Consumer ID-204117416) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02904/2023-2024 | BP-2023-24-328 | 03/11/2023 | 0 | WBSEDCL | 4.24 | 0 | 0
2018 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Electric quotation bill for Ad Tw no-IV of Keshiary PWSS. (Ref Consumer ID-204117417) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02905/2023-2024 | BP-2023-24-329 | 03/11/2023 | 0 | WBSEDCL | 3.2 | 0 | 0
2019 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | ADDITIONAL QUOTATION FOR SHIFTING OF LTOH AT CENTRAL BUS STAND PH NO-III OF KESHIARY PWSS, REFERENCE ID-860319179,APPLICATION ID-100000125209, APPLICATION TYPE- DEPOSIT WORKS OTHER THAN SERVICE CONNECTION, NAME OF CCC-KESHAIRY CCC, NAME OF BLOCK- KESHIARY. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/03672/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 0.92 | 0 | 0
2020 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001292/2022-2023 | 2295/W/MMD | 29/12/2022 | 883 | BUSR ENGINEERING | 22.99 | 10.94 | 20
2021 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-II) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001953/2022-2023 | 866/W/MMD | 27/03/2023 | 180 | S.S.GHORAI | 23.01 | 18.64 | 20
2022 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Keshiary to Accommodate FHTC, Block - Keshiary, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. (Part-III) | Assistant Engineer (HQ),Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002028/2022-2023 | 936/W/MMD | 28/03/2023 | 180 | EMCON | 11.49 | 0 | 0
2023 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Quotation for service connection(Ref ID: 204307608, Application No: 2004733766) for Dherua Augmentation Zone-ii(BHatpara SSK) (SM/19051) under Pirakata CCC,WBSEDCL | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01224/2024-2025 | BP-2024-25-280 | 14/06/2024 | 0 | WBSEDCL | 0.54 | 0 | 0
2024 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of pumping machineries and other electromechanical equipments for Augmentation of Dherua and its adj. mouzas Water Supply Scheme, Block - Midnapore Sadar, Dist.- Paschim Medinipur.under JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001445/2023-2024 | 3101/W/MMD | 29/11/2023 | 540 | DEBJYOTI BASU | 90.58 | 16.36 | 30
2025 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.29 | 0 | 100
2026 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 306 | M/S BIKASH DE | 6.3 | 0.14 | 50
2027 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 60 | M/S BIKASH DE | 0.83 | 0 | 100
2028 | Midnapore Mechanical | Midnapur Sadar Sub-Division | ELECTRIC QUOTATION BILL FOR TW NO-I OF BAJGERYA PWSS. REF CONSUMER ID-204325522, APPLICATION NO-2004767121, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-ANANDAPUR CCC, NAME OF BLOCK-KESHPUR | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01213/2024-2025 | BP-2024-25-291 | 18/06/2024 | 0 | WBSEDCL | 5.83 | 0 | 0
2029 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAJGERYA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000386/2023-2024 | 1725/W/MMD | 09/08/2023 | 180 | B.P.TRADING CORPORATION | 25.26 | 15.55 | 20
2030 | Midnapore Mechanical | Midnapur Sadar Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
2031 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, T W NO 4 / ZONE-I [ KERUR ] , JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004884722, REFERENCE ID 204391136, SABANG CCC, WBSEDCL | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02444/2024-2025 | BP-2024-25-696 | 27/09/2024 | 0 | WBSEDCL | 5.62 | 0 | 0
2032 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, AUGMENTATION , ZONE-II, T W 4, JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004923771, REFERENCE ID 204414194, SABANG CCC, WBSEDCL | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02978/2024-2025 | BP-2024-25-784 | 12/11/2024 | 0 | WBSEDCL | 7.05 | 0 | 0
2033 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | QUOTATION MONEY FOR BURAL WATER SUPPLY SCHEME, ZONE-I, T W -III, [ GUNDUT ] JJM WORKS, SCHEME CODE SM/19037, APPLICATION NO 2004884758, REFERENCE ID 204391138, SABANG CCC, WBSEDCL | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02989/2024-2025 | C112422745630 | 18/11/2024 | 0 | WBSEDCL | 6.87 | 0 | 0
2034 | Midnapore Mechanical | Midnapur Mechanical Sub Division-I | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at BURAL Water supply scheme, Sabang block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | AE/RWS Midnapore Sub Division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001681/2023-2024 | 59/W/MMD | 15/01/2024 | 180 | M/S. SAJAHAN CHOWDHURY | 47.41 | 33.55 | 40
2035 | Midnapore Mechanical |  | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for 1 (One) No. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme of Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. within Purba Medinipur Districtunder JJM Program under MMD PHE Dte. |  |  | ORD/001437/2023-2024 | 3091/W/MMD | 29/11/2023 | 180 | M/S. S.R. ENTERPRISE | 11.83 | 0 | 0
2036 | Midnapore Mechanical | Digha Sub-Division | Quotation for new service connection at Zone-1, TW-1 of Shankarpur (Ramnagar)ws scheme under MMD,PHE Dte Ref. Application no.-2004577423, Con ID-204203250 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/03723/2023-2024 | BP-2023-24-675 | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0
2037 | Midnapore Mechanical | Digha Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments atPiped Water Supply Scheme for Sankarpur Zone-I in Purba Medinipur District,under JJM Program under MMD PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000745/2023-2024 | 2289/W/MMD | 29/08/2023 | 701 | S.S.GHORAI | 23.52 | 11.31 | 90
2038 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR MOHAR-KATINA WATER SUPPLY SCHEME, T W NO I, [ MOHAR ] , JJM WORKS, SCHEME CODE SM/18620, APPLICATION NO 2004806860, REFERENCE ID 204348023, SABANG CCC, WBSEDCL | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | BILL/01458/2024-2025 | BP-2024-25-421 | 15/07/2024 | 0 | WBSEDCL | 5.53 | 0 | 0
2039 | Midnapore Mechanical | Kharagpur Sub-Division | QUOTATION MONEY FOR MOHAR-KATINA WATER SUPPLY SCHEME, T W NO I, [ KATINA] , JJM WORKS, SCHEME CODE SM/18620, APPLICATION NO 2004806819, REFERENCE ID 204348010, SABANG CCC, WBSEDCL | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | BILL/01459/2024-2025 | BP-2024-25-422 | 15/07/2024 | 0 | WBSEDCL | 6.29 | 0 | 0
2040 | Midnapore Mechanical | Kharagpur Sub-Division | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Mohar, Katina & its adjoining mouzas (Zone-I & II), Block - Sabang.under JJM Program under MMD PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000387/2023-2024 | 1726/W/MMD | 09/08/2023 | 180 | DAS ENTERPRISE | 47.42 | 31.08 | 30
2041 | Midnapore Mechanical | Kharagpur Sub-Division | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 180 | SWAPAN BANERJEE | 10.42 | 0 | 100
Total | [10 empty] | 28752.97 | 8033.07