## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 120KVA to 155 KVA at 11KV having Consumer ID : 942304500 at the premises at Anandapur, Saltora water supply scheme(Intake), Bankura. | Assistant Engineer | Junior Engineer | BILL/00956/2024-2025 | BP-2024-25-237 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.17 | 0 | 0
2 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 60KVA to 98 KVA at 11KV having Consumer ID : 942304600 at the premises at Biharinath, Saltora, Bankura. | Assistant Engineer | Junior Engineer | BILL/00957/2024-2025 | BP-2024-25-238 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0
3 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work of Providing and installation of High Lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation of subsurface water based water supply scheme Saltora for providing FHTC in Saltora Block under Bankura Mechanical Division PHE Dte, Block: Saltora Dist : Bankura. | Assistant Engineer | Junior Engineer | ORD/000614/2023-2024 | 2070/BMD | 12/09/2023 | 180 | DAS ENTERPRISE | 303.87 | 222.57 | 40
4 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pumping machineries with other electro-mechanical accessories for 4 nos vertical tubewell at Intake Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 147/BMD | 30/04/2025 | 90 | ORIENTAL ENGINEERING CO. | 27.6 | 0 | 100
5 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, Delivery and installation of Voltage Correction device and allied works for Augmentation of subsurface water based water supply scheme Saltora for providing FHTC in Saltora Block under Bankura Mechanical Division PHE Dte, Block: Saltora Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 784/BMD | 20/08/2024 | 240 | DAS ENTERPRISE | 29.99 | 0 | 80
6 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work-Providing and Installation of Low lift pumping machineries and other electro-mechanical accessories for Augmentation of source by sinking of river bed Tube well including connecting line & M.S. Rising main at Kukrakuri in the river bed of Damodar and providing FHTC for Saltora Chhatna water supply scheme (BRGF Phase-I) under Jal Jeevan Mission under Bankura Mechanical Division PHE Dte. Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000426/2022-2023 | 341/BMD | 03/03/2023 | 184 | ORIENTAL ENGINEERING CO. | 99.53 | 89.03 | 100
7 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for Kenjakura augmentation site at Bankura-I block under BMD PHE Dte.(SM/09877) | Assistant Engineer | Junior Engineer | BILL/01337/2024-2025 | BP-2024-25-355 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0
8 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of piped water supply scheme for Kenjakura its adjoining mouzas (JJM Revision) under Bankura Mechanical Division PHE Dte Bankura-I Block- Dist -Bankura. | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 1170/BMD | 01/06/2023 | 180 | M/S SOMA ENTERPRISES | 64.3 | 51.14 | 8
9 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Augmentation works for Bikna and its adjoining mouzas Water Supply Scheme (Phase- I). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 860/BMD | 29/08/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 41.19 | 0 | 0
10 | Bankura Mechanical | Bankura Sadar Sub-Division | MINI PIPED WATER SUPPLY SCHEME FOR RAMNAGAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | Assistant Engineer | Junior Engineer | BILL/01671/2023-2024 |  | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
11 | Bankura Mechanical | Brishnupur Sub-Division | Hirapur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01548/2023-2024 | BP-2023-24-107 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.45 | 0 | 0
12 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Hirapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000188/2025-2026 | 460/BMD | 10/06/2025 | 90 | KASHINATH DEY | 11.69 | 0 | 0
13 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATSOLE TW-1(JL NO-68, PLOT-159/188LR) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00017/2024-2025 | BP-2024-25-27 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.15 | 0 | 0
14 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATSOLE TW-2 (JL NO-68, PLOT-159/188) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00024/2024-2025 | BP-2024-25-28 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.58 | 0 | 0
15 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing & installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Patsol Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000062/2025-2026 | 401/BMD | 04/06/2025 | 90 | S.DUTTA | 15.08 | 0 | 0
16 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-4B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000239/2023-2024 | 1124/BMD | 24/05/2023 | 30 | M/S DAS & SARKAR ENTERPRISE | 2.39 | 0 | 0
17 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for GOALA DANGA water supply scheme under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | BILL/00016/2024-2025 | BP-2024-25-32 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.63 | 0 | 0
18 | Bankura Mechanical | Brishnupur Sub-Division | Goala Danga Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01614/2023-2024 | BP-2023-24-142 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.78 | 0 | 0
19 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Goala Danga Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000022/2025-2026 | 233/BMD | 14/05/2025 | 90 | M/S BIPUL BANERJEE | 10.88 | 0 | 0
20 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Kubir Bandh Zone-II TW1 Water supply scheme of sonamukhi Block under Bankura Mechanical Division PHE DTE.(SM/14008) | Assistant Engineer | Junior Engineer | BILL/01179/2024-2025 | BP-2024-25-306 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.7 | 0 | 0
21 | Bankura Mechanical | Brishnupur Sub-Division | Kubir Bandh Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01666/2023-2024 | BP-2023-24-183 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.51 | 0 | 0
22 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kubir Bandh piped water supply scheme (Zone- II) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 655/BMD | 17/04/2023 | 180 | UNITED TRADERS | 31.37 | 13.99 | 45
23 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kubir Bandh piped water supply scheme (Zone-I) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000427/2023-2024 | 1687/BMD | 27/07/2023 | 180 | PRADIP KUMAR DHABAL | 36.76 | 19.54 | 53
24 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Kushawdip (T/W-II) water supply scheme at patrasayer block under BMD PHE Dte.(SM/15266) | Assistant Engineer | Junior Engineer | BILL/01472/2024-2025 | BP-2024-25-356 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0
25 | Bankura Mechanical | Brishnupur Sub-Division | Kushadwip Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01655/2023-2024 | BP-2023-24-181 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.42 | 0 | 0
26 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Mukundapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000021/2025-2026 | 232/BMD | 14/05/2025 | 90 | ABHIJIT MUKHERJEE | 11.53 | 0 | 0
27 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Kushadwip Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000140/2025-2026 | 435/BMD | 10/06/2025 | 90 | M/S DAS AND SARKAR ENTERPRISE | 11.74 | 0 | 0
28 | Bankura Mechanical | Brishnupur Sub-Division | Lankajol Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01509/2023-2024 | BP-2023-24-95 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0
29 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Lankajol Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000152/2025-2026 | 447/BMD | 10/06/2025 | 90 | PRADIP KUMAR DHABAL | 11.84 | 0 | 0
30 | Bankura Mechanical | Brishnupur Sub-Division | Narayanpur | Assistant Engineer | Junior Engineer | BILL/01505/2023-2024 | BP-2023-24-101 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.1 | 0 | 0
31 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Narayanpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura | Assistant Engineer | Junior Engineer | ORD/000150/2025-2026 | 445/BMD | 10/06/2025 | 90 | GOPAL CHANDRA CHOWDHURY | 11.87 | 0 | 0
32 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00160/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
33 | Bankura Mechanical | Bankura Sadar Sub-Division | Service connection charge for Saulia (Zone -G) water supply scheme at head works site Barjora block under BMD,PHE Dte.(SM/16960) | Assistant Engineer | Junior Engineer | BILL/00348/2024-2025 | BP-2024-25-170 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.51 | 0 | 0
34 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Saulia (Zone-G) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 503/BMD | 09/07/2024 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 13.19 | 0 | 0
35 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Saulia ( Zone-G) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000303/2023-2024 | 1406/BMD | 18/07/2023 | 60 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 81.3 | 61.78 | 75
36 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No- II at Tail End site of Augmentation works for Saulia (Zone-G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000314/2024-2025 | 855/BMD | 29/08/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 19.1 | 0 | 0
37 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00148/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
38 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01611/2023-2024 | BP-2023-24-137 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.75 | 0 | 0
39 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Bankati (Zone-R ) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000009/2025-2026 | 144/BMD | 30/04/2025 | 90 | EASTERN INDIA SALES & SERVICE | 20.27 | 0 | 0
40 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Bonkati (Zone R) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000524/2023-2024 | 1888/BMD | 17/08/2023 | 120 | SUNRISE ENGINEERING CORPORATION | 81.75 | 52.37 | 64
41 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kalayani (Zone-A) and Adjoining mouza water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Onda , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000609/2023-2024 | 2083/BMD | 12/09/2023 | 120 | P.K. ENGINEERING | 71.94 | 59.66 | 60
42 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Dhansimla TW-1 | Assistant Engineer | Junior Engineer | BILL/00027/2024-2025 | BP-2024-25-17 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.53 | 0 | 0
43 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Dhansimla T/W-II water supply under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00030/2024-2025 | BP-2024-25-18 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.07 | 0 | 0
44 | Bankura Mechanical | Brishnupur Sub-Division | Additional Quotation payment for diversion of HTOH line due to objection of local people for effecting of new connection at Dhansimla T/W-II | Assistant Engineer | Junior Engineer | BILL/00729/2024-2025 | BP-2024-25-212 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0
45 | Bankura Mechanical | Brishnupur Sub-Division | Dhan Simla Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01516/2023-2024 | BP-2023-24-113 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.04 | 0 | 0
46 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Dhansimla piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000423/2023-2024 | 1685/BMD | 27/07/2023 | 1080 | PRADIP KUMAR DHABAL | 37.28 | 17.48 | 46
47 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00181/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
48 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AMRUL ZONE B water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00432/2024-2025 | BP-2024-25-103 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
49 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Mahespur (Amrul Zone-B) | Assistant Engineer | Junior Engineer | BILL/01332/2024-2025 | BP-2024-25-339 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.36 | 0 | 0
50 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01619/2023-2024 | BP-2023-24-158 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.6 | 0 | 0
51 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Amrul (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000363/2023-2024 | 1697/BMD | 28/07/2023 | 720 | WEST BENGAL ENGINEERING CO. | 73.36 | 0 | 40
52 | Bankura Mechanical | Bankura Sadar Sub-Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | Assistant Engineer | Junior Engineer | BILL/00196/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
53 | Bankura Mechanical | Bankura Sadar Sub-Division | New 3 phase service connection for Pabra w/s Scheme | Assistant Engineer | Junior Engineer | BILL/00728/2024-2025 | BP-2024-25-210 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.59 | 0 | 0
54 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation work of 06 nos OHR under Saltora-Chhatna Water scheme under Bankura Mechanical Division, PHE Dte. Block : Saltora , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000020/2025-2026 | 155/BMD | 30/04/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 29.72 | 0 | 0
55 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Proposed surface water based Pabra under Water Supply Scheme Block- Saltora under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000446/2023-2024 | 1774/BMD | 01/08/2023 | 60 | ABHIJIT MUKHERJEE | 46.8 | 32.3 | 37
56 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00139/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
57 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Maliara (Zone-A) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000158/2024-2025 | 500/BMD | 09/07/2024 | 120 | SUTRADHAR TRADERS | 13.17 | 0 | 0
58 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Maliara ( Zone-A) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000301/2023-2024 | 1404/BMD | 18/07/2023 | 851 | B T PROJECTS PRIVATE LIMITED | 82.62 | 51.28 | 73
59 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00138/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
60 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for Sonadaha water supply scheme at Bankura -II block under BMD PHE Dte.(SM/17240) | Assistant Engineer | Junior Engineer | BILL/01338/2024-2025 | BP-2024-25-338 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.02 | 0 | 0
61 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Sonadaha( Zone-Q) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000166/2024-2025 | 508/BMD | 09/07/2024 | 120 | M/S BIPUL BANERJEE | 8.77 | 5.34 | 60
62 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Sonadaha (Zone-Q) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000525/2023-2024 | 1889/BMD | 17/08/2023 | 1032 | PREMNATH MITRA | 81.81 | 0 | 65
63 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00150/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
64 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for Anchuri augmentation at Kasiadoba,Bankura-I block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01489/2024-2025 | BP-2024-25-378 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.38 | 0 | 0
65 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Anchuri (Zone-T ) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000010/2025-2026 | 145/BMD | 30/04/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.59 | 0 | 0
66 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Achuri (Zone-T) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2023-2024 | 1468/BMD | 18/07/2023 | 600 | ABHIJIT MUKHERJEE | 81.82 | 57.08 | 76
67 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Morar Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00165/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
68 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Marar Zone-B TW-II Mouza Agunkumari ,Block Bishnupur.SM/17243 | Assistant Engineer | Junior Engineer | BILL/01094/2024-2025 | BP-2024-25-249 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.76 | 0 | 0
69 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Morar Z-B TW-III Mouza Belsulia.SM-17243 | Assistant Engineer | Junior Engineer | BILL/01140/2024-2025 | BP-2024-25-286 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.33 | 0 | 0
70 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Morar Z-B TW-I Mouza Chandabila .Block Bishnupur SM-17243 | Assistant Engineer | Junior Engineer | BILL/01144/2024-2025 | BP-2024-25-287 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.23 | 0 | 0
71 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HSC pumping machineries with allied work for Augmentation of Marar Zone-B and adjoining mouzas water supply scheme (BRGF Ph I) at CWR site Gopalpur , Block Bishnupur under Jal Jeevan Mission programme under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000267/2024-2025 | 775/BMD | 20/08/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 44.9 | 0 | 0
72 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Marar Zone-B piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000390/2023-2024 | 1711/BMD | 28/07/2023 | 900 | M.S. ENTERPRISE | 95.96 | 72.81 | 81
73 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IV). | Assistant Engineer | Junior Engineer | BILL/00158/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
74 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories at Tail End at GOPBANDHI, Saharjora for Augmentation works under BARJORA (ZONE -IV) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000183/2024-2025 | 578/BMD | 24/07/2024 | 120 | NUPUR CHANDRA HALDER | 13.15 | 0 | 0
75 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IV) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 1402/BMD | 18/07/2023 | 60 | WEST BENGAL ENGINEERING CO. | 81.8 | 54.19 | 55
76 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible pumping machineries and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I) ( Zone IV) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001037/2023-2024 | 2969/BMD | 29/02/2024 | 725 | M/S S.G. ENTERPRISE | 27.54 | 0 | 99
77 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Masanjhar (Zone- F) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00206/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
78 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Masanjhar (Zone F) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000055/2025-2026 | 251/BMD | 14/05/2025 | 90 | NUPUR CHANDRA HALDER | 28.18 | 0 | 0
79 | Bankura Mechanical | Brishnupur Sub-Division | Dwarika Pipe Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01610/2023-2024 | BP-2023-24-136 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.76 | 0 | 0
80 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for proposed ground water based Dwarika piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001082/2023-2024 | 3060/BMD | 12/03/2024 | 835 | RAJIB COMPANY | 44.62 | 7.42 | 55
81 | Bankura Mechanical | RWS Bankura Sub-Division | Augmentation works for Tilaboni (Zone- B) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00204/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
82 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Tilaboni (Zone B ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000058/2025-2026 | 254/BMD | 14/05/2025 | 90 | S.P. CONSTRUCTION | 28.43 | 0 | 0
83 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Panchal Water Supply Scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | BILL/00025/2024-2025 |  | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0
84 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Panchal Water Supply Scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | BILL/00026/2024-2025 | 1 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0
85 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Panchal Zone-II Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00187/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
86 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Sukhsayer water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00380/2024-2025 | BP-2024-25-85 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.2 | 0 | 0
87 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Panchal water supply scheme under Bankura Mechanical Division PHE Dte.(SM-17423) | Assistant Engineer | Junior Engineer | BILL/00417/2024-2025 | BP-2024-25-97 | 04/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0 | 0 | 0
88 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Panchal (Zone-II) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1789/BMD | 01/08/2023 | 1080 | TAPAN KUMAR SARKAR | 41.85 | 16.61 | 40
89 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Dadhimukha (Zone - D) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00135/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
90 | Bankura Mechanical | Bankura Sadar Sub-Division | Service connection charge for at Rautara tail end T/W under Dadhimukha (zone-D) water supply scheme Barjora block under BMD,PHE Dte.(SM/17424 ) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00347/2024-2025 | 12 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
91 | Bankura Mechanical | Bankura Sadar Sub-Division | Load enhancement Service connection charge for Dadhimukha (zone-D) OHR site water supply scheme Barjora block under BMD,PHE Dte.(SM/17424 ) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/02192/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.97 | 0 | 0
92 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for Augmentation works at Rautara Pump house (Tail End) under Dadhimukha (Zone -D) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000154/2024-2025 | 497/BMD | 09/07/2024 | 480 | GOENKA ENTERPRISE | 23.1 | 9.32 | 30
93 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Dadhimukha ( Zone-D) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000455/2023-2024 | 1781/BMD | 01/08/2023 | 120 | SUNRISE ENGINEERING CORPORATION | 81.75 | 0 | 30
94 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chakuparsole Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00169/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
95 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new serrvice connection at Chak Uparsole Z-A TW-II JL 135 Mouza Bhaluka.SM -17425 | Assistant Engineer | Junior Engineer | BILL/01142/2024-2025 | BP-2024-25-282 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.43 | 0 | 0
96 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Chakuparsole zone-A ,Mouza - Baramara. GP-Bankadaha.SM-17425 | Assistant Engineer | Junior Engineer | BILL/01173/2024-2025 | BP-2024-25-295 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.65 | 0 | 0
97 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Chak Uparsole Z-A Mouza -Majuria. Block -Bishnupur.SM-17425 | Assistant Engineer | Junior Engineer | BILL/01184/2024-2025 | BP-2024-25-296 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.29 | 0 | 0
98 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Hetagora of Chakuparsole Zone-A w/s scheme .SM/17425 | Assistant Engineer | Junior Engineer | BILL/01655/2024-2025 | 107/W-612 | 01/08/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.55 | 0 | 0
99 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW I to IV for Augmentation of Chakuparsole and Adjoining mouza water supply scheme (Zone-A) Block-Bishnupurunder Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000141/2024-2025 | 484/BMD | 09/07/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 40.43 | 24.39 | 100
100 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chakuparsole (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000518/2023-2024 | 1883/BMD | 17/08/2023 | 1020 | SUNRISE ENGINEERING CORPORATION | 71.39 | 0 | 75
101 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible Pump Motor set and other allied works at Prakash Zone-A & Chakuparsol Zone-A water supply scheme under Bishnupur Block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2025-2026 | 640/BMD | 11/07/2025 | 90 | MIK ENTERPRISES | 20.18 | 0 | 0
102 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-III). | Assistant Engineer | Junior Engineer | BILL/00157/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
103 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Hatasuria OHR site under Barjora (Zone-III) water supply scheme (left out mouza of Barjora) , Barjora block under BMD, PHE Dte. (SM/17428) | Assistant Engineer | Junior Engineer | BILL/01335/2024-2025 | BP-2024-25-334 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.75 | 0 | 0
104 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories at Tail end site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) ( Zone-III) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000155/2024-2025 | 498/BMD | 09/07/2024 | 120 | S.DUTTA | 13.17 | 5.03 | 38
105 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-III) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000298/2023-2024 | 1401/BMD | 18/07/2023 | 60 | M.S. ENTERPRISE | 81.83 | 61.51 | 48
106 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IA) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 519/BMD | 09/07/2024 | 120 | SINHA ELECTRICALS | 11.28 | 0 | 0
107 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Rol Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00182/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
108 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for ROLL ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00433/2024-2025 | BP-2024-25-106 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0
109 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rol (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000377/2023-2024 | 1703/BMD | 28/07/2023 | 611 | M/S BIPUL BANERJEE | 39.07 | 19.6 | 50
110 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Joykrisnapur (Zone - I) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00159/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
111 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Joykrishnapur (Zone-I) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 501/BMD | 09/07/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 13.36 | 0 | 0
112 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Joykrisnapur ( Zone-I) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000300/2023-2024 | 1403/BMD | 18/07/2023 | 60 | M/S SOMA ENTERPRISES | 81.75 | 66.22 | 35
113 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for shifting of 11KV HTOH at Jhatiboni ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00287/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.8 | 0 | 0
114 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground water based Jhatiboni pipe water supply scheme under Bankura Division, Block - Onda, Dist. Bankura. | Assistant Engineer | Junior Engineer | BILL/01607/2023-2024 | BP-2023-24-134 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.73 | 0 | 0
115 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at TW No-I & TW No-II Premises of Jhatiboni piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000124/2024-2025 | 1072/BMSD | 05/07/2024 | 60 | M/S DE ENGINEERING CONCERN | 4.37 | 0 | 0
116 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Jhatiboni piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000443/2023-2024 | 1772/BMD | 01/08/2023 | 720 | INDRAJIT MITRA | 36.9 | 18.79 | 90
117 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Ratanpur (Zone-B) Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 1994/BMD | 28/08/2023 | 120 | UNITED TRADERS | 46.43 | 29.8 | 80
118 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Radhanagar Zone-I Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00162/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
119 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Sarada Pally (Bankati) of Radhanagar Zone-I ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00294/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0
120 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Swasan of Radhanagar Zone-I ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00295/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.85 | 0 | 0
121 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for Kankila OHR of Radhanagar w/s scheme. | Assistant Engineer | Junior Engineer | BILL/00536/2024-2025 | 1 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0
122 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at OHR, CWR and Tail end site for Augmentation of Radhanagar (Zone I) piped water supply scheme(BRGF Phase I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000120/2024-2025 | 430/BMD | 27/06/2024 | 120 | M/S NABIN GOPAL SENGUPTA | 61.72 | 17.33 | 100
123 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineryes with allied works for Augmentation of Radhanagar Zone-I Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000322/2024-2025 | 863/BMD | 29/08/2024 | 480 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 20.86 | 0 | 50
124 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Radhanagar (Zone-I) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000373/2023-2024 | 1701/BMD | 28/07/2023 | 704 | TAPAN KUMAR SARKAR | 40.91 | 22.96 | 82
125 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Jambedia (Zone Q) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000051/2025-2026 | 250/BMD | 14/05/2025 | 90 | JAL PRAVAHIKA PVT LTD | 25.68 | 0 | 0
126 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Kadra (Zone G) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000042/2025-2026 | 246/BMD | 14/05/2025 | 90 | WEST BENGAL ENGINEERING CO. | 28.18 | 0 | 0
127 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Kadra (Zone- G) ( Boosting at Tail end) under Khatra-Hirbandh-Ranibandh Water Supply Scheme piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000168/2024-2025 | 510/BMD | 09/07/2024 | 719 | RAJIB COMPANY | 13.22 | 0 | 75
128 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System other work at Pathardoba Zone -A water supply scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000192/2025-2026 | 637/BMD | 11/07/2025 | 90 | GOPAL CHANDRA CHOWDHURY | 15.72 | 0 | 0
129 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement and installation od new charger panel and other allied works for Augmentation for PATHARDOBA ZONE -B water supply scheme under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000274/2024-2025 | 779/BMD | 20/08/2024 | 371 | M/S BIPUL BANERJEE | 18.58 | 0 | 55
130 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Pathardoba Zone-B and adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000994/2023-2024 | 2854/BMD | 09/02/2024 | 545 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 134.65 | 89.23 | 65
131 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of water supply scheme for Parsola Zone-B and its adjoining mouzas under simlapal water (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000991/2023-2024 | 2851/BMD | 09/02/2024 | 518 | QUAZI NOZRUL ISLAM | 102.52 | 0 | 40
132 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Pathardoba, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01656/2023-2024 | BP-2023-24-172 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.44 | 0 | 0
133 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Pathardoba Zone-A and adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000993/2023-2024 | 2853/BMD | 09/02/2024 | 720 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 135.08 | 114.91 | 70
134 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing And Installation Of Pumping Machineries And Other Electro-Mechanical Accessories for Improvement of Hirbandh And Adjoining Mouzas Water supply Scheme. Block- Hirbandh, Dist- Bankura. | Assistant Engineer | Junior Engineer | ORD/000073/2021-2022 | 895/BMD | 27/07/2021 | 120 | M/S P.P ELECTRICALS | 36.91 | 36.91 | 0
135 | Bankura Mechanical | Khatra Sub-Division | Formal work order for the work of Providing and Installation of High Lift & Low Lift pumping machineries and other electro-mechanical accessories for Syamsundarpur (Zone-IIA & IIB) water supply scheme under Raipur water supply scheme (BRGF Ph-I) under JJM Programme under Bankura Mechanical Division PHE Dte. Block-Raipur, Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000248/2023-2024 | 951/BMD | 17/05/2023 | 866 | R.N.S. TRADING | 276.53 | 0 | 32
136 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of ground water based piped supply scheme for Moynapur to accommodate FSTC under Jal Swapna mission under Joypur Block in Bankura District under Bankura Mechanical Division, PHE Dte t: Bankura. | Assistant Engineer | Junior Engineer | ORD/000193/2023-2024 | 1016/BMD | 22/05/2023 | 1080 | KASHINATH DEY | 23.01 | 17.72 | 30
137 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Rani Bandh water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 875/BMD | 04/05/2023 | 1260 | TAPAN KUMAR SARKAR | 35.82 | 20.2 | 56
138 | Bankura Mechanical | Brishnupur Sub-Division | Continuation Order for Trial run of operation and guarding of pumping machinery & other at Rani Bandh (P.H-I) water supply scheme under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001220/2025-2026 | 1798/BMSD | 29/10/2025 | 90 | TAPAN KUMAR SARKAR | 0.43 | 0 | 0
139 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-3A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000459/2023-2024 | 1785/BMD | 01/08/2023 | 60 | M/S DE ENGINEERING CONCERN | 2.39 | 0 | 0
140 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-5A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000240/2023-2024 | 1125/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
141 | Bankura Mechanical | Brishnupur Sub-Division | Jibta Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01501/2023-2024 | BP-2023-24-96 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.55 | 0 | 0
142 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Jibta piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 771/BMD | 24/04/2023 | 738 | ABHIJIT MUKHERJEE | 31.26 | 13.14 | 64
143 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for RAMNAGAR water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00020/2024-2025 | BP-2024-25-31 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
144 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Ramnagar (T/W-II) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/14005) | Assistant Engineer | Junior Engineer | BILL/01478/2024-2025 | BP-2024-25-358 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.29 | 0 | 0
145 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Ramnagar Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000033/2025-2026 | 238/BMD | 14/05/2025 | 90 | UNITED TRADERS | 11.66 | 0 | 0
146 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Ramnagar Piped water supply scheme Block : Patrashayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000110/2023-2024 | 770/BMD | 24/04/2023 | 1095 | RAJIB COMPANY | 46.94 | 18.92 | 80
147 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for CHAKAI (JL NO-23, PLOT-177) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00018/2024-2025 | BP-2024-25-26 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.28 | 0 | 0
148 | Bankura Mechanical | Brishnupur Sub-Division | Chakai Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01665/2023-2024 | BP-2023-24-192 | 27/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.36 | 0 | 0
149 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Chakai Piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000106/2023-2024 | 768/BMD | 24/04/2023 | 1260 | GOENKA ENTERPRISE | 47 | 19.47 | 80
150 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-6 of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000242/2023-2024 | 1127/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
151 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00147/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
152 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01612/2023-2024 | BP-2023-24-139 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
153 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System at Kendboni (Zone-P) OHR under Bankura-I.II and Barjora Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000142/2025-2026 | 437/BMD | 10/06/2025 | 90 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 26.41 | 0 | 0
154 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kendbani (Zone P) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000526/2023-2024 | 1890/BMD | 17/08/2023 | 853 | EASTERN INDIA SALES & SERVICE | 81.78 | 49.86 | 56
155 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00141/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
156 | Bankura Mechanical | Bankura Sadar Sub-Division | Quotation Bill for New Service Connection at Kotalpukur (zone-B) Water supply scheme under Bankura Mechanical Division PHE DTE (scheme code: SM/16955) | Assistant Engineer | Junior Engineer | BILL/01254/2024-2025 | BP-2024-25-321 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.5 | 0 | 0
157 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for Augmentation works at OHR site under Kotalpukur (ZONE -B) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000374/2024-2025 | 1003/BMD | 24/09/2024 | 240 | KINGKINI TRADERS | 9.12 | 0 | 25
158 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kotalpukur ( Zone B) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000519/2023-2024 | 1884/BMD | 17/08/2023 | 120 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.09 | 69
159 | Bankura Mechanical | Brishnupur Sub-Division | New sevice connection for Karajbani water supply scheme (SM/16702) at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01247/2024-2025 | BP-2024-25-322 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0
160 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I and TW No II of Karajbani piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Patrashayar, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000116/2024-2025 | 427/BMD | 27/06/2024 | 240 | GOENKA ENTERPRISE | 51.06 | 8.49 | 21
161 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Lachiapur (Zone D) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000059/2025-2026 | 255/BMD | 14/05/2025 | 90 | ORIENTAL ENGINEERING CO. | 29.05 | 0 | 0
162 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Biradihi (Zone C ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000060/2025-2026 | 256/BMD | 14/05/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 27.35 | 0 | 0
163 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Lachiapur(Zone-D) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000196/2025-2026 | 642/BMD | 11/07/2025 | 90 | JAL PRAVAHIKA PVT LTD | 34 | 0 | 0
164 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Lachiapur (Zone-D) under Khatra-Hirbandh-Ranibandh water supply scheme (BRGF-Ph-I) under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000608/2023-2024 | 2082/BMD | 12/09/2023 | 720 | RABINDRA NATH KHAN | 61.4 | 0 | 30
165 | Bankura Mechanical | Khatra Sub-Division | New service connection charge at T/W-III of Makhnu. | Assistant Engineer | Junior Engineer | BILL/01148/2024-2025 | BP-2024-25-284 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.98 | 0 | 0
166 | Bankura Mechanical | Khatra Sub-Division | New service connection charge at T/W-IV of Makhnu | Assistant Engineer | Junior Engineer | BILL/01150/2024-2025 | BP-2024-25-285 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.47 | 0 | 0
167 | Bankura Mechanical | Khatra Sub-Division | New Service Connection at Makhnu T/W-I | Assistant Engineer | Junior Engineer | BILL/01482/2024-2025 | BP-2024-25-371 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.58 | 0 | 0
168 | Bankura Mechanical | Khatra Sub-Division | New Service Connection at Makhnu T/W-II | Assistant Engineer | Junior Engineer | BILL/01483/2024-2025 | BP-2024-25-371 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.58 | 0 | 0
169 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Makhnu (Zone- K) ( boosting at tail end) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000150/2024-2025 | 493/BMD | 09/07/2024 | 659 | M/S BIPUL BANERJEE | 49.9 | 9.41 | 76
170 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Makhnu (Zone k) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000418/2025-2026 | 579/BMD | 03/07/2025 | 90 | GOENKA ENTERPRISE | 28.19 | 0 | 0
171 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at existing Tubewell for Augmentation of Agarda and adjoining mouzas piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000167/2024-2025 | 509/BMD | 09/07/2024 | 720 | CHAKRABORTY MINING & ENGINEERING. | 24.55 | 4.08 | 100
172 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Agarda & its adjoining Mouzas water supply scheme under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000544/2023-2024 | 1980/BMD | 28/08/2023 | 120 | TAPAN KUMAR SARKAR | 56.61 | 35.89 | 64
173 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-E) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000548/2023-2024 | 1984/BMD | 28/08/2023 | 120 | EASTERN INDIA SALES & SERVICE | 74.01 | 44.3 | 60
174 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other electro mechanical accessories for Augmentation of Aguri bandh Punisole and its adjoining mouzas water supply scheme (Zone E) under Onda Block (BRGF Ph-I) at CWR site Nischintapur under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001076/2023-2024 | 3055/BMD | 12/03/2024 | 480 | M.S. ENTERPRISE | 77.57 | 27.13 | 100
175 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Deuli (Zone Malian ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000057/2025-2026 | 253/BMD | 14/05/2025 | 90 | SINHA ELECTRICALS | 27.35 | 0 | 0
176 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Zone Malian OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000197/2025-2026 | 643/BMD | 11/07/2025 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 35.2 | 0 | 0
177 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00184/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
178 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AKUI ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00438/2024-2025 | BP-2024-25-114 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0
179 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01626/2023-2024 | BP-2023-24-161 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.41 | 0 | 0
180 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Akui (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000358/2023-2024 | 1694/BMD | 28/07/2023 | 967 | KINGKINI TRADERS | 41.83 | 23.77 | 40
181 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Prakash Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00168/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
182 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Prakash (Zone-B) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000388/2023-2024 | 1710/BMD | 28/07/2023 | 60 | KASHINATH DEY | 20.9 | 0 | 0
183 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Prakash Zone -B and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001099/2023-2024 | 3074/BMD | 12/03/2024 | 120 | S. G. TECHNICAL SERVICE | 15.72 | 0 | 0
184 | Bankura Mechanical | Bankura Sadar Sub-Division | 'Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project).' | Assistant Engineer | Junior Engineer | BILL/00128/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
185 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for DHABAN water supply scheme under BMD PHE Dte. (SM code : SM/17702) | Assistant Engineer | Junior Engineer | BILL/00429/2024-2025 | BP-2024-25-105 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.01 | 0 | 0
186 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at Intermediate Boosting pumping station(IBS) and sub-station equipments at Upargora under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000338/2023-2024 | 1470/BMD | 18/07/2023 | 60 | DAS ENTERPRISE | 173.06 | 164.82 | 70
187 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Replacement of Valves on delivery line at Intermediate Boosting pumping station(IBS) at Upargora under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura for Augmentation work Dhaban( Zone-A) under Saltora-Chhatna Water supply scheme (BRGF Phase-I) | Assistant Engineer | Junior Engineer | ORD/000612/2023-2024 | 2086/BMD | 12/09/2023 | 611 | DAS ENTERPRISE | 17.65 | 0 | 60
188 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machinery and other electromagnetically accessories for Augmentation works DHABAN (Zone - A) under Saltora- Chhatna Water Supply Scheme PWS Scheme under Bankura Mechanical Division PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001089/2023-2024 | 3064/BMD | 12/03/2024 | 420 | WEST BENGAL ENGINEERING CO. | 84.1 | 0 | 37
189 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED GROUND WATER BASED HARIRAMPUR PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : HIRBANDH, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer | BILL/00202/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
190 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00303/2024-2025 |  | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0
191 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00304/2024-2025 |  | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0
192 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at Harirampur Piped Water Supply Scheme,Guniada of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00305/2024-2025 | BP-2024-25-52 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.79 | 0 | 0
193 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Harirampur piped water supply scheme Block Hirbandh under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000565/2023-2024 | 2032/BMD | 01/09/2023 | 600 | M/S SWAPAN BANERJEE | 35.43 | 0 | 30
194 | Bankura Mechanical | Brishnupur Sub-Division | Mahaldanga T/W-III | Assistant Engineer | Junior Engineer | BILL/00853/2023-2024 | BP-2023-24-39 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
195 | Bankura Mechanical | Brishnupur Sub-Division | Mahaldanga T/W-II | Assistant Engineer | Junior Engineer | BILL/00854/2023-2024 | BP-2023-24-40 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0
196 | Bankura Mechanical | Brishnupur Sub-Division | New service connection charge at P/H-I of Mahaldanga W/S Scheme | Assistant Engineer | Junior Engineer | BILL/01240/2024-2025 | BP-2024-25-308 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.97 | 0 | 0
197 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & T/W No-III of Mahaldanga piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Joypur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000166/2023-2024 | 878/BMD | 04/05/2023 | 180 | UNIVERSAL ENTERPRISE | 53.32 | 22.94 | 32
198 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chuamasina Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00166/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
199 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Chuamosina Zone-A Mouza Arjunpur. SM/17696. | Assistant Engineer | Junior Engineer | BILL/00724/2024-2025 | BP-2024-25-196 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.35 | 0 | 0
200 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Chuamosina Zone -A Mouza Chuamosina JL no 17. SM /17696. | Assistant Engineer | Junior Engineer | BILL/00725/2024-2025 | BP-2024-25-197 | 28/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.6 | 0 | 0
201 | Bankura Mechanical | Brishnupur Sub-Division | Quotation as per WBSEDCL Procedure -A (2010) on turn key /full deposit basis for new service connection at Mouza Jhatabon under Bankura Mechanica Division ,PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00730/2024-2025 | BP-2024-25-207 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.74 | 0 | 0
202 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Exsistingt TW I,III,IV and V for Augmentation of Chuamosina and Adjoining mouza water supply scheme (Zone-A) Block-Bishnupurunder Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000143/2024-2025 | 486/BMD | 09/07/2024 | 120 | INDRAJIT MITRA | 31.42 | 20.67 | 40
203 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chuamasina (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000523/2023-2024 | 1887/BMD | 17/08/2023 | 1020 | SUNRISE ENGINEERING CORPORATION | 75.13 | 0 | 75
204 | Bankura Mechanical | Bankura Division | Proposed sub surface water based Parashibana pipe water supply scheme under Bankura Division, Block Chhatna, District: Bankura. | Assistant Engineer | Junior Engineer | BILL/00197/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
205 | Bankura Mechanical | Bankura Division | New service connection for PARASHIBANA water supply scheme under BMD PHE Dte. (SM CODE : SM/18043) | Assistant Engineer | Junior Engineer | BILL/00430/2024-2025 | BP-2024-25-104 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.47 | 0 | 0
206 | Bankura Mechanical | Bankura Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Proposed surface water based Parashibana under Water Supply Scheme Block- Chatna under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000449/2023-2024 | 1776/BMD | 01/08/2023 | 60 | RAJIB COMPANY | 45.33 | 32.16 | 11
207 | Bankura Mechanical | Bankura Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machinery and other electromagnetically accessories for Augmentation of sub Surface water base water supply Scheme for Parashibana to accommodate FHTC in Chhatna Block under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001071/2023-2024 | 3054/BMD | 12/03/2024 | 180 | RAJIB COMPANY | 25.63 | 0 | 40
208 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Beliatore & its adjoining mouzas Water Supply Scheme (Phase- I). | Assistant Engineer | Junior Engineer | BILL/00193/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
209 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for Augmentation of Beliatore and adjoining mouzas (Phase-I) under Bankura Mechanical Division PHE Dte Block- Barjora Dist -Bankura | Assistant Engineer | Junior Engineer | ORD/000574/2023-2024 | 2036/BMD | 01/09/2023 | 580 | M/S BIPUL BANERJEE | 45.43 | 20.43 | 45
210 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Bikna & its adjoining mouzas Water Supply Scheme (Phase- I). | Assistant Engineer | Junior Engineer | BILL/00192/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
211 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection at Domanbandi for augmenrtation of Bikna water supply scheme (SM/17291) under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00952/2024-2025 | BP-2024-25-233 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.07 | 0 | 0
212 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of Bikna and its adjoining mouzas piped water supply scheme (JJM Revision) Block-Bankura-II Dist -Bankura under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000559/2023-2024 | 1995/BMD | 28/08/2023 | 120 | M/S NABIN GOPAL SENGUPTA | 63.49 | 47.01 | 67
213 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries for Augmentation for Belatikri Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000138/2024-2025 | 444/BMD | 27/06/2024 | 604 | M.S. ENTERPRISE | 16.65 | 0 | 89
214 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement , installation of new charger panel , construction of neutralization pit , supply of XLPE cables , chlorinator items for Augmentation of Belatikari Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000164/2024-2025 | 506/BMD | 09/07/2024 | 120 | M/S SAJAHAN CHOWDHURY | 22.11 | 0 | 0
215 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System & construction of one no RBTW with other allied work at Belatikari water supply scheme under Sarenga Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000194/2025-2026 | 639/BMD | 11/07/2025 | 90 | DEBJYOTI BASU | 19.49 | 0 | 0
216 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Additional Work for Augmentation works for Belatikri, Zone-B water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000316/2024-2025 | 857/BMD | 29/08/2024 | 60 | M.S. ENTERPRISE | 1.18 | 1.18 | 100
217 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Belatikri Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000570/2023-2024 | 2027/BMD | 01/09/2023 | 914 | M.S. ENTERPRISE | 83.1 | 73.16 | 77
218 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Supply and delivery of different types of Drilling Martials in connection with Jal Jeevan Mission Program at Jhargram under Bankura Mechanical Division P.H.E Dte | DIC(D)_MMSD(D) | JE (M) | ORD/000577/2023-2024 | 2038/BMD | 01/09/2023 | 60 | CHAKRABORTY MINING & ENGINEERING. | 22.91 | 22.91 | 100
219 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W. in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D (D) under Bankura Mechanical Division PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000756/2023-2024 | 948/BMSD(D) | 17/11/2023 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 100
220 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D., P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000794/2023-2024 | 984/BMSD(D) | 01/12/2023 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 100
221 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling site in Bhelaidiha GP of Binpur-II Block of Jhargram District in Connection to JJM programme under Bankura Mechanical Division P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001022/2023-2024 | 20/BMSD(D) | 05/01/2024 | 20 | DEBJYOTI BASU | 0.97 | 0.97 | 100
222 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D., P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001103/2023-2024 | 1028/BMSD(D) | 15/12/2023 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 100
223 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division P.H.E. Dte | DIC(D)_MMSD(D) | JE (M) | ORD/001195/2023-2024 | 101/BMSD(D) | 31/01/2024 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 73
224 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling pin point place of Banksol, Barasol, Mahulbani, Hijla, Bansgar, Adgari etc site in Bhelaidiha gp, Binpur-II Block of Jhargram District in connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001246/2023-2024 | 250/BMSD(D) | 13/03/2024 | 122 | DEBJYOTI BASU | 0.97 | 0 | 100
225 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001278/2023-2024 | 254/BMSD(D) | 14/03/2024 | 75 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 100
226 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM Programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under B.M.D, P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001279/2023-2024 | 264/BMSD(D) | 15/03/2024 | 15 | CHAKRABORTY MINING & ENGINEERING. | 0.8 | 0 | 100
227 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for chiltore and its Adjoining mouza water supply scheme under jal jeevan mission programme | Assistant Engineer | Junior Engineer | BILL/00207/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
228 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries and allied works for Augmentation of Chiltore water supply scheme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 154/BMD | 30/04/2025 | 90 | DEBJYOTI BASU | 10.26 | 0 | 0
229 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Supply and installation of submersible pumping machinery and Voltage Stabilizer with allied items for Augmentation for Chiltore water supply scheme under Sarenga water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000173/2024-2025 | 515/BMD | 09/07/2024 | 530 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 15.77 | 0 | 60
230 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Construction of one no RBTW with providing and installation of Neutralization System , installation of 1 no Submersible Pump Motor set other work at Chiltore water supply scheme under Sarenga Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000193/2025-2026 | 638/BMD | 11/07/2025 | 90 | GOENKA ENTERPRISE | 33.03 | 0 | 0
231 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low lift pumping machineries and other electromechanical accessories for Augmentation works for Chiltore and its Adjoining mouzas water supply scheme under Jal Jeevan Mission programe under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000717/2023-2024 | 2174/BMD | 30/10/2023 | 850 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 62.99 | 54.24 | 80
232 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Kushmuri Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00177/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
233 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Paharpur boosting Tw site of Karisunda water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00986/2024-2025 |  | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.08 | 0 | 0
234 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Pratapmath ( Khusmuri Zone-B) | Assistant Engineer | Junior Engineer | BILL/01333/2024-2025 | BP-2024-25-333 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.34 | 0 | 0
235 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kushmuri (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000610/2023-2024 | 2084/BMD | 12/09/2023 | 1140 | GOENKA ENTERPRISE | 70.65 | 33.7 | 60
236 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement for Augmentation for Baricha Zone -A water supply scheme under Baricha water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer |  | ORD/000331/2024-2025 | 868/BMD | 29/08/2024 | 120 | M/S TARUN KUMAR PATRA | 4.84 | 0 | 0
237 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation for Boricha Zone-A and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer |  | ORD/000572/2023-2024 | 2028/BMD | 01/09/2023 | 1080 | S.P. CONSTRUCTION | 96.37 | 78.56 | 80
238 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00208/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
239 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation work for Dhemusunia (Zone IV) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000879/2024-2025 | 2039/BMD | 07/03/2025 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 95.37 | 0 | 10
240 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Miscellaneous work for Gaseous Chlorination System at Head work site for Augmentation works for Dhemushunya (Zone-IV) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division PHE Dte, | Assistant Engineer | Junior Engineer | ORD/001096/2023-2024 | 3071/BMD | 12/03/2024 | 600 | EASTERN INDIA SALES & SERVICE | 14.32 | 13.41 | 80
241 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Khiri W/ S schme | Assistant Engineer | Junior Engineer | BILL/00418/2024-2025 | BP-2024-25-94 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.68 | 0 | 0
242 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Khiri W/S scheme | Assistant Engineer | Junior Engineer | BILL/00419/2024-2025 | BP-2024-25-95 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.88 | 0 | 0
243 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Khiri Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000147/2025-2026 | 442/BMD | 10/06/2025 | 90 | RAJIB COMPANY | 11.88 | 0 | 0
244 | Bankura Mechanical | Brishnupur Sub-Division | New service connection of P/H-II of Lowgram W/S scheme | Assistant Engineer | Junior Engineer | BILL/00523/2024-2025 | BP-2024-25-140 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.52 | 0 | 0
245 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Laugram Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000145/2025-2026 | 440/BMD | 10/06/2025 | 90 | INDRAJIT MITRA | 12.37 | 0 | 0
246 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Pabra piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Saltora , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 153/BMD | 30/04/2025 | 90 | M/S DAS AND SARKAR ENTERPRISE | 9.72 | 0 | 0
247 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at clear water pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1408/BMD | 18/07/2023 | 420 | ORIENTAL ENGINEERING CO. | 216.67 | 206.36 | 95
248 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of VT pumps at Intake pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura. | Assistant Engineer | Junior Engineer | ORD/000310/2023-2024 | 1409/BMD | 18/07/2023 | 60 | ORIENTAL ENGINEERING CO. | 110.62 | 105.21 | 95
249 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Replacement of Valves on delivery line at Intake and clear water pumping station at Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. Block Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000611/2023-2024 | 2085/BMD | 12/09/2023 | 300 | M/S NABIN GOPAL SENGUPTA | 48.09 | 45.89 | 97
250 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 100KVA to 138 KVA at 11KV having Consumer ID : 942304300 at the premises at Jhantipahari water supply scheme(Intake), Jhantipahari, Bankura. | Assistant Engineer | Junior Engineer | BILL/00958/2024-2025 | BP-2024-25-236 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.23 | 0 | 0
251 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation of sub Surface water base water supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Mechanical Division PHE Dte, Dist :Bankura under JJM. | Assistant Engineer | Junior Engineer | ORD/000487/2023-2024 | 1818/BMD | 09/08/2023 | 180 | EASTERN INDIA SALES & SERVICE | 176.93 | 116.89 | 45
252 | Bankura Mechanical | Brishnupur Sub-Division | Bhat Pushkarini Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01514/2023-2024 | BP-2023-24-118 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.76 | 0 | 0
253 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Bhat Pushkarini piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 772/BMD | 24/04/2023 | 180 | PRADIP KUMAR DHABAL | 39.43 | 20.99 | 54
254 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Karachmoni Khayrasol TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/12420) | Assistant Engineer | Junior Engineer | BILL/01255/2024-2025 | BP-2024-25-326 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0
255 | Bankura Mechanical | Brishnupur Sub-Division | Karachmani Khayarsol Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01515/2023-2024 | BP-2023-24-116 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0
256 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Karachmani Khayarsol piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 654/BMD | 17/04/2023 | 715 | UNITED TRADERS | 31.37 | 13.99 | 50
257 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for proposed CWR water based Karachmani Khayarsol PWSS piped water supply scheme Block Sonamukhi under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000147/2024-2025 | 490/BMD | 09/07/2024 | 120 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 24.25 | 0 | 0
258 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 1B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000235/2023-2024 | 1121/BMD | 24/05/2023 | 30 | M/S DE ENGINEERING CONCERN | 2.28 | 0 | 0
259 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Jamkuri w/s (T/W-II) at Patrasayer block under BMD PHE Dte.(SM/14007) | Assistant Engineer | Junior Engineer | BILL/00366/2025-2026 |  | 12/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6 | 0 | 0
260 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Jamkuri (T/W-II) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/14007) | Assistant Engineer | Junior Engineer | BILL/01466/2024-2025 | BP-2024-25-365 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0
261 | Bankura Mechanical | Brishnupur Sub-Division | Jamkuri Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01667/2023-2024 | BP-2023-24-184 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.94 | 0 | 0
262 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Jamkuri Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000025/2025-2026 | 236/BMD | 14/05/2025 | 90 | KINGKINI TRADERS | 11.67 | 0 | 0
263 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Makarandapur Piped Water Supply Scheme t/w-II ,Makarandapur(Adhakata) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00131/2024-2025 | BP-2024-25-23 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.34 | 0 | 0
264 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Makarandapur Piped Water Supply Scheme t/w-I ,Makarandapur(Magura) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00132/2024-2025 | BP-2024-25-24 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.8 | 0 | 0
265 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Markandapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000186/2025-2026 | 458/BMD | 10/06/2025 | 90 | M/S SOMA ENTERPRISES | 11.86 | 0 | 0
266 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Banna Piped Water Supply Scheme t/w-II ,Banna (Lokepur) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00137/2024-2025 | BP-2024-25-19 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0
267 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Banna Piped Water Supply Scheme t/w-III ,Banna (Gelia Ruidas Para) of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00139/2024-2025 | BP-2024-25-20 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.57 | 0 | 0
268 | Bankura Mechanical | Brishnupur Sub-Division | Banna Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01496/2023-2024 | BP-2023-24-97 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
269 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Banna Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000181/2025-2026 | 453/BMD | 10/06/2025 | 90 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 12.93 | 0 | 0
270 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Deshra W/S Scheme. | Assistant Engineer | Junior Engineer | BILL/01349/2024-2025 | BP-2024-25-348 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.86 | 0 | 0
271 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Deshra W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01352/2024-2025 | BP-2024-25-349 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 25.15 | 0 | 0
272 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Deshra Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000143/2025-2026 | 438/BMD | 10/06/2025 | 90 | KINGKINI TRADERS | 12.94 | 0 | 0
273 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00145/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
274 | Bankura Mechanical | Bankura Sadar Sub-Division | Load extension for Arjunpur augmentation OHR site (SM/16966) of Bankura I,II & Barjora water supply scheme under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01236/2024-2025 | BP-2024-25-311 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
275 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Arjunpur ( Zone-N) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000163/2024-2025 | 505/BMD | 09/07/2024 | 120 | RAJIB COMPANY | 8.79 | 0 | 0
276 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Arjunpur (Zone-N) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 1465/BMD | 18/07/2023 | 60 | DAS ENTERPRISE | 81.56 | 48.97 | 71
277 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-5B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000241/2023-2024 | 1126/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
278 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kalayani (Zone-B) & Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000552/2023-2024 | 1988/BMD | 28/08/2023 | 120 | R.N.S. TRADING | 48.56 | 0 | 0
279 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Kalyani Zone -B and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001097/2023-2024 | 3072/BMD | 12/03/2024 | 720 | P.K. ENGINEERING | 47.94 | 0 | 65
280 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01629/2023-2024 | BP-2023-24-157 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.2 | 0 | 0
281 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of H/L and L/L Pumping machinery with other elector mechanical accessories for Augmentation of Chingani and Adjoining mouza water supply scheme at mouza Dhengasole under Bankura Mechanical Division, PHE Dte. Block Onda, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000122/2024-2025 | 432/BMD | 27/06/2024 | 360 | UNITED TRADERS | 40.96 | 0 | 70
282 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chingani & Adjoining mouza water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000551/2023-2024 | 1987/BMD | 28/08/2023 | 120 | MITRA ENTERPRISE | 35.6 | 24.58 | 60
283 | Bankura Mechanical | Brishnupur Sub-Division | Quotation as per WBSEDCL procedure -A(2010) on turn key/full deposit basis for new service connection at Mouza Amrel of Ajodhya w/s scheme .SM/17246 | Assistant Engineer | Junior Engineer | BILL/00031/2024-2025 | BP-2024-25-14 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0
284 | Bankura Mechanical | Brishnupur Sub-Division | Quotation as per WBSEDCL Procedure -A(2010) on turn key /full deposit basis for new service connection at Mouza Paikpara of Ajodhya W/S scheme. | Assistant Engineer | Junior Engineer | BILL/00112/2024-2025 | BP-2024-25-15 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.52 | 0 | 0
285 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Ajodhya Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00172/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
286 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Ajodhya piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000456/2023-2024 | 1782/BMD | 01/08/2023 | 720 | ABHIJIT MUKHERJEE | 52.17 | 32.83 | 63
287 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High Lift pumping machineries and other electromechanical accessories at CWPH for Augmentation of Ajodhya and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001098/2023-2024 | 3073/BMD | 12/03/2024 | 600 | TAPAN KUMAR SARKAR | 39.24 | 0 | 65
288 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for load enhancement at mouza Kotalpur of Aguriband Punisole Z-B ws scheme under BMD ,PHED. | Assistant Engineer | Junior Engineer | BILL/00290/2024-2025 | BP-2024-25-62 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.08 | 0 | 0
289 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineryes and H.T Switch Gear with allied works for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- B) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000373/2024-2025 | 1002/BMD | 24/09/2024 | 360 | PRADIP KUMAR DHABAL | 50.06 | 0 | 45
290 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-B) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000546/2023-2024 | 1982/BMD | 28/08/2023 | 120 | S.DUTTA | 45.88 | 29.29 | 64
291 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Additional Tubewell for Augmentation works for Aguribandh Punisole (Zone C) Water Supply Scheme in the Block Onda under Bankura Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000874/2024-2025 | 2036/BMD | 07/03/2025 | 120 | SWAPAN ENTERPRISE | 17.36 | 0 | 0
292 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection charge for CHINABARI water supply scheme under BMD PHE Dte. (SM CODE : SM/17705) | Assistant Engineer | Junior Engineer | BILL/00630/2026-2027 |  | 10/06/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.46 | 0 | 0
293 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for BIRSINGPUR TW-2 (JL NO-48, PLOT-147)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00014/2024-2025 | BP-2024-25-16 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0
294 | Bankura Mechanical | Brishnupur Sub-Division | Birsingpur Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01517/2023-2024 | BP-2023-24-112 | 22/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.1 | 0 | 0
295 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Birsingpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000031/2023-2024 | 658/BMD | 17/04/2023 | 1080 | M/S S G ENTERPRISE | 40.22 | 13.3 | 33
296 | Bankura Mechanical | Khatra Sub-Division | New service connection at CWR site of Tilaboni Piped Water Supply Scheme Mouza-Jamda,Vill-Tilaboni GP- Lakshmisagar JL No-38, Plot no.-67 of Simlapal block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00985/2024-2025 | BP-2024-25-244 | 21/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.04 | 0 | 0
297 | Bankura Mechanical | Khatra Sub-Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer | BILL/01658/2023-2024 | BP-2023-24-180 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.93 | 0 | 0
298 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for proposed Sub surface water based Tilabani piped water supply scheme Block Simlapal under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000617/2023-2024 | 2089/BMD | 12/09/2023 | 720 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 38.3 | 0 | 60
299 | Bankura Mechanical | Brishnupur Sub-Division | Jamuna Band Pipe Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00173/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
300 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Jamunabundh TW-I W/S scheme under BMD.PHE Dte. SM/18037 | Assistant Engineer | Junior Engineer | BILL/00497/2024-2025 | BP-2023-24- | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.68 | 0 | 0
301 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Jamunabundh T/W-II.SM/18037 | Assistant Engineer | Junior Engineer | BILL/01354/2024-2025 | BP-2024-25-330 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.18 | 0 | 0
302 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Jamuna Bandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000442/2023-2024 | 1771/BMD | 01/08/2023 | 692 | M/S BIPUL BANERJEE | 36.9 | 20.14 | 65
303 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00175/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
304 | Bankura Mechanical | Brishnupur Sub-Division | Load Enhancement charges for SASPUR ZONE-B Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00721/2024-2025 | BP-2024-25-198 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
305 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Ashwinpur Boosting Tw Site of Sashpur Zone B water supply scheme under B.M.D PHE Dte.(SM/17421) | Assistant Engineer | Junior Engineer | BILL/01136/2024-2025 | BP-2024-25-283 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.07 | 0 | 0
306 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01618/2023-2024 | BP-2023-24-152 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.52 | 0 | 0
307 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sashpur (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000530/2023-2024 | 1894/BMD | 17/08/2023 | 655 | M/S SAJAHAN CHOWDHURY | 75.78 | 42.72 | 60
308 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling pin point place of Banksol(T/w-II), Barasol (T/w-II) etc site in Bhelaidiha gp, Binpur-II Block of Jhargram District in Connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000334/2024-2025 | 548/BMSD(D) | 19/06/2024 | 183 | DEBJYOTI BASU | 0.97 | 0 | 0
309 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Supply and delivery of Cutting tools, Lubricants etc for KLR Rig machine in connection with Jal Jeevan Mission programme at Jhargram under Bankura Mechanical Division ,PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000615/2023-2024 | 2087/BMD | 12/09/2023 | 120 | SUDIP ENGINEERING CO | 23.85 | 23.85 | 100
310 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001226/2023-2024 | 252/BMSD(D) | 13/03/2024 | 18 | CHAKRABORTY MINING & ENGINEERING. | 0.97 | 0 | 100
311 | Bankura Mechanical | Midnapur Mechanical (Drill.) Sub-Division | Acceptance cum Formal work order for the work of Repairing & Rectification Truck portion and air valve of Compressor at KLR truck mounted Rig machine in connection of Jhargram JJM programme under B.M.S.D.(D) P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001238/2023-2024 | 11/BMSD(D) | 03/01/2024 | 182 | PRADIP KUMAR DHABAL | 0.73 | 0 | 100
312 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Ratanpur( Zone-A) Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000557/2023-2024 | 1993/BMD | 28/08/2023 | 120 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 33.54 | 25.39 | 76
313 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Ratanpur Zone -A and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001100/2023-2024 | 3075/BMD | 12/03/2024 | 120 | INDRAJIT MITRA | 15.85 | 4.2 | 100
314 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | BILL/00217/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
315 | Bankura Mechanical | Khatra Sub-Division | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 900 | A.K.INDUSTRIES | 127.79 | 0 | 85
316 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Baricha Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000576/2023-2024 | 2037/BMD | 01/09/2023 | 1140 | S.P. CONSTRUCTION | 83.04 | 43.68 | 39
317 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00212/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
318 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01659/2023-2024 | BP-2023-24-178 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.83 | 0 | 0
319 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible Pump Motor set other allied work at Dubrajpur Zone-A & Dubrajpur Zone-B water supply scheme under Simlapal Block under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000199/2025-2026 | 645/BMD | 11/07/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 27.64 | 0 | 0
320 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of water supply scheme Dubrajpur Zone-A and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2024/BMD | 01/09/2023 | 120 | ABHIJIT MUKHERJEE | 70.19 | 48.69 | 65
321 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro allied electro-mechanical accessories for Augmentation for Dubrajpur Zone-A piped water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Simlapal , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001091/2023-2024 | 3066/BMD | 12/03/2024 | 120 | ABHIJIT MUKHERJEE | 26.71 | 22.72 | 35
322 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Dubrajpur Zone-A water supply scheme under Dubrajpur water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001093/2023-2024 | 3068/BMD | 12/03/2024 | 480 | JAL PRAVAHIKA PVT LTD | 40.01 | 34.66 | 70
323 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for INDUS BPHC CAMPUS (JL NO-14, PLOT-1947)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00012/2024-2025 | BP-2024-25-8 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0
324 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for INDUS BPHC CAMPUS (JL NO-14, PLOT-1947)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00013/2024-2025 |  | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0
325 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Indas Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00188/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
326 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for Augmentation of Indas water supply scheme under indus Block under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000117/2024-2025 | 428/BMD | 27/06/2024 | 300 | M/S BIPUL BANERJEE | 35.24 | 25.77 | 40
327 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Birdabanpur Tw-1 Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00953/2024-2025 | BP-2024-25-225 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5 | 0 | 0
328 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Brindabanpur Tw-2 water supply scheme under Bankura Mechanical Division PHE DTE. | Assistant Engineer | Junior Engineer | BILL/00954/2024-2025 | BP-2024-25-226 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.45 | 0 | 0
329 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Birdabanpur TW3 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/ | Assistant Engineer | Junior Engineer | BILL/01246/2024-2025 | BP-2024-25-320 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.51 | 0 | 0
330 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Brindabanpur Piped Water Supply Scheme under BMD PHE Dte Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000061/2025-2026 | 257/BMD | 14/05/2025 | 90 | INDRAJIT MITRA | 12.68 | 0 | 0
331 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for ghoradanga(T/W-I) water supply scheme under BMD PHE Dte.(SM/18611) | Assistant Engineer | Junior Engineer | BILL/01356/2024-2025 | BP-2024-25-327 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
332 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Ghoradanga (T/W-II) water supply scheme under BMD PHE Dte.(SM/18611) | Assistant Engineer | Junior Engineer | BILL/01464/2024-2025 | BP-2024-25-360 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.96 | 0 | 0
333 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for newly sunk TW No I, TW No II of Ghora danga Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000114/2024-2025 | 425/BMD | 27/06/2024 | 600 | RAJIB COMPANY | 50.06 | 0 | 30
334 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for T/W III of Rampur water supply scheme at Patrasayer Block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01137/2024-2025 | BP-2024-25-275 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.91 | 0 | 0
335 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for P/H II of Rampur water supply scheme at Patrasayer Block (SM/18349) | Assistant Engineer | Junior Engineer | BILL/01138/2024-2025 | BP-2024-25-276 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0
336 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for P/H no I of Rampur Water supply scheme at Patrasayer Block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01139/2024-2025 | BP-2024-25-277 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.11 | 0 | 0
337 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Rampur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000039/2025-2026 | 243/BMD | 14/05/2025 | 90 | CHAKRABORTY MINING & ENGINEERING. | 12.22 | 0 | 0
338 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Rampur Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000249/2023-2024 | 1169/BMD | 01/06/2023 | 1080 | ORIENTAL ENGINEERING CO. | 68.63 | 23.1 | 33
339 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Parsola, Zone-A and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01663/2023-2024 | BP-2023-24-173 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.43 | 0 | 0
340 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation Submersible Pump Motor set, Neutralization System with other work at Parsola Zone -A water supply scheme under BMD PHE Dte | Assistant Engineer | Junior Engineer | ORD/000200/2025-2026 | 646/BMD | 11/07/2025 | 90 | WEST BENGAL ENGINEERING CO. | 19.42 | 0 | 0
341 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of illumination arrangement for Augmentation for Parsola Zone -A water supply scheme under Parsala water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000324/2024-2025 | 865/BMD | 29/08/2024 | 120 | M/S DE ENGINEERING CONCERN | 5.93 | 0 | 0
342 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of water supply scheme for Parsola Zone-A and its adjoining mouzas under simlapal water (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000992/2023-2024 | 2852/BMD | 09/02/2024 | 360 | R.N.S. TRADING | 122.02 | 0 | 35
343 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Barageria W/S scheme | Assistant Engineer | Junior Engineer | BILL/00422/2024-2025 | BP-2024-25-99 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.36 | 0 | 0
344 | Bankura Mechanical | Brishnupur Sub-Division | New service connection charge at P/H-II of Bargeria W/S scheme | Assistant Engineer | Junior Engineer | BILL/00530/2024-2025 | BP-2024-25-139 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.79 | 0 | 0
345 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Baragaria Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 2066/BMD | 11/09/2023 | 1080 | M/S SOMA ENTERPRISES | 68.06 | 34.69 | 37
346 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Biur-Betur (T/W-I) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/18754) | Assistant Engineer | Junior Engineer | BILL/01485/2024-2025 | BP-2024-25-368 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.15 | 0 | 0
347 | Bankura Mechanical | Brishnupur Sub-Division | Biur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01672/2023-2024 | BP-2023-24-174 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
348 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk at TW No I and T.W No II of Biur piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000113/2024-2025 | 424/BMD | 27/06/2024 | 360 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 49.86 | 0 | 33
349 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Nandamohanpur TW1 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/19178) | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-2024-25-317 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.49 | 0 | 0
350 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Nandamohanpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/19178) | Assistant Engineer | Junior Engineer | BILL/01251/2024-2025 | BP-2024-25-318 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.67 | 0 | 0
351 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Nandamohanpur TW3 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/19178) | Assistant Engineer | Junior Engineer | BILL/01252/2024-2025 | BP-2024-25-319 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.95 | 0 | 0
352 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandamohonpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000179/2025-2026 | 452/BMD | 10/06/2025 | 90 | M/S BIPUL BANERJEE | 12.36 | 0 | 0
353 | Bankura Mechanical | Khatra Sub-Division | New service connection at JOVI village, Extension of Ghagra IBS Piped Water Supply Scheme's on-line boosting pump, Rudra gp of Ranibandh block under BMD PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00335/2025-2026 | 281/W-1714 | 19/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.32 | 0 | 0
354 | Bankura Mechanical | Khatra Sub-Division | New service connection at Dhankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01477/2024-2025 | BP-2024-25-369 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.42 | 0 | 0
355 | Bankura Mechanical | Khatra Sub-Division | New Service connection at Dhankura IBS OHR | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01479/2024-2025 |  | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.95 | 0 | 0
356 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation works of gaseous chlorination system and neutralisation system at Mukutmanipur WTP(old) site under Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000006/2025-2026 | 141/BMD | 30/04/2025 | 360 | GOPAL CHANDRA CHOWDHURY | 41.17 | 0 | 90
357 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Supply delivery & Installation of submersible Pump motor set & HSC Pump at CWR for Augmentation of WTP under Khatra-Hirbandh-Ranibandh Surface Water based piped water supply scheme under Bankura Mechanical Division, PHE Dte.Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000007/2025-2026 | 142/BMD | 30/04/2025 | 90 | MAHADEV ENTERPRISE | 94.53 | 0 | 0
358 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation works of gaseous chlorination system and nutralisation system with related allied works at WTP of Hatikheda (Zone I), Rudra(Zone J), Dhankura(Zone L), Purnapani (Zone M), Madandihi (Zone O), Nachna(Zone P), under Khatra Hirbandh Ranibandh water supply scheme under BMD PHE DTE. Dist- Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000037/2025-2026 | 242/BMD | 14/05/2025 | 90 | DEY ENTERPRISE | 58.21 | 0 | 0
359 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Proposed surface water based IBS of Dhankura for Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) Block- Ranibandh under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000149/2024-2025 | 492/BMD | 09/07/2024 | 480 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 96.64 | 0 | 41
360 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Rudra (Zone-J) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000198/2025-2026 | 644/BMD | 11/07/2025 | 90 | TAPAN KUMAR SARKAR | 11.33 | 0 | 0
361 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of high lift and low lift Pumping machineries with other electro-mechanical accessories at tail end & CWR site for Augmentation works for Purnapani Augmentation works for Zone-I (Hatikheda), Zone-J (Rudra), Zone-L (Dhankura), Zone-M (Purnapani), Zone-O (Madandihi) and Zone-P (Nachna) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000171/2024-2025 | 513/BMD | 09/07/2024 | 120 | EASTERN INDIA SALES & SERVICE | 56.1 | 0 | 0
362 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter with related allied works at Hatikheda (Zone-I), Rudra(Zone-J),Dhankura (Zone-L),Purnapani (Zone-M), Madandihi (Zone-O),Nachna (Zone-P), under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000415/2025-2026 | 2060/BMD | 18/09/2025 | 90 | ORIENTAL ENGINEERING CO. | 200.39 | 0 | 0
363 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Joypur Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00124/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
364 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Katul of Joypur Piped Water Supply Scheme t/w-III ,Katul of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00381/2024-2025 | BP-2024-25-89 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.27 | 0 | 0
365 | Bankura Mechanical | Brishnupur Sub-Division | Joypur Pump house-II | Assistant Engineer | Junior Engineer | BILL/01508/2023-2024 | BP-2023-24-108 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.59 | 0 | 0
366 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmantation of Joypur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Joypur Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000425/2023-2024 | 1686/BMD | 27/07/2023 | 859 | PRADIP KUMAR DHABAL | 39.53 | 30.88 | 30
367 | Bankura Mechanical | Brishnupur Sub-Division | Ghagara Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01497/2023-2024 | BP-23-24 -110 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.38 | 0 | 0
368 | Bankura Mechanical | Bankura Sadar Sub-Division | Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of water supply scheme for Ashna (Karjuridanga) and adjoiningmouza under Bankura Mechanical Division, PHE Dte., Block: Bankura-I Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000535/2024-2025 | 449/BMD | 28/06/2024 | 180 | MAHADEV ENTERPRISE | 127.99 | 0 | 30
369 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection for Atra(T/W-I) water supply scheme at patrasayer block under BMD PHE Dte.(SM/14000) | Assistant Engineer | Junior Engineer | BILL/01469/2024-2025 | BP-2024-25-366 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.5 | 0 | 0
370 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at Atra (T/W-II) water supply scheme at patrasayer block under BMD PHE Dte.(SM/14000) | Assistant Engineer | Junior Engineer | BILL/01470/2024-2025 | BP-2024-25-367 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0
371 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Atra Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000026/2025-2026 | 237/BMD | 14/05/2025 | 90 | M/S D. PALIT AND CO. | 11.66 | 0 | 0
372 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Atra Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000168/2023-2024 | 880/BMD | 04/05/2023 | 1080 | RAJIB COMPANY | 47 | 18.97 | 40
373 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-8B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000245/2023-2024 | 1130/BMD | 24/05/2023 | 30 | SUTRADHAR TRADERS | 2.39 | 0 | 0
374 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Kalyanpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14010) | Assistant Engineer | Junior Engineer | BILL/01253/2024-2025 | BP-2024-25-325 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.71 | 0 | 0
375 | Bankura Mechanical | Brishnupur Sub-Division | Kalyanpur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01513/2023-2024 | BP-2023-24-115 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0
376 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Kalyanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 870/BMD | 04/05/2023 | 180 | INDRAJIT MITRA | 31.37 | 14.56 | 46
377 | Bankura Mechanical | Brishnupur Sub-Division | Jadabnagar T/W-I | Assistant Engineer | Junior Engineer | BILL/00848/2023-2024 | BP-2023-24-41 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.08 | 0 | 0
378 | Bankura Mechanical | Brishnupur Sub-Division | Jadabnagar T/W-II | Assistant Engineer | Junior Engineer | BILL/00849/2023-2024 | BP-2023-24-42 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.87 | 0 | 0
379 | Bankura Mechanical | Brishnupur Sub-Division | Jadabnagar T/W-III | Assistant Engineer | Junior Engineer | BILL/00850/2023-2024 | BP-2023-24-43 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.56 | 0 | 0
380 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Jadabnagar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Joypur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000165/2023-2024 | 877/BMD | 04/05/2023 | 1035 | EASTERN INDIA SALES & SERVICE | 59.05 | 30.27 | 55
381 | Bankura Mechanical | Brishnupur Sub-Division | New sevice connection at Hamirpur-II for Dhagoria water supply scheme at Patrasater block under BMD PHE Dte.(SM/15023) | Assistant Engineer | Junior Engineer | BILL/01467/2024-2025 | BP-2024-25-364 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.31 | 0 | 0
382 | Bankura Mechanical | Brishnupur Sub-Division | Dhagaria Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01670/2023-2024 | BP-2023-24-182 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.51 | 0 | 0
383 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Dhagaria Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000035/2025-2026 | 240/BMD | 14/05/2025 | 90 | M/S SOMA ENTERPRISES | 11.67 | 0 | 0
384 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Dhagaria Piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrashayar , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 769/BMD | 24/04/2023 | 1080 | M/S SWAPAN BANERJEE | 47.1 | 27.72 | 58
385 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Kotulpur Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00125/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
386 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at P/H-IV of Kotulpur W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01350/2024-2025 | BP-2024-25-353 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.84 | 0 | 0
387 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at Kotulpur H/W site under Augmentation of Kotulpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000119/2024-2025 | 1070/BMSD | 05/07/2024 | 119 | PRADIP KUMAR DHABAL | 4.38 | 0 | 100
388 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kotulpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000176/2023-2024 | 936/BMD | 12/05/2023 | 1080 | M/S SOMA ENTERPRISES | 45.85 | 34.16 | 75
389 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | Assistant Engineer | Junior Engineer | BILL/00154/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
390 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL, Quotation Bill for new power connection at Sahebdanga Pump House augmentation work under Barjora (Left out Mouza) (zone-IA ) water supply scheme (SM/16974) | Assistant Engineer | Junior Engineer | BILL/00723/2024-2025 | BP-2024-25-200 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.63 | 0 | 0
391 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IA) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 519/BMD | 09/07/2024 | 120 | SINHA ELECTRICALS | 11.28 | 0 | 0
392 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IA) under Bankura Mechanical Division, PHED. | Assistant Engineer | Junior Engineer | ORD/000454/2023-2024 | 1780/BMD | 01/08/2023 | 120 | SUNRISE ENGINEERING CORPORATION | 81.75 | 0 | 30
393 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC cum PDB and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I) (Zone IA) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001034/2023-2024 | 2966/BMD | 29/02/2024 | 180 | TAPAN KUMAR SARKAR | 28.66 | 20.01 | 68
394 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection of Biradihi OHR zone-C Piped Water Supply Scheme at t/w-I ,Moshiara of Hirbandh block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00537/2024-2025 | BP-2024-25-145 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.49 | 0 | 0
395 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories and providing spares of existing gaseous chlorination system for Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000140/2024-2025 | 483/BMD | 09/07/2024 | 600 | TAPAN KUMAR SARKAR | 27.35 | 0 | 20
396 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Biradihi (Zone-C) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000195/2025-2026 | 641/BMD | 11/07/2025 | 90 | ABHIJIT MUKHERJEE | 22.82 | 0 | 0
397 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Benda water supply scheme | Assistant Engineer | Junior Engineer | BILL/00186/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
398 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Mouza Ranikhamar of Benda w/s scheme.SM/17244 | Assistant Engineer | Junior Engineer | BILL/00538/2024-2025 | BP-2024-25-144 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.15 | 0 | 0
399 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Additional quotation for full deposit work at mouza Ranikhamar ,JL no 53, Pl no 514 ,Dwarika, Bishnupur.SM/17244 | Assistant Engineer | Junior Engineer | BILL/01238/2024-2025 | BP-2024-25-310 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.68 | 0 | 0
400 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Zone-II CWR site of Kathjuridanga w/s scheme at Bidisha Nagar Mouza-Ailakandi.SM/17244 | Assistant Engineer | Junior Engineer | BILL/01471/2024-2025 | BP-2024-25-362 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.02 | 0 | 0
401 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Deuli ,Benda W/S scheme.SM/17244 | Assistant Engineer | Junior Engineer | BILL/01602/2024-2025 |  | 17/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.69 | 0 | 0
402 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Benda and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000137/2024-2025 | 443/BMD | 27/06/2024 | 360 | UNITED TRADERS | 21.56 | 0 | 100
403 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Benda piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000515/2023-2024 | 1880/BMD | 17/08/2023 | 840 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 65.93 | 39.69 | 48
404 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service connection for Basudebpur TW-I water supply scheme of sonamukhi block under Bankura Mechanical Division P.H.E Dte.(SM/16944) | Assistant Engineer | Junior Engineer | BILL/01180/2024-2025 | BP-2024-25-300 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0
405 | Bankura Mechanical | Brishnupur Sub-Division | New three phase Service Connection for Basudebpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/16944) | Assistant Engineer | Junior Engineer | BILL/01181/2024-2025 | BP-2024-25-301 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.86 | 0 | 0
406 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Basudebpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000030/2023-2024 | 657/BMD | 17/04/2023 | 180 | RAJIB COMPANY | 40.25 | 19.17 | 48
407 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Baragari (Zone- IIA) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00210/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
408 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter Motorized Sulice valve with related allied works at Baragari (Zone-G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000023/2025-2026 | 234/BMD | 14/05/2025 | 90 | JAL PRAVAHIKA PVT LTD | 28.18 | 0 | 0
409 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer (Contractual) | BILL/00201/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
410 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED SUB SURFACE WATER BASED KHAYERBANI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer (Contractual) | BILL/01662/2023-2024 | BP-2023-24-177 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
411 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Khayerbani piped water supply scheme Block Khatra under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000566/2023-2024 | 2033/BMD | 01/09/2023 | 597 | RAJIB COMPANY | 45.28 | 21.8 | 48
412 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00178/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
413 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01624/2023-2024 | BP-2023-24-151 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.77 | 0 | 0
414 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical accessories at boosting P.H for augmentation of Betanal Zone A water supply scheme under B.M.D. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2025-2026 | 151/BMD | 30/04/2025 | 90 | ABHIJIT MUKHERJEE | 18.95 | 0 | 0
415 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and Installation of Valves with other electro-mechanical accessories at Betanal CWR pipe line based water supply schemes of Indus under B.M.D, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2024-2025 | 777/BMD | 20/08/2024 | 347 | M/S SWAPAN BANERJEE | 12.56 | 0 | 95
416 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Betanal Zone-A piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000516/2023-2024 | 1881/BMD | 17/08/2023 | 684 | EASTERN INDIA SALES & SERVICE | 48.95 | 14.71 | 45
417 | Bankura Mechanical | Khatra Sub-Division | PROPOSED SUB SURFACE WATER BASED PIRRA BAKRA PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : KHATRA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer | BILL/00200/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
418 | Bankura Mechanical | Khatra Sub-Division | New service connection at PH-II of Pirra bankra W/S scheme. | Assistant Engineer | Junior Engineer | BILL/00357/2025-2026 | 107/W-612 | 01/08/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.99 | 0 | 0
419 | Bankura Mechanical | Khatra Sub-Division | New service connection at Pirrabakra. | Assistant Engineer | Junior Engineer | BILL/01475/2024-2025 | BP-2024-25-359 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.6 | 0 | 0
420 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Pirra Bakra piped water supply scheme Block Khatra under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000571/2023-2024 | 2035/BMD | 01/09/2023 | 960 | M/S BIPUL BANERJEE | 35.44 | 22.61 | 65
421 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Low lift Pumping machineries with other electro mechanical accessories for 2nd no tubewell for proposed ground water based Pirra Bankra piped water supply scheme Block Khatra under Bankura Mechanical Division, PHE Dte. Block Khatra , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000881/2024-2025 | 2041/BMD | 07/03/2025 | 240 | M/S BIPUL BANERJEE | 9.91 | 0 | 60
422 | Bankura Mechanical | Bankura Sadar Sub-Division | Proposed Ground water based Kantabari pipe water supply scheme under Bankura Division, Block - Onda, Dist - Bankura. | Assistant Engineer | Junior Engineer | BILL/00134/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.5 | 0 | 0
423 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electro mechanical accessories at CWR site at mouza Punisole for Augmentation of Aguriband Punisole (Zone E) and Adj. mouzas piped water supply scheme in the Block Onda under Bankura Mechanical Division PHE Dte Block Bankura-I Dist Bankura | Assistant Engineer | Junior Engineer | ORD/001009/2024-2025 | 2042/BMD | 07/03/2025 | 120 | M.S. ENTERPRISE | 67.43 | 0 | 0
424 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Water Supply Scheme for Dubrajpur, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01657/2023-2024 | BP-2023-24-179 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.16 | 0 | 0
425 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories in boosting site and existing pump house for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000146/2024-2025 | 489/BMD | 09/07/2024 | 360 | PRADIP KUMAR DHABAL | 25.33 | 0 | 20
426 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Dubrajpur Zone-B water supply scheme under Dubrajpur water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000266/2024-2025 | 774/BMD | 20/08/2024 | 651 | GOENKA ENTERPRISE | 40.86 | 0 | 90
427 | Bankura Mechanical | Khatra Sub-Division | Formal work order for the work of Providing and Installation of High lift & Low lift pumping machineries and other electromehanical accessories for Augmentation of Simlapal piped water supply scheme for providing FHTC, Block - Simlapal Dist - Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2023-2024 | 1792/BMD | 01/08/2023 | 900 | A.K.INDUSTRIES | 127.79 | 19.91 | 85
428 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of water supply scheme Dubrajpur Zone-B and its adjoining mouzas under Simlapal water supply scheme (BRGF Ph-I) under Jal jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000567/2023-2024 | 2025/BMD | 01/09/2023 | 723 | SINHA ELECTRICALS | 71.68 | 47.77 | 66
429 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Mandalkuli (Zone-IIIB) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00216/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
430 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Mandalkuli (IIIB) under Raipur Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000014/2025-2026 | 149/BMD | 30/04/2025 | 90 | M/S SWAPAN BANERJEE | 13.38 | 0 | 0
431 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-3B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000238/2023-2024 | 1123/BMD | 24/05/2023 | 30 | UNICON | 2.38 | 0 | 0
432 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation work for Mandalkuli (Zone IIIB) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000876/2024-2025 | 2037/BMD | 07/03/2025 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 84.8 | 0 | 0
433 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement work for Betanal Zone-B water supply scheme at Indus Block Under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00006/2024-2025 | BP-2024-25-92 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.47 | 0 | 0
434 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00179/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
435 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01617/2023-2024 | BP-2023-24-154 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.74 | 0 | 0
436 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Betanal Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01627/2023-2024 | BP-2023-24-155 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
437 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical acessories at boosting P.H for Augmentation of Betanal Zone-B Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 858/BMD | 29/08/2024 | 300 | M/S SAJAHAN CHOWDHURY | 18.51 | 0 | 0
438 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Augmentation of sub- station equipment at Betanal Zone-B piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 859/BMD | 29/08/2024 | 120 | M.S. ENTERPRISE | 15.51 | 0 | 100
439 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Betanal Zone-B piped water supply scheme(BRGF Ph-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000366/2023-2024 | 1698/BMD | 28/07/2023 | 777 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 67.31 | 34.66 | 40
440 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chuamasina Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00167/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
441 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chuamasina (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000522/2023-2024 | 1886/BMD | 17/08/2023 | 1020 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 75.75 | 47.23 | 55
442 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for load enhancement at mouza Shingahati of Puncha zone C ws scheme under BMD PHED. | Assistant Engineer | Junior Engineer | BILL/00288/2024-2025 | BP-2024-25-59 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.94 | 0 | 0
443 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-C) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000556/2023-2024 | 1992/BMD | 28/08/2023 | 120 | MENAKA ENTERPRISE | 41.73 | 28.3 | 60
444 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Binod Nagar water supply scheme(T/W-II) at Patrasayer block under BMD PHE Dte.(SM/18340) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01235/2024-2025 | BP-2024-25-379 | 13/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0
445 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Binod Nagar (T/W-I) water supplyb scheme at Patrasayer Block under BMD PHE Dte.(SM/18340) | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01340/2024-2025 | BP-2024-25-392 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.27 | 0 | 0
446 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Binod Nagar Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000024/2025-2026 | 235/BMD | 14/05/2025 | 90 | AMITAVA CHAKRABORTY | 11.65 | 0 | 0
447 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for MATHURABATI (JL NO-70,PLOT-2)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00023/2024-2025 | BP-2024-25-102 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0
448 | Bankura Mechanical | Brishnupur Sub-Division | Shifting work of 11KV HT power line at Mathurabati HW site under B.M.D PHE Dte | Assistant Engineer | Junior Engineer | BILL/01098/2024-2025 | BP-2024-25-255 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.38 | 0 | 0
449 | Bankura Mechanical | Brishnupur Sub-Division | Mathurabati Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01518/2023-2024 | BP-2023-24-117 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
450 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Mathurabati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 874/BMD | 04/05/2023 | 180 | ABHIJIT MUKHERJEE | 35.79 | 15.18 | 43
451 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Hetia Piped Water Supply Scheme t/w-II ,hetia gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00140/2024-2025 | BP-2024-25-101 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.72 | 0 | 0
452 | Bankura Mechanical | Brishnupur Sub-Division | Hatia T/W -I | Assistant Engineer | Junior Engineer | BILL/01506/2023-2024 | BP-2023-24-105 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.02 | 0 | 0
453 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing & installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Hetia Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000070/2025-2026 | 261/BMD | 14/05/2025 | 90 | M/S MANABESH ROY | 11.64 | 0 | 0
454 | Bankura Mechanical | Khatra Sub-Division | New service connection for OHR site of Sarenga | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00028/2024-2025 | BP-2024-25-38 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.53 | 0 | 0
455 | Bankura Mechanical | Khatra Sub-Division | New 3 Phase service connection for Sarenga OHR | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/00696/2024-2025 | BP-2024-25-187 | 13/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.53 | 0 | 0
456 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for sub-surface water base Sarenga piped water supply scheme Block-Sarenga Dist -Bankura under Bankura Mechanical Division PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000304/2023-2024 | 1407/BMD | 18/07/2023 | 60 | TAPAN KUMAR SARKAR | 55.92 | 40.62 | 15
457 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for new service connection at Digha w/s scheme under BMD ,PHE ,Dte. SM/11923 | Assistant Engineer | Junior Engineer | BILL/00524/2024-2025 | BP-2023-24-144 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.24 | 0 | 0
458 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Name of Work: Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Digha piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000177/2023-2024 | 937/BMD | 12/05/2023 | 1080 | KINGKINI TRADERS | 37.12 | 20.06 | 80
459 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 7A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000243/2023-2024 | 1128/BMD | 24/05/2023 | 30 | CHAKRABORTY MINING & ENGINEERING. | 2.39 | 0 | 0
460 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-4A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer (Contractual) | ORD/000247/2023-2024 | 1131/BMD | 24/05/2023 | 30 | M/S DAS & SARKAR ENTERPRISE | 2.39 | 0 | 0
461 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I at Patrabandh W/S scheme | Assistant Engineer | Junior Engineer | BILL/00420/2024-2025 | BP-2024-25-100 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.7 | 0 | 0
462 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Patrabandh W/S scheme | Assistant Engineer | Junior Engineer | BILL/01346/2024-2025 | BP-2024-25-352 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 14.18 | 0 | 0
463 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pratapbandh Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000151/2025-2026 | 446/BMD | 10/06/2025 | 90 | GOPAL CHANDRA CHOWDHURY | 11.84 | 0 | 0
464 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Madhabbati Piped Water Supply Scheme t/w-II ,Madhabbati, Kuchiakole of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00130/2024-2025 | BP-2024-25-22 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.49 | 0 | 0
465 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Madhab bati Piped Water Supply Scheme t/w-III ,Madhabbati,Kuchiakole of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00534/2024-2025 | BP-2024-25-150 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.37 | 0 | 0
466 | Bankura Mechanical | Brishnupur Sub-Division | Madhab Bati Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01495/2023-2024 | BP-2023-24-99 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.7 | 0 | 0
467 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Madhabbati Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000063/2025-2026 | 259/BMD | 14/05/2025 | 90 | TAPAN KUMAR SARKAR | 11.97 | 0 | 0
468 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Basantapur Piped Water Supply Scheme t/w-II ,Basantapur, Routhkhanda of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00135/2024-2025 | BP-2024-25-21 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0
469 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Routhkhanda Piped Water Supply Scheme t/w-III ,Routhkhanda gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01242/2024-2025 | BP-2024-25-314 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.14 | 0 | 0
470 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Routhkhanda Piped Water Supply Scheme t/w-II ,Routhkhanda gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01243/2024-2025 | BP-2024-25-315 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.59 | 0 | 0
471 | Bankura Mechanical | Brishnupur Sub-Division | Rautkhanda Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01511/2023-2024 | BP-2023-24-98 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.6 | 0 | 0
472 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Routhkhanda Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000182/2025-2026 | 454/BMD | 10/06/2025 | 90 | DEY ENTERPRISE | 13.05 | 0 | 0
473 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Karakberia W/S scheme | Assistant Engineer | Junior Engineer | BILL/00531/2024-2025 | BP-2024-25-151 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.42 | 0 | 0
474 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Karakberia W/S scheme | Assistant Engineer | Junior Engineer | BILL/00532/2024-2025 | BP-2024-25-152 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.17 | 0 | 0
475 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Karak Beriya Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000146/2025-2026 | 441/BMD | 10/06/2025 | 90 | P.K. ENGINEERING | 11.79 | 0 | 0
476 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00143/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
477 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Barabendya CWR Site under Joytunga (zone-H) Water supply scheme Barjora block under BMD,PHE Dte. (SM/16961) | Assistant Engineer | Junior Engineer | BILL/01343/2024-2025 | BP-2024-25-344 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.51 | 0 | 0
478 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for JOYTUNGA (Zone-H) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 504/BMD | 09/07/2024 | 120 | A.G.ENTERPRISE | 13.16 | 0 | 0
479 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Joytunga ( Zone-H) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000529/2023-2024 | 1893/BMD | 17/08/2023 | 120 | A.G.ENTERPRISE | 81.78 | 50.13 | 62
480 | Bankura Mechanical | Bankura Sadar Sub-Division | Load enhancement charges for CHATURDIHI OHR under Bankura -I,II & Borjora (BRGF Ph-I) water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00379/2024-2025 | BP-2024-25-81 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
481 | Bankura Mechanical | Bankura Sadar Sub-Division | New service conection at puramouli mouza of Chaturdihi augmentation site undfer Bankura-I,II & Barjora water supply scheme at Bankura-I block under BMD PHE dte.(SM/16971) | Assistant Engineer | Junior Engineer | BILL/01358/2024-2025 | BP-2024-25-342 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.24 | 0 | 0
482 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation works for CHATURDIHI (Zone U) under Bankura I, II and Barjora Block Water Supply Scheme (BRGF Ph I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001039/2023-2024 | 2971/BMD | 29/02/2024 | 360 | ORIENTAL ENGINEERING CO. | 97.69 | 0 | 53
483 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 7B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000244/2023-2024 | 1129/BMD | 24/05/2023 | 30 | CHAKRABORTY MINING & ENGINEERING. | 2.39 | 0 | 0
484 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Pratappur (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer |  | BILL/00132/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
485 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL Service connection charge for Pratappur (Manachar) water supply scheme, Barjora block under BMD,PHE Dte. (sm/16695 ) | Assistant Engineer |  | BILL/01096/2024-2025 | BP-2024-25-254 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.3 | 0 | 0
486 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Pratappur( Manachar) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Barjora Dist: Bankura | Assistant Engineer |  | ORD/000450/2023-2024 | 1777/BMD | 01/08/2023 | 706 | UNITED TRADERS | 32.7 | 16.2 | 80
487 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machineries and other electromechanical accessories for Ground water based Krishnanagar (Manachar) piped water supply scheme under Bankura Mechanical Division, P.H.E Dte.Block Barjora Dist: Bankura | Assistant Engineer |  | ORD/000578/2024-2025 | 1400/BMD | 12/12/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 39.35 | 0 | 0
488 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pratappur (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer |  | ORD/000580/2024-2025 | 1401/BMD | 12/12/2024 | 120 | GOPAL CHANDRA CHOWDHURY | 21.44 | 0 | 0
489 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00161/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
490 | Bankura Mechanical | Bankura Sadar Sub-Division | Load enhancement Service connection charge for Kanchanpur (zone-C) OHR site water supply scheme Barjora block under BMD,PHE Dte. (SM/16956) | Assistant Engineer | Junior Engineer | BILL/02193/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.89 | 0 | 0
491 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Kanchanpur (Zone-C) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000160/2024-2025 | 502/BMD | 09/07/2024 | 360 | KINGKINI TRADERS | 23.07 | 0 | 25
492 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kanchanpur ( Zone C) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000521/2023-2024 | 1885/BMD | 17/08/2023 | 120 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.06 | 69
493 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Gopalpur W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01241/2024-2025 | BP-2024-25-313 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.7 | 0 | 0
494 | Bankura Mechanical | Brishnupur Sub-Division | Gopalpur | Assistant Engineer | Junior Engineer | BILL/01504/2023-2024 | BP-2023-24-94 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.11 | 0 | 0
495 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Gopalpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000172/2023-2024 | 885/BMD | 04/05/2023 | 698 | ORIENTAL ENGINEERING CO. | 40.24 | 14.33 | 36
496 | Bankura Mechanical | Brishnupur Sub-Division | Manik Bazar Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/01512/2023-2024 | BP-2023-24-114 | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.85 | 0 | 0
497 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Manikbazar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 886/BMD | 04/05/2023 | 60 | KINGKINI TRADERS | 37.08 | 19.35 | 45
498 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00180/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
499 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AMRUL ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00435/2024-2025 | BP-2024-25-112 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0
500 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Nuriduri (8Amrul Zone-A) | Assistant Engineer | Junior Engineer | BILL/01339/2024-2025 | BP-2024-25-340 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.35 | 0 | 0
501 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Amrul Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01622/2023-2024 | BP-2023-24-159 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.2 | 0 | 0
502 | Bankura Mechanical | Brishnupur Sub-Division | Quotation money bill for new power application at Mourai boosting pump house under Augmentation of Amrul Zone-A water supply scheme, SM Code-SM/17229, Application no-2005272877, Ref. id-204646763 | Assistant Engineer | Junior Engineer | BILL/01703/2025-2026 |  | 06/02/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.31 | 0 | 0
503 | Bankura Mechanical | Brishnupur Sub-Division | Quotation money bill for new electric connection at Amrul boosting pump house under Augmentation of Amrul Zone-A, Scheme code-SM/17229, Ref. Application No. 2005511388, Ref. Id. 204751657 | Assistant Engineer | Junior Engineer | BILL/01704/2025-2026 |  | 06/02/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.6 | 0 | 0
504 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Amrul (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 1696/BMD | 28/07/2023 | 60 | PRADIP KUMAR DHABAL | 54.01 | 28.75 | 53
505 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IB). | Assistant Engineer | Junior Engineer | BILL/00155/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
506 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL, Quotation Bill for new power connection at Bhairabpur Pump House augmentation work under Barjora (Left out mouza) (zone-IB) water supply scheme (SM/17245) | Assistant Engineer | Junior Engineer | BILL/00722/2024-2025 | BP-2024-25-199 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.18 | 0 | 0
507 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IB) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2024-2025 | 499/BMD | 09/07/2024 | 360 | UNITED TRADERS | 13.19 | 0 | 83
508 | Bankura Mechanical | Bankura Sadar Sub-Division | Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IB) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 1400/BMD | 18/07/2023 | 60 | M.S. ENTERPRISE | 81.81 | 61.5 | 74
509 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-II). | Assistant Engineer | Junior Engineer | BILL/00156/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
510 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I)( Zone II) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000513/2023-2024 | 1878/BMD | 17/08/2023 | 120 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.09 | 69
511 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Sub-Station Equipment and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I)( Zone II) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001031/2023-2024 | 2963/BMD | 29/02/2024 | 540 | COMBINE ENTERPRISES | 28.82 | 0 | 35
512 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electromechanical acessories w for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- D) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000323/2024-2025 | 864/BMD | 29/08/2024 | 360 | AMITAVA CHAKRABORTY | 35.75 | 0 | 90
513 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-D) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000716/2023-2024 | 2173/BMD | 30/10/2023 | 120 | PRADIP KUMAR DHABAL | 32.67 | 21.75 | 60
514 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Adwaitabati W/S scheme | Assistant Engineer | Junior Engineer | BILL/00526/2024-2025 | BP-2024-25-146 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.12 | 0 | 0
515 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Adwitabati W/S Scheme | Assistant Engineer | Junior Engineer | BILL/00533/2024-2025 | BP-2024-25-147 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.69 | 0 | 0
516 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Adwitabati Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 766/BMD | 24/04/2023 | 1080 | TAPAN KUMAR SARKAR | 46.96 | 26.82 | 58
517 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Replacement TW for Augmentation of Bikrampur and Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 445/BMD | 27/06/2024 | 600 | M/S SWAPAN BANERJEE | 19.55 | 0 | 80
518 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Bikrampur & Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000550/2023-2024 | 1986/BMD | 28/08/2023 | 1020 | JAGANNATH ENTERPRISE | 21.15 | 15.38 | 90
519 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for proposed Tubewell-II of Bikrampur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001087/2023-2024 | 3063/BMD | 12/03/2024 | 180 | M/S BIPUL BANERJEE | 25.39 | 11.78 | 40
520 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charges for for WBSEDCL power for Aghuribandh Punisole Zone-A water supply scheme under PHE Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01496/2024-2025 | BP-2024-25-375 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.03 | 0 | 0
521 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-C) under Onda Block (BRGF Ph-I) at CWR site Nischintapur under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000136/2024-2025 | 442/BMD | 27/06/2024 | 480 | M.S. ENTERPRISE | 60.77 | 0 | 100
522 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-C) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000547/2023-2024 | 1983/BMD | 28/08/2023 | 840 | KASHINATH DEY | 31.55 | 0 | 75
523 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Additional Tubewell for Augmentation works for Aguribandh Punisole (Zone C) Water Supply Scheme in the Block Onda under Bankura Mechanical Division, PHE Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000874/2024-2025 | 2036/BMD | 07/03/2025 | 120 | SWAPAN ENTERPRISE | 17.36 | 0 | 0
524 | Bankura Mechanical | Bankura Sadar Sub-Division | Total payable load enhancement charges at Tetulmuri of Nikunjapur Zone-B ws scheme under BMD PHED. | Assistant Engineer | Junior Engineer | BILL/00291/2024-2025 | 1 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.55 | 0 | 0
525 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-B) (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000554/2023-2024 | 1990/BMD | 28/08/2023 | 120 | DIPALI CONSTRUCTION | 47.88 | 28.5 | 76
526 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of MCC Panel and other electro-mechanical accessories for Augmentation works at CWPH at Gamidya under Nikunjapur Zone B water supply scheme (BRGF Ph I) Block Onda under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001078/2023-2024 | 3057/BMD | 12/03/2024 | 480 | TAPAN KUMAR SARKAR | 38.32 | 8.95 | 100
527 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00185/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
528 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for AKUI ZONE B water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00439/2024-2025 | BP-2024-25-113 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.85 | 0 | 0
529 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Akui Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01625/2023-2024 | BP-2023-24-160 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.09 | 0 | 0
530 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and installation of Panel with Automatic Chlorinator and Stabilizer machineries along with other allied electro-mechanical works for newly sunk TW at Akui Zone B boosting TW site of Indus water supply scheme under B.M.D. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2025-2026 | 152/BMD | 30/04/2025 | 270 | SEN BROTHERS | 18.86 | 0 | 30
531 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Akui (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000359/2023-2024 | 1695/BMD | 28/07/2023 | 669 | ABHIJIT MUKHERJEE | 74.38 | 46.82 | 36
532 | Bankura Mechanical | Bankura Sadar Sub-Division | Upward revision of contract Demand from 50KVA to 80 KVA at 11KV having Consumer ID : 942309800 at the premises at Indpur Xone-1, Kaladihi, Bankura. | Assistant Engineer | Junior Engineer | BILL/00959/2024-2025 | BP-2024-25-228 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.92 | 0 | 0
533 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Indpur piped water supply Scheme Block-Bankura-I under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000990/2023-2024 | 2850/BMD | 09/02/2024 | 180 | M.S. ENTERPRISE | 120.1 | 101.77 | 30
534 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Somsar Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00190/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
535 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for SOMSAR PH-I Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00434/2024-2025 | BP-2024-25-108 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0
536 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for SOMSAR PH-II water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00441/2024-2025 | BP-2024-25-109 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.66 | 0 | 0
537 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Somsar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Indus, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000461/2023-2024 | 1787/BMD | 01/08/2023 | 300 | A.G.ENTERPRISE | 53.61 | 24.55 | 60
538 | Bankura Mechanical | Bankura Sadar Sub-Division | Proposed sub surface water based Dhabani pipe water supply scheme under Bankura Division, Block- Barjora, District: Bankura. | Assistant Engineer | Junior Engineer | BILL/00198/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
539 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Dhabani water supply scheme (CWR, OHR site), Barjora block under BMD, PHE Dte. (SM/1804) | Assistant Engineer | Junior Engineer | BILL/01336/2024-2025 | BP-2024-25-329 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.3 | 0 | 0
540 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Proposed surface water based Dhabani under Water Supply Scheme Block- Barjora under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 1769/BMD | 01/08/2023 | 60 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 45.35 | 26.22 | 31
541 | Bankura Mechanical | Khatra Sub-Division | quotation Bill for New Pump house no.1 at Katalda under Danara w/s scheme augmentation work (SM/17297) | Assistant Engineer | Junior Engineer | BILL/00946/2024-2025 | BP-2024-25-231 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.3 | 0 | 0
542 | Bankura Mechanical | Khatra Sub-Division | Quotation Bill for New Pump house no.2 at Katalda under Danara w/s scheme augmentation work (SM/17297) | Assistant Engineer | Junior Engineer | BILL/00947/2024-2025 | BP-2024-25-232 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.58 | 0 | 0
543 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Submersible pumping machineries and other electromechanical accessories for Augmentation works at T/W No-II at Katalda Pump house under Dhanara Water supply scheme and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme,Under Raipur Block under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000262/2024-2025 | 517/BMD | 09/07/2024 | 120 | R.K. ENTERPRISE | 7.09 | 0 | 0
544 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Dhanara and its adjoining mouzas water supply scheme under Jal Jeeven mission Progremme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000989/2023-2024 | 2849/BMD | 09/02/2024 | 900 | DEY ENTERPRISE | 144.45 | 0 | 21
545 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00129/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
546 | Bankura Mechanical | Bankura Sadar Sub-Division | Total payable load enhancement charges at Angariaof Nikunjapur Zone-A ws scheme under BMD PHED. | Assistant Engineer | Junior Engineer | BILL/00292/2024-2025 | BP-2024-25-98 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.09 | 0 | 0
547 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of Quotation for new service connection at Nikunjapurr Zone-A , Mouza -Gamidya.SM/ 17280 | Assistant Engineer | Junior Engineer | BILL/01239/2024-2025 | BP-2024-25-309 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.1 | 0 | 0
548 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Nikunjapur and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01628/2023-2024 | BP-2023-24-156 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.65 | 0 | 0
549 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-A) (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000553/2023-2024 | 1989/BMD | 28/08/2023 | 120 | DEBJYOTI BASU | 60.81 | 29.87 | 70
550 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of CWPH Pumping machineries with other electro-mechanical accessories for Augmentation of Nikanjapur & Adjoining mouza water supply scheme (Zone-A) (BRGF Phase I) at CWR site Gamirda under Bankura Mechanical Division, PHE Dte. Block : Onda , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001077/2023-2024 | 3056/BMD | 12/03/2024 | 480 | M.S. ENTERPRISE | 40.56 | 0 | 95
551 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Gargariya, Zone-B Water Supply Scheme under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00214/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
552 | Bankura Mechanical | Khatra Sub-Division | New Service Connection for Gargaria water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00382/2024-2025 | BP-2024-25-86 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
553 | Bankura Mechanical | Khatra Sub-Division | New 3 Phase Service Connection for Gargaria Zone B | Assistant Engineer | Junior Engineer | BILL/00700/2024-2025 | 1BP-2024-25-167 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
554 | Bankura Mechanical | Khatra Sub-Division | New connection for 3 Gargaria Zone-B, Bikrampur Hatibari , JL-216 Plot-139 | Assistant Engineer | Junior Engineer | BILL/01152/2024-2025 | BP-2024-25-270 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.31 | 0 | 0
555 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Construction of Guard Piller for cable laying of river bed T/W with allied works for Gargaria Zone-A and Adjoining mouza for Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000320/2024-2025 | 861/BMD | 29/08/2024 | 120 | PRADIP KUMAR DHABAL | 11.13 | 11.12 | 100
556 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Gargariya Zone-B water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000575/2023-2024 | 2030/BMD | 01/09/2023 | 120 | TAPAN KUMAR DEY | 61.7 | 17.98 | 35
557 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries for Augmentation for Gargariya Zone A water supply scheme under Sarenga water supply scheme (BRGF Ph I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/001036/2023-2024 | 2968/BMD | 29/02/2024 | 730 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 37.8 | 18.77 | 40
558 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL Pumping machineries & MCC panel with other electromechanical accessories for Augmentation for Gargariya Zone-B and adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001095/2023-2024 | 3070/BMD | 12/03/2024 | 480 | DEBJYOTI BASU | 67.22 | 28.47 | 55
559 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-III of Panahar W/S scheme | Assistant Engineer | Junior Engineer | BILL/00527/2024-2025 | BP-2024-25-136 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.18 | 0 | 0
560 | Bankura Mechanical | Brishnupur Sub-Division | New service connection connection at P/H no-I of panahar W/S scheme. | Assistant Engineer | Junior Engineer | BILL/00528/2024-2025 | BP-2024-25-137 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.8 | 0 | 0
561 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-III of Panahar W/S scheme | Assistant Engineer | Junior Engineer | BILL/00529/2024-2025 | BP-2024-25-138 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.99 | 0 | 0
562 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Panahar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Kotulpur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000167/2023-2024 | 2065/BMD | 11/09/2023 | 180 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 59.03 | 27.3 | 46
563 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for DHULAI (JL NO-14,PLOT-1910)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00011/2024-2025 | BP-2024-25-5 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.62 | 0 | 0
564 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for DHULAI (JL NO-14, PLOT-2041/2108LR) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00021/2024-2025 | BP-2024-25-6 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.39 | 0 | 0
565 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for DHALUI (JL NO-14, PLOT-486) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00022/2024-2025 | BP-2024-25-7 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.91 | 0 | 0
566 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Dhulai Piped water supply scheme Block : Sonamukhi under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000531/2023-2024 | 1930/BMD | 21/08/2023 | 1072 | EASTERN INDIA SALES & SERVICE | 68.77 | 0 | 10
567 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00149/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
568 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Chichura mouza of Jagadalla augmentation site under Bankura-I,II & Barjora water supply scheme under BMD PHE dte.(SM/16970) | Assistant Engineer | Junior Engineer | BILL/01359/2024-2025 | BP-2024-25-343 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.68 | 0 | 0
569 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Jagdalla ( Zone-S) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000152/2024-2025 | 495/BMD | 09/07/2024 | 120 | M/S DE ENGINEERING CONCERN | 8.8 | 0 | 0
570 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Jagadalla (Zone-S) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 1466/BMD | 18/07/2023 | 60 | M.S. ENTERPRISE | 81.82 | 61.5 | 48
571 | Bankura Mechanical | Brishnupur Sub-Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer | BILL/00127/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
572 | Bankura Mechanical | Brishnupur Sub-Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR RAMPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER SONAMUKHI BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer | BILL/01664/2023-2024 | BP-2023-24-177 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
573 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rampur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 938/BMD | 12/05/2023 | 180 | M/S BIPUL BANERJEE | 19.85 | 8.24 | 41
574 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of -Electrical and illumination works related to instrument and laboratory requirment for proposed Water Testing Laboratory at PHED OHR site, Sonamukhi Municipal Water Supply scheme , Bankura under infrostructure development and diffrent water testing laboratories regarding NABL Accreditation recognition under Bankura Mechanical Division, PHE Dte.Dist-Bankura, Releted to supported activities under Jal Jiban Mission. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 985/BMSD | 29/07/2022 | 15 | RAJIB COMPANY | 4.27 | 3.82 | 100
575 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01673/2023-2024 | BP-2023-24-186 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.46 | 0 | 0
576 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission program under Raipur Block in Bankura District under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000715/2023-2024 | 2172/BMD | 30/10/2023 | 960 | DEY ENTERPRISE | 50.24 | 2.55 | 78
577 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATHRA TW-1(JL NO-153 PLOT-689)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer |  | BILL/00009/2024-2025 | BP-2024-25-29 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.97 | 0 | 0
578 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for PATHRA TW-2(JL NO-153, PLOT NO-351)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer |  | BILL/00010/2024-2025 | BP-2024-25-30 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.35 | 0 | 0
579 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Pathra piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi, Dist: Bankura. | Assistant Engineer |  | ORD/000159/2023-2024 | 871/BMD | 04/05/2023 | 180 | INDRAJIT MITRA | 31.37 | 14.56 | 46
580 | Bankura Mechanical | Brishnupur Sub-Division | New service connection of P/H-II Dhuladanga W/S scheme | Assistant Engineer | Junior Engineer | BILL/00599/2024-2025 | BP-2024-25-169 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.62 | 0 | 0
581 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at P/H-I of Dhuladanga W/S scheme | Assistant Engineer | Junior Engineer | BILL/01348/2024-2025 | BP-2024-25-351 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.48 | 0 | 0
582 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Dhuladanga Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000144/2025-2026 | 439/BMD | 10/06/2025 | 90 | M/S SAJAHAN CHOWDHURY | 11.85 | 0 | 0
583 | Bankura Mechanical | Brishnupur Sub-Division | Additional quotation for Rautora. | Assistant Engineer | Junior Engineer | BILL/00367/2025-2026 | 107/W-612 | 01/08/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.16 | 0 | 0
584 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for RautaraTW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14521) | Assistant Engineer | Junior Engineer | BILL/01249/2024-2025 | BP-2024-25-323 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.47 | 0 | 0
585 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Rautara TW1 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14521) | Assistant Engineer | Junior Engineer | BILL/01250/2024-2025 | BP-2024-25-324 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.65 | 0 | 0
586 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR at Routara Piped Water Supply Scheme under BMD PHE Dte Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000069/2025-2026 | 260/BMD | 14/05/2025 | 90 | SUMIT KUMAR CHAKRABORTY | 11.66 | 0 | 0
587 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Pratappur. | Assistant Engineer | Junior Engineer | BILL/00421/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.61 | 0 | 0
588 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-I of Pratabpur W/S scheme | Assistant Engineer | Junior Engineer | BILL/00522/2024-2025 | BP-2024-25-149 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0
589 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pratabpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000153/2025-2026 | 448/BMD | 10/06/2025 | 90 | ABHIJIT MUKHERJEE | 11.84 | 0 | 0
590 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00151/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
591 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Jamboni mouza of Andherthole augmentaion site at Bankura-I block under BMD PHE Dte.(SM/16972) | Assistant Engineer | Junior Engineer | BILL/01357/2024-2025 | BP-2024-25-341 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.45 | 0 | 0
592 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Andharthole (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 146/BMD | 30/04/2025 | 90 | SWAPAN ENTERPRISE | 40.67 | 0 | 0
593 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at Belboni IBS, under Bankura I ,II and Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000127/2024-2025 | 433/BMD | 27/06/2024 | 240 | RABINDRA NATH KHAN | 96.81 | 0 | 98
594 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Adarsole (Zone-V) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 1469/BMD | 18/07/2023 | 60 | R.N.S. TRADING | 81.81 | 0 | 0
595 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares for Horizontal Split Cashing Centrifugal Pumping Machineries at Belboni IBS Block Bankura-II under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 1783/BMD | 01/08/2023 | 90 | B T PROJECTS PRIVATE LIMITED | 99.61 | 98.15 | 98
596 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00144/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
597 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Monoharpur OHR near Bankura university at Bakura-II block under BMD PHE.(SM/16964) | Assistant Engineer | Junior Engineer | BILL/01601/2024-2025 | BP-2024-25-380 | 13/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.93 | 0 | 0
598 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Telebedia (Zone M) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000040/2025-2026 | 244/BMD | 14/05/2025 | 90 | DAS ENTERPRISE | 27.33 | 0 | 0
599 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Telebedia( Zone-M) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000165/2024-2025 | 507/BMD | 09/07/2024 | 176 | CHAKRABORTY MINING & ENGINEERING. | 13.17 | 0 | 53
600 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Telibedia ( Zone-M) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000441/2023-2024 | 1770/BMD | 01/08/2023 | 60 | WEST BENGAL ENGINEERING CO. | 81.8 | 48.24 | 59
601 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Krishna Nagar (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | BILL/00130/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.5 | 0 | 0
602 | Bankura Mechanical | Bankura Sadar Sub-Division | Service connection charge for Krishnanagar (Manachar) water supply scheme Barjora block under BMD,PHE Dte.(SM/16696 ) | Assistant Engineer | Junior Engineer | BILL/01097/2024-2025 | BP-2024-25-253 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.35 | 0 | 0
603 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Krishna Nagar( Manachar) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000444/2023-2024 | 1773/BMD | 01/08/2023 | 970 | GOENKA ENTERPRISE | 35.15 | 13.7 | 39
604 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machineries and other electromechanical accessories for Ground water based Krishnanagar (Manachar) piped water supply scheme under Bankura Mechanical Division, P.H.E Dte.Block Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000578/2024-2025 | 1400/BMD | 12/12/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 39.35 | 0 | 0
605 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | BILL/00131/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
606 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL Service connection charge for Pakhanna (Manachar) water supply scheme Barjora block under BMD,PHE Dte.(SM/16697) | Assistant Engineer | Junior Engineer | BILL/01095/2024-2025 | BP-2024-25-252 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 15.86 | 0 | 0
607 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Pakhanna( Manachar) piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Barjora Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000447/2023-2024 | 1775/BMD | 01/08/2023 | 60 | TAPAN KUMAR SARKAR | 35.18 | 15.54 | 45
608 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1402/BMD | 12/12/2024 | 120 | SK ENTERPRISE | 30.4 | 0 | 0
609 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Bhubut water supply scheme (T/W-II) at Patrasayer block under BMD PHE Dte.(SM/16700) | Assistant Engineer | Junior Engineer | BILL/01237/2024-2025 | BP-2024-25-312 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.98 | 0 | 0
610 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Bhubut (T/W-I) water supply scheme at Patrasayer block under BMD PHE Dte.(SM/16700) | Assistant Engineer | Junior Engineer | BILL/01465/2024-2025 | BP-2024-25-363 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.02 | 0 | 0
611 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I and TW No II of Bhubut piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Patrashayar, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000112/2024-2025 | 423/BMD | 27/06/2024 | 720 | ABHIJIT MUKHERJEE | 51.08 | 22.44 | 52
612 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Morar Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00164/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
613 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new serrvice connection at Morar Z-A TW-I Mouza Chowgan.SM-17237 | Assistant Engineer | Junior Engineer | BILL/01093/2024-2025 | BP-2024-25-251 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.52 | 0 | 0
614 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection at Morar Z-A TW-III Mouza Bankati.SM - 17237 | Assistant Engineer | Junior Engineer | BILL/01141/2024-2025 | BP-2024-25-288 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.75 | 0 | 0
615 | Bankura Mechanical | Brishnupur Sub-Division | Quotation for new service connection charges at Morar Z-A TW-II Mouza Morar JL -117 plot- 121/1313.SM/17237 | Assistant Engineer | Junior Engineer | BILL/01143/2024-2025 | BP-2024-25-289 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.69 | 0 | 0
616 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Marar Zone-A piped water supply scheme (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000385/2023-2024 | 1708/BMD | 28/07/2023 | 900 | M.S. ENTERPRISE | 82.01 | 56.01 | 70
617 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of CWPH pumping machineries and other electromechanical accessories for Augmentation of Marar Zone-A and adjoining mouzas water supply scheme (BRGF Ph I) at CWR site Gopalpur , Block Bishnupur under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001079/2023-2024 | 3058/BMD | 12/03/2024 | 540 | M/S NABIN GOPAL SENGUPTA | 54.11 | 0 | 40
618 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for KUSTORA (Zone- W) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00152/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
619 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Kalpather of Kustora w/s scheme under BMD PHE Dte.(SM/17242) | Assistant Engineer | Junior Engineer | BILL/00364/2025-2026 |  | 12/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.08 | 0 | 0
620 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Kalpathar of Kustara Augmentation site (SM/17242) under BMD, PHE, Dte. | Assistant Engineer | Junior Engineer | BILL/01099/2024-2025 | BP-2024-25-250 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.28 | 0 | 0
621 | Bankura Mechanical | Bankura Sadar Sub-Division | New serevice connection at Kalpathar of Kustara(Zone-W)augmentation scheme under BMD PHE Dte.(SM/17242) | Assistant Engineer | Junior Engineer | BILL/02196/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.45 | 0 | 0
622 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and installation of online Boosting pumping machineries and other electromechanical accessories at OHR site of Kustora (Zone-W) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000273/2024-2025 | 778/BMD | 20/08/2024 | 360 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 29.28 | 5.08 | 65
623 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kustora (Zone-W) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2023-2024 | 1467/BMD | 18/07/2023 | 240 | RABINDRA NATH KHAN | 81.75 | 51.24 | 63
624 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Soft stater Panel MCC Panel and other electromechanical acessories for Augmentation works for Aguri Band Punisol and its adjoining Mouzas Water Supply Scheme (Zone- A) under Onda Block (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000325/2024-2025 | 866/BMD | 29/08/2024 | 240 | M.S. ENTERPRISE | 59.58 | 0 | 100
625 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Aguri bandh Punisole & its adjoining mouzas water supply scheme (Zone-A) under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000545/2023-2024 | 1981/BMD | 28/08/2023 | 120 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 34.93 | 22.84 | 66
626 | Bankura Mechanical | Bankura Mechanical Sub-Division | PROPOSED GROUND WATER BASED BANSI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SARANGA, DISTRICT : BANKURA | Assistant Engineer | Junior Engineer (Contractual) | BILL/00203/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
627 | Bankura Mechanical | Bankura Mechanical Sub-Division | New 3 phase connection for Banshi water Supply Scheme | Assistant Engineer | Junior Engineer (Contractual) | BILL/00949/2024-2025 | BP-2024-25-227 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.87 | 0 | 0
628 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Bansi piped water supply scheme Block Sarenga under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000464/2023-2024 | 1806/BMD | 03/08/2023 | 1320 | M/S BIPUL BANERJEE | 35.21 | 16.42 | 35
629 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Dhengasole Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00171/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
630 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new connection at Mouza Haraboti. Aug of Dhengasole w/s scheme.SM/17699 | Assistant Engineer | Junior Engineer | BILL/00631/2026-2027 |  | 10/06/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.85 | 0 | 0
631 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Dhengasole Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01608/2023-2024 | BP-2023-24-135 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.74 | 0 | 0
632 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro-mechanical accessories at Boosting tubewell for Augmentation of Dhengasole piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 143/BMD | 30/04/2025 | 90 | TAPAN KUMAR SARKAR | 21.51 | 0 | 0
633 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW at OHR and PH site for Augmentation of Dhengasole and Adjoining mouza water supply scheme Block-Bishnupur under Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000153/2024-2025 | 496/BMD | 09/07/2024 | 360 | PRADIP KUMAR DHABAL | 23.32 | 0 | 61
634 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Dhengasole piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000514/2023-2024 | 1879/BMD | 17/08/2023 | 1020 | SUNRISE ENGINEERING CORPORATION | 67.88 | 0 | 50
635 | Bankura Mechanical | Khatra Sub-Division | New service connection of Handulia PWSS ,Mouza-Ramchandrapur, G.p.- Parsala JL No.-5 Plot no.-8 under BMSD(D) PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00001/2024-2025 | BP-2024-25-96 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0
636 | Bankura Mechanical | Khatra Sub-Division | Proposed sub-surface Water Based Handulia Piped Water Supply Scheme Under Bankura Division,Block-Simlapal,District-Bankura. | Assistant Engineer | Junior Engineer | BILL/00199/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0
637 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for proposed ground water based Handulia piped water supply scheme Block Simlapal under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000564/2023-2024 | 2031/BMD | 01/09/2023 | 836 | M/S SOMA ENTERPRISES | 48.85 | 35.67 | 30
638 | Bankura Mechanical | Khatra Sub-Division | New service connection for Kuldiha water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00029/2024-2025 | BP-2024-25-12 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
639 | Bankura Mechanical | Khatra Sub-Division | New service connection for Kuldiha water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00122/2024-2025 | BP-2024-25-13 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.23 | 0 | 0
640 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Kadra (Zone- G) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00218/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
641 | Bankura Mechanical | Khatra Sub-Division | New service connection charges for Kuldihi, Application No- 2004835893 | Assistant Engineer | Junior Engineer | BILL/00701/2024-2025 | BP-2024-25-164 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.31 | 0 | 0
642 | Bankura Mechanical | Khatra Sub-Division | New Service Connection for Kuldihi , Application No- 2004835760 | Assistant Engineer | Junior Engineer | BILL/00702/2024-2025 | BP-2024-25-165 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
643 | Bankura Mechanical | Khatra Sub-Division | New Service connection charge of WBSEDCL Kuldiha | Assistant Engineer | Junior Engineer | BILL/00703/2024-2025 | BP-2024-25-166 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.23 | 0 | 0
644 | Bankura Mechanical | Khatra Sub-Division | New 3 phase connection for Kuldihi W/S (Scheme) Telijant site | Assistant Engineer | Junior Engineer | BILL/00950/2024-2025 | BP-2024-25-230 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.16 | 0 | 0
645 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other allied electro-mechanical accessories for Augmentation for KULDIHI piped water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000135/2024-2025 | 441/BMD | 27/06/2024 | 187 | ABHIJIT MUKHERJEE | 19.59 | 4.57 | 65
646 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Kuldiha & its adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000568/2023-2024 | 2034/BMD | 01/09/2023 | 1763 | A.K.INDUSTRIES | 72.58 | 54 | 66
647 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Gaseous Chlorination System for Augmentation of Kuldihi water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001094/2023-2024 | 3069/BMD | 12/03/2024 | 120 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 41.85 | 36.21 | 70
648 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chaknakaijuri & its adjoining Mouzas water supply scheme under Onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000540/2023-2024 | 1976/BMD | 28/08/2023 | 612 | INDRAJIT MITRA | 56.67 | 36.52 | 70
649 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation of piped water supply schemes for Kenjakura and its adjoining mouzas (Phase - I). | Assistant Engineer | Junior Engineer | BILL/00191/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
650 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Low Lift pumping machinery and other electro mechanical accessories for Augmentation of piped water supply scheme for Kenjakura and its adjoining Mouzas water supply scheme under Bankura Mechanical Division PHE Dte, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001090/2023-2024 | 3065/BMD | 12/03/2024 | 120 | SWAPAN ENTERPRISE | 18.27 | 17.98 | 100
651 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation money for load enhancement at Puncha Teliberia under BMD, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00296/2024-2025 | BP-2024-25-60 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.94 | 0 | 0
652 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-B) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000677/2023-2024 | 2122/BMD | 22/09/2023 | 725 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 75.09 | 41.99 | 45
653 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Danna (T/W-II) w/s scheme at Patrasayer block under BMD PHE Dte.(SM/18302) | Assistant Engineer | Junior Engineer | BILL/01600/2024-2025 | BP-2024-25-391 | 27/03/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0
654 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Danna Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000034/2025-2026 | 239/BMD | 14/05/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 12.46 | 0 | 0
655 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at TW No-I & TW No-II Premises of Nakaijuri piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000125/2024-2025 | 1073/BMSD | 05/07/2024 | 60 | KASHINATH DEY | 4.38 | 0 | 0
656 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at P/H of adjoining mouza of Danna piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrasayer, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000126/2024-2025 | 1075/BMSD | 05/07/2024 | 60 | KINGKINI TRADERS | 4.39 | 4.27 | 100
657 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Danna Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000171/2023-2024 | 883/BMD | 04/05/2023 | 870 | M/S NABIN GOPAL SENGUPTA | 68.09 | 29.42 | 55
658 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for load enhancement at Banshdanga under BMD, PHE dte. | Assistant Engineer | Junior Engineer | BILL/00289/2024-2025 | 1 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0
659 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Puncha & its adjoining Mouzas water supply scheme (Zone-A) under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000555/2023-2024 | 1991/BMD | 28/08/2023 | 600 | ABHIJIT MUKHERJEE | 47.76 | 24.56 | 10
660 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for new WTP for Augmentation of Intake WTP and rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, and Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000001/2025-2026 | 95/BMD | 23/04/2025 | 120 | M/S P.P ELECTRICALS | 314.08 | 0 | 0
661 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro-mechanical accessories for at new intake for Augmentation of Intake WTP & rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, & Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000634/2024-2025 | 1475/BMD | 10/01/2025 | 120 | DEBJYOTI BASU | 107.35 | 0 | 0
662 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing Yard lighting arrangement at new WTP site for Augmentation of Intake WTP and rising main for surface water based piped water supply scheme Mukutmanipur, Khatra, and Ranibandh under Bankura Mechanical Division, P.H.E Dte. Dist Bankura (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000872/2024-2025 | 2035/BMD | 07/03/2025 | 240 | UNITED TRADERS | 14 | 0 | 60
663 | Bankura Mechanical | Brishnupur Sub-Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | Assistant Engineer | Junior Engineer | BILL/00126/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
664 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of installation of Pumping machineries with other electro-mechanical accessories for ground base piped water supply scheme for Patrasayar to commanded FSTC under Jal Swapna mission under Patarasyar Block in Bankura District under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 1014/BMD | 22/05/2023 | 1080 | INDRAJIT MITRA | 19.94 | 10.79 | 54
665 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for TELRUI TW-1 (JL NO-132, PLOT-506LR) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00015/2024-2025 | BP-2024-25-36 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.43 | 0 | 0
666 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for Telrui Tw-2 Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00955/2024-2025 | BP-2024-25-235 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.45 | 0 | 0
667 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Telrui Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 451/BMD | 10/06/2025 | 90 | UNITED TRADERS | 11.69 | 0 | 0
668 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Shalkhara piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Patrasayer, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 656/BMD | 17/04/2023 | 180 | P.K. ENGINEERING | 31.31 | 15.39 | 49
669 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Chandalbandi T/W-II watwer supply scheme (SM/13999) at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01207/2024-2025 | BP-2024-25-291 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.5 | 0 | 0
670 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Chandalbandi w/s scheme(T/W-I) at Patrasayer block under PHE Dte.(SM/13999) | Assistant Engineer | Junior Engineer | BILL/01231/2024-2025 | BP-2024-25-307 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 30.25 | 0 | 0
671 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Chandal Bandi piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Patrashayar, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 872/BMD | 04/05/2023 | 1080 | GOENKA ENTERPRISE | 35.78 | 16.49 | 46
672 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-2B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000236/2023-2024 | 1122/BMD | 24/05/2023 | 30 | UNICON | 2.38 | 0 | 0
673 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Mukundapur Water supply scheme (SM/14006) at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01244/2024-2025 | BP-2024-25-316 | 10/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.2 | 0 | 0
674 | Bankura Mechanical | Brishnupur Sub-Division | MUKUNDAPUR WATER SUPPLY SCHEME | Assistant Engineer | Junior Engineer | BILL/01669/2023-2024 | BP-2023-24-185 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.76 | 0 | 0
675 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Nabasan Piped Water Supply Scheme t/w-I ,Nabasan, Salda of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00133/2024-2025 | BP-2024-25-33 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.63 | 0 | 0
676 | Bankura Mechanical | Brishnupur Sub-Division | Nabasan Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01500/2023-2024 | BP-2023-24-102 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.33 | 0 | 0
677 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nabasan Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000187/2025-2026 | 459/BMD | 10/06/2025 | 90 | M/S BIPUL BANERJEE | 11.85 | 0 | 0
678 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for RANPUR( JL NO-141,PLOT NO-676LR)Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00019/2024-2025 | BP-2024-25-25 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.2 | 0 | 0
679 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Ranpur TW3 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14519) | Assistant Engineer | Junior Engineer | BILL/01182/2024-2025 | BP-2024-25-304 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.4 | 0 | 0
680 | Bankura Mechanical | Brishnupur Sub-Division | New three phase service Connection for Ranpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/14519) | Assistant Engineer | Junior Engineer | BILL/01183/2024-2025 | BP-2024-25-305 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.46 | 0 | 0
681 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Ranpur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000155/2025-2026 | 450/BMD | 10/06/2025 | 90 | M/S NABIN GOPAL SENGUPTA | 13.1 | 0 | 0
682 | Bankura Mechanical | Brishnupur Sub-Division | Dangamakrandapur T/W-I | Assistant Engineer | Junior Engineer | BILL/00851/2023-2024 | BP-2023-24-44 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0
683 | Bankura Mechanical | Brishnupur Sub-Division | Dangamakrandapur T/W-II | Assistant Engineer | Junior Engineer | BILL/00852/2023-2024 | BP-2023-24-45 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0
684 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Danga Makarandapur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Joypur , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000383/2023-2024 | 1706/BMD | 28/07/2023 | 1018 | P.K. ENGINEERING | 59.05 | 27.6 | 20
685 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at T/W-I of Khundanga W/S Scheme. | Assistant Engineer | Junior Engineer | BILL/01345/2024-2025 | BP-2024-25-346 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0
686 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at P/H-II of Khundanga W/S Scheme | Assistant Engineer | Junior Engineer | BILL/01351/2024-2025 | BP-2024-25-347 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.86 | 0 | 0
687 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Khundanga piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 873/BMD | 04/05/2023 | 180 | M/S SWAPAN BANERJEE | 35.82 | 21.78 | 61
688 | Bankura Mechanical | Brishnupur Sub-Division | Additional work for New service connection at Kantaban t/w-I of Kantaban Piped Water Supply Scheme of joypur block under BMD PHE Dte. SM/14526 | Assistant Engineer | Junior Engineer | BILL/01486/2024-2025 | BP-2024-25-357 | 21/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.56 | 0 | 0
689 | Bankura Mechanical | Brishnupur Sub-Division | Kataban Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01605/2023-2024 | BP-2023-24-141 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.35 | 0 | 0
690 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Kantaban Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000183/2025-2026 | 455/BMD | 10/06/2025 | 90 | JAL PRAVAHIKA PVT LTD | 11.85 | 0 | 0
691 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Katabani piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Onda Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000528/2023-2024 | 1892/BMD | 17/08/2023 | 1080 | MENAKA ENTERPRISE | 36.9 | 21.69 | 90
692 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at Add T/W for Augmentation of Ola and Suklai and its adjoining mouzas water supply scheme under onda block(BRGF Phase I) under Bankura Mechanical Division, PHE Dte Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 429/BMD | 27/06/2024 | 480 | INDRAJIT MITRA | 9.2 | 0 | 100
693 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Ola and Suktai and its adjoining mouzas water supply scheme under onda block(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000542/2023-2024 | 1978/BMD | 28/08/2023 | 120 | JAL PRAVAHIKA PVT LTD | 19.84 | 17.53 | 95
694 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Kakatia Near Baura Para (SM/16701)water supply scheme at Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/01175/2024-2025 | BP-2024-25-302 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0
695 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at Kaktia water supply scheme near football ground at Patrasayer block under BMD PHE Dte.(SM/16701) | Assistant Engineer | Junior Engineer | BILL/01355/2024-2025 | BP-2024-25-345 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.34 | 0 | 0
696 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Kakatia water supply scheme(SM/16701) in Patrasayer block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/02101/2024-2025 |  | 09/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0
697 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I, TW No II, TW No III of Kaktia Piped water supply scheme Block Patrashayar under Bankura Mechanical Division, PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000115/2024-2025 | 426/BMD | 27/06/2024 | 360 | EASTERN INDIA SALES & SERVICE | 74.66 | 0 | 50
698 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00142/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
699 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and fitting Fixing of Pump spares for VT pump and Valves on delivery line installed at Intake (Raw water) pumping station near Durgapur Barrage Block Borjora, Dist- Bankura under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division. | Assistant Engineer | Junior Engineer | ORD/000185/2023-2024 | 962/BMD | 19/05/2023 | 1080 | MAHADEV ENTERPRISE | 55.76 | 35.99 | 89
700 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Talanjuri (Zone-F) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 1410/BMD | 18/07/2023 | 60 | DEBJYOTI BASU | 81.81 | 65.63 | 64
701 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and fitting Fixing of Pump spares for HSC pump installed at water treatment plant and pumping station at Dejuri , Block Borjora, Dist- Bankura under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000460/2023-2024 | 1786/BMD | 01/08/2023 | 90 | S.P. CONSTRUCTION | 70.44 | 67.16 | 95
702 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for new service connection at Bhulanpur ws scheme TW-II, Mouza-Dhabani ,SM-17261 | Assistant Engineer | Junior Engineer | BILL/01177/2024-2025 | BP-2024-25-297 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.37 | 0 | 0
703 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of Quotation for new service connection at PH-I Gengari of Bhulanpur ws scheme.Sm-17261 | Assistant Engineer | Junior Engineer | BILL/01178/2024-2025 | BP-2024-25-298 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0
704 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Bhulanpur and its and its adjoining Mouzas water supply scheme under Onda Block (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000549/2023-2024 | 1985/BMD | 28/08/2023 | 840 | UNIVERSAL ENTERPRISE | 53.98 | 29.4 | 80
705 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of Bhulanpur and adjoining mouzas water supply scheme (BRGF Ph I) Block Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001080/2023-2024 | 3059/BMD | 12/03/2024 | 180 | GOENKA ENTERPRISE | 42.08 | 0 | 0
706 | Bankura Mechanical | Bankura Sadar Sub-Division | Submission of quotation for new service connection at Jamdhara w/s scheme. mouza-Bhedua.SM/17262 | Assistant Engineer | Junior Engineer | BILL/01353/2024-2025 | BP-2024-25-337 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.57 | 0 | 0
707 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Jamdhara & its adjoining Mouzas water supply scheme under onda block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000541/2023-2024 | 1977/BMD | 28/08/2023 | 600 | GOENKA ENTERPRISE | 56.67 | 22.22 | 75
708 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00174/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
709 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for SASHPUR ZONE A water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00437/2024-2025 | BP-2024-25-111 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
710 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Dharampur ( Sashpur Zone-A) | Assistant Engineer | Junior Engineer | BILL/01331/2024-2025 | BP-2024-25-328 | 28/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.66 | 0 | 0
711 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Sashpur Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01623/2023-2024 | BP-2023-24-159 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0
712 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sashpur (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000381/2023-2024 | 1705/BMD | 28/07/2023 | 427 | A.G.ENTERPRISE | 75.74 | 35.75 | 60
713 | Bankura Mechanical | Bankura Mechanical Sub-Division | Augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer (Contractual) | BILL/00211/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
714 | Bankura Mechanical | Bankura Mechanical Sub-Division | New 3 phase connection at Phulberia W/S Scheme (near school) | Assistant Engineer | Junior Engineer (Contractual) | BILL/00951/2024-2025 | BP-2024-25-229 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.44 | 0 | 0
715 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Phulberia piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Sarenga , Dist Bankura | Assistant Engineer | Junior Engineer (Contractual) | ORD/000275/2024-2025 | 780/BMD | 20/08/2024 | 485 | INDRAJIT MITRA | 16.02 | 0 | 80
716 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of piped water supply scheme at Sarenga block, Phulberia , Gargaria water supply scheme under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer (Contractual) | ORD/000416/2025-2026 | 2023/BMD | 12/09/2025 | 90 | M/S P.P ELECTRICALS | 57.8 | 0 | 0
717 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for augmentation works for Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas under Jal Jeevan Mission Programme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000779/2023-2024 | 2294/BMD | 26/12/2023 | 540 | QUAZI NOZRUL ISLAM | 118.75 | 0 | 50
718 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Bhuakana (Zone- A) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | Assistant Engineer | Junior Engineer | BILL/00205/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
719 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Bhuakhana under Khatra-Hirbandh-Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000045/2025-2026 | 249/BMD | 14/05/2025 | 90 | ORIENTAL ENGINEERING CO. | 28.14 | 0 | 0
720 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Radhanagar Zone-II Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00163/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
721 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Janta of Augmentation of Radhanagar ws scheme under BMD ,PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00297/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.68 | 0 | 0
722 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at mouza Layer of Radhanagar ws scheme under BMD,PHED | Assistant Engineer | Junior Engineer | BILL/00298/2024-2025 | 1 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.42 | 0 | 0
723 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for Radhanagar OHR of Radhanagar w/s scheme. | Assistant Engineer | Junior Engineer | BILL/00535/2024-2025 | BP-2024-25-142 | 25/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.65 | 0 | 0
724 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at OHR for Augmentation of Radhanagar (Zone II) piped water supply scheme(BRGF Phase I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000121/2024-2025 | 431/BMD | 27/06/2024 | 360 | PRADIP KUMAR DHABAL | 19.46 | 0 | 61
725 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Radhanagar (Zone-II) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000376/2023-2024 | 1702/BMD | 28/07/2023 | 630 | GOENKA ENTERPRISE | 40.9 | 15.11 | 45
726 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection for KHYERKANAKI (Zone-J) OHR site under Bankura-I,II & Barjora water supply scheme(BRGF Ph-I project) | Assistant Engineer | Junior Engineer | BILL/01145/2024-2025 | BP-2024-25-280 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.31 | 0 | 0
727 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electro mechanical accessories at OHR site of Augmentation works for KHYERKANALI (Zone- J) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 854/BMD | 29/08/2024 | 450 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 40.9 | 0 | 89
728 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Replacement of Valves on the delivery line at IBS Belboni, for Augmentation work for Khyerkanali ( Zone-J) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000415/2024-2025 | 440./BMD | 27/06/2024 | 300 | SARVATAH PROJECTS PRIVATE LIMITED | 42.76 | 23.6 | 55
729 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Mandalkuli (Zone-IIIA) of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/00215/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
730 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Supply installation of riverbed submersible pump motor and allied work for augmentation work at Mandalkuli (IIIA) under Raipur Block sub Surface Water Based Piped Water Supply Scheme , under Bankura Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000015/2025-2026 | 150/BMD | 30/04/2025 | 270 | PRADIP KUMAR DHABAL | 32.25 | 0 | 10
731 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Augmentation work for Mandalkuli (Zone IIIA) of Raipur water supply scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000878/2024-2025 | 2038/BMD | 07/03/2025 | 120 | GOENKA ENTERPRISE | 63.94 | 0 | 0
732 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Modification and up gradation of Gaseous chlorination system at Head work site under Augmentation work of Mandalkuli (zone IIIA ) of Raipur water supply scheme (BRGF Phase I) under JJM , under Bankura Mechanical Division ,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001033/2023-2024 | 2965/BMD | 29/02/2024 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 14.2 | 14.14 | 98
733 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing of drilling materials for sinking of RBTW for rejuvenation of Onda water supply Scheme connection to JJM Program Block: Onda in the district of Bankura under Bankura Mechanical Division P.H.E Dte | Assistant Engineer | Junior Engineer | ORD/000210/2022-2023 | 1346/BMD | 11/11/2022 | 30 | ALPHA ENTERPRISE | 23.3 | 23.19 | 0
734 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Sub Surface water based water supply scheme(Left outfrom BRGF Mouza) for Onda under onda block under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000543/2023-2024 | 1979/BMD | 28/08/2023 | 120 | UNITED TRADERS | 56.54 | 31.01 | 55
735 | Bankura Mechanical | Brishnupur Sub-Division | Bagdoba Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01547/2023-2024 | BP-2023-24-93 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.38 | 0 | 0
736 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Bagdoba Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000169/2023-2024 | 881/BMD | 04/05/2023 | 1080 | TAPAN KUMAR SARKAR | 47.08 | 26.89 | 60
737 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Karisunda Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00189/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
738 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Karisunda Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01620/2023-2024 | BP-2023-24-153 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.19 | 0 | 0
739 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Karisunda piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000384/2023-2024 | 1707/BMD | 28/07/2023 | 244 | ABHIJIT MUKHERJEE | 61.17 | 40.16 | 66
740 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Chakuparsole Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00170/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
741 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at mouza -Upar Amdahara jl no 146.SM/17426 | Assistant Engineer | Junior Engineer | BILL/00365/2025-2026 | 236/W-1262 | 12/02/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.58 | 0 | 0
742 | Bankura Mechanical | Brishnupur Sub-Division | Submission of Quotation for new service connection at Mouza Phulboni of Chakuparsole Zone-B ws scheme.SM/17426 | Assistant Engineer | Junior Engineer | BILL/00539/2024-2025 | BP-2024-25-208 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0
743 | Bankura Mechanical | Brishnupur Sub-Division | Submission of quotation for new service connection at Mouza Upar Amdahara of Chakuparsole Zone-B W/S scheme Boosting TW-I. SM/17426. | Assistant Engineer | Junior Engineer | BILL/00540/2024-2025 | BP-2024-25-209 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.9 | 0 | 0
744 | Bankura Mechanical | Brishnupur Sub-Division | Additional Quotation for Mouza Fulbani ,GP Bankadaha .Chakuparsole zone-B.SM/17426 | Assistant Engineer | Junior Engineer | BILL/01341/2024-2025 | BP-2024-25-335 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.91 | 0 | 0
745 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at Existing TW II to IV for Augmentation of Chakuparsole and Adjoining mouza water supply scheme (Zone-B) Block-Bishnupur under Under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000142/2024-2025 | 485/BMD | 09/07/2024 | 386 | GOENKA ENTERPRISE | 34.36 | 0 | 100
746 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chakuparsole (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Bishnupur , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000368/2023-2024 | 1699/BMD | 28/07/2023 | 960 | S.P. CONSTRUCTION | 71.56 | 0 | 0
747 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Rol Zone-B Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00183/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
748 | Bankura Mechanical | Brishnupur Sub-Division | Load enhancement charges for ROLL ZONE B water supply scheme under B.M.D P.H.E Dte | Assistant Engineer | Junior Engineer | BILL/00431/2024-2025 | BP-2024-25-107 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.84 | 0 | 0
749 | Bankura Mechanical | Brishnupur Sub-Division | New 3 phase connection at Dhamur (Roll Zone-B) | Assistant Engineer | Junior Engineer | BILL/01330/2024-2025 | BP-2024-25-331 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.96 | 0 | 0
750 | Bankura Mechanical | Brishnupur Sub-Division | New three service phase connection for boosting TW site of Arapur(Gopalpur) under Roll Zone -B water supply scheme under Bankura Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer | BILL/01344/2024-2025 | BP-2024-25-332 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.26 | 0 | 0
751 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Rol (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000378/2023-2024 | 1704/BMD | 28/07/2023 | 60 | R.N.S. TRADING | 73.25 | 0 | 0
752 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at T/W-III of Khejuria | Assistant Engineer |  | BILL/01146/2024-2025 | BP-2024-25-271 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.71 | 0 | 0
753 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at T/W-IV of Khejuria | Assistant Engineer |  | BILL/01147/2024-2025 | BP-2024-25-272 | 19/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.46 | 0 | 0
754 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service connection at P/H-I of Khejuria | Assistant Engineer |  | BILL/01149/2024-2025 | BP-2024-25-281 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.8 | 0 | 0
755 | Bankura Mechanical | Bankura Mechanical Sub-Division | New service Connection at Khejuria T/W-II | Assistant Engineer |  | BILL/01480/2024-2025 | BP-2024-25-370 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.88 | 0 | 0
756 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Khejura (Zone N) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer |  | ORD/000044/2025-2026 | 248/BMD | 14/05/2025 | 90 | M.S. ENTERPRISE | 29.11 | 0 | 0
757 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for Augmentation works for Khejuria (Zone- N) ( Boosting at OHR Site) under Improvement of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte. Block : Ranibandh , Dist: Bankura | Assistant Engineer |  | ORD/000170/2024-2025 | 512/BMD | 09/07/2024 | 720 | DEBJYOTI BASU | 92.97 | 0 | 68
758 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | Assistant Engineer | Junior Engineer | BILL/00195/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
759 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Gargariya zone A water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme | Assistant Engineer | Junior Engineer | BILL/00213/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
760 | Bankura Mechanical | Khatra Sub-Division | New service connection for Gargaria water supply scheme under Bankura Mechanical Division Dte. | Assistant Engineer | Junior Engineer | BILL/00383/2024-2025 | BP-2024-25-84 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
761 | Bankura Mechanical | Khatra Sub-Division | New service connection for Gargaria water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00384/2024-2025 | BP-2024-25-87 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0
762 | Bankura Mechanical | Khatra Sub-Division | New 3 phase service connection for site Gargaria Zone A | Assistant Engineer | Junior Engineer | BILL/00697/2024-2025 | BP-2024-25-163 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.18 | 0 | 0
763 | Bankura Mechanical | Khatra Sub-Division | New 3 phase service connection for site Gargaria Zone A | Assistant Engineer | Junior Engineer | BILL/00698/2024-2025 | BP-2024-25-168 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.43 | 0 | 0
764 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of HL Pumping machineries with illumination system other electromechanical accessories for Augmentation for Gargariya Zone-A and adjoining mouzas under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 514/BMD | 09/07/2024 | 600 | S.P. CONSTRUCTION | 78.81 | 0 | 20
765 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing installation of High lift Pumping machineries with allied works for Augmentation works for Gargariya Zone B water supply scheme under sarenga water supply scheme (BRGF ph 1) under jal jeevan mission programme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000321/2024-2025 | 862/BMD | 29/08/2024 | 240 | TAPAN KUMAR SARKAR | 34.3 | 0 | 70
766 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation works for Gargariya Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Bankura Mechanical Division, PHE Dte, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000573/2023-2024 | 2029/BMD | 01/09/2023 | 1070 | S.P. CONSTRUCTION | 90.11 | 0 | 30
767 | Bankura Mechanical | Khatra Sub-Division | Service connection charge for SONAGARA water supply scheme (scheme code: SM/18390) | Assistant Engineer | Junior Engineer | BILL/00350/2024-2025 | BP-2024-25-82 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 36.61 | 0 | 0
768 | Bankura Mechanical | Khatra Sub-Division | Laying rising main, distribution system, collecting line from RBTW to CWR, construction of CWR, Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including provision of FHTC under balance work of Improvement of Sonagara Water Supply Scheme under BRGF (Phase - I) under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer | BILL/01519/2023-2024 | BP-2023-24-119 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.05 | 0 | 0
769 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of submersible pumping machineries & gaseous chlorination system and other electromechanical accessories and Making an arrangement for proper material management and handling at Ailakandi PHE Mechanical office campus for Augmentation of Sonagara and its adjoining mouzas water supply scheme under Jal Jeeven mission Progremme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000144/2024-2025 | 487/BMD | 09/07/2024 | 390 | WEST BENGAL ENGINEERING CO. | 83.28 | 0 | 30
770 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing of pumping machineries, Sub-Station equipment¿s and other Electro-mechanical accessories For the scheme of Laying rising main distribution system collecting line from RBTW to CWR Pump House, Sub-Station, Chlorine Room, OHR and boundary wall including providing of FHTC under balance work of improvement of Sanagara water supply scheme under BRGF( Phase-I) under Jal Jeevan Mission Programme Block - Raipur , Dist - Bankura | Assistant Engineer | Junior Engineer | ORD/000613/2023-2024 | 2068/BMD | 12/09/2023 | 809 | WEST BENGAL ENGINEERING CO. | 409.3 | 200.9 | 56
771 | Bankura Mechanical | Brishnupur Sub-Division | Submission of application fee for Solar Power Plant of 12.42 KWP at Chak Patrasayer J.L No-48,Plot No-4623 under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00361/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0
772 | Bankura Mechanical | Brishnupur Sub-Division | Submissioin of application fee for Solar Power Plant of 12.42 KWP at Chak Patrasayer JL no-48 plot no-4621 under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00362/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0
773 | Bankura Mechanical | Brishnupur Sub-Division | Submission of application fee for Solar Power Plant of 12.42 KWP at Chak Patrasayer J.L No-48,Plot No-4622 under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00363/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.01 | 0 | 0
774 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Chak Patrasayer water supply scheme at Patrasayer block under BMD PHE Dte.(SM/18401) | Assistant Engineer | Junior Engineer | BILL/01599/2024-2025 |  | 17/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.75 | 0 | 0
775 | Bankura Mechanical | Brishnupur Sub-Division | Chak Patrasaer Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01615/2023-2024 | BP-2023-24-132 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.29 | 0 | 0
776 | Bankura Mechanical | Brishnupur Sub-Division | Chak Patrasaer Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01668/2023-2024 | BP-2023-24-176 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.03 | 0 | 0
777 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Chak Patrasayer Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000036/2025-2026 | 241/BMD | 14/05/2025 | 90 | KASHINATH DEY | 12.22 | 0 | 0
778 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II & TW No-III of Chak Patrasayar Piped water supply scheme Block : Patrasayar under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 882/BMD | 04/05/2023 | 701 | M.S. ENTERPRISE | 68.15 | 34.26 | 45
779 | Bankura Mechanical | Brishnupur Sub-Division | Basantapur Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01499/2023-2024 | BP-2023-24-106 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.47 | 0 | 0
780 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Basantapur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000184/2025-2026 | 456/BMD | 10/06/2025 | 90 | AMITAVA CHAKRABORTY | 11.91 | 0 | 0
781 | Bankura Mechanical | Bankura Sadar Sub-Division | WBSEDCL, Quotation Bill for new power connection at Purakanda Pump House augmentation work under Pakhanna water supply scheme (SM/03512) | Assistant Engineer | Junior Engineer | BILL/00727/2024-2025 | BP-2024-25-211 | 03/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0
782 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge for Gopalpur Pump house under Pakhanna and its Adjoining mouzas water supply scheme Barjora block under BMD,PHE Dte.(SM/16973 ) | Assistant Engineer | Junior Engineer | BILL/02195/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.88 | 0 | 0
783 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No-I & II at Tail End site of Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000328/2024-2025 | 867/BMD | 29/08/2024 | 120 | SK ENTERPRISE | 12.1 | 3.1 | 71
784 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Pakhanna & its adjoining mouzas water supply scheme Block Barjora under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 1768/BMD | 01/08/2023 | 60 | M/S NABIN GOPAL SENGUPTA | 72.97 | 55 | 74
785 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1402/BMD | 12/12/2024 | 120 | SK ENTERPRISE | 30.4 | 0 | 0
786 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (JJM REVISION) | Assistant Engineer | Junior Engineer | BILL/00194/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
787 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation od surface water based piped water supply scheme for Sanband, Kargahir and adjoining mouza under Bankura Mechanical Division PHE Dte Block-Bankura-I Dist -Bankura. | Assistant Engineer | Junior Engineer | ORD/000192/2023-2024 | 1015/BMD | 22/05/2023 | 720 | M.S. ENTERPRISE | 43.65 | 34.65 | 100
788 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | Assistant Engineer | Junior Engineer | BILL/00121/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.4 | 0 | 0
789 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmantation of Nabakishore Ground Base piped water supply scheme under JJM program under Bankura Mechanical Division, PHE Dte Block : Patrasayar, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 934/BMD | 12/05/2023 | 180 | M/S NABIN GOPAL SENGUPTA | 56.49 | 43.47 | 76
790 | Bankura Mechanical | Khatra Sub-Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | Assistant Engineer | Junior Engineer | BILL/00122/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
791 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000188/2023-2024 | 964/BMD | 19/05/2023 | 1065 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 39.1 | 22.9 | 70
792 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Name of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/001353/2023-2024 | 1013/BMD | 22/05/2023 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 47.59 | 0 | 0
793 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Jayrambati Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00123/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
794 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Jayrambati Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00133/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.6 | 0 | 0
795 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Name of Work:Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Joyrambati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 935/BMD | 12/05/2023 | 180 | KASHINATH DEY | 29.69 | 22.96 | 77
796 | Bankura Mechanical | Brishnupur Sub-Division | Harinsuli T/W-I | Assistant Engineer | Junior Engineer | BILL/00846/2023-2024 | BP-2023-24-46 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.01 | 0 | 0
797 | Bankura Mechanical | Brishnupur Sub-Division | Harinasuli T/W-II | Assistant Engineer | Junior Engineer | BILL/00847/2023-2024 | BP-2023-24-47 | 18/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.23 | 0 | 0
798 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk at TW No-I & T.W No-II of Harinashuli piped water supply scheme Block : Joypur under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 876/BMD | 04/05/2023 | 180 | MITRA ENTERPRISE | 39.3 | 23.71 | 50
799 | Bankura Mechanical | Brishnupur Sub-Division | New service connection at Pankhai t/w-II ,hetia gp of joypur block under BMD PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00129/2024-2025 | BP-2024-25-37 | 10/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.17 | 0 | 0
800 | Bankura Mechanical | Brishnupur Sub-Division | Pankhai Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01498/2023-2024 | BP-2023-24-103 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.68 | 0 | 0
801 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Pankhai Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000185/2025-2026 | 457/BMD | 10/06/2025 | 90 | A.G.ENTERPRISE | 11.86 | 0 | 0
802 | Bankura Mechanical | Khatra Sub-Division | New Service connection at Dhghora. | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01476/2024-2025 | BP-2024-25-373 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.06 | 0 | 0
803 | Bankura Mechanical | Khatra Sub-Division | Payment for WBSEDCL Net Billing meter arrangement for 90KW solar power at Mukutmanipur (Old) water supply scheme [SM/115007] | Assistant Engineer,Driller-in-Charge | Junior Engineer | BILL/01484/2024-2025 | BP-2024-25-374 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0
804 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-1A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000233/2023-2024 | 1119/BMD | 24/05/2023 | 45 | KASHINATH DEY | 26.4 | 0 | 0
805 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, and installation of Flow Meter with other electro mechanical accessories of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme for OHR site Zone 1A under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001085/2023-2024 | 3062/BMD | 12/03/2024 | 360 | UNITED TRADERS | 9.08 | 0 | 100
806 | Bankura Mechanical | Khatra Sub-Division | New service connection at OHR site Zone-2A of Augmentation of Mukutmonipur,khatra Ranibandh piped water supply scheme ( Tentulchita) | Assistant Engineer | Junior Engineer | BILL/01174/2024-2025 | BP-2024-25-303 | 09/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.62 | 0 | 0
807 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing & installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-2A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 1784/BMD | 01/08/2023 | 120 | S P ENTERPRISE (SILIGURI) | 26.41 | 0 | 0
808 | Bankura Mechanical | Brishnupur Sub-Division | New Service connection at P/H-I of Lego W/S scheme. | Assistant Engineer | Junior Engineer | BILL/01347/2024-2025 | BP-2024-25-350 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.65 | 0 | 0
809 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Lego Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000148/2025-2026 | 443/BMD | 10/06/2025 | 90 | TAPAN KUMAR SARKAR | 11.86 | 0 | 0
810 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for NARUALA TW-1 Water supply scheme(JLNO-123,PLOT-1041) under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00007/2024-2025 | BP-2024-25-34 | 10/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.47 | 0 | 0
811 | Bankura Mechanical | Brishnupur Sub-Division | New Service Connection for NARUALA TW-2(JL NO-122, PLOT-70) Water supply scheme under Bankura Mechanical Division PHE DTE | Assistant Engineer | Junior Engineer | BILL/00008/2024-2025 | BP-2023-24 | 28/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.8 | 0 | 0
812 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Narula Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000154/2025-2026 | 449/BMD | 10/06/2025 | 90 | S. G. TECHNICAL SERVICE | 10.9 | 0 | 0
813 | Bankura Mechanical | Khatra Sub-Division | New service connection at Mukutmonipur,Khatra & Ranibandh W/S scheme ,Zone-VIII/A (Bhurkura) | Assistant Engineer | Junior Engineer | BILL/02194/2025-2026 |  | 12/03/2026 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.62 | 0 | 0
814 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Pumping machineries with other electro-mechanical accessories for OHR site Zone-8A of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 1120/BMD | 24/05/2023 | 45 | AMITAVA CHAKRABORTY | 26.24 | 0 | 0
815 | Bankura Mechanical | Brishnupur Sub-Division | Nandagram Piped Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/01502/2023-2024 | BP-2023-24-100 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 18.36 | 0 | 0
816 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandagram Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000149/2025-2026 | 444/BMD | 10/06/2025 | 90 | AMITAVA CHAKRABORTY | 12.97 | 0 | 0
817 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for Godardihi (Zone - E) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00140/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
818 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Godardihi ( Zone-E) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000302/2023-2024 | 1405/BMD | 18/07/2023 | 60 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 81.77 | 61.83 | 74
819 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00146/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
820 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for HARIALGARA (Zone- O) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/01613/2023-2024 | BP-2023-24-138 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0
821 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System at Harialgara (Zone-O) OHR under Bankura-I.II and Barjora Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000141/2025-2026 | 436/BMD | 10/06/2025 | 90 | M.S. ENTERPRISE | 26.28 | 0 | 0
822 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Harialgara (Zone O) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000517/2023-2024 | 1882/BMD | 17/08/2023 | 120 | MAHADEV ENTERPRISE | 81.83 | 34.82 | 42
823 | Bankura Mechanical | Bankura Sadar Sub-Division | Ground Water Based Nakaijuri Pipe Water Supply Scheme under Bankura Division, Block - Onda, District - Bankura. | Assistant Engineer | Junior Engineer | BILL/01606/2023-2024 | BP-2023-24-140 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.34 | 0 | 0
824 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories at TW No-III of Nakaijuri and its Adjoining mouza water supply scheme under Onda Block under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000148/2024-2025 | 491/BMD | 09/07/2024 | 120 | SWAPAN ENTERPRISE | 19.95 | 0 | 0
825 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for proposed ground water based Nakaijuri piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Onda , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000387/2023-2024 | 1709/BMD | 28/07/2023 | 60 | M/S BIPUL BANERJEE | 37.92 | 18.15 | 48
826 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation for Gouripur Water Supply Scheme. | Assistant Engineer | Junior Engineer | BILL/00153/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
827 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Gouripur Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block : Bankura-I ,Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000452/2023-2024 | 1778/BMD | 01/08/2023 | 600 | KASHINATH DEY | 23.42 | 22.34 | 100
828 | Bankura Mechanical | Khatra Sub-Division | New service connection at 1st CWR site of Banpukuria Water supply scheme | Assistant Engineer | Junior Engineer | BILL/01176/2024-2025 | BP-2024-25-299 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.97 | 0 | 0
829 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation work for Banpukuria under Khatra- Hirbandh- Ranibandh water supply scheme Block- Ranibandh under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000732/2023-2024 | 2207/BMD | 21/11/2023 | 180 | M/S BIPUL BANERJEE | 40.48 | 31.94 | 78
830 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Arkama (Zone H) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 247/BMD | 14/05/2025 | 90 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 29.11 | 0 | 0
831 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at tail end and CWR site for for Augemention works for Arkama (zone - H) Under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF - I) under Bankura Mechanical Division, PHE Dte. Block : Khatra , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000169/2024-2025 | 511/BMD | 09/07/2024 | 120 | RAJIB COMPANY | 44.01 | 0 | 0
832 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of High lift and Low Lift Pumping machineries with other electro-mechanical accessories at CWR site for for Augemention works for Arkama (zone H) Under Khatra Hirbandh Ranibandh Water Supply Scheme under Bankura Mechanical Division, PHE Dte. Block Khatra , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000880/2024-2025 | 2040/BMD | 07/03/2025 | 120 | M/S TARUN KUMAR PATRA | 42.61 | 0 | 0
833 | Bankura Mechanical | Brishnupur Sub-Division | Augmentation of Kushmuri Zone-A Water Supply Scheme | Assistant Engineer | Junior Engineer | BILL/00176/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
834 | Bankura Mechanical | Brishnupur Sub-Division | 3 phase new connection at Khatnagar (Khusmuri Zone-A) Indus Block | Assistant Engineer | Junior Engineer | BILL/01334/2024-2025 | BP-2024-25-336 | 13/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.72 | 0 | 0
835 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of External illumination system at Kushmuri CWR site under Kushmuri zone-A piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Indus, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000123/2024-2025 | 1071/BMSD | 05/07/2024 | 376 | UNICON | 4.38 | 0 | 100
836 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Augmentation of sub- station equipment at Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Indus , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000268/2024-2025 | 776/BMD | 20/08/2024 | 120 | M.S. ENTERPRISE | 14.05 | 0 | 100
837 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kushmuri (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000370/2023-2024 | 1700/BMD | 28/07/2023 | 891 | TAPAN KUMAR SARKAR | 59.31 | 31.25 | 53
838 | Bankura Mechanical | Brishnupur Sub-Division | New service connection for Nandur w/s scheme at Patrasayer block under BMD PHE Dte.(SM/18252) | Assistant Engineer | Junior Engineer | BILL/00359/2025-2026 |  | 03/06/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.38 | 0 | 0
839 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Electromagnetic flowmeter with motorized Sluice Valve for respective OHR for at Nandur Piped Water Supply Scheme under BMD PHE Dte Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000417/2025-2026 | 581/BMD | 04/07/2025 | 90 | OSMAN SEKH | 12.68 | 0 | 0
840 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00136/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
841 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Cherabasta (Zone-K) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000312/2023-2024 | 1411/BMD | 18/07/2023 | 60 | DEBJYOTI BASU | 81.81 | 65.59 | 80
842 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No- I at Tail End site of Augmentation works for CHERABASTA (Zone- K) under Bankura - I, II and Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000315/2024-2025 | 856/BMD | 29/08/2024 | 120 | CHAKRABORTY MINING & ENGINEERING. | 9.23 | 3.87 | 60
843 | Bankura Mechanical | Bankura Sadar Sub-Division | Augmentation works for CHATERKANALI (Zone- L) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | Assistant Engineer | Junior Engineer | BILL/00137/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0
844 | Bankura Mechanical | Bankura Sadar Sub-Division | New service connection at Narrah mouza for Chaterkanali augmentation site under BMD PHE Dte.(SM/17698) | Assistant Engineer | Junior Engineer | BILL/01468/2024-2025 | BP-2024-25-361 | 07/02/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0
845 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work ofProviding and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Chaterkanali (Zone-L) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 1464/BMD | 18/07/2023 | 60 | TAPAN KUMAR DEY | 81.77 | 52.56 | 64
846 | Bankura Mechanical | RWS Bankura Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Naria (Zone E) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000056/2025-2026 | 252/BMD | 14/05/2025 | 90 | WEST BENGAL ENGINEERING CO. | 28.18 | 0 | 0
847 | Bankura Mechanical | Brishnupur Sub-Division | Acceptance cum Formal work order for the work of Supply, delivery and installation of HSC Pumping machinery set with other allied works at CWR site for augmentation of Somsar water supply scheme under Bankura Mechanical Division P.H.E Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000341/2024-2025 | 785/BMD | 20/08/2024 | 240 | ABHIJIT MUKHERJEE | 34.91 | 7.48 | 60
848 | Bankura Mechanical | Khatra Sub-Division | Augmentation works for Belatikri, Zone-A water Supply Scheme under Sarenga water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | BILL/00209/2023-2024 |  | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0
849 | Bankura Mechanical | Khatra Sub-Division | New service connection for Belatikri water supply scheme under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00385/2024-2025 | BP-2024-25-83 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
850 | Bankura Mechanical | Khatra Sub-Division | New3 Phase Service Connection for Belatikri | Assistant Engineer | Junior Engineer | BILL/00699/2024-2025 | BP-2024-25-162 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0
851 | Bankura Mechanical | Khatra Sub-Division | New service connection for Belatikri Zone-A JL-30, Plot-104 | Assistant Engineer | Junior Engineer | BILL/01151/2024-2025 | BP-2024-25-278 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.65 | 0 | 0
852 | Bankura Mechanical | Khatra Sub-Division | New service connection for Belatikri Zone-A , Jl -39, Plot-233 | Assistant Engineer | Junior Engineer | BILL/01153/2024-2025 | BP-2024-25-279 | 21/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0
853 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Additional work for Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation for Belatikri Zone-A water supply scheme(BRGF Ph-I) under Jal Jeevan Mission Progremme under Bankura Mechanical Division PHE Dte, Dist.-Bankura. | Assistant Engineer | Junior Engineer | ORD/000011/2024-2025 | 519/BMSD(D) | 11/06/2024 | 21 | M.S. ENTERPRISE | 2.8 | 2.77 | 100
854 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Voltage Stabilizer and submersible pumping machineries with other allied works for Augmentation of Sarenga water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000513/2024-2025 | 573/BMD | 23/07/2024 | 750 | TAPAN KUMAR SARKAR | 25.19 | 0 | 0
855 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation for Belatikri Zone-A water supply scheme under Sarenga water supply scheme (BRGF Ph-I) under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000569/2023-2024 | 2026/BMD | 01/09/2023 | 911 | M.S. ENTERPRISE | 96.39 | 84.82 | 70
856 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase-I) at tubewell No I Pump House No I under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001032/2023-2024 | 2964/BMD | 29/02/2024 | 180 | INDRAJIT MITRA | 12.8 | 8.18 | 50
857 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No II Pump House No II under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001035/2023-2024 | 2967/BMD | 29/02/2024 | 712 | PRADIP KUMAR DHABAL | 12.8 | 0 | 65
858 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation for Belatikari (Zone A) piped water supply scheme (BRGF Phase I) at tubewell No III Pump House No III under Bankura Mechanical Division, PHE Dte. Block : Sarenga , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001038/2023-2024 | 2970/BMD | 29/02/2024 | 180 | M/S DAS & SARKAR ENTERPRISE | 12.76 | 7.52 | 50
859 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Hetiasol (Zone IIB) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000041/2025-2026 | 245/BMD | 14/05/2025 | 90 | TAPAN KUMAR DEY | 28.18 | 0 | 0
860 | Bankura Mechanical | Khatra Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low lift pumping machineries and other electromechanical accessories for Dahala W.S Scheme under Augmentation Works for Hetiasol (Zone-IIB) under Khatra-Hirbandh-Ranibandh Water Supply-Scheme (BRGF Ph-I) under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/000151/2024-2025 | 494/BMD | 09/07/2024 | 328 | ABHIJIT MUKHERJEE | 65.43 | 0 | 63
861 | Bankura Mechanical | Bankura Sadar Sub-Division | Formal work order for the work of Providing And Installation Of Pumping Machineries, Substation Equipments And Other Electro-Mechanical Accessories at Head Works site for Improvement of Khatra-Ranibandh-Hirbandh Water supply Scheme, Block- Ranibandh, Dist- Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001000/2020-2021 | 1319/BMD | 18/11/2020 | 181 | DEY ENTERPRISE | 107.65 | 105.5 | 95
862 | Bankura Mechanical | Bankura Mechanical Sub-Division | Augmentation works for Piped Water Supply Scheme for Lakshmisagar & Its Adjoining Mouzas under Jal Jeevan Mission Programme | Assistant Engineer | Junior Engineer (Contractual) | BILL/01661/2023-2024 | BP-2023-24-175 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.19 | 0 | 0
863 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories in boosting site and HWS site for Augmentation works for Piped Water Supply Scheme for Lakshmisagar and Its Adjoining Mouzas under Jal Jeevan Mission Programme under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000145/2024-2025 | 488/BMD | 09/07/2024 | 600 | MAHADEV ENTERPRISE | 54.94 | 0 | 23
864 | Bankura Mechanical | Bankura Mechanical Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation works for Augmentation of piped water supply scheme for Lakshmisagar and its adjoining mouzas under Jal Jeevan mission programe under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Contractual) | ORD/000618/2023-2024 | 2090/BMD | 12/09/2023 | 840 | MAHADEV ENTERPRISE | 86.97 | 0 | 13
865 | Bankura Mechanical | Bankura Sadar Sub-Division | New Service connection charge at Chhandar,Molbagan Pump House tail end T/W under Beliatore water supply scheme Barjora block under BMD,PHE Dte. (sm/09924) | Assistant Engineer | Junior Engineer | BILL/01342/2024-2025 | BP-2024-25-354 | 29/01/2025 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.55 | 0 | 0
866 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Beliatore w/s scheme under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000263/2024-2025 | 518/BMD | 09/07/2024 | 120 | DEY ENTERPRISE | 17.63 | 0 | 0
867 | Bankura Mechanical | Bankura Sadar Sub-Division | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for Augmentation of Beliatore its adjoining mouzas piped water supply scheme (JJM Revision) under Bankura Mechanical Division PHE Dte Block Borjora Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000511/2023-2024 | 1876/BMD | 17/08/2023 | 720 | DEY ENTERPRISE | 64.51 | 0 | 51
Total | [10 empty] | 20789.21 | 6909.41