## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | NTK Mechanical |  | Supply & Installation of pumping machineries & other electro-mechanical accessories in Sulanggari piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000225/2023-2024 | 2133/NTKMD | 11/08/2023 | 180 | GLACIER ENGINEERING CO. | 65.81 | 0 | 0
2 | NTK Mechanical |  | Supply & Installation of pumping machineries & other electro-mechanical accessories in Thakdari piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000041/2023-2024 | 783 / NTKMD | 26/05/2023 | 180 | DIPALI CONSTRUCTION | 27.24 | 0 | 85
3 | NTK Mechanical |  | Supply & Installation of pumping machineries & other electro-mechanical accessories in Raigachhi piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000224/2023-2024 | 2131/NTKMD | 11/08/2023 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 47.44 | 0 | 0
4 | NTK Mechanical |  | Supply & Installation of pumping machineries & other electro-mechanical accessories in Tarulia piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000227/2023-2024 | 2134/NTKMD | 11/08/2023 | 180 | AHALYA ENGINEERING WORKS | 73.96 | 0 | 0
5 | NTK Mechanical |  | Supply & Installation of pumping machineries & other electro-mechanical accessories in Jatragachi piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000223/2023-2024 | 2132/NTKMD | 11/08/2023 | 180 | GLACIER ENGINEERING CO. | 43.91 | 0 | 0
6 | NTK Mechanical |  | Supply & Installation of pumping machineries & other electro-mechanical accessories in Ghuni piped W/S scheme under New Town Kolkata Mechanical Division, P.H.E. Dte. |  |  | ORD/000226/2023-2024 | 2135/NTKMD | 11/08/2023 | 180 | GLACIER ENGINEERING CO. | 65.81 | 0 | 0
Total | [10 empty] | 324.18 | 0