## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Functional household Tap Connection by retrofitting of Betuabati W/S Scheme for Betuabatirajarampur, Kishorpur and Betuabati Mouzas under Budge Budge I Block with allied works under "Surface water Based Mega water Supply Scheme for Falta Mathurapur¿ | AE SWSD-I |  | ORD/000115/2020-2021 | 1464/SWD-I | 21/12/2020 | 120 | M/S. GOUTAM ROY | 66.54 | 55.28 | 0
2 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance work of Providing Functional Household Tap Connection for Bethuabati W/S Scheme & Adjoining Areas under Budge Budge-I block with alied works under Surface Water Based Water Supply Scheme for Falta-Mathurapur under South-24 Pns W/S- Divn-I, PHE Dte. | AE SWSD-I |  | ORD/000328/2022-2023 | 2045/SWD-I | 30/11/2022 | 60 | P.S. AND ASSOCIATES | 20.98 | 20.84 | 35
3 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Functional household Tap Connection by retrofitting of Betuabati W/S Scheme for Betuabatirajarampur, Kishorpur and Betuabati Mouzas under Budge Budge I Block with allied works under "Surface water Based Mega water Supply Scheme for Falta Mathurapur¿ | AE SWSD-I |  | ORD/000329/2020-2021 | 1464/SWD-I JJM | 21/12/2020 | 120 | M/S. GOUTAM ROY | 66.37 | 15.09 | 100
4 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Nandarampur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000103/2021-2022 | 1105/SWD-I JJM | 25/10/2021 | 120 | M/S. S.S. ENTERPRISE | 59.13 | 36.36 | 100
5 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nandarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8296) Part -F | AE SWSD-I |  | ORD/000465/2022-2023 | 2780/SWD-I | 31/01/2023 | 45 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 6.1 | 6.08 | 100
6 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Nandarampur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | VCH/001189/2021-2022 | BP-2021-22-214 | 25/03/2022 | 0 | M/S. S.S. ENTERPRISE | 19.63 | 0 | 0
7 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for DOSATINA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000030/2022-2023 | 914/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.2 | 12.15 | 100
8 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed DOSATINA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 924] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000187/2022-2023 | 1489/SWD-I | 28/09/2022 | 1001 | NEW STAR CONSTRUCTION | 110.18 | 106.57 | 70
9 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
10 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/09/2025 to 31/10/2025) [Vehhicle No - WB-19J-3488] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000212/2025-2026 | 2155/SWD-I | 25/08/2025 | 61 | NIRMAL UDYOG | 0.29 | 0 | 0
11 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, pump house, laying of additional pipeline, and other allied works for DOSATINA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11503] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000258/2024-2025 | 2675/SWD-I | 07/06/2024 | 450 | NEW STAR CONSTRUCTION | 43.67 | 0 | 85
12 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for DOSATINA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011196] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000385/2023-2024 | 1821/SWD-I | 16/08/2023 | 30 | MOULI CONSTRUCTION | 15.87 | 4 | 70
13 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "DOSTINA Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000403/2022-2023 | 457/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 2.51 | 100
14 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of DOSATINA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11503) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000444/2022-2023 | 2663/SWD-I | 18/01/2023 | 60 | M/S P. PURKAIT ENTERPRISE. | 6.02 | 5.85 | 100
15 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DOSATINA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011196] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000506/2022-2023 | 2904/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 100
16 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed DOSATINA Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011196] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000807/2022-2023 | 3699/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.96 | 0.95 | 100
17 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000013/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.69 | 0 | 0
18 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000109/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 23.65 | 0 | 0
19 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at PANCH GACHIA of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1143] | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 117/SWD-I | 11/04/2023 | 985 | M/S. GOUTAM ROY | 172.9 | 45.01 | 60
20 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Construction of boundary walls, platform for FHTC, protection of pipeline, development of land and other allied works for Ground water based PANCH GACHHIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/12240) | Assistant Engineer | Junior Engineer | ORD/000333/2024-2025 | 3271/SWD-I | 22/07/2024 | 45 | S. ROY AND ASSOCIATES | 66.2 | 0 | 0
21 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Preparation and submission of Detailed Project Report of PANCH GACHHIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000405/2021-2022 | 1940/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 2.56 | 0
22 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PANCHGACHIA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/12240] | Assistant Engineer | Junior Engineer | ORD/000563/2022-2023 | 3060/SWD-I | 21/02/2023 | 30 | AKBAR ALI | 31.75 | 30.56 | 100
23 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000185/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 24.23 | 0 | 0
24 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 1 (One) no. boundary wall at Burul for Providing FHTC with allied works for Zone-1, 3 & 5 of Budge Budge-II Block under South 24 Parganas W/S Division-I, P.H.E. Dte. of South 24-Pargans District (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000017/2025-2026 | 969/SWD-I | 09/04/2025 | 60 | MS POUSALI ENTERPRISE | 12.01 | 0 | 0
25 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance Upvc Pipeline laying at Burul W/S Scheme for Providing FHTC with allied works for Zone 1, Zone 3 & Zone 5 of Budge Budge-II under South 24 pgs. W/S Division-I, PHED, Dist.-South 24 pgs.(TSM/010530) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000045/2023-2024 | 184/SWD-I | 18/04/2023 | 30 | ARKADEEP ENTERPRISE | 19.78 | 19.78 | 100
26 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of pipe line for interconnection from proposed Tubewell to Distribution Main for Burul Village (Part) to Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000054/2022-2023 | 1014/SWD-I | 02/08/2022 | 60 | AHANA ENTERPRISE | 3.81 | 3.76 | 100
27 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of pipe line for interconnection from proposed Tubewell to Distribution Main for Rania & Kuchigadi Village to Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000055/2022-2023 | 1016/SWD-I | 02/08/2022 | 60 | HASIBA ENTERPRISE | 3.81 | 3.76 | 100
28 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Blower room (Size 3.60m X 3.00m) at Burul Village (Part) of Budge Budge-II block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000057/2022-2023 | 1015/SWD-I | 02/08/2022 | 60 | AHANA ENTERPRISE | 3.07 | 2.99 | 100
29 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Blower room (Size 3.60m X 3.00m) at Chakmanik Village (Part) Village of Budge Budge-II block under South 24 Pgs W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000059/2022-2023 | 1019/SWD-I | 02/08/2022 | 60 | MS POUSALI ENTERPRISE | 3.06 | 2.99 | 100
30 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2025 to 30/11/2025] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000059/2025-2026 | 1368/SWD-I | 22/05/2025 | 183 | AVIK HALDER | 0.89 | 0 | 0
31 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Burul Village (Part) of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000108/2022-2023 | 1238/SWD-I | 08/09/2022 | 30 | PADMA ENGINEERING CO. | 20.09 | 18.8 | 100
32 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Rania & Kuchigadi village of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000109/2022-2023 | 1239/SWD-I | 08/09/2022 | 30 | M/S. S.S. ENTERPRISE | 20.09 | 18.73 | 100
33 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Chakmanik village (Part) of Budge Budge - II Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000110/2022-2023 | 1240/SWD-I | 08/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 20.08 | 18.5 | 100
34 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Burul Village (Part) of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000111/2022-2023 | 1241/SWD-I | 08/09/2022 | 60 | SANJAY MIDDEY | 5.41 | 5.17 | 100
35 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Rania & Kuchigadi village of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000112/2022-2023 | 1242/SWD-I | 08/09/2022 | 60 | M/S. DAS ENTERPRISE | 8.03 | 7.77 | 100
36 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of pipeline for retrofitting of distribution system of Chakmanik Village under South 24-Parganas Water Supply Division-I, P.H.E. Dte. District South 24 Parganas. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000163/2022-2023 | 1408/SWD-I | 22/09/2022 | 90 | M/S. S.S. ENTERPRISE | 77.23 | 72.48 | 80
37 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Upvc pipeline for retrofitting of distribution system of Burul (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000238/2022-2023 | 1713/SWD-I | 02/11/2022 | 120 | M/S. S.S. ENTERPRISE | 165.97 | 153.9 | 90
38 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Upvc pipeline for retrofitting of distribution system of KUCHIGADI (PART) Village & RANIA GOBINDAPUR (PART) under SWD - I, P.H.E. Dte District South 24 Parganas. (No. of FHTC = 632) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000240/2022-2023 | 1727/SWD-I | 03/11/2022 | 90 | FIDERE MARINE SERVICES PVT LTD. | 100.42 | 100.25 | 80
39 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Upvc pipeline for retrofitting of distribution system of Part of Chak Kashipur and Chak Alampur Village under SWD - I, P.H.E. Dte District South 24 Parganas. [SM/11487] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000257/2022-2023 | 1698/SWD-I | 01/11/2022 | 90 | TIYASHA ENTERPRISE | 65.45 | 45.12 | 100
40 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repairing of Pump House and construction of toilet at tubewell site of Chak Kashipur (Part) & Chak Alampur (Part) of Budge Budge-II under South 24-Pgns W/S Division-I, PHE Dte. [SM/11487] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000258/2022-2023 | 1699/SWD-I | 01/11/2022 | 60 | ROYAL CONSTRUCTION | 4.54 | 4.45 | 100
41 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection of pipeline from proposed Tubewell to Distribution Main for Chak Kashipur (Part) & Chak Alampur(Part) of Budge Budge II Block under South 24 Pgs W/S Division-I, PHE Dte. [SM/11487] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000259/2022-2023 | 1700/SWD-I | 01/11/2022 | 45 | S.R. CONSTRUCTION | 3.94 | 3.87 | 0
42 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2024 to 30/11/2024] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000288/2024-2025 | 2481/SWD-I | 28/05/2024 | 183 | AVIK HALDER | 0.89 | 2.38 | 0
43 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chakmanik village (Part) of Budge Budge-II Block under South 24-Pgns W/S Divn.-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000289/2022-2023 | 1782/SWD-I | 07/11/2022 | 60 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 8.54 | 8.34 | 100
44 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 01 no. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Chak Kashipur (Part) & Chak Alampur (Part) of Budge Budge-II block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000329/2022-2023 | 2047/SWD-I | 30/11/2022 | 30 | BARI ENTERPRISE | 21.09 | 18.85 | 100
45 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 11.3 | 98
46 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 3 (Three) nos. boundary walls for Providing FHTC with allied works for Zone-1, 3 & 5 of Budge Budge-II Block under South 24- parganas W/S Division-I, P.H.E. Dte. of South 24-Pargans District (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000363/2024-2025 | 3505/SWD-I | 07/08/2024 | 45 | MS KRISHNA MONDAL | 44.65 | 16.67 | 50
47 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supplying, Fabrication, Erection and Commissioning of Pressure Type Iron Elimination Plant (35 Cum capacity) including other allied works at Satgachia village of Budge Budge-II Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000383/2022-2023 | 2362/SWD-I | 22/12/2022 | 150 | RAMASISH ENTERPRISE | 16.78 | 16.71 | 100
48 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Route Survey and pipeline network design of "RANIA KUCHIGADI & CHAKMANIK Ground Water Based Piped Water Supply Scheme" in BUDGE BUDGE-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000535/2022-2023 | 472/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 1.9 | 1.85 | 100
49 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Route Survey and pipeline network design of "SEKHPARA & BURUL Ground Water Based Piped Water Supply Scheme" in BUDGE BUDGE-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000537/2022-2023 | 471/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.01 | 2.01 | 100
50 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/12/2023 to 31/05/2024] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000664/2023-2024 | 2997/SWD-I | 29/11/2023 | 183 | AVIK HALDER | 0.89 | 1.57 | 30
51 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method at ChakAlampur Village for Zone- 1,3&5 PWSS of Budge Budge-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010530] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000695/2022-2023 | 3498/SWD-I | 16/03/2023 | 15 | BARI ENTERPRISE | 2.2 | 2.2 | 100
52 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing pipe supporting structures at Burul Water Supply Scheme and other allied works under Providing FHTC with allied works for Zone 1, Zone-3 & Zone-5 of Budge Budge-II under South 24-pgns. Water Supply Division.-I, PHE Dte. Dist- South 24-Pgns. (SM/11487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000721/2023-2024 | 363/SWD-I | 16/01/2024 | 60 | SOURIK ENTERPRISE | 4.33 | 4.16 | 100
53 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road crossing of pipeline for interconnection of LDS under Zone-1, 3 & 5 PWSS at 02 locations under Budge Budge-II Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (TSM/10530) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000745/2022-2023 | 3596/SWD-I | 23/03/2023 | 15 | S. ROY AND ASSOCIATES | 7.88 | 7.85 | 0
54 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/12/2024 to 31/05/2025] [Vehicle No:- WB-19L-3415] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000888/2024-2025 | 4875/SWD-I | 29/11/2024 | 182 | AVIK HALDER | 0.88 | 1.17 | 0
55 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000008/2022-2023 | 1573 | 16/10/2022 | 0 | Resource Division | 16.2 | 0 | 0
56 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall and Laying Distribution System including FHTC for Augmentation of Laying Distribution System to extend benefit off 100% household in Zone-IV at HIJALHAT under Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 6310] [TSM/015076] | AE SWSD-II | JE4 | ORD/000125/2023-2024 | 568/SWD-I | 15/05/2023 | 1078 | M/S GHOSH AND CO. | 1160.71 | 0 | 56
57 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000134/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 38.87 | 0 | 0
58 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of ARUNNAGAR DAKSHIN Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000207/2021-2022 | 1933/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.03 | 2.65 | 100
59 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for ARUNNAGAR DAKSHIN PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the arsenic Affected Areas of South 24 Pgs district. [TSM/014830] [2nd Call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000681/2022-2023 | 3481/SWD-I | 15/03/2023 | 30 | KHANDAKAR CONSTRUCTION | 31.75 | 0 | 100
60 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig ground bored 250mm X 150mm dia Tubewell having 66 mtr. housing to achieve 360 mtr. deep Tubewell by Rotary method for ARUN NAGAR DAKSHIN PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/12208] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000710/2024-2025 | 4540/SWD-I | 06/11/2024 | 15 | KHANDAKAR CONSTRUCTION | 4.73 | 0 | 100
61 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, protection wall for laying pipeline and other allied works for Ground water based ARUN NAGAR DAKSHIN piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12208) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000770/2024-2025 | 4746/SWD-I | 20/11/2024 | 180 | S P ENTERPRISE (MURSHIDABAD) | 80.92 | 0 | 40
62 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional House Hold Tap Connection (FHTC) alongwith construction of Chlorine Room (two nos.) for augmentation of ARUN NAGAR DAKSHIN Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [No. of FHTC = 1261] [TSM/014830] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000814/2022-2023 | 3722/SWD-I | 31/03/2023 | 900 | BARI ENTERPRISE | 275.49 | 135.76 | 55
63 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000141/2022-2023 | 3424/SWD-I | 13/03/2023 | 0 | Resource Division | 7.77 | 0 | 0
64 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000192/2023-2024 | 338/SWD-I | 26/04/2023 | 0 | Resource Division | 22.3 | 0 | 0
65 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KALYANPUR, Khodar Bazar (Khodar Bazar C.T, J.L- 40) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [AFS- GO2223004568PH] [Project ID- PH222355709S000] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000067/2022-2023 | 1112/SWD-I | 23/08/2022 | 90 | M/S N ISLAM AND CO. | 71.8 | 53.71 | 25
66 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tubewell by Rotary method for KALYANPUR (Khodar Bazar) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte., within South 24 Parganas District under JJM [AFS- GO2223004568PH] [Project ID- PH222355709S000] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000070/2022-2023 | 1115/SWD-I | 23/08/2022 | 30 | PADMA ENGINEERING CO. | 20.08 | 19.02 | 100
67 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KALYANPUR (KHODAR BAZAR), PART-I Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000214/2021-2022 | 1956/SWD-I | 27/01/2022 | 30 | RAMKRISHNA CHAKABORTY | 2.62 | 2.47 | 100
68 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at KALYANPUR (Khodar Bazar) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns W/S Divn.-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000283/2022-2023 | 1780/SWD-I | 07/11/2022 | 60 | SOMNATH ENTERPRISE | 5.75 | 5.05 | 100
69 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kalyanpur (Khodar Bazar) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/009672] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000792/2022-2023 | 3667/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 2.2 | 0 | 100
70 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000126/2022-2023 | 3329/SWD-I | 09/03/2023 | 0 | Resource Division | 5.01 | 0 | 0
71 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for SITAKUNDU ZONE-I Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11645] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000028/2025-2026 | 1061/SWD-I | 22/04/2025 | 30 | MONDAL TUBEWELL | 15.82 | 0 | 0
72 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for SITAKUNDU (ZONE-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000080/2022-2023 | 1191/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 16.45 | 50
73 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at SITAKUNDU (Zone-I) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1753) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000230/2022-2023 | 1691/SWD-I | 01/11/2022 | 300 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 379.75 | 171.29 | 80
74 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Sitakundu (Zone-I)at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000363/2022-2023 | 2206/SWD-I | 13/12/2022 | 584 | JOY GURU TRADING | 11.52 | 4.74 | 50
75 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SITAKUNDU(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000450/2021-2022 | 1949/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.62 | 100
76 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for FHTC, restoration of road after laying of pipeline, development of land and other allied works for "Ground Water Based SITAKUNDU (ZONE -I) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/11645) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000524/2024-2025 | 4017/SWD-I | 13/09/2024 | 60 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 84.63 | 0 | 0
77 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of SITAKUNDU (Zone-I) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [SM/11645] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000552/2023-2024 | 2500/SWD-I | 06/10/2023 | 15 | TAPAS KUMAR GIRI | 4.41 | 2.2 | 100
78 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000084/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 11.9 | 0 | 0
79 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-VII AT AJODHYANAGAR of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 3427 Nos.) | AE SWSD-II | JE1 | ORD/000515/2022-2023 | 2881/SWD-I | 13/02/2023 | 998 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 379.95 | 0 | 79
80 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000124/2022-2023 | 3365/SWD-I | 09/03/2023 | 0 | Resource Division | 21.11 | 0 | 0
81 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000137/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 21.11 | 0 | 0
82 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work of Laying distribution system for KESHABPUR PWSS to accommodate FHTC in Baruipur Block under South 24 Pgns Water Supply Division-I, PHE. Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Paraganas District (TSM/012609) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000044/2023-2024 | 182/SWD-I | 18/04/2023 | 90 | CREATION CONSTRUCTION | 25.93 | 13.31 | 50
83 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KESHABPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000093/2022-2023 | 1205/SWD-I | 02/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 36.09 | 100
84 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at KESHABPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012609] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000119/2022-2023 | 1287/SWD-I | 14/09/2022 | 60 | SUBHRA ENTERPRISE | 10.92 | 9.41 | 100
85 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KESHABPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000159/2021-2022 | 1919/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.53 | 100
86 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KESHABPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 591) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000219/2022-2023 | 1628/SWD-I | 20/10/2022 | 90 | CREATION CONSTRUCTION | 134.38 | 112.97 | 85
87 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for Ground Water based KESABPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12059) [2nd call] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000718/2024-2025 | 4552/SWD-I | 06/11/2024 | 320 | SHAH ENTERPRISE | 71.43 | 0 | 50
88 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000272/2023-2024 | 2419/SWD-I | 30/09/2023 | 0 | Resource Division | 33.16 | 0 | 0
89 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000336/2023-2024 | 264/SWD-I | 10/01/2024 | 0 | Resource Division | 3.64 | 0 | 0
90 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Sahebpur PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015503] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000338/2022-2023 | 2074/SWD-I | 01/12/2022 | 30 | SIMPLEX DRILLING COMPANY | 30.59 | 28.48 | 100
91 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAHEBPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13675] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000517/2022-2023 | 2914/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 3.19 | 3.19 | 50
92 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for SAHEBPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2108] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000543/2022-2023 | 3032/SWD-I | 20/02/2023 | 300 | SUPER SKILL | 389.1 | 219.62 | 30
93 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 150.0 Mtr Boundary Wall Temporary approach road and land development at head work site and Eucaliptus Bullah piling work with drum sheet near Sahebpur FP school of Sahebpur PWSS within Sonarpur block SAHEBPUR piped water scheme to accommodate FHTC in Sonarpur Block under South 24-Pgns, W/S Division-I, P.H.E. Dte. for Augmentation of Surface Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13675] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000758/2023-2024 | 659/SWD-I | 06/02/2024 | 60 | SUPER SKILL | 36.95 | 19.52 | 30
94 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of SAHEBPUR PWSS within Sonarpur Block "SAHEBPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13675) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000760/2023-2024 | 661/SWD-I | 06/02/2024 | 45 | NILKANTHA ENTERPRISE | 10.37 | 10.3 | 100
95 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Temporary approach road, Eucalyptus Bullah piling work with Drumsheet and allied works at SAHEBPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13675) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001140/2024-2025 | 4652/SWD-I | 14/11/2024 | 30 | S M ENTERPRISE (SANAT MONDAL) | 22.65 | 0 | 0
96 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000029/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 26.26 | 0 | 0
97 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000239/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.99 | 0 | 0
98 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for RAJAK GOHALIA Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11778] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000177/2022-2023 | 1452/SWD-I | 26/09/2022 | 30 | DIPALI CONSTRUCTION | 14.26 | 12.7 | 100
99 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
100 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of RAJAK GOHATIA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000227/2021-2022 | 1980/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 2.51 | 100
101 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Rajakgohalia PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11778) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000256/2024-2025 | 2673/SWD-I | 07/06/2024 | 475 | LAKSHMI NARAYAN SAHOO | 63.98 | 0 | 57
102 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of RAJAK GOHALIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11778) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000443/2022-2023 | 2662/SWD-I | 18/01/2023 | 60 | M/S PANJA ENTERPRISE | 6.02 | 5.85 | 100
103 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based RAJAK GOHALIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 963 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000472/2022-2023 | 2791/SWD-I | 01/02/2023 | 570 | LAKSHMI NARAYAN SAHOO | 107.44 | 99.91 | 40
104 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAJAK GOHALIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011742] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000523/2022-2023 | 2913/SWD-I | 14/02/2023 | 15 | DIPALI CONSTRUCTION | 1.57 | 1.57 | 0
105 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for RAJAK GOHALIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011742] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000589/2022-2023 | 3109/SWD-I | 24/02/2023 | 736 | MOULI CONSTRUCTION | 15.88 | 0 | 70
106 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000114/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.18 | 0 | 0
107 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chandaneswar PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011097] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 26/SWD-I | 05/04/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.13 | 3.13 | 100
108 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for CHANDANESWAR PWSS of Joynagar-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011097] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000213/2022-2023 | 1585/SWD-I | 17/10/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 26.23 | 100
109 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, approach road, development of land and other allied works for Ground water based CHANDANESWAR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/13011) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000222/2024-2025 | 2640/SWD-I | 07/06/2024 | 450 | M/S L.P CONSTRUCTION | 62.59 | 0 | 70
110 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHANDANESWAR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000224/2021-2022 | 1928/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.76 | 100
111 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Chandaneswar of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 2213/SWD-I | 13/12/2022 | 60 | ALISHA CONSTRUCTION | 11.52 | 10.05 | 100
112 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHANDANESWAR Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1531) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000489/2022-2023 | 2819/SWD-I | 03/02/2023 | 900 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 511.76 | 130.17 | 60
113 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000304/2023-2024 | 2441/SWD-I | 30/09/2023 | 0 | Resource Division | 12.91 | 0 | 0
114 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III A at Mandaler lat mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4631] | AE BSD |  | ORD/000031/2023-2024 | 115/SWD-I | 11/04/2023 | 120 | SUPRITI ENTERPRISE | 352.02 | 141.48 | 30
115 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-III-B ( MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000127/2021-2022 | 2561/SWD-I | 11/03/2022 | 120 | MANASH GHOSH | 626.38 | 213.82 | 91
116 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III B at Mandaler lat mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4773] | AE BSD |  | ORD/000588/2022-2023 | 3123/SWD-I | 24/02/2023 | 120 | MANASH GHOSH | 363.26 | 130.59 | 50
117 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000074/2022-2023 | 2990/SWD-I | 20/02/2023 | 0 | Resource Division | 57.93 | 0 | 0
118 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary wall (length = 144.00m), Approach Road (length = 30.00m) and Construction of Pump House (5.40 Mtr. X 3.60 Mtr.) with water supply & sanitary arrangementat OHR site (1st Tube well Site) for HERIA PWSS to accommodate FHTC in MAGRAHAT-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12772) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000009/2025-2026 | 933/SWD-I | 07/04/2025 | 60 | SUBHO CONSTRUCTION | 32.33 | 0 | 0
119 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Heria PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014760] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000015/2023-2024 | 39/SWD-I | 06/04/2023 | 15 | DIPALI CONSTRUCTION | 3.13 | 0 | 0
120 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Heria PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000296/2022-2023 | 1876/SWD-I | 16/11/2022 | 30 | DIPALI CONSTRUCTION | 30.03 | 0 | 0
121 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "HERIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000390/2022-2023 | 409/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.76 | 2.64 | 0
122 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 200 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of HERIA of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1561] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000529/2022-2023 | 2949/SWD-I | 16/02/2023 | 300 | M/S PRADIP KUMAR PAL (EMAIL ID- PRADIPKUMARPAL.CO@GMAIL.COM) | 378.82 | 0 | 0
123 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for HERIA Piped Water Supply Scheme of MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. (SM/12772) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000788/2023-2024 | 1071/SWD-I | 04/03/2024 | 30 | M/S ARINDAM MONDAL | 29.88 | 0 | 0
124 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for HERIA Piped Water Supply Scheme of MOGRAHAT-II Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12772] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000845/2023-2024 | 1251/SWD-I | 13/03/2024 | 30 | M/S ARINDAM MANDAL | 3.12 | 0 | 0
125 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length = 57.60m), Development of land, Construction of Service Road (length = 15.00m) and Pump House at 2nd Tubewell site for HERIA PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Divn.-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12772) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/001160/2024-2025 | 401/SWD-I | 06/02/2025 | 60 | BHANDARY CONSTRUCTION | 15.38 | 0 | 0
126 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000160/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 26.16 | 0 | 0
127 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 500 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of TAJPUR FATEPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2497] [TSM/018300] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000127/2023-2024 | 587/SWD-I | 16/05/2023 | 300 | DIVINE | 531.16 | 187.91 | 25
128 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Restoration of Road, and other allied works for "Ground Water Based Tajpur Fatepur Piped Water Supply Scheme to Accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/14861) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000356/2024-2025 | 3456/SWD-I | 02/08/2024 | 45 | DIVINE | 84.28 | 0 | 0
129 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for TAJPUR FATEPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018300] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000613/2022-2023 | 3212/SWD-I | 28/02/2023 | 30 | NAJMUL HAQUE | 31.62 | 0 | 5
130 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Tajpur Fatepur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000954/2022-2023 | 1305/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.66 | 2.64 | 100
131 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000096/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 35.84 | 0 | 0
132 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of CHAK HARANANDAPUR MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1956] [TSM/018438] | Assistant Engineer | Junior Engineer | ORD/000059/2023-2024 | 276/SWD-I | 24/04/2023 | 90 | M/S. GOUTAM ROY | 237.12 | 70.39 | 70
133 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK HARANANDAPUR Piped Water Supply Scheme to accommodate FHTC in MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14864] | Assistant Engineer | Junior Engineer | ORD/000094/2025-2026 | 1769/SWD-I | 02/07/2025 | 30 | PADMA ENGINEERING CO. | 19.14 | 0 | 0
134 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based CHAK HARANANDAPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14864) | Assistant Engineer | Junior Engineer | ORD/000349/2024-2025 | 3443/SWD-I | 02/08/2024 | 90 | M/S. GOUTAM ROY | 201.5 | 0 | 0
135 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for CHAK HARANANDAPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018438][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000689/2022-2023 | 3478/SWD-I | 15/03/2023 | 30 | MUNNA AGROTECH ENTERPRISE | 31.78 | 15.19 | 50
136 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Chak Haranandapur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000972/2022-2023 | 1406/SWD-I | 21/09/2022 | 30 | GEO SOLUTION | 2.55 | 2.53 | 100
137 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000156/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 16.64 | 0 | 0
138 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, Pipeline protection, Platform for FHTC, Land development and other allied works for Ground water based PURBA BEGAMPUR ZONE - II piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns District.(SM/13779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000353/2024-2025 | 3453/SWD-I | 02/08/2024 | 45 | SRIJON ENTERPRISE | 80.58 | 0 | 0
139 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of PURBO BEGAMPUR (ZONE-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1967] [TSM/011437] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000360/2023-2024 | 1763/SWD-I | 10/08/2023 | 300 | ROSENBLUTH CONSTRUCTION PRIVATE LIMITED | 670.09 | 150.8 | 55
140 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BEGAMPUR(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000447/2021-2022 | 1952/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
141 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PURBA BEGAMPUR (Zone-II) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13779] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000565/2022-2023 | 3061/SWD-I | 21/02/2023 | 30 | M/S B.M. INDUSTRIES (BM.INDUSTRY@GMAIL.COM) | 31.76 | 30.88 | 100
142 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000164/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 27.14 | 0 | 0
143 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of BAKESWAR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2430) [TSM/016358]. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000169/2023-2024 | 966/SWD-I | 08/06/2023 | 90 | M/S B.D. ENTERPRISE | 266.82 | 0 | 28
144 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of BAKESWAR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000422/2021-2022 | 1972/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.66 | 0
145 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
146 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for BAKESWAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016358] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000556/2022-2023 | 3046/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
147 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BAKESWAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016358] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000579/2022-2023 | 3096/SWD-I | 23/02/2023 | 616 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.87 | 0 | 100
148 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, land development, approach road, pipeline protection and road restoration for BAKESWAR PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/13782) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000656/2024-2025 | 4381/SWD-I | 22/10/2024 | 482 | A.K. SIKDAR | 180.08 | 0 | 12
149 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land development of OHR / 1st Tubewell site at Bakeswar PWSS in the Arsenic Affected areas South 24-Pgns. Dist in Bishnupur-I Block under South 24-Parganas W/S Division-I, P.H.E. Dte. (SM/13782) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000711/2024-2025 | 4541/SWD-I | 06/11/2024 | 30 | SRIJON ENTERPRISE | 28.8 | 28.66 | 100
150 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000092/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 41.75 | 0 | 0
151 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional laying of pipeline for distribution system due to revision of Laying Distribution System drawing for providing Functional Household Tap Connection (FHTC) for Proposed BAGI PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24 Pgs W/S Sub-Division-I, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (SM/14547) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000016/2025-2026 | 968/SWD-I | 09/04/2025 | 45 | RAJLAXMI CONSTRUCTION | 43.03 | 0 | 0
152 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of BAGI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4890) [TSM/017322]. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000159/2023-2024 | 841/SWD-I | 05/06/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 749.97 | 0 | 0
153 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of BAGI PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/017322] (2nd call) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000237/2023-2024 | 1420/SWD-I | 17/07/2023 | 60 | MS KRISHNA MONDAL | 18.75 | 0 | 0
154 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, approach road and land development for BAGI PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/14547) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000346/2024-2025 | 3345/SWD-I | 25/07/2024 | 60 | M/S B.N. ENTERPRISES | 201.23 | 0 | 0
155 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for KANNYANAGAR, BAGI & BHANDARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018432, TSM/017332, TSM/017323] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000422/2023-2024 | 1969/SWD-I | 24/08/2023 | 300 | H. T. R. CONSTRUCTION | 572.68 | 0 | 0
156 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at second & third Tubewell Site for BAGI PWSS of Bishnupur-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017322] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000548/2022-2023 | 3038/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 0
157 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Bagi Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000959/2022-2023 | 1138/SWD-I | 25/08/2022 | 30 | GEO SOLUTION | 3.16 | 3.14 | 100
158 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 02 nos. (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement (as per Deptt. drawing) for 2nd and 3rd Tubewell sites of BAGI Pipe Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24 Parganas district, South 24 Pgns WS Division-I, P.H.E Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. (SM/14547) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/001147/2024-2025 | 328/SWD-I | 29/01/2025 | 60 | ROYAL CONSTRUCTION | 11.52 | 0 | 0
159 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000088/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 70.75 | 0 | 0
160 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sarberia- Dhamua Road,from 0+00 to 6+520 Km Restoration of Damage occurred due to damage caused/ to be caused by laying of pipe line by PHE Dte under Sarberia PWSS, Jaldhapa PWSS, Multi PWSS under South 24 Parganas Highway Division in the District of South 24 Parganas. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00635/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 19.6 | 0 | 0
161 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at SARBERIA Mouza of Joynagar-I Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district [No. of FHTC = 2209] [TSM/017755] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000013/2023-2024 | 32/SWD-I | 05/04/2023 | 990 | MILAN GHOSH | 299.38 | 277.17 | 98
162 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, development of land, pipeline protection work and other allied works for Ground water based SARBERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14874) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000355/2024-2025 | 3455/SWD-I | 02/08/2024 | 45 | MILAN GHOSH | 85.25 | 0 | 0
163 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SARBERIA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000414/2021-2022 | 1967/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.7 | 0
164 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for SARBERIA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017755] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000583/2022-2023 | 3068/SWD-I | 21/02/2023 | 690 | WATER TECH (E-MAIL :- ENVO.WATERTECH@GMAIL.COM) | 31.79 | 7.92 | 100
165 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000342/2023-2024 | 261/SWD-I | 10/01/2024 | 0 | Resource Division | 13.61 | 0 | 0
166 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at SHYAMPUR Part-I Mouza of Mograhat-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 3180] [TSM/018169] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000288/2023-2024 | 1609/SWD-I | 01/08/2023 | 90 | UCON | 433.14 | 123.81 | 25
167 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for SHYAMPUR (PART-I) PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000568/2022-2023 | 3064/SWD-I | 21/02/2023 | 30 | G M ENTERPRISE (19AQFPM3953P1Z3) | 47.4 | 46.02 | 100
168 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Shyampur(part-I) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000974/2022-2023 | 1427/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.74 | 2.74 | 100
169 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000134/2022-2023 | 3393/SWD-I | 10/03/2023 | 0 | Resource Division | 19.59 | 0 | 0
170 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000198/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 57.67 | 0 | 0
171 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.20] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00479/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 6.93 | 0 | 0
172 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.21] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00480/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 5.39 | 0 | 0
173 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for SANGUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2506] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 30/SWD-I | 05/04/2023 | 1026 | EFFLUENT AND WATER TREATMENT ENGINEERS PRIVATE LIMITED | 633.23 | 375.81 | 50
174 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Rejuvenation / upgradation of Existing R.C.C. Reservoir of capacity 550 CUM and staging height 20 mtr at 2nd Tubewell site of "SANGUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14545) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 964/SWD-I | 09/04/2025 | 45 | M/S. JAYDEEP DASGUPTA | 10.94 | 0 | 0
175 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of Land & other allied works of " SANGUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/14545). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000234/2024-2025 | 2654/SWD-I | 07/06/2024 | 497 | SAHI MASUM | 42.97 | 0 | 50
176 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR SANGUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/017137) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000560/2022-2023 | 3052/SWD-I | 20/02/2023 | 30 | BARI ENTERPRISE | 30.02 | 26.73 | 100
177 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SANGUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/017137] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000777/2022-2023 | 3653/SWD-I | 28/03/2023 | 15 | BARI ENTERPRISE | 3.13 | 3.13 | 100
178 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pumphouse, Chlorine room, Office room, Land Development, Construction of Pathway & Drain of Sangur PWSS within Sonarpur Block "Sangur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pargnas District under Jal Jeevan Mission. (SM/14545) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001103/2024-2025 | 62/SWD-I | 06/01/2025 | 45 | MIDHAH ENTERPRISE | 22.12 | 0 | 0
179 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000031/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 34.19 | 0 | 0
180 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000255/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 15.44 | 0 | 0
181 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 750 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of piped water supply scheme in Zone-I at Bainchberia Mouza of Mograhat-I Block for augmentation of Mega surface water based water supply scheme and providing Functional Household Tap connection (FHTC) in Zone-I at Bainchberia of Mograhat-I Block within Mega surface water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (No.of FHTC - 5799 Nos.) | AE SWSD-II | JE3 | ORD/000114/2023-2024 | 526/SWD-I | 11/05/2023 | 782 | RADIANT | 911.48 | 78.12 | 20
182 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of Zone-I (Bainchberia) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 116 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II | JE3 | ORD/000343/2021-2022 | 2692/SWD-I | 25/03/2022 | 90 | NIKHIL SAMADDAR | 16.45 | 16.44 | 100
183 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of additional pipe line, protection of distribution pipe line & construction of FHTC Platform, approach road, land development, chlorination room, and other allied works for Zone-I (Bainchberia) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14726] | AE SWSD-II | JE3 | ORD/000503/2024-2025 | 3719/SWD-I | 23/08/2024 | 312 | RADIANT | 414.1 | 0 | 15
184 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Carriage of DI (K9) pipes of various diameter from different PHE stores to work site at Mograhat-I block for laying of Secondary Grid pipeline for Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% household in Zone-I at Bainchberia under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur dist. South 24 Pgns. under South 24 Parganas Water Supply Division-I, PHE, Dte. (SM/ 14726) | AE SWSD-II | JE3 | ORD/000554/2023-2024 | 2520/SWD-I | 09/10/2023 | 7 | TIRUPATI ENTERPRISES | 7.85 | 0 | 0
185 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Protection work of Boundary wall along canal inside Magrahat-I GLR under Augmentation of existing laying distribution system including old OHR and allied works to extend the benefit of 100% Household in ZONE-I at BAINCHBERIA under Magrahat-I block within Mega Surface water based water supply scheme of Falta-Mathurapur dist- South 24-Pgns, Under south 24-Pgns, water supply Division-I, P.H.E. Dte. (SM/14726) | AE SWSD-II | JE3 | ORD/000778/2023-2024 | 806/SWD-I | 16/02/2024 | 15 | PROJECT AND MAINTENANCE | 11.16 | 11.17 | 95
186 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sludge cleaning including repeated washing with fresh water with allied work disinfection of Magrahat-I (1400 cum) GLRs under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in Zone-I at BAINCHBERIA under MAGRAHAT-I block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/14726) | AE SWSD-II | JE3 | ORD/000779/2023-2024 | 807/SWD-I | 16/02/2024 | 15 | NIRMAL UDYOG | 3.84 | 3.64 | 100
187 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for Magrahat-I Block under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in Zone-I at BAINCHBERIA under Magrahat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/14726) | AE SWSD-II | JE3 | ORD/001074/2024-2025 | 5342/SWD-I | 30/12/2024 | 90 | TIRUPATI ENTERPRISES | 25.7 | 0 | 1
188 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000061/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 3.53 | 0 | 0
189 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying Distribution System, Rising Main, Functional Household Tap Connection for BAGDAHA PWSS to accommodate FHTC in Baruipur Block under Surface water based water supply scheme in the arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. (TSM/018476) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 469/SWD-I | 04/05/2023 | 90 | M/S ASHIRBAD (INDIA) | 148.94 | 89.19 | 90
190 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, development of land, pipeline protection work and other allied works for Ground water based BAGDAHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/15782) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000335/2024-2025 | 3273/SWD-I | 22/07/2024 | 495 | KAMALA ENTERPRISE (DIAMOND HARBOUR) | 59.7 | 0 | 100
191 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BAGDAHA PWSS to accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018476) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000708/2022-2023 | 3522/SWD-I | 17/03/2023 | 30 | MURSHID JAHAN | 31.76 | 29.05 | 100
192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Bagdah Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000927/2022-2023 | 1175/SWD-I | 31/08/2022 | 30 | GEO SOLUTION | 2.46 | 2.46 | 100
193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000179/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 29.87 | 0 | 0
194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for DHOPA GACHI Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 917] [TSM/018424] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000084/2023-2024 | 418/SWD-I | 02/05/2023 | 720 | MONDAL CONSTRUCTION | 168.94 | 125.72 | 95
195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of OHR/ 2nd TW site, platform for providing FHTC, restoration of road and other allied works for Augmentation of Ground Water based DHOPAGACHHI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. (SM/15786) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000373/2024-2025 | 3551/SWD-I | 09/08/2024 | 225 | MONDAL CONSTRUCTION (BARUIPUR) | 46.21 | 0 | 30
196 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method at Head work site for DHOPAGACHI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/15786] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000385/2024-2025 | 3588/SWD-I | 13/08/2024 | 15 | PADMA ENGINEERING CO. | 15.88 | 0 | 0
197 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for DHOPAGACHI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018424] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000643/2022-2023 | 3316/SWD-I | 06/03/2023 | 30 | M/S M.S. ENTERPRISE | 31.77 | 0 | 0
198 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DHOPAGACHI Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15786] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000878/2024-2025 | 4976/SWD-I | 05/12/2024 | 30 | M/S. SHYAM CONSTRUCTION | 15.53 | 0 | 0
199 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dhopa Gachhi Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000941/2022-2023 | 1258/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.48 | 2.47 | 100
200 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000122/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 29.34 | 0 | 0
201 | South 24 Pgs W/S Division I | Baruipur Sub-Division | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas | AE BSD |  | BILL/00637/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0
202 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional laying of pipeline of secondary grid from Sikirhat to Ghatarnia and allied works for Nolgora of Joynagar-II Block under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur, South 24 pgns. District under South 24 pgns W/S Division-I, PHE Dte. (SM/16185) | AE BSD |  | ORD/000006/2025-2026 | 909/SWD-I | 02/04/2025 | 60 | BISWAS CONSTRUCTION | 47.37 | 0 | 70
203 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Gap Negotiation for Secondary grid of JOYNAGAR-II Block under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-III at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur, South 24-Pgns. District under South 24-Pgns W/S Division-I, PHE Dte. (SM/16185) | AE BSD |  | ORD/000015/2025-2026 | 967/SWD-I | 09/04/2025 | 30 | BISWAS CONSTRUCTION | 8.68 | 0 | 80
204 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of development of land, approach road, protection work for pipeline, and other allied works for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-III at JOYNAGAR-II Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, of South 24-Pgns. W/S Circle, PHE Dte." (SM/16185) | AE BSD |  | ORD/000277/2024-2025 | 2648/SWD-I | 07/06/2024 | 360 | R.S. CONSTRUCTION CO. | 55.65 | 0 | 40
205 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIIB (Beledurganagar) of Joynagar-II block, under Baruipur Sub-Division, for "Augmentation of laying distribution system to extend the benefit of 100% Households in Zone-III at Joynagar-II block within Mega surface water based W/S scheme of Falta-Mathurapur dist. South 24 pgns water supply division-I,PHE Dte.". Erstwhile "Laying distribution system of piped water supply at Zone-IIIB (Beledurganagar) of Joynagar-II Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte." | AE BSD |  | ORD/000339/2021-2022 | 2338/SWD-I | 22/02/2022 | 120 | AJIT PRAMANICK | 416.96 | 120.71 | 85
206 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-III-A (Beladurganagar) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000409/2021-2022 | 2337/SWD-I | 22/02/2022 | 120 | MS LOKENATH CONSTRUCTION PROP SILPI DAS | 322.66 | 121.33 | 0
207 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000066/2022-2023 | 2981/SWD-I | 20/02/2023 | 0 | Resource Division | 326.04 | 0 | 0
208 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VI (Radha Ballavpur) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000359/2021-2022 | 2599/SWD-I | 15/03/2022 | 1080 | SUPRITI ENTERPRISE | 740.59 | 663.01 | 88
209 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 900 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (RADHABALLAVPUR) at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur District South 24 Parganas under South 24 parganas water Supply Division-I of PHEDte." [TSM : 014964] | AE BSD |  | ORD/000535/2023-2024 | 2364/SWD-I | 26/09/2023 | 900 | ATCO ENTERPRISE | 364 | 0 | 30
210 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Pipeline at different areas & others ancillary works including Land development of 900 Cu.M. Capacity R.C.C. Over Head Reservoir site for "Augmentation of laying distribution system to extend the benefit of 100% Household in Zone-VI (Radhaballavpur mouza) at Joynagar-II block within the Mega Surface Water Based Water Supply scheme, District Southy 24 Parganas" under Baruipur Sub Division of South 24 Parganas Water Supply Division-I of PHE Dte. [SM/ 16191] | AE BSD |  | ORD/000620/2023-2024 | 2804/SWD-I | 09/11/2023 | 45 | WALL FORT INDIA | 15.71 | 14.41 | 50
211 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of additional pipeline for parallel connections from main pipeline to provide FHTC in Zone-VI RADHABALLAVPUR Mouza under Augmentation of laying distribution system to extend the benefit of 100% households in Zone-VI at Joynagar-II Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur Dist.- South 24-Pgns. under South 24-Pgns W/S Division-I, PHE Dte. (SM/16191) | AE BSD |  | ORD/001157/2024-2025 | 375/SWD-I | 04/02/2025 | 135 | SUPRITI ENTERPRISE | 50.03 | 0 | 50
212 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000068/2022-2023 | 2983/SWD-I | 20/02/2023 | 0 | Resource Division | 30.76 | 0 | 0
213 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000205/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 24.9 | 0 | 0
214 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.27] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00487/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 12.32 | 0 | 0
215 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall, along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for CHANDANPUKUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 949] [TSM/018249] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000083/2023-2024 | 417/SWD-I | 02/05/2023 | 700 | PINKI CONSTRUCTION | 163.36 | 84.1 | 75
216 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDANPUKUR PWSS to accommodate FHTC in Baruipur Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018249) (2nd Call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000225/2023-2024 | 1401/SWD-I | 14/07/2023 | 30 | P N DASS AND GRANDSON | 31.65 | 15.55 | 50
217 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Chandanpukur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000942/2022-2023 | 1259/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.49 | 2.48 | 100
218 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000121/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 26.99 | 0 | 0
219 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALLIKPUR (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2368] [TSM/017349] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000131/2023-2024 | 665/SWD-I | 24/05/2023 | 90 | M/S B.N. ENTERPRISE | 284.55 | 0 | 0
220 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MALLIKPUR , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000506/2021-2022 | 1905/SWD-I | 27/01/2022 | 30 | RADIANT | 2.62 | 2.56 | 100
221 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (Four) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MALLIKPUR (PART-II) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017349] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000685/2022-2023 | 3484/SWD-I | 15/03/2023 | 30 | HUMAYUN KABIR | 63.52 | 0 | 0
222 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000182/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 73.07 | 0 | 0
223 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall, along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for CHAKARBAR Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 737] [TSM/018426] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000349/2023-2024 | 1735/SWD-I | 10/08/2023 | 669 | J.K. CONSTRUCTION | 134.15 | 0 | 40
224 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Development of Land, and other allied works for "Ground Water Based CHAKAR BAR Piped Water Supply Scheme to Accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15784) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000411/2024-2025 | 3707/SWD-I | 23/08/2024 | 45 | A MONDAL ENTERPRISE | 49.74 | 0 | 0
225 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAKAR BAR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division-I, P.H.E. Dte. [TSM/018426] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000649/2022-2023 | 3321/SWD-I | 06/03/2023 | 30 | AKTARUZZAMAN | 31.76 | 14.53 | 50
226 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Chakar Bar Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000943/2022-2023 | 1265/SWD-I | 12/09/2022 | 30 | GEO SOLUTION | 2.43 | 2.43 | 100
227 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000120/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.96 | 0 | 0
228 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for NOR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 668] [TSM/018252] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000168/2023-2024 | 965/SWD-I | 08/06/2023 | 657 | M/S B.N. ENTERPRISE | 140.38 | 70.57 | 60
229 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for Providing FHTC, Protection work for Pipeline, Development of Land, and other allied works for "Ground Water Based NOR Piped Water Supply Scheme to Accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." SM/16126 | AE BSD,Assistant Engineer | Junior Engineer | ORD/000341/2024-2025 | 3315/SWD-I | 23/07/2024 | 45 | MILAN GHOSH | 48.46 | 0 | 0
230 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NOR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018252] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000640/2022-2023 | 3286/SWD-I | 03/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 14.5 | 50
231 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Nor Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000937/2022-2023 | 1250/SWD-I | 08/09/2022 | 30 | GEO SOLUTION | 2.45 | 2.43 | 100
232 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000126/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 9.28 | 0 | 0
233 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying distribution, Rising main, Funtional Household Tap Connection (FHTC) for PASCHIM MADHABPUR PWSS of BARUIPUR Block for Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [TSM/018425] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000088/2023-2024 | 346/SWD-I | 26/04/2023 | 90 | S.N. ENTERPRISE | 67.07 | 29.21 | 60
234 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PASCHIM MADHABPUR PWSS of BARUIPUR Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018425] (3rd Call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000230/2023-2024 | 1406/SWD-I | 14/07/2023 | 30 | KHAN CONSTRUCTION | 15.87 | 0 | 0
235 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Pachim Madhabpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000936/2022-2023 | 1237/SWD-I | 07/09/2022 | 30 | GEO SOLUTION | 2.37 | 2.36 | 100
236 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000262/2023-2024 | 2427/SWD-I | 30/09/2023 | 0 | Resource Division | 9.81 | 0 | 0
237 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000331/2023-2024 | 273/SWD-I | 10/01/2024 | 0 | Resource Division | 2.05 | 0 | 0
238 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for RATANPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1004] [TSM/017962]. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000100/2023-2024 | 470/SWD-I | 04/05/2023 | 720 | M. MUKHERJEE | 187.27 | 122.14 | 90
239 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based RATANPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/16133) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000223/2024-2025 | 2641/SWD-I | 07/06/2024 | 585 | SUPER CONSTRUCTION | 41.68 | 0 | 50
240 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RATANPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division-I, P.H.E. Dte. [TSM/017962] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000647/2022-2023 | 3319/SWD-I | 06/03/2023 | 30 | M/S SABITA ENTERPRISE | 31.72 | 14.83 | 50
241 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Rantanpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000933/2022-2023 | 1225/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.54 | 2.5 | 100
242 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000133/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.6 | 0 | 0
243 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1377) (TSM/017730) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000077/2023-2024 | 391/SWD-I | 28/04/2023 | 888 | M/S MITRA CONSTRUCTION | 357.88 | 96.87 | 32
244 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HOGALKURIA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/017730] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000668/2022-2023 | 3408/SWD-I | 10/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 15.32 | 100
245 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Up-gradation of pump house, chlorine room, office room, boundary wall and construction of pathway, drain & others allied works of HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000746/2024-2025 | 4668/SWD-I | 18/11/2024 | 60 | R.K ENTERPRISE | 20.9 | 0 | 0
246 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site "HOGALKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission." ( SM/15771). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000818/2023-2024 | 1311/SWD-I | 15/03/2024 | 45 | MS KRISHNA MONDAL | 55.36 | 0 | 0
247 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000018/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 17.47 | 0 | 0
248 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000232/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 8.48 | 0 | 0
249 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road edge and Hard shoulder damaged due to laying of pipes by PHE Dte. of Dakshin Barasat Mograhat Usthi Road from 0.00 kmp to 21.0 kmp in different stretched of Diamond Harbour Highway Sub-Division under Diamond Harbour Highway Division in the district of South 24 Parganas | AE RWS, Alipore Division | JE RWS, HQ | BILL/00654/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 6.93 | 0 | 0
250 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MIRZAPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [TSM/016565] [2nd Call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000228/2023-2024 | 1404/SWD-I | 14/07/2023 | 30 | M/S SACHIDULAL CHOWDHURY | 47.53 | 43.34 | 80
251 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 814 | S & P ENTERPRISE | 1745.38 | 175.31 | 6
252 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Extension of Boundary wall and development of land at 2nd and 3rd Tubewell site for MIRZAPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/18268) | AE RWS, Alipore Division | JE RWS, HQ | ORD/000291/2024-2025 | 3108/SWD-I | 09/07/2024 | 333 | BISWAS CONSTRUCTION | 23.23 | 0 | 40
253 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Mirzapur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division | JE RWS, HQ | ORD/000979/2022-2023 | 1435/SWD-I | 23/09/2022 | 30 | GEO SOLUTION | 2.76 | 2.72 | 100
254 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division | JE RWS, HQ | RTOR000289/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 50.05 | 0 | 0
255 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division | JE RWS, HQ | RTOR000309/2023-2024 | 2736/SWD-I | 06/11/2023 | 0 | Resource Division | 18.66 | 0 | 0
256 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 550 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Laying Distribution System and providing FHTC for Augmentation of Piped W/S Scheme of Zone-III at PRATAPBERIA (Baneswarpur) of Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 4102] [TSM/015075 & TSM/010756] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000073/2023-2024 | 387/SWD-I | 28/04/2023 | 705 | PROJECT AND MAINTENANCE | 418.32 | 157.44 | 95
257 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of balance FHTC platform, Chlorination Room (5.50m X 4.50m) and protection of pipelines for ZONE-III at BANESWARPUR under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at BANESWARPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist- South 24 pgns. under South 24 pgns W/S Division-I, PHE, Dte. (SM/16184) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000437/2024-2025 | 3882/SWD-I | 03/09/2024 | 411 | PROJECT AND MAINTENANCE | 36.45 | 0 | 35
258 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BAHARU PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017335] |  |  | ORD/000365/2023-2024 | 1774/SWD-I | 11/08/2023 | 30 | MATRI ENTERPRISE | 47.62 | 45.92 | 100
259 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of BAHARU MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4292] [TSM/017335] |  |  | ORD/000408/2023-2024 | 1925/SWD-I | 22/08/2023 | 90 | M/S G. C. CONSTRUCTION | 530.53 | 331.85 | 60
260 | South 24 Pgs W/S Division I |  | Construction of Platform for providing FHTC, approach road, protection work for pipeline and other allied works for Ground water based BAHARU piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18677) [2nd call] |  |  | ORD/000546/2024-2025 | 4134/SWD-I | 23/09/2024 | 360 | RANADHIR SINHA | 94.75 | 0 | 30
261 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Baharu Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000969/2022-2023 | 1386/SWD-I | 20/09/2022 | 30 | MEASURE LAND | 2.91 | 2.89 | 100
262 | South 24 Pgs W/S Division I |  | Construction of 02 (two) nos. chlorination rooms for BAHARU Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I Block under South 24-Pgns. W/S Divn.-I, PHE Dte., South 24-Pgs. Dist. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/18677) |  |  | ORD/001127/2024-2025 | 190/SWD-I | 17/01/2025 | 300 | S.M. ENTERPRISE (MOGRAHAT) | 11.41 | 0 | 100
263 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 99.15 | 0 | 0
264 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 141 to 144 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000362/2020-2021 | 1411/SWD-I | 14/12/2020 | 120 | BANIK BROTHERS | 94.35 | 88.77 | 100
265 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system by extension of pipeline for Buita W/S Scheme for Booth No - 141 to 144 and adjoining areas under Budge Budge-I Block with allied works unuder South 24-Parganas W/S Divn-I, P.H.E. Dte, South 24-Pgns District. | AE SWSD-I |  | ORD/000586/2021-2022 | 1471/SWD-I | 15/12/2021 | 45 | BANIK BROTHERS | 2.54 | 2.54 | 100
266 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nandarampur W/S Scheme for Booth 170 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000116/2020-2021 | 1394/SWD-I | 11/12/2020 | 120 | PROJECT AND MAINTENANCE | 92.1 | 149.21 | 90
267 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Moukhali W/S Scheme for Durgapur Moukhali and Jagat Ballavpur under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000309/2020-2021 | 1414/SWD- I | 14/12/2020 | 120 | SUPRITI ENTERPRISE | 96.89 | 15.31 | 100
268 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nandarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6127) Part -H | AE SWSD-I |  | ORD/000470/2022-2023 | 2782/SWD-I | 31/01/2023 | 45 | R.D CONSTRUCTION | 2.51 | 0.23 | 100
269 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 141 to 144) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000060/2021-2022 | 1206/SWD-I | 09/11/2021 | 120 | STARCO CONSTRUCTION | 288.89 | 286.45 | 96
270 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Buita W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM/ 8293 ) PART-VIII | AE SWSD-I |  | ORD/000467/2022-2023 | 2776/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 4.95 | 0 | 100
271 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance of Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD |  | ORD/000040/2022-2023 | 978/SWD-I | 27/07/2022 | 892 | CALCON CONSTRUCTIONS | 75.21 | 18.82 | 100
272 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD |  | ORD/000085/2021-2022 | 1162/SWD-I JJM | 02/11/2021 | 120 | UNICON INDIA | 125.43 | 26.28 | 25
273 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 8300 ) PART-I | AE BSD |  | ORD/000459/2022-2023 | 2771/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 8.53 | 8.52 | 100
274 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Booth 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000089/2021-2022 | 1163/SWD-I JJM | 02/11/2021 | 120 | CALCON CONSTRUCTIONS | 137.48 | 64.94 | 10
275 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Divn. - I P.H.E Dte. (TSM/8301) PART-II | AE SWSD-I |  | ORD/000455/2022-2023 | 2730/SWD-I | 27/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 23.13 | 23.08 | 100
276 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for under Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza including Balarampur Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000087/2021-2022 | 1161/SWD-I JJM | 02/11/2021 | 120 | M/S. S.S. ENTERPRISE | 152.75 | 148.38 | 100
277 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Atmarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8298) Part -E | AE SWSD-I |  | ORD/000453/2022-2023 | 2727/SWD-I | 27/01/2023 | 45 | MOUMITA ENTERPRISE | 10.71 | 10.62 | 100
278 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Narayanitala PWSS of BaruipurBlock for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011225] | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 28/SWD-I | 05/04/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.13 | 3.01 | 100
279 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for NARAYANITALA PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2022-2023 | 1189/SWD-I | 02/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 28.44 | 100
280 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of NARAYANITALA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000216/2021-2022 | 1966/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.63 | 100
281 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at NARAYANITALA Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1527) | Assistant Engineer | Junior Engineer | ORD/000270/2022-2023 | 1800/SWD-I | 09/11/2022 | 900 | PATH MAKERS | 382.32 | 357.42 | 100
282 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (Two) nos. chlorination rooms at Narayanitala of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000378/2022-2023 | 2212/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 0 | 0
283 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional laying of pipeline for NARAYANITALA Pipe Water Supply Scheme of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (TSM / 011225) | Assistant Engineer | Junior Engineer | ORD/000404/2023-2024 | 1913/SWD-I | 21/08/2023 | 60 | A.B. ASSOCIATES | 19.49 | 18.78 | 70
284 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of boundary wall and platform for providing FHTC for Ground water based NARAYANITALA piped water supply scheme to accommodate FHTC in Jaynagar-I & BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11495) | Assistant Engineer | Junior Engineer | ORD/000439/2024-2025 | 3884/SWD-I | 03/09/2024 | 45 | AYUSH ENTERPRISE | 48.14 | 0 | 0
285 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000263/2023-2024 | 2425/SWD-I | 30/09/2023 | 0 | Resource Division | 44.41 | 0 | 0
286 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000341/2023-2024 | 262/SWD-I | 10/01/2024 | 0 | Resource Division | 9.41 | 0 | 0
287 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for LAKSHMIKANTAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000029/2022-2023 | 913/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.19 | 12.22 | 100
288 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed LAKSHMIKANTAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 932] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000149/2022-2023 | 1389/SWD-I | 21/09/2022 | 953 | MS MANABESH ROY | 111.29 | 91.39 | 95
289 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.06.2023 to 30.11.2023] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000176/2023-2024 | 778/SWD-I | 31/05/2023 | 183 | PUSPA JAISWAL | 0.87 | 2.23 | 40
290 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.06.2024 to 30.11.2024] [Vehicle No- WB-04G-7357] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000198/2024-2025 | 2356/SWD-I | 24/05/2024 | 183 | PUSPA JAISWAL | 0.87 | 2.24 | 60
291 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
292 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of LAKSHMIKANTAPUR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000230/2021-2022 | 1979/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 2.52 | 100
293 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Lakshikantapur PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte, South 24-Pgns disct. (SM/11502) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000270/2024-2025 | 2920/SWD-I | 25/06/2024 | 45 | NIKHIL SAMADDAR | 39.42 | 0 | 31
294 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of LAKSHMIKANTAPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11502) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000442/2022-2023 | 2661/SWD-I | 18/01/2023 | 60 | M/S P. PURKAIT ENTERPRISE. | 6.02 | 5.85 | 100
295 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for LAKSHMIKANTAPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011195] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000587/2022-2023 | 3108/SWD-I | 24/02/2023 | 210 | MOULI CONSTRUCTION | 15.87 | 0 | 10
296 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of HDPE pipe from Second Tubewell to distribution network under Proposed ground water based LAKSHMIKANTAPUR piped water supply scheme to accommodate FHTC in BISHNUPUR-I Block under South 24 pgns W/S Division-I, South 24 Parganas District. [SM Code: TSM/011195, SM/11502] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000669/2023-2024 | 3020/SWD-I | 30/11/2023 | 60 | MS MANABESH ROY | 24.39 | 19.27 | 98
297 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven non-Air-conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Desire Car) with driver for monitoring different JJM activities of Bishnupur-II Block under the Assistant Engineer, South 24-Pgns. W/S Division-I, PHE Dte., Govt. of West Bengal. with all costs towards the owner except cost of fuel and lubricant. [w.e.f. 01.12.2023 to 31.05.2024] [Vehicle No- WB-04G-7357] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000700/2023-2024 | 2924/SWD-I | 23/11/2023 | 183 | PUSPA JAISWAL | 0.87 | 2.3 | 30
298 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for LAKSHMIKANTAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000860/2022-2023 | 2963/SWD-I | 16/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 0
299 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000012/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.74 | 0 | 0
300 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000110/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 25.56 | 0 | 0
301 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DANGA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12230] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 618/SWD-I | 17/05/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 1.6 | 5
302 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Repairing and renovation of Pump House, Chlorine Room, Construction of Pathway,Drain, Development of land & others allied works at HW Site of "DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12230). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000235/2024-2025 | 2655/SWD-I | 07/06/2024 | 45 | M/S PIONEER CONSTRUCTION | 22.49 | 18.31 | 70
303 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for DANGA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000262/2022-2023 | 1774/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 13.69 | 0
304 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1991] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000500/2022-2023 | 2882/SWD-I | 13/02/2023 | 1201 | M/S PIONEER CONSTRUCTION | 418.22 | 211.19 | 50
305 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of DANGA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12230) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000764/2024-2025 | 4685/SWD-I | 18/11/2024 | 45 | ARASTA ENGINEERING & CO | 10.18 | 0 | 0
306 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for 2nd Tubewell site of DANGA Piped Water Supply Scheme of SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under South 24-Parganas W/S Division-I, PHE Dte. [SM/12230] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001100/2024-2025 | 76/SWD-I | 07/01/2025 | 30 | B.K.ENTERPRISE | 15.68 | 0 | 0
307 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000014/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 15.6 | 0 | 0
308 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000251/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.26 | 0 | 0
309 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V B at Kantamari mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4346] | AE BSD |  | ORD/000155/2023-2024 | 806/SWD-I | 02/06/2023 | 669 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 330.69 | 86.22 | 40
310 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V A at Kantamari mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5791] | AE BSD |  | ORD/000156/2023-2024 | 807/SWD-I | 02/06/2023 | 669 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 440.56 | 151.33 | 50
311 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000086/2022-2023 | 3002/SWD-I | 20/02/2023 | 0 | Resource Division | 520.49 | 0 | 0
312 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II A at Mayahauri mouza of Joynagar-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [ No. of FHTC = 5789 ] | AE BSD |  | ORD/000370/2022-2023 | 2314/SWD-I | 19/12/2022 | 840 | SAMIRON GHOSH | 440.83 | 102.66 | 50
313 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II B at Mayahauri mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3400] | AE BSD |  | ORD/000534/2022-2023 | 2966/SWD-I | 17/02/2023 | 120 | PRITAM SENGUPTA (EMAIL ID-SENGUPTA408@YAHOO.COM) | 207.24 | 25.63 | 30
314 | South 24 Pgs W/S Division I | Baruipur Sub-Division | SupplyofdifferentCIDFspecialsfor layingof DIpipe(250mm dia & 400mm dia)at zone-II B (Mayahauri)of Joynagar-II Blockof BaruipurSub-Division, for "MegaSurface Based water supply schemeforFalta-Mathurapur, DistrictSouth24-Pgns, W/S Division-I, PHE. Dte. | AE BSD |  | ORD/000998/2022-2023 | 1073/SWD-I | 16/08/2022 | 15 | S.K. ENTERPRISE | 0.72 | 0 | 0
315 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF specials for layingof DIpipeat zone-II A (Mayahauri)of Joynagar-II Block of Baruipur Sub-Division, for "Mega Surface Based water supply scheme for Falta-Mathurapur, District South 24-Pgns, W/S Division-I, PHE. Dte. | AE BSD |  | ORD/000999/2022-2023 | 1072/SWD-I | 16/08/2022 | 15 | S.K. ENTERPRISE | 3.18 | 0 | 80
316 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF special for laying of DI pipe (250 mm dia. & 400 mm dia.) at zone -II B (Mayahauri) of Joynagar-II Block of Baruipur Sub-Division for Mega Surface Based Water supply Scheme for Falta - Mathurapur, District South 24-Pgns, W/S Division-I, P.H.E. Dte. | AE BSD |  | ORD/001036/2022-2023 | 1065/SWD-I | 12/08/2022 | 15 | S.K. ENTERPRISE | 0.72 | 0 | 0
317 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF special for laying of DI pipe (250 mm dia. & 400 mm dia.) at zone -II A (Mayahauri) of Joynagar-II Block of Baruipur Sub-Division for Mega Surface Based Water supply Scheme for Falta - Mathurapur, District South 24-Pgns, W/S Division-I, P.H.E. Dte. | AE BSD |  | ORD/001037/2022-2023 | 1066/SWD-I | 12/08/2022 | 15 | S.K. ENTERPRISE | 3.18 | 0 | 0
318 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 750 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of piped water supply scheme in Zone-I at Bainchberia Mouza of Mograhat-I Block for augmentation of Mega surface water based water supply scheme and providing Functional Household Tap connection (FHTC) in Zone-I at Bainchberia of Mograhat-I Block within Mega surface water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (No.of FHTC - 5799 Nos.) | AE SWSD-II | JE3 | ORD/000114/2023-2024 | 526/SWD-I | 11/05/2023 | 782 | RADIANT | 911.48 | 0 | 20
319 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000130/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 35.72 | 0 | 0
320 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
321 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for MATSYAKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/12045] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000232/2022-2023 | 1682/SWD-I | 01/11/2022 | 30 | ANIK ENTERPRISE | 14.96 | 0 | 1
322 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of MATSYAKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12045) (3rd Call) | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000253/2023-2024 | 1500/SWD-I | 20/07/2023 | 60 | RIDIP ENTERPRISE | 6.04 | 0 | 0
323 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Matshyakhali PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/12045) | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000271/2024-2025 | 2921/SWD-I | 25/06/2024 | 45 | BHOLANATH CONSTRUCTION (PROPRIETOR) | 91.73 | 0 | 0
324 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "MATSYAKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000398/2022-2023 | 462/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 2.51 | 100
325 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based MATSYAKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 750 nos.] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000448/2022-2023 | 2686/SWD-I | 20/01/2023 | 90 | ULTRA CONSTRUCTION | 101.39 | 76.67 | 60
326 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for MATSYAKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011202] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000509/2022-2023 | 2907/SWD-I | 14/02/2023 | 15 | ANIK ENTERPRISE | 1.57 | 0 | 0
327 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for MATSYAKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011202] | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000590/2022-2023 | 3110/SWD-I | 24/02/2023 | 675 | DEBASHIS DAS | 15.86 | 0 | 100
328 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development for 1st Tubewell site at MATSYAKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgns Dist. under South 24-Pgns W/S-I, PHE Dte. (SM/12045) | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | ORD/000867/2024-2025 | 4925/SWD-I | 03/12/2024 | 30 | SRIJON ENTERPRISE | 32 | 31.89 | 100
329 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -I | JE2,Junior Engineer | RTOR000106/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 30.18 | 0 | 0
330 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000087/2022-2023 | 1199/SWD-I | 02/09/2022 | 30 | UMAR ALI KHAN | 20.06 | 18.08 | 100
331 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at CHANDIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [Nos of FHTC- 472] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000096/2022-2023 | 1208/SWD-I | 02/09/2022 | 90 | M/S. SUMAN ENTERPRISE | 92.16 | 51.06 | 60
332 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at CHANDIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012519] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000126/2022-2023 | 1294/SWD-I | 14/09/2022 | 60 | JYOTI ENTERPRISE | 5.46 | 4.28 | 100
333 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHANDIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000168/2021-2022 | 1911/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 2.45 | 100
334 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based Chandipur piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12046) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000336/2024-2025 | 3310/SWD-I | 23/07/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 41.61 | 0 | 0
335 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chandipur PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/012519] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000788/2022-2023 | 3676/SWD-I | 29/03/2023 | 15 | UMAR ALI KHAN | 2.2 | 0 | 0
336 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000265/2023-2024 | 2416/SWD-I | 30/09/2023 | 0 | Resource Division | 4.06 | 0 | 0
337 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000340/2023-2024 | 269/SWD-I | 10/01/2024 | 0 | Resource Division | 2.91 | 0 | 0
338 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KAPINDAPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000089/2022-2023 | 1201/SWD-I | 02/09/2022 | 30 | BENGAL ENTERPRISE | 20.07 | 19.03 | 100
339 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KAPINDAPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000165/2021-2022 | 1913/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 2.62 | 100
340 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KAPINDAPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 941) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000236/2022-2023 | 1711/SWD-I | 02/11/2022 | 971 | SAKTI ENTERPRISE | 224.76 | 202.07 | 100
341 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at KAPINDAPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012516] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000288/2022-2023 | 1784/SWD-I | 07/11/2022 | 60 | M/S. FAIZUL HAQUE BISWAS | 5.75 | 4.75 | 0
342 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based Kapindapur piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12051) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000359/2024-2025 | 3459/SWD-I | 02/08/2024 | 45 | S R ENTERPRISE (BIRBHUM) | 50.51 | 0 | 0
343 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000101/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 6.89 | 0 | 0
344 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 0 | 8
345 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall Land development & Construction of service road at 2 nd Tube Well site for PANCHPARA PWSS to accommodate FHTC in within Mograhat-II Block for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of of South 24 Parganas District. (SM/13919) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000400/2024-2025 | 3689/SWD-I | 22/08/2024 | 225 | M/S UNIQUE ENTERPRISE | 18.87 | 0 | 50
346 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for PANCHPARA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13919] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000573/2022-2023 | 3066/SWD-I | 21/02/2023 | 30 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 31.79 | 31.17 | 100
347 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, Construction of Approach Road, Earth Filling, Drum Sheet walling for PANCHPARA Head Work Site to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Div-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/13919) [2nd call] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000771/2024-2025 | 4553/SWD-I | 06/11/2024 | 175 | KANAK GIRI | 35.53 | 0 | 70
348 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Panchpara Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000975/2022-2023 | 1428/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.76 | 2.72 | 100
349 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000197/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 30.38 | 0 | 0
350 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of DEHI MADAN MOLLA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2670] [TSM/018699] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000103/2023-2024 | 473/SWD-I | 04/05/2023 | 782 | BISWAS ENTERPRISE | 312.42 | 60.37 | 70
351 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, platform for FHTC, pipeline protection development of land and other allied works for Ground water based DEHI MEDAN MALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14856) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000340/2024-2025 | 3314/SWD-I | 23/07/2024 | 45 | BISWAS ENTERPRISE | 95.68 | 0 | 0
352 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for DEHI MEDAN MALLA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018699] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000622/2022-2023 | 3245/SWD-I | 01/03/2023 | 30 | RUBY ENTERPRISE | 31.65 | 0 | 0
353 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Head Work site for DEHIMEDAN MALLA PWSS to acccommodate FHTC in BARUIPUR block under South 24-Parganas W/S Division-I, South 24-Pgns district for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/14856] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000870/2023-2024 | 1327/SWD-I | 15/03/2024 | 15 | G.M. ENTERPRISE (MURSHIDABAD) | 15.8 | 15.27 | 100
354 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dehimedan Malla Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000930/2022-2023 | 1220/SWD-I | 05/09/2022 | 30 | GEO SOLUTION | 2.63 | 2.61 | 100
355 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DEHI MEDAN MALLA Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14856] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001151/2024-2025 | 369/SWD-I | 04/02/2025 | 30 | SIMPLEX DRILLING COMPANY | 15.8 | 0 | 0
356 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000100/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 54.56 | 0 | 0
357 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Head Work site for TEURHAT (ZONE-41) PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/14862] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000299/2024-2025 | 3180/SWD-I | 15/07/2024 | 15 | PADMA ENGINEERING CO. | 15.9 | 13.79 | 100
358 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (Four nos.) at TEURHAT piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/14862) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000683/2024-2025 | 4478/SWD-I | 30/10/2024 | 60 | R.K ENTERPRISE | 19.65 | 0 | 100
359 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (four) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TEURHAT PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/14862] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000719/2023-2024 | 362/SWD-I | 16/01/2024 | 45 | SAIKAT ENTERPRISE | 63.59 | 0 | 0
360 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TEURHAT MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2688] [TSM/018362] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000802/2022-2023 | 3693/SWD-I | 30/03/2023 | 90 | PATHIK PABAN NANDI | 428.89 | 350.24 | 85
361 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based TEAUR HAT Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000918/2022-2023 | 1169/SWD-I | 30/08/2022 | 30 | ASTER CONSULTANCY | 3.12 | 3.12 | 100
362 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000150/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 21.65 | 0 | 0
363 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for zone-VII, Ajodhyanagar (OHR Cap-450 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000308/2021-2022 | 2606/SWD-I | 15/03/2022 | 30 | MS R. DUTTA AND CO | 1.98 | 1.92 | 100
364 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-VII AT AJODHYANAGAR of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VII at AJODHYANAGAR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 3427 Nos.) | AE SWSD-II | JE1 | ORD/000515/2022-2023 | 2881/SWD-I | 13/02/2023 | 998 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 379.95 | 88.57 | 79
365 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of chlorination room, land development, repairing and renovation boundary wall and other allied works for Zone-VII (Ajodhyanagar) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. | AE SWSD-II | JE1 | ORD/000742/2024-2025 | 4640/SWD-I | 14/11/2024 | 75 | M/S SHIBAM ENTERPRISE | 130.62 | 0 | 2
366 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000125/2022-2023 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 20.45 | 0 | 0
367 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for initial 50% amount of the estimated cost Rs 17288159.00(Rupees one crore seventy two lakh eighty eight thousand one hundred fifty nine only) i.e. Rs 8644079.50 round off Rs 8644080.00( Rupees eighty six lakh forty four thousand eighty only) toward road restoration work of Keorapukur Julpia, Pailan Nepalgunj & Amgachiya Health Centre Road under Chak Balaibag, Bakeswar, Kismat Karimpur & Kastamahal Pipe Water Supply Scheme in Bishnupur-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | BILL/00346/2024-2025 | BP-2024-25-243 | 08/08/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 86.44 | 0 | 0
368 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of CHAK BALAIBAG AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000234/2021-2022 | 1974/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 3.1 | 2.94 | 100
369 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for CHAK BALAIBAG PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2793) [TSM/016350]. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000719/2022-2023 | 3564/SWD-I | 22/03/2023 | 90 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 414.08 | 18.06 | 32
370 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of rising main and additional pipeline for distribution system, construction of Boundary Wall, approach road, land development, protection of pipeline and road restoration for CHAK BALAIBAG Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/13783) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000741/2024-2025 | 4639/SWD-I | 14/11/2024 | 60 | M/S SHIBAM ENTERPRISE | 138.16 | 0 | 0
371 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000087/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 49.73 | 0 | 0
372 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of RAMMAKHALER CHAK PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 1749) [TSM/016316]. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000076/2023-2024 | 390/SWD-I | 28/04/2023 | 734 | MALAY KANTI DEY | 261.78 | 54.72 | 61
373 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
374 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design, construction of Boundary wall, Pump House for RAMMAKHALER CHAK PWSS of Bishnupur-I Block under South 24 Parganas W/S Division-I, PHE Dte., Dist.-South 24 Parganas. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000275/2024-2025 | 2925/SWD-I | 25/06/2024 | 300 | M/S SUBHODEEP ENTERPRISE | 140.22 | 0 | 0
375 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional distribution pipeline, Construction of approach road, protection of pipeline and other allied works for Rammakhaler Chak PWSS of Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas. (SM/13784) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000414/2024-2025 | 3730/SWD-I | 27/08/2024 | 45 | MALAY KANTI DEY | 65.01 | 0 | 4
376 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of RAMMAKHALER CHAK AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000421/2021-2022 | 1973/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.83 | 2.75 | 0
377 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for RAMMAKHALER CHAK PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016316] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000552/2022-2023 | 3041/SWD-I | 20/02/2023 | 30 | PADMA ENGINEERING CO. | 15.9 | 0 | 0
378 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RAMMAKHALER CHAK PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016316] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000601/2022-2023 | 3129/SWD-I | 24/02/2023 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 14.37 | 98
379 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at 2nd Tubewell site of Rammakhaler Chak Piped Water Supply Scheme under proposed ground water based Rammakhaler Chak PWSS to accommodate FHTC in Bishnupur-I Block, District-South 24-Pgns. under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/13784) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000756/2023-2024 | 656/SWD-I | 06/02/2024 | 15 | N ENTERPRISE | 3.97 | 0 | 0
380 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000119/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 36.66 | 0 | 0
381 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00664/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
382 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for LAKSHMIKANTAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000041/2023-2024 | 106/SWD-I | 10/04/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 0 | 0
383 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different Head Work Sites around South 24-Pgns. for the Engineering Teams of South 24-Pgns. W/S Circle, PHE Dte. under Executive Engineer, South 24-Pgns. Divn.-I, PHE Dte. [SM/14873] [w.e.f. 01/05/2025 to 29/10/2025] [Vehicle No- WB-05-4231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000057/2025-2026 | 1153/SWD-I | 28/04/2025 | 182 | PALASH DAS | 0.86 | 0 | 0
384 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of LAKSHMINARAYANPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2868] [TSM/018292] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000102/2023-2024 | 472/SWD-I | 04/05/2023 | 1080 | M/S A.B. ENTERPRISE | 389.11 | 0 | 60
385 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for LAKSHMINARAYANPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018292] (2nd Call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000117/2023-2024 | 529/SWD-I | 11/05/2023 | 30 | N.A. ENTERPRISE | 47.62 | 15.2 | 30
386 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC, restoration of road damaged due to laying of pipeline and other allied works for Ground water based LAKSHMINARAYANPUR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14873) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000737/2024-2025 | 4635/SWD-I | 14/11/2024 | 45 | ALISHA CONSTRUCTION | 87.6 | 0 | 0
387 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different Head Work Sites around South 24-Pgns. for the Engineering Teams of South 24-Pgns. W/S Circle, PHE Dte. under Executive Engineer, South 24-Pgns. Divn.-I, PHE Dte. [SM/14873] [w.e.f. 01/11/2024 to 30/04/2025] [Vehicle No- WB-05-4231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000875/2024-2025 | 4425/SWD-I | 28/10/2024 | 182 | PALASH DAS | 0.86 | 2.34 | 0
388 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Lakshminarayanpur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000960/2022-2023 | 1330/SWD-I | 15/09/2022 | 30 | GEO SOLUTION | 2.7 | 2.66 | 100
389 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000094/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 71.11 | 0 | 0
390 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for Initial 50% of Rs 18504950.00 (Rupees One Crore Eighty Five lakh Four Thousand Nine Hu8ndred Fifty only) i.e. Rs. 9252475.00 (Rupees Ninety two lakh Fifty Two Thousand Four Hundred seventy Five only) For road restoration, damaged due to laying of pipeline at Usthi Sirakol, Sirakol Amratala, Usthi Deula roads and road crossings under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (TSM/014912, SM/14729) | AE SWSD-II | JE4 | BILL/00593/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 92.52 | 0 | 0
391 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. chlorination room at O.H.R. sites for Zone-IV (Hijalhat), Zone-VIII (Khelarampur) & Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Division-I, PHE Dte. South 24 Parganas District. (SM/16187), (SM/14729), (SM/14725) | AE SWSD-II | JE4 | ORD/000026/2025-2026 | 978/SWD-I | 09/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 19.37 | 0 | 0
392 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, road restoration and other allied works for Zone-VIII (Khelarampur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14729] | AE SWSD-II | JE4 | ORD/000289/2024-2025 | 3105/SWD-I | 09/07/2024 | 241 | M/S. S.S. ENTERPRISE (NODAKHALI) | 426.02 | 34.58 | 20
393 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Widening & strengthening of the approach road from the main road towards the OHR Site (From Sirakole road to Pranab Sardar's house) of Zone-8 of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II | JE4 | ORD/000340/2021-2022 | 1233/SWD-I | 12/11/2021 | 15 | J. ENTERPRISE | 4.81 | 4.76 | 100
394 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Widening & strengthening of the approach road from the main road towards the OHR Site (From Samsuddin Mondal's house to Zone 8 OHR site) of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II | JE4 | ORD/000341/2021-2022 | 1234/SWD-I | 12/11/2021 | 15 | J. ENTERPRISE | 4.73 | 4.7 | 100
395 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Widening & strengthening of the approach road from the OHR Site of Zone-8 to Paschim Khelarampur F.P. School of Mograhat-I Block, Khelarampur mouza, G.P.- Srichanda under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur under South 24-Pgs. W/S Sub-Divn.-II PHE Dte. | AE SWSD-II | JE4 | ORD/000342/2021-2022 | 1236/SWD-I | 12/11/2021 | 15 | S.P. ENTERPRISE | 4.8 | 4.8 | 100
396 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of Zone-VIII (Khelarampur) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 116 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | AE SWSD-II | JE4 | ORD/000344/2021-2022 | 2693/SWD-I | 25/03/2022 | 90 | J. ENTERPRISE | 16.51 | 15.21 | 100
397 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1450 cum capacity 20 mtr. staging heigtht Over Head Reservoir as per Departmental Drawing and specification including RCC bored pile and pile cap, Laying Distribution System of piped water supply scheme in Zone - VIII at Khelarampur Mouza of Mograhat-I Block, for augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (Number of FHTC-11274 Nos.) | AE SWSD-II | JE4 | ORD/000677/2022-2023 | 3454/SWD-I | 14/03/2023 | 902 | M/S. S.S. ENTERPRISE | 1859.15 | 544.31 | 52
398 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000065/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 3.52 | 0 | 0
399 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.41] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00471/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 26.07 | 0 | 0
400 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Bodra - Champahati Road, from 2.30km to 4.50km(R/S) and 6.00 km to 11.00km (R/S) [ Total Length =7200.00m] . Restoration work damaged during laying of PHE pipe line under Bodra Pipe Line Prpject under South 24 Parganas Highway Division in the District of South 24 Parganas SM/14487 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00643/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 45.04 | 0 | 0
401 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for BADI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2842] (TSM/014173) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000499/2023-2024 | 2175/SWD-I | 05/09/2023 | 573 | SAMSUL ENTERPRISE | 511.61 | 129.46 | 35
402 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of BADI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/14487] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000557/2024-2025 | 4230/SWD-I | 30/09/2024 | 60 | SAMSUL ENTERPRISE | 81.96 | 0 | 0
403 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BADI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14487] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000572/2024-2025 | 4271/SWD-I | 01/10/2024 | 30 | PRANTIK DRILLING AGENCY | 15.9 | 0 | 0
404 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for BADI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014173] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000625/2022-2023 | 3238/SWD-I | 01/03/2023 | 30 | SETABUR RAHAMAN | 31.67 | 15.28 | 50
405 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000048/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 21.97 | 0 | 0
406 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000245/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 17.51 | 0 | 0
407 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (3 Nos.) for Augmentation of UTTAR GOPINATHPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 3706) [TSM/017505] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000101/2023-2024 | 471/SWD-I | 04/05/2023 | 90 | H. ENTERPRISE | 523.07 | 456.89 | 92
408 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (two) nos. Boundary walls (48.00mtr each) & Construction of approach Roads at TW-2 & TW-3 sites for UTTAR GOPINATHPUR PWSS to accommodate FHTC in Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14551) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000311/2024-2025 | 3223/SWD-I | 18/07/2024 | 30 | PADMA ENGINEERING CO. | 17.61 | 0 | 0
409 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional Laying distribution system for UTTAR GOPINATHPUR PWSS to accommodate FHTC in MOGRAHAT-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas. (SM/14551) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000415/2024-2025 | 3731/SWD-I | 27/08/2024 | 45 | AVIK ENTERPRISE | 90.2 | 0 | 0
410 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR GOPINATHPUR PWSS of MOGRAHAT-II block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017505] [2nd Call] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000683/2022-2023 | 3487/SWD-I | 15/03/2023 | 901 | SHAH ENTERPRISE | 47.64 | 30.97 | 76
411 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Land development of 2nd Tubewell site for the proposed ground water based UTTAR GOPINATHPUR Piped Water Supply Scheme to accommodate FHTC in Mograhat-II Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14551) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000839/2023-2024 | 1254/SWD-I | 13/03/2024 | 15 | HASIBA ENTERPRISE | 1.02 | 0 | 0
412 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Gopinathpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000976/2022-2023 | 1429/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.78 | 2.78 | 100
413 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000132/2022-2023 | 3391/SWD-I | 10/03/2023 | 0 | Resource Division | 22.83 | 0 | 0
414 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000154/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 60.07 | 0 | 0
415 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of GANGADUARA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1426] [TSM/018365] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000012/2023-2024 | 31/SWD-I | 05/04/2023 | 910 | SUN CONSTRUCTION | 330 | 168.83 | 80
416 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for GANGADUARA PWSS at Zone-43 of Baruipur block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018365] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000559/2022-2023 | 3051/SWD-I | 20/02/2023 | 30 | DEV & COMPANY (EMAIL ID- DEVANDCOMPANYKOL@GMAIL.COM) | 31.8 | 29.87 | 100
417 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based GANGADUARA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000924/2022-2023 | 1177/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 2.68 | 2.66 | 100
418 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000146/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.53 | 0 | 0
419 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for KHARUPATALIA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 839] [TSM/018473] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 935/SWD-I | 06/06/2023 | 390 | PARAMESWAR CHOWDHURY | 199.89 | 17.67 | 50
420 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Kharupatalia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000938/2022-2023 | 1251/SWD-I | 08/09/2022 | 30 | GEO SOLUTION | 2.54 | 2.54 | 100
421 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000125/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 24.11 | 0 | 0
422 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00545/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 62.5 | 0 | 0
423 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-III) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 943] [TSM/018222] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000055/2023-2024 | 274/SWD-I | 24/04/2023 | 918 | MS SARADA UDYOG | 151.16 | 124.14 | 90
424 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMNAGAR(III) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000406/2021-2022 | 1947/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 2.53 | 0
425 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC, protection work for pipeline and other allied works for "Proposed Ground water based RAMNAGAR ZONE-III piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district". (SM/15756) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000547/2024-2025 | 4135/SWD-I | 23/09/2024 | 45 | MS SARADA UDYOG | 25.01 | 0 | 0
426 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-III) PWSS to accommodate FHTC in BARUIPUR block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018222] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000630/2022-2023 | 3257/SWD-I | 02/03/2023 | 30 | BENGAL ENTERPRISE | 31.76 | 30.44 | 0
427 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000110/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 8.72 | 0 | 0
428 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for PETUA (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =1306] [TSM/018705] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000079/2023-2024 | 393/SWD-I | 28/04/2023 | 900 | L.N. ENTERPRISE | 214.84 | 154.56 | 90
429 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for PETUA (PART-II) PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018705] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000748/2022-2023 | 3610/SWD-I | 24/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 15.15 | 50
430 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Development of land of OHR site / 2nd TW site including Construction of approch road and other allied works for Ground Water Based PETUA (Part-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/17299) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000848/2023-2024 | 1253/SWD-I | 13/03/2024 | 630 | L.N. ENTERPRISE | 27.77 | 0 | 50
431 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Petua (Part-II) Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000929/2022-2023 | 1198/SWD-I | 02/09/2022 | 30 | GEO SOLUTION | 2.54 | 2.54 | 100
432 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for PETUA (PART-II) Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/17299] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/001146/2024-2025 | 327/SWD-I | 29/01/2025 | 30 | M/S MAA TARA ENTERPRISE | 15.57 | 0 | 0
433 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000112/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 33.22 | 0 | 0
434 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000178/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 33.22 | 0 | 0
435 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (Two) Pump Houses, one at TW-2 site and other at OHR site of NAINAN PWSS to accommodate FHTC in MAGRAHAT-II block South 24-Pgns District under South 24-Pgns W/S Division-I, PHE Dte. for augmentation of surface water bassed W/S scheme in the arsenic affected areas of South 24 Parganas District. (SM/12803) | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 1759/SWD-I | 02/07/2025 | 60 | SRI RAM CONSTRUCTION | 12.02 | 0 | 0
436 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Nainan PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000357/2022-2023 | 2276/SWD-I | 15/12/2022 | 30 | SAHI MASUM | 29.69 | 0 | 0
437 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "NAINAN Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000392/2022-2023 | 404/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.9 | 2.57 | 0
438 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary wall (length = 175.00m) & Construction of Approach Road (length = 50.00m) at Head Work Site for NAINAN PWSS to Accommodate FHTC in Mograhat-II Block under South 24 Pngs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12803) | Assistant Engineer | Junior Engineer | ORD/000421/2024-2025 | 3749/SWD-I | 28/08/2024 | 405 | SRI RAM CONSTRUCTION | 43.25 | 0 | 50
439 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of NAINAN of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1684] | Assistant Engineer | Junior Engineer | ORD/000546/2022-2023 | 3028/SWD-I | 20/02/2023 | 751 | SRI RAM CONSTRUCTION | 382.88 | 29.59 | 70
440 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Nainan PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014759] | Assistant Engineer | Junior Engineer | ORD/000735/2022-2023 | 3586/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 0 | 0
441 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000175/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 28.49 | 0 | 0
442 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1500 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I PURBO TETULBERIA MOUZA Piped Water Supply Scheme of KULTALI Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 14340] [TSM/011555 & TSM/016360] | AE BSD |  | ORD/000529/2023-2024 | 2344/SWD-I | 22/09/2023 | 558 | MADAN MOHAN MONDAL | 1916.42 | 0 | 60
443 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000072/2022-2023 | 2988/SWD-I | 20/02/2023 | 0 | Resource Division | 34.13 | 0 | 0
444 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of 315 mm diameter (OD) HDPE pipe by Horizontal Directional Drilling (HDD) process at South Bishnupur More on PWD road in between nodes 17 & 17a within Mandirbazar Block for Secondry Grid of under Providing Functional Household Tap Connection (FHTC) in Zone-VIII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte.(SM/11239) | AE HQ-I |  | ORD/000253/2024-2025 | 2716/SWD-I | 10/06/2024 | 25 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 50.53 | 49.11 | 100
445 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-VIII at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5655] | AE HQ-I |  | ORD/000618/2022-2023 | 3218/SWD-I | 28/02/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 377.53 | 0 | 0
446 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000058/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 34.83 | 0 | 0
447 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. no.43] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00466/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 27.93 | 0 | 0
448 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of MATHURAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13500) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000561/2024-2025 | 4234/SWD-I | 30/09/2024 | 60 | SUPER CONSTRUCTION | 81.22 | 0 | 0
449 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for MATHURAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015390] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000627/2022-2023 | 3236/SWD-I | 01/03/2023 | 30 | SABYASACHI CHAKI | 31.6 | 13.49 | 50
450 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Mathurapur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 1611] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000750/2022-2023 | 3612/SWD-I | 24/03/2023 | 300 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 404.21 | 239.22 | 50
451 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of MATHURAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13500) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000752/2024-2025 | 4674/SWD-I | 18/11/2024 | 45 | BANGA NIRMAN | 12.67 | 0 | 0
452 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000058/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 33.04 | 0 | 0
453 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000256/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 9.92 | 0 | 0
454 | South 24 Pgs W/S Division I |  | Construction of 4 (four) nos pipe carrying structures including laying of 150mm dia M.S. distribution Pipe at Node Point 71-101 (27.50mtr), 100mm M.S. distribution Pipe at Node Point 107-111 (44.00mtr) and 80mm M.S. distribution Pipe at Node Point 302-310 (22.00mtr) & Node Point 214-215 (16.50mtr) over Nepalgaunge-Julpia canal and 2 (two) nos Culvert crossing by laying of 150mm dia M.S distribution Pipe at Node point 358-359 (11.00mtr) & Node point 358-359 (11.00mtr) for ANDHARMANIK PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24-Pgns. W/S Divn.-I, PHE Dte. for Augmentation of surface water based water supply scheme in arsenic affected areas of South 24 Parganas District. [SM/18680] |  |  | ORD/000127/2025-2026 | 1782/SWD-I | 02/07/2025 | 60 | SRIJON ENTERPRISE | 24.53 | 0 | 0
455 | South 24 Pgs W/S Division I |  | Laying rising main and additional pipeline for distribution system, construction of boundary wall, approach road, pipeline protection, land development and road restoration for ANDHARMANIK PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/18680) |  |  | ORD/000371/2024-2025 | 3530/SWD-I | 07/08/2024 | 60 | J. D. ENTERPRISE | 204.18 | 0 | 0
456 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for ANDHARMANIK PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 3023) [TSM/016562]. |  |  | ORD/000410/2023-2024 | 1937/SWD-I | 22/08/2023 | 90 | TARUN ENTERPRISE | 475.56 | 218.34 | 40
457 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of ANDHARMANIK AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000463/2021-2022 | 1975/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 3.1 | 3.1 | 100
458 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 23.18 | 0 | 0
459 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for initial 50% amount of the estimated cost Rs 3983175.00(Rupees thirty nine lakh eighty three thousand one hundred seventy five only) i.e. Rs 1991587.50 round off Rs 1991588.00( Rupees nineteen lakh ninety one thousand five hundred eighty eight only) toward road restoration work of Pailan Nepalgunj (ch from 0.00 km to 1.450 km, left hand side) Road under Doulatpur & Kastamahal Pipe Water Supply Scheme in Bishnupur-I Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. | AE SWSD-II | JE1 | BILL/00347/2024-2025 | BP-2024-25-243 | 08/08/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 19.92 | 0 | 0
460 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall for 2nd & 3rd T/W site for BHANDARIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas for Augmentation of Surface Water Based Water Supply Sheme in the Arsenic affected areas of South 24 Parganas District. (51 mtr. For each site) [SM/18681] | AE SWSD-II | JE1 | ORD/000262/2024-2025 | 2677/SWD-I | 07/06/2024 | 524 | S.P. ENTERPRISE | 13.56 | 0 | 93
461 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Rising Main and additional pipeline as per revised design and drawing of distribution system for BHANDARIA piped water supply scheme to accommodate FHTC in Bishnupur-I block under South 24 Pgs W/S Division-I, South 24-Pgns District for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Pgns. District. (SM/18681) | AE SWSD-II | JE1 | ORD/000263/2024-2025 | 2678/SWD-I | 07/06/2024 | 417 | M/S. S.S. ENTERPRISE (NODAKHALI) | 91.24 | 27.15 | 65
462 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 02 nos. pump houses, approach road, land development and pipeline protection of rising and distribution system for BHANDARIA piped water supply scheme to accommodate FHTC in BISHNUPUR-I block under South 24 Parganas W/S Division-I, South 24-Parganas District for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/18681) | AE SWSD-II | JE1 | ORD/000272/2024-2025 | 2922/SWD-I | 25/06/2024 | 331 | M/S. S.S. ENTERPRISE (NODAKHALI) | 76.09 | 8.86 | 22
463 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second & Third Tubewell site for BHANDARIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017323] | AE SWSD-II | JE1 | ORD/000357/2023-2024 | 1743/SWD-I | 10/08/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 0
464 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of BHANDARIA PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/017323] (2nd call) | AE SWSD-II | JE1 | ORD/000383/2023-2024 | 1819/SWD-I | 16/08/2023 | 60 | KAMALA TRADING COMPANY | 17.64 | 0 | 0
465 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed BHANDARIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3721] | AE SWSD-II | JE1 | ORD/000406/2023-2024 | 1923/SWD-I | 22/08/2023 | 757 | M/S. S.S. ENTERPRISE | 482.45 | 321.65 | 78
466 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for KANNYANAGAR, BAGI & BHANDARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018432, TSM/017332, TSM/017323] | AE SWSD-II | JE1 | ORD/000422/2023-2024 | 1969/SWD-I | 24/08/2023 | 300 | H. T. R. CONSTRUCTION | 572.68 | 0 | 0
467 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Bhandaria Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000955/2022-2023 | 1130/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 2.89 | 2.87 | 100
468 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of temporary approach road and land development for the 2nd Tubewell site of Bhandaria PWSS of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District [SM/18681] | AE SWSD-II | JE1 | ORD/001081/2024-2025 | 5348/SWD-I | 30/12/2024 | 30 | MD RUHUL AMIN GOLDER | 7.8 | 0 | 0
469 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000093/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 58.78 | 0 | 0
470 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-I at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9379) | AE HQ-I |  | ORD/000423/2023-2024 | 1970/SWD-I | 24/08/2023 | 556 | MAA MANASA VYAPAAR | 1837.75 | 17.42 | 5
471 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000050/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 57.77 | 0 | 0
472 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 1.8 | 98
473 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for water supply at Dakhin Raypur W/S Scheme under South 24 Pgs W/S Division - I, PHE Dte. in the district of South 24 Parganas. [TSM/017296] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000349/2022-2023 | 2165/SWD-I | 09/12/2022 | 30 | ZINARUL ISLAM | 14.64 | 13.31 | 100
474 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall for proposed Pump House Site at Dakhin Raypur Mouza of Budge Budge-II block under South 24 Parganas W/S Divn.-I, PHE Dte. [TSM/ 017296] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000350/2022-2023 | 2194/SWD-I | 13/12/2022 | 45 | MODERN CONSTRUCTION | 6.92 | 6.82 | 100
475 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Dakhin Roypur Village(JL 70) of Budge Budge-II under South 24-Pgns W/S Divn.-I, PHE Dte. [TSM/017296] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000351/2022-2023 | 2195/SWD-I | 13/12/2022 | 60 | JYOTI ENTERPRISE | 6.81 | 6.73 | 100
476 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing pipe supporting structures for crossing gaps over newly constructed irrigation culverts with allied works for DAKSHIN RAYPUR PWSS to accommodate FHTC in Budge Budge -II block under South 24 Parganas W/S division-I, P.H.E. Dte of South 24-Pgns District for Augmentation of Surface Water Based Water Supply Scheme in the arsenic affected areas South 24-Pgns District (SM/13920) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000362/2024-2025 | 3504/SWD-I | 07/08/2024 | 45 | SUKUMAR DEBNATH | 13.33 | 13.3 | 50
477 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Pipe supporting structure with allied works under "Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District." (TSM/017296) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000399/2023-2024 | 1908/SWD-I | 21/08/2023 | 60 | SUKUMAR DEBNATH | 4.08 | 4.08 | 100
478 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Constructure of retaining Structure near Pump House under "Proposed Ground water based DAKHIN RAYPUR piped water supply scheme to accommodate FHTC in BUDGE BUDGE -II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District." (TSM/017296) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000413/2023-2024 | 1915/SWD-I | 21/08/2023 | 60 | SOHINI ENTERPRISE | 2.02 | 2.01 | 100
479 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection from proposed Tubewell to existing Distribution Line with Laying of HDPE pipeline for retrofitting of distribution system of Dakhin Raypur Village & providing FHTC under SWD - I, P.H.E. Dte District South 24 Parganas. (TSM/017296) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000511/2022-2023 | 2941/SWD-I | 16/02/2023 | 60 | M/S. S.S. ENTERPRISE | 104.69 | 101.32 | 90
480 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying HDPE pipeline under Ground Water Based Piped Water Supply Scheme of Dakshin Roypur to accommodate Functional Household Tap Connection (FHTC) in Budge Budge-II block South 24 Pgns. Dist. For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns Dist. under South 24 Pgns. Water Supply Division-I, PHE Dte. (SM/13920) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000662/2022-2023 | 3378/SWD-I | 10/03/2023 | 45 | S.P. ENTERPRISE | 6.05 | 6.03 | 100
481 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method at Dakshin Roypur PWSS of Budge Budge-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13920] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000698/2022-2023 | 3501/SWD-I | 16/03/2023 | 15 | MAHI CONSTRUCTION | 2.17 | 2.17 | 0
482 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Development of land at Dakdhin Roypur PWSS Tubewell site (JL No.-70, RS-352/984, LR Dag No.- 495) under Dakshin Roypur PWSS to accomodate FHTC in Budge Budge-II Block under South 24 Pgs W/S Division-I, PHE Dte. Dist. For Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Area of South 24-Pgns. Dist. (SM/13920) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000744/2022-2023 | 3595/SWD-I | 23/03/2023 | 15 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 5.05 | 5.05 | 0
483 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Dakshin Roypur Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000992/2022-2023 | 1532/SWD-I | 29/09/2022 | 30 | GEO SOLUTION | 2.42 | 2.41 | 100
484 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000122/2022-2023 | 3473/SWD-I | 15/03/2023 | 0 | Resource Division | 2.37 | 0 | 0
485 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "JAGADISHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18497) |  |  | ORD/000244/2024-2025 | 2664/SWD-I | 07/06/2024 | 45 | JYOTI ENTERPRISE | 10.26 | 0 | 0
486 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAGADISHPUR PWSS of Sonarpur Blockfor Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/017715] |  |  | ORD/000293/2023-2024 | 1658/SWD-I | 03/08/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 30.85 | 50
487 | South 24 Pgs W/S Division I |  | Construction of 350 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for JAGADISHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2503) (TSM/017715) |  |  | ORD/000426/2023-2024 | 1986/SWD-I | 25/08/2023 | 799 | G.B. CONSTRUCTION AND CO. | 703.02 | 274.19 | 50
488 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall,Land Development, Pathway,Drain & others allied works of Jagadishpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/18497] |  |  | ORD/000842/2023-2024 | 1208/SWD-I | 11/03/2024 | 45 | G.B. CONSTRUCTION AND CO. (DUMDUM) | 46.14 | 0 | 0
489 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000019/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 18.81 | 0 | 0
490 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000319/2023-2024 | 255/SWD-I | 10/01/2024 | 0 | Resource Division | 15.42 | 0 | 0
491 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SERPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018414] |  |  | ORD/000362/2023-2024 | 1771/SWD-I | 11/08/2023 | 30 | JSSM CONSTRUCTION | 31.72 | 0 | 50
492 | South 24 Pgs W/S Division I |  | Construction of 450 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for SERPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2549) (TSM/018414) |  |  | ORD/000421/2023-2024 | 1968/SWD-I | 24/08/2023 | 300 | SAMSUL ENTERPRISE | 468.39 | 108.36 | 20
493 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of SERPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18500) |  |  | ORD/001084/2024-2025 | 5212/SWD-I | 20/12/2024 | 60 | SAMSUL ENTERPRISE | 64.9 | 0 | 0
494 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1727/SWD-I | 09/08/2023 | 0 | Resource Division | 17.47 | 0 | 0
495 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000327/2023-2024 | 249/SWD-I | 10/01/2024 | 0 | Resource Division | 15.7 | 0 | 0
496 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. no.37] |  |  | BILL/00467/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 65.69 | 0 | 0
497 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TARDAHA KAPASATI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018470] |  |  | ORD/000301/2023-2024 | 1666/SWD-I | 03/08/2023 | 30 | ASIT PRAMANIK | 31.76 | 30.2 | 99
498 | South 24 Pgs W/S Division I |  | Construction of 450 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for TARDAHA KAPASATI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 3298) (TSM/018470) |  |  | ORD/000354/2023-2024 | 1740/SWD-I | 10/08/2023 | 300 | MRA NIRMAN UDYOG | 1034.36 | 663.37 | 35
499 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of TARDAH KAPASATI PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18501) |  |  | ORD/000678/2024-2025 | 4467/SWD-I | 29/10/2024 | 75 | MRA NIRMAN UDYOG | 201.31 | 0 | 0
500 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1727/SWD-I | 09/08/2023 | 0 | Resource Division | 44.58 | 0 | 0
501 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000321/2023-2024 | 256/SWD-I | 10/01/2024 | 0 | Resource Division | 20.32 | 0 | 0
502 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nischintipur W/S Scheme for Nischintipur Mouza near Head work Site and ajoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000114/2020-2021 | 1359/SWD-I | 08/12/2020 | 120 | JDJ ENTERPRISE | 91.87 | 160.03 | 0
503 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 186 to 190 & 192 to 196) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte. District South 24 Parganas. | AE SWSD-I |  | ORD/000088/2021-2022 | 1205/SWD-I | 09/11/2021 | 120 | SATYABRATA CHAKRABORTY | 268.77 | 148.17 | 60
504 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Buita W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM/ 8292 ) PART-VII | AE SWSD-I |  | ORD/000456/2022-2023 | 2728/SWD-I | 27/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 18.68 | 18.55 | 100
505 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for ALIPOREPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000031/2022-2023 | 915/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.18 | 13.06 | 100
506 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed ALIPORE PIPE WATER SUPPLY SCHEME Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 1038] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000184/2022-2023 | 1487/SWD-I | 28/09/2022 | 90 | MAA LAXMI ENTERPRISE | 119.84 | 113.91 | 90
507 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 7.3 | 60
508 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at 1st Tubewell site under Alipore PWSS to accommodate FHTC in Bishnupur-I Block under South 24 pgs W/S Division-I, P.H.E Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000245/2023-2024 | 1487/SWD-I | 19/07/2023 | 15 | MAA LAXMI ENTERPRISE | 2.97 | 2.97 | 100
509 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main & additional pipeline for distribution system, construction of boundary walls for 1st & 2nd Tubewell sites and other allied works for proposed ground water based ALIPORE PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11493) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000274/2024-2025 | 2924/SWD-I | 25/06/2024 | 45 | MAA LAXMI ENTERPRISE | 67.93 | 0 | 0
510 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "ALIPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000400/2022-2023 | 458/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 2.5 | 100
511 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ALIPORE PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000507/2022-2023 | 2905/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 100
512 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for ALIPORE PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000597/2022-2023 | 3124/SWD-I | 24/02/2023 | 752 | CIVIL CONSULTANT | 15.88 | 0 | 100
513 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed ALIPORE Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011230] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000811/2022-2023 | 3703/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.88 | 0.75 | 100
514 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000014/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 6.39 | 0 | 0
515 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000116/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.09 | 0 | 0
516 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JOYKRISHNA NAGAR PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000086/2022-2023 | 1197/SWD-I | 02/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 0 | 100
517 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of JOYKRISHNANAGAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000217/2021-2022 | 1939/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.76 | 100
518 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JOYKRISHNANAGAR Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1904) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000341/2022-2023 | 2091/SWD-I | 02/12/2022 | 300 | SUPRITI ENTERPRISE | 534.05 | 184.52 | 40
519 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Joykrishnanagar of Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000376/2022-2023 | 2210/SWD-I | 13/12/2022 | 60 | S.M ENTERPRISE | 11.49 | 0 | 0
520 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of JOYKRISHNA NAGAR PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011093] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 2111/SWD-I | 30/08/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.14 | 0 | 0
521 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000022/2022-2023 | 1983 | 25/11/2022 | 0 | Resource Division | 11.73 | 0 | 0
522 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000080/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
523 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.34] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00494/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 0.68 | 0 | 0
524 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for BELEGACHI PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000085/2022-2023 | 1196/SWD-I | 02/09/2022 | 30 | VISHAL CONSTRUCTION CO. | 28.53 | 25.99 | 100
525 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BELGACHHI Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000215/2021-2022 | 1937/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.76 | 100
526 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at BELEGACHI Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1604) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000343/2022-2023 | 2148/SWDI | 08/12/2022 | 300 | M/S. S.S. ENTERPRISE | 524.03 | 245.46 | 50
527 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Belegachi at Baruipur Block for under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 2202/SWD-I | 13/12/2022 | 60 | M/S. TORSA ENTERPRISE | 11.51 | 10.64 | 100
528 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of BELEGACHI PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011099] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000458/2023-2024 | 2110/SWD-I | 30/08/2023 | 15 | VISHAL CONSTRUCTION CO. (E-MAIL ID :- VISHALCONSTRUCTION.VALVES@GMAIL.COM) | 3.14 | 3.13 | 100
529 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000082/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 14.96 | 0 | 0
530 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 500 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.3829) | AE HQ-I |  | ORD/000461/2023-2024 | 2139/SWD-I | 31/08/2023 | 780 | BALAJEE ENTERPRISES | 760.19 | 185.61 | 75
531 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000054/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 23.59 | 0 | 0
532 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.45] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00474/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 53.13 | 0 | 0
533 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for GARANBERIA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Bhangar-I Block, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000268/2022-2023 | 1779/SWD-I | 07/11/2022 | 30 | MOMINUL BISWAS | 30.03 | 24.44 | 100
534 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for GARANBERIA PWSS at headwork site & 2nd Tubewell site of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12206] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000480/2022-2023 | 2809/SWD-I | 02/02/2023 | 15 | MOMINUL BISWAS | 3.13 | 3.13 | 100
535 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of GARANBERIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12206) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000564/2024-2025 | 4237/SWD-I | 30/09/2024 | 456 | SRI RAM CONSTRUCTION | 81.81 | 0 | 30
536 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Garanberia Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 1146] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000723/2022-2023 | 3566/SWD-I | 22/03/2023 | 853 | SRI RAM CONSTRUCTION | 355.71 | 159.13 | 60
537 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000054/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 11.8 | 0 | 0
538 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000221/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 7.06 | 0 | 0
539 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work , cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00759/2024-2025 | BP-2024-25-451 | 06/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 12 | 0 | 0
540 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for SITAKUNDU (ZONE-II) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000079/2022-2023 | 1190/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 37.11 | 100
541 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at SITAKUNDU (Zone-II) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1753) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000234/2022-2023 | 1710/SWD-I | 02/11/2022 | 881 | M/S R.K. ENTERPRISE | 372.96 | 129.32 | 80
542 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Sitakundu (Zone-II) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000361/2022-2023 | 2204/SWD-I | 13/12/2022 | 60 | JOY GURU TRADING | 11.52 | 9.49 | 0
543 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SITAKUNDU(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000444/2021-2022 | 1950/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.63 | 100
544 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SITAKUNDU [Zone-II] PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11646] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000806/2023-2024 | 1289/SWD-I | 15/03/2024 | 15 | TAPAS KUMAR GIRI | 4.41 | 0 | 100
545 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls with land development and other allied works for Ground Water Based SITAKUNDU (Zone-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/11646) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000847/2023-2024 | 1252/SWD-I | 13/03/2024 | 609 | BAIDYA ENTERPRISE | 49.19 | 0 | 51
546 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000085/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 11.9 | 0 | 0
547 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Chakraborty Abad (Kalabaru,J.L-114) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1100) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000185/2022-2023 | 1488/SWD-I | 28/09/2022 | 120 | TANMOY ROY CHOWDHURY | 197.72 | 123.17 | 77
548 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHAKRABORTY ABAD PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009670] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000241/2022-2023 | 1684/SWD-I | 01/11/2022 | 30 | SIMPLEX DRILLING COMPANY | 21.48 | 0 | 0
549 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at CHAKRABORTY ABAD of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009670] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000290/2022-2023 | 1785/SWD-I | 07/11/2022 | 60 | SANJAY ENTERPRISE | 5.8 | 0 | 0
550 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chakraborty Abad PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000632/2022-2023 | 3261/SWD-I | 02/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 2.24 | 0 | 0
551 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground Water Based Water Supply Scheme at CHAKRABORTY ABAD (Kalabaru, JL-114) Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns District. (SM/11296) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000913/2023-2024 | 1203/SWD-I | 11/03/2024 | 315 | UNI DEVELOPERS AND CONTRACTORS | 23.98 | 10.73 | 40
552 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000075/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 6.78 | 0 | 0
553 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000277/2023-2024 | 2426/SWD-I | 30/09/2023 | 0 | Resource Division | 1.73 | 0 | 0
554 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V A at Monirtat mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4150] | AE BSD |  | ORD/000270/2023-2024 | 1550/SWD-I | 25/07/2023 | 120 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 316.11 | 0 | 0
555 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-V B at Monirtat mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3958] | AE BSD |  | ORD/000813/2022-2023 | 3692/SWD-I | 30/03/2023 | 120 | CALCON CONSTRUCTIONS | 299.61 | 39.88 | 30
556 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000082/2022-2023 | 2998/SWD-I | 20/02/2023 | 0 | Resource Division | 49.95 | 0 | 0
557 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-IX at GHOLA NOAPARA Mouza of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-IX at GHOLA NOAPARA of MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 5309 Nos.) | AE SWSD-II | JE4 | ORD/000803/2022-2023 | 3694/SWD-I | 30/03/2023 | 120 | MANASH GHOSH | 603.4 | 160.33 | 30
558 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000141/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 32.7 | 0 | 0
559 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1 (one) no pipe carrying structures for laying of distribution pipeline over Nainpur Deula canal at Node Point 946 - 1205 for the laying of distribution system at Zone-V, Magrahat-I Block within 'MEGA SURFACE WATER BASED WATER SUPPLY SCHEME' for Falta-Mathurapur, Dist- South 24 Pgs W/S Division-I, P.H.E. Dte. (SM/11267) | AE SWSD-II | JE3 | ORD/000098/2025-2026 | 1773/SWD-I | 02/07/2025 | 45 | SRIJON ENTERPRISE | 32.96 | 0 | 0
560 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | 9305 Nos. Functional Household Tap Connection (FHTC) in Zone-V at Barijpur mouza of Mograhat-I block for providing 100% FHTC within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC-9305 Nos.) | AE SWSD-II | JE3 | ORD/000678/2022-2023 | 3457/SWD-I | 14/03/2023 | 840 | M/S. S.S. ENTERPRISE | 554.56 | 61.13 | 70
561 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000135/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 57.32 | 0 | 0
562 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KASTHAMAHAL Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11733] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000175/2022-2023 | 1450/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.26 | 13.26 | 100
563 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
564 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Kasthamahal PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11733) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000264/2024-2025 | 2679/SWD-I | 07/06/2024 | 45 | S.R ENTERPRISE (KARUNAMOYEE) | 50.56 | 0 | 10
565 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "KASTHA MAHAL Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000408/2022-2023 | 465/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 2.51 | 100
566 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KASTHAMAHAL Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11733) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000432/2022-2023 | 2576/SWD-I | 10/01/2023 | 60 | R.G ENTERPRISE | 6.04 | 5.8 | 100
567 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KASTHAMAHAL PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 985 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000498/2022-2023 | 2866/SWD-I | 09/02/2023 | 90 | S.R ENTERPRISE (EMAIL- SOMENATH.MAJUMDER9874@GMAIL.COM) | 119.6 | 115.8 | 95
568 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KASTHAMAHAL PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011792] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000524/2022-2023 | 2920/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 100
569 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method at Second Tube-well site for KASTHAMAHAL PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011792] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000540/2022-2023 | 3018/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
570 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000111/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 36.56 | 0 | 0
571 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9619) | AE HQ-I |  | ORD/000054/2023-2024 | 273/SWD-I | 24/04/2023 | 708 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1667.83 | 51.23 | 20
572 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of 600 mm dia DI Secondary Grid pipeline including allied works infront of Mandirbazar GLR & Bijoyganj Bazar (gap negotiation) within Mandirbazar Block in connection with Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply scheme for Falta-Mathurapur, Dist. South 24-pgs. under South 24-Pgns W/S Division-I, PHE Dte. (SM/11243) | AE HQ-I |  | ORD/000798/2023-2024 | 1146/SWD-I | 07/03/2024 | 30 | S. ROY AND ASSOCIATES | 39.85 | 29.31 | 90
573 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000051/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 59.25 | 0 | 0
574 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia& 300 mtr. deepTubewell by Rotary method for MASTIKARI PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/011743] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000106/2022-2023 | 1233/SWD-I | 07/09/2022 | 30 | DIPALI CONSTRUCTION | 28.52 | 0 | 100
575 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 01 No. 300 Cum. capacity OHR and 02 Nos. 350 Cum capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of JANGALIA, MASTIKARI and PADMERHAT MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 5561] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 1374/SWD-I | 12/07/2023 | 900 | KAR CONSTRUCTION | 1262.63 | 0 | 30
576 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection work for pipeline, approach road, development of land and other allied works for Ground water based MASTIKARI piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/11779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000226/2024-2025 | 2643/SWD-I | 07/06/2024 | 45 | S.C. ENTERPRISE | 16.76 | 0 | 0
577 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "MASTIKARI Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000388/2022-2023 | 470/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.76 | 2.73 | 100
578 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000161/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 41.06 | 0 | 0
579 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II B at Jalaberia mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4835] | AE BSD |  | ORD/000218/2022-2023 | 1627/SWD-I | 20/10/2022 | 1131 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 367.31 | 99.53 | 40
580 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-II A at Jalaberia mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur district.- South 24 Pgns. under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4568] | AE BSD |  | ORD/000524/2023-2024 | 2306/SWD-I | 20/09/2023 | 690 | SPA ENTERPRISE | 365.25 | 0 | 40
581 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000073/2022-2023 | 2989/SWD-I | 20/02/2023 | 0 | Resource Division | 57.92 | 0 | 0
582 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VII B at Binodpur (Maipith) mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4614] | AE BSD |  | ORD/000222/2022-2023 | 1640/SWD-I | 20/10/2022 | 960 | K P CONSTRUCTION | 352.6 | 202.14 | 80
583 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VII A at Binodpur (Maipith) mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 4892] | AE BSD |  | ORD/000306/2022-2023 | 1910/SWD-I | 18/11/2022 | 120 | MRITYUNJOY MUKHERJEE AND CO | 373.71 | 0 | 30
584 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000077/2022-2023 | 2993/SWD-I | 20/02/2023 | 0 | Resource Division | 58.56 | 0 | 0
585 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of DHOPA HAT MOUZA in MANDIRBAZAR (ZONE-IV) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000390/2021-2022 | 1986/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 4 | 2.91 | 100
586 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-IV at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2270) | AE HQ-I |  | ORD/000712/2022-2023 | 3528/SWD-I | 17/03/2023 | 300 | SUPER SKILL | 458.61 | 144.44 | 25
587 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed OHR Site of Zone-IV within Mandirbazar block, Mouza-Dhopahat (JL No-119), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas under South 24-Pgns. W/S Division-I, PHE Dte. (Length- 160 mtr.) | AE HQ-I |  | ORD/000727/2022-2023 | 190/SWD-I | 26/04/2022 | 60 | M/S. KALPANA CONSTRUCTION | 21.75 | 21.69 | 100
588 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Protection of pipe line and other allied work for laying of distribution pipes in between Zone X and Zone IV under Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone IV at Mandirbazar block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/12204) | AE HQ-I |  | ORD/001131/2024-2025 | 194/SWD-I | 17/01/2025 | 45 | BISWAS CONSTRUCTION | 26.73 | 0 | 0
589 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000046/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 2.74 | 0 | 0
590 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | Assistant Engineer | Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 0 | 8
591 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for DHANPOTA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13918] | Assistant Engineer | Junior Engineer | ORD/000624/2022-2023 | 3241/SWD-I | 01/03/2023 | 30 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 0
592 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Dhanpota Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000982/2022-2023 | 1456/SWD-I | 26/09/2022 | 30 | GEO SOLUTION | 2.65 | 2.62 | 100
593 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000169/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 29.13 | 0 | 0
594 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DIHI NARAYANI MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1571] [TSM/014903] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000282/2023-2024 | 1566/SWD-I | 27/07/2023 | 644 | M/S. SUMAN ENTERPRISE | 397.95 | 0 | 50
595 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Approach Road (length = 25.00m) & Land Development at OHR site for DIHI NARAYANI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/13921) [2nd call] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000548/2024-2025 | 4136/SWD-I | 23/09/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 7.28 | 0 | 0
596 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Head work site for DIHI NARAYANI Piped Water Supply Scheme to accommodate FHTC in MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13921] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000665/2024-2025 | 4395/SWD-I | 23/10/2024 | 30 | M/S. SHYAM CONSTRUCTION | 18.69 | 0 | 0
597 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for DIHI NARAYANI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [SM/13921][2nd Call] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000690/2022-2023 | 3479/SWD-I | 15/03/2023 | 30 | BENGAL ENTERPRISE | 31.75 | 0 | 0
598 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 900mm Dia Double Row Hume Pipe Culvert for DIHI NARAYANI PWSS to accommodate FHTC under Mograhat-II Block in the District of South 24 Parganas for Augmentation of Surfacc Water Based Water Supply Scheme under South 24-Pgns. W/S Division-I, PHE Dte. (SM/13921) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000813/2023-2024 | 1149/SWD-I | 07/03/2024 | 30 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 5.77 | 0 | 80
599 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "DIHINARAYANI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000881/2022-2023 | 412/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.76 | 2.64 | 0
600 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000203/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 31.74 | 0 | 0
601 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sarberia-Dhamua Road from 0+00 to 6+520 km Restoration of Damages occurred due to damages caused/ to be caused by laying of pipe line by PHE Dte. under Sarberia PWSS,Jaldhapa PWSS,Multi PWSS under South 24 Parganas Highway Division in the district of South 24 Parganas. | Assistant Engineer | Junior Engineer | BILL/00645/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 106.91 | 0 | 0
602 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (3 Nos.) for Augmentation of MULTI Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 3314) [TSM/017503] | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 468/SWD-I | 04/05/2023 | 719 | KINGS & CO. | 512.59 | 416.99 | 87
603 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall, Box Culvert & Development of Land at TW-2 site and Construction of Service Road at OHR site & TW2 site for MULTI PWSS to accommodate FHTC within Mograhat-II Block underSouth 24-Pgns, W/S Divn-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of of South 24 Parganas District (SM/14663) | Assistant Engineer | Junior Engineer | ORD/000330/2024-2025 | 3268/SWD-I | 22/07/2024 | 272 | TIYASHA ENTERPRISE | 23.89 | 0 | 40
604 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional 60mtr. boring of Sinking of 02 (Two ) nos. (for 2nd TW a7 3rd TW) Rig bored 250mm X 150mm dia. & upto 360 mtr. deep Tubewell by Rotary method for MULTI PWSS of Mograhat-II Block under South 24-Pgns. W/S Divn.-I, PHE Dte. for Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas District. (SM/14663) | Assistant Engineer | Junior Engineer | ORD/000530/2024-2025 | 4076/SWD-I | 19/09/2024 | 194 | TRAYEE DECORATOR | 4.72 | 0 | 30
605 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MULTI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [TSM/017503][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000686/2022-2023 | 3485/SWD-I | 15/03/2023 | 713 | TRAYEE DECORATOR | 47.63 | 15.43 | 66
606 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length = 51.00m), Development of Land at 3rd Tubewell site and Construction of Service Road (length = 25.00m) at 3rd Tubewell site for MULTI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14663) | Assistant Engineer | Junior Engineer | ORD/000868/2024-2025 | 4926/SWD-I | 03/12/2024 | 60 | M/S ASHA ENGINEERING | 12.41 | 0 | 0
607 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Multi Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000978/2022-2023 | 1434/SWD-I | 23/09/2022 | 30 | GEO SOLUTION | 2.84 | 2.84 | 100
608 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000131/2022-2023 | 3390/SWD-I | 10/03/2023 | 0 | Resource Division | 20.41 | 0 | 0
609 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000158/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 52.85 | 0 | 0
610 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at UREL CHANDPUR Mouza of Mograhat-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2247] [TSM/017336] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000063/2023-2024 | 367/SWD-I | 27/04/2023 | 811 | M/S V.P. JAIN | 319.81 | 222.58 | 95
611 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based UREL CHANDPUR piped water supply scheme to accommodate FHTC in Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14863) | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000323/2024-2025 | 3256/SWD-I | 19/07/2024 | 60 | M/S V.P. JAIN | 41.83 | 0 | 0
612 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tub-ewell having 66 mtr. housing pipe by Rotary method for UREL CHANDPUR PWSS of Mograhat-II block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017336] | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000550/2022-2023 | 3049/SWD-I | 20/02/2023 | 780 | PADMA ENGINEERING CO. | 31.8 | 15.11 | 100
613 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Urel Chandpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | ORD/000970/2022-2023 | 1387/SWD-I | 20/09/2022 | 30 | GEO SOLUTION | 2.7 | 2.69 | 100
614 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000133/2022-2023 | 3392/SWD-I | 10/03/2023 | 0 | Resource Division | 13.84 | 0 | 0
615 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | Junior Engineer | RTOR000176/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 39.14 | 0 | 0
616 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Joynagar-Moydah-Jibonmondalerhat Road from1.50Kmp to 6.00kmp and 7.30 Kmp to 8.40Kmp. Restoration of Hard Shoulder due to laying of Pipeline by PHED. Go WO under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W.(Roads Directorate in District of South 24- Parganas. | AE BSD |  | BILL/00656/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.8 | 0 | 0
617 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD |  | BILL/00666/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
618 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall along with humepipe culvert bridge for the approch road of proposed OHR Site at Nayapukuria Mouza, JL No.43, Khatian No. 1079, Plot No. 661 & 662; within Joynagar-II block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. [Length - 180.0 mtr.] | AE BSD |  | ORD/000378/2021-2022 | 1581/SWD-I | 27/12/2021 | 90 | SANKAR HALDER | 33.44 | 31.65 | 0
619 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I NAYAPUKURIA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 10830] [TSM/015333 & TSM/011546] | AE BSD |  | ORD/000568/2023-2024 | 2650/SWD-I | 27/10/2023 | 904 | M/S GHOSH AND CO. | 1544.66 | 214.33 | 75
620 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for MATHURAPUR-I Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] | AE BSD |  | ORD/000653/2024-2025 | 4376/SWD-I | 22/10/2024 | 90 | A.P POWER AND CONCRETE | 15.66 | 0 | 0
621 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for JOYNAGAR-II Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-I at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/14140] | AE BSD |  | ORD/000654/2024-2025 | 4377/SWD-I | 22/10/2024 | 90 | BISWAS CONSTRUCTION | 15.58 | 0 | 100
622 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Laying Distribution System of ZONE-I at JOYNAGAR-II Block, for implementation of JJM under Augmentation of Surface Based Water Supply Scheme in the Arsenic affected areas of South 24-Parganas district. under Baruipur Sub-Division of South 24 pgns. W/S Division -I P.H.E Dte. (SM/14140) | AE BSD |  | ORD/000727/2024-2025 | 4614/SWD-I | 13/11/2024 | 305 | MILAN GHOSH | 478.06 | 0 | 40
623 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for application of protective coating on M.S pipe for Railway crossing at Dakshin Bishnupur Rail gate under Mega Surface water Based Water Supply Scheme for Falta-Mathurapur, Dist. South24-Pgns. of South 24-Pgs. Water Supply Divn.-I, PHE Dte. [SM/14140] | AE BSD |  | ORD/000756/2024-2025 | 4677/SWD-I | 18/11/2024 | 15 | DIAMOND ENTERPRISE | 3.81 | 3.8 | 100
624 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of G.I. Pipe, Collapsible Gate, Laying of 100 mm thick interlocking design concrete paver block (M-15) grade for Mathurapur-I GLR in connection with Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist.-South 24-Parganas under Baruipur Sub-Division of SWD-I, PHE Dte. (SM/14140) | AE BSD |  | ORD/000760/2024-2025 | 4681/SWD-I | 18/11/2024 | 30 | DIAMOND ENTERPRISE | 9.4 | 9.39 | 100
625 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Raidighi River in between nodes 12 & 13 of Secondary Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/14140) | AE BSD |  | ORD/000775/2024-2025 | 4761/SWD-I | 21/11/2024 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 139.05 | 0 | 0
626 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000206/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 76.87 | 0 | 0
627 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000299/2023-2024 | 2438/SWD-I | 30/09/2023 | 0 | Resource Division | 132.42 | 0 | 0
628 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of JALGHARA in MOGRAHAT-I (ZONE-X/A) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | Assistant Engineer | JE2 | ORD/000305/2021-2022 | 1982/SWD-I | 27/01/2022 | 30 | RADIANT | 3.32 | 3.01 | 0
629 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of Zone-X/A (Jal Ghara) at Mograhat-I block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur (Length- 112 mtr.) under South 24-Pgs. W/S Division-I PHE Dte. | Assistant Engineer | JE2 | ORD/000379/2021-2022 | 2691/SWD-I | 25/03/2022 | 90 | MS P B CONSTRUCTION | 15.28 | 14.92 | 100
630 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, additional pipelines of distribution system, protection of pipelines, construction of approach road and Chlorination Room under Augmentation of existing laying distribution system and new OHR and allied works to extend the benefit of 100% household in Zone-X/A at JALGHARA of Magrahat -I Block within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under South 24 Pgns W/S Division-I. PHE Dte (SM/14724) | Assistant Engineer | JE2 | ORD/000442/2024-2025 | 3892/SWD-I | 04/09/2024 | 90 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 333.65 | 0 | 0
631 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/A AT JALGHARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/A AT JALGHARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Total Number of FHTC ¿ 9256 Nos.) | Assistant Engineer | JE2 | ORD/000804/2022-2023 | 3695/SWD-I | 30/03/2023 | 734 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1210.7 | 142.51 | 25
632 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000067/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 298.22 | 0 | 0
633 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room alongwith Laying distribution system, Rising main, Functional Household Tap connection(FHTC) for piped water supply scheme at KALIKAPUR BARASAT Mouza of Joynagar-I Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2904] [TSM/018436] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 100/SWD-I | 10/04/2023 | 817 | MILAN GHOSH | 363.92 | 294.76 | 90
634 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based KALIKAPUR BARASAT piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14872) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000401/2024-2025 | 3681/SWD-I | 22/08/2024 | 322 | MILAN GHOSH | 92.68 | 0 | 50
635 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for KALIKAPUR BARASAT PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018436] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000582/2022-2023 | 3067/SWD-I | 21/02/2023 | 975 | WATER TECH (E-MAIL :- ENVO.WATERTECH@GMAIL.COM) | 47.69 | 0 | 100
636 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Kalikapur Barasat Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000967/2022-2023 | 1384/SWD-I | 20/09/2022 | 30 | GEO SOLUTION | 2.77 | 2.74 | 100
637 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000135/2022-2023 | 3394/SWD-I | 10/03/2023 | 0 | Resource Division | 17.89 | 0 | 0
638 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000283/2023-2024 | 2415/SWD-I | 30/09/2023 | 0 | Resource Division | 52.36 | 0 | 0
639 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying on distribution system at zone-V, Mograhat-I Block under 'MEGA SURFACE WTER BASED WATER SUPPLY SCHEME" for Falta-Mathurapur, Dist. South 24-Pgs. Under South 24-Pgns. W/S Divn.-I, PHE Dte. | AE SWSD-II | JE3 | ORD/000140/2022-2023 | 1359/SWD-I | 19/09/2022 | 925 | M/S. S.S. ENTERPRISE | 511.9 | 131.02 | 75
640 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of additional pipe line, protection of distribution pipe line & construction of FHTC Platform, approach road, land development, chlorination room, and other allied works for Zone-V (Barijpur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/14727] | AE SWSD-II | JE3 | ORD/000368/2024-2025 | 3527/SWD-I | 07/08/2024 | 273 | M/S. S.S. ENTERPRISE (NODAKHALI) | 480.15 | 0 | 40
641 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE3 | RTOR000257/2023-2024 | 1718/SWD-I | 08/08/2023 | 0 | Resource Division | 188.58 | 0 | 0
642 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for zone-X/B, Kalikapota (OHR Cap-600 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II | JE2 | ORD/000309/2021-2022 | 2605/SWD-I | 15/03/2022 | 365 | MS R. DUTTA AND CO | 2.08 | 2.08 | 100
643 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, additional pipelines of distribution system, protection of pipelines, upgradation of boundary wall and construction of Chlorination Roomunder Augmentation of existing laying distribution system and new OHR and allied works to extend the benefit of 100% household in Zone-X/B at KALIKAPOTA of Magrahat -I Block within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under South 24 Pgns W/S Division-I. PHE Dte (SM/14728) | AE SWSD-II | JE2 | ORD/000406/2024-2025 | 3630/SWD-I | 20/08/2024 | 316 | HUMAYUN SK. CONSTRUCTION | 209.98 | 0 | 20
644 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 600 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/B AT KALIKAPOTA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/B KALIKAPOTA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 4780 Nos.) | AE SWSD-II | JE2 | ORD/000751/2022-2023 | 3618/SWD-I | 24/03/2023 | 740 | TARUN ENTERPRISE | 922.07 | 544.12 | 70
645 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BELARIA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016728] (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000111/2023-2024 | 518/SWD-I | 10/05/2023 | 30 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 47.68 | 0 | 0
646 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 450 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of BELARIA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2889] [TSM/016728] | Assistant Engineer | Junior Engineer | ORD/000372/2023-2024 | 1781/SWD-I | 11/08/2023 | 300 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 600.96 | 0 | 0
647 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary Wall (length=175.00m) & Construction of Service Road (length=300.00m) at OHR Site (1st Tubewell Site) for BELARIA PWSS to accommodate FHTC in Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based WAter Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/14548) | Assistant Engineer | Junior Engineer | ORD/000671/2024-2025 | 4397/SWD-I | 23/10/2024 | 90 | M/S SHIBAM ENTERPRISE | 83.71 | 0 | 0
648 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "BELARIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000879/2022-2023 | 418/SWD-I | 20/05/2022 | 15 | CHAYANIKA ENGINEERING CONSULTANCY | 2.83 | 2.76 | 0
649 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000286/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 41.07 | 0 | 0
650 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAMALHATI PWSS of BARUIPUR Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/019799] (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 559/SWD-I | 12/05/2023 | 30 | BHATTACHARJEE AND CO | 31.68 | 0 | 90
651 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for JAMALHATI MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =508] [TSM/019799] | Assistant Engineer | Junior Engineer | ORD/000146/2023-2024 | 718/SWD-I | 29/05/2023 | 90 | MS MANABESH ROY | 132.6 | 28.05 | 40
652 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Jamalhati Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000920/2022-2023 | 1171/SWD-I | 30/08/2022 | 30 | GEO SOLUTION | 2.46 | 2.45 | 100
653 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000264/2023-2024 | 2429/SWD-I | 30/09/2023 | 0 | Resource Division | 21.25 | 0 | 0
654 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000329/2023-2024 | 274/SWD-I | 10/01/2024 | 0 | Resource Division | 3.13 | 0 | 0
655 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump House cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for SANKARPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC =556] [TSM/017762] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000161/2023-2024 | 934/SWD-I | 06/06/2023 | 900 | DIPTI ENTERPRISE | 138.93 | 61.56 | 80
656 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SANKARPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017762] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000652/2022-2023 | 3349/SWD-I | 09/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 15.15 | 50
657 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Sankarpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000932/2022-2023 | 1224/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.46 | 2.45 | 100
658 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000113/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 25.88 | 0 | 0
659 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.25] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00485/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 5.42 | 0 | 0
660 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work , cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00760/2024-2025 | BP-2024-25-451 | 06/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 48.96 | 0 | 0
661 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-I) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1885] [TSM/018210] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000160/2023-2024 | 843/SWD-I | 05/06/2023 | 887 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 276.76 | 197.24 | 88
662 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMNAGAR(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000407/2021-2022 | 1945/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 2.69 | 0
663 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for FHTC, restoration of road after laying of pipeline, development of land and other allied works for "Ground Water Based RAMNAGAR (Zone-I) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15755) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000523/2024-2025 | 4016/SWD-I | 13/09/2024 | 60 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 95.5 | 0 | 0
664 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-I) PWSS to accommodate FHTC in BARUIPUR block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018210] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000631/2022-2023 | 3258/SWD-I | 02/03/2023 | 30 | MUNNA AGROTECH ENTERPRISE | 31.76 | 15.6 | 100
665 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000108/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 19.94 | 0 | 0
666 | South 24 Pgs W/S Division I |  | Lakshmikantapur Dhola Road from 1.00KM to 2.00km Restoration of hard shoulder due to laying of pipelinesby PHE Department under Lakshmikantapur Highway Sub Division in the district of South 24 Parganas. (SM/18715) |  |  | BILL/00634/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 4.47 | 0 | 0
667 | South 24 Pgs W/S Division I |  | Construction of Boundary wall for proposed 500 Cum OHR Site of Zone-V within Mandirbazar block, Mouza-PurbaShrinagar (JL No-98), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 135 mtr.) |  |  | ORD/000021/2022-2023 | 876/SWD-I | 14/07/2022 | 60 | MS P B CONSTRUCTION | 25.37 | 23.74 | 100
668 | South 24 Pgs W/S Division I |  | Construction of Hume Pipe Culvert 4.80 Mtr.span with 195 Mtr.Long temporary approach road(Plot No-183,189,189) for proposed Zone -V,OHR Site at Purba Srinagar Mouza(J.L.NO-98,Dag No-80,Khatian No-(60,147&256).at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/014532) |  |  | ORD/000381/2023-2024 | 1817/SWD-I | 16/08/2023 | 508 | M/S. KALPANA CONSTRUCTION | 13.51 | 13.37 | 60
669 | South 24 Pgs W/S Division I |  | Diversion of Water for "Construction of Hume Pipe Culvert of 10.00 Mtr span for proposed Zone-V OHR Site at Purba Shreenagar Mouza (J.L.NO-132) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-V at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/18715) |  |  | ORD/000432/2024-2025 | 3874/SWD-I | 03/09/2024 | 30 | M/S. KALPANA CONSTRUCTION | 6.06 | 5.96 | 100
670 | South 24 Pgs W/S Division I |  | Construction of 500 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-V at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.3829) |  |  | ORD/000461/2023-2024 | 2139/SWD-I | 31/08/2023 | 780 | BALAJEE ENTERPRISES | 760.19 | 349.21 | 75
671 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of PURBA SRINAGAR MOUZA in MANDIRBAZAR (ZONE-V) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. |  |  | ORD/000462/2021-2022 | 1987/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 4.42 | 3.58 | 100
672 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 58.22 | 0 | 0
673 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KHARAMBA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018344] |  |  | ORD/000300/2023-2024 | 1665/SWD-I | 03/08/2023 | 745 | ASIT PRAMANIK | 31.76 | 0 | 50
674 | South 24 Pgs W/S Division I |  | Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) and construction of Pump House cum Chlorine Room (2 Nos.) for KHARAMBA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 3153) (TSM/018344) |  |  | ORD/000359/2023-2024 | 1751/SWD-I | 10/08/2023 | 90 | SSN NIRMAN UDYOG | 554.06 | 163.83 | 40
675 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of KHARAMBA PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18545) |  |  | ORD/000679/2024-2025 | 4468/SWD-I | 29/10/2024 | 75 | SSN NIRMAN UDYOG | 170.84 | 0 | 0
676 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 38.49 | 0 | 0
677 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000325/2023-2024 | 251/SWD-I | 10/01/2024 | 0 | Resource Division | 19.42 | 0 | 0
678 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for JAGATIPOTA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018121] |  |  | ORD/000294/2023-2024 | 1659/SWD-I | 03/08/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 15.5 | 50
679 | South 24 Pgs W/S Division I |  | Construction of 300 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for JAGOTIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1766) (TSM/018121) |  |  | ORD/000420/2023-2024 | 1967/SWD-I | 24/08/2023 | 300 | SAMSUL ENTERPRISE | 617.72 | 312.03 | 20
680 | South 24 Pgs W/S Division I |  | Construction of Hume Pipe Culvert 4.80 Mtr.span with 23 Mtr.Long temporary approach road at OHR Site of "JAGATIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18546) |  |  | ORD/000529/2024-2025 | 4075/SWD-I | 19/09/2024 | 30 | SAMSUL ENTERPRISE | 13.07 | 0 | 0
681 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Pathway, Drain, Development of land & others allied works of JAGATIPOTA PWSS within Sonarpur Block "JAGATIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18546) |  |  | ORD/000825/2023-2024 | 1299/SWD-I | 15/03/2024 | 45 | SAMSUL ENTERPRISE | 43.64 | 0 | 0
682 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 17.9 | 0 | 0
683 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000320/2023-2024 | 257/SWD-I | 10/01/2024 | 0 | Resource Division | 10.88 | 0 | 0
684 | South 24 Pgs W/S Division I |  | Construction of platform for FHTC, pipeline protection work, development of land and other allied works for "Ground Water Based SANKHARIPUR PWSS Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/18870) |  |  | ORD/000358/2024-2025 | 3458/SWD-I | 02/08/2024 | 45 | MOUMITA ENTERPRISE | 58.31 | 0 | 0
685 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional Household Tap Connection (FHTC) for Augmentation of SANKHARIPUR of Baruipur Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24-Parganas District [No. of FHTC = 917] |  |  | ORD/000565/2023-2024 | 2611/SWD-I | 17/10/2023 | 623 | MOUMITA ENTERPRISE | 139.7 | 86.92 | 94
686 | South 24 Pgs W/S Division I |  | Sinking of 02 (two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SANKHARIPUR PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/18870] |  |  | ORD/000715/2023-2024 | 3431/SWD-I | 29/12/2023 | 45 | DEV & COMPANY | 31.8 | 28.59 | 100
687 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Sankharipur Piped Water Supply Scheme to accommodate FHTC in Baruipuri Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000987/2022-2023 | 1484/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.46 | 2.45 | 100
688 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-IVA at Gardoani mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 6618] | AE BSD |  | ORD/000277/2023-2024 | 1559/SWD-I | 26/07/2023 | 120 | RELIABLE SANITARY AND PLUMBING CO. | 446.56 | 0 | 0
689 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-IVB at Gardoani mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC= 6319] | AE BSD |  | ORD/000371/2022-2023 | 2315/SWD-I | 19/12/2022 | 840 | SAMIRON GHOSH | 426.47 | 87.58 | 40
690 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Supply of different CIDF specials for laying of DI pipe (250mm dia, 400mm dia & 450mm dia) at zone-IV B (Gardoani) of Joynagar-II Block of Baruipur Sub-Division, for "Mega Surface Based water supply scheme for Falta-Mathurapur, District South 24-Pgns, W/S Division-I, PHE. Dte | AE BSD |  | ORD/000997/2022-2023 | 1078/SWD-I | 16/08/2022 | 15 | S.K. ENTERPRISE | 3.65 | 1.47 | 100
691 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000081/2022-2023 | 2997/SWD-I | 20/02/2023 | 0 | Resource Division | 79.69 | 0 | 0
692 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at NABAGRAM of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 2040] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000024/2023-2024 | 96/SWD-I | 10/04/2023 | 90 | TANMOY ROY CHOWDHURY | 459.09 | 276.84 | 80
693 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of NABAGRAM Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000367/2021-2022 | 1944/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 2.76 | 100
694 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for NABAGRAM PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000564/2022-2023 | 3058/SWD-I | 21/02/2023 | 30 | MD NOOR ALAM | 47.63 | 32.68 | 100
695 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based NABAGRAM Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/13311) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000905/2023-2024 | 1204/SWD-I | 11/03/2024 | 45 | R. UNIQUE CONSTRUCTION | 40.41 | 0 | 0
696 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000188/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 45.61 | 0 | 0
697 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of backwash pipe line from newly installed IEP to nearby canal at Birlapur under Birlapur (CT) PWSS to accommodate FHTC in Budge Budge-I block under South 24 Pgns. W/S Division-I, for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000018/2025-2026 | 970/SWD-I | 09/04/2025 | 45 | MONDAL PRECISION PVT. LTD. | 20.63 | 0 | 0
698 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Engagement of expertise to improve the performance and functionality at the end of consumers (FHTC) of the water supply system using Hydraulic Isolation Structures near Birlapur (CT) under South 24-Parganas Water Supply Division-I, PHE Dte. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000070/2025-2026 | 1509/SWD-I | 03/06/2025 | 45 | AJIVAM WATER PRIVATE LIMITED | 10 | 0 | 100
699 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Piped Water Supply Scheme at Mayapur Village (JL. - 46) (Sansad III & IV) of Budge Budge - I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. (Route surveying of 40KM) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000194/2022-2023 | 714/SWD-I | 24/06/2022 | 180 | CHAYANIKA ENGINEERING CONSULTANCY | 2.9 | 2.53 | 100
700 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia & 300 mtr. deep tube-well by rotary method for water supply at Birlapur (CT) Piped Water Supply Scheme of Budge Budge-I Block under South 24-Parganas W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000299/2022-2023 | 1885/SWD-I | 16/11/2022 | 30 | PADMA ENGINEERING CO. | 40.15 | 34.47 | 100
701 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 5.04 | 98
702 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 2 (Two) nos. boundary walls with allied works for Birlapur CT pipe water supply scheme to accommodate FHTC in Budge Budge-I block under South 24- Parganas. W/S Division-I, PHE Dte. South 24-Pargans District for Augmentation of surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns District. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000366/2024-2025 | 3506/SWD-I | 07/08/2024 | 45 | MS KRISHNA MONDAL | 36.9 | 0 | 0
703 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Restoration of road and providing pipe supporting structures near Mayapur GP Kabarsthan for BIRLAPUR (CT) piped water supply scheme to accommodate FHTC in Budge Budge -I block under South 24 Parganas W/S Division-I, South 24-Pgns District for Augmentation of Surface Based Water Supply Scheme in the affected areas of South 24-Pgns (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000382/2024-2025 | 3573/SWD-I | 12/08/2024 | 45 | MS POUSALI ENTERPRISE | 3.09 | 3.09 | 100
704 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection of Tubewell Sites in Mayapur GP "Ground water based BIRLAPUR (CT) piped water supply scheme to accommodate FHTC in BUDGE BUDGE I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas". (TSM/013487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000400/2023-2024 | 1909/SWD-I | 21/08/2023 | 45 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 7.69 | 7.66 | 100
705 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 02nos. Pump House (Size 4.80mX3.66m) at tubewell site zone- I & II of Birlapur (CT) PWSS of Budge Budge-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000430/2022-2023 | 2579/SWD-I | 10/01/2023 | 60 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 13.69 | 13.02 | 100
706 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of distribution pipeline and providing FHTC for BIRLAPUR (CT) PWSS including restoration of roads under South 24-Pgns W/S Division-I, P.H.E. Dte., District South 24 Parganas. [No. of FHTC = 2032] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000510/2022-2023 | 2940/SWD-I | 16/02/2023 | 60 | M/S. S.S. ENTERPRISE | 208.47 | 180.05 | 60
707 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 02 (Two) nos. 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Birlapur (CT) PWSS of Budge Budge-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas ofSouth 24 Paraganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12214] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000697/2022-2023 | 3500/SWD-I | 16/03/2023 | 15 | PADMA ENGINEERING CO. | 6.1 | 6.1 | 0
708 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of additional pipeline for Birlapur (CT) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-I Block under South 24-Pgns. Water Supply Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in Arsenic Affected Areas of South 24-Pgns. Dist. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000776/2023-2024 | 804/SWD-I | 16/02/2024 | 45 | STAR ENTERPRISE | 43.78 | 43.76 | 60
709 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Blower room (Size 3.60mX3.00m) Birlapur Piped Water Supply Scheme for Zone-I & Zone-II of Budge Budge-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000834/2023-2024 | 1096/SWD-I | 05/03/2024 | 45 | SANJAY MIDDEY | 7.06 | 3.39 | 100
710 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of RIDF Road at Chakatala near Birlapur with allied works under Ground Water Based BIRLAPUR(CT) Piped Water Supply Scheme of South 24 Pargana W/S Supply Division- I, P.H.E Dte. (TSM/013487) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000837/2023-2024 | 1151/SWD-I | 07/03/2024 | 45 | PROJECT AND MAINTENANCE | 16.89 | 16.87 | 100
711 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supply, installation, trail run and commissioning of Pressure Transmitter and display arrangement in connection to Piped water supply scheme for Birlapur CT under South 24 pgs W/S Division-I, PHE Dte. Dist. South 24 pgs. [SM/12214] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001121/2024-2025 | 115/SWD-I | 10/01/2025 | 7 | B.S. RUBBER INDUSTRIES | 0.53 | 0 | 0
712 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Fitting of Air Valves and Pressure Gauges to different points of Rising Main towards Mayapur Gp near Birlapur (CT) under Birlapur (CT) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-I Block under South 24-Pgns W/S Divn.-I, South 24pgns Dist. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas. (SM/12214) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001130/2024-2025 | 193/SWD-I | 17/01/2025 | 30 | SRIJON ENTERPRISE | 21.72 | 0 | 0
713 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12209) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000141/2025-2026 | 2247/SWD-I | 02/09/2025 | 45 | RIMON ENTERPRISE | 10.04 | 0 | 0
714 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BADEHUGLI Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000265/2022-2023 | 1776/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
715 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall , Pathway, Drain & others allied works at HW Site of " BADEHUGLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/12209) [2nd call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000405/2024-2025 | 3683/SWD-I | 22/08/2024 | 252 | MAJUMDER ENTERPRISE | 40.94 | 0 | 20
716 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BADEHUGLI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 995] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000514/2022-2023 | 2944/SWD-I | 16/02/2023 | 990 | MAJUMDER ENTERPRISE | 299.69 | 86.34 | 50
717 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube-well to achieve 66 mtr. housing pipe by Rotary Method for BADEHUGLI PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12209] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000736/2022-2023 | 3574/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
718 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at head work site for BADEHUGLI PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12209] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000768/2023-2024 | 777/SWD-I | 13/02/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 16.32 | 100
719 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000006/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 13.62 | 0 | 0
720 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000227/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.13 | 0 | 0
721 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road damaged due to laying of pipeline from Post Office More to Kalitala More, Kalitala More to Dharmatala, Rajballabhpur Bazar to Zone-II OHR site,Nilkuthi More to Dharmatala More and Nilkuthi More to Beramara More under the Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-II at RAJBALLABHPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 Pgns. under South 24 Pgns Water Supply Division-I, PHE Dte. (SM/18707) | Assistant Engineer | JE1 | ORD/000088/2025-2026 | 1763/SWD-I | 02/07/2025 | 135 | SANJAY ENTERPRISE | 32.4 | 0 | 60
722 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of additional pipeline for distribution system,Protection of distribution pipeline and Construction of FHTC Platform for Zone-II (Rajballabhpur) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. | Assistant Engineer | JE1 | ORD/000280/2024-2025 | 3004/SWD-I | 28/06/2024 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 206.32 | 0 | 2
723 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site in Zone-II at Rajballabhpur of Mograhat-I block for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-II AT RAJBALLABHPUR OF MOGRAHAT-I BLOCK within "Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, District- South 24-Parganas" under South 24 Parganas W/S Division-I, PHE Dte. (Total Length-114 mtr excluding Gate) (TSM/014908) | Assistant Engineer | JE1 | ORD/000356/2023-2024 | 1742/SWD-I | 10/08/2023 | 594 | SANJAY ENTERPRISE | 19.15 | 5.28 | 60
724 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1000 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in Zone-II at Rajballabhpur of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in Zone-II at Rajballabhpur of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 6219 Nos.) | Assistant Engineer | JE1 | ORD/000418/2023-2024 | 1964/SWD-I | 24/08/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1097.7 | 172.67 | 30
725 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of chlorination room, approach road, land development and other allied works under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% HouseHold in Zone-II (Rajballabhpur) under Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. (SM/18707) | Assistant Engineer | JE1 | ORD/000431/2024-2025 | 3873/SWD-I | 03/09/2024 | 45 | ROYAL CONSTRUCTION | 29.29 | 0 | 20
726 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road after laying of pipe line for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in Zone-II at Rajballabhpur under Magrahat-I Block within 'Mega Surface water based water supply scheme for Falta-Mathurapur' under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas. (SM/18707) | Assistant Engineer | JE1 | ORD/000434/2024-2025 | 3876/SWD-I | 03/09/2024 | 45 | SANJAY ENTERPRISE | 26.45 | 19.39 | 85
727 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system for Zone-II, Rajballabhpur (OHR Capacity- 1000 cum.) under Mograhat-I Block" under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. District. | Assistant Engineer | JE1 | ORD/000897/2022-2023 | 19/SWD-I | 06/04/2022 | 30 | LEMNISCATE | 2.4 | 2.4 | 100
728 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000062/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 149.81 | 0 | 0
729 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at INDRAPALLA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012606] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000117/2022-2023 | 1285/SWD-I | 14/09/2022 | 60 | S.C. ENTERPRISE | 10.92 | 7.99 | 100
730 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of INDRAPALLA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000167/2021-2022 | 1923/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.67 | 100
731 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for INDRAPALLA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/012606] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000186/2022-2023 | 1480/SWD-I | 27/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 34.66 | 100
732 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at INDRAPALLA of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1009) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000308/2022-2023 | 1912\SWD-I | 18/11/2022 | 905 | MANAS CHATTERJEE | 219.29 | 97.61 | 90
733 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Platform for providing FHTC, Protection works for pipeline and other allied works for Proposed Ground Water based INDRAPALLA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12264) (2nd call) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000732/2024-2025 | 4619/SWD-I | 13/11/2024 | 90 | MUNNA AGROTECH ENTERPRISE | 83.18 | 11.67 | 30
734 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Indrapalla PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/012606] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000794/2022-2023 | 3670/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 4.41 | 100
735 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000105/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 41.78 | 0 | 0
736 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.18] |  |  | BILL/00477/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 10.46 | 0 | 0
737 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18571)" |  |  | ORD/000232/2024-2025 | 2652/SWD-I | 07/06/2024 | 45 | SUJOY SADHUKHAN | 10.55 | 0 | 10
738 | South 24 Pgs W/S Division I |  | Construction of 500 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2838) (TSM/019595) |  |  | ORD/000447/2023-2024 | 2102/SWD-I | 30/08/2023 | 945 | O.K. CONSTRUCTION | 627.54 | 361.89 | 20
739 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Bidyadharpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000990/2022-2023 | 1502/SWD-I | 28/09/2022 | 30 | GEO SOLUTION | 2.9 | 2.89 | 100
740 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of BIDYADHARPUR PWSS within Sonarpur Block BIDYADHARPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18571) |  |  | ORD/001067/2024-2025 | 5219/SWD-I | 20/12/2024 | 132 | MAA GITA ENTERPRISE | 34.7 | 0 | 50
741 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 23.28 | 0 | 0
742 | South 24 Pgs W/S Division I |  | Supplying, fabrication & laying of 610 mm dia (OD) MS Pipe conduit 60 mtr. in length, to be prepared from 12.5 mm thick MS Plate, by pipe jacking technique, including supplying and laying of 219 mm dia (OD) MS water main within the conduit, 90 mtr. in length to be prepared from 10 mm thick MS Plate, across and underneath the Railway Track at Bidyadharpur Railway Station in between Station Sonarpur Jn. (SPR) - Bidyadharpur (BDYP), OHE Mast No. 18/25C-18/26C and 18/27C-18/28C as per permission of Railway Authority for "Bidyadharpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. District under Jal Jeevan Mission." (SM/18571) |  |  | ORD/001167/2024-2025 | 451/SWD-I | 11/02/2025 | 45 | SRIJON ENTERPRISE | 71.31 | 0 | 0
743 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Functional household Tap Connection by retrofitting of Atmarampur W/S Scheme for Atmarampur, Chingripota and Santoshpur mouza under Budge Budge I Block with allied works under " Surface water Based Mega water Supply Scheme for Falta Mathurapur" | AE SWSD-I |  | ORD/000111/2020-2021 | 1358/SWD-I | 08/12/2020 | 120 | M/S. S.S. ENTERPRISE | 97.1 | 167.6 | 0
744 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Atmarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6114) Part -I | AE SWSD-I |  | ORD/000471/2022-2023 | 2783/SWD-I | 31/01/2023 | 45 | R.D CONSTRUCTION | 2.86 | 2.78 | 100
745 | South 24 Pgs W/S Division I |  | Restoration of carriageway and Hard Sholder damaged due to laying of pipes by PHE Dte. Location - Ch.6.584 km to 14.50km along Burul Bowali Road under Diamond Harbour Highway Division in the district of South 24 Parganas. |  |  | BILL/01492/2023-2024 | BP-2023-24-499 | 24/11/2023 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 14.07 | 0 | 0
746 | South 24 Pgs W/S Division I |  | Surveying, Design, Construction, Supply, Laying, Erection & Commissioning of 1(one) Clear Water Reservoir and 1(one) Ground Level Reservoir, Pumping main (M.S., D.I. etc.) for conveyance of Treated water to 29 (Twenty Nine) nos. OHR sites(old and New) including construction of Pump Houses, Sub-Station Buildings, Chlorine and Chlorine Tonner Rooms, 16 (sixteen) nos new OHRs of different capacities, Boundary wall, land development, pathway, arboriculture, Distribution System(M.S. D.I./ uPVC/HDPE Pipes etc.) in all the 29(twenty Nine) distribution zones including providing functional household tap connections(FHTC) to all the rural households and Public Institutions(e.g. Schools, AWC, Health Centers etc.), pipe carrying bridges & pipe carrying supports and other related Structure, Restoration of Roads to its original condition as required and related Electro-Mechanical, Instrumentation and Supervisory Control and Data Acquisition System (SCADA) as per scope of works including 03(three) months trial run and 72 Hrs performance guarantee test followed by 60(Sixty) months operation and maintenance (O&M) for Augmentation of surface water based water supply Scheme for arsenic affected areas of BUDGE BUDGE-II, BISHNUPUR-II and part of BUDGE BUDGE-I (MAYAPUR GP only) Blocks in the district of South 24 Parganas. |  |  | ORD/000002/2022-2023 | 799 /SWD-I | 06/07/2022 | 731 | WPIL LTD. | 43087 | 35053.08 | 100
747 | South 24 Pgs W/S Division I |  | Providing FHTC in connection to "Augmentation of surface water based water supply scheme for Budge Budge-II, Bishnupur-II and Budge Budge-I Blocks (Mayapur GP only)" under South 24-Pgns. W/S Division-I, PHE Dte., District - South 24-Parganas. [No. of FHTC = 90081] |  |  | ORD/000231/2023-2024 | 1375/SWD-I | 12/07/2023 | 901 | WPIL LTD. | 3016.78 | 1321.06 | 10
748 | South 24 Pgs W/S Division I |  | Construction of temporary Boundary Wall at Jagat Ballavpur JL 45 Dag No: 834, Kh -1 , Dist. South 24 Paraganas in connection with Augmentation of Budge Budge I/II and Bisnupur II Water Supply Scheme under South 24-Parganas Water Supply Division-I, PHE Dte. |  |  | ORD/000443/2021-2022 | 2608/SWD-I | 15/03/2022 | 60 | MS POUSALI ENTERPRISE | 1.86 | 1.79 | 100
749 | South 24 Pgs W/S Division I |  | Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2022 to 31/05/2023] |  |  | ORD/000612/2022-2023 | 519/SWD-I | 30/05/2022 | 365 | AHMED REZA | 1.73 | 0.4 | 100
750 | South 24 Pgs W/S Division I |  | Continuation Order for the work of Engagement of Office attendant 01(one) no. for different JJM works at Boosting Station-I (Begampur) under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, P.H. Engineering Dte. Period from 16/02/2023 to 15/06/2023 (Four months). |  |  | ORD/000765/2022-2023 | 2938/SWD-I | 15/02/2023 | 120 | PEECON | 0.83 | 0 | 0
751 | South 24 Pgs W/S Division I |  | Continuation Order for the work of Engagement of Office attendant 01(one) no. for different JJM works at Boosting Station-II (Krishnamohan) under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, P.H. Engineering Dte. Period from 16/02/2023 to 15/06/2023 (Four months). |  |  | ORD/000766/2022-2023 | 2939/SWD-I | 15/02/2023 | 120 | PEECON | 0.83 | 0 | 0
752 | South 24 Pgs W/S Division I |  | Engagement of 01 no. Computer Operator / Data Entry Operator [Category - A] for the office works of Executive Engineer (Deputed from PWD) under Superintending Engineer, South 24-Parganas W/S Circle, PHE Dte. [w.e.f. 01.04.2023 to 31.03.2024] |  |  | ORD/000815/2022-2023 | 3720/SWD-I | 31/03/2023 | 365 | M/S. SYSCON | 2.52 | 2.35 | 90
753 | South 24 Pgs W/S Division I |  | Engagement of 01 no. Computer Operator / Data Entry Operator [Category - C] for the office works of Superintending Engineer, PMU, WBDWSIP (ADB), PHE Dte. under Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01.04.2023 to 31.03.2024] |  |  | ORD/000816/2022-2023 | 3721/SWD-I | 31/03/2023 | 365 | M/S. SYSCON | 2.05 | 1.91 | 95
754 | South 24 Pgs W/S Division I |  | Balance work for Laying Distribution System, Rising Main pipe line, gap filling and construction of Approach Road, shifting of DI pipe, road restoration and other allied works in connection with Augmentation of Surface Water Based Water Supply Scheme of Budge Budge II, Bishnupur II and Budge Budge I (Mayapur Part) under South 24 Pgns W/S Division-I, PHE Dte. (SM/08869) |  |  | ORD/000863/2024-2025 | 4909/SWD-I | 02/12/2024 | 151 | WPIL LTD. | 1746.84 | 79.46 | 60
755 | South 24 Pgs W/S Division I |  | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] |  |  | ORD/000875/2022-2023 | 3728/SWD-I | 31/03/2023 | 183 | SUBRAT KUMAR SETHY | 0.87 | 0.72 | 50
756 | South 24 Pgs W/S Division I |  | Acceptance-cum-Work Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2022 to 31/05/2023] |  |  | ORD/000894/2022-2023 | 515/SWD-I | 30/05/2022 | 365 | AVIK HALDER | 1.77 | 0.4 | 100
757 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1522/SWD-I | 29/09/2022 | 0 | Resource Division | 258.14 | 0 | 0
758 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 2119/SWD-I | 06/12/2022 | 0 | Resource Division | 1967.83 | 0 | 0
759 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 2192/SWD-I | 13/12/2022 | 0 | Resource Division | 530.06 | 0 | 0
760 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 398/SWD-I | 28/04/2023 | 0 | Resource Division | 2346 | 0 | 0
761 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000307/2023-2024 | 2727/SWD-I | 06/11/2023 | 0 | Resource Division | 129.85 | 0 | 0
762 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000308/2023-2024 | 2727/SWD-I | 06/11/2023 | 0 | Resource Division | 106.93 | 0 | 0
763 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Wayleave Facility Charge (Station From-To Lakshmikantapur (LKPR) - Udairampur Halt (URP)) (Revenue Village Lakshmikantapur) | AE HQ-I |  | BILL/00102/2024-2025 | BP-2024-25-85 | 22/05/2024 | 0 | EASTERN RAILWAY SEALDAH DIVISION | 5.38 | 0 | 0
764 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Permanent Restoration work of probable Black top damage which would caused due to laying of PHED pipe (Falta-Mathurapur Mega surface water supply scheme of PHED) on Purbabishnupur-Lakshmikantapur-Kulpi Road at Dayarampur (Ch. 10.33 kmp.), Raghunathpur (Ch. 11.55 kmp.) Madhusudanpur (Ch. 12.65 kmp.), Tantirhat (Ch.13.15 kmp.) and Mollarchak (Ch. 13.80 kmp.), under Diamond Harbour Division,P.W.Dte. in the district of South 24 Pgs. (SM/12205) | AE HQ-I |  | BILL/00683/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 7.66 | 0 | 0
765 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed OHR Site of Zone-VI within Mandirbazar block, Mouza-Shibpur (JL No-59), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas under South 24 Pgns. Water Supply Division-I, PHE Dte. (Length- 110 mtr.) | AE HQ-I |  | ORD/000072/2022-2023 | 1153/SWD-I | 26/08/2022 | 60 | ARYA ENGINEERS | 15.32 | 13.04 | 0
766 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 400 cum capacity Over Head Reservoir as per Departmental Drawing and specifications including RCC bored pile and pile cap within Zone-VI at Shibpur Mouza of Mandirbazar Block, for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24 Pgs District, under South 24 Pgns Water Supply Divn.-I, PHE Dte. (TSM/014544) | AE HQ-I |  | ORD/000308/2023-2024 | 1697/SWD-I | 07/08/2023 | 633 | M/S SUBHODEEP ENTERPRISE | 133.72 | 110.29 | 20
767 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of SHIBPUR MOUZA in MANDIRBAZAR (ZONE-VI) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000392/2021-2022 | 2603/SWD-I | 15/03/2022 | 30 | MS R. DUTTA AND CO | 4.62 | 3.13 | 100
768 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Approach Road with Land Development and construction of Boundary Wall gate to facilitate the works within Head Work Site under the Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-VI at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme Water Based Water Supply Scheme for Falta-Mathurapur, Dist- South 24-Pgns." under South 24-Pgns. W/S Divn.-I, PHE Dte. (TSM/014544) | AE HQ-I |  | ORD/000619/2023-2024 | 2803/SWD-I | 09/11/2023 | 45 | M/S SUBHODEEP ENTERPRISE | 5.82 | 5.44 | 100
769 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-VI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (TSM/014544) [5th SLSSC (2022-23)] | AE HQ-I |  | ORD/000771/2022-2023 | 3645/SWD-I | 28/03/2023 | 761 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 328.19 | 207.31 | 60
770 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000048/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 2.74 | 0 | 0
771 | South 24 Pgs W/S Division I |  | Additional Laying of distribution Network System for different dia HDPE pipe & Road Restoration for DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18499) |  |  | ORD/000020/2025-2026 | 972/SWD-I | 09/04/2025 | 45 | THE TEESTA CONSTRUCTION | 71.48 | 0 | 0
772 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DEBIPUR PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018469] |  |  | ORD/000303/2023-2024 | 1671/SWD-I | 04/08/2023 | 580 | M/S BANERJEE ENGINEERING SYSTEM | 31.79 | 3.6 | 50
773 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) |  |  | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 180 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 16.06 | 60
774 | South 24 Pgs W/S Division I |  | Construction of 400 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for DEBIPUR Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2830) (TSM/018469) |  |  | ORD/000534/2023-2024 | 2360/SWD-I | 26/09/2023 | 300 | THE TEESTA CONSTRUCTION | 780.87 | 46.99 | 25
775 | South 24 Pgs W/S Division I |  | Development of land, construction of approach road and other allied works at HW site & 2nd Tubewell site of "DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Pgns. W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under Jal Jeevan Mission". (SM/18499) |  |  | ORD/000538/2024-2025 | 4095/SWD-I | 20/09/2024 | 60 | M/S SONALI CONSTRUCTION | 39.61 | 0 | 0
776 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of DEBIPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/18499] |  |  | ORD/000755/2024-2025 | 4676/SWD-I | 18/11/2024 | 60 | SUJIT KUMAR SHARMA | 31.4 | 0 | 0
777 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1727/SWD-I | 09/08/2023 | 0 | Resource Division | 22.96 | 0 | 0
778 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000323/2023-2024 | 253/SWD-I | 10/01/2024 | 0 | Resource Division | 17.43 | 0 | 0
779 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 186 to 190 and 192 to 196 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000109/2020-2021 | 1413/SWD-I | 14/12/2020 | 120 | FUTURE | 92.9 | 165.27 | 100
780 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system by extension of pipeline for Buita W/S Scheme for Booth No- 186 to 190, Booth no- 192 and adjoining areas under Budge Budge-I Block with allied works under South 24-Pgns, W/S Division-I, P.H.E. Dte., DistSouth 24-Pgns. | AE SWSD-I |  | ORD/000585/2021-2022 | 1470/SWD-I | 15/12/2021 | 45 | FUTURE | 2.53 | 2.53 | 100
781 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Land Development of Ganney Gangadharpur OHR (1250 cum capacity) Head work Site under Asuti I / Asuti II W/S Scheme under South 24 Pgns W/S Div I , PHED. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000041/2022-2023 | 441/SWD-I | 24/05/2022 | 15 | MS POUSALI ENTERPRISE | 4.61 | 4.55 | 0
782 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Distribution System, Road Restoration including providing FHTC for Asuti-I & II GP and adjoining areas under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, P.H.E. Dte., District-South 24 Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000065/2022-2023 | 1110/SWD-I | 23/08/2022 | 1071 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1559.44 | 947.21 | 80
783 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Modification of foundation of awarded 1500 Cum. OHR at Chatta as per sustainability and best engineering practice including site development under ¿Water Supply Arrangement for Asuti I/II and Chatta GP¿ under South 24 Pgns. W/S Divn.-I, PHED. [TSM/005082] [2nd Call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000074/2022-2023 | 1160/SWD-I | 29/08/2022 | 906 | M/S. S.S. ENTERPRISE | 34.1 | 32.32 | 90
784 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of 63mm & 75mm dia pipeline for PWSS of Asuti-I & Asuti-II GP in Thakurpukur-Maheshtala Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/11160) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000115/2023-2024 | 527/SWD-I | 11/05/2023 | 814 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 122.8 | 66.71 | 80
785 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supplying, Fabrication, Erection, Commissioning, Trail Run (3 Months) and 1 (one) year Operation & Maintenance of 2 Nos. Pressure Type Iron Elimination Plant (310 Cum capacity) for Zone-I of Chata GP PWSS and (300 Cum capacity) for Zone-II of Asuti-I & Asuti-II GP PWSS in Thakurpukur-Maheshtala Block including other allied works under South 24 Pgs W/S Divn-I, P.H.E. Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000121/2023-2024 | 536/SWD-I | 11/05/2023 | 720 | WATREAT ENGINEERS | 184.41 | 0 | 50
786 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Scorpio / Bolero / Swift Dezire / Indica Car) with driver for official use of the Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/06/2023 to 30/11/2023] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000290/2023-2024 | 702/SWD-I | 26/05/2023 | 183 | AVIK HALDER | 0.89 | 2.32 | 30
787 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000002/2022-2023 | 560 | 27/07/2022 | 0 | Resource Division | 417.66 | 0 | 0
788 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000018/2022-2023 | 1660 | 21/10/2022 | 0 | Resource Division | 66.08 | 0 | 0
789 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000285/2023-2024 | 2008/SWD-I | 28/08/2023 | 0 | Resource Division | 15.6 | 0 | 0
790 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for DEULIPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000032/2022-2023 | 916/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.19 | 12.86 | 100
791 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of DEULI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11498) (2nd Call) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000094/2023-2024 | 451/SWD-I | 04/05/2023 | 60 | M/S ASHA ENGINEERING | 6.05 | 5.79 | 100
792 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 7.47 | 60
793 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Deuli PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11498) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000265/2024-2025 | 2680/SWD-I | 07/06/2024 | 45 | SWATHI ENTERPRISE | 76 | 0 | 15
794 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "DEULI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000404/2022-2023 | 459/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 2.55 | 100
795 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed DEULI PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 822] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000427/2022-2023 | 2565/SWD-I | 10/01/2023 | 60 | TANMOY ROY CHOWDHURY | 123.95 | 102.44 | 80
796 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for DEULI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011201] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000596/2022-2023 | 3116/SWD-I | 24/02/2023 | 754 | CIVIL CONSULTANT | 15.88 | 0 | 100
797 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed DEULI Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011201] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000810/2022-2023 | 3702/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.9 | 0.86 | 100
798 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000103/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.53 | 0 | 0
799 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHITRASALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000103/2022-2023 | 1229/SWD-I | 07/09/2022 | 30 | DIPALI CONSTRUCTION | 20.07 | 0 | 100
800 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Chitrasali ( Chitrasali, J.L-112) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [No. of FHTC - 520] [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000113/2022-2023 | 1243/SWD-I | 08/09/2022 | 1080 | KAMALA ENTERPRISE | 65.91 | 49.64 | 80
801 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHITRASALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000228/2021-2022 | 1957/SWD-I | 27/01/2022 | 30 | CHAYANIKA ENGINEERING CONSULTANCY | 2.62 | 2.46 | 100
802 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at CHITRASALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000292/2022-2023 | 1786/SWD-I | 07/11/2022 | 840 | SANJAY ENTERPRISE | 5.8 | 0 | 100
803 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chitrasali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 3675/SWD-I | 29/03/2023 | 15 | DIPALI CONSTRUCTION | 2.2 | 0 | 0
804 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHITRASALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000791/2023-2024 | 1131/SWD-I | 06/03/2024 | 345 | BORING HOUSE | 19.97 | 0 | 100
805 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chitrasali PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009669] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000792/2023-2024 | 1132/SWD-I | 06/03/2024 | 345 | BORING HOUSE | 2.19 | 0 | 100
806 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000276/2023-2024 | 2424/SWD-I | 30/09/2023 | 0 | Resource Division | 6.08 | 0 | 0
807 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000332/2023-2024 | 267/SWD-I | 10/01/2024 | 0 | Resource Division | 3.2 | 0 | 0
808 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BARAGACHHIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1892] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000112/2023-2024 | 524/SWD-I | 11/05/2023 | 967 | M/S R.K. ENTERPRISE | 500.51 | 97.81 | 50
809 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000182/2023-2024 | 774/SWD-I | 31/05/2023 | 183 | INDRADEV JHA | 0.87 | 2.27 | 30
810 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte."(w.e.f. 01/06/2024 to 30/11/2024) [Vehicle No- WB-04F-8738] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000217/2024-2025 | 2451/SWD-I | 24/05/2024 | 183 | INDRADEV JHA | 0.87 | 2.19 | 50
811 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BARAGACHHIA Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000264/2022-2023 | 1772/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 13.59 | 0
812 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway,Drain, Development of Land & others allied works at HW Site of "BARAGACHHIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12211) [2nd call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000408/2024-2025 | 3705/SWD-I | 23/08/2024 | 45 | M/S R.K. ENTERPRISE (BARASAT) | 48.08 | 0 | 0
813 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pump house, Chlorine room, Office room, Construction of Pathway at existing OHR site of Baragachhia Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pargnas District under Jal Jeevan Mission. (SM/12211) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000701/2024-2025 | 4503/SWD-I | 30/10/2024 | 45 | ISHIYA ENTERPRISE | 20.73 | 0 | 0
814 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte."(w.e.f. 01/12/2023 to 31/05/2024) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000705/2023-2024 | 3001/SWD-I | 29/11/2023 | 183 | INDRADEV JHA | 0.87 | 2.39 | 10
815 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BARAGACHHIA PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12211] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000764/2022-2023 | 3603/SWD-I | 24/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 1.57 | 0
816 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000007/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 19.21 | 0 | 0
817 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000250/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 11.65 | 0 | 0
818 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at HARIMUL Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC= 1433) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 110/SWD-I | 11/04/2023 | 300 | CE INFRASTRUCTURE | 433.03 | 168.76 | 70
819 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for HARIMUL PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011095] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2022-2023 | 1584/SWD-I | 17/10/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 0 | 100
820 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of HARIMUL Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000218/2021-2022 | 1935/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.68 | 100
821 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at Harimul at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000352/2022-2023 | 2200/SWD-I | 13/12/2022 | 900 | BANGA NIRMAN | 11.51 | 0 | 50
822 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls including development of land and other allied works for Ground water based HARIMUL piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12635) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000409/2024-2025 | 3706/SWD-I | 23/08/2024 | 45 | C.E. INFRASTRUCTURE | 43.76 | 0 | 0
823 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for HARIMUL PWSS of BARUIPUR Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/011095] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000449/2023-2024 | 2104/SWD-I | 30/08/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 0 | 0
824 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for HARIMUL Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12635] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001156/2024-2025 | 374/SWD-I | 04/02/2025 | 30 | G.S. CONSTRUCTION | 15.9 | 0 | 0
825 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000301/2023-2024 | 2439/SWD-I | 30/09/2023 | 0 | Resource Division | 62.89 | 0 | 0
826 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VI at Radha Ballavpur mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5849] | AE BSD |  | ORD/000633/2022-2023 | 3266/SWD-I | 02/03/2023 | 7320 | SUPRITI ENTERPRISE | 444.62 | 211.49 | 37
827 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000083/2022-2023 | 2999/SWD-I | 20/02/2023 | 0 | Resource Division | 36.03 | 0 | 0
828 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing FHTC for Zone I (Part) and adjoining areas under Thakurpukur Maheshtala Block, PHE Dte. under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I |  | ORD/000007/2022-2023 | 821/SWD-I | 08/07/2022 | 1090 | M/S. S.S. ENTERPRISE | 316.71 | 75.97 | 80
829 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supplying, Fabrication, Erection, Commissioning, Trail Run (3 Months) and 1 (one) year Operation & Maintenance of 2 Nos. Pressure Type Iron Elimination Plant (310 Cum capacity) for Zone-I of Chata GP PWSS and (300 Cum capacity) for Zone-II of Asuti-I & Asuti-II GP PWSS in Thakurpukur-Maheshtala Block including other allied works under South 24 Pgs W/S Divn-I, P.H.E. Dte. | AE SWSD-I |  | ORD/000121/2023-2024 | 536/SWD-I | 11/05/2023 | 720 | WATREAT ENGINEERS | 184.41 | 0 | 50
830 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Over Head Reservoir of capacity 1250 cum at ZONE - II of Asuti-I/II & Chata water supply scheme under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I |  | ORD/000152/2022-2023 | 1392/SWD-I | 21/09/2022 | 983 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 309.69 | 263.49 | 90
831 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying Rising Main from proposed Tubewell to existing OHR for Zone II with interconnection and bypass arrangement of Asuti W/S Scheme within Thakurpukur-Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000260/2022-2023 | 1701/SWD-I | 01/11/2022 | 60 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 58.23 | 37.69 | 65
832 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Investigation of Soil for the proposed Over Head Reservoir (Capacity - 1200 m3) site inside Zone no.- II (Mouza-Goney Gangadharpur, JL No.- 25, Plot No.- 694) of Asuti-I/Asuti-II and Chata GP W/S Scheme within Thakurpukur Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I |  | ORD/000461/2021-2022 | 1222/SWD-I | 12/11/2021 | 30 | G TECH INDIA | 0.54 | 0.54 | 100
833 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of 63mm & 75 mm dia balance pipeline for piped water supply scheme including FHTC for Chatta GP in Thakurpukur Maheshtala Block under South 24 Pgns. W/S Division-I, PHE Dte. (TSM/010374) | AE SWSD-I |  | ORD/000661/2022-2023 | 3377/SWD-I | 10/03/2023 | 60 | M/S. S.S. ENTERPRISE | 36.25 | 36.09 | 95
834 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall with allied works for Balance Pump House Sites under Chatta Water Supply Scheme of Thakurpukur Mahestala Block, under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/11488) | AE SWSD-I |  | ORD/000774/2023-2024 | 801/SWD-I | 16/02/2024 | 60 | RIDIP ENTERPRISE | 26.52 | 0 | 0
835 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Land Development of Rameswarpur Pump House 2nd Site with construction of approach road to facilitate the boring of Tubewell under Pipe Water Supply of Chatta W/S Scheme under South 24 Pgns W/S Division-I , PHE Dte. (SM/11488) | AE SWSD-I |  | ORD/000775/2023-2024 | 803/SWD-I | 16/02/2024 | 7 | MS POUSALI ENTERPRISE | 6.86 | 6.84 | 100
836 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I |  | RTOR000023/2022-2023 | 1984/SWD-I | 25/11/2022 | 0 | Resource Division | 45.95 | 0 | 0
837 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Payment of Enhanced GST Rate vide W/O No.1690/SWD-I dt. 01/11/2022 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/02031/2023-2024 | BP-2023-24-755 | 13/03/2024 | 0 | MRA NIRMAN UDYOG | 27.18 | 0 | 0
838 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR SATBERIA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 437, KHATIAN NO. 3227/1, JL. NO. 110, MOUZA - SATBERIA) & 2ND TUBE WELL SITE (DAG NO. 578, KHATIAN NO. 3744, JL NO. 115, MOUZA - KASHINATHPUR), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 1444/SWD-I | 26/09/2022 | 30 | SIMPLEX DRILLING COMPANY | 28.4 | 26.67 | 100
839 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Satberia Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000228/2022-2023 | 1690/SWD-I | 01/11/2022 | 300 | MRA NIRMAN UDYOG | 613.53 | 507.33 | 80
840 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pathway at 2nd site of Satberia PWSS within Bhangar-I Block in connetion with" SATBERIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/11274). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000558/2023-2024 | 2597/SWD-I | 16/10/2023 | 757 | MAA CONSTRUCTION | 4.82 | 0 | 100
841 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing 905 nos. Functional Household Tap connection (FHTC) For Satberia PWSS Under Block:Bhangar-I, District: South 24 parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission[No. of FHTC (1721-816)=905] (SM/11274) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000625/2023-2024 | 2806/SWD-I | 09/11/2023 | 60 | A S BUILDCON | 33.11 | 33.11 | 100
842 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of SATBERIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11274) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000724/2024-2025 | 4601/SWD-I | 12/11/2024 | 60 | MRA NIRMAN UDYOG | 94.4 | 0 | 0
843 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000021/2022-2023 | 1921/SWD-I | 18/11/2022 | 0 | Resource Division | 5.03 | 0 | 0
844 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000032/2022-2023 | 2691/SWD-I | 20/01/2023 | 0 | Resource Division | 11.72 | 0 | 0
845 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-VI at EKTARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VI at EKTARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 9230 Nos.) | AE SWSD-II | JE2 | ORD/000373/2023-2024 | 1782/SWD-I | 11/08/2023 | 300 | CONCORD ENGINEERING | 1862.26 | 10.26 | 55
846 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE2 | RTOR000136/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 56.86 | 0 | 0
847 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for DADPUR DIGHIRPAR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000095/2022-2023 | 1207/SWD-I | 02/09/2022 | 30 | MAMON ENTERPRISE AND CONSTRUCTION | 20.06 | 19.32 | 100
848 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at DADPUR DIGHIRPAR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012523] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000123/2022-2023 | 1291/SWD-I | 14/09/2022 | 60 | SANJAY ENTERPRISE | 5.47 | 4.64 | 100
849 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DADPUR DIGHIRPAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000161/2021-2022 | 1915/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 2.61 | 100
850 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at DADPUR DIGHIRPAR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 911) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000203/2022-2023 | 1559/SWD-I | 13/10/2022 | 90 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 178.64 | 107.2 | 60
851 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work and other allied works for Ground water based DADPUR DIGHIRPAR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/12053) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000337/2024-2025 | 3311/SWD-I | 23/07/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 62.15 | 0 | 0
852 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000103/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 6.7 | 0 | 0
853 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-XI at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2329) (TSM/015099 & TSM/010837) | AE HQ-I |  | ORD/000387/2023-2024 | 1840/SWD-I | 17/08/2023 | 775 | M/S. B.M. CONSTRUCTION | 327.12 | 24.45 | 80
854 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000056/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 14.35 | 0 | 0
855 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte. [WB092725] [SM/12043] [w.e.f. 01/06/2025 to 30/11/2025] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000058/2025-2026 | 1367/SWD-I | 22/05/2025 | 183 | GOPAL KUMAR JHA | 0.87 | 0.4 | 18
856 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for ERENDA piped water supply scheme at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tubewell site (Dag No. 391, Khatian No. 1321 , JL No. 132, Mouza- Noapara), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000167/2022-2023 | 1441/SWD-I | 26/09/2022 | 30 | ABU TALEB MONDAL | 28.52 | 0 | 0
857 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for ERENDA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 3188] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000428/2023-2024 | 2002/SWD-I | 28/08/2023 | 90 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 347.5 | 129.05 | 25
858 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "ERENDA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12043) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000676/2024-2025 | 4465/SWD-I | 29/10/2024 | 305 | SUJIT KUMAR SHARMA | 10.53 | 0 | 100
859 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ERENDA PWSS at headwork site (Dag No. 2362, Khatian No. 1233, JL. No. 120, Mouza- Erenda) & 2nd Tube-well site (Dag No. 391 Khatian No. 1321, JL No. 132, Mouza- Noapara) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12043] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000742/2022-2023 | 3568/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 0 | 0
860 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ERENDA PWSS of Bhangar-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/010678] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000748/2023-2024 | 562/SWD-I | 31/01/2024 | 15 | TRAYEE DECORATOR | 15.88 | 13.05 | 100
861 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell for ERENDA Piped Water Supply Scheme in BHANGAR-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12043] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000786/2023-2024 | 1069/SWD-I | 04/03/2024 | 30 | ASHIM SHIL | 15.8 | 13.32 | 100
862 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-II), South 24-Pgns. W/S Division-I, PHE Dte. [WB092725] [SM/12043] [w.e.f. 01/12/2024 to 31/05/2025] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001111/2024-2025 | 4847/SWD-I | 28/11/2024 | 182 | GOPAL KUMAR JHA | 0.86 | 2.37 | 30
863 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000053/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 14.98 | 0 | 0
864 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000246/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 19.64 | 0 | 0
865 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE BENIABOW PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANASWATER SUPPLY DIV-1, PHE.DTE. (TSM/016028) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 2422/SWD-I. | 27/12/2022 | 30 | SAHI MASUM | 29.69 | 27.96 | 100
866 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BENIABOW Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1079] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000497/2022-2023 | 2865/SWD-I | 09/02/2023 | 918 | M/S S. C. CIVIL ENTERPRISES | 263.16 | 94.45 | 30
867 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BENIABOW PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13774] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000717/2022-2023 | 3554/SWD-I | 21/03/2023 | 15 | SAHI MASUM | 3.14 | 3.14 | 100
868 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development & Road Restoration of BENIABOW Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13774] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000829/2023-2024 | 1110/SWD-I | 05/03/2024 | 60 | M/S S.C. CIVIL ENTERPRISES | 46.11 | 0 | 0
869 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000009/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 24.99 | 0 | 0
870 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000229/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.65 | 0 | 0
871 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAYPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24- Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1992] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 93/SWD-I | 10/04/2023 | 722 | EQUIPMENTS AND SPARES AGENCIES | 471 | 223.06 | 75
872 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE RAYPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016075) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000355/2022-2023 | 2262/SWD-I | 15/12/2022 | 766 | SAHI MASUM | 29.69 | 14.03 | 100
873 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAYPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13737] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 2915/SWD-I | 14/02/2023 | 704 | SAHI MASUM | 3.14 | 1.57 | 100
874 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development, Road Restoration & Drumsheet Walling of RAYPUR PWSS within Sonarpur Block to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13773] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000771/2023-2024 | 783/SWD-I | 15/02/2024 | 455 | EQUIPMENTS AND SPARES AGENCIES | 50.02 | 0 | 60
875 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000028/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 23.26 | 0 | 0
876 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000238/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.27 | 0 | 0
877 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.19] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00478/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 10.76 | 0 | 0
878 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Natagachhi PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015394] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000336/2022-2023 | 2073/SWD-I | 01/12/2022 | 30 | SIMPLEX DRILLING COMPANY | 30.59 | 28.9 | 100
879 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for NATAGACHHI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1022] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000542/2022-2023 | 3030/SWD-I | 20/02/2023 | 901 | SAKTI ENTERPRISE (DEBASISH.SAKTI2015@GMAIL.COM) | 306.26 | 127.67 | 30
880 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for NATAGACHI PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/015394] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000571/2022-2023 | 2975/SWD-I | 21/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 3.17 | 3.17 | 100
881 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling , Land Development, Road Restoration & others allied works of NATAGACHHI PWSS within Sonarpur Block to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13499] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000770/2023-2024 | 784/SWD-I | 15/02/2024 | 457 | SAKTI ENTERPRISE | 86.16 | 0 | 20
882 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000033/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 34.35 | 0 | 0
883 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000242/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.3 | 0 | 0
884 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection for Replacement Tubewell of Buita Water Supply Scheme under "Repair And Replacement of TubeWell Zones of Different Water Supply Scheme under Budge Budge-I Under South 24 Pgns. W/S Division-I, PHE Dte. (TSM/ 013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000243/2023-2024 | 1440/SWD-I | 18/07/2023 | 30 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 4.84 | 4.82 | 100
885 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 02 (two) nos. Replacement Rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for water supply at Nandarampur W/S Scheme and Buita W/S Scheme of Budge Budge-I Block under South 24-Parganas W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000304/2022-2023 | 1884/SWD-I | 16/11/2022 | 30 | SUBHRA ENTERPRISE | 30.03 | 26.46 | 50
886 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair / renovation / overhauling of Iron elimination Plant of 100 cum capacity (aprox) for Nischintapur Water Supply Scheme under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/013413] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000327/2022-2023 | 2044/SWD-I | 30/11/2022 | 15 | RAMASISH ENTERPRISE | 12.92 | 12.92 | 50
887 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair & Restoration of road damaged due to laying of pipeline for Buita, Jamalpur and Nandarampur Schemes under Repair and Replacement of Tubewell zones of different water supply schemes under Budge Budge-I under South 24-Parganas W/S Division-I, PHE Dte. (SM/12884) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000534/2024-2025 | 4080/SWD-I | 19/09/2024 | 30 | SRIJON ENTERPRISE | 19.32 | 0 | 100
888 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Inter connection of DI pipeline with distribution in Uttar Roypur Water Supply Scheme Head Work Site for Repair And Replacement Of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge -I Under South 24-Partganas, W/S Division-I, PHE Dte. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000616/2023-2024 | 2800/SWD-I | 09/11/2023 | 45 | SRIJON ENTERPRISE | 10.94 | 10.34 | 100
889 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Nandarampur&Buita PWSS for repair and replacement of Tubewell zones of different W/S Scheme under Budge Budge-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/013413] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000696/2022-2023 | 3499/SWD-I | 16/03/2023 | 15 | SUBHRA ENTERPRISE | 3.14 | 3.14 | 0
890 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road restoration of Inter connection of DI pipeline with distribution in Uttar Roypur Water Supply Scheme Head Work Site for Repair And Replacement of Tube Well Zones Of Different Water Supply Schemes Under Budge Budge I Under South 24-Partganas, W/S Division-I, PHE Dte. (TSM/013413) [2nd call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000717/2023-2024 | 360/SWD-I | 16/01/2024 | 30 | SRIJON ENTERPRISE | 7.83 | 7.81 | 100
891 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repairing Rising Main from Existing Tubewell to existing OHR for BUITA Distribution Zone for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. South 24 Pgs. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000746/2022-2023 | 3597/SWD-I | 23/03/2023 | 30 | PEECON | 3.28 | 3.05 | 0
892 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Boundary Wall for proposed Pump House Site at Abhirampur for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. Sdouth 24 Pgs. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000747/2022-2023 | 3598/SWD-I | 23/03/2023 | 60 | SANJAY MIDDEY | 6.47 | 5.05 | 100
893 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying Rising Main from Existing Tubewell to existing OHR for JAMALPUR & MOUKHALI Distribution Zone with interconnection and bypass arrangement including interconnection of Distribution mains for Repair and Replacement of Tube Well Zones of Different Water Supply Schemes under Budge Budge I under South 24 Pgs W/S Division-I, PHE Dte. Dist. South 24 Pgs. (TSM/013413) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000780/2022-2023 | 3664/SWD-I | 29/03/2023 | 45 | M/S. S.S. ENTERPRISE | 19.82 | 14.27 | 75
894 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
895 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Karimpur Kismat PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns district. (SM/13922) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000257/2024-2025 | 2674/SWD-I | 07/06/2024 | 418 | RAJLAXMI CONSTRUCTION | 49.25 | 11.18 | 40
896 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of KARIMPUR KISMAT AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000419/2021-2022 | 1969/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 2.51 | 0
897 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for KARIMPUR KISMAT PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016376] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000551/2022-2023 | 3040/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
898 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KARIMPUR KISMAT PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016562] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000600/2022-2023 | 3128/SWD-I | 24/02/2023 | 30 | MRA NIRMAN UDYOG | 15.89 | 0 | 90
899 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of KARIMPUR KISMAT PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 738) [TSM/016376]. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000722/2022-2023 | 3565/SWD-I | 22/03/2023 | 665 | RAJLAXMI CONSTRUCTION | 117.95 | 85.81 | 90
900 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000094/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 4.82 | 0 | 0
901 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) alongwith construction of Chlorine Room (2 Nos.) for Augmentation of MALLARCHAK ISHWARIPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. (No of FHTC = 1962) [TSM/016725] | Assistant Engineer | Junior Engineer | ORD/000065/2023-2024 | 368/SWD-I | 27/04/2023 | 705 | M/S ROY CHOWDHURY AND CO. | 290.21 | 174.43 | 50
902 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MOLLARCHAK ISHWARPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016725] | Assistant Engineer | Junior Engineer | ORD/000626/2022-2023 | 3240/SWD-I | 01/03/2023 | 30 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 0
903 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Mallarchak Ishwaripur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000995/2022-2023 | 1466\SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.6 | 2.59 | 100
904 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary Wall for 2nd Tubewell, land development for OHR and allied works for Mallarchak Iswaripur piped water supply scheme to accomodate FHTC in Mograhat II Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14661) [2nd call] | Assistant Engineer | Junior Engineer | ORD/001122/2024-2025 | 156/SWD-I | 15/01/2025 | 45 | MAMONI ENTERPRISE | 94.94 | 0 | 0
905 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000130/2022-2023 | 3389/SWD-I | 10/03/2023 | 0 | Resource Division | 12.09 | 0 | 0
906 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000173/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 27.39 | 0 | 0
907 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of UTTAR PARANIJ MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2168] [TSM/018529] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000317/2023-2024 | 1709/SWD-I | 08/08/2023 | 816 | M/S SALIM CONSTRUCTION | 478.77 | 0 | 70
908 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for UTTAR PARANIJ PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018529] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000615/2022-2023 | 3213/SWD-I | 28/02/2023 | 30 | NAJMUL HAQUE | 31.62 | 0 | 100
909 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Paranji Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000951/2022-2023 | 1297/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.74 | 2.66 | 100
910 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000098/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 41.92 | 0 | 0
911 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at ALIPUR for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [No. of FHTC =244] [TSM/014211] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000167/2023-2024 | 964/SWD-I | 08/06/2023 | 90 | RAJ KUMAR MONDAL | 122.78 | 72.52 | 40
912 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at ALIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014211] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000251/2022-2023 | 1752/SWD-I | 04/11/2022 | 8460 | B.M. TRADERS | 10.93 | 0 | 100
913 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for ALIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000275/2022-2023 | 1838/SWD-I | 11/11/2022 | 30 | UMAR ALI KHAN | 40.12 | 0 | 0
914 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at ALIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1186) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000323/2022-2023 | 2020/SWD-I | 29/11/2022 | 1080 | RAJ KUMAR MONDAL | 190.68 | 80.39 | 65
915 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of ALIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000346/2021-2022 | 1908/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.76 | 2.74 | 100
916 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, platform for FHTC, road restoration, protection work for pipeline and other allied works for Ground water based ALIPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte, South 24 Parganas district. (SM/13442) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000509/2024-2025 | 3964/SWD-I | 10/09/2024 | 484 | SANDHYA ENTERPRISE | 58.48 | 6.02 | 60
917 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Alipur PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014211] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000781/2022-2023 | 3665/SWD-I | 29/03/2023 | 15 | UMAR ALI KHAN | 4.4 | 0 | 0
918 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000111/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 14.32 | 0 | 0
919 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of boundary wall & other allied works at Head Work Site of DAULATPUR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/016355] | Assistant Engineer -II | Junior Engineer | ORD/000042/2023-2024 | 183/SWD-I | 18/04/2023 | 60 | NIRMAL UDYOG | 18.78 | 14.92 | 100
920 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Layiing of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, land development, approach road, protection of pipeline and road restoration for DOULATPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/13780) | Assistant Engineer -II | Junior Engineer | ORD/000290/2024-2025 | 3106/SWD-I | 09/07/2024 | 476 | PROJECT AND MAINTENANCE | 188.62 | 0 | 35
921 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of DAULATOUR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer -II | Junior Engineer | ORD/000420/2021-2022 | 1968/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.75 | 0
922 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | Assistant Engineer -II | Junior Engineer | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
923 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for DAULATPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016355] | Assistant Engineer -II | Junior Engineer | ORD/000549/2022-2023 | 3039/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
924 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for DAULATPUR PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/016355] | Assistant Engineer -II | Junior Engineer | ORD/000578/2022-2023 | 3093/SWD-I | 23/02/2023 | 30 | MD RUHUL AMIN GOLDER | 15.89 | 13.83 | 100
925 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DAULATPUR Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13780] | Assistant Engineer -II | Junior Engineer | ORD/000689/2024-2025 | 4484/SWD-I | 30/10/2024 | 30 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0
926 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of DAULATPUR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4918) [TSM/016355]. | Assistant Engineer -II | Junior Engineer | ORD/000763/2022-2023 | 3638/SWD-I | 27/03/2023 | 919 | PROJECT AND MAINTENANCE | 300.71 | 140.58 | 80
927 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer -II | Junior Engineer | RTOR000090/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 39.25 | 0 | 0
928 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of UTTAR MOHANPUR MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1742] [TSM/015329] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000051/2023-2024 | 270/SWD-I | 24/04/2023 | 738 | TUMPA ASSOCIATES | 438.46 | 0 | 30
929 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Approach road, Development of Land at OHR site for UTTAR MOHANPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas. (SM/13781) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000394/2024-2025 | 3642/SWD-I | 20/08/2024 | 60 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 17.76 | 0 | 40
930 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR MOHANPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13781] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000623/2022-2023 | 3239/SWD-I | 01/03/2023 | 933 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 31.71 | 0 | 50
931 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "UTTAR MOHANPUR Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000883/2022-2023 | 411/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.9 | 2.7 | 0
932 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000167/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 24.89 | 0 | 0
933 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2025 to 30.11.2025) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000063/2025-2026 | 1372/SWD-I | 22/05/2025 | 183 | MINTU SOMADDAR | 0.87 | 0 | 100
934 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities under the Assistant Engineers (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 787/SWD-I | 04/05/2023 | 183 | DIPAK NASKAR | 0.87 | 0 | 0
935 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2023 to 30.11.2023) [SM/13785] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 779/SWD-I | 31/05/2023 | 183 | MINTU SOMADDAR | 0.87 | 2.23 | 20
936 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.06.2024 to 30.11.2024) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000218/2024-2025 | 2482/SWD-I | 28/05/2024 | 183 | MINTU SOMADDAR | 0.87 | 2.38 | 18
937 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR RAGHUNATHPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016318) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000348/2022-2023 | 2168/SWD_I | 09/12/2022 | 30 | PADMA ENGINEERING CO. | 30.07 | 12.02 | 50
938 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2039] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000437/2023-2024 | 2012/SWD-I | 28/08/2023 | 703 | MILAN GHOSH | 472.62 | 0 | 20
939 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.12.2023 to 31.05.2024) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000702/2023-2024 | 3000/SWD-I | 29/11/2023 | 183 | MINTU SOMADDAR | 0.87 | 2.4 | 20
940 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pumphouse, Cholorine room, Office Room, Construction of Pathway at OHR Site of "RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13785) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000703/2024-2025 | 4505/SWD-I | 30/10/2024 | 60 | M/S UNIQUE ENTERPRISE | 20.87 | 0 | 0
941 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13785) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000753/2024-2025 | 4675/SWD-I | 18/11/2024 | 45 | MILAN GHOSH | 10.04 | 0 | 0
942 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAGHUNATHPUR PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13785] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000769/2022-2023 | 3643/SWD-I | 28/03/2023 | 15 | PADMA ENGINEERING CO. | 3.14 | 1.57 | 50
943 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities under the Assistant Engineers (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000876/2022-2023 | 3729/SWD-I | 31/03/2023 | 183 | DIPAK NASKAR | 0.87 | 0.38 | 0
944 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for monitoring different JJM activities of Sonarpur/ Bhangore-I/ Mandirbazar/ Kulpi Block under the Assistant Engineer, (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01.12.2024 to 31.05.2025) [SM/13785] [Vehicle No- WB-19G-6957] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001068/2024-2025 | 4888/SWD-I | 29/11/2024 | 182 | MINTU SOMADDAR | 0.86 | 2.39 | 15
945 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000026/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 57.09 | 0 | 0
946 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000254/2023-2024 | 1006/SWD-1 | 09/06/2023 | 0 | Resource Division | 12.56 | 0 | 0
947 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24- Parganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1764] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000026/2023-2024 | 109/SWD-I | 11/04/2023 | 300 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 533.56 | 134.97 | 25
948 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of Land & other allied works of SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13787). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000266/2024-2025 | 2681/SWD-I | 07/06/2024 | 45 | M/S SHIBAM ENTERPRISE | 47.6 | 0 | 0
949 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR SAMUKPOTA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016319) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000347/2022-2023 | 2167/SWD_I | 09/12/2022 | 800 | PADMA ENGINEERING CO. | 30.07 | 0 | 100
950 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of SAMUKPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13787) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000747/2024-2025 | 4669/SWD-I | 18/11/2024 | 45 | R.G ENTERPRISE | 10.02 | 0 | 0
951 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAMUKPOTA PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13787] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000768/2022-2023 | 3642/SWD-I | 28/03/2023 | 691 | PADMA ENGINEERING CO. | 3.14 | 0 | 50
952 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000030/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 54.07 | 0 | 0
953 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000240/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.87 | 0 | 0
954 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 200 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for GABBARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district, under South 24 Pgns Water Supply Division-1, PHE Dte. [TSM/018429] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000030/2023-2024 | 111/SWD-I | 11/04/2023 | 988 | SHAKUNTALA CONSTRUCTION | 107.41 | 37.91 | 65
955 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of GABBERIA PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2259) [TSM/018429] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000046/2023-2024 | 242/SWD-I | 20/04/2023 | 1077 | MONDAL PRECISION PVT. LTD. | 311.23 | 202.08 | 30
956 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Interconnection of 2 nos. OHRs with existing 1422 mm rising main pipe for Gabberia PWSS under Bishnupur -I District.- South-24 Pgns.' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/14871) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000089/2025-2026 | 1764/SWD-I | 02/07/2025 | 30 | S. ROY AND ASSOCIATES | 8.88 | 0 | 0
957 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Upgradation of Store including preparation of approach road at GABBERIA PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24-Pgns. W/S Division-I, PHE Dte. for augmentation surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. (SM/14871) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000095/2025-2026 | 1770/SWD-I | 02/07/2025 | 30 | SRIJON ENTERPRISE | 10.5 | 0 | 1
958 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of approach road, protection work of pipeline, upgradation of existing boundary wall, laying rising mai nand other allied works for GABBARIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/14871] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000247/2024-2025 | 2667/SWD-I | 07/06/2024 | 298 | SHAKUNTALA CONSTRUCTION | 82.98 | 0 | 45
959 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for GABBARIA PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018429] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000581/2022-2023 | 3095/SWD-I | 23/02/2023 | 30 | MD RUHUL AMIN GOLDER | 15.88 | 0 | 0
960 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Repairing and renovation of Overhead Reservoir (220 cum. Capacity) for Gabberia P.W.S.S. under South 24-Pgs. W/S Sub-Divn- II under surface water based water supply scheme in the Arsenic affected area of South 24 Pgs. Dist. [SM/14871] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000836/2023-2024 | 1291/SWD-I | 15/03/2024 | 45 | S.P. ENTERPRISE | 6.38 | 6.22 | 96
961 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Gabbaria Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000966/2022-2023 | 1165/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.7 | 2.7 | 100
962 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000117/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 67.3 | 0 | 0
963 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed 1250 Cum OHR Site of Zone-II within Mandirbazar block, Mouza-PurbaBishnupur (JL No-23), under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 145 mtr.) | AE HQ-I |  | ORD/000023/2022-2023 | 878/SWD-I | 14/07/2022 | 60 | A P POWER AND CONCRETE | 27.53 | 24.91 | 50
964 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9619) | AE HQ-I |  | ORD/000054/2023-2024 | 273/SWD-I | 24/04/2023 | 708 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1667.83 | 327.78 | 20
965 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of PUKURIA MOUZA in MANDIRBAZAR (ZONE-II) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000514/2021-2022 | 1984/SWD-I | 27/01/2022 | 30 | RADIANT | 4.83 | 3.75 | 100
966 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fitting & fixing Doors, Windows & allied works in Mandirbazar GLR cum Pump house, Sub-Station Building, Chlorination Building, Office Building, Dormitory Building & Guard Room etc. for Augmentation of existing Laying Distribution System to extend the benefit of 100% households in Zone-II at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (TSM/014522) | AE HQ-I |  | ORD/000547/2023-2024 | 2495/SWD-I | 06/10/2023 | 60 | AVIK ENTERPRISE | 33.18 | 31.72 | 100
967 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Approach Road with allied for Head Work Site Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-II at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 pgns under South-24 pgns W/S Divn-I of South 24-pgns. W/S Circle, Phe Dte. (TSM/14522) | AE HQ-I |  | ORD/000618/2023-2024 | 2802/SWD-I | 09/11/2023 | 45 | A.P POWER AND CONCRETE | 8.99 | 8.94 | 100
968 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Piling work for protection of Mandirbazar Hatuganj road near Mandirbazar P.S. damaged due to construction of 1200 mm dia valve chamber for in connection with Augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-II at Mandirbazar block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist. South 24-Pgs. under South 24-Pgns. W/S Division-I, PHE Dte. (SM/ 15485) [2nd call] | AE HQ-I |  | ORD/000716/2023-2024 | 359/SWD-I | 16/01/2024 | 15 | M/S SUBHODEEP ENTERPRISE | 1.19 | 1.16 | 100
969 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of Land and Construction of Temporary pathway at OHR Site of Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-II at Mandirbazar Block within Mega Surface Water Based W/S Scheme for Falta-Mathurapur, Dist- South 24-Pgns. under South 24-Parganas W/S Divn.-I, PHE Dte. (TSM/014522) | AE HQ-I |  | ORD/000744/2023-2024 | 549/SWD-I | 31/01/2024 | 30 | RIVER BENZ CONSTRUCTION | 3.01 | 3.01 | 100
970 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000044/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 395.19 | 0 | 0
971 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000212/2023-2024 | 670 | 24/05/2023 | 0 | Resource Division | 500.47 | 0 | 0
972 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional laying & allied works from Ghatarnia to Nolgora of Secondary Grid pipeline for Nolgora of Joynagar-II Block within Mega surface water based water supply scheme of Falta Mathurapur under "Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-VII at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under South 24 Pgns W/S Division-I, PHE Dte." (SM/16183) | AE BSD |  | ORD/000074/2025-2026 | 1577/SWD-I | 11/06/2025 | 45 | ARASTA ENGINEERING & CO | 48.34 | 0 | 70
973 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-VII NOLGORA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 11912] [TSM/011554] and [TSM/015335] 124076810.5 | AE BSD |  | ORD/000260/2023-2024 | 1515/SWD-I | 21/07/2023 | 894 | MRA NIRMAN UDYOG | 1590.17 | 419.29 | 65
974 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Laying distribution system at Zone-VII (NOLGORA) of JOYNAGAR-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte.(SM/ 11770 , SM/16183) | AE BSD |  | ORD/000364/2024-2025 | 3511/SWD-I | 07/08/2024 | 327 | MRA NIRMAN UDYOG | 434.23 | 0 | 40
975 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall for proposed OHR Site at Nolgora Mouza , JL No.145, Khatian No. 1361, Plot No. 3932; within Joynagar-II block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur , Dist. South 24 Paraganas. [Length - 140.0 mtr.] | AE BSD |  | ORD/000595/2021-2022 | 1580/SWD-I | 27/12/2021 | 1350 | M/S. KALPANA CONSTRUCTION | 25.11 | 0 | 100
976 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000209/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 163.2 | 0 | 0
977 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000298/2023-2024 | 2435/SWD-I | 30/09/2023 | 0 | Resource Division | 297.49 | 0 | 0
978 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-V at Monirtar Mouza of Joynagar-II Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000143/2022-2023 | 1337/SWD-I | 16/09/2022 | 300 | AJIT PRAMANICK | 322.51 | 165.52 | 45
979 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VB (Monirtala) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000369/2021-2022 | 2339/SWD-I | 22/02/2022 | 120 | CALCON CONSTRUCTIONS | 267.4 | 98.46 | 40
980 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VA (Monirtala) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000676/2022-2023 | 71/SWD-I | 13/04/2022 | 120 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 565.06 | 197.88 | 40
981 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipeline protection works, restoration of roads damaged due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-V at JOYNAGAR-II block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/16190) (2nd call) | AE BSD |  | ORD/000773/2024-2025 | 4758/SWD-I | 21/11/2024 | 405 | MAMONI ENTERPRISE | 89.72 | 0 | 30
982 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000067/2022-2023 | 2983/SWD-I | 20/02/2023 | 0 | Resource Division | 230.38 | 0 | 0
983 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land development and other allied works for "Ground Water Based Tilpi ZONE-I Piped Water Supply Scheme to Accommodate FHTC in Jaynagar-I Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15781) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000354/2024-2025 | 3454/SWD-I | 02/08/2024 | 405 | GARAI INFRA PROJECT | 83.17 | 0 | 85
984 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 208.2 | 96
985 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for TILPI Zone-I PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018024) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000704/2022-2023 | 3513/SWD-I | 17/03/2023 | 30 | MALLICK CONSTRUCTION | 15.82 | 14.7 | 100
986 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "TILPI Zone-I Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000756/2022-2023 | 707/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.56 | 2.56 | 100
987 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method at 2nd Tubewell site for TILPI (Zone-I) Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/15781] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000807/2023-2024 | 1286/SWD-I | 15/03/2024 | 30 | M/S BASAK CONSTRUCTION | 18.9 | 0 | 0
988 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000153/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 31.28 | 0 | 0
989 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TEKA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 853] [TSM/017759] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 933/SWD-I | 06/06/2023 | 90 | A.K. INDUSTRIES | 159.51 | 75.52 | 70
990 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for TEKA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017759] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000646/2022-2023 | 3318/SWD-I | 06/03/2023 | 977 | SUMAN ENTERPRISE | 31.72 | 15.47 | 50
991 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for providing FHTC, restoration of road damaged due to laying of pipeline and other allied works for Ground Water based TEKA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/16137) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000716/2024-2025 | 4550/SWD-I | 06/11/2024 | 45 | A.K. INDUSTRIES | 49.41 | 0 | 0
992 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Teka Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000931/2022-2023 | 1222/SWD-I | 05/09/2022 | 30 | GEO SOLUTION | 2.47 | 2.46 | 100
993 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000129/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 26.12 | 0 | 0
994 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Augmentation for Providing balance FHTC in BUITA, CHINGRIPOTA, NISCHINTIPUR, RAJIBPUR & UTTAR ROYPUR GP under South 24 Parganas W/S Division-I, PHE, Dte. Dist. South 24 Pgns. | AE SWSD-I |  | ORD/000564/2023-2024 | 2637/SWD-I | 20/10/2023 | 726 | STAR ENGINEERS CO-OPERATIVE SOCEITY LTD. | 80.22 | 52.37 | 60
995 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I |  | RTOR000317/2023-2024 | 24/SWSD-I | 09/01/2024 | 0 | Resource Division | 15.76 | 0 | 0
996 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.24] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00483/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 8.08 | 0 | 0
997 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1683) (TSM/017714) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000233/2023-2024 | 1417/SWD-I | 17/07/2023 | 899 | SAMSUL ENTERPRISE | 487.01 | 308.34 | 70
998 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/15773) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000243/2024-2025 | 2663/SWD-I | 07/06/2024 | 45 | NILKANTHA ENTERPRISE | 10.43 | 10.37 | 100
999 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GANGAJOARA PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/017714] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000666/2022-2023 | 3406/SWD-I | 10/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 15.32 | 50
1000 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional LDS and Road Restoration of GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15773) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000792/2024-2025 | 4843/SWD-I | 27/11/2024 | 60 | SAMSUL ENTERPRISE | 36.02 | 0 | 0
1001 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Protection Wall and Land Development at 2nd Tubewell site GANGAJOARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15773) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000804/2023-2024 | 1250/SWD-I | 13/03/2024 | 30 | KALAM ENTERPRISE | 3.85 | 3.85 | 100
1002 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall,Land Development,Pathway,Drain & others allied works of Gangajoara Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15773] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000843/2023-2024 | 1209/SWD-I | 11/03/2024 | 45 | SAMSUL ENTERPRISE | 41.07 | 0 | 0
1003 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000016/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 58.79 | 0 | 0
1004 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000252/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.37 | 0 | 0
1005 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall for proposed OHR Site at Purbatetulberia Mouza, JL No.10, Khatian No. 899/1, Plot No. 916 & 918; within Kultali block, under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. [Length - 140.0 mtr.] | AE BSD |  | ORD/000418/2021-2022 | 1798/SWD_I | 14/01/2022 | 90 | KHAN ENTERPRISE | 26.92 | 23.51 | 0
1006 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1500 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I PURBO TETULBERIA MOUZA Piped Water Supply Scheme of KULTALI Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 14340] [TSM/011555 & TSM/016360] | AE BSD |  | ORD/000529/2023-2024 | 2344/SWD-I | 22/09/2023 | 558 | MADAN MOHAN MONDAL | 1916.42 | 197.99 | 60
1007 | South 24 Pgs W/S Division I |  | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based MAGRAHAT piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. |  |  | ORD/000313/2024-2025 | 3245/SWD-I | 19/07/2024 | 90 | CHANDAN ROY | 307.51 | 0 | 0
1008 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MOGRAHAT PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018189] |  |  | ORD/000355/2023-2024 | 1741/SWD-I | 10/08/2023 | 30 | JENARUL ISLAM | 47.38 | 0 | 0
1009 | South 24 Pgs W/S Division I |  | Construction of 500 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of MOGRAHAT ZONE-33 MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3012] [TSM/018189] |  |  | ORD/000527/2023-2024 | 2340/SWD-I | 22/09/2023 | 300 | M/S R.K. ENTERPRISE | 510.3 | 0 | 0
1010 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Magrahat Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000971/2022-2023 | 1405/SWD-I | 21/09/2022 | 30 | GEO SOLUTION | 2.64 | 2.6 | 100
1011 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000291/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 48.64 | 0 | 0
1012 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1450 cum capacity 20 mtr. staging heigtht Over Head Reservoir as per Departmental Drawing and specification including RCC bored pile and pile cap, Laying Distribution System of piped water supply scheme in Zone - VIII at Khelarampur Mouza of Mograhat-I Block, for augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VIII at KHELARAMPUR under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (Number of FHTC-11274 Nos.) | AE SWSD-II | JE4 | ORD/000677/2022-2023 | 3454/SWD-I | 14/03/2023 | 902 | M/S. S.S. ENTERPRISE | 1859.15 | 44.96 | 52
1013 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000139/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 69.45 | 0 | 0
1014 | South 24 Pgs W/S Division I |  | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for Bhangar Raghunathpur Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District under Jal Jeevan Mission. [SM/18569] |  |  | ORD/000076/2025-2026 | 1579/SWD-I | 11/06/2025 | 174 | PADMA ENGINEERING CO. | 15.9 | 0 | 100
1015 | South 24 Pgs W/S Division I |  | Construction of 350 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for BHANGAR RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2835) (TSM/018465) |  |  | ORD/000394/2023-2024 | 1879/SWD-I | 18/08/2023 | 920 | SHIV CONSTRUCTION | 477.4 | 0 | 20
1016 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of BHANGAR RAGHUNATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18569) |  |  | ORD/000563/2024-2025 | 4236/SWD-I | 30/09/2024 | 420 | SUJIT KUMAR SHARMA | 68.52 | 0 | 60
1017 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 20.72 | 0 | 0
1018 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000322/2023-2024 | 254/SWD-I | 10/01/2024 | 0 | Resource Division | 17.46 | 0 | 0
1019 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for RAMKRISHNAPUR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018530](3rd call) |  |  | ORD/000374/2023-2024 | 1772/SWD-I | 11/08/2023 | 30 | SNEHA CONSTRUCTION | 46.94 | 0 | 0
1020 | South 24 Pgs W/S Division I |  | Construction of 450 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of RAMKRISHNAPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3080] [TSM/018530] |  |  | ORD/000416/2023-2024 | 1962/SWD-I | 24/08/2023 | 900 | MANASH GHOSH | 659.95 | 0 | 30
1021 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Ramkrishnapur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000952/2022-2023 | 1298/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.92 | 2.83 | 100
1022 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 68.17 | 0 | 0
1023 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for CHAMPAHATI (ZONE-II) PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/010745] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000214/2022-2023 | 1586/SWD-I | 17/10/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 34.72 | 100
1024 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Champahati (Zone-II) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000358/2022-2023 | 2201/SWD-I | 13/12/2022 | 60 | THE DESIGN IN | 10.72 | 0 | 0
1025 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHAMPAHATI(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000446/2021-2022 | 1954/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
1026 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of CHAMPAHATI (Zone-II) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/010745] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000455/2023-2024 | 2112/SWD-I | 30/08/2023 | 15 | TAPAS KUMAR GIRI | 4.41 | 4.23 | 100
1027 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 500 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHAMPAHATI (Zone-II) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2991) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000570/2023-2024 | 2667/SWD-I | 31/10/2023 | 518 | RKS ENGINEER & CONTRACTOR | 578.64 | 143.14 | 65
1028 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000087/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 18.42 | 0 | 0
1029 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000302/2023-2024 | 2440/SWD-I | 30/09/2023 | 0 | Resource Division | 48.26 | 0 | 0
1030 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GANESHPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000094/2022-2023 | 1206/SWD-I | 02/09/2022 | 30 | JEWS CONSTRUCTION AND CO | 60.07 | 39.69 | 67
1031 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 03 (Three) nos. chlorination room at GANESHPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012659] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000118/2022-2023 | 1286/SWD-I | 14/09/2022 | 60 | M/S. SREEJIT ENTERPRISE | 16.38 | 4.41 | 33
1032 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of GANESHPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000160/2021-2022 | 1921/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 3.03 | 2.66 | 100
1033 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at GANESHPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 2233) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000223/2022-2023 | 1657/SWD-I | 21/10/2022 | 960 | PATHIK PABAN NANDI | 262.37 | 190.5 | 100
1034 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for Proposed Ground Water based GANESHPUR piped water supply schee to accoodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12061) (2nd call) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000731/2024-2025 | 4618/SWD-I | 13/11/2024 | 427 | PINKI CONSTRUCTION | 91.61 | 0 | 30
1035 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000266/2023-2024 | 2421/SWD-I | 30/09/2023 | 0 | Resource Division | 44.65 | 0 | 0
1036 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000335/2023-2024 | 265/SWD-I | 10/01/2024 | 0 | Resource Division | 13.76 | 0 | 0
1037 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Shyamnagar PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000298/2022-2023 | 1877/SWD-I | 16/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
1038 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based SHYAMNAGAR piped water supply scheme to accommodate FHTC in Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12806) | Assistant Engineer | Junior Engineer | ORD/000324/2024-2025 | 3257/SWD-I | 19/07/2024 | 60 | JAMIRUL CONSTRUCTION | 30.56 | 0 | 0
1039 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "SHYAMNAGAR Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000385/2022-2023 | 405/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 2.54 | 0
1040 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of SHYAMNAGAR of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1642] | Assistant Engineer | Junior Engineer | ORD/000513/2022-2023 | 2943/SWD-I | 16/02/2023 | 835 | JAMIRUL CONSTRUCTION | 339.61 | 0 | 10
1041 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 900mm Dia Double Row Hume Pipe Culvert for SHYAMNAGAR PWSS under Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12806) | Assistant Engineer | Junior Engineer | ORD/000662/2024-2025 | 4392/SWD-I | 23/10/2024 | 30 | N CONSTRUCTION | 6.18 | 0 | 0
1042 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary Wall (length=175.00m) & Construction of Service Road (length=140.00m) at OHR Site (1st Tubewell Site) for SHYAMNAGAR PWSS within Mograhat-II Block under S24 Pgns W/S Divn-I, PHE Dte. for Augmentation of Surface Water Based WAter Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District. (SM/12806) | Assistant Engineer | Junior Engineer | ORD/000681/2024-2025 | 4476/SWD-I | 30/10/2024 | 90 | R.K ENTERPRISE | 55.77 | 0 | 0
1043 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Shyam Nagar PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014761] | Assistant Engineer | Junior Engineer | ORD/000731/2022-2023 | 3583/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
1044 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000165/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 24.48 | 0 | 0
1045 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Uttar Roypur W/S Scheme for Booth No: 145 to 152 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000108/2020-2021 | 1360/SWD-I | 08/12/2020 | 120 | CALCON CONSTRUCTIONS | 96.86 | 178.74 | 100
1046 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline of within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6133) PART-V | AE SWSD-I |  | ORD/000464/2022-2023 | 2774/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 2.41 | 2.36 | 100
1047 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of damages due to laying of water-line by PHE Directorate at Sashan Station to Durgapur station connecting road from 0.000 kmp 0.830kmp under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.38,91,559/- x 50% = Rs.19,45,780/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. | AE BSD |  | BILL/00562/2023-2024 | BP-2023-24-266 | 25/08/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 19.46 | 0 | 0
1048 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of damages due to laying of water-line by PHE Directorate at Kalyanpur - Indralala - Durgapur Station Road from 0.000 kmp to 3.15 km (R/S: 230m & L/S: 1520m) under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.73,16,902/- x 50% = Rs.36,58,451/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. | AE BSD |  | BILL/00563/2023-2024 | BP-2023-24-266 | 25/08/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 36.58 | 0 | 0
1049 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Improvement of water supply by Interconnection from existing Big dia tube well and laying distribution system with CIDF, UPVC pipes Including providing Functional House Hold Tap Connection by retrofitting of scheme ¿Improvement of water supply [Phase-III] in Baruipur and Mograhat-II block¿ of Sankarpur-II GP within zone-43, covering Nur, Durgo, Balbalia, Surjopur hat mouzas under surface water based water supply scheme for arsenic affected areas of south 24- Parganas district. | AE BSD |  | ORD/000071/2021-2022 | 479 /SWD-I JJM p | 07/07/2021 | 120 | M/S. S.S. ENTERPRISE | 193.14 | 2.58 | 100
1050 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Interconection including laying distribution system from Big dia Tube well covering Kundarali, Mamudpur & Indraballa for improvement of water supply & Providing Functional House Hold Tap Connection within Sikharbali-II G.P of Baruipur Block, South 24 Paraganas District. | AE BSD |  | ORD/000295/2020-2021 | 2131/SWD-I | 26/02/2021 | 120 | PEECON | 203.09 | 153.23 | 100
1051 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Nischintipur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000081/2021-2022 | 1106/SWD-I JJM | 25/10/2021 | 120 | M/S. JAYDEEP DASGUPTA | 82.35 | 78.53 | 100
1052 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nischintipur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8297) Part - A | AE SWSD-I |  | ORD/000468/2022-2023 | 2777/SWD-I | 31/01/2023 | 30 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 8.58 | 8.53 | 75
1053 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for final 50% amount of the estimate value after completion of restoration work near chainage 10 km on Amtala Baruipur road as per minutes of the meeting taken by HMIC, PHED with SE's on 12/09/2022 whose total estimate value Rs.53,10,997/-, Less advance 50% payment Rs.26,55,499/-, So. Payment to be made Rs.26,55,498/- | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/00063/2024-2025 | BP-2024-25-52 | 09/05/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 26.55 | 0 | 0
1054 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of damages due to laying of water supply line of PHE Directorate near chainage 10.00 kmp of Amtala - Baruipur Road in the district of South 24 pgs under South 24 pgs. Division, PWD during the year 2022-2023 (Estimated cost Rs.53,10,997/- x 50% = 2655499/-) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | BILL/01314/2023-2024 | BP-2023-24-456 | 03/11/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 26.55 | 0 | 0
1055 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1056 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "JULPIA Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000420/2022-2023 | 467/SWD-I C | 24/05/2022 | 15 | CHAYANIKA ENGINEERING CONSULTANCY | 2.62 | 2.62 | 100
1057 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based JULPIA Pipe Water Supply Scheme for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs. District. [No. of FHTC=901 nos.] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000421/2022-2023 | 2566/SWD-I | 10/01/2023 | 90 | RELIABLE CONSTRUCTIONS | 163.03 | 54.77 | 60
1058 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of JULPIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/12234) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000434/2022-2023 | 2578/SWD-I | 10/01/2023 | 60 | BAKSHI ENTERPRISE | 6.05 | 5.67 | 100
1059 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for JULPIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014900] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000554/2022-2023 | 3044/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
1060 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for JULPIA Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgn. in BISHNUPUR-I Block Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/014900] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000592/2023-2024 | 2754/SWD-I | 07/11/2023 | 30 | SAIKAT ENTERPRISE | 15.03 | 0 | 95
1061 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for JULPIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014900] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000634/2022-2023 | 3278/SWD-I | 03/03/2023 | 15 | MOMINUL BISWAS | 1.57 | 0 | 0
1062 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, laying of additional pipeline and other allied works for JULPIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/12234] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000667/2024-2025 | 4414/SWD-I | 24/10/2024 | 361 | BAKSHI ENTERPRISE | 58.69 | 0 | 12
1063 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for JULPIA PWSS of BISHNUPUR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12234] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000785/2023-2024 | 1068/SWD-I | 04/03/2024 | 15 | SAIKAT ENTERPRISE | 1.57 | 0 | 95
1064 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land development at JULPIA Piped Water Supply Scheme for 1st Tubewell site in the Arsenic Affected Areas of South 24 Parganas District in Bishnupur-I Block under South 24-Pgns. W/S Sub Division-II, PHE Dte. (SM/12234) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000838/2023-2024 | 1255/SWD-I | 13/03/2024 | 15 | HASIBA ENTERPRISE | 2.65 | 0 | 95
1065 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000121/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 37.13 | 0 | 0
1066 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PIYALI KOLAGHATA (Part-I) PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009673] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000101/2022-2023 | 1228/SWD-I | 07/09/2022 | 30 | SAIKAT ENTERPRISE | 19.98 | 0 | 0
1067 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at PIYALI KOLAGHATA (Zone-I) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009673] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000155/2022-2023 | 1413/SWD-I | 22/09/2022 | 60 | SHUBHA UDYOG | 5.5 | 0 | 0
1068 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-II) (No. of FHTC = 1906) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000237/2022-2023 | 1712/SWD-I | 02/11/2022 | 1001 | M/S. S.S. ENTERPRISE | 285.6 | 140.4 | 92
1069 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at piyali kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-I) (No. of FHTC = 1032) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 1798/SWD-I | 09/11/2022 | 990 | KARUNAMOYEE ENTERPRISE | 140.23 | 44.53 | 75
1070 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PiyaliKolaghata-I PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000729/2022-2023 | 3572/SWD-I | 22/03/2023 | 15 | SAIKAT ENTERPRISE | 2.2 | 0 | 0
1071 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000073/2023-2024 | 293/SWD-I | 24/04/2023 | 0 | Resource Division | 8.71 | 0 | 0
1072 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1000 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-III at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.7715) | AE HQ-I |  | ORD/000542/2023-2024 | 2461/SWD-I | 04/10/2023 | 607 | SUPRITI ENTERPRISE | 1557.57 | 69.44 | 50
1073 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000052/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 47.52 | 0 | 0
1074 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000105/2022-2023 | 1231/SWD-I | 07/09/2022 | 30 | BARI ENTERPRISE | 40.12 | 33.85 | 100
1075 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Baruipur Sub-Division under South 24-Pgns. W/S Division-I, PHE Dte. [WB04J1932] [SM/11279] [w.e.f. 01/07/2025 to 31/12/2025] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 1730/SWD-I | 26/06/2025 | 184 | SUBRAT KUMAR SETHY | 0.87 | 0 | 0
1076 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PIYALI KOLAGHATA (Zone-II) of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010734] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000159/2022-2023 | 1412/SWD-I | 22/09/2022 | 60 | M/S. SREEJIT ENTERPRISE | 10.99 | 5.93 | 100
1077 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Piyali Kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-II) (No. of FHTC = 1906) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000237/2022-2023 | 1712/SWD-I | 02/11/2022 | 1001 | M/S. S.S. ENTERPRISE | 285.6 | 96.2 | 92
1078 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at piyali kolaghata (Solghoalia C.T, J.L- 25) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist.(PART-I) (No. of FHTC = 1032) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000271/2022-2023 | 1798/SWD-I | 09/11/2022 | 990 | KARUNAMOYEE ENTERPRISE | 140.23 | 57.01 | 75
1079 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based PIYALI KOLAGHATA (PART-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000306/2024-2025 | 3219/SWD-I | 18/07/2024 | 60 | M/S. S.S. ENTERPRISE (NODAKHALI) | 35.48 | 0 | 0
1080 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall including development of land and other allied works for Ground water based PIYALI KOLAGHATA(P-II) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11279) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 3239/SWD-I | 19/07/2024 | 45 | M/S. S.S. ENTERPRISE (NODAKHALI) | 31.32 | 0 | 0
1081 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of PIYALI KOLAGHATA (Part-II) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/010734] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000456/2023-2024 | 2115/SWD-I | 30/08/2023 | 15 | BARI ENTERPRISE | 4.4 | 2.03 | 100
1082 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PIYALI KOLAGHATA , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000507/2021-2022 | 1906/SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 2.76 | 100
1083 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Baruipur Sub-Division under South 24-Pgns. W/S Division-I, PHE Dte. [WB04J1932] [SM/11279] [w.e.f. 01/01/2025 to 30/06/2025] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001109/2024-2025 | 5303/SWD-I | 27/12/2024 | 181 | SUBRAT KUMAR SETHY | 0.86 | 2.08 | 33
1084 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for PIYALI KOLAGHATA (PART-I) Piped Water Supply Scheme of BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/11279] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001154/2024-2025 | 372/SWD-I | 04/02/2025 | 30 | M/S MAA TARA ENTERPRISE | 15.65 | 0 | 0
1085 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000072/2023-2024 | 293/SWD-I | 24/04/2023 | 0 | Resource Division | 38.58 | 0 | 0
1086 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at GOBINDAPUR of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000157/2022-2023 | 1410/SWD-I | 22/09/2022 | 60 | J H K ENTERPRISE | 11.01 | 0 | 100
1087 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for GOBINDAPUR PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010741] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000242/2022-2023 | 1685/SWD-I | 01/11/2022 | 360 | SIMPLEX DRILLING COMPANY | 42.98 | 36.72 | 100
1088 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at GOBINDAPUR Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1510) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000351/2023-2024 | 1737/SWD-I | 10/08/2023 | 900 | TAAS ENTERPRISE | 511.22 | 262.75 | 80
1089 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of GOBINDAPUR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000448/2021-2022 | 1962/SWD-I | 21/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
1090 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000071/2023-2024 | 292/SWD-I | 24/04/2023 | 0 | Resource Division | 45.97 | 0 | 0
1091 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room for DARI MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2135] (TSM/014441) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 466/SWD-I | 04/05/2023 | 90 | PROJECT INDIA | 412.54 | 407.52 | 85
1092 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DARI MADHABPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014441] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000605/2022-2023 | 3136/SWD-I | 27/02/2023 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 31.78 | 31.71 | 100
1093 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of "DARI MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13674) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000677/2024-2025 | 4466/SWD-I | 29/10/2024 | 60 | PROJECT INDIA | 79.05 | 0 | 0
1094 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation for the work of Engagement of 01 no. Computer Operator / Data Entry Operator [Category - A] for the office works of Executive Engineer (Deputed from PWD) under Superintending Engineer, South 24-Parganas W/S Circle, PHE Dte. [w.e.f. 01.04.2024 to 31.06.2024] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000902/2023-2024 | 1467/SWD-I | 27/03/2024 | 92 | M/S. SYSCON | 0.51 | 0.51 | 100
1095 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Engagement of 01 no. Computer Operator / Data Entry Operator [Category - C] for the office works of Superintending Engineer, PMU, WBDWSIP (ADB), PHE Dte. under Executive Engineer, South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01.04.2024 to 31.06.2024] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000903/2023-2024 | 1468/SWD-I | 27/03/2024 | 92 | M/S. SYSCON | 0.41 | 0.41 | 99
1096 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000052/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 13.13 | 0 | 0
1097 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000220/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 13.15 | 0 | 0
1098 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | As per Minutes of Hon'ble PHED Minister in Charge 50% advance payment of total estimate value for road restoration work for Mahishot Chattabazar Road which was submitted vide SE memo no.374/6-1391 dt.06/04/2022 | AE SWSD-I |  | BILL/00008/2022-2023 | BP-2022-23-106 | 02/12/2022 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 165.54 | 0 | 0
1099 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Restoration of road for laying of water pipeline by PHE Dte, in Mohisgot Chata bazar 0.00 to 5.40 km Under South 24 Parganas Division P.W.D in the Dist of South 24 Pgs During the year 2024-25 | AE SWSD-I |  | BILL/00345/2024-2025 | BP-2024-25-243 | 08/08/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 165.54 | 0 | 0
1100 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Balance FHTC for ThakurpukurMaheshtala Block (PART) in connection to "Retrofitting of pipeline for FHTC drive including PWD road restoration in connection with pipe water supply scheme including FHTC for CHATTA GP in ThakurpukurMaheshtala Block under South 24 Parganas W/S Division-I, PHE, Dte. [TSM/014924] | AE SWSD-I |  | ORD/000700/2022-2023 | 3509/SWD-I | 17/03/2023 | 60 | M/S. S.S. ENTERPRISE | 40.63 | 0 | 0
1101 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House at Rameswarpur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I |  | ORD/000768/2020-2021 | 2064/SWD-I | 19/02/2021 | 90 | SAMPSON INFRA DESIGN LLP | 8.92 | 8.66 | 100
1102 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000104/2022-2023 | 1230/SWD-I | 07/09/2022 | 30 | DIPALI CONSTRUCTION | 20.07 | 0 | 0
1103 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Harendrapally ( Atniramish, J.L-141) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 910) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000280/2022-2023 | 1842/SWD-I | 11/11/2022 | 900 | A. G. ENTERPRISE | 121.8 | 63.91 | 75
1104 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at HARENDRAPALLY of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000293/2022-2023 | 1787\SWD-I | 07/11/2022 | 60 | SANJAY ENTERPRISE | 5.8 | 0 | 100
1105 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for HARENDRAPALLY PWSS of BARUIPUR Block for under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 323/SWD-I | 11/01/2024 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 20.07 | 18.15 | 100
1106 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000723/2023-2024 | 324/SWD-I | 11/01/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 2.2 | 2.11 | 100
1107 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Harendrapally PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/009671] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000784/2022-2023 | 3674/SWD-I | 29/03/2023 | 15 | DIPALI CONSTRUCTION | 2.2 | 0 | 0
1108 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000074/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 7.02 | 0 | 0
1109 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDANESWAR piped water supply scheme at headwork site (Dag No. 514, Khatian No. 1673, 1674, JL. No. 117, Mouza- Bausahar) & 2nd Tubewell site (Dag No. 1003, Khatian No. 1322, JL No. 117, Mouza- Bausahar), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000165/2022-2023 | 1440/SWD-I | 26/09/2022 | 30 | ABU TALEB MONDAL | 28.51 | 14.12 | 50
1110 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of CHANDANESWAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12044) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000560/2024-2025 | 4233/SWD-I | 30/09/2024 | 361 | RAKHI CONSTRUCTION | 90.69 | 0 | 50
1111 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for CHANDANESWAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2499] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000714/2022-2023 | 3553/SWD-I | 21/03/2023 | 300 | TRISHA CONSTRUCTION | 434.18 | 207.88 | 50
1112 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDANESWAR PWSS at headwork site (Dag No. 514, Khatian No. 1673 & 1674 JL. No. 117, Mouza- Bausahar) & 2nd Tubewell site (Dag No. 1003 Khatian No. 1322, JL No. 117, Mouza- Bausahar) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12044] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 3570/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 1.57 | 50
1113 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000050/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 7.08 | 0 | 0
1114 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000218/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 15.39 | 0 | 0
1115 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at BIRALDHAM NAGAR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014396] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000127/2022-2023 | 1299/SWD-I | 14/09/2022 | 60 | M/S. ARPAN ENTERPRISE. | 10.91 | 4.48 | 50
1116 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for BIRALDHAM NAGAR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000146/2022-2023 | 1377/SWD-I | 20/09/2022 | 30 | CAPITAL CONSTRUCTION | 40.13 | 23.75 | 100
1117 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at BIRALDHAM NAGAR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 848) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000250/2022-2023 | 1738/SWD-I | 03/11/2022 | 90 | SUJATA CONSTRUCTION | 149.78 | 122.28 | 90
1118 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BIRALDHAM NAGAR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000357/2021-2022 | 1959/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.62 | 2.55 | 100
1119 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Biraldham Nagar PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014396] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000790/2022-2023 | 3669/SWD-I | 29/03/2023 | 15 | CAPITAL CONSTRUCTION | 4.4 | 0 | 0
1120 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based BIRALDHAM NAGAR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12213) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000908/2023-2024 | 1207/SWD-I | 11/03/2024 | 45 | S.S. CONSULTANCY & CONSTRUCTION | 26.19 | 0 | 0
1121 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000007/2022-2023 | 1574/SWD-I | 16/10/2022 | 0 | Resource Division | 5.22 | 0 | 0
1122 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000183/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 19.84 | 0 | 0
1123 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of KAMARIA (ZONE-I) MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2051] [TSM/016158] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000171/2023-2024 | 968/SWD-I | 08/06/2023 | 300 | MANASH GHOSH | 397.59 | 0 | 0
1124 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KAMARIA (I) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000361/2021-2022 | 1963/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.56 | 100
1125 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for KAMARIA (Zone-I) PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016158] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000504/2022-2023 | 2893/SWD-I | 13/02/2023 | 30 | PURE RENOVATION GROUP | 31.78 | 30.89 | 100
1126 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000091/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 82.6 | 0 | 0
1127 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kuldia PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014902] | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 40/SWD-I | 06/04/2023 | 15 | MUNNA AGROTECH ENTERPRISE | 3.13 | 0 | 0
1128 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 02 (Two) Pump Houses, one at TW-2 site and other at OHR site of KULDIA PWSS to accommodate FHTC in MAGRAHAT-II block South 24-Pgns District under South 24-Pgns W/S Division-I, P.H.E. Dte. (SM/12802) | Assistant Engineer | Junior Engineer | ORD/000083/2025-2026 | 1758/SWD-I | 02/07/2025 | 60 | KALAM ENTERPRISE | 12.03 | 0 | 0
1129 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Kuldia PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000303/2022-2023 | 1880-SWD-I | 16/11/2022 | 561 | MUNNA AGROTECH ENTERPRISE | 30.02 | 5.89 | 38
1130 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "KULDIA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000395/2022-2023 | 419/SWD-I | 20/05/2022 | 15 | CHAYANIKA ENGINEERING CONSULTANCY | 2.9 | 2.6 | 0
1131 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of Land, Construction of Boundary wall (length = 175.00m) & Construction of Approach Road (length = 50.00m) at Head Work Site for Kuldia PWSS to Accommodate FHTC in Mograhat-II Block under South 24 Pngs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/12802) | Assistant Engineer | Junior Engineer | ORD/000422/2024-2025 | 3750/SWD-I | 28/08/2024 | 45 | J. ENTERPRISE | 50.01 | 0 | 0
1132 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of KULDIA of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1615] (SM/12802) | Assistant Engineer | Junior Engineer | ORD/000583/2024-2025 | 4343/SWD-I | 08/10/2024 | 365 | I.S ENTERPRISE | 372.46 | 0 | 0
1133 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000200/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 18.19 | 0 | 0
1134 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR KHODAHATI PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016076) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000356/2022-2023 | 2263/SWD_I | 15/12/2022 | 30 | SAHI MASUM | 29.69 | 27.59 | 100
1135 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for KHODAHATI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2039] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000530/2022-2023 | 2961/SWD-I | 16/02/2023 | 1050 | G.B. CONSTRUCTION AND CO. | 472.39 | 212.37 | 20
1136 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Temporary approach road construction for entering H/W Site of KHODAHATI Pipe water supply scheme in Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I,PHE.Dte. (TSM/016076) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000536/2023-2024 | 2141/SWD-I | 31/08/2023 | 7 | SAHI MASUM | 0.97 | 0.95 | 100
1137 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KHODAHATI PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13772] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000718/2022-2023 | 3560/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 3.14 | 100
1138 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Walls and others allied works at headwork site and 2nd Tubewell site of KHODAHATI PWSS within Sonarpur Block "KHODAHATI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13772) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000850/2023-2024 | 1300/SWD-I | 15/03/2024 | 45 | G.B. CONSTRUCTION AND CO. (DUMDUM) | 62.99 | 0 | 0
1139 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000024/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 9.54 | 0 | 0
1140 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000235/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.6 | 0 | 0
1141 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway,Drain, Development of Land & others allied works at HW Site of " JAYKRISHNAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13514) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000236/2024-2025 | 2656/SWD-I | 07/06/2024 | 540 | SUSHANTA MANDAL | 46.28 | 0 | 50
1142 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Jaykrishnapur PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015398] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000335/2022-2023 | 2075/SWD-I | 01/12/2022 | 30 | CAPITAL CONSTRUCTION | 30.03 | 14.18 | 58
1143 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for JAYKRISHNAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13514] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000482/2022-2023 | 2811/SWD-I | 02/02/2023 | 15 | CAPITAL CONSTRUCTION | 3.13 | 1.57 | 15
1144 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for JAYKRISHNAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1718] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000528/2022-2023 | 2948/SWD-I | 16/02/2023 | 928 | HARBAUER INDIA PVT. LTD. | 463.9 | 204.9 | 40
1145 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of JAYKRISHNAPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13514) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001142/2024-2025 | 312/SWD-I | 28/01/2025 | 60 | AFRINA ENTERPRISE | 9.61 | 0 | 0
1146 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000020/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 11.94 | 0 | 0
1147 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000233/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.58 | 0 | 0
1148 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 300 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of HANSURI MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2556] [TSM/015218] | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 269/SWD-I | 24/04/2023 | 649 | TUMPA ASSOCIATES | 427.98 | 26.72 | 55
1149 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [WB04G4525] [SM/13985] [w.e.f. 01/06/2025 to 30/11/2025] | Assistant Engineer | Junior Engineer | ORD/000119/2025-2026 | 1436/SWD-I | 28/05/2025 | 183 | AJAY KUMAR | 0.87 | 0 | 0
1150 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for HANSURI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district. [SM/13985][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000684/2022-2023 | 3483/SWD-I | 15/03/2023 | 30 | K.P.D. & SONS. | 31.76 | 0 | 0
1151 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based HANSURI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. | Assistant Engineer | Junior Engineer | ORD/000743/2024-2025 | 4641/SWD-I | 14/11/2024 | 90 | M/S ESSENCE J.V. CONSTRUCTION CO. | 263.03 | 0 | 0
1152 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "HANSURI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000893/2022-2023 | 403/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 2.63 | 100
1153 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [WB04G4525] [SM/13985] [w.e.f. 01/12/2024 to 31/05/2025] | Assistant Engineer | Junior Engineer | ORD/001110/2024-2025 | 4874/SWD-I | 28/11/2024 | 182 | AJAY KUMAR | 0.86 | 1.92 | 11
1154 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000152/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 25.67 | 0 | 0
1155 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional Laying of distribution system including construction of pipe carrying structure for Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14662) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000096/2025-2026 | 1771/SWD-I | 02/07/2025 | 45 | ARNAB KUMAR SARKAR | 28.64 | 0 | 0
1156 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for MARJYADA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/015217] (2nd Call) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000119/2023-2024 | 531/SWD-I | 11/05/2023 | 512 | SHANTI CONSTRUCTION | 47.45 | 22.69 | 34
1157 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based MARJYADA piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14662) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000317/2024-2025 | 3250/SWD-I | 19/07/2024 | 60 | ALOKE KUMAR SARKAR | 46.04 | 0 | 0
1158 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of MARYADA MOUZA of Mograhat-II Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2475] [TSM/015217] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000520/2023-2024 | 2265/SWD-I | 14/09/2023 | 595 | ALOKE KUMAR SARKAR | 506.02 | 250.02 | 50
1159 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Concrete work for Repairing of Road damaged by Laying of pipe line for Proposed Ground water based MARJYADA piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block under South 24-Pgns, Water Supply Division-I, South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/14662) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000673/2024-2025 | 4399/SWD-I | 23/10/2024 | 60 | ARNAB KUMAR SARKAR | 16.78 | 4.44 | 100
1160 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 900mm Dia Double Row Hume Pipe Culvert, Land Development & other allied works at OHR site under Ground water based MARJYADA PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, South 24 Pgns. District for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [SM/14662] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000820/2023-2024 | 1237/SWD-I | 12/03/2024 | 45 | ARNAB KUMAR SARKAR | 23.69 | 0 | 100
1161 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "MARJYADA Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000880/2022-2023 | 414/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 2.77 | 0
1162 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000170/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 29.04 | 0 | 0
1163 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Auliapur to Uttarbhag road,Permanent rsetoration work for 13000 mtr of trench (0.00 Km-5.0 Km(L/S),5.00Km-7.75 Km(B/S), 7.75 km-9.30 Km(R/S), 9.30 Km-9.55 Km(B/S) & 9.55 Km-10.0 Km) Total trench length:13000 mtr cause due to pipe laying work of PHED under South 24 Parganas Division, PWD in the district of South 24 Parganas-During the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00541/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 107.89 | 0 | 0
1164 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (Three nos.) at HARAL piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/14859) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 935/SWD-I | 07/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 13.59 | 0 | 0
1165 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of HARAL MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2089] [TSM/018361] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000027/2023-2024 | 98/SWD-I | 10/04/2023 | 90 | SAMSUL ENTERPRISE | 398.11 | 310.74 | 90
1166 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based HARAL piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/14859) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000229/2024-2025 | 2646/SWD-I | 07/06/2024 | 45 | SAMSUL ENTERPRISE | 50.8 | 0 | 0
1167 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at HARAL Piped Water Supply Scheme to accommodate FHTC in Baruipur Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/14859) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000443/2024-2025 | 3893/SWD-I | 04/09/2024 | 60 | KALPANA BUILDERS (SALTLAKE) | 47.65 | 0 | 0
1168 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based HARAL Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000921/2022-2023 | 1173/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 3.08 | 3.08 | 100
1169 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000147/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 16.72 | 0 | 0
1170 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of HARIHARPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2142] [TSM/017835] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000034/2023-2024 | 120/SWD-I | 12/04/2023 | 1020 | SRI RAM CONSTRUCTION | 464.05 | 36.38 | 70
1171 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipeline protection work, platform fo FHTC, restoration of road after laying of pipeline, development of land and other allied works for Ground water based HARIHARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/14860) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000374/2024-2025 | 3547/SWD-I | 09/08/2024 | 45 | SRI RAM CONSTRUCTION | 77.29 | 0 | 30
1172 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of HARIHARPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000508/2021-2022 | 1910\SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 2.76 | 100
1173 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for HARIHARPUR PWSS of Baruipur block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017835] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000558/2022-2023 | 3050/SWD-I | 20/02/2023 | 30 | DEV & COMPANY (EMAIL ID- DEVANDCOMPANYKOL@GMAIL.COM) | 31.8 | 29.88 | 100
1174 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Hariharpara Piped Water Supply Scheme to accommodate FHTC in Baruipuri Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district | AE BSD,Assistant Engineer | Junior Engineer | ORD/000988/2022-2023 | 1485/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.99 | 2.99 | 100
1175 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000138/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 48.41 | 0 | 0
1176 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.26] | Assistant Engineer | Junior Engineer | BILL/00486/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 10.71 | 0 | 0
1177 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for JAGADISHPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/014216] | Assistant Engineer | Junior Engineer | ORD/000199/2022-2023 | 1547/SWD-I | 12/10/2022 | 30 | M/S SABITA ENTERPRISE | 40.02 | 18.14 | 100
1178 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Construction of 02 (Two) nos. chlorination room at JAGADISHPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014216] | Assistant Engineer | Junior Engineer | ORD/000200/2022-2023 | 1548/SWD-I | 12/10/2022 | 960 | NARAYAN ENTERPRISE | 10.93 | 4.35 | 50
1179 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at JAGADISHPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 859) | Assistant Engineer | Junior Engineer | ORD/000325/2022-2023 | 2024/SWD-I | 29/11/2022 | 906 | A ONE CONSTRUCTION | 149.52 | 107.94 | 90
1180 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Preparation and submission of Detailed Project Report of JAGADISHPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000356/2021-2022 | 1960/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.62 | 2.53 | 100
1181 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for JAGADISHPUR PWSS of BARUIPUR Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/014216] | Assistant Engineer | Junior Engineer | ORD/000450/2023-2024 | 2105/SWD-I | 30/08/2023 | 15 | M/S SABITA ENTERPRISE | 4.4 | 0 | 0
1182 | South 24 Pgs W/S Division I | South 24Pgs.Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000106/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 28.97 | 0 | 0
1183 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 200 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (1 No.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of BRINDAKHALI (Zone-II) Mouza of BARUIPUR Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 1182) [TSM/015225] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000061/2023-2024 | 365/SWD-I | 27/04/2023 | 888 | M/S V.P. JAIN | 335.23 | 248.87 | 94
1184 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for providing FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based BRINDAKHALI ZONE-II Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/13310) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 3313/SWD-I | 23/07/2024 | 45 | M/S V.P. JAIN | 89.54 | 0 | 0
1185 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BRINDAKHALI-II PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13310] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000389/2024-2025 | 3607/SWD-I | 14/08/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.88 | 14.2 | 100
1186 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BRINDAKHALI(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000510/2021-2022 | 1943/SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 2.65 | 100
1187 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BRINDAKHALI-II PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000561/2022-2023 | 3057/SWD-I | 21/02/2023 | 30 | M/S MONDAL ENTERPRISE | 15.88 | 0 | 0
1188 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000128/2022-2023 | 3387/SWD-I | 10/03/2023 | 0 | Resource Division | 7.28 | 0 | 0
1189 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000187/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 1.46 | 0 | 0
1190 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 107.47 | 96
1191 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia & 360 mtr. deep Tubewell having 66 mtr. housing by Rotary method for DHOSA Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I block under South 24-Pgns. W/S Division-I, South 24-Pgns. District for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/16117] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000809/2023-2024 | 1287/SWD-I | 15/03/2024 | 630 | ASHIM SHIL | 38.02 | 16.97 | 100
1192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "DHOSA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000917/2022-2023 | 706/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.56 | 2.55 | 100
1193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000151/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 21.79 | 0 | 0
1194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.32] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00492/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 4.4 | 0 | 0
1195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00544/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 20 | 0 | 0
1196 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for DUDHNAI Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 661] [TSM/017763] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000305/2023-2024 | 1694/SWD-I | 07/08/2023 | 876 | A.G.S. ENTERPRISE | 151.11 | 137 | 100
1197 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based DUDHNAI Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/16118) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000375/2024-2025 | 3548/SWD-I | 09/08/2024 | 494 | A.G.S. ENTERPRISE | 87.42 | 0 | 90
1198 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DUDHNAI PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division-I, P.H.E. Dte. [TSM/017763] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000650/2022-2023 | 3322/SWD-I | 06/03/2023 | 30 | MAHI CONSTRUCTION | 31.77 | 15.29 | 50
1199 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dudhnai Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000940/2022-2023 | 1257/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.5 | 2.46 | 100
1200 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000123/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.32 | 0 | 0
1201 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Jamtala Petkulchand Road from 0.20 to 0.35 km, 4.50 to 6.00 km, 8.20 to 8.50 km, 8.80 to 9.00 km & 12.50 to 13.00 km Restoration of Brick top surface & Saucer drain in different chainage due to laying of pipelines by PHE Department under Lakshmikantapur Highway Sub Division of Diamond Harbour Highway Division in the District of South 24 Parganas. | AE BSD |  | BILL/00640/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 13.26 | 0 | 0
1202 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-III-B ( MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000127/2021-2022 | 2561/SWD-I | 11/03/2022 | 120 | MANASH GHOSH | 626.38 | 103.55 | 91
1203 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of 315 mm diameter (OD) HDPE pipe by Horizontal Directional Drilling (HDD) process for crossing Piyali River at Panchuakhali Bridge in between nodes 8 & 8a within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/16186) | AE BSD |  | ORD/000252/2024-2025 | 2715/SWD-I | 10/06/2024 | 20 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 67.9 | 0 | 100
1204 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIIA (MONDALER LAT) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000360/2021-2022 | 2532/SWD-I | 08/03/2022 | 120 | SUPRITI ENTERPRISE | 808.84 | 365.38 | 85
1205 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap for Augmentation of laying distribution system to extend the benefit of 100% House hold in Zone-III (MONDALER LAT) at KULTALI Block within Mega Surface water based Water Supply scheme of Falta-Mathurapur District South 24 Pgns. under South 24 Pgns Water Supply Division-1, PHE Dte. [TSM : 015332] | AE BSD |  | ORD/000557/2023-2024 | 2585/SWD-I | 13/10/2023 | 300 | M/S LOKENATH CONSTRUCTION | 439.11 | 0 | 0
1206 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Three months trial run for secondary grid D.I pipe lines of different diameters including GLR cleaning for MATHURAPUR-II & KULTALI Block under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-III at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/16186] | AE BSD |  | ORD/000685/2024-2025 | 4480/SWD-I | 30/10/2024 | 90 | CHANDAN ROY | 30.79 | 0 | 0
1207 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Hume Pipe Culvert bridge for the approach road of proposed OHR Site at Zone-VI (Madhya Gurguria) within KULTALI Block under "Augmentation of Laying Distribution System to extend the benefit of 100% Household in ZONE-III at KULTALI Block within Mega Surface Water Based W/S Scheme of Falta-Mathurapur, South 24-Parganas District under South 24 Pgns W/S Division-I, PHE Dte." (SM/16186) | AE BSD |  | ORD/000700/2024-2025 | 4502/SWD-I | 30/10/2024 | 45 | S.S. ENTERPRISE (DAKHIN HAZIPUR) | 10.18 | 0 | 100
1208 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000070/2022-2023 | 2986/SWD-I | 20/02/2023 | 0 | Resource Division | 233.8 | 0 | 0
1209 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2106) (TSM/017116) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 99/SWD-I | 10/04/2023 | 300 | MILAN GHOSH | 488.23 | 122.9 | 15
1210 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15861) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000559/2024-2025 | 4232/SWD-I | 30/09/2024 | 60 | MOLLICK ENTERPRISE | 48.21 | 0 | 0
1211 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for DAKSHIN RAJAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017116] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000637/2022-2023 | 3283/SWD-I | 03/03/2023 | 30 | SAMSUDDIN MANDAL | 31.76 | 29.75 | 100
1212 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of DAKSHIN RAJAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15861) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000877/2024-2025 | 4975/SWD-I | 05/12/2024 | 45 | Grafton Tarmac Engineering And Civil | 11.2 | 0 | 0
1213 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000037/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 27.61 | 0 | 0
1214 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000214/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.97 | 0 | 0
1215 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMNAGAR (PART-II) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1885] [TSM/018217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 112/SWD-I | 11/04/2023 | 720 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 288.53 | 249.37 | 100
1216 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMNAGAR(II) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000404/2021-2022 | 1946/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 2.72 | 0
1217 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providung FHTC, Protection works for Pipeline and other allied Works for ''Proposed Ground Water based RAMNAGAR [ZONE-II] piped water supply schee to accoodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.'' (SM/15634) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000425/2024-2025 | 3752/SWD-I | 28/08/2024 | 45 | SUPER CONSTRUCTION | 72.09 | 0 | 0
1218 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RAMNAGAR (ZONE-II) PWSS to accommodate FHTC in BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000602/2022-2023 | 3125/SWD-I | 24/02/2023 | 30 | SARWAR JAMAN | 31.77 | 15.54 | 50
1219 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000109/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 18.89 | 0 | 0
1220 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of BODRA PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15757) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000039/2025-2026 | 1118/SWD-I | 24/04/2025 | 75 | SARDAR ENTERPRISE | 121 | 0 | 0
1221 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for BODRA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2064) (TSM/017117) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000047/2023-2024 | 254/SWD-I | 20/04/2023 | 957 | SARDAR ENTERPRISE | 455.71 | 195.71 | 20
1222 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BODRA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017117] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000638/2022-2023 | 3284/SWD-I | 03/03/2023 | 30 | M/S MONDAL ENTERPRISE | 31.76 | 0 | 0
1223 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BODRA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/15757) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000666/2024-2025 | 4396/SWD-I | 23/10/2024 | 400 | M/S. SHYAM CONSTRUCTION | 31.05 | 0 | 50
1224 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000036/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 35.63 | 0 | 0
1225 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000213/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.71 | 0 | 0
1226 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed DAKSHIN GOURIPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3883] |  |  | ORD/000315/2023-2024 | 1708/SWD-I | 08/08/2023 | 770 | CE INFRASTRUCTURE | 485.85 | 216.64 | 80
1227 | South 24 Pgs W/S Division I |  | Laying of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, approach road and land development for DAKSHIN GOURIPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/18330) |  |  | ORD/000397/2024-2025 | 3686/SWD-I | 22/08/2024 | 491 | M M ENTERPRISE | 220.68 | 0 | 60
1228 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Dakshin Gouripur Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000950/2022-2023 | 1129/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 2.91 | 2.9 | 100
1229 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 68.93 | 0 | 0
1230 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for Proposed RASHKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 3624] |  |  | ORD/000419/2023-2024 | 1965/SWD-I | 24/08/2023 | 770 | M/S N. H. ENTERPRISE | 448.48 | 98.33 | 20
1231 | South 24 Pgs W/S Division I |  | Laying of rising main and additional pipeline for distribution system, construction of Boundary Wall, pump house, approach road and land development for RASHKHALI Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, PHE Dte. Dist.-South 24-Parganas. (SM/18331) |  |  | ORD/000774/2024-2025 | 4760/SWD-I | 21/11/2024 | 90 | M/S N.H. ENTERPRISE | 208.36 | 0 | 1
1232 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Raskhali Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000947/2022-2023 | 1128/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 2.94 | 2.94 | 100
1233 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 88.83 | 0 | 0
1234 | South 24 Pgs W/S Division I |  | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 01/06/2025 to 30/11/2025] [Vehicle No-WB-09-1333] |  |  | ORD/000060/2025-2026 | 1369/SWD-I | 22/05/2025 | 183 | SUDIP GHOSH | 0.87 | 0 | 0
1235 | South 24 Pgs W/S Division I |  | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 13/06/2024 to 30/11/2024] [Vehicle No-WB-09-1333] |  |  | ORD/000219/2024-2025 | 2572/SWD-I | 04/06/2024 | 171 | SUDIP GHOSH | 0.81 | 2.15 | 0
1236 | South 24 Pgs W/S Division I |  | Retrofitting of old recirculation system of 34 MGD WTP (Civil Part) at Budge Budge II Block Under South 24 Pgns W/S Division-I, P.H.E Dte. |  |  | ORD/000339/2023-2024 | 1608/SWD-I | 31/07/2023 | 75 | S. ROY AND ASSOCIATES | 224.5 | 166.58 | 25
1237 | South 24 Pgs W/S Division I |  | Providing Balance FHTC for Budge Budge-II, Bishnupur-II and Mayapur GP with allied works in connection to Retrofitting and providing FHTC including Special Repair and Rejuvenation of different units of 34 MGD Treatment Plant at Dakshin Roypur for FHTC Drive under Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Pgns. District. [No. of FHTC = 23728] (TSM/014925) |  |  | ORD/000567/2023-2024 | 2649/SWD-I | 27/10/2023 | 90 | WPIL LTD. | 1600.01 | 534.16 | 20
1238 | South 24 Pgs W/S Division I |  | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 16/12/2023 to 12/06/2024] [Vehicle No- WB-09-1333] |  |  | ORD/000762/2023-2024 | 3247/SWD-I | 15/12/2023 | 180 | SUDIP GHOSH | 0.86 | 1.96 | 66
1239 | South 24 Pgs W/S Division I |  | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of Assistant Engineer, Sub-Division-I for monitoring of JJM sites under South 24-Pgns W/S Division-I, PHE Dte. (SM/18253) [w.e.f. 01/12/2024 to 31/05/2025] [Vehicle No-WB-09-1333] |  |  | ORD/000890/2024-2025 | 4877/SWD-I | 29/11/2024 | 182 | SUDIP GHOSH | 0.86 | 2.18 | 0
1240 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 248/SWD-I | 20/04/2023 | 0 | Resource Division | 146.16 | 0 | 0
1241 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE BONHOOGHLY PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I. PHE.DTE. (TSM/016321) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 443/SWD-I | 03/05/2023 | 420 | SARFARAZ CONSTRUCTION | 30.04 | 14.1 | 50
1242 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BONHOOGHLY PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/016321] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 444/SWD-I | 03/05/2023 | 421 | SARFARAZ CONSTRUCTION | 3.14 | 1.57 | 50
1243 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BONHOOGHLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 3040] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 972/SWD-I | 08/06/2023 | 785 | DASGUPTA CONSTRUCTION | 610.86 | 97.04 | 50
1244 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Development of land, Pathway, Drain & others allied works of "BONHOOGHLY Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18225) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000418/2024-2025 | 3739/SWD-I | 27/08/2024 | 45 | M/S SANJAY ADHIKARI | 33.99 | 0 | 0
1245 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000011/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 25.05 | 0 | 0
1246 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000314/2023-2024 | 247/SWD-I | 10/01/2024 | 0 | Resource Division | 18.73 | 0 | 0
1247 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.40] |  |  | BILL/00470/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 39.52 | 0 | 0
1248 | South 24 Pgs W/S Division I |  | Construction of pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for NARAYANPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2308) (TSM/018316) |  |  | ORD/000396/2023-2024 | 1877/SWD-I | 18/08/2023 | 90 | ATCO ENTERPRISE | 380.84 | 198.35 | 45
1249 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) |  |  | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 180 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 14.58 | 60
1250 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of NARAYANPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18547) |  |  | ORD/000704/2024-2025 | 4506/SWD-I | 30/10/2024 | 60 | ATCO ENTERPRISE | 92.01 | 0 | 0
1251 | South 24 Pgs W/S Division I |  | Protection of pipeline of distribution of N.P-300-348, 39-35, 21-14, 13-08, 20-25, 27-37, 37-49, 52-66, 66-32 & 143-182 of Narayanpur Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18547) |  |  | ORD/000828/2023-2024 | 1109/SWD-I | 05/03/2024 | 15 | ATCO ENTERPRISE | 9.78 | 0 | 0
1252 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 23.63 | 0 | 0
1253 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000328/2023-2024 | 258/SWD-I | 10/01/2024 | 0 | Resource Division | 14.22 | 0 | 0
1254 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall, FHTC Platform, approach road, land development, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based CHAK JALSI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 3032/SWD-I | 02/07/2024 | 453 | BASIR CONSTRUCTION | 195.85 | 0 | 22
1255 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Chak Jalsi PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2022-2023 | 1879/SWD-I | 16/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
1256 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "CHAK JALASI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000384/2022-2023 | 413/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 2.62 | 0
1257 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of CHAK JALSI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1611] | Assistant Engineer | Junior Engineer | ORD/000598/2022-2023 | 3126/SWD-I | 24/02/2023 | 708 | MD NURNABI CONSTRUCTION (NUMABISK1992@GMAIL.COM) | 435.58 | 24.47 | 25
1258 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000172/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 22.37 | 0 | 0
1259 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Crossing Of Culvert and Road Crossing at 9(Nine) Different Locations Within Zone -III At Mandir Bazar Block Under augmentation of existing laying distribution system to extend the benefit of 100% households in Zone-III at Mandirbazar Block within ' Mega surface water based water supply scheme for Falta- Mathurapur, district- South 24 Pgns' under South-24 Pgns w/s Divn-i of south 24-pgns. w/s circle, PHE Dte. (SM/15484) | AE HQ-I |  | ORD/000077/2025-2026 | 1580/SWD-I | 11/06/2025 | 45 | SRIJON ENTERPRISE | 36.06 | 0 | 0
1260 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Boundary wall for proposed OHR Site Uttar Akrabaria within Mandirbazar block, Mouza-Uttar Akrabaria under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 397 mtr.) | AE HQ-I |  | ORD/000111/2021-2022 | 1115/SWD-I | 26/10/2021 | 90 | UNITED BUILDERS | 60.18 | 18 | 100
1261 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of pipe lines for distribution system of Zone-VIII in Mandirbazar Block under under Falta-Mathurapur Mega surface based water supply project under South 24-Pgns. W/S Division-I, P.H.E Dte. (SM/03906) | AE HQ-I |  | ORD/000278/2024-2025 | 2926/SWD-I | 25/06/2024 | 301 | M/S LOKENATH BUILDERS | 243.92 | 0 | 55
1262 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of UTTAR AKRABERIA MOUZA in MANDIRBAZAR (ZONE-III) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE HQ-I |  | ORD/000391/2021-2022 | 1985/SWDI | 27/01/2022 | 30 | MS R. DUTTA AND CO | 4.83 | 4.65 | 100
1263 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 1000 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-III at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.7715) | AE HQ-I |  | ORD/000542/2023-2024 | 2461/SWD-I | 04/10/2023 | 607 | SUPRITI ENTERPRISE | 1557.57 | 458.14 | 50
1264 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/10/2023 to 31/03/2024] | AE HQ-I |  | ORD/000582/2023-2024 | 2389/SWD-I | 27/09/2023 | 183 | SUBRAT KUMAR SETHY | 0.87 | 2.19 | 25
1265 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Critical gap negotiation in Secondary Grid along with land development at Zone III at Mandir Bazar Block for AUGMENTATION OF EXISTING LAYING DISTRIBUTION SYSTEM TO EXTEND THE BENEFIT OF 100% HOUSEHOLDS IN ZONE-III AT MANDIRBAZAR BLOCK WITHIN ' MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA- MATHURAPUR, DISTRICT- SOUTH 24 PGNS' UNDER SOUTH-24 PGNS W/S DIVN-I OF SOUTH 24-PGNS. W/S CIRCLE, PHE DTE. (SM/15484) | AE HQ-I |  | ORD/000762/2024-2025 | 4683/SWD-I | 18/11/2024 | 30 | AVIK ENTERPRISE | 7.7 | 0 | 100
1266 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2023 to 30/09/2023] | AE HQ-I |  | ORD/000875/2022-2023 | 3728/SWD-I | 31/03/2023 | 183 | SUBRAT KUMAR SETHY | 0.87 | 1.55 | 50
1267 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cabhaving BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-25J-9045] [w.e.f. 01/10/2024 to 31/03/2025] | AE HQ-I |  | ORD/000884/2024-2025 | 4186/SWD-I | 27/09/2024 | 182 | SUBRAT KUMAR SETHY | 0.86 | 2.29 | 0
1268 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cabhaving BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [w.e.f. 01/04/2024 to 30/09/2024] | AE HQ-I |  | ORD/000904/2023-2024 | 1493/SWD-I | 30/03/2024 | 183 | SUBRAT KUMAR SETHY | 0.87 | 2.36 | 0
1269 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cabhaving BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineers under South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-25J-9045] [w.e.f. 01/04/2025 to 30/09/2025] | AE HQ-I |  | ORD/001206/2024-2025 | 876/SWD-I | 26/03/2025 | 183 | SUBRAT KUMAR SETHY | 0.87 | 0.78 | 0
1270 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000045/2022-2023 | 3016-SWD-I | 20/02/2023 | 0 | Resource Division | 368.04 | 0 | 0
1271 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.23] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00482/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 12.08 | 0 | 0
1272 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Repairing and Renovation of Pumphouse, Office Room, Boundary Wall & allied works at 2nd TW site of Kalikapur PWSS within Sonarpur Block" KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (TSM/014873) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000010/2023-2024 | 34/SWD-I | 05/04/2023 | 60 | SUSHANTA MANDAL | 13.21 | 12.34 | 100
1273 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for OHR site for Sonarpur Block, in support work of Augmentation (part) of balance distribution pipeline (restoration) in different places of Zone-31 (Block-Sonarpur) under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. District. [PART-A, Front side (S), Right side (E) & Back side (N) 240 mtr] (SM/05835) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000256/2022-2023 | 1696/SWD-I | 01/11/2022 | 60 | SUSHANTA MANDAL | 31.72 | 31.56 | 100
1274 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for KALIKAPUR Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. [SM/014837] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000261/2022-2023 | 1773/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 27.24 | 100
1275 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1717] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000525/2022-2023 | 2959/SWD-I | 16/02/2023 | 836 | HARBAUER INDIA PVT. LTD. | 445.06 | 197.74 | 50
1276 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pathway at 2nd site of Kalikapur PWSS within Sonarpur Block in connetion with" KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/12207). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000562/2023-2024 | 2603/SWD-I | 16/10/2023 | 30 | NILKANTHA ENTERPRISE | 4.53 | 4.38 | 100
1277 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fitting, fixing of Barbed wire fencing over existing Boundary wall & Construction of Drain at 2nd Tubewell site of Kalikapur PWSS within Sonarpur Block " KALIKAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/12207) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000668/2023-2024 | 3019/SWD-I | 30/11/2023 | 15 | KALAM ENTERPRISE | 1.89 | 1.79 | 100
1278 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KALIKAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12207] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000773/2022-2023 | 3652/SWD-I | 28/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 3.14 | 100
1279 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000021/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 17.51 | 0 | 0
1280 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000234/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.58 | 0 | 0
1281 | South 24 Pgs W/S Division I |  | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas |  |  | BILL/00638/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0
1282 | South 24 Pgs W/S Division I |  | Payment of Enhanced GST Rate vide W/O No.2484/SWD-I dt. 02/03/2022 |  |  | BILL/01808/2023-2024 | BP-2023-24-637 | 31/01/2024 | 0 | SAMIRON GHOSH | 7.62 | 0 | 0
1283 | South 24 Pgs W/S Division I |  | Construction of development of land, approach road, protection work for pipeline, and other allied works for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-IV at JOYNAGAR-II Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, of South 24-Pgns. W/S Circle, PHE Dte." (SM/18655) |  |  | ORD/000251/2024-2025 | 2649/SWD-I | 07/06/2024 | 270 | P.L. CONSTRUCTION | 46.65 | 2.04 | 45
1284 | South 24 Pgs W/S Division I |  | Laying distribution system of piped water supply at Zone-IV- B (Gardoani) of Joynagar -II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. |  |  | ORD/000453/2021-2022 | 2484/SWD-I | 02/03/2022 | 1200 | SAMIRON GHOSH | 485.75 | 142.23 | 95
1285 | South 24 Pgs W/S Division I |  | Construction of 1500 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile and raft foundation within Zone-IV at Gordoani Mouza of Joynagar-II Block for Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at JOYNAGAR-II block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte. (SM/18655) |  |  | ORD/000695/2023-2024 | 3190\SWD-I | 12/12/2023 | 300 | UNITED BUILDERS | 440.77 | 0 | 0
1286 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 2957/SWD-I | 16/02/2023 | 0 | Resource Division | 121.77 | 0 | 0
1287 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 182.71 | 0 | 0
1288 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000300/2023-2024 | 2437/SWD-I | 30/09/2023 | 0 | Resource Division | 199.31 | 0 | 0
1289 | South 24 Pgs W/S Division I |  | Construction of pipe carrying structure with laying of 610 mm dia M.S. Secondary Rising Main for crossing of Canal at Bakultala Natunhaater Culvert and Nimpith Tulsighata Bridge under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VIII at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/18656] |  |  | ORD/000284/2024-2025 | 3040/SWD-I | 02/07/2024 | 30 | SRIJON ENTERPRISE | 45.72 | 5.31 | 100
1290 | South 24 Pgs W/S Division I |  | Construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap for " Augmentation of laying distribution system to extend the benifit of 100 % Household in ZONE-VIII at JAYNAGAR-II block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist. South 24 Parganas under South 24 Paraganas Water Supply Division-I Division of PHE Dte." (TSM/015336 ) |  |  | ORD/000432/2023-2024 | 2006/SWD-I | 28/08/2023 | 581 | M/S. S.S. ENTERPRISE | 357.14 | 0 | 30
1291 | South 24 Pgs W/S Division I |  | Laying distribution system of piped water supply at Zone-VIII (Nimpith) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. |  |  | ORD/000454/2021-2022 | 2340/SWD-I | 22/02/2022 | 120 | K P CONSTRUCTION | 432.84 | 238.27 | 90
1292 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 126.39 | 0 | 0
1293 | South 24 Pgs W/S Division I |  | Construction of boundary wall & other allied works at Head Work in Zone-VI at Ektara of Mograhat-I block for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-VI AT EKTARA OF MOGRAHAT-I BLOCK within "Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, District- South 24-Parganas" under South 24 Parganas W/S Division-I, PHE Dte. (Total Length-112 mtr excluding Gate) (TSM/014910) |  |  | ORD/000352/2023-2024 | 1738/SWD-I | 10/08/2023 | 60 | NIKHIL SAMADDAR | 18.85 | 15.99 | 1
1294 | South 24 Pgs W/S Division I |  | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-VI at EKTARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-VI at EKTARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 9230 Nos.) |  |  | ORD/000373/2023-2024 | 1782/SWD-I | 11/08/2023 | 300 | CONCORD ENGINEERING | 1862.26 | 453.15 | 55
1295 | South 24 Pgs W/S Division I |  | Land development at Head Work site of EKTARA ZONE-VI PWSS under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Pgns. under South 24-Pgns W/S Divn-I, PHE Dte. (SM/18708) |  |  | ORD/000412/2024-2025 | 3713/SWD-I | 23/08/2024 | 45 | TIYASHA ENTERPRISE | 20.8 | 20.74 | 1
1296 | South 24 Pgs W/S Division I |  | Construction of Platform for FHTC, Additional pipelines for distribution system, Protection of pipeline, Approach road and construction of Chlorination Room for Augmentation of existing laying distribution system and allied works to extend the benifit of 100% Household in Zone-VI at Ektara under Magrahat-I Block within Mega surface Water based water supply scheme of Falta-Mathurapur,Dist. S-24 pgns under South 24 parganas W/S Division-I, P.H.E Dte. (SM/18708) |  |  | ORD/000537/2024-2025 | 4093/SWD-I | 20/09/2024 | 90 | CONCORD ENGINEERING | 319.66 | 0 | 0
1297 | South 24 Pgs W/S Division I |  | Supplying, fabrication & laying of 700 mm dia (ID) MS Pipe conduits 72 mtr. in length to be prepared from 12 mm thick MS Plate by pipe jacking technique, including supplying and laying of 250 mm dia (ID) MS water supply pipe line within the conduit 90 mtr. in length to be prepared from 06 mm thick MS Plate across and underneath the Railway Track in between mast no-50/11, 50/13 and mast no-50/12, 56/14 in between Deula Station and Netra Stations on Baruipur - Diamond Harbour Section as per permission obtained from Railway Authority, including construction of Drive Pit & Receiving Pit, as requred, for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-VI at Mograhat-I Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/03906) |  |  | ORD/000499/2022-2023 | 2868/SWD-I | 09/02/2023 | 60 | S. ROY AND ASSOCIATES | 76.87 | 76.87 | 100
1298 | South 24 Pgs W/S Division I |  | Construction of Balance portion of Boundary Wall for EKTARA ZONE-VI PWSS under Augmentation of existing laying distribution system including new OHR and allied works to extend the benefit of 100% Household in ZONE-VI at EKTARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Pgns. under South 24-Pgns W/S Divn-I, PHE Dte. (SM/18708) [2nd call] |  |  | ORD/001119/2024-2025 | 155/SWD-I | 15/01/2025 | 30 | NIKHIL SAMADDAR | 12.03 | 0 | 0
1299 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 8.27 | 0 | 0
1300 | South 24 Pgs W/S Division I |  | Land development at 3rd Tubewell site and approach road of Kannyanagar PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgs. W/S Divn.-I, P.H.E. Dte., for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (SM/18574) |  |  | ORD/000005/2025-2026 | 908/SWD-I | 02/04/2025 | 30 | CHANDAN ROY | 4.71 | 0 | 0
1301 | South 24 Pgs W/S Division I |  | Construction of 2 nos. (4.80 Mtr. X 3.66 Mtr.) PUMP HOUSE with water supply and sanitary arrangement (as per Deptt. drawing) for 2nd and 3rd tubewell sites of KANNYANAGAR PIPE WATER SUPPLY SCHEME to accommodate FHTC in Bishnupur-I Block under South 24 Pgns. W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in Arsenic affected areas of South 24-Pgs. Dist. [SM/18574] |  |  | ORD/000032/2025-2026 | 983/SWD-I | 09/04/2025 | 60 | GLOBAL CONSTRUCTION | 11.5 | 0 | 0
1302 | South 24 Pgs W/S Division I |  | Construction of boundary wall, approach road, laying of rising main and other allied works for KANYANAGAR PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/12234] |  |  | ORD/000250/2024-2025 | 2670/SWD-I | 07/06/2024 | 45 | CHANDAN ROY | 96.96 | 0 | 0
1303 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second & Third Tubewell site for KANNYANAGAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018432] |  |  | ORD/000358/2023-2024 | 1744/SWD-I | 10/08/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 0
1304 | South 24 Pgs W/S Division I |  | Construction of boundary wall & other allied works at Head Work Site of KANNYANAGAR PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018432] |  |  | ORD/000415/2023-2024 | 1959/SWD-I | 24/08/2023 | 60 | T. K. ENTERPRISE | 18.3 | 0 | 0
1305 | South 24 Pgs W/S Division I |  | Construction of 03 (three) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for KANNYANAGAR, BAGI & BHANDARIA PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018432, TSM/017332, TSM/017323] |  |  | ORD/000422/2023-2024 | 1969/SWD-I | 24/08/2023 | 300 | H. T. R. CONSTRUCTION | 572.68 | 0 | 0
1306 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of KANNYANAGAR PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 4562) [TSM/018432]. |  |  | ORD/000427/2023-2024 | 1987/SWD-I | 25/08/2023 | 676 | DEBAPRASAD MONDAL | 527.21 | 0 | 45
1307 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Kannyanagar Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000962/2022-2023 | 1166/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.92 | 2.92 | 100
1308 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000098/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 49.9 | 0 | 0
1309 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BHAGABANPUR PWSS within Sonarpur Block "BHAGABANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18575) |  |  | ORD/000231/2024-2025 | 2651/SWD-I | 07/06/2024 | 360 | MOTIONMASS TECHNO OPC PVT LTD | 12.17 | 0 | 50
1310 | South 24 Pgs W/S Division I |  | Construction of Platform for providing FHTC for Ground water based BHAGABANPUR piped water supply scheme to accommadate FHTC in Sonarpur block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18575) |  |  | ORD/000331/2024-2025 | 3269/SWD-I | 22/07/2024 | 60 | KALIPADA JANA | 56.68 | 0 | 0
1311 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BHAGABANPUR PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017739] |  |  | ORD/000370/2023-2024 | 1779/SWD-I | 11/08/2023 | 15 | DEBASHIS DAS | 31.76 | 29.92 | 100
1312 | South 24 Pgs W/S Division I |  | Construction of 400 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for BHAGABANPUR Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 3047) (TSM/017739) |  |  | ORD/000384/2023-2024 | 1820/SWD-I | 16/08/2023 | 685 | GARAI INFRA PROJECT | 628.07 | 414.87 | 25
1313 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Pathway, Drain, development of land & others allied works at headwork site of BHAGABANPUR PWSS within Sonarpur Block "BHAGABANPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18575) |  |  | ORD/000817/2023-2024 | 1310/SWD-I | 15/03/2024 | 405 | TOJO ENTERPRISE | 37.21 | 3.31 | 20
1314 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 21.59 | 0 | 0
1315 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000318/2023-2024 | 248/SWD-I | 10/01/2024 | 0 | Resource Division | 18.77 | 0 | 0
1316 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BISHWESHWAR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017284] |  |  | ORD/000364/2023-2024 | 1773/SWD-I | 11/08/2023 | 30 | JYOTY SOLAR POWER (EMAIL ID-INFO.JYOTYSOLARPOWER@GMAIL.COM) | 31.79 | 30.95 | 100
1317 | South 24 Pgs W/S Division I |  | Construction of Boundary wall, FHTC Platform, approach road, land development, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based BISHWESHWARPUR piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of aurface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18678) |  |  | ORD/000384/2024-2025 | 3575/SWD-I | 12/08/2024 | 383 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 241.51 | 0 | 15
1318 | South 24 Pgs W/S Division I |  | Construction of 01 (one) no. 350 Cum capacity 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 02 (two) nos. chlorination room of size 5.0m x 4.0m for BISHWESHWARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 2530] [TSM/017284] |  |  | ORD/000507/2023-2024 | 2221/SWD-I | 12/09/2023 | 781 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 646.17 | 150.9 | 45
1319 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Bishweshwarpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000981/2022-2023 | 1455/SWD-I | 26/09/2022 | 30 | GEO SOLUTION | 2.8 | 2.75 | 100
1320 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000136/2022-2023 | 3395/SWD-I | 10/03/2023 | 0 | Resource Division | 15.58 | 0 | 0
1321 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 32.9 | 0 | 0
1322 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tubewell by Rotary method for MALLICKPUR (Part-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte., within South 24 Parganas District under JJM. [AAFS - GO22223004569PH] [Project ID- PH222355766S000] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000069/2022-2023 | 1114/SWD-I | 23/08/2022 | 1200 | PADMA ENGINEERING CO. | 20.08 | 0 | 100
1323 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MALLIKPUR, PART-I Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000222/2021-2022 | 1958/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.62 | 2.51 | 100
1324 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at Mallickpur (Mallickpur C.T, J.L- 10) of Baruipur Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (PART-I) (No. of FHTC = 813) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 1799/SWD-I | 09/11/2022 | 90 | DIPALI CONSTRUCTION | 102.68 | 0 | 0
1325 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Mallikpur (I) PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24- Parganas W/S Division- I, P.H.E. Dte. [TSM/009674] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000800/2022-2023 | 3672/SWD-I | 29/03/2023 | 960 | PADMA ENGINEERING CO. | 2.2 | 0 | 100
1326 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000184/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 5.99 | 0 | 0
1327 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHARAGHATA Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1857) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000273/2022-2023 | 1806/SWD-I | 09/11/2022 | 900 | PATH MAKERS | 485.76 | 472.21 | 100
1328 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Charaghata of Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000377/2022-2023 | 2211/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 0 | 0
1329 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHARAGHATA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000449/2021-2022 | 1961/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.74 | 100
1330 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of Irrigation embankment road for Ground water based CHARAGHATA Piped Water Based Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns. W/S Division-I, P.H.E Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/11787) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000795/2023-2024 | 1143/SWD-I | 07/03/2024 | 30 | L.N. ENTERPRISE | 24.27 | 24.1 | 100
1331 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for laying distribution system, at CHARAGHATA PWSS of JOYNAGAR-I Block, for implementation of surface water based W/S scheme in the arsenic affected areas of South 24-Parganas district under Baruipur Sub-Division of South 24-Pgns, W/S Division-I, P.H.E. Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 1136/SWD-I | 06/03/2024 | 60 | PATH MAKERS | 34.21 | 29.09 | 100
1332 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 no. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHARAGHATA Piped Water Supply Scheme to accommodate FHTC in JOYNAGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/11787] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001123/2024-2025 | 157/SWD-I | 15/01/2025 | 30 | ANCHAR ALI GHORAMI | 19.11 | 0 | 0
1333 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000076/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 142.64 | 0 | 0
1334 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration charges on Amtala Baruipur Road due to laying of HDPE of 50% of estimate value i.e. 4357850 x 50% = 217893 as per minutes of meeting with Hon'ble MIC. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/00289/2022-2023 | BP-2022-23-223 | 09/03/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 2.18 | 0 | 0
1335 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Payment for Initial 50% Amount of the Estimated cost Rs. 1791575.00 (Seventeen Lakh Ninety One Thousand Five Hundred Seventy Five Only) i.e Rs. 895788.00 ( Eight Lakh Ninty Five Thousand Seven Hundred Eighty Eight only). Towards Road Restoration work for damages due to Laying of HDPE pipe line near Chainage 6.300 kmp to 7.300kmp of Amtala Baruipur road in the district of s24 parganas under ground water based Jalilpur PWSS to accommodate FHTC in Bishnupur I block under SWD-I PHE.Dte (TSM/011226,SM/11988) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | BILL/00652/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 8.96 | 0 | 0
1336 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig Ground bored 150mm x 100 mm dia. & 300 mtr. deep Tubewell by Rotary method for JALILPUR PWSS of BISHNUPUR-I Block Under South 24 Paraganas W/S Division-I, P.H.E Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000166/2022-2023 | 1345/SWD-I | 19/09/2022 | 30 | ANANTA KUMAR GIRI | 9.65 | 8.83 | 100
1337 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed JALILPUR PWSS in Arsenic affected areas of South 24 Pgs. Dist in BISHNUPUR-I Block, under South 24 Pgs W/S Division - I, PHE Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000168/2022-2023 | 1346/SWD-I | 19/09/2022 | 986 | GROWING CONCERN | 53.19 | 41.99 | 99
1338 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at second tubewell site for JALILPUR Piped Water Supply Scheme OF BISHNUPUR-I Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011226] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000202/2023-2024 | 1386/SWD-I | 12/07/2023 | 30 | MONA CONSTRUCTION | 15.87 | 0 | 0
1339 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1340 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for JALILPUR Piped Water Supply Scheme of Bishnupur-I Block under South 24-Pgns. W/S Division-I, Dist.-South 24-Pgns. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000326/2022-2023 | 2026/SWD-I | 29/11/2022 | 60 | MONDAL PRECISION PVT. LTD. | 122.11 | 109.9 | 90
1341 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "JALILPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000401/2022-2023 | 461/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.44 | 2.42 | 100
1342 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying additional pipeline of distribution system with laying of rising main from 2nd tubewell site for JALILPUR PWSS to accommondate FHTC in BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000512/2024-2025 | 3980/SWD-I | 11/09/2024 | 30 | S.P. ENTERPRISE | 13.77 | 1.44 | 80
1343 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall and Pump House at 2nd tubewell site for JALILPUR PWSS of BISHNUPUR-I Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/11988) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000518/2024-2025 | 3981/SWD-I | 11/09/2024 | 60 | S. DAS ENTERPRISE | 12.61 | 0 | 1
1344 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Providing Additional FHTC, C.C base of existing and new FHTC and restoration of damaged concrete road at JALILPUR PWSS in Arsenic affected areas of South 24 pargans District in Bishnupur-I Block, under South 24 pgs W/S Division-I, P.H.E Dte. (New FHTC =60 nos) [Scheme Code: SM/11988] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000545/2023-2024 | 2493/SWD-I | 06/10/2023 | 631 | S.P. ENTERPRISE | 6.99 | 6.83 | 80
1345 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 150mm x 100mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for JALILPUR PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Divn-I, P.H.E. Dte. [TSM/011226][2nd Call] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000687/2022-2023 | 3486/SWD-I | 15/03/2023 | 30 | MD. IFTIKAR HASAN | 10.6 | 0 | 0
1346 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000016/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 3.34 | 0 | 0
1347 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000105/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 16.97 | 0 | 0
1348 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance of Retrofitting of distribution system for Uttar Roypur W/S Scheme for Booth 153 to 169 under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000039/2022-2023 | 977/SWD-I | 27/07/2022 | 45 | CALCON CONSTRUCTIONS | 15.8 | 0 | 100
1349 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6134 ) PART-VI | AE SWSD-I |  | ORD/000466/2022-2023 | 2775/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 2.72 | 2.71 | 100
1350 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No: 197 to 198) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000157/2021-2022 | 1101/SWD-I | 25/10/2021 | 120 | NIRMAL UDYOG | 38.2 | 33.73 | 90
1351 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning road, permanent restoration work for 5800 mtr of trench(0.00 Km-1.2 Km, 1.70 K.m-2.50 Km & 3.50Km-4.40 Km) Total trench length=5800 Mtr cause due to pipe laying work of PHED under South Parganas Division, PWD in the District of South 24 Parganas-During the year 2024-2025. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00542/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 75 | 0 | 0
1352 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for KURULI PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000077/2022-2023 | 1188/SWD-I | 02/09/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 25.61 | 100
1353 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KURULI Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000221/2021-2022 | 1938/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.69 | 100
1354 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KURULI Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1516) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000276/2022-2023 | 1807/SWD-I | 09/11/2022 | 300 | SE TILES MANUFACTURING COMPANY PRIVATE LIMITED | 392.81 | 211.25 | 82
1355 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Kuruli at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000362/2022-2023 | 2205/SWD-I | 13/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 11.52 | 10.03 | 100
1356 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls including development of land and other allied works for Ground water based KURULI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11500) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000392/2024-2025 | 3640/SWD-I | 20/08/2024 | 45 | SE TILES MANUFACTURING COMPANY PRIVATE LIMITED | 45.6 | 0 | 0
1357 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for KURULI PWSS of BARUIPUR Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/011008] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000448/2023-2024 | 2103/SWD-I | 30/08/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 3.14 | 100
1358 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000009/2022-2023 | 1574/SWD-I | 16/10/2022 | 0 | Resource Division | 9.34 | 0 | 0
1359 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000081/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 4.14 | 0 | 0
1360 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JAYATALA PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000075/2022-2023 | 1186/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 28.52 | 24.79 | 100
1361 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of JOYATALA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000219/2021-2022 | 1941/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.72 | 100
1362 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JAYATALA Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1419) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000272/2022-2023 | 1805/SWD-I | 09/11/2022 | 900 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 415.42 | 53.57 | 50
1363 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Jayatala at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000360/2022-2023 | 2203/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 9.74 | 100
1364 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of JAYATALA PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [SM/11501] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000551/2023-2024 | 2499/SWD-I | 06/10/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
1365 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000010/2022-2023 | 1574/SWD-I | 16/10/2022 | 0 | Resource Division | 8.74 | 0 | 0
1366 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000083/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 2.66 | 0 | 0
1367 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III B at Beladurganagar mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC= 3903] | AE BSD |  | ORD/000269/2023-2024 | 1549/SWD-I | 25/07/2023 | 120 | AJIT PRAMANICK | 294.9 | 69.1 | 40
1368 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-III A at Beladurganagar mouza of Joynagar-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3828] | AE BSD |  | ORD/000271/2023-2024 | 1551/SWD-I | 25/07/2023 | 120 | M/S LOKENATH CONSTRUCTION | 289.12 | 0 | 0
1369 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000080/2022-2023 | 2996/SWD-I | 20/02/2023 | 0 | Resource Division | 47.62 | 0 | 0
1370 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-VII NOLGORA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 11912] [TSM/011554] and [TSM/015335] 124076810.5 | AE BSD |  | ORD/000260/2023-2024 | 1515/SWD-I | 21/07/2023 | 894 | MRA NIRMAN UDYOG | 1590.17 | 102.94 | 65
1371 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Laying distribution system at Zone-VII (NOLGORA) of JOYNAGAR-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte.(SM/ 11770 , SM/16183) | AE BSD |  | ORD/000364/2024-2025 | 3511/SWD-I | 07/08/2024 | 327 | MRA NIRMAN UDYOG | 434.23 | 36.81 | 40
1372 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000084/2022-2023 | 3000/SWD-I | 20/02/2023 | 0 | Resource Division | 73.38 | 0 | 0
1373 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Road Restoration and Bullah Piling work for laying of distribution pipes between node point from 1 to 2, 2 to 59, 59 to 60, 60 to 61, 61 to 62, 62 to 63, 63 to 64, 64 to 65 for Laying Distribution System to extend the benefit of 100% FHTC at Mandirbazar Block in Zone X within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. [SM/11237] | AE HQ-I |  | ORD/000521/2024-2025 | 4014/SWD-I | 13/09/2024 | 136 | BISWAS CONSTRUCTION | 42.19 | 0 | 50
1374 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-X at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5689] | AE HQ-I |  | ORD/000616/2022-2023 | 3216/SWD-I | 28/02/2023 | 763 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 379.55 | 12.07 | 30
1375 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000060/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 35.04 | 0 | 0
1376 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum OHR , Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-IV at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2270) | AE HQ-I |  | ORD/000712/2022-2023 | 3528/SWD-I | 17/03/2023 | 300 | SUPER SKILL | 458.61 | 60 | 25
1377 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000053/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 13.98 | 0 | 0
1378 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for JELERHAT PWSS of Baruipur Block Under South 24 Paraganas W/S Division-I, PHE Dte. [TSM/011011] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000216/2022-2023 | 1593/SWD-I | 17/10/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 4.04 | 10
1379 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of JELERHAT Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000220/2021-2022 | 1936/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.69 | 0
1380 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Jelerhat at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000365/2022-2023 | 2208/SWD-I | 13/12/2022 | 60 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 11.52 | 0 | 0
1381 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Jelerhat PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011011] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000724/2022-2023 | 3573/SWD-I | 22/03/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 0 | 0
1382 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at JELERHAT Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1675) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000739/2022-2023 | 3592/SWD-I | 23/03/2023 | 300 | THE UNICON ENGINEERS | 422.87 | 259.26 | 70
1383 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method having 66 mtr. housing pipe for JELERHAT Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12636] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001155/2024-2025 | 373/SWD-I | 04/02/2025 | 30 | RAJKUMAR MONDAL | 15.9 | 0 | 0
1384 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000333/2023-2024 | 266/SWD-I | 10/01/2024 | 0 | Resource Division | 10.32 | 0 | 0
1385 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at Head works site at JALGHARA Zone-X/A of Magrahat-I Block for Providing 100% FHTC in Zone-X/A at Jal Ghara mouza of Mograhat-I Block within "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District- South 24-Pgns." under South 24-Pgns W/S Division-I, PHE Dte. (SM/11263) | Assistant Engineer | JE2 | ORD/000531/2024-2025 | 4077/SWD-I | 19/09/2024 | 15 | SRIJON ENTERPRISE | 37.44 | 37.32 | 90
1386 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1250 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/A AT JALGHARA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/A AT JALGHARA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Total Number of FHTC ¿ 9256 Nos.) | Assistant Engineer | JE2 | ORD/000804/2022-2023 | 3695/SWD-I | 30/03/2023 | 734 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 1210.7 | 91.64 | 25
1387 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000143/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 57.02 | 0 | 0
1388 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Purba Gabberia Zone-II PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 42/SWD-I | 06/04/2023 | 15 | M/S. S M ENTERPRISE | 4.4 | 0 | 0
1389 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PURBA GABBERIA (Zone-II) PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 1232/SWD-I | 07/09/2022 | 30 | M/S. S M ENTERPRISE | 40.13 | 5.44 | 12
1390 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PURBA GABBERIA (Zone-II) of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000158/2022-2023 | 1411/SWD-I | 22/09/2022 | 60 | ANANDA MAITY | 11.01 | 0 | 100
1391 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PURBA GABBERIA(II) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000363/2021-2022 | 1930/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
1392 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at PURBO GABBERIA (Zone-II) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2086) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000372/2022-2023 | 2316/SWD-I | 19/12/2022 | 900 | M/S. S.S. ENTERPRISE | 662.96 | 305.17 | 65
1393 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000070/2023-2024 | 292/SWD-I | 24/04/2023 | 0 | Resource Division | 76.13 | 0 | 0
1394 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at CHAMPAHATI Zone-I of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000154/2022-2023 | 1407/SWD-I | 22/09/2022 | 60 | M/S P. PURKAIT ENTERPRISE. | 10.95 | 0 | 0
1395 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHAMPAHATI Zone-I PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000225/2022-2023 | 1683/SWD-I | 01/11/2022 | 30 | K P CONSTRUCTION | 42.29 | 37.58 | 100
1396 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHAMPAHATI(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000451/2021-2022 | 1953/SWD_I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.44 | 100
1397 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at CHAMPAHATI Zone-I Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 918) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000738/2022-2023 | 3591/SWD-I | 23/03/2023 | 300 | M/S SUMAN SHIL | 226.66 | 23.04 | 30
1398 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Champahati-I PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/010744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000783/2022-2023 | 3666/SWD-I | 29/03/2023 | 15 | K P CONSTRUCTION | 4.41 | 4.39 | 100
1399 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform Development of Land, Pipeline Protection Work and others allied works Ground Water Based CHAMPAHATI ZONE-I PWSS to accommodate FHTC in BARUIPUR Block under South 24 Pgns W/S Divn-I PHE Dte for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District. [SM/11278] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000791/2024-2025 | 4842/SWD-I | 27/11/2024 | 60 | SANKAR MONDAL | 73.66 | 0 | 30
1400 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000181/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 17.75 | 0 | 0
1401 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for DHANBERIA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000090/2022-2023 | 1202/SWD-I | 02/09/2022 | 30 | PAPPU ENTERPRISE | 20.06 | 17 | 100
1402 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at DHANBERIA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012518] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000122/2022-2023 | 1290/SWD-I | 14/09/2022 | 60 | LAKSHMI IRON | 5.44 | 4.1 | 100
1403 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DHANBERIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000166/2021-2022 | 1916/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 2.56 | 100
1404 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at DHANBERIA of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 209) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000312/2022-2023 | 1953/SWD-I | 22/11/2022 | 90 | M/S ASHIRBAD (INDIA) | 127.29 | 19.27 | 18
1405 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 01 (One) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for DHANBERIA PWSS of BARUIPUR Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/012518] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000453/2023-2024 | 2108/SWD-I | 30/08/2023 | 15 | PAPPU ENTERPRISE | 2.2 | 2.11 | 100
1406 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000104/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
1407 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.30] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00490/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 16.53 | 0 | 0
1408 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for DAKSHIN SASAN PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000091/2022-2023 | 1203/SWD-I | 02/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 34.42 | 100
1409 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at DAKSHIN SASAN of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012622] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000121/2022-2023 | 1289/SWD-I | 14/09/2022 | 60 | M/S. ARPAN ENTERPRISE. | 10.88 | 8.7 | 100
1410 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DAKSHIN SASAN Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000170/2021-2022 | 1917/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.76 | 100
1411 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at DAKSHIN SASAN of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1759) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000239/2022-2023 | 1726/SWD-I | 03/11/2022 | 120 | PRASUN ENTERPRISE | 342.27 | 167.16 | 60
1412 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Platform for providing FHTC, Protection works for pipeline and other allied works for Proposed Ground Water based DAKSHIN SASAN piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12057) (2nd call) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000730/2024-2025 | 4617/SWD-I | 13/11/2024 | 90 | MUNNA AGROTECH ENTERPRISE | 75.82 | 0 | 40
1413 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Dakshin Sasan PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/012622] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000797/2022-2023 | 3679/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 4.23 | 100
1414 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000268/2023-2024 | 2420/SWD-I | 30/09/2023 | 0 | Resource Division | 112.13 | 0 | 0
1415 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000338/2023-2024 | 263/SWD-I | 10/01/2024 | 0 | Resource Division | 10.84 | 0 | 0
1416 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for KASHINATHPUR piped water supply scheme at headwork site (Dag No. 1562, Khatian No. 2581, JL. No. 115, Mouza- Kashinathpur) & 2nd Tubewell site (Dag No. 1300, Khatian No. 1361 , JL No. 115, Mouza- Kashinathpur), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000171/2022-2023 | 1442/SWD-I | 26/09/2022 | 30 | ABU TALEB MONDAL | 28.51 | 0 | 50
1417 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Kashinathpur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2255] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000395/2023-2024 | 1878/SWD-I | 18/08/2023 | 300 | SAMSUL ENTERPRISE | 486.03 | 141.11 | 40
1418 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of KASHINATHPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12016) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000565/2024-2025 | 4238/SWD-I | 30/09/2024 | 60 | SAMSUL ENTERPRISE | 89.07 | 0 | 0
1419 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KASHINATHPUR PWSS at headwork site (Dag No. 1562, Khatian No. 2581, JL. No. 115, Mouza- Kashinathpur) & 2nd Tube-well site (Dag No. 1300 Khatian No. 1361, JL No. 115, Mouza- Kashinathpur) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12016] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000737/2022-2023 | 3567/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 0 | 50
1420 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000056/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 47.08 | 0 | 0
1421 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000247/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 13.89 | 0 | 0
1422 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-VII at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 9193] | AE HQ-I |  | ORD/000053/2023-2024 | 272/SWD-I | 24/04/2023 | 708 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 591.54 | 79.39 | 35
1423 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supply of various D.I. fittings of different diameters for laying of pipeline in connection Providing Functional Household Tap Connection (FHTC) in Zone-VII at Mandirbazar block within ' Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns' under South-24 Pgns W/S Divn-I, P.H.E Dte. (SM/11235) | AE HQ-I |  | ORD/000348/2024-2025 | 3377/SWD-I | 27/07/2024 | 30 | B.S. RUBBER INDUSTRIES | 11.6 | 11.6 | 100
1424 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000057/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 56.63 | 0 | 0
1425 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia& 300 mtr. deepTubewell by Rotary method for Padmerhat PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/011744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000102/2022-2023 | 1234/SWD-I | 07/09/2022 | 30 | SAIKAT ENTERPRISE | 28.4 | 25.67 | 100
1426 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 01 No. 300 Cum. capacity OHR and 02 Nos. 350 Cum capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of JANGALIA, MASTIKARI and PADMERHAT MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 5561] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 1374/SWD-I | 12/07/2023 | 900 | KAR CONSTRUCTION | 1262.63 | 169.51 | 30
1427 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "PADMERHAT Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000387/2022-2023 | 469/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.65 | 2.63 | 100
1428 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Padmerhat PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011744] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000725/2022-2023 | 3571/SWD-I | 22/03/2023 | 15 | SAIKAT ENTERPRISE | 3.14 | 3.14 | 0
1429 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based PADMERHAT Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/11780) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000864/2023-2024 | 1200/SWD-I | 11/03/2024 | 45 | BENGAL BUILDERS | 53.81 | 0 | 0
1430 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000157/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 41.81 | 0 | 0
1431 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for SAPHKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11781] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000176/2022-2023 | 1451/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.27 | 12.44 | 100
1432 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
1433 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "SAPKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000399/2022-2023 | 468/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.51 | 2.51 | 100
1434 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based SAPHKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 868 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000418/2022-2023 | 2472/SWD-I | 30/12/2022 | 823 | MERCANTILE HALL | 103.26 | 79.81 | 90
1435 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of SAPHKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11781) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000446/2022-2023 | 2665/SWD-I | 18/01/2023 | 60 | M/S. TORSA ENTERPRISE | 6.04 | 5.87 | 100
1436 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, pump house, restoration of road, laying of additional pipeline and other allied works for SAPKHALI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11781] [2nd call] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000506/2024-2025 | 3963/SWD-I | 10/09/2024 | 264 | SUKUMAR DEBNATH | 48 | 0 | 80
1437 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SAPKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011741] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000522/2022-2023 | 2912/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 100
1438 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for SAPKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011741] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000584/2022-2023 | 3105/SWD-I | 24/02/2023 | 650 | MOULI CONSTRUCTION | 15.88 | 5.1 | 98
1439 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Repairing of R.C.C. elevated reservoir (1135 Cum capacity) of staging height 20.0 mtr. of ZONE-14 under ground water based SAPKHALI PWSS to Accommodate FHTC in Bishnupur-I Block under South 24-Pgs. W/S Divn.-I, P.H.E. Dte. for augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. [SM/11781] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000622/2023-2024 | 2805/SWD-I | 09/11/2023 | 45 | NIKHIL SAMADDAR | 17.95 | 17.06 | 98
1440 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Balance portion of LDS at Sapkhali PWSS under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in Bishnupur-I Block within South 24-Pgs. W/S Divn.-I, P.H.E. Dte., South 24-Pgs. Dist. [Scheme code: SM/11781][2nd call] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000724/2023-2024 | 398/SWD-I | 18/01/2024 | 15 | T.T. ENTERPRISE (PANIHATI) | 7.77 | 7.73 | 99
1441 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000026/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.35 | 0 | 0
1442 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000102/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 25.83 | 0 | 0
1443 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Providing protection work of drum sheet walling along with other allied works for the construction of the Boundary Wall at 1st Tubewell site of Chak Nurshikdar PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division-I, P.H.E. Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District [SM/11782] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000003/2025-2026 | 906/SWD-I | 02/04/2025 | 30 | CONCORD PROJECTS PRIVATE LIMITED | 3.33 | 0 | 75
1444 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000181/2023-2024 | 773/SWD-I | 31/05/2023 | 183 | AHMED REZA | 0.87 | 2.39 | 30
1445 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1446 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2024 to 30/11/2024) [Vehicle NoWB-11D-3607] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000220/2024-2025 | 2449/SWD-I | 24/05/2024 | 183 | AHMED REZA | 0.87 | 2.4 | 0
1447 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of CHAK NURSHIKDAR AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000229/2021-2022 | 1978/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.55 | 2.55 | 100
1448 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for CHAK NURSHIKDAR Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11782] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000231/2022-2023 | 1681/SWD-I | 01/11/2022 | 30 | KUNTAL CHOWDHURY | 14.89 | 14.51 | 100
1449 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump hopuse, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for CHAK NURSIKDER PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11782] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000246/2024-2025 | 2666/SWD-I | 07/06/2024 | 496 | SRIJON ENTERPRISE | 71.67 | 0 | 50
1450 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based CHAK NURSHIKDAR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 865 nos.] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000415/2022-2023 | 2469/SWD_I | 30/12/2022 | 90 | SANJUKTA ENGINEERS. | 138.64 | 91.85 | 92
1451 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of CHAK NURSHIKDAR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11782) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000441/2022-2023 | 2660/SWD-I | 18/01/2023 | 60 | M/S. TORSA ENTERPRISE | 6.04 | 6 | 100
1452 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for CHAK NURSHIKDAR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011738] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000592/2022-2023 | 3112/SWD-I | 24/02/2023 | 727 | DEBASHIS DAS | 15.87 | 12.37 | 98
1453 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/12/2023 to 31/05/2024) [Vehicle No- WB-11D-3607] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000674/2023-2024 | 2999/SWD-I | 29/11/2023 | 183 | AHMED REZA | 0.87 | 2.4 | 90
1454 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/12/2024 to 31/05/2025) [Vehicle NoWB-11D-3607] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001061/2024-2025 | 4878/SWD-I | 29/11/2024 | 182 | AHMED REZA | 0.86 | 2.4 | 1
1455 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000028/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.33 | 0 | 0
1456 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000099/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.32 | 0 | 0
1457 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 30.08 | 20
1458 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KRISHNARAMPUR Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11789] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000229/2022-2023 | 1680/SWD-I | 01/11/2022 | 30 | M/S PURE RENOVATION CONSTRUCTION GROUP | 14.85 | 0 | 100
1459 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KRISHNARAMPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11789) (3rd Call) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000252/2023-2024 | 1499/SWD-I | 20/07/2023 | 60 | S.P. ENTERPRISE | 6.05 | 5.88 | 100
1460 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Krishnarampur PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11789) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000255/2024-2025 | 2672/SWD-I | 07/06/2024 | 491 | NIKHIL SAMADDAR | 50.05 | 0 | 30
1461 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "KRISHNARAMPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000396/2022-2023 | 464/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.62 | 2.62 | 100
1462 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KRISHNARAMPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 868 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000419/2022-2023 | 2473/SWD-I | 30/12/2022 | 90 | SRIKRISHNA CO OP LABOUR CONT AND CONS SOCIETY LTD | 157.64 | 139.21 | 98
1463 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KRISHNARAMPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011787] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000516/2022-2023 | 2908/SWD-I | 14/02/2023 | 15 | M/S PURE RENOVATION CONSTRUCTION GROUP (EMAIL ID-SAJIDMOLLA93@GMAIL.COM) | 1.57 | 0 | 0
1464 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for KRISHNARAMPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011787] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000586/2022-2023 | 3107/SWD-I | 24/02/2023 | 30 | MOULI CONSTRUCTION | 15.88 | 15.62 | 100
1465 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000029/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.35 | 0 | 0
1466 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000101/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 30.22 | 0 | 0
1467 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VI A at Madhya Gurguria mouza of Kultali block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3302] | AE BSD |  | ORD/000183/2022-2023 | 1486/SWD-I | 28/09/2022 | 1200 | MS GOUTAM CHAKRABORTY | 252.19 | 130.5 | 40
1468 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VI B at Madhya Gurguria mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3487] | AE BSD |  | ORD/000460/2023-2024 | 2137/SWD-I | 31/08/2023 | 90 | M/S SARADA CONSTRUCTION | 280.24 | 0 | 0
1469 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000076/2022-2023 | 2992/SWD-I | 20/02/2023 | 0 | Resource Division | 41.82 | 0 | 0
1470 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Gokarni PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014757] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000007/2023-2024 | 29/SWD-I | 05/04/2023 | 15 | KUNTAL CHOWDHURY | 3.13 | 3.13 | 100
1471 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Hume Pipe culvert for the approach road of proposed "Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block, South 24 Parganas District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE, Dte. (TSM/014757) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000152/2023-2024 | 721/SWD-I | 29/05/2023 | 60 | TOJO ENTERPRISE | 10.17 | 8.4 | 100
1472 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of rig ground bored 02 nos. (Two) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Gokarni PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000300/2022-2023 | 1878/SWD-I | 16/11/2022 | 30 | KUNTAL CHOWDHURY | 30.03 | 27.09 | 100
1473 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of boundary wall & approach Road at 2nd Tube Well site for GOKARNI PWSS to accommodate FHTC in Magrahat-II block under South 24 Parganas W/S division-I, P.H.E. Dte for augmentation of surface water Based Water supply Scheme in the arsenic affected areas of South 24-Pgns district (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000328/2024-2025 | 3265/SWD-I | 22/07/2024 | 90 | SANJAY MIDDEY | 12.19 | 0 | 60
1474 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall at HW site for GOKARNI PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for AUGMENTATION of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas.(SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000329/2024-2025 | 3267/SWD-I | 22/07/2024 | 45 | M/S. SREEJIT ENTERPRISE | 23.82 | 0 | 50
1475 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Platform for providing FHTC for Ground water based GOKARNI piped water supply scheme to accommodate FHTC in MOGRAHAT-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. [No. of FHTC= 1585] (SM/12771) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000344/2024-2025 | 3318/SWD-I | 23/07/2024 | 60 | MONDAL PRECISION PVT. LTD. | 29.5 | 0 | 0
1476 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of "GOKARNEE Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000386/2022-2023 | 406/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 2.72 | 0
1477 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of GOKARNI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1585] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000487/2022-2023 | 2792/SWD-I | 01/02/2023 | 300 | MONDAL PRECISION PVT. LTD. | 463.13 | 168.84 | 25
1478 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Balance work for Construction of Humc Pipe culvert for the approach road of proposcd "Ground water bascd GOKARNI piped watcr supply schcmc to accommodate FHTC tn MAGRAHAT-II block, South 24 Parganas Djstnct for Augmentation of Surfacc Water Based Water Supply Scheme In the Arscmc Affected Areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE. Dle (TSM/014757) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000794/2023-2024 | 1142/SWD-I | 07/03/2024 | 30 | TOJO ENTERPRISE | 2.41 | 2.38 | 100
1479 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000196/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 26.3 | 0 | 0
1480 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of CHHAYANI MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 907] [SM/12217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000072/2023-2024 | 373/SWD-I | 27/04/2023 | 90 | M/S SALIM CONSTRUCTION | 162.11 | 74.26 | 80
1481 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for CHHAYANI PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 3069/SWD-I | 21/02/2023 | 30 | SWASTIK CONSTRUCTION (E-MAIL ID- SIDDHARTHA1978SAMADDER@GMAIL.COM) | 15.46 | 0 | 0
1482 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for CHHAYANI PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/12217] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000852/2023-2024 | 1326/SWD-I | 15/03/2024 | 450 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.46 | 0 | 100
1483 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based CHHAYANI Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under south 24-Pgns W/S Division-I, P.H.E. Dte., for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000916/2022-2023 | 1221/SWD-I | 05/09/2022 | 30 | GEO SOLUTION | 2.54 | 2.49 | 100
1484 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000174/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 6 | 0 | 0
1485 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall & land development at 2nd Tubewell site including provision of M.S. gate for CHAK PARANKANTA KHALI PWSS to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. (SM/12801) [Length - 52.0 mtr. of boundary wall] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000087/2025-2026 | 1762/SWD-I | 02/07/2025 | 45 | MOTIONMASS TECHNO OPC PVT LTD | 9.61 | 0 | 0
1486 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Chak Parankanta Khali PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000294/2022-2023 | 1881/SWD-I | 16/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 0 | 0
1487 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and Approach Road With Drum Sheet walling & Earth filling for CHAK PARANKANTA KHALI PWSS to accommodate FHTC within Mograhat-II Block under South 24 pgs water supply Division-I, PHE Dte. Dist S24 Pgs. (SM/12801) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000295/2024-2025 | 3135/SWD-I | 10/07/2024 | 222 | LASKAR CONSTRUCTION | 38.36 | 6.26 | 45
1488 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of "CHAK PARANKANTAKHALI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000391/2022-2023 | 410/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 2.67 | 0
1489 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of chlorination room 5.00mx4.00m(One no) at Head work site of CHAK PARANKANTA KHALI PWSS to accommondate FHTC in MOGRAHAT-II Block under South 24 Pgns Divn-I, (SM/12801) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000440/2024-2025 | 3885/SWD-I | 03/09/2024 | 30 | AHANA ENTERPRISE | 4.87 | 0 | 0
1490 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of CHAK PARANKANTA KHALI of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1785] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000486/2022-2023 | 2790/SWD-I | 01/02/2023 | 300 | M/S GHOSH AND CO. | 435.23 | 80.33 | 30
1491 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of (4.80 Mtr. X 3.66 Mtr.) Pump House with water supply & sanitary arrangement at CHAK PARANKANTA KHALI Head Work site of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based WS scheme in the arsenicaffected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns WS Division-I, P.H.E Dte. (SM/12801) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000542/2024-2025 | 4099/SWD-I | 20/09/2024 | 60 | LASKAR CONSTRUCTION | 5.89 | 0 | 0
1492 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ChakParankanta Khali PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014899] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000734/2022-2023 | 3585/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 0 | 0
1493 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell by Rotary method for CHAK PARANKATA KHALI Piped Water Supply Scheme to accommodate FHTC in MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/12801] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/001153/2024-2025 | 371/SWD-I | 04/02/2025 | 210 | TITUMIR INTERNATIONAL | 36.84 | 0 | 50
1494 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000204/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 23.83 | 0 | 0
1495 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00667/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
1496 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 01 No. 300 Cum. capacity OHR and 02 Nos. 350 Cum capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of JANGALIA, MASTIKARI and PADMERHAT MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 5561] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000212/2023-2024 | 1374/SWD-I | 12/07/2023 | 900 | KAR CONSTRUCTION | 1262.63 | 0 | 30
1497 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection work for pipeline, approach road, development of land, and other allied works for Proposed Ground water based JANGALIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/13986) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000225/2024-2025 | 2687/SWD-I | 07/06/2024 | 45 | KAMALA ENTERPRISE (DIAMOND HARBOUR) | 16.7 | 0 | 0
1498 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for JANGALIA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017293] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000619/2022-2023 | 3242/SWD-I | 01/03/2023 | 30 | MATRI ENTERPRISE | 31.75 | 29.49 | 100
1499 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "JANGALIA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000755/2022-2023 | 705/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.63 | 2.54 | 100
1500 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000159/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 40.81 | 0 | 0
1501 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BEJEORANCHA PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13917] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 3182/SWD-I | 15/07/2024 | 15 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.46 | 3.73 | 100
1502 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for BEJEORANCHA PWSS of BARUIPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/13917] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000577/2022-2023 | 3070/SWD-I | 21/02/2023 | 30 | SWASTIK CONSTRUCTION (E-MAIL ID- SIDDHARTHA1978SAMADDER@GMAIL.COM) | 15.46 | 0 | 80
1503 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (One no.) at 1st Tube well site of BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [For T/W site-1] (SM/13917) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000660/2024-2025 | 4390/SWD-I | 23/10/2024 | 60 | RAJ ENTERPRISE | 4.92 | 0 | 100
1504 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at BEJEORANCHA of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 620] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000740/2022-2023 | 3593/SWD-I | 23/03/2023 | 990 | AQUATECH ENGINEERS | 108.64 | 64.42 | 85
1505 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Bejerancha Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000949/2022-2023 | 1280/SWD-I | 13/09/2022 | 30 | GEO SOLUTION | 2.44 | 2.41 | 100
1506 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based BEJEORANCHA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/13917) [3rd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001139/2024-2025 | 242/SWD-I | 22/01/2025 | 45 | R.K ENTERPRISE | 23.83 | 0 | 0
1507 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000191/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 4.04 | 0 | 0
1508 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of KAMARIA (ZONE-II) MOUZA of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2051] [TSM/016159] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000170/2023-2024 | 967/SWD-I | 08/06/2023 | 300 | MANASH GHOSH | 359.97 | 125.81 | 50
1509 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for KAMARIA (Zone-II) PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016159] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000503/2022-2023 | 2894/SWD-I | 13/02/2023 | 30 | PURE RENOVATION GROUP | 31.78 | 30.16 | 100
1510 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000092/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 65.22 | 0 | 0
1511 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.29] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/00489/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 4.06 | 0 | 0
1512 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for Laying distribution system, Rising main, Funtional Household Tap connection(FHTC) for piped water supply scheme at CHADOKHALI for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [No. of FHTC =1517] [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000052/2023-2024 | 271/SWD-I | 24/04/2023 | 708 | J.D. CONSTRUCTION | 221.14 | 210.19 | 80
1513 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by having 66 mtr. Housing by Rotary method for 3rd tubewell site for Augmentation of ground water based CHADOKHALI PWSS to accomodate FHTC in Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000229/2023-2024 | 1405/SWD-I | 14/07/2023 | 30 | M/S. S M ENTERPRISE | 21.54 | 20.05 | 100
1514 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at CHADOKHALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000252/2022-2023 | 1753/SWD-I | 04/11/2022 | 900 | MA TARA CONSTRUCTION | 10.93 | 4.3 | 100
1515 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for CHADOKHALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000277/2022-2023 | 1839/SWD-I | 11/11/2022 | 30 | G D S ENTERPRISE | 39.87 | 35.69 | 100
1516 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at CHADOKHALI of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 988) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000282/2022-2023 | 1843/SWD-I | 11/11/2022 | 871 | J.D. CONSTRUCTION | 153.54 | 135.64 | 100
1517 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of CHADOKHALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000347/2021-2022 | 1907/SWD-I | 27/01/2022 | 30 | TECH VISION | 3.03 | 2.75 | 100
1518 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house / chlorination room at 3rd Tubewell site for Augmentation of ground water based CHADOKHALI PWSS to accomodatte FHTC in Baruipur Block under South 24-Pgns, W/S Divn-I, PHE Dte. within South 24-Pgns district. [TSM/014213] [2nd call] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000521/2023-2024 | 2268/SWD-I | 14/09/2023 | 60 | MOLLICK ENTERPRISE | 5.68 | 0 | 0
1519 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Chadokhali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014213] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000786/2022-2023 | 3668/SWD-I | 29/03/2023 | 15 | G.D.S ENTERPRISE | 4.39 | 4.21 | 100
1520 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000107/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 23.82 | 0 | 0
1521 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, service road and land development at 2nd and 3rd Tubewell Site for SHYAMPUR PART-II PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. (SM/14550) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000031/2025-2026 | 982/SWD-I | 09/04/2025 | 45 | M/S MJA ENTERPRISE | 15.4 | 0 | 0
1522 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 814 | S & P ENTERPRISE | 1745.38 | 18.63 | 6
1523 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of boundary wall, approach pathway for SHYAMPUR PART- II PWSS to accommodate FHTC in Magrahat-II block under South 24-Pgns W/S Division-I, P.H.E. Dte for Augmentation of Surface Water Based Water Supply Scheme in the arsenic affected areas of South 24-Pgns District (SM/14550) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000381/2024-2025 | 3572/SWD-I | 12/08/2024 | 315 | SWATHI ENTERPRISE | 30.64 | 0 | 75
1524 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of land by filling of silver sand at the head work site for proposed "Ground water waste SHYAMPUR PART-II piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District under South 24-Pgns, Water Supply Division-I, P.H.E. Dte. (SM/14550) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000672/2024-2025 | 4398/SWD-I | 23/10/2024 | 70 | LASKAR CONSTRUCTION | 13.42 | 6.05 | 40
1525 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Shyampur(part-II) Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000973/2022-2023 | 1426/SWD-I | 22/09/2022 | 30 | GEO SOLUTION | 2.73 | 2.73 | 100
1526 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000201/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 37.72 | 0 | 0
1527 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALAYPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 841] [TSM/018360] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000068/2023-2024 | 369/SWD-I | 27/04/2023 | 975 | JAI BHARAT COMMERCIAL CORPORATION | 121.47 | 43.48 | 80
1528 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary walls, platform for providing FHTC, protection of pipeline work, Restoration of road and other allied works for Ground water based MALAYAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15180) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000342/2024-2025 | 3316/SWD-I | 23/07/2024 | 405 | JAI BHARAT COMMERCIAL CORPORATION | 59.41 | 0 | 30
1529 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based MALAYAPUR Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000922/2022-2023 | 1174/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 2.57 | 2.56 | 100
1530 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000148/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 6.56 | 0 | 0
1531 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Initial 50% payment for the amount Rs. 4160934/- (forty-one lakh sixty thousand nine hundred & thirty four) only i.e. Rs. 2080467/- (twenty lakh eighty thousand four hundred & sixty-seven) only for restoration of road edge and hard shoulder damaged due to laying of pipeline of Dakshin Barasat to Usthi Road under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT and Zone -IX at Ghola Noapara under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/16187 and SM/14725). | AE SWSD-II | JE4 | BILL/00801/2024-2025 | BP-2024-25-492 | 21/11/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 20.8 | 0 | 0
1532 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Shifting of 2 nos. LT pole for construction of OHR at Alampur under JJM project of PHED | AE SWSD-II | JE4 | BILL/01763/2023-2024 | BP-2023-24-617 | 22/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.32 | 0 | 0
1533 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. chlorination room at O.H.R. sites for Zone-IV (Hijalhat), Zone-VIII (Khelarampur) & Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Division-I, PHE Dte. South 24 Parganas District. (SM/16187), (SM/14729), (SM/14725) | AE SWSD-II | JE4 | ORD/000026/2025-2026 | 978/SWD-I | 09/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 19.37 | 0 | 0
1534 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of pipe carrying structure over the canals at village Amtwali Hariharpur GP for the laying of distribution pipeline within Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24-Pgns Water Supply Division-I, PHE Dte. [SM/16187] | AE SWSD-II | JE4 | ORD/000097/2025-2026 | 1772/SWD-I | 02/07/2025 | 45 | ADRIK ENTERPRISE | 10.88 | 0 | 0
1535 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall and Laying Distribution System including FHTC for Augmentation of Laying Distribution System to extend benefit off 100% household in Zone-IV at HIJALHAT under Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 6310] [TSM/015076] | AE SWSD-II | JE4 | ORD/000125/2023-2024 | 568/SWD-I | 15/05/2023 | 1078 | M/S GHOSH AND CO. | 1160.71 | 474.66 | 56
1536 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, road restoration and other allied works for Zone-IV (Hijalhat) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. | AE SWSD-II | JE4 | ORD/000495/2024-2025 | 3867/SWD-I | 02/09/2024 | 90 | MILAN GHOSH | 310.34 | 0 | 0
1537 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Design of Route survey of distribution system of Mograhat Zone-IV within Mograhat-I Block for Augmentation of Laying Distribution System, to extend the benefit of 100% households in Zone-IV at HIJALHAT of Mograhat-I Block within "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist. South 24-Pgs. under South 24-Pgns W/S Divn-I, P.H.E. Dte. (Route Surveying of 60 KM) [TSM/015076] | AE SWSD-II | JE4 | ORD/000658/2022-2023 | 3361/SWD-I | 09/03/2023 | 7 | GEO SOLUTION | 2.38 | 2.37 | 0
1538 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000063/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 5.03 | 0 | 0
1539 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (Two) nos. chlorine room (size 5.90 m x 4.10 m out to out) with sanitary and water supply arrangement at Head work Site at Ghateswar in Zone-X and Achina in Zone-VII for Augmentation of laying distribution system to extend the benefit of 100% house hold in Zone-XI at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta Mathurapur, District-South 24 Parganas under South 24-Pgns W/S Division-I, PHE Dte. (SM/16188) | AE HQ-I |  | ORD/000029/2025-2026 | 980/SWD-I | 09/04/2025 | 60 | SANKAR HALDER | 13.37 | 0 | 0
1540 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Laying distrbution main pipe line with FHTC for 'Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-XI at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte'. (No of FHTC.2329) (TSM/015099 & TSM/010837) | AE HQ-I |  | ORD/000387/2023-2024 | 1840/SWD-I | 17/08/2023 | 775 | M/S. B.M. CONSTRUCTION | 327.12 | 107.64 | 80
1541 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of 90mm &160mm dia HDPE Pipe line over Kulpi Road near Uttar Sultanpur Railway Gate, over Dhola Road near Dhola Railway Gate & over Shibpur Road near Polerhat Railway Gate with allied works for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (TSM/015099). | AE HQ-I |  | ORD/000548/2023-2024 | 2496/SWD-I | 06/10/2023 | 60 | R.D CONSTRUCTION | 3.39 | 3.36 | 100
1542 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 600 mm dia (ID) 10mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track at Uttar Sultanpur Railway Gate over Kulpi Road near Lakshmikantapur Railway Station in between Lakshmikantapur (LKPR) - Udairampur Halt (URP) KM/TP 62/17 - 62/18, as per permission of Railway Authority, for laying of 200 mm dia (ID) 6 mm thick MS water supply pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099) [2nd Call] | AE HQ-I |  | ORD/000671/2022-2023 | 3434/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 49.49 | 49.49 | 0
1543 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & laying of 600 mm dia (ID) MS Pipe conduits 60 mtr. in length to be prepared from 10 mm thick MS Plate by pipe jacking technique, including supplying and laying of 200 mm dia (ID) MS water main within the conduit 90 mtr. in length to be prepared from 06 mm thick MS Plate across and underneath the Railway Track at Shibpur Railway Gate near Polerhat Railway Gate of Lakshmikantapur Station in between Lakshmikantapur (LKPR) - Udairampur Halt (URP) KM/TP 63/14 - 63/15 as per permission obtained from Railway Authority, including construction of Drive Pit & Receiving Pit, as requred, for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (TSM/015099) | AE HQ-I |  | ORD/000664/2022-2023 | 3351/SWD-I | 09/03/2023 | 60 | M/S. GOUTAM ROY | 51.13 | 51.13 | 100
1544 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 600 mm dia (ID) 10mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track at Dhola Railway Gate over Dhola Road near Lakshmikantapur Railway Station in between Lakshmikantapur (LKPR) - Udairampur Halt (URP) KM/TP 62/07 - 62/08 as per permission of Railway Authority, for laying of 300 mm dia (ID) 7 mm thick MS water supply pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099)[2nd call] | AE HQ-I |  | ORD/000672/2022-2023 | 3435/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 55.47 | 55.47 | 0
1545 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 700 mm dia (ID) 12mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track in between Basuldanga station and Gurudasnagar station and in between Mast No.56/27, 56/29 and 56/28, 56/30 as per permission of Railway Authority, for laying of 450 mm dia (ID) 8.6 mm thick MS water supply pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099)[2nd call] | AE HQ-I |  | ORD/000673/2022-2023 | 3436/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 69.23 | 49.43 | 50
1546 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & insertion of 700 mm dia (ID) 12mm thick MS casing pipe line 135 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track near Karanjali Railway Station in between Karanjali Halt (KNJI) - Nischindopur Market Halt (NCPM) KM/TP 75/13-75/14 as per permission of Railway Authority, for laying of 500 mm dia (ID) 10 mm thick MS water supply pipe 160 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-XI at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte. (TSM/015099)[2nd call] | AE HQ-I |  | ORD/000674/2022-2023 | 3437/SWD-I | 13/03/2023 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 134.2 | 134.2 | 100
1547 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Existing R.C.C. Reservoir of capacity 250 CUM and staging height 20 mtr at Head Work site of Uttar Sultanpur (Zone XI) within Mandir Bazar Block Block " for Mega Surface Water Based Water Supply Scheme for Falta -Mathurapur, South 24 Parganas, under South 24 Pgns. Water Supply Division-I, PHE, Dte. (SM/16188) | AE HQ-I |  | ORD/000699/2024-2025 | 4501/SWD-I | 30/10/2024 | 45 | SRIJON ENTERPRISE | 10.52 | 0 | 100
1548 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of Pumphouse, Cholorine room, Office Room, Construction of Pathway at Head work site of of Uttar Sultanpur (Zone XI) within Mandir Bazar Block for Mega Surface Water Based Water Supply Scheme for Fakta -Mathurapur, South 24 Parganas, under South 24 Pgns. Water Supply Division-I, PHE, Dte. [SM/16188] | AE HQ-I |  | ORD/000766/2024-2025 | 4687/SWD-I | 18/11/2024 | 30 | G.M. ENTERPRISE (MURSHIDABAD) | 7.85 | 0 | 0
1549 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pump House cum chlorine room (size 5.90 m x 4.10 m) with sanitary and water supply arrangement at Head work sites for various zones of Mandirbazar block under Mega Surface Water Based W/S Scheme for Falta-Mathurapur, South 24-Parganas, under South 24 Parganas W/S Division-I, PHE Dte. [SM/18706, SM/15485, SM/12204, SM/18715, SM/12205] | AE HQ-I |  | ORD/000790/2024-2025 | 4759/SWD-I | 21/11/2024 | 60 | NIKHIL SAMADDAR | 35.04 | 0 | 0
1550 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system for Zone-XI, Uttar Sultanpur (OHR Capacity- 250cum.) under Mandirbazar Block" under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. District. | AE HQ-I |  | ORD/000852/2022-2023 | 18/SWD-I | 06/04/2022 | 30 | LEMNISCATE | 1.98 | 1.98 | 100
1551 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000049/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 2.74 | 0 | 0
1552 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Development of land, Construction of approach road and other allied works for Ground Water Based TILPI (Zone-II) Piped Water Supply Scheme to Accommodate FHTC in JAYNAGAR-I Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/15865) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000404/2024-2025 | 3684/SWD-I | 22/08/2024 | 251 | GARAI INFRA PROJECT | 43.89 | 0 | 65
1553 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 290.7 | 96
1554 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based TILPI (ZONE-II) piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15865) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000575/2024-2025 | 4274/SWD-I | 01/10/2024 | 60 | GARAI INFRA PROJECT | 29.92 | 0 | 0
1555 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for TILPI Zone-II PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018041) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000709/2022-2023 | 3523/SWD-I | 17/03/2023 | 30 | M/S SUNDARI CONSTRUCTION | 31.76 | 30.99 | 100
1556 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "TILPI Zone-II Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000757/2022-2023 | 708/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.56 | 2.56 | 100
1557 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000155/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 40.5 | 0 | 0
1558 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of BALBALIA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2078] [TSM/017761] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000157/2023-2024 | 840/SWD-I | 05/06/2023 | 783 | ASHOKA ENTERPRISE | 480.17 | 83.91 | 60
1559 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BALBALIA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017761] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000651/2022-2023 | 3323/SWD-I | 06/03/2023 | 30 | MAHI CONSTRUCTION | 31.77 | 15.26 | 0
1560 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Balbalia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000946/2022-2023 | 1278/SWD-I | 13/09/2022 | 30 | GEO SOLUTION | 2.76 | 2.7 | 100
1561 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for providing FHTC, protection work for laying pipeline and other allied works for Ground water based BALBALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/15866) | AE BSD,Assistant Engineer | Junior Engineer | ORD/001118/2024-2025 | 154/SWD-I | 15/01/2025 | 360 | PINKI CONSTRUCTION | 86.35 | 0 | 40
1562 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000118/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 45.75 | 0 | 0
1563 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump House cum Chlorine Room, Boundary Wall along with Laying Distribution System, Rising Main and providing FHTC for Augmentation of Piped W/S Scheme of KALYANPUR (KHODAR BAZAR) (PART-II) of BARUIPUR Block of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1180] [TSM/018149] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 971/SWD-I | 08/06/2023 | 90 | APORUPA CONSTRUCTION | 151.88 | 0 | 0
1564 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KALYANPUR (KHODAR BAZAR) , PART-II Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000505/2021-2022 | 1904/SWD-I | 27/01/2022 | 30 | RADIANT | 2.62 | 2.47 | 100
1565 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing by Rotary method for KALYANPUR KHODARBAZAR (Part-II) Piped Water Supply Scheme to accommodate FHTC in Baruipur block under South 24-Pgns. W/S Division-I, PHE Dte. for Augnemtation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. [SM/15776] (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000719/2024-2025 | 4577/SWD-I | 11/11/2024 | 30 | RAJKUMAR MONDAL | 31.8 | 0 | 0
1566 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000171/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 31.37 | 0 | 0
1567 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for BERALIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 990] [TSM/018427] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000069/2023-2024 | 370/SWD-I | 27/04/2023 | 790 | SOMA ENTERPRISE | 207.4 | 174.63 | 93
1568 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, protection work for pipeline, approach road, development of land and other allied works for Ground water based BERALIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/15783) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000221/2024-2025 | 2639/SWD-I | 07/06/2024 | 45 | ALISHA CONSTRUCTION | 33.95 | 0 | 0
1569 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BERALIA PWSS to accommodate FHTC in Baruipur Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018427) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000706/2022-2023 | 3519/SWD-I | 17/03/2023 | 30 | M/S A.M. CONSTRUCTION | 31.76 | 15.43 | 50
1570 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Beralia Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000945/2022-2023 | 1266/SWD-I | 12/09/2022 | 30 | GEO SOLUTION | 2.54 | 2.53 | 100
1571 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000119/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.83 | 0 | 0
1572 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for MAHISHMARI MOUZA Piped Water Supply Scheme of JAYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1025] [TSM/018296] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000350/2023-2024 | 1736/SWD-I | 10/08/2023 | 630 | M. MUKHERJEE | 350.46 | 68.36 | 40
1573 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for MAHISMARI PWSS to Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018296) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000707/2022-2023 | 3520/SWD-I | 17/03/2023 | 30 | MALLICK CONSTRUCTION | 31.63 | 30.23 | 100
1574 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC, protection wall for laying pipeline, restoraton of damaged roads due to laying of pieline other allied worksand miscelleneous work for Ground water based MAHISMARI piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/16125) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000772/2024-2025 | 4757/SWD-I | 21/11/2024 | 45 | B.M. ENTERPRISE | 57.33 | 0 | 0
1575 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Mahishmari Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000958/2022-2023 | 1183/SWD-I | 01/09/2022 | 30 | GEO SOLUTION | 2.76 | 2.75 | 100
1576 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000115/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 25.32 | 0 | 0
1577 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for PURANDARPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 934] [TSM/018251] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000070/2023-2024 | 371/SWD-I | 27/04/2023 | 90 | SUJATA CONSTRUCTION | 172.64 | 69.58 | 80
1578 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall, platform for FHTC, pipeline protection development of land and other allied works for Ground water based PURANDARPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district.(SM/16129) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000294/2024-2025 | 3133/SWD-I | 10/07/2024 | 265 | RAJLAXMI CONSTRUCTION | 67.13 | 4.51 | 30
1579 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PURANDARPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018251] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000648/2022-2023 | 3320/SWD-I | 06/03/2023 | 30 | M/S BASAK CONSTRUCTION | 31.72 | 19.29 | 64
1580 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Purandarpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000935/2022-2023 | 1227/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.5 | 2.48 | 100
1581 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000127/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 27.76 | 0 | 0
1582 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of RAJPUR KORABEG MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1692] [TSM/018299] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000361/2023-2024 | 1766/SWD-I | 10/08/2023 | 900 | EQUIPMENTS AND SPARES AGENCIES | 411.03 | 77.32 | 45
1583 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for RAJPUR KORABEG PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018299) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000705/2022-2023 | 3514/SWD-I | 17/03/2023 | 30 | SOURAV GHOSH | 31.75 | 31.09 | 5
1584 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based RAJPUR KORABAG piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/16131) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000738/2024-2025 | 4636/SWD-I | 14/11/2024 | 45 | EQUIPMENTS AND SPARES AGENCIES | 71.4 | 0 | 0
1585 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Rajpur Korabag Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000957/2022-2023 | 1307/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.64 | 2.62 | 100
1586 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000116/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 32.75 | 0 | 0
1587 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising main,including Funtional Household Tap connection(FHTC) for SURJAPUR piped water supply scheme of BARUIPUR Block, under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under South 24 Pgns. W/S Division-I, P.H.E Dte. (TSM/018700) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000087/2023-2024 | 347/SWD-I | 26/04/2023 | 675 | BAIDYA ENTERPRISE | 53.26 | 42.68 | 76
1588 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall (Two nos) for SURJAPUR PWSS of Baruipur block, under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Paraganas district under South 24 Pgns. W/S Divn-I, PHE, Dte. (TSM/018700) [Length - 50.0 mtr.] (Tube Well site-1 & 2) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000089/2023-2024 | 442/SWD-I | 03/05/2023 | 60 | B.M. TRADERS | 13.85 | 0 | 0
1589 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum chlorination room (Two nos) for SURJAPUR PWSS of Baruipur Block under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district under South 24 Pgns W/S Division-I, PHE, Dte. (TSM/018700) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000126/2023-2024 | 569/SWD-I | 15/05/2023 | 60 | BINAPANI ENTERPRISE | 11.28 | 0 | 100
1590 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for SURJAPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018700] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000653/2022-2023 | 3350/SWD-I | 09/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 29.86 | 100
1591 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Surjapur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000928/2022-2023 | 1180/SWD-I | 01/09/2022 | 30 | GEO SOLUTION | 2.36 | 2.36 | 100
1592 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000261/2023-2024 | 2428/SWD-I | 30/09/2023 | 0 | Resource Division | 22.03 | 0 | 0
1593 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000330/2023-2024 | 268/SWD-I | 10/01/2024 | 0 | Resource Division | 2.14 | 0 | 0
1594 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Bhangor Bodra Road from 0.00 kmp to 204kmp, Permanent restoration work, damaged due tp " Pipeline Laying of 250mm to 90mm dia HDPE Pipe Line along flank by PHE DEpartment " within Alipore Highway sub-Division under South 24 Parganas Highway Division in the district of South 24 Parganas. (SM/15754) | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00641/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.37 | 0 | 0
1595 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) and construction of Pump House cum Chlorine Room (2 Nos.) for JAGULGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2089) (TSM/018474) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 125/SWD-I | 12/04/2023 | 744 | A P POWER AND CONCRETE | 279.5 | 129.85 | 10
1596 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method for JAGULGACHI PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018474] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000639/2022-2023 | 3287/SWD-I | 03/03/2023 | 30 | M/S MONDAL ENTERPRISE | 31.76 | 14.53 | 50
1597 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of JAGULGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15754] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000750/2024-2025 | 4672/SWD-I | 18/11/2024 | 60 | A.P POWER AND CONCRETE | 75.42 | 0 | 0
1598 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000046/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 24.11 | 0 | 0
1599 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000216/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.87 | 0 | 0
1600 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Supplying, fabrication & laying of 610 mm dia (OD) MS Pipe conduits 50 mtr. in length to be prepared from 12.5 mm thick MS Plate by pipe jacking technique, including supplying and laying of 219 mm dia (OD) MS water main within the conduit 60 mtr. in length to be prepared from 10 mm thick MS Plate, across and underneath the Railway Track at Bidyadharpur Railway Station in between Station Champahati (CHT) - Bidyadharpur (BDYP), OHE Mast No. 20/4C as per permission of Railway Authority for "Hasanpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission"(SM/15759) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000022/2025-2026 | 974/SWD-I | 09/04/2025 | 60 | SRIJON ENTERPRISE | 64.28 | 0 | 0
1601 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pump House cum Chlorine Room along with Laying Distribution System for HASANPUR Piped W/S Scheme to accommodate FHTC in Sonarpur Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/018119] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000074/2023-2024 | 388/SWD-I | 28/04/2023 | 704 | J.D. CONSTRUCTION | 165.4 | 137.46 | 30
1602 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HASANPUR PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018119] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000667/2022-2023 | 3407/SWD-I | 10/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 30.78 | 50
1603 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000017/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 6.03 | 0 | 0
1604 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000231/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 8.84 | 0 | 0
1605 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.59] |  |  | BILL/00484/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 31.8 | 0 | 0
1606 | South 24 Pgs W/S Division I |  | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for DEARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2233] |  |  | ORD/000238/2023-2024 | 1435/SWD-I | 18/07/2023 | 898 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 593.7 | 234.21 | 50
1607 | South 24 Pgs W/S Division I |  | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for DEARA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/016320] |  |  | ORD/000296/2023-2024 | 1661/SWD-I | 03/08/2023 | 15 | PADMA ENGINEERING CO. | 3.14 | 3.14 | 100
1608 | South 24 Pgs W/S Division I |  | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR DEARA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016320) |  |  | ORD/000299/2023-2024 | 1664/SWD-I | 03/08/2023 | 30 | PADMA ENGINEERING CO. | 30.07 | 23.92 | 100
1609 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at Headwork and 2nd Tubewell site of DEARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18329) |  |  | ORD/000823/2023-2024 | 1297/SWD-I | 15/03/2024 | 45 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 52.22 | 0 | 0
1610 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 35.83 | 0 | 0
1611 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000315/2023-2024 | 245/SWD-I | 10/01/2024 | 0 | Resource Division | 13.76 | 0 | 0
1612 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Negotiation of gap of Secondary Grid pipeline under Augmentation of laying distribution system to extend the benefit of 100% household in Zone-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur Dist.-South 24 pgns. under South 24-Pgns Water Supply Division-I, PHE Dte. (SM/18220) | AE BSD |  | ORD/000092/2025-2026 | 1767/SWD-I | 02/07/2025 | 180 | CHANDAN ROY | 88.79 | 0 | 80
1613 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VIA of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte.. | AE BSD |  | ORD/000403/2021-2022 | 2551/SWD-I | 10/03/2022 | 120 | MS GOUTAM CHAKRABORTY | 640.41 | 290.58 | 0
1614 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 900 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design with balance work for Augmentation of Laying Distribution System to extend benefit off 100% household in at MADHYA GURUIA (Zone-VI) Mouza in Kultali Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016361] | AE BSD |  | ORD/000459/2023-2024 | 2136/SWD-I | 31/08/2023 | 300 | M/S SARADA CONSTRUCTION | 669.13 | 75.22 | 30
1615 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of HDPE pipe of 500 mm diameter by Horizontal Directional Drilling (HDD) process for crossing Matla-Tribtary between Kantamari and Madhya Gurguria on Maypith Road in between nodes 4 & 5 within Kultali Block for Secondry Grid of under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-VI at KULTALI block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.". (SM/18220) | AE BSD |  | ORD/000737/2023-2024 | 495/SWD-I | 25/01/2024 | 30 | ATINDRA CONSTRUCTION PRIVATE LIMITED. | 84.5 | 84.5 | 100
1616 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000038/2022-2023 | 2955/SWD-I | 16/02/2023 | 0 | Resource Division | 1655.16 | 0 | 0
1617 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE CHAKBERIA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016026) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000346/2022-2023 | 2164/SWD-I | 09/12/2022 | 754 | ARASTA ENGINEERING & CO | 29.84 | 18 | 100
1618 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1724] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000495/2022-2023 | 2863/SWD-I | 09/02/2023 | 900 | MAHI ENTERPRISE | 372.71 | 103.04 | 25
1619 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Hume Pipe Culvert 4.80 Mtr.span with 32 Mtr. Long temporary approach road (Plot No-35) for proposed Chakberia OHR Site at Navasan Mouza (JL No-109, Dag No-35, Khatian No-01) at CHAKBERIA PWSS within Sonarpur Block " CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000568/2024-2025 | 4241/SWD-I | 30/09/2024 | 124 | MAHI ENTERPRISE | 13.38 | 1.94 | 60
1620 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHAKBERIA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13771] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000726/2022-2023 | 3575/SWD-I | 22/03/2023 | 661 | ARASTA ENGINEERING & CO | 3.13 | 1.57 | 100
1621 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of land at proposed Headwork site of CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000726/2024-2025 | 4603/SWD-I | 12/11/2024 | 60 | MAHI ENTERPRISE | 37.97 | 0 | 0
1622 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional laying of pipeline and restoration of road near PROPOSED OHR site of "CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000748/2024-2025 | 4670/SWD-I | 18/11/2024 | 45 | MAHI ENTERPRISE | 21.74 | 0 | 0
1623 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of CHAKBERIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13771) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000822/2023-2024 | 1296/SWD-I | 15/03/2024 | 45 | MAHI ENTERPRISE | 44.33 | 0 | 0
1624 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000012/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 23.87 | 0 | 0
1625 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000230/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.62 | 0 | 0
1626 | South 24 Pgs W/S Division I |  | Land Developement Protection work for pipeline, construction of Boundary Wall with Internal Pavement and others allied works at HW & 2nd Tube-well site of NALMURI PWSS to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/18548) |  |  | ORD/000107/2025-2026 | 1869/SWD-I | 14/07/2025 | 75 | SUJIT KUMAR SHARMA | 161.85 | 0 | 0
1627 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for NALMURI PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018471] |  |  | ORD/000304/2023-2024 | 1672/SWD-I | 04/08/2023 | 30 | M/S BANERJEE ENGINEERING SYSTEM | 31.79 | 14.74 | 50
1628 | South 24 Pgs W/S Division I |  | Construction of 350 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for NALMURI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 2582) (TSM/018471) |  |  | ORD/000439/2023-2024 | 2089/SWD-I | 29/08/2023 | 752 | SE TILES MANUFACTURING COMPANY PRIVATE LIMITED | 708.85 | 105.17 | 30
1629 | South 24 Pgs W/S Division I |  | Laying of different diameters HDPE pipe in distribution pipe lines by Horizontal Directional Drilling (HDD) process at different locations for Canal / Road crossing adjacent to Basanti Highway under NALMURI, DEBIPUR & NARAYANPUR PWSS of Bhangar-I Block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District under South 24 Pgns W/S Divn-I, PHE Dte. (SM/18548, SM/18499 & SM/18547) |  |  | ORD/000507/2024-2025 | 3976/SWD-I | 11/09/2024 | 180 | TELETONE INDIA PRIVATE LIMITED | 70.04 | 17.14 | 60
1630 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 28.02 | 0 | 0
1631 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000326/2023-2024 | 250/SWD-I | 10/01/2024 | 0 | Resource Division | 15.91 | 0 | 0
1632 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration charges of damage road due to phed pipe laying between Ch.7.40 km of Thakurpukur Bibirhat Bakhrahat Raipur Road under South 24 pgs. Division, PWD during 2023-24, 50% of estimate cost i.e.1,04,88,089/- in advance as per minutes of the meeting with HMIC, PHED on 12.09.2022 | AE SWSD-II | JE1 | BILL/02110/2023-2024 | BP-2023-24-799 | 22/03/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 52.44 | 0 | 0
1633 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall & other allied works at Head Work Site of UTTAR KAZIRHAT PWSS at Bishnupur-I block District- South 24-Parganas for augmentation of Surface Water Based W/S scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018475] (2nd call) | AE SWSD-II | JE1 | ORD/000242/2023-2024 | 1439/SWD-I | 18/07/2023 | 60 | UNI DEVELOPERS AND CONTRACTORS | 18.17 | 17.76 | 100
1634 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-II | JE1 | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
1635 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed UTTAR KAZIRHAT PIPE WATER SUPPLY SCHEME in BISHNUPUR-I & Thakurpukur-Mahestala Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 5617) [TSM/018475]. | AE SWSD-II | JE1 | ORD/000528/2023-2024 | 2345/SWD-I | 22/09/2023 | 526 | SUPRITI ENTERPRISE | 638.94 | 118.94 | 60
1636 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Kazirhat Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000963/2022-2023 | 1167/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.97 | 2.95 | 100
1637 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000118/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 43.62 | 0 | 0
1638 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000312/2023-2024 | 3116/SWD-I | 07/12/2023 | 0 | Resource Division | 94.04 | 0 | 0
1639 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-IV at Daskhin Garankathi mouza of Kultali block for Augmentation of Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 5540] | AE BSD |  | ORD/000429/2023-2024 | 2003/SWD-I | 28/08/2023 | 90 | PATH MAKERS | 444.58 | 346.95 | 75
1640 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling work with Drumsheet walling, Approach Road and Road Restoration of USHPARA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/13307) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000370/2024-2025 | 3529/SWD-I | 07/08/2024 | 90 | I.S ENTERPRISE | 100.98 | 41.08 | 45
1641 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for USPARA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015202] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000606/2022-2023 | 3135/SWD-I | 27/02/2023 | 30 | SABYASACHI CHAKI | 31.75 | 15.57 | 50
1642 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional Laying of distribution Network System for different dia HDPE pipe under Ushpara PWSS, Block-Bhangar-I, Dist-South 24 Parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2114]. [SM Code - SM/13307] [2nd Call] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000706/2023-2024 | 3403/SWD-I | 28/12/2023 | 60 | I.S ENTERPRISE | 53.48 | 47.53 | 100
1643 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for USHPARA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2114] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000713/2022-2023 | 3538/SWD-I | 20/03/2023 | 745 | I.S ENTERPRISE | 429.22 | 287.48 | 30
1644 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Land development at HW & 2nd tube well site and restoration of road damaged due to laying of pipe line for USHPARA PWSS in Bhangar-I Block under South 24-Parganas, W/S Division-I, P.H.E. Dte. for Augmentation of Surface Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. District under Jal Jeevan Mission (SM/13307) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000871/2024-2025 | 4929/SWD-I | 03/12/2024 | 61 | I.S ENTERPRISE | 60.86 | 0 | 50
1645 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for USHPARA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/13307] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001152/2024-2025 | 370/SWD-I | 04/02/2025 | 30 | HI-LIGHT ELECTRONICS | 15.9 | 0 | 0
1646 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000060/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 23.39 | 0 | 0
1647 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000224/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 13.02 | 0 | 0
1648 | South 24 Pgs W/S Division I |  | Restoration of road after laying of pipeline, protection work for pipeline, development of land and other allied works for Ground water based AKNA MIRZAPUR piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/18573) |  |  | ORD/000332/2024-2025 | 3270/SWD-I | 22/07/2024 | 45 | MONDAL AND CO | 50.41 | 0 | 0
1649 | South 24 Pgs W/S Division I |  | Sinking of 04 (Four) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for AKNA MIRZAPUR PWSS at Zone-29 of Baruipur block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018363] |  |  | ORD/000386/2023-2024 | 1822/SWD-I | 16/08/2023 | 30 | TAPAS KUMAR GIRI | 63.59 | 0 | 0
1650 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of AKNA MIRZAPUR MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4257] [TSM/018363] |  |  | ORD/000407/2023-2024 | 1924/SWD-I | 22/08/2023 | 583 | MONDAL AND CO | 592.29 | 336.64 | 70
1651 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based AKNA MIRJAPUR Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000919/2022-2023 | 1170/SWD-I | 30/08/2022 | 30 | ASTER CONSULTANCY | 3.34 | 3.3 | 100
1652 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 31.31 | 0 | 0
1653 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road for laying of water pipeline by PHE Dte, in Ch- 5.00 Km to Ch - 12.00 km of Thakurpukur Bakrahat Raipur Road Under South 24 Parganas Division P.W.D in the Dist of South 24 Pgs During the year 2024-25 | AE SWSD-II | JE1 | BILL/00263/2024-2025 | BP-2024-25-192 | 16/07/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 133.51 | 0 | 0
1654 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration charges of damage road due to phed pipe laying between Ch.7.40 km of Thakurpukur Bibirhat Bakhrahat Raipur Road under South 24 pgs. Division, PWD during 2023-24, 50% of estimate cost i.e.1,04,88,089/- in advance as per minutes of the meeting with HMIC, PHED on 12.09.2022 | AE SWSD-II | JE1 | BILL/02110/2023-2024 | BP-2023-24-799 | 22/03/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 52.44 | 0 | 0
1655 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of balance pipeline and road restoration for Raspunja PWSS to accommodate FHTC in Thakurpukur - Maheshtala Block under South 24 Parganas W/S Division-I , PHE Dte. for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/ 18576) | AE SWSD-II | JE1 | ORD/000279/2024-2025 | 3003/SWD-I | 28/06/2024 | 90 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 109 | 94.28 | 60
1656 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for the stand alone site at SHIBRAMPUR under RASAPUNJA PWSS of Thakurpukur-Maheshtala Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/18576] | AE SWSD-II | JE1 | ORD/000282/2024-2025 | 3038/SWD-I | 02/07/2024 | 30 | K.P CONSTRUCTION | 15.89 | 14.58 | 100
1657 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and construction of PUMP HOUSE (4.80 Mtr. X 3.66 Mtr.) for Stand alone scheme at Shibrampur under ground water based RASAPUNJA PIPE WATER SUPPLY SCHEME to accomodate FHTC in Thakurpukur-Maheshtala Block under South 24 Pgns W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (TSM/018477) | AE SWSD-II | JE1 | ORD/000353/2023-2024 | 1739/SWD-I | 10/08/2023 | 640 | JOY GURU TRADING | 38.27 | 0 | 40
1658 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and construction of PUMP HOUSE (4.80 Mtr. X 3.66 Mtr.) for Stand alone scheme at Joka under ground water based RASAPUNJA PIPE WATER SUPPLY SCHEME to accomodate FHTC in Thakurpukur-Maheshtala Block under South 24 Pgns W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (TSM/018477) | AE SWSD-II | JE1 | ORD/000382/2023-2024 | 1818/SWD-I | 16/08/2023 | 623 | BAIDYA ENTERPRISE | 30.15 | 10.5 | 30
1659 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for RASAPUNJA PIPE WATER SUPPLY SCHEME in BISHNUPUR-I & Thakurpukur-Mahestala Block for augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 5908) [TSM/018477]. | AE SWSD-II | JE1 | ORD/000417/2023-2024 | 1963/SWD-I | 24/08/2023 | 706 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 744.93 | 231.09 | 45
1660 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Temporary road repairing at Thakurpukur Bakhrahat Road under Rasapunja W/S Scheme under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/18576] | AE SWSD-II | JE1 | ORD/000713/2024-2025 | 4543/SWD-I | 06/11/2024 | 30 | SRIJON ENTERPRISE | 11.64 | 0 | 100
1661 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig Ground bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for the stand alone site at JOKA under RASAPUNJA PWSS of Thakurpukur-Maheshtala Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018477] | AE SWSD-II | JE1 | ORD/000725/2023-2024 | 391/SWD-I | 17/01/2024 | 30 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 15.89 | 15.43 | 100
1662 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Boundary wall for proposed pump house site under for Joka and Shibrampur including allied works for Rasapunja Piped Water Supply Schme under Thakurpukur Maheshtala Block, South 24 Pgs W/S Divn-I, P.H.E. Dte. (TSM/018477) | AE SWSD-II | JE1 | ORD/000793/2023-2024 | 1141/SWD-I | 07/03/2024 | 30 | MODERN CONSTRUCTION (DONGARIA) | 17.38 | 0 | 0
1663 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land development for construction of Pump house and other civil structures for Ground water based RASAPUNJA Piped Water Supply Scheme to accommodate FHTS in Thakurpukur Maheshtala block under South 24 Parganas W/S Divn-I, P.H.E Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Pgns. District. (SM/18576) [2nd call] | AE SWSD-II | JE1 | ORD/000796/2023-2024 | 1144/SWD-I | 07/03/2024 | 30 | MODERN CONSTRUCTION (DONGARIA) | 7.3 | 7.27 | 100
1664 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Supplying, Fabrication, Erection and Commissioning of Pressure Type Iron Elimination Plant (7.00 Cum capacity) at Joka including other allied works for Rasapunja Piped Water Supply Scheme to accommodate FHTC in Thakurpukur Mahestala Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/18576) | AE SWSD-II | JE1 | ORD/000812/2023-2024 | 1148/SWD-I | 07/03/2024 | 430 | AMRT INDUSTRIES PRIVATE LIMITED | 10.22 | 0 | 100
1665 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Supplying, Fabrication, Erection and Commissioning of Pressure Type Iron Elimination Plant (10.00 Cum capacity) at Sibrampur including other allied works for Rasapunja Piped Water Supply Scheme in Thakurpukur Mahestala Block under South 24 Pgs W/S Divn-I, P.H.E. Dte. (SM/18576) | AE SWSD-II | JE1 | ORD/000864/2024-2025 | 4922/SWD-I | 03/12/2024 | 30 | RAMASISH ENTERPRISE | 10.67 | 0 | 0
1666 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Rashapunja Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II | JE1 | ORD/000965/2022-2023 | 1168/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 3.11 | 3.05 | 100
1667 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Design, Supply, installation, trial run, commissioning of necessary pumping assembly including laying of Interconnection of rising main with header line and necessary Civil Works inclusive of 01(One) Year operation and maintenance and DLP for all components during maintenance period in connection to "Pipe Water Supply Scheme for Raspunja PWSS. (SM/18576) [Time of completion for construction and installation 45 days and 12 Months for subsequent O & M] | AE SWSD-II | JE1 | ORD/001097/2024-2025 | 5146/SWD-I | 16/12/2024 | 410 | RELIABLE CONSTRUCTIONS | 91.5 | 0 | 0
1668 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000177/2023-2024 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 36.39 | 0 | 0
1669 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE1 | RTOR000313/2023-2024 | 3117 | 07/12/2023 | 0 | Resource Division | 48.53 | 0 | 0
1670 | South 24 Pgs W/S Division I |  | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. |  |  | BILL/00665/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
1671 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for RAYNAGAR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018294] (2nd Call) |  |  | ORD/000369/2023-2024 | 1778/SWD-I | 11/08/2023 | 639 | N.A. ENTERPRISE | 47.65 | 0 | 34
1672 | South 24 Pgs W/S Division I |  | Construction of Platform and for providing FHTC , Construction of approach road and other allied works for Ground water based RAYNAGAR piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/18577) |  |  | ORD/000396/2024-2025 | 3680/SWD-I | 22/08/2024 | 45 | MILAN GHOSH | 93.83 | 0 | 0
1673 | South 24 Pgs W/S Division I |  | Construction of 500 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of RAYNAGAR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3284] [TSM/018294] |  |  | ORD/000519/2023-2024 | 2263/SWD-I | 14/09/2023 | 779 | M/S GHOSH AND CO. | 734.31 | 203.61 | 55
1674 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Raynagar Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000956/2022-2023 | 1306/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.95 | 2.91 | 100
1675 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 45.18 | 0 | 0
1676 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 197 to 198 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000107/2020-2021 | 1272/SWD-I | 23/11/2020 | 120 | BANIK BROTHERS | 27.48 | 54.17 | 0
1677 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nandarampur W/S Scheme for ChakNabashan Mouza and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000102/2020-2021 | 1273/SWD-I | 23/11/2020 | 120 | NIRMAL UDYOG | 25.27 | 48.84 | 0
1678 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Improvement of water supply by Interconnection from existing Big dia tube well and laying distribution system with CIDF, UPVC pipes Including providing Functional House Hold Tap Connection by retrofitting of scheme ¿Improvement of water supply [Phase-III] in Baruipur and Mograhat-II block¿ of Sankarpur-II GP within zone-43, covering Nur, Durgo, Balbalia, Surjopur hat mouzas under surface water based water supply scheme for arsenic affected areas of south 24- Parganas district. | AE BSD |  | ORD/000061/2021-2022 | 479 /SWD-I JJM | 07/07/2021 | 120 | M/S. S.S. ENTERPRISE | 193.14 | 136.05 | 0
1679 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Uttar Roypur W/S Scheme for Uttar Roypur, Balarampur (Part) and Chak Nabasan (Part) under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000080/2021-2022 | 1164/SWD-I JJM | 02/11/2021 | 120 | SRIJON ENTERPRISE | 141.41 | 138.51 | 100
1680 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte.(TSM / 8302) PART-III | AE SWSD-I |  | ORD/000461/2022-2023 | 2772/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 13.64 | 13.64 | 100
1681 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000102/2021-2022 | 1103/SWD-I | 25/10/2021 | 120 | PREMANANDA ROY BISWAS | 57.11 | 38.53 | 100
1682 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Betuabati W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8299) Part -D | AE SWSD-I |  | ORD/000462/2022-2023 | 2779/SWD-I | 31/01/2023 | 45 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 7.62 | 7.59 | 0
1683 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I |  | RTOR000123/2022-2023 | 3472/SWD-I | 15/03/2023 | 0 | Resource Division | 2.21 | 0 | 0
1684 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Betuabati W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | VCH/001194/2021-2022 | BP-2021-22-219 | 30/03/2022 | 0 | PREMANANDA ROY BISWAS | 15.5 | 0 | 0
1685 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Buita W/S Scheme (For Booth No:137 to 140) and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000078/2021-2022 | 1204/SWD-I JJM | 09/11/2021 | 120 | VISHAL CONSTRUCTION CO. | 254.11 | 250.68 | 100
1686 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.31] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00491/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 18.74 | 0 | 0
1687 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BARUIPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000163/2021-2022 | 1922/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.76 | 100
1688 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for BARUIPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/012660] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000182/2022-2023 | 1479/SWD-I | 27/09/2022 | 930 | PADMA ENGINEERING CO. | 40.17 | 16.92 | 100
1689 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at BARUIPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1018) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000217/2022-2023 | 1597/SWD-I | 18/10/2022 | 120 | SHRAYA ROADS LINE. | 330.06 | 69.19 | 100
1690 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at BARUIPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000291/2022-2023 | 1783/SWD-I | 07/11/2022 | 840 | ALISHA CONSTRUCTION | 10.93 | 4.67 | 100
1691 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based BARUIPUR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12261) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000863/2023-2024 | 1199/SWD-I | 11/03/2024 | 45 | M/S SHIBAM ENTERPRISE | 32.54 | 0 | 0
1692 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000267/2023-2024 | 2422/SWD-I | 30/09/2023 | 0 | Resource Division | 58.71 | 0 | 0
1693 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000334/2023-2024 | 271/SWD-I | 10/01/2024 | 0 | Resource Division | 6.27 | 0 | 0
1694 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Providing bullah pilling works and other allied works for the construction of the Boundary Wall at 1st Tubewell site of Panakua PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte. [SM/11494] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000002/2025-2026 | 905/SWD-I | 02/04/2025 | 30 | CONCORD PROJECTS PRIVATE LIMITED | 4.07 | 0 | 0
1695 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for PANAKUA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000028/2022-2023 | 912/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.2 | 13.42 | 100
1696 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed PANAKUA PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 993] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000148/2022-2023 | 1388/SWD-I | 21/09/2022 | 90 | NIRMAL UDYOG | 139.04 | 106.08 | 94
1697 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1698 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of PANAKUA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000223/2021-2022 | 1970/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.69 | 2.54 | 100
1699 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, additional laying of pipeline and other allied works for PANAKUA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11494] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000269/2024-2025 | 2918/SWD-I | 25/06/2024 | 45 | NIRMAL UDYOG | 66.18 | 0 | 0
1700 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 01/11/2022] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000316/2022-2023 | 1470/SWD-I | 27/09/2022 | 180 | NIRMAL UDYOG | 0.86 | 0.71 | 50
1701 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of PANAKUA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11494) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000428/2022-2023 | 2573/SWD-I | 10/01/2023 | 60 | GOUTAM MAZUMDER | 6.05 | 5.77 | 100
1702 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for PANAKUA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011229] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000594/2022-2023 | 3114/SWD-I | 24/02/2023 | 646 | DEBASHIS DAS | 15.88 | 0 | 98
1703 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development of Head work site (1st tube well) in connection with Ground Water Based PANAKUA Piped Water Supply Scheme to accomodation FHTC in Bishnupur-I Block under South 24 Pgs W/S Divn-I PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. [TSM/011229] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000808/2022-2023 | 3700/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.96 | 0.96 | 100
1704 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of temporary approach road, land development and allied works related to the 2nd Tubewell site of Panakua PWSS to accommodate FHTC in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte. South 24 Parganas District [SM/11494] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001073/2024-2025 | 5341/SWD-I | 30/12/2024 | 30 | DEBASHIS DAS | 5.13 | 0 | 0
1705 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000011/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 6.06 | 0 | 0
1706 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000115/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 28.03 | 0 | 0
1707 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for BHARU RAMKRISHNAPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000034/2022-2023 | 918/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.19 | 13.4 | 100
1708 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed BHARU RAMKRISHNAPUR PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 853] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000151/2022-2023 | 1391/SWD-I | 21/09/2022 | 1720 | ODISSI INNOVATIONS ENGINEERS PVT. LTD. | 132.6 | 100.57 | 90
1709 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 8.32 | 60
1710 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying rising main and additional pipeline for distribution system, construction of boundary wall, pump house, approach road and land development for BHARU RAMKRISHNAPUR PWSS of Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas (SM/11497) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000351/2024-2025 | 3363/SWD-I | 26/07/2024 | 60 | ODISSI INNOVATIONS | 132.11 | 0 | 5
1711 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "BHARU RAMKRISHNAPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000402/2022-2023 | 463/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 2.55 | 100
1712 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of BHARU RAMKRISHNAPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11497) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000431/2022-2023 | 2575/SWD-I | 10/01/2023 | 60 | OHAB SK. | 6.05 | 0 | 1
1713 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BHARU RAMKRISHNAPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011211] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000570/2022-2023 | 2974/SWD-I | 17/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.58 | 1.58 | 100
1714 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for BHARU RAMKRISHNAPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011211] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000585/2022-2023 | 3106/SWD-I | 24/02/2023 | 800 | MOULI CONSTRUCTION | 15.89 | 0 | 100
1715 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at 1st Tubewell site including development of approach road under Bharu Ramkrishnapur Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns Water Supply Division-I, PHE Dte. (TSM/011211) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000730/2023-2024 | 435/SWD-I | 22/01/2024 | 15 | ROYAL CONSTRUCTION | 8.92 | 6.5 | 50
1716 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed BHARU RAMKRISHNAPUR Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011211] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000812/2022-2023 | 3704/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.6 | 0.6 | 100
1717 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000017/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.25 | 0 | 0
1718 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000108/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 59 | 0 | 0
1719 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) for pipe water supply scheme at UTTAR BHAG of Baruipur Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur Sub-Division of South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1761] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000113/2023-2024 | 525/SWD-I | 11/05/2023 | 781 | JAL PRAVAHIKA PVT. LTD. | 527.08 | 172.56 | 80
1720 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of UTTAR BHAG Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000208/2021-2022 | 1948/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 2.76 | 100
1721 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for UTTAR BHAG Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, South 24 Parganas District for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/12231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000573/2024-2025 | 4272/SWD-I | 01/10/2024 | 30 | M/S SUNDARI CONSTRUCTION | 15.72 | 0 | 0
1722 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary wall including development of land and other allied works for Ground water based UTTAR BHAG piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/12231) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000856/2023-2024 | 1248/SWD-I | 13/03/2024 | 585 | ARNAB ENTERPRISE | 33.68 | 0 | 50
1723 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Head works site for UTTAR BHAG PWSS to accommodate FHTC in BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/12231] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000901/2023-2024 | 1328/SWD-I | 15/03/2024 | 15 | ARUP ENTERPRISE | 15.73 | 14.94 | 100
1724 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000189/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 26.57 | 0 | 0
1725 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cum. capacity OHR (20 mtr. staging height) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of ZONE-I NAYAPUKURIA MOUZA Piped Water Supply Scheme of JOYNAGAR-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 10830] [TSM/015333 & TSM/011546] | AE BSD |  | ORD/000568/2023-2024 | 2650/SWD-I | 27/10/2023 | 904 | M/S GHOSH AND CO. | 1544.66 | 0 | 75
1726 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000078/2022-2023 | 2994/SWD-I | 20/02/2023 | 0 | Resource Division | 60.86 | 0 | 0
1727 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system alongwith laying new distribution system in Zone-IX at Mandirbazar block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 3434] | AE HQ-I |  | ORD/000617/2022-2023 | 3217/SWD-I | 28/02/2023 | 763 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 250.59 | 63.16 | 15
1728 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000059/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 21.15 | 0 | 0
1729 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at KUNDARALI of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012662] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000116/2022-2023 | 1284/SWD-I | 14/09/2022 | 1080 | MA DURGA ENTERPRISE | 10.93 | 0 | 100
1730 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of additional 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 3rd Tubewell Site for KUNDARALI PWSS to accommodate FHTC in Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte. for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Pgns. District. [SM/12266] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000128/2025-2026 | 2026/SWD-I | 04/08/2025 | 30 | DEV & COMPANY | 15.9 | 0 | 0
1731 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KUNDALI Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000162/2021-2022 | 1924/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.76 | 100
1732 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for KUNDARALI PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/012662] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000188/2022-2023 | 1481/SWD-I | 27/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 17.92 | 100
1733 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at KUNDARALI of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1571) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000221/2022-2023 | 1639/SWD-I | 20/10/2022 | 1138 | PROJECT AND MAINTENANCE | 333.83 | 220.29 | 98
1734 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall, Platform for providing FHTC, Protection works for Pipeline and other allied Works for ''Proposed Ground Water based KUNDARALI piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District.'' (SM/12266) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000367/2024-2025 | 3507/SWD-I | 07/08/2024 | 495 | PROJECT AND MAINTENANCE | 96.98 | 14.73 | 30
1735 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kundarali PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/012662] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000798/2022-2023 | 3671/SWD-I | 29/03/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 2.2 | 100
1736 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000269/2023-2024 | 2423/SWD-I | 30/09/2023 | 0 | Resource Division | 64.82 | 0 | 0
1737 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000306/2023-2024 | 2443/SWD-I | 30/09/2023 | 0 | Resource Division | 54.51 | 0 | 0
1738 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-11C-6886] "(w.e.f. 01/06/2025 to 30/11/2025) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000061/2025-2026 | 1370/SWD-I | 22/05/2025 | 183 | SRIMANTA MONDAL | 0.87 | 0.4 | 100
1739 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte." (w.e.f. 01/06/2023 to 30/11/2023. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000183/2023-2024 | 775/SWD-I | 31/05/2023 | 183 | SRIMANTA MONDAL | 0.87 | 2.39 | 30
1740 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-19E-2060] " (w.e.f. 01/06/2024 to 30/11/2024) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000197/2024-2025 | 2355/SWD-I | 24/05/2024 | 183 | SRIMANTA MONDAL | 0.87 | 2.36 | 18
1741 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of "BARULI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/12212) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000237/2024-2025 | 2657/SWD-I | 07/06/2024 | 45 | M/S B.M. INDUSTRIES | 47.54 | 0 | 0
1742 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (two) nos. Rig bored Tube well 250mm x 150mm dia & 300 mtr. deep for BARULI Piped Water Supply Scheme at headwork site & 2nd Tubewell site in Sonarpur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000263/2022-2023 | 1775/SWD-I | 07/11/2022 | 30 | TAPAS KUMAR GIRI | 30.07 | 28.32 | 0
1743 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BARULI Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1435] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000496/2022-2023 | 2864/SWD-I | 09/02/2023 | 1200 | M/S B.M. INDUSTRIES (BM.INDUSTRY@GMAIL.COM) | 391.4 | 188.62 | 60
1744 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-19E-2060] " (w.e.f. 01/12/2023 to 31/05/2024) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000673/2023-2024 | 2998/SWD-I | 29/11/2023 | 183 | SRIMANTA MONDAL | 0.87 | 2.38 | 15
1745 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BARULI PWSS at headwork site & 2nd Tube-well site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014838] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000767/2022-2023 | 3604/SWD-I | 24/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 3.14 | 0
1746 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation Order for the work of "Hiring of diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer (HQ-I), South 24-Pgns. W/S Division-I, PHE Dte. [Vehicle No- WB-11C-6886] "(w.e.f. 01/12/2024 to 31/05/2025) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000889/2024-2025 | 4876/SWD-I | 29/11/2024 | 182 | SRIMANTA MONDAL | 0.86 | 2.36 | 20
1747 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000008/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 7.88 | 0 | 0
1748 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000228/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 8.84 | 0 | 0
1749 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Payment of Enhanced GST Rate vide W/O No.1689/SWD-I dt. 01/11/2022 | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/02030/2023-2024 | BP-2023-24-756 | 13/03/2024 | 0 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 19.39 | 0 | 0
1750 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR SHAKSAHAR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 882, KHATIAN NO. 843, JL. NO. 104, MOUZA - CHAKBHIKA) & 2ND TUBE WELL SITE (DAG NO. 308, KHATIAN NO. 567, JL NO. 119, MOUZA - SHAKSAHAR), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 757/SWD-I | 29/06/2022 | 30 | SIMPLEX DRILLING CO. | 28.39 | 26.63 | 50
1751 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of low Land and temporary approach road entering 1st Tubewell site for SHAKSAHAR pipe water supply scheme in Bhangar-I block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000066/2023-2024 | 90/SWD-I | 06/04/2023 | 15 | CIVILEX COMBINE | 0.61 | 0.61 | 100
1752 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of low Land and temporary approach road entering 2nd Tubewell site SHAKSAHAR pipe water supply scheme in Bhangar-I block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. Water Supply Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000067/2023-2024 | 91/SWD-I | 06/04/2023 | 15 | CIVILEX COMBINE | 0.55 | 0.47 | 100
1753 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Shaksahar Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000227/2022-2023 | 1689/SWD-I | 01/11/2022 | 300 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 526.17 | 361.98 | 68
1754 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for Sinking of 01 (One) no. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell to achive 66 mtr. housing pipe by Rotary method for SHAKSAHAR PWSS at 2nd Tubewell site of Bhangar-I Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/0010765] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000292/2023-2024 | 1398/SWD-I | 13/07/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.57 | 1.57 | 100
1755 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for proposed OHR Site of SHAKSAHAR Piped Water Suplly Scheme in BHANGAR-I Block in South 24-Pgns West Bengal, under South 24 Paraganas W/S Division-I, P.H.E. Dte. [SM/11275] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000509/2023-2024 | 2247/SWD-I | 13/09/2023 | 30 | MS KRISHNA MONDAL | 29.66 | 17.13 | 10
1756 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of SHAKSAHAR PWSS within Bhangar-I Block "SHAKSAHAR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/11275) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000757/2024-2025 | 4678/SWD-I | 18/11/2024 | 60 | ASHIANA INFRASTRUCTURE CONSULTANTS PVT LTD. | 77.5 | 0 | 0
1757 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000020/2022-2023 | 1921/SWD-I | 18/11/2022 | 0 | Resource Division | 13.92 | 0 | 0
1758 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000033/2022-2023 | 2689/SWD-I | 20/01/2023 | 0 | Resource Division | 15.91 | 0 | 0
1759 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Purba Gabberia Zone-I PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010747] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 41/SWD-I | 06/04/2023 | 15 | K P CONSTRUCTION | 4.41 | 4.23 | 100
1760 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PURBA GABBERIA (Zone-I) of Joynagar-I Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/010754] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000156/2022-2023 | 1409/SWD-I | 22/09/2022 | 60 | NIRMAN | 11.01 | 0 | 100
1761 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PURBA GABBERIA (Zone-I) PWSS of Joynagar-I Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/010747] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000243/2022-2023 | 1686/SWD-I | 01/11/2022 | 30 | K P CONSTRUCTION | 42.29 | 35.45 | 90
1762 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at PURBO GABBERIA (Zone-I) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1909) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000274/2022-2023 | 1808/SWD-I | 09/11/2022 | 1200 | PASCON | 449.74 | 282.8 | 65
1763 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PURBA GABBERIA(I) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000364/2021-2022 | 1929/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.72 | 100
1764 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000069/2023-2024 | 291/SWD-I | 24/04/2023 | 0 | Resource Division | 240.21 | 0 | 0
1765 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for RAMGOPALPUR PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000092/2022-2023 | 1204/SWD-I | 02/09/2022 | 30 | PAPPU ENTERPRISE | 20.06 | 16.83 | 100
1766 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at RAMGOPALPUR of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [Nos of FHTC- 566] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000098/2022-2023 | 1209/SWD-I | 02/09/2022 | 942 | MONDAL CONSTRUCTION | 91.26 | 85.78 | 98
1767 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at RAMGOPALPUR of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012521] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000120/2022-2023 | 1288/SWD-I | 14/09/2022 | 60 | LAKSHMI IRON | 5.44 | 4.4 | 100
1768 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of RAMGOPALPUR Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000205/2021-2022 | 1918/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 2.46 | 100
1769 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 01 (One) no. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for RAMGOPALPUR PWSS of BARUIPUR Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/012521] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000454/2023-2024 | 2109/SWD-I | 30/08/2023 | 15 | PAPPU ENTERPRISE | 2.2 | 0 | 100
1770 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based RAMGOPALPUR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12058) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000907/2023-2024 | 1206/SWD-I | 11/03/2024 | 630 | S.S. CONSULTANCY & CONSTRUCTION | 21.03 | 0 | 55
1771 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000273/2023-2024 | 2418/SWD-I | 30/09/2023 | 0 | Resource Division | 4.19 | 0 | 0
1772 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000337/2023-2024 | 270/SWD-I | 10/01/2024 | 0 | Resource Division | 3.04 | 0 | 0
1773 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
1774 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary wall, Pump House, Development of Land, Laying of Rising Main, Distribution Pipeline and Other Allied works for Kaikhali PWSS to accomodate FHTC in Bishnupur-I Block, under South 24-Pgns W/S Divn-I, PHE Dte. For Augmentation of surface water based W/S scheme in the arsenic affected areas of South 24-Pgns disct. (SM/11730) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000267/2024-2025 | 2682/SWD-I | 07/06/2024 | 45 | SHRAYA ROADS LINE. | 52.47 | 0 | 10
1775 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "KAIKHALI Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000409/2022-2023 | 466/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 2.55 | 100
1776 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of KAIKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11730) | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000433/2022-2023 | 2577/SWD-I | 10/01/2023 | 60 | N&N ENTERPRISE | 6.04 | 0 | 0
1777 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based KAIKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Based W/S Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block within South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 790 nos.] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000447/2022-2023 | 2685/SWD-I | 20/01/2023 | 90 | M/S BIMALENDU BOSE | 122.59 | 93.93 | 82
1778 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KAIKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011788] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000521/2022-2023 | 2911/SWD-I | 14/02/2023 | 15 | M/S PURE RENOVATION CONSTRUCTION GROUP (EMAIL ID-SAJIDMOLLA93@GMAIL.COM) | 1.57 | 0 | 0
1779 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for KAIKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011788] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000553/2022-2023 | 3043/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
1780 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for KAIKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11730] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000585/2023-2024 | 2753/SWD-I | 07/11/2023 | 30 | SAIKAT ENTERPRISE | 15.03 | 0 | 20
1781 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KAIKHALI PWSS of BISHNUPUR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11730] | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | ORD/000784/2023-2024 | 1067/SWD-I | 04/03/2024 | 15 | SAIKAT ENTERPRISE | 1.57 | 0 | 0
1782 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE4,Junior Engineer | RTOR000104/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 32.27 | 0 | 0
1783 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of GANGRAI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11493) (2nd Call) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000095/2023-2024 | 452/SWD-I | 04/05/2023 | 60 | A.M. ENTERPRISE (BASIRHAT) | 6.04 | 5.82 | 100
1784 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for GANGARAI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11732] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000174/2022-2023 | 1449/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.26 | 13.46 | 100
1785 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
1786 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of GANGRAL AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000233/2021-2022 | 1976/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.55 | 100
1787 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for GANGARAI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/11732] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000268/2024-2025 | 2919/SWD-I | 25/06/2024 | 45 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 86.61 | 0 | 0
1788 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based GANGRAI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 882 nos.] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000417/2022-2023 | 2471/SWD-I | 30/12/2022 | 748 | MS BUILDWELL | 125.23 | 104.9 | 80
1789 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for GANGRAI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011791] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000526/2022-2023 | 2921/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 100
1790 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for GANGRAI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011791] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000557/2022-2023 | 3047/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
1791 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000030/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.43 | 0 | 0
1792 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000113/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 23.5 | 0 | 0
1793 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length = 51.00m), Service Road (length = 15.00m), Development of Land, Construction of Pump House (4.80 Mtr. X 3.60 Mtr.) at TW-2 site and Pump House (5.40 Mtr. X 3.60 Mtr.) at OHR site for RAMCHANDRANAGAR (Part-II) PWSS to accommodate FHTC in MAGRAHAT-II Block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12805) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000010/2025-2026 | 934/SWD-I | 07/04/2025 | 60 | SUBHO CONSTRUCTION | 19.99 | 0 | 0
1794 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Ramchandra Nagar (Zone-II) PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000297/2022-2023 | 1883/SWD-I | 16/11/2022 | 30 | MERAJUL ALAM | 29.97 | 0 | 0
1795 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Land development, Construction of Boundary wall (length = 204.00m) & Construction of Service Road (length = 140.00m) at OHR site for RAMCHANDRANAGAR (Part-II) PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns, W/S Divn-I, for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas. (SM/12805) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000365/2024-2025 | 3510/SWD-I | 07/08/2024 | 45 | PRONICON INDIA | 54.27 | 0 | 0
1796 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "RAMCHANDRANAGAR (PART-II) Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000394/2022-2023 | 408/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.76 | 2.64 | 0
1797 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of RAMCHANDRANAGAR (Part-II) of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1580] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000490/2022-2023 | 2820/SWD-I | 03/02/2023 | 1063 | NEW ALIGNMENT | 384.03 | 99.37 | 40
1798 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Ramchandra Nagar (II) PWSS of Mograhat- II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014755] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000629/2022-2023 | 3256/SWD-I | 02/03/2023 | 15 | MERAJUL ALAM | 3.14 | 0 | 0
1799 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Repairing of Damaged road by Laying of pipe line for Ground water based RAMCHANDRANAGAR (Part-II) piped water supply scheme to accommodate FHTC in MAGRAHAT-II Block under South 24-Pgns, Water Supply Division-I, South 24-Pgns. District for Augmentation of surface water based water supply scheme in the Arsenic Affected Areas of South 24-Parganas District. (SM/12805) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000674/2024-2025 | 4463/SWD-I | 29/10/2024 | 60 | MOTIONMASS TECHNO OPC PVT LTD | 21.67 | 0 | 0
1800 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000195/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 25.52 | 0 | 0
1801 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of damages due to laying of water-line by PHE Directorate at Durgapur Station Road to Hotor and Mahespur connecting Road from 0.0 Km to 2.4 Km under South 24 pgs. Division, PWD in the district of South 24 Pgs during the year 2021-2022 of 50% of estimate value i.e. Rs.65,08,952/- x 50% = Rs.32,54,476/- as per minutes of meeting taken by HMIC, PHED with SEs on 12th Sept, 2022. | AE BSD |  | BILL/00564/2023-2024 | BP-2023-24-266 | 25/08/2023 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 32.54 | 0 | 0
1802 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Interconnection including laying distribution system from Big dia Tube well covering Chandanpukur, Bagdaha, Dhanberia, Durgapur & Gazipur mouzas for improvement of water supply & Providing functional house hold tap connection within Sikharbali-II G.P of Baruipur Block, South 24 Paraganas District. | AE BSD |  | ORD/000303/2020-2021 | 2132/SWD-I | 26/02/2021 | 120 | ALOK ENTERPRISE | 169.36 | 125.33 | 100
1803 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Protection work by drum sheet walling on Sal-bullah / Eucaliptus bullah piling for protection of rising main at chandanpukur site of shikharbali-II G.P under Baruipur Sub-Division of South24-Pgns, W/S Division-I, P.H.E.Dte. | AE BSD |  | ORD/000996/2022-2023 | 1079/SWD-I | 16/08/2022 | 15 | MONDAL CONSTRUCTION (BARUIPUR) | 1.18 | 1.15 | 100
1804 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Zone-VI at Mandirbazar block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. (TSM/010830) [10th SLSSC (2021-22)] | AE HQ-I |  | ORD/000770/2022-2023 | 3644/SWD-I | 28/03/2023 | 825 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 192.73 | 30.44 | 55
1805 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I |  | RTOR000055/2022-2023 | 3015/SWD-I | 20/02/2023 | 0 | Resource Division | 19.44 | 0 | 0
1806 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for SALPUKURIA Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11783] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000178/2022-2023 | 1453/SWD-I | 26/09/2022 | 30 | DIPALI CONSTRUCTION | 14.26 | 0 | 5
1807 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/05/2023 to 30/09/2023) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000180/2023-2024 | 333/SWD-I | 25/04/2023 | 153 | NIRMAL UDYOG | 0.73 | 1.95 | 30
1808 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1809 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of SALPUKURIA AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XVIII) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000226/2021-2022 | 1971/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.69 | 2.65 | 100
1810 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, Pump house, laying of additional pipeline and other allied works for SALPUKURIA PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/11783] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000249/2024-2025 | 2669/SWD-I | 07/06/2024 | 45 | BHASKAR MONDAL | 72.69 | 0 | 5
1811 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based SALPUKURIA PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 910 nos.] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000416/2022-2023 | 2470/SWDI | 30/12/2022 | 90 | BHASKAR MONDAL | 179.64 | 109.96 | 90
1812 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of SALPUKURIA Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11783) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000429/2022-2023 | 2574/SWD-I | 10/01/2023 | 60 | LAKSHMI IRON | 6.04 | 0 | 87
1813 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for SALPUKURIA PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011734] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000520/2022-2023 | 2910/SWD-I | 14/02/2023 | 15 | DIPALI CONSTRUCTION | 1.57 | 0 | 0
1814 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for SALPUKURIA PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011734] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000593/2022-2023 | 3113/SWD-I | 24/02/2023 | 30 | DEBASHIS DAS | 15.87 | 15.76 | 98
1815 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/10/2023 to 29/02/2024) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000623/2023-2024 | 2388/SWD-I | 27/09/2023 | 152 | NIRMAL UDYOG | 0.72 | 1.54 | 99
1816 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at Salpukuria Piped Water Supply Scheme for 1st Tubewell site in the Arsenic affected areas of South 24-Parganas Water Supply Division-I, PHE Dte. (SM/11783) | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000749/2023-2024 | 525/SWD-I | 29/01/2024 | 15 | KALAM ENTERPRISE | 3.35 | 3.29 | 99
1817 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell for SALPUKURIA Piped Water Supply Scheme in BISHNUPUR-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [SM/11783] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000789/2023-2024 | 1072/SWD-I | 04/03/2024 | 30 | MONDAL TUBEWELL | 15.9 | 0 | 98
1818 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/03/2024 to 31/08/2024) [Vehhicle No - WB-19J-3488] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000909/2023-2024 | 917/SWD-I | 21/02/2024 | 184 | NIRMAL UDYOG | 0.87 | 2.23 | 70
1819 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/09/2024 to 28/02/2025) [Vehhicle No - WB-19J-3488] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001063/2024-2025 | 3766/SWD-I | 28/08/2024 | 181 | NIRMAL UDYOG | 0.86 | 2.18 | 70
1820 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Continuation Order for the work of "Hiring of additional 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-II under South 24-Pgns. W/S Division-I, PHE Dte. (w.e.f. 01/03/2025 to 31/08/2025) [Vehhicle No - WB-19J-3488] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001204/2024-2025 | 581/SWD-I | 25/02/2025 | 184 | NIRMAL UDYOG | 0.87 | 0.75 | 0
1821 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000027/2022-2023 | 2555/SWD-I | 09/01/2023 | 0 | Resource Division | 5.61 | 0 | 0
1822 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000100/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 23.31 | 0 | 0
1823 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for PURBO BEGAMPUR (ZONE-I) PWSS of Baruipur Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000081/2022-2023 | 1192/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 18.94 | 100
1824 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based PURBA BEGAMPUR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11784) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000302/2024-2025 | 3215/SWD-I | 18/07/2024 | 60 | SRIJON ENTERPRISE | 36.54 | 0 | 0
1825 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at BEGAMPUR (ZONE-I) Mouza of BARUIPUR Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1967) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000344/2022-2023 | 2149/SWD-I | 08/12/2022 | 1028 | GHOSH ENTERPRISE | 557.87 | 451.71 | 90
1826 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Begampur (Zone-I) at Baruipur Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000364/2022-2023 | 2207/SWD-I | 13/12/2022 | 60 | PRAGATI CONSTRUCTION AND CO. | 11.51 | 0 | 0
1827 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SITAKUNDU(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000445/2021-2022 | 1951/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 0 | 100
1828 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BEGAMPUR(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000455/2021-2022 | 1951/SWD_I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.76 | 100
1829 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PURBA BEGAMPUR [Zone-I] PWSS of Baruipur Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/11748] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000805/2023-2024 | 1290/SWD-I | 15/03/2024 | 15 | TAPAS KUMAR GIRI | 4.41 | 0 | 100
1830 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls including development of land and other allied works for Ground water based PURBA BEGAMPUR (ZONE-I) piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/11784) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000857/2023-2024 | 1249/SWD-I | 13/03/2024 | 45 | SRIJON ENTERPRISE | 43.44 | 0 | 0
1831 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000086/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 12.85 | 0 | 0
1832 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for KAMARIA (ZONE-IV) PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000084/2022-2023 | 1195/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 40.13 | 36.22 | 100
1833 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation along with Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KAMARIA (ZONE-IV) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2051) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000278/2022-2023 | 1841/SWD-I | 11/11/2022 | 300 | MANASH GHOSH | 411.42 | 178.97 | 50
1834 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of KAMARIA (IV) Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000362/2021-2022 | 1964/SWD-I | 27/01/2022 | 30 | MS R. DUTTA AND CO | 2.76 | 2.61 | 100
1835 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Kamaria (Zone-IV) of Jaynagar-I Block uunder Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000382/2022-2023 | 2215/SWD-I | 13/12/2022 | 60 | ALISHA CONSTRUCTION | 11.52 | 4.77 | 50
1836 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kamaria Zone-IV PWSS of Joynagar-I Block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011004] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000743/2022-2023 | 3587/SWD-I | 23/03/2023 | 15 | TAPAS KUMAR GIRI | 4.41 | 4.41 | 100
1837 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscelleneous work for KAMARIA ZONE - IV piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 pgns district. (SM/11788) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000912/2023-2024 | 1202/SWD-I | 11/03/2024 | 630 | BANGA NIRMAN | 16.78 | 0 | 30
1838 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000078/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 13.73 | 0 | 0
1839 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform for providing FHTC for Ground Water Based GARIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/13443) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000303/2024-2025 | 3216/SWD-I | 18/07/2024 | 60 | TIRUPATI ENTERPRISES | 36.67 | 0 | 0
1840 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of GARIA Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000311/2021-2022 | 1955/SWD-I | 27/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.76 | 2.76 | 100
1841 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for GARIA PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13443] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000567/2022-2023 | 3063/SWD-I | 21/02/2023 | 30 | M/S MONDAL ENTERPRISE | 31.75 | 18.76 | 50
1842 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system, Rising Main, Functional House Hold Tap Connection (FHTC) alongwith construction of Chlorine Room (two nos.) for Augmentation of GARIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. [No. of FHTC = 1970] [TSM/015205] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000626/2023-2024 | 20/SWD-I | 05/04/2023 | 90 | TIRUPATI ENTERPRISES | 360.05 | 229.88 | 85
1843 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000140/2022-2023 | 3423/SWD-I | 13/03/2023 | 0 | Resource Division | 12.14 | 0 | 0
1844 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000190/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 22.21 | 0 | 0
1845 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Jamalpur W/S Scheme for habitations of Jamalpur Mouza and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000113/2020-2021 | 1415/SWD-I | 14/12/2020 | 120 | J.D. CONSTRUCTION | 80.07 | 146.4 | 0
1846 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Jamalpur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6138) Part -G | AE SWSD-I |  | ORD/000469/2022-2023 | 2781/SWD-I | 31/01/2023 | 45 | M/S ASHA ENGINEERING | 2.27 | 2.24 | 100
1847 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road edge and Hard shoulder damaged due to laying of pipes by PHE Dte. of Dakshin Barasat Mograhat Usthi Road from 0.00 kmp to 21.0 kmp in different stretched of Diamond Harbour Highway Sub-Division under Diamond Harbour Highway Division in the district of South 24 Parganas | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | BILL/00653/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 20.8 | 0 | 0
1848 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional Laying of Pipeline for distribution system of HARISANKARPUR piped water supply scheme to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 pgs. District. (SM/14643) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000085/2025-2026 | 1760/SWD-I | 02/07/2025 | 60 | BAIDYA ENTERPRISE | 51.8 | 0 | 0
1849 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 360 mtr. deep Tubewell by Rotary method at Harisankarpur 2nd & 3rd Tubewell site for HARISANKARPUR Piped Water Supply Scheme of MOGRAHAT-II Block under South 24-Parganas W/S Division-I, PHE Dte. [SM/14643] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000093/2025-2026 | 1768/SWD-I | 02/07/2025 | 30 | PADMA ENGINEERING CO. | 38.27 | 0 | 0
1850 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 161.9 | 8
1851 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Renovation of approach Road inside of the head work site and construction of entrance gate for Harishankarpur PWSS to accommodate FHTC in Magrahat-II block South 24-Parganas district. for augmentation of surface water Based water Supply Scheme in the arsenic Affected areas of South 24-Parganas District. (SM/14643) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000427/2024-2025 | 3784/SWD-I | 29/08/2024 | 30 | N & N ENTERPRISE | 6.5 | 0 | 50
1852 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Harisankarpur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000984/2022-2023 | 1477/SWD-I | 27/09/2022 | 30 | MEASURE LAND | 2.76 | 2.72 | 100
1853 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional estimate for construction of approach road inside of the Head work site for existing HARISANKARPUR PWSS under MAGRAHAT-II Block, South 24 Parganas Distnct for Augmentation of surfacc water based water supply scheme in the Arsenic affected areas of South 24 Parganas District under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/14643) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/001078/2024-2025 | 5346/SWD-I | 30/12/2024 | 15 | N & N ENTERPRISE | 3 | 0 | 60
1854 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000199/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 60.24 | 0 | 0
1855 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000311/2023-2024 | 2737/SWD-I | 06/11/2023 | 0 | Resource Division | 18.95 | 0 | 0
1856 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 963 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 9.15 | 15
1857 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PUNPO Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000293/2021-2022 | 1925/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.62 | 0
1858 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for PUNPO PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000501/2022-2023 | 2890/SWD-I | 13/02/2023 | 30 | IQBAL CONSTRUCTION (EMAIL ID- AANPI8149M@GMAIL.COM) | 31.77 | 22.65 | 50
1859 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000088/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 32.55 | 0 | 0
1860 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000139/2022-2023 | 3422/SWD-I | 13/03/2023 | 0 | Resource Division | 10.39 | 0 | 0
1861 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, service road & toilet for pump house at 3rd Tube well site for BENIPUR PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [SM/14659] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000027/2025-2026 | 979/SWD-I | 09/04/2025 | 135 | MAHABUB RAHAMAN LASKAR | 11.79 | 0 | 60
1862 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of Additional Pipeline for distribution system for BENIPUR piped water supply scheme to accommodate FHTC in Mograhat-II Block under South 24 Parganas W/S Division-I, PHE Dte. for augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 pgs. District (SM/14659) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000086/2025-2026 | 1761/SWD-I | 02/07/2025 | 45 | AHANA ENTERPRISE | 13.36 | 0 | 0
1863 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BENIPUR PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017337] (2nd Call) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000093/2023-2024 | 450/SWD-I | 04/05/2023 | 90 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 47.69 | 44.08 | 66
1864 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 10 (ten) nos. chlorination room of size 5.0m x 4.0m for PANCHPARA, DHANPOTA, BENIPUR & HARISANKARPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9957] [TSM/017504, TSM/016727, TSM/017337, TSM/016566] | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000106/2023-2024 | 483/SWD-I | 08/05/2023 | 887 | S & P ENTERPRISE | 1866.59 | 190.37 | 8
1865 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of boundary wall, construction of service road and land development with protection work at 2nd Tubewell site for BENIPUR PWSS under Gokarnee G.P within Mograhat-II Block under Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District of South 24 Parganas. [Length - 43.0 mtr.] (SM/14659) | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000684/2024-2025 | 4479/SWD-I | 30/10/2024 | 300 | R.K ENTERPRISE | 12.01 | 0 | 75
1866 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Benipur Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | ORD/000985/2022-2023 | 1482/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.92 | 2.82 | 100
1867 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000162/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 64.27 | 0 | 0
1868 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | RTOR000310/2023-2024 | 2735/SWD-I | 06/11/2023 | 0 | Resource Division | 15.99 | 0 | 0
1869 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of BANBERA MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2949] [TSM/018364] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 842/SWD-I | 05/06/2023 | 90 | RELIABLE CONSTRUCTIONS | 349.93 | 289.34 | 85
1870 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (four) nos. Rig Ground bored 250mm x 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for BANBERA (Zone-40) Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block Block for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under South 24 Paraganas W/S Division-I, PHE Dte. (SM/14858) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000445/2024-2025 | 3895/SWD-I | 04/09/2024 | 213 | ASIT PRAMANIK | 63.43 | 0 | 50
1871 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for providing FHTC, restoration of road damaged due to laying of pipeline and other allied works for Ground Water based BANBERA piped water supply scheme to accommodate FHTC in BARUIPUR Block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/14858) [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000717/2024-2025 | 4551/SWD-I | 06/11/2024 | 45 | SANA ENTERPRISE | 73.31 | 0 | 0
1872 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based BANBERIA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000923/2022-2023 | 1176/SWD-I | 31/08/2022 | 30 | ASTER CONSULTANCY | 3.01 | 3.01 | 100
1873 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000144/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.39 | 0 | 0
1874 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.38] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00468/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 30.72 | 0 | 0
1875 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1996] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000064/2023-2024 | 243/SWD-I | 20/04/2023 | 300 | ASSOCIATED CONSTRUCTION AND CONSULTANCY | 449.98 | 330.14 | 35
1876 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for MADHABPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015478] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000628/2022-2023 | 3237/SWD-I | 01/03/2023 | 30 | MRA NIRMAN UDYOG | 31.77 | 31.66 | 100
1877 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and other allied works at HW & 2nd Tubewell site of "MADHABPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13778) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000675/2024-2025 | 4464/SWD-I | 29/10/2024 | 45 | REALIENCE CONSTRUCTION | 91.13 | 0 | 0
1878 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000057/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 9.67 | 0 | 0
1879 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000223/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.3 | 0 | 0
1880 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of MALLIKPUR (PART-III) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1718] [TSM/012612] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 482/SWD-I | 08/05/2023 | 90 | RANJIT KAR | 161.99 | 0 | 0
1881 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MALLIKPUR , PART-III Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000204/2021-2022 | 1920/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.72 | 100
1882 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for MALLICKPUR (PART-III) PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13444] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000569/2022-2023 | 3065/SWD-I | 21/02/2023 | 30 | MD NURUZZUMAN (EMAIL ID- MDNGRPKR@GMAIL.COM) | 47.64 | 15.07 | 34
1883 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000166/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 42.16 | 0 | 0
1884 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.28] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/00488/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 11.1 | 0 | 0
1885 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 300 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of BRINDAKHALI (Zone-I) Mouza of BARUIPUR Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 1773) [TSM/015376] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000062/2023-2024 | 366/SWD-I | 27/04/2023 | 976 | M/S V.P. JAIN | 395.19 | 251.91 | 98
1886 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based BRINDAKHALI ZONE-I Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/13309) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000338/2024-2025 | 3312/SWD-I | 23/07/2024 | 45 | M/S V.P. JAIN | 91.18 | 0 | 0
1887 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of BRINDAKHALI(I) Ground Water Based Piped Water Supply Scheme in BARUIPUR PURBA Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000509/2021-2022 | 1942/SWD-I | 27/01/2022 | 30 | RADIANT | 2.76 | 2.64 | 100
1888 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for BRINDAKHALI-I PWSS of BARUIPUR block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [SM/13309] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000562/2022-2023 | 3059/SWD-I | 21/02/2023 | 30 | ABDUL LOTIB MOLLA | 31.76 | 14.46 | 50
1889 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000127/2022-2023 | 3328/SWD-I | 09/03/2023 | 0 | Resource Division | 10.92 | 0 | 0
1890 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000186/2023-2024 | 296/SWD-I | 25/04/2023 | 0 | Resource Division | 28.44 | 0 | 0
1891 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | "ANANDAPUR-KHARKI-BOYNALA-TARDAH ROAD-Restoration of road side flank damaged by PHE Department under bhojerhat pipeline project from 3.872 km to 4.195 km (left side),3.475 km to 4.095 km (R/S),[Total length=943.00m] under South 24-Parganas Highway Division." | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00497/2024-2025 |  | 13/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 12.1 | 0 | 0
1892 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | 50% Payment for ANANDAPUR-KHARKI-BOYNALA-TARDAH ROAD-Restoration of road side flank damaged by PHE Department under bhojerhat pipeline project from 3.872 km to 4.195 km (left side),3.475 km to 4.095 km (R/S),[Total length=943.00m] under South 24-Parganas Highway Division | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00534/2024-2025 | BP-2024-25-308 | 18/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.05 | 0 | 0
1893 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road Side Flank damaged by PHE Department under Bhojerhat Pipe Line Project from 3,872 km to 4.195 km (Left Side) 3.475 km to 4.095km (RS) [Total Length - 943.00m] under South 24 Parganas Highway Division" | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00546/2024-2025 | BP-2024-25-338 | 25/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.23 | 0 | 0
1894 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Kolkata Basanti Road from 12.427 km to 15.581 km, Permanent restoration work , damaged due to " Pipeline Laying of 90mm,140mm, & 225mm dia HDPE Pipoe Line along road flank by PHE Department " within Alipore Highway Sub-Division under South 24 Parganas Highway Division in the District of South 24 Parganas. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00850/2024-2025 | BP-2024-25-504 | 11/12/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 6.92 | 0 | 0
1895 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling work with Drumsheet walling, Approach Road and Road Restoration of BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000260/2024-2025 | 2857/SWD-I | 20/06/2024 | 275 | BOSE ENTERPRISES | 164.67 | 101.27 | 45
1896 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional Laying of distribution Network System for different dia HDPE pipe under Bhatipota PWSS, Block-Bhangar-I, Dist-South 24 Parganas to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1942] (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000617/2023-2024 | 2801/SWD-I | 09/11/2023 | 60 | K.K. BUILDER. | 34.34 | 34.28 | 55
1897 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for BHATIPOTA PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/015204] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000621/2022-2023 | 3235/SWD-I | 01/03/2023 | 30 | SETABUR RAHAMAN | 31.67 | 15.18 | 50
1898 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1942] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000710/2022-2023 | 3527/SWD-I | 17/03/2023 | 787 | K.K. BUILDER. | 465.21 | 386.71 | 70
1899 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (Two) nos. Pipe Carrying Structure- Near Bhatipota OHR Site over 56.0 mtr. width canal and Near Kolkata-Basanti Highway,opp. Kolkata Leather Complex Police Station over 66.0 mtr. width canal within Bhatipota Mouza of Tardaha GP under Bhangar-I Block, BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000738/2023-2024 | 523/SWD-I | 29/01/2024 | 45 | GANAPATI ENTERPRISE | 31.83 | 31.74 | 100
1900 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of BHATIPOTA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13341) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000765/2024-2025 | 4686/SWD-I | 18/11/2024 | 60 | K.K. BUILDER | 23.12 | 0 | 52
1901 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000049/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 21.02 | 0 | 0
1902 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000217/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 11.96 | 0 | 0
1903 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 350 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DAKSHIN KASHI MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2171] [TSM/017968] | Assistant Engineer | Junior Engineer | ORD/000036/2023-2024 | 122/SWD-I | 12/04/2023 | 811 | KUDUCH MOLYA | 388.6 | 57.4 | 55
1904 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based DAKSHIN KASHI piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14870) | Assistant Engineer | Junior Engineer | ORD/000301/2024-2025 | 3199/SWD-I | 16/07/2024 | 259 | KUDUCH MOLYA | 269.02 | 0 | 50
1905 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for DAKSHIN KASHI PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017968][2nd Call] | Assistant Engineer | Junior Engineer | ORD/000688/2022-2023 | 3477/SWD-I | 15/03/2023 | 30 | MUNNA AGROTECH ENTERPRISE | 31.75 | 0 | 0
1906 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "DAKSHIN KASHI Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000882/2022-2023 | 417/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.9 | 2.58 | 0
1907 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000202/2023-2024 | 629 | 19/05/2023 | 0 | Resource Division | 22.78 | 0 | 0
1908 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of UTTAR DURGAPUR MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2779] [TSM/017757] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 1567/SWD-I | 27/07/2023 | 90 | RELIABLE CONSTRUCTIONS | 358.16 | 3.41 | 45
1909 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for UTTAR DURGAPUR PWSS of JOYNAGAR-I block under South 24- Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017757] [2nd Call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000682/2022-2023 | 3482/SWD-I | 15/03/2023 | 30 | KHANDAKAR CONSTRUCTION | 47.64 | 45.33 | 100
1910 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Platform and for providing FHTC , protection wall for laying pipeline and other allied works for Ground water based UTTAR DURGAPUR piped water supply scheme to accommodate FHTC in JOYNAGAR-I block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District.(SM/14876) (2nd call) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000739/2024-2025 | 4637/SWD-I | 14/11/2024 | 45 | SANJAY ENTERPRISE | 82.6 | 0 | 0
1911 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Uttar Durgapur Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000953/2022-2023 | 1304/SWD-I | 14/09/2022 | 30 | GEO SOLUTION | 2.72 | 2.65 | 100
1912 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000097/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 45.58 | 0 | 0
1913 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Initial 50% payment for the amount Rs. 4160934/- (forty-one lakh sixty thousand nine hundred & thirty four) only i.e. Rs. 2080467/- (twenty lakh eighty thousand four hundred & sixty-seven) only for restoration of road edge and hard shoulder damaged due to laying of pipeline of Dakshin Barasat to Usthi Road under Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-IV at HIJALHAT and Zone -IX at Ghola Noapara under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/16187 and SM/14725). | AE SWSD-II | JE4 | BILL/00801/2024-2025 | BP-2024-25-492 | 21/11/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR DIVISION, PWD | 20.8 | 0 | 0
1914 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of R.C.C. Retaining wall for laying of 1422 mm dia MS Rising Main pipeline at Usthi bridge to extened the benefit of 100% Household in Zone-IX at GHOLANOAPARA under Mograhat-I Block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur Dist- South 24 Pgns. under South 24 Pgns Water Supply Division-I, PHE Dte. (TSM/014913) | AE SWSD-II | JE4 | ORD/000004/2023-2024 | 27/SWD-I | 05/04/2023 | 60 | A.M. ENTERPRISE (BASIRHAT) | 8.92 | 0 | 0
1915 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of concrete road from the main road to the OHR Site of Zone-IX Ghola Noapara mouza of Mograhat-I Block under Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in ZONE-IX at GHOLA NOAPARA under MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur district- South 24 Pgns. Under south 24 Pgns Water Supply Division-I, PHE Dte. (TSM/014913) | AE SWSD-II | JE4 | ORD/000009/2023-2024 | 33/SWD-I | 05/04/2023 | 30 | ROYAL CONSTRUCTION | 16.77 | 16.76 | 100
1916 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 03 (three) nos. chlorination room at O.H.R. sites for Zone-IV (Hijalhat), Zone-VIII (Khelarampur) & Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Division-I, PHE Dte. South 24 Parganas District. (SM/16187), (SM/14729), (SM/14725) | AE SWSD-II | JE4 | ORD/000026/2025-2026 | 978/SWD-I | 09/04/2025 | 60 | CIVIL TECH CONSTRUCTION AND CONSULTANT | 19.37 | 0 | 0
1917 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Survey, Design and Drawing of laying Distribution System for Zone-IX,Ghola Noyapara (OHR Cap-700 cum) under Mograhat-I Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. | AE SWSD-II | JE4 | ORD/000310/2021-2022 | 2604/SWD-I | 15/03/2022 | 30 | MS R. DUTTA AND CO | 2.15 | 2.07 | 0
1918 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of FHTC platform, road restoration and other allied works for Zone-IX (Ghola Noapara) to accommodate FHTC in Magrahat-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. (SM/14725) | AE SWSD-II | JE4 | ORD/000350/2024-2025 | 3444/SWD-I | 02/08/2024 | 90 | MANASH GHOSH | 294.26 | 0 | 0
1919 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Pathway, Surface Drain, Balance boundary wall, gate, plinth protection and internal works of G.L.R including necessary grouting & painting with other allied works at G.L.R. at Usthi in connection with Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% Household in MOGRAHAT-I BLOCK within ¿Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, District South 24 Parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. (TSM/014913) | AE SWSD-II | JE4 | ORD/000492/2022-2023 | 2858/SWD-I | 08/02/2023 | 60 | NIRMAL UDYOG | 45.61 | 42.26 | 100
1920 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of pipe carrying structure with laying of 355.6 mm dia M.S. Secondary Rising Main and 150 mm dia M.S. Distribution Main for crossing of Karbala Canal for Augmentation of existing laying distribution system including New OHR and allied works to extend the benefit of 100% household in Zone-IX at Ghola Noapara Usthi mouza of Magrahat-I block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns.' under South-24 Pgns W/S Division-I, P.H.E Dte. (SM/ 14725) | AE SWSD-II | JE4 | ORD/000802/2023-2024 | 1274/SWD-I | 14/03/2024 | 30 | SRIJON ENTERPRISE | 50.64 | 50.59 | 98
1921 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying distribution system of pipe water supply scheme in ZONE-IX at GHOLA NOAPARA Mouza of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-IX at GHOLA NOAPARA of MOGRAHAT-I block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 5309 Nos.) | AE SWSD-II | JE4 | ORD/000803/2022-2023 | 3694/SWD-I | 30/03/2023 | 120 | MANASH GHOSH | 603.4 | 275.06 | 30
1922 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE4 | RTOR000066/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 51.28 | 0 | 0
1923 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Rejuvenation / upgradation of Existing R.C.C. Reservoir of capacity 700 CUM and staging height 20 mtr at 2nd Tubewell site of "TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000013/2025-2026 | 965/SWD-I | 09/04/2025 | 45 | J.D. CONSTRUCTION | 11.09 | 0 | 0
1924 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Pathway, Drain & others allied works at HW Site of " TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000233/2024-2025 | 2653/SWD-I | 07/06/2024 | 45 | MRA NIRMAN UDYOG | 13.19 | 0 | 0
1925 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR TARDAHA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016779) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000457/2022-2023 | 2748/SWD-I | 27/01/2023 | 30 | SAHI MASUM | 29.69 | 13.91 | 50
1926 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Earthwork in filling in Head Work Site with good earth for proposed TARDAHA Pipe water supply scheme to accommodate FHTC in Sonarpur Block under South 24 parganas, W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas Dist. under Jal Jeevan Mission.(SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000667/2023-2024 | 3017/SWD-I | 30/11/2023 | 15 | A S BUILDCON | 11.42 | 11.37 | 100
1927 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2297] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000675/2022-2023 | 3446/SWD-I | 13/03/2023 | 1025 | MRA NIRMAN UDYOG | 783.17 | 428.91 | 60
1928 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for TARDAHA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/016779] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000720/2022-2023 | 3559/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 1.57 | 50
1929 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Upgradation of Pump house, Chlorine room, Office Room, Boundary wall, Land Development Construction of pathway, drain & other allied work of "TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14488) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000745/2024-2025 | 4667/SWD-I | 18/11/2024 | 60 | R.K ENTERPRISE | 19.12 | 0 | 0
1930 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall for Head works site of TARDAHA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Parganas. (Length-150.0 mtr.) [SM/14488] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000752/2023-2024 | 554/SWD-I | 31/01/2024 | 45 | MONDAL ENTERPRISE (SANDESHKHALI-2) | 20.64 | 0 | 0
1931 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000032/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 13.83 | 0 | 0
1932 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000241/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 14.15 | 0 | 0
1933 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for PARULDAHA (ZONE 26) MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 1030] [TSM/018359] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000166/2023-2024 | 963/SWD-I | 08/06/2023 | 90 | M/S B.N. ENTERPRISE | 231.58 | 168.67 | 50
1934 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based PARULDAHA Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000926/2022-2023 | 1182/SWD-I | 01/09/2022 | 30 | ASTER CONSULTANCY | 2.82 | 2.82 | 100
1935 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000180/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 7.72 | 0 | 0
1936 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1000 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-IV at Gopalganj Mouza of Kultali Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000015/2022-2023 | 867/SWD-I | 13/07/2022 | 300 | M/S PATH MAKERS | 269.19 | 234.16 | 90
1937 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of pipe carrying structure with laying of 323.9 mm dia M.S. Secondary Rising Main for crossing of Canal at Brindaban Kheya Bridge and Raju Vata Culvert under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI Block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S Division-I of South 24-pgns. W/S Circle, PHE Dte. [SM/16189] | AE BSD |  | ORD/000283/2024-2025 | 3039/SWD-I | 02/07/2024 | 30 | SRIJON ENTERPRISE | 26.01 | 25.68 | 100
1938 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Protection work for pipeline restoration of road, construction of approach Road, development of Land for "Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-IV at KULTALI Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, PHE Dte." (SM/16189) | AE BSD |  | ORD/000357/2024-2025 | 3457/SWD-I | 02/08/2024 | 180 | ARNAB ENTERPRISE | 89.77 | 70.15 | 100
1939 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IV (DASKHIN GARANKATHI MOUZA) of Kultali Block, under Raidighi Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000366/2021-2022 | 2533/SWD-I | 08/03/2022 | 1440 | GHOSH BROTHERS | 855.67 | 510.54 | 85
1940 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Gap Negotiation for Secondary grid of Mathurapur-II block within Mega surface water based water supply scheme of Falta Mathurapur under "Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-IV at KULTALI block within Mega surface water based water supply scheme for Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns W/S division-I of South 24-pgns. W/S Circle, PHE Dte." [SM/16189] | AE BSD |  | ORD/001083/2024-2025 | 5350/SWD-I | 30/12/2024 | 60 | CHANDAN ROY | 96.58 | 0 | 75
1941 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for RANIGACHI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1320) (TSM/018478) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 267/SWD-I | 24/04/2023 | 752 | SAMARJIT ENTERPRISE | 303.12 | 63.22 | 35
1942 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall at HW Site & 2nd Tubewell site of "RANIGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgns. District under Jal Jeevan Mission". (SM/15863) (3rd call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000103/2025-2026 | 1816/SWD-I | 07/07/2025 | 60 | SUJIT KUMAR SHARMA | 28.52 | 0 | 0
1943 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of land, drum sheet walling, approach road of HW site & 2nd Tubewell site and allied works of "RANIGACHI Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Pgns. W/S Division-I, PHE Dte. for augmentation of surface water based water supply scheme in the Arsenic affected areas of South 24-Pgns. Dist. under Jal Jeevan Mission". (SM/15863) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000539/2024-2025 | 4096/SWD-I | 20/09/2024 | 60 | SAMARJIT ENTERPRISE | 52.37 | 0 | 0
1944 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RANIGACHI PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018478] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000670/2022-2023 | 3412/SWD-I | 10/03/2023 | 30 | REALIENCE CONSTRUCTION | 31.79 | 12.97 | 50
1945 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000039/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 20.91 | 0 | 0
1946 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000215/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 8.13 | 0 | 0
1947 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Layiing Distribution System with providing Functional Household Tap Connection (FHTC) and construction of (4.80 mtr. X 3.66mtr.) Pump House with water supply and Sanitary arrangement (as per dept. drawing) of CHAK ROSANMAMUD Piped Water Supply Scheme in Bishnupur-I Block for augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018431] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000128/2023-2024 | 588/SWD-I | 16/05/2023 | 90 | M/S B.S. CONSTRUCTION | 118.62 | 0 | 0
1948 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 12 (twelve) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000209/2023-2024 | 1377/SWD-I | 12/07/2023 | 873 | CONCORD PROJECTS PVT. LTD. | 105.47 | 0 | 60
1949 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, land development, road restoration, additional laying of pipeline, rising main and protection work of pipeline for CHAK ROSANMAMUD PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected areas of South 24-Pgns, W/S Divn-I, PHE Dte. [SM/15867] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000287/2024-2025 | 3051/SWD-I | 03/07/2024 | 287 | P ENTERPRISE | 68.52 | 0 | 55
1950 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Layiing Distribution System with providing Functional Household Tap Connection (FHTC) and construction of (4.80 mtr. X 3.66mtr.) Pump House with water supply and Sanitary arrangement (as per dept. drawing) of CHAK ROSANMAMUD Piped Water Supply Scheme in Bishnupur-I Block for augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District. [TSM/018431] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000292/2024-2025 | 3107/SWD-I | 09/07/2024 | 60 | TIYASHA ENTERPRISE | 118.7 | 0 | 55
1951 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAK ROSANMAMUD PWSS of BISHNUPUR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018431] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000691/2022-2023 | 3480/SWD-I | 15/03/2023 | 678 | BARI ENTERPRISE | 15.88 | 0 | 98
1952 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Chak Rasanmamud Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/000964/2022-2023 | 1164/SWD-I | 29/08/2022 | 30 | GEO SOLUTION | 2.46 | 2.43 | 100
1953 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK ROSANMAMUD Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. District in BISHNUPUR-I Block under South 24 Pgns W/S Sub-Division-II, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15867] | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | ORD/001192/2024-2025 | 772/SWD-I | 18/03/2025 | 30 | SATHI ENTERPRISE | 15.88 | 0 | 0
1954 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE1,Junior Engineer | RTOR000120/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 27.73 | 0 | 0
1955 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platfrom for FHTC, restoration of road after laying of Pipeline, Land devolopment and other allied works for "Ground Water Based RANA Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/16132) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000334/2024-2025 | 3272/SWD-I | 22/07/2024 | 45 | BAIDYA ENTERPRISE | 91.55 | 10 | 25
1956 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for RANA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 998] [TSM/018248] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000440/2023-2024 | 2090/SWD-I | 29/08/2023 | 90 | MS BUILDWELL | 181.82 | 69.68 | 80
1957 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for RANA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018248] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000644/2022-2023 | 3285/SWD-I | 03/03/2023 | 30 | M/S SYCHROTECH INDUSTRY | 31.11 | 29.07 | 100
1958 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Rana Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000934/2022-2023 | 1226/SWD-I | 06/09/2022 | 30 | GEO SOLUTION | 2.54 | 2.5 | 100
1959 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000128/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 11.59 | 0 | 0
1960 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 963 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 110.46 | 15
1961 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PASCHIM CHAKPANCHGHORA Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000388/2021-2022 | 1926/SWD-I NEW | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.61 | 0
1962 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well by Rotary method for PASCHIM CHAKPANCHGHORA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012513] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000749/2022-2023 | 3609/SWD-I | 24/03/2023 | 30 | MONDAL ENTERPRISE | 31.77 | 29.96 | 100
1963 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000089/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 32.55 | 0 | 0
1964 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000138/2022-2023 | 3421/SWD-I | 13/03/2023 | 0 | Resource Division | 7.63 | 0 | 0
1965 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOPALPUR PWSS of Sonarpur Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/019594] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000092/2023-2024 | 402/SWD-I | 28/04/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 15.21 | 50
1966 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GOPALPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (No of FHTC = 1097) (TSM/019594) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000104/2023-2024 | 481/SWD-I | 08/05/2023 | 687 | GUHA CONSTRUCTION | 274.08 | 207.74 | 27
1967 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of Land, Construction of Pathway, Drain & others allied works of GOPALPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15775) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000824/2023-2024 | 1298/SWD-I | 15/03/2024 | 323 | GUHA CONSTRUCTION | 39.38 | 0 | 50
1968 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Gopalpur Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000991/2022-2023 | 1503/SWD-I | 28/09/2022 | 30 | GEO SOLUTION | 2.76 | 2.74 | 100
1969 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000003/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 17.6 | 0 | 0
1970 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000249/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 6.76 | 0 | 0
1971 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.17] |  |  | BILL/00476/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 14.02 | 0 | 0
1972 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at 2nd Tubewell site of "CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/18328) |  |  | ORD/000240/2024-2025 | 2660/SWD-I | 07/06/2024 | 495 | M/S ASHA ENGINEERING | 10.58 | 0 | 60
1973 | South 24 Pgs W/S Division I |  | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 3295] |  |  | ORD/000291/2023-2024 | 1622/SWD-I | 02/08/2023 | 608 | SAFECO ENTERPRISES | 683.19 | 230.67 | 20
1974 | South 24 Pgs W/S Division I |  | Additional Laying Pipeline for 63mm dia (OD) & 75mm dia (OD) HDPE pipe under ¿CHANDPUR piped water supply scheme to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S scheme in the Arsenic Affected Areas of South 24 Parganas Under JJM.¿ [SM/18328] |  |  | ORD/000544/2024-2025 | 4101/SWD-I | 20/09/2024 | 10 | SAFECO ENTERPRISES | 27.53 | 0 | 0
1975 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Pathway, Drain and other allied works of CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18328) |  |  | ORD/000887/2024-2025 | 4992/SWD-I | 05/12/2024 | 60 | SAFECO ENTERPRISES | 38.98 | 0 | 0
1976 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 1721/SWD-I | 08/08/2023 | 0 | Resource Division | 22.24 | 0 | 0
1977 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000316/2023-2024 | 246/SWD-I | 10/01/2024 | 0 | Resource Division | 20.3 | 0 | 0
1978 | South 24 Pgs W/S Division I | Baruipur Sub-Division | joynagar Jalaberia Kultali Road from 7.47 Kmp to 8.00 Kmp restoration of Paver Block,from 8.00 Kmp to 9.5 Kmp & 16.0 Kmp to 18.50 Kmp restoration of Head Shoulder due to laying of pipes by PHED under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W(Roads) Directorate in the District of South 24 Parganas | AE BSD |  | BILL/00639/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 10.48 | 0 | 0
1979 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-II at Jalaberia Mouza of Kultali Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000014/2022-2023 | 866/SWD-I | 13/07/2022 | 300 | M/S PATH MAKERS | 322.19 | 309.12 | 91
1980 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Restoration of boundary wall at Headworks site of Zone-II within kultali block, under Augmentation of laying distribution system to extend the benefit of 100% Households in Zone-II at KULTALI block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur dist. South 24 Pgns. under South 24 Pgns. Water Supply Division-I, PHE Dte. (TSM/ 016053) | AE BSD |  | ORD/000250/2023-2024 | 1492/SWD-I | 19/07/2023 | 60 | A.B. ASSOCIATES | 14.14 | 13.23 | 100
1981 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIA (JALABERIA) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000401/2021-2022 | 2597/SWD-I | 15/03/2022 | 120 | SPA ENTERPRISE | 631.68 | 582.5 | 70
1982 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-IIB (JALABARIA MOUZA) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000402/2021-2022 | 2600/SWD-I | 15/03/2022 | 1350 | MAHAVIR PUMPS MANUFACTURING PVT LTD | 644.11 | 365.58 | 65
1983 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000295/2023-2024 | 2433/SWD-I | 30/09/2023 | 0 | Resource Division | 92.47 | 0 | 0
1984 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Jamtala Petkulchand Road from 0.20 to 0.35 km, 4.50 to 6.00 km, 8.20 to 8.50 km, 8.80 to 9.00 km & 12.50 to 13.00 km Restoration of Brick top surface & Saucer drain in different chainage due to laying of pipelines by PHE Department under Lakshmikantapur Highway Sub Division of Diamond Harbour Highway Division in the District of South 24 Parganas. | AE BSD |  | BILL/00636/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, DIAMOND HARBOUR HIGHWAY DIVISION PW(ROADS) DTE. | 13.26 | 0 | 0
1985 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance civil works of Kultali GLR under the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000006/2022-2023 | 839/SWD-I | 08/07/2022 | 1260 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD | 113.5 | 17.93 | 90
1986 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VB of Kultali Block, under BARUIPUR Sub-Division, for ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000037/2022-2023 | 17/SWD-I | 06/04/2022 | 1144 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 589.08 | 68.62 | 50
1987 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Waterproofing of Reservoir at Kultali GLR under Augmentation of laying distribution system to extend the benefit of 100% household in Zone-V at KULTALI block within Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, Dist. South 24 Parganas under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/18224) | AE BSD |  | ORD/000090/2025-2026 | 1765/SWD-I | 02/07/2025 | 30 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 10.26 | 0 | 100
1988 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection wall for laying pipeline, restoration of damaged road due to laying of pipeline and other allied works for Augmentation of laying distribution system to extend the benifit of 100% House hold in Zone-V at KULTALI Block within Mega surface water based water supply scheme for Falta Mathurapur District South 24 Pgns under South 24 Parganas W/S Division-I, PHE Dte. (SM/ 18224) (2nd call) | AE BSD |  | ORD/000740/2024-2025 | 4638/SWD-I | 14/11/2024 | 45 | MOUMITA ENTERPRISE | 89.32 | 0 | 0
1989 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VA of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000874/2022-2023 | 16/SWD-I | 06/04/2022 | 1068 | TARUN KUMAR BHATTACHARYA PROPRIETOR | 602.94 | 217.67 | 65
1990 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000041/2022-2023 | 2956/SWD-I | 16/02/2023 | 0 | Resource Division | 50.12 | 0 | 0
1991 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000064/2022-2023 | 2979/SWD-I | 20/02/2023 | 0 | Resource Division | 37.62 | 0 | 0
1992 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000075/2022-2023 | 2991/SWD-I | 20/02/2023 | 0 | Resource Division | 62.44 | 0 | 0
1993 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000207/2023-2024 | 382/SWD-I | 27/04/2023 | 0 | Resource Division | 119.44 | 0 | 0
1994 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000297/2023-2024 | 2432/SWD-I | 30/09/2023 | 0 | Resource Division | 71.69 | 0 | 0
1995 | South 24 Pgs W/S Division I |  | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ABJAKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017506] |  |  | ORD/000226/2023-2024 | 1402/SWD-I | 14/07/2023 | 30 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 15.86 | 0 | 0
1996 | South 24 Pgs W/S Division I |  | Laying of rising main and additional pipelines for distribution system, construction of boundary wall, approach road, land development, pipeline protection and road restoration for ABJAKHALI PWSS to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Divn-I, PHE Dte. South 24 Parganas District. [SM/18266] |  |  | ORD/000254/2024-2025 | 2671/SWD-I | 07/06/2024 | 45 | AVIK ENTERPRISE | 96.46 | 0 | 0
1997 | South 24 Pgs W/S Division I |  | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of ABJAKHALI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 3239) [TSM/017506]. |  |  | ORD/000306/2023-2024 | 1695/SWD-I | 07/08/2023 | 603 | PRASUN ENTERPRISE | 495.25 | 73.72 | 70
1998 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Abjakhali Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000961/2022-2023 | 1139/SWD-I | 25/08/2022 | 30 | GEO SOLUTION | 2.85 | 2.82 | 100
1999 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 323/SWD-I | 25/04/2023 | 0 | Resource Division | 84.26 | 0 | 0
2000 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sarberia-Dhamua Road from 0+00 to 6+520 km Restoration of Damages occurred due to damages caused/ to be caused by laying of pipe line by PHE Dte. under Sarberia PWSS,Jaldhapa PWSS,Multi PWSS under South 24 Parganas Highway Division in the district of South 24 Parganas. | AE RWS, Alipore Division | JE RWS, HQ | BILL/00644/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 105.27 | 0 | 0
2001 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for JALDHAPA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017282] [2nd call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000227/2023-2024 | 1403/SWD-I | 14/07/2023 | 30 | HOQUE BUILDERS, M/S SEW | 47.65 | 0 | 0
2002 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation, Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) and Construction of 09 (nine) nos. chlorination room of size 5.0m x 4.0m for JALDHAPA, SHYAMPUR (PART-II) & MIRZAPUR Mouza of MOGRAHAT-II Block, for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns. W/S Division-I, P.H.E Dte. [No. of FHTC = 9688] [TSM/017282, TSM/017546, TSM/016565] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000280/2023-2024 | 1552/SWD-I | 25/07/2023 | 814 | S & P ENTERPRISE | 1745.38 | 24.3 | 6
2003 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary wall, Construction of Approach Road, Earth Filling, Drum Sheet walling for JALDHAPA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Div-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/18269) [2nd call] | AE RWS, Alipore Division | JE RWS, HQ | ORD/000720/2024-2025 | 4554/SWD-I | 06/11/2024 | 45 | VITAE CO INTERNATIONAL | 39.73 | 0 | 0
2004 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Jaldhapa Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division | JE RWS, HQ | ORD/000980/2022-2023 | 1436/SWD-I | 23/09/2022 | 30 | MEASURE LAND | 2.89 | 2.84 | 100
2005 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE RWS, Alipore Division | JE RWS, HQ | RTOR000288/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 29.61 | 0 | 0
2006 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (two) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PETUA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 1200/SWD-I | 02/09/2022 | 30 | PADMA ENGINEERING CO. | 40.17 | 15.21 | 100
2007 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination room at PETUA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012604] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 1293/SWD-I | 14/09/2022 | 60 | JHARNA ENTERPRISE | 10.93 | 1.32 | 100
2008 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PETUA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000164/2021-2022 | 1912/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.76 | 100
2009 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of boundary walls, platform for providing FHTC, protection works for laying pipeline and other allied works for Ground water based PETUA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas district. (SM/12047) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000436/2024-2025 | 3881/SWD-I | 03/09/2024 | 60 | CHANDAN ROY | 91.78 | 0 | 0
2010 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system under ground water based piped water supply scheme at PETUA of BARUIPUR Block, under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas. (SM/12047) (No. of FHTC = 1422) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000522/2023-2024 | 2291/SWD-I | 20/09/2023 | 90 | M/S SUKUMAR SINHA | 360.14 | 0 | 0
2011 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 02 (Two) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for PWSS of PETUA PWSS of Baruipur Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Pgns. district under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/012604] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000711/2023-2024 | 2178/SWD-I | 05/09/2023 | 15 | PADMA ENGINEERING CO. | 4.41 | 2.2 | 50
2012 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000270/2023-2024 | 2417/SWD-I | 30/09/2023 | 0 | Resource Division | 39.97 | 0 | 0
2013 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000339/2023-2024 | 272/SWD-I | 10/01/2024 | 0 | Resource Division | 8.76 | 0 | 0
2014 | South 24 Pgs W/S Division I |  | Construction of approach road, land development, FHTC Platform, laying of additional pipe line, protection of distribution pipe line and other allied works for Ground Water based DIHI KALAS piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/18568) |  |  | ORD/000314/2024-2025 | 3244/SWD-I | 19/07/2024 | 347 | SUPER ENTERPRISES | 286.8 | 0 | 60
2015 | South 24 Pgs W/S Division I |  | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for DIHI KALASH PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/018231] |  |  | ORD/000367/2023-2024 | 1776/SWD-I | 11/08/2023 | 30 | SAYANDIP CONSTRUCTION | 47.45 | 15.08 | 34
2016 | South 24 Pgs W/S Division I |  | Construction of 600 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of DIHI KALAS MOUZA Piped Water Supply Scheme of MOGRAHAT-II Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3846] [TSM/018231] |  |  | ORD/000405/2023-2024 | 1922/SWD-I | 22/08/2023 | 741 | SUPER ENTERPRISES | 702.55 | 153.63 | 60
2017 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000290/2023-2024 | 2414/SWD-I | 30/09/2023 | 0 | Resource Division | 32.22 | 0 | 0
2018 | South 24 Pgs W/S Division I |  | Road Restoration and Horizontal Boring for laying of Secondary Grid within Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I, PHE Dte.(TSM/014517) |  |  | ORD/000398/2023-2024 | 1891/SWD-I | 18/08/2023 | 45 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 7.01 | 3.9 | 50
2019 | South 24 Pgs W/S Division I |  | Development of land and construction of approach road for Head Work site (Zone I) at Mallick Pratap Mouja (J.L. No 02) at Mandirbazar Block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under SWD-I, PHE Dte. (SM/18706) |  |  | ORD/000416/2024-2025 | 3736/SWD-I | 27/08/2024 | 45 | MAA MANASA VYAPAAR | 20.12 | 0 | 0
2020 | South 24 Pgs W/S Division I |  | Construction of 1250 cum OHR, Laying distrbution main pipe line with FHTC for Augmentation of existing Laying Distribution System to extend the benefit of 100% households and providing FHTC from existing distribution system in Zone-I at Mandirbazar Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns under South-24 Pgns W/S Divn-I of South 24-Pgns. W/S Circle, PHE Dte. (No of FHTC = 9379) |  |  | ORD/000423/2023-2024 | 1970/SWD-I | 24/08/2023 | 556 | MAA MANASA VYAPAAR | 1837.75 | 437.71 | 5
2021 | South 24 Pgs W/S Division I |  | Diversion of Water for "Construction of Hume Pipe Culvert infront of 10.00 Mtr span for proposed Zone-I OHR Site at Mallick Pratap Mouza (J.L.NO-02, Plot No-964) at Mandirbazar Block for Augmentation of existing Laying Distribution System to extend the benefit of 100% households from existing distribution system in Zone-I at Mandirbazar Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas" under South-24 Pgns W/S Divn-I, PHE Dte. (SM/18706) |  |  | ORD/000433/2024-2025 | 3875/SWD-I | 03/09/2024 | 30 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.68 | 4.63 | 100
2022 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Survey, Design and Drawing for laying distribution system of MALLICKPRATAP MOUZA in MANDIRBAZAR (ZONE-I) Block under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, South 24-Pgns. district. |  |  | ORD/000512/2021-2022 | 1983/SWD-I | 27/01/2022 | 30 | RADIANT | 4.83 | 4.17 | 100
2023 | South 24 Pgs W/S Division I |  | Laying of 600 mm dia MS Secondary Grid Pipe from Mandirbazar GLR-Pump House to 600mm Dia DI Secondary Grid Pipeline under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, Dist.- South 24-Pgns.Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-I at Mandirbazar Block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Pgns" under South-24 Pgns W/S Divn-I (SM/018706) |  |  | ORD/000549/2023-2024 | 2497/SWD-I | 06/10/2023 | 30 | S. ROY AND ASSOCIATES | 4.91 | 4.9 | 100
2024 | South 24 Pgs W/S Division I |  | Construction of boundary wall for proposed OHR Site of Zone-I within Mandirbazar block, Mouza-Mallik Protap under Mega Surface Water Based Water Supply Secheme for Falta-Mathurapur, Dist. South 24 Paraganas. (Length- 200.6 mtr.) under South 24-Pgns. W/S Division-I, PHE Dte. |  |  | ORD/000566/2021-2022 | 2694/SWD-I | 25/03/2022 | 90 | SADHURHAT CO OP LABOUR CONSTRACT AND CONSTRUCTION SOCIETY LTD. | 26.82 | 6.33 | 100
2025 | South 24 Pgs W/S Division I |  | Carriage of K9 DI pipes of various diameters from Dongaria WTP PHE stores to work site at Mandirbazar for laying of Secondary Grid pipeline within Mandirbazar Block under the Augmentation of LDS to extend the benefit of 100% households in Zone-I at Mandirbazar Block within the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas¿ under South 24 Parganas Water Supply Division-I, PHE Dte. (SM/18706) |  |  | ORD/000662/2023-2024 | 2958/SWD-I | 24/11/2023 | 7 | M/S SHIBAM ENTERPRISE | 1.24 | 0 | 0
2026 | South 24 Pgs W/S Division I |  | Gap Negotiation for secondary grid of Mandirbazar Block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. [SM/18706] |  |  | ORD/000697/2024-2025 | 4499/SWD-I | 30/10/2024 | 60 | S. ROY AND ASSOCIATES | 56.45 | 0 | 0
2027 | South 24 Pgs W/S Division I |  | Three months trial run for secondary grid D.I pipe lines of different diameters of Mandirbazar Block within Mega surface water based water supply scheme of Falta-Mathurapur District South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte. (SM/18706) |  |  | ORD/000873/2024-2025 | 4931/SWD-I | 03/12/2024 | 45 | M/S. GOUTAM ROY | 16.98 | 0 | 0
2028 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 3016/SWD-I | 20/02/2023 | 0 | Resource Division | 276.01 | 0 | 0
2029 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BANTRA PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/018420) |  |  | ORD/000295/2023-2024 | 1660/SWD-I | 03/08/2023 | 780 | MALLICK CONSTRUCTION | 31.62 | 0 | 25
2030 | South 24 Pgs W/S Division I |  | Construction of platform for providing FHTC, restoration of damaged road due to laying of pipeline for BANTRA PWSS to accommodate FHTC in JAYNAGAR-I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. South 24 Paraganas for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM /18498) |  |  | ORD/000423/2024-2025 | 3751/SWD-I | 28/08/2024 | 45 | M/S SALIM CONSTRUCTION | 82.76 | 0 | 0
2031 | South 24 Pgs W/S Division I |  | Construction of 450 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Pump house cum Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of BANTRA MOUZA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 3046] [TSM/018420] |  |  | ORD/000438/2023-2024 | 2088/SWD-I | 29/08/2023 | 300 | M/S SALIM CONSTRUCTION | 659.79 | 103.61 | 50
2032 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Bantra Piped Water Supply Scheme to accommodate FHTC in Joynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. |  |  | ORD/000968/2022-2023 | 1385/SWD-I | 20/09/2022 | 30 | GEO SOLUTION | 2.92 | 2.84 | 100
2033 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 72.16 | 0 | 0
2034 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Uttar Roypur W/S Scheme for Uttar Roypur , Balarampur (Part), ChakNabashan (Part) Mouza under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000117/2020-2021 | 1396/SWD-I | 11/12/2020 | 120 | SRIJON ENTERPRISE | 86.18 | 100.49 | 60
2035 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Uttar Roypur W/S Scheme forUttar Roypur , Balarampur (Part), ChakNabashan (Part) Mouza under Budge Budge I Block with alliedworks under SWD - I, P.H.E. Dte District South 24 Parganas | AE SWSD-I |  | ORD/000328/2020-2021 | 1396/SWD-I JJM | 11/12/2020 | 120 | SRIJON ENTERPRISE | 85.74 | 25.57 | 60
2036 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance repair of Bitumen Road damaged due to laying of pipeline within Uttar Roypur W/S Scheme under South 24 Pargana W/S Division - I, PHE Dte. (TSM / 6136) PART-IV | AE SWSD-I |  | ORD/000463/2022-2023 | 2773/SWD-I | 31/01/2023 | 30 | M/S SHIBAM ENTERPRISE (EMAIL ID- CYBER.CW@GMAIL.COM) | 3.07 | 3.06 | 100
2037 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Nandarampur W/S Scheme for Booth 170 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000116/2020-2021 | 1394/SWD-I | 11/12/2020 | 120 | PROJECT AND MAINTENANCE | 92.1 | 10.62 | 90
2038 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Moukhali W/S Scheme for Durgapur Moukhali and Jagat Ballavpur under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000309/2020-2021 | 1414/SWD- I | 14/12/2020 | 120 | SUPRITI ENTERPRISE | 96.89 | 6.17 | 100
2039 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Nandarampur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/6127) Part -H | AE SWSD-I |  | ORD/000470/2022-2023 | 2782/SWD-I | 31/01/2023 | 45 | R.D CONSTRUCTION | 2.51 | 4.73 | 100
2040 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of distribution system for Buita W/S Scheme for Booth No: 137 to 140 and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000308/2020-2021 | 1412/SWD-I | 14/12/2020 | 120 | BHOLANATH CONSTRUCTION | 96.19 | 90.33 | 100
2041 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000037/2021-2022 | 1102/SWD-I | 25/10/2021 | 120 | SUPRITI ENTERPRISE | 82.25 | 56.28 | 100
2042 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Retrofitting of pipeline for supporting FHTC drive for Moukhali W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE SWSD-I |  | ORD/000079/2021-2022 | 1202/SWD-I JJM | 25/10/2021 | 120 | SUPRITI ENTERPRISE | 82.17 | 20.66 | 60
2043 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Moukhali W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8295) Part -C | AE SWSD-I |  | ORD/000460/2022-2023 | 2778/SWD-I | 31/01/2023 | 45 | RIDIP ENTERPRISE | 7.14 | 7.14 | 100
2044 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for BIJOYRAMPURPIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24 Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division-II, P.H.E. Dte. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000033/2022-2023 | 917/SWD-I | 19/07/2022 | 30 | SIMPLEX DRILLING CO. | 14.2 | 12.08 | 100
2045 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Proposed BIJOYRAMPUR PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. [No. of FHTC = 821] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000150/2022-2023 | 1390/SWD-I | 21/09/2022 | 90 | JAYANTA KUMAR DEY | 107.26 | 105.12 | 95
2046 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
2047 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development at Bijoyrampur PWSS Tubewell site (Bahadurpur) in the Arsenic affected areas of South 24 pgs. Dist in Bishnupur-I Block under South 24 pgs W/S Division-I, P.H.E Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000244/2023-2024 | 1486/SWD-I | 19/07/2023 | 15 | MAA LAXMI ENTERPRISE | 3.81 | 3.78 | 100
2048 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Bijoyrampur PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/11496) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000248/2024-2025 | 2668/SWD-I | 07/06/2024 | 45 | TIYASHA ENTERPRISE | 81.5 | 0 | 15
2049 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of "BIJOYRAMPUR Ground Water Based Piped Water Supply Scheme" in BISHNUPUR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000397/2022-2023 | 460/SWD-I | 24/05/2022 | 15 | GEO SOLUTION | 2.55 | 2.51 | 100
2050 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of BIJOYRAMPUR Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11496) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000445/2022-2023 | 2664/SWD-I | 18/01/2023 | 60 | M/S. SREEJIT ENTERPRISE (EMAIL ID- RAYTARUN1974@GMAIL.COM) | 6.05 | 5.86 | 100
2051 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BIJOYRAMPUR PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000508/2022-2023 | 2906/SWD-I | 14/02/2023 | 15 | SIMPLEX DRILLING COMPANY | 1.59 | 1.59 | 100
2052 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for BIJOYRAMPUR PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000591/2022-2023 | 3111/SWD-I | 24/02/2023 | 708 | DEBASHIS DAS | 15.89 | 0 | 100
2053 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Development of low land and temporary aproach road for entering Tubewell site for proposed BIJOYRAMPUR Piped Water Supply Scheme in Bishnupur-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Pgs. Dist. under South 24 Pgs. Water Supply Division-I, PHE Dte. [TSM/011224] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000809/2022-2023 | 3701/SWD-I | 30/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 0.95 | 0.68 | 100
2054 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000015/2022-2023 | 1583/SWD-I | 17/10/2022 | 0 | Resource Division | 5.06 | 0 | 0
2055 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000107/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 26.06 | 0 | 0
2056 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 300mm X 200mm dia & 300 mtr. deep Tubewell by Rotary method for KAMARIA (ZONE-III) PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000083/2022-2023 | 1194/SWD-I | 02/09/2022 | 30 | AYUB KHAN | 37.76 | 4.28 | 10
2057 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of protection work for pipeline, approach road, development of land and other allied works for KAMARIA ZONE - III piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 pgns district.(SM/11647) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000224/2024-2025 | 2642/SWD-I | 07/06/2024 | 45 | AYUSH ENTERPRISE | 16.77 | 0 | 0
2058 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation along with Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at KAMARIA (ZONE-III) Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 2051) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000279/2022-2023 | 1840/SWD-I | 11/11/2022 | 872 | MANASH GHOSH | 391.21 | 0 | 45
2059 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Kamaria Zone-III PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011003] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000732/2022-2023 | 3582/SWD-I | 22/03/2023 | 15 | AYUB KHAN | 4.35 | 0.14 | 10
2060 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000077/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 23.23 | 0 | 0
2061 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1000 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap of piped water supply within Zone-VIII at Nimpith Mouza of Joynagar-II Block for the "Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas" under Baruipur Sub-Division of South 24 Paraganas Water Supply Division-I Division of PHE Dte. | AE BSD |  | ORD/000201/2022-2023 | 1557/SWD-I | 13/10/2022 | 300 | RAJ BROTHERS | 268.09 | 0 | 0
2062 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC in Zone-VIII at Nimpith mouza of Joynagar-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur district.- South 24 Pgns" under South-24 Pgns W/S Divn-I, P.H.E Dte. [No. of FHTC = 7302] | AE BSD |  | ORD/000345/2022-2023 | 2150/SWD-I | 08/12/2022 | 811 | M/S. S.S. ENTERPRISE | 556.22 | 242.52 | 75
2063 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000085/2022-2023 | 3001/SWD-I | 20/02/2023 | 0 | Resource Division | 44.98 | 0 | 0
2064 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 600 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in ZONE-X/B AT KALIKAPOTA of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in ZONE-X/B KALIKAPOTA of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 4780 Nos.) | Assistant Engineer | JE2 | ORD/000751/2022-2023 | 3618/SWD-I | 24/03/2023 | 740 | TARUN ENTERPRISE | 922.07 | 48.35 | 70
2065 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Three months trial run for Secondary Grid for Providing 100% FHTC in Zone-X/B at Kalikapota mouza of Mograhat-I within 'Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under South-24 Pgns W/S Divn-I, P.H.E Dte. [SM/11262] [w.e.f. 01/02/2025 to 01/05/2025] | Assistant Engineer | JE2 | ORD/001128/2024-2025 | 191/SWD-I | 17/01/2025 | 105 | AVIK ENTERPRISE | 30.87 | 0 | 90
2066 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000068/2023-2024 | 284/SWD-I | 24/04/2023 | 0 | Resource Division | 234.99 | 0 | 0
2067 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE2 | RTOR000145/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 29.44 | 0 | 0
2068 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 550 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Laying Distribution System and providing FHTC for Augmentation of Piped W/S Scheme of Zone-III at PRATAPBERIA (Baneswarpur) of Mograhat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.-South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 4102] [TSM/015075 & TSM/010756] | AE SWSD-II | JE2 | ORD/000073/2023-2024 | 387/SWD-I | 28/04/2023 | 705 | PROJECT AND MAINTENANCE | 418.32 | 112.57 | 95
2069 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Restoration of road from Baneswarpur Bazar to Nabin Sangha for providing 100% FHTC in Zone-III at PRATAPBERIA (Baneswarpur) of Magrahat-I Block within Mega Surface Water based Water Supply Scheme of Falta-Mathurapur Dist.- South 24-Parganas under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11266) | AE SWSD-II | JE2 | ORD/000732/2023-2024 | 437/SWD-I | 22/01/2024 | 15 | PROJECT AND MAINTENANCE | 7.09 | 7.09 | 25
2070 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II | JE2 | RTOR000132/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 25.27 | 0 | 0
2071 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of (Size 4.80mX3.66m) Pump House with water supply and sanitary arrangement (as per Deptt. drawing) of PIRKHALI Pipe Water Supply Scheme in Bishnupur-I block under South 24-Pgns W/S Divn-I, PHE Dte. (SM/11731) (2nd Call) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000110/2023-2024 | 517/SWD-I | 10/05/2023 | 60 | DEBAYAN MONDAL | 5.75 | 5.56 | 100
2072 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for PIRKHALI Piped Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. Dist. in Bishnupur-I Block Under South 24 Paraganas W/S Division-I, PHE Dte. [SM/11731] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000173/2022-2023 | 1448/SWD-I | 26/09/2022 | 30 | SUBHRA ENTERPRISE | 14.27 | 13.9 | 100
2073 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
2074 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of PIRKHALI AND ADJOINING AREAS Ground Water Based Piped Water Supply Scheme in BISHNUPUR-I (ZONE-XIX) Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000232/2021-2022 | 1977/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.76 | 2.61 | 100
2075 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of boundary wall, approach road, pump house, laying of pipeline and other allied works for ground water based PIRKHALI PWSS to accomodate FHTC in Bishnupur -I Block under South 24-Pgns W/S Divn-I, PHE Dte. Dist. for Augmentation of Surface water based water supply scheme in the Arsenic affected areas of South 24 Paraganas District. (SM/11731) | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000391/2024-2025 | 3631/SWD-I | 20/08/2024 | 407 | S.C. ENTERPRISE | 107.87 | 0 | 10
2076 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) for Ground Water Based PIRKHALI PIPE WATER SUPPLY SCHEME for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Division -I, P.H.E. Dte., South-24 Pgs. Dist. [No. of FHTC - 815 nos.] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000422/2022-2023 | 2583/SWD-I | 10/01/2023 | 903 | LOKENIRMAN | 141.2 | 123.7 | 100
2077 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Additional work for sinking of Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for PIRKHALI PWSS of Bishnupur-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011789] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000519/2022-2023 | 2909/SWD-I | 14/02/2023 | 15 | SUBHRA ENTERPRISE | 1.57 | 1.57 | 0
2078 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for PIRKHALI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/011789] | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | ORD/000555/2022-2023 | 3045/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
2079 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE3,Junior Engineer | RTOR000112/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 38.38 | 0 | 0
2080 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work for Laying distribution system, Rising main for piped water supply scheme at PADMAJOLA for implementation of JJM under augmentation of ground water based W/S scheme to accommodate FHTC in Baruipur Block under South 24 Pgns water Supply Division-I, south 24-Parganas District [TSM/014212] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000058/2023-2024 | 275/SWD-I | 24/04/2023 | 90 | N.G. ENGINEERING | 111.21 | 62.55 | 70
2081 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for PADMAJALA PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. [TSM/014212] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000309/2022-2023 | 1934/SWD-I | 21/11/2022 | 30 | MUNNA AGROTECH ENTERPRISE | 20.07 | 18.86 | 100
2082 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of chlorination room at PADMAJALA of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/014212] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000310/2022-2023 | 1935-SWD-I | 21/11/2022 | 60 | JYOTI ENTERPRISE | 5.46 | 4.3 | 100
2083 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at PADMAJALA of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 1761) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000322/2022-2023 | 2018/SWD-I | 29/11/2022 | 90 | N.G. ENGINEERING | 196.66 | 125.65 | 70
2084 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of PADMOJOLA Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000348/2021-2022 | 1909/SWD-I | 27/01/2022 | 30 | TECH VISION | 2.76 | 2.71 | 100
2085 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary wall at head work site, platform for providung FHTC, restoration of road and other allied works for Augmentation of Ground Water based PADMAJALA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte. (SM/13766) [2nd call] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000886/2024-2025 | 4991/SWD-I | 05/12/2024 | 135 | G M ENTERPRISE (BERHAMPORE) | 68.43 | 0 | 80
2086 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000194/2023-2024 | 338/SWD-I | 26/04/2023 | 0 | Resource Division | 14.59 | 0 | 0
2087 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KASHIA DANGA PWSS of BHANGAR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/014455] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000604/2022-2023 | 3134/SWD-I | 27/02/2023 | 30 | KUNTAL CHOWDHURY | 31.76 | 31.55 | 100
2088 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tubewell site of KASHIADANGA PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13512) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000668/2024-2025 | 4415/SWD-I | 24/10/2024 | 343 | BABLU KUMAR MONDAL (Partnership Firm) | 121.32 | 0 | 50
2089 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for KASHIADANGA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1406] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000752/2022-2023 | 3619/SWD-I | 24/03/2023 | 790 | BABLU KUMAR MONDAL | 496.35 | 424.51 | 55
2090 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000055/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 11 | 0 | 0
2091 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000222/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 8.66 | 0 | 0
2092 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 3 Nos. OHR of different capacities, Chlorine Room (six nos.) along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile cap after soil investigation for Augmentation of SRIKRISHNANAGAR, PASCHIM CHAK PANCHGHORA & PUNPO PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 4272] [TSM/012514, TSM/012513, TSM/012506] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000038/2023-2024 | 152/SWD-I | 13/04/2023 | 963 | BKB INFRA PROJECTS (P) LTD. | 1132.95 | 0 | 15
2093 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of SRIKRISHNANAGAR Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000206/2021-2022 | 1927/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.76 | 2.65 | 100
2094 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deepTubewell by Rotary method for SRIKRISHNANAGAR PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. forAugmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/012514] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000505/2022-2023 | 2892/SWD-I | 13/02/2023 | 30 | PURE RENOVATION GROUP | 31.78 | 15.16 | 33
2095 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000090/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 40.8 | 0 | 0
2096 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000137/2022-2023 | 3420/SWD-I | 13/03/2023 | 0 | Resource Division | 8.24 | 0 | 0
2097 | South 24 Pgs W/S Division I |  | Construction of M.S. Manifold of 1000 mm dia 10 mm thickness for Improvement of Water Supply at Zone 9 Head Work Site under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000245/2022-2023 | 1731/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 4.38 | 3.03 | 20
2098 | South 24 Pgs W/S Division I |  | Construction of foundation with supporting arrangement including erection of M.S. Manifold and distribution pipeline & some allied works at zone 9 Head Works Site under SWBWSS in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000246/2022-2023 | 1732/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 3.36 | 2.8 | 100
2099 | South 24 Pgs W/S Division I |  | Laying of 300 mm dia MS & DI distribution pipe line from proposed Manifold to existing distribution pipeline with interconnection at zone 9 Head Works Site under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000247/2022-2023 | 1733/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 4.09 | 1.74 | 20
2100 | South 24 Pgs W/S Division I |  | Laying of 250 mm dia MS & DI distribution pipe line from proposed Manifold to existing distribution pipeline with interconnection at zone 9 Head Work Site under Surface Water Based Water Supply scheme in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000248/2022-2023 | 1734/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 3.24 | 1.14 | 20
2101 | South 24 Pgs W/S Division I |  | Supplying and laying of 450 mm dia 8 mm thickness MS Casing pipe by open cutting method at two (2) places including supplying and laying of 300 mm and 250 mm dia MS Water Distribution pipeline across the PWD road (Bakrahat-Thakurpukur) near zone 9 Head Work Site under SWBWSS in the Arsenic affected areas of South 24-pgs. Dist. |  |  | ORD/000249/2022-2023 | 1735/SWD-I | 03/11/2022 | 15 | SRIJON ENTERPRISE | 6.05 | 1.11 | 20
2102 | South 24 Pgs W/S Division I |  | Laying a rising main from existing pump house to nearer distribution line of Zone- 8 and Zone - 9 for boosting existing scheme which arise after successfully installation of manifold in connection with Construction and installation of Manifold and allied works at OHR site of Zone-9, Bishnupur-II Block, under surface water based water supply scheme in the arsenic affected areas of South 24 Pgs. district. (TSM/014338) |  |  | ORD/000249/2023-2024 | 1491/SWD-I | 19/07/2023 | 30 | SRIJON ENTERPRISE | 6.56 | 6.45 | 100
2103 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of rig ground bored 02 nos. (Two nos) 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for Ramchandra Nagar (Zone-I) PWSS of Mograhat-II Block under South 24-Parganas W/S Division-I, PHE Dte. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000295/2022-2023 | 1882/SWD-I | 16/11/2022 | 30 | BARI ENTERPRISE | 30.03 | 0 | 0
2104 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Platform for providing FHTC for Ground water based RAMCHANDRANAGAR (PART-I) piped water supply scheme at Mograhat-II block under South 24 Parganas W/S Division-I, PHE Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000319/2024-2025 | 3252/SWD-I | 19/07/2024 | 60 | RELIABLE ENTERPRISE (MURSHIDABAD) | 31.12 | 0 | 0
2105 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of "RAMCHANDRANAGAR (PART-I) Ground Water Based Piped Water Supply Scheme" in MOGRAHAT-II block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000393/2022-2023 | 407/SWD-I | 20/05/2022 | 15 | GEO SOLUTION | 2.83 | 2.67 | 0
2106 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 250 Cum capacity OHR (20 mtr Staging Height) including design and drawing of Pile Foundation & Pile Cap after Soil Investigation along with Laying distribution system, Rising main, Functional Household Tap Connection (FHTC) for Augmentation of RAMCHANDRANAGAR (Part-I) of MOGRAHAT-II Block for implementation of JJM under augmentation of surface water based W/S scheme in the arsenic affected areas of South 24 Parganas district under Baruipur sub Division of South 24 Pgns W/S Division-I, P.H.E Dte [No. of FHTC = 1672] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000512/2022-2023 | 2942/SWD-I | 16/02/2023 | 927 | RELIABLE ENTERPRISE | 420.98 | 30.04 | 15
2107 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Ramchandra Nagar-I PWSS of Mograhat-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/014752] | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000782/2022-2023 | 3673/SWD-I | 29/03/2023 | 15 | BARI ENTERPRISE | 3.13 | 0 | 0
2108 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Service Road (length = 550.00m) and Culvert at OHR site for RAMCHANDRANAGAR (Part-I) PWSS within Mograhat-II under South 24-Pgns, W/S Division-I. P.H.E. Dte. for Augmentation of Surface Water based Water Supply Scheme for Arsenic Affected areas of South 24 Parganas District. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/000870/2024-2025 | 4928/SWD-I | 03/12/2024 | 30 | S.M. ENTERPRISE (MOGRAHAT) | 79.56 | 0 | 0
2109 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of Boundary wall (length= 51.00m), Development of land, Construction of Service Road (Length = 15.00m) and pumphouse (4.80 Mtr x 366 Mtr) at 2nd Tubewell site for RAMCHANDRANAGAR (Part-I) PWSS to accommodate FHTC in Mograhat-II Block under South 24-Pgns. W/S Division-I, PHE Dte. of Surface Water Based Water Supply Scheme in the Arsenic affected areas of District South 24-Parganas. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/001176/2024-2025 | 502/SWD-I | 18/02/2025 | 60 | SAYAN ENTERPRISE | 14.96 | 0 | 0
2110 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of land, Construction of Boundary wall, Approach Road and Pump house with water supply and sanitary arrangement at Head Work site for RAMCHANDRANAGAR (Part-I) PWSS OHR site of Mograhat-II Block under South 24 Pgs W/S Division -I, P.H.E. Dte. for Augmentation of Surface Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. (SM/12804) | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | ORD/001181/2024-2025 | 607/SWD-I | 27/02/2025 | 45 | M/S LAKHI CONSTRUCTION | 29.15 | 0 | 0
2111 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | AE RWS, Alipore Division,Assistant Engineer | JE, RWS, DH-II,Junior Engineer | RTOR000140/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 26.75 | 0 | 0
2112 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site HAORI Village of Budge Budge-II under South 24-Pgns W/S Divn-I, PHE Dte. (TSM/015373) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000011/2023-2024 | 35/SWD-I | 05/04/2023 | 60 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 6.79 | 6.2 | 100
2113 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of Rig bored 250mm x 150mm dia & 300 mtr. deep Tubewell by Rotary method for water supply at HAORI Piped Water Supply Scheme within Budge Budge-II Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000267/2022-2023 | 1778/SWD-I | 07/11/2022 | 30 | MOMINUL BISWAS | 14.69 | 13.53 | 100
2114 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site HAORI Village of Budge Budge-II under South 24-Pgns W/S Divn-I, PHE Dte. (TSM/015373) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000340/2022-2023 | 2071/SWD-I | 01/12/2022 | 60 | UNI DEVELOPERS AND CONTRACTORS | 6.2 | 0 | 0
2115 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of HDPE Pipes for rising main and distributions of different augmentation schemes of Budge Budge I/ II Blocks under TSM/010530, TSM/015373, TSM/013487 & TSM/017296 Schemes under South 24 Pgns W/S Div -I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000342/2022-2023 | 2077SWD-I | 01/12/2022 | 60 | M/S. SREEJIT ENTERPRISE | 19 | 0.76 | 98
2116 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnection from proposed Tubewell to existing Distribution Line with Laying of HDPE pipeline for distribution system & providing FHTC of HAORI piped water supply scheme for Augmentation of Surface Water Supply Scheme in the Arsenic affected areas of South 24-Pgs. Dist. under South 24 Pgs W/S Division -I, P.H.E. Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000369/2022-2023 | 2313/SWD-I | 19/12/2022 | 90 | SUKUMAR DEBNATH | 110.48 | 110.37 | 60
2117 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of 02 (two) Nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method HAORI PWSS of Budge Budge-II Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs. district under South 24-Parganas W/S Divn- I, P.H.E. Dte. [SM/13297] [2nd Call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000680/2022-2023 | 3476/SWD-I | 15/03/2023 | 15 | MOMINUL BISWAS | 2.17 | 2.17 | 100
2118 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Haori Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000993/2022-2023 | 1533/SWD-I | 29/09/2022 | 30 | GEO SOLUTION | 2.45 | 2.44 | 100
2119 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Moydah-Khakudah-Beliachandi Road-Repairing & Restoration of Road side flank from 0.30Km to 2.00 Km(Right Side) 2.30 Km to 3.50 Km (R/S). from 6.60 Km to 7.25Km (both side) (Total length- 4200.00m under South 24-Parganas Highway Division. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00668/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 3.35 | 0 | 0
2120 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Development of land, Construction of approach road and other allied works for Ground Water Based KHAKURDAHA Piped Water Supply Scheme to Accommodate FHTC in JAYNAGAR-I Block under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District. (SM/13923) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000407/2024-2025 | 3685/SWD-I | 22/08/2024 | 296 | GARAI INFRA PROJECT | 56.45 | 5.87 | 25
2121 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 2 Nos. OHR of different capacities including design and drawing of pile cap after soil investigation, Pump House cum Chlorine Room (7 nos.), Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of TILPI (ZONE-I), TILPI (ZONE-II), KHAKURDAHA & DHOSA Mouza PWSS of JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2610/SWD-I | 17/10/2023 | 652 | GARAI INFRA PROJECT | 1193.4 | 212.9 | 96
2122 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for KHAKURDAHA PWSS of JOYNAGAR-I block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/017164] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000620/2022-2023 | 3244/SWD-I | 01/03/2023 | 30 | MATRI ENTERPRISE | 31.75 | 15.05 | 50
2123 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "KHAKURDAHA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000754/2022-2023 | 711/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.83 | 2.63 | 100
2124 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000193/2023-2024 | 338/SWD-I | 26/04/2023 | 0 | Resource Division | 45.83 | 0 | 0
2125 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Chak Netai Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000078/2023-2024 | 399/SWD-I | 28/04/2023 | 30 | GEO SOLUTION | 3.05 | 0 | 0
2126 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of Boundary Wall & other allied works at 11 (eleven) nos. Head Work Sites of different PWSS within Bishnupur-I Block, Dist.-South 24-Parganas for Augmentation of Surface Water based Water Supply Scheme in the Arsenic Affected areas of South 24-Parganas District. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000210/2023-2024 | 1376/SWD-I | 12/07/2023 | 858 | CONCORD PROJECTS PVT. LTD. | 106.79 | 0 | 20
2127 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying of Additional Pipeline for distribution system, rising main, construction of boundary walls, pump house and other allied works for Chak Nitai PWSS to accommodate FHTC in Bishnupur - I Block under South 24 parganas W/S Divn-I, PHE Dte. South 24 Pgns District. (SM/14657) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000273/2024-2025 | 2923/SWD-I | 25/06/2024 | 45 | DEY ENTERPRISE | 71.64 | 0 | 0
2128 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for CHAK NETAI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017334] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000494/2022-2023 | 2855/SWD-I | 08/02/2023 | 30 | JINAT CONSTRUCTION | 15.89 | 0 | 1
2129 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 04 (four) nos. different capacities 20 mtr. staging height R.C.C. Over Head Reservoirs as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap including Soil investigation and foundation design for DAULATPUR, CHAK NITAI, BAKESWAR & UTTAR KAZIRHAT PWSS of Bishnupur-I Block for Augmentation of Surface Water based Water Supply Schme in the arsenic affected areas of South 24 Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [TSM/016355, TSM/017334, TSM/016358, TSM/018475] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000506/2023-2024 | 2220/SWD-I | 12/09/2023 | 665 | KESHAVPRIYA INFRASTRUCTURES | 541.95 | 0 | 35
2130 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at Second Tubewell site for CHAK NITAI PWSS of BISHNUPUR-I block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017334] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000547/2022-2023 | 3037/SWD-I | 20/02/2023 | 30 | TAPAS KUMAR GIRI | 15.9 | 0 | 0
2131 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for CHAK NITAI Piped Water Supply Scheme to accommodate FHTC in BISHNUPUR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/14657] | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000696/2024-2025 | 4491/SWD-I | 30/10/2024 | 30 | BORING HOUSE | 15.83 | 0 | 0
2132 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Laying Distribution System with providing Functional Household Tap Connection (FHTC) and Construction of Pump House with water supply and sanitary arrangement (as per deptt. drawing) of CHAK NITAI PIPE WATER SUPPLY SCHEME in BISHNUPUR-I Block for Augmentation of surface water based water supply scheme in the arsenic affected areas of South 24 Parganas District. (No of FHTC = 2257). | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000715/2022-2023 | 3550/SWD-I | 21/03/2023 | 994 | MAA LAXMI ENTERPRISE | 288.95 | 35.75 | 10
2133 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Preparation and submission of Detailed Project Report of Ground Water Based Chak Netai Piped Water Supply Scheme to accommodate FHTC in Bishnupur-I Block under South 24-Pgns W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/000944/2022-2023 | 1127/SWD-I | 24/08/2022 | 30 | GEO SOLUTION | 3.05 | 2.7 | 100
2134 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Land Development work & Protection work for approach road at Headwork site of Chak Netai PWSS for pipe lines at providing 100 % Functional Household Tap Connection (FHTC) for Proposed CHAK NETAI PIPE WATER SUPPLY SCHEME in the Arsenic affected areas of South 24-Pgs. Dist. in BISHNUPUR-I Block under South 24 Pgs W/S Sub-Division -II, P.H.E. Dte. (SM/14657) | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | ORD/001125/2024-2025 | 188/SWD-I | 17/01/2025 | 271 | SRIJON ENTERPRISE | 29.94 | 0 | 80
2135 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | AE SWSD-II,Assistant Engineer -II | JE2,Junior Engineer | RTOR000095/2022-2023 | 3249/SWD-I | 01/03/2023 | 0 | Resource Division | 38.56 | 0 | 0
2136 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for ATGHARA Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2247) (TSM/018118) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000049/2023-2024 | 268/SWD-I | 24/04/2023 | 300 | TUMPA ASSOCIATES | 421.83 | 31.27 | 30
2137 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ATGHARA PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018118] (2nd Call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000224/2023-2024 | 1400/SWD-I | 14/07/2023 | 30 | G.B. CONSTRUCTION | 31.7 | 0 | 0
2138 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of ATGHARA PWSS within Sonarpur Block "ATGHARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/14857) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000230/2024-2025 | 2650/SWD-I | 07/06/2024 | 45 | JHARNA ENTERPRISE (PROP. PINAKY KARMAKAR) | 10.83 | 9.88 | 100
2139 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ATGHARA PWSS of SONARPUR block for Augmentaion of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018118] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000747/2023-2024 | 561/SWD-I | 31/01/2024 | 15 | MUNNA AGROTECH ENTERPRISE | 15.85 | 15.53 | 100
2140 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Land Development, Pathway, Drain & others allied works of Head Work Site ATGHARA PWSS within Sonarpur Block ATGHARA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas W/S Division-I PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14857) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001071/2024-2025 | 5339/SWD-I | 30/12/2024 | 315 | RAJ CONSTRUCTION | 39.61 | 0 | 50
2141 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000034/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 18.93 | 0 | 0
2142 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000243/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 13.84 | 0 | 0
2143 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for KANTIPOTA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1783] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000213/2023-2024 | 1373/SWD-I | 12/07/2023 | 300 | ANUP PAUL | 467.02 | 231.21 | 25
2144 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR KANTIPOTA PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE. DTE. (TSM/016074) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000353/2022-2023 | 2260/SWD-I | 15/12/2022 | 30 | MOUSUMI DAS SARKAR | 29.69 | 27.71 | 100
2145 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, development of land & others allied works of ¿KANTIPOTA HW site to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13777). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000377/2024-2025 | 3550/SWD-I | 09/08/2024 | 45 | ANUP PAUL | 32.6 | 0 | 0
2146 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for KANTIPOTA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13777] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000716/2022-2023 | 3562/SWD-I | 22/03/2023 | 15 | MOUSUMI DAS SARKAR | 3.14 | 3.14 | 100
2147 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Drum sheet walling, Road Restoration & other allied works of KANTIPOTA 2ND Site to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/13777) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001194/2024-2025 | 868/SWD-I | 26/03/2025 | 183 | MAA GITA ENTERPRISE | 41.44 | 0 | 50
2148 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000022/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 38.1 | 0 | 0
2149 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000253/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 10.98 | 0 | 0
2150 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Malipukuria PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015504] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000337/2022-2023 | 2076/SWD-I | 01/12/2022 | 30 | CAPITAL CONSTRUCTION | 30.03 | 0 | 0
2151 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for MALIPUKURIA PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13515] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000481/2022-2023 | 2810/SWD-I | 02/02/2023 | 15 | CAPITAL CONSTRUCTION | 3.13 | 0 | 0
2152 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for MALIPUKURIA Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2076] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000545/2022-2023 | 3029/SWD-I | 20/02/2023 | 300 | CE INFRASTRUCTURE | 425.11 | 41.12 | 20
2153 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall,Land Development,Pathway,Drain & others allied works of Malipukuria Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13515] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000844/2023-2024 | 1210/SWD-I | 11/03/2024 | 45 | C.E. INFRASTRUCTURE | 43.91 | 0 | 0
2154 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of MALIPUKURIA Piped Water Supply Scheme to accommodate FHTC in SONARPUR Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission". (SM/13515) (2nd call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001148/2024-2025 | 333/SWD-I | 29/01/2025 | 60 | GRANTHAM WATFORD | 10.07 | 0 | 0
2155 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000025/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 24.51 | 0 | 0
2156 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000236/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 12.79 | 0 | 0
2157 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 nos. (Two) rig bored 250 mm x 150 mm dia & 300 mtr. deep tube-well by rotary method for the Bhabanipur PWSS at Headwork Site & 2nd Tube Well site, Block- Sonarpur under South 24-Parganas W/S Division-I, PHE Dte. [TSM/015505] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000334/2022-2023 | 2072/SWD-I | 01/12/2022 | 30 | SIMPLEX DRILLING COMPANY | 30.59 | 28.63 | 100
2158 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for BHABANIPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 1292] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000544/2022-2023 | 3031/SWD-I | 20/02/2023 | 300 | CREATION CONSTRUCTION | 282.1 | 93.93 | 50
2159 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Eucalyptus Bullah piling, Land Development, Road Restoration & others allied works of BHABANIPUR PWSS within Sonarpur Block to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/13308] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000769/2023-2024 | 785/SWD-I | 15/02/2024 | 90 | DUNCON (INDIA) | 54.86 | 0 | 0
2160 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for BHABANIPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13308] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000866/2022-2023 | 3449/SWD-I | 13/03/2023 | 15 | SIMPLEX DRILLING COMPANY | 3.14 | 3.14 | 0
2161 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000005/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 13.21 | 0 | 0
2162 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000226/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 7.96 | 0 | 0
2163 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain and Development of Land & others allied works of ¿RAMCHANDRAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/13786). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000238/2024-2025 | 2658/SWD-I | 07/06/2024 | 45 | BALAJI UDYOG | 67.34 | 0 | 33
2164 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF 02 (TWO) NOS. TUBE WELL (250X150)MM DIA, 300M DEEP FOR THE RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME AT HEADWORK SITE AND 2ND TUBE WELL SITE, BLOCK- SONARPUR, UNDER SOUTH 24 PARGANAS WATER SUPPLY DIV-I, PHE.DTE. (TSM/016148) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000354/2022-2023 | 2261/SWD_I | 15/12/2022 | 30 | SAHI MASUM | 29.69 | 28.37 | 100
2165 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of Road at Publi Garden, Nil Mrittika (NP-1-5, 73-90, 112-90, 90-105, 90-115, 115-120, 151-115, 93-151, 151-154, 122-266, 266-267, 249-266, 27-43, 19-33, 25-50 & 9-18) of RAMCHANDRAPUR Piped Water Supply Scheme, Block- Sonarpur under South 24 Pgns W/S Division-I, PHE Dte. (SM/13786) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000551/2024-2025 | 4224/SWD-I | 30/09/2024 | 211 | BALAJI UDYOG | 19.97 | 0 | 80
2166 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) to all households for RAMCHANDRAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2871] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000665/2022-2023 | 3386/SWD-I | 10/03/2023 | 1008 | BALAJI UDYOG | 455.95 | 162.62 | 33
2167 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for RAMCHANDRAPUR PWSS at headwork site & 2nd Tubewell site of SONARPUR Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/13786] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000721/2022-2023 | 3561/SWD-I | 22/03/2023 | 15 | SAHI MASUM | 3.14 | 3.14 | 50
2168 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Restoration of PWD Road damaged due to laying of HDPE pipe line from chainage 0.280Kmp to 1.110 (L/S, R/S, C/L) Kmp of Narendrapur More N.S Road to EM Bye pass, Ramchandrapur, Dhamaitola Payra bagan, Karbala School Road under RAMCHANDRAPUR PWSS to accommodate FHTC in SONARPUR block under South 24 Parganas W/S Division-I for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District (SM/13786) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000744/2024-2025 | 4666/SWD-I | 18/11/2024 | 30 | BALAJI UDYOG | 26.02 | 0 | 0
2169 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Laying of additional pipeline at Ramchandrapur PWSS to accommodate FHTC in Sonarpur Block under south 24 Parganas W/S Division-I under JalJeevan Mission. [SM Code - SM/13786] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000855/2023-2024 | 1325/SWD-I | 15/03/2024 | 407 | BALAJI UDYOG | 21.72 | 0 | 80
2170 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000027/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 21.88 | 0 | 0
2171 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000237/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 17.69 | 0 | 0
2172 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Construction of 500 cum capacity OHR (20 mtr. Staging Height), Chlorine Room (3 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for Augmentation of JUGDIA Mouza of MOGRAHAT-II Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24 Pgns District. (No of FHTC = 3406) [TSM/016726] | Assistant Engineer | Junior Engineer | ORD/000081/2023-2024 | 415/SWD-I | 02/05/2023 | 730 | ROSENBLUTH CONSTRUCTION PRIVATE LIMITED | 621.42 | 0 | 45
2173 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Additional Laying of pipeline for distribution system for Proposed Ground water based JUGDIA piped water supply scheme to accommodate FHTC in MAGRAHAT-II block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14549) | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 1815/SWD-I | 07/07/2025 | 60 | RAJLAXMI CONSTRUCTION | 40.58 | 0 | 0
2174 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Sinking of 03 (Three) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for JUGDIA PWSS of MOGRAHAT-II block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district. [TSM/016726] (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 530/SWD-I | 11/05/2023 | 539 | SHANTI CONSTRUCTION | 47.45 | 29.67 | 90
2175 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 01/08/2025 to 31/01/2026] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/000120/2025-2026 | 1941/SWD-I | 23/07/2025 | 184 | AJAY KUMAR | 0.87 | 0 | 17
2176 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of land, Construction of Boundary wall (length = 133.54m) & Construction of Approach Road (length = 30.00m) at OHR site (1st Tube well Site) for JUGDIA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/14549) | Assistant Engineer | Junior Engineer | ORD/000369/2024-2025 | 3508/SWD-I | 07/08/2024 | 45 | TIYASHA ENTERPRISE | 0 | 0 | 0
2177 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Development of land, Construction of Boundary wall (length = 133.54m) & Construction of Approach Road (length = 30.00m) at OHR site (1st Tube well Site) for JUGDIA PWSS to accommodate FHTC in Mograhat-II Block under South 24 Pgns. W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24 Parganas District. (SM/14549) | Assistant Engineer | Junior Engineer | ORD/000379/2024-2025 | 3571/SWD-I | 12/08/2024 | 45 | TIYASHA ENTERPRISE | 26.83 | 0 | 0
2178 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 25/08/2024 to 31/01/2025] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/000428/2024-2025 | 3700/SWD-I | 22/08/2024 | 160 | AJAY KUMAR | 0.76 | 2.01 | 40
2179 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (TSM/016726) [w.e.f. 25/08/2023 to 23/02/2024] | Assistant Engineer | Junior Engineer | ORD/000665/2023-2024 | 1958/SWD-I | 24/08/2023 | 183 | AJAY KUMAR | 0.87 | 2.1 | 60
2180 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 24/02/2024 to 24/08/2024] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/000811/2023-2024 | 854/SWD-I | 19/02/2024 | 183 | AJAY KUMAR | 0.87 | 2.09 | 100
2181 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Preparation and submission of Detailed Project Report of Ground Water Based Jugdia Piped Water Supply Scheme to accommodate FHTC in Magrahat-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | Assistant Engineer | Junior Engineer | ORD/000983/2022-2023 | 1457/SWD-I | 26/09/2022 | 30 | GEO SOLUTION | 2.77 | 2.73 | 100
2182 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Continuation order for the work of Hiring of 1 (one) No additional Motor Cab with engine capacity less than or equal to 2000 cc, in good condition with driver and cleaner for inspection of sites of JJM works within Mograhat-II Block for the Assistant Engineer, RWS, Alipore Sub-Division, P.H.E. Dte. under south 24-Pgns, W/S Division-I, P.H.E. Dte, Govt of West Bengal with all costs towards the owner except cost of fuel and lubricant. (SM/14549) [w.e.f. 01/02/2025 to 31/07/2025] [Vehicle No:- WB-04-F-9231] | Assistant Engineer | Junior Engineer | ORD/001178/2024-2025 | 299/SWD-I | 27/01/2025 | 181 | AJAY KUMAR | 0.86 | 1.92 | 19
2183 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000129/2022-2023 | 3388/SWD-I | 10/03/2023 | 0 | Resource Division | 20.98 | 0 | 0
2184 | South 24 Pgs W/S Division I | South 24 Pgs Mechanical Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000163/2023-2024 | 630 | 19/05/2023 | 0 | Resource Division | 28.59 | 0 | 0
2185 | South 24 Pgs W/S Division I |  | Sinking of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell by Rotary method for CHANDIPUR PWSS of BUDGE BUDGE-II block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/017980] |  |  | ORD/000599/2022-2023 | 3127/SWD-I | 24/02/2023 | 30 | PROJECT AND MAINTENANCE | 15.88 | 15.18 | 100
2186 | South 24 Pgs W/S Division I |  | Construction of Pump House at Tubewell site for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000654/2022-2023 | 3352/SWD-I | 09/03/2023 | 60 | MODERN CONSTRUCTION | 10.35 | 9.94 | 100
2187 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall at Tubewell site for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000655/2022-2023 | 3353/SWD-I | 09/03/2023 | 45 | S.M ENTERPRISE | 8.02 | 6.97 | 100
2188 | South 24 Pgs W/S Division I |  | Interconnection from Tubewell to Head Work Site for chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000656/2022-2023 | 3355/SWD-I | 09/03/2023 | 30 | SUJOY SADHUKHAN | 3.97 | 3.2 | 100
2189 | South 24 Pgs W/S Division I |  | Laying distribution pipeline for Chandipur (part) PWSS to accommodate FHTC in Budge Budge-II Block under South 24-Pgns W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Area of South 24-Pgns. District (TSM/017980) |  |  | ORD/000657/2022-2023 | 3356/SWD-I | 09/03/2023 | 60 | P S CONSTRUCTION | 41.26 | 41.11 | 100
2190 | South 24 Pgs W/S Division I |  | Land Development of Tubewell site and construction of approach road of Chandipur (Part) Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II under South 24-Pgns W/S Division-I for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/14877) |  |  | ORD/000814/2023-2024 | 1150/SWD-I | 07/03/2024 | 30 | MS KRISHNA MONDAL | 9.6 | 9.54 | 100
2191 | South 24 Pgs W/S Division I |  | Preparation and submission of Detailed Project Report of Ground Water Based Chandipur Piped Water Supply Scheme to accommodate FHTC in Budge Budge-II Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. |  |  | ORD/000994/2022-2023 | 1534/SWD-I | 29/09/2022 | 30 | GEO SOLUTION | 2.37 | 2.34 | 100
2192 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.33] | AE BSD,Assistant Engineer | Junior Engineer | BILL/00493/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 4.06 | 0 | 0
2193 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Baruipur Ramnagar Uttarbhag Port Canning Road Permanent restoration work for 5800.0 mtr of trench(0.00 Km-1.20 Km, 1.70 Km-2.50 Km, and 3.50 Km-4.40 Km) Total trench length=5800 mtr, cause due to pipe laying work of PHED under South 24 Pgns.Divn, PWD in the District of South 24 Pgns during the year 2024-2025. | AE BSD,Assistant Engineer | Junior Engineer | BILL/00543/2024-2025 | BP-2024-25-332 | 24/09/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS. DIVISION, PWD | 65 | 0 | 0
2194 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for Augmentation of RAMDHARI MOUZA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 2971] [TSM/018366] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 97/SWD-I | 10/04/2023 | 90 | TANMOY ROY CHOWDHURY | 396.58 | 270.28 | 80
2195 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 04 (Four) nos. Rig Ground bored 250mm x 150mm dia. & 300 mtr. Deep Tubewell by Rotary method for RAMDHARI PWSS of Baruipur Block under South 24 Pgns. W/S Division-I, PHE Dte. (SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000426/2024-2025 | 3753/SWD-I | 28/08/2024 | 180 | ASIT PRAMANIK | 63.36 | 3.81 | 50
2196 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine room (Four nos.) at RAMDHARI piped water supply scheme to accommodate FHTC in BARUIPUR BLOCK under South 24 Parganas W/S Division-I, PHE Dte for augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (SM/15337) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 4306/SWD-I | 04/10/2024 | 60 | ALISHA CONSTRUCTION | 19.94 | 0 | 0
2197 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based RAMDHARI Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 27-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000925/2022-2023 | 1181/SWD-I | 01/09/2022 | 30 | ASTER CONSULTANCY | 3.04 | 3.04 | 100
2198 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000149/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.39 | 0 | 0
2199 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for KANTHALBERIA Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 634] [TSM/018250] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000082/2023-2024 | 416/SWD-I | 02/05/2023 | 836 | SUJAN KUMAR MISTRY | 149.57 | 84.83 | 85
2200 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for providing FHTC, protection for pipeline and other allied works for Ground water based KANTHAL BERIA piped water supply scheme to accommodate FHTC in BARUIPUR block under South 24 Parganas W/S Division-I, PHE Dte for AUGMENTATION of surface water based W/S scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15870) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000435/2024-2025 | 3879/SWD-I | 03/09/2024 | 60 | SUJAN KUMAR MISTRY | 47.19 | 0 | 0
2201 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for KANTHAL BERIA PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018250] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000641/2022-2023 | 3290/SWD-I | 03/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 29.87 | 100
2202 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Kanthal Beria Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000939/2022-2023 | 1256/SWD-I | 09/09/2022 | 30 | GEO SOLUTION | 2.46 | 2.45 | 100
2203 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000124/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 11.83 | 0 | 0
2204 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum capacity OHR (20 mtr. Staging Height) including design drawing of Pile Foundation & pile cap after soil investigation, construction of Pump House cum Chlorine Room, Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) for PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1985) (TSM/018416) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1696/SWD-I | 07/08/2023 | 751 | M.R.U. CONSTRUCTION | 472.58 | 258.43 | 25
2205 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Development of Land, Construction of internal service road, pipeline protection, drum sheet walling and others allied works at HW site & 2nd Tubewell site of "PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24 Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas District under Jal Jeevan Mission." (SM/15772) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000519/2024-2025 | 3982/SWD-I | 11/09/2024 | 386 | D-4 CONSTRUCTION | 77.7 | 0 | 50
2206 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Tube Well (250mm X 150mm) dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for PADMAPUKURIA PWSS at Head Work site and 2nd Tube Well site of Bhangar-I Block for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/018416] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000669/2022-2023 | 3411/SWD-I | 10/03/2023 | 30 | REALIENCE CONSTRUCTION | 31.79 | 7.53 | 100
2207 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 02 (two) nos. Boundary Walls, one at Headwork site & other at 2nd tube-well site, of PADMAPUKURIA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [SM/15772] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000827/2023-2024 | 1108/SWD-I | 05/03/2024 | 577 | M.R.U. CONSTRUCTION | 27.66 | 0 | 70
2208 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000044/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 21.61 | 0 | 0
2209 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000244/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 12.23 | 0 | 0
2210 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 200 Cum. capacity OHR (20 mtr. staging height), Boundary Wall, Chlorine Room along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) including design and drawing of pile foundation and pile cap after soil investigation for Augmentation of GOALBERIA Piped Water Supply Scheme of JOYNAGAR-I Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 878] [TSM/018461] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000258/2023-2024 | 1507/SWD-I | 20/07/2023 | 600 | KALPANA TRADERS | 280.17 | 107.72 | 35
2211 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for GOALBERIA PWSS of JOYNAGAR-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018461] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000645/2022-2023 | 3317/SWD-I | 06/03/2023 | 30 | MOUSUMI DAS SARKAR | 31.72 | 0 | 0
2212 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of "GOYALBERIA Ground Water Based Piped Water Supply Scheme" in JOYNAGAR-I block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. [2nd call] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000753/2022-2023 | 709/SWD-I | 23/06/2022 | 15 | ECO CARE | 2.77 | 2.52 | 100
2213 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based GOALBERIA piped water supply scheme to accommodate FHTC in JAYNAGAR-I block under South 24 Parganas W/S Division-I, South 24 Parganas District for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (SM/15774) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000865/2023-2024 | 1201/SWD-I | 11/03/2024 | 45 | MONDAL CONSTRUCTION (BARUIPUR) | 44.48 | 0 | 0
2214 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000305/2023-2024 | 2442/SWD-I | 30/09/2023 | 0 | Resource Division | 21.51 | 0 | 0
2215 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.16] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00475/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 17.53 | 0 | 0
2216 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.22] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00481/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 1.07 | 0 | 0
2217 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 200 cum OHR with soil investigation, pump house cum chlorine room, Laying rising and distrbution main pipe line with FHTC for GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 1543) (TSM/017732) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 392/SWD-I | 28/04/2023 | 887 | NIRMAN ENTERPRISE | 370.71 | 41.22 | 25
2218 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall, Pathway, Drain, Development of Land & others allied works of ¿GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission" (SM/15862). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000239/2024-2025 | 2659/SWD-I | 07/06/2024 | 45 | NIRMAN ENTERPRISE | 59.77 | 0 | 0
2219 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. Rig bored 250mm X 150mm dia & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOBINDAPUR PWSS of Sonarpur Blockfor Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24 Parganas district under South 24 Parganas Water Supply Division-I, PHE Dte. [SM/15862] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000679/2022-2023 | 3465/SWD-I | 15/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 0 | 0
2220 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Sonarpur Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/15862) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000754/2024-2025 | 4706/SWD-I | 18/11/2024 | 45 | N. ENTERPRISE | 10 | 0 | 0
2221 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000002/2023-2024 | 286/SWD-I | 24/04/2023 | 0 | Resource Division | 30.53 | 0 | 0
2222 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000225/2023-2024 | 1006/SWD-I | 09/06/2023 | 0 | Resource Division | 9.5 | 0 | 0
2223 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for BELADANGA Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15864] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 911/SWD-I | 02/04/2025 | 30 | ARUP ENTERPRISE | 15.58 | 0 | 0
2224 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 250 Cum. capacity RCC Overhead Reservoir of 20 Mtr. Staging Height as per departmental design, drawing & specification with RCC Bored Pile & Pile Cap including Soil Investigation and foundation design, Boundary Wall, Pump House cum Chlorine Room and Laying Distribution System, Rising Main and providing FHTC for Augmentation of BELADANGA Piped W/S Scheme of Joynagar-I Block for Augmentation of Surface Water based W/S Scheme in the Arsenic affected areas of South 24-Parganas District under South 24-Pgns. W/S Division-I, PHE Dte. [No. of FHTC = 1424] [TSM/020328]. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000075/2023-2024 | 389/SWD-I | 28/04/2023 | 300 | M/S T.R. CONSTRUCTION | 312.36 | 53.38 | 5
2225 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos Rig bored 250mm x 150 mm dia. & 300 mtr. deep Tubewell by Rotary method for BELADANGA PWSS to accommodate FHTC in Joynagar-I Block Under South 24 Parganas W/S Division-I, P.H.E Dte. for AUGMENTATION of surface water based Water Supply scheme in the Arsenic Affected Areas of South 24 Parganas District. (TSM/020328) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000703/2022-2023 | 3512/SWD-I | 17/03/2023 | 660 | ASIT PRAMANIK | 31.76 | 0 | 75
2226 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Beladanga Piped Water Supply Scheme to accommodate FHTC in Jaynagar-I Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000989/2022-2023 | 1493/SWD-I | 27/09/2022 | 30 | MEASURE LAND | 2.47 | 2.47 | 100
2227 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000168/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 23.95 | 0 | 0
2228 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Pump house cum Chlorine Room, Boundary Wall, along with Laying of Distribution System, Rising Main, Providing Functional Household Tap Connection (FHTC) for DAKSHIN KALYANPUR Piped Water Supply Scheme of BARUIPUR Block for implementation of JJM under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [No. of FHTC = 968] [TSM/018483] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000498/2023-2024 | 2156/SWD-I | 04/09/2023 | 850 | RAKESH ENTERPRISE | 155.54 | 96.69 | 75
2229 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of platform for FHTC, restoration of road after laying of pipeline, and other allied works for "Ground Water Based DAKSHIN KALYANPUR Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, South 24 Parganas District For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/15779) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000525/2024-2025 | 4018/SWD-I | 13/09/2024 | 60 | RAKESH ENTERPRISE (HOWRAH) | 78.26 | 0 | 0
2230 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for DAKSHIN KALYANPUR PWSS of BARUIPUR Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018483] | AE BSD,Assistant Engineer | Junior Engineer | ORD/000642/2022-2023 | 3291/SWD-I | 03/03/2023 | 30 | TAPAS KUMAR GIRI | 31.8 | 15.28 | 50
2231 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dakshin Kalyanpur Piped Water Supply Scheme to accommodate FHTC in Baruipur Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000948/2022-2023 | 1279/SWD-I | 13/09/2022 | 30 | GEO SOLUTION | 2.47 | 2.44 | 100
2232 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 01 (one) no. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method at 2nd Tubewell site for DAKSHIN KALYANPUR Piped Water Supply Scheme to accommodate FHTC in BARUIPUR Block under South 24-Parganas W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs District. [SM/15779] | AE BSD,Assistant Engineer | Junior Engineer | ORD/001190/2024-2025 | 775/SWD-I | 18/03/2025 | 30 | M/S PURNENDU SHEKHAR NASKAR | 15.87 | 0 | 0
2233 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | Junior Engineer | RTOR000117/2023-2024 | 295/SWD-I | 25/04/2023 | 0 | Resource Division | 35.27 | 0 | 0
2234 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional House Hold Tap Connection (FHTC) at DONGAJORA of KULTALI Block for Ground Water Based DONGAJORA Piped Water Supply Scheme under South 24 Paragana W/S Division-I, PHE Dte. under South 24 Pgns. Dist. (TSM/020398) | AE BSD,Assistant Engineer | Junior Engineer | ORD/000702/2022-2023 | 3511/SWD-I | 17/03/2023 | 90 | AYUSH ENTERPRISE | 77.23 | 0 | 0
2235 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of Ground Water Based Dongajora Piped Water Supply Scheme to accommodate FHTC in Kultoli Block under South 24-Pgs W/S Division-I, PHE Dte for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district.. | AE BSD,Assistant Engineer | Junior Engineer | ORD/000986/2022-2023 | 1483/SWD-I | 27/09/2022 | 30 | GEO SOLUTION | 2.4 | 2.39 | 100
2236 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Retrofitting of pipeline for supporting FHTC drive for Jamalpur W/S Scheme and adjoining areas under Budge Budge I Block with allied works under SWD - I, P.H.E. Dte District South 24 Parganas. | AE BSD |  | ORD/000077/2021-2022 | 1104/SWD-I JJM | 25/10/2021 | 120 | J.D. CONSTRUCTION | 90.16 | 88.67 | 100
2237 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Repair of Concrete Road in Budge Budge I Block for laying of Pipeline within Jamalpur W/S Scheme under South 24 Pargana W/S Divn. - I, P.H.E Dte. (TSM/8294) Part - B | AE BSD |  | ORD/000454/2022-2023 | 2729/SWD-I | 27/01/2023 | 45 | GREENS CONSTRUCTION (EMAIL ID- SUDIPTAMANNA251@GMAIL.COM) | 9.53 | 9.53 | 100
2238 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing FHTC for Zone I (Part) and adjoining areas under Thakurpukur Maheshtala Block, PHE Dte. under South 24-Pgns. W/S Division-I, PHE Dte., District-South 24 Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000007/2022-2023 | 821/SWD-I | 08/07/2022 | 1090 | M/S. S.S. ENTERPRISE | 316.71 | 0 | 80
2239 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall for proposed Pump House Site at Sonamukhi Krishnanagar under Asuti Chatta W/S Scheme , Dist. South 24 Paraganas under South 24-Pgns. W/S Divn.-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000008/2022-2023 | 850/SWD-I | 12/07/2022 | 60 | M/S. TORSA ENTERPRISE | 7.04 | 6.33 | 100
2240 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 3 nos. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Zone-I under Ashuti Chata water supply scheme in Thakurpukur-Maheshtala Block, South 24 Paraganas District. [2nd Call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000009/2022-2023 | 853/SWD-I | 12/07/2022 | 60 | M/S. S.S. ENTERPRISE | 50.84 | 47.64 | 100
2241 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supply and Installation of DI specials with allied works under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24 Pgns W/S Division-I, PHE Dte, South 24 Pgns Dist. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000021/2025-2026 | 973/SWD-I | 09/04/2025 | 30 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 18.93 | 0 | 75
2242 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Boundary wall for proposed Pump House Site at Ganney Gangadharpur Mouza near Asuti II GP under Asuti Chatta W/S Scheme , Dist. South 24 Paraganas under South 24-Pgns. W/S Divn.-I, PHE Dte. [2nd call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000068/2022-2023 | 1113/SWD-I | 23/08/2022 | 60 | JYOTI ENTERPRISE | 6.01 | 5.97 | 0
2243 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Restoration of Road (Sonamukhi Chowmatha More, Das Para road, Nandalal Chatterjee road Shibrampur Main road) damaged due to laying of 150 & 200mm dia DI Pipe of KMC Bagpota Road under Asuti I, Asuti - II and Chatta Water Supply scheme of South 24 Pargana W/S Division-I, P.H.E Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000091/2025-2026 | 1766/SWD-I | 02/07/2025 | 45 | GAYATRI CONSTRUCTION | 33.77 | 0 | 0
2244 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 03 (Three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for ASUTI- I & II and CHATTA PWSS to accomodate FHTC in THAKURPUKUR - MAHESHTALA block under South 24-Parganas W/S Division-I, P.H.E. Dte. within South 24 Parganas district. (PART-I) [TSM/019643] [2nd call] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000120/2023-2024 | 532/SWD-I | 11/05/2023 | 30 | PADMA ENGINEERING CO. | 64.72 | 61.67 | 100
2245 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance pipeline laying, road repair with allied works under proposed ground water based Asuti I Asuti II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under SWD - I, P.H.E. Dte District South 24 Parganas. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000131/2025-2026 | 2096/SWD-I | 14/08/2025 | 289 | M/S. S.S. ENTERPRISE (NODAKHALI) | 139.27 | 0 | 20
2246 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying Rising Main from proposed Tubewell to existing OHR for zone I with interconnection and bypass arrangement of Asuti Chatta W/S Scheme under Thakurpukur Maheshtala Block under South 24-Parganas W/S Division-I, PHE Dte | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000175/2021-2022 | 2389/SWD-I | 25/02/2022 | 1131 | M/S. S.S. ENTERPRISE | 67.25 | 45.42 | 25
2247 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Hiring of 01 (one) no. diesel driven Non-Air conditioned Motor Cab having BS-III & above category (Luxury Ambassador/ Indica/ Swift Dezire Car) with driver for official use of the Assistant Engineers, South 24-Pgns. W/S Sub-Division-I, under South 24-Pgns, W/S Divn-I, P.H.E. Dte. (w.e.f. 01/06/2023 to 30/11/2023) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000179/2023-2024 | 780/SWD-I | 31/05/2023 | 183 | AMARI BHADRA | 0.87 | 1.52 | 40
2248 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of UPVC pipeline for Zone-I of Chata GP under Thakurpukur-Maheshtala Water Supply Scheme under SWD-I, PHE Dte., District-South 24-Parganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000205/2022-2023 | 733/SWD-I | 27/06/2022 | 1285 | M/S. S.S. ENTERPRISE | 526.13 | 383.61 | 65
2249 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Over Head Reservoir of capacity 1500 cum at ZONE - I of Asuti-I/II & Chata water supply scheme under South 24 Pgs Water Supply Divn.-I . PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000206/2022-2023 | 158/SWD-I | 25/04/2022 | 1347 | M/S. S.S. ENTERPRISE | 344.98 | 314.94 | 100
2250 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation order for the work of Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 13/06/2024 to 30/11/2024] [Vehicle No- WB-23D-8048] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000276/2024-2025 | 2683/SWD-I | 07/06/2024 | 171 | SAROJ KUMAR SINGH | 0.81 | 2.06 | 0
2251 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road restoration from Malangermath to Neemtala damaged due to pipeline under Asuti and Asuti-II Water Supply Scheme under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000293/2024-2025 | 3132/SWD-I | 10/07/2024 | 45 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 21.38 | 21.38 | 100
2252 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 2 nos. Rig Ground bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for Zone-II under Ashuti Chata water supply scheme in Thakurpukur-Maheshtala Block, South 24 Paraganas District. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000331/2021-2022 | 2388/SWD-I JJM | 25/02/2022 | 60 | M/S. S.S. ENTERPRISE | 34.05 | 32.55 | 0
2253 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Ganney Gangadharpur (JL-28, Plot-510) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000358/2021-2022 | 2384/SWD-I | 25/02/2022 | 60 | JYOTI ENTERPRISE | 7.57 | 7.49 | 0
2254 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House at Chatta Kalikapur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000385/2020-2021 | 2065/SWD-I | 19/02/2021 | 90 | SAMPSON INFRA DESIGN LLP | 8.63 | 8.49 | 100
2255 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Shankharipota (JL-36, Plot-69) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000389/2021-2022 | 2386/SWD-I | 25/02/2022 | 60 | M/S. DAS ENTERPRISE | 7.57 | 7.19 | 100
2256 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Interconnections of 04 (Four) nos. pumps for Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur Maheshtala Block under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000393/2024-2025 | 3641/SWD-I | 20/08/2024 | 30 | M/S. S.S. ENTERPRISE (NODAKHALI) | 22.07 | 0 | 0
2257 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Sonamukhi Krishnanagar (JL-38, Plot-22) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000416/2021-2022 | 2385/SWD-I | 25/02/2022 | 60 | M/S. TORSA ENTERPRISE | 7.56 | 7.1 | 0
2258 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Balance Concrete for Over Head Reservoir of capacity 1500 cum at Zone-I of Asuti-I/II & Chata Water Supply Scheme under South 24-Pgns. Water Supply Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000441/2023-2024 | 2097/SWD-I | 30/08/2023 | 30 | M/S. S.S. ENTERPRISE | 4.02 | 4.02 | 100
2259 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chata Kalikapur (JL-22, Kh-1) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000459/2021-2022 | 2382/SWD-I | 25/02/2022 | 60 | SNEHA CONSTRUCTION | 5.02 | 4.85 | 100
2260 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Investigation of Soil for the proposed Over Head Reservoir (Capacity - 1300 m3) site inside Zone no.- I (Mouza- Kalikapur, JL No.- 22, Plot No.- 4323) of Asuti-I/Asuti-II and Chata GP W/S Scheme within Thakurpukur Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000460/2021-2022 | 1221/SWD-I | 12/11/2021 | 30 | G TECH INDIA | 0.54 | 0.54 | 100
2261 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House (Size 4.80mX3.66m) at tubewell site Chata Kalikapur (JL-22, Plot-4350) for water supply arrangement of Ashuti-Chata Water supply scheme under South 24-Pgns W/S-I, PHE Dte. Dist. South 24 Paraganas. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000606/2021-2022 | 2383/SWD-I | 25/02/2022 | 60 | M/S. SREEJIT ENTERPRISE | 6.08 | 0 | 0
2262 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Sinking of 02 (Three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tube-well having 66 mtr. housing pipe by Rotary method for ASUTI- I & II and CHATTA PWSS to accommodate FHTC in THAKURPUKUR - MAHESHTALA block under South 24-Parganas W/S Division-I, P.H.E. Dte. within South 24 Parganas district. (PART-II) [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000635/2022-2023 | 3259/SWD-I | 02/03/2023 | 30 | PADMA ENGINEERING CO. | 43.15 | 38.31 | 100
2263 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing FHTC for ground water based ASUTI I & II and CHATTA GP PWSS in Thakurpukur Maheshtala Block under South 24 Parganas W/S Division-I, PHE, Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000660/2022-2023 | 3376/SWD-I | 10/03/2023 | 60 | STAR ENTERPRISE | 17.94 | 7.98 | 40
2264 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 05 (Five) nos. Boundary Wall (Length 51 m X 5 nos.) at tubewell site for ASUTI I & II and CHATTA GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000663/2022-2023 | 3379/SWD-I | 10/03/2023 | 45 | SIMRAN ENTERPRISE | 42.26 | 13.33 | 60
2265 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Repair & Retrofitting of Civil Structures at Chatta Head Work Site with allied Works at ZONE - I of Asuti-I/II & Chatta under Proposed Ground Water Based Asuti-I/II & Chatta GP Piped Water Supply Scheme to accomodates FHTC in Thakurpukur-Maheshtala Block under South 24 Pgs Water Supply Divn.-I . PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000677/2023-2024 | 3094/SWD-I | 06/12/2023 | 757 | M/S. S.S. ENTERPRISE (NODAKHALI) | 19.5 | 5.89 | 60
2266 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 1, Plot No.- 22) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000692/2022-2023 | 3495/SWD-I | 16/03/2023 | 15 | M/S. S.S. ENTERPRISE | 2.2 | 2.11 | 100
2267 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 1, Plot No.- 510) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000693/2022-2023 | 3496/SWD-I | 16/03/2023 | 15 | M/S. S.S. ENTERPRISE | 2.2 | 2.14 | 100
2268 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Additional work for sinking of Rig bored 300 mm x 200 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for ASUTI-I/II & CHATTA PWSS of ThakurpukurMaheshtala Block for Sonamukhi- Hrishnanagar (Khatian No.- 2922, Plot No.- 4350) under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000694/2022-2023 | 3497/SWD-I | 16/03/2023 | 15 | M/S. S.S. ENTERPRISE | 2.2 | 2.14 | 100
2269 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Balance UPVC pielines within Asuti-I/II GP and extended areas under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakur pukur Mahestala Block under South 24 Pgns W/S Div I PHED (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000698/2024-2025 | 4500/SWD-I | 30/10/2024 | 152 | SUPRITI ENTERPRISE | 94.83 | 0 | 40
2270 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Providing Balance FHTC for ThakurpukurMaheshtala Block (Part) in connection to "Piped Water Supply Scheme for ASUTI I & ASUTI II GP under South 24 Parganas W/S Division-I, PHE, Dte. Dist. South 24 Pgns. [TSM/010373] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000701/2022-2023 | 3510/SWD-I | 17/03/2023 | 714 | J D J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 72.39 | 0 | 10
2271 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 05 (Five) nos. Pump Houses (Size 4.80 m X 3.66 m) at tubewell site for ASUTI I & II and CHATTA GP PWSS to accommodate FHTC in Thakurpukur-Maheshtala Block under South 24 Parganas Water Supply Division-I, PHE Dte. [TSM/019643] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000711/2022-2023 | 3536/SWD-I | 20/03/2023 | 60 | M/S J. ENTERPRISE | 34.14 | 14.76 | 55
2272 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Land Development of Chatta Kalikapur Pump House Site to facilitate the boring of Tubewell under Asuti-I / Asuti-II & Chatta W/S Scheme under South 24 Pgns W/S Division-I , PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000718/2023-2024 | 361/SWD-I | 16/01/2024 | 30 | MS POUSALI ENTERPRISE | 4.83 | 4.8 | 100
2273 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Laying of Balance UPVC pielines within Chatta GP and extended areas under Asuti-I/II & Chatta GP PWSS to accommodate FHTC in Thakurpukur-Mahestala Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000728/2024-2025 | 4615/SWD-I | 13/11/2024 | 120 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 174.51 | 0 | 45
2274 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Road Restoration of Different pathways excavates for laying of pipeline underground water based ASUTI I/II & Chatta GP PWSS to accommodate FHTC in Thakur Pukur Maheshtala Block under South 24 Parganas W/S Division -I P.H.E. Dte. (SM/ 15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000729/2024-2025 | 4616/SWD-I | 13/11/2024 | 169 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 135.92 | 0 | 45
2275 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Modification of foundation of awarded of Over Head Reservoir of capacity 1250 cum at ZONE - II of Asuti-I/II & Chata Piped Water Supply Scheme to accommodate FHTC in Thakurpukur-Maheshtala block under South 24 Pgs Water Supply Divn.-I . PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000750/2023-2024 | 552/SWD-I | 31/01/2024 | 20 | J.D.J ENTERPRISE (A UNIT OF J D J TRADERS PVT. LTD.) | 11.88 | 11.8 | 100
2276 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Development and yield testing of (4 Nos) rig ground bored 300 mm x 200 mm dia & 300 mtr. deep tube-well for Asuti-I, II and Chatta GP PWSS at Rameswarpur, Chatta Head work site, Ganney Gangadharpur and Sarsuna in the Arsenic afeected areas of South 24-Parganas district under South 24-Parganas W/S Division-I, PHE Dte. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000759/2024-2025 | 4680/SWD-I | 18/11/2024 | 30 | PADMA ENGINEERING CO. | 2.71 | 0 | 0
2277 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 16/12/2023 to 12/06/2024] [Vehicle No- WB-23D-8048] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000761/2023-2024 | 3246/SWD-I | 15/12/2023 | 180 | SAROJ KUMAR SINGH | 0.86 | 2.25 | 50
2278 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of Pump House at Ganney Gangadharpur Mouza in connection to Water Supply arrangement for Asuti I / II and Chatta under Thakurpukur Maheshtala Block under South 24-Pgns. W/S Division-I, PHE Dte. | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000767/2020-2021 | 2063/SWD-I | 19/02/2021 | 90 | J. ENTERPRISE | 9.43 | 9.3 | 100
2279 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Construction of 04 (four) nos. Switching cum control room at Kalikapur, Kalagachia, Khalpar and near Ashuti-I Panchayat office for ASUTI I/II & CHATTA GP Piped Water Supply Scheme to accommondate FHTC in THAKURPUKUR MAHESHTALA Block under South 24 Pngs Divn-I, PHE Dte, South 24 Parganas District. (SM/15660) | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/000879/2024-2025 | 4977/SWD-I | 05/12/2024 | 180 | MOTIONMASS TECHNO OPC PVT LTD | 17.66 | 0 | 50
2280 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Continuation order for the work of Hiring of 01 (one) no. diesel driven Non-Air conditioner Motor Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Assistant Engineer, Sub-Division-I under South 24-Pgns. W/S Division-I, PHE Dte.[w.e.f. 01/12/2024 to 31/05/2025] [Vehicle NoWB-23D-8048] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001062/2024-2025 | 4879/SWD-I | 29/11/2024 | 182 | SAROJ KUMAR SINGH | 0.86 | 1.84 | 50
2281 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Supply, installation, trail run, commissioning of Full Bore Electromagnetic Flow Meter in connection to PWS Scheme of proposed ground water based ASUTI- I /II & CHATTA GP piped water supply scheme to accommodate FHTC in THAKURPUKUR MAHESHTALA block under South 24 Parganas W/S Division-I, PHE Dte., South 24-Parganas District. [SM/15660] | AE SWSD-I,Assistant Engineer -II | Junior Engineer | ORD/001129/2024-2025 | 192/SWD-I | 17/01/2025 | 15 | B.S. RUBBER INDUSTRIES | 4.77 | 0 | 0
2282 | South 24 Pgs W/S Division I | Sub-Division - I under South 24 W/s Division - I | Material Requisition To Resource Division | AE SWSD-I,Assistant Engineer -II | Junior Engineer | RTOR000284/2023-2024 | 2007/SWD-I | 28/08/2023 | 0 | Resource Division | 3.73 | 0 | 0
2283 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VIIB (BINODPUR) of Kultali Block, under BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000399/2021-2022 | 2534/SWD-I | 08/03/2022 | 120 | M/S. S.S. ENTERPRISE | 739.71 | 56.36 | 0
2284 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-VIIA (BINODPUR MOUZA) of Kultali Block, under BARUIPUR Sub-Division, for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000873/2022-2023 | 72/SWD-I | 13/04/2022 | 120 | MRITYUNJOY MUKHERJEE AND CO | 518.85 | 177.33 | 60
2285 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification with R.C.C. Bored Pile & Pile Cap for Augmentation of laying distribution system to extend the benefit of 100% House hold in Zone-VII (Binodpur) at KULTALI Block within Mega Surface water based Water Supply scheme of Falta-Mathurapur District South 24 Pgns. under South 24 Pgns Water Supply Division-1, PHE Dte. [SM / 18221] | AE BSD |  | ORD/001182/2024-2025 | 629/SWD-I | 28/02/2025 | 300 | PATH MAKERS | 436.4 | 0 | 0
2286 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000042/2022-2023 | 2958/SWD-I | 16/02/2023 | 0 | Resource Division | 1067.77 | 0 | 0
2287 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000063/2022-2023 | 2978/SWD-I | 20/02/2023 | 0 | Resource Division | 443.48 | 0 | 0
2288 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000071/2022-2023 | 2987/SWD-I | 20/02/2023 | 0 | Resource Division | 29.22 | 0 | 0
2289 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000296/2023-2024 | 2434/SWD-I | 30/09/2023 | 0 | Resource Division | 33.95 | 0 | 0
2290 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Joynagar-Moydah-Jibonmondalerhat Road from1.50Kmp to 6.00kmp and 7.30 Kmp to 8.40Kmp. Restoration of Hard Shoulder due to laying of Pipeline by PHED. Go WO under Lakshmikantapur Highway Sub-Division of Diamond Harbour Highway Division, P.W.(Roads Directorate in District of South 24- Parganas. | AE BSD |  | BILL/00655/2024-2025 | BP-2024-25-396 | 04/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 11.8 | 0 | 0
2291 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Payment of Enhanced GST Rate vide W/O No.2336/SWD-I dt. 22/02/2022 | AE BSD |  | BILL/01807/2023-2024 | BP-2023-24-637 | 31/01/2024 | 0 | SAMIRON GHOSH | 20.95 | 0 | 0
2292 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Payment of Enhanced GST Rate vide W/O No.2483/SWD-I dt. 02/03/2022 | AE BSD |  | BILL/01809/2023-2024 | BP-2023-24-637 | 31/01/2024 | 0 | SAMIRON GHOSH | 4.66 | 0 | 0
2293 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Making arrangements for laying of 406.4 mm dia M.S. pipe of Tertiary Grid over Canal at Jibon Mandaler Haat under Augmentation of laying distribution system to extend the benefit of 100% Households in ZONE-II at JOYNAGAR-II Block within Mega surface water based water supply scheme of Falta-Mathurapur Dist.- South 24 pgns. under South 24 pgns Water Supply Division-I, PHE Dte. [SM/18222] | AE BSD |  | ORD/000075/2025-2026 | 1578/SWD-I | 11/06/2025 | 45 | SRIJON ENTERPRISE | 32.71 | 0 | 0
2294 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-II-B (Mayahauri) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000400/2021-2022 | 2483/SWD-I | 02/03/2022 | 1200 | SAMIRON GHOSH | 385.01 | 87.02 | 95
2295 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Laying distribution system of piped water supply at Zone-II-A (Mayahauri) of Joynagar-II Block, of BARUIPUR Sub-Division, for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under South 24 Parganas W/S Division - I, P.H.E. Dte. | AE BSD |  | ORD/000408/2021-2022 | 2336/SWD-I | 22/02/2022 | 1320 | SAMIRON GHOSH | 579.07 | 391 | 95
2296 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 1250 Cu.m. capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap For " Augmentation of laying distribution system to extend the benefit of 100% Household in ZONE-II at JOYNAGAR-II block within Mega surface water based water supply scheme of Falta-Mathurapur dist.- South 24 pgns. Under south 24 pgns water supply division-I, PHE Dte.(TSM/016052) | AE BSD |  | ORD/000431/2023-2024 | 2005/SWD-I | 28/08/2023 | 300 | M/S. S.S. ENTERPRISE | 435.92 | 0 | 0
2297 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of restoration of road, pipeline protection works and other allied works for Augmentation of laying distribution system to extend the benefit of 100% House Hold in ZONE-II at JOYNAGAR-II block within Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur District South 24 Parganas under South 24 Pgns W/S Division-I, PHE Dte. (SM/18222) (2nd call) | AE BSD |  | ORD/000736/2024-2025 | 4634/SWD-I | 14/11/2024 | 225 | P.L. CONSTRUCTION | 83.92 | 0 | 45
2298 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000065/2022-2023 | 2980/SWD-I | 20/02/2023 | 0 | Resource Division | 28.62 | 0 | 0
2299 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD |  | RTOR000293/2023-2024 | 2431/SWD-I | 30/09/2023 | 0 | Resource Division | 709.28 | 0 | 0
2300 | South 24 Pgs W/S Division I |  | Construction of platfrom for FHTC, restoration of road, Protection of Pipeline and other allied works for "Ground Water Based Hariharpur(Part-II) Piped Water Supply Scheme to Accommodate FHTC in BARUIPUR Block Under South 24 Parganas W/S Division-I, PHE Dte. For Augmentation of Surface Water Based Water Supply Scheme In Arsenic Affected Areas of South 24 Parganas District." (SM/18869) |  |  | ORD/000522/2024-2025 | 4015/SWD-I | 13/09/2024 | 60 | MODERN CONSTRUCTION (MURSHIDABAD) | 79.26 | 0 | 0
2301 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall, Chlorine Room along with Laying Distribution, Rising Main, Functional Household Tap Connection (FHTC) for Augmentation of HARIHARPUR (PART-II) of Baruipur Block of Surface Water based Water Supply Scheme in the arsenic affected areas of South 24-Parganas District [No. of FHTC = 1763] |  |  | ORD/000566/2023-2024 | 2639/SWD-I | 20/10/2023 | 523 | MODERN CONSTRUCTION (MURSHIDABAD) | 216.74 | 18.94 | 60
2302 | South 24 Pgs W/S Division I |  | Sinking of 04 (four) nos. of Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for HARIHARPUR (Part-II) PWSS to accommodate FHTC in Baruipur Block under South 24-Parganas W/S Division-I, P.H.E. Dte. for Augmentation of Surface Water Based Water Supply in the Arsenic Affected areas of South 24 Pgns. Dist. [SM/18869] |  |  | ORD/000714/2023-2024 | 3430/SWD-I | 29/12/2023 | 45 | PADMA ENGINEERING CO. | 63.59 | 32.18 | 75
2303 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Construction of 1000 cum. Capacity 20.0 M staging height R.C.C. overhead Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile and pile cap, Laying distribution system of pipe water supply scheme in Zone-II at Rajballabhpur of Mograhat-I Block for Augmentation of Mega surface water based water supply scheme and providing Functional Household Tap Connection (FHTC) in Zone-II at Rajballabhpur of Mograhat-I Block within Mega surface water based water supply scheme for Falta-Mathurapur, district ¿ South 24 Parganas under South 24 Parganas water supply Sub-Division-II of South 24 Parganas Division-I, PHE Dte. (Number of FHTC ¿ 6219 Nos.) | Assistant Engineer | JE1 | ORD/000418/2023-2024 | 1964/SWD-I | 24/08/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1097.7 | 0 | 30
2304 | South 24 Pgs W/S Division I | Sub-Division - II under South 24pgs W/s Division - I | Material Requisition To Resource Division | Assistant Engineer | JE1 | RTOR000131/2023-2024 | 322/SWD-I | 25/04/2023 | 0 | Resource Division | 38.31 | 0 | 0
2305 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance work of Laying distribution system for MAJHERHAT PWSS to accommodate FHTC in Baruipur Block under South 24 Pgns Water Supply Division-I, PHE. Dte. for Augmentation of Surface Water Based Water Supply Scheme in the Arsenic Affected Areas of South 24-Paraganas District (TSM/012625) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000043/2023-2024 | 181/SWD-I | 18/04/2023 | 90 | K P CONSTRUCTION | 31.15 | 0 | 0
2306 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of 03 (three) nos. Rig bored 300mm x 200mm dia. & 300 mtr. deep Tubewell by Rotary method for MAJERHAT PWSS of Baruipur Block under South-24 Pns W/S- Divn-I, PHE Dte., within South 24 Parganas District. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000115/2022-2023 | 1276/SWD-I | 13/09/2022 | 30 | M/S S R ENTERPRISE | 60.19 | 55.18 | 100
2307 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 03 (Three) nos. chlorination room at MAJERHAT of Baruipur Block for disinfection of ground water from big dia tube well due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. [TSM/012625] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000124/2022-2023 | 1292/SWD-I | 14/09/2022 | 961 | SWASTIK CONSTRUCTION | 16.4 | 8.34 | 100
2308 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of MAJERHAT Ground Water Based Piped Water Supply Scheme in BARUIPUR PASCHIM Assembly Constituency of BARUIPUR Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000169/2021-2022 | 1914/SWD-I | 27/01/2022 | 30 | ASTER CONSULTANCY | 2.62 | 2.62 | 100
2309 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well under ground water based piped water supply scheme at MAJERHAT of BARUIPUR Block, under surface water based W/S scheme in the arsenic affected areas of South 24 Parganas dist. (No. of FHTC = 2233) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000202/2022-2023 | 1558/SWD-I | 13/10/2022 | 120 | K P CONSTRUCTION | 358.83 | 202.91 | 100
2310 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for Sinking of 03 (Three) nos. Rig bored 300mm X 200mm dia & 300 mtr. deep Tubewell to achieve 66 mtr. housing pipe by Rotary method for Water supply arrangement for MAJHERHAT PWSS of BARUIPUR Block under South 24 Paraganas Water Supply Division-I, PHE Dte. [TSM/012625] | AE BSD,Assistant Engineer | JE-2,Junior Engineer | ORD/000782/2023-2024 | 810/SWD-I | 16/02/2024 | 30 | M/S S.R ENTERPRISE | 6.6 | 6.34 | 100
2311 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-2,Junior Engineer | RTOR000102/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 108.14 | 0 | 0
2312 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | SINKING OF RIG BORED 02 (TWO) NOS. TUBE WELL(250X150)MM DIA, 300M DEEP BY ROTARY METHOD FOR JHUNGRI PIPED WATER SUPPLY SCHEME AT HEADWORK SITE (DAG NO. 26, KHATIAN NO. 743, JL. NO. 118, MOUZA - GHUMRI) & 2ND TUBE WELL SITE (DAG NO. 116/1166, KHATIAN NO. 743, JL NO. 118, MOUZA - GHUMRI), BLOCK -BHANGAR-I, DISTRICT SOUTH 24 PARGANAS. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000003/2022-2023 | 756/SWD-I | 29/06/2022 | 30 | SIMPLEX DRILLING CO. | 28.38 | 26.02 | 100
2313 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 400 cum. capacity 20 mtr. staging height RCC Over Head Reservoir (with Soil Investigation and Pile) as per departmental drawing, 2 Nos. Pump House cum Chlorine Room, construction of approach road, Road restoration etc. along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households for Jhungri Water Supply Scheme, Block - Bhangar-I for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000307/2022-2023 | 1911/SWD-I | 18/11/2022 | 1019 | STARCO CONSTRUCTION | 660.5 | 608.02 | 85
2314 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of JHUNGRI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11273) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000562/2024-2025 | 4235/SWD-I | 30/09/2024 | 60 | TOJO ENTERPRISE | 36.45 | 0 | 0
2315 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd TW site of JHUNGRI Piped Water Supply Scheme to accommodate FHTC in BHANGAR-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/11273) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000751/2024-2025 | 4673/SWD-I | 18/11/2024 | 45 | GANAPATI ENTERPRISE | 11.47 | 0 | 0
2316 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000019/2022-2023 | 1921/SWD-I | 18/11/2022 | 0 | Resource Division | 16.4 | 0 | 0
2317 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000031/2022-2023 | 2690/SWD-I | 20/01/2023 | 0 | Resource Division | 14.98 | 0 | 0
2318 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Sinking of Rig bored 02 (Two) nos. 250mm X 150mm dia & 300 mtr. deep Tubewell by Rotary method for DEWANGANJ PWSS of Joynagar-I Block Under South 24 Parganas W/S Division-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000076/2022-2023 | 1187/SWD-I | 02/09/2022 | 30 | TAPAS KUMAR GIRI | 28.52 | 12.01 | 50
2319 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 200 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap after soil investigation alongwith Providing 100% FHTC & Laying distribution system from Big dia deep Tube Well at DEWANGANJ Mouza of JOYNAGAR-I Block due to improvement of water supply in the water Scarcity area/non command area under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns district. (No. of FHTC = 1095) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000220/2022-2023 | 1629/SWD-I | 20/10/2022 | 300 | SRIJON ENTERPRISE | 308.29 | 237.55 | 100
2320 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Preparation and submission of Detailed Project Report of DEWANGANJ Ground Water Based Piped Water Supply Scheme in JOYNAGAR-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas of South 24-Pgns. district. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000225/2021-2022 | 1965/SWD-I | 27/01/2022 | 30 | GEO SOLUTION | 2.62 | 2.59 | 100
2321 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of 02 (Two) nos. chlorination rooms at Dewanganj at Jaynagar-I Block under Surface Water Based Water Supply Scheme in the Arsenic affected areas under South 24-Pgns Water Supply Divn-I, PHE Dte. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000375/2022-2023 | 2209/SWD-I | 13/12/2022 | 60 | KHAN ENTERPRISE | 11.52 | 9.5 | 100
2322 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Construction of approach road in front of OHR site and construction of Boundary Walls at Tubewell site- 1 & 2 under Ground Water Based DEWANGANJ Pipe Water Supply Scheme to Accommodate FHTC in Jaynagar-I Block under South 24-Pgns. W/S Division-I, PHE Dte. (SM/11499) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000666/2023-2024 | 3026/SWD-I | 30/11/2023 | 60 | SRIJON ENTERPRISE | 49.36 | 21.24 | 80
2323 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for Dewanganj PWSS of Joynagar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/011007] | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000733/2022-2023 | 3584/SWD-I | 22/03/2023 | 15 | TAPAS KUMAR GIRI | 3.14 | 1.57 | 50
2324 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Balance miscellaneous work for Ground water based DEWANGANJ Piped Water Supply Scheme to accommodate FHTC in JAYNAGAR-I block under South 24-Pgns W/S Division-I, PHE Dte for AUGMENTATION of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgns District. (SM/11499) | AE BSD,Assistant Engineer | JE-1,Junior Engineer | ORD/000906/2023-2024 | 1205/SWD-I | 11/03/2024 | 360 | M/S THE BASU ENTERPRISE | 16.06 | 0 | 70
2325 | South 24 Pgs W/S Division I | Baruipur Sub-Division | Material Requisition To Resource Division | AE BSD,Assistant Engineer | JE-1,Junior Engineer | RTOR000079/2023-2024 | 294/SWD-I | 25/04/2023 | 0 | Resource Division | 46.39 | 0 | 0
2326 | South 24 Pgs W/S Division I |  | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.44] |  |  | BILL/00473/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 47.79 | 0 | 0
2327 | South 24 Pgs W/S Division I |  | Bhangor Kulti Canal from 0.00 kmp to 2.00kmp, Permanent restoration work, damaged due tp " Pipeline Laying of 90mm to 280mm dia HDPE Pipe Line along flank by PHE DEpartment " within Alipore Highway sub-Division under South 24 Parganas Highway Division in the district of South 24 Parganas. (SM/18572) |  |  | BILL/00642/2024-2025 | BP-2024-25-364 | 02/10/2024 | 0 | EXECUTIVE ENGINEER, SOUTH 24 PGS HIGHWAY DIVISION PW (ROADS) DTE | 14.93 | 0 | 0
2328 | South 24 Pgs W/S Division I |  | Sinking of 02 (Two) nos. Rig bored 250mm x 150mm dia. & 300 mtr. deep Tubewell having 66 mtr. housing pipe by Rotary method for GOBINDAPUR PWSS of BHANGAR-I block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24 Pgs district under South 24-Parganas W/S Division-I, P.H.E. Dte. [TSM/018472] (2nd Call) |  |  | ORD/000366/2023-2024 | 1775/SWD-I | 11/08/2023 | 30 | M/S SUNDARI CONSTRUCTION | 31.61 | 25.87 | 50
2329 | South 24 Pgs W/S Division I |  | Construction of 450 cum capacity OHR (20 mtr. Staging Height), Pump House cum Chlorine Room (2 Nos.) along with Laying Distribution System, Rising Main, Functional Household Tap Connection (FHTC) including design drawing of Pile Foundation & pile cap after soil investigation for GOBINDAPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (No of FHTC = 2856) (TSM/018472) |  |  | ORD/000375/2023-2024 | 1799/SWD-I | 14/08/2023 | 300 | MAJUMDER ENTERPRISE | 476.89 | 278.95 | 30
2330 | South 24 Pgs W/S Division I |  | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of GOBINDAPUR PWSS within Bhangar-I Block to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/18572) |  |  | ORD/000930/2024-2025 | 5062/SWD-I | 10/12/2024 | 75 | MAJUMDER ENTERPRISE | 172.05 | 0 | 0
2331 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1719/SWD-I | 08/08/2023 | 0 | Resource Division | 22.96 | 0 | 0
2332 | South 24 Pgs W/S Division I |  | Material Requisition To Resource Division |  |  | RTOR000324/2023-2024 | 252/SWD-I | 10/01/2024 | 0 | Resource Division | 17.59 | 0 | 0
2333 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. capacity 20 mtr. staging height RCC Over Head Reservoir alongwith Soil Investigation work, Laying Distribution System and Rising Main, providing Functional Household Tap Connection (FHTC), Construction of Pump House cum Chlorine Room etc. for Chandpur Piped Water Supply Scheme, Block-Bhangar-I, District-South 24-Parganas for for implementation of JJM under South 24-Pgns. W/S Division-I, P.H.E. Dte. [No. of FHTC = 2810] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000085/2023-2024 | 419/SWD-I | 02/05/2023 | 300 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 581.79 | 281.58 | 50
2334 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDPUR piped water supply scheme at headwork site (Dag No. 893, 894, 895 & 896/1231, Khatian No. 2422, JL. No. 124, Mouza- Chandpur) & 2nd Tubewell site (Dag No. 12, Khatian No. 359, JL No. 126, Mouza- Srirampur), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. [TSM/010665] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000458/2022-2023 | 2749/SWD-I | 27/01/2023 | 30 | ABUTALEB MONDAL | 28.51 | 0 | 0
2335 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW site of CHANDPUR PWSS within Bhangar-I Block CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission (SM/14419). | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000556/2024-2025 | 4229/SWD-I | 30/09/2024 | 60 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 96.12 | 0 | 0
2336 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/10/2023 to 31/03/2024] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000663/2023-2024 | 2387/SWD-I | 27/09/2023 | 183 | AJAY KUMAR | 0.89 | 2.11 | 30
2337 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for CHANDPUR PWSS at headwork site (Dag No. 893, 894, 895 & 896/1231, Khatian No. 2422, JL. No. 124, Mouza- Chandpur) & 2nd Tube-well site (Dag No. 12 Khatian No. 359, JL No. 126, Mouza- Srirampur) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [TSM/010665] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000741/2022-2023 | 3569/SWD-I | 22/03/2023 | 15 | ABUTALEB MONDAL | 3.13 | 0 | 0
2338 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for CHANDPUR piped water supply scheme at headwork site under Bhangar-I Block, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. [SM/14419] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000783/2023-2024 | 853/SWD-I | 19/02/2024 | 15 | M/S SABITA ENTERPRISE | 15.84 | 0 | 0
2339 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/04/2023 to 30/09/2023] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000878/2022-2023 | 3730/SWD-I | 31/03/2023 | 183 | AJAY KUMAR | 0.89 | 2.35 | 60
2340 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Continuation order for the work of "Hiring of diesel driven Non-Air conditioner Maxi Cab having BS-III & above category (Luxury Ambassador / Indica / Swift Dezire Car) with driver for official use of the Deputy Secretary / Assistant Secretary, Public Health Engineering Department, Govt. of West Bengal under South 24- Parganas Water Supply Division-I, PHE Dte " [w.e.f 01/04/2024 to 30/09/2024] [Vehicle No- WB-09-1725] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000914/2023-2024 | 1496/SWD-I | 30/03/2024 | 183 | AJAY KUMAR | 0.89 | 2.37 | 0
2341 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at 2nd Tubewell site of CHANDPUR PWSS within Bhangar-I Block "CHANDPUR Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/14419) (2nd call) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/001149/2024-2025 | 334/SWD-I | 29/01/2025 | 45 | MAHABUB RAHAMAN LASKAR | 11.37 | 0 | 0
2342 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000051/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 14.98 | 0 | 0
2343 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000219/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 17.31 | 0 | 0
2344 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.39] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00469/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 27.93 | 0 | 0
2345 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Distressed / Affected stretches of different road under P&RD Deptt. in West Bengal due to pipeline laying work by PHED [Sl. No.42] | AE HQ-I,Assistant Engineer | Junior Engineer | BILL/00472/2024-2025 | BP-2024-25-293 | 11/09/2024 | 0 | WBSRDA SOUTH 24 PGS ALIPORE | 31.04 | 0 | 0
2346 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Sinking of 02 (Two) nos. big dia Tubewell 250mm X 150mm dia & 300 mtr. deep for NAORA piped water supply scheme at headwork site (Dag No. 140, Khatian No. 586, JL. No. 130, Mouza- Kandia) & 2nd Tubewell site (Dag No. 152,160,161,166 & 174 Khatian No. 1320, JL No. 130, Mouza- Kandia), Block- Bhangar-I, Dist.- South 24-Pgns. Under South 24 Parganas W/S Division-I, PHE Dte. | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000172/2022-2023 | 1443/SWD-I | 26/09/2022 | 30 | MUNNA AGROTECH ENTERPRISE | 28.51 | 21.87 | 100
2347 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design and drawing of pile foundation and pile cap after soil investigation along with Pump House, Rising Main, Laying distribution system, Functional Household Tap Connection (FHTC) for NAORA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Partganas, W/S Division-I for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. [No. of FHTC = 2739] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000430/2023-2024 | 2004/SWD-I | 28/08/2023 | 300 | M/S SALIM CONSTRUCTION | 501.09 | 195.67 | 35
2348 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Additional work for sinking of 02 (two) nos. Rig bored 250 mm x 150 mm dia. & 300 mtr. deep Tube well to achieve 66 mtr. housing pipe by Rotary Method for NAORA PWSS at headwork site (Dag No. 140, Khatian No. 586, JL. No. 130, Mouza- Kandia) & 2nd Tubewell site (Dag No. 152, 160, 161, 166 & 174 Khatian No. 1320, JL No. 130, Mouza- Kandia) of BHANGAR-I Block under South 24-Parganas W/S Division- I, P.H.E. Dte. [SM/12017] | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000488/2022-2023 | 2808/SWD-I | 02/02/2023 | 15 | MUNNA AGROTECH ENTERPRISE | 3.13 | 3.04 | 100
2349 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Construction of Boundary Wall and others allied works at HW & 2nd Tube-well site of NAORA Piped Water Supply Scheme to accommodate FHTC in Bhangar-I Block under South 24-Parganas, W/S Division-I, PHE Dte. for Augmentation of Surface Water Based W/S Scheme in the Arsenic Affected Areas of South 24-Parganas District under Jal Jeevan Mission. (SM/12017) | AE HQ-I,Assistant Engineer | Junior Engineer | ORD/000558/2024-2025 | 4231/SWD-I | 30/09/2024 | 60 | M/S SALIM CONSTRUCTION | 93.92 | 0 | 0
2350 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000059/2023-2024 | 287/SWD-I | 24/04/2023 | 0 | Resource Division | 46.1 | 0 | 0
2351 | South 24 Pgs W/S Division I | South 24 Pgs. W/S Division - I | Material Requisition To Resource Division | AE HQ-I,Assistant Engineer | Junior Engineer | RTOR000248/2023-2024 | 1007/SWD- I | 09/06/2023 | 0 | Resource Division | 16.87 | 0 | 0
Total | [10 empty] | 313060.87 | 103520.98