## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Dwarir Jangle Mouza of Sandeshkhali-II Block from Dwarir Jangle Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000040/2020-2021 | 1882/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 96.31 | 77.3 | 1
2 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hod Connection and Allied workas at Kamduni and Kharibari Mouzas of Barasat II Block from Mahisgadi & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000053/2021-2022 | 1710/B.Ar.D. | 01/10/2021 | 90 | BALAJEE ENTERPRISES | 51.31 | 0 | 1
3 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent works of Development of Land, Protection of Pipe line and Road restoration due to laying of UPVC/HDPE Pipe line for providing FHTC of MAHISHGADI Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000054/2023-2024 | 1647/B.Ar.D. | 14/07/2023 | 45 | BALAJEE ENTERPRISES | 24.37 | 0 | 100
4 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing and renovation of 02 (two) nos pump house and 01 (one) no I.E.P room and allied works at the site of Mahisgadi W/S Scheme at Barasat - II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000082/2021-2022 | 1732/B.Ar.D | 05/10/2021 | 30 | SUN ENTERPRISE | 4.77 | 0 | 100
5 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent protection of UPVC distribution pipe line near Haroa Khal from Dilip Mondal House to Kharibari Purba para of Mahisgadi W/S scheme related to the work FHTCat Barasat - II under Barasat Arsenic Division, P.H.E. Dte. (Approx. Length = 70 mtr) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000190/2021-2022 | 362/B.Ar.D | 03/03/2022 | 15 | M/S B. B. ENGINEERING | 4.8 | 0 | 1
6 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing & Renovation of damaged Ladder of OHR & allied works at Mahishgadi Water Supply Scheme under Barasat -II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000218/2021-2022 | 337/B.Ar.D | 28/02/2022 | 15 | BALAJEE ENTERPRISES | 4.63 | 0 | 1
7 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no 250 mm. X 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation at 2nd T/W site of Atapur w/s scheme of Sandeshkhali- II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000007/2022-2023 | 849/B.Ar.D. | 06/05/2022 | 45 | M/S. S. S. ENTERPRISE | 19.74 | 0 | 1
8 | Barasat Arsenic Division | Barasat Arsenic Division | Withdrawing and relaying of pipelines and Sal-Bullah Pilling for pipe protection work at Atapur under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000010/2024-2025 | 984/B.Ar.D. | 18/06/2024 | 30 | DEL DELTA CONSTRUCTION | 5.88 | 0 | 100
9 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at ATAPUR under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000094/2022-2023 | 1567/B.Ar.D. | 25/08/2022 | 990 | M/S NIRMAN CONSTRUCTION | 192.73 | 0 | 90
10 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Atapur Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000110/2022-2023 | 1839/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0 | 1
11 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation of 136 Cum capacity OHR, Construction of 2nd Pump House Boundary Wall at OHR Site, 1st pump house & 2nd pump house pump connection and allied work for Atapur W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000198/2023-2024 | 3028/B.Ar.D. | 29/12/2023 | 50 | M/S NIRMAN CONSTRUCTION | 73.1 | 0 | 55
12 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no Replacement 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 42 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Atapur w/s Scheme at PH-I of Sandeshkhali-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000200/2022-2023 | 467/B.Ar.D. | 27/02/2023 | 45 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.81 | 0 | 1
13 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000010/2022-2023 | 2112/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 3.53 | 0 | 0
14 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000015/2022-2023 | 2288/B.Ar.D | 02/12/2022 | 0 | Resource Division | 10.97 | 0 | 0
15 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for TEGHARIA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000005/2023-2024 | 982/B.Ar.D. | 20/04/2023 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 6.01 | 0 | 100
16 | Barasat Arsenic Division |  | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area & construction of 2 nos. pump house & Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir including soil test as per Departmental design, drawing and specification including bored pile & pile cap at TEGHARIA water supply scheme, Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. |  |  | ORD/000092/2023-2024 | 1883/B.Ar.D. | 04/08/2023 | 366 | R. K. MANDAL & CO. | 343.74 | 0 | 0
17 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 74/B.Ar.D | 11/01/2024 | 0 | Resource Division | 8.9 | 0 | 0
18 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for NEW PWSS (JATRAGACHHI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000003/2023-2024 | 983/B.Ar.D. | 20/04/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.05 | 0 | 100
19 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of JATRAGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000051/2023-2024 | 1651/B.Ar.D. | 17/07/2023 | 60 | R. UNIQUE CONSTRUCTION | 6.21 | 0 | 0
20 | Barasat Arsenic Division |  | Construction of 5.48 mtr. x 3.60 mtr. size new Pump House at Head Work Site of JATRAGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000055/2023-2024 | 1661/B.Ar.D. | 18/07/2023 | 60 | M.R.H CONSTRUCTION | 7.49 | 0 | 0
21 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Jatragachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000059/2023-2024 | 1671/B.Ar.D. | 19/07/2023 | 45 | SARKAR ENTERPRISE AND CO | 18.23 | 0 | 0
22 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Jatragachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000060/2023-2024 | 1672/B.Ar.D. | 19/07/2023 | 45 | ANKUSH CONSTRUCTION & CO. | 18.22 | 0 | 0
23 | Barasat Arsenic Division |  | Jatragachhi Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 350 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Jatragachhi under Rajarhat block, Dist.- North 24 Parganas. |  |  | ORD/000081/2023-2024 | 1841/B.Ar.D. | 02/08/2023 | 366 | G. B. CONSTRUCTION AND CO. | 462.81 | 0 | 0
24 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 80/B.Ar.D | 11/01/2024 | 0 | Resource Division | 12.65 | 0 | 0
25 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for BARDASIA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000002/2023-2024 | 981/B.Ar.D. | 20/04/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.16 | 0 | 100
26 | Barasat Arsenic Division |  | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area, Construction of 2 nos pump house and Construction of 400 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir including soil test as per Departmental design, drawing and specification including bored pile & pile cap for BARDASIA Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000091/2023-2024 | 1882/B.Ar.D. | 04/08/2023 | 366 | SINGHA ROY AND CO | 430.21 | 0 | 0
27 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 62/B.Ar.D | 09/01/2024 | 0 | Resource Division | 12.12 | 0 | 0
28 | Barasat Arsenic Division |  | Laying of Distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from distribution system within command area, construction of 2 nos. pump house & construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir & soil test as per Departmental design, drawing and specification including bored pile & pile cap at KOLA water supply scheme, Barasat-II block under Barasat Arsenic Division, P.H.E. Dte |  |  | ORD/000093/2023-2024 | 1937/B.Ar.D. | 14/08/2023 | 366 | MONDAL ENTERPRISE | 639.02 | 0 | 0
29 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for KOLA Water Supply Scheme (NEW PWSS) in BARASAT-II BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000124/2023-2024 | 1836/B.Ar.D. | 01/08/2023 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 11.36 | 0 | 100
30 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 68/B.Ar.D | 10/01/2024 | 0 | Resource Division | 20.22 | 0 | 0
31 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete at Naskar Para, 3 no Para, 9 No Katkhali Para for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at DWARIR JANGLE under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000001/2023-2024 | 918/B.Ar.D. | 11/04/2023 | 45 | M/S DATTA ENTERPRISE | 46.93 | 0 | 100
32 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of Boundary Wall & Repairing of Pump House-I, IEP Room and approach road with allied work of Head Work Site for DWARIR JANGLE W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000007/2023-2024 | 917/B.Ar.D. | 11/04/2023 | 45 | M/S. PROGATI ENTERPRISE | 28.62 | 0 | 100
33 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab ( Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.06.2024 to 30.06.2024". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000020/2024-2025 | 919/B.Ar.D | 30/05/2024 | 30 | PROBIR SHAW | 0.14 | 0 | 0
34 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus - Bullah pilling for Protection of UPVC distribution pipe line at Sardarpara of Dwarir Jangle W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000031/2023-2024 | 1166/B.Ar.D. | 16/05/2023 | 21 | R. K. MANDAL & CO. | 4.79 | 0 | 100
35 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel operated motor cab (Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.07.2023 to 16.01.2024. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000047/2023-2024 | 1472/B.Ar.D | 26/06/2023 | 200 | PROBIR SHAW | 0.95 | 0 | 100
36 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of Pipeline and Repairing of House Hold Connection and Allied works at Dwarir Jangle Water Supply Scheme under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000049/2024-2025 | 1523/B.Ar.D. | 12/09/2024 | 40 | MONDAL ENTERPRISE | 13.09 | 0 | 40
37 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at DWARIR JANGLE under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000096/2022-2023 | 1568/B.Ar.D. | 25/08/2022 | 939 | M/S DIPAK ENTERPRISE | 227.76 | 0 | 92
38 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Dwarir Jangle Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000112/2022-2023 | 1841/B.Ar.D | 19/09/2022 | 20 | RISHAN ENGINEERING CONSULTANCY | 0.99 | 0 | 1
39 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 250 Cu.m. at Dwarir Jungle W/S Scheme uder Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. (SM/11707) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000158/2022-2023 | 2470/B.Ar.D. | 21/12/2022 | 60 | MONDAL ENTERPRISE | 16.13 | 0 | 1
40 | Barasat Arsenic Division | Barasat Arsenic Division | Continuation Order for "Hiring of Power Driven Mini Launch of office of the Executive Engineer, Barasat Arsenic Division, P.H.E. Dte." for the period of 183 days (i.e. from 01.10.2023 to 31.03.2024)''. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000183/2023-2024 | 2397/B.Ar.D | 29/09/2023 | 183 | RANJIT KUMAR MANDAL | 2.1 | 0 | 100
41 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of Platform for FHTC works at Dwarir Jungle Ground Water Supply Scheme under Sandeshkhali-II Block under "Jal Jiban Mission" programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000198/2022-2023 | 311/B.Ar.D. | 09/02/2023 | 30 | MONDAL ENTERPRISE | 2.97 | 0 | 100
42 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of Boundary Wall & Repairing of Pump House-II and approach road with allied work at PH-II for DWARIR JANGLE W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000207/2022-2023 | 471/B.Ar.D. | 27/02/2023 | 45 | M/S ROY CHOWDHURY & CO. | 13.15 | 0 | 100
43 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab ( Car No. WB-07J-8656) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 17.01.2024 to 31.05.2024". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000209/2023-2024 | 85/B.Ar.D | 11/01/2024 | 136 | PROBIR SHAW | 0.65 | 0 | 70
44 | Barasat Arsenic Division | Barasat Arsenic Division | Pipe protection work with Sal- Bullah Pilling and FHTC Strengthening with other allied works at DWARIR JANGLE water supply scheme under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000221/2023-2024 | 385/B.Ar.D. | 21/02/2024 | 30 | SUTAPA ENTERPRISE | 14.21 | 0 | 100
45 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method 3 No. School Para with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Dwarir Jangle w/s scheme of Sandeshkhali-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000222/2023-2024 | 386/B.Ar.D. | 21/02/2024 | 45 | M/S RAJPATH CONSTRUCTION | 19.49 | 0 | 100
46 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of Pipe line in place of damage portion of distribution system & Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at 3 No. School Para of Dwarir Jangle Supply Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000223/2023-2024 | 387/B.Ar.D. | 21/02/2024 | 60 | A 8T CONSTRUCTION | 9.77 | 0 | 80
47 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000009/2022-2023 | 2111/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 4.33 | 0 | 0
48 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000017/2022-2023 | 2290/B.ar.D | 02/12/2022 | 0 | Resource Division | 9.3 | 0 | 0
49 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Bahira & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000060/2021-2022 | 1692/B.Ar.D | 30/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 0 | 1
50 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Chakaminpur, Pakdaha and Balipur Mouzas of Barasat- II Block from Bahira Ground Water Supply Scheme Under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000126/2020-2021 | 135/B.Ar.D. | 21/01/2021 | 90 | BANI ENGINEERING CO | 87.16 | 0 | 100
51 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC Pipe Line at damaged portion of distribution network near Dadpur Gabtala Market of Bahira water supply scheme at Barasat-II Block due to construction of culvert and Drain under Barasat Arsenic Division, PHE Dte. under 'JAL JIBAN MISSION' Programme. (SM/07708) (Sl No. 3) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000140/2022-2023 | 2088/B.Ar.D. | 28/10/2022 | 21 | M/S DATTA ENTERPRISE | 4.93 | 0 | 1
52 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Fanindra Nath Karmakar and Kena Ghosh at Baghyabantapur under Bahira W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000266/2021-2022 | 476/B.Ar.D | 16/03/2022 | 15 | SAHA ENTERPRISE | 4.73 | 0 | 1
53 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Aribulla at Pagdha Dakshinpara under Bahira W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000274/2021-2022 | 480/B.Ar.D | 16/03/2022 | 15 | DIPA CHHETRI | 4.59 | 0 | 1
54 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional Household Tap Connection (FHTC) and allied works Malrameswarpur, Kharigacchi, Chaturbhujpur and Kalikapur mouza of Barasat-II Block from Chowlpur & Its Adjoining Mouzas Ground Water Supply Scheme Under "JAL SWAPNA" programme under Barasat Arsenic Division, PHE Dte. Phase-II | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000124/2021-2022 | 2077/B.Ar.D. | 02/12/2021 | 90 | BANERJEE CONSTRUCTION | 99.13 | 0 | 100
55 | Barasat Arsenic Division | Barasat Arsenic Division | Road restoration due to laying of various dia UPVC/HDPE Pipe distribution line at Kalikapur of Chowlpur W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000177/2022-2023 | 36/B.Ar.D | 05/01/2023 | 21 | P. & S. ASSOCIATES | 0.95 | 0 | 1
56 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 48 mtr length) for protection of different dia UPVC/HDPE Pipeline near pond of Sardarhati opposite Sardarhati Hari Mandir under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000178/2021-2022 | 265/B.Ar.D | 18/02/2022 | 20 | M/S DAS & CO | 4.71 | 0 | 0
57 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional School, Anganwadi and Health Center Tap Connection and allied works of Command area at Chowlpur & others Ground Water Supply Scheme under Barasat-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000192/2021-2022 | 364/B.Ar.D | 03/03/2022 | 15 | SANTU GHOSH | 3.91 | 0 | 1
58 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 50 mtr length) for protection of different dia UPVC/HDPE Pipeline near two ponds at Ghoradaria opposite Ranjit Mandal house and at Malrameswarpur Sardarhati opposite Pradip Sarkar house under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000289/2021-2022 | 563/B.Ar.D | 23/03/2022 | 15 | NANDY UDYOG | 4.66 | 0 | 0
59 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at kankrasuti mouza of Baduria Block from Jashaikati Zone -I & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000002/2021-2022 | 1035/B.Ar.D. | 07/06/2021 | 90 | UTPAL CONSTRUCTION AND CO | 96.04 | 0 | 100
60 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jasaikhati Zone - I & its adjoining mouza Water Supply Scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000027/2021-2022 | 1441/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.7 | 0 | 1
61 | Barasat Arsenic Division | Barasat Arsenic Division | Bullah Pilling for protection of Pipeline ( Approx 60 m) near pond of Sumon Haldar at Jasaikathi (Z-I) W/S Scheme at Baduria Block under Jal Swapna Programme under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000150/2021-2022 | 2232/B.Ar.D | 28/12/2021 | 30 | M/S DATTA ENTERPRISE | 4.45 | 0 | 100
62 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Mulluk Chand at danga uttarpara and Sumon Mondal at uttar chowdhury para under Jasaikathi - I W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000276/2021-2022 | 482/B.Ar.D | 16/03/2022 | 15 | TEN STAR ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.58 | 0 | 1
63 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Ramchandrapur mouza of Baduria Block from Jashaikati Zone -II & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000003/2021-2022 | 1036/B.Ar.D. | 07/06/2021 | 90 | M/S. S. S. ENTERPRISE | 91.6 | 37.95 | 1
64 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-25F-6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 08.06.2024 to 30.06.2024". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000021/2024-2025 | 944/B.Ar.D | 06/06/2024 | 23 | TOJO ENTERPRISE | 0.12 | 0 | 0
65 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Rohanda w/s scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000039/2022-2023 | 1221/B.Ar.D. | 05/07/2022 | 45 | ACME CONSTRUCTION | 14.82 | 0 | 1
66 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area of Barpol, Palitpara, Rohanda for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000048/2024-2025 | 1851/B.Ar.D. | 21/11/2024 | 30 | DEL DELTA CONSTRUCTION | 8.61 | 0 | 60
67 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000091/2022-2023 | 1711/B.Ar.D. | 02/09/2022 | 90 | GARGO TRADERS | 406.42 | 0 | 94
68 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Rohanda Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000115/2022-2023 | 1951/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0 | 1
69 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 450 Cu.m. at Rohanda W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. (SM/11557) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000157/2022-2023 | 2469/B.Ar.D. | 21/12/2022 | 60 | M.R.CONSTRUCTION | 14.74 | 0 | 1
70 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-25F-6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.12.2023 to 07.06.2024. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000167/2023-2024 | 2696/B.Ar.D | 23/11/2023 | 190 | TOJO ENTERPRISE | 0.99 | 0 | 64
71 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for ROHANDA W/S Scheme Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000213/2022-2023 | 469/B.Ar.D. | 27/02/2023 | 60 | PRAGATI CONSTRUCTION & CO | 11.55 | 0 | 90
72 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within Kachua, Noapara and Singhpara area for Augmentation of Ground Based Water Supply Scheme at Rohanda under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000238/2023-2024 | 536/B.Ar.D. | 13/03/2024 | 30 | TOJO ENTERPRISE | 24.34 | 0 | 5
73 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000012/2022-2023 | 2211/B.Ar.D. | 22/11/2022 | 0 | Resource Division | 16.29 | 0 | 0
74 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000030/2022-2023 | 30/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 16.27 | 0 | 0
75 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Magurati Srirampur Mouza of Baduria Block from Magurati Srirampur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000043/2020-2021 | 1886/B.Ar.D. | 18/12/2020 | 90 | UMA CONSTRUCTION | 39.19 | 26.02 | 1
76 | Barasat Arsenic Division | Barasat Arsenic Division | Protection of UPVC Pipeline ( approx 50 m.) near Pond of Ajarul Gazi, Safikul Islam and near Ramkrishna Brick Field under Command area of Magurati Srirampur W/S Scheme of Baduria Block in Connection of Retrofiting work for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000152/2020-2021 | 300/B.Ar.D | 03/02/2021 | 20 | NEW BRIGHT CONSTRUCTION | 3.99 | 0 | 1
77 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing and Renovation of 02 ( two) nos Pump House and allied works at the site of Magurati Srirampur W/S Scheme at Baduria block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000187/2021-2022 | 282/B.Ar.D | 22/02/2022 | 20 | NIKHIL SAMADDAR | 4.62 | 0 | 1
78 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Srikrishna Sarkar at purbapara under Magurati Srirampur W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000291/2021-2022 | 560/B.Ar.D | 23/03/2022 | 15 | A 8T CONSTRUCTION | 4.11 | 0 | 100
79 | Barasat Arsenic Division | Barasat Arsenic Division | Surrender and transfer of unspent JJM fund. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | VCH/000759/2021-2022 | 518 | 11/02/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 259.1 | 0 | 0
80 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, Distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Krishnapara & its adjoining mouza Water Supply Scheme in Hasnabad Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000030/2021-2022 | 1444/B.Ar.D | 31/08/2021 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.49 | 0 | 1
81 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Muragachha, Harikati and Krishnapara Mouzas of Hasnabad Block from Krishnapara Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000041/2020-2021 | 1884/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 83.3 | 64.89 | 1
82 | Barasat Arsenic Division | Barasat Arsenic Division | Wayleave plan & survey charges | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | BILL/00118/2023-2024 | 180 | 24/07/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 0.21 | 0 | 0
83 | Barasat Arsenic Division | Barasat Arsenic Division | Wayleave facility charges from Stn. Sondalia to Beliaghata Road Halt | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | BILL/00164/2023-2024 | 237 | 16/08/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 15.24 | 0 | 0
84 | Barasat Arsenic Division | Barasat Arsenic Division | Road Restoration of Aminpur - Boalghata road due to Laying of different dia UPVC pipe line under Paltadanga W/S Scheme at Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000073/2024-2025 | 1848/B.Ar.D | 21/11/2024 | 21 | P & S ASSOCIATES | 0.94 | 0 | 100
85 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials , valves all complete Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Paltadanga under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000092/2022-2023 | 1708/B.Ar.D. | 02/09/2022 | 1185 | M/S. S. S. ENTERPRISE | 344.61 | 0 | 98
86 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Paltadanga Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000120/2022-2023 | 1957/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0 | 1
87 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-20BP-9500) with driver for official use for Deputy Superintending Engineer, Eastern Circle, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 02.07.2023 to 30.12.2023)". | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000151/2023-2024 | 1535/B.Ar.D | 30/06/2023 | 182 | RAJ ENTERPRISE | 0.86 | 0 | 100
88 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel operated motor cab (WB-07J-7190) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 09.01.2023 to 09.07.2023). | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000178/2022-2023 | 2512/B.Ar.D | 23/12/2022 | 182 | PRIYANKI SADHUKHAN | 0.86 | 0 | 100
89 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-20BP-9500) with driver for official use for Deputy Superintending Engineer, Eastern Circle, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 01.01.2023 to 01.07.2023). | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000182/2022-2023 | 2549/B.Ar.D | 29/12/2022 | 182 | RAJ ENTERPRISE | 0.86 | 0 | 1
90 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. - WB-08C-5757) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for six months (w.e.f. 02.01.2023 to 02.07.2023). | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000183/2022-2023 | 2550/B.Ar.D | 29/12/2022 | 182 | RANA PAUL | 0.95 | 0 | 0
91 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of R.C.C. Elevated Reservoir of Capacity 550 CUM at Paltadanga W/S Scheme of Barasat - II block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000206/2022-2023 | 466/B.Ar.D. | 27/02/2023 | 60 | G. S. CONSTRUCTION & CO. | 19.14 | 0 | 100
92 | Barasat Arsenic Division | Barasat Arsenic Division | Supplying, Laying, fitting and fixing of DI pipe and Repairing, Renovation and protection of boundary wall, Fencing work etc. and other allied works at Head work site of Paltadanga Ground Water Based Piped W/S Scheme under Barasat-II Block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | ORD/000228/2023-2024 | 389/B.Ar.D | 21/02/2024 | 246 | NIKHIL SAMADDAR | 19.27 | 0 | 70
93 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | RTOR000003/2022-2023 | 2105/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 12.6 | 0 | 0
94 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, Barasat Arsenic Division | Junior Engineer | RTOR000018/2022-2023 | 2291/B.Ar.D | 02/12/2022 | 0 | Resource Division | 146.5 | 0 | 0
95 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No.- WB05 2594) with driver for official use for Deputy Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. w.e.f. 01.07.2025 to 30.11.2025". | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000044/2025-2026 | 1102/B.Ar.D | 23/06/2025 | 153 | SANGJOG | 0.73 | 0 | 0
96 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Konanagar at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000098/2022-2023 | 1571/B.Ar.D. | 25/08/2022 | 810 | M/S R. K. ENTERPRISE | 190.29 | 0 | 70
97 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Preparation of Augmentation DPR for Konanagar Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000109/2022-2023 | 1837/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.99 | 0 | 1
98 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB07J - 1216) with driver for official use of Assistant Engineer (Sub-Division), Barasat Arsenic Sub Division under B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 30.08.2024 to 31.10.2024". | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000119/2024-2025 | 1414/B.Ar.D | 29/08/2024 | 63 | OM ENTERPRISE | 0.3 | 0 | 0
99 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Konanagar W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000193/2022-2023 | 375/B.Ar.D. | 17/02/2023 | 60 | NIKHIL SAMADDAR | 13.23 | 0 | 0
100 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Hiring of one (1) no. Diesel operated motor cab (Car No. WB 07J - 1216) with driver for official use of Assistant Engineer (Sub-Division), Barasat Arsenic Sub ¿ Division under B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.03.2024 to 29.08.2024. | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | ORD/000243/2023-2024 | 430/B.Ar.D | 28/02/2024 | 182 | OM ENTERPRISE | 0.86 | 0 | 0
101 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | RTOR000013/2022-2023 | 2210/B.Ar.D. | 22/11/2022 | 0 | Resource Division | 6.92 | 0 | 0
102 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Barasat Arsenic Sub-Division | Junior Engineer | RTOR000022/2022-2023 | 2296/B.Ar.D | 02/12/2022 | 0 | Resource Division | 10.09 | 0 | 0
103 | Barasat Arsenic Division |  | Wall writing on smooth wall surface (Preferably on Govt. premises / Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and two coat best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo picture etc. of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the blocks of Hasnabad (Part), Sandeshkhali-II (Part), Baduria (Part), Haroa, Rajarhat and Barasat-II (Part) all completed as per direction of EIC. (Rate inclusive 18% GST & 1% CESS) |  |  | ORD/000084/2024-2025 | 53/B.Ar.D. | 08/01/2025 | 45 | IMAGIN | 12.33 | 0 | 80
104 | Barasat Arsenic Division |  | Restoration of damaged UPVC pipeline and withdrawing relaying of DI/HDPE pipe distribution System including specials all complete and necessary road restoration work for the scheme of "Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte". |  |  | ORD/000146/2024-2025 | 593/B.Ar.D. | 26/03/2025 | 180 | SUPRITI ENTERPRISE | 380.56 | 0 | 20
105 | Barasat Arsenic Division |  | Laying, fitting, fixing, jointing etc of Primary & Secondary Rising Main and Construction of Ground Level Reservoir (GLR) Capacity 1100 CUM with all allied works of Barasat-II Block for Surface Based PWSS for Barasat-II Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000211/2023-2024 | 159/B.Ar.D. | 25/01/2024 | 730 | SUPRITI ENTERPRISE | 2710.36 | 0 | 10
106 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for Surface Based PWSS for Barasat-II Block under Barasat Arsenic Division, P.H.E. Dte. |  |  | ORD/000241/2023-2024 | 539/B.Ar.D. | 13/03/2024 | 21 | UMWELT ENGINEER PVT. LTD. | 66.14 | 0 | 100
107 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000011/2023-2024 | 244/B.Ar.D. | 06/02/2024 | 0 | Resource Division | 4012.31 | 0 | 0
108 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bagband Saiberia w/s Scheme at Kayemba Mouza of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000009/2023-2024 | 920/B.Ar.D. | 11/04/2023 | 45 | ACME CONSTRUCTION | 15.62 | 0 | 100
109 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB25K-2915) with driver for official use for Assistant Engineer (HQ-II), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.05.2023 to 16.11.2023. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000025/2023-2024 | 1007/B.Ar.D | 26/04/2023 | 200 | PREMANANDA ROY BISWAS | 0.95 | 0 | 40
110 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No.- WB-25J-3845) with driver for official use for Superintending Engineer, PIU, North 24 Pgs., WBDWSIP, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000030/2024-2025 | 1051/B.Ar.D | 28/06/2024 | 184 | OM ENTERPRISE | 0.87 | 0 | 0
111 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (AC) (Car No. WB-25F-6815) with driver for official use for Chief Engineer (Head Quarters) in place of Director, WSSO, PHE Department. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.06.2023 to 31.08.2023." | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000040/2023-2024 | 1281/B.Ar.D | 30/05/2023 | 92 | NASIRUDDIN BISWAS | 0.48 | 0 | 100
112 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of Pipeine for Pump Connection with necessarey inter connection arrangement for Two (02) nos Pump House at Kayemba and Nababpur at Baghband Saiberia Water Supply Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000046/2024-2025 | 1581/B.Ar.D. | 23/09/2024 | 30 | SAHA ENTERPRISE | 13.53 | 0 | 100
113 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Bagband Saiberia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000093/2022-2023 | 1721/B.Ar.D. | 05/09/2022 | 630 | PUSPA ENTERPRISE | 442.01 | 0 | 86
114 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Bagband Saiberia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000121/2022-2023 | 1958/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0 | 1
115 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of 01 (one) no. pump house (4.88 X 3.66 mtr.) at the site Kayemba of Baghband Saiberia W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000147/2023-2024 | 2354/B.Ar.D. | 22/09/2023 | 45 | SUJAN KUMAR MISTRI | 5.97 | 0 | 80
116 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 800 Cu.m. at Bagband Saiberia W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. (SM/11558) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000156/2022-2023 | 2468/B.Ar.D. | 21/12/2022 | 60 | SAHA ENTERPRISE | 16.6 | 0 | 60
117 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of 01 (one) no. pump house (4.88 X 3.66 mtr.) at the site Nababpur of Baghband Saiberia W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000157/2023-2024 | 2488/B.Ar.D. | 11/10/2023 | 45 | AT CONSTRUCTION | 7.51 | 0 | 50
118 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-25K-2915) with driver for official use for Assistant Engineer (HQ - II), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 17.11.2023 to 30.11.2023". | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000178/2023-2024 | 2660/B.Ar.D | 09/11/2023 | 14 | PREMANANDA ROY BISWAS | 0.07 | 0 | 0
119 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bagband Saiberia w/s Scheme at Nababpur Mouza of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000214/2022-2023 | 468/B.Ar.D. | 27/02/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 15.62 | 0 | 100
120 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB-25L-0302) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 01.04.2023 to 30.04.2023." | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000227/2022-2023 | 827/B.Ar.D | 30/03/2023 | 30 | RANJIT KUMAR MONDAL | 0.14 | 0 | 0
121 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000014/2022-2023 | 2212/B.Ar.D. | 22/11/2022 | 0 | Resource Division | 20.91 | 0 | 0
122 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000031/2022-2023 | 31/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 20.91 | 0 | 0
123 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chowmuha & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000062/2021-2022 | 1699/B.Ar.D | 30/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.38 | 0 | 1
124 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hod Connection and Allied workas at Dhokra and Khamar Nowabad Mouzas of Barasat II Block from Chaumuha & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000073/2021-2022 | 1724/B.Ar.D. | 01/10/2021 | 90 | BALAJEE ENTERPRISES | 72.05 | 0 | 1
125 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent protection of UPVC distribution pipe line at Choumuh more of Choumah W/S scheme at Barasat II under Barasat Arsenic Division, P.H.E. Dte. (Length - 70 mtr. Approx) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000093/2021-2022 | 1830/B.Ar.D | 01/11/2021 | 30 | IDEAL CONSTRUCTION | 4.79 | 0 | 1
126 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent protection work of UPVC distribution pipe line near Chaumuha Chotopol (between Node 2-21) releted to the work of FHTC" of Chaumuha W/S scheme at Barasat - II under JALSWAPNA Programme under Barasat Arsenic Division, P.H.E. Dte. (Approx Lenth 70 mtr) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000148/2021-2022 | 2234/B.Ar.D | 28/12/2021 | 30 | A. K. DUTTA & CO. | 4.79 | 0 | 0
127 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent protection of UPVC distribution pipe line near dhokra (In between Node 44-45) of Chaumuha W/S scheme related to the work FHTCat Barasat - II under Barasat Arsenic Division, P.H.E. Dte. (Approx. Length = 70 mtr). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000191/2021-2022 | 363/B.Ar.D | 03/03/2022 | 15 | AT CONSTRUCTION | 4.79 | 0 | 1
128 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing & Renovation of damaged Ladder of OHR & Allied works of Chowmuha Water Supply Scheme under Barasat -II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000219/2021-2022 | 338/B.Ar.D | 28/02/2022 | 15 | BALAJEE ENTERPRISES | 4.64 | 0 | 1
129 | Barasat Arsenic Division | Barasat Arsenic Division | Balance portion work of repairing and renovation of 02 (two) nos pump house and 01 (one) no I.E.P room and allied works at the site of Chowma W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000259/2021-2022 | 468/B.Ar.D | 16/03/2022 | 15 | SANTU GHOSH | 4.78 | 0 | 1
130 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Bahira W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000092/2021-2022 | 1829/B.Ar.D | 01/11/2021 | 30 | S. S. CONSULTANCY & CONSTRUCTION | 4.79 | 0 | 70
131 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Connection and Allied workas at Bahira and BhagyantpurMouzas of Barasat II Block from Bahira & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000171/2020-2021 | 467/B.Ar.D. | 19/02/2021 | 90 | M/S JHARNA ENTERPRISE | 80.88 | 79.23 | 1
132 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of pathway and allied works at the site of Bahira W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000189/2021-2022 | 277/B.Ar.D | 21/02/2022 | 20 | S. S. CONSULTANCY & CONSTRUCTION | 4.59 | 0 | 1
133 | Barasat Arsenic Division | Barasat Arsenic Division | Specials Repairing of Rising Main & Interconnection of 168.3 mm dia Ms pipe 250mm dia & 150 mm dia DI pipe at Bahira H/W Site under Bahira W/S Scheme at Barasat-II block under Barasat Arsenic Division, PHE Dte. under JAL SWAPNA Programme. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000220/2021-2022 | 339/B.Ar.D | 28/02/2022 | 15 | BANI ENGINEERING CO | 4.6 | 0 | 0
134 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete at Pipre khali, 52 Para, Jeliakhali 6 no, adibashi Para for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at JELIAKHALI PASCHIM KHANDA under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000008/2023-2024 | 919/B.Ar.D. | 11/04/2023 | 45 | TRISHA ENTERPRISE AND CO. | 44.17 | 0 | 95
135 | Barasat Arsenic Division | Barasat Arsenic Division | Sal-Bullah Pilling for pipe protection work at Jeliakhali Paschim Khanda under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000012/2024-2025 | 992/B.Ar.D. | 19/06/2024 | 45 | OM ENTERPRISE | 14.47 | 0 | 100
136 | Barasat Arsenic Division | Barasat Arsenic Division | Bullah piling for protection of UPVC distribution pipe line at Jeliakhali Paschim Khanda 3 no Para of Jeliakhali Paschim Khanda W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000028/2023-2024 | 1167/B.Ar.D. | 16/05/2023 | 30 | ABDUL ALIM MONDAL | 7.52 | 0 | 100
137 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB23F - 6448) with driver for official use for Executive Engineer, Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000035/2024-2025 | 1022/B.Ar.D | 21/06/2024 | 184 | RANJIT KUMAR MANDAL | 0.87 | 0 | 0
138 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel / Petrol operated motor cab ( Car No.- WB25M 3675) with driver for official use of Assistant Engineer (HQ-I) & Assistant Engineer (HQ-II), B.Ar.D, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 14.08.2024 to 28.02.2025. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000042/2024-2025 | 1330/B.Ar.D | 14/08/2024 | 199 | SUSMITA MANDAL | 0.95 | 0 | 0
139 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of Pipeine for Pump Connection and Construction of 4.88 mtr. x 3.60 mtr. size new Pump House with at Jekiakhali Paschimkhanda Water Supply Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000044/2024-2025 | 1850/B.Ar.D. | 21/11/2024 | 45 | AMIT KUMAR BOSE | 10.45 | 0 | 0
140 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System, Laying of Rising Main including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at JELIAKHALI PASCHIM KHANDA under Sandeshkhali - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000097/2022-2023 | 1569/B.Ar.D. | 25/08/2022 | 899 | PIKASU BOSE | 193.42 | 0 | 95
141 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Jeliakhali Paschim Khanda Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000111/2022-2023 | 1840/B.Ar.D | 19/09/2022 | 20 | RISHAN ENGINEERING CONSULTANCY | 0.98 | 0 | 1
142 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No. WB23F - 6448) with driver for official use for Executive Engineer, Barasat Arsenic Division PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.01.2025 to 28.02.2025. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000134/2024-2025 | 2050/B.Ar.D | 30/12/2024 | 59 | RANJIT KUMAR MANDAL | 0.28 | 0 | 0
143 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC Pipe at damaged portion from npde 33-34, 33a-33,44a-47-470 of Jeliakhali Paschim Khanda W/S scheme of Sandeshkhali Block II for providing FHTC under Jalaswapna Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000143/2021-2022 | 2253/B.Ar.D. | 30/12/2021 | 45 | BALAJEE ENTERPRISES | 28.09 | 0 | 1
144 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 250 Cu.m. at Jeliakhali Paschim Khanda W/S Scheme under Sandeshkhali-II Block under Barasat Arsenic Division, PHE Dte. (SM/11662) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000159/2022-2023 | 2471/B.Ar.D. | 21/12/2022 | 60 | MAHALAXMI CONSTRUCTION | 15.65 | 0 | 1
145 | Barasat Arsenic Division | Barasat Arsenic Division | Bullah piling for Protection of UPVC distribution pipe line at Jeliakhali Paschim Khanda Jhil para of Jeliakhali Paschim khanda W/S Scheme under Sandeshkhali- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000202/2022-2023 | 474/B.Ar.D. | 27/02/2023 | 25 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 9.87 | 0 | 1
146 | Barasat Arsenic Division | Barasat Arsenic Division | Repair & Renovation of Iron Elementation Plant of 58 M3 including Media Change of Jeliakhali Paschim Khanda Water Supply Scheme under Sandeshkhali-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000211/2022-2023 | 476/B.Ar.D. | 27/02/2023 | 30 | IDEAL CONSTRUCTION | 4.83 | 0 | 100
147 | Barasat Arsenic Division | Barasat Arsenic Division | Continuation Order for "Hiring of Power Driven Mini Launch of office of the Executive Engineer, Barasat Arsenic Division, P.H.E. Dte." for the period of 91 days (i.e. from 01.04.2024 to 30.06.2024)''. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000256/2023-2024 | 679/B.Ar.D | 28/03/2024 | 91 | RANJIT KUMAR MANDAL | 1.04 | 0 | 100
148 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000011/2022-2023 | 2109/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 2.41 | 0 | 0
149 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000016/2022-2023 | 2289/B.Ar.D | 02/12/2022 | 0 | Resource Division | 10.97 | 0 | 0
150 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Paltadanga & its adjoining mouza water supply scheme in Barasat - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000064/2021-2022 | 1701/B.Ar.D | 30/09/2021 | 15 | UMWELT ENGINEER PVT. LTD. | 4.7 | 0 | 1
151 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Paltadanga W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000138/2021-2022 | 2218/B.Ar.D | 24/12/2021 | 30 | KUNDU CONSTRUCTION CO. | 4.79 | 0 | 1
152 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Connection and Allied workas at Kismat sonatikari, Sonatikari, Dugdia and Bharparbara Malik Mouzas of Barasat II Block from Paltadanga & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000169/2020-2021 | 465/B.Ar.D. | 19/02/2021 | 90 | BALAJEE ENTERPRISES | 60.68 | 57.65 | 1
153 | Barasat Arsenic Division | Barasat Arsenic Division | Withdrawing and Laying of UPVC Pipe Line in damaged portion of distribution network and protection work of UPVC line at Puturia -Kharbil of Puturia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000096/2021-2022 | 1833/B.Ar.D | 01/11/2021 | 30 | M/S. BAKSHI ENTERPRISE | 4.78 | 0 | 1
154 | Barasat Arsenic Division | Barasat Arsenic Division | Laying UPVC Pipeline for Providing Functional Household Tap Connection of Command area at Puturia Ground Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division PHE, Dte. (SM/08179) (Sl No. 4) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000141/2022-2023 | 2124/B.Ar.D. | 04/11/2022 | 15 | SAKTI ENTERPRISE | 2.63 | 0 | 1
155 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Connection and Allied workas at puturia and Tona Mouzas of Barasat II Block from Puturia & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000172/2020-2021 | 468/B.Ar.D. | 19/02/2021 | 90 | SAKTI ENTERPRISE | 75.31 | 18.04 | 100
156 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent protection of UPVC distribution pipe line near 2nd Pump House at PUTURIA W/S of Barasat II block under retrofitting of Puturia W/S for providing FHTC (Phase-I) under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000181/2021-2022 | 268/B.Ar.D | 18/02/2022 | 21 | BAKSHI ENTERPRISE | 4.47 | 0 | 1
157 | Barasat Arsenic Division | Barasat Arsenic Division | Withdrawal and Relaying of 160 mm dia. HDPE rising main pipeline along with protection work and other allied works near 2nd Pump House under Tildanga W/S Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000029/2023-2024 | 1168/B.Ar.D. | 16/05/2023 | 30 | M/S DATTA ENTERPRISE | 4.84 | 0 | 100
158 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Magurati Srirampur, Tildanga & its adjoining mouza Water Supply Scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000031/2021-2022 | 1445/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.06 | 0 | 1
159 | Barasat Arsenic Division | Barasat Arsenic Division | Road restoration due to laying of UPVC/HDPE Pipe line for providing FHTC of Tildanga Water Supply Scheme under Baduria Block under Barasat Arsenic Division, PHE Dte. (SM/07712) (Sl No. 1) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000138/2022-2023 | 2086/B.Ar.D. | 28/10/2022 | 15 | BALAJEE ENTERPRISES | 3.95 | 0 | 1
160 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Dakshindiara, Chak Khamarpur, Shrikati, Jagannathpur and Mahespur Mouzas of Baduria Block from Tildanga Ground Water Supply Scheme under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000217/2020-2021 | 562/B.Ar.D. | 26/02/2021 | 90 | SANJUKTA ENGINEERS | 82.47 | 40.66 | 1
161 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Asraf Ali at Srikati Sesher para under Tildanga W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000263/2021-2022 | 473/B.Ar.D | 16/03/2022 | 15 | G. S. CONSTRUCTION & CO. | 4.45 | 0 | 1
162 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jeliakhali Paschim Khanda Water Supply Scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000028/2021-2022 | 1442/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.71 | 0 | 1
163 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hod Connection and Allied workas at 4 nos habitation of Jelia Khali Paschim Khanda Mouzas of Sandeshkhali II Block from Jeliakhali Paschim Khanda Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000074/2021-2022 | 1725/B.Ar.D. | 01/10/2021 | 90 | BALAJEE ENTERPRISES | 51.57 | 0 | 85
164 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Chaumuha Mouza of Barasat- II Block from Chaumuha Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000042/2020-2021 | 1885/B.Ar.D. | 18/12/2020 | 90 | UMWELT ENGINEER PVT. LTD. | 91.5 | 82.54 | 1
165 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Jeliakhali Pashchim Mouza of Sandeshkhali-II Block from Jeliakhali Pashchim Khanda Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000038/2020-2021 | 1883/B.Ar.D. | 18/12/2020 | 90 | M/S. S. S. ENTERPRISE | 96.55 | 95.72 | 1
166 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Konanagar , Rajapura & its adjoining mouza Water Supply Scheme in Hasnabad Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000029/2021-2022 | 1443/B.Ar.D | 31/08/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.74 | 0 | 1
167 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Khorda, Jalsira and Konanagar Mouzas of Hasnabad Block from Konanagar Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000035/2020-2021 | 1880/B.Ar.D. | 18/12/2020 | 90 | M/S ROY CHOWDHURY & CO. | 82.2 | 73.19 | 1
168 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Magurati Srirampur Mouza of Baduria Block from Magurati Srirampur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000043/2020-2021 | 1886/B.Ar.D. | 18/12/2020 | 90 | UMA CONSTRUCTION | 39.19 | 7.11 | 1
169 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chowlpur & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000061/2021-2022 | 1698/B.Ar.D | 30/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.04 | 0 | 1
170 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Chowlpur W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000140/2021-2022 | 2217/B.Ar.D | 24/12/2021 | 30 | CHOWDHURY CONSTRUCTION | 4.8 | 0 | 1
171 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 50 mtr length) for protection of different dia UPVC/HDPE Pipeline near two ponds at Ghoradaria opposite Gour Biswas house and at Malrameswarpur Sardarhati opposite Pranab Sarkar house under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000184/2021-2022 | 288/B.Ar.D | 23/02/2022 | 20 | CHOWDHURY CONSTRUCTION | 4.8 | 0 | 1
172 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Chowlpur, Ghoradaria and Mitpukuria Mouzas of Barasat- II Block from Chowlpur Ground Water Supply Scheme under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000216/2020-2021 | 561/B.Ar.D. | 26/02/2021 | 90 | SANJUKTA ENGINEERS | 77.59 | 44.48 | 1
173 | Barasat Arsenic Division | Barasat Arsenic Division | Renovation of Pathway and Painting of boundary wall and other allied works at Chowlpur Head Work Site under Chowlpur Water Supply scheme of Barasat ll Block under JAL SWAPNA Programme under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000278/2021-2022 | 484/B.Ar.D | 16/03/2022 | 15 | MODERN CONSTRUCTIONS | 4.64 | 0 | 1
174 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation at 2nd T/W site of Magurati Srirampur w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 2) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000027/2022-2023 | 1106/B.Ar.D. | 17/06/2022 | 45 | ACME CONSTRUCTION | 14.61 | 0 | 1
175 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC pipe line for Providing Functional House Hold Tap Connection under command area of Magurati Srirampur water supply scheme of Baduria Block under JJM Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000191/2022-2023 | 243/B.Ar.D. | 02/02/2023 | 30 | UMA CONSTRUCTION | 13.6 | 0 | 90
176 | Barasat Arsenic Division | Barasat Arsenic Division | Sal-Bullah Pilling for pipe protection work at Bahira under Barasat-II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000007/2024-2025 | 981/B.Ar.D. | 18/06/2024 | 25 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 5.85 | 0 | 100
177 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel operated motor cab (Car No.- WB25L-3454) with driver for official use for Assistant Engineer (Sub-Division), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 01.05.2023 to 16.11.2023. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000026/2023-2024 | 1008/B.Ar.D | 26/04/2023 | 200 | PREMANANDA ROY BISWAS | 0.95 | 0 | 70
178 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Bahira Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000119/2022-2023 | 1956/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0 | 1
179 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking of 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near H/W Side with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter for Augmentation of Bahira w/s scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 1) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000131/2022-2023 | 2055/B.Ar.D. | 19/10/2022 | 45 | UNIFIED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 15.58 | 0 | 70
180 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials, valves all complete Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Bahira under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000136/2022-2023 | 1742/B.Ar.D. | 07/09/2022 | 90 | MADE AND TRADE CO. | 311.1 | 0 | 72
181 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (Car No.- WB-25L-3454) with driver for official use for Assistant Engineer (Sub-Division), under Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil w.e.f. 17.11.2023 to 30.11.2023". | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000177/2023-2024 | 2661/B.Ar.D | 09/11/2023 | 14 | PREMANANDA ROY BISWAS | 0.07 | 0 | 0
182 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 550 Cu.m. at Bahira W/S Scheme under Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000187/2022-2023 | 237/B.Ar.D. | 02/02/2023 | 841 | MONDAL ENTERPRISE | 16.32 | 0 | 40
183 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000029/2022-2023 | 28/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 12.26 | 0 | 0
184 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000033/2022-2023 | 205/B.Ar.D. | 30/01/2023 | 0 | Resource Division | 16.41 | 0 | 0
185 | Barasat Arsenic Division | Barasat Arsenic Division | Increse of Water pressure through by pass Pipeline from Second tubewell to main distribution pipeline and allied repairing works in Chaumuha Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000009/2024-2025 | 983/B.Ar.D. | 18/06/2024 | 21 | BANERJEE CONSTRUCTION | 2.53 | 0 | 100
186 | Barasat Arsenic Division | Barasat Arsenic Division | Restoration of Road due to Laying of 200 mm dia D.I rising main from 2nd Tubewell to Head work site at Chaumuha Purbapara of Chaumuha W/S scheme at Barasat - II under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000071/2024-2025 | 1847/B.Ar.D | 21/11/2024 | 21 | R. UNIQUE CONSTRUCTION | 0.95 | 0 | 100
187 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000087/2022-2023 | 1557/B.Ar.D. | 24/08/2022 | 900 | BANERJEE CONSTRUCTION | 168.13 | 0 | 90
188 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Chowmuha Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000118/2022-2023 | 1954/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0 | 1
189 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 459-460&106-107 related to the work " Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte." (60mtr) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000148/2023-2024 | 2374/B.Ar.D. | 27/09/2023 | 30 | NEELAM ENTERPRISE | 5.89 | 0 | 100
190 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 459-460 & 106-107 related to the work "Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte." (60mtr). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000173/2023-2024 | 2658/B.Ar.D. | 09/11/2023 | 30 | MONDAL ENTERPRISE | 5.93 | 0 | 100
191 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of 250 Cum OHR and allied water supply component infrastructure under Chaumuha W/S Scheme of Barasat -II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000196/2023-2024 | 3026/B.Ar.D. | 29/12/2023 | 45 | BANERJEE CONSTRUCTION | 19.55 | 0 | 100
192 | Barasat Arsenic Division | Barasat Arsenic Division | Emergent Protection of 90 mm dia UPVC Pipeline in between Node 374-376 related to the work " Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chaumuha Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000200/2023-2024 | 3029/B.Ar.D. | 29/12/2023 | 30 | RHINE CONSTRUCTION | 4.63 | 0 | 100
193 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of 200 mm dia D.I rising main from 2nd Tubewell to Head work site of Chaumuha W/S scheme at Barasat - II under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000202/2023-2024 | 3007/B.Ar.D | 28/12/2023 | 21 | R. UNIQUE CONSTRUCTION | 0.93 | 0 | 100
194 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000028/2022-2023 | 29/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 1.53 | 0 | 0
195 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Bagband-Sarberia, Kirttipur and Krishnamati Mouzas of Barasat- II Block from Bagband Saiberia Ground Water Supply Scheme Under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000124/2020-2021 | 128/B.Ar.D. | 20/01/2021 | 90 | R. K. MANDAL & CO. | 85.38 | 70.76 | 100
196 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of HDPE Pipe Line in damaged portion of distribution network at Gobindapur under Bagband-Saiberia Water Supply Scheme under under Barasat Arsenic Division, PHE Dte. (SM/07709) (Sl No. 2) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000139/2022-2023 | 2087/B.Ar.D. | 28/10/2022 | 21 | BALAJEE ENTERPRISES | 4.2 | 0 | 1
197 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional School , Anganwadi and Health Center Tap Connection and allied works of Command area at Bagband-Saiberia Ground Water Supply Scheme under Barasat-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000180/2021-2022 | 267/B.Ar.D | 18/02/2022 | 20 | A P POWER AND CONCRETE | 3.9 | 0 | 1
198 | Barasat Arsenic Division |  | Sinking of 300 mm. x 200 mm. dia. x 330 mtr. deep tube well by direct rotary rig method for 3rd Tubewell at Thakdari of Zone - V, near Thakdari Head Work site under SWBPWSS under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000022/2022-2023 | 1000/B.Ar.D. | 02/06/2022 | 45 | AUXILIARY TUBEWELL DRILLERS | 21.16 | 0 | 100
199 | Barasat Arsenic Division |  | Construction of 1 (one) no. (G+1 Storied) switch room cum chlorine room and Scada Room (4.1m x 5.9m) including sanitary arrangement the site of Thakdari W/S scheme under Barasat Arsenic Division. PHE Dte. |  |  | ORD/000056/2024-2025 | 1875/B.Ar.D. | 26/11/2024 | 50 | ROY BISWAS CONSTRUCTION | 15.43 | 0 | 0
200 | Barasat Arsenic Division |  | Supplying & laying, fitting, fixing, jointing etc. of different dia HDPE pipe line for distribution system and Laying of Rising Main from existing H/W Site to OHR Site and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN6) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete for Thakdari Water Supply Scheme under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000061/2023-2024 | 1775/B.Ar.D. | 27/07/2023 | 366 | SAHA ENTERPRISE | 123.54 | 0 | 0
201 | Barasat Arsenic Division |  | Connection of Newly constructed OHR at Thakdari and Other Allied Works under Thakdari Water Supply Scheme under Barasat Arsenic Division. |  |  | ORD/000104/2024-2025 | 79/B.Ar.D | 13/01/2025 | 45 | OM ENTERPRISE | 5.37 | 0 | 100
202 | Barasat Arsenic Division |  | Supply, delivery, installation & commissioning of 200 mm Dia Electromagnetic Flowmeter, RTU, Sluice valve etc. and other allied works at Thakdari water supply Scheme under Rajarhat Block under SWBPWSS in Rajarhat, Haroa & Bhangar II Block in North 24 Parganas District under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000123/2023-2024 | 1936/B.Ar.D. | 14/08/2023 | 723 | MSA INSTRUMENTS | 6.43 | 0 | 80
203 | Barasat Arsenic Division |  | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme Thakdari under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000141/2023-2024 | 2334/B.Ar.D. | 21/09/2023 | 21 | UMWELT ENGINEER PVT. LTD. | 3.23 | 0 | 100
204 | Barasat Arsenic Division |  | Construction of Boundary Wall at Thakdari OHR site under SWBPWSS for arsenic affected areas of Haroa, Rajarhat & Bhangar-II Block under Barasat Arsenic Division. PHE Dte. |  |  | ORD/000188/2023-2024 | 2941/B.Ar.D. | 22/12/2023 | 70 | AZAD CONSTRUCTION | 20.36 | 0 | 85
205 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Atapur Water Supply Scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000026/2021-2022 | 1440/B.Ar.D | 31/08/2021 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.41 | 0 | 0
206 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Atapur Mouza of Sandeshkhali-II Block from Atapur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000127/2020-2021 | 136/B.Ar.D. | 21/01/2021 | 90 | M/S NIRMAN CONSTRUCTION | 60.13 | 35.13 | 80
207 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC Pipe Line from pump house no 1 towards Duchnekhali bazar for Functional House Hold Tap Connection under command area of Atapur water supply scheme of Sandeshkhali - II Block under JJM Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000189/2022-2023 | 470/B.Ar.D. | 27/02/2023 | 30 | P. & S. ASSOCIATES | 11.83 | 0 | 0
208 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional School , Anganwadi and Health Center Tap Connection and allied works of Command area at Atapur, Dwarir Jungle & Jeliakhali Paschim Khanda Ground Water Supply Scheme under Sandeshkhali-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000223/2021-2022 | 341/B.Ar.D | 28/02/2022 | 15 | M/S.KRISHNA MONDAL | 3.97 | 0 | 0
209 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of OHR and allied water supply component infrastructure under Tildanga W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000023/2023-2024 | 949/B.Ar.D. | 17/04/2023 | 60 | MONDAL ENTERPRISE | 12.55 | 0 | 100
210 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Tildanga at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000099/2022-2023 | 1572/B.Ar.D. | 25/08/2022 | 900 | AMIT KUMAR BOSE | 249.41 | 0 | 81
211 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Tildanga Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000105/2022-2023 | 1833/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0 | 1
212 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Tildanga w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 4) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000134/2022-2023 | 2058/B.Ar.D. | 19/10/2022 | 45 | TRISHA ENTERPRISE AND CO. | 15.35 | 0 | 1
213 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of pipe line & inter connection at PH No.-3 for Tildanga water supply scheme under Baduria Block in the district of North 24 Parganas under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000180/2024-2025 | 433/B.Ar.D. | 10/03/2025 | 30 | CHOWDHURY CONSTRUCTION | 4.68 | 0 | 0
214 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC/HDPE pipeline and Repairing , Rennovation of Boundary wall, Fencing work etc and other allied works at Head work site of Tildanga W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000230/2023-2024 | 391/B.Ar.D | 21/02/2024 | 45 | KUNDU CONSTRUCTION CO. | 12.41 | 0 | 100
215 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000007/2022-2023 | 2113/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 9.89 | 0 | 0
216 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000023/2022-2023 | 2294/B.Ar.D | 02/12/2022 | 0 | Resource Division | 9.3 | 0 | 0
217 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Raigachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000082/2023-2024 | 1940/B.Ar.D. | 14/08/2023 | 45 | NEW LIFE CONSTRUCTION | 18.18 | 0 | 0
218 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Raigachhi Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000083/2023-2024 | 1941/B.Ar.D. | 14/08/2023 | 45 | ABDUL HAMID GAZI | 18.17 | 0 | 0
219 | Barasat Arsenic Division |  | Raigachhi Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 350 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Raigachhi under Rajarhat block, Dist.- North 24 Parganas. |  |  | ORD/000094/2023-2024 | 1934/B.Ar.D. | 11/08/2023 | 731 | BALAJEE ENTERPRISES | 416.01 | 0 | 20
220 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for NEW PWSS (RAIGACHHI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000125/2023-2024 | 1837/B.Ar.D. | 01/08/2023 | 30 | TIYAS CONSULTANCY AND INFRASTRUCTURE PRIVATE LIMITED | 7.85 | 0 | 100
221 | Barasat Arsenic Division |  | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of RAIGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000133/2023-2024 | 1990/B.Ar.D. | 18/08/2023 | 60 | SAFE STEP ENTERPRISE | 7.29 | 0 | 0
222 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of RAIGACHI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000134/2023-2024 | 1991/B.Ar.D. | 18/08/2023 | 60 | B.M.TRADERS | 6.19 | 0 | 0
223 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 79/B.Ar.D | 11/01/2024 | 0 | Resource Division | 12.75 | 0 | 0
224 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB25K - 2915) with driver for official use for Assistant Engineer (HQ-II), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000037/2024-2025 | 1024/B.Ar.D | 21/06/2024 | 184 | PREMANANDA ROY BISWAS | 0.87 | 0 | 0
225 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated AC motor cab / maxi cab (Car No. WB-08C-5757) with engine capacity less than or equal to 2000 C.C. with driver for official use for Chief Engineer (Head Quarters), PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 03.07.2023 to 30.09.2023". | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000041/2023-2024 | 1533/B.Ar.D | 30/06/2023 | 90 | RANA PAUL | 0.47 | 0 | 100
226 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No.- WB07J - 1216) with driver for official use of Assistant Engineer, Sub - Division under Barasat Arsenic Division, PHE Dte. for different works under JJM Schemes with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil (w.e.f. 01.05.2025 to 30.09.2025)". | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000050/2025-2026 | 760/B.Ar.D | 23/04/2025 | 153 | OM ENTERPRISE | 0.73 | 0 | 0
227 | Barasat Arsenic Division | Barasat Arsenic Division | Supplying, laying , fitting & fixing of different dia DI(K7) and UPVC pipes for distribution network and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000138/2024-2025 | 233/B.Ar.D | 06/02/2025 | 300 | P & S ASSOCIATES | 54.21 | 0 | 15
228 | Barasat Arsenic Division | Barasat Arsenic Division | Reconnection and strenthening of existing Functional Household Tap Connection and other allied works at Command area of Chowlpur Ground Water Supply Scheme under Barasat-II Block Under '' JAL JIVAN MISSION'' programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000149/2023-2024 | 2375/B.Ar.D. | 27/09/2023 | 30 | PRAGATI CONSTRUCTION & CO | 2.93 | 0 | 100
229 | Barasat Arsenic Division | Barasat Arsenic Division | Supplying, Laying, fitting & fixing of different dia UPVC pipe and other allied works at Command area of Chowlpur Ground Water Supply Scheme under Barasat-II Block Under '' JAL JIVAN MISSION'' programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000150/2023-2024 | 2376/B.Ar.D. | 27/09/2023 | 30 | CHOWDHURY CONSTRUCTION | 4.81 | 0 | 100
230 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of R.C.C. Elevated Reservoir of Capacity 350 CUM at Chowlpur W/S Scheme of Barasat - II block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000170/2023-2024 | 2655/B.Ar.D. | 09/11/2023 | 45 | B S ENTERPRISE | 13.24 | 0 | 100
231 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000175/2022-2023 | 120/B.Ar.D. | 18/01/2023 | 60 | M.R.CONSTRUCTION | 63.85 | 0 | 100
232 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional Household Tap Connection and allied works of Command area at Chowlpur Ground Water Supply Scheme under Barasat-II Block Under '' JAL JIVAN MISSION'' programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000204/2022-2023 | 475/B.Ar.D. | 27/02/2023 | 30 | TOJO ENTERPRISE | 6.09 | 0 | 100
233 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection (FHTC) for uncovered area and laying UPVC / HDPE pipeline and alied works within command area at Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000219/2023-2024 | 383/B.Ar.D. | 21/02/2024 | 30 | P. & S. ASSOCIATES | 68.22 | 0 | 65
234 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000001/2024-2025 | 1472/B.Ar.D. | 06/09/2024 | 0 | Resource Division | 49.19 | 0 | 0
235 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Sal-Bullah Pilling for pipe protection work at Rajapura under Hasnabad Block Under Barasat Arsenic Division, PHE Dte. |  | Junior Engineer | ORD/000013/2024-2025 | 993/B.Ar.D. | 19/06/2024 | 40 | M/S ROY CHOWDHURY & CO. | 14.43 | 0 | 100
236 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Preparation of Augmentation DPR for Rajapura Water Supply Scheme under Barasat Arsenic Division, PHE Dte. |  | Junior Engineer | ORD/000024/2023-2024 | 1030/B.Ar.D | 28/04/2023 | 21 | SIRCON ENGINEERING SERVICES | 0.98 | 0 | 100
237 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Laying of distribution system including specials all providing Functional House hold Tap Connection (FHTC) from existing and new proposed distribution system system within command area for Augmentation of Ground Based Water Supply Scheme at Rajapura at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. |  | Junior Engineer | ORD/000048/2023-2024 | 1621/B.Ar.D. | 12/07/2023 | 60 | B S ENTERPRISE | 48.59 | 0 | 100
238 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Rajapura at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. |  | Junior Engineer | ORD/000155/2022-2023 | 2326/BArD | 06/12/2022 | 90 | SAKTI ENTERPRISE | 115.75 | 0 | 100
239 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Rajapura W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. |  | Junior Engineer | ORD/000195/2022-2023 | 276/B.Ar.D. | 06/02/2023 | 60 | MONDAL ENTERPRISE | 11.21 | 0 | 1
240 | Barasat Arsenic Division | Barasat Arsenic Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000027/2022-2023 | 27/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 1.72 | 0 | 0
241 | Barasat Arsenic Division | Barasat Arsenic Division | Repair & Renovation of Iron Elimination Plant of 161 M3 including Media Change of Puturia Water Supply Scheme under Barasat- II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000027/2023-2024 | 1165/B.Ar.D. | 16/05/2023 | 30 | GHOSH CONSTRUCTION | 8.71 | 0 | 100
242 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Puturia & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000039/2021-2022 | 1563/B.Ar.D. | 15/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.19 | 0 | 1
243 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Simulgachhi, Bonkanda and Baidyapur Mouzas of Barasat- II Block from Puturia Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000123/2020-2021 | 127/B.Ar.D. | 20/01/2021 | 90 | BANI ENGINEERING CO | 94.63 | 19.75 | 100
244 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Jiyawal at Bokanda Majher Para under Puturia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000265/2021-2022 | 475/B.Ar.D | 16/03/2022 | 15 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 4.68 | 0 | 1
245 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near Najrul house and Hafijul house at Simulgachi under Puturia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000275/2021-2022 | 481/B.Ar.D | 16/03/2022 | 15 | M/S.KRISHNA MONDAL | 4.79 | 0 | 70
246 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hod Connection and Allied workas at Ramchandra pur khas pur, Hugle and Keutsa Mouzas of Baduria Block from Jasikhati Zone-II & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000052/2021-2022 | 1709/B.Ar.D. | 01/10/2021 | 90 | UTPAL CONSTRUCTION AND CO | 73.47 | 0 | 1
247 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jashaikati Zone - II & its adjoining mouza water supply scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000066/2021-2022 | 1703/B.Ar.D | 30/09/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.7 | 0 | 1
248 | Barasat Arsenic Division | Barasat Arsenic Division | Repairing and Renovation of 02 ( two) nos Pump House and allied works at the site of Jasaikathi ( Zone-II ) W/S Scheme at Baduria block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000179/2021-2022 | 266/B.Ar.D | 18/02/2022 | 20 | NEELAM ENTERPRISE | 4.72 | 0 | 1
249 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Akbar Biswas and others at Hugle under Jasaikathi - II W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000277/2021-2022 | 483/B.Ar.D | 16/03/2022 | 15 | RHINE CONSTRUCTION | 4.72 | 0 | 1
250 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Jashaikati mouza of Baduria Block from Jashaikati ( Zone-I ) & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000123/2021-2022 | 2078/B.Ar.D. | 02/12/2021 | 90 | KINGS & CO. | 117.37 | 0 | 100
251 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Sumon Mondal under Jasaikathi - I W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000267/2021-2022 | 477/B.Ar.D | 16/03/2022 | 15 | M/S DATTA ENTERPRISE | 4.47 | 0 | 100
252 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Palitpara, Rohanda, Noapara, Banpol, Singhapra mouza's of Barasat - II Block from Rohanda & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000004/2021-2022 | 1037/B.Ar.D. | 07/06/2021 | 90 | S. P. CONSTRUCTION | 95.15 | 85.36 | 100
253 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Rohanda & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000040/2021-2022 | 1564/B.Ar.D. | 15/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.78 | 0 | 1
254 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel / Petrol operated AC motor cab / maxi cab (Car No. - WB25F - 6815) with engine capacity less than or equal to 2000 C.C. with driver for official use of the Chief Engineer (Head Quarters), Office, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000033/2024-2025 | 1047/F/B.Ar.D | 27/06/2024 | 184 | TOJO ENTERPRISE | 0.96 | 0 | 0
255 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for Jasaikathi ( Z-II ) W/S Scheme Under Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000071/2023-2024 | 1796/B.Ar.D. | 28/07/2023 | 60 | AFRINA ENTERPRISE | 11.68 | 0 | 100
256 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Jasaikathi (Zone-II) Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000107/2022-2023 | 1835/B.Ar.D | 19/09/2022 | 20 | RISHAN ENGINEERING CONSULTANCY | 0.98 | 0 | 1
257 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Jasaikathi Zone -II at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000113/2022-2023 | 1635/B.Ar.D. | 30/08/2022 | 990 | CHANCHAL ENTERPRISE & CO. | 284.52 | 0 | 86
258 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Jasaikathi (Z-II) w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 3) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000133/2022-2023 | 2057/B.Ar.D. | 19/10/2022 | 45 | M/S RAJPATH CONSTRUCTION | 15.35 | 0 | 1
259 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 550 Cu.m. at Jasaikathi (Z-II) W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000188/2022-2023 | 238/B.Ar.D. | 02/02/2023 | 60 | M/S DATTA ENTERPRISE | 13.66 | 0 | 1
260 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of DI pipe and Repairing, Rennovation and protection of boundary wall, Fencing work etc and other allied works at Head work site of Jasaikathi-(Z-II) W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000232/2023-2024 | 393/B.Ar.D | 21/02/2024 | 45 | MAHALAXMI CONSTRUCTION | 14.79 | 0 | 100
261 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000004/2022-2023 | 2106/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 9.61 | 0 | 0
262 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000020/2022-2023 | 2293/B.Ar. | 02/12/2022 | 0 | Resource Division | 10.97 | 0 | 0
263 | Barasat Arsenic Division | Barasat Arsenic Division | Increse of Water pressure through by pass Pipeline from Second tubewell to main distribution pipeline and dedicated pipeline for I.E.P. to haroa khal in Mahisgadi Water Supply Scheme under Barasat Arsenic Division, P.H.E Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000008/2024-2025 | 982/B.Ar.D. | 18/06/2024 | 40 | SUJAN KUMAR MISTRI | 4.08 | 0 | 0
264 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of one (1) no. Diesel / Petrol operated motor cab (Car No. - WB19J - 2141) with driver for official use for Assistant Engineer (HQ-I), Barasat Arsenic Division, PHE Dte. with all costs towards the owner except fuel cost i.e. Diesel / Petrol, Mobil oil w.e.f. 01.07.2024 to 31.12.2024. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000036/2024-2025 | 1023/B.Ar.D | 21/06/2024 | 184 | OM ENTERPRISE | 0.87 | 0 | 0
265 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of pipeline at damaged portion due to construction of road, drain by panchayet related to the work "Providing Functional House Hold Tap Connection (FHTC) from the existing and new proposed distribution system within Command area at Mahisgadi & its adjoining mouza water supply Scheme under Barasat-II Block Under Barasat Arsenic, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000069/2023-2024 | 1827/B.Ar.D. | 01/08/2023 | 45 | P. & S. ASSOCIATES | 28.23 | 0 | 100
266 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Mahisgadi & its adjoining mouza Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000090/2022-2023 | 1559/B.Ar.D. | 24/08/2022 | 90 | M/S R. M. CONSTRUCTION | 131.17 | 0 | 85
267 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Mahisgadi Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000116/2022-2023 | 1952/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0 | 1
268 | Barasat Arsenic Division | Barasat Arsenic Division | Withdrawling and re laying of 250 mm dia upvc pipeline related to the work "Providing Functional House Hold Tap Connection (FHTC) from the existing and new proposed distribution system within Command area at Mahisgadi & its adjoining mouza water supply Scheme under Barasat-II Block Under Barasat Arsenic, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000145/2023-2024 | 2339/B.Ar.D. | 21/09/2023 | 30 | M/S R. M. CONSTRUCTION | 6.45 | 0 | 95
269 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of 350 Cum OHR and allied water supply component infrastructure under Mahisgadi W/S Scheme of Barasat -II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000197/2023-2024 | 3027/B.Ar.D. | 29/12/2023 | 45 | UMA CONSTRUCTION | 19.75 | 0 | 100
270 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000005/2022-2023 | 2107/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 0.79 | 0 | 0
271 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000024/2022-2023 | 2297/B.Ar.D | 02/12/2022 | 0 | Resource Division | 0.37 | 0 | 0
272 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Ghola, Rajapura and Chalitabaria Mouzas of Hasnabad Block from Rajapura Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000039/2020-2021 | 1881/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 96.59 | 29.15 | 1
273 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Muragachha, Harikati and Krishnapara Mouzas of Hasnabad Block from Krishnapara Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000041/2020-2021 | 1884/B.Ar.D. | 18/12/2020 | 90 | UTPAL CONSTRUCTION AND CO | 83.3 | 50 | 1
274 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000087/2023-2024 | 1945/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0
275 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000088/2023-2024 | 1946/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0
276 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 3rd Pump House site of Tarulia Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000089/2023-2024 | 1947/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0
277 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for NEW PWSS (TARULIA Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000126/2023-2024 | 1838/B.Ar.D. | 01/08/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 11.11 | 0 | 100
278 | Barasat Arsenic Division |  | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000130/2023-2024 | 1987/B.Ar.D. | 18/08/2023 | 60 | M/S DAS & CO | 7.38 | 0 | 0
279 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000131/2023-2024 | 1988/B.Ar.D. | 18/08/2023 | 60 | B. S. ENTERPRISE | 6.23 | 0 | 0
280 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 3rd Tube Well Site of TARULIA Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000132/2023-2024 | 1989/B.Ar.D. | 18/08/2023 | 60 | SHIVAM CONSTRUCTION | 6.18 | 0 | 0
281 | Barasat Arsenic Division |  | Tarulia Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 600 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Tarulia under Rajarhat block, Dist.- North 24 Parganas. |  |  | ORD/000163/2023-2024 | 2557/B.Ar.D. | 30/10/2023 | 366 | AZAD ENTERPRISE | 663.57 | 0 | 0
282 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 76/B.Ar.D | 11/01/2024 | 0 | Resource Division | 26.28 | 0 | 0
283 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for NEW PWSS (SULANGGARI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000004/2023-2024 | 984/B.Ar.D. | 20/04/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 9.68 | 0 | 100
284 | Barasat Arsenic Division |  | Sulanggari Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 550 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Sulanggari under Rajarhat block, Dist.- North 24 Parganas. |  |  | ORD/000036/2023-2024 | 1341/B.Ar.D. | 07/06/2023 | 366 | BARMAN ASSOCIATES | 580.02 | 0 | 5
285 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Sulanggari Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000056/2023-2024 | 1664/B.Ar.D. | 18/07/2023 | 720 | SAHA CONSTRUCTION AND CO | 18.26 | 0 | 100
286 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Sulanggari Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000057/2023-2024 | 1665/B.Ar.D. | 18/07/2023 | 45 | SAHA CONSTRUCTION AND CO | 18.26 | 0 | 0
287 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 3rd Pump House site of Sulanggari Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000058/2023-2024 | 1666/B.Ar.D. | 18/07/2023 | 45 | POWER TOOLS AND ENGINEERING | 18.18 | 0 | 0
288 | Barasat Arsenic Division |  | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of SULANGURI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000063/2023-2024 | 1696/B.Ar.D. | 20/07/2023 | 60 | BARMAN ASSOCIATES | 7.03 | 0 | 0
289 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of SULANGURI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000064/2023-2024 | 1697/B.Ar.D. | 20/07/2023 | 60 | PRAGATI CONSTRUCTION & CO | 6.2 | 0 | 0
290 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 3rd Tube Well Site of SULANGURI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000065/2023-2024 | 1698/B.Ar.D. | 20/07/2023 | 60 | CHOWDHURY CONSTRUCTION | 6.24 | 0 | 0
291 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 78/B.Ar.D | 11/01/2024 | 0 | Resource Division | 23.32 | 0 | 0
292 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Bagband Saiberia & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000038/2021-2022 | 1562/B.Ar.D. | 15/09/2021 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.94 | 0 | 1
293 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Connection and Allied workas at Gobindapur, Madanpur Krishnapur and Andulia Mouzas of Barasat II Block from Bagband Saiberia & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000170/2020-2021 | 466/B.Ar.D. | 19/02/2021 | 90 | BALAJEE ENTERPRISES | 79.53 | 54.43 | 1
294 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Bablu Ali at Saiberia Uttarpara and Mosharef Ali at Saiberia Moral Para under Bagband Saiberia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000264/2021-2022 | 474/B.Ar.D | 16/03/2022 | 15 | WATERCOMP INDIA | 4.71 | 0 | 1
295 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Ajibar Baidhya at Saiberia Baidhyapara and Akkaj Ali at saiberia Uttar para under Bagbandh Saiberia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000292/2021-2022 | 561/B.Ar.D | 23/03/2022 | 15 | KAKALI ENTERPRISE | 4.71 | 0 | 100
296 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Mahisgadi & its adjoining mouza water supply scheme in Barasat - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000063/2021-2022 | 1700/B.Ar.D | 30/09/2021 | 15 | UMWELT ENGINEER PVT. LTD. | 2.95 | 0 | 1
297 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Mahishgadi Mouza of Barasat- II Block from Mahishgadi Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000125/2020-2021 | 134/B.Ar.D. | 21/01/2021 | 90 | BANI ENGINEERING CO | 96.59 | 53.67 | 1
298 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of MS Pipe and allied work at Haroa Khal Crossing of Mahisgadi water supply Scheme and Boaring works related to FHTC works of Mahisgadi water supply Scheme at Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000270/2021-2022 | 479/B.Ar.D | 16/03/2022 | 15 | BALAJEE ENTERPRISES | 4.77 | 0 | 1
299 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hold Tap Connection and allied works at Sondalia and Paltadanga Mouzas of Barasat- II Block from Paltadanga Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000122/2020-2021 | 126/B.Ar.D. | 20/01/2021 | 90 | BALAJEE ENTERPRISES | 86.87 | 81.47 | 1
300 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional House Hod Connection and Allied workas at 6 nos habitation of Dwarir Jangle Mouzas of Sandeshkhali II Block from Dwarir Jangle Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000054/2021-2022 | 1711/B.Ar.D. | 01/10/2021 | 90 | A P POWER AND CONCRETE | 45.66 | 0 | 1
301 | Barasat Arsenic Division | Barasat Arsenic Division | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Dwarir Jangle water supply scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000065/2021-2022 | 1702/B.Ar.D | 30/09/2021 | 15 | SIRCON ENGINEERING SERVICES | 4.68 | 0 | 1
302 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC Pipe at khulnaghat of Dwarirjangal W/S scheme at Sandeshkhali Block- II for providing FHTC under " JAL JIBAN MISSION" under Barasat Arsenic Division, PHE Dte. (SM/08725) (Sl No. 5) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000142/2022-2023 | 2125/B.Ar.D. | 04/11/2022 | 21 | A P POWER AND CONCRETE | 4.83 | 0 | 1
303 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC Pipe at damaged portion at Giri Para of Dwarir Jangal W/S scheme at Sandeshkhali Block- II for providing FHTC under Jalswapna Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000151/2021-2022 | 2233/B.Ar.D | 28/12/2021 | 30 | M/S L.P. CONSTRUCTION | 4.8 | 0 | 1
304 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC Pipe at damaged portion at Karnakhali of Dwarir Jangal W/S scheme at Sandeshkhali Block- II for providing FHTC under Jalswapna Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000153/2021-2022 | 2257/B.Ar.D | 30/12/2021 | 30 | A P POWER AND CONCRETE | 4.12 | 0 | 1
305 | Barasat Arsenic Division | Barasat Arsenic Division | Protection of UPVC distribution pipe line at 7 no. Sarder Para of Dwarir Jungle W/S scheme at Sandeshkhali- II under Barasat Arsenic Division, P.H.E. Dte. (Length - 60 mtr. Approx) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000174/2022-2023 | 2483/B.Ar.D. | 21/12/2022 | 20 | M/S ASHA ENGINEERING | 5.41 | 0 | 1
306 | Barasat Arsenic Division | Barasat Arsenic Division | Repair & Renovation of Iron Elimination Plant of 69 M3 including Media Change of Chowlpur Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000049/2022-2023 | 1352/B.Ar.D | 22/07/2022 | 30 | WATERCOMP INDIA | 4.74 | 0 | 1
307 | Barasat Arsenic Division | Barasat Arsenic Division | Providing Functional Household Tap Connection (FHTC) and allied works at left out portion of different Mouzas under command area of Chowlpur W/S scheme of Barasat - II blocks from Chowlpur and it adjoining mouzas ground water supply scheme under "JAL SWAPNA" programme under Barasat Arsenic Division, PHE Dte. (Phase - III). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000173/2021-2022 | 254/B.Ar.D. | 17/02/2022 | 90 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 81.34 | 0 | 1
308 | Barasat Arsenic Division | Barasat Arsenic Division | Restoration due to laying of various dia UPVC/HDPE Pipe distribution line at Malrameswarpur mouza of Chowlpur W/S Scheme under Barasat -II block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000204/2023-2024 | 3030/B.Ar.D. | 29/12/2023 | 30 | SIRCON ENGINEERING SERVICES | 7.69 | 0 | 100
309 | Barasat Arsenic Division |  | Laying and Refixing of Ferrule of distribution Pipeline for Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area of Krishnapara W/S Scheme at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. (SM/11706) |  |  | ORD/000003/2025-2026 | 795/B.Ar.D. | 30/04/2025 | 45 | BABUSONA CONSTRUCTION | 37.18 | 0 | 0
310 | Barasat Arsenic Division |  | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Krishnapara at Hasnabad Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000089/2022-2023 | 1558/B.Ar.D. | 24/08/2022 | 90 | PALCON | 103.23 | 0 | 100
311 | Barasat Arsenic Division |  | Preparation of Augmentation DPR for Krishnapara Water Supply Scheme under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000108/2022-2023 | 1836/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0 | 1
312 | Barasat Arsenic Division |  | Construction of Remaining portion of boundary wall & allied works at Krishnapara Head Work site at Krishnapara Water Supply scheme of Hasnabad Block under Barasat Arsenic Division, P.H.E. Dte. |  |  | ORD/000172/2023-2024 | 2657/B.Ar.D. | 09/11/2023 | 45 | M/S DAS & CO | 8.62 | 0 | 100
313 | Barasat Arsenic Division |  | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 250 Cu.m. at Krishnapara W/S Scheme of Hasnababad Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000194/2022-2023 | 275/B.Ar.D. | 06/02/2023 | 60 | M/S SANJAY ADHIKARI | 13.9 | 0 | 0
314 | Barasat Arsenic Division |  | Repair & Renovation of I.E.Plant (Capacity-38 Cu.m.) for Augmentation of Krishnapara Water Supply Scheme under Hasnabad Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000213/2024-2025 | 578/B.Ar.D. | 24/03/2025 | 45 | SUNIL DULE | 3.77 | 0 | 80
315 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 2108/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 1.07 | 0 | 0
316 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 2295/B.Ar.D | 02/12/2022 | 0 | Resource Division | 7.71 | 0 | 0
317 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of 3.6 mtr. x 3.0 mtr. size new Pump House ( Pump House-III ) with sanitary arrangement, construction of boundary wall and Allied Works for Jasaikathi ( Z-I ) W/S Scheme Under Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000070/2023-2024 | 1795/B.Ar.D. | 28/07/2023 | 60 | DEL DELTA CONSTRUCTION | 11.59 | 0 | 100
318 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System Including specials all Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Jasaikathi Zone -I at Baduria Block in North 24 Pgs District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000095/2022-2023 | 1570/B.Ar.D. | 25/08/2022 | 900 | M/S DATTA ENTERPRISE | 216.55 | 0 | 90
319 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Jasaikathi (Zone-I) Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000106/2022-2023 | 1834/B.Ar.D | 19/09/2022 | 20 | SIRCON ENGINEERING SERVICES | 0.98 | 0 | 1
320 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking for 1 no 250 mm. x 150 mm. dia. 330 mtr deep Tubewell by D.R. Rig method near at Pump House no.-2 with PVC pipe & strainer having 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Jasaikathi (Z-I) w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. (Sl No. 2) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000132/2022-2023 | 2056/B.Ar.D. | 19/10/2022 | 45 | M/S RAJPATH CONSTRUCTION | 15.35 | 0 | 1
321 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir of Capacity 450 Cu.m. at Jasaikathi (Z-I) W/S Scheme of Baduria Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000171/2023-2024 | 2656/B.Ar.D. | 09/11/2023 | 45 | B. S. ENTERPRISE | 12.03 | 0 | 100
322 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of boundary wall & allied works at Jasaikathi 2nd T/W site at Jasaikathi ( Z-I ) Water Supply scheme of Baduria Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000176/2023-2024 | 2674/B.Ar.D. | 10/11/2023 | 45 | ASHIM ENTERPRISE | 7.02 | 0 | 100
323 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking for 1 no. 200 mm. x 150 mm. dia. 300 mtr deep Tubewell by D.R. Rig method near at Kankrasuti Mouza with PVC pipe & strainer having 200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Jasaikathi (Z-I ) w/s scheme of Baduria block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000207/2023-2024 | 82/B.Ar.D. | 11/01/2024 | 30 | M/S DATTA ENTERPRISE | 12.7 | 0 | 0
324 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of UPVC/HDPE pipeline and Repairing, Renovation of Boundary wall, Fencing work etc and other allied works at Head work site of Jasaikathi-(Z-I) W/S Scheme under Baduria Block under Barasat Arsenic Division PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000231/2023-2024 | 392/B.Ar.D | 21/02/2024 | 45 | P. & S. ASSOCIATES | 12.55 | 0 | 100
325 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000008/2022-2023 | 2110/B.Ar.D. | 02/11/2022 | 0 | Resource Division | 0.92 | 0 | 0
326 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | RTOR000019/2022-2023 | 2293/B.Ar.D | 02/12/2022 | 0 | Resource Division | 11.83 | 0 | 0
327 | Barasat Arsenic Division | Barasat Arsenic Division | Wayleave plan & survey charges (Stn.Sondalia to Beliaghata Road Halt) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | BILL/00116/2023-2024 | 181 | 24/07/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 0.07 | 0 | 0
328 | Barasat Arsenic Division | Barasat Arsenic Division | Wayleave facility charges Sondalia to Beliaghata Road Halt | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | BILL/00166/2023-2024 | 236 | 16/08/2023 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS) | 5.95 | 0 | 0
329 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for within leftout area of Falti and Bamandanga area for the scheme 'Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte'. (SM/10551) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000004/2025-2026 | 796/B.Ar.D. | 30/04/2025 | 180 | TOJO ENTERPRISE | 41.81 | 0 | 100
330 | Barasat Arsenic Division | Barasat Arsenic Division | Sinking for 1 nos 250 mm. x 150 mm. dia. 270 mtr deep Tubewell by D.R. Rig method with UPVC pipe & strainer having 250 mm dia 42 mtr. long housing pipe & 150 mm dia 30 mtr. long filter at Puturia W/S Scheme of Barasat-II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000017/2024-2025 | 997/B.Ar.D. | 19/06/2024 | 107 | B. S. ENTERPRISE | 13.46 | 0 | 100
331 | Barasat Arsenic Division | Barasat Arsenic Division | Repair and Renovation works of Existing R.C.C. Elevated Reservoir & other existing civil component of Capacity 700 Cu.m. at Puturia W/S Scheme uder Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000022/2023-2024 | 948/B.Ar.D. | 17/04/2023 | 60 | MONDAL ENTERPRISE | 16.73 | 0 | 100
332 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for restoration of Damaged Pipeline and house connection due to construction and widening of village Roads under Pathashree-3 from North 24 Parganas Zilla Parishad and other within command area of Bokanda, Puturia, Baidyapur and Tona for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000047/2024-2025 | 1582/B.Ar.D. | 23/09/2024 | 270 | M/S RAJPATH CONSTRUCTION | 22.02 | 0 | 90
333 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for "Hiring of one (1) no. Diesel operated motor cab (AC) (Car No. WB-25F-6815) with driver for official use for Chief Engineer (Head Quarters) in place of Director,WSSO, PHE Department. with all costs towards the owner except fuel cost i.e. Diesel & Mobil oil for the period from 22.08.2022 to 21.02.2023." | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000066/2022-2023 | 1520/B.Ar.D | 18/08/2022 | 184 | NASIRUDDIN BISWAS | 0.96 | 0 | 1
334 | Barasat Arsenic Division | Barasat Arsenic Division | Preparation of Augmentation DPR for Puturia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000117/2022-2023 | 1953/B.Ar.D | 26/09/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.99 | 0 | 1
335 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000135/2022-2023 | 1743/B.Ar.D. | 07/09/2022 | 90 | S. P. CONSTRUCTION | 382.09 | 0 | 100
336 | Barasat Arsenic Division | Barasat Arsenic Division | Construction of 4.88 mtr. x 3.6 mtr. size new Pump House (Pump House-IV) with Boundary Wall and Allied Works for PUTURIA W/S Scheme Under Barasat Arsenic Division, PHE Dte. (SM/10551) | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000147/2024-2025 | 329/B.Ar.D. | 27/02/2025 | 60 | GRAVITA ENTERPRISE | 9.11 | 0 | 100
337 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring of Contract carriage (BS-IV) of the office use of the DSE PIU N24PGS WBDWSIP PHE DTE. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000161/2022-2023 | 1402//B.Ar.D | 29/07/2022 | 184 | BISWADIP SIKDAR | 0.87 | 0 | 1
338 | Barasat Arsenic Division | Barasat Arsenic Division | CONTINUATION ORDER for ''Hiring of one (1) no Diesel operated Motor cab 9Non AC) Car No WB-11C 8013) with driver for offical use for Chief Engineer & Director ,WSSO. PHE Department with all costs towards the owner excpet fuel cost i.e. Diesel & Mobil oil for the period from 22.08.2022 to 21.02.2023.'' | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000170/2022-2023 | 1521 //B.Ar.D | 18/08/2022 | 184 | GOUR HARI SAHOO | 0.86 | 0 | 1
339 | Barasat Arsenic Division | Barasat Arsenic Division | construction order No - Horing of one (1) No Diseal Operated Motor Cab ( Car No -WB-25K-2915) with driver for offical use for Assistent Engineer (HQ-I) ,Barasat Arsenic Divisuion ,PHE Dte with all costs towards the owner except fuel cost i.e Diesel & Mobil oil for the period from 01.05.2022 to 30.04.2023 | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000180/2022-2023 | 796//B.Ar.D | 26/04/2022 | 365 | PREMANANDA ROY BISWAS | 1.73 | 0 | 100
340 | Barasat Arsenic Division | Barasat Arsenic Division | Continuation order for -Hiring of One (1) no Diesel operated cab (Car no-WB-25K-2915) with driver for offical use for Assistent Engineer (HQ-II) Barasat Arsenic Division PHE Dte with all cost towards the owner except fuel cost i.e Diesel & Mobil oil for the period from 01.05.2022 to 30.04.2023 | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000181/2022-2023 | 796/ B.Ar.D | 26/04/2022 | 365 | PREMANANDA ROY BISWAS | 1.73 | 0 | 1
341 | Barasat Arsenic Division | Barasat Arsenic Division | Eucalyptus Bullah piling for Protection of UPVC distribution pipe line at Bokanda Ghosh Para of Puturia W/S Scheme under Barasat- II Block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000210/2022-2023 | 472/B.Ar.D. | 27/02/2023 | 30 | KAKALI ENTERPRISE | 10.72 | 0 | 100
342 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Mochpol mouza for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000233/2023-2024 | 394/B.Ar.D | 21/02/2024 | 280 | THREE MAA ENTERPRISE | 46.15 | 0 | 100
343 | Barasat Arsenic Division | Barasat Arsenic Division | Submission of all documents regarding crossing of Railway track for laying Water Pipe line main for Puturia W/S Scheme in between Sondalia & Beliaghata Road Railway Station on Barasat - Hasnabad Section under Barasat-II Block. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000234/2022-2023 | 747/B.Ar.D. | 24/03/2023 | 15 | P & S ASSOCIATES | 1.96 | 0 | 0
344 | Barasat Arsenic Division | Barasat Arsenic Division | Submission of all documents regarding crossing of Railway track for laying Water Pipe line main for Surface Based PWSS for Barasat-II Block in between Sondalia & Beliaghata Road Railway Station on Barasat - Hasnabad Section. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000235/2022-2023 | 748/B.Ar.D. | 24/03/2023 | 15 | P & S ASSOCIATES | 1.96 | 0 | 100
345 | Barasat Arsenic Division | Barasat Arsenic Division | Laying of distribution System including specials all complete and Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Falti Beliaghata and Tona area for Augmentation of Ground Based Water Supply Scheme at Puturia under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000239/2023-2024 | 537/B.Ar.D. | 13/03/2024 | 280 | AYUSH ENTERPRISE | 49.47 | 0 | 5
346 | Barasat Arsenic Division | Barasat Arsenic Division | Hiring charges of vehicle. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000328/2021-2022 | 3812/EC | 30/12/2021 | 365 | PRABIR RONG | 1.73 | 0 | 1
347 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000026/2022-2023 | 26/B.Ar.D. | 05/01/2023 | 0 | Resource Division | 14.73 | 0 | 0
348 | Barasat Arsenic Division | Barasat Arsenic Division | Material Requisition To Resource Division | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | RTOR000032/2022-2023 | 204/B.Ar.D. | 30/01/2023 | 0 | Resource Division | 258.81 | 0 | 0
349 | Barasat Arsenic Division |  | Survey, Design Drawing & DPR Preparation for NEW PWSS (GHUNI Water Supply Scheme) in RAJARHAT BLOCK under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000062/2023-2024 | 1809/B.Ar.D. | 31/07/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 12.92 | 0 | 100
350 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at Head Work site of Ghuni Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000084/2023-2024 | 1942/B.Ar.D. | 14/08/2023 | 45 | ACME CONSTRUCTION | 18.27 | 0 | 0
351 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 2nd Pump House site of Ghuni Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000085/2023-2024 | 1943/B.Ar.D. | 14/08/2023 | 45 | NAJMUL HOQUE | 18.26 | 0 | 0
352 | Barasat Arsenic Division |  | Sinking of 1 No. Tube Well 300 MM X 200 MM Big dia Tube Well 300 Mtr. deep by rotary rig method using PVC pipe & UPVC medium well screen pipes with ribs etc. all complete including cost of materials at 3rd Pump House site of Ghuni Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000086/2023-2024 | 1944/B.Ar.D. | 14/08/2023 | 45 | PIYALI CONSTRUCTION AND GENERAL ORDER SUPPLIERS | 18.26 | 0 | 0
353 | Barasat Arsenic Division |  | Construction of 4.88 mtr. x 3.60 mtr. size new Pump House at Head Work Site of GHUNI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000127/2023-2024 | 1984/B.Ar.D. | 18/08/2023 | 60 | SWAPNO ENTERPRISE | 7.02 | 0 | 0
354 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 2nd Tube Well Site of GHUNI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000128/2023-2024 | 1985/B.Ar.D. | 18/08/2023 | 60 | M.R.CONSTRUCTION | 6.18 | 0 | 0
355 | Barasat Arsenic Division |  | Construction of 3.60 mtr. x 3.00 mtr. size new Pump House for at 3rd Tube Well Site of GHUNI Water Supply Scheme under Rajarhat Block under Barasat Arsenic Division, PHE Dte. |  |  | ORD/000129/2023-2024 | 1986/B.Ar.D. | 18/08/2023 | 60 | JUPITER CONSTRUCTION | 6.2 | 0 | 0
356 | Barasat Arsenic Division |  | Ghuni Piped Water Supply Scheme with Rising Main, LDS, FHTC & construction of 900 cum capacity Overhead Reservoir (OHR) including Soil investigation and foundation design at Ghuni under Rajarhat block, Dist.- North 24 Parganas. |  |  | ORD/000162/2023-2024 | 2555/B.Ar.D. | 19/10/2023 | 366 | M/S. S. S. ENTERPRISE | 952.88 | 0 | 0
357 | Barasat Arsenic Division |  | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 77/B.Ar.D | 11/01/2024 | 0 | Resource Division | 35.76 | 0 | 0
Total | [10 empty] | 21825.01 | 1184.51