## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of Kazisaha,Kapasdanga (village code 315607,315618), under MANIKNAGAR (Zone-J) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000291/2022-2023 | 1805/BD-I | 31/03/2023 | 961 | KAMIRUL SK AND CO. | 259.69 | 0 | 72
2 | Berhampore Division I | Berhampur Division I | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nasipur (Village code 314186) under Nasipur Zone-I Ground Water based Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division - I, PHE Dte.(Part-III) (Sl-02) | Assistant Engineer-I | JE | ORD/000292/2021-2022 | 1133/BD-I | 06/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 97.21 | 88.6 | 1
3 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Nasipur ( Village code-314186) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Nasipur Ground water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000792/2021-2022 | 2303/BD-I | 28/12/2021 | 30 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 17.79 | 14.29 | 1
4 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of village of Char Mirzapur (village code 315616), under Mirzapur (Zone-H) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000275/2023-2024 | 978/BD-I | 18/10/2023 | 90 | M/S. DAS ENTERPRISE MAHULA, DASPARA, VILL +P.O-GOPINATHPUR, MURSHIDABAD. | 43.31 | 0 | 0
5 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidabad District Under Berhampore Division-I,PHE Dte. in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000110/2024-2025 | 1446/BD-I | 04/09/2024 | 60 | PRANAB KUMAR GHOSH | 32.27 | 0 | 0
6 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mathbarenda (Village code 314480) , Patti Bahadurpur (Village code 314489) Sultanpur (Village code 314490),Madapur (Village code 314482) under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000100/2020-2021 | 166/BD-I | 03/02/2021 | 30 | DECON INDIA | 80.84 | 66.39 | 1
7 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000109/2024-2025 | 1444/BD-I | 04/09/2024 | 60 | BHOWMIK CONSTRUCTION | 18.28 | 0 | 0
8 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000114/2024-2025 | 1434/BD-I | 04/09/2024 | 60 | MOLLA ENTERPRISE | 34.65 | 0 | 0
9 | Berhampore Division I | Berhampur Division I | Formal Work Order for laying of balance portion and relaying of damage portion in different dia on different nodes of UPVC and DI (K-7) pipe line under Gopinathpur (Zone-B) Surface based water supply scheme under uncovered arsenic areas of Beldanga-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-I | ORD/000844/2021-2022 | 100/BD-I | 01/02/2022 | 90 | C.X.CONSTRUCTION & CO. | 119.44 | 0 | 100
10 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangapur, Binkar, Mahisasthali, Gopinathpur, Gopalpur & Pulinda (Village code 315562, 315563, 315564, 315565, 315566 & 315567) under Gopinathpur (Zone-B) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000847/2021-2022 | 103/BD-I | 01/02/2022 | 1390 | DOBAY CONSTRUCTION | 261.58 | 162.27 | 92
11 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Prasadpur,Arazi Mathurapur,Gouripur Khastaluk, Mathurapur & Bele (Village code 314835,314836,314837,314842 & 314843) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000215/2021-2022 | 1013/BD-I | 21/06/2021 | 1440 | M/S. SUKUMAR SINHA | 53.54 | 0 | 100
12 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gauripur (Village code 315412) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000216/2021-2022 | 1014/BD-I | 21/06/2021 | 45 | SARAJIT KUMAR MAJUMDAR | 51.33 | 42.45 | 1
13 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pashchim Gobindapur,Hanribhanga & Biranpur (Village code 314844,314833 & 314834) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000217/2021-2022 | 1015/BD-I | 21/06/2021 | 60 | KAMIRUL SK AND CO. | 71.45 | 64.58 | 1
14 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begamnagar,Bhartadoba & Palasdanga (Village code 314879,314880 & 314881) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000218/2021-2022 | 1016/BD-I | 21/06/2021 | 60 | KAMIRUL SK AND CO. | 61.91 | 50.82 | 1
15 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopalnagar,Singa & Banoaripur (Village code 314869,314877 & 314878) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000219/2021-2022 | 1017/BD-I | 21/06/2021 | 60 | ULTRA CONSTRUCTION | 66.11 | 51.85 | 1
16 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
17 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gudhia (Village code 314870) under Begamnagar (Zone-D) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000501/2021-2022 | 1908/BD-I | 08/10/2021 | 180 | DECON INDIA | 134.39 | 108.31 | 90
18 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalikapur,Hasnabad & Sashidharpur (Village code 314861,314862 & 314863) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000210/2021-2022 | 1008/BD-I | 21/06/2021 | 701 | M/S JAN MAHAMMAD | 77.98 | 44.9 | 100
19 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dilalpur & Baranda Sibnagar (Village code 314859 & 314860) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000211/2021-2022 | 1009/BD-I | 21/06/2021 | 60 | DECON INDIA | 88.47 | 73.95 | 0
20 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kapasdanga (Village code 314868) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000212/2021-2022 | 1010/BD-I | 21/06/2021 | 60 | M/S JAN MAHAMMAD | 68.61 | 44.6 | 1
21 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rambhadrapur & Gouribag (Village code 314839 & 314838) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000213/2021-2022 | 1011/BD-I | 21/06/2021 | 45 | SANDHAN ADHIKARY | 46.7 | 41.27 | 0
22 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhatpara,Ramdaspur,Kamalpur & Jafrabad (Village code 314864,314865,314866 & 314867) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000214/2021-2022 | 1012/BD-I | 21/06/2021 | 60 | M/S JAN MAHAMMAD | 68.64 | 55.59 | 1
23 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ransagar, Aliganj,Akherighata ,Chirakuti,Samserganj, Noada,Akbarpur,Sabjikatra, Topkhana, Kadamsarif (Village code 314853,314854,314855,314856,314857,314858,314852,314840 & 314851) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000277/2021-2022 | 1170/BD-I | 15/07/2021 | 60 | ARINDAM MAJUMDAR | 59.21 | 49.86 | 100
24 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2024 to 31.12.2024 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000378/2023-2024 | 1280/BD-I | 27/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.68 | 21
25 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
26 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Aragi Kulgachi (Village code 314471) under Digha Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000097/2020-2021 | 163/BD-I | 03/02/2021 | 20 | SARAJIT KUMAR MAJUMDAR | 33.52 | 0 | 0
27 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Subarna Mrigi (Village code 314473) under Digha Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000189/2020-2021 | 842/BD-I | 23/11/2020 | 90 | PRADIP KUMAR DAS | 25.8 | 19.56 | 0
28 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Subarna Mrigi (Village Code-314473) under Digha Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000209/2020-2021 | 276/ BD-I | 15/02/2021 | 10 | DAS TRADING CO | 4.87 | 0 | 0
29 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area of Harirampur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte.. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000072/2024-2025 | 1220/BD-I | 29/07/2024 | 30 | PRADIP DAS | 5.61 | 0 | 0
30 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Joyrampur (Village Code-314553) and others under Harirampur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000114/2021-2022 | 916/BD-I | 19/05/2021 | 20 | M/S. M.G. CONSTRUCTION | 4.31 | 2.59 | 0
31 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Harirampur (Village code 314554) under Harirampur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000195/2020-2021 | 974/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 22.63 | 42.51 | 1
32 | Berhampore Division I | Berhampur Division I | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Harirampur and others under Harirampur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000414/2021-2022 | 1452/BD-I | 13/08/2021 | 10 | KAMIRUL SK AND CO. | 4.62 | 2.51 | 1
33 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Ramchandrapur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000141/2024-2025 | 1607/BD-I | 03/10/2024 | 30 | SUJIT CHOWDHURY | 5.13 | 0 | 0
34 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramchandrapur (Village code 314592) under Ramchandrapur Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000221/2020-2021 | 985/BD-I | 17/12/2020 | 60 | SOM CONSTRUCTION AGENCY | 16.15 | 19.07 | 1
35 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Gobindapur (Village code 314448) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000237/2020-2021 | 66/BD-I | 18/01/2021 | 30 | JAHANGIR ALAM | 32.15 | 25.67 | 1
36 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Barbaria (Village code 314462) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000238/2020-2021 | 67/BD-I | 18/01/2021 | 30 | M/S SINHA & SONS | 40.34 | 35.18 | 0
37 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION at Sadatpur(VillageCode-315671) ,Chhatiai (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000116/2024-2025 | 1451/BD-I | 04/09/2024 | 30 | K.S.ENTERPRISE (PROP. SAMIM SK.) | 3.55 | 0 | 0
38 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhatiani (Village code 315673) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000230/2020-2021 | 1045/BD-I | 28/12/2020 | 90 | MS RUBIET HOSSAIN | 43.95 | 39.68 | 0
39 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadatpur (Village code 315671) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000231/2020-2021 | 1046/BD-I | 28/12/2020 | 60 | MAHATO ENTERPRISE | 4.04 | 0 | 0
40 | Berhampore Division I | Berhampur Division I | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-II | ORD/000853/2021-2022 | 157/BD-I | 11/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0
41 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahatpur(Village code 314442) under Telia Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000109/2020-2021 | 176/BD-I | 03/02/2021 | 20 | KAMIRUL SK AND CO. | 12.76 | 9.51 | 1
42 | Berhampore Division I | Berhampur Division I | Additional of different dia of UPVC pipeline for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahatpur (Village code 314442) under Telia Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000415/2021-2022 | 1453/BD-I | 13/08/2021 | 10 | KAMIRUL SK AND CO. | 1.03 | 0 | 0
43 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Karttikpur(Village code 314220) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000128/2020-2021 | 204/BD-I | 04/02/2021 | 30 | SARAJIT KUMAR MAJUMDAR | 61.23 | 45.46 | 1
44 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 315524) under Bali Zone-II Ground Water Supply Scheme in Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | Assistant Engineer-II | JE | ORD/000555/2021-2022 | 1886/BD-I | 07/10/2021 | 180 | SANJAY BISWAS | 248.74 | 133.42 | 85
45 | Berhampore Division I | Berhampur Division I | Formal work order for Water Supply arrangement for arsenic affected habitation with SOLAR Power connection by Construction/ installation of Community Purification Plant (CPP) unit including Tubewell (125 x50 mm dia ) with DTH (for Population 351-500 & Raw Water As concentration upto 0.15 ppm) at Different habitations [For-9 nos Unit] in different Villages of Block of Farakka ( 9 Units) under Berhampore Division-I , P.H.E. Dte. in the District of Murshidabad. (Site list S/L No 04) | Assistant Engineer-II | JE | ORD/000563/2021-2022 | 1917/BD-I | 08/10/2021 | 75 | MODERN CONSTRUCTION | 143.25 | 89.49 | 1
46 | Berhampore Division I | Berhampur Division I | Laying of Extension and parallel pipeline at Ramnachandpur village due to smooth Functioning of Functional Hosehold Tap Connection at Ramnachandpur zone-I ground Water based water Supply Scheme Under Berhampore Division-I,P.H.E Dte. | Assistant Engineer-II | JE | ORD/000008/2022-2023 | 551/BD-I | 13/05/2022 | 45 | ULTRA CONSTRUCTION | 40.55 | 29.76 | 1
47 | Berhampore Division I | Berhampur Division I | Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.06.2022 to 31.12.2022. | Assistant Engineer-II | JE | ORD/000014/2022-2023 | 628/BD-I | 30/05/2022 | 214 | SOUVIK HALDER | 1.06 | 2.56 | 1
48 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bundai Nagar (village code 315530) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000242/2021-2022 | 1852/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.17 | 68.46 | 1
49 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alampur (village code 315519) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000243/2021-2022 | 1853/BD-I | 07/10/2021 | 90 | SRIJON ENTERPRISE | 88.19 | 65.18 | 1
50 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kedarchandpur (village code 315518) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000244/2021-2022 | 1854/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 98.62 | 63.5 | 1
51 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnachandpur (Village code 315520) under Ramnachandpur Water Supply Scheme of Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-14) | Assistant Engineer-II | JE | ORD/000580/2021-2022 | 1924/BD-I | 08/10/2021 | 180 | M/S GUHA AND ROY ENTERPRISE | 217.79 | 123.15 | 1
52 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Kedarchandpur, Bundai Nagar and Alampur (Village code-315518,315530, and 315519) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Ramnachandpur Ground water based Water supply scheme (Nawda,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | JE | ORD/000793/2021-2022 | 2309/BD-I | 29/12/2021 | 90 | SRIJON ENTERPRISE | 43.88 | 35.92 | 1
53 | Berhampore Division I | Berhampur Division I | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer-II | JE | ORD/000871/2021-2022 | 2281/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 1.58 | 1
54 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | JE | RTOR000010/2021-2022 | 144/BD-I | 10/02/2022 | 0 | Resource Division | 16.44 | 0 | 0
55 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of Hareknagar, Andiran ,Begunbari and Chakhijli (village code 315604,315610,315608 and 315609), under BEGUNBARI (Zone-I) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHED | Assistant Engineer-II | Junior Engineer-I | ORD/000290/2022-2023 | 1804/BD-I | 31/03/2023 | 120 | SARAJIT KUMAR MAJUMDAR | 350.09 | 0 | 0
56 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under DAULATABAD(Zone-F) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000111/2023-2024 | 440/BD-I | 12/07/2023 | 90 | A.P CONSTRUCTION | 42.93 | 0 | 0
57 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatabad (Village code 315415) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000232/2021-2022 | 1819/BD-I | 05/10/2021 | 90 | PRADIP KUMAR DAS | 88.49 | 79.01 | 1
58 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muliarazi,Harirampur and Balia Danga (Village code 315400,315401,315402) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000233/2021-2022 | 1823/BD-I | 05/10/2021 | 80 | KAMIRUL SK AND CO. | 76.53 | 39.07 | 1
59 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Purandarpur (Village code 315403) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000234/2021-2022 | 1825/BD-I | 05/10/2021 | 60 | M/S SINHA & SONS | 55.92 | 51.43 | 100
60 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dadpur (Village code 315422) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000253/2021-2022 | 1818/BD-I | 05/10/2021 | 100 | DOBAY CONSTRUCTION | 98.25 | 72.16 | 1
61 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kulbaria (Village code 315414) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000254/2021-2022 | 1820/BD-I | 05/10/2021 | 90 | USHA ENTERPRISE | 84.7 | 61.07 | 1
62 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gauripur and Ruhia (Village code 315412,315413) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000255/2021-2022 | 1821/BD-I | 05/10/2021 | 90 | MAMATA USHA ENTERPRISE | 90.65 | 40.97 | 1
63 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha,Benidaspur,Garabasa,Maharajpur and Hanumanta Nagar (Village code 315407,315408,315409,315410,315411) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000256/2021-2022 | 1822/BD-I | 05/10/2021 | 100 | BANIK BROTHERS | 97.4 | 82.14 | 100
64 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muli and Gangaprasad (Village code 315406,315423) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000257/2021-2022 | 1824/BD-I | 05/10/2021 | 20 | ROY AND ROY CONSTRUCTION | 10.62 | 8.6 | 1
65 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mukundapur and Purbagopinathpur (Village code 315416,315420) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000258/2021-2022 | 1826/BD-I | 05/10/2021 | 30 | SUDIPA SINGHA ROY | 23.87 | 18.26 | 1
66 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
67 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chutipur (village code 315419), under Doulatabad (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-I for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000743/2021-2022 | 2205/BD-I | 10/12/2021 | 120 | SAMRIDDHI ASSOCIATED | 96 | 90.17 | 1
68 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Doulatabad Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE | ORD/000759/2021-2022 | 2225/BD-I | 15/12/2021 | 90 | AJOY GHOSH | 74.29 | 74.76 | 1
69 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Daulatabad Surface water based water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000874/2021-2022 | 244/BD-I | 03/03/2022 | 15 | MONDAL ENTERPRISE VILL. + P.O.- CHALTIA, P.S.- BERHAMPORE | 8.58 | 7.05 | 1
70 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000002/2021-2022 | 64/BD-I | 27/01/2022 | 0 | Resource Division | 1.24 | 0 | 0
71 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000006/2021-2022 | 71/BD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
72 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda, Sahapur, Ratanpur, Betberia, Kheali, Palaighata, Jafrabad, Sattarpur, Chaitanyapur & Bhadur (Village code 315568, 315569, 315570, 315571, 315572, 315574, 315575, 315576, 315577 & 315579) under Chaitanyapur (Zone-C) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000848/2021-2022 | 104/BD-I | 01/02/2022 | 180 | M/S JAN MAHAMMAD | 318.48 | 300.19 | 1
73 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-I | RTOR000007/2021-2022 | 139/BD-I | 10/02/2022 | 0 | Resource Division | 28.46 | 0 | 0
74 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hasanpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000116/2022-2023 | 1366/BD-I | 21/12/2022 | 30 | SARIFUL ISLAM | 2.49 | 2.45 | 100
75 | Berhampore Division I | Berhampur Division I | Augmentation of Hasanpur Piped water supply scheme to accommodate construction of OHR,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Swapna in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000119/2023-2024 | 831/BD-I | 01/09/2023 | 310 | A ONE CONSTRUCTION | 238.41 | 0 | 0
76 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HASANPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000889/2021-2022 | 272/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.53 | 2.53 | 0
77 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000050/2023-2024 | 196/BD-I/1 | 09/02/2024 | 0 | Resource Division | 2.08 | 0 | 0
78 | Berhampore Division I | Berhampur Division I | Laying of different dia UPVC distribution pipe Line in connection with JJM (Jal Jeevan Mission) on damaged portion and Rukunpur Satsang Kandra with alied works of Rukunpur (Zone-G) based water supply scheme under CS Part-II of BD-I, P.H.E Dte | Assistant Engineer-II | Junior Engineer-II | ORD/000015/2023-2024 | 86/BD-I | 03/05/2023 | 30 | CHATTERJEE ENTERPRISE | 2.89 | 2.81 | 100
79 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of RUKUNPUR (Village code 315481) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte | Assistant Engineer-II | Junior Engineer-II | ORD/000077/2020-2021 | 976/BD-I | 17/12/2020 | 180 | PRADIP KUMAR DAS | 235.52 | 246.56 | 1
80 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (Village code 315480) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000133/2020-2021 | 232/BD-I | 10/02/2021 | 1633 | M/S GOUTAM CHAKRABORTY | 130.13 | 103.4 | 1
81 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Biharia (Village code 315478) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000137/2020-2021 | 237/BD-I | 10/02/2021 | 180 | UNIVERSAL CONSTRUCTION | 160.94 | 154.25 | 0
82 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000223/2021-2022 | 1812/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 53.67 | 1
83 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2024 to 31.12.2024. | Assistant Engineer-II | Junior Engineer-II | ORD/000377/2023-2024 | 1282/BD-I | 27/12/2023 | 366 | SEBAYAN CONSTRUCTION | 1.81 | 4.79 | 30
84 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tehatta (village code 315479) under RUKUNPUR ( Zone - G ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000462/2021-2022 | 1835/BD-I | 05/10/2021 | 60 | PARTHA PRATIM DAS | 49.71 | 26.51 | 1
85 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
86 | Berhampore Division I | Berhampur Division I | Additional and balance work of HDPE pipe for house service connection for retrofitting FHTC and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna under command area of village Rukunpur ( village code-315481 ) under Rukunpur (Zone -G )Surface Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000577/2021-2022 | 1846/BD-I | 07/10/2021 | 60 | DAS TRADING CO | 50.67 | 50.64 | 1
87 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000029/2024-2025 | 2096/BD-I/10 | 25/11/2024 | 0 | Resource Division | 12.32 | 0 | 0
88 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Sundarpur ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000089/2025-2026 | 949/BD-I | 18/07/2025 | 300 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0
89 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Sundarpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000109/2022-2023 | 1439/BD-I | 16/01/2023 | 30 | M/S RAMI CONSTRUCTION | 1.81 | 0 | 100
90 | Berhampore Division I | Berhampur Division I | Balance work for the work of Augmentation of Sundarpur Piped water supply scheme to accommodate construction of Pump House ,Boundary Wall, Service Road and laying of distribution of pipeline under Jal Jeevan Mission within Bhagwangola -I Block of Murshidabad District under Berhampore Division -I PHE. Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000126/2024-2025 | 1474/BD-I | 06/09/2024 | 60 | M/S TAPAS KUMAR CHAKRABORTY | 89.63 | 0 | 0
91 | Berhampore Division I | Berhampur Division I | Formal Work order for Augmentation of Sundarpur Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000161/2022-2023 | 1447/BD-I | 17/01/2023 | 789 | M/S TAPAS KUMAR CHAKRABORTY | 397.04 | 131.89 | 80
92 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sundarpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000284/2022-2023 | 1807/BD-I | 31/03/2023 | 900 | SUJIT KUMAR SAHA | 18.01 | 6.99 | 50
93 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SUNDARPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000881/2021-2022 | 265/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.68 | 2.68 | 100
94 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000067/2023-2024 | 196/BD-I/14 | 09/02/2024 | 0 | Resource Division | 34.78 | 0 | 0
95 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Diar Shyampur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE | ORD/000104/2022-2023 | 1413/BD-I | 04/01/2023 | 10 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 2.36 | 1.52 | 100
96 | Berhampore Division I | Berhampur Division I | Augmentation of Diar Syampur Zone-I Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE | ORD/000148/2023-2024 | 671/BD-I | 09/08/2023 | 310 | S.K. CONSTRUCTION DEBKUNDU , P.S.- BELDANGA, | 121.57 | 0 | 0
97 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-I Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000879/2021-2022 | 263/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.37 | 2.35 | 100
98 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000060/2023-2024 | 196/BD-I/7 | 09/02/2024 | 0 | Resource Division | 10.99 | 0 | 0
99 | Berhampore Division I | Berhampur M/E Division | Augmentation of Brohmottar Manikchak Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000203/2023-2024 | 848/BD-I | 05/09/2023 | 574 | M/S TAPAS KUMAR CHAKRABORTY | 458.37 | 103.88 | 50
100 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BRAHAMOTTAR MANIKCHAK Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000262/2022-2023 | 1685/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.6 | 2.62 | 1
101 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BRAHIMOTTAR MANIKCHAK Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000280/2024-2025 | 10/BD-I | 06/01/2025 | 15 | HARUN ALL RASHID & BROTHERS | 8.92 | 0 | 0
102 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000007/2024-2025 | 1510/BD-I/1 | 12/09/2024 | 0 | Resource Division | 4.13 | 0 | 0
103 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000068/2023-2024 | 201/BD-1/9 | 10/02/2024 | 0 | Resource Division | 31.4 | 0 | 0
104 | Berhampore Division I | Berhampur Division I | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMNACHANDPUR ZONE - IV PWSS under Jal Jeevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000010/2025-2026 | 598/BD-I | 22/04/2025 | 60 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 19 | 0 | 0
105 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-IV" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-52.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000033/2024-2025 | 996/BD-I | 20/06/2024 | 365 | M/S RUBIET HOSSAIN | 159.77 | 0 | 0
106 | Berhampore Division I | Berhampur Division I | Augmentation of Ramnachandpur zone_IV Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in NAWDA Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000139/2023-2024 | 622/BD-I | 03/08/2023 | 821 | AJAY MONDAL | 277.49 | 0 | 20
107 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room at Head Work site of RAMNACHANDPUR ZONE-IV Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division-I, PHE.Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000331/2024-2025 | 282/BD-I | 12/02/2025 | 60 | MD NAJRUL ISLAM | 7.5 | 0 | 0
108 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMNACHANDPUR ZONE - IV Water Supply Scheme( 1st & 2nd TW Site) within Nawda Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000374/2024-2025 | 429/BD-I | 19/03/2025 | 30 | GENUINE | 18.02 | 0 | 0
109 | Berhampore Division I | Berhampur Division I | RAMNACHANDRAPUR ZONE-IV to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000448/2023-2024 | 451/BD-I | 15/03/2024 | 539 | PRAVAT KUMAR GHOSH | 21.46 | 0 | 95
110 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | RTOR000054/2023-2024 | 196/BD-I/27 | 09/02/2024 | 0 | Resource Division | 31.44 | 0 | 0
111 | Berhampore Division I | Berhampur M/E Division | Balance works i.c.w of Existing AIRP (Modified Sujapur Sadipur Model) capacity 53.12 cum/hr at Head Work Site of Jhumra Nayagram Water Supply Scheme under JJM within Lalgola block under Berhampore Division -I, P.H.E. Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000074/2025-2026 | 841/BD-I | 23/06/2025 | 30 | GITA CONSTRUCTION | 26.5 | 0 | 0
112 | Berhampore Division I | Berhampur M/E Division | Bored Cast-in-situ_M30_grade 450 mm. dia. 22.00 m (Shaft Length) R.C.C pile for construction of OHR at Head work site of Jhumra Nayagram Ground Piped Water Supply Scheme under Jal Jeevan Mission of Lalgola Block, Murshidabad district under Berhampore Division - I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000090/2024-2025 | 1302/BD-I | 07/08/2024 | 180 | AICH CONSTRUCTION | 26.19 | 0 | 100
113 | Berhampore Division I | Berhampur M/E Division | Augmentation of Jumra Nayagram Piped water supply scheme to accommodate construction of OHR,Arsenic cum Iron Removal Plant( AIRP ),Pump house,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000210/2022-2023 | 1621/BD-I | 02/03/2023 | 310 | AICH CONSTRUCTION | 360.29 | 12.38 | 5
114 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JUMRA NAYAGRAM Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000260/2022-2023 | 1683/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.6 | 2.6 | 1
115 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (250 Cum) of Ground water supply scheme for Jumra Nayagram of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000262/2023-2024 | 984/BD-I | 30/10/2023 | 30 | AJOY GHOSH | 8.56 | 0 | 0
116 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000009/2024-2025 | 1510/BD-I/3 | 12/09/2024 | 0 | Resource Division | 2.27 | 0 | 0
117 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000069/2023-2024 | 201/BD-1/10 | 10/02/2024 | 0 | Resource Division | 43.36 | 0 | 0
118 | Berhampore Division I | Raghunathganj Sub-Division | Balance work of Boundary Wall at Augmentation of Udaynagar Diar PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000028/2024-2025 | 984/BD-I | 19/06/2024 | 45 | BISWAS CONSTRUCTION | 11.94 | 0 | 0
119 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Udaynagar Diar Piped water supply scheme to accommodate construction of Pump House ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000214/2022-2023 | 1551/BD-I | 17/02/2023 | 720 | BISWAS CONSTRUCTION | 82.74 | 56.19 | 75
120 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for UDAYNAGARDIAR Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000281/2022-2023 | 1559/BD-I | 20/02/2023 | 10 | M/S SOBHA & CO | 2.53 | 2.48 | 100
121 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000013/2023-2024 | 61/BD-1/11 | 27/04/2023 | 0 | Resource Division | 26.29 | 0 | 0
122 | Berhampore Division I | Berhampur Division I | Replacement of Filter media of Existing AIRP of (Capacity 46 Cum/hr.) with allied work at Sadhukhali Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000012/2024-2025 | 911/BD-I | 07/06/2024 | 30 | MS BAPPA ENTERPRISE | 17 | 0 | 0
123 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd Tube Well Site of SADHUKHALI ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000014/2025-2026 | 603/BD-I | 22/04/2025 | 45 | BARUN DUTTA | 10.19 | 0 | 0
124 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of Sadhukhali Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000183/2022-2023 | 1658/BD-I | 13/03/2023 | 984 | NOVELTY CONSTRUCTION | 181.42 | 134.82 | 95
125 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sadhukhali Zone-I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000242/2023-2024 | 939/BD-I | 11/10/2023 | 30 | B.R SUPPLIERS | 9 | 0 | 0
126 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000267/2022-2023 | 1690/BD-I | 14/03/2023 | 10 | TECHVISION | 2.67 | 2.67 | 100
127 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000086/2023-2024 | 196/BD-I/21 | 09/02/2024 | 0 | Resource Division | 33.74 | 0 | 0
128 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-IV under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000060/2023-2024 | 157/BD-I | 15/05/2023 | 90 | GANGULY ENTERPRISE | 30.54 | 0 | 0
129 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-IV under Lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000052/2023-2024 | 151/BD-I | 15/05/2023 | 90 | RISHIKA GHOSH | 30.23 | 0 | 0
130 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Hariganja" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-30 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000029/2024-2025 | 992/BD-I | 20/06/2024 | 365 | NATIONAL CONSTRUCTION | 142.73 | 0 | 5
131 | Berhampore Division I | Berhampur Division I | HARIGANJA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000043/2023-2024 | 74/BD-I | 28/04/2023 | 730 | M/S SAJEDA ENTERPRISE | 141.8 | 26.5 | 65
132 | Berhampore Division I | Berhampur Division I | HARIGANJA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000284/2023-2024 | 1001/BD-I | 31/10/2023 | 90 | SUSHANTA MANDAL | 39.1 | 14 | 31
133 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HARIGANJ PWSS (H/W Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000381/2024-2025 | 443/BD-I | 20/03/2025 | 15 | M/S S. DAS & ENTERPRISE | 9 | 0 | 0
134 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000021/2024-2025 | 2096/BD-I/2 | 25/11/2024 | 0 | Resource Division | 5.01 | 0 | 0
135 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000029/2023-2024 | 61/BD-1/16 | 27/04/2023 | 0 | Resource Division | 12.25 | 0 | 0
136 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MALIPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000060/2025-2026 | 772/BD-I | 22/05/2025 | 15 | M/S GUHA AND ROY ENTERPRISE | 9 | 0 | 0
137 | Berhampore Division I | Berhampur Division I | MALIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000099/2023-2024 | 209/BD-I | 17/05/2023 | 720 | PRANAB KUMAR GHOSH | 39.48 | 22.82 | 55
138 | Berhampore Division I | Berhampur Division I | MALIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. . | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000131/2023-2024 | 610/BD-I | 02/08/2023 | 900 | ROY CONSTRUCTION (AVIJIT ROY) | 85.64 | 51.33 | 90
139 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | RTOR000044/2023-2024 | 61/BD-1/30 | 27/04/2023 | 0 | Resource Division | 18.6 | 0 | 0
140 | Berhampore Division I | Raghunathganj Sub-Division | Relaying of Different dia UPVC pipeline instead of damage portion in between node point (mouza - Maheswarpur, Chatra, Char Alampur) under Muktarpur ground water supply scheme of Raghunathganj Sub- Division under Berhampore Division - I, P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000267/2021-2022 | 1109/BD-I | 28/06/2021 | 30 | S.P CONSTRUCTION | 35.66 | 28 | 1
141 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KRISHNAPUR DINURPARA PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidbad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000015/2025-2026 | 604/BD-I | 22/04/2025 | 15 | M/S BIMALENDU BOSE | 9.01 | 0 | 0
142 | Berhampore Division I | Berhampur M/E Division | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000166/2023-2024 | 652/BD-I | 08/08/2023 | 850 | M/S GOUTAM CHAKRABORTY | 232.47 | 72.29 | 10
143 | Berhampore Division I | Berhampur M/E Division | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000167/2023-2024 | 653/BD-I | 08/08/2023 | 601 | SOUMYADIP MISRA | 326.54 | 0 | 10
144 | Berhampore Division I | Berhampur M/E Division | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000168/2023-2024 | 654/BD-I | 08/08/2023 | 549 | ULTRA CONSTRUCTION | 91.86 | 0 | 50
145 | Berhampore Division I | Berhampur M/E Division | KRISHNAPURDINURPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000186/2023-2024 | 730/BD-I | 16/08/2023 | 90 | M/S SWAPAN KUAMR NATH & CO | 72.82 | 21.2 | 41
146 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000098/2023-2024 | 201/BD-1/27 | 10/02/2024 | 0 | Resource Division | 34.21 | 0 | 0
147 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000112/2023-2024 | 304/BD-1/1 | 22/02/2024 | 0 | Resource Division | 21.31 | 0 | 0
148 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Komnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000083/2024-2025 | 1244/BD-I | 30/07/2024 | 30 | R.S. CONSTRUCTION | 9.36 | 0 | 0
149 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Komnagar (Village code 314572) under Komnagar Ground Water Supply Scheme in Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer | Junior Engineer-II | ORD/000441/2021-2022 | 968/BD-I | 07/06/2021 | 180 | S.P CONSTRUCTION | 49.3 | 34.35 | 0
150 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for JAL JEEVAN MISSION under command area of Sitesnagar ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000112/2024-2025 | 1448/BD-I | 04/09/2024 | 60 | GOUTAM KUMAR CHAUDHURI | 16.63 | 0 | 0
151 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Siteshnagar (Village code 314238) under Lalgola Ground Water Supply Scheme in Lalgola Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-10) | Assistant Engineer-I | JE | ORD/000271/2021-2022 | 1142/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 70.73 | 62 | 0
152 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jagarpara (Village code 314183),Chamunda(Village code 314171),Janardanpur( Village code 314184), under Nasipur Zone-I Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-I | JE | ORD/000127/2020-2021 | 203/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 79.1 | 55.03 | 1
153 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000140/2024-2025 | 1606/BD-I | 03/10/2024 | 30 | PAMIR ROY | 11.94 | 0 | 0
154 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000081/2024-2025 | 1233/BD-I | 30/07/2024 | 60 | PRIME CONSTRUCTION | 28.06 | 0 | 0
155 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egdalia(Village code 314213) under Bajipur Madhupur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000098/2020-2021 | 165/BD-I | 03/02/2021 | 20 | LAXMI CONSTRUCTION | 4.93 | 9.48 | 1
156 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314214) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte | Assistant Engineer-I | JE | ORD/000179/2020-2021 | 828/BD-I | 13/11/2020 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 10.28 | 12.88 | 1
157 | Berhampore Division I | Berhampur Division I | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur and others under Bajipur Madhupur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000412/2021-2022 | 1441/BD-I | 11/08/2021 | 10 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 1.16 | 0.73 | 1
158 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000797/2021-2022 | 2314/BD-I | 29/12/2021 | 45 | BIJOY CHOWDHURY | 13.36 | 2.47 | 1
159 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kharsadanga, Putijol, Sundhipur & Rajdharpara (Village code 315377, 315395, 315371 & 315375) respectively under Purba Narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000142/2020-2021 | 242/BD-I | 10/02/2021 | 180 | MADE & TRADE CO. | 306.14 | 323.76 | 1
160 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda Panur, Tarakpur, Kaya & Purba Narayanpur (Village code 315378, 315380, 315379 & 315376) under Purba narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000143/2020-2021 | 249/BD-I | 11/02/2021 | 180 | J.D.J ENTERPRISE | 393.6 | 268.7 | 1
161 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Gopinathpur (Village code 315393) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000158/2020-2021 | 296/BD-I | 19/02/2021 | 30 | M/S BIMALENDU BOSE | 9.59 | 9.18 | 1
162 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kariagachhi (Village code 315394) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000159/2020-2021 | 297/BD-I | 19/02/2021 | 30 | A.P CONSTRUCTION | 7.15 | 6.69 | 1
163 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
164 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Uday Nagar (village code 315396) , Gar Baharampur ( village code 315388 ) and Pakuria ( village code 315381 ) under PURBONARAYANPUR ( Zone - B ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000464/2021-2022 | 1836/BD-I | 05/10/2021 | 70 | HOQUEDAR ALI | 58.64 | 0 | 0
165 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Kharsadanga, Putijol,Sundhipur and Rajdharpara (Village code-315377,315395,315371 and 315375) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Purba Narayanpur (Zone-B)Surface water based Water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000791/2021-2022 | 2302/BD-I | 28/12/2021 | 90 | SOUNAK ENTERPRISE | 73.56 | 73.26 | 1
166 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Upar Orahar(Village code 314444) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000105/2020-2021 | 171/BD-I | 03/02/2021 | 30 | KAMIRUL SK AND CO. | 50.99 | 86.53 | 0
167 | Berhampore Division I | Berhampur Division I | Laying of new UPVC pipeline with allied work for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Upar Orahar (Village code 314444) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE | ORD/000411/2021-2022 | 1440/BD-I | 11/08/2021 | 10 | KAMIRUL SK AND CO. | 4.67 | 0 | 0
168 | Berhampore Division I | Berhampur Division I | Additional laying works at village Diar Syampur (Village Code-314439) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Diar Syampur Ground Water Supply Scheme (Bhagawangola-I Block) under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | Assistant Engineer-I | JE | ORD/000007/2022-2023 | 549/BD-I | 13/05/2022 | 10 | BURIMA CONSTRUCTION | 3.37 | 2.63 | 50
169 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Diar Syampur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000091/2024-2025 | 1303/BD-I | 07/08/2024 | 30 | DAS ENTERPRISE(GORABAZAR) | 2.91 | 0 | 0
170 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Diar Syampur (Village code 314439) under Diar Syampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000152/2020-2021 | 270/ BD-I | 12/02/2021 | 30 | BURIMA CONSTRUCTION | 44.88 | 42.38 | 1
171 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Meoakhana (Village code 314438) under Diar Syampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000239/2020-2021 | 68/BD-I | 18/01/2021 | 30 | M/S. DAS ENTERPRISE | 22.56 | 35.45 | 1
172 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Diar Syampur( Village code -314439 ) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Diar Syampur Ground water supply scheme (Bhagwangola-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000779/2021-2022 | 2294/BD-I | 28/12/2021 | 10 | AICH CONSTRUCTION | 6.77 | 0 | 0
173 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hurshi (village code 314752), under Hurshi Zone-II Ground water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000744/2021-2022 | 2206/BD-I | 10/12/2021 | 90 | SRIJON ENTERPRISE | 66.87 | 51.38 | 0
174 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Arazi Kanaipur (village code 314751), under Hurshi Zone-II Ground water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000745/2021-2022 | 2252/BD-I | 21/12/2021 | 20 | ANUPA ENTERPRISE | 5.11 | 5.03 | 1
175 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte | Assistant Engineer | Junior Engineer-II | ORD/000075/2024-2025 | 1223/BD-I | 29/07/2024 | 60 | M/S. MONDAL ENTERPRISE | 23.39 | 0 | 0
176 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khemrajpur (Village code 314761),Naodapara (Village code 314763),Srirampur(Village code 314762) under Lochanpur Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000123/2020-2021 | 199/BD-I | 04/02/2021 | 30 | M/S S.S ENTERPRISE | 71.38 | 79.87 | 1
177 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000115/2024-2025 | 1450/BD-I | 04/09/2024 | 60 | SUDIPA SINGHA ROY | 13.53 | 0 | 0
178 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Charkamnagar (Village code 315620),Nagar (Village code 315622),Maklishpur (Village code 315623) under Charkamnagar Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-II | Junior Engineer-II | ORD/000208/2021-2022 | 1006/BD-I | 21/06/2021 | 30 | KAMIRUL SK AND CO. | 69.19 | 37.16 | 1
179 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-C)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000106/2024-2025 | 1442/BD-I | 04/09/2024 | 60 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 19.16 | 0 | 0
180 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mohanpur (Village code 314764),Gopinathpur (Village code 314765) under Lochanpur Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-C) | Assistant Engineer | Junior Engineer-II | ORD/000115/2020-2021 | 187/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.96 | 103.62 | 1
181 | Berhampore Division I | Raghunathganj Sub-Division | Additional Laying works at village Mohanpur (village code 314764) and Gopinathpur (village code 314765) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Lochanpur Ground water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000566/2021-2022 | 1919/BD-I | 08/10/2021 | 10 | BIMALENDU BOSE | 7.03 | 7.02 | 1
182 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Shankarpara, Rameswarpur, Nalkunda & Bhabtakharida (Village Code- 315561, 315581, 315582 and 315583 under Mahespur (ZONE-F) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000016/2022-2023 | 946/BD-I | 23/08/2022 | 120 | DHIRENDRA NATH MONDAL | 107.44 | 0 | 0
183 | Berhampore Division I | Berhampur Division I | Laying of 150 mm dia (K-9),250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 180 mm dia ,200 mm dia&225 mm dia UPVC pipeline of unlead portion within command area of Mahespur(Zone-F) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000235/2023-2024 | 895/BD-I | 05/10/2023 | 30 | SANTA TRADING | 20.6 | 0 | 0
184 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under AMAIPARA (Zone-A) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000120/2023-2024 | 516/BD-I | 25/07/2023 | 90 | M/S. M.G. CONSTRUCTION | 102.61 | 0 | 0
185 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.07.2023. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000172/2022-2023 | 1387/BD-I | 23/12/2022 | 212 | SOUVIK HALDER | 1.06 | 2.47 | 70
186 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000184/2022-2023 | 1388/BD-I | 23/12/2022 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.77 | 90
187 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Tantipara (Village code 314895) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000455/2021-2022 | 1859/BD-I | 07/10/2021 | 60 | BIJOY SINGHA | 9.03 | 6.19 | 1
188 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bahadurpur (Village code 314894) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000456/2021-2022 | 1860/BD-I | 07/10/2021 | 90 | M/S. SUKUMAR SINHA | 21.72 | 0 | 0
189 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Goljarbag (Village code 314893) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000457/2021-2022 | 1861/BD-I | 07/10/2021 | 90 | M/S. SUKUMAR SINHA | 42.48 | 0 | 0
190 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bhrigurambati (Village code 314892) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000458/2021-2022 | 1862/BD-I | 07/10/2021 | 60 | AZAD ENTERPRISE | 12.67 | 11.77 | 1
191 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gujasti Rampur (Village code 314898) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000460/2021-2022 | 1864/BD-I | 07/10/2021 | 60 | N.H ENTERPRISE | 13.74 | 11.84 | 1
192 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Jayenpur (Village code 314900) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000461/2021-2022 | 1865/BD-I | 07/10/2021 | 90 | AJAY MONDAL | 26.81 | 19.86 | 1
193 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
194 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Ganespur (Village code 314938) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000472/2021-2022 | 1874/BD-I | 07/10/2021 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 21.49 | 18.74 | 1
195 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Amaipara (Village code 314910) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000473/2021-2022 | 1875/BD-I | 07/10/2021 | 90 | AJAY MONDAL | 27.02 | 20.95 | 1
196 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (Village code 314909) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000474/2021-2022 | 1876/BD-I | 07/10/2021 | 60 | GOUTAM KUMAR CHAUDHURI | 6.69 | 6.11 | 1
197 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bagdhar (Village code 314906) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000475/2021-2022 | 1877/BD-I | 07/10/2021 | 60 | MAA SANKARI ENTERPRISE | 20.03 | 17.93 | 1
198 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ambarnagar (Village code 314905) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000476/2021-2022 | 1878/BD-I | 07/10/2021 | 90 | DOBAY CONSTRUCTION | 24.01 | 19.7 | 1
199 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilkandi (Village code 314904) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000477/2021-2022 | 1879/BD-I | 07/10/2021 | 90 | SANJAY BISWAS | 33.81 | 24.37 | 90
200 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raichandpur (Village code 314902) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000478/2021-2022 | 1880/BD-I | 07/10/2021 | 90 | DOBAY CONSTRUCTION | 21.62 | 18.26 | 1
201 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begampur (Village code 314908) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000552/2021-2022 | 1910/BD-I | 08/10/2021 | 30 | PRADIP KUMAR SAHA | 2.61 | 0 | 0
202 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Payasti Katiganga (Village code 314891) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000553/2021-2022 | 1911/BD-I | 08/10/2021 | 30 | PRAVAT KUMAR GHOSH | 2.97 | 2.27 | 1
203 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanchannagar (Village code 314907) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000554/2021-2022 | 1912/BD-I | 08/10/2021 | 30 | ANKITA ENTERPRISE | 3.35 | 2.8 | 1
204 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadek Sarai (Village code 314897) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000752/2021-2022 | 118/BD-I | 03/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 11.58 | 8.85 | 1
205 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baliapukur(Village code 314901) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000753/2021-2022 | 217/BD-I | 24/02/2022 | 45 | DAS TRADING CO | 36.42 | 27.95 | 1
206 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaipara (Village code 314896) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000754/2021-2022 | 2209/BD-I | 10/12/2021 | 20 | PRATIMA CONSTRUCTION | 5.21 | 5 | 1
207 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chandipur(Village code 314903) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000755/2021-2022 | 2210/BD-I | 10/12/2021 | 30 | ASHIS KUMAR BHATTACHARYYA | 24.26 | 22.55 | 100
208 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Amaipara Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000757/2021-2022 | 2223/BD-I | 15/12/2021 | 90 | SOM CONSTRUCTION AGENCY | 83.92 | 83.05 | 1
209 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314899) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000849/2021-2022 | 117/BD-I | 03/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 13.73 | 11.88 | 100
210 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hogaldanga (Village code 315432) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000235/2021-2022 | 1829/BD-I | 05/10/2021 | 60 | NIRMAL UDYOG | 51.89 | 0 | 0
211 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Goraipur,Sadipur and Sundalpur (Village code 315417,315418 ,315431) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000236/2021-2022 | 1830/BD-I | 05/10/2021 | 40 | M/S SINHA & SONS | 40.25 | 26.91 | 1
212 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hajidanga,Baradha,Ganti Baisnab Charan,Kaladanga and Charislampur (Village code 315434,315435 ,315437,315436,315438) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000237/2021-2022 | 1831/BD-I | 05/10/2021 | 80 | KAMIRUL SK AND CO. | 73.49 | 65.78 | 1
213 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ruharpara,Baliharpur,Habipur,Dhanaipur,Mirpur and Garamgari (Village code 315426,315427 ,315428,315429,315430,315439) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000238/2021-2022 | 1832/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 97.55 | 81.51 | 0
214 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nutanpara and Madanpur (Village code 315424,315425) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000239/2021-2022 | 1833/BD-I | 05/10/2021 | 80 | M/S GUHA AND ROY ENTERPRISE | 81.18 | 80.7 | 1
215 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
216 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhayghari (Village code 315433) under Habibpur (Zone-G) Water Supply Scheme of Central Sector Part-I in Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer-I | JE | ORD/000495/2021-2022 | 1885/BD-I | 07/10/2021 | 180 | M/S S.DAS & ENTERPRISE | 275.21 | 151.91 | 1
217 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nidhi Nagar Sarsabad,Char Harharia and Char Panchananpur (Village code 315440,315441,315442) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000581/2021-2022 | 1994/BD-I | 01/11/2021 | 100 | NAYLA CONSTRUCTION | 90.2 | 72.42 | 1
218 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Habibpur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE | ORD/000760/2021-2022 | 2226/BD-I | 15/12/2021 | 90 | KUNDU CONSTRUCTION | 72.9 | 60.13 | 1
219 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Kasba Bahadurpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000108/2022-2023 | 1361/BD-I | 21/12/2022 | 30 | KAKALI ENTERPRISE | 2.41 | 1.66 | 100
220 | Berhampore Division I | Berhampur Division I | Formal Work order for Augmentation of KASBA BAHADURPUR Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000162/2022-2023 | 1454/BD-I | 17/01/2023 | 365 | DECON INDIA | 444.11 | 216.93 | 70
221 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasba Bahadurpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000285/2022-2023 | 1809/BD-I | 31/03/2023 | 30 | HARUN ALL RASHID & BROTHERS | 17.66 | 14.75 | 100
222 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000064/2023-2024 | 196/BD-I/11 | 09/02/2024 | 0 | Resource Division | 70.91 | 0 | 0
223 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of HARIRAMPUR Piped water supply scheme to accommodate construction of OHR, Service Road, Laying of Design Pipe Line and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I, PHE. Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000136/2022-2023 | 1445/BD-I | 17/01/2023 | 1275 | S.K. CONSTRUCTION DEBKUNDU , P.S.- BELDANGA, | 310.02 | 93.79 | 65
224 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Harirampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000169/2022-2023 | 1440/BD-I | 16/01/2023 | 30 | K.B CONSTRUCTION | 2.41 | 2.39 | 100
225 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HARIRAMPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000890/2021-2022 | 273/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.45 | 1
226 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000048/2023-2024 | 196/BD-I/4 | 09/02/2024 | 0 | Resource Division | 116.19 | 0 | 0
227 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Kazipara zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in JALANGI Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000022/2023-2024 | 96/BD-I | 04/05/2023 | 365 | MS JAKIR HOSSAIN | 291.08 | 189.31 | 70
228 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of KAZIPARA ZONE-II PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000059/2024-2025 | 1136/BD-I | 15/07/2024 | 60 | U.S BUILDERS | 7.92 | 0 | 0
229 | Berhampore Division I | Raghunathganj Sub-Division | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000295/2022-2023 | 1777/BD-I | 27/03/2023 | 10 | M/S SOBHA & CO | 2.74 | 2.7 | 100
230 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000039/2023-2024 | 194/BD-I/8 | 09/02/2024 | 0 | Resource Division | 31.41 | 0 | 0
231 | Berhampore Division I | Berhampur Division I | Augmentation of Mashimpur Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000029/2023-2024 | 81/BD-I | 28/04/2023 | 180 | SUJIT KUMAR SAHA | 241.41 | 73.06 | 40
232 | Berhampore Division I | Berhampur Division I | Improvement of Existing AIRP of (Capacity 51 Cum/hr.) with allied works at Mashimpur Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Eengineering Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000079/2025-2026 | 846/BD-I | 23/06/2025 | 30 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 6.4 | 0 | 0
233 | Berhampore Division I | Berhampur Division I | Allied works of Laying of distribution pipeline of MASHIMPUR piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000128/2024-2025 | 1478/BD-I | 06/09/2024 | 30 | SANTANU BISWAS | 16.93 | 0 | 0
234 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MASHIMPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000233/2022-2023 | 1591/BD-I | 28/02/2023 | 10 | TECHVISION | 2.6 | 2.6 | 0
235 | Berhampore Division I | Berhampur Division I | Proposed balance work for office room at 1st floor over AIRP pump house with staircase at Mashimpur ground water supply scheme under JJM under Berhampore Division-I, P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000442/2023-2024 | 441/BD-I | 15/03/2024 | 30 | CLASSIC CONSTRUCTION | 2.61 | 0 | 0
236 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000088/2023-2024 | 196/BD-I/22 | 09/02/2024 | 0 | Resource Division | 14.87 | 0 | 0
237 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Boundary Wall With Main Entrance gate and barbed wire facing ,Service Road for approach and Pump House at Augmentation of Komnagar PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. (2nd Site)/New OHR Site | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000053/2024-2025 | 1119/BD-I | 11/07/2024 | 335 | MODERN CONSTRUCTION (DOMKAL) | 25.76 | 0 | 75
238 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Komnagar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000122/2023-2024 | 506/BD-I | 24/07/2023 | 647 | PRATICHI ENTERPRISE | 194.85 | 130.92 | 83
239 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KOMNAGAR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000279/2022-2023 | 1763/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.53 | 2.49 | 100
240 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Komnagar ground water supply scheme in Raninagar-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000288/2024-2025 | 56/BD-I | 14/01/2025 | 300 | SUMAN ENTERPRISE AND SUMAN AQUA | 122.79 | 0 | 0
241 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000009/2023-2024 | 61/BD-1/8 | 27/04/2023 | 0 | Resource Division | 29.2 | 0 | 0
242 | Berhampore Division I | Berhampur M/E Division | Formal work order for Augmentation of Bansgara Zone-III Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000117/2023-2024 | 463/BD-I | 17/07/2023 | 899 | SAMBHUNATH ROY | 291.11 | 0 | 15
243 | Berhampore Division I | Berhampur M/E Division | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000297/2022-2023 | 1742/BD-I | 22/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.55 | 0 | 95
244 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000082/2023-2024 | 201/BD-1/23 | 10/02/2024 | 0 | Resource Division | 66.74 | 0 | 0
245 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of ANDULBERIA ZONE-II" ground water supply scheme in BELDANGA-II Block under Berhampore Division-I, P.H.E Dte(Capacity-72.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000031/2024-2025 | 994/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 197.4 | 0 | 0
246 | Berhampore Division I | Berhampur Division I | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of ANDULBERIA ZONE-II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000042/2025-2026 | 724/BD-I | 15/05/2025 | 60 | M/S. MONDAL ENTERPRISE | 19 | 0 | 0
247 | Berhampore Division I | Berhampur Division I | Augmentation of Andulberia Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000211/2022-2023 | 1821/BD-I | 31/03/2023 | 1007 | KAMIRUL SK AND CO. | 399.58 | 125.59 | 70
248 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000235/2022-2023 | 1593/BD-I | 28/02/2023 | 10 | TECHVISION | 3.15 | 2.92 | 0
249 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDULBERIA ZONE - II Water Supply Scheme(3rd TW Site) within Beldanga - II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000297/2024-2025 | 103/BD-I | 20/01/2025 | 15 | HARUN ALL RASHID & BROTHERS | 8.95 | 0 | 0
250 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000090/2023-2024 | 196/BD-I/24 | 09/02/2024 | 0 | Resource Division | 46.35 | 0 | 0
251 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of Arsenic cum Iron Removal Plant(AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | ORD/000025/2023-2024 | 313/BD-I | 14/06/2023 | 892 | MODERN CONSTRUCTION | 261.29 | 91.62 | 70
252 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road, Improvement of RCC OHR and Pump House of Bansgara Zone-II PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | ORD/000097/2025-2026 | 1014/BD-I | 06/08/2025 | 45 | GOUTAM MANDAL | 32.21 | 0 | 0
253 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | ORD/000277/2022-2023 | 1760/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.46 | 2.46 | 100
254 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer-II | RTOR000038/2023-2024 | 194/BD-I/7 | 09/02/2024 | 0 | Resource Division | 32.78 | 0 | 0
255 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Hurshi New PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000048/2024-2025 | 1110/BD-I | 10/07/2024 | 60 | PRADIP DAS | 8.04 | 0 | 0
256 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Hurshi Zone-I Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP), pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000196/2023-2024 | 844/BD-I | 05/09/2023 | 620 | M/S B.M. INDUSTRIES | 423.99 | 190.56 | 70
257 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000268/2022-2023 | 1691/BD-I | 14/03/2023 | 10 | RADIANT | 2.6 | 2.6 | 100
258 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000004/2023-2024 | 61/BD-1/5 | 27/04/2023 | 0 | Resource Division | 49.26 | 0 | 0
259 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Halalpur Zone-IV under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000070/2023-2024 | 172/BD-I | 16/05/2023 | 90 | JALALUDDIN SHAH | 22.51 | 0 | 0
260 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Narayanpur under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000074/2023-2024 | 175/BD-I | 16/05/2023 | 90 | SANTANU BISWAS | 28.53 | 0 | 0
261 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sonar Diar Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000071/2023-2024 | 173/BD-I | 16/05/2023 | 90 | MAA DURGA ENTERPRISE | 30.5 | 0 | 0
262 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-I under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000051/2023-2024 | 148/BD-I | 15/05/2023 | 90 | KAUSHIK MAJUMDAR | 30.23 | 0 | 0
263 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Maia Zone - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000012/2025-2026 | 599/BD-I | 22/04/2025 | 60 | SUJAUDDIN SHAIKH | 18.99 | 0 | 0
264 | Berhampore Division I | Berhampur M/E Division | Augmentation of Maia Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000127/2023-2024 | 540/BD-I | 28/07/2023 | 608 | MD SAJAHAN ALI | 364.59 | 117.99 | 35
265 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Maia Zone-II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000379/2024-2025 | 441/BD-I | 20/03/2025 | 60 | SHIBAM ENTERPRISE | 19 | 0 | 0
266 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000019/2024-2025 | 1510/BD-I/13 | 12/09/2024 | 0 | Resource Division | 7.2 | 0 | 0
267 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000078/2023-2024 | 201/BD-1/19 | 10/02/2024 | 0 | Resource Division | 23.75 | 0 | 0
268 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PURBA GOBINDAPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000058/2025-2026 | 770/BD-I | 22/05/2025 | 15 | M/S UNIVERSAL TRADING | 9.01 | 0 | 0
269 | Berhampore Division I | Berhampur Division I | PURBA GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000095/2023-2024 | 217/BD-I | 17/05/2023 | 90 | SUPTI ENTERPRISE | 40.92 | 22.25 | 50
270 | Berhampore Division I | Berhampur Division I | PURBA GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA -II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | ORD/000246/2023-2024 | 967/BD-I | 17/10/2023 | 840 | SAMBHUNATH ROY | 298.57 | 96.39 | 35
271 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_Pravin Kumar Gupta,Junior engineer-III | RTOR000041/2023-2024 | 61/BD-1/33 | 27/04/2023 | 0 | Resource Division | 13.12 | 0 | 0
272 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAMOORAHAR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000003/2025-2026 | 547/BD-I | 09/04/2025 | 15 | BHOWMIK CONSTRUCTION | 8.99 | 0 | 0
273 | Berhampore Division I | Berhampur M/E Division | NAMOORAHAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000080/2023-2024 | 732/BD-I | 16/08/2023 | 90 | MASOOM TRADERS | 34.64 | 0 | 25
274 | Berhampore Division I | Berhampur M/E Division | NAMOORAHAR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000195/2023-2024 | 746/BD-I | 17/08/2023 | 868 | M/S. UNIQUE BUILDERS | 244.5 | 103.36 | 10
275 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000022/2023-2024 | 61/BD-1/28 | 27/04/2023 | 0 | Resource Division | 16.52 | 0 | 0
276 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000118/2023-2024 | 304/BD-1/11 | 22/02/2024 | 0 | Resource Division | 6.42 | 0 | 0
277 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000175/2023-2024 | 690/BD-I | 10/08/2023 | 180 | SARAJIT KUMAR MAJUMDAR | 289.91 | 209.31 | 60
278 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000176/2023-2024 | 689/BD-I | 10/08/2023 | 980 | MD MAIDUL ISLAM | 330.82 | 112.73 | 65
279 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -C) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000177/2023-2024 | 691/BD-I | 10/08/2023 | 900 | M/S BIMALENDU BOSE | 214.12 | 185.32 | 90
280 | Berhampore Division I | Berhampur M/E Division | KHAMARDIAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000187/2023-2024 | 734/BD-I | 16/08/2023 | 90 | NATIONAL CONSTRUCTION | 50.37 | 11.84 | 25
281 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Khamardiar Water Supply Scheme under JJM under Berhampore Division - I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000270/2024-2025 | 2331/BD-I | 30/12/2024 | 30 | KAMIRUL SK AND CO. | 18.01 | 0 | 0
282 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000100/2023-2024 | 201/BD-1/4 | 10/02/2024 | 0 | Resource Division | 12.11 | 0 | 0
283 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Bishnupur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000001/2025-2026 | 506/BD-I | 03/04/2025 | 300 | NATIONAL CONSTRUCTION | 122.54 | 0 | 90
284 | Berhampore Division I | Raghunathganj Sub-Division | Replacement of Filter media of Existing AIRP of (Capacity 80 Cum/hr.) with allied work at Bishnupur Zone-I Water Supply Scheme under Jal Jeevan Mission of Raninagar-I under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000009/2024-2025 | 903/BD-I | 06/06/2024 | 209 | SUMAN ENTERPRISE AND SUMAN AQUA | 40.09 | 25.37 | 85
285 | Berhampore Division I | Raghunathganj Sub-Division | BISHNUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000085/2024-2025 | 1265/BD-I | 01/08/2024 | 300 | SHIBAM ENTERPRISE | 21.91 | 0 | 80
286 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Bishnupur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000092/2024-2025 | 1304/BD-I | 07/08/2024 | 60 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0
287 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Bishnupur Zone-I Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000141/2023-2024 | 627/BD-I | 04/08/2023 | 1123 | NATIONAL CONSTRUCTION | 452.24 | 347.4 | 25
288 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Based Supply Scheme for Bishnupur Zone-I of Raninagar-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000250/2023-2024 | 1034/BD-I | 01/11/2023 | 30 | ARJU CONSTRUCTION | 8.5 | 6.71 | 100
289 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000019/2023-2024 | 194/BD-I/5 | 09/02/2024 | 0 | Resource Division | 56.41 | 0 | 0
290 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000108/2024-2025 | 1445/BD-I | 04/09/2024 | 60 | HI-LIGHT ELECTRONICS | 19.95 | 0 | 0
291 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilnasipur (Village code 314170),Salmara(Village code 314182),Kulgachi( Village code 314169), Haripur( Village code 314185),Singa ( Village code 314181 ) under Nasipur Zone-I Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-I | JE | ORD/000126/2020-2021 | 202/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 78.52 | 73.75 | 0
292 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Telia (Village code 314466) under Telia Ground Water Supply Scheme in Bhagawangola-I Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-2) | Assistant Engineer-I | JE | ORD/000499/2021-2022 | 1906/BD-I | 08/10/2021 | 180 | RAJ KUMAR MONDAL | 103.96 | 95.85 | 1
293 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Benipur (Village code 314546) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000119/2020-2021 | 191/BD-I | 04/02/2021 | 30 | SRIJON ENTERPRISE | 92.74 | 153.74 | 1
294 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000103/2024-2025 | 1437/BD-I | 04/09/2024 | 30 | M/S ROY & BOSE ENTERPRISE | 17.87 | 0 | 0
295 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pukhuria (Village code 314547) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000120/2020-2021 | 192/BD-I | 04/02/2021 | 30 | M/S S.S ENTERPRISE | 71.4 | 44.98 | 1
296 | Berhampore Division I | Berhampur Division I | Commissioning of Moktarpur ground water based Pipe water Supply scheme under Jal Swapna at NAWDA Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000044/2023-2024 | 117/BD-I | 10/05/2023 | 966 | M/S GOUTAM CHAKRABORTY | 233.73 | 105.09 | 75
297 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000104/2023-2024 | 201/BD-1/3 | 10/02/2024 | 0 | Resource Division | 2.51 | 0 | 0
298 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Sarkarpara Piped water supply scheme to accommodate construction of boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000224/2022-2023 | 1557/BD-I | 20/02/2023 | 1032 | AZAD ENTERPRISE | 63.96 | 53.83 | 75
299 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SARKARPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000282/2022-2023 | 1370/BD-I | 21/12/2022 | 10 | M/S SOBHA & CO | 2.46 | 2.39 | 100
300 | Berhampore Division I | Raghunathganj Sub-Division | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SARKARPARA Water Supply Scheme within Jalangi Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000375/2024-2025 | 430/BD-I | 19/03/2025 | 15 | TAPESH MONDAL | 11.56 | 0 | 100
301 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000015/2023-2024 | 194/BD-I/9 | 09/02/2024 | 0 | Resource Division | 14.79 | 0 | 0
302 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Rajarampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000121/2022-2023 | 1678/BD-I | 14/03/2023 | 30 | SOMNATH DEY | 2.35 | 2.31 | 100
303 | Berhampore Division I | Berhampur M/E Division | Augmentation of Rajarampur Piped water supply scheme to accommodate construction of OHR ,Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000208/2022-2023 | 1618/BD-I | 02/03/2023 | 310 | DHIRENDRA NATH MONDAL | 366.26 | 0 | 0
304 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAJARAMPUR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000261/2022-2023 | 1684/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.66 | 2.69 | 1
305 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Supply Scheme for Rajarampur of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000277/2023-2024 | 994/BD-I | 30/10/2023 | 639 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 8.12 | 0 | 0
306 | Berhampore Division I | Berhampur M/E Division | RAJARAMPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000454/2023-2024 | 457/BD-I | 15/03/2024 | 60 | MAA DURGA ENTERPRISE | 22.87 | 0 | 0
307 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000010/2024-2025 | 1510/BD-I/4 | 12/09/2024 | 0 | Resource Division | 8.03 | 0 | 0
308 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000080/2023-2024 | 201/BD-1/21 | 10/02/2024 | 0 | Resource Division | 50.95 | 0 | 0
309 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room at Head Work site of MOKIMNAGAR PWSS (H/W Site & 2nd Site) under Jal Jevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000008/2025-2026 | 595/BD-I | 22/04/2025 | 60 | M/S MEGHNA CONSTRUCTION | 12.78 | 0 | 0
310 | Berhampore Division I | Berhampur M/E Division | Augmentation of Makimnagar Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000158/2023-2024 | 682/BD-I | 10/08/2023 | 728 | M/S BIMALENDU BOSE | 427.29 | 0 | 30
311 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAKIMNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000263/2022-2023 | 1686/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.59 | 2.62 | 1
312 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (180 Cum) of Ground Water Based Supply Scheme for Makimnagar of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000274/2023-2024 | 992/BD-I | 30/10/2023 | 30 | MATIUR RAHAMAN | 8.07 | 3.67 | 65
313 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOKIMNAGAR Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000363/2024-2025 | 318/BD-I | 24/02/2025 | 15 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0
314 | Berhampore Division I | Berhampur M/E Division | MAKIMNAGAR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000452/2023-2024 | 455/BD-I | 15/03/2024 | 60 | M/S UNIVERSAL TRADING | 22.87 | 18.79 | 50
315 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000008/2024-2025 | 1510/BD-I/2 | 12/09/2024 | 0 | Resource Division | 6.78 | 0 | 0
316 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000070/2023-2024 | 201/BD-1/11 | 10/02/2024 | 0 | Resource Division | 36.15 | 0 | 0
317 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000197/2022-2023 | 1380/BD-I | 22/12/2022 | 10 | RADIANT | 2.6 | 2.6 | 100
318 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Ramnagar Doemkanun ZoneII Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000254/2022-2023 | 1660/BD-I | 13/03/2023 | 180 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 186.74 | 82.9 | 30
319 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000016/2023-2024 | 194/BD-I/2 | 09/02/2024 | 0 | Resource Division | 30.59 | 0 | 0
320 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-III under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000059/2023-2024 | 156/BD-I | 15/05/2023 | 90 | NATIONAL ENTERPRISES | 30.54 | 0 | 0
321 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sonar Diar Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000073/2023-2024 | 174/BD-I | 16/05/2023 | 90 | SHIBAM ENTERPRISE | 26.55 | 0 | 0
322 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Mohespur under Beldanga -I block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000062/2023-2024 | 159/BD-I | 15/05/2023 | 90 | TITLI ENTERPRISE | 27.81 | 0 | 0
323 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Alighata under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000049/2023-2024 | 146/BD-I | 15/05/2023 | 899 | M/S. DAS ENTERPRISE MAHULA, DASPARA, VILL +P.O-GOPINATHPUR, MURSHIDABAD. | 30.54 | 0 | 15
324 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-V under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000061/2023-2024 | 158/BD-I | 15/05/2023 | 90 | SUJAUDDIN SHAIKH | 23.91 | 0 | 0
325 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Ajodhya Nagar & Chumrigacha to faciliate Functional Household Tap connection(FHTC) works in connection to Jal Jeevan Mission under Bairgachi (Zone-C) surface water based Water Supply Scheme of Central Sector Part-II under Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2023-2024 | 21/BD-I | 11/04/2023 | 30 | JIBENDRA NARAYAN SUKUL | 50.51 | 50.5 | 100
326 | Berhampore Division I | Berhampur Division I | Additional laying work of 300 mm dia DI Pipe Line at pond side of near Chumrigacha Primary School due to damage of UPVC Pipe line and with allied works of Distribution pipe line under Bairgachi Surface Water based Water Supply Scheme under Berhampore Division - I, PHE Dte.in Murshidabad District | Assistant Engineer-I | Junior Engineer-I | ORD/000004/2022-2023 | 547/BD-I | 13/05/2022 | 10 | JIBENDRA NARAYAN SUKUL | 4.54 | 4.31 | 45
327 | Berhampore Division I | Berhampur Division I | Laying of 350 mm dia DI (K-7) distribution Pipeline including allied works along with attached sheet of node point over command area of Bhakuri-I G.P under Bairgachi W/S scheme under Berhampore Division -I ,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000009/2022-2023 | 552/BD-I | 13/05/2022 | 45 | DHIMAN SARKAR | 20.59 | 6.02 | 100
328 | Berhampore Division I | Berhampur Division I | Laying of different dia DI pipe Line in connection with JJM (Jal Jeevan Mission) over damaged portion with allied works at Karim more and near Balarampur High School for smooth running of FHTC Work under Bairgachi (Zone-C) surface based water supply scheme under CS Part-II of BD-I, P.H.E Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000014/2023-2024 | 85/BD-I | 03/05/2023 | 30 | JIBENDRA NARAYAN SUKUL | 5.69 | 4.97 | 100
329 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2025 to 31.10.2025. | Assistant Engineer-I | Junior Engineer-I | ORD/000094/2025-2026 | 991/BD-I | 31/07/2025 | 92 | SOUVIK HALDER | 0.45 | 0 | 0
330 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2023 to 31.01.2024. | Assistant Engineer-I | Junior Engineer-I | ORD/000128/2023-2024 | 517/BD-I | 25/07/2023 | 184 | SOUVIK HALDER | 0.91 | 2.39 | 10
331 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Fate Sing Diar and Char Narayanpur (Village code 315364,315384) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000246/2021-2022 | 1841/BD-I | 05/10/2021 | 60 | UNIVERSE UNEMPLOYED ENGINEERS CO. OPT. & CONSTRUCTION SOCIETY LTD. | 55.84 | 18.71 | 40
332 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baninathpur (Village code 315367) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000247/2021-2022 | 1842/BD-I | 05/10/2021 | 50 | JIBENDRA NARAYAN SUKUL | 41.36 | 41.73 | 1
333 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhatpara (Village code 315370) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000248/2021-2022 | 1843/BD-I | 05/10/2021 | 30 | PROSENJIT DAS | 24.41 | 21.86 | 1
334 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2024 to 31.01.2025. | Assistant Engineer-I | Junior Engineer-I | ORD/000262/2024-2025 | 1195/BD-I | 26/07/2024 | 184 | SOUVIK HALDER | 0.91 | 2.38 | 0
335 | Berhampore Division I | Berhampur Division I | Laying of different dia UPVC distribution pipeline with allied works along with attached sheet of node point over command area of Chaltia village of Bhakuri-I gram panchayat under Bairgachi Water Supply Scheme,Central Sector Part-II under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000379/2021-2022 | 1463/BD-I | 16/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 51.34 | 10.12 | 0
336 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2025 to 31.07.2025. | Assistant Engineer-I | Junior Engineer-I | ORD/000384/2024-2025 | 193/BD-I | 30/01/2025 | 181 | SOUVIK HALDER | 0.91 | 1.6 | 0
337 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2024 to 31.07.2024. | Assistant Engineer-I | Junior Engineer-I | ORD/000427/2023-2024 | 131/BD-I | 31/01/2024 | 182 | SOUVIK HALDER | 0.91 | 2.39 | 100
338 | Berhampore Division I | Berhampur Division I | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under Command area of village of Haridasmati (Village code 315451) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | Assistant Engineer-I | Junior Engineer-I | ORD/000450/2021-2022 | 1882/BD-I | 07/10/2021 | 180 | DHIMAN SARKAR | 88.21 | 78.75 | 50
339 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
340 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Math Binkar (Village code 315366) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000468/2021-2022 | 1870/BD-I | 07/10/2021 | 60 | M/S ADHIKARI CONSTRUCTION | 6.47 | 0 | 0
341 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baikunthapur (Village code 315369) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000469/2021-2022 | 1871/BD-I | 07/10/2021 | 90 | M/S BIMALENDU BOSE | 22.56 | 21.5 | 1
342 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bairgachi Village- village code-315382, Habitation-Char Begpur (ID-0001295651) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000470/2021-2022 | 1872/BD-I | 07/10/2021 | 60 | TANUSHREE ENTERPRISE | 14.92 | 0 | 0
343 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ajodhyanagar village-Village Code-315449, Habitation-Belia khari (ID-0001295654) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID ? 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000471/2021-2022 | 1873/BD-I | 07/10/2021 | 90 | J.S. CONSTRUCTION | 22.08 | 21.87 | 0
344 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mankara, Bezpara, Baragachi, Paschim Narayanpur (Village code 315365, 315368, 315382 & 315383) respectively under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-15) | Assistant Engineer-I | Junior Engineer-I | ORD/000558/2021-2022 | 1889/BD-I | 07/10/2021 | 180 | M/S S.S ENTERPRISE ALAMPUR, NODAKHALI, SOUTH 24 PARGANAS | 296.55 | 139.52 | 1
345 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaltia (Village code 315450) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-01) | Assistant Engineer-I | Junior Engineer-I | ORD/000569/2021-2022 | 1955/BD-I | 27/10/2021 | 180 | UNICON INDIA | 267.92 | 90.56 | 1
346 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Bairgachi Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | Junior Engineer-I | ORD/000761/2021-2022 | 2227/BD-I | 15/12/2021 | 90 | JIBENDRA NARAYAN SUKUL | 74.65 | 77.64 | 1
347 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Bhatpara ( Village code-315370) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission & JalSwapna under Bairgachi (Zone-C) Surface water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | Junior Engineer-I | ORD/000842/2021-2022 | 98/BD-I | 01/02/2022 | 15 | MINA DAS | 8.88 | 7.63 | 1
348 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Ramchandrapur (Habitation ID-0001294189 ) in the village of Ramchandrapur (Village code 314219) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000223/2020-2021 | 987/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 28.26 | 0 | 0
349 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Hanumantanagar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000102/2022-2023 | 1359/BD-I | 21/12/2022 | 30 | PRANAB KUMAR GHOSH | 3.8 | 2.19 | 72
350 | Berhampore Division I | Berhampur Division I | Augmentation of DAKSHIN HANUMANTANAGAR Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000193/2023-2024 | 744/BD-I | 17/08/2023 | 1059 | M/S SINHA & SONS | 478.03 | 0 | 45
351 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN HANUMANTANAGAR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000877/2021-2022 | 261/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.77 | 2.77 | 100
352 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000063/2023-2024 | 196/BD-I/10 | 09/02/2024 | 0 | Resource Division | 102.96 | 0 | 0
353 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Bansgara Zone-I PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000045/2024-2025 | 1068/BD-I | 03/07/2024 | 300 | MAHATO ENTERPRISE | 9 | 0 | 75
354 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road & extension of boundary wall of Bansgara Zone-I PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000076/2025-2026 | 843/BD-I | 23/06/2025 | 45 | SUBHRANIL DAS | 17.81 | 0 | 0
355 | Berhampore Division I | Raghunathganj Sub-Division | BANSGARA ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000084/2024-2025 | 1245/BD-I | 30/07/2024 | 180 | M.K.CONSTRUCTION | 22.29 | 0 | 30
356 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of BANSGARA ZONE-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000142/2023-2024 | 628/BD-I | 04/08/2023 | 310 | SUNIL RABI DAS | 388.8 | 242.14 | 10
357 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Bansgara Zone-I of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000248/2023-2024 | 1032/BD-I | 01/11/2023 | 30 | ALOK BANERJEE ENTERPRISE | 6.83 | 4.46 | 80
358 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000264/2022-2023 | 1687/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.73 | 2.76 | 1
359 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000276/2022-2023 | 1759/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
360 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000011/2023-2024 | 61/BD-1/10 | 27/04/2023 | 0 | Resource Division | 30.97 | 0 | 0
361 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000081/2023-2024 | 201/BD-1/22 | 10/02/2024 | 0 | Resource Division | 83.89 | 0 | 0
362 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMPARA FARIDPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000021/2025-2026 | 638/BD-I | 25/04/2025 | 60 | MASTER CONSTRUCTION | 18.98 | 0 | 0
363 | Berhampore Division I | Berhampur M/E Division | Improvement of Existing AIRP (Capacity 68 Cum/hr.) with allied work at Rampara Faridpur (Zone-I) Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Engineering Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000050/2025-2026 | 759/BD-I | 22/05/2025 | 30 | SANJAY BISWAS | 27.45 | 0 | 0
364 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMPARA FORIDPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000191/2023-2024 | 720/BD-I | 14/08/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100
365 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Rampara Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000253/2024-2025 | 2249/BD-I | 10/12/2024 | 30 | M/S B.R. SUPPLIERS | 9 | 0 | 0
366 | Berhampore Division I | Berhampur M/E Division | Augmentation of Rampara Faridpur Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant(AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000288/2023-2024 | 1017/BD-I | 31/10/2023 | 793 | SANJAY BISWAS | 558.97 | 10.45 | 65
367 | Berhampore Division I | Berhampur M/E Division | RAMPARA FARIDPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, under Jal Jeevan Mission within BELDANGA-II Block in the district of Murshidabad under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000382/2024-2025 | 444/BD-I | 20/03/2025 | 45 | DATA ENTERPRISE | 9.84 | 0 | 0
368 | Berhampore Division I | Berhampur M/E Division | RAMPARA FARIDPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000456/2023-2024 | 460/BD-I | 15/03/2024 | 480 | SAHA CONSTRUCTION | 22.63 | 0 | 75
369 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000107/2023-2024 | 201/BD-1/8 | 10/02/2024 | 0 | Resource Division | 36.69 | 0 | 0
370 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidabad District" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000104/2024-2025 | 1436/BD-I | 04/09/2024 | 30 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 15.6 | 0 | 0
371 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ilimpur (Village code 314175) under Maia Ground Water Supply Scheme of Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000139/2020-2021 | 239/BD-I | 10/02/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 66.88 | 122.7 | 10
372 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000080/2024-2025 | 1228/BD-I | 29/07/2024 | 60 | M/S S. DAS & ENTERPRISE | 74.15 | 0 | 0
373 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kazipara (Village code 314608) under Kazipara Water Supply Scheme of Jalangi Block and village of Ramnagar Doemkanun (Village code 314578) under Ramnagar Doemkanun Water Supply Scheme of Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000838/2021-2022 | 49/BD-I | 27/01/2022 | 180 | M/S S.DAS & ENTERPRISE | 337.04 | 0 | 1
374 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-II | RTOR000008/2021-2022 | 143/BD-I | 10/02/2022 | 0 | Resource Division | 13.51 | 0 | 0
375 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Udaynagar Diar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000173/2024-2025 | 2038/BD-I | 12/11/2024 | 30 | SHIV SHAKTI CONSTRUCTION | 9.1 | 0 | 100
376 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Udaynagar Diar (Village code 314613) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000181/2020-2021 | 918/BD-I | 10/12/2020 | 90 | M/S S.DAS & ENTERPRISE | 34.84 | 39.5 | 0
377 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Azimpur (Village code 314612) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 - 2021,SL-01). | Assistant Engineer | JE | ORD/000240/2020-2021 | 73 /BD-I | 19/01/2021 | 20 | M/S ROY & BOSE ENTERPRISE | 7.67 | 6.18 | 0
378 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jumra Nayagram (Village Code-314190) and others under Jumra Nayagram Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000115/2021-2022 | 917/BD-I | 19/05/2021 | 20 | MODERN CONSTRUCTION | 4.63 | 0 | 0
379 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL JEEVAN MISSION under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000188/2024-2025 | 2196/BD-I | 02/12/2024 | 15 | MAHAMAYA ENTERPRISE | 1.95 | 0 | 0
380 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jumra Nayagram (Village code 314190) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000201/2020-2021 | 966/BD-I | 17/12/2020 | 90 | MODERN CONSTRUCTION | 43.07 | 78.14 | 1
381 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hurshi zone-I ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte | Assistant Engineer | Junior Engineer-II | ORD/000174/2024-2025 | 2089/BD-I | 22/11/2024 | 30 | REDSEA CONSTRUCTION | 3.79 | 0 | 0
382 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatpur (Village code 314749) under Hurshi Zone-I Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-11) | Assistant Engineer | Junior Engineer-II | ORD/000272/2021-2022 | 1143/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 71.98 | 20.6 | 0
383 | Berhampore Division I | Raghunathganj Sub-Division | Additional Laying works at village BEGAMPUR (village code 314750) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hurshi Zone-I Ground water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000567/2021-2022 | 1920/BD-I | 08/10/2021 | 10 | M/S SAJAHAN CHOWDHURY | 5.99 | 4.59 | 1
384 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000101/2024-2025 | 1439/BD-I | 04/09/2024 | 30 | KUNTAL SAHA | 10.13 | 0 | 0
385 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naodapara(Village code 314456) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE | ORD/000103/2020-2021 | 169/BD-I | 03/02/2021 | 20 | M/S SINHA & SONS | 38.69 | 29.48 | 1
386 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000078/2024-2025 | 1226/BD-I | 29/07/2024 | 60 | SARKAR BROTHERS | 12.07 | 0 | 0
387 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamnagar (Village code 315621),Saharbati (Village code 315624) under Charkamnagar Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-II | Junior Engineer-II | ORD/000122/2020-2021 | 194/BD-I | 04/02/2021 | 30 | RAJ KUMAR MONDAL | 98.71 | 98.1 | 97
388 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Saharbati of Kamnagar G.P to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Charkamnagar Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-II | ORD/000777/2021-2022 | 2291/BD-I | 28/12/2021 | 10 | RAJ KUMAR MONDAL | 7.63 | 7.61 | 1
389 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhau Danga (Village code 314195), under Rajarampur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-I | JE | ORD/000114/2020-2021 | 186/BD-I | 04/02/2021 | 20 | S. K. ENTERPRISE | 8.41 | 15.57 | 1
390 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Jhau Danga to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Rajarampur Ground water supply scheme (Lalgola,,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000568/2021-2022 | 1921/BD-I | 08/10/2021 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 0.6 | 0.6 | 1
391 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobindotala(Village code 314454) ,Paschim Rampur(Village code 314455) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000099/2020-2021 | 164/BD-I | 03/02/2021 | 30 | M/S SINHA & SONS | 70.39 | 66.78 | 100
392 | Berhampore Division I | Berhampur Division I | Laying of 150 mm dia (K-9), 200 mm,250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 200 mm dia UPVC pipeline of unlead portion within command area of Dayanagar (Zone-E) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000244/2023-2024 | 954/BD-I | 13/10/2023 | 30 | JAMIRUL CONSTRUCTION | 33.95 | 5.88 | 10
393 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahespur, Ratnagopbati, Sujapur, Radhaballabhpur, Banamalipur, Harinarayanpur, Sibpur, Srikrishnapur, Arazi Giridharpur, Dayanagar, Arazi Jalalpur, Jhunka and Jalalpur under DAYANAGAR (ZONE-E) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000282/2023-2024 | 979/BD-I | 18/10/2023 | 180 | M/S. SUKUMAR SINHA | 402.21 | 0 | 0
394 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000171/2022-2023 | 1386/BD-I | 23/12/2022 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.67 | 100
395 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sani Baharapara (Village code 314841) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000222/2021-2022 | 1811/BD-I | 05/10/2021 | 50 | M/S. SUKUMAR SINHA | 42.52 | 0 | 36
396 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000223/2021-2022 | 1812/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 27.15 | 1
397 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobindapur Lakheraj,Sahamatganj and Bansbari (Village code 314826,314849,314827) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000224/2021-2022 | 1813/BD-I | 05/10/2021 | 631 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 78.62 | 66.83 | 100
398 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kumarpara,Ukta and Ayesbag (Village code 314847,314824,314825) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000225/2021-2022 | 1814/BD-I | 05/10/2021 | 50 | KAMIRUL SK AND CO. | 45.04 | 40.31 | 1
399 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baramganj and Tiktikipara (Village code 314828,314831) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000226/2021-2022 | 1815/BD-I | 05/10/2021 | 50 | KAMIRUL SK AND CO. | 50.58 | 42.78 | 1
400 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalikapur Kadamkhandi (Village code 315389) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000227/2021-2022 | 1816/BD-I | 05/10/2021 | 60 | M/S GUHA AND ROY ENTERPRISE | 59.54 | 15.67 | 1
401 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopinathpur and Chunakhali (Village code 314829,314830) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000228/2021-2022 | 1817/BD-I | 05/10/2021 | 90 | SANJAY BISWAS | 90.82 | 56.22 | 85
402 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 314832) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000454/2021-2022 | 1866/BD-I | 07/10/2021 | 180 | RAJ KUMAR MONDAL | 100.22 | 86.37 | 1
403 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
404 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chainpara, Sanyasidanga & Talgachi (Village code 314821, 314822 & 314823) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-02) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000557/2021-2022 | 1888/BD-I | 07/10/2021 | 180 | M/S SINHA & SONS | 211.59 | 95.29 | 65
405 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Ayesbag Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000758/2021-2022 | 2224/BD-I | 15/12/2021 | 90 | TANUSHREE ENTERPRISE | 78.96 | 76.91 | 1
406 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS | RTOR000011/2021-2022 | 146/BD-I | 10/02/2022 | 0 | Resource Division | 4.67 | 0 | 0
407 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Kaharpara (Habitation ID-0001294214 ) and Santalpara (Habitation ID-0001792540) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000222/2020-2021 | 986/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 42.55 | 0 | 0
408 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Bramhottor (Habitation ID-0001294213 ) and Ilishmari (Habitation ID-0001792563) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000226/2020-2021 | 990/BD-I | 17/12/2020 | 60 | S. K. ENTERPRISE | 11.8 | 18.21 | 1
409 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of B.M. Para,Bausmari and Bramhottor Manikchak (Habitation ID 0001792822,0001792589,0001294212) under Bramhottor Manikchak Ground Water based Water Supply Scheme in Lalgola Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000245/2021-2022 | 1855/BD-I | 07/10/2021 | 50 | KAMIRUL SK AND CO. | 48.43 | 42.31 | 1
410 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Diarmanik chak (village code 314228) under BRAHIMOTTAR MANIKCHAK Ground water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000748/2021-2022 | 2250/BD-I | 21/12/2021 | 45 | ARINDAM MAJUMDAR | 30.87 | 12.15 | 1
411 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Balijana (Village code 314514) ,Nandanpur (Village code 314515) ,Jibanpur (Village code 314516) under Jhikra Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000111/2020-2021 | 183/BD-I | 04/02/2021 | 30 | JAHANGIR ALAM | 73.4 | 57.79 | 1
412 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-B)" Under Bhagwangola-II Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000138/2024-2025 | 1553/BD-I | 24/09/2024 | 30 | M/S. OBAIDUR RAHAMAN | 18.33 | 0 | 0
413 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000111/2024-2025 | 1447/BD-I | 04/09/2024 | 15 | KALAM SK | 0.99 | 0 | 0
414 | Berhampore Division I | Berhampur Division I | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadhukhali (Village code 315672) under Sadhukhali Ground Water Supply Scheme in Beldanga-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer-II | Junior Engineer-II | ORD/000427/2021-2022 | 1635/BD-I | 02/09/2021 | 180 | TARUN KUMAR BHATTACHARYA | 51.96 | 48.51 | 0
415 | Berhampore Division I | Berhampur Division I | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-II | ORD/000853/2021-2022 | 157/BD-I | 11/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0
416 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Telia ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000105/2022-2023 | 1360/BD-I | 21/12/2022 | 661 | PRAVAT KUMAR GHOSH | 2.41 | 0 | 100
417 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of Telia Piped water supply scheme to accommodate construction of OHR, toilet ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000134/2022-2023 | 1446/BD-I | 17/01/2023 | 911 | MUNNA AGROTECH ENTERPRISE | 338.52 | 134.86 | 80
418 | Berhampore Division I | Berhampur Division I | Allied work for construction of Cast-in-situ Pile (grade M30) (Shaft Length 25 Mtr.) to accommodate construction of OHR, pump house, boundary wall and road restoration of Augmentation of TELIA Piped water supply scheme under Jal Jeevan Mission and Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000157/2024-2025 | 1629/BD-I | 04/10/2024 | 177 | MUNNA AGROTECH ENTERPRISE | 50.58 | 0 | 90
419 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for TELIA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000883/2021-2022 | 267/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.63 | 2.63 | 100
420 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000066/2023-2024 | 196/BD-I/13 | 09/02/2024 | 0 | Resource Division | 8.05 | 0 | 0
421 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Hurshi Zone-II Piped water supply scheme to accommodate construction of OHR, pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000136/2023-2024 | 615/BD-I | 02/08/2023 | 790 | ROY AND ROY CONSTRUCTION | 246.81 | 110.57 | 30
422 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000195/2022-2023 | 1330/BD-I | 16/12/2022 | 10 | RADIANT | 2.53 | 2.53 | 100
423 | Berhampore Division I | Raghunathganj Sub-Division | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hurshi Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (For 2 nos. Tubewell) | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000314/2023-2024 | 1148/BD-I | 04/12/2023 | 30 | NADIA TUBEWELLS | 23.12 | 0 | 0
424 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000006/2023-2024 | 61/BD-1/7 | 27/04/2023 | 0 | Resource Division | 19.67 | 0 | 0
425 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bansgara Zone-I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000024/2023-2024 | 312/BD-I | 14/06/2023 | 898 | MODERN CONSTRUCTION | 281.33 | 112.91 | 30
426 | Berhampore Division I | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub- Division, PHE Dte. Under Berhampore Division ¿ I, P.H.E. Dte in the district of Murshidabad. Period from 01.05.2025 to 31.10.2025 Car No- W.B-57B/5069 | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000044/2025-2026 | 656/BD-I | 28/04/2025 | 183 | DEBADITYA TRANSPORT | 0.91 | 0 | 0
427 | Berhampore Division I | Berhampur M/E Division | Balance and Allied work for Laying Rising Main (DI K-9) and Distribution System (DI-K7) including inter connection with supply of necessary CI special and valve at Head Work Site including road restoration for augmentation work of Bansgrara Zone -I Water Supply Scheme , under Jal Jeevan Mission within Lalgola block under Berhampore DIvision -I , PHE.Dte. in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000077/2025-2026 | 844/BD-I | 23/06/2025 | 180 | MODERN CONSTRUCTION | 57.56 | 0 | 80
428 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd/3rd/4th site) and Allied Works for Bansgara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000126/2022-2023 | 1669/BD-I | 14/03/2023 | 30 | JIYARUL SK | 4.19 | 2.35 | 100
429 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Dakshin Gopalpur ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000040/2025-2026 | 704/BD-I | 13/05/2025 | 300 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 122.64 | 0 | 0
430 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of Dakshin Gopalpur PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000050/2024-2025 | 1113/BD-I | 10/07/2024 | 45 | KHANDAKAR CONSTRUCTION | 22.05 | 0 | 0
431 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of DAKSHIN GOPALPUR Piped water supply scheme for laying of design pipeline, rising main and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000241/2022-2023 | 1598/BD-I | 28/02/2023 | 733 | GOUTAM CHAKRABORTY | 134.6 | 134.53 | 32
432 | Berhampore Division I | Raghunathganj Sub-Division | Allied work of Dakshin Gopalpur Piped Water Supply Scheme for laying of Pipeline ,Rising Main, Pump House Repairing under Jal Jeevan Mission within Raninagar - I Block under Berhampore Division - I PHE Dte in Murshidabad District. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000257/2024-2025 | 2270/BD-I | 16/12/2024 | 227 | M/S GOUTAM CHAKRABORTY | 4.31 | 0 | 100
433 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN GOPALPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000275/2022-2023 | 1504/BD-I | 07/02/2023 | 10 | M/S SOBHA & CO | 2.67 | 2.57 | 100
434 | Berhampore Division I | Raghunathganj Sub-Division | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2025 to 30.06.2025. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000287/2024-2025 | 2326/BD-I | 27/12/2024 | 182 | TARUN KUMAR BHATTACHARYA | 0.91 | 1.59 | 0
435 | Berhampore Division I | Raghunathganj Sub-Division | Renovation for Modified Sujapur Sadipur Model after washing of AIRP (Capacity 29.06 Cum/hr.) at Dakshin Gopalpur Water Supply Scheme under Jal Jivan Mission of Raninagar-I Block under Raghunathganj Sub-Division under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000439/2023-2024 | 410/BD-I | 13/03/2024 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 51.69 | 44.75 | 75
436 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000020/2023-2024 | 194/BD-I/4 | 09/02/2024 | 0 | Resource Division | 36.44 | 0 | 0
437 | Berhampore Division I | Berhampur Division I | Improvement of OHR (180 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-III PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000027/2024-2025 | 983/BD-I | 19/06/2024 | 60 | U.S BUILDERS | 9.46 | 0 | 0
438 | Berhampore Division I | Berhampur Division I | Allied works of Laying of distribution pipeline of RAMNACHANDPUR ZONE-III under JJM within Nowda Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000147/2024-2025 | 1615/BD-I | 03/10/2024 | 30 | MD ENTERPRISE | 12.65 | 0 | 0
439 | Berhampore Division I | Berhampur Division I | Augmentation of Ramnachandpur Zone-III Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000207/2022-2023 | 1622/BD-I | 02/03/2023 | 670 | SAMAR MUKHERJEE | 112.68 | 105.45 | 99
440 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-III Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000236/2022-2023 | 1594/BD-I | 28/02/2023 | 10 | TECHVISION | 2.53 | 2.53 | 0
441 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | RTOR000055/2023-2024 | 196/BD-I/17 | 09/02/2024 | 0 | Resource Division | 14.91 | 0 | 0
442 | Berhampore Division I | Berhampur M/E Division | AMARKUNDA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000027/2023-2024 | 94/BD-I | 04/05/2023 | 881 | TANUSHREE ENTERPRISE | 240.28 | 89.12 | 100
443 | Berhampore Division I | Berhampur M/E Division | AMARKUNDA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000086/2023-2024 | 206/BD-I | 17/05/2023 | 744 | G M ENTERPRISE | 53.43 | 27.52 | 20
444 | Berhampore Division I | Berhampur M/E Division | AMARKUNDA PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000293/2022-2023 | 1825/BD-I | 31/03/2023 | 180 | AJOY GHOSH | 96.88 | 58.27 | 20
445 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000017/2023-2024 | 61/BD-1/35 | 27/04/2023 | 0 | Resource Division | 13.43 | 0 | 0
446 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000108/2023-2024 | 304/BD-1/8 | 22/02/2024 | 0 | Resource Division | 9.83 | 0 | 0
447 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000064/2024-2025 | 1193/BD-I | 25/07/2024 | 180 | SOUMEN ADHIKARY | 10.19 | 0 | 0
448 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Rianpur (village code 315397) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Jumra Nayagram ground water supply scheme (Block-Lalgola)under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000076/2022-2023 | 632/BD-I | 31/05/2022 | 10 | CHATTERJEE ENTERPRISE | 8.92 | 4.55 | 1
449 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Panisala (Village code 314191) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000200/2020-2021 | 965/BD-I | 17/12/2020 | 90 | SAMBHUNATH ROY | 37.24 | 33.5 | 1
450 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rianpur (Village code 314192) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000202/2020-2021 | 968/BD-I | 17/12/2020 | 90 | JAHANGIR ALAM | 38.56 | 38.03 | 1
451 | Berhampore Division I | Berhampur Division I | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000047/2023-2024 | 143/BD-I | 15/05/2023 | 893 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 96.62 | 0 | 5
452 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHISASTHALI and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000080/2025-2026 | 847/BD-I | 23/06/2025 | 30 | WATER TECH | 17.75 | 0 | 0
453 | Berhampore Division I | Berhampur Division I | MAHISHASTHALI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000106/2023-2024 | 211/BD-I | 17/05/2023 | 90 | MANAB KUMAR GHOSH | 38.89 | 12.99 | 15
454 | Berhampore Division I | Berhampur Division I | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 350 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000374/2023-2024 | 116/BD-I | 30/01/2024 | 620 | RANADHIR SINHA | 268.39 | 0 | 30
455 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000035/2023-2024 | 61/BD-1/21 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
456 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chhalimpur under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000066/2023-2024 | 163/BD-I | 16/05/2023 | 90 | DEBJIT DAS | 22.79 | 0 | 100
457 | Berhampore Division I | Raghunathganj Sub-Division | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under RAMNAGAR DOEMKANUN ,KOMNAGAR and BANSGARA ZONE-II ground Water based Water Supply Scheme under Raninagar-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000109/2023-2024 | 438/BD-I | 12/07/2023 | 692 | MAA CONSTRUCTION | 93.76 | 24.1 | 30
458 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egrarashi (Village code 314576) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000218/2020-2021 | 982/BD-I | 17/12/2020 | 60 | MAA CONSTRUCTION | 5.73 | 4.6 | 1
459 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000219/2020-2021 | 983/BD-I | 17/12/2020 | 60 | AZAD ENTERPRISE | 11.16 | 2.24 | 1
460 | Berhampore Division I | Raghunathganj Sub-Division | Laying of new pipeline for Providing Balanced Functional Household Tap Connection (FHTC) which is not covered by existing distribution pipeline from nearest Ground water supply scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Khastaluk (Village code 314586) under Ramnagar Doemkanun Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000380/2021-2022 | 1464/BD-I | 16/08/2021 | 15 | SANTANU BISWAS | 8.61 | 6.57 | 0
461 | Berhampore Division I | Raghunathganj Sub-Division | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanun Ground Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-II) | Assistant Engineer | Junior Engineer-II | ORD/000413/2021-2022 | 1442/BD-I | 11/08/2021 | 10 | AZAD ENTERPRISE | 4.61 | 3.86 | 1
462 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | Assistant Engineer | Junior Engineer-II | ORD/000455/2020-2021 | 443/BD-I | 30/03/2021 | 184 | AVINABA ENGINEERING CONCERN | 0.91 | 2.11 | 1
463 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | Assistant Engineer | Junior Engineer-II | ORD/000456/2020-2021 | 444/ BD-I | 30/03/2021 | 184 | AVINABA ENGINEERING CONCERN | 0.91 | 2.37 | 1
464 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalyanpur (village code 314577) under Ramnagar Doemkanun Ground water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000749/2021-2022 | 187/BD-I | 18/02/2022 | 45 | DAS ENTERPRISE | 37.01 | 27.06 | 71
465 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Chhoemkanun (village code 314579) under Ramnagar Doemkanun Ground water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000750/2021-2022 | 2208/BD-I | 10/12/2021 | 120 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 89.24 | 59.76 | 1
466 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.10.2021 to 31.12.2021. | Assistant Engineer | Junior Engineer-II | ORD/000825/2021-2022 | 1779/BD-I | 30/09/2021 | 92 | AVINABA ENGINEERING CONCERN | 0.45 | 0 | 1
467 | Berhampore Division I | Raghunathganj Sub-Division | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.10.2021 to 31.12.2021 | Assistant Engineer | Junior Engineer-II | ORD/000826/2021-2022 | 1780/BD-I | 30/09/2021 | 92 | AVINABA ENGINEERING CONCERN | 0.45 | 1.14 | 1
468 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kazipara (Village code 314608) under Kazipara Water Supply Scheme of Jalangi Block and village of Ramnagar Doemkanun (Village code 314578) under Ramnagar Doemkanun Water Supply Scheme of Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000838/2021-2022 | 49/BD-I | 27/01/2022 | 180 | M/S S.DAS & ENTERPRISE | 337.04 | 82.3 | 1
469 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No- W.B-57E/2525 Scorpio Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000869/2021-2022 | 2278/BD-I | 27/12/2021 | 365 | M/S SAJAHAN CHOWDHURY | 1.81 | 1.82 | 1
470 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000870/2021-2022 | 2279/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 2.65 | 1
471 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000871/2021-2022 | 2281/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 1
472 | Berhampore Division I | Raghunathganj Sub-Division | Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000872/2021-2022 | 2280/BD-I | 27/12/2021 | 365 | SEBAYAN CONSTRUCTION | 1.81 | 4.76 | 1
473 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-II | RTOR000009/2021-2022 | 140/BD-I | 10/02/2022 | 0 | Resource Division | 15.4 | 0 | 0
474 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-I under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000057/2023-2024 | 154/BD-I | 15/05/2023 | 90 | DATA ENTERPRISE | 30.53 | 0 | 0
475 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BELIA SHYAMPUR and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000082/2025-2026 | 849/BD-I | 23/06/2025 | 30 | JOY GURU ENTERPRISE | 17.75 | 0 | 0
476 | Berhampore Division I | Berhampur Division I | BELIA SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000092/2023-2024 | 214/BD-I | 17/05/2023 | 991 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 40.8 | 13.26 | 50
477 | Berhampore Division I | Berhampur Division I | BELIA SYAMPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000132/2023-2024 | 611/BD-I | 02/08/2023 | 180 | ROY CONSTRUCTION (AVIJIT ROY) | 69 | 0 | 0
478 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000033/2023-2024 | 61/BD-1/17 | 27/04/2023 | 0 | Resource Division | 11.74 | 0 | 0
479 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Koasbagoas Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000023/2023-2024 | 375/BD-I | 28/06/2023 | 730 | MAMATA USHA ENTERPRISE | 534.97 | 287.74 | 75
480 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASBAGOAS ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division-I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000083/2025-2026 | 875/BD-I | 01/07/2025 | 60 | TAIMUR SK | 16.51 | 0 | 0
481 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASBAGOAS Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000269/2022-2023 | 1692/BD-I | 14/03/2023 | 10 | RADIANT | 2.67 | 2.67 | 100
482 | Berhampore Division I | Raghunathganj Sub-Division | Construction Pump House Cum Chlorine Room at KASBAGOAS Water Supply Scheme under Jal Jevan Mission within Raninagar-I Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000325/2024-2025 | 272/BD-I | 11/02/2025 | 60 | TAIMUR SK | 7.5 | 0 | 0
483 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000018/2023-2024 | 194/BD-I/3 | 09/02/2024 | 0 | Resource Division | 55.6 | 0 | 0
484 | Berhampore Division I | Berhampur M/E Division | KALIAGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000082/2023-2024 | 1258/BD-I | 22/12/2023 | 630 | SATELLITE CONSTRUCTION | 39.24 | 0 | 25
485 | Berhampore Division I | Berhampur M/E Division | KALIAGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000271/2023-2024 | 975/BD-I | 18/10/2023 | 531 | PRANAB KUMAR GHOSH | 61.78 | 4.5 | 25
486 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000025/2023-2024 | 61/BD-1/22 | 27/04/2023 | 0 | Resource Division | 13.36 | 0 | 0
487 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000117/2023-2024 | 304/BD-1/10 | 22/02/2024 | 0 | Resource Division | 2.82 | 0 | 0
488 | Berhampore Division I | Raghunathganj Sub-Division | Wayleave Facility Charge FOR Laying of 600MM Dia. Casing Pipe FOR Passing of 350MM Dia. Carrier Water Pipeline B/W KM-254/2-254/3 Between Station Ballalpur-New Farakka under Malda Division of Eastern Railway. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | BILL/00296/2024-2025 | BP-2024-25-207 | 03/10/2024 | 0 | EASTERN RAILWAY MALDA DIVISION | 5.35 | 0 | 0
489 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of different units of WTP premises of Beniagram Water Supply scheme under, Berhampore Division -I PHE.Dte. under JJM | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | ORD/000024/2024-2025 | 945/BD-I | 11/06/2024 | 60 | P.M CONSTRUCTION | 97.98 | 17.2 | 25
490 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Beniagram Surface water based water supply scheme to accommodate construction of OHR, pump house and boundary wall, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Farakka Block of Murshidabad District under Berhampore Division-I,PHE.Dte. in the district Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | ORD/000200/2023-2024 | 841/BD-I | 05/09/2023 | 365 | CHAKRABORTY CONSTRUCTION | 3038.97 | 305.29 | 50
491 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | RTOR000003/2024-2025 | 1341/BD-I/1 | 20/08/2024 | 0 | Resource Division | 89.82 | 0 | 0
492 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-II | RTOR000040/2023-2024 | 194/BD-I/1 | 09/02/2024 | 0 | Resource Division | 89.82 | 0 | 0
493 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-A)" Under Lalgola Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000139/2024-2025 | 1554/BD-I | 24/09/2024 | 189 | TANUSHREE ENTERPRISE | 66.93 | 0 | 0
494 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Bansgara ( Habitation ID: 0001294178) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.¿ | Assistant Engineer-I | JE | ORD/000140/2020-2021 | 240/BD-I | 10/02/2021 | 90 | SARAJIT KUMAR MAJUMDAR | 25.45 | 24.24 | 1
495 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Chataidubi ( Habitation ID: 0001294180) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000141/2020-2021 | 241/BD-I | 10/02/2021 | 90 | SANJAY BISWAS | 29.77 | 22.86 | 85
496 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Latiberpara(HabitationID: 0001294181),Naldahari ( Habitation ID: 0001294179) ,Uttar Latiberpara ( Habitation ID: 0001796720) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000144/2020-2021 | 250/BD-I | 11/02/2021 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 32.47 | 31.99 | 0
497 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Krishnapur village (Village code 314218) under Bansgara Ground Water Supply Scheme in Lalgola Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-13) | Assistant Engineer-I | JE | ORD/000274/2021-2022 | 1145/BD-I | 07/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 200.42 | 50.52 | 1
498 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000095/2024-2025 | 1307/BD-I | 07/08/2024 | 60 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 28.84 | 0 | 0
499 | Berhampore Division I | Berhampur Division I | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Hanumantanagar (Village code 314436) under Dakshin Hanumantanagar Ground Water based Water Supply Scheme in Bhagawangola-I Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer-I | JE | ORD/000384/2021-2022 | 1488/BD-I | 18/08/2021 | 180 | H.I ENTERPRISE | 217.42 | 172.18 | 1
500 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Dakhshin Hanumantanagar (Village code-314436) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Dakhshin Hanumantanagar Ground water based Water supply scheme (Bhagwangola-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-I | JE | ORD/000795/2021-2022 | 2311/BD-I | 29/12/2021 | 60 | H.I ENTERPRISE | 30.49 | 25.99 | 1
501 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000012/2021-2022 | 142/BD-I | 10/02/2022 | 0 | Resource Division | 4.56 | 0 | 0
502 | Berhampore Division I | Berhampur Division I | Additional laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna for the village of Hasanpur (Habitation Id-0001294589) at village of Hasanpur (Village Code-314405) under Hasanpur Ground Water Supply Scheme (Bhagawangola-II Block) under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000006/2022-2023 | 548/BD-I | 13/05/2022 | 10 | JAHANGIR ALAM | 2.83 | 1.87 | 1
503 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hasanpur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000079/2024-2025 | 1227/BD-I | 29/07/2024 | 60 | M/S JOY MA BANAMALI | 15.89 | 0 | 0
504 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur and Others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000113/2021-2022 | 915/BD-I | 19/05/2021 | 7 | M/S J.A CONSTRUCTION | 0.77 | 0 | 0
505 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasanpur (Habitation ID-0001294589 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000196/2020-2021 | 967/BD-I | 17/12/2020 | 90 | JAHANGIR ALAM | 21.8 | 18.01 | 35
506 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Shibnagar (Habitation ID-0001294590 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000197/2020-2021 | 975/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 24.37 | 36.68 | 1
507 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur (Village code 314510) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000198/2020-2021 | 963/BD-I | 17/12/2020 | 60 | SWARUP KUMAR BHATTA | 8.42 | 8.28 | 1
508 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 314536) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000199/2020-2021 | 964/BD-I | 17/12/2020 | 60 | M/S J.A CONSTRUCTION | 4.46 | 0 | 0
509 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur and others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000208/2020-2021 | 275/ BD-I | 15/02/2021 | 10 | SWARUP KUMAR BHATTA | 2.26 | 0.75 | 1
510 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under HASANPUR ground Water based Water Supply Scheme of Bhagawangola-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000272/2023-2024 | 976/BD-I | 18/10/2023 | 90 | PRAVAT KUMAR GHOSH | 11.83 | 0 | 0
511 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Arazi Alaipur (village code 314537) under HASANPUR Ground water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000746/2021-2022 | 2260/BD-I | 22/12/2021 | 20 | KUNTAL SAHA | 6.91 | 0 | 0
512 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshidabad District in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000063/2024-2025 | 1204/BD-I | 26/07/2024 | 60 | AZAD ENTERPRISE | 43.72 | 0 | 0
513 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhundar Kismat (Village code 314468) under Bhundar Kismat Water Supply Scheme of Bhagawangola-I Block and village of Maniknagar (Village code 315606) under Maniknagar (Zone-D) Surface water based Water Supply Scheme of Beldanga-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000841/2021-2022 | 82/BD-I | 31/01/2022 | 180 | J.D.J ENTERPRISE | 248.16 | 0 | 5
514 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasba Bahadurpur (Village code 314488) , under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000101/2020-2021 | 167/BD-I | 03/02/2021 | 728 | M/S SINHA & SONS | 95.89 | 19.57 | 1
515 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rasulpur (Village code 314492) , Chandipur Ramkantapur (Village code 314483) under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000102/2020-2021 | 168/BD-I | 03/02/2021 | 20 | KAMIRUL SK AND CO. | 33.2 | 38.46 | 1
516 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Saaragachhi(Village code 314453),Chainpara(Village code 314457),Rameswarbati(Village code 314458),Maliapara(Village code 314452) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000104/2020-2021 | 170/BD-I | 03/02/2021 | 30 | M/S. SUKUMAR SINHA | 49.93 | 37.79 | 0
517 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.07.2025 to 31.10.2025. | Assistant Engineer-II | Junior Engineer-II | ORD/000092/2025-2026 | 855/BD-I | 30/06/2025 | 123 | SEBAYAN CONSTRUCTION | 0.6 | 0 | 0
518 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Pradipdanga(Zone-H) Surface Water based Water Supply Scheme of Central Sector (Part-II) under Hariharpara Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000112/2023-2024 | 441/BD-I | 12/07/2023 | 90 | S DUTTA | 48.85 | 0 | 0
519 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II) Under Hariharpara Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000159/2024-2025 | 1647/BD-I | 23/10/2024 | 181 | NOVELTY CONSTRUCTION | 68.93 | 0 | 70
520 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahishmara (Village code 315474) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000229/2021-2022 | 1027/BD-I | 21/06/2021 | 50 | SARAJIT KUMAR MAJUMDAR | 42.39 | 0 | 0
521 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara and Bhandardaha (Village code 315475,315476) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000230/2021-2022 | 1029/BD-I | 21/06/2021 | 70 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 65.72 | 85.65 | 1
522 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baruipara (Village code 315465) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000231/2021-2022 | 1033/BD-I | 21/06/2021 | 70 | DECON INDIA | 62.7 | 21.06 | 1
523 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naopara,Simulia and Panch Baria (Village code 315372,315373,315374) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000249/2021-2022 | 1028/BD-I | 21/06/2021 | 80 | M/S JHA CONSTRUCTION | 76.94 | 18.86 | 1
524 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekpara and Jagannathpur (Village code 315472,315477) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000250/2021-2022 | 1030/BD-I | 21/06/2021 | 90 | NEOGI ENTERPRISE | 87.92 | 59.34 | 1
525 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lal Nagar and Bil Bhandardaha (Village code 315471,315473) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000251/2021-2022 | 1031/BD-I | 21/06/2021 | 90 | SUBHAS CHANDRA KESHARI | 86.54 | 42.48 | 1
526 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamalpur and Pradipdanga (Village code 315469,315470) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000252/2021-2022 | 1032/BD-I | 21/06/2021 | 70 | M/S AMIT KUMAR GUPTA | 69.96 | 26.19 | 60
527 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2025 to 30.06.2025. | Assistant Engineer-II | Junior Engineer-II | ORD/000273/2024-2025 | 2335/BD-I | 30/12/2024 | 182 | SEBAYAN CONSTRUCTION | 0.91 | 2.4 | 0
528 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khidirpur & Simulia Jot (Village code 315466) under Pradipdanga (Zone-H)Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | Assistant Engineer-II | Junior Engineer-II | ORD/000424/2021-2022 | 1595/BD-I | 31/08/2021 | 180 | NAYLA CONSTRUCTION | 105.36 | 91.58 | 1
529 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
530 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kismat Imadpur (Village code 315468) under Pradipdanga (Zone-H) Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | Assistant Engineer-II | Junior Engineer-II | ORD/000497/2021-2022 | 1904/BD-I | 08/10/2021 | 180 | MS RUBIET HOSSAIN | 176.97 | 0 | 0
531 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Pradipdanga Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-II | ORD/000756/2021-2022 | 2222/BD-I | 15/12/2021 | 90 | APURBA SAHA CHOWDHURY | 82.14 | 79.33 | 1
532 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Jamalpur and Pradipdanga (Village code-315469 and 315470) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Pradipdanga Surface water based Water supply scheme (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-II | ORD/000786/2021-2022 | 2290/BD-I | 28/12/2021 | 20 | M/S AMIT KUMAR GUPTA | 12.67 | 8.95 | 1
533 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nesta & Kumirdaha (Village code 314871 & 314872) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000220/2021-2022 | 1018/BD-I | 21/06/2021 | 60 | MODERN CONSTRUCTION | 80.88 | 76.68 | 85
534 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanksa & Hulaspur (Village code 314882 & 314885) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000221/2021-2022 | 1019/BD-I | 21/06/2021 | 60 | RAJ KUMAR MONDAL | 78.07 | 65.04 | 1
535 | Berhampore Division I | Berhampur Division I | Laying of CI/DI pipeline and sluice valve with chamber at different places under Rampur Zone-C,central sector part-I under JJM under Berhampore Division-I ,P.H.E Dte. In the district of Murshidabad. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000258/2024-2025 | 2271/BD-I | 16/12/2024 | 30 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 5.02 | 0 | 0
536 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Neoai Khamarpara, Purba Gobindapur & Rampur (Village code 314876,314883 & 314884) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000259/2021-2022 | 1047/BD-I | 21/06/2021 | 60 | A ONE CONSTRUCTION | 83.87 | 71.41 | 1
537 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dangapara,Bati & Char Ramipur (Village code 314887,314888 & 314889) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000260/2021-2022 | 1048/BD-I | 21/06/2021 | 60 | BOSE & CO | 98.62 | 77.92 | 1
538 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2025 to 31.12.2025 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000267/2024-2025 | 2328/BD-I | 27/12/2024 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 0.8 | 0
539 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharmmapur (Village code 314875) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000276/2021-2022 | 1169/BD-I | 15/07/2021 | 90 | SHYAMAL KUMAR SAHA | 84.96 | 72.88 | 1
540 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tentulia & Char Chatra (Village code 314873 & 314874) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000294/2021-2022 | 1180/BD-I | 16/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 114.26 | 98.18 | 1
541 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasenpur (Village code 314886) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000295/2021-2022 | 1181/BD-I | 16/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 117.76 | 105.56 | 1
542 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
543 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Rampur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000852/2021-2022 | 133/BD-I | 08/02/2022 | 90 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 79.8 | 77.93 | 100
544 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sundarpur(Village code 314445) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE | ORD/000106/2020-2021 | 172/BD-I | 03/02/2021 | 30 | KAMIRUL SK AND CO. | 53.12 | 92.99 | 0
545 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Bansgara ground water supply scheme within Raninagar-II block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000096/2024-2025 | 1320/BD-I | 12/08/2024 | 60 | JEWS CONSTRUCTION &CO | 16.78 | 0 | 0
546 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bansgara (Village code 314587) and Majhardiar (Village code 314588) under Bansgara Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000150/2020-2021 | 271/ BD-I | 12/02/2021 | 30 | M/S S.S ENTERPRISE | 79.51 | 58.68 | 0
547 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhikra (Village code 314512) ,Ranitala (Village code 314513) under Jhikra Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000110/2020-2021 | 182/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.83 | 91.14 | 1
548 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramganpara (Village code 315662) under Rampara Faridpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000227/2020-2021 | 991/BD-I | 17/12/2020 | 90 | M/S S.DAS & ENTERPRISE | 38.85 | 29.89 | 75
549 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000107/2024-2025 | 1443/BD-I | 04/09/2024 | 60 | SUPTI ENTERPRISE | 17.42 | 0 | 0
550 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bikal Nagar (Village code 315678), under Kashipur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-II | Junior Engineer-I | ORD/000116/2020-2021 | 188/BD-I | 04/02/2021 | 30 | HANNAN BUILDERS PVT. LTD. | 60.34 | 49.9 | 1
551 | Berhampore Division I | Berhampur Division I | Additional Laying works at village BIKALNAGAR( Village code-315678) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Kashipur Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | Junior Engineer-I | ORD/000571/2021-2022 | 1923/BD-I | 08/10/2021 | 10 | AHS (R) INFRA PRIVATE LIMITED | 7.21 | 6.55 | 1
552 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alampur (village code 315519) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000243/2021-2022 | 1853/BD-I | 07/10/2021 | 90 | SRIJON ENTERPRISE | 88.19 | 0 | 1
553 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Moktarpur (Village code 314766) under Moktarpur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-I)(Sl-06) | Assistant Engineer | Junior Engineer-II | ORD/000382/2021-2022 | 1471/BD-I | 17/08/2021 | 1454 | M/S GOUTAM CHAKRABORTY | 122.27 | 96.08 | 75
554 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Halalpur, Mohula, Binkar, Mahishasthali, Gopinathpur & Bhabta under Mohula (ZONE-A) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000075/2022-2023 | 1641/BD-I | 09/03/2023 | 180 | M/S JAN MAHAMMAD | 558.19 | 0 | 0
555 | Berhampore Division I | Berhampur Division I | Laying of connection for supply of drinking water at Tiktikipara Baharul Ulum Madrasah Kendra in connection with JJM (Jal Jeevan Mission) under different Berhampore Block under different water supply scheme of Behampore Division-I, P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000018/2023-2024 | 89/BD-I | 03/05/2023 | 30 | SO-FINE AQUARIUM | 1.5 | 1.5 | 100
556 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Banjetia (Village code 315445), Sibpur (Village Code 315391) & Nagpara (Village Code 315390) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000245/2020-2021 | 978/BD-I | 17/12/2020 | 979 | ACQUA CONSTRUCTION CONSORTIUM | 272.06 | 161.82 | 85
557 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janmahammadpur (Village code 315398), Ustia (Village Code-315399) & Hatinagar (Village Code-315397) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000246/2020-2021 | 979/BD-I | 17/12/2020 | 826 | M/S JAN MAHAMMAD | 264.94 | 91.9 | 100
558 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Cossimbazar (Village code 315444), Sibnagar Badarpur (Village Code-315446) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000313/2020-2021 | 980/BD-I | 17/12/2020 | 180 | CHAKRABORTY CONSTRUCTION | 307.25 | 43.36 | 69
559 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
560 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Madapur ( village code 315392 ) under HATINAGAR ( Zone - A ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000467/2021-2022 | 1840/BD-I | 05/10/2021 | 30 | MAA CONSTRUCTION | 24.5 | 23.96 | 1
561 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Janmahammadpur (village code 315398),Ustia(village code315399),Hatinagar (village code 315397) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hatinagar (Zone-A) Surface water supply scheme (Block-Berhampore)under Berhampore Division-I, PHE Dte. In the District of Murshidabad. (Part-I) | Assistant Engineer-I | Junior Engineer-I | ORD/000579/2021-2022 | 1856/BD-I | 07/10/2021 | 40 | M/S JAN MAHAMMAD | 32.92 | 32.92 | 1
562 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Banjetia, Sibpur and Nagpara (Village code-315445,315391 and 315390) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hatinagar (Zone-A)Surface water based Water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | Junior Engineer-I | ORD/000822/2021-2022 | 11/BD-I | 05/01/2022 | 20 | ACQUA CONSTRUCTION CONSORTIUM | 25.71 | 0 | 0
563 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Bhundar Kismat ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000106/2022-2023 | 1362/BD-I | 21/12/2022 | 630 | GHOSH BUILDERS | 2.41 | 0 | 100
564 | Berhampore Division I | Berhampur Division I | Augmentation of Bhundar kismat Piped water supply scheme to accommodate construction of pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000201/2022-2023 | 1617/BD-I | 02/03/2023 | 180 | DHIRENDRA NATH MONDAL | 222.61 | 186.56 | 60
565 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BHUNDAR KISMAT Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000885/2021-2022 | 268/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 0
566 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000059/2023-2024 | 196/BD-I/6 | 09/02/2024 | 0 | Resource Division | 48.07 | 0 | 0
567 | Berhampore Division I | Berhampur Division I | Balance work for the work of Laying distribution pipe line of Diar Syampur Zone-II PWSS under Jal Jeevan Mission within Bhagwangola-I block in connection with Augmentation under Berhampore Division-I,PHE.Dte. In the district of Murshidabad. | Assistant Engineer-I | JE | ORD/000055/2025-2026 | 767/BD-I | 22/05/2025 | 90 | SANDHAN ADHIKARI | 69.54 | 0 | 0
568 | Berhampore Division I | Berhampur Division I | Augmentation of Diar Syampur Zone-II Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE | ORD/000200/2022-2023 | 1623/BD-I | 02/03/2023 | 670 | SANDHAN ADHIKARY | 152.01 | 56.56 | 40
569 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-II Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000880/2021-2022 | 264/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.44 | 2.39 | 100
570 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE | RTOR000061/2023-2024 | 196/BD-I/8 | 09/02/2024 | 0 | Resource Division | 10.99 | 0 | 0
571 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Ramnapara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000113/2022-2023 | 1410/BD-I | 04/01/2023 | 30 | KAKALI ENTERPRISE | 2.23 | 1.23 | 100
572 | Berhampore Division I | Berhampur Division I | Augmentation of RAMNAPARA Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000190/2022-2023 | 1456/BD-I | 17/01/2023 | 180 | S.K ENTERPRISE (RANITALA) | 34.01 | 33.78 | 100
573 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAPARA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000887/2021-2022 | 270/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.41 | 1
574 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS | RTOR000052/2023-2024 | 196/BD-I/3 | 09/02/2024 | 0 | Resource Division | 1.74 | 0 | 0
575 | Berhampore Division I | Berhampur M/E Division | Construction Pump House Cum Chlorine Room at Head Work site of Nasipur Zone -II Water Supply Scheme under Jal Jevan Mission of Lalgola Block of Murshidabad District under Berhampore Division -I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000069/2025-2026 | 823/BD-I | 18/06/2025 | 45 | M/S B. P. ENTERPRISE | 8.47 | 0 | 50
576 | Berhampore Division I | Berhampur M/E Division | Augmentation of Nasipur zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000140/2023-2024 | 625/BD-I | 03/08/2023 | 790 | M/S BIMALENDU BOSE | 374.96 | 194.24 | 10
577 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE-II Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000364/2024-2025 | 319/BD-I | 24/02/2025 | 15 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0
578 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of NASIPUR ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000376/2024-2025 | 431/BD-I | 19/03/2025 | 60 | ABA CONTRACTOR | 18.98 | 0 | 0
579 | Berhampore Division I | Berhampur M/E Division | NASIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000451/2023-2024 | 454/BD-I | 15/03/2024 | 60 | INDRAJIT DUBEY | 22.41 | 14.28 | 50
580 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000017/2024-2025 | 1510/BD-I/11 | 12/09/2024 | 0 | Resource Division | 5.48 | 0 | 0
581 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000075/2023-2024 | 201/BD-1/16 | 10/02/2024 | 0 | Resource Division | 303.88 | 0 | 0
582 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000005/2023-2024 | 41/BD-I | 20/04/2023 | 10 | TECHVISION | 2.63 | 2.56 | 100
583 | Berhampore Division I | Berhampur Division I | Augmentation of Sadhukhali Zone-II Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP ), pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. [2nd Call for WBPHED/EE/BD-I/NIeT-20 of 2022 ¿ 2023(sl-02)] | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000126/2023-2024 | 845/BD-I | 05/09/2023 | 310 | RAJ KUMAR MONDAL | 302.11 | 0 | 0
584 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sadhukhali Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000389/2023-2024 | 151/BD-I | 05/02/2024 | 421 | INDRAJIT MAZUMDER | 9 | 0 | 100
585 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000093/2023-2024 | 196/BD-I/26 | 09/02/2024 | 0 | Resource Division | 3.7 | 0 | 0
586 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Bali Zone-III" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-57.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000030/2024-2025 | 993/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 165.61 | 0 | 0
587 | Berhampore Division I | Berhampur Division I | Augmentation of Bali Zone-III Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000255/2023-2024 | 972/BD-I | 18/10/2023 | 532 | BISWAJYOTI BHATTACHARYYA | 322.8 | 104.56 | 95
588 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-III Water Supply Scheme, under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000324/2024-2025 | 271/BD-I | 11/02/2025 | 239 | M/S MUKTI CONSTRUCTION | 8.55 | 0 | 90
589 | Berhampore Division I | Berhampur Division I | BALI ZONE-III PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000447/2023-2024 | 450/BD-I | 15/03/2024 | 338 | ANUPA ENTERPRISE | 21.03 | 3.84 | 100
590 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000057/2023-2024 | 196/BD-I/19 | 09/02/2024 | 0 | Resource Division | 18.26 | 0 | 0
591 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Kazipara Zone_I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000121/2023-2024 | 505/BD-I | 24/07/2023 | 180 | M/S S.DAS & ENTERPRISE | 178 | 0 | 10
592 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000280/2022-2023 | 1764/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.74 | 2.74 | 100
593 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000014/2023-2024 | 61/BD-1/12 | 27/04/2023 | 0 | Resource Division | 35.26 | 0 | 0
594 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
595 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Swaruppur (Village code 315505) under Lochanmati (Zone-E) Water Supply Scheme of Central Sector Part-II in Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-10) | Assistant Engineer-II | Junior Engineer-II | ORD/000498/2021-2022 | 1905/BD-I | 08/10/2021 | 180 | M/S RUBIET HOSSAIN | 144.19 | 0 | 0
596 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lochanmati Dangapara (village code 315498) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000729/2021-2022 | 2201/BD-I | 10/12/2021 | 90 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 85.79 | 81.81 | 1
597 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sankarpur (village code 315489) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000730/2021-2022 | 2202/BD-I | 10/12/2021 | 689 | UTTAM MUKHERJEE | 76.01 | 65.33 | 87
598 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur Ramna (village code 315497) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000731/2021-2022 | 153/BD-I | 11/02/2022 | 70 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 59.15 | 41.11 | 1
599 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Siddhi Nandi (village code 315504) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000732/2021-2022 | 241/BD-I | 03/03/2022 | 45 | PRANAB KUMAR GHOSH | 36.64 | 30.74 | 85
600 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kaludiar (village code 315501) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000733/2021-2022 | 154/BD-I | 11/02/2022 | 45 | MUNNA AGROTECH ENTERPRISE | 34.19 | 0 | 0
601 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekona (village code 315492) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000734/2021-2022 | 186/BD-I | 18/02/2022 | 1279 | DAS ENTERPRISE | 32.28 | 0 | 70
602 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramkrishnapur (village code 315490) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000736/2021-2022 | 2251/BD-I | 21/12/2021 | 45 | S DUTTA | 28.82 | 0 | 0
603 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sundalpur (village code 315502) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000737/2021-2022 | 2204/BD-I | 10/12/2021 | 30 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 24.6 | 22.86 | 1
604 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khamarbati (village code 315494) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000738/2021-2022 | 2253/BD-I | 21/12/2021 | 30 | RAJEN DAS | 24.27 | 22.02 | 1
605 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur (village code 315496) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000739/2021-2022 | 2304/BD-I | 28/12/2021 | 30 | SUKUMAR ROY | 22.73 | 21.68 | 1
606 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janarddanpur (village code 315493) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000740/2021-2022 | 155/BD-I | 11/02/2022 | 30 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 10.56 | 10.17 | 1
607 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha (village code 315503) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000741/2021-2022 | 242/BD-I | 03/03/2022 | 20 | ANKITA ENTERPRISE | 4.64 | 3.4 | 1
608 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamlabad (village code 315495) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000742/2021-2022 | 156/BD-I | 11/02/2022 | 20 | U.S BUILDERS | 7.58 | 5.6 | 1
609 | Berhampore Division I | Berhampur Division I | KHAGJANA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000011/2023-2024 | 93/BD-I | 03/05/2023 | 1079 | S.K ENTERPRISE (RANITALA) | 290.8 | 135.76 | 75
610 | Berhampore Division I | Berhampur Division I | KHAGJANA PWSS to accommodate FHTC, Laying Distribution System,, under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000040/2023-2024 | 118/BD-I | 11/05/2023 | 180 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 96.97 | 32.53 | 50
611 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAGJANA and Adjoining Mouzas PWSS (TW - II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division - I, P.H.Engineering Dte. (01 No TW). | Assistant Engineer-I | JE,Junior engineer-III | ORD/000047/2025-2026 | 754/BD-I | 22/05/2025 | 15 | AJOY GHOSH | 9.01 | 0 | 0
612 | Berhampore Division I | Berhampur Division I | KHAGJANA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000100/2023-2024 | 218/BD-I | 17/05/2023 | 630 | S.K ENTERPRISE (RANITALA) | 53.17 | 7.81 | 65
613 | Berhampore Division I | Berhampur Division I | Allied work of Laying of Distribution system for the work of Khagjana PWSS to accommodate FHTC, OHR, Laying distribution system, Rising Main under Jal Jeevan Mission of Bhagwangola- II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (Part-A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000165/2024-2025 | 1684/BD-I | 28/10/2024 | 155 | S.K ENTERPRISE (RANITALA) | 68.11 | 0 | 96
614 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000027/2023-2024 | 61/BD-1/18 | 27/04/2023 | 0 | Resource Division | 11.87 | 0 | 0
615 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Arazi Saikuli under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000063/2023-2024 | 160/BD-I | 15/05/2023 | 90 | ABA CONTRACTOR | 28.97 | 0 | 0
616 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Paschim Gobindapur under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000068/2023-2024 | 739/BD-I | 17/08/2023 | 90 | M/S MODERN CONSTRUCTION AND CO | 23.95 | 0 | 0
617 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Bilgobra under Bhagwangola-I block of Murshidabad district under Berhampore division-I,P.H.E Dte | Assistant Engineer-I | JE,Junior engineer-III | ORD/000079/2023-2024 | 185/BD-I | 17/05/2023 | 90 | BIJOY SINGHA | 26.73 | 0 | 0
618 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gobindrapur" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-34 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000036/2024-2025 | 997/BD-I | 20/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 146.58 | 0 | 0
619 | Berhampore Division I | Berhampur Division I | GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000045/2023-2024 | 142/BD-I | 15/05/2023 | 1047 | DEBASISH SARKAR | 73.41 | 10.51 | 30
620 | Berhampore Division I | Berhampur Division I | GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Berhampore Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000101/2023-2024 | 219/BD-I | 17/05/2023 | 716 | AZAD CONSTRUCTION & CO. | 40.55 | 11.5 | 90
621 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GOBINDAPUR Water Supply Scheme(TW -II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000294/2024-2025 | 100/BD-I | 20/01/2025 | 180 | SUJIT KUMAR SAHA | 9.01 | 0 | 100
622 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000025/2024-2025 | 2096/BD-I/6 | 25/11/2024 | 0 | Resource Division | 4.65 | 0 | 0
623 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000031/2023-2024 | 61/BD-1/14 | 27/04/2023 | 0 | Resource Division | 17.81 | 0 | 0
624 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KISMATTATLA and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW). | Assistant Engineer-I | JE,Junior engineer-III | ORD/000061/2025-2026 | 773/BD-I | 22/05/2025 | 15 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 9.01 | 0 | 0
625 | Berhampore Division I | Berhampur Division I | KISMATTATLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000093/2023-2024 | 215/BD-I | 17/05/2023 | 990 | RUDRA NARAYAN GHOSH | 40.74 | 0 | 25
626 | Berhampore Division I | Berhampur Division I | KISMATTATLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. [ 2ND Call for WBPHED/EE/BD-I/NIeT-30 of 2022 ¿ 2023 (sl no-02)] | Assistant Engineer-I | JE,Junior engineer-III | ORD/000125/2023-2024 | 514/BD-I | 25/07/2023 | 930 | U TURN CONSTRUCTION | 172.1 | 32.42 | 15
627 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000024/2023-2024 | 61/BD-1/24 | 27/04/2023 | 0 | Resource Division | 7.05 | 0 | 0
628 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur Zone-III under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000090/2023-2024 | 168/BD-I | 16/05/2023 | 90 | CHAND ENTERPRISE | 24.78 | 0 | 0
629 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of BHAGWANGOLA PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000006/2025-2026 | 593/BD-I | 22/04/2025 | 180 | AMAN CONSTRUCTION | 15.2 | 0 | 82
630 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHAGWANGOLA PWSS(TW-I&II) under Jal Jeevan Mission in Bhagwangola-I Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000018/2025-2026 | 617/BD-I | 23/04/2025 | 30 | JOY HIND TUBEWELLS | 17.99 | 0 | 0
631 | Berhampore Division I | Berhampur Division I | BHAGWANGOLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000091/2023-2024 | 213/BD-I | 17/05/2023 | 90 | ARJIMA CONSTRUCTION | 39.48 | 0 | 0
632 | Berhampore Division I | Berhampur Division I | BHAGWANGOLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000115/2023-2024 | 377/BD-I | 28/06/2023 | 280 | S.D PROJECT | 160.98 | 0 | 0
633 | Berhampore Division I | Berhampur Division I | BHAGWANGOLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of BHAGWANGOLA -I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000269/2023-2024 | 974/BD-I | 18/10/2023 | 280 | GIRIDHARI SAHA | 359.56 | 0 | 0
634 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000046/2023-2024 | 61/BD-1/27 | 27/04/2023 | 0 | Resource Division | 13.43 | 0 | 0
635 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Romnapara (Village code 314496) under Romnapara Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 ¿ 2021,SL-11). | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000242/2020-2021 | 75/BD-I | 19/01/2021 | 20 | MAA CONSTRUCTION | 12.9 | 16.68 | 0
636 | Berhampore Division I | Berhampur Division I | Additional Laying works at villages to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Ramnapara Ground water supply scheme (Bhagwangola-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000782/2021-2022 | 2297/BD-I | 28/12/2021 | 15 | MS BAPPA ENTERPRISE | 6.01 | 5 | 0
637 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR and Adjoining Mouzas PWSS (TW- I, II, III & IV Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (04 Nos TW) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000062/2025-2026 | 774/BD-I | 22/05/2025 | 45 | SARKAR WATER SUPPLY AGENCY | 36.02 | 0 | 0
638 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000182/2023-2024 | 698/BD-I | 11/08/2023 | 180 | JAHANGIR ALAM | 263.59 | 0 | 0
639 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000183/2023-2024 | 701/BD-I | 11/08/2023 | 900 | RAJ KUMAR MONDAL | 193.43 | 0 | 5
640 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 750 cum) under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000202/2023-2024 | 846/BD-I | 05/09/2023 | 310 | JAHANGIR ALAM | 466.95 | 0 | 0
641 | Berhampore Division I | Berhampur M/E Division | NASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000340/2023-2024 | 1254/BD-I | 22/12/2023 | 90 | MASOOM TRADERS | 56.23 | 3.94 | 25
642 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000101/2023-2024 | 201/BD-1/5 | 10/02/2024 | 0 | Resource Division | 86.32 | 0 | 0
643 | Berhampore Division I | Berhampur M/E Division | Augmentation of Ramnachandpur Zone-II Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Swapna in Nawda Block of Murshidabad District under Berhampore Division-I, PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000130/2023-2024 | 608/BD-I | 02/08/2023 | 1117 | KAMIRUL SK AND CO. | 583.11 | 257.76 | 80
644 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000190/2023-2024 | 538/BD-I | 27/07/2023 | 10 | TECHVISION | 2.87 | 2.87 | 100
645 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000105/2023-2024 | 201/BD-1/6 | 10/02/2024 | 0 | Resource Division | 48.66 | 0 | 0
646 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000130/2024-2025 | 1529/BD-I | 19/09/2024 | 30 | M/S. THE LOTUS ENTERPRISE | 5.12 | 0 | 0
647 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarpakhia (Village code 314194) under Rajarampur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-I | JE | ORD/000275/2021-2022 | 1168/BD-I | 15/07/2021 | 30 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 21.65 | 19.52 | 1
648 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Sarpakhia( Village code-314194) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Rajarampur Ground water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000873/2021-2022 | 243/BD-I | 03/03/2022 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 4.9 | 3.81 | 1
649 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Makimnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000065/2024-2025 | 1198/BD-I | 26/07/2024 | 60 | BURIMAA CONSTRUCTION | 12.74 | 0 | 0
650 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mokimnagar (Village code 314172) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000203/2020-2021 | 969/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 40.85 | 23.23 | 1
651 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Simulia (Village code 314155) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000204/2020-2021 | 970/BD-I | 17/12/2020 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 6.79 | 5.24 | 1
652 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mridapur(Village code 314157) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000205/2020-2021 | 971/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 33.94 | 28.8 | 1
653 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasbagoas (Village code 314795) under Kasbagoas Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000264/2020-2021 | 338/BD-I | 24/02/2021 | 120 | DOBAY CONSTRUCTION | 81.22 | 95.58 | 0
654 | Berhampore Division I | Raghunathganj Sub-Division | Additional Laying works at village Kasbagoas (Village code-314795) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Kasbagoas Ground water based Water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer | Junior Engineer-II | ORD/000796/2021-2022 | 2312/BD-I | 29/12/2021 | 45 | BENOY DOBEY | 14.34 | 0 | 0
655 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of NAOAPUKURIA (village code 315617), under NAOAPUKURIA (Zone-K) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000039/2023-2024 | 104/BD-I | 04/05/2023 | 120 | RAJ KUMAR MONDAL | 179.66 | 0 | 0
656 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000099/2024-2025 | 1441/BD-I | 04/09/2024 | 362 | A.P CONSTRUCTION | 27.91 | 0 | 70
657 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasba Bahadurpur (Village code 314488) , under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000101/2020-2021 | 167/BD-I | 03/02/2021 | 728 | M/S SINHA & SONS | 95.89 | 116.96 | 1
658 | Berhampore Division I | Berhampur Division I | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under KASBA BAHADURPUR ground Water based Water Supply Scheme of Bhagawangola-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000273/2023-2024 | 977/BD-I | 18/10/2023 | 90 | NAMDAR ALI | 15.83 | 0 | 0
659 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Basantapur(Village code 314446),Lalitakuri(Village code 314449) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000107/2020-2021 | 173/BD-I | 03/02/2021 | 30 | DECON INDIA | 76.45 | 32.65 | 1
660 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000132/2024-2025 | 1530/BD-I | 19/09/2024 | 60 | HAFIZUL SEIKH | 17.26 | 0 | 0
661 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area of Gobra ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000160/2024-2025 | 1663/BD-I | 25/10/2024 | 30 | LAKSHMI IRON | 16.77 | 0 | 0
662 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chengta (Village code 314463) under Gobra Ground Water based Water Supply Scheme for Bhagawangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000185/2020-2021 | 919/BD-I | 10/12/2020 | 60 | PRATICHI ENTERPRISE | 10.11 | 15.22 | 100
663 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagobra (Village code 314461) under Gobra Ground Water based Water Supply Scheme for Bhagawangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000187/2020-2021 | 920/BD-I | 10/12/2020 | 60 | SHIBAM ENTERPRISE THAKURPARA VILL BHAKURI CHALTIA | 11.5 | 18.33 | 0
664 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobra (Village code 314470) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000236/2020-2021 | 65/BD-I | 18/01/2021 | 30 | DECON INDIA | 44.55 | 43.75 | 100
665 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kulberia (Village code 315685) under Andulberia Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | Assistant Engineer-II | Junior Engineer-II | ORD/000113/2020-2021 | 185/BD-I | 04/02/2021 | 20 | HANNAN BUILDERS PVT. LTD. | 43.67 | 31.27 | 0
666 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ganespur (Village Code-314215) under Bajipur Madhupur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000111/2021-2022 | 913/BD-I | 19/05/2021 | 7 | SHIBAM ENTERPRISE | 4.81 | 4.24 | 1
667 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jot Bhikan (Village code 314211) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000228/2020-2021 | 992/BD-I | 17/12/2020 | 90 | SANJAY BISWAS | 26.93 | 10.91 | 1
668 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ganespur (Village code 314215) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000229/2020-2021 | 993/BD-I | 17/12/2020 | 90 | M/S. NIRAPADA BHATTACHARJEE | 29.45 | 37.64 | 1
669 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Molladanga (Village code 314558) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000121/2020-2021 | 193/BD-I | 04/02/2021 | 30 | NIRMAL UDYOG | 50.18 | 65.92 | 1
670 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (village code 314757) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000240/2021-2022 | 1850/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.18 | 43.74 | 1
671 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamalpur (village code 314778) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000241/2021-2022 | 1851/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.73 | 30.24 | 1
672 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bishnupur (Village code 314780) under Bishnupur Ground Water Supply Scheme of Raninagar I Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-16) | Assistant Engineer | Junior Engineer-II | ORD/000451/2021-2022 | 1884/BD-I | 07/10/2021 | 180 | M/S NAYLA CONSTRUCTION | 98.17 | 83.62 | 1
673 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-II | RTOR000014/2021-2022 | 141/BD-I | 10/02/2022 | 0 | Resource Division | 5.82 | 0 | 0
674 | Berhampore Division I | Berhampur Division I | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of GOBRA PWSS under Jal Jeevan Mission within Bhagwangola-I interconnection with Augmentation under Berhampore Division-I, P.H.E. Dte. In the districtof Murshidabad.. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000053/2025-2026 | 762/BD-I | 22/05/2025 | 30 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 9.68 | 0 | 0
675 | Berhampore Division I | Berhampur Division I | Augmentation of GOBRA Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road,laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000194/2023-2024 | 745/BD-I | 17/08/2023 | 715 | DAS TRADING CO | 315.08 | 16.72 | 21
676 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after successful completion of 3 (Three) months Trial Run of "Augmentation of Gobra ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000333/2024-2025 | 286/BD-I | 12/02/2025 | 300 | MODERN CONSTRUCTION | 122.8 | 0 | 0
677 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOBRA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000882/2021-2022 | 266/ BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.71 | 2.61 | 1
678 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000065/2023-2024 | 196/BD-I/12 | 09/02/2024 | 0 | Resource Division | 3.11 | 0 | 0
679 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Jhikra ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000112/2022-2023 | 1365/BD-I | 21/12/2022 | 30 | AZAD ENTERPRISE | 2.41 | 2.37 | 100
680 | Berhampore Division I | Berhampur Division I | Augmentation of JHIKRA Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000202/2022-2023 | 1615/BD-I | 02/03/2023 | 310 | KAMIRUL SK AND CO. | 418.14 | 68.93 | 35
681 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jhikra Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000283/2022-2023 | 1806/BD-I | 31/03/2023 | 30 | SUJIT KUMAR SAHA | 8.99 | 0 | 100
682 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JHIKRA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000888/2021-2022 | 271//BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.75 | 2.75 | 100
683 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000053/2023-2024 | 196/BD-I/5 | 09/02/2024 | 0 | Resource Division | 5.7 | 0 | 0
684 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of Benipur Piped water supply scheme to accommodate construction of OHR, toilet, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000138/2022-2023 | 1448/BD-I | 17/01/2023 | 1000 | KAMIRUL SK AND CO. | 472.43 | 66.33 | 40
685 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BENIPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000174/2022-2023 | 1076/BD-I | 29/09/2022 | 10 | NATSOL CONSULTANT | 2.92 | 2.92 | 0
686 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Benipur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000286/2022-2023 | 1810/BD-I | 31/03/2023 | 898 | SUJIT KUMAR SAHA | 18.01 | 6.42 | 100
687 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Benipur ground water supply scheme in Bhagwabgola-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000367/2024-2025 | 327/BD-I | 25/02/2025 | 300 | J.S. CONSTRUCTION | 122.8 | 0 | 0
688 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000001/2023-2024 | 61/BD-1/3 | 27/04/2023 | 0 | Resource Division | 36.06 | 0 | 0
689 | Berhampore Division I | Raghunathganj Sub-Division | Formal work order for Augmentation of Bishnupur Zone-II Piped water supply scheme to accommodate construction of Pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000178/2022-2023 | 1541/BD-I | 16/02/2023 | 925 | NATIONAL CONSTRUCTION | 190.09 | 181.89 | 95
690 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BISHNUPUR ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000270/2022-2023 | 1761/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
691 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000021/2023-2024 | 194/BD-I/6 | 09/02/2024 | 0 | Resource Division | 42.69 | 0 | 0
692 | Berhampore Division I | Berhampur Division I | Replacement of Filter media of Existing AIRP of (Capacity 87 Cum/hr.) with allied work at Charkamnagar Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000010/2024-2025 | 905/BD-I | 07/06/2024 | 30 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 29.25 | 0 | 0
693 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd Tube Well Site of CHARKAMNAGAR ZONE-I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000039/2025-2026 | 672/BD-I | 29/04/2025 | 45 | JAMUNA CONSTRUCTION | 10.18 | 0 | 0
694 | Berhampore Division I | Berhampur Division I | Augmentation of Charkamnagar Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000157/2023-2024 | 681/BD-I | 10/08/2023 | 990 | MERCURY ENGINEERING COMPANY | 418.24 | 0 | 7
695 | Berhampore Division I | Berhampur Division I | Allied work for Laying of distribution pipeline of CHARKAMNAGAR and allied works within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000179/2024-2025 | 2122/BD-I | 27/11/2024 | 45 | NOVELTY CONSTRUCTION | 46.47 | 0 | 0
696 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for CHARKAMNAGAR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000234/2022-2023 | 1592/BD-I | 28/02/2023 | 10 | TECHVISION | 2.74 | 2.74 | 0
697 | Berhampore Division I | Berhampur Division I | Bored Cast-in-situ_ M30 _ grade 500 mm dia. R.C.C. pile for Construction of OHR at Head Work site of CHARKAMNAGAR Ground Piped Water Supply Scheme under Jal Jeevan Mission within Beldanga - II Block under Berhampore Division-I, PHE.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000332/2024-2025 | 279/BD-I | 12/02/2025 | 30 | MERCURY ENGINEERING COMPANY | 25.63 | 0 | 0
698 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000084/2023-2024 | 196/BD-I/20 | 09/02/2024 | 0 | Resource Division | 77.09 | 0 | 0
699 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Ramnagar Doemkanon Zone-I (Part-B) PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000054/2024-2025 | 1120/BD-I | 11/07/2024 | 60 | S.K ENTERPRISE (RANITALA) | 7.92 | 0 | 0
700 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Ramnagar Doemkanun Zone-I (Part-B) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000073/2025-2026 | 840/BD-I | 23/06/2025 | 60 | PRADIP MAHATO | 19 | 0 | 0
701 | Berhampore Division I | Raghunathganj Sub-Division | RAMNAGAR DOEMKANUN ZONE-I PART-B PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000137/2024-2025 | 1552/BD-I | 24/09/2024 | 60 | M/S B.M. INDUSTRIES | 20.64 | 0 | 0
702 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Ramnagar Doemkanun Zone-I(Part-B) Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000179/2023-2024 | 695/BD-I | 11/08/2023 | 627 | M/S SINHA & SONS | 408.86 | 0 | 25
703 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000010/2023-2024 | 61/BD-1/9 | 27/04/2023 | 0 | Resource Division | 57.59 | 0 | 0
704 | Berhampore Division I | Raghunathganj Sub-Division | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Ramnagar Domkanun Zone-I Part-A of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000003/2024-2025 | 891/BD-I | 06/06/2024 | 30 | PRAVAT KUMAR GHOSH | 8.66 | 6.89 | 100
705 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Ramnagar Doemkanun Zone- I(Part-A) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000087/2025-2026 | 876/BD-I | 01/07/2025 | 60 | BISWAS CONSTRUCTION | 18.97 | 0 | 0
706 | Berhampore Division I | Raghunathganj Sub-Division | Allied work for Laying of Distribution pipeline of Ramnagar Doemkanon Zone - I PWSS within Raninagar - II Block under JJM of Murshidabad district under Berhampore Division - I P.H.Engg Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000123/2024-2025 | 1471/BD-I | 06/09/2024 | 225 | MAA CONSTRUCTION | 26.47 | 0 | 85
707 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000196/2022-2023 | 1379/BD-I | 22/12/2022 | 10 | RADIANT | 2.94 | 2.85 | 100
708 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of RamnagarDoemkanun Zone_I (Part-A)Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000243/2022-2023 | 1613/BD-I | 02/03/2023 | 1080 | SUJIT KUMAR SAHA | 249.53 | 195.75 | 85
709 | Berhampore Division I | Raghunathganj Sub-Division | Construction Pump House Cum Chlorine Room at RAMNAGAR DOEMKANUN ZONE-I Water Supply Scheme under Jal Jevan Mission within Raninagar-II Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000326/2024-2025 | 273/BD-I | 11/02/2025 | 60 | TAIMUR SK | 7.5 | 0 | 0
710 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000037/2023-2024 | 61/BD-1/25 | 27/04/2023 | 0 | Resource Division | 29.78 | 0 | 0
711 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bajipur Madhupur Zone-II Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(Part-B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000123/2023-2024 | 508/BD-I | 24/07/2023 | 800 | H.I ENTERPRISE | 340.79 | 0 | 44
712 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bajipur Madhupur Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000181/2023-2024 | 697/BD-I | 11/08/2023 | 310 | UNIVERSE UNEMPLOYED ENGINEERS CONSTRUCTION CO. | 335.43 | 0 | 0
713 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000205/2022-2023 | 1383/BD-I | 23/12/2022 | 10 | ENVIROTECH SOLUTIONS | 2.87 | 2.9 | 1
714 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (450 Cum) for Bajupur Madhupur Zone-II water supply scheme of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000359/2023-2024 | 15/BD-I | 04/01/2024 | 330 | MAA SANKARI ENTERPRISE | 8.61 | 0 | 100
715 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000014/2024-2025 | 1510/BD-I/8 | 12/09/2024 | 0 | Resource Division | 9.8 | 0 | 0
716 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000076/2023-2024 | 201/BD-1/17 | 10/02/2024 | 0 | Resource Division | 280.69 | 0 | 0
717 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000004/2023-2024 | 40/BD-I | 20/04/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100
718 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-I" ground water supply scheme in NAWDA Block, under Berhampore Division-I, P.H.E Dte(Capacity-98.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000038/2024-2025 | 1037/BD-I | 28/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 234.01 | 0 | 0
719 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000192/2022-2023 | 1320/BD-I | 13/12/2022 | 10 | TECHVISION | 2.81 | 2.81 | 0
720 | Berhampore Division I | Berhampur Division I | Augmentation of Ramnachandpur Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | ORD/000250/2022-2023 | 1655/BD-I | 13/03/2023 | 752 | SOFIQUL ISLAM | 371.52 | 316.8 | 95
721 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-II | RTOR000056/2023-2024 | 196/BD-I/18 | 09/02/2024 | 0 | Resource Division | 7.99 | 0 | 0
722 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000003/2023-2024 | 32/BD-I | 19/04/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100
723 | Berhampore Division I | Berhampur Division I | Allied works for upgradation,Improvement and laying of Augmentation of Bali Zone-II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000172/2024-2025 | 2037/BD-I | 12/11/2024 | 360 | S.D PROJECT | 55.74 | 0 | 60
724 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000238/2022-2023 | 1596/BD-I | 28/02/2023 | 10 | TECHVISION | 2.81 | 2.81 | 0
725 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-II Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000299/2024-2025 | 148/BD-I | 29/01/2025 | 60 | SUPRIYA DEY | 8.77 | 0 | 60
726 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000085/2023-2024 | 1156/BD-I | 05/12/2023 | 0 | Resource Division | 47.43 | 0 | 0
727 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augmentation of Lochanpur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000055/2024-2025 | 1125/BD-I | 11/07/2024 | 60 | KHANDAKAR CONSTRUCTION | 8.19 | 0 | 0
728 | Berhampore Division I | Raghunathganj Sub-Division | LOCHANPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000060/2024-2025 | 1175/BD-I | 25/07/2024 | 60 | DEBJIT DAS | 21.57 | 0 | 0
729 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Lochanpur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000090/2025-2026 | 950/BD-I | 18/07/2025 | 300 | HARBAUER INDIA (P) LTD. | 122.79 | 0 | 0
730 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Lochanpur Zone-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar -I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000180/2023-2024 | 696/BD-I | 11/08/2023 | 310 | ARABINDA GHOSH | 323.45 | 69.64 | 10
731 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for LOCHANPUR ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000271/2022-2023 | 1762/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
732 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000008/2023-2024 | 61/BD-1/2 | 27/04/2023 | 0 | Resource Division | 29.7 | 0 | 0
733 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Kathalia (Part-A) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000076/2023-2024 | 182/BD-I | 17/05/2023 | 910 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 28.45 | 0 | 82
734 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Kathalia (Part-B) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000077/2023-2024 | 183/BD-I | 17/05/2023 | 90 | PRADIP DAS | 28.45 | 0 | 60
735 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Kathalia (Part-C) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000078/2023-2024 | 184/BD-I | 17/05/2023 | 90 | GOUTAM KUMAR CHAUDHURI | 28.32 | 0 | 0
736 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur (Part-A) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000067/2023-2024 | 165/BD-I | 16/05/2023 | 822 | MAHATO ENTERPRISE | 28.44 | 0 | 80
737 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur (Part-B) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000069/2023-2024 | 166/BD-I | 16/05/2023 | 90 | DEBJYOTI MUKHERJEE | 27.91 | 0 | 0
738 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000046/2023-2024 | 145/BD-I | 15/05/2023 | 822 | RAWSHAN FOUNDATION | 30.49 | 0 | 80
739 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chandabag under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000065/2023-2024 | 162/BD-I | 16/05/2023 | 90 | PRAVAT KUMAR GHOSH | 24.63 | 0 | 0
740 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Hallalpur Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000094/2023-2024 | 169/BD-I | 16/05/2023 | 90 | SAMRAT MAZUMDAR | 30.5 | 0 | 0
741 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Hallalpur Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000096/2023-2024 | 170/BD-I | 16/05/2023 | 90 | M/S. MONDAL ENTERPRISE 12/6/1, OLD POLICE LINE ROAD, GORABAZAR | 30.49 | 0 | 0
742 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-II under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000053/2023-2024 | 149/BD-I | 15/05/2023 | 90 | DHRITIPALI | 30.23 | 0 | 0
743 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Kuchiadanga under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000055/2023-2024 | 152/BD-I | 15/05/2023 | 90 | ANUPA ENTERPRISE | 22.59 | 0 | 0
744 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Katalia" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-36 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | ORD/000037/2024-2025 | 1000/BD-I | 20/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 147.9 | 0 | 0
745 | Berhampore Division I | Berhampur Division I | KATALIA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | ORD/000103/2023-2024 | 221/BD-I | 17/05/2023 | 865 | NURUL HASAN BISWAS | 52.76 | 0 | 66
746 | Berhampore Division I | Berhampur Division I | KATALIA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | ORD/000160/2023-2024 | 685/BD-I | 10/08/2023 | 870 | C.X.CONSTRUCTION & CO. | 259.02 | 13.63 | 30
747 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | RTOR000026/2023-2024 | 61/BD-1/20 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
748 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-II | RTOR000026/2024-2025 | 2096/BD-I/7 | 25/11/2024 | 0 | Resource Division | 8.46 | 0 | 0
749 | Berhampore Division I | Berhampur Division I | KULGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000089/2023-2024 | 212/BD-I | 17/05/2023 | 630 | NATIONAL CONSTRUCTION | 36.84 | 19.95 | 85
750 | Berhampore Division I | Berhampur Division I | KULGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000098/2023-2024 | 111/BD-I | 10/05/2023 | 963 | RAJ KUMAR MONDAL | 251.46 | 101.19 | 20
751 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000045/2023-2024 | 61/BD-1/29 | 27/04/2023 | 0 | Resource Division | 12.73 | 0 | 0
752 | Berhampore Division I | Berhampur M/E Division | KESABPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000081/2023-2024 | 199/BD-I | 17/05/2023 | 951 | AZAD ENTERPRISE | 40.95 | 17.52 | 20
753 | Berhampore Division I | Berhampur M/E Division | KESABPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main , Construction of OHR (Capacity - 200 cum ) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000172/2023-2024 | 664/BD-I | 09/08/2023 | 784 | D.N SARKAR AND SONS | 294.7 | 130.11 | 30
754 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000043/2023-2024 | 61/BD-1/31 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
755 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000111/2023-2024 | 304/BD-1/2 | 22/02/2024 | 0 | Resource Division | 7.74 | 0 | 0
756 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000118/2023-2024 | 512/BD-I | 25/07/2023 | 885 | SRIJON ENTERPRISE | 244.14 | 0 | 30
757 | Berhampore Division I | Berhampur M/E Division | Designing, making and errection of Display Board for Scheme information by using Logo and tag line of Jal Jeevan Mission at different PWSS work sites in the district of Murshidabad under Berhampore Division-I, PHE Dte. (Block :- Raninagar - I, Raninagar - II, Beldanga - I, Beldanga - II, Jalangi & Nowda) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000134/2024-2025 | 1532/BD-I | 19/09/2024 | 30 | SUMAN ENTERPRISE AND SUMAN AQUA | 18.91 | 10.11 | 54
758 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000137/2023-2024 | 620/BD-I | 03/08/2023 | 548 | RAJEN DAS | 55.72 | 11.76 | 50
759 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000147/2023-2024 | 634/BD-I | 04/08/2023 | 1095 | M/S GHOSH AND CO | 383.82 | 0 | 50
760 | Berhampore Division I | Berhampur M/E Division | BAYRA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000341/2023-2024 | 1255/BD-I | 22/12/2023 | 445 | MASOOM TRADERS | 61.36 | 4.85 | 30
761 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAYRA PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000378/2024-2025 | 438/BD-I | 20/03/2025 | 30 | HARUN ALL RASHID & BROTHERS | 17.97 | 0 | 0
762 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000097/2023-2024 | 201/BD-1/26 | 10/02/2024 | 0 | Resource Division | 39.6 | 0 | 0
763 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000109/2023-2024 | 304/BD-1/6 | 22/02/2024 | 0 | Resource Division | 24.04 | 0 | 0
764 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000144/2023-2024 | 631/BD-I | 04/08/2023 | 970 | H.I ENTERPRISE | 440.19 | 188.98 | 17
765 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000145/2023-2024 | 632/BD-I | 04/08/2023 | 720 | SRIJON ENTERPRISE | 240.5 | 148.76 | 15
766 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000146/2023-2024 | 633/BD-I | 04/08/2023 | 180 | NIRMAL UDYOG | 116.86 | 25.85 | 20
767 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PAIKPARA Water Supply Scheme(2nd & 3rd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000328/2024-2025 | 274/BD-I | 11/02/2025 | 30 | NADIA TUBEWELLS | 17.99 | 0 | 0
768 | Berhampore Division I | Berhampur M/E Division | PAIKPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000342/2023-2024 | 1256/BD-I | 22/12/2023 | 90 | SATELLITE CONSTRUCTION | 67.11 | 0 | 0
769 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000099/2023-2024 | 201/BD-1/28 | 10/02/2024 | 0 | Resource Division | 66.86 | 0 | 0
770 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000113/2023-2024 | 304/BD-1/3 | 22/02/2024 | 0 | Resource Division | 27.92 | 0 | 0
771 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000009/2025-2026 | 596/BD-I | 22/04/2025 | 60 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 19 | 0 | 0
772 | Berhampore Division I | Berhampur M/E Division | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Palitpara" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-111 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000034/2024-2025 | 998/BD-I | 20/06/2024 | 730 | M/S GOUTAM CHAKRABORTY | 257.77 | 0 | 0
773 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000037/2025-2026 | 666/BD-I | 29/04/2025 | 60 | INDIAN TRADING CORPORATION | 19 | 0 | 0
774 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000173/2023-2024 | 686/BD-I | 10/08/2023 | 730 | SUJIT KUMAR SAHA | 401.71 | 91.16 | 55
775 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000174/2023-2024 | 687/BD-I | 10/08/2023 | 180 | BANIK BROTHERS | 89.01 | 0 | 0
776 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000178/2023-2024 | 688/BD-I | 10/08/2023 | 180 | M/S AMIT KUMAR GUPTA | 167.04 | 0 | 0
777 | Berhampore Division I | Berhampur M/E Division | PALITPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000188/2023-2024 | 736/BD-I | 16/08/2023 | 716 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 72.82 | 12.05 | 40
778 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000022/2024-2025 | 2096/BD-I/3 | 25/11/2024 | 0 | Resource Division | 27.02 | 0 | 0
779 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000103/2023-2024 | 201/BD-1/2 | 10/02/2024 | 0 | Resource Division | 56.21 | 0 | 0
780 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahebnagar (village code 314609) under KAZIPARA (Part-A) Ground water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000747/2021-2022 | 2207/BD-I | 10/12/2021 | 90 | SRIJON ENTERPRISE | 61.97 | 0 | 0
781 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara Foridpur (Village code 315664) under Rampara Foridpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-II | Junior Engineer-II | ORD/000112/2020-2021 | 184/BD-I | 04/02/2021 | 30 | DOBAY CONSTRUCTION | 98.77 | 70.91 | 1
782 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Rampara Foridpur (Village code-315664) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Rampara Foridpur Ground water based Water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-II | ORD/000794/2021-2022 | 2310/BD-I | 29/12/2021 | 45 | BENOY DOBEY | 15.18 | 0 | 0
783 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Goukhana and Others under Goukhana Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000112/2021-2022 | 914/BD-I | 19/05/2021 | 7 | N.H ENTERPRISE | 3.62 | 6.32 | 0
784 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramna Bagsarai (Village code 314160) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000190/2020-2021 | 960/BD-I | 17/12/2020 | 60 | S.ENTERPRISE | 8.24 | 0 | 0
785 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Deoan Sarai (Village code 314161) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000191/2020-2021 | 961/BD-I | 17/12/2020 | 90 | SAMBHUNATH ROY | 30.8 | 30.75 | 1
786 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gaukhana (Village code 314162) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000192/2020-2021 | 972/BD-I | 17/12/2020 | 60 | N.H ENTERPRISE | 12.91 | 18.53 | 100
787 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Laskarpur (Village code 314167) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000193/2020-2021 | 973/BD-I | 17/12/2020 | 60 | SUSHANTA MANDAL | 11.01 | 10.4 | 1
788 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramna Bagsarai and Others under Gaukhana Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE | ORD/000210/2020-2021 | 277/BD-I | 15/02/2021 | 10 | S.ENTERPRISE | 2.73 | 0 | 0
789 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raipur (Village code 315460) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | Assistant Engineer-II | Junior Engineer-II | ORD/000270/2021-2022 | 1141/BD-I | 07/07/2021 | 180 | M/S JOYDEEP DASGUPTA | 79 | 73.28 | 1
790 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
791 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Masurdanga ( village code 315464 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2021-2022 | 1838/BD-I | 05/10/2021 | 70 | NIRMAL UDYOG | 62.56 | 0 | 0
792 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jitarpur (village code 315461) , Harishpur (village code 315462) , Khosalpur ( village code 315463 ) , under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000465/2021-2022 | 1837/BD-I | 05/10/2021 | 70 | HOQUEDAR ALI | 61.23 | 41.59 | 1
793 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nasipur ( village code 315482 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000466/2021-2022 | 1839/BD-I | 05/10/2021 | 40 | PARTHA PRATIM DAS | 35.44 | 0 | 0
794 | Berhampore Division I | Berhampur Division I | Laying of additional extension and parallel pipe line at Mamdalipur,Raipur and Sadananpur village due to smooth functioning of Functional Household Tap Connection (FHTC) at RAIPUR Surface Water based Water Supply Scheme of Central Sector Part - II of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000494/2021-2022 | 1881/BD-I | 07/10/2021 | 90 | M/S JOYDEEP DASGUPTA | 36.18 | 32.68 | 1
795 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dasturpara (Village code 315484) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-03) | Assistant Engineer-II | Junior Engineer-II | ORD/000559/2021-2022 | 1891/BD-I | 07/10/2021 | 180 | M/S S.DAS & ENTERPRISE | 75.05 | 63.52 | 1
796 | Berhampore Division I | Berhampur Division I | Relaying of different dia DI and UPVC distribution Pipe Line instead of damage portion in between different node point for faciliating FHTC works under Raipur Surface based Water Supply Scheme under Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000561/2021-2022 | 1989/BD-I | 01/11/2021 | 30 | DEBASIS BOSE | 31.04 | 0 | 0
797 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bainpur, Balarampur, Khalshi, Saharbasa, Mamlatpur, Chhota Saharbasa, Hosenpur, Jamira, Fatepur-Gobindapur & Kumipur Patharghata (Village code 315454, 315455, 315456, 315457, 315458, 315459, 315485, 315486, 315487 & 315488) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Hariharpara Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer-II | Junior Engineer-II | ORD/000585/2021-2022 | 2012/BD-I | 08/11/2021 | 180 | SANJAY BISWAS | 130.03 | 89.24 | 85
798 | Berhampore Division I | Berhampur Division I | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Raipur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-II | Junior Engineer-II | ORD/000775/2021-2022 | 2255/BD-I | 21/12/2021 | 90 | M/S GHOSH ENTERPRISE | 77.39 | 75.21 | 1
799 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hariharpara, Bochadanga, & Gobindapur (Village code 315483, 315452 & 315453) under RAIPUR (Zone-D) Water Supply Scheme of Central Sector Part-II inHariharpara of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000845/2021-2022 | 101/BD-I | 01/02/2022 | 180 | J.D.J ENTERPRISE | 246.75 | 0 | 0
800 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000001/2021-2022 | 62/BD-I | 27/01/2022 | 0 | Resource Division | 7.67 | 0 | 0
801 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000004/2021-2022 | 70/BD-I | 28/01/2022 | 0 | Resource Division | 2.48 | 0 | 0
802 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000028/2024-2025 | 2096/BD-I/9 | 25/11/2024 | 0 | Resource Division | 24.64 | 0 | 0
803 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Digha (Village code 314460) under Digha Ground Water based Water Supply Scheme for Bhagwangola-I (Part-A) Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000096/2020-2021 | 162/BD-I | 03/02/2021 | 30 | M/S. SUKUMAR SINHA | 71.28 | 29.55 | 1
804 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of MAIA (Village code 314146) under Maia Ground Water Supply Scheme of Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000248/2020-2021 | 37/BD-I | 13/01/2021 | 180 | H.I ENTERPRISE | 158.61 | 212.9 | 1
805 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Dakhsin Gopalpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000071/2024-2025 | 1219/BD-I | 29/07/2024 | 60 | CHATTERJEE ENTERPRISE | 15.96 | 0 | 0
806 | Berhampore Division I | Raghunathganj Sub-Division | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Dakshin Gopalpur ground Water based Water Supply Scheme under Raninagar -I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000108/2023-2024 | 437/BD-I | 12/07/2023 | 90 | SOMNATH DEY | 2.32 | 1.31 | 75
807 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gajepara (Village code 314796) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000180/2020-2021 | 829/BD-I | 13/11/2020 | 60 | M/S SAJAHAN CHOWDHURY | 20.51 | 30.67 | 0
808 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of DakshinGopalpur (Village code 314797) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-06 of 2020 ¿ 2021,SL-06) | Assistant Engineer | Junior Engineer-II | ORD/000381/2021-2022 | 1465/BD-I | 16/08/2021 | 30 | DOBAY CONSTRUCTION | 44.57 | 27.2 | 1
809 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000073/2024-2025 | 1221/BD-I | 29/07/2024 | 60 | SWARUP KUMAR BHATTA | 14.97 | 0 | 0
810 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nalbatta (Village code 314801) under Kasbagoas Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-09) | Assistant Engineer | Junior Engineer-II | ORD/000425/2021-2022 | 1598/BD-I | 31/08/2021 | 180 | NOVELTY CONSTRUCTION | 58.29 | 46.21 | 1
811 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Villages Of Madhya Gobindopur (Code-314485), Maheshpur(Code-314486) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-B) Under Bhagwangola-I Block)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000077/2024-2025 | 1225/BD-I | 29/07/2024 | 60 | AZAD CONSTRUCTION & CO. | 17.71 | 0 | 100
812 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Madhya Gobindapur (Village code 314485) ,Mahespur (Village code 314486) under Bhundar Kismat Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | Assistant Engineer-I | JE | ORD/000125/2020-2021 | 201/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 63.97 | 48.54 | 1
813 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of BAUSI (Village code 314208) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000149/2020-2021 | 266/ BD-I | 12/02/2021 | 180 | M/S JOGMAYA ENTERPRISE | 62.05 | 54.25 | 100
814 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Bausi to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000843/2021-2022 | 99/BD-I | 01/02/2022 | 20 | M/S JOGMAYA ENTERPRISE | 23.01 | 20.92 | 100
815 | Berhampore Division I | Berhampur Division I | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-II | JE | ORD/000170/2022-2023 | 1385/BD-I | 23/12/2022 | 365 | SEBAYAN CONSTRUCTION | 1.81 | 3.17 | 71
816 | Berhampore Division I | Berhampur Division I | Additional Laying works at village DAKATIAPOTA( Village code-315523) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bali Zone-I Ground water supply scheme (Nawda,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-II | JE | ORD/000570/2021-2022 | 1922/BD-I | 08/10/2021 | 10 | KAMIRUL SK AND CO. | 5.29 | 5.19 | 1
817 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part-B)" Under Beldanga-II Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000105/2024-2025 | 1435/BD-I | 04/09/2024 | 30 | M/S ARIYAN ENTERPRISE | 14.6 | 0 | 0
818 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Santoshpur (Village code 315634), Chandpur (Village code 315635) under Mashimpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-II | Junior Engineer-II | ORD/000124/2020-2021 | 200/BD-I | 04/02/2021 | 20 | MD TALEB ALI | 34.35 | 0 | 0
819 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kaimegha(Village code 314221) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-D) | Assistant Engineer-I | JE | ORD/000129/2020-2021 | 205/BD-I | 04/02/2021 | 30 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 83.83 | 81.09 | 1
820 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000066/2024-2025 | 1203/BD-I | 26/07/2024 | 60 | M/S S.R.K ENTERPRISE | 31.89 | 0 | 0
821 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhundar Kismat (Village code 314468) under Bhundar Kismat Water Supply Scheme of Bhagawangola-I Block and village of Maniknagar (Village code 315606) under Maniknagar (Zone-D) Surface water based Water Supply Scheme of Beldanga-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000841/2021-2022 | 82/BD-I | 31/01/2022 | 180 | J.D.J ENTERPRISE | 248.16 | 0 | 5
822 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of NADAIPUR (Village code 314205) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000249/2020-2021 | 921/BD-I | 11/12/2020 | 1846 | H.I ENTERPRISE | 95.04 | 18.68 | 59
823 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 315210), Upar Fatepur (Village Code 314212) & Bajupur Madhupur (Village Code 314235) under Bajupur Madhupur Ground Water Supply Scheme for Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000299/2020-2021 | 994/BD-I | 17/12/2020 | 180 | BIJOY CHOWDHURY | 253.85 | 176.93 | 1
824 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | Assistant Engineer-I | JE | ORD/000797/2021-2022 | 2314/BD-I | 29/12/2021 | 45 | BIJOY CHOWDHURY | 13.36 | 10.9 | 1
825 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kashipur (Village code 315687) under Kashipur Water Supply Scheme of Beldanga II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-13) | Assistant Engineer-II | Junior Engineer-I | ORD/000453/2021-2022 | 1867/BD-I | 07/10/2021 | 180 | TEKNO ENTERPRISE | 122.6 | 107.94 | 1
826 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhikra (Village code 315688) under Kashipur Water Supply Scheme of Beldanga II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-12) | Assistant Engineer-II | Junior Engineer-I | ORD/000556/2021-2022 | 1887/BD-I | 07/10/2021 | 180 | HANNAN BUILDERS PVT. LTD. | 92.96 | 90.95 | 1
827 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Kashipur (Village code-315687) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Kashipur Ground water based Water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | Junior Engineer-I | ORD/000839/2021-2022 | 97/BD-I | 01/02/2022 | 30 | TEKNO ENTERPRISE | 9.18 | 8.98 | 100
828 | Berhampore Division I | Berhampur M/E Division | Improvement of existing AIRP(Gober Danga Model) ( Capacity - 21.0 Cum/ Hr.) of Hazi Mahammadpur Zone-II Water supply Scheme under Jal Jeevan Mission within Lalgola block under Berhampore Division - I, P.H.E Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000078/2025-2026 | 845/BD-I | 23/06/2025 | 45 | ABIDA CONSTRUCTION | 22.63 | 0 | 0
829 | Berhampore Division I | Berhampur M/E Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Hazi Mahammadpur Zone-I ground water supply scheme in Lalgola Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000088/2025-2026 | 948/BD-I | 18/07/2025 | 300 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0
830 | Berhampore Division I | Berhampur M/E Division | Augmentation of Hazi Mohammadpur Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000213/2022-2023 | 1550/BD-I | 17/02/2023 | 180 | N.H ENTERPRISE | 61.96 | 55.63 | 95
831 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000257/2022-2023 | 1679/BD-I | 14/03/2023 | 30 | TAHID SK | 2.41 | 2.37 | 100
832 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000893/2021-2022 | 278/BD-I | 08/03/2022 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.46 | 1
833 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000013/2024-2025 | 1510/BD-I/7 | 12/09/2024 | 0 | Resource Division | 2.3 | 0 | 0
834 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000073/2023-2024 | 201/BD-1/14 | 10/02/2024 | 0 | Resource Division | 21.36 | 0 | 0
835 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-II ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000119/2022-2023 | 1443/BD-I | 16/01/2023 | 10 | MIR SABNAM BEGUM | 2.37 | 2.33 | 100
836 | Berhampore Division I | Berhampur M/E Division | Augmentation of Hazi Mohammadpur Z-II Piped water supply scheme to accommodate construction of service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000191/2022-2023 | 1457/BD-I | 17/01/2023 | 180 | MODERN CONSTRUCTION | 45.93 | 39.48 | 60
837 | Berhampore Division I | Berhampur M/E Division | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Hazi Mohammadpur Zone-II of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000280/2023-2024 | 997/BD-I | 30/10/2023 | 600 | TANBEER CONSTRUCTION | 6.76 | 5 | 100
838 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000894/2021-2022 | 279/BD-I | 08/03/2022 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.45 | 1
839 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000018/2024-2025 | 1510/BD-I/12 | 12/09/2024 | 0 | Resource Division | 1.31 | 0 | 0
840 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000074/2023-2024 | 201/BD-1/15 | 10/02/2024 | 0 | Resource Division | 15.25 | 0 | 0
841 | Berhampore Division I | Berhampur Division I | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00065/2024-2025 | BP-2024-25-62 | 19/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0
842 | Berhampore Division I | Berhampur Division I | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 600 mm dia M.S Casing Pipe through 250 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station NLSF-LCAE at KM, 166-33/34-166/35/36 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00066/2024-2025 | BP-2024-25-63 | 19/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.94 | 0 | 0
843 | Berhampore Division I | Berhampur Division I | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I (for Raw Water) | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00089/2024-2025 | BP-2024-25-65 | 20/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0
844 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION NLSF-LCAE AT KM 170/27-29 & 170/28-30 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00153/2024-2025 | BP-2024-25-114 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 7.19 | 0 | 0
845 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00154/2024-2025 | BP-2024-25-115 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.32 | 0 | 0
846 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 160/13-15 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00155/2024-2025 | BP-2024-25-116 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.43 | 0 | 0
847 | Berhampore Division I | Berhampur Division I | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. (R.A-2) | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00175/2024-2025 | BP-2024-25-135 | 21/08/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 0 | 0 | 0
848 | Berhampore Division I | Berhampur Division I | HYDRAGRAPHIC SURVEY CHARGE FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART BERHAMPORE AND MURSHIDABAD JIAGANJ BLOCKS OF DISTRICT OF MURSHIDABAD | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00208/2023-2024 | BP-2023-24-127 | 15/09/2023 | 0 | SYAMA PRASAD MOOKERJEE PORT KOLKATA | 55.55 | 0 | 0
849 | Berhampore Division I | Berhampur Division I | Consultancy charges along with the work order in respect of the project title "EIA and EMP for proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad (IPBN) | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00313/2023-2024 | BP-2023-24-205 | 13/12/2023 | 0 | IIT CONSULTATIVE PRATICE | 5.52 | 0 | 0
850 | Berhampore Division I | Berhampur Division I | Second Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00800/2023-2024 | BP-2023-24-290 | 01/03/2024 | 0 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0
851 | Berhampore Division I | Berhampur Division I | Third Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | BILL/00801/2023-2024 | BP-2023-24-291 | 01/03/2024 | 0 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0
852 | Berhampore Division I | Berhampur Division I | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Monthly hire basis for official use for the Office of the Assistant Engineer-I,BD-I,PHE Dte. [Period for 03.07.2024 to 30.06.2025]. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000040/2024-2025 | 1047/BD-I | 02/07/2024 | 365 | AMAN CONSTRUCTION | 1.81 | 4.3 | 45
853 | Berhampore Division I | Berhampur Division I | Continuation Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Monthly hire basis for official use for the Office of the Assistant Engineer-I,BD-I,PHE Dte. [Period for 01.07.2025 to 31.10.2025]. [Car No-WB-58BB/0191] | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000096/2025-2026 | 858/BD-I | 30/06/2025 | 123 | AMAN CONSTRUCTION | 0.6 | 0 | 0
854 | Berhampore Division I | Berhampur Division I | SUPPLY, CARRIAGE , LAYING AND COMMISSIONING OF DISTRIBUTION PIPE NETWORK INCLUDING PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) AND PIPED WATER SUPPLY ARRANGEMENT FOR DIFFERENT SCHOOL ,SSK, MSK ETC.OF DIFFERENT DISTRIBUTION ZONES OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPUR AND MURSHIDABAD - JIAGANJ BLOCK OF MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION-I, PHE Dte. IN CONNECTION WITH JJM. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000283/2023-2024 | 983/BD-I | 30/10/2023 | 884 | WPIL LIMITED | 12076.79 | 3575.71 | 16
855 | Berhampore Division I | Berhampur Division I | Formal work order for Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and completion in all respect of all Civil, Electrical and Mechanical works like Raw Water Intake, WTP, Raw Water Rising Main, Clear Water Rising Main (CWR at WTP to different OHR sites), OHR, Chlorine cum Switch Room, Boundary Wall etc. including all allied related and enabling works for surface water based piped water supply scheme for entire NABAGRAM Block, Part of Berhampore & Murshidabad-Jiaganj Blocks of District Murshidabad followed by 6(Six) months of Trial Run and subsequent Operation & Maintenance of 5(Five) years. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000288/2022-2023 | 1802/BD-I | 31/03/2023 | 914 | GBC INFRASTRUCTURE PVIVATE LIMITED | 15290.9 | 7669.51 | 70
856 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000002/2023-2024 | 61/BD-1/36 | 27/04/2023 | 0 | Resource Division | 8607.44 | 0 | 0
857 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | RTOR000119/2023-2024 | 360/BD-1 | 05/03/2024 | 0 | Resource Division | 123.2 | 0 | 0
858 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Ramchandrapur Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000246/2022-2023 | 1651/BD-I | 13/03/2023 | 180 | MS BAPPA ENTERPRISE | 49.53 | 28.79 | 71
859 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMCHANDRAPUR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000278/2022-2023 | 1391/BD-I | 27/12/2022 | 10 | M/S SOBHA & CO | 2.46 | 2.43 | 100
860 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (35 Cum) of Ground Water Based Supply Scheme for Ramchandrapur of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000301/2023-2024 | 1069/BD-I | 21/11/2023 | 30 | MADAN MOHAN SASMAL | 5.13 | 4.68 | 70
861 | Berhampore Division I | Raghunathganj Sub-Division | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMCHANDRAPUR Water Supply Scheme (1st TW site) within RANINAGAR-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | ORD/000330/2024-2025 | 280/BD-I | 12/02/2025 | 15 | HAFIZUL SEIKH | 11.56 | 0 | 0
862 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | Junior Engineer-II | RTOR000012/2023-2024 | 61/BD-1/1 | 27/04/2023 | 0 | Resource Division | 13.4 | 0 | 0
863 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE-I PWSS (TW - III Site) within Lalgola Block under JAL JEEVAN MISSION in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (01 No TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000049/2025-2026 | 758/BD-I | 22/05/2025 | 15 | AZAD ENTERPRISE | 9.01 | 0 | 0
864 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Nasipur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000117/2022-2023 | 1368/BD-I | 21/12/2022 | 30 | CHATTERJEE ENTERPRISE | 2.46 | 2.42 | 100
865 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for NASIPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000204/2022-2023 | 1374/BD-I | 21/12/2022 | 10 | ENVIROTECH SOLUTIONS | 2.94 | 2.62 | 1
866 | Berhampore Division I | Berhampur M/E Division | Augmentation of Nasipur Zone_I Piped water supply scheme to accommodate construction of Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000245/2022-2023 | 1625/BD-I | 02/03/2023 | 180 | DHIMAN SARKAR | 176.03 | 155.11 | 26
867 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000012/2024-2025 | 1510/BD-I/6 | 12/09/2024 | 0 | Resource Division | 4.99 | 0 | 0
868 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000072/2023-2024 | 201/BD-1/13 | 10/02/2024 | 0 | Resource Division | 60.04 | 0 | 0
869 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room at Head Work Site of BAJUPUR MADHUPUR ZONE -I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000007/2025-2026 | 594/BD-I | 22/04/2025 | 45 | JAKIR HOSSAIN PRAMANIK | 8.66 | 0 | 1
870 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Bajipur Madhupur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000125/2022-2023 | 1671/BD-I | 14/03/2023 | 30 | JAMUNA CONSTRUCTION | 2.85 | 2.82 | 100
871 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bajipur Madhupur Zone-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000155/2023-2024 | 672/BD-I | 09/08/2023 | 730 | VISION ENTERPRISE | 353.85 | 0 | 10
872 | Berhampore Division I | Berhampur M/E Division | Formal work order for Augmentation of Bajipur Madhupur Zone-I Piped water supply scheme to accommodate construction of laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000240/2022-2023 | 1597/BD-I | 28/02/2023 | 180 | SAMBHUNATH ROY | 207.9 | 178.49 | 100
873 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000266/2022-2023 | 1689/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 3.14 | 3.17 | 1
874 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bajupur Madhupur Zone - I Water Supply Scheme (TW - I & II Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000365/2024-2025 | 320/BD-I | 24/02/2025 | 15 | MERCURY ENGINEERING COMPANY | 18 | 0 | 0
875 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BAJUPUR MADHUPUR ZONE-I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000380/2024-2025 | 442/BD-I | 20/03/2025 | 60 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 19 | 0 | 0
876 | Berhampore Division I | Berhampur M/E Division | BAJUPUR MADHUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000449/2023-2024 | 452/BD-I | 15/03/2024 | 747 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 21.46 | 9.7 | 30
877 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000092/2023-2024 | 201/BD-1/25 | 10/02/2024 | 0 | Resource Division | 139.52 | 0 | 0
878 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Gaukhana ground Water Supply Scheme under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000013/2023-2024 | 60/BD-I | 25/04/2023 | 30 | SAIF TRADERS | 2.25 | 2.21 | 100
879 | Berhampore Division I | Berhampur M/E Division | Improvement of existing AIRP(Gober Danga Model) (Capacity-21.0 Cum/ Hr.) of GAUKHANA Water supply Scheme under Jal Jeevan Mission within Lalgola block under Berhampore Division-I, P.H.E Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000068/2025-2026 | 721/BD-I | 14/05/2025 | 30 | MS GUNGUN CONSTRUCTION | 20.25 | 0 | 0
880 | Berhampore Division I | Berhampur M/E Division | Augmentation of Gaukhana Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant( AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000153/2023-2024 | 680/BD-I | 10/08/2023 | 630 | ARABINDA GHOSH | 317.21 | 0 | 50
881 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOUKHANA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000258/2022-2023 | 1681/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.48 | 1
882 | Berhampore Division I | Berhampur M/E Division | GAUKHANA PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000428/2023-2024 | 328/BD-I | 29/02/2024 | 542 | SANTA TRADING | 22.94 | 0 | 60
883 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000011/2024-2025 | 1510/BD-I/5 | 12/09/2024 | 0 | Resource Division | 3.44 | 0 | 0
884 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000071/2023-2024 | 201/BD-1/12 | 10/02/2024 | 0 | Resource Division | 36.3 | 0 | 0
885 | Berhampore Division I | Raghunathganj Sub-Division | MOKTARPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000070/2025-2026 | 824/BD-I | 18/06/2025 | 45 | BURIMAA CONSTRUCTION | 23.3 | 0 | 0
886 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of MUKTARPUR ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000075/2025-2026 | 842/BD-I | 23/06/2025 | 60 | GOUTAM KUMAR CHAUDHURI | 19 | 0 | 0
887 | Berhampore Division I | Raghunathganj Sub-Division | Construction of Service Road for approach and Pump House at Augnentation of MUKTARPUR PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000093/2024-2025 | 1306/BD-I | 07/08/2024 | 60 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0
888 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Moktarpur Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000205/2023-2024 | 871/BD-I | 12/09/2023 | 310 | MS RUBIET HOSSAIN | 333.41 | 0 | 0
889 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MOKTARPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | ORD/000274/2022-2023 | 1758/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.67 | 2.67 | 100
890 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior Engineer-II | RTOR000007/2023-2024 | 61/BD-1/7 | 27/04/2023 | 0 | Resource Division | 37.29 | 0 | 0
891 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Durgapur zone-III under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000054/2023-2024 | 150/BD-I | 15/05/2023 | 90 | SAHA CONSTRUCTION | 30.31 | 0 | 0
892 | Berhampore Division I | Berhampur Division I | SAMASKAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000102/2023-2024 | 220/BD-I | 17/05/2023 | 960 | BINAPANI ENTERPRISE | 52.7 | 16.88 | 5
893 | Berhampore Division I | Berhampur Division I | SAMASKAR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART -A) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000159/2023-2024 | 669/BD-I | 09/08/2023 | 723 | BAHETI CONSTRUCTION | 209.2 | 34.16 | 20
894 | Berhampore Division I | Berhampur Division I | SAMASKAR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000294/2022-2023 | 1824/BD-I | 31/03/2023 | 180 | ARINDAM MAJUMDAR | 109.77 | 0 | 0
895 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000005/2023-2024 | 61/BD-1/6 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0
896 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000023/2024-2025 | 2096/BD-I/4 | 25/11/2024 | 0 | Resource Division | 10 | 0 | 0
897 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Lahari under Bhagwangola-II block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000056/2023-2024 | 153/BD-I | 15/05/2023 | 90 | SANTA TRADING | 30.53 | 0 | 0
898 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at DIAR FATEPUR PWSS under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidbad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000072/2025-2026 | 839/BD-I | 23/06/2025 | 15 | B.M. ENGINEERING & CONSTRUCTION | 8.99 | 0 | 0
899 | Berhampore Division I | Berhampur M/E Division | DIAR FATHEPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000085/2023-2024 | 205/BD-I | 17/05/2023 | 1001 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 40.93 | 26.96 | 35
900 | Berhampore Division I | Berhampur M/E Division | DIAR FATHEPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000129/2023-2024 | 606/BD-I | 02/08/2023 | 787 | M/S J.S ENTERPRISE | 362.92 | 155.37 | 30
901 | Berhampore Division I | Berhampur M/E Division | DIAR FATHEPUR PWSS to accommodate FHTC Laying distribution system under Jal Jeevan Mission of Lalgola Block Murshidabad District under Berhampore Division-I, PHE Dte. (Part-B) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000258/2023-2024 | 973/BD-I | 18/10/2023 | 622 | SWAPAN DAS | 95.38 | 29.88 | 30
902 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000042/2023-2024 | 61/BD-1/32 | 27/04/2023 | 0 | Resource Division | 38.25 | 0 | 0
903 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000110/2023-2024 | 304/BD-1/4 | 22/02/2024 | 0 | Resource Division | 19.21 | 0 | 0
904 | Berhampore Division I | Berhampur Division I | SHUKUR PUKUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000087/2023-2024 | 207/BD-I | 17/05/2023 | 865 | ABIDA CONSTRUCTION | 40.82 | 0 | 51
905 | Berhampore Division I | Berhampur Division I | SHUKUR PUKUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000133/2023-2024 | 612/BD-I | 02/08/2023 | 697 | NOVELTY CONSTRUCTION | 52.15 | 14.56 | 60
906 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURPUKUR Water Supply Scheme(2nd TW Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | ORD/000323/2024-2025 | 262/BD-I | 07/02/2025 | 183 | SINGHA AND CO. | 9 | 0 | 100
907 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000024/2024-2025 | 2096/BD-I/5 | 25/11/2024 | 0 | Resource Division | 3.7 | 0 | 0
908 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-III | RTOR000047/2023-2024 | 61/BD-1/34 | 27/04/2023 | 0 | Resource Division | 8.65 | 0 | 0
909 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000100/2024-2025 | 1440/BD-I | 04/09/2024 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 26.67 | 0 | 0
910 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alikpur(Village code 315626), Mashimpur (Village code 315627),Sekandarpur(Village code 315628) under Mashimpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-II | Junior Engineer-I | ORD/000209/2021-2022 | 1007/BD-I | 21/06/2021 | 30 | KAMIRUL SK AND CO. | 65.2 | 60.17 | 1
911 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of GHOLLA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000022/2025-2026 | 639/BD-I | 25/04/2025 | 60 | SAIF TRADERS | 19 | 0 | 0
912 | Berhampore Division I | Berhampur M/E Division | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gholla" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-119 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000035/2024-2025 | 999/BD-I | 20/06/2024 | 730 | M/S GOUTAM CHAKRABORTY | 272.44 | 0 | 0
913 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000150/2023-2024 | 660/BD-I | 08/08/2023 | 730 | GITA CONSTRUCTION | 69.92 | 8.05 | 40
914 | Berhampore Division I | Berhampur M/E Division | Allied works for upgradation ,Improvement and laying of "GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A)". | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000156/2024-2025 | 1644/BD-I | 23/10/2024 | 223 | GITA CONSTRUCTION | 16.79 | 0 | 90
915 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000163/2023-2024 | 648/BD-I | 08/08/2023 | 689 | HARAPRASAD DAS | 118.61 | 0 | 65
916 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000164/2023-2024 | 647/BD-I | 08/08/2023 | 180 | M/S JHA CONSTRUCTION | 180.62 | 0 | 0
917 | Berhampore Division I | Berhampur M/E Division | GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000165/2023-2024 | 649/BD-I | 08/08/2023 | 1028 | RAJ KUMAR MONDAL | 404.58 | 0 | 50
918 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHOLLA PWSS (3rd TW Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000383/2024-2025 | 445/BD-I | 20/03/2025 | 15 | MARUTI CONSTRUCTION & CO. | 9.01 | 0 | 0
919 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000020/2024-2025 | 2096/BD-I/1 | 25/11/2024 | 0 | Resource Division | 29.76 | 0 | 0
920 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000102/2023-2024 | 201/BD-1/1 | 10/02/2024 | 0 | Resource Division | 25 | 0 | 0
921 | Berhampore Division I | Berhampur M/E Division | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-I" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-30.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000032/2024-2025 | 995/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 143.92 | 0 | 60
922 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASHIPUR ZONE-I (Part-B) PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000041/2025-2026 | 722/BD-I | 15/05/2025 | 60 | PRAVAT KUMAR GHOSH | 19 | 0 | 0
923 | Berhampore Division I | Berhampur M/E Division | Construction of Boundary wall at 2nd & 3rd Tube Well Site of KASHIPUR ZONE -I PWSS(Part-A) under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000043/2025-2026 | 725/BD-I | 15/05/2025 | 60 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 19.02 | 0 | 0
924 | Berhampore Division I | Berhampur M/E Division | Balance work for Improvement Existing AIRP of (Capacity 126 Cum/hr) with allied work at Kashipur Zone-I water supply scheme under JJM within Beldanga-II under Berhampore Division-I, PHE Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000056/2025-2026 | 768/BD-I | 22/05/2025 | 45 | M/S SAJAHAN CHOWDHURY | 58.23 | 0 | 0
925 | Berhampore Division I | Berhampur M/E Division | KASHIPUR ZONE-I PROPOSED PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000061/2024-2025 | 1176/BD-I | 25/07/2024 | 180 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.39 | 0 | 100
926 | Berhampore Division I | Berhampur M/E Division | Replacement of Filter media of Existing AIRP of (Capacity 126 Cum/hr.) with allied work at Kashipur Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000068/2024-2025 | 1206/BD-I | 26/07/2024 | 300 | M/S SAJAHAN CHOWDHURY | 35.07 | 0 | 80
927 | Berhampore Division I | Berhampur M/E Division | Balance work for Laying of distribution pipeline of Kashipur Zone-I and allied works under JJM within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000081/2025-2026 | 848/BD-I | 23/06/2025 | 90 | SOUNAK ENTERPRISE | 84.84 | 0 | 0
928 | Berhampore Division I | Berhampur M/E Division | Augmentation of Kashipur Zone-I Piped water supply scheme to accommodate construction of laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000161/2023-2024 | 668/BD-I | 09/08/2023 | 720 | MAMON ENTERPRISE AND CONSTRUCTION | 236.94 | 202.92 | 35
929 | Berhampore Division I | Berhampur M/E Division | Augmentation of Kashipur Zone-I Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000162/2023-2024 | 667/BD-I | 09/08/2023 | 876 | SAMIMA ENTERPRISE | 358.74 | 108.67 | 22
930 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-I Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000189/2023-2024 | 531/BD-I | 27/07/2023 | 10 | TECHVISION | 2.87 | 2.87 | 100
931 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KASHIPUR ZONE-I (PART-B) Water Supply Scheme (TW-I & II Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000293/2024-2025 | 99/BD-I | 20/01/2025 | 240 | SUJIT KUMAR SAHA | 18.02 | 0 | 100
932 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000106/2023-2024 | 201/BD-1/7 | 10/02/2024 | 0 | Resource Division | 101.3 | 0 | 0
933 | Berhampore Division I | Berhampur M/E Division | Safety Checking of 9 (Nine) nos Over Head Reservoit at various places of Murshidabad District under P.H.Engineering Department, Govt of West Bengal. | ASSISTANT ENGINEER-I | Junior engineer-II | BILL/00347/2024-2025 | BP-2024-25-259 | 27/11/2024 | 0 | SRCC NIT DURGAPUR | 3.54 | 0 | 0
934 | Berhampore Division I | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 05.07.2024 to 30.06.2025.] Car No-WB58CC 9776 | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000046/2024-2025 | 1082/BD-I | 04/07/2024 | 365 | MD MUKLESUR RAHAMAN | 1.81 | 4.79 | 0
935 | Berhampore Division I | Berhampur M/E Division | Consultancy for Engineering support of six numbers of Suspended OHR constructed in stages initially during 2011-2012 and after 5-6 years gap in Berhampore Division-I of PHE Dte. based on Joint Inspection, Non-destructive Test and subsequent Structural Analysis of their As Built Numerical Models in FEM Platform including Seismic Considerations. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000091/2025-2026 | 959/BD-I | 22/07/2025 | 60 | JADAVPUR UNIVERSITY | 49.21 | 0 | 0
936 | Berhampore Division I | Berhampur M/E Division | Continuation Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 01.07.2025 to 31.10.2025.] Car No-WB58CC 9776 | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000095/2025-2026 | 1082/BD-I | 30/06/2025 | 123 | MD MUKLESUR RAHAMAN | 0.6 | 0 | 0
937 | Berhampore Division I | Berhampur M/E Division | Withdrawing and Laying of different dia. D.I. pipe along NH12 from Bhakuri to Talbagan more with connection work to Rising Mains of Central Sector Part-II near Bhakuri more and Balarampur Halt Station under Berhampore Division-I, P.H.E. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000120/2024-2025 | 1469/BD-I | 06/09/2024 | 240 | SAMBHUNATH ROY | 53.6 | 0 | 80
938 | Berhampore Division I | Berhampur M/E Division | Improvement of existing Pump House & Construction of Boundary Wall at different head work sites for Augmentation of different PWSS within MJ & Berhampore Block under Central Sector Part-I under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000142/2024-2025 | 1610/BD-I | 03/10/2024 | 240 | M/S J.S ENTERPRISE | 85.47 | 0 | 40
939 | Berhampore Division I | Berhampur M/E Division | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-I under BERHAMPORE DIVISION - I in the district of MURSHIDABAD. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000256/2024-2025 | 2269/BD-I | 16/12/2024 | 30 | M/S MOHAN LAL JAIN | 36.33 | 0 | 0
940 | Berhampore Division I | Berhampur M/E Division | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-II under BERHAMPORE DIVISION - I in the district of MURSHIDABAD | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000266/2024-2025 | 2324/BD-I | 26/12/2024 | 30 | ECO PROTECTION ENGINEERS PVT LTD. | 35.3 | 0 | 0
941 | Berhampore Division I | Berhampur M/E Division | Renovation and upgradation of all existing infrastructures (Sludge Sump House, Sludge pond, Substation Building,Boundary Wall, Clariflocculator, Flash Mixer, Inlet Well and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000271/2024-2025 | 2333/BD-I | 30/12/2024 | 45 | CONCORD ENGINEERING | 42.16 | 0 | 0
942 | Berhampore Division I | Berhampur M/E Division | Renovation and upgradation of all existing infrastructures (Filter House Building,Chemical House Building,Laboratory/SCADA Building,Clear Water Pump House, Clear Water Reservoir, Outhouse, Staff Quarters and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000272/2024-2025 | 2334/BD-I | 30/12/2024 | 45 | CONCORD ENGINEERING | 59.47 | 0 | 0
943 | Berhampore Division I | Berhampur M/E Division | Rejuvanation of 54.11 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture,Clarifoculator, Chemical Dosing and Filter House ) at Central Sector Part-II UNDER BERHAMPORE DIVISION - I , IN THE DISTRICT MURSHIDABAD , PHE DTE . | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000432/2023-2024 | 385/BD-I | 12/03/2024 | 477 | CONCORD ENGINEERING | 296.54 | 0 | 60
944 | Berhampore Division I | Berhampur M/E Division | Survey, Investigation, Planning, Design, Execution commissioning and completion in all respect of all Civil, Electrical and Mechanical work of 11 MLD capacity conventional water treatment plant (WTP) using River Bhagirathi as source including Intake Structures, Raw Water rising main, and Clear Water rising main upto boundary limit of WTP for the Augmentation of surface water based piped water supply scheme for Murshidabad Central Sector (Part-I) in Murshidabad District under PHE Dte. including 12 (Twelve) months of Operation and Maintenance after successful completion of 3 (Three) months Trial Run | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000434/2023-2024 | 386/BD-I | 12/03/2024 | 549 | CONCORD ENGINEERING | 3354.92 | 0 | 0
945 | Berhampore Division I | Berhampur M/E Division | EXECUTION OF CLEAR WATER RISING MAIN, OVERHEAD RESERVOIRS WITH ALLIED WORKS, DISTRIBUTION NETWORK WITH FHTC COMPLETE FOR AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CENTRAL SECTOR PART-I OF MURSHIDABAD DISTRICT | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000435/2023-2024 | 387/BD-I | 12/03/2024 | 849 | M/S MOHAN LAL JAIN | 7952.07 | 1331.31 | 60
946 | Berhampore Division I | Berhampur M/E Division | EXECUTION OF CLEAR WATER RISING MAIN, OVERHEAD RESERVOIRS WITH ALLIED WORKS, DISTRIBUTION NETWORK WITH FHTC COMPLETE FOR AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CENTRAL SECTOR PART-II OF MURSHIDABAD DISTRICT | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000436/2023-2024 | 388/BD-I | 12/03/2024 | 872 | ECO PROTECTION ENGINEERS PVT LTD. | 16059.7 | 808.08 | 35
947 | Berhampore Division I | Berhampur M/E Division | Rejuvanation of of 30.33 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture ,Clarifoculator , Chemical Dosing and Filter House ) at Central Sector Part- I (At Lalbagh) Under Berhampore Division - I , In The District Murshidabad , PHE Dte . | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000437/2023-2024 | 391/BD-I | 12/03/2024 | 540 | DHIMAN SARKAR | 270.68 | 0 | 80
948 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000001/2024-2025 | 790/BD-I | 09/05/2024 | 0 | Resource Division | 478.82 | 0 | 0
949 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000002/2024-2025 | 1148/BD-I | 18/07/2024 | 0 | Resource Division | 817.87 | 0 | 0
950 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000004/2024-2025 | 1341/BD-I/2 | 20/08/2024 | 0 | Resource Division | 387.17 | 0 | 0
951 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000005/2024-2025 | 1412/BD-I | 30/08/2024 | 0 | Resource Division | 1050.72 | 0 | 0
952 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000006/2024-2025 | 1462/BD-I | 05/09/2024 | 0 | Resource Division | 123.2 | 0 | 0
953 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Sarkarpara ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | JE | ORD/000158/2024-2025 | 1646/BD-I | 23/10/2024 | 30 | PRATAP KUMAR SINHA | 5.92 | 0 | 0
954 | Berhampore Division I | Raghunathganj Sub-Division | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarkarpara (Village code 314647) under Sarkarpara Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-18 of 2020 ¿ 2021,SL-03). | Assistant Engineer | JE | ORD/000244/2020-2021 | 77/BD-I | 19/01/2021 | 30 | SARAJIT KUMAR MAJUMDAR | 24.4 | 16.81 | 0
955 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahajadpur (Village code 315513) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000138/2020-2021 | 238/BD-I | 10/02/2021 | 180 | M/S UNIVERSAL TRADING | 91.12 | 87.7 | 1
956 | Berhampore Division I | Berhampur Division I | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village of Joykrishnapur (Village code 315508) under Choa (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000145/2020-2021 | 252/BD-I | 11/02/2021 | 90 | DOBAY CONSTRUCTION | 42.77 | 34.79 | 1
957 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of GAZNIPUR (Village code 315512)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000146/2020-2021 | 261/ BD-I | 12/02/2021 | 180 | RAJ KUMAR MONDAL | 78.63 | 113.73 | 1
958 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of PADMANABHPUR (Village code 315507)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000147/2020-2021 | 264/ BD-I | 12/02/2021 | 180 | SARAJIT KUMAR MAJUMDAR | 113.25 | 87.25 | 80
959 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SRIPUR (Village code 315511) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000148/2020-2021 | 265/ BD-I | 12/02/2021 | 180 | MS RUBIET HOSSAIN | 107.3 | 87.96 | 1
960 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of CHOA (Village code 315510) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000247/2020-2021 | 977/BD-I | 17/12/2020 | 180 | MS RUBIET HOSSAIN | 240.3 | 288.79 | 1
961 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-II | Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 1
962 | Berhampore Division I | Berhampur Division I | Additional and balance work of HDPE pipe for house service connection and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna from Choa Thana more towards Sahebnagar & Tangramari Village and at Borakhali village and Pirtala village of Choa G.P of Choa Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000578/2021-2022 | 1847/BD-I | 07/10/2021 | 50 | M/S RUBIET HOSSAIN | 44.49 | 0 | 0
963 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-II | RTOR000027/2024-2025 | 2096/BD-I/8 | 25/11/2024 | 0 | Resource Division | 24.64 | 0 | 0
964 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code-314521) in Faridpur ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000082/2024-2025 | 1243/BD-I | 30/07/2024 | 30 | NOBEL CONSTRUCTION | 4.82 | 0 | 0
965 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalyan Nagar (Village code 314519) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000184/2020-2021 | 840/BD-I | 23/11/2020 | 60 | DOBAY CONSTRUCTION | 18.39 | 25.67 | 0
966 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jot Sahabaj (Village code 314521) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000186/2020-2021 | 841/BD-I | 23/11/2020 | 60 | DOBAY CONSTRUCTION | 20.69 | 35.31 | 0
967 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Foridpur (Village code 314520) under Foridpur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000207/2021-2022 | 1005/BD-I | 21/06/2021 | 20 | AICH CONSTRUCTION | 45.66 | 40.29 | 1
968 | Berhampore Division I | Berhampur Division I | Additional Laying works at village Foridpur (Village code-314520) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under ForidpurGround water supply scheme (Bhagwangola-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000781/2021-2022 | 2296/BD-I | 28/12/2021 | 15 | AICH CONSTRUCTION | 9.57 | 9.06 | 1
969 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-314529) , Boalia (Village Code-314530) in Faridpur ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000097/2024-2025 | 1369/BD-I | 22/08/2024 | 30 | ANIRBAN CHATTERJEE | 7.59 | 0 | 0
970 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamal Chak (Village code 314529) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000182/2020-2021 | 839/BD-I | 23/11/2020 | 60 | AJAY MONDAL | 11.86 | 9.18 | 1
971 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dhwajamat (Village code 314528) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000183/2020-2021 | 817/BD-I | 12/11/2020 | 60 | KAKALI ENTERPRISE | 10.81 | 17.54 | 1
972 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Boalia (Village code 314530) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000188/2020-2021 | 816/BD-I | 12/11/2020 | 60 | SAMBHUNATH ROY | 19.03 | 27.25 | 1
973 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamal Chak and others under Faridpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000207/2020-2021 | 274/ BD-I | 15/02/2021 | 10 | AJAY MONDAL | 3.12 | 1.7 | 1
974 | Berhampore Division I | Berhampur Division I | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dhwajamat (Village Code-314528) under Faridpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000211/2020-2021 | 278/BD-I | 15/02/2021 | 10 | KAKALI ENTERPRISE | 2.02 | 3.12 | 0
975 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Topi Danga (Village code 314522) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 ¿ 2021,SL-06). | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000241/2020-2021 | 74/BD-I | 19/01/2021 | 30 | SANDIP KUMAR BISWAS | 35.16 | 28.7 | 100
976 | Berhampore Division I | Raghunathganj Sub-Division | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000076/2024-2025 | 1224/BD-I | 29/07/2024 | 60 | SOM CONSTRUCTION AGENCY | 44.6 | 0 | 0
977 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lochanpur (Village code 314758), Char Pirojpur (Village Code-314760) under Lochanpur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-I) (Sl-01) | Assistant Engineer | Junior Engineer-II | ORD/000383/2021-2022 | 1475/BD-I | 17/08/2021 | 1630 | M/S GOUTAM CHAKRABORTY | 121.97 | 57.28 | 1
978 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000074/2024-2025 | 1222/BD-I | 29/07/2024 | 60 | SANTA TRADING | 25.6 | 0 | 0
979 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopalpur (Village code 315686) under Kashipur Ground Water Supply Scheme in Beldanga-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-12) | Assistant Engineer-II | Junior Engineer-II | ORD/000273/2021-2022 | 1144/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 70.23 | 62.88 | 0
980 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rajabati (Village code 314552),Fulpur (Village code 314511) under Dakshin Sahar Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000117/2020-2021 | 189/BD-I | 04/02/2021 | 20 | GOUTAM CHAKRABORTY | 32.54 | 45.63 | 1
981 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000166/2024-2025 | 1685/BD-I | 28/10/2024 | 30 | ARJU CONSTRUCTION | 10.34 | 0 | 0
982 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000113/2024-2025 | 1449/BD-I | 04/09/2024 | 60 | S DUTTA | 21.89 | 0 | 0
983 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jogopur (Village code 314533),Kamari (Village code 314551) under Dakshin Sahar Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000118/2020-2021 | 190/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.63 | 48.98 | 1
984 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgola Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000102/2024-2025 | 1438/BD-I | 04/09/2024 | 30 | ALOK BANERJEE ENTERPRISE | 8.85 | 0 | 0
985 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paranpur(Village code 314173),Fatepur(Village code 314174) under Maia Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | Assistant Engineer-I | JE | ORD/000108/2020-2021 | 174/BD-I | 03/02/2021 | 20 | SAMAR MUKHERJEE | 35.05 | 50.51 | 1
986 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Debaipur (Village code 314548) under Benipur Ground Water based Water Supply Scheme for Bhagwangola- II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000224/2020-2021 | 988/BD-I | 17/12/2020 | 90 | DOBAY CONSTRUCTION | 37.11 | 54.62 | 0
987 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Saralpur (Village code 314538) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000232/2020-2021 | 38/BD-I | 13/01/2021 | 90 | JAHANGIR ALAM | 41.33 | 32.43 | 1
988 | Berhampore Division I | Berhampur Division I | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Andulberia (Village code 315690) under Andulberia Ground Water Supply Scheme in Beldanga-II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-15) | Assistant Engineer-II | Junior Engineer-I | ORD/000500/2021-2022 | 1907/BD-I | 08/10/2021 | 180 | M/S JAN MAHAMMAD | 161.38 | 161.22 | 1
989 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur (village code 315684) under ANDULBERIA Ground Water based Water Supply Scheme in Beldanga-II Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000586/2021-2022 | 2016/BD-I | 08/11/2021 | 652 | MANASH GHOSH | 96.77 | 50.73 | 100
990 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-I | RTOR000003/2021-2022 | 63/BD-I | 27/01/2022 | 0 | Resource Division | 13.74 | 0 | 0
991 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-I | RTOR000005/2021-2022 | 72/BD-I | 28/01/2022 | 0 | Resource Division | 4.44 | 0 | 0
992 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of village of Sarulia (village code 315611) ,Mirzapur (village code 315615)under (Zone-G) and additional remaining villages under Begunbari (Part) ,Maniknagar (Part) and Naoapukhuria (Part) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000289/2022-2023 | 1803/BD-I | 31/03/2023 | 120 | M/S GUHA & ROY | 373.58 | 0 | 0
993 | Berhampore Division I | Berhampur Division I | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Cossimbazar (Village code 315444), Sibnagar Badarpur (Village Code-315446) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000313/2020-2021 | 980/BD-I | 17/12/2020 | 180 | CHAKRABORTY CONSTRUCTION | 307.25 | 117.5 | 69
994 | Berhampore Division I | Berhampur Division I | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I | Junior Engineer-I | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 19.13 | 1
995 | Berhampore Division I | Berhampur Division I | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of DIGHA PWSS under Jal Jeevan Mission within Bhagwangola-I inconnection with Augmentation under Berhampore Division-I , P.H.E. Dte. In the districtof Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000048/2025-2026 | 755/BD-I | 22/05/2025 | 30 | DEBASISH SARKAR | 24.4 | 0 | 0
996 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Digha ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000107/2022-2023 | 1364/BD-I | 21/12/2022 | 30 | SELIM SARKAR | 2.27 | 1.73 | 100
997 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of DIGHA Piped water supply scheme to accommodate contruction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000135/2022-2023 | 1822/BD-I | 31/03/2023 | 642 | SUJIT KUMAR SAHA | 255.85 | 27.9 | 10
998 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIGHA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000878/2021-2022 | 262/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.43 | 2.43 | 0
999 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000062/2023-2024 | 196/BD-I/9 | 09/02/2024 | 0 | Resource Division | 3.75 | 0 | 0
1000 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Paschim Rampur ground water supply scheme in Bhagwangola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-90.00 Cum/Hr.) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000017/2025-2026 | 614/BD-I | 22/04/2025 | 300 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 207.69 | 0 | 0
1001 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Rampur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000032/2023-2024 | 124/BD-I | 12/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 17.74 | 7.36 | 50
1002 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PASCHIMRAMPUR PWSS (TW-III Site) within BHAGWANGOLA-I Block under JAL JEEVAN MISSION in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. (01 No TW) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000063/2025-2026 | 776/BD-I | 22/05/2025 | 15 | M/S GHOSH ENTERPRISE | 9 | 0 | 0
1003 | Berhampore Division I | Berhampur Division I | Formal Work order for Augmentation of PASCHIM RAMPUR Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000160/2022-2023 | 1453/BD-I | 17/01/2023 | 365 | NILKAMAL BASAK | 398.64 | 0 | 0
1004 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for PASCHIM RAMPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000876/2021-2022 | 260/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.82 | 2.82 | 100
1005 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000087/2023-2024 | 196/BD-I/15 | 09/02/2024 | 0 | Resource Division | 41.52 | 0 | 0
1006 | Berhampore Division I | Berhampur Division I | Augmentation of Dakshin Sahar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000026/2023-2024 | 103/BD-I | 04/05/2023 | 1098 | RAJ KUMAR MONDAL | 352.91 | 0 | 10
1007 | Berhampore Division I | Berhampur Division I | Augmentation of Dakshin Sahar Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(Part-B) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000105/2023-2024 | 105/BD-I | 08/05/2023 | 909 | A ONE CONSTRUCTION | 303.14 | 92.05 | 50
1008 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Sahar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000115/2022-2023 | 1412/BD-I | 04/01/2023 | 10 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 3.61 | 2.46 | 100
1009 | Berhampore Division I | Berhampur Division I | Dakshin Sahar PWSS to accommodate construction of Pump House Cum Chlorine Room, Boundary Wall and Service Road, under Jal Jivan Mission of BHAGWANGOLA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000131/2024-2025 | 1528/BD-I | 19/09/2024 | 60 | GITA CONSTRUCTION | 32.4 | 0 | 0
1010 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN SAHAR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000173/2022-2023 | 1077/BD-I | 29/09/2022 | 10 | NATSOL CONSULTANT | 2.71 | 2.71 | 0
1011 | Berhampore Division I | Berhampur Division I | Repair And Renovation Works Of OHR (450 Cum) forDakshinSahar water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000257/2023-2024 | 1027/BD-I | 01/11/2023 | 30 | DEBJIT DAS | 7.5 | 0 | 0
1012 | Berhampore Division I | Berhampur Division I | DAKSHINSAHAR PART-A PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BHAGAWANGOLA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000458/2023-2024 | 462/BD-I | 15/03/2024 | 480 | RELIABLE ENTERPRISE | 21.99 | 0 | 100
1013 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000051/2023-2024 | 196/BD-I/2 | 09/02/2024 | 0 | Resource Division | 41.96 | 0 | 0
1014 | Berhampore Division I | Berhampur Division I | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000041/2023-2024 | 44/BD-I | 24/04/2023 | 30 | SUJIT KUMAR SAHA | 8.99 | 0 | 0
1015 | Berhampore Division I | Berhampur Division I | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Foridpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000114/2022-2023 | 1411/BD-I | 04/01/2023 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 2.23 | 1.41 | 100
1016 | Berhampore Division I | Berhampur Division I | Formal work order for Augmentation of FARIDPUR Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall,service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000140/2022-2023 | 1450/BD-I | 17/01/2023 | 1045 | BIJOY CHOWDHURY | 435.9 | 224.38 | 70
1017 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for FARIDPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | ORD/000886/2021-2022 | 269/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 1
1018 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE_RAJIB BISWAS,Junior engineer-III | RTOR000049/2023-2024 | 196/BD-I/16 | 09/02/2024 | 0 | Resource Division | 38.7 | 0 | 0
1019 | Berhampore Division I | Berhampur Division I | Construction of Boundary Wall with Main Entrance gate and barbed wire facing at Augmentation of BALI ZONE-I PWSS of Nawda Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000057/2024-2025 | 1129/BD-I | 11/07/2024 | 45 | KHANDAKAR CONSTRUCTION | 18.69 | 0 | 0
1020 | Berhampore Division I | Berhampur Division I | Augmentation of Bali Zone-I Piped water supply scheme to accomodate construction of service road,repairing of Existing OHR, laying of Distribution pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000113/2023-2024 | 507/BD-I | 24/07/2023 | 180 | N.H ENTERPRISE | 56.14 | 35.79 | 50
1021 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000237/2022-2023 | 1595/BD-I | 28/02/2023 | 10 | TECHVISION | 2.46 | 2.46 | 0
1022 | Berhampore Division I | Berhampur Division I | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Bali Zone-I ground water supply scheme in Nawda Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000366/2024-2025 | 322/BD-I | 24/02/2025 | 300 | M/S SAJAHAN CHOWDHURY | 122.62 | 0 | 0
1023 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | RTOR000058/2023-2024 | 94/BD1 | 22/01/2024 | 0 | Resource Division | 3.29 | 0 | 0
1024 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd Tube Well Site of KASHIPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000038/2025-2026 | 667/BD-I | 29/04/2025 | 45 | DEBEN RAJAK | 10.18 | 0 | 100
1025 | Berhampore Division I | Berhampur Division I | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-II" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-48.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Up flow Polishing | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000039/2024-2025 | 1038/BD-I | 28/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 156.07 | 0 | 60
1026 | Berhampore Division I | Berhampur Division I | KASHIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000051/2024-2025 | 1117/BD-I | 11/07/2024 | 180 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.67 | 0 | 100
1027 | Berhampore Division I | Berhampur Division I | Allied Work for Road Restoration, Laying of Balance portion of UPVC and Rising Mains at Kashipur Zone-II PWSS under Jal Jeevan Mission within Beldanga-II block under Berhampore Division-I, P.H.E. Dte. In the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000064/2025-2026 | 777/BD-I | 22/05/2025 | 90 | MARUTI CONSTRUCTION & CO. | 64.87 | 0 | 0
1028 | Berhampore Division I | Berhampur Division I | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-II Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000232/2022-2023 | 1590/BD-I | 28/02/2023 | 10 | TECHVISION | 2.6 | 2.6 | 0
1029 | Berhampore Division I | Berhampur Division I | Augmentation of Kashipur zone_II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000242/2022-2023 | 1599/BD-I | 28/02/2023 | 900 | MARUTI CONSTRUCTION & CO. | 150.14 | 122.97 | 95
1030 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000091/2023-2024 | 196/BD-I/25 | 09/02/2024 | 0 | Resource Division | 48.51 | 0 | 0
1031 | Berhampore Division I | Berhampur M/E Division | Augmentation of Sitesnagar Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000222/2022-2023 | 1542/BD-I | 17/02/2023 | 988 | M/S JOGMAYA ENTERPRISE | 87.18 | 54.67 | 30
1032 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SITESNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000259/2022-2023 | 1682/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 1
1033 | Berhampore Division I | Berhampur M/E Division | Balance and allied Work Laying Rising Main with DI (K-9) and distribution system with UPVC pipe including supply of necessary special for augmentation work of Siteshnagar Water Supply Scheme , under Jal Jevan Mission under Berhampore Division -I , PHE.Dte. of LALGOLA Block of Murshidabad District. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000281/2024-2025 | 09/BD-I | 06/01/2025 | 179 | M/S. JOGMAYA ENTERPRISE | 23.22 | 0 | 30
1034 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000016/2024-2025 | 1510/BD-I/10 | 12/09/2024 | 0 | Resource Division | 2.19 | 0 | 0
1035 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000077/2023-2024 | 201/BD-1/18 | 10/02/2024 | 0 | Resource Division | 16.95 | 0 | 0
1036 | Berhampore Division I | Berhampur M/E Division | Balance i.c.w Improvement of Existing AIRP (Modified Sujapur Sadipur Model) capacity 130.00 cum/hr at Head Work Site of Maia Zone-I Water Supply Scheme under JJM within Lalgola under Berhampore Division -I, P.H.E. Dte. In the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000065/2025-2026 | 778/BD-I | 22/05/2025 | 30 | M/S J.S ENTERPRISE | 30.11 | 0 | 0
1037 | Berhampore Division I | Berhampur M/E Division | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Maia ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000124/2022-2023 | 1676/BD-I | 14/03/2023 | 30 | RAJIB SAHA | 3.62 | 2.38 | 80
1038 | Berhampore Division I | Berhampur M/E Division | Augmentation of Maia Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000124/2023-2024 | 511/BD-I | 25/07/2023 | 900 | SOM CONSTRUCTION AGENCY | 208.44 | 19.28 | 20
1039 | Berhampore Division I | Berhampur M/E Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAIA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000265/2022-2023 | 1688/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.87 | 2.69 | 1
1040 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000015/2024-2025 | 1510/BD-I/9 | 12/09/2024 | 0 | Resource Division | 6.73 | 0 | 0
1041 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000079/2023-2024 | 201/BD-1/20 | 10/02/2024 | 0 | Resource Division | 34.89 | 0 | 0
1042 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room at Head Work Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000016/2025-2026 | 613/BD-I | 22/04/2025 | 45 | BIJOY SINGHA | 8.81 | 0 | 0
1043 | Berhampore Division I | Berhampur M/E Division | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000020/2025-2026 | 626/BD-I | 24/04/2025 | 60 | SUSHANTA MANDAL | 18.91 | 0 | 0
1044 | Berhampore Division I | Berhampur M/E Division | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000138/2023-2024 | 621/BD-I | 03/08/2023 | 310 | BURIMA CONSTRUCTION | 367.54 | 0 | 0
1045 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BANSGARA-II PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000377/2024-2025 | 432/BD-I | 19/03/2025 | 30 | SARKAR WATER SUPPLY AGENCY | 18 | 0 | 0
1046 | Berhampore Division I | Berhampur M/E Division | BANSGARA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000450/2023-2024 | 453/BD-I | 15/03/2024 | 60 | KAUSHIK MAJUMDAR | 21.78 | 0 | 0
1047 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000083/2023-2024 | 201/BD-1/24 | 10/02/2024 | 0 | Resource Division | 13.68 | 0 | 0
1048 | Berhampore Division I | Berhampur Division I | Construction of Boundary wall at 2nd & 3rd Tube Well Site of ANDULBERIYA ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000013/2025-2026 | 600/BD-I | 22/04/2025 | 60 | AICH CONSTRUCTION | 20.36 | 0 | 0
1049 | Berhampore Division I | Berhampur Division I | Allied works of Laying of distribution pipeline of ANDULBERIA ZONE-I piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000127/2024-2025 | 1477/BD-I | 06/09/2024 | 60 | SUSHANTA MANDAL | 45.66 | 0 | 0
1050 | Berhampore Division I | Berhampur Division I | Augmentation of Andulberia Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000255/2022-2023 | 1661/BD-I | 13/03/2023 | 720 | M/S BIMALENDU BOSE | 433.78 | 433.17 | 100
1051 | Berhampore Division I | Berhampur Division I | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | ORD/000296/2022-2023 | 1648/BD-I | 10/03/2023 | 10 | TECHVISION | 2.81 | 2.8 | 100
1052 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,Assistant Engineer-II | Junior Engineer-I,Junior engineer-III | RTOR000089/2023-2024 | 196/BD-I/23 | 09/02/2024 | 0 | Resource Division | 64.29 | 0 | 0
1053 | Berhampore Division I | Raghunathganj Sub-Division | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Lochanpur Zone-II ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000002/2025-2026 | 508/BD-I | 03/04/2025 | 300 | NATIONAL CONSTRUCTION | 122.74 | 0 | 0
1054 | Berhampore Division I | Raghunathganj Sub-Division | Construction Service Road for approach and Pump House at Augmentation of LOCHANPUR ZONE-II PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000066/2025-2026 | 786/BD-I | 26/05/2025 | 60 | BHOLEBABA CONSTRUCTION CO | 7.34 | 0 | 0
1055 | Berhampore Division I | Raghunathganj Sub-Division | Augmentation of Lochanpur Zone-II Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000154/2023-2024 | 679/BD-I | 10/08/2023 | 964 | APU CONSTRUCTION | 273.83 | 136.47 | 5
1056 | Berhampore Division I | Raghunathganj Sub-Division | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for LOCHANPUR ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000273/2022-2023 | 1757/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100
1057 | Berhampore Division I | Raghunathganj Sub-Division | Repair And Renovation Works Of OHR (250 Cum) of Ground Water Based Supply Scheme for Lochanpur Zone-II of Raninagar-I block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | ORD/000291/2023-2024 | 1038/BD-I | 03/11/2023 | 30 | BHOLE BABA CONSTRUCTION CO. | 8.02 | 0 | 100
1058 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-II | RTOR000036/2023-2024 | 61/BD-1/23 | 27/04/2023 | 0 | Resource Division | 24.65 | 0 | 0
1059 | Berhampore Division I | Berhampur Division I | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PURBA KASHIPUR PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000019/2025-2026 | 625/BD-I | 24/04/2025 | 60 | SHIV SHAKTI CONSTRUCTION | 18.82 | 0 | 80
1060 | Berhampore Division I | Berhampur Division I | Balance work of distribution pipe line under Jal Jeevan Mission for Purba Kashipur Piped Water Supply scheme under Berhampore Division - I , P.H.Engg Dte. In the district of Murshidabad. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000069/2024-2025 | 1207/BD-I | 26/07/2024 | 60 | MARUTI CONSTRUCTION & CO. | 42.9 | 0 | 85
1061 | Berhampore Division I | Berhampur Division I | PURBA KASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000088/2023-2024 | 210/BD-I | 17/05/2023 | 905 | MARUTI CONSTRUCTION & CO. | 53.43 | 0 | 70
1062 | Berhampore Division I | Berhampur Division I | PURBA KASHIPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000116/2023-2024 | 407/BD-I | 06/07/2023 | 1000 | SANKAR KUMAR BISWAS | 290.34 | 105.33 | 40
1063 | Berhampore Division I | Berhampur Division I | PURBA KASHIPUR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I | JE,Junior engineer-III | ORD/000292/2022-2023 | 1823/BD-I | 31/03/2023 | 180 | MARUTI CONSTRUCTION & CO. | 112.84 | 49.88 | 85
1064 | Berhampore Division I | Berhampur Division I | Material Requisition To Resource Division | Assistant Engineer-I | JE,Junior engineer-III | RTOR000003/2023-2024 | 61/BD-1/4 | 27/04/2023 | 0 | Resource Division | 9.47 | 0 | 0
1065 | Berhampore Division I | Berhampur M/E Division | GAYESPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000048/2023-2024 | 144/BD-I | 15/05/2023 | 809 | SAPTADIP CONSTRUCTION | 58.85 | 0 | 30
1066 | Berhampore Division I | Berhampur M/E Division | GAYESPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000343/2023-2024 | 1257/BD-I | 22/12/2023 | 544 | M/S HUMAYUN BISWAS | 39.06 | 0 | 60
1067 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000032/2023-2024 | 61/BD-1/15 | 27/04/2023 | 0 | Resource Division | 6.62 | 0 | 0
1068 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000115/2023-2024 | 304/BD-1/7 | 22/02/2024 | 0 | Resource Division | 3.02 | 0 | 0
1069 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Chak Chandpara under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000075/2023-2024 | 181/BD-I | 17/05/2023 | 90 | ADITYA ENTERPRISE | 29.09 | 0 | 0
1070 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Hallalpur Zone-III under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-II | ORD/000097/2023-2024 | 171/BD-I | 16/05/2023 | 90 | HI-LIGHT ELECTRONICS | 30.32 | 0 | 0
1071 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Char Sujapur Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I | JE,Junior engineer-III | ORD/000072/2023-2024 | 167/BD-I | 16/05/2023 | 90 | ALOK BANERJEE ENTERPRISE | 30.49 | 0 | 0
1072 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Sibnagar Zone-II under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | ASSISTANT ENGINEER-I,Assistant Engineer-II | JE,Junior engineer-II | ORD/000058/2023-2024 | 155/BD-I | 15/05/2023 | 90 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 30.53 | 0 | 0
1073 | Berhampore Division I | Berhampur M/E Division | Mini Piped Water Supply Scheme for Arazi Narayanpur under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000050/2023-2024 | 147/BD-I | 15/05/2023 | 90 | INDRAJIT DUBEY | 28.9 | 0 | 0
1074 | Berhampore Division I | Berhampur Division I | Mini Piped Water Supply Scheme for Darura under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | Assistant Engineer-I,ASSISTANT ENGINEER-II | JE,Junior engineer-III | ORD/000064/2023-2024 | 161/BD-I | 16/05/2023 | 90 | PRITAM KUMAR PAUL | 23.62 | 0 | 0
1075 | Berhampore Division I | Berhampur M/E Division | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SHYAMPUR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000071/2025-2026 | 838/BD-I | 23/06/2025 | 15 | B.M. ENGINEERING & CONSTRUCTION | 9 | 0 | 0
1076 | Berhampore Division I | Berhampur M/E Division | SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000104/2023-2024 | 222/BD-I | 17/05/2023 | 639 | SKY CONSTRUCTION | 50.19 | 28.32 | 40
1077 | Berhampore Division I | Berhampur M/E Division | SYAMPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000171/2023-2024 | 663/BD-I | 09/08/2023 | 784 | M/S ABDUL MATIN | 290.59 | 115.52 | 30
1078 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000034/2023-2024 | 61/BD-1/19 | 27/04/2023 | 0 | Resource Division | 15.51 | 0 | 0
1079 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000114/2023-2024 | 304/BD-1/5 | 22/02/2024 | 0 | Resource Division | 7.38 | 0 | 0
1080 | Berhampore Division I | Berhampur M/E Division | GOURIDASPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000084/2023-2024 | 202/BD-I | 17/05/2023 | 987 | M/S ROY & BOSE ENTERPRISE | 41.09 | 2.65 | 75
1081 | Berhampore Division I | Berhampur M/E Division | GOURIDASPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | ORD/000151/2023-2024 | 655/BD-I | 08/08/2023 | 923 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 209.18 | 93.25 | 85
1082 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000023/2023-2024 | 61/BD-1/26 | 27/04/2023 | 0 | Resource Division | 11.84 | 0 | 0
1083 | Berhampore Division I | Berhampur M/E Division | Material Requisition To Resource Division | Assistant Engineer,ASSISTANT ENGINEER-I | JE,Junior engineer-III | RTOR000116/2023-2024 | 304/BD-1/9 | 22/02/2024 | 0 | Resource Division | 4.82 | 0 | 0
1084 | Berhampore Division I | Berhampur Division I | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hazi Mahammadpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000129/2024-2025 | 1479/BD-I | 06/09/2024 | 60 | MURSHID ALOM | 11.94 | 0 | 0
1085 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Hazi Mahammadpur ( Habitation ID: 0001294220) in the village of Hazi Mahammadpur (Village code 314231) under Hazi Mahammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000233/2020-2021 | 1048/BD-I | 28/12/2020 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 32.81 | 30.16 | 1
1086 | Berhampore Division I | Berhampur Division I | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Dakshin Ashariadaha (Village code 314229) under Hazi Mohammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-16 of 2020 ¿ 2021,SL-10) | Assistant Engineer-I | JE | ORD/000243/2020-2021 | 76/BD-I | 19/01/2021 | 30 | JIBENDRA NARAYAN SUKUL | 24.9 | 39.42 | 0
1087 | Berhampore Division I | Raghunathganj Sub-Division | Relaying of different dia UPVC Pipe line in connection with JJM (Jal Jeevan Mission) over damaged portion and Interconnection between over flow line and Delivery Line at Beniagram Zone-II OHR Site under Beniagram Surface Based water supply scheme of Zone-II of Murshidabad District under Berhampore Division-I PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000019/2023-2024 | 90/BD-I | 03/05/2023 | 30 | BABAI GHOSH | 3.05 | 3.01 | 100
1088 | Berhampore Division I | Raghunathganj Sub-Division | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2024 to 31.12.2024. | Assistant Engineer | Junior Engineer-I | ORD/000379/2023-2024 | 1281/BD-I | 27/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 1.81 | 3.94 | 33
1089 | Berhampore Division I | Raghunathganj Sub-Division | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer | Junior Engineer-I | ORD/000462/2020-2021 | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 1
1090 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baikunthapur, Asua, Hosenpur & Jafarganj (Village code 313816, 313817, 313818 & 313809) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | Assistant Engineer | Junior Engineer-I | ORD/000583/2021-2022 | 2010/BD-I | 08/11/2021 | 1229 | DECON INDIA | 167.27 | 134.55 | 100
1091 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Beniagram (Village code 313832) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | Assistant Engineer | Junior Engineer-I | ORD/000584/2021-2022 | 2011/BD-I | 08/11/2021 | 180 | M/S S.DAS & ENTERPRISE | 162.77 | 0 | 1
1092 | Berhampore Division I | Raghunathganj Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chauki, Kashinagar, Samaspur & Imamnagar (Village code 313803, 313806, 313810 & 313815) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | Assistant Engineer | Junior Engineer-I | ORD/000615/2021-2022 | 2050/BD-I | 17/11/2021 | 900 | DOBAY CONSTRUCTION | 142.86 | 118.84 | 80
1093 | Berhampore Division I | Raghunathganj Sub-Division | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Beniagram Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer-I | ORD/000762/2021-2022 | 2228/BD-I | 15/12/2021 | 90 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 71 | 68.22 | 1
1094 | Berhampore Division I | Raghunathganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer-I | RTOR000013/2021-2022 | 145/BD-I | 10/02/2022 | 0 | Resource Division | 18.66 | 0 | 0
Total | [10 empty] | 144159.11 | 39163.5