## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000084/2021-2022 | 980/ALD | 13/09/2021 | 60 | DILIP MAHATO | 48.35 | 39.41 | 68
2 | Alipurduar Division | Alipurduar Sadar Sub-Division | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000108/2020-2021 | 729/ALD | 22/09/2020 | 45 | TAPAN CHANDA | 4.97 | 9.27 | 0
3 | Alipurduar Division | Alipurduar Sadar Sub-Division | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000109/2020-2021 | 730/ALD | 22/09/2020 | 45 | TAPAN CHANDA | 5 | 0.74 | 0
4 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000148/2020-2021 | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 2.5 | 79
5 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA ZONE- I water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000167/2020-2021 | 911/ALD | 16/10/2020 | 30 | TAPAN CHANDA | 4.98 | 9.97 | 0
6 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000170/2021-2022 | 1320/ALD | 05/10/2021 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 6.06 | 66
7 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000225/2021-2022 | 1575/ALD | 22/11/2021 | 90 | TAPAN CHANDA | 75.74 | 30.67 | 69
8 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 6.95 | 94
9 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000317/2020-2021 | 1449/ALD | 25/01/2021 | 45 | MAHENDRA CHHETRI | 43.86 | 2.86 | 67
10 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 4.02 | 60
11 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Truss roof for office cum Godown Path way at KAIJALI BUSTY WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000085/2022-2023 | 449/ALD | 13/05/2022 | 30 | DAS ENTERPRISE | 4.79 | 0 | 0
12 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Delivary line with M.S FOR Connection of KAIJALI BUSTY WSS under Jainti TG Water Supply Scheme . | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000087/2022-2023 | 451/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.94 | 0 | 66
13 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Kaijali Basti Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000110/2022-2023 | 702/ALD | 08/06/2022 | 30 | NARENDRA BHADANI. | 4.98 | 4.98 | 66
14 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAIJALI BUSTY water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000210/2020-2021 | 1164/ALD | 15/12/2020 | 60 | GHOSH & SAHA CONSTRUCTION | 19.93 | 4.39 | 68
15 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of pipe line for Turturi Khanda (Kaijali Busty Area), Culvert crossing and Laying Delivery line with DI and MS under Kaijali Busty TG WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000329/2021-2022 | 2202/ALD | 11/01/2022 | 60 | TAPASH KUMAR BHOWMICK | 41.95 | 14.92 | 66
16 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of HDPE/DI pipeline for TURTURI TG area, Kaijali Busty PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000480/2021-2022 | 2899/ALD | 08/03/2022 | 60 | ASHOK SAPKOTA | 34.24 | 0 | 68
17 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | RTOR000004/2022-2023 | 396/ALD | 11/05/2022 | 0 | Resource Division | 9.83 | 0 | 0
18 | Alipurduar Division | Birpara Sub-Division | Providing House connection for PASCHIM KHAYERBARI water supply scheme at MADARIHAT-BIRPARA Block under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000159/2020-2021 | 871/ALD | 14/10/2020 | 30 | NARENDRA BHADANI. | 4.98 | 8.97 | 93
19 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Paschim Khayerbari water supply scheme at Madarihat-Birpara Block under Alipuduar Division, P.H.E. Dte.(Part-III) | Birpara A.E | Birpara Sub Division | ORD/000213/2020-2021 | 1133/ALD | 10/12/2020 | 30 | NARENDRA BHADANI. | 4.98 | 4.98 | 92
20 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS Distribution pipe line and other misc. work for retrofitting of Paschim Khayerbari WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(Part-II) | Birpara A.E | Birpara Sub Division | ORD/000231/2020-2021 | 1177/ALD | 15/12/2020 | 60 | MATARA CONSTRUCTION CO | 45.1 | 42.34 | 92
21 | Alipurduar Division | Birpara Sub-Division | Restotation of pipeline by providing steel piles for JJM at Paschim Khairbari WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000235/2022-2023 | 1227/ALD | 10/08/2022 | 30 | MATARA CONSTRUCTION CO | 1.3 | 0 | 62
22 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc work for retrofitting of PASCHIM KHAYERBAR WSS under Birpara Sub-Division, Alipurduar Division,PHE Dte. Part-I | Birpara A.E | Birpara Sub Division | ORD/000236/2020-2021 | 1181/ALD | 15/12/2020 | 60 | SANJIT SAHA | 43.88 | 16.68 | 100
23 | Alipurduar Division | Birpara Sub-Division | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000264/2020-2021 | 1255/ALD | 28/12/2020 | 60 | MITHUN DAS | 45.83 | 36.48 | 80
24 | Alipurduar Division | Birpara Sub-Division | Providing House connection for PASCHIM KHAYERBARI water supply scheme at Madarihat-Birpara Block under Alipuduar Division, P.H.E. Dte. Part-II | Birpara A.E | Birpara Sub Division | ORD/000219/2020-2021 | 1170/ALD | 15/12/2020 | 60 | MITHUN DAS | 29.88 | 29.88 | 91
25 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS Distribution pipe line and other misc. work for retrofitting of Paschim Khayerbari WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(Part-II) | Birpara A.E | Birpara Sub Division | ORD/000231/2020-2021 | 1177/ALD | 15/12/2020 | 60 | MATARA CONSTRUCTION CO | 45.1 | 21.58 | 92
26 | Alipurduar Division | Birpara Sub-Division | Restotation of pipeline by providing steel piles for JJM at Paschim Khairbari WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000235/2022-2023 | 1227/ALD | 10/08/2022 | 30 | MATARA CONSTRUCTION CO | 1.3 | 1.26 | 62
27 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc work for retrofitting of PASCHIM KHAYERBAR WSS under Birpara Sub-Division, Alipurduar Division,PHE Dte. Part-I | Birpara A.E | Birpara Sub Division | ORD/000236/2020-2021 | 1181/ALD | 15/12/2020 | 60 | SANJIT SAHA | 43.88 | 14.43 | 100
28 | Alipurduar Division | Birpara Sub-Division | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000264/2020-2021 | 1255/ALD | 28/12/2020 | 60 | MITHUN DAS | 45.83 | 0 | 80
29 | Alipurduar Division | Birpara Sub-Division | Providing House connection for DHEKLAPARA PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED PART 1 | Birpara A.E | Birpara Sub Division | ORD/000082/2020-2021 | 634/ALD | 03/09/2020 | 90 | DILIP MAHATO | 21.8 | 14.92 | 0
30 | Alipurduar Division | Birpara Sub-Division | Preparation of Augmentation D.P.R after investigation For Jateswar W/S scheme under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000111/2021-2022 | 914/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.31 | 0.32 | 0
31 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE/DI pipe line at different area of flank of Dheklapara Bandapani under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000180/2020-2021 | 1005/ALD | 12/11/2020 | 60 | M/S PALIT ENTERPRISE | 11.75 | 41.37 | 48
32 | Alipurduar Division | Birpara Sub-Division | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Birpara A.E | Birpara Sub Division | ORD/000184/2020-2021 | 1009/ALD | 12/11/2020 | 60 | M/S PALIT ENTERPRISE | 14.4 | 8.95 | 70
33 | Alipurduar Division | Birpara Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 15 | 100
34 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 0
35 | Alipurduar Division | Birpara Sub-Division | Fuel bill for the month of August 2021 | Birpara A.E | Birpara Sub Division | VCH/000569/2021-2022 | 120/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.18 | 0 | 0
36 | Alipurduar Division | Birpara Sub-Division | Supply, delivery and Installation of split type Air Conditioner for Chamber of Assistant Engineer, Alipurduar, Sadar Sub-Division, P.H.E Dte. | Birpara A.E | Birpara Sub Division | ORD/000301/2022-2023 | 1731/ALD | 22/09/2022 | 7 | M/S BADAL CHANDRA SAHA | 0.64 | 0.64 | 20
37 | Alipurduar Division | Birpara Sub-Division | Supply, delivery and Installation of split type Air Conditioner for Junior Engineer Section of Alipurduar, Sadar Sub-Division, P.H.E Dte. | Birpara A.E | Birpara Sub Division | ORD/000302/2022-2023 | 1732/ALD | 22/09/2022 | 7 | M/S BADAL CHANDRA SAHA | 0.64 | 0.64 | 20
38 | Alipurduar Division | Birpara Sub-Division | Retrofitting of pipeline for Ramjhora TG PWSS area at Madarihat-Birpara Block under Alipurduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000316/2020-2021 | 1447/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 16.96 | 0 | 58
39 | Alipurduar Division | Birpara Sub-Division | Laying of balance DI/MS/HDPE pipeline for the Dalmore-Ramjhora WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000324/2020-2021 | 1456/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 21.28 | 0 | 59
40 | Alipurduar Division | Birpara Sub-Division | Repairing bottom dome, conical, shell wall etc. of existing Dalmore 350 cum OHR including protective and Decorative Acrylic exterior paint of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/07132) | Birpara A.E | Birpara Sub Division | ORD/000508/2023-2024 | 826/ALD | 14/03/2024 | 90 | BHAGWATI BHUJEL | 4.79 | 4.79 | 100
41 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipe line for Dalmore Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000524/2021-2022 | 2996/ALD | 15/03/2022 | 60 | MS DEYS CONSTRUCTION | 8.33 | 0 | 58
42 | Alipurduar Division | Birpara Sub-Division | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000072/2021-2022 | 879/ALD | 03/09/2021 | 60 | TAPASH KUMAR BHOWMICK | 45.7 | 25.94 | 76
43 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 73
44 | Alipurduar Division | Birpara Sub-Division | Preparation of Augmentation D.P.R after investigation For Purba Kathalbari W/S scheme under Alipurduar Division. | Alipurduar RWS | Birpara Sub Division | ORD/000108/2021-2022 | 911/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.14 | 4.28 | 0
45 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000148/2020-2021 | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 0.24 | 79
46 | Alipurduar Division | Birpara Sub-Division | Providing House connection for PATLAKHAWA water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte. Part-IV | Alipurduar RWS | Birpara Sub Division | ORD/000221/2020-2021 | 1172/ALD | 15/12/2020 | 60 | SOUVIK ROY PALADHI | 23.92 | 12.68 | 79
47 | Alipurduar Division | Birpara Sub-Division | Laying of DI pipeline, painting, plastering, land development and other misc works related to Patlakhawa OHR under Patlakhawa PWSS at Alipurduar-I Block, under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000286/2021-2022 | 1855/ALD | 13/12/2021 | 45 | TAPAN CHANDA | 4.26 | 2.62 | 77
48 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | Alipurduar RWS | Birpara Sub Division | ORD/000468/2021-2022 | 2766/ALD | 25/02/2022 | 60 | TAPASH KUMAR BHOWMICK | 42.34 | 0 | 75
49 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for TOTOPARA PWSS under madarihat - Birpara Block under Alipurduar Division PHE Dte. | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000044/2025-2026 | 669/ALD | 21/05/2025 | 90 | DULAL DAS | 23.27 | 0 | 0
50 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.01.2022 to 31.12.2022) | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000306/2021-2022 | 2013/ALD | 29/12/2021 | 365 | MATRI ENTERPRISE | 1.76 | 0 | 0
51 | Alipurduar Division | Birpara Sub-Division | Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. in soft copy.(Part-B) | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000515/2020-2021 | 844/ALD | 13/10/2020 | 60 | TAPASH KUMAR BHOWMICK | 0.98 | 1.96 | 0
52 | Alipurduar Division | Birpara Sub-Division | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. (Part-B) | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000516/2020-2021 | 845/ALD | 13/10/2020 | 60 | TAPASH KUMAR BHOWMICK | 0.96 | 1.92 | 0
53 | Alipurduar Division | Birpara Sub-Division | Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. in soft copy.(Part-C) | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000517/2020-2021 | 1091/ALD | 02/12/2020 | 60 | HARIDAS GHOSH | 0.98 | 1.96 | 0
54 | Alipurduar Division | Birpara Sub-Division | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. (Part-C) | Birpara A.E | RWS Madarihat - Birpara Block | ORD/000518/2020-2021 | 1092/ALD | 02/12/2020 | 60 | HARIDAS GHOSH | 0.96 | 1.92 | 0
55 | Alipurduar Division | Alipurduar Division | Balance work of OHR Construction of PHouse B/Wall Godown & ODEX-165 Tubewell incl. laying of DI/HDPE Pipe for Nayabasti SSB Camp at RADHARANI PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000076/2020-2021 | 627/ALD | 03/09/2020 | 120 | UMWELT ENGINEER PVT. LTD. | 65.53 | 6.18 | 92
56 | Alipurduar Division | Alipurduar Division | Balance work of construction of RADHARANI GODOWN cum REST SHED at RADHARANI WSS under Alipurduar Division , PHE Dte ( Part - A) | HQ-A.E | RWS Kalchini Block | ORD/000090/2022-2023 | 454/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 5.02 | 4.79 | 92
57 | Alipurduar Division | Alipurduar Division | Construction of Approach Road with paver Block at RADHARANI WSS under Alipurduar Division , PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000091/2022-2023 | 455/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 4.96 | 4.66 | 92
58 | Alipurduar Division | Alipurduar Division | Plinth protection of office cum GODOWN surface dressing & land development (H/W) at RADHARANI WSS under Alipurduar Division , PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000093/2022-2023 | 457/ALD | 13/05/2022 | 30 | DILIP MAHATO | 4.39 | 3.84 | 82
59 | Alipurduar Division | Alipurduar Division | Construction of Approach road for 2nd TWS & others misc work of Radharani WSS under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000106/2021-2022 | 904/ALD | 03/09/2021 | 30 | SOUVIK ROY PALADHI | 4.98 | 1.35 | 86
60 | Alipurduar Division | Alipurduar Division | Balance work of Radharani Godown cum rest shed under Radharani WSS under Alipurduar Division, PHE Dte. (Part-B) | HQ-A.E | RWS Kalchini Block | ORD/000186/2022-2023 | 1020/ALD | 21/07/2022 | 30 | ASHOK PRADHAN | 2.82 | 2.77 | 89
61 | Alipurduar Division | Alipurduar Division | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-1 | HQ-A.E | RWS Kalchini Block | ORD/000196/2020-2021 | 1027/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 0 | 92
62 | Alipurduar Division | Alipurduar Division | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | HQ-A.E | RWS Kalchini Block | ORD/000197/2020-2021 | 1028/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 0 | 91
63 | Alipurduar Division | Alipurduar Division | Laying HDPE pipe , Road crossing and other misc woks related to Radharani WSS under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000272/2021-2022 | 1838/ALD | 10/12/2021 | 45 | UMWELT ENGINEER PVT. LTD. | 3.01 | 2.35 | 91
64 | Alipurduar Division | Alipurduar Division | Balance work of office cum Godown at Radharani WSS under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000273/2021-2022 | 1839/ALD | 10/12/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 4.97 | 5.18 | 92
65 | Alipurduar Division | Alipurduar Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 72
66 | Alipurduar Division | Alipurduar Division | Construction of Pump House, Boundary wall, Tube well boring (ODEX- 165 Method) Rising main of 4th T/W site of Radharani TG WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000298/2022-2023 | 1689/ALD | 20/09/2022 | 120 | BHAGWATI BHUJEL | 20.53 | 19.48 | 100
67 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipe line for Bijaynagar Busty Area under Radharani Water Supply Scheme, Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000328/2021-2022 | 2201/ALD | 11/01/2022 | 60 | SOUVIK ROY PALADHI | 41.96 | 6.57 | 92
68 | Alipurduar Division | Alipurduar Division | Providing FHTC at surrounding area of Radharani Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000476/2021-2022 | 2762/ALD | 25/02/2022 | 60 | SOUVIK ROY PALADHI | 34.95 | 24.47 | 92
69 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar RWS | Birpara Sub Division | ORD/000277/2021-2022 | 1844/ALD | 10/12/2021 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 2.02 | 87
70 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar RWS | Birpara Sub Division | ORD/000280/2021-2022 | 1843/ALD | 10/12/2021 | 1422 | PROJIT HALDER | 5.02 | 2.18 | 87
71 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BANCHUKAMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | Birpara Sub Division | ORD/000315/2021-2022 | 2191/ALD | 11/01/2022 | 90 | HITANGSHU CHOUDHURY | 21.92 | 19.14 | 56
72 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000378/2021-2022 | 2378/ALD | 31/01/2022 | 60 | SHIBA ENTERPRISE | 51.82 | 9.81 | 87
73 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension and replacement of damaged pipeline and providing house connection at Salsalabari area under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000082/2021-2022 | 978/ALD | 13/09/2021 | 180 | HARIDAS GHOSH | 17.44 | 5.95 | 100
74 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000148/2020-2021 | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 0.09 | 79
75 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for FALAKATA AUG. piped water supply scheme (Subhaspally area, right side of NH) under Alipuduar Division, P.H.E. Dte. Part-5 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000248/2020-2021 | 1248/ALD | 28/12/2020 | 60 | BILTU DAS | 29.59 | 0.09 | 82
76 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under SALSALABARI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000267/2020-2021 | 1279/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 45.43 | 37.63 | 97
77 | Alipurduar Division | Alipurduar Sadar Sub-Division | "Providing House Connection (FHTC) at Salsalabari WSS under Alipurduar Division, PHE Dte. Part-5" | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000339/2021-2022 | 2115/ALD | 05/01/2022 | 30 | MATRI ENTERPRISE | 5.04 | 5.04 | 97
78 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 10 | 100
79 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Salsalabari Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000469/2021-2022 | 2765/ALD | 25/02/2022 | 1140 | NARENDRA BHADANI. | 47.7 | 29.58 | 97
80 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 0
81 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE pipeline for Hantapara Topline under Hatapara WSS within Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000429/2021-2022 | 2627/ALD | 18/02/2022 | 60 | DILIP MAHATO | 16.19 | 0 | 69
82 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for HANTUPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000433/2021-2022 | 2713/ALD | 23/02/2022 | 90 | SUBIR GHOSH | 25.31 | 7.67 | 41
83 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of additional dedicated HDPE pipeline near PH No-1 village for the Hantapara WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000482/2021-2022 | 2904/ALD | 08/03/2022 | 60 | SUBIR GHOSH | 11.78 | 8.03 | 39
84 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for DAKSHIN PAITKAPARA PWSS under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000011/2022-2023 | 21/ALD | 01/04/2022 | 120 | SOUVIK ROY PALADHI | 230.7 | 10.07 | 55
85 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 90 | ANUP GUPTA | 20.99 | 10.6 | 80
86 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 2nd TW site of PAITKAPARA PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000573/2024-2025 | 5387/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.79 | 0 | 0
87 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at HEADWORK site of PAITKAPARA PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000575/2024-2025 | 5389/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.95 | 0 | 0
88 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 3rd site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000066/2022-2023 | 338/ALD | 02/05/2022 | 883 | SUBRATA DAS | 24.16 | 22.94 | 8
89 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at 4th site for SALKUMARHAT PWSS Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000067/2022-2023 | 339/ALD | 02/05/2022 | 980 | SHYAMAL ROY | 24.17 | 9.7 | 100
90 | Alipurduar Division | Birpara Sub-Division | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 0 | 62
91 | Alipurduar Division | Birpara Sub-Division | Providing balance FHTC and construction of new sluice valve chamber for controlling water including laying UPVC pipe at leftout area of Chhoto Salkumar PWSS and other allied works adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000103/2025-2026 | 1188/ALD | 26/06/2025 | 90 | M/S DUTTA AND CO | 26.37 | 0 | 0
92 | Alipurduar Division | Birpara Sub-Division | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Salkumarhat PWSS within APD-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000104/2025-2026 | 1222/ALD | 01/07/2025 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 53.57 | 0 | 0
93 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumarhat Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000131/2021-2022 | 1242/ALD | 27/09/2021 | 60 | KAMALESH ROY | 25.25 | 4.65 | 9
94 | Alipurduar Division | Birpara Sub-Division | Repairing of Pump house at 3rd site of Chhoto Salkumar adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000159/2025-2026 | 1744/ALD | 13/08/2025 | 60 | ANIRBAN DEY SARKAR CONSTRUCTION | 2.31 | 0 | 0
95 | Alipurduar Division | Birpara Sub-Division | Painting of Old OHR (350 cum) at Chhoto Salkumar adjacent to Augmentation of Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000198/2025-2026 | 2105/ALD | 23/09/2025 | 60 | NARENDRA BHADANI. | 3.04 | 0 | 0
96 | Alipurduar Division | Birpara Sub-Division | Cons. Of Rising line, pathway, surface drain, laying of DI and UPVC pipeline and restoration of FHTC at Salkumarhat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000222/2023-2024 | 1582/ALD | 24/08/2023 | 90 | TAPASH DAS | 18.46 | 14.21 | 5
97 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
98 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Salkumarhat PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000479/2021-2022 | 2898/ALD | 08/03/2022 | 1381 | DILIP MAHATO | 48.52 | 0 | 65
99 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 2nd site of SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000570/2024-2025 | 5385/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.79 | 0 | 0
100 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at HEADWORK site of SALKUMARHAT PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000576/2024-2025 | 5390/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.94 | 0 | 0
101 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte. (from 01.04.2025 to 31.03.2026) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000602/2024-2025 | 5302/ALD | 28/03/2025 | 365 | DIPAK DAS | 4.8 | 0 | 0
102 | Alipurduar Division | Birpara Sub-Division | Distribution line for Barobisha (Zone-III) water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | HQ-A.E | Birpara Sub Division | ORD/000109/2020-2021 | 730/ALD | 22/09/2020 | 45 | TAPAN CHANDA | 5 | 9.21 | 0
103 | Alipurduar Division | Birpara Sub-Division | Providing House connection for PURBA KATHALBARI water supply scheme at ALIPURDUAR-I Block under Alipuduar Division, P.H.E. Dte. | HQ-A.E | Birpara Sub Division | ORD/000164/2020-2021 | 908/ALD | 16/10/2020 | 30 | SREE MAA CONSTRUCTION & CO. | 4.98 | 6.89 | 0
104 | Alipurduar Division | Birpara Sub-Division | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 0.49 | 69
105 | Alipurduar Division | Birpara Sub-Division | Providing House connection for UTTAR LATABARI piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | Birpara Sub Division | ORD/000242/2020-2021 | 1244/ALD | 28/12/2020 | 60 | SHIB RATAN BHOWMIK | 9.97 | 9.97 | 0
106 | Alipurduar Division | Birpara Sub-Division | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-A | HQ-A.E | Birpara Sub Division | ORD/000273/2020-2021 | 1285/ALD | 05/01/2021 | 60 | ASHOK SAPKOTA | 22.45 | 38.24 | 46
107 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | HQ-A.E | Birpara Sub Division | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 2.89 | 72
108 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | HQ-A.E | Birpara Sub Division | VCH/000942/2020-2021 | 570/20-21 | 26/03/2021 | 0 | GOUTAM KUMAR DAS | 15 | 0 | 0
109 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of pump house at headwork site of Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000041/2025-2026 | 666/ALD | 21/05/2025 | 60 | SHYAMAL ROY | 1.02 | 0 | 0
110 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of damaged FHTCs, Replacement of old damaged pipeline at Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000063/2025-2026 | 815/ALD | 03/06/2025 | 60 | SHYAMAL ROY | 6.23 | 0 | 0
111 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of Pump House at 2nd TW site of BAKLA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000154/2025-2026 | 1591/ALD | 31/07/2025 | 60 | SHYAMAL ROY | 0.95 | 0 | 0
112 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Bakla PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000206/2023-2024 | 1560/ALD | 23/08/2023 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 2.47 | 2.44 | 99
113 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new UPVC pipeline and others allied works for providing functional household Tap Connection(FHTC) in connection with the Augmentation of Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000321/2022-2023 | 2230/ALD | 21/11/2022 | 840 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 42.04 | 40.79 | 23
114 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000351/2023-2024 | 2603/ALD | 04/12/2023 | 90 | SHYAMAL ROY | 32.04 | 4.74 | 50
115 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land Development, Paver Block installation and Laying and distribution of UPVC pipeline at 2nd Pumphouse site and Adjacent Area of Bakla PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000487/2022-2023 | 3319/ALD | 13/03/2023 | 90 | SHYAMAL ROY | 11.1 | 10.92 | 100
116 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including providing FHTC, laying distribution system and Rising main for Gangutia Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000003/2022-2023 | 13/ALD | 01/04/2022 | 120 | SHREE RANISATI ENTERPRISE | 193.63 | 124.7 | 67
117 | Alipurduar Division | Birpara Sub-Division | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 58
118 | Alipurduar Division | Birpara Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Gangutia Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000115/2022-2023 | 707/ALD | 08/06/2022 | 30 | DAS CONSTRUCTION | 4.89 | 4.89 | 68
119 | Alipurduar Division | Birpara Sub-Division | Construction of OHR 200cum for Gangutia Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000420/2021-2022 | 2599/ALD | 17/02/2022 | 180 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 55.36 | 24.23 | 68
120 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 0
121 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000030/2022-2023 | 1704/ALD | 21/09/2022 | 0 | Resource Division | 61.51 | 0 | 0
122 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe line by DI pipe(with piller ) along the flack of Alipurduar - Bhatibari - Salsalabari Road of Chandijhar WSS under Alipurduar Division , PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000075/2022-2023 | 440/ALD | 13/05/2022 | 30 | SREE MAA CONSTRUCTION | 4.59 | 4.52 | 9
123 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000164/2021-2022 | 1305/ALD | 05/10/2021 | 60 | SASANKA ROY | 50.06 | 0 | 36
124 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of pump house at headwork site of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000175/2025-2026 | 1857/ALD | 26/08/2025 | 60 | HARI CONSTRUCTION | 1.01 | 0 | 0
125 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Laying of UPVC/DI pipeline,and other allied works including filling of gap in the distribution system for Augmentation of Chandirjhar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000231/2022-2023 | 1228/ALD | 10/08/2022 | 30 | MATRI ENTERPRISE | 3.21 | 2.87 | 8
126 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land development of 3rd Tubewell site at Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000236/2022-2023 | 1232/ALD | 10/08/2022 | 30 | DULAL DAS | 1.36 | 1.26 | 9
127 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF Specials & Jeffy Coupling for Augmentation of Chandirjhar (SM/10677) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000402/2024-2025 | 4538/ALD | 26/12/2024 | 30 | MAHENDRA CHHETRI | 19.05 | 0 | 0
128 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
129 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
130 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of 90 mm HDPE pipeline in uncovered area and construction of excess work of boundary wall and 3 m span open foundation culvert with boulder protection works and other allied works at 2nd site of Shrinathpur TG PWSS under alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000131/2025-2026 | 1628/ALD | 04/08/2025 | 75 | PRAPTI DUTTA | 11.82 | 0 | 0
131 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline for providing FHTC in the Command area of Shrinathpur TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000193/2023-2024 | 1469/ALD | 16/08/2023 | 60 | CHANDAN KIRTONIA | 13 | 13 | 100
132 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway, surface drain and chatal, land development, along with other allied works at Shrinathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000194/2023-2024 | 1470/ALD | 16/08/2023 | 420 | KAMALESH ROY | 12.83 | 4.56 | 50
133 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE/DI pipeline and other allied works for providing FHTC in connection with the Shrinathpur TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000195/2023-2024 | 1471/ALD | 16/08/2023 | 420 | KAMALESH ROY | 32.95 | 30.78 | 100
134 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Srinathpur TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000232/2023-2024 | 1599/ALD | 25/08/2023 | 30 | GIRIRAJ ENTERPRISE | 6.7 | 6.56 | 98
135 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline (Part- B) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000286/2022-2023 | 1640/ALD | 19/09/2022 | 60 | TAPASH KUMAR BHOWMICK | 55.91 | 45.38 | 50
136 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline (Part- C) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000287/2022-2023 | 1641/ALD | 19/09/2022 | 960 | DAS CONSTRUCTION | 58.4 | 54.08 | 45
137 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline (Part- D) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000288/2022-2023 | 1642/ALD | 19/09/2022 | 900 | KAMALESH ROY | 45.33 | 31.15 | 100
138 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline (Part- E) and providing FHTC and others allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000289/2022-2023 | 1643/ALD | 19/09/2022 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 55.49 | 49.11 | 45
139 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline (Part-F) with Rising Main and delivery line connection, providing FHTC and other allied works for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000290/2022-2023 | 1644/ALD | 19/09/2022 | 60 | TAPAN CHANDA | 49.13 | 35.12 | 44
140 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land Development, paver block installation and laying of distribution of UPVC Pipeline at 2nd Pump House site and adjacent area of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000290/2023-2024 | 2014/ALD | 15/09/2023 | 60 | SAMIR SARKAR | 6.97 | 2.97 | 100
141 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline (Part- G) with Rising Main and delivery line connection for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000291/2022-2023 | 1645/ALD | 19/09/2022 | 360 | DEBAJYOTI SUTRADHAR | 62.99 | 61.3 | 45
142 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE pipeline (Part-H) with Rising Main and delivery line connection for SHRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000292/2022-2023 | 1646/ALD | 19/09/2022 | 60 | MADHAB SAHA | 56.38 | 54.16 | 45
143 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works at head works site for SRINATHPUR TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000311/2022-2023 | 2135/ALD | 10/11/2022 | 30 | MOYTEC | 0.7 | 0.7 | 100
144 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new DI line & Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at HW site of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000336/2022-2023 | 2245/ALD | 21/11/2022 | 120 | TRIBENI CONSTRUCTION | 14.48 | 0 | 0
145 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new DI line and Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at 2nd site of Shrinathpur TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000337/2022-2023 | 2246/ALD | 21/11/2022 | 660 | PRAPTI DUTTA | 11.32 | 11.07 | 100
146 | Alipurduar Division | Alipurduar Sadar Sub-Division | 2 nos Tube well boring by ODEX-165 Method of drilling for the works implementation of Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000354/2022-2023 | 2499/ALD | 13/12/2022 | 45 | S.G. CONSTRUCTION | 13.14 | 10.24 | 0
147 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system the new HDPE pipeline (Part-A) with rising and delivery line connection, providing FHTC and others allied works for Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000392/2022-2023 | 2657/ALD/ | 22/12/2022 | 600 | DEBAJYOTI SUTRADHAR | 96.35 | 94.46 | 95
148 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 300 cum OHR as per departmental design and drawing, soil investigation work, laying of DI/CI pipeline, supplying of CI Specials and other allied works at headwork site of Shrinathpur Tea Garden Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000412/2022-2023 | 2690/ALD | 23/12/2022 | 180 | KAMALESH ROY | 93.98 | 90.03 | 100
149 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000413/2022-2023 | 2728/ALD | 30/12/2022 | 365 | APSARI BHOWMICK | 4.8 | 0 | 0
150 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000024/2023-2024 | 1269/ALD | 11/08/2023 | 0 | Resource Division | 21.78 | 0 | 0
151 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000118/2023-2024 | 142/ALD | 10/01/2024 | 0 | Resource Division | 10.48 | 0 | 0
152 | Alipurduar Division | Alipurduar Division | Laying distribution system along with the other allied works at Santalabari under Augmentation of Jainti Wter Supply Scheme under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000209/2022-2023 | 1278/ALD | 17/08/2022 | 60 | ASHOK SAPKOTA | 22.72 | 22.51 | 63
153 | Alipurduar Division | Alipurduar Division | Extension pipeline (HDPE) for providing FHTC at Santalbari area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000222/2021-2022 | 1619/ALD | 23/11/2021 | 60 | M/S BHOWMICK CONSTRUCTION | 24.53 | 23.54 | 60
154 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipeline for restoration of damaged pipeline and others allied works for Jainty WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000346/2022-2023 | 2490/ALD | 13/12/2022 | 30 | TAPASH KUMAR BHOWMICK | 2.14 | 2.14 | 64
155 | Alipurduar Division | Alipurduar Division | Land development, construction of pathway of HWS and 2nd site of different sluice valve chamber and concrete blocks for MS pipe Jainti TG (Nimbu Dhora) WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000349/2022-2023 | 2491/ALD | 13/12/2022 | 60 | DAS CONSTRUCTION | 9.41 | 0 | 0
156 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000354/2021-2022 | 2119/ALD | 05/01/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.28 | 0 | 71
157 | Alipurduar Division | Alipurduar Division | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000431/2021-2022 | 2629/ALD | 18/02/2022 | 60 | GHOSH & SAHA CONSTRUCTION | 13.4 | 3.48 | 64
158 | Alipurduar Division | Alipurduar Division | Land development, construction of new pathway, surface drain (2nd site near Tea Factory) and other misc. works related to Jayanti TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000559/2022-2023 | 3503/ALD | 23/03/2023 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.39 | 0 | 0
159 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000023/2023-2024 | 1261/ALD | 10/08/2023 | 0 | Resource Division | 7.92 | 0 | 0
160 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of DI pipe & CI special for Baruipara PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000045/2023-2024 | 391/ALD | 19/05/2023 | 30 | HARI CONSTRUCTION | 34.33 | 34.27 | 90
161 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI Pipeline for interconnection in the distribution system and bridge/culvert crossing and other allied works in connection with Baruipara PWSS Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000050/2025-2026 | 675/ALD | 21/05/2025 | 90 | TAPAN CHANDA | 29.05 | 0 | 50
162 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
163 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Baruipara PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000211/2023-2024 | 1565/ALD | 24/08/2023 | 30 | RAMEN DEY & CO | 4.89 | 0 | 0
164 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 Cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for BARUIPARA PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000429/2022-2023 | 2856/ALD | 17/01/2023 | 985 | TAPAN CHANDA | 403.77 | 186.44 | 80
165 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
166 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000033/2023-2024 | 1278/ALD | 11/08/2023 | 0 | Resource Division | 12.57 | 0 | 0
167 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000044/2024-2025 | 4260/ALD | 13/12/2024 | 0 | Resource Division | 13.75 | 0 | 0
168 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000103/2023-2024 | 127/ALD | 10/01/2024 | 0 | Resource Division | 8.85 | 0 | 0
169 | Alipurduar Division | Alipurduar Division | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Nimti Domohini Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000058/2025-2026 | 786/ALD | 30/05/2025 | 30 | MADHAB SAHA. | 10.8 | 0 | 0
170 | Alipurduar Division | Alipurduar Division | 1 Nos TW boring of ODEX-165 for additional T/W for 3rd site of Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000069/2025-2026 | 967/ALD | 12/06/2025 | 30 | CHINMOY BHATTACHARJEE | 8.07 | 0 | 0
171 | Alipurduar Division | Alipurduar Division | Construction of 1no Pump house, boundary wall and other allied works at 3rd TW Site of Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000163/2025-2026 | 1771/ALD | 18/08/2025 | 120 | SATYABRATA BHATTACHERJEE | 21.28 | 0 | 0
172 | Alipurduar Division | Alipurduar Division | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Nimtijhora Domohoni Water Supply Scheme (SM/13244) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000215/2024-2025 | 2067/ALD | 12/07/2024 | 30 | MANSAROVAR CASTING | 9.63 | 9.63 | 100
173 | Alipurduar Division | Alipurduar Division | Providing FHTC from existing distribution system as per specification for Nimti Domohani PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000267/2023-2024 | 1885/ALD | 07/09/2023 | 30 | DEBAJYOTI SUTRADHAR | 5.22 | 0 | 0
174 | Alipurduar Division | Alipurduar Division | Balance portion of 110 mm HDPE/DI pipe laying, boundary wall, pump house, land development for HWS and 1st site and platform for FHTC for Nimti Domohoni PWSS Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000475/2023-2024 | 693/ALD | 07/03/2024 | 449 | PINTU SAHA | 79.36 | 5.12 | 30
175 | Alipurduar Division | Alipurduar Division | Supply of DI specials and CI Jeffy coupling for Nimjhora TG Water Supply Scheme(SM/14215) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000535/2023-2024 | 851/ALD | 14/03/2024 | 30 | MANSAROVAR CASTING | 13.34 | 13.34 | 50
176 | Alipurduar Division | Alipurduar Division | Construction of 2 nos. Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Pump House , Boundary Wall, Path way including soil test, Providing FHTC and other allied works for NIMTI DOMOHANI PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000548/2022-2023 | 3571/ALD | 27/03/2023 | 480 | DOOARS CONSTRUCTION COMPANY | 446.14 | 376.24 | 90
177 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000081/2023-2024 | 105/ALD | 10/01/2024 | 0 | Resource Division | 9.02 | 0 | 0
178 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing and relaying of 90 mm dia damaged HDPE pipeline (from node-33 to 32 to 29 to 25) for Kartika PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000169/2025-2026 | 1777/ALD | 18/08/2025 | 45 | TAPASH DAS | 1.4 | 0 | 0
179 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Kartika TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000223/2023-2024 | 1594/ALD | 25/08/2023 | 30 | JUGAL CHOUDHURY | 6.76 | 5.59 | 68
180 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works for proposed overhead reservoir of KARTIKA TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000315/2022-2023 | 2224/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 0
181 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 method at 2nd TW Site, Cons. of Pump house and boundary wall at HW site, LDS with new HDPE pipeline (Part-B) with Rising Main and delivery line connection, providing FHTC and other allied works for Kartika Tea Garden PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000330/2022-2023 | 2239/ALD | 21/11/2022 | 120 | TAPASH DAS | 79.55 | 66.61 | 84
182 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new DI line and Supply of necessary specials, construction of sluice valve chamber, Construction of pump house and boundary wall at 2nd site of Kartika TG Area PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000338/2022-2023 | 2247/ALD | 21/11/2022 | 120 | MONORAMA ENTERPRISE | 10.8 | 9.7 | 78
183 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for KARTIKA TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000455/2022-2023 | 2976/ALD | 02/02/2023 | 180 | MAHENDRA CHHETRI | 238.07 | 191.37 | 90
184 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of DI specials and CI Jeffy coupling for Kartika TG Water Supply Scheme (SM/11991) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000522/2023-2024 | 841/ALD | 14/03/2024 | 30 | MANSAROVAR CASTING | 13.34 | 13.34 | 92
185 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000011/2023-2024 | 217/ALD | 03/05/2023 | 0 | Resource Division | 18.8 | 0 | 0
186 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000110/2023-2024 | 134/ALD | 10/01/2024 | 0 | Resource Division | 6.95 | 0 | 0
187 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works for proposed overhead reservoir of PHASKHAWA TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000316/2022-2023 | 2225/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 0
188 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House at Head Work site and providing FHTC and other allied works for Phaskhawa TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000319/2022-2023 | 2228/ALD | 21/11/2022 | 360 | PRITAM DAS | 9.88 | 6.8 | 51
189 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at Head work site of Phaskhawa TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000322/2022-2023 | 2231/ALD | 21/11/2022 | 90 | SANKAR ROY | 13.56 | 10.82 | 65
190 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at 2nd site of Phaskhawa TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000324/2022-2023 | 2233/ALD | 21/11/2022 | 90 | RAMEN DEY & CO | 9.7 | 9.17 | 94
191 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 method of drilling at 2nd TW Site, Construction of Pump house at 2nd site, laying of Rising Main and delivery line connection, providing FHTC and other allied works for Phaskhawa Tea Garden PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000329/2022-2023 | 2238/ALD | 21/11/2022 | 549 | ASHOK SAPKOTA | 22.24 | 20.8 | 100
192 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 200 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for PHASKHAWA TEA GARDEN PWSS under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division | Birpara Sub Division | ORD/000456/2022-2023 | 2977/ALD | 02/02/2023 | 180 | DILIP MAHATO | 133.11 | 96.44 | 61
193 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division | Birpara Sub Division | RTOR000013/2023-2024 | 219/ALD | 03/05/2023 | 0 | Resource Division | 13.81 | 0 | 0
194 | Alipurduar Division | Alipurduar Sadar Sub-Division | Road Restoration of Volka Road against Brajerkuthi PWSS | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00320/2024-2025 | 189/24-25/PFMS | 10/09/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 10.73 | 0 | 0
195 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Brajerkuthi PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000209/2023-2024 | 1563/ALD | 23/08/2023 | 508 | TAPASH KUMAR BHOWMICK | 6.25 | 0 | 0
196 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Brajerkuti WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000230/2023-2024 | 1602/ALD | 25/08/2023 | 30 | TAPASH KUMAR BHOWMICK | 6.76 | 6.76 | 99
197 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Brajerkuti PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000349/2023-2024 | 2601/ALD | 04/12/2023 | 404 | TAPASH KUMAR BHOWMICK | 77.06 | 52.52 | 25
198 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new additional pipeline opposite flanks of the higher dia UPVC pipeline and to connect the scattered house with the distribution system in view of providing FHTC, bridge/culvert crossing, Construction of Sluice Valve Chamber, trial run and others allied works in connection with the Brajerkuthi PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000409/2024-2025 | 4583/ALD | 02/01/2025 | 60 | TAPASH KUMAR BHOWMICK | 35.65 | 0 | 0
199 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. Big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 Cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for Brajerkuthi PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000428/2022-2023 | 2855/ALD | 17/01/2023 | 804 | TAPASH KUMAR BHOWMICK | 460.44 | 415.1 | 95
200 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2023 to 31.01.2024) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000456/2023-2024 | 2340/ALD | 30/10/2023 | 92 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 0
201 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation for the work of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2023 to 31.01.2024) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000457/2023-2024 | 2341/ALD | 30/10/2023 | 92 | NIRANJAN KIRTANIA | 0.7 | 0.5 | 0
202 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
203 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Brajerkuthi Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000484/2023-2024 | 740/ALD | 12/03/2024 | 30 | TAPASH KUMAR BHOWMICK | 17.3 | 8.49 | 51
204 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000036/2023-2024 | 1474/ALD | 16/08/2023 | 0 | Resource Division | 38.52 | 0 | 0
205 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000117/2023-2024 | 141/ALD | 10/01/2024 | 0 | Resource Division | 11.38 | 0 | 0
206 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
207 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation work order for the work of 'Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/9/2024-EE(ALI_D) SEC-DPHE (Computer No-974282)) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000201/2024-2025 | 1915/ALD | 26/06/2024 | 60 | SOUVIK ROY PALADHI | 15.17 | 0 | 0
208 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC from existing distribution system as per specification for Atiabari TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000263/2023-2024 | 1881/ALD | 07/09/2023 | 30 | SOUVIK ROY PALADHI | 9.84 | 0 | 0
209 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of CIDI Pipes & UPVC pipeline and other allied works for Atiabari Tea Garden PWSS under ALipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000351/2024-2025 | 3421/ALD | 26/09/2024 | 60 | SOUVIK ROY PALADHI | 35.9 | 0 | 0
210 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil investigation works , 2nos pump house & boundary wall, providing FHTC and others allied works for ATIABARI TEA GARDEN PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000460/2022-2023 | 2981/ALD | 02/02/2023 | 540 | SOUVIK ROY PALADHI | 438.53 | 371.6 | 75
211 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
212 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF/CIPE pipes and specials and Sluice Valve for Atiabari TG Water Supply Scheme(SM/14092) of Kalchini Block under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000521/2023-2024 | 840/ALD | 14/03/2024 | 459 | MADHAB SAHA | 16.01 | 0 | 15
213 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000026/2023-2024 | 1271/ALD | 11/08/2023 | 0 | Resource Division | 35.15 | 0 | 0
214 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000034/2024-2025 | 4250/ALD | 13/12/2024 | 0 | Resource Division | 31.17 | 0 | 0
215 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000044/2023-2024 | 1952/ALD | 12/09/2023 | 0 | Resource Division | 129.38 | 0 | 0
216 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000072/2023-2024 | 2785/ALD | 18/12/2023 | 0 | Resource Division | 11.61 | 0 | 0
217 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
218 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000084/2025-2026 | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
219 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC from existing distribution system as per specification for Rajabhat TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000266/2023-2024 | 1884/ALD | 07/09/2023 | 300 | PRITAM DAS | 7.83 | 7.82 | 100
220 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
221 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 Method drilling at HW, First TW Site including laying distribution system with new UPVC PIPELINE, Cons. of 150cum OHR as per departmental Design & drawing , 2nos Pump House & boundary wall, providing FHTC, soil investigation works and others allied works for Rajabhat Tea Garden PWSS Under Alipurduar Division PHE DTE. (2nd call) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000477/2022-2023 | 3194/ALD | 27/02/2023 | 720 | ASHIM KUMAR GHOSH | 219.89 | 192.74 | 77
222 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000035/2022-2023 | 3015/ALD/2022-23 | 07/02/2023 | 0 | Resource Division | 13.69 | 0 | 0
223 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of TW, Cons. Of Pump House, boundary wall, OHR (400 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for BARIGURI PWSS under Alipurduar Division PHE DTE. (2nd call) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000029/2023-2024 | 333/ALD | 16/05/2023 | 720 | MESSRS A.B.G CONSTRUCTION | 592.24 | 248.77 | 4
224 | Alipurduar Division | Alipurduar RWS Sub-Division | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Bairiguri Water Supply(SM/13246) of Alipurduar-I Block Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000216/2024-2025 | 2068/ALD | 12/07/2024 | 30 | BARMAN ENTERPRISE | 11.35 | 10.11 | 100
225 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC from existing distribution system as per specification for Bariguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000259/2023-2024 | 1877/ALD | 07/09/2023 | 30 | DAS CONSTRUCTION | 8.1 | 0 | 0
226 | Alipurduar Division | Alipurduar RWS Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
227 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC in school in Paitkapara PWSS under Alipurduar Division P.H.E Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000492/2022-2023 | 3356/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.07 | 0 | 100
228 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC in school in Banchukamari PWSS under Alipurduar Division P.H.E Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000493/2022-2023 | 3357/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.87 | 0 | 100
229 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000039/2024-2025 | 4254/ALD | 13/12/2024 | 0 | Resource Division | 38.94 | 0 | 0
230 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-I Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000082/2025-2026 | 1050/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
231 | Alipurduar Division | Alipurduar RWS Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
232 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Prodhanpara PWSS Under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000512/2022-2023 | 3394/ALD | 16/03/2023 | 838 | MESSRS A.B.G CONSTRUCTION | 425.86 | 169.6 | 20
233 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000009/2024-2025 | 3614/ALD | 24/10/2024 | 0 | Resource Division | 8.11 | 0 | 0
234 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000093/2023-2024 | 117/ALD | 10/01/2024 | 0 | Resource Division | 8.33 | 0 | 0
235 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for Ballalguri PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000258/2023-2024 | 1876/ALD | 07/09/2023 | 30 | RATAN DUTTA | 4.38 | 0 | 0
236 | Alipurduar Division | Birpara Sub-Division | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (100cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Ballalguri PWSS Under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000459/2022-2023 | 2980/ALD | 02/02/2023 | 847 | DILIP MAHATO | 255.82 | 177.55 | 70
237 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000463/2023-2024 | 162/ALD | 11/01/2024 | 366 | BHAGWATI BHUJEL | 4.8 | 0 | 0
238 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | RTOR000112/2023-2024 | 136/ALD | 10/01/2024 | 0 | Resource Division | 3.5 | 0 | 0
239 | Alipurduar Division | Birpara Sub-Division | New service connection charges for Mujnai Cha Sundori PH NO-VI under NMD-II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00392/2024-2025 | 20249706 | 02/12/2024 | 0 | WBSEDCL | 8.09 | 0 | 0
240 | Alipurduar Division | Birpara Sub-Division | CONS. OF BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 60 unit) CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000387/2020-2021 | 1946/ALD | 25/02/2021 | 840 | GHOSH & SAHA CONSTRUCTION | 36.68 | 22.66 | 100
241 | Alipurduar Division | Birpara Sub-Division | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 475 unit) CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000388/2020-2021 | 1947/ALD | 25/02/2021 | 812 | BILTU DAS | 113.04 | 82.72 | 80
242 | Alipurduar Division | Birpara Sub-Division | Supply and installation of sign board for different Cha Sundori projects under Madarihat -Birpara Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000397/2023-2024 | 208/ALD | 16/01/2024 | 30 | KOUSHIK BHOWMICK | 1.09 | 1.09 | 100
243 | Alipurduar Division | Birpara Sub-Division | Construction of tube wells (3 nos.) by Reverse rotary method of drilling Method of drilling at HW site, 2nd TW site and 3rd site, soil investigation at HW site, constructions of 100 Cum OHR at HW, construction of pump house and boundary wall at H/W, 2nd site and 3rd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dalmoney Tea Garden PWSS (Zone-I & Zone-II) Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000574/2022-2023 | 3635/ALD | 31/03/2023 | 180 | M/S HARI BHUSHAN GHOSH AND CO. | 202.87 | 0 | 10
244 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000042/2023-2024 | 1481/ALD | 16/08/2023 | 0 | Resource Division | 16.32 | 0 | 0
245 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000111/2023-2024 | 135/ALD | 10/01/2024 | 0 | Resource Division | 2.16 | 0 | 0
246 | Alipurduar Division | Birpara Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
247 | Alipurduar Division | Birpara Sub-Division | Soil investigation at OHR site, constructions of 300 Cum OHR at HW , distribution line and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000022/2023-2024 | 258/ALD | 08/05/2023 | 180 | DILIP MAHATO | 217.32 | 199.14 | 80
248 | Alipurduar Division | Birpara Sub-Division | Cons. of tube wells at 2nd site by Reverse rotary method of drilling, cons. of pump house and boundary wall at 2nd site, rising main, distribution line(C) and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000023/2023-2024 | 257/ALD | 08/05/2023 | 120 | PRAMESH LAMA | 176.9 | 61.7 | 10
249 | Alipurduar Division | Birpara Sub-Division | Cons. Of tube wells at H/W site by Reverse rotary method of drilling , cons. of pump house and boundary wall at H/W , rising main, distribution line(B) and providing FHTC as per Departmental Design & drawing for Khagenhat PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000053/2023-2024 | 422/ALD | 24/05/2023 | 1003 | MADHAB SAHA | 201.45 | 0 | 50
250 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline (parallel and balance line ) at Khagenhat PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000132/2025-2026 | 1627/ALD | 04/08/2025 | 75 | DILIP MAHATO | 77.79 | 0 | 0
251 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for Khagenhat PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000305/2023-2024 | 2170/ALD | 06/10/2023 | 60 | TAPASH DAS | 5.58 | 0 | 0
252 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
253 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte. (from 01.04.2025 to 31.03.2026) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000603/2024-2025 | 5304/ALD | 28/03/2025 | 365 | DILIP MAHATO (OPC) PRIVATE LIMITED | 4.85 | 0 | 0
254 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000077/2023-2024 | 101/ALD | 10/01/2024 | 0 | Resource Division | 12.67 | 0 | 0
255 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including providing FHTC and Rising main for SIDHABARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000005/2022-2023 | 15/ALD | 01/04/2022 | 120 | BILTU DAS | 181.3 | 116.95 | 56
256 | Alipurduar Division | Birpara Sub-Division | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 58
257 | Alipurduar Division | Birpara Sub-Division | Construction of 250cum OHR for Sidhabari Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000418/2021-2022 | 2585/ALD | 17/02/2022 | 180 | MS CTR CONSTRUCTION | 57.53 | 35.97 | 55
258 | Alipurduar Division | Birpara Sub-Division | Preparation of detailed D.P.R. booklets in connection to Sidhabari PWSS under Alipurduar-I Block under Alipurduar Division P.H.E Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000418/2022-2023 | 2821/ALD | 11/01/2023 | 30 | ANIK BHATTACHARJEE | 0.97 | 0.97 | 56
259 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE and distribution pipes in different suitable locations of Sidhabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000453/2022-2023 | 2970/ALD | 31/01/2023 | 90 | BILTU DAS | 165.16 | 58.58 | 61
260 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 60 | 0
261 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000016/2022-2023 | 827/ALD | 28/06/2022 | 0 | Resource Division | 25.2 | 0 | 0
262 | Alipurduar Division | Alipurduar Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-I Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000082/2025-2026 | 1050/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
263 | Alipurduar Division | Alipurduar Division | Constructions of 250 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of 2(TWO) NOS of BOUNDARY WALL, 3(THREE) NOS ODEX-165 TUBE WELL, 3(THREE) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for UTTAR MANDABARI PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000177/2023-2024 | 1113/ALD | 28/07/2023 | 720 | MAHENDRA CHHETRI | 736.75 | 575.12 | 77
264 | Alipurduar Division | Alipurduar Division | Supply of DIDF pipes and specials and Sluice Valve for Uttar Mendabari Water Supply (SM/16539) Scheme OF Kalchini Block under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000203/2024-2025 | 1952/ALD | 02/07/2024 | 30 | KAMALA VALVES AND ENGINEERING PRIVATE LIMITED | 16.5 | 0 | 85
265 | Alipurduar Division | Alipurduar Division | Providing balance FHTC from existing distribution system as per specification for UTTAR MANDABARI PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000281/2023-2024 | 1988/ALD | 15/09/2023 | 60 | SHYAMAL ROY | 11.35 | 0 | 0
266 | Alipurduar Division | Alipurduar Division | Construction of 1 no. pump house, boundary wall, 1 no. T/W boring by ODEX- 165 method of drilling at Uttar Mendabari pwss area under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000463/2024-2025 | 5297/ALD | 07/03/2025 | 120 | D.K & SONS | 20.47 | 0 | 0
267 | Alipurduar Division | Alipurduar Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
268 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000011/2024-2025 | 3946/ALD | 26/11/2024 | 0 | Resource Division | 14.35 | 0 | 0
269 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000019/2023-2024 | 1257/ALD | 10/08/2023 | 0 | Resource Division | 35.74 | 0 | 0
270 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000037/2024-2025 | 4253/ALD | 13/12/2024 | 0 | Resource Division | 43.88 | 0 | 0
271 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000087/2023-2024 | 111/ALD | 10/01/2024 | 0 | Resource Division | 14.35 | 0 | 0
272 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000170/2021-2022 | 1320/ALD | 05/10/2021 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 6.22 | 66
273 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA Zone-II water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000207/2020-2021 | 1161/ALD | 15/12/2020 | 60 | TAPAN CHANDA | 29.9 | 59.81 | 0
274 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA ZONE-II piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-4 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000249/2020-2021 | 1249/ALD | 28/12/2020 | 60 | TAPAN CHANDA | 39.91 | 79.82 | 0
275 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 30 | DAS ENTERPRISE | 5.02 | 0.87 | 77
276 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 0.17 | 60
277 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 6.83 | 70
278 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline for Jainti TG including connection from Reservoir-2 under Jainti TG Water Supply Scheme (Part-A). | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000123/2020-2021 | 795/ALD | 01/10/2020 | 60 | CALCON CONSTRUCTIONS | 40.62 | 64.59 | 90
279 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 6.6 | 69
280 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000354/2021-2022 | 2119/ALD | 05/01/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.28 | 3.87 | 71
281 | Alipurduar Division | Alipurduar Sadar Sub-Division | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000431/2021-2022 | 2629/ALD | 18/02/2022 | 60 | GHOSH & SAHA CONSTRUCTION | 13.4 | 8.21 | 64
282 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000078/2021-2022 | 876/ALD | 03/09/2021 | 60 | M/S AMIT KUMAR GUPTA | 35.43 | 6.67 | 75
283 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 27.31 | 73
284 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Tapshikhata water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000098/2020-2021 | 719/ALD | 22/09/2020 | 30 | KAMALESH ROY | 4.98 | 9.96 | 0
285 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying of UPVC and DI pipeline due to damaged during bitumen road construction and other misc works at Tapshikhata PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000146/2020-2021 | 941/ALD | 19/10/2020 | 60 | KAMALESH ROY | 10.81 | 3.01 | 77
286 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Purba Chepani water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte.(Part-IV | Alipurduar RWS | Birpara Sub Division | ORD/000212/2020-2021 | 1132/ALD | 10/12/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.93 | 6.82 | 0
287 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Tapshikatha water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte.(Part-III) | Alipurduar RWS | Birpara Sub Division | ORD/000226/2020-2021 | 1136/ALD | 10/12/2020 | 30 | KAMALESH ROY | 4.98 | 9.95 | 0
288 | Alipurduar Division | Birpara Sub-Division | Providing extension of distribution line, AT TAPSHIKATHA G.P from the commissioned TAPSHIKATHA PWSS (UID-APD-022) UNDER ALIPURDUAR DIVISION PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000308/2020-2021 | 1481/ALD | 27/01/2021 | 60 | KAMALESH ROY | 12.16 | 0 | 76
289 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | Birpara Sub Division | ORD/000321/2021-2022 | 2197/ALD | 11/01/2022 | 1116 | DEBABRATA DUTTA | 21.58 | 0 | 69
290 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar RWS | Birpara Sub Division | ORD/000350/2021-2022 | 2143/ALD | 06/01/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 5.03 | 3.02 | 76
291 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of North side of Pukuritola area under Tapshikatha PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000369/2021-2022 | 2292/ALD | 24/01/2022 | 60 | DEBAJYOTI SUTRADHAR | 26.52 | 0 | 78
292 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000442/2021-2022 | 2750/ALD | 24/02/2022 | 60 | AMBITIOUS ENTERPRISE | 36.94 | 0.87 | 68
293 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method)and Rising Main for Additional T/W of BAKLA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000314/2021-2022 | 2190/ALD | 11/01/2022 | 1081 | SHYAMAL ROY | 21.81 | 10.18 | 100
294 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000444/2021-2022 | 2753/ALD | 24/02/2022 | 1200 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 0 | 43
295 | Alipurduar Division | Alipurduar Sadar Sub-Division | Quotation for New Connection in Dalgaon | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | BILL/00108/2022-2023 | 446/22-23/PFMS | 21/01/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
296 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Beltali Road and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000026/2022-2023 | 24/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 12.33 | 80
297 | Alipurduar Division | Alipurduar Sadar Sub-Division | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 58
298 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Jateswar PWSS under Alipurduar Division, PHE Dte. Part-4 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000118/2022-2023 | 411/ALD | 11/05/2022 | 45 | SOUVIK ROY PALADHI | 24.47 | 10.14 | 63
299 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Jateswar PWSS under Alipurduar Division, PHE Dte. Part-5 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000119/2022-2023 | 412/ALD | 11/05/2022 | 45 | AASHIRBAD ENTERPRISE | 24.1 | 0 | 65
300 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC/DI distribution pipeline including road and culvert crossing of different area for augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000195/2022-2023 | 1225/ALD | 10/08/2022 | 60 | SOUVIK ROY PALADHI | 41.01 | 39.23 | 63
301 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC/DI distribution pipeline including road and culvert crossing of different area for augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000202/2022-2023 | 1226/ALD | 10/08/2022 | 120 | TAPASH DAS | 41.01 | 38.71 | 63
302 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 450cum OHR for Bhutnirghat Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000310/2021-2022 | 2186/ALD | 11/01/2022 | 180 | DILIP MAHATO | 87.59 | 12.6 | 80
303 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 500cum OHR for Augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000409/2021-2022 | 2525/ALD | 11/02/2022 | 180 | ASHIT KUMAR SINGHA | 91.76 | 82.23 | 80
304 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for JATESWAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000411/2021-2022 | 2527/ALD | 11/02/2022 | 990 | ASHIT KUMAR SINGHA | 44.59 | 18.47 | 63
305 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000450/2021-2022 | 2747/ALD | 24/02/2022 | 60 | TAPASH DAS | 49.62 | 39.08 | 59
306 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000451/2021-2022 | 2748/ALD | 24/02/2022 | 60 | KAMALESH ROY | 49.62 | 47.81 | 63
307 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC from existing distribution system as per specification for JATESWAR PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000453/2023-2024 | 235/ALD | 17/01/2024 | 90 | BILTU DAS | 63.54 | 0 | 0
308 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC/DI pipe line at flank of Asian Highway Road at Jateswar to towards Kazali Bazar under Jateswar PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000454/2022-2023 | 2944/ALD | 20/01/2023 | 60 | TAPASH DAS | 16.1 | 11.31 | 95
309 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-I | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000467/2021-2022 | 2812/ALD | 28/02/2022 | 60 | SOUVIK ROY PALADHI | 98.49 | 96.3 | 63
310 | Alipurduar Division | Alipurduar Sadar Sub-Division | Sinking big dia. Tube well of 250mm X 200mm dia. Using MS slotted strainer at required depth by Reverse Rotary Method of drilling at 2nd site for Aug. of Jateswar PWSS (SM/10156) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000494/2023-2024 | 750/ALD | 12/03/2024 | 90 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.48 | 19.91 | 100
311 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of pump house at 2nd site, laying of UPVC pipeline for left out household connection and rising main with CIDF pipe and specials and other allied works for Augmentation of Jateswar PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte.(SM/10156) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000504/2023-2024 | 822/ALD | 14/03/2024 | 480 | TAPASH DAS | 50.51 | 13.5 | 75
312 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Sahapara and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000539/2021-2022 | 3191/ALD | 28/03/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 10.78 | 78
313 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000007/2021-2022 | 2928/ALD | 10/03/2022 | 0 | Resource Division | 17.75 | 0 | 0
314 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000033/2022-2023 | 2107/ALD | 09/11/2022 | 0 | Resource Division | 10.92 | 0 | 0
315 | Alipurduar Division | Birpara Sub-Division | New service connection charges for Dheklapara T.G PWSS P/H no-I (Cha Sundari) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | BILL/00489/2024-2025 | 325/24-25/PFMS | 02/12/2024 | 0 | WBSEDCL | 5.04 | 0 | 0
316 | Alipurduar Division | Birpara Sub-Division | CONS. FOR RESERVOIR (200 M3), RISING MAIN AND DISTRIBUTION LINE FOR DHEKLAPARA MAIN DIVISION CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000030/2022-2023 | 284/ALD | 26/04/2022 | 150 | SUBHAS CHANDRA ROY | 86.68 | 70.85 | 100
317 | Alipurduar Division | Birpara Sub-Division | CONS. OF STORAGE TANK, BOUNDARY WALL, PUMP HOUSE, TUBE WELL (1 No.), RISING MAIN AND LAND DEVELOPMENT FOR NEPANIA MAIN DIVISION (150 Unit) CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000032/2022-2023 | 296/ALD | 27/04/2022 | 1345 | S.N. POLYMERS PRIVATE LIMITED | 108.37 | 0 | 75
318 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for Dekhlapara PWSS. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000326/2023-2024 | 2423/ALD | 09/11/2023 | 60 | SHYAMAL ROY | 7.21 | 0 | 0
319 | Alipurduar Division | Alipurduar Division | New Connection for Toorsa TG Zone-I Phase-II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | BILL/00032/2022-2023 | 357/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0
320 | Alipurduar Division | Alipurduar Division | New Connection for Torsa TG Zone-II Phase-I | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | BILL/00033/2022-2023 | 358/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0
321 | Alipurduar Division | Alipurduar Division | New Connection for Torsa TG Zone-II | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | BILL/00034/2022-2023 | 359/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0
322 | Alipurduar Division | Alipurduar Division | New Connection for Torsa TG Zone-I Phase-I | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | BILL/00035/2022-2023 | 360/22-23/PFMS | 12/12/2022 | 0 | WBSEDCL | 1.19 | 0 | 0
323 | Alipurduar Division | Alipurduar Division | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80m), PUMP HOUSE (1No.), TUBE WELL (2 Nos.), RISING MAIN AND LAND DEVELOPMENT FOR TORSHA (Hat Khola Line, Naya Line, 3 No. Line (A) AND (B) and Khoyar line) 256 unit CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000028/2022-2023 | 282/ALD | 26/04/2022 | 150 | DILIP MAHATO | 104 | 103.66 | 88
324 | Alipurduar Division | Alipurduar Division | CONS. OF RESERVOIR (100M3), BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND LAND DEVELOPMENT FOR TORSHA (Sawa Line, Chetri Line, Bancha Line,Gopal Line, Jiten Line)220 unit CHA SUNDARAI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000029/2022-2023 | 283/ALD | 26/04/2022 | 300 | MAHENDRA CHHETRI | 100.66 | 97.34 | 86
325 | Alipurduar Division | Alipurduar Division | Providing FHTC from existing distribution system as per specification for Torsha Cha Sundari PWSS PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000268/2023-2024 | 1886/ALD | 07/09/2023 | 30 | D. K. & SONS | 1.01 | 0 | 100
326 | Alipurduar Division | Alipurduar Division | Soil investigation work for Cha Sundori Project at 4 different places of Torsha TG & Dekhlapara TG within Alipurduar District under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000448/2021-2022 | 2655/ALD | 21/02/2022 | 30 | M/S HAZRA CONSTRUCTION | 4.9 | 4.9 | 87
327 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for replacement of 75mm dia UPVC pipe with 90mm dia pipeline, gap filling and re distribution system along with the others allied works under Jashodanga PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000005/2023-2024 | 26/ALD | 06/04/2023 | 540 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 44.98 | 20.52 | 45
328 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Jashodanga PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000218/2023-2024 | 1559/ALD | 23/08/2023 | 30 | JUGAL CHOUDHURY | 1.67 | 0 | 0
329 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC in school in Josodanga PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000498/2022-2023 | 3362/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.36 | 0.36 | 100
330 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at HW site and 2nd TW site of Jashodanga PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000568/2024-2025 | 5384/ALD | 17/03/2025 | 60 | TAPASH KUMAR BHOWMICK | 0.96 | 0 | 0
331 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
332 | Alipurduar Division | Alipurduar Sadar Sub-Division | Sinking of 250 mm x 200 mm x 150 mtr Big dia TW by reverse rotary drilling method at 4th TW site of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000028/2025-2026 | 437/ALD | 30/04/2025 | 30 | MADHAB SAHA | 11.51 | 0 | 0
333 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC Pipeline Distrbutation system, Delivery line connection, Cons. of surface drain, Pathway and Land Development works for 4th site at Paschim Chepani under Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000072/2025-2026 | 970/ALD | 12/06/2025 | 90 | PROGRESSIVE UN EMPLOYED CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD | 38.43 | 0 | 0
334 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of damaged FHTCs of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000074/2025-2026 | 972/ALD | 12/06/2025 | 45 | KOUSHIK BHOWMICK | 2.44 | 0 | 0
335 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for "Jal Swapno Program" (FHTC for every house hold) under Purba Chenpani PWSS under Alipurduar-II Block under Alipurduar Division, PHE Dte.(Re-tenter) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000079/2022-2023 | 443/ALD | 13/05/2022 | 30 | MATRI ENTERPRISE | 4.2 | 4.06 | 10
336 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000193/2022-2023 | 1220/ALD | 10/08/2022 | 60 | SREE MAA CONSTRUCTION | 21.55 | 9.35 | 94
337 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000247/2023-2024 | 1589/ALD | 25/08/2023 | 30 | ANIRBAN KAR | 3.32 | 0 | 0
338 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
339 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pump House, boundary wall, laying of UPVC pipe linr & Rising main connection for Purba Chepani PWSS proposed 4th TW SITE under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000519/2022-2023 | 3494/ALD | 23/03/2023 | 90 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.66 | 0 | 48
340 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000002/2024-2025 | 3607/ALD | 24/10/2024 | 0 | Resource Division | 5.11 | 0 | 0
341 | Alipurduar Division | Alipurduar Sadar Sub-Division | Sinking of 250 mm x 200 mm x 150 mtr Big dia TW by reverse rotary drilling method at 4th TW site of Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000029/2025-2026 | 438/ALD | 30/04/2025 | 30 | MADHAB SAHA | 11.51 | 0 | 0
342 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of damaged FHTCs and replacement of Old damaged pipelines at Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000079/2025-2026 | 977/ALD | 12/06/2025 | 60 | KOUSHIK BHOWMICK | 3.88 | 0 | 0
343 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Laying of UPVC/DI Pipe line, dismantling concrete road and recasting same and other allied works at Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000284/2022-2023 | 1638/ALD | 19/09/2022 | 60 | NARENDRA BHADANI. | 30.82 | 29.6 | 96
344 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Salsalabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000359/2023-2024 | 2745/ALD | 14/12/2023 | 420 | MATRI ENTERPRISE | 16.16 | 0 | 100
345 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC in school in Salsalabari PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000497/2022-2023 | 3361/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.29 | 0.29 | 100
346 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pumphouse, boundary wall,laying of UPVC pipeline & rising main connection for Salsalabari PWSS proposed 4th TW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000515/2022-2023 | 3400/ALD | 16/03/2023 | 90 | BRAJA GOPAL SAHA | 39.58 | 0 | 0
347 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at HW and 2nd TW site of SALSALABARI PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000567/2024-2025 | 5383/ALD | 17/03/2025 | 60 | HARI CONSTRUCTION | 0.96 | 0 | 0
348 | Alipurduar Division | Birpara Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME IN 4(Four) nos. villages under different blocks having less than 100 household under Alipurduar district in connection with Jal Swapna. | Birpara A.E | Birpara Sub Division | ORD/000101/2022-2023 | 605/ALD | 31/05/2022 | 946 | M/S KAMAK ENGINEERS AND CO | 159.94 | 97.37 | 90
349 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Birpara A.E | Birpara Sub Division | RTOR000019/2022-2023 | 967/ALD | 15/07/2022 | 0 | Resource Division | 1.43 | 0 | 0
350 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for PASCHIM CHENGMARI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000248/2023-2024 | 1590/ALD | 25/08/2023 | 90 | ANKIT SARKAR | 1.66 | 1.49 | 90
351 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, land development works, construction of surface drain, pathway, supply of CIDF specials and other allied works in connection with the Paschim Chengmari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000337/2023-2024 | 2523/ALD | 24/11/2023 | 270 | M/S SSB CONSTRUCTION CO. | 83.57 | 48.17 | 57
352 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L including rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for PASCHIM CHENGMARI PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000435/2022-2023 | 2862/ALD | 17/01/2023 | 806 | M/S SSB CONSTRUCTION CO. | 312.15 | 201.82 | 65
353 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
354 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000109/2023-2024 | 133/ALD | 10/01/2024 | 0 | Resource Division | 5.72 | 0 | 0
355 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
356 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Purba Khalshamari WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000229/2023-2024 | 1604/ALD | 25/08/2023 | 30 | HARI CONSTRUCTION | 6.76 | 0 | 100
357 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, Land development works, construction of surface drain, pathway, trial run and others allied works in connection with the Purba Khailshmari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000397/2024-2025 | 4236/ALD | 12/12/2024 | 60 | HARI CONSTRUCTION | 75.41 | 0 | 0
358 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
359 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Purba Khalishamari Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000481/2023-2024 | 699/ALD | 07/03/2024 | 30 | HARI CONSTRUCTION | 15.31 | 15.31 | 70
360 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house & Sinking of 250 mm x 200 mm X 150 mtr. Big dia. Tube well at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 250 Cum OHR as per Departmental Design & drawing including soil test, providing FHTC and others allied works for Purba Khalisamari PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000557/2022-2023 | 3577/ALD | 27/03/2023 | 840 | HARIDAS GHOSH | 438.25 | 358.4 | 72
361 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000008/2024-2025 | 3613/ALD | 24/10/2024 | 0 | Resource Division | 7.78 | 0 | 0
362 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000036/2022-2023 | 3044/ALD | 08/02/2023 | 0 | Resource Division | 21.01 | 0 | 0
363 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000053/2024-2025 | 4273/ALD | 13/12/2024 | 0 | Resource Division | 11.33 | 0 | 0
364 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000082/2023-2024 | 106/ALD | 10/01/2024 | 0 | Resource Division | 11.82 | 0 | 0
365 | Alipurduar Division | Alipurduar RWS Sub-Division | Gap Filling of distribution line, land development at Pump House and others allied works for NAOTHOARTARI PWSS within Alipurduar Block-I under Alipuduar Division PHE.Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000075/2025-2026 | 973/ALD | 12/06/2025 | 90 | CHINMOY BHATTACHARJEE | 42.38 | 0 | 0
366 | Alipurduar Division | Alipurduar RWS Sub-Division | Construction of Tube Well, Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Naothoartari PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000577/2022-2023 | 3638/ALD | 31/03/2023 | 900 | CHINMOY BHATTACHARJEE | 267.68 | 164.49 | 40
367 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000037/2022-2023 | 3045/ALD | 08/02/2023 | 0 | Resource Division | 7.53 | 0 | 0
368 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000041/2024-2025 | 4256/ALD | 13/12/2024 | 0 | Resource Division | 9.16 | 0 | 0
369 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary wall at proposed 4th TW site of Kaijali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000004/2023-2024 | 07/ALD | 04/04/2023 | 120 | PRITAM DAS | 17.41 | 16.17 | 100
370 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
371 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Rising Main, providing FHTC, Repairing existing Pipe line, Restoration of FHTC at 4th TW site and Gap filing in distribution system at Kaijali Busty PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000101/2025-2026 | 1186/ALD | 26/06/2025 | 75 | RAMEN DEY & CO | 15.59 | 0 | 0
372 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of damaged FHTCs of Kaijali Busty PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000102/2025-2026 | 1187/ALD | 26/06/2025 | 45 | RAMEN DEY & CO | 4 | 0 | 0
373 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land development works, Construction of surface drain, pathway, and other allied works at Kaijali Busty 3rd tube well site with the Augmentation of Kaijili Busty PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE.(SM/11958) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000221/2024-2025 | 2274/ALD | 05/08/2024 | 60 | KAMALESH ROY | 3.84 | 0.18 | 50
374 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 method of drilling at 3rd TWsite including laying Distribution system with new HDPE Pipeline (Part-A), Providing FHTC and other allied works for augmentation of KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000331/2022-2023 | 2240/ALD | 21/11/2022 | 600 | KAMALESH ROY | 70.16 | 60.09 | 68
375 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works for proposed overhead reservoir of KAIJALI BUSTI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000339/2022-2023 | 2248/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 11
376 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 200 cum OHR as per Departmental Design and drawing at KAIJALI BUSTY PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000353/2022-2023 | 2497/ALD | 13/12/2022 | 540 | MAHENDRA CHHETRI | 68.63 | 66.32 | 70
377 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new HDPE pipeline for interconnection in the distribution system and bridge/culvert crossing land developmentworks, construction of surface drain, pathway and other allied works in connection with the Augmentation of KAijali Basty PWSS (SM/11958) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000392/2024-2025 | 3958/ALD | 26/11/2024 | 60 | MAHENDRA CHHETRI | 29.4 | 0 | 0
378 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
379 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at Headwork site of Kaijali Basty PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000565/2024-2025 | 5381/ALD | 17/03/2025 | 60 | TAPASH KUMAR BHOWMICK | 0.94 | 0 | 0
380 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at 2nd TW site of Kaijali Basty PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000566/2024-2025 | 5382/ALD | 17/03/2025 | 60 | TAPASH KUMAR BHOWMICK | 0.92 | 0 | 0
381 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000004/2024-2025 | 3609/ALD | 24/10/2024 | 0 | Resource Division | 11.11 | 0 | 0
382 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000023/2022-2023 | 1588/ALD | 14/09/2022 | 0 | Resource Division | 30.75 | 0 | 0
383 | Alipurduar Division | Birpara Sub-Division | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main, laying of DI and UPVC pipeline for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000041/2023-2024 | 387/ALD | 19/05/2023 | 480 | MITHUN DAS | 93.44 | 40.47 | 62
384 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000080/2025-2026 | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
385 | Alipurduar Division | Birpara Sub-Division | Soil investigation at OHR site and construction of 450cum OHR at Uttar Sishubari under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000197/2024-2025 | 1767/ALD | 07/06/2024 | 300 | BISWAJIT DUTTA | 118.67 | 0 | 0
386 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. Part-4 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000260/2022-2023 | 1492/ALD | 05/09/2022 | 90 | MITHUN DAS | 24.32 | 0 | 0
387 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for UTTAR SISHUBARI PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000284/2023-2024 | 1991/ALD | 15/09/2023 | 90 | MITHUN DAS | 57.24 | 0 | 0
388 | Alipurduar Division | Birpara Sub-Division | Laying of distribution pipe in Uttar Sishubari Bazar area and Madarihat Bazar Area and allied works Under Birpara Sub-division, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000396/2022-2023 | .2663/ALD | 22/12/2022 | 120 | MITHUN DAS | 25.68 | 25.17 | 100
389 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
390 | Alipurduar Division | Birpara Sub-Division | Construction of Tubewell by ODEX-165 method of drilling at HWS, construction of pump house and boundary wall at HWS, laying of rising main for Aug. Of Uttar Sishubari PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000473/2023-2024 | 691/ALD | 07/03/2024 | 45 | MITHUN DAS | 31.88 | 0 | 0
391 | Alipurduar Division | Birpara Sub-Division | Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC AT BIRPARA Zone-II Area under BIRPARA PWSS under Alipurduar Division, PHE Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC AT BIRPARA Zone-II Area under BIRPARA PWSS under Alipurduar Division, PHE DTE.. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000001/2025-2026 | 111/ALD | 16/04/2025 | 45 | RATAN DUTTA | 120.16 | 0 | 0
392 | Alipurduar Division | Birpara Sub-Division | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-II 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000009/2023-2024 | 93/ALD | 18/04/2023 | 120 | SUBHAK CHIK BARAIK | 31.63 | 9.71 | 100
393 | Alipurduar Division | Birpara Sub-Division | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000010/2023-2024 | 94/ALD | 18/04/2023 | 120 | FAUDA SINGH CHHETRI | 34.7 | 29.27 | 100
394 | Alipurduar Division | Birpara Sub-Division | Construction of pump house boundary wall Tubewell boring (by ODEX-165 method of drilling) and rising main for Zone-III 3rd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000014/2023-2024 | 166/ALD | 26/04/2023 | 480 | RATAN DUTTA | 31.78 | 18.23 | 65
395 | Alipurduar Division | Birpara Sub-Division | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-I 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000040/2023-2024 | 386/ALD | 19/05/2023 | 120 | KAJAL KUMAR DE | 32.74 | 20.26 | 30
396 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000080/2025-2026 | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
397 | Alipurduar Division | Birpara Sub-Division | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-II 1st TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000158/2023-2024 | 663/ALD | 07/06/2023 | 480 | BRAJA GOPAL SAHA | 31.58 | 22.36 | 20
398 | Alipurduar Division | Birpara Sub-Division | Construction of pump house, Boundary Wall, Tube well Boring (by ODEX-165 method of drilling) and Rising main for Zone-III 2nd TW site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000171/2023-2024 | 962/ALD | 12/07/2023 | 120 | SUBIR GHOSH | 32.45 | 0 | 0
399 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipe line for the Birpara Water Supply Scheme under Alipurduar Division,PHE Dte.(Part-2) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000230/2021-2022 | 1571/ALD | 22/11/2021 | 60 | PRAMESH LAMA | 51.34 | 44.47 | 7
400 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipe line for the Birpara Water Supply Scheme under Alipurduar Division,PHE Dte.(Part-3) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000231/2021-2022 | 1570/ALD | 22/11/2021 | 420 | SOUVIK ROY PALADHI | 37.07 | 29.87 | 61
401 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for BIRPARA PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000296/2023-2024 | 2105/ALD | 29/09/2023 | 60 | GIRIRAJ ENTERPRISE | 34.39 | 0 | 0
402 | Alipurduar Division | Birpara Sub-Division | Supply of drinking water through tanker by hired vehicle to mitigate drinking water crisis at Huntapara TG, Dhumchipara TG and Gargenda TG and lankapara TG under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000309/2023-2024 | 2174/ALD | 06/10/2023 | 45 | BHAGWATI BHUJEL | 9.82 | 9.82 | 100
403 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 0 | 100
404 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I Headwork TW Site at Augmentation od Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000342/2023-2024 | 2543/ALD | 28/11/2023 | 600 | KAMALESH ROY | 44.55 | 5.69 | 50
405 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-III Headwork TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000343/2023-2024 | 2544/ALD | 28/11/2023 | 850 | RATAN DUTTA | 46.23 | 6.37 | 5
406 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, B/wall, TW boring by ODEX-165 method of drilling and rising main for Zone-I 3rd TW Site at Augmentation of Birpara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000350/2023-2024 | 2602/ALD | 04/12/2023 | 482 | FAUDA SINGH CHHETRI | 31.46 | 18.97 | 61
407 | Alipurduar Division | Birpara Sub-Division | Fabrication,Erection of Signage (268 nos) of Pump house/OHR site democration with in Kumargram, Falakata,Madarihat-Birpara Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000354/2024-2025 | 3520/ALD | 04/10/2024 | 330 | LIMRA SOCIAL WELFARE SOCIETY | 31.26 | 7.09 | 92
408 | Alipurduar Division | Birpara Sub-Division | Laying of DI & HDPE Pipe line, Construction of sluice valve chamber, trenchless pipe laying & other works for providing FHTC at Birpara Zone-I Area under Birpara PWSS under Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000412/2024-2025 | 4595/ALD | 03/01/2025 | 225 | KAMALESH ROY | 149.76 | 0 | 1
409 | Alipurduar Division | Birpara Sub-Division | SOIL INVESTIGATION AT OHR AND CONS. OF 450 CUM OHR AT ZONE-3 FOR AUGMENTATIN OF BIRPARA PWSS UNDER ALIPURDUAR DIVISION OF NORTH BENGAL CIRCLE-I, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000433/2023-2024 | 234/ALD | 17/01/2024 | 381 | AMBITIOUS ENTERPRISE | 239.31 | 25.15 | 55
410 | Alipurduar Division | Birpara Sub-Division | Construction of 550cum. OHR for Birpara TG (Middle) Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000438/2022-2023 | 2867/ALD | 17/01/2023 | 180 | DILIP MAHATO | 98.12 | 86.15 | 85
411 | Alipurduar Division | Birpara Sub-Division | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-2) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000440/2022-2023 | 2869/ALD | 17/01/2023 | 60 | AMBITIOUS ENTERPRISE | 97.44 | 41.77 | 7
412 | Alipurduar Division | Birpara Sub-Division | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-A | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000441/2022-2023 | 2870/ALD | 17/01/2023 | 60 | ANUP KUNDU CONSTRUCTION CO. | 95.98 | 81.06 | 7
413 | Alipurduar Division | Birpara Sub-Division | Laying of CI/DI/MS/HDPE pipe and providing FHTC for BIRPARA TEA GARDEN (ZONE-3) AREA PWSS Under Alipurduar Division PHE DTE. PART-C | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000443/2022-2023 | 2872/ALD | 17/01/2023 | 60 | DILIP MAHATO | 96.76 | 74.45 | 65
414 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for BirparaZone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-1 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000444/2022-2023 | 2873/ALD | 17/01/2023 | 888 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 24.27 | 2.95 | 58
415 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-I (North) PWSS under Alipurduar Division, PHE Dte. Part-2 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000445/2022-2023 | 2874/ALD | 17/01/2023 | 45 | BILTU DAS | 24.22 | 0 | 0
416 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara Zone-II (Middle) PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000446/2022-2023 | 2875/ALD | 17/01/2023 | 45 | NARENDRA BHADANI. | 24.11 | 0 | 0
417 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Birpara (South) PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000447/2022-2023 | 2876/ALD | 17/01/2023 | 45 | DILIP MAHATO | 34.6 | 0 | 0
418 | Alipurduar Division | Birpara Sub-Division | Soil investigation at OHR site and construction of 450cum OHR at Zone-1 for Augmentation of Birpara PWSS under Alipurduar Divisionof North Bengal Circle-I, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000459/2023-2024 | 495/ALD | 16/02/2024 | 585 | KAMALESH ROY | 120.29 | 58.79 | 10
419 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
420 | Alipurduar Division | Birpara Sub-Division | Sinking of Big dia. Tubewell (200 x 150 mm dia.)by modified DTH -ODEX method of drilling at Paschim Khairbari PWSS(SM/10672) and Birpara PWSS Zone-II, 4th TW site(SM/14233)of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000493/2023-2024 | 749/ALD | 12/03/2024 | 135 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 33.26 | 25.29 | 50
421 | Alipurduar Division | Birpara Sub-Division | Protective and Decorative Acrylic exterior paint on existing 350 cum OHR at Birpara of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/14233) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000506/2023-2024 | 824/ALD | 14/03/2024 | 60 | BHAGWATI BHUJEL | 1.96 | 1.95 | 10
422 | Alipurduar Division | Birpara Sub-Division | Cons. of pump house, boundary wall and Rising Main for Zone-II 4thTube well site at Aug. of Birpara PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/14233) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000531/2023-2024 | 850/ALD | 14/03/2024 | 360 | RATAN DUTTA | 18.26 | 3.06 | 65
423 | Alipurduar Division | Birpara Sub-Division | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer ,Birpara Sub- Division ,P.H.E. Dte..(from 01.04.2024 to 01.03.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000538/2023-2024 | 893/ALD | 15/03/2024 | 365 | PARITOSH SUTRADHAR | 4.8 | 4.78 | 0
424 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000022/2024-2025 | 3980/ALD | 27/11/2024 | 0 | Resource Division | 30.8 | 0 | 0
425 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000060/2023-2024 | 2722/ALD | 13/12/2023 | 0 | Resource Division | 137.01 | 0 | 0
426 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000114/2023-2024 | 138/ALD | 10/01/2024 | 0 | Resource Division | 61.13 | 0 | 0
427 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for MARAKHATA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000215/2023-2024 | 1569/ALD | 23/08/2023 | 30 | HARI CONSTRUCTION | 4.69 | 0 | 0
428 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Marakhata WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000225/2023-2024 | 1598/ALD | 25/08/2023 | 30 | HARI CONSTRUCTION | 6.76 | 6.76 | 100
429 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, Supply of DI pipe and specials, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at MARAKHATA HW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000369/2023-2024 | 85/ALD | 10/01/2024 | 360 | HARIDAS GHOSH | 65.13 | 42.19 | 35
430 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L inclu. rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing alongwith soil investigation, providing FHTC and others allied works for MARAKHATA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000436/2022-2023 | 2863/ALD | 17/01/2023 | 900 | HARIDAS GHOSH | 355.8 | 264.97 | 27
431 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
432 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000010/2024-2025 | 3615/ALD | 24/10/2024 | 0 | Resource Division | 8.11 | 0 | 0
433 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000037/2023-2024 | 1475/ALD | 16/08/2023 | 0 | Resource Division | 29.72 | 0 | 0
434 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000107/2023-2024 | 131/ALD | 10/01/2024 | 0 | Resource Division | 8.44 | 0 | 0
435 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
436 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Dakshin Majidkhana PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000210/2023-2024 | 1564/ALD | 23/08/2023 | 45 | HARI CONSTRUCTION | 6.77 | 0 | 0
437 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF Specials and Jeffy Coupling for Dakshin Majidkhana (SM/13305) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000398/2024-2025 | 4264/ALD | 13/12/2024 | 60 | GUHA ENTERPRISE | 19.58 | 4.23 | 50
438 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. Big dia. TW at HW and 2nd site, LDS with UPVC pipeline, Cons. of 200 cum OHR as per Departmental Design and drawing inclu. Soil testing, providing FHTC and others allied works for Dakshin Majidkhana PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000427/2022-2023 | 2854/ALD | 17/01/2023 | 1020 | HARIDAS GHOSH | 390.45 | 339.65 | 75
439 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
440 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.01.2024 to 29.02.2024) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000544/2023-2024 | 2905/ALD | 29/12/2023 | 62 | MATRI ENTERPRISE | 0.8 | 0 | 0
441 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000034/2023-2024 | 1472/ALD | 16/08/2023 | 0 | Resource Division | 24.3 | 0 | 0
442 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000047/2023-2024 | 2395/ALD | 08/11/2023 | 0 | Resource Division | 8.64 | 0 | 0
443 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte. (from01.05.2025 to 30.04.2026) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000031/2025-2026 | 419/ALD | 30/04/2025 | 365 | APSARI BHOWMICK | 4.8 | 0 | 0
444 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. (From 01.05.2025 to 30.04.2026) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000032/2025-2026 | 420/ALD | 30/04/2025 | 365 | MATRI ENTERPRISE | 4.8 | 0 | 0
445 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
446 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for CHALNIPAK PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000214/2023-2024 | 1568/ALD | 23/08/2023 | 45 | SOUVIK ROY PALADHI | 9.97 | 0 | 0
447 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/ culvert crossing , Land developement works , Constructions of surface drain , pathway and others allied works in connection with the Chalnipak PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/15534) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000223/2024-2025 | 2276/ALD | 05/08/2024 | 60 | SOUVIK ROY PALADHI | 77.22 | 0 | 0
448 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Chalnipak WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000238/2023-2024 | 1607/ALD | 25/08/2023 | 30 | SOUVIK ROY PALADHI | 7.89 | 0 | 0
449 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF Specials & Jeffy Coupling for Chalnipak (SM/15534) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000404/2024-2025 | 4540/ALD | 26/12/2024 | 30 | SOUVIK ROY PALADHI | 19.94 | 0 | 0
450 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
451 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house and Sinking of 250 mm x 200 mm X 150 mtr Big dia Tubewel at HW site , 2nd site and 3 rd Site Laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design and drawing , including the Soil investigation works providing FHTC and others allied works for Chalnipak PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000472/2022-2023 | 3156/ALD | 22/02/2023 | 720 | SOUVIK ROY PALADHI | 481.77 | 424.68 | 50
452 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | RTOR000018/2023-2024 | 224/ALD | 03/05/2023 | 0 | Resource Division | 13.14 | 0 | 0
453 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | RTOR000051/2023-2024 | 2399/ALD | 08/11/2023 | 0 | Resource Division | 10.15 | 0 | 0
454 | Alipurduar Division | Alipurduar Division | Supply of DIDF pipes and specials and Sluice Valve for Beech TG Water Supply Scheme (SM/14214) under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000204/2024-2025 | 1953/ALD | 02/07/2024 | 30 | KAMALA VALVES AND ENGINEERING PRIVATE LIMITED | 15.43 | 8.46 | 85
455 | Alipurduar Division | Alipurduar Division | Providing balance FHTC from existing distribution system as per specification for BEECH TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000316/2023-2024 | 2184/ALD | 06/10/2023 | 300 | D. K. & SONS | 16.37 | 16.32 | 100
456 | Alipurduar Division | Alipurduar Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000462/2023-2024 | 161/ALD | 11/01/2024 | 366 | DIPAK DAS | 4.8 | 4.42 | 0
457 | Alipurduar Division | Alipurduar Division | Balance portion of boundary wall and pump house and land development of HW site, 1st site and construction of culvert and platform for BEECH TG PWSS under Kalchini Block, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000491/2023-2024 | 747/ALD | 12/03/2024 | 180 | MAHENDRA CHHETRI | 29.65 | 28.95 | 90
458 | Alipurduar Division | Alipurduar Division | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 150 Cum OHR as per Departmental Design & drawing , TWO nos. pump house & boundary wall, providing FHTC, Soil Investigation work and others allied works for BEECH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. (2nd call) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000511/2022-2023 | 3398/ALD | 16/03/2023 | 540 | MAHENDRA CHHETRI | 309.23 | 304.6 | 91
459 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000014/2023-2024 | 220/ALD | 03/05/2023 | 0 | Resource Division | 36.92 | 0 | 0
460 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000076/2023-2024 | 100/ALD | 10/01/2024 | 0 | Resource Division | 9.73 | 0 | 0
461 | Alipurduar Division | Birpara Sub-Division | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 350 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Paschim Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000173/2023-2024 | 1047/ALD | 20/07/2023 | 360 | SOUVIK ROY PALADHI | 547.06 | 239.02 | 26
462 | Alipurduar Division | Birpara Sub-Division | Laying of DI & HDPE pipeline, construction of sluice valve chamber, trenchless pipe, laying & other works for providing FHTC at Paschim deogaon PWSS under Birpara Sub-Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000350/2024-2025 | 3420/ALD | 26/09/2024 | 60 | SOUVIK ROY PALADHI | 35.92 | 0 | 0
463 | Alipurduar Division | Birpara Sub-Division | Gap filling in main and branch road of Nabanagar area by HDPE/DI pipe as required under Pashchim Deogaon PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000365/2023-2024 | 81/ALD | 10/01/2024 | 90 | SOUVIK ROY PALADHI | 38.2 | 0 | 0
464 | Alipurduar Division | Birpara Sub-Division | Supply of CI Sluice Valve and Special and CI Jeffy Coupling for Paschim Deogaon Water Supply Scheme(SM/15207) of Falakata Block under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000529/2023-2024 | 848/ALD | 14/03/2024 | 90 | SOUVIK ROY PALADHI | 18.86 | 18.86 | 90
465 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000006/2023-2024 | 187/ALD | 28/04/2023 | 0 | Resource Division | 24.01 | 0 | 0
466 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000027/2024-2025 | 3985/ALD | 27/11/2024 | 0 | Resource Division | 12.92 | 0 | 0
467 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000097/2023-2024 | 121/ALD | 10/01/2024 | 0 | Resource Division | 12.92 | 0 | 0
468 | Alipurduar Division | Birpara Sub-Division | Construction of tubewells (2 nos.) by Reverse rotary method of drilling , soil investigation at OHR site, constructions of 450 Cum OHR at HW , construction of pump house and boundary wall at HW site and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uttar Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000172/2023-2024 | 1046/ALD | 20/07/2023 | 661 | DILIP MAHATO | 539.38 | 351.12 | 61
469 | Alipurduar Division | Birpara Sub-Division | Continuation work order for the work of "Construction of tube wells (2 nos.) by Reverse rotary method of drilling , soil investigation at OHR site, constructions of 450 Cum OHR at HW , construction of pump house and boundary wall at HW site and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uttar Deogaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/4/2024-EE(ALI_D) SEC-DPHE (Computer No-973240)) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000198/2024-2025 | 1912/ALD | 26/06/2024 | 60 | DILIP MAHATO | 21.25 | 0 | 100
470 | Alipurduar Division | Birpara Sub-Division | Laying of DI & HDPE pipeline, construction of sluice valve chamber, trenchless pipe, laying & other works for providing FHTC at Uttar deogaon PWSS under Birpara Sub-Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000342/2024-2025 | 3230/ALD | 10/09/2024 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 43.7 | 0 | 0
471 | Alipurduar Division | Birpara Sub-Division | "Supply of DIDF Special and CI Jeffy Coupling for Uttar Deogaon TG Water Supply Scheme(SM/16817) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000528/2023-2024 | 847/ALD | 14/03/2024 | 90 | SOUVIK ROY PALADHI | 16.48 | 16.48 | 59
472 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000021/2024-2025 | 3955/ALD | 26/11/2024 | 0 | Resource Division | 9.86 | 0 | 0
473 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000040/2023-2024 | 1479/ALD | 16/08/2023 | 0 | Resource Division | 21.37 | 0 | 0
474 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000061/2023-2024 | 2723/ALD | 13/12/2023 | 0 | Resource Division | 84.45 | 0 | 0
475 | Alipurduar Division | Alipurduar Division | Tube well Boring by ODEX-165 Method of drilling at HW, 2nd TUBE WELL site including two nos. pump house and boundary wall, providing FHTC and others allied works for MALANGI TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000018/2023-2024 | 236/ALD | 04/05/2023 | 748 | RAMESH SHARMA | 139.9 | 21.2 | 10
476 | Alipurduar Division | Alipurduar Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000084/2025-2026 | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
477 | Alipurduar Division | Alipurduar Division | Constructions of 300 Cum OHR as per Departmental Design & drawing, including laying distribution system with new HDPE pipeline , Rising Main, Soil Investigation work and others allied works for MALANGI TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000175/2023-2024 | 1049/ALD | 20/07/2023 | 720 | CAPITAL ENGINEERS | 201.31 | 52.22 | 45
478 | Alipurduar Division | Alipurduar Division | Providing balance FHTC from existing distribution system as per specification for MALANGI TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000282/2023-2024 | 1989/ALD | 15/09/2023 | 60 | KAMALESH ROY | 10.86 | 0 | 0
479 | Alipurduar Division | Alipurduar Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
480 | Alipurduar Division | Alipurduar Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte. (from 01.04.2025 to 31.03.2026) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000604/2024-2025 | 5303/ALD | 28/03/2025 | 365 | SASANKA ROY | 4.8 | 0 | 0
481 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000024/2024-2025 | 3982/ALD | 27/11/2024 | 0 | Resource Division | 13.03 | 0 | 0
482 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000074/2023-2024 | 99/ALD | 10/01/2024 | 0 | Resource Division | 13.03 | 0 | 0
483 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, Laying of distribution system with HDPE/DI pipeline, providing FHTC and others allied works for Dhantali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000016/2023-2024 | 234/ALD | 04/05/2023 | 240 | SOUVIK ROY PALADHI | 190.55 | 131.42 | 70
484 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000051/2024-2025 | 4271/ALD | 13/12/2024 | 0 | Resource Division | 19.92 | 0 | 0
485 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000099/2023-2024 | 123/ALD | 10/01/2024 | 0 | Resource Division | 1.27 | 0 | 0
486 | Alipurduar Division | Alipurduar Sadar Sub-Division | Installation of additional new tube well by ODEX-165 method of drilling for Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000104/2022-2023 | 776/ALD | 20/06/2022 | 30 | ANUP GUPTA | 6.99 | 5.44 | 57
487 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000114/2022-2023 | 706/ALD | 08/06/2022 | 30 | DEBAJYOTI SUTRADHAR | 4.95 | 4.95 | 57
488 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte. (Part-4) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000162/2021-2022 | 1304/ALD | 05/10/2021 | 60 | DULAL MAJUMDER | 34.38 | 32.66 | 76
489 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000167/2021-2022 | 1306/ALD | 05/10/2021 | 60 | GOUTAM KUMAR DAS | 25.34 | 0 | 74
490 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAMAKHYAGURI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000173/2020-2021 | 917/ALD | 16/10/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.98 | 4.9 | 57
491 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000180/2021-2022 | 1307/ALD | 05/10/2021 | 60 | TAPASH DAS | 25.34 | 0 | 76
492 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land development and laying of UPVC pipeline at additional TW Site of Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000203/2023-2024 | 1556/ALD | 23/08/2023 | 60 | SREE MAA CONSTRUCTION | 8.6 | 8.54 | 100
493 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAMAKHYAGURI water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000209/2020-2021 | 1163/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.94 | 7.66 | 77
494 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Laying of UPVC/DI Pipe Line, Providing FHTC & Other allied works at Uttar Kamakhyaguri PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000211/2022-2023 | 1306/ALD | 22/08/2022 | 60 | DILIP MAHATO | 28.04 | 21 | 57
495 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and Providing House Connection of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000226/2021-2022 | 1574/ALD | 22/11/2021 | 60 | M/S PALIT ENTERPRISE | 48.63 | 29.64 | 78
496 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for filling of gap in the distribution system and laying of delivery line connection, providing FHTC, land development cons. Of surface drain, pathway and other allied work in connection with the Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000347/2023-2024 | 2564/ALD | 29/11/2023 | 540 | DEBAJYOTI SUTRADHAR | 46.9 | 5.15 | 65
497 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 400cum OHR for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000412/2021-2022 | 2580/ALD | 17/02/2022 | 180 | DILIP MAHATO | 77.31 | 58.71 | 74
498 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000414/2022-2023 | 2729/ALD | 30/12/2022 | 365 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.8 | 4.48 | 100
499 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and laying distribution system for Uttar Kamkhyaguri Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000424/2021-2022 | 2608/ALD | 17/02/2022 | 90 | GOUTAM KUMAR DAS | 90.8 | 77.36 | 74
500 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for UTTAR KAMAKHYAGURI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000426/2021-2022 | 2610/ALD | 17/02/2022 | 90 | ANUP GUPTA | 23.99 | 0 | 0
501 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of pipeline at PASCHIM NARATHALI by extension of pipeline from Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000440/2021-2022 | 2746/ALD | 24/02/2022 | 1020 | AKANSHA COMMERCIAL PRIVATE LTD. | 93.92 | 23.12 | 100
502 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000010/2022-2023 | 715/ALD | 13/06/2022 | 0 | Resource Division | 71.41 | 0 | 0
503 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Chhoto Daldali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000208/2023-2024 | 1562/ALD | 23/08/2023 | 30 | DAS CONSTRUCTION | 3.35 | 0 | 0
504 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC p/l, bridge and culvert crossing, construction of pathway, surface drain and chatal, instalation of paver block, land development along with the other allied works, chhoto Daldali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000208/2025-2026 | 2350/ALD | 10/11/2025 | 90 | DAS CONSTRUCTION | 86.28 | 0 | 0
505 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
506 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for Chuota Daldali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000508/2022-2023 | 3393/ALD | 16/03/2023 | 777 | DAS CONSTRUCTION | 278.2 | 126.18 | 65
507 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000017/2024-2025 | 3951/ALD | 26/11/2024 | 0 | Resource Division | 6.17 | 0 | 0
508 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000031/2023-2024 | 1276/ALD | 11/08/2023 | 0 | Resource Division | 11.58 | 0 | 0
509 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000046/2024-2025 | 4262/ALD | 13/12/2024 | 0 | Resource Division | 22.34 | 0 | 0
510 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000101/2023-2024 | 125/ALD | 10/01/2024 | 0 | Resource Division | 6.17 | 0 | 0
511 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2021-2022 | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 48.46 | 70
512 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA Zone-III water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000208/2020-2021 | 1162/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 19.93 | 19.93 | 77
513 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-I) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000473/2021-2022 | 2763/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 29.41 | 69
514 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 0.89 | 60
515 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 0 | 70
516 | Alipurduar Division | Birpara Sub-Division | Providing House connection for JOGENDRAPUR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | Birpara A.E | RWS Falakata Block | ORD/000217/2020-2021 | 1168/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 13.08 | 67
517 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Jogijhora water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte.(Part-I) | Birpara A.E | RWS Falakata Block | ORD/000286/2020-2021 | 1334/ALD | 11/01/2021 | 30 | BHAGWATI BHUJEL | 4.98 | 9.96 | 0
518 | Alipurduar Division | Birpara Sub-Division | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000414/2021-2022 | 2582/ALD | 17/02/2022 | 180 | ASHIM KUMAR GHOSH | 63.76 | 11.26 | 43
519 | Alipurduar Division | Birpara Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 17.04 | 100
520 | Alipurduar Division | Birpara Sub-Division | Laying of distribution of HDPE/DI pipeline for Jogijhora Barabak PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000477/2021-2022 | 2896/ALD | 08/03/2022 | 960 | MS DEYS CONSTRUCTION | 56.01 | 0 | 100
521 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | RWS Falakata Block | VCH/000944/2020-2021 | 571/20-21 | 26/03/2021 | 0 | PRAMESH LAMA | 10 | 0 | 0
522 | Alipurduar Division | Alipurduar Division | Balance work of OHR Construction of PHouse B/Wall Godown & ODEX-165 Tubewell incl. laying of DI/HDPE Pipe for Nayabasti SSB Camp at RADHARANI PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000076/2020-2021 | 627/ALD | 03/09/2020 | 120 | UMWELT ENGINEER PVT. LTD. | 65.53 | 0 | 92
523 | Alipurduar Division | Alipurduar Division | Balance work of construction of RADHARANI GODOWN cum REST SHED at RADHARANI WSS under Alipurduar Division , PHE Dte ( Part - A) | HQ-A.E | RWS Kalchini Block | ORD/000090/2022-2023 | 454/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 5.02 | 0 | 92
524 | Alipurduar Division | Alipurduar Division | Construction of Approach Road with paver Block at RADHARANI WSS under Alipurduar Division , PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000091/2022-2023 | 455/ALD | 13/05/2022 | 30 | BHAGWATI BHUJEL | 4.96 | 0 | 92
525 | Alipurduar Division | Alipurduar Division | Balance work of Radharani Godown cum rest shed under Radharani WSS under Alipurduar Division, PHE Dte. (Part-B) | HQ-A.E | RWS Kalchini Block | ORD/000186/2022-2023 | 1020/ALD | 21/07/2022 | 30 | ASHOK PRADHAN | 2.82 | 0 | 89
526 | Alipurduar Division | Alipurduar Division | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-1 | HQ-A.E | RWS Kalchini Block | ORD/000196/2020-2021 | 1027/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 22.54 | 92
527 | Alipurduar Division | Alipurduar Division | PROVIDING HOUSE CONNECTION FOR RADHARANI PWSS AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | HQ-A.E | RWS Kalchini Block | ORD/000197/2020-2021 | 1028/ALD | 18/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 37.24 | 32.53 | 91
528 | Alipurduar Division | Alipurduar Division | Laying HDPE pipe , Road crossing and other misc woks related to Radharani WSS under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000272/2021-2022 | 1838/ALD | 10/12/2021 | 45 | UMWELT ENGINEER PVT. LTD. | 3.01 | 0 | 91
529 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipe line for Bijaynagar Busty Area under Radharani Water Supply Scheme, Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000328/2021-2022 | 2201/ALD | 11/01/2022 | 60 | SOUVIK ROY PALADHI | 41.96 | 33.82 | 92
530 | Alipurduar Division | Alipurduar Division | Providing FHTC at surrounding area of Radharani Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000476/2021-2022 | 2762/ALD | 25/02/2022 | 60 | SOUVIK ROY PALADHI | 34.95 | 0 | 92
531 | Alipurduar Division | Alipurduar Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 9.97 | 0
532 | Alipurduar Division | Alipurduar Sadar Sub-Division | Balance part of laying of HDPE/DI pipe line alongwith construction of RCC piller at different area of DIMDIMA TG under ALIPURDUAR Division, PHED. | Birpara A.E | Alipurduar Sub Division | ORD/000069/2020-2021 | 622/ALD | 03/09/2020 | 120 | M/S SSB CONSTRUCTION | 34.11 | 0 | 88
533 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | Birpara A.E | Alipurduar Sub Division | ORD/000319/2020-2021 | 1452/ALD | 25/01/2021 | 45 | GOUTAM KUMAR DAS | 43.73 | 0 | 87
534 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | Alipurduar Sub Division | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 0 | 100
535 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of DI/MS/HDPE Pipe line for the Dimdima Zone-II and Nangdala Extension, Dimdima WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000357/2020-2021 | 1795/ALD | 22/02/2021 | 60 | DILIP MAHATO | 31.27 | 9.09 | 87
536 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 2.53 | 0
537 | Alipurduar Division | Birpara Sub-Division | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000072/2021-2022 | 879/ALD | 03/09/2021 | 60 | TAPASH KUMAR BHOWMICK | 45.7 | 0 | 76
538 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 73
539 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BAROBISHA ZONE- I water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000142/2020-2021 | 858/ALD | 14/10/2020 | 30 | TAPAN CHANDA | 4.98 | 9.97 | 0
540 | Alipurduar Division | Birpara Sub-Division | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS | Birpara Sub Division | ORD/000183/2020-2021 | 1008/ALD | 12/11/2020 | 60 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 9 | 100
541 | Alipurduar Division | Birpara Sub-Division | Providing House connection for PATLAKHAWA water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte. Part-IV | Alipurduar RWS | Birpara Sub Division | ORD/000221/2020-2021 | 1172/ALD | 15/12/2020 | 60 | SOUVIK ROY PALADHI | 23.92 | 0 | 79
542 | Alipurduar Division | Birpara Sub-Division | Providing House connection for PURBA KATHALBARI water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar RWS | Birpara Sub Division | ORD/000222/2020-2021 | 1173/ALD | 15/12/2020 | 60 | MADHAB SAHA | 19.93 | 11.96 | 0
543 | Alipurduar Division | Birpara Sub-Division | Laying of DI pipeline, painting, plastering, land development and other misc works related to Patlakhawa OHR under Patlakhawa PWSS at Alipurduar-I Block, under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000286/2021-2022 | 1855/ALD | 13/12/2021 | 45 | TAPAN CHANDA | 4.26 | 1.65 | 77
544 | Alipurduar Division | Birpara Sub-Division | Construction of boulder apron and land development at Patlakhawa WSS (Pump House no-2) under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000296/2020-2021 | 1339/ALD | 11/01/2021 | 30 | SHIBA ENTERPRISE | 4.98 | 9.95 | 0
545 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | Alipurduar RWS | Birpara Sub Division | ORD/000468/2021-2022 | 2766/ALD | 25/02/2022 | 60 | TAPASH KUMAR BHOWMICK | 42.34 | 0 | 75
546 | Alipurduar Division | Birpara Sub-Division | House connection Providing for MAKRAPARA TG PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED . | Birpara A.E | Birpara Sub Division | ORD/000091/2020-2021 | 697/ALD | 16/09/2020 | 120 | DILIP MAHATO | 25.73 | 15.24 | 0
547 | Alipurduar Division | Birpara Sub-Division | Repair of Gate, Drainage System & Rest Shed infront of Office cum Godown building at H/W Site of Birpara WSS under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000129/2020-2021 | 875/ALD | 14/10/2020 | 45 | DILIP MAHATO | 4.97 | 9.61 | 0
548 | Alipurduar Division | Birpara Sub-Division | PROVIDING HOUSE CONNECTION FOR DIMDIMA Z-II PWSS AT MADARIHAT-BIRPARA BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | Birpara A.E | Birpara Sub Division | ORD/000195/2020-2021 | 1026/ALD | 18/11/2020 | 60 | ASHIT KUMAR SINGHA | 19.61 | 30.28 | 0
549 | Alipurduar Division | Birpara Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Birpara A.E | Birpara Sub Division | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 26.98 | 94
550 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2022 to 31.12.2022) | Birpara A.E | Birpara Sub Division | ORD/000308/2021-2022 | 2015/ALD | 29/12/2021 | 365 | RATAN DUTTA | 1.76 | 0 | 0
551 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE pipeline for the Hantapara WSS (Jamtala Area) under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000323/2020-2021 | 1455/ALD | 25/01/2021 | 45 | M/S SURAJIT DEY & CO | 8.92 | 7.79 | 98
552 | Alipurduar Division | Birpara Sub-Division | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS and infront of bhutnirghat WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | Birpara A.E | Birpara Sub Division | ORD/000394/2021-2022 | 2308/ALD | 25/01/2022 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 2.49 | 0 | 89
553 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline for Hantapara Topline under Hatapara WSS within Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000429/2021-2022 | 2627/ALD | 18/02/2022 | 60 | DILIP MAHATO | 16.19 | 0 | 69
554 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | Birpara A.E | Birpara Sub Division | VCH/000942/2020-2021 | 570/20-21 | 26/03/2021 | 0 | GOUTAM KUMAR DAS | 15 | 0 | 0
555 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Delivary line with M.S FOR Connection of KAIJALI BUSTY WSS under Jainti TG Water Supply Scheme . | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000087/2022-2023 | 451/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.94 | 4.86 | 66
556 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAIJALI BASTYI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000150/2020-2021 | 862/ALD | 14/10/2020 | 30 | DAS ENTERPRISE | 4.96 | 4.96 | 68
557 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAIJALI BUSTY water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2020-2021 | 913/ALD | 16/10/2020 | 30 | DAS ENTERPRISE | 4.96 | 4.96 | 67
558 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAIJALI BUSTY water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000210/2020-2021 | 1164/ALD | 15/12/2020 | 60 | GHOSH & SAHA CONSTRUCTION | 19.93 | 14.95 | 68
559 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of pipe line for Turturi Khanda (Kaijali Busty Area), Culvert crossing and Laying Delivery line with DI and MS under Kaijali Busty TG WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000329/2021-2022 | 2202/ALD | 11/01/2022 | 60 | TAPASH KUMAR BHOWMICK | 41.95 | 24.34 | 66
560 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of HDPE/DI pipeline for TURTURI TG area, Kaijali Busty PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000480/2021-2022 | 2899/ALD | 08/03/2022 | 60 | ASHOK SAPKOTA | 34.24 | 32.92 | 68
561 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000193/2022-2023 | 1220/ALD | 10/08/2022 | 60 | SREE MAA CONSTRUCTION | 21.55 | 0 | 94
562 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pump House, boundary wall, laying of UPVC pipe linr & Rising main connection for Purba Chepani PWSS proposed 4th TW SITE under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000519/2022-2023 | 3494/ALD | 23/03/2023 | 90 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.66 | 20.16 | 48
563 | Alipurduar Division | Birpara Sub-Division | Laying of DI / UPVC Pipeline & other Misc. works related to DIMA PWSS under Alipurduar Division PHED. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000068/2020-2021 | 623/ALD | 03/09/2020 | 120 | TILAK SHARMA | 29.43 | 8.26 | 30
564 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 2nd site of Dima TG PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000141/2025-2026 | 1578/ALD | 31/07/2025 | 60 | TAPASH DAS | 0.99 | 0 | 0
565 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at Headwork site of Dima TG PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000142/2025-2026 | 1579/ALD | 31/07/2025 | 60 | TAPASH DAS | 0.79 | 0 | 0
566 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 3.06 | 72
567 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000321/2021-2022 | 2197/ALD | 11/01/2022 | 1116 | DEBABRATA DUTTA | 21.58 | 0 | 69
568 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000349/2021-2022 | 2142/ALD | 06/01/2022 | 30 | DEBAJYOTI SUTRADHAR | 5.02 | 0 | 52
569 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000442/2021-2022 | 2750/ALD | 24/02/2022 | 60 | AMBITIOUS ENTERPRISE | 36.94 | 15.64 | 68
570 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0
571 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC from existing distribution system as per specification for JAGIJHORA PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000286/2023-2024 | 1993/ALD | 15/09/2023 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 33.81 | 0 | 0
572 | Alipurduar Division | Alipurduar Sadar Sub-Division | soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-2 Venue: 1) Jogijhora 2)Jateswar 3)Gopalpur 4)Madhya Parokata | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000360/2021-2022 | 2122/ALD | 05/01/2022 | 30 | MOYTEC | 4.9 | 4.9 | 26
573 | Alipurduar Division | Alipurduar Sadar Sub-Division | LAYING OF HDPE PIPELINE FOR LEFTOUT PORTION OF FHTC AT JOGIJHORA & BHUTNIRGHAT MOUZA UNDER AUGMENTATION OF JAGIJHORA BARABAK SCHEME (SM/10169) UNDER ALIPURDUAR DIVISION, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000394/2024-2025 | 4180/ALD | 03/12/2024 | 331 | NARENDRA BHADANI. | 57.58 | 0 | 80
574 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000414/2021-2022 | 2582/ALD | 17/02/2022 | 180 | ASHIM KUMAR GHOSH | 63.76 | 43.25 | 43
575 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for JAGIJHORA BARABAK PWSS under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000425/2021-2022 | 2609/ALD | 17/02/2022 | 90 | SUBHAS CHANDRA ROY | 21.13 | 13.24 | 100
576 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
577 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of HDPE/DI pipeline for Jogijhora Barabak PWSS under Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000477/2021-2022 | 2896/ALD | 08/03/2022 | 960 | MS DEYS CONSTRUCTION | 56.01 | 53.21 | 100
578 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of boundary wall for Jogijhora Barabak PWSS of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/10169) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000509/2023-2024 | 827/ALD | 14/03/2024 | 60 | MANI PRADHAN | 2.5 | 0 | 0
579 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE pipe line for left out house hold connection at Ethelbari TG PWSS(SM/13449) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000540/2023-2024 | 894/ALD | 15/03/2024 | 360 | DILIP MAHATO | 18.65 | 0 | 100
580 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Jogijhora WSS under Alipurduar Division, PHE Dte. Part-3 (2 nd call) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000572/2021-2022 | 3145/ALD | 25/03/2022 | 30 | M/S SURAJIT DEY & CO | 5.02 | 0 | 0
581 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at 1st site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000609/2024-2025 | 5599/ALD | 27/03/2025 | 60 | NARENDRA BHADANI. | 0.78 | 0 | 0
582 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at 2nd site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000610/2024-2025 | 5600/ALD | 27/03/2025 | 60 | NARENDRA BHADANI. | 0.79 | 0 | 0
583 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at 3nd site of Jogijhora Barabak PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000614/2024-2025 | 5604/ALD | 27/03/2025 | 60 | NARENDRA BHADANI. | 0.95 | 0 | 0
584 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000001/2024-2025 | 3606/ALD | 24/10/2024 | 0 | Resource Division | 9.11 | 0 | 0
585 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at H/W site including laying distribution system and providing FHTC for DAKSHIN PAITKAPARA PWSS Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000006/2022-2023 | 16/ALD | 01/04/2022 | 240 | HARIDAS GHOSH | 230.68 | 200.3 | 86
586 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for DAKSHIN PAITKAPARA PWSS under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000011/2022-2023 | 21/ALD | 01/04/2022 | 120 | SOUVIK ROY PALADHI | 230.7 | 199.21 | 55
587 | Alipurduar Division | Birpara Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Dakshin Paitkapara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000107/2022-2023 | 699/ALD | 08/06/2022 | 30 | HARIDAS GHOSH | 4.92 | 4.92 | 84
588 | Alipurduar Division | Birpara Sub-Division | Construction of Boundary Wall and pathway for Dakshin Paitkapara PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000237/2022-2023 | 1329/ALD | 24/08/2022 | 1064 | M/S BASU CONSTRUCTION AND CO | 36.21 | 10.83 | 82
589 | Alipurduar Division | Birpara Sub-Division | Cons. Of balance portion of pump house, boundary wall, rising main, laying of DI and HDPE pipeline for 3rd site of Dakshin Paitkapara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000241/2023-2024 | 1787/ALD | 29/08/2023 | 120 | ANUP GUPTA | 22.82 | 0 | 40
590 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 90 | ANUP GUPTA | 20.99 | 5.91 | 80
591 | Alipurduar Division | Birpara Sub-Division | Construction of 300cum OHR for Dakshin Paitkapara Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000416/2021-2022 | 2584/ALD | 17/02/2022 | 180 | Z STAR COMMOTRADE PVT LTD. | 63.78 | 33.8 | 83
592 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 160 | 0
593 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000002/2022-2023 | 394/ALD | 11/05/2022 | 0 | Resource Division | 11.54 | 0 | 0
594 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline and connection with main line by UPVC, GI, DI pipe and construction of valve chamberand others at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000065/2022-2023 | 342/ALD | 02/05/2022 | 45 | DILIP MAHATO | 25.7 | 16.89 | 92
595 | Alipurduar Division | Alipurduar Sadar Sub-Division | Loop Connention between West Falakata & Barodoba area via Mujnai River Bridge incl interconnection with the existing BHUTNIRGHAT PWSS under FALAKATA Aug. PWSS under Alipurduar Division PHED. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000072/2020-2021 | 626/ALD | 03/09/2020 | 120 | GOUTAM KUMAR DAS | 26.08 | 1.53 | 83
596 | Alipurduar Division | Alipurduar Sadar Sub-Division | Sinking of Big Dia T/Well P/House B/Wall & Rising Main of 3rd T/Well Site at FALAKATA Aug. PWSS under Alipurduar Division PHED. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000083/2020-2021 | 655/ALD | 08/09/2020 | 120 | BILTU DAS | 22.65 | 16.12 | 82
597 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of 250 mm dia CI Sluice Valve for Augmentation of Bhutnirghat Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000117/2022-2023 | 709/ALD | 08/06/2022 | 30 | DILIP MAHATO | 4.93 | 4.93 | 98
598 | Alipurduar Division | Alipurduar Sadar Sub-Division | Gap filling by UPVC/DI pipe for Bhutnirghat WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000253/2021-2022 | 1600/ALD | 22/11/2021 | 30 | GOUTAM KUMAR DAS | 4.99 | 4.99 | 98
599 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/Jal Swapna (Schools, AWC and others) for Bhutnirghat PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. Part-4 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000258/2021-2022 | 1605/ALD | 22/11/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 5.04 | 95
600 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/Jal Swapna for Bhutnirghat PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. Part-5 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000259/2021-2022 | 1606/ALD | 22/11/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 0 | 97
601 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of CIDF, Rising Main, Delivery line, Hydraulic Testing, disinfection of UPVC pipeline and other allied works at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000297/2022-2023 | 1688/ALD | 20/09/2022 | 60 | DILIP MAHATO | 5.82 | 0 | 0
602 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 450cum OHR for Bhutnirghat Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000310/2021-2022 | 2186/ALD | 11/01/2022 | 180 | DILIP MAHATO | 87.59 | 74.96 | 80
603 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-3 VENUE : 1)Chuniajhora TG 2) Dakshin Paitkapara 3)Jay Birpara 4) Bhutnirghat | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000361/2021-2022 | 2123/ALD | 05/01/2022 | 30 | R B TESTING | 4.86 | 4.86 | 67
604 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000379/2021-2022 | 2379/ALD | 31/01/2022 | 90 | DILIP MAHATO | 92.34 | 80.57 | 98
605 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC pipeline and Tube well Boring by Reverse Rotary method of drilling for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000380/2021-2022 | 2380/ALD | 31/01/2022 | 60 | DILIP MAHATO | 95.15 | 81.04 | 97
606 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC including Rising main and laying of distribution pipeline for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000381/2021-2022 | 2381/ALD | 31/01/2022 | 60 | DILIP MAHATO | 89.08 | 64.5 | 94
607 | Alipurduar Division | Alipurduar Sadar Sub-Division | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS and infront of bhutnirghat WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000394/2021-2022 | 2308/ALD | 25/01/2022 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 2.49 | 2.45 | 89
608 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 100
609 | Alipurduar Division | Alipurduar Sadar Sub-Division | Shifting and Laying distribution of P/line due to Widening of Falkata to Dhupguri rd. & other allied works to Bhutnirghat PWSS under Alipurduar Division PHED. part (II). | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000438/2020-2021 | 08/ALD | 02/04/2020 | 1826 | SHIB RATAN BHOWMIK | 17.51 | 6.68 | 0
610 | Alipurduar Division | Birpara Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
611 | Alipurduar Division | Birpara Sub-Division | Gap filling of distribution pipeline and other allied works for Satkodali and adjoining area under Banchukamari PWSS within Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000207/2025-2026 | 2351/ALD | 10/11/2025 | 75 | DAS CONSTRUCTION | 68.41 | 0 | 0
612 | Alipurduar Division | Birpara Sub-Division | Cons. Of balance portion of pump house, boundary wall, rising main, laying of DI and UPVC pipeline for Aug. of Banchukamari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000220/2023-2024 | 1580/ALD | 24/08/2023 | 120 | HITANGSHU CHOUDHURY | 20.36 | 8.25 | 35
613 | Alipurduar Division | Birpara Sub-Division | Construction of Piller and Repairing of pipeline with GI Pipe near the house of Durga Oraon, kamal Roy & Banchukamari 1No. BFP School for Banchukamari WSS unedr Alipurduar Division, PHE Dte | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000232/2022-2023 | 1229/ALD | 10/08/2022 | 30 | TAPASH DAS | 3.07 | 0 | 80
614 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC and DI distribution line, repairing and renovation of 2nos pump house for Aug. Of Banchukamari PWSS Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000477/2023-2024 | 695/ALD | 07/03/2024 | 180 | DAS CONSTRUCTION | 50.59 | 35.81 | 2
615 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000032/2022-2023 | 1705/ALD | 21/09/2022 | 0 | Resource Division | 61.6 | 0 | 0
616 | Alipurduar Division | Birpara Sub-Division | Laying of new UPVC/DI pipeline for replacement of 75mm dia UPVC pipe with 90mm dia pipeline, gap filling and re distribution of branch line in the distribution system along with the others allied works under Munshipara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000516/2022-2023 | 3401/ALD | 16/03/2023 | 955 | NARENDRA BHADANI. | 90.61 | 51.29 | 85
617 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at HEADWORK site of MUNSHIPARA PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000579/2024-2025 | 5393/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.94 | 0 | 0
618 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 2nd TW site of MUNSHIPARA PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000581/2024-2025 | 5395/ALD | 17/03/2025 | 60 | TAPASH DAS | 0.79 | 0 | 0
619 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Connection for Assistant Engineer Alipurduar RWS Sub-Division PHE Reti Forest, Bandapani | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00106/2022-2023 | 444/22-23/PFMS | 21/01/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
620 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 150cum. OHR for Bandapani ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000137/2022-2023 | 974/ALD | 15/07/2022 | 540 | MITHUN DAS | 49.89 | 43.12 | 86
621 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply Installation Commissioning and Trial Operation of Electro Mechanical components at Bandapani TG Hindi High School within Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Part-1) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000233/2022-2023 | 1230/ALD | 10/08/2022 | 30 | BHAGWATI BHUJEL | 3.92 | 3.88 | 25
622 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply Installation Commissioning and Trial Operation of Electro Mechanical components at Bandapani TG Hindi High School withing Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Part-2) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000234/2022-2023 | 1231/ALD | 10/08/2022 | 30 | BHAGWATI BHUJEL | 3.8 | 3.3 | 24
623 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 method of drilling at Head work site, Construction of 1 no. Pump house and Boundary wall at headwork site, Rising Main and Distribution line with FHTC (Part-1) for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000285/2022-2023 | 1639/ALD | 19/09/2022 | 775 | PRAMESH LAMA | 43.08 | 20.04 | 50
624 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 1 no. Pump House, 1 no. Boundary wall at headwork site, distribution of pipeline and providing FHTC for BANDAPANI TG AREA PWSS (ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000296/2022-2023 | 1687/ALD | 20/09/2022 | 720 | MITHUN DAS | 53.39 | 46.7 | 78
625 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works at head works site for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000310/2022-2023 | 2134/ALD | 10/11/2022 | 30 | MOYTEC | 0.7 | 0.64 | 0
626 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of drinking water through tanker by hired vehicle to mitigate drinking water crisis at Bandapani TG under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000310/2023-2024 | 2175/ALD | 06/10/2023 | 45 | NARENDRA BHADANI. | 3.48 | 3.48 | 100
627 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works at head works site for BANDAPANI TG AREA PWSS (ZONE-2) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000312/2022-2023 | 2136/ALD/ | 10/11/2022 | 30 | MOYTEC | 0.66 | 0.61 | 0
628 | Alipurduar Division | Alipurduar Sadar Sub-Division | SUPPLY, INSTALLATION,COMMISSIONING AND TRIAL OPERATION OF ELECTRO MECHANICAL COMPONENTS OF RIGBORE T/W(2NOS.) FOR BANDAPANI AREA ALONG WITH CONS. OF 2NOS. P/H OF SIZE 3.00M X 3.60M | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000335/2020-2021 | 1485/ALD | 27/01/2021 | 60 | DILIP MAHATO | 22 | 3.75 | 25
629 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system (Part-2) and providing FHTC for BANDAPANI TG AREA PWSS (ZONE-I) under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000340/2022-2023 | 2249/ALD | 21/11/2022 | 130 | PRAMESH LAMA | 52.84 | 30.31 | 83
630 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 150 cum OHR as per Departmental Design and drawing, Tube well Boring by ODEX-165 method of drilling 1 nos. respectively at H/W site, Rising main and distribution line (part-1) for BANDAPANI TG AREA PWSS (ZONE-II) under Birpara Sub-Division , Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000341/2022-2023 | 2250/ALD | 21/11/2022 | 540 | SAMIRON PODDER | 88.7 | 85.63 | 85
631 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pump house, boundary wall, TW boring (by ODEX-165 method of drilling) and Rising main for 2nd TW site at Bandapani PWSS (Zone-II) under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000367/2023-2024 | 83/ALD | 10/01/2024 | 240 | MITHUN DAS | 24.21 | 19.15 | 85
632 | Alipurduar Division | Birpara Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
633 | Alipurduar Division | Birpara Sub-Division | Replacement of damaged pipeline with HDPE pipes for Purba Kathalbari Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000105/2025-2026 | 1223/ALD | 01/07/2025 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 5.3 | 0 | 0
634 | Alipurduar Division | Birpara Sub-Division | Laying of different dia. Pipeline and providing FHTC for Northern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000141/2022-2023 | 978/ALD | 15/07/2022 | 60 | DILIP MAHATO | 99.77 | 76.96 | 15
635 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-II PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000142/2022-2023 | 979/ALD | 15/07/2022 | 1081 | JYOTI CHHETRI | 45.88 | 38.27 | 61
636 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-IV PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000143/2022-2023 | 980/ALD | 15/07/2022 | 720 | MAHENDRA CHHETRI | 46.09 | 27.06 | 60
637 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Purba Kathalbari PWSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000144/2022-2023 | 981/ALD | 15/07/2022 | 45 | MAHENDRA CHHETRI | 24.2 | 7.33 | 26
638 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for PurbaKathalbari PWSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000145/2022-2023 | 982/ALD | 15/07/2022 | 45 | DAS CONSTRUCTION | 24.14 | 0 | 27
639 | Alipurduar Division | Birpara Sub-Division | Construction of 150cum. OHR for PURBA KATHALBARI ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000149/2022-2023 | 984/ALD | 15/07/2022 | 720 | MAHENDRA CHHETRI | 50.44 | 38.98 | 52
640 | Alipurduar Division | Birpara Sub-Division | Construction of OHR 200cum for PURBA KATHALBARI ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000152/2022-2023 | 986/ALD | 15/07/2022 | 180 | MADHAB SAHA | 55.36 | 45.63 | 51
641 | Alipurduar Division | Birpara Sub-Division | Construction of 250cum OHR for PURBA KATHALBARI ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000155/2022-2023 | 987/ALD | 15/07/2022 | 180 | NEOGI ENTERPRISE | 57.61 | 38.03 | 35
642 | Alipurduar Division | Birpara Sub-Division | Soil investigation work at 4 different places of Purba Kanthalbari within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000157/2022-2023 | 1006/ALD | 15/07/2022 | 30 | MABCO CONSULTANT, | 4.87 | 4.87 | 27
643 | Alipurduar Division | Birpara Sub-Division | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection for Purba Kathalbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000158/2022-2023 | 988/ALD | 15/07/2022 | 60 | NEOGI ENTERPRISE | 98.79 | 80.1 | 30
644 | Alipurduar Division | Birpara Sub-Division | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Purba Kathalbari Zone-II PWSS within APD-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000158/2025-2026 | 1743/ALD | 13/08/2025 | 60 | ANIRBAN DEY SARKAR CONSTRUCTION | 41.04 | 0 | 0
645 | Alipurduar Division | Birpara Sub-Division | Laying Distribution of pipeline with DI and UPVC pipeline along with FHTC Connection at Jogendranagar area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000159/2022-2023 | 989/ALD | 15/07/2022 | 60 | UTTAM KUMAR DUTTA | 98.45 | 87.43 | 27
646 | Alipurduar Division | Birpara Sub-Division | Construction of OHR 200cum for PURBA KATHALBARI ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000161/2022-2023 | 991/ALD | 15/07/2022 | 180 | MS DEYS CONSTRUCTION | 55.5 | 25 | 55
647 | Alipurduar Division | Birpara Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Sirubari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000163/2022-2023 | 993/ALD | 15/07/2022 | 783 | MS DEYS CONSTRUCTION | 99.93 | 69.73 | 85
648 | Alipurduar Division | Birpara Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection surrounding Palashbari area, Purba Kathalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000164/2022-2023 | 994/ALD | 15/07/2022 | 180 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 87.56 | 53.26 | 28
649 | Alipurduar Division | Birpara Sub-Division | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding, Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000165/2022-2023 | 995/ALD | 15/07/2022 | 60 | DAS ENTERPRISE | 99.06 | 67.23 | 27
650 | Alipurduar Division | Birpara Sub-Division | Laying of different dia. Pipeline and providing FHTC for Purba Kathalbari Zone(IV) PWSS area and surrounding area of NH-31D at Alipurduar-I Block under Alipurduar Division, PHE Dte.(Part-B) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000166/2022-2023 | 996/ALD | 15/07/2022 | 60 | NARAYAN CHANDRA SAHA | 99.18 | 75.08 | 76
651 | Alipurduar Division | Birpara Sub-Division | Laying of different dia. Pipeline and providing FHTC for Southern side of Purba Kathalbari Zone (II) PWSS and surrounding areas at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000167/2022-2023 | 997/ALD | 15/07/2022 | 60 | M/S JHA CONSTRUCTION | 99.69 | 76.99 | 27
652 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Purba Kathalbari Zone-III PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000168/2022-2023 | 1008/ALD | 15/07/2022 | 90 | MADHAB SAHA | 45.9 | 39.6 | 86
653 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of 1 no. pump house for Purba Kathalbari Zone-I PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000169/2022-2023 | 1007/ALD | 15/07/2022 | 90 | SAMIRON PODDER | 43.06 | 40.49 | 0
654 | Alipurduar Division | Birpara Sub-Division | Laying of pipeline distribution system (Parallel and left out Area) and other allied works at Purba Kathalbari Zone-I PWSS within APD-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000211/2025-2026 | 2414/ALD | 18/11/2025 | 60 | ANIRBAN DEY SARKAR CONSTRUCTION | 54.38 | 0 | 0
655 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for PURBA KATHALBARI PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000288/2023-2024 | 1996/ALD | 15/09/2023 | 60 | M/S SIBU DEY AND CO | 24.2 | 0 | 0
656 | Alipurduar Division | Birpara Sub-Division | Development of TW, Yield testing with BHT Pump and water sample collection and chemical test at different tubewell of Purba Kathal Bari PWSS at Alipurduar-I Block, Alipurduar Division PHED. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000351/2022-2023 | 2495/ALD | 13/12/2022 | 60 | SAMIRON PODDER | 5.68 | 0 | 0
657 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000416/2022-2023 | 2731/ALD | 30/12/2022 | 365 | KAMALESH ROY | 4.8 | 4.58 | 100
658 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
659 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Deputy Superintending Engineer, North Bengal Circle-I , P.H.E. Dte.(from 01.03.2023 to 29.02.2024) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000473/2022-2023 | 3232/ALD | 27/02/2023 | 365 | MAHENDRA CHHETRI | 4.8 | 0 | 0
660 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000499/2023-2024 | 488/ALD | 15/02/2024 | 366 | SASANKA ROY | 4.8 | 3.54 | 0
661 | Alipurduar Division | Birpara Sub-Division | Laying of DI and HDPE pipeline, Trenchless Pipe laying by HDD Process & other works for PURBA KATHALBARI ZONE-I 3rd pump house area for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000503/2023-2024 | 821/ALD | 14/03/2024 | 480 | KAJAL KUMAR DE | 39.26 | 0 | 70
662 | Alipurduar Division | Birpara Sub-Division | Laying of different dia., CIDF, DI, UPVC, HDPE Pipeline, Trenchless Pipe laying by HDD Process, HDPE pipe line for left out household connection,Trial and run the entire PURBA KATHALBARI ZONE-3 PWSS Scheme with maintaining for 3 months after successfully running water, cons. of surface drain, pathway at H/W site and other works works for Purba Kathalbari PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/11459) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000534/2023-2024 | 892/ALD | 15/03/2024 | 355 | MADHAB SAHA | 49.29 | 4.78 | 60
663 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000007/2024-2025 | 3612/ALD | 24/10/2024 | 0 | Resource Division | 7.78 | 0 | 0
664 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000025/2022-2023 | 1590/ALD | 14/09/2022 | 0 | Resource Division | 130.15 | 0 | 0
665 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including laying distribution system, Rising main and providing FHTC for MECHPARA TEA GARDEN AREA PWSS under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000004/2022-2023 | 14/ALD | 01/04/2022 | 120 | SHREE RANISATI ENTERPRISE | 224.94 | 114.03 | 38
666 | Alipurduar Division | Birpara Sub-Division | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 58
667 | Alipurduar Division | Birpara Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Mechpara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000116/2022-2023 | 708/ALD | 08/06/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.89 | 4.89 | 40
668 | Alipurduar Division | Birpara Sub-Division | Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 08.08.2022 to 31.10.2022) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000343/2022-2023 | 1191/ALD | 05/08/2022 | 92 | NIRANJAN KIRTANIA | 0.7 | 0.39 | 100
669 | Alipurduar Division | Birpara Sub-Division | Construction of OHR 200cum for Mechpara Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000421/2021-2022 | 2600/ALD | 17/02/2022 | 180 | M/S KAMAK ENGINEERS AND CO | 55.33 | 21.1 | 80
670 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 120 | 0
671 | Alipurduar Division | Birpara Sub-Division | Supply ,delivery and installation of split type air condition for the Chamber of Division Account Office under Alipurduar Division , P.H.E Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000499/2022-2023 | 3363/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.64 | 0 | 0
672 | Alipurduar Division | Birpara Sub-Division | Supply ,delivery and installation of split type air condition for the Accounts section under Alipurduar Division , P.H.E Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000500/2022-2023 | 3364/ALD | 14/03/2023 | 30 | HARI CONSTRUCTION | 0.64 | 0 | 0
673 | Alipurduar Division | Birpara Sub-Division | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-A) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000583/2021-2022 | 1967/ALD | 24/12/2021 | 90 | HARIDAS GHOSH | 0.96 | 0.96 | 39
674 | Alipurduar Division | Birpara Sub-Division | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-A) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000589/2021-2022 | 359/ALD | 08/06/2021 | 90 | HARIDAS GHOSH | 0.96 | 0.96 | 40
675 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000015/2022-2023 | 826/ALD | 28/06/2022 | 0 | Resource Division | 30.31 | 0 | 0
676 | Alipurduar Division | Alipurduar Sadar Sub-Division | Road Restoration of Volka Road against PURBA CHIKLIGURI PWSS | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | BILL/00321/2024-2025 | 190/24-25/PFMS | 10/09/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 8.85 | 0 | 0
677 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, land development works, construction of surface drain, pathway, supply of CIDF specials and other allied works in connection with the PURBA CHIKLIGURI PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000387/2023-2024 | 198/ALD | 16/01/2024 | 450 | SOUVIK ROY PALADHI | 60.36 | 43.39 | 5
678 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house & Sinking of 250 mm x 200 mm X 150 mtr Big dia Tubewel at HW site & 2nd site , laying of distribution system with UPVC pipeline , Constructions of 200 Cum OHR as per Departmental Design & drawing including soil test, providing FHTC and others allied works for Purba Chikliguri PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000431/2022-2023 | 2858/ALD | 17/01/2023 | 815 | SOUVIK ROY PALADHI | 481.73 | 324.69 | 65
679 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main line with HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block along with the others allied works at Madhya Parokata head works site PWSS adjacent to adjacent to Purba Chikliguri WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000486/2023-2024 | 742/ALD | 12/03/2024 | 450 | SOUVIK ROY PALADHI | 57.31 | 0 | 30
680 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000035/2023-2024 | 1473/ALD | 16/08/2023 | 0 | Resource Division | 35.41 | 0 | 0
681 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000043/2022-2023 | 3485/ALD | 23/03/2023 | 0 | Resource Division | 11.64 | 0 | 0
682 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000085/2023-2024 | 109/ALD | 10/01/2024 | 0 | Resource Division | 11.51 | 0 | 0
683 | Alipurduar Division | Birpara Sub-Division | Construction of Tubewell by ODEX-165 method of drilling at HW site, construction of pump house and boundary wall at H/W site, laying of distribution line and providing FHTC as per Departmental Design & drawing for Garochera Bandapani PWSS Under Birpara Sub-division, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000451/2022-2023 | 2922/ALD | 19/01/2023 | 120 | RATAN DUTTA | 73.26 | 49.44 | 62
684 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000045/2023-2024 | 1953/ALD | 12/09/2023 | 0 | Resource Division | 33.29 | 0 | 0
685 | Alipurduar Division | Alipurduar Sadar Sub-Division | Gap filling of distribution line with DI/CI/UPVC pipe at Nurpur WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000192/2023-2024 | 1468/ALD | 16/08/2023 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 20.69 | 17.31 | 70
686 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for NURPUR WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000237/2023-2024 | 1591/ALD | 25/08/2023 | 30 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 6.76 | 0 | 0
687 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at NURPUR HW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000368/2023-2024 | 84/ALD | 10/01/2024 | 90 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 33.28 | 0 | 0
688 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. Of pump house & TW boring by ODEX-165 method of drilling at HW & 2nd site, LDS with UPVC pipeline including rising main & delivery connection, cons. Of 100cum OHR as per departmental design & drawing along with soil investigation works, providing FHTC including platform and others allied works for NURPUR PWSS Under Alipurduar Division PHE DTE. (2nd call) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000478/2022-2023 | 3195/ALD | 27/02/2023 | 721 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 182.4 | 141.29 | 95
689 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. (from 01.01.2024 to 31.12.2024) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000498/2023-2024 | 487/ALD | 15/02/2024 | 366 | MATRI ENTERPRISE | 4.8 | 0 | 0
690 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000020/2023-2024 | 1258/ALD | 10/08/2023 | 0 | Resource Division | 13.15 | 0 | 0
691 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for Uttar Rangalibazna PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000304/2023-2024 | 2135/ALD | 03/10/2023 | 30 | MANI PRADHAN | 1.08 | 0 | 0
692 | Alipurduar Division | Birpara Sub-Division | Cons. of Rig bored TW(2nos) by ODEX-165 method of drilling at HW and 2nd site, cons of 100 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing , providing FHTC and others allied works for Uttar Rangalibazna PWSS under Birpara Sub-Division, Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000546/2022-2023 | 3570/ALD | 27/03/2023 | 918 | SAMIRON PODDER | 271.9 | 112.72 | 11
693 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000055/2023-2024 | 2701/ALD | 12/12/2023 | 0 | Resource Division | 84.45 | 0 | 0
694 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000090/2023-2024 | 114/ALD | 10/01/2024 | 0 | Resource Division | 4.49 | 0 | 0
695 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2021-2022 | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 0 | 70
696 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000225/2021-2022 | 1575/ALD | 22/11/2021 | 90 | TAPAN CHANDA | 75.74 | 39.37 | 69
697 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-I) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000473/2021-2022 | 2763/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 19.82 | 69
698 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 30.98 | 60
699 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 0 | 70
700 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
701 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of DI pipe & CI special for Madhya Kamakhyaguri PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000044/2023-2024 | 390/ALD | 19/05/2023 | 30 | DILIP MAHATO | 71.61 | 68.44 | 75
702 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
703 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, Construction of surface drain, pathway other allied works in connection with the Madhya Kamakhyaguri PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/15517) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000226/2024-2025 | 2279/ALD | 05/08/2024 | 180 | GHOSH & SAHA CONSTRUCTION | 61.08 | 0 | 70
704 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for MADHYA KAMAKHYAGURI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000249/2023-2024 | 1850/ALD | 04/09/2023 | 45 | MONORAMA ENTERPRISE | 5.85 | 0 | 0
705 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of DI/DIDF Specials for Madhya Kamakhyaguri (SM/15517)WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000396/2024-2025 | 4235/ALD | 12/12/2024 | 30 | MADHAB SAHA | 16.91 | 0 | 0
706 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
707 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 350 cum OHR as per Departmental Design & drawing , providing FHTC and others allied works for MADHYA KAMAKHYAGURI PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000466/2022-2023 | 3155/ALD | 22/02/2023 | 180 | GHOSH & SAHA CONSTRUCTION | 478.58 | 453.17 | 85
708 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation of work of Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte. (from 01.04.2025 to 30.04.2025) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000745/2024-2025 | 5591/ALD | 26/03/2025 | 31 | APSARI BHOWMICK | 0.4 | 0 | 0
709 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.04.2025 to 30.04.2025) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000746/2024-2025 | 5592/ALD | 26/03/2025 | 31 | MATRI ENTERPRISE | 0.4 | 0 | 0
710 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000032/2023-2024 | 1277/ALD | 11/08/2023 | 0 | Resource Division | 49.36 | 0 | 0
711 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000045/2024-2025 | 4261/ALD | 13/12/2024 | 0 | Resource Division | 13.19 | 0 | 0
712 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000104/2023-2024 | 128/ALD | 10/01/2024 | 0 | Resource Division | 10.13 | 0 | 0
713 | Alipurduar Division | Birpara Sub-Division | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 350 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for MAIRADANGA PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000030/2023-2024 | 334/ALD | 16/05/2023 | 720 | MESSRS A.B.G CONSTRUCTION | 653.77 | 362.94 | 65
714 | Alipurduar Division | Birpara Sub-Division | Laying of additional DI & HDPE pipeline, Costruction of Sluice Valve chamber & other works for Providing FHTC at Mairadanga PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000051/2025-2026 | 677/ALD | 21/05/2025 | 90 | ANIRBAN DEY SARKAR CONSTRUCTION | 44.3 | 0 | 0
715 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0
716 | Alipurduar Division | Birpara Sub-Division | Construction of slab culvert, pathway and other allied works at 3rd TW Site, painting existing boundary wall, pump house, roof treatment, plinth protection at 2nd TW site of Chhoto Salkumar WSS adjacent to Mairadanga PWSS including gap filling in distribution line (90mm dia) under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000354/2023-2024 | 2606/ALD | 04/12/2023 | 692 | ASSOCIATE CONSTRUCTION COMPANY | 23.88 | 0 | 95
717 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
718 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000058/2023-2024 | 2720/ALD | 13/12/2023 | 0 | Resource Division | 68.94 | 0 | 0
719 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000096/2023-2024 | 120/ALD | 10/01/2024 | 0 | Resource Division | 15.91 | 0 | 0
720 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site , Laying of distribution system with HDPE pipeline including rising main & delivery connection , Constructions of 100 Cum OHR as per Departmental Design & drawing along with the Soil investigation works , providing FHTC and others allied works for Uttar Dhalkar PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000021/2023-2024 | 237/ALD | 04/05/2023 | 720 | TAPASH KUMAR BHOWMICK | 226.42 | 153.23 | 45
721 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of balance portion of boundary wall, pathway, surface drain and chatal, land development, laying of rising main line & delivery line connection along with the other allied works at Putimari PWSS adj. To Uttar Dhalkar PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000339/2023-2024 | 2540/ALD | 28/11/2023 | 90 | TAPASH KUMAR BHOWMICK | 25.47 | 20.77 | 100
722 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000026/2024-2025 | 3984/ALD | 27/11/2024 | 0 | Resource Division | 3.66 | 0 | 0
723 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tube Well by reverse rotary method, Construction of Pump House, Boundary Wall, Laying Of Distribution System and providing FHTC for Parpatlakhawa PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000017/2023-2024 | 235/ALD | 04/05/2023 | 720 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 113.69 | 70.52 | 16
724 | Alipurduar Division | Alipurduar RWS Sub-Division | Supply and installation of sign board at different PWSS site of Kumargram Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000053/2025-2026 | 679/ALD | 21/05/2025 | 45 | TAPASH DAS | 4.69 | 0 | 100
725 | Alipurduar Division | Alipurduar RWS Sub-Division | Gap filling of distribution line, land development and other allied works for ParpatlaKhawa Piped Water Supply Scheme within Alipurduar Block-I under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000066/2025-2026 | 818/ALD | 03/06/2025 | 75 | CHITTA RANJAN DEY | 20.25 | 0 | 0
726 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000084/2021-2022 | 980/ALD | 13/09/2021 | 60 | DILIP MAHATO | 48.35 | 0 | 68
727 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2021-2022 | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 0 | 70
728 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC & DI (with pillar) pipeline for Barobisha Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000170/2021-2022 | 1320/ALD | 05/10/2021 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 79.02 | 61.39 | 66
729 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA Zone-I water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000206/2020-2021 | 1160/ALD | 15/12/2020 | 60 | M/S SURAJIT DEY & CO | 29.98 | 0 | 69
730 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA Zone-III water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000208/2020-2021 | 1162/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 19.93 | 0 | 77
731 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC and DI (with pillar) pipeline Barobisa Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000225/2021-2022 | 1575/ALD | 22/11/2021 | 90 | TAPAN CHANDA | 75.74 | 0 | 69
732 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-I) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000473/2021-2022 | 2763/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 0 | 69
733 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 0 | 70
734 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House with Sanitary & Plumbing arrangement at H/W Site (Old) of Dalmore Water supply scheme under Alipurduar Division. P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000062/2020-2021 | 538/ALD | 20/08/2020 | 120 | PRAPTI DUTTA | 4.75 | 8.4 | 0
735 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House with Sanitary & Plumbing arrangement at 2nd Pump House Site of Dalmore-Ramjhora WSS (Ramjhora Pump House no-2) under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000094/2021-2022 | 893/ALD | 03/09/2021 | 60 | PRAMESH LAMA | 4.96 | 4.97 | 60
736 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House with Sanitary & Plumbing arrangement at Headwork Site of Dalmore-Ramjhora WSS (Ramjhora Pump House no-1) under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000095/2021-2022 | 894/ALD | 03/09/2021 | 60 | PRAMESH LAMA | 4.96 | 4.97 | 0
737 | Alipurduar Division | Birpara Sub-Division | Retrofitting work of pipeline of Dalmore PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000198/2021-2022 | 971/ALD | 13/09/2021 | 30 | MS DEYS CONSTRUCTION | 5.04 | 5.04 | 59
738 | Alipurduar Division | Birpara Sub-Division | Retrofitting of pipeline for Ramjhora TG PWSS area at Madarihat-Birpara Block under Alipurduar Division, P.H.E. Dte. | Birpara A.E | Birpara Sub Division | ORD/000316/2020-2021 | 1447/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 16.96 | 3.58 | 58
739 | Alipurduar Division | Birpara Sub-Division | Laying of balance DI/MS/HDPE pipeline for the Dalmore-Ramjhora WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000324/2020-2021 | 1456/ALD | 25/01/2021 | 45 | ASHIT KUMAR SINGHA | 21.28 | 4.28 | 59
740 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipe line for Dalmore Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000524/2021-2022 | 2996/ALD | 15/03/2022 | 60 | MS DEYS CONSTRUCTION | 8.33 | 7.04 | 58
741 | Alipurduar Division | Birpara Sub-Division | Fuel bill for the month of August 2021 | Birpara A.E | Birpara Sub Division | VCH/000567/2021-2022 | 117/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.11 | 0 | 0
742 | Alipurduar Division | Birpara Sub-Division | Fuel bill for the month of August 2021 | Birpara A.E | Birpara Sub Division | VCH/000570/2021-2022 | 121/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.22 | 0 | 0
743 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of old UPVC pipe line , FHTC and other misc. work related to DHAOLAJHORA PWSS Alipurduar - II Block under Alipurduar Division , PHE Dte | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000071/2022-2023 | 436/ALD | 13/05/2022 | 30 | MATARA CONSTRUCTION CO | 3.3 | 3.29 | 27
744 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, left out portion of household connection with HDPE pipe, providing balance FHTC, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at DHAOLAJHORA (SM/07191) 3rd TW site PWSS of Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000205/2024-2025 | 1954/ALD | 02/07/2024 | 270 | CHANDAN KIRTONIA | 33.15 | 7.5 | 70
745 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000540/2021-2022 | 3192/ALD | 28/03/2022 | 60 | GOUTAM KUMAR DAS | 49.89 | 1.8 | 81
746 | Alipurduar Division | Birpara Sub-Division | Construction of Soak well, Fencing and other works at Madhu TG PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000039/2020-2021 | 516/ALD | 20/08/2020 | 60 | TAPASH KUMAR BHOWMICK | 3.91 | 7.82 | 0
747 | Alipurduar Division | Birpara Sub-Division | Construction of Fire hydrant, parking area for water collecting vehicles, surface drain and other miscellaneous works for Madhu T.G. P/W/S/S, Under Alipurduar Division P.H.E. Dte. | HQ-A.E | Birpara Sub Division | ORD/000051/2020-2021 | 530/ALD | 20/08/2020 | 60 | TAPASH KUMAR BHOWMICK | 5 | 10 | 0
748 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Munshipara piped water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | HQ-A.E | Birpara Sub Division | ORD/000101/2020-2021 | 722/ALD | 22/09/2020 | 30 | TAPASH DAS | 4.98 | 9.97 | 0
749 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting of Mujnai PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000144/2020-2021 | 943/ALD | 19/10/2020 | 60 | VEDATRAYEE AND CO | 29.81 | 57.1 | 92
750 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline to Bharnabari TG area under Hasimara PWSS for providing at Kalchini Block under Alipurduar Division, P.H.E. Dte.(Part-B) | HQ-A.E | Birpara Sub Division | ORD/000185/2020-2021 | 1010/ALD | 12/11/2020 | 60 | ASHIT KUMAR SINGHA | 39.34 | 49.96 | 0
751 | Alipurduar Division | Birpara Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | HQ-A.E | Birpara Sub Division | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 2.8 | 94
752 | Alipurduar Division | Birpara Sub-Division | Fuel bill for the month of August 2021 | HQ-A.E | Birpara Sub Division | VCH/000570/2021-2022 | 121/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.22 | 0 | 0
753 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for Bakla Piped water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000107/2020-2021 | 728/ALD | 22/09/2020 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.98 | 9.96 | 0
754 | Alipurduar Division | Alipurduar Sadar Sub-Division | Preparation of Augmentation D.P.R after investigation For SamuktalaW/S scheme under Alipurduar Division. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000112/2021-2022 | 915/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.81 | 5.61 | 0
755 | Alipurduar Division | Alipurduar Sadar Sub-Division | "Providing House connection for Bakla water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. (Part-II)" | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000227/2020-2021 | 1137/ALD | 10/12/2020 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.98 | 9.96 | 0
756 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2020-2021 | 1283/ALD | 05/01/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 56.51 | 74
757 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000444/2021-2022 | 2753/ALD | 24/02/2022 | 1200 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 0 | 43
758 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 0
759 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of pipe line by providing steel piles at Turturi River for LOKNATHPUR Water Supply Scheme Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000088/2020-2021 | 692/ALD | 16/09/2020 | 120 | MATARA CONSTRUCTION CO | 6.04 | 5.77 | 100
760 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the 'Jal Sapna' programme (FHTC for every house hold) under Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000368/2021-2022 | 2296/ALD | 24/01/2022 | 60 | GOUTAM KUMAR DAS | 45.8 | 16.58 | 94
761 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000540/2021-2022 | 3192/ALD | 28/03/2022 | 60 | GOUTAM KUMAR DAS | 49.89 | 24.57 | 81
762 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Banchukamari piped water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000100/2020-2021 | 721/ALD | 22/09/2020 | 30 | DAS CONSTRUCTION | 4.99 | 9.99 | 0
763 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar RWS | Birpara Sub Division | ORD/000277/2021-2022 | 1844/ALD | 10/12/2021 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 0.94 | 87
764 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Banchukamari WSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar RWS | Birpara Sub Division | ORD/000280/2021-2022 | 1843/ALD | 10/12/2021 | 1422 | PROJIT HALDER | 5.02 | 0 | 87
765 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BHOLARDABRI water supply scheme at ALIPURDUAR-I Block under Alipuduar Division, P.H.E. Dte.(Part-2) | Alipurduar RWS | Birpara Sub Division | ORD/000321/2020-2021 | 1462/ALD | 25/01/2021 | 30 | HARI CONSTRUCTION | 5.01 | 10.02 | 0
766 | Alipurduar Division | Birpara Sub-Division | Providing House connection for KALCHINI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(Part-3) | Alipurduar RWS | Birpara Sub Division | ORD/000327/2020-2021 | 1463/ALD | 25/01/2021 | 30 | HARI CONSTRUCTION | 4.98 | 5.66 | 97
767 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BHOLARDABRI PWSS under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000371/2020-2021 | 1767/ALD | 19/02/2021 | 60 | HARIDAS GHOSH | 10.03 | 20.07 | 0
768 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000378/2021-2022 | 2378/ALD | 31/01/2022 | 60 | SHIBA ENTERPRISE | 51.82 | 0 | 87
769 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BHOLARDABRI WSS at Alipurduar-II Block under Alipurduar Division, PHE Dte. (Part-4) | Alipurduar RWS | Birpara Sub Division | ORD/000399/2020-2021 | 1585/ALD | 10/02/2021 | 60 | HARIDAS GHOSH | 4.98 | 9.96 | 0
770 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BHOLARDABRI WSS at Alipurduar-II Block under Alipurduar Division, PHE Dte. (Part-5) | Alipurduar RWS | Birpara Sub Division | ORD/000400/2020-2021 | 1586/ALD | 10/02/2021 | 60 | HARIDAS GHOSH | 4.98 | 9.97 | 0
771 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE pipeline and interconnection of other different dia pipe line with CIDF Specials & Providing house connection (FHTC) at Uttar Madarihat WSS under Alipurduar Division PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000127/2021-2022 | 1241/ALD | 27/09/2021 | 60 | M/S SURAJIT DEY & CO | 47.32 | 22.91 | 96
772 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repair of Pump House with additional Toilet at 2nd Pump House site of Madarihat WSS under Alipuduar Division, P.H.E. | Birpara A.E | Alipurduar Sub Division | ORD/000131/2020-2021 | 877/ALD | 14/10/2020 | 45 | DILIP MAHATO | 2.13 | 1.86 | 91
773 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting work of pipeline of Madarihat PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000199/2021-2022 | 972/ALD | 13/09/2021 | 30 | MS DEYS CONSTRUCTION | 4.99 | 4.99 | 99
774 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for AWC and school under Madarihat WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000266/2021-2022 | 1831/ALD | 10/12/2021 | 30 | RATAN DUTTA | 5.04 | 4.07 | 59
775 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of RCC boundary wall for Uttar Latabari WSS Pump House (rabindra nagar) at Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000268/2021-2022 | 1834/ALD | 10/12/2021 | 45 | SHIB RATAN BHOWMIK | 4.9 | 0 | 75
776 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE pipe line for Madarihat Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000358/2021-2022 | 2284/ALD | 21/01/2022 | 60 | DILIP MAHATO | 37.73 | 35.81 | 97
777 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE pipe line for Madarihat Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000359/2021-2022 | 2285/ALD | 21/01/2022 | 60 | MAHENDRA CHHETRI | 37.73 | 32.37 | 99
778 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for MADARIHAT PWSS under Alipuduar Division, P.H.E. Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000386/2020-2021 | 1806/ALD | 22/02/2021 | 60 | DILIP MAHATO | 20.13 | 18.11 | 90
779 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 350cum OHR for Madarihat TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000417/2021-2022 | 2586/ALD | 17/02/2022 | 180 | DILIP MAHATO | 71.4 | 20.13 | 90
780 | Alipurduar Division | Birpara Sub-Division | Construction of boundary wall at 2nd PH Site of Uttar Sishubari WSS under Alipurduar Division. | Birpara A.E | Birpara Sub Division | ORD/000096/2021-2022 | 895/ALD | 03/09/2021 | 45 | MITHUN DAS | 4.98 | 4.99 | 56
781 | Alipurduar Division | Birpara Sub-Division | Repairing of 2 nos. P/H with toilet block (PH-1 and 2) and Replacement of old existing AC p/l with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Sishubari High School and adjacent area) | Birpara A.E | Birpara Sub Division | ORD/000179/2021-2022 | 1309/ALD | 05/10/2021 | 60 | MITHUN DAS | 45.4 | 35.57 | 100
782 | Alipurduar Division | Birpara Sub-Division | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Opposite of Rail line area) | Birpara A.E | Birpara Sub Division | ORD/000236/2021-2022 | 1577/ALD | 22/11/2021 | 60 | ASHOK SAPKOTA | 22.55 | 20.81 | 54
783 | Alipurduar Division | Birpara Sub-Division | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Uttar Sishubari WSS under Alipurduar Division, PHE Dte. (Opposite of Rail line area) | Birpara A.E | Birpara Sub Division | ORD/000237/2021-2022 | 1578/ALD | 22/11/2021 | 60 | KAMALESH ROY | 22.55 | 20.81 | 55
784 | Alipurduar Division | Birpara Sub-Division | Extension/Merging of Distribution pipeline (UPVC/DI/MS/CI) from Paschim Khairbari WSS to Uttar Sishubari WSS and others misc. work under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000264/2020-2021 | 1255/ALD | 28/12/2020 | 60 | MITHUN DAS | 45.83 | 9 | 80
785 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling of Chapaguri area at Uttar Sishubari PWSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000435/2021-2022 | 2652/ALD | 21/02/2022 | 45 | KAMALESH ROY | 4.94 | 4.68 | 55
786 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Birpara A.E | Birpara Sub Division | RTOR000013/2022-2023 | 718/ALD | 13/06/2022 | 0 | Resource Division | 87.66 | 0 | 0
787 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of MUNSHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000326/2021-2022 | 2227/ALD | 14/01/2022 | 90 | TAPASH DAS | 21.92 | 13.85 | 25
788 | Alipurduar Division | Alipurduar Sadar Sub-Division | Renovation of Pump house and boundary wall at 3rd Pump house of Dhumchipara TG PWSS under Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000091/2025-2026 | 1175/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.05 | 0 | 0
789 | Alipurduar Division | Alipurduar Sadar Sub-Division | Renovation of Pump house and boundary wall at 2nd Pump house site of Dhumchipara TG PWSS under Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000092/2025-2026 | 1176/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.04 | 0 | 0
790 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for DHUMCHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000399/2021-2022 | 2390/ALD | 31/01/2022 | 90 | DILIP MAHATO | 27.18 | 0 | 18
791 | Alipurduar Division | Alipurduar Sadar Sub-Division | Sinking of Big dia. Tubewell (200 x 150 mm dia.)By modified DTH -ODEX method of drilling at Dhumchipara-2nos. site (SM/09896 & SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000533/2023-2024 | 891/ALD | 15/03/2024 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 34.47 | 14.05 | 10
792 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline under Birpara APD PWSS at Alipurduar-I under Alipurduar Division, P.H.E. Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000077/2021-2022 | 883/ALD | 03/09/2021 | 45 | KAMALESH ROY | 15.92 | 3.32 | 0
793 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BIRPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000316/2021-2022 | 2192/ALD | 11/01/2022 | 90 | DAS CONSTRUCTION | 22.03 | 7.86 | 65
794 | Alipurduar Division | Birpara Sub-Division | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 15 | 61
795 | Alipurduar Division | Birpara Sub-Division | Extension work order for Hiring of Diesel vehicle Maxi Cab(At least 7 seater) for Executive Engineer, Alipurduar Division under Alipurduar Division, PHE Dte.( 01.04.2021 to 30.06.2021) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000609/2020-2021 | 3051/ALD | 31/03/2021 | 91 | APSARI BHOWMICK | 0.54 | 0 | 100
796 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pumphouse, boundary wall,laying of UPVC pipeline & rising main connection for Salsalabari PWSS proposed 4th TW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000515/2022-2023 | 3400/ALD | 16/03/2023 | 90 | BRAJA GOPAL SAHA | 39.58 | 0 | 0
797 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
798 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 250cum. OHR for Newlands TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000138/2022-2023 | 975/ALD | 15/07/2022 | 1143 | TAPASH KUMAR BHOWMICK | 57.61 | 41.99 | 75
799 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.08.2022 to 31.10.2022) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000201/2022-2023 | 1122/ALD | 29/07/2022 | 92 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 100
800 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for NEWLANDS TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000206/2022-2023 | 1275/ALD | 17/08/2022 | 501 | TAPASH KUMAR BHOWMICK | 96.78 | 90.66 | 95
801 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for NEWLANDS TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000213/2022-2023 | 1307/ALD | 22/08/2022 | 120 | MADHAB SAHA | 97.2 | 91.59 | 94
802 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for NEWLAND TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000246/2023-2024 | 1792/ALD | 29/08/2023 | 60 | SUBHAK CHIK BARAIK | 13.39 | 0 | 0
803 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of Rising Main line with HDPE PN 10, bridge and culvert crossing, cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Newlands TG H/W Site under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000336/2023-2024 | 391/ALD | 05/02/2024 | 450 | K S ENTERPRISE | 48.23 | 0 | 65
804 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2022 to 31.01.2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000344/2022-2023 | 2013/ALD | 28/10/2022 | 92 | NIRANJAN KIRTANIA | 0.7 | 0.47 | 100
805 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.11.2022 to 31.01.2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000345/2022-2023 | 2014/ALD | 28/10/2022 | 92 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 100
806 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000007/2023-2024 | 188/ALD | 28/04/2023 | 0 | Resource Division | 18.72 | 0 | 0
807 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000043/2024-2025 | 4259/ALD | 13/12/2024 | 0 | Resource Division | 11.34 | 0 | 0
808 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 250cum. OHR for Sankosh TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000140/2022-2023 | 977/ALD | 15/07/2022 | 180 | SOUVIK ROY PALADHI | 57.62 | 39.52 | 80
809 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House,Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for SANKOSH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000207/2022-2023 | 1276/ALD | 17/08/2022 | 120 | SOUVIK ROY PALADHI | 96.66 | 90.94 | 50
810 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for SANKOSH TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000208/2022-2023 | 1277/ALD | 17/08/2022 | 120 | SOUVIK ROY PALADHI | 83.75 | 73.88 | 70
811 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for SANKOSH TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000244/2023-2024 | 1790/ALD | 29/08/2023 | 533 | SOUVIK ROY PALADHI | 12.27 | 0 | 75
812 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of Rising Main line with HDPE PN 10, bridge and culvert crossing, cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Sankosh TG H/W Site under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000335/2023-2024 | 390/ALD | 05/02/2024 | 450 | K S ENTERPRISE | 48.17 | 0 | 65
813 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE/DI Pipeline for filling up the gap & bridge / culvert crossing, specials repair with trial run of pipeline and allied works at Sankosh TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000398/2023-2024 | 209/ALD | 16/01/2024 | 450 | SOUVIK ROY PALADHI | 19.84 | 3.66 | 80
814 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000008/2023-2024 | 189/ALD | 28/04/2023 | 0 | Resource Division | 15.48 | 0 | 0
815 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000026/2022-2023 | 1591/ALD | 14/09/2022 | 0 | Resource Division | 6.68 | 0 | 0
816 | Alipurduar Division | Alipurduar Division | Extension of pipeline from Santali TG connection line to upper line of Madhu TG area (booster line) under Hasimara TG PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000024/2022-2023 | 19/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.61 | 0 | 49
817 | Alipurduar Division | Alipurduar Division | Extension of pipeline from Malangi TW to Bharnobari TG area (booster line) under Hasimara PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000025/2022-2023 | 20/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 14.64 | 0 | 50
818 | Alipurduar Division | Alipurduar Division | Construction of valve chamber, dismantling concrete road and other misc works at Malangi TG area within Hasimara W/S/S under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000077/2022-2023 | 442/ALD | 13/05/2022 | 30 | MADHAB SAHA | 4.9 | 0 | 49
819 | Alipurduar Division | Alipurduar Division | Construction of HP Culvert for drainage purpose with 900 mm dia humepipe and construction of screening and inspection chamber at Hasimara PWSS HWS under Alipurduar Division PHE Dte.,Part-B | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000215/2022-2023 | 1105/ALD | 29/07/2022 | 30 | ALATYA CONSTRUCTION & CO. | 3.6 | 3.59 | 100
820 | Alipurduar Division | Alipurduar Division | Construction of HP Culvert for drainage purpose with 900 mm dia humepipe and construction of screening and inspection chamber at Hasimara PWSS HWS under Alipurduar Division PHE Dte., Part-C | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000216/2022-2023 | 1106/ALD | 29/07/2022 | 30 | ALATYA CONSTRUCTION & CO. | 4.08 | 4.08 | 100
821 | Alipurduar Division | Alipurduar Division | Laying of DI pipe and connection with Tubewell, Construction of Pathway, Fencing work and other works at Malangi TG Pump House under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000220/2022-2023 | 1110/ALD | 29/07/2022 | 990 | MAHENDRA CHHETRI | 4.99 | 0 | 100
822 | Alipurduar Division | Alipurduar Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of HASIMARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000294/2021-2022 | 1992/ALD | 27/12/2021 | 90 | MAHENDRA CHHETRI | 42.03 | 0 | 49
823 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipeline for Malangi Tea Garden Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000375/2021-2022 | 2375/ALD | 31/01/2022 | 60 | MADHAB SAHA | 74.82 | 5.1 | 94
824 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000012/2022-2023 | 717/ALD | 13/06/2022 | 0 | Resource Division | 49.83 | 0 | 0
825 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000083/2023-2024 | 107/ALD | 10/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
826 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Totpara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000112/2022-2023 | 704/ALD | 08/06/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.92 | 4.92 | 99
827 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing and renovation of 2 nos. pump house, boundary wall (H/W Site, 2nd site), Pathway, Cons. Of 2 nos New Toilet and restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Totpara Water Supply Scheme under Alipurduatr Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000238/2021-2022 | 1579/ALD | 22/11/2021 | 1200 | NARENDRA BHADANI. | 22.78 | 19.7 | 100
828 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing and renovation of 2 nos. pump house, boundary wall (H/W Site, 2nd site), Pathway, Cons. Of 2 nos New Toilet and restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Totpara Water Supply Scheme under Alipurduatr Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000239/2021-2022 | 1580/ALD | 22/11/2021 | 1200 | SASANKA ROY | 22.78 | 20.11 | 100
829 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Totpara WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000283/2021-2022 | 1852/ALD | 13/12/2021 | 30 | HARI CONSTRUCTION | 5.04 | 5.04 | 96
830 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 250cum OHR for TATPARA Piped Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000441/2021-2022 | 2749/ALD | 24/02/2022 | 180 | M/S DUTTA AND CO | 57.62 | 42.05 | 99
831 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of Laying Distribution system by replacing damaged AC pipeline with DI and UPVC pipe for TATPARA WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000498/2021-2022 | 3003/ALD | 15/03/2022 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 39.2 | 37.8 | 98
832 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI pipe with pillar of TATPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000532/2021-2022 | 3106/ALD | 24/03/2022 | 60 | HARI CONSTRUCTION | 7.06 | 6.94 | 98
833 | Alipurduar Division | Birpara Sub-Division | Providing House connection and extension of pipe line for Silbarihat area within PATLAKHAWA PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000072/2021-2022 | 879/ALD | 03/09/2021 | 60 | TAPASH KUMAR BHOWMICK | 45.7 | 12.33 | 76
834 | Alipurduar Division | Birpara Sub-Division | Laying of Different Dia pipeline And providing FHTC For Patlakhowa and Adjoining area under Patlakhowa PWSS at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000122/2022-2023 | 919/ALD | 07/07/2022 | 45 | M/S DUTTA AND CO | 72.26 | 47.54 | 70
835 | Alipurduar Division | Birpara Sub-Division | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000183/2020-2021 | 1008/ALD | 12/11/2020 | 60 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 0.25 | 100
836 | Alipurduar Division | Birpara Sub-Division | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000184/2020-2021 | 1009/ALD | 12/11/2020 | 60 | M/S PALIT ENTERPRISE | 14.4 | 0.28 | 70
837 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of Patlakhawa Piped Water Supply Scheme | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000239/2022-2023 | 1331/ALD | 24/08/2022 | 60 | UTTAM SAHA | 29.37 | 28.52 | 97
838 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Silbarihat under Patlakhawa PWSS. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000468/2021-2022 | 2766/ALD | 25/02/2022 | 60 | TAPASH KUMAR BHOWMICK | 42.34 | 30.19 | 75
839 | Alipurduar Division | Birpara Sub-Division | Laying of additional HDPE pipeline at Ramjhora TG under Ranjhora WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000128/2025-2026 | 1536/ALD | 29/07/2025 | 45 | SUNIL HAJANG THAKUR | 13.14 | 0 | 0
840 | Alipurduar Division | Birpara Sub-Division | Soil investigation work for proposed overhead reservoir, cons. Of 150cum OHR at Dalmore, 2nos. Of TW boring by ODEX-165 method of drilling at Dalmore and Ramjhora, cons. of pump house and boundary wall at both TW site, LDS as per Departmental Design & drawing for DALMORE & RAMJHORA TG PWSS under Birpara Sub-Division, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000131/2023-2024 | 638/ALD | 06/06/2023 | 180 | SUKAMAL GHOSH | 158.82 | 0 | 0
841 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for DALMORE RAMJHORA PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000293/2023-2024 | 2024/ALD | 19/09/2023 | 60 | SUDDHYA SING LAMA | 23.76 | 0 | 0
842 | Alipurduar Division | Birpara Sub-Division | Soil investigation work for proposed overhead reservoir , Constructions of 150 Cum OHR at HW site and providing FHTC as per Departmental Design & drawing for Ramjhora PWSS Under Birpara Sub-division, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000398/2022-2023 | 2661/ALD | 22/12/2022 | 600 | SUDDHYA SING LAMA | 91.76 | 89.94 | 90
843 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000417/2022-2023 | 2732/ALD | 30/12/2022 | 365 | PARITOSH SUTRADHAR | 4.8 | 2.3 | 90
844 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
845 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000005/2024-2025 | 3610/ALD | 24/10/2024 | 0 | Resource Division | 11.11 | 0 | 0
846 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline and connection with main line by UPVC, GI, DI pipe and construction of valve chamberand others at Bhutnirghat WSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000065/2022-2023 | 342/ALD | 02/05/2022 | 45 | DILIP MAHATO | 25.7 | 0.68 | 92
847 | Alipurduar Division | Birpara Sub-Division | Preparation of Augmentation D.P.R after investigation For Dalimpur W/S scheme under Alipurduar Division. | Birpara A.E | RWS Falakata Block | ORD/000114/2021-2022 | 920/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.18 | 4.37 | 0
848 | Alipurduar Division | Birpara Sub-Division | Extension of Distribution line with UPVC pipe line (From B.Ed College to Pulin Biswas House) under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000132/2020-2021 | 878/ALD | 14/10/2020 | 30 | NARAYAN CHANDRA SAHA | 3.14 | 5.95 | 0
849 | Alipurduar Division | Birpara Sub-Division | Extension of Distribution line with UPVC pipe line (From Pulin Biswas House to Bipul Islam House) under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000133/2020-2021 | 879/ALD | 14/10/2020 | 30 | PARAMJYOTI ENTERPRISE | 3.14 | 5.94 | 0
850 | Alipurduar Division | Birpara Sub-Division | Providing House connection for DALIMPUR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | Birpara A.E | RWS Falakata Block | ORD/000154/2020-2021 | 866/ALD | 14/10/2020 | 30 | SANJIT SAHA | 4.93 | 4.93 | 88
851 | Alipurduar Division | Birpara Sub-Division | Extension of Distribution line with UPVC pipe line (From Bhaben Biswas House to Ghughurertala Hridoy Barman's House) at Deodanga under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000174/2020-2021 | 918/ALD | 16/10/2020 | 30 | PARAMJYOTI ENTERPRISE | 3.16 | 5.96 | 0
852 | Alipurduar Division | Birpara Sub-Division | Extension of Distribution line with UPVC pipe line (From Bamoner Bhangha Nagesh barman's House to Kashikanta Biswas House) near Bulet Club under Dalimpur Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000175/2020-2021 | 919/ALD | 16/10/2020 | 30 | NARAYAN CHANDRA SAHA & SONS | 3.16 | 5.99 | 0
853 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Dalimpur water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte.(Part-II) | Birpara A.E | RWS Falakata Block | ORD/000214/2020-2021 | 1134/ALD | 10/12/2020 | 30 | PARAMJYOTI ENTERPRISE | 4.98 | 4.98 | 85
854 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc work for Dalimpur WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000232/2020-2021 | 1178/ALD | 15/12/2020 | 60 | M/S PALIT ENTERPRISE | 45.48 | 54.37 | 86
855 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc work for Dalimpur WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte.(under Jateswar-I GP area) | Birpara A.E | RWS Falakata Block | ORD/000234/2020-2021 | 1179/ALD | 15/12/2020 | 60 | NARAYAN CHANDRA SAHA | 45.66 | 21.5 | 0
856 | Alipurduar Division | Alipurduar Division | Hydro-Geologica! investigation aboutWater evaluation, availability and quality parameterfor both ground and surface sources at Lankapara and Gentral Dooars Tea Estate within Alipuduar district. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | BILL/00683/2023-2024 | 429/23-24/PFMS | 28/03/2024 | 0 | IIT CONSULTATIVE PRACTICE | 2.36 | 0 | 0
857 | Alipurduar Division | Alipurduar Division | Constructions of 2(TWO) NOS 150 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline, RISING MAIN, Construction of BOUNDARY WALL, 4(FOUR) NOS ODEX-165 TUBE WELL, 4(FOUR) NOS PUMP HOUSE, Soil Investigation work, providing FHTC and others allied works for RANGAMATI TEA GAEDEN PWSS(ZONE-I+ZONE-II), Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000182/2023-2024 | 1171/ALD | 03/08/2023 | 720 | M/S RADHASWAMI ENTERPRISE | 440.2 | 89.83 | 40
858 | Alipurduar Division | Alipurduar Division | Providing FHTC from existing distribution system as per specification for Rangamati TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000262/2023-2024 | 1880/ALD | 07/09/2023 | 30 | ASHOK PRADHAN | 9.49 | 0 | 0
859 | Alipurduar Division | Alipurduar Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
860 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000019/2024-2025 | 3953/ALD | 26/11/2024 | 0 | Resource Division | 13.97 | 0 | 0
861 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000080/2023-2024 | 104/ALD | 10/01/2024 | 0 | Resource Division | 9.73 | 0 | 0
862 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline (left out ) at Dhanirampur PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000133/2025-2026 | 1626/ALD | 04/08/2025 | 60 | DILIP MAHATO | 30.28 | 0 | 0
863 | Alipurduar Division | Birpara Sub-Division | Laying of rising main, delivery main, bypass arrangement, Laying of HDPE Pipeline for left out household connection and other allied works at Dhanirampur PWSS (both H/W and 2nd site) of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/15208) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000511/2023-2024 | 829/ALD | 14/03/2024 | 45 | DILIP MAHATO | 58.7 | 47.31 | 70
864 | Alipurduar Division | Birpara Sub-Division | Supply of DIDF pipes and DI specials and CI Jeffy Coupling for Dhanirampur Water Supply Scheme (SM/15208) of Falakata Block under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000519/2023-2024 | 838/ALD | 14/03/2024 | 30 | BARMAN ENTERPRISE | 9.78 | 9.78 | 90
865 | Alipurduar Division | Birpara Sub-Division | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 250 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for DHANIRAMPUR PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000575/2022-2023 | 3636/ALD | 31/03/2023 | 900 | DILIP MAHATO | 457.51 | 430.34 | 95
866 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000095/2023-2024 | 119/ALD | 10/01/2024 | 0 | Resource Division | 9.56 | 0 | 0
867 | Alipurduar Division | Birpara Sub-Division | Replacement of damaged pipeline with HDPE pipes for Sidhabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000076/2025-2026 | 974/ALD | 12/06/2025 | 60 | SANKAR ROY | 8.53 | 0 | 0
868 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE and distribution pipes in different suitable locations of Sidhabari PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000453/2022-2023 | 2970/ALD | 31/01/2023 | 90 | BILTU DAS | 165.16 | 61.62 | 61
869 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
870 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
871 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Rising Main and delivery main connection along with laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing and other allied works for Nararthali PWSS adjacent to Purba Narathali WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000067/2025-2026 | 819/ALD | 03/06/2025 | 90 | NARAYANIMAA EXIM PVT. LTD. | 32.53 | 0 | 0
872 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
873 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land Development, repairing of Pump house, construction of Pathway and protection work of 3rd TW site of Narathali PWSS under Alipurduar Divn, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000334/2023-2024 | 2520/ALD | 24/11/2023 | 60 | SREE MAA CONSTRUCTION | 6.99 | 4.93 | 100
874 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of HW site boundary wall (40M), construction of pathway, surface drain, chatal and other misc works related to Narathali PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000338/2023-2024 | 2524/ALD | 24/11/2023 | 60 | TAPAN CHANDA | 5.33 | 5.33 | 100
875 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system, fixing of FHTC by means of PCC Concrete Block and others allied works in connection with the Purba Narathali (SM/16537) PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000348/2024-2025 | 3418/ALD | 26/09/2024 | 60 | MADHAB SAHA | 57.8 | 0 | 0
876 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main line with HDPE PN10, horizontal boring by HDD method , bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block, land development along with the other allied works at PURBA NARATHALI HW site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000371/2023-2024 | 87/ALD | 10/01/2024 | 90 | MADHAB SAHA | 34.86 | 16.14 | 45
877 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF Specials and Jeffy Coupling for Purba Narathali (SM/16537) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000400/2024-2025 | 4266/ALD | 13/12/2024 | 30 | HITANGSHU CHOUDHURY | 19.67 | 0 | 0
878 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
879 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of DI specials and CI Jeffy coupling for Purba Narathali Water Supply Scheme(SM/16537) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000514/2023-2024 | 833/ALD | 14/03/2024 | 30 | DILIP MAHATO | 13.51 | 0 | 0
880 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house & Tube well Boring by ODEX-165 Method of drilling at HW site & 2nd site , laying of distribution system with UPVC pipeline including rising main & delivery connection, Constructions of 250 Cum OHR as per Departmental Design & drawing along with the Soil investigation works , providing FHTC and others allied works for Purba Narathali PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000550/2022-2023 | 3573ALD | 27/03/2023 | 720 | MADHAB SAHA | 373.15 | 311.75 | 5
881 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000005/2023-2024 | 186/ALD | 28/04/2023 | 0 | Resource Division | 246.11 | 0 | 0
882 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000047/2024-2025 | 4267/ALD | 13/12/2024 | 0 | Resource Division | 13.19 | 0 | 0
883 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000102/2023-2024 | 26/ALD | 10/01/2024 | 0 | Resource Division | 10.95 | 0 | 0
884 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
885 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
886 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for UTTAR MAJIDKHANA PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000213/2023-2024 | 1567/ALD | 23/08/2023 | 225 | TAPASH KUMAR BHOWMICK | 9.36 | 0 | 0
887 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Uttar Majidkhana WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000227/2023-2024 | 1606/ALD | 25/08/2023 | 30 | TAPASH KUMAR BHOWMICK | 7.89 | 7.88 | 100
888 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
889 | Alipurduar Division | Alipurduar Sadar Sub-Division | CONS of PH and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site and 2nd site , LDS with UPVC P/LINE , CONS of 200 Cum OHR , incl the Soil investigation works, providing FHTC and others allied works for Uttar Majidkhana PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000518/2022-2023 | 3416/ALD | 17/03/2023 | 925 | TAPASH KUMAR BHOWMICK | 490.21 | 376.32 | 95
890 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation order of "Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (in soft copy) to PHE Dte. PART-B" | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000547/2023-2024 | 313/ALD | 25/01/2024 | 180 | TAPASH KUMAR BHOWMICK | 4.67 | 4.67 | 100
891 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation order of "Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte." | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000548/2023-2024 | 314/ALD | 25/01/2024 | 180 | TAPASH KUMAR BHOWMICK | 4.29 | 4.29 | 100
892 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000017/2023-2024 | 223/ALD | 03/05/2023 | 0 | Resource Division | 16.73 | 0 | 0
893 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000048/2023-2024 | 2396/ALD | 08/11/2023 | 0 | Resource Division | 11.63 | 0 | 0
894 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000055/2024-2025 | 4275/ALD | 13/12/2024 | 0 | Resource Division | 26.21 | 0 | 0
895 | Alipurduar Division | Alipurduar Sadar Sub-Division | payment against proposal No : FP/WB/Others/443310/2023for boundary demarcation and construction of boundary pillar for diversion of forest land of area 0.0464 ha for 28 and 29 mile basty PWSS ( Z-IV) Garam basty under JJM at garam basty forest Village under BTR ( West) Division under WDPO Range . | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00182/2024-2025 | 144/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.94 | 0 | 0
896 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment for NPV for diversion of forest land of 0.0464 ha area against proposal No : FP/WB/Others/443310/2023 for water supply scheme 28 and 29 Mile Basty PWSS ( Z-VI) Garam Basty under JJM Garam Basty Forest Village under BTR(West ) Division under WDPO Range under DPO_9 Compartment | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00183/2024-2025 | 145/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 5.18 | 0 | 0
897 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cost of raising and maintenance of the compensatory afforestation ( 100 trees plantation and mtc for 10 years ) against proposed diversion of forest land for 28 and 29 mile basty PWSS (Z-IV) Garam Basty under JJM against Proposal No : FP/WB/Others/443310/2023 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00184/2024-2025 | 146/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0
898 | Alipurduar Division | Alipurduar Sadar Sub-Division | payment for NPV Demand Note against In-principal (Stage-l) approval of Central Government under Section 2 (1) (ii) of the Van (Sanrakshan Evam Samvardhan) Adhiniyam-1980 for non-forestry use of 0.1458 ha. of forest land in favour of West Bengal Public Health Engineering Directorate for Gravity Based Water Supply Scheme (GBWSS) under Jal Jeevan Mission (JJM) 28 & 29 Mile Basty PWSS under Buxa Tiger Reserve (East) Forest Division. (Proposal No. FPWBIOTHERSI442029/2023). | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00188/2024-2025 | 147/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 15.59 | 0 | 0
899 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cost of raising and maintenance of the Compensatory Afforestation demand note against In-principal (Stage-l) approval of Central Government under Section 2 (1) (ü) of the Van (Sanrakshan Evam Samvardhan) Adhiniyam-1980 for Directorate non-forestry use of 0.1458 ha. of forest land in favour of West Bengal Public Health Engineering for Gravity Based Water Supply Scheme (GBWSS) under Jal Jeevan Mission (JJM) 28 & 29 Mile Basty PWSS under Buxa Tiger Reserve (East) Forest Division. (Proposal No. FPWBIOTHERS/442029/2023 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00189/2024-2025 | 148/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0
900 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment against proposal no . FP/ WB/ Others/ 442029/2023- for erection of Boundary pillar at diverted site against In - principal ( stage - I ) approval of water supply scheme for Buxa Forest PWSS uder Jal Jeevan Mission at 28 & 29 Mile Basty , Buxa tiger Reserve ( East) Division - reg | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00339/2024-2025 |  | 18/09/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.21 | 0 | 0
901 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment against proposal no . FP/ WB/ Others/ 442029/2023- for erection of Boundary pillar at diverted site against In - principal ( stage - I ) approval of water supply scheme for Buxa Forest PWSS uder Jal Jeevan Mission at 28 & 29 Mile Basty , Buxa tiger Reserve ( East) Division - reg | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00506/2024-2025 | 329/24-25/PFMS | 19/12/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.31 | 0 | 0
902 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 200cum OHR as per departmental design and drawing, providing FHTC for 28 and 29 mile Busty PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000002/2023-2024 | 05/ALD | 04/04/2023 | 180 | A B TECHNO ENTERPRISE | 91.25 | 0 | 0
903 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000084/2025-2026 | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
904 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC from existing distribution system as per specification for 28 and 29 MILE BASTY PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000294/2023-2024 | 2103/ALD | 29/09/2023 | 60 | EVEREST INFRATECH INC | 47.79 | 0 | 0
905 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new UPVC pipeline, Construction of 2 Nos Pump House ,Pipe Support Structure, Land Development, Boundary Wall, Path way, Providing FHTC, and other allied works for Gram Busty Area Under 28 & 29 Mile Basty (Zone-IV) PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000357/2023-2024 | 2608/ALD | 04/12/2023 | 270 | HITANGSHU CHOUDHURY | 70.82 | 14.23 | 45
906 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of additional Diesel Vehicle Maxi Cab (At least 7 seater) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000391/2024-2025 | 3883/ALD | 22/11/2024 | 365 | SOUVIK ROY PALADHI | 4.8 | 0 | 0
907 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation of work of Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000457/2024-2025 | 4552/ALD | 30/12/2024 | 90 | APSARI BHOWMICK | 1.2 | 0 | 0
908 | Alipurduar Division | Alipurduar Sadar Sub-Division | Arrangement for online application in Paribesh Portal for getting Forest permission at 7nos BOPs under Alipurduar Division P.H.E Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000458/2023-2024 | 496/ALD | 16/02/2024 | 30 | HILL GROUND CONSULTANCY | 1.83 | 0 | 100
909 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Head Quarter, Alipurduar Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000458/2024-2025 | 4553/ALD | 30/12/2024 | 90 | DIPAK DAS | 1.2 | 1.07 | 0
910 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.01.2024 to 31.12.2024) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000461/2023-2024 | 160/ALD | 11/01/2024 | 366 | APSARI BHOWMICK | 4.8 | 0 | 0
911 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
912 | Alipurduar Division | Alipurduar Sadar Sub-Division | Conceptualization, design and implementing mass awareness generation through Wall writing at 113 nos. villages (Block - Falakata, Kalchini, Madarihat) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal.(SM/16506) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2023-2024 | 751/ALD | 12/03/2024 | 130 | LIMRA SOCIAL WELFARE SOCIETY | 27.08 | 26.66 | 100
913 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 2nos Tw boring by ODEX-165 method of drilling including distribution system with new UPVC pipeline, 2 nos Pump house, Boundary wall, pathway, providing FHTC and other allied works for 28 and 29 mile busty PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000558/2022-2023 | 3502/ALD | 23/03/2023 | 600 | HITANGSHU CHOUDHURY | 76.18 | 29.23 | 80
914 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000035/2024-2025 | 4251/ALD | 13/12/2024 | 0 | Resource Division | 31.69 | 0 | 0
915 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000073/2023-2024 | 98/ALD | 10/01/2024 | 0 | Resource Division | 10.79 | 0 | 0
916 | Alipurduar Division | Birpara Sub-Division | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , Soil investigation at OHR site, constructions of 400 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Narasingpur PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000174/2023-2024 | 1048/ALD | 20/07/2023 | 672 | DILIP MAHATO | 567.48 | 496.14 | 90
917 | Alipurduar Division | Birpara Sub-Division | Rising Main, Laying of DI (K7), gap filling of HDPE pipe, construction of sluice valve chamber for washout purpose in the command area of NARASINGPUR PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000322/2023-2024 | 2417/ALD | 09/11/2023 | 60 | DILIP MAHATO | 36.67 | 35.44 | 80
918 | Alipurduar Division | Birpara Sub-Division | Laying of Rising main, delivery main, bypass arrangement, laying of HDPE pipeline for left out household connecting to Narasingpur PWSS (both H/W and 2nd site) (SM/15758) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000492/2023-2024 | 748/ALD | 12/03/2024 | 120 | DILIP MAHATO | 91.41 | 79.14 | 85
919 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000041/2023-2024 | 1480/ALD | 16/08/2023 | 0 | Resource Division | 21.43 | 0 | 0
920 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000064/2023-2024 | 2774 | 18/12/2023 | 0 | Resource Division | 15.16 | 0 | 0
921 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000067/2023-2024 | 2774/ALD | 18/12/2023 | 0 | Resource Division | 15.16 | 0 | 0
922 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for MAKRAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000398/2021-2022 | 2389/ALD | 31/01/2022 | 90 | INDRAYOODH BHOWAL | 27.18 | 23.11 | 0
923 | Alipurduar Division | Alipurduar Sadar Sub-Division | Shifting of pipeline along the road of Birpara-Makrapara Gomtu Road under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000447/2021-2022 | 2654/ALD | 21/02/2022 | 30 | DILIP MAHATO | 3.62 | 3.11 | 0
924 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of HDPE pipeline and providing FHTC for Garochira area, Makrapara PWSS under Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000478/2021-2022 | 2897/ALD | 08/03/2022 | 60 | DILIP MAHATO | 33.9 | 0 | 42
925 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE pipeline near existing PH No-01 village for the Makrapara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000554/2021-2022 | 3046/ALD | 21/03/2022 | 30 | DILIP MAHATO | 4.95 | 0 | 42
926 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0
927 | Alipurduar Division | Birpara Sub-Division | Supply of fuel for Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 08/08/2022 to 31.12.2022) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000178/2022-2023 | 1184/ALD | 05/08/2022 | 153 | MATRI ENTERPRISE | 1.27 | 0 | 0
928 | Alipurduar Division | Birpara Sub-Division | Laying of different dia DI,UPVC pipeline, bridge and culvert crossing and other works for providing FHTC at Jogendrapur and Satpukuri mouza at Augmentation of Jogendrapur PWSS under Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10678) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000230/2024-2025 | 2283/ALD | 05/08/2024 | 60 | MONORAMA ENTERPRISE | 21.88 | 0 | 0
929 | Alipurduar Division | Birpara Sub-Division | Painting of Old OHR at Jogendrapur PWSS (400cum) under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000440/2024-2025 | 5044/ALD | 17/02/2025 | 45 | DILIP MAHATO (OPC) PRIVATE LIMITED | 3.14 | 0 | 0
930 | Alipurduar Division | Birpara Sub-Division | Laying distribution line, providing road and culvert crossing, and providing FHTC for Jogendrapur and Satpukuria Mouzas and adjacent areas, Cons. of Tubewell by ODEX-165 method of drilling, cons. of pump house and boundary wall for augmentation of JOGENDRAPUR PWSS. (2nd call) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000481/2022-2023 | 3198/ALD | 27/02/2023 | 180 | BIJOY ROY | 159.61 | 67.65 | 25
931 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary Wall at Proposed 3rd TW site of Kohinur TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000039/2023-2024 | 370/ALD | 18/05/2023 | 120 | DILIP MAHATO | 17.39 | 17.27 | 100
932 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE/DI pipe line near Dangi Bazar area for interconnection in the distribution system and bridge /culvert crossing under KOHINUR TEA GARDEN PWSS , Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000227/2024-2025 | 2280/ALD | 05/08/2024 | 240 | JAYDAB ADHIKARI | 26.67 | 0 | 85
933 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE/DI pipe line near kohinur TG factory area for interconnection in the distribution system and bridge /culvert crossing , Construction of Pump House, Boundary Wall at Head work site of KOHINUR TEA GARDEN PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113). | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000229/2024-2025 | 2282/ALD | 05/08/2024 | 240 | DILIP MAHATO | 60.91 | 13.08 | 95
934 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for KOHINUR TG PWSS (PART-II) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000243/2023-2024 | 1789/ALD | 29/08/2023 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 16.73 | 0 | 0
935 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for KOHINUR TG PWSS (PART-I) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000250/2023-2024 | 1852/ALD | 04/09/2023 | 60 | TAPASH DAS | 16.73 | 13.52 | 81
936 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works for proposed overhead reservoir of KOHINUR TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000314/2022-2023 | 2223/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 16
937 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 method of drilling at 2nd TW site, Construction of Pump house and Boundary wall at 2nd site, Laying of Rising and delivery line connection, Providing FHTC and other allied works for KOHINUR TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000326/2022-2023 | 2235/ALD | 21/11/2022 | 120 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 96.96 | 53.89 | 56
938 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE/DI pipe line near Dangi Aashram Ground and Kohinur Gram Panchayat office area for interconnection in the distribution system and bridge /culvert crossing under KOHINUR TEA GARDEN PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/12113) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000393/2024-2025 | 4179/ALD | 03/12/2024 | 60 | MAHAPRABHU ENTERPRISE | 61.89 | 0 | 0
939 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 400 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for KOHINUR TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000458/2022-2023 | 2979/ALD | 02/02/2023 | 360 | DILIP MAHATO | 237.14 | 203.99 | 86
940 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. (from 01.01.2025 to 31.03.2025) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000459/2024-2025 | 4554/ALD | 30/12/2024 | 90 | MATRI ENTERPRISE | 1.2 | 0 | 0
941 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
942 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Kohinur TG Water Supply Scheme under Alipurduar Division P.H.E. Dte.(SM/12113) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000468/2023-2024 | 674/ALD | 06/03/2024 | 150 | BHAGWATI BHUJEL | 11.36 | 11.33 | 80
943 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000012/2023-2024 | 218/ALD | 03/05/2023 | 0 | Resource Division | 35.18 | 0 | 0
944 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000052/2024-2025 | 4272/ALD | 13/12/2024 | 0 | Resource Division | 12.78 | 0 | 0
945 | Alipurduar Division | Alipurduar Division | Laying of CI/DI/MS Pipe for delivery line, cons. of RCC Pillar with ISMB and balance part of boundary wall of CWR Project Area and earth filling at River Bed site of JDA (JAIGAON DEVELOPMENT AUTHORITY) Area Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000013/2021-2022 | 405/ALD | 17/06/2021 | 30 | DILIP MAHATO | 49.78 | 4 | 67
946 | Alipurduar Division | Alipurduar Division | PROVIDING FHTC IN CONNECTION WITH JALDHARA JAL SAPNA FOR AUGMENTATION OF FALAKATA WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION, PHE DTE. (COMMAND AREA : OLD OHR) | HQ-A.E | RWS Kalchini Block | ORD/000031/2021-2022 | 579/ALD | 15/07/2021 | 45 | NARENDRA BHADANI. | 21.24 | 35.05 | 0
947 | Alipurduar Division | Alipurduar Division | Constrcution of Pump House with Sanitary & Plumbing arrangement at 2nd Site (Old) of Dalmore Water supply scheme under Alipurduar Division. P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000061/2020-2021 | 537/ALD | 20/08/2020 | 120 | M/S MONORAMA ENTERPRISE | 4.75 | 8.4 | 0
948 | Alipurduar Division | Alipurduar Division | Gap filling and culvert crossing along the main road at Zone-II and Zone-I by MS, DI Pipe and other allied works at JDA WSS under Alipurduar Division, PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000064/2022-2023 | 341/ALD | 02/05/2022 | 45 | DILIP MAHATO | 10.82 | 0 | 63
949 | Alipurduar Division | Alipurduar Division | Loop Connention between West Falakata & Barodoba area via Mujnai River Bridge incl interconnection with the existing BHUTNIRGHAT PWSS under FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000072/2020-2021 | 626/ALD | 03/09/2020 | 120 | GOUTAM KUMAR DAS | 26.08 | 0 | 83
950 | Alipurduar Division | Alipurduar Division | Repairing of old UPVC pipe line , FHTC and other misc. work related to FALAKATA PWSS FALAKATA Block under Alipurduar Division , PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000072/2022-2023 | 437/ALD | 13/05/2022 | 30 | NARENDRA BHADANI. | 4.66 | 3.81 | 66
951 | Alipurduar Division | Alipurduar Division | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling and FHTC connection at different location of AUG. of Falakata PWSS (ZONE -II & III) under Alipurduar Division , PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000074/2022-2023 | 439/ALD | 13/05/2022 | 30 | SASANKA ROY | 4.73 | 4.75 | 66
952 | Alipurduar Division | Alipurduar Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000078/2021-2022 | 876/ALD | 03/09/2021 | 60 | M/S AMIT KUMAR GUPTA | 35.43 | 3.03 | 75
953 | Alipurduar Division | Alipurduar Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 73
954 | Alipurduar Division | Alipurduar Division | Sinking of Big Dia T/Well P/House B/Wall & Rising Main of 3rd T/Well Site at FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000083/2020-2021 | 655/ALD | 08/09/2020 | 120 | BILTU DAS | 22.65 | 0 | 82
955 | Alipurduar Division | Alipurduar Division | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Augmentation of Falakata WSS under Alipurduar Division, PHE Dte.( Masterpara, BDO Office and adjacent area.) | HQ-A.E | RWS Kalchini Block | ORD/000083/2021-2022 | 979/ALD | 13/09/2021 | 60 | MESSRS R N TRADERS | 40.51 | 38.36 | 67
956 | Alipurduar Division | Alipurduar Division | Laying of UPVC/DI/MS/CI Distribution pipe line for Gap filling and FHTC connection at different location of AUG. of Falakata PWSS (ZONE - I & III) under Alipurduar Division , PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000089/2022-2023 | 453/ALD | 13/05/2022 | 30 | NARENDRA BHADANI. | 5.05 | 5.04 | 65
957 | Alipurduar Division | Alipurduar Division | Installation of rising main with CI/DI pipeline and others misc. works for augmentation of Falakata PWSS (For Old OHR) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000096/2022-2023 | 460/ALD | 13/05/2022 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 5.02 | 5.02 | 100
958 | Alipurduar Division | Alipurduar Division | Preparation of Agumentation D.P.R after investigation For Kumargram W/Sscheme under Alipurduar Division. | HQ-A.E | RWS Kalchini Block | ORD/000109/2021-2022 | 912/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.77 | 2.58 | 0
959 | Alipurduar Division | Alipurduar Division | Laying of Distribution Line (by using metal Pipes) of Zone-I for JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000118/2020-2021 | 789/ALD | 01/10/2020 | 150 | M/S SSB CONSTRUCTION CO. | 185.6 | 22.05 | 65
960 | Alipurduar Division | Alipurduar Division | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000153/2020-2021 | 865/ALD | 14/10/2020 | 30 | GOUTAM KUMAR DAS | 4.98 | 3.68 | 0
961 | Alipurduar Division | Alipurduar Division | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte.(PART-2) | HQ-A.E | RWS Kalchini Block | ORD/000161/2020-2021 | 905/ALD | 16/10/2020 | 30 | GOUTAM KUMAR DAS | 4.98 | 9.97 | 0
962 | Alipurduar Division | Alipurduar Division | Replacement of old existing AC pipeline with UPVC pipe and providing FHTC in connection with Jaldhara/Jal Sapna for Augmentation of Falakata WSS under Alipurduar Division, PHE Dte.( Subhaspally and adjacent area.) | HQ-A.E | RWS Kalchini Block | ORD/000186/2021-2022 | 1314/ALD | 05/10/2021 | 60 | SOUVIK ROY PALADHI | 41.3 | 26.04 | 67
963 | Alipurduar Division | Alipurduar Division | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Block Faakata & Madarihat Block under Alipurduar Division P.H.E Dte. | HQ-A.E | RWS Kalchini Block | ORD/000187/2023-2024 | 1205/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100
964 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipeline including Providing FHTC at Jaigaon Development Area Zone-II from Krishna Pradhan house to Geeta Chhetri house within Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000196/2022-2023 | 1222/ALD | 10/08/2022 | 60 | MAHENDRA CHHETRI | 36.35 | 0 | 67
965 | Alipurduar Division | Alipurduar Division | Providing House connection for BHUTNIRGHAT water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | HQ-A.E | RWS Kalchini Block | ORD/000216/2020-2021 | 1167/ALD | 15/12/2020 | 60 | GOUTAM KUMAR DAS | 19.91 | 39.83 | 0
966 | Alipurduar Division | Alipurduar Division | Providing House connection for JOGENDRAPUR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | HQ-A.E | RWS Kalchini Block | ORD/000217/2020-2021 | 1168/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 23.36 | 67
967 | Alipurduar Division | Alipurduar Division | Carrying of AC pipe and DI pipe and specials from Bhutnirghat PWSS to Falakata Stackyard due to widening PWD Road under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000218/2022-2023 | 1108/ALD | 29/07/2022 | 30 | SASANKA ROY | 0.92 | 0.92 | 67
968 | Alipurduar Division | Alipurduar Division | Laying of water Supply pipeline due to widening of Road at industrial park by JDA (Jaigaon Development Authority Area) at Jaigaon Zone-2 WSS under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000225/2022-2023 | 1115/ALD | 29/07/2022 | 30 | D. K. & SONS | 4.84 | 0 | 0
969 | Alipurduar Division | Alipurduar Division | Laying of CI/DI/MS Pipe for Rising and delivery line, cons. Of valve chamber and other allied works for Zone-II and III at JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000229/2021-2022 | 1572/ALD | 22/11/2021 | 60 | DILIP MAHATO | 26.46 | 0 | 66
970 | Alipurduar Division | Alipurduar Division | Providing House connection for FALAKATA AUG. piped water supply scheme (Falakata-Dhupguri Road) under Alipuduar Division, P.H.E. Dte. Part-4 | HQ-A.E | RWS Kalchini Block | ORD/000246/2020-2021 | 1246/ALD | 28/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 30.04 | 54.27 | 67
971 | Alipurduar Division | Alipurduar Division | Providing House connection for BANGSHIDHARPUR piped water supply scheme under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000247/2020-2021 | 1247/ALD | 28/12/2020 | 60 | MESSRS R N TRADERS | 40.06 | 40.06 | 0
972 | Alipurduar Division | Alipurduar Division | Providing House connection for FALAKATA AUG. piped water supply scheme (Subhaspally area, right side of NH) under Alipuduar Division, P.H.E. Dte. Part-5 | HQ-A.E | RWS Kalchini Block | ORD/000248/2020-2021 | 1248/ALD | 28/12/2020 | 60 | BILTU DAS | 29.59 | 29.5 | 82
973 | Alipurduar Division | Alipurduar Division | Preparation of DPR after investigation for Tasti Tea Garden, Dalgaon Tea Garden and Dalmoney Tea Garden Piped Water Supply Scheme under Falakata Block, Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000251/2022-2023 | 1392/ALD | 29/08/2022 | 30 | M/S SOBHA AND CO | 6.51 | 6.51 | 100
974 | Alipurduar Division | Alipurduar Division | Providing House connection for FALAKATA AUG. piped water supply (Masalapatty area, left side of NH)under Alipuduar Division, P.H.E. Dte. Part-6 | HQ-A.E | RWS Kalchini Block | ORD/000252/2020-2021 | 1252/ALD | 28/12/2020 | 60 | SOUVIK ROY PALADHI | 30.05 | 57.06 | 60
975 | Alipurduar Division | Alipurduar Division | Gap filling by UPVC/DI pipe and bridge crossing near Hat Khola Bazar Area for Augmenttion of Falakata WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000256/2021-2022 | 1603/ALD | 22/11/2021 | 30 | NARENDRA BHADANI. | 5 | 4.82 | 67
976 | Alipurduar Division | Alipurduar Division | Gap filling by UPVC/DI pipe at Parangerpar (near rail gate) of Augmenttion of Falakata WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000257/2021-2022 | 1604/ALD | 22/11/2021 | 30 | ASSOCIATE CONSTRUCTION COMPANY | 4.98 | 5 | 61
977 | Alipurduar Division | Alipurduar Division | Providing House connection for FALAKATA AUG. piped water supply scheme (Barodoba Area) under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000263/2020-2021 | 1254/ALD | 28/12/2020 | 60 | HARIDAS GHOSH | 43.86 | 74.64 | 66
978 | Alipurduar Division | Alipurduar Division | Providing House connection for FALAKATA AUG. piped water supply scheme (College Para Area) under Alipuduar Division, P.H.E. Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000265/2020-2021 | 1256/ALD | 28/12/2020 | 60 | BILTU DAS | 43.41 | 78.8 | 62
979 | Alipurduar Division | Alipurduar Division | Providing House connection for FALAKATA AUG. piped water supply scheme (Falakata-Birpara Road) under Alipuduar Division, P.H.E. Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000266/2020-2021 | 1257/ALD | 28/12/2020 | 60 | BILTU DAS | 43.41 | 33.23 | 70
980 | Alipurduar Division | Alipurduar Division | Repairing of drainage system & painting of office cum Godown building at Head Work site of Falakata WSS (OLD) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000267/2021-2022 | 1832/ALD | 10/12/2021 | 60 | NARENDRA BHADANI. | 4.47 | 4.36 | 63
981 | Alipurduar Division | Alipurduar Division | Road crossing (by NP3 Hume pipe) at Dhupguri Road under under Zone-II of augmentation of Falakata WSS due to widening of PWD Road under Alipurduar Division, PHE Dte. (3 nos) | HQ-A.E | RWS Kalchini Block | ORD/000270/2021-2022 | 1836/ALD | 10/12/2021 | 45 | SASANKA ROY | 2.49 | 2.49 | 67
982 | Alipurduar Division | Alipurduar Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | HQ-A.E | RWS Kalchini Block | ORD/000271/2020-2021 | 1283/ALD | 05/01/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 0.45 | 74
983 | Alipurduar Division | Alipurduar Division | Construction of gasious chlorine room for Zone-IIIB of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000280/2020-2021 | 1330/ALD | 11/01/2021 | 90 | MAHENDRA CHHETRI | 5 | 0 | 67
984 | Alipurduar Division | Alipurduar Division | Construction of gasious chlorine room for Zone-IV of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000281/2020-2021 | 1331/ALD | 11/01/2021 | 90 | MAHENDRA CHHETRI | 5 | 0 | 60
985 | Alipurduar Division | Alipurduar Division | Construction of gasious chlorine room for Zone-VB of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000285/2020-2021 | 1333/ALD | 11/01/2021 | 90 | MAHENDRA CHHETRI | 5 | 0 | 65
986 | Alipurduar Division | Alipurduar Division | Providing Functional Household Tap connection (FHTC) in connection with Jaldhara Jal Sapno for Jogendrapur PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000301/2020-2021 | 1381/ALD | 19/01/2021 | 45 | ASSOCIATE CONSTRUCTION COMPANY | 15.78 | 14.66 | 67
987 | Alipurduar Division | Alipurduar Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for interconnection between Jogendrapur and Augmentation of Falakata PWSS under Alipurduar Division, PHE Dte.(Part-II) | HQ-A.E | RWS Kalchini Block | ORD/000302/2020-2021 | 1382/ALD | 19/01/2021 | 45 | SASANKA ROY | 15.06 | 15.06 | 100
988 | Alipurduar Division | Alipurduar Division | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000317/2020-2021 | 1449/ALD | 25/01/2021 | 45 | MAHENDRA CHHETRI | 43.86 | 33.73 | 67
989 | Alipurduar Division | Alipurduar Division | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000318/2020-2021 | 1451/ALD | 25/01/2021 | 45 | AQUEDUCT PLASTICS PVT. LTD. | 43.86 | 30 | 90
990 | Alipurduar Division | Alipurduar Division | Laying of UPVC/DI/MS/CI Distribution line for gap filling and FHTC Connection in ward no. 03, 04, 07, 08, 11, 15 location of augmentation of Falakata PWSS (Zone-I AND Zone-III) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000327/2022-2023 | 2236/ALD/ | 21/11/2022 | 60 | NARENDRA BHADANI. | 33.38 | 33.37 | 0
991 | Alipurduar Division | Alipurduar Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000343/2021-2022 | 2136/ALD | 06/01/2022 | 30 | D. K. & SONS | 5.02 | 0 | 67
992 | Alipurduar Division | Alipurduar Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000344/2021-2022 | 2137/ALD | 06/01/2022 | 30 | D. K. & SONS | 5.02 | 0 | 65
993 | Alipurduar Division | Alipurduar Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000353/2021-2022 | 2152/ALD | 06/01/2022 | 30 | D. K. & SONS | 5.02 | 0 | 61
994 | Alipurduar Division | Alipurduar Division | Providing House connection for MADARI ROAD/ PARANGERPAR, FALAKATA AUG. PWSS ZONE-I under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000365/2020-2021 | 1758/ALD | 19/02/2021 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 39.97 | 48.77 | 63
995 | Alipurduar Division | Alipurduar Division | Providing House connection for RABINDRANAGAR, FALAKATA AUG. PWSS ZONE-III under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000366/2020-2021 | 1759/ALD | 19/02/2021 | 1320 | BILTU DAS | 39.46 | 30.3 | 86
996 | Alipurduar Division | Alipurduar Division | Providing House connection for DESHBANDHUPARA, FALAKATA AUG. PWSS ZONE-III under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000367/2020-2021 | 1760/ALD | 19/02/2021 | 60 | ASHIT KUMAR SINGHA | 40.25 | 40.25 | 65
997 | Alipurduar Division | Alipurduar Division | Providing House connection for SOUTH FALAKATA AREA, FALAKATA AUG. PWSS ZONE-III under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000368/2020-2021 | 1761/ALD | 19/02/2021 | 60 | HARIDAS GHOSH | 40.13 | 20.44 | 66
998 | Alipurduar Division | Alipurduar Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000371/2021-2022 | 2153/ALD | 06/01/2022 | 30 | MAHENDRA CHHETRI | 5.02 | 0 | 66
999 | Alipurduar Division | Alipurduar Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC, school & public/Govt. organisations etc. ) at JDA WSS (Existing) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000372/2021-2022 | 2154/ALD | 06/01/2022 | 30 | MAHENDRA CHHETRI | 5.02 | 0 | 62
1000 | Alipurduar Division | Alipurduar Division | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-IV under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000373/2021-2022 | 2373/ALD | 31/01/2022 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 55.55 | 1.23 | 71
1001 | Alipurduar Division | Alipurduar Division | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-5A and 5B under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000374/2021-2022 | 2374/ALD | 31/01/2022 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 52.63 | 0 | 80
1002 | Alipurduar Division | Alipurduar Division | Providing House connection for DALSINGPARA, JAIGAON DEVLOPMENT AREA ZONE-5A under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000379/2020-2021 | 1762ALD | 19/02/2021 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 40.17 | 0
1003 | Alipurduar Division | Alipurduar Division | Providing House connection for JAIGAON DEVLOPMENT AREA ZONE-5B under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000380/2020-2021 | 1763ALD | 19/02/2021 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 40.17 | 0
1004 | Alipurduar Division | Alipurduar Division | Providing House connection for existing PWSS, JAIGAON DEVLOPMENT AREA ZONE- 1 and 2 under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000382/2020-2021 | 1765/ALD | 19/02/2021 | 60 | MAHENDRA CHHETRI | 40.23 | 40.23 | 63
1005 | Alipurduar Division | Alipurduar Division | Construction of roof truss, field development and other allied works at Headwork site of Old Jaigaon WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000393/2021-2022 | 2307/ALD | 25/01/2022 | 30 | DILIP MAHATO | 4.17 | 4.14 | 75
1006 | Alipurduar Division | Alipurduar Division | Gap filling by UPVC pipe at different zone of Falakata water supply scheme under Alipurduar Division, PHE Dte. Part-4 | HQ-A.E | RWS Kalchini Block | ORD/000396/2020-2021 | 1582/ALD | 10/02/2021 | 60 | SWAPAN SAHA | 5.01 | 5.06 | 64
1007 | Alipurduar Division | Alipurduar Division | Gap filling by UPVC pipe at different zone of Falakata water supply scheme under Alipurduar Division, PHE Dte. Part-5 | HQ-A.E | RWS Kalchini Block | ORD/000397/2020-2021 | 1583/ALD | 10/02/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.01 | 5.01 | 67
1008 | Alipurduar Division | Alipurduar Division | Laying of DI pipe line for discharge of washed out water from Tube well No. 1 within Falakata PWSS(Existing) under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000404/2021-2022 | 57/PHE-Brp | 03/02/2022 | 30 | KANKAN SARKAR | 0.22 | 0 | 67
1009 | Alipurduar Division | Alipurduar Division | Laying of CI/ DI, HDPE pipe including valve chamber and other misc. works at JDA PWSS ZONE-II under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000500/2021-2022 | 3005/ALD | 15/03/2022 | 30 | DILIP MAHATO | 30.59 | 0 | 60
1010 | Alipurduar Division | Alipurduar Division | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (East side) within Alipurduar District under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000565/2021-2022 | 3139/ALD | 25/03/2022 | 20 | MAHENDRA CHHETRI | 3.32 | 0 | 67
1011 | Alipurduar Division | Alipurduar Division | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (West side) within Alipurduar District under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000566/2021-2022 | 3140/ALD | 25/03/2022 | 20 | D. K. & SONS | 3.32 | 0 | 61
1012 | Alipurduar Division | Alipurduar Division | Construction of pathway with paver block and repairing of old H/W site's Guest House of Jaigaon WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000570/2021-2022 | 3143/ALD | 25/03/2022 | 30 | D. K. & SONS | 4.86 | 0 | 67
1013 | Alipurduar Division | Alipurduar Division | Remaining portion of pipeline of JDA Zone-I & Zone-II and special Road repairing of Zone-I and II and Zone-4B, providing pipeline and FHTC of Ramgaon. | HQ-A.E | RWS Kalchini Block | ORD/000570/2022-2023 | 3623/ALD | 30/03/2023 | 810 | D. K. & SONS | 54.46 | 11.23 | 96
1014 | Alipurduar Division | Alipurduar Division | Construction of Boundary wall 2nd TW site of Jaigaon PWSS (near Hanuman Mandir) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000571/2021-2022 | 3144/ALD | 25/03/2022 | 45 | D. K. & SONS | 4.75 | 0 | 62
1015 | Alipurduar Division | Alipurduar Division | Providing House connection for TORSA TG AREA, JAIGAON DEVLOPMENT AREA ZONE-3B under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000726/2020-2021 | 1764/ALD | 19/02/2021 | 60 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 0 | 67
1016 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | HQ-A.E | RWS Kalchini Block | RTOR000018/2022-2023 | 917/ALD | 07/07/2022 | 0 | Resource Division | 61.6 | 0 | 0
1017 | Alipurduar Division | Alipurduar Division | Fuel bill for the month of August 2021 | HQ-A.E | RWS Kalchini Block | VCH/000569/2021-2022 | 120/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.18 | 0 | 0
1018 | Alipurduar Division | Alipurduar Division | Fuel bill for the month of August 2021 | HQ-A.E | RWS Kalchini Block | VCH/000571/2021-2022 | 122/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.22 | 0 | 0
1019 | Alipurduar Division | Birpara Sub-Division | Dismantling Concrete road and re -casting the same for providing FHTC at different area of BIRPARA (APD) PWSS AND Alipurduar - I Block under Alipurduar Division , PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000078/2022-2023 | 441/ALD | 13/05/2022 | 30 | R.K.CONSTRUCTION | 4.96 | 4.95 | 71
1020 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at Alipurduar Birpara Bazar Chowpathi and surrounding area under Birpara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000178/2021-2022 | 1308/ALD | 05/10/2021 | 60 | DAS CONSTRUCTION | 43.41 | 23.31 | 99
1021 | Alipurduar Division | Birpara Sub-Division | Repairing of office Quarter and construction of attached toilet for Assistant Engineer Chamber of Birpara Sub-Division Office under Alipurduar Division PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000284/2021-2022 | 1853/ALD | 13/12/2021 | 45 | DAS ENTERPRISE | 4.91 | 0 | 97
1022 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Alipurduar ITI College area under Birpara PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | Alipurduar RWS | Birpara Sub Division | ORD/000327/2021-2022 | 2200/ALD | 11/01/2022 | 60 | DAS CONSTRUCTION | 42.69 | 30.1 | 98
1023 | Alipurduar Division | Birpara Sub-Division | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte. Part-7 | Alipurduar RWS | Birpara Sub Division | ORD/000342/2021-2022 | 2118/ALD | 05/01/2022 | 30 | DAS CONSTRUCTION | 5 | 0 | 96
1024 | Alipurduar Division | Birpara Sub-Division | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 3.97 | 61
1025 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Birpara PWSS (APD) Under Alipurduar Division, PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000443/2021-2022 | 2751/ALD | 24/02/2022 | 60 | R.K.CONSTRUCTION | 31.74 | 17.01 | 60
1026 | Alipurduar Division | Birpara Sub-Division | Withdrawing & relaying & laying of pipeline and other misc. works for retrofitting of DHUMCHIPARA PWSS under Alipurduar Division PHED. | Birpara A.E | Birpara Sub Division | ORD/000084/2020-2021 | 688/ALD | 16/09/2020 | 120 | MITHUN DAS | 24.86 | 0.51 | 37
1027 | Alipurduar Division | Birpara Sub-Division | Preparation of operation and maintenance DPR booklet in connection to 92 no's piped water supply scheme under Alipurduar Division P.H.E Dte | Birpara A.E | Birpara Sub Division | ORD/000184/2023-2024 | 1202/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100
1028 | Alipurduar Division | Birpara Sub-Division | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Alipurduar-I and Alipurduar- II Block under Alipurduar Division P.H.E Dte. | Birpara A.E | Birpara Sub Division | ORD/000185/2023-2024 | 1203/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100
1029 | Alipurduar Division | Birpara Sub-Division | Repairing of boundary wall with Gate and pump house at 2nd Tubewell site of Dhumchipara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000224/2022-2023 | 1114/ALD | 29/07/2022 | 30 | KAMALESH ROY | 2.58 | 1.66 | 37
1030 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000379/2021-2022 | 2379/ALD | 31/01/2022 | 90 | DILIP MAHATO | 92.34 | 8.37 | 98
1031 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for DHUMCHIPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000399/2021-2022 | 2390/ALD | 31/01/2022 | 90 | DILIP MAHATO | 27.18 | 26.69 | 18
1032 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI distribution pipeline and other misc. works for Dhumchipara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000481/2021-2022 | 2900/ALD | 08/03/2022 | 60 | MITHUN DAS | 25.93 | 25.83 | 100
1033 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 10 | 0
1034 | Alipurduar Division | Birpara Sub-Division | "Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. (for the financial year 2022-2023 from 01/04/2022 onwards)" | Birpara A.E | Birpara Sub Division | ORD/000578/2021-2022 | 3223/ALD | 31/03/2022 | 365 | DILIP MAHATO | 4.96 | 1.89 | 54
1035 | Alipurduar Division | Alipurduar Sadar Sub-Division | Quotation for New Connection for Dangapara, Sishujumra | Birpara A.E | Alipurduar Sub Division | BILL/00107/2022-2023 | 445/22-23/PFMS | 21/01/2023 | 0 | WBSEDCL | 0.1 | 0 | 0
1036 | Alipurduar Division | Alipurduar Sadar Sub-Division | Balance part of laying of HDPE/DI pipe line alongwith construction of RCC piller at different area of DIMDIMA TG under ALIPURDUAR Division, PHED. | Birpara A.E | Alipurduar Sub Division | ORD/000069/2020-2021 | 622/ALD | 03/09/2020 | 120 | M/S SSB CONSTRUCTION | 34.11 | 3 | 88
1037 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of DI/MS/HDPE pipe line from Nepali School (H.S.) towards Birpara Boro Houda WSS providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-I) | Birpara A.E | Alipurduar Sub Division | ORD/000319/2020-2021 | 1452/ALD | 25/01/2021 | 45 | GOUTAM KUMAR DAS | 43.73 | 11.67 | 87
1038 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | Alipurduar Sub Division | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 6.5 | 100
1039 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of DI/MS/HDPE Pipe line for the Dimdima Zone-II and Nangdala Extension, Dimdima WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000357/2020-2021 | 1795/ALD | 22/02/2021 | 60 | DILIP MAHATO | 31.27 | 0 | 87
1040 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC pipeline and Tube well Boring by Reverse Rotary method of drilling for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Alipurduar Sub Division | ORD/000380/2021-2022 | 2380/ALD | 31/01/2022 | 60 | DILIP MAHATO | 95.15 | 13.81 | 97
1041 | Alipurduar Division | Alipurduar Sadar Sub-Division | Protective and Decorative Acrylic exterior paint on existing 350 cum OHR at Dimdima of Birpara Sub-Division under Alipurduar Division, P.H.E.Dte. (SM/07068) | Birpara A.E | Alipurduar Sub Division | ORD/000507/2023-2024 | 825/ALD | 14/03/2024 | 60 | BHAGWATI BHUJEL | 1.96 | 1.94 | 10
1042 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline for implementation of FHTC at Bandapani TG Area attached with Nangdala TG (for Dimdima PWSS Zone-II) under Alipurduar Division, PHE Dte. | Birpara A.E | Alipurduar Sub Division | ORD/000523/2021-2022 | 2997/ALD | 15/03/2022 | 60 | DILIP MAHATO | 15.04 | 15.04 | 87
1043 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Bhutia Basty and Jayanti water supply scheme at Kalchini Block under Alipuduar Division, P.H.E. Dte | HQ-A.E | Birpara Sub Division | ORD/000103/2020-2021 | 724/ALD | 22/09/2020 | 30 | M/S BHOWMICK CONSTRUCTION | 4.99 | 9.99 | 0
1044 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline for Jainti TG including connection from Reservoir-2 under Jainti TG Water Supply Scheme (Part-A). | HQ-A.E | Birpara Sub Division | ORD/000123/2020-2021 | 795/ALD | 01/10/2020 | 60 | CALCON CONSTRUCTIONS | 40.62 | 0 | 90
1045 | Alipurduar Division | Birpara Sub-Division | Providing House connection for JAYANTI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(PART-2) | HQ-A.E | Birpara Sub Division | ORD/000172/2020-2021 | 916/ALD | 16/10/2020 | 30 | M/S BHOWMICK CONSTRUCTION | 4.95 | 9.9 | 0
1046 | Alipurduar Division | Birpara Sub-Division | Laying balance portion pipeline and providing house connection at Jayanti Water Supply Scheme and Bhutiya Busty Area under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000202/2021-2022 | 975/ALD | 13/09/2021 | 30 | GHOSH & SAHA CONSTRUCTION | 5.04 | 0 | 54
1047 | Alipurduar Division | Birpara Sub-Division | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 17.07 | 69
1048 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | HQ-A.E | Birpara Sub Division | VCH/000944/2020-2021 | 571/20-21 | 26/03/2021 | 0 | PRAMESH LAMA | 10 | 0 | 0
1049 | Alipurduar Division | Birpara Sub-Division | Supplying & laying of UPVC/DI/GI Distribution pipeline for Mujnai PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000103/2021-2022 | 902/ALD | 03/09/2021 | 30 | DILIP MAHATO | 4.99 | 3.81 | 91
1050 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting of Mujnai PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000144/2020-2021 | 943/ALD | 19/10/2020 | 60 | VEDATRAYEE AND CO | 29.81 | 1.8 | 92
1051 | Alipurduar Division | Birpara Sub-Division | Supply of fuel for Diesel Vehicle Maxi Cab(At least 7 seater) (Preferably Scorpio) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 08.08.2022 to 31.12.2022) | Birpara A.E | Birpara Sub Division | ORD/000181/2022-2023 | 1187/ALD | 05/08/2022 | 153 | MITHU DAS | 1.16 | 1.09 | 100
1052 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Executive Engineer, Alipurduar Division, P.H.E. Dte.(from 01.08.2022 to 31.12.2022) | Birpara A.E | Birpara Sub Division | ORD/000200/2022-2023 | 1121/ALD | 29/07/2022 | 153 | MITHU DAS | 0.84 | 0.84 | 100
1053 | Alipurduar Division | Birpara Sub-Division | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-5 Venue : 1)Madarihat (1 no.) 2)Mujnai (2 nos) 3)Sidhabari (1 no.) | Birpara A.E | Birpara Sub Division | ORD/000363/2021-2022 | 2125/ALD | 05/01/2022 | 30 | G. MITRA & ASSOCIATES, | 4.9 | 4.9 | 50
1054 | Alipurduar Division | Birpara Sub-Division | CONS. OF BOUNDARY WALL (80 m), PUMPHOUSE( 1.Nos) ,TUBEWELL (2 Nos.), RISING MAIN AND DISTRIBUTION LINE FOR MUJNAI T.G (All Other Division & Line 60 unit) CHA SUNDARI WATER SUPPLY SCHEME UNDER ALIPURDUAR DIVISION PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000387/2020-2021 | 1946/ALD | 25/02/2021 | 840 | GHOSH & SAHA CONSTRUCTION | 36.68 | 6.84 | 100
1055 | Alipurduar Division | Birpara Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 10 | 100
1056 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 25 | 0
1057 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Birpara water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000099/2020-2021 | 720/ALD | 22/09/2020 | 30 | KAMALESH ROY | 4.98 | 9.96 | 0
1058 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at Alipurduar Birpara Bazar Chowpathi and surrounding area under Birpara PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000178/2021-2022 | 1308/ALD | 05/10/2021 | 60 | DAS CONSTRUCTION | 43.41 | 13.05 | 99
1059 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Birpara water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar RWS | Birpara Sub Division | ORD/000203/2020-2021 | 1157/ALD | 15/12/2020 | 60 | DAS CONSTRUCTION | 29.9 | 29.9 | 97
1060 | Alipurduar Division | Birpara Sub-Division | Repairing of damaged pipe line, arrangement of water supply pipe line on emergency basis and other works due to widening and strengthening of PWD road at Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000269/2021-2022 | 1835/ALD | 10/12/2021 | 30 | HARI CONSTRUCTION | 2.56 | 2.56 | 97
1061 | Alipurduar Division | Birpara Sub-Division | Repairing of office Quarter and construction of attached toilet for Assistant Engineer Chamber of Birpara Sub-Division Office under Alipurduar Division PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000284/2021-2022 | 1853/ALD | 13/12/2021 | 45 | DAS ENTERPRISE | 4.91 | 4.75 | 97
1062 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Alipurduar ITI College area under Birpara PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | Alipurduar RWS | Birpara Sub Division | ORD/000327/2021-2022 | 2200/ALD | 11/01/2022 | 60 | DAS CONSTRUCTION | 42.69 | 0 | 98
1063 | Alipurduar Division | Birpara Sub-Division | Laying of 90mm & 110 mm dia UPVC pipeline for Bholardabri Water Supply Scheme uner Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000331/2020-2021 | 1467/ALD | 25/01/2021 | 45 | HARI CONSTRUCTION | 5.08 | 10.16 | 0
1064 | Alipurduar Division | Birpara Sub-Division | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte.Part-6 | Alipurduar RWS | Birpara Sub Division | ORD/000341/2021-2022 | 2117/ALD | 05/01/2022 | 30 | DAS CONSTRUCTION | 5 | 5 | 96
1065 | Alipurduar Division | Birpara Sub-Division | Providing House Connection (FHTC) at Birpara (APD) WSS under Alipurduar Division, PHE Dte. Part-7 | Alipurduar RWS | Birpara Sub Division | ORD/000342/2021-2022 | 2118/ALD | 05/01/2022 | 30 | DAS CONSTRUCTION | 5 | 4.38 | 96
1066 | Alipurduar Division | Birpara Sub-Division | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 4.42 | 61
1067 | Alipurduar Division | Birpara Sub-Division | Hydro Geological investigation about water evaluation availability and quality parameter for both Ground and surface sources at Lankapara central Dooars Tea Estates within Alipurduar District | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | BILL/00215/2024-2025 | 164/24-25/PFMS | 12/08/2024 | 0 | IIT CONSULTATIVE PRACTICE | 9.74 | 0 | 0
1068 | Alipurduar Division | Birpara Sub-Division | New Service Connection Charges for Lankapara TG PWSS PH NO-VII ( AT VES-4) Near Chha Sundari | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | BILL/00485/2024-2025 | 324/24-25/PFMS | 22/11/2024 | 0 | WBSEDCL | 16.11 | 0 | 0
1069 | Alipurduar Division | Birpara Sub-Division | Route surveying and revalidation of Household data with digitization of LDS for Cha Sundari Cluster-I,, Cluster-II, Cluster-III & Cluster-IV (with 2 options) PWSS under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000098/2025-2026 | 1182/ALD | 26/06/2025 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.4 | 0 | 0
1070 | Alipurduar Division | Birpara Sub-Division | Construction of boundary wall, pump house, tubewell, rising main for (Mouza- Lankapara TG, JL No. 30, Sheet No. 5, Plot No. 704) 327 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000189/2023-2024 | 1280/ALD | 11/08/2023 | 827 | ASHOK PRADHAN | 57.36 | 15.93 | 35
1071 | Alipurduar Division | Birpara Sub-Division | Construction of boundary wall, pump house, tubewell, rising main for (Mouza- Lankapara TG, JL NO. 30, Sheet No. 8, Plot No. 1052) 117 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000190/2023-2024 | 1460/ALD | 14/08/2023 | 540 | SUDDHYA SING LAMA | 39.38 | 11.24 | 61
1072 | Alipurduar Division | Birpara Sub-Division | Construction of boundary wall, pump house, tubewell, rising main and land development for (Mouza- Lankapara TG, JL No. 30, Sheet No. 7, Plot No. 920,921, 922 & 923 ) 375 units Cha Sundori Water Supply Scheme under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000196/2023-2024 | 1486/ALD | 16/08/2023 | 120 | SUBIR GHOSH | 55.7 | 0 | 0
1073 | Alipurduar Division | Birpara Sub-Division | Making arrangement for pumping test with suitable pump and required column pipes etc. including all charges at 6 locations. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000209/2024-2025 | 1825/ALD | 14/06/2024 | 360 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 15.96 | 0 | 30
1074 | Alipurduar Division | Birpara Sub-Division | Laying of proposed Rising main (Length- 1085 mtr, 4817 mtr & 1320 mtr.) of Cha-Sundori Project (JJM- SM/10054) within Lankapara Tea Garden Area Piped Water Supply Scheme, Madarihat-Birpara block of Birpara Sub-Division under Alipurduar Division, PHE Dte.[As per new DPR guided by Planning Circle-II, PHE Dte.] | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000267/2024-2025 | 3116/ALD | 30/08/2024 | 45 | DILIP MAHATO (OPC) PRIVATE LIMITED | 36.54 | 5.51 | 28
1075 | Alipurduar Division | Birpara Sub-Division | Soil investigation work for Cha Sundori Project at 4 different places of Lankapara TG (3 nos GLR & 1 No OHR) within Alipurduar District under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division | ORD/000489/2021-2022 | .2660/ALD | 21/02/2022 | 30 | GLORY ENGINEERS SYNDICATE | 4.89 | 4.89 | 80
1076 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including laying distribution system, Rising main and providing FHTC for CHUNIAJHORA TEA GARDEN AREA PWSS under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000002/2022-2023 | 12/ALD | 01/04/2022 | 120 | AKANSHA COMMERCIAL PRIVATE LTD. | 168.43 | 168.43 | 100
1077 | Alipurduar Division | Alipurduar Sadar Sub-Division | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 58
1078 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of OHR 200cum for Chuniajhora TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000419/2021-2022 | 2598/ALD | 17/02/2022 | 180 | AKANSHA COMMERCIAL PRIVATE LTD. | 55.36 | 47.96 | 65
1079 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE/DI Pipeline, horizontal boring by HDD method, bridge and culvert crossing, providing FHTC, specials repair with trial run of pipeline and allied works at Chuniajhora PWSS under Alipurduar Division, PHE Dte.(SM/14219 & SM/10179) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000460/2023-2024 | 672/ALD | 06/03/2024 | 240 | ASHOK SAPKOTA | 19.39 | 0 | 100
1080 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 0
1081 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000005/2022-2023 | 397/ALD | 11/05/2022 | 0 | Resource Division | 3.59 | 0 | 0
1082 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1083 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00601/2023-2024 |  | 29/02/2024 | 0 | HARIDAS GHOSH | 2.68 | 0 | 0
1084 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00749/2023-2024 | 448/23-24/PFMS | 30/03/2024 | 0 | HARIDAS GHOSH | 1.49 | 0 | 0
1085 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE.(2382/ALD DT:31/01/2022) Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. (2187/ALD DT:29/02/2022) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00750/2023-2024 | 449/23-24/PFMS | 30/03/2024 | 0 | HARIDAS GHOSH | 1.19 | 0 | 0
1086 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Bholardabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000105/2022-2023 | 697/ALD | 08/06/2022 | 30 | KAMALESH ROY | 4.84 | 4.84 | 63
1087 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of pump house at 2nd TW site of Bholardabri PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000164/2025-2026 | 1772/ALD | 18/08/2025 | 30 | TAPASH DAS | 1.01 | 0 | 0
1088 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying rising main line from 2nd side to HW Site of Bholardabri WSS and construction of different dia valve chamber and restoration of damaged FHTC connection and other allied work at Bholardabri PWSS under JJM Programme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000170/2025-2026 | 1778/ALD | 18/08/2025 | 60 | TAPASH DAS | 2.88 | 0 | 0
1089 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing and renovation of 2 nos. P/H, cons. Of 2 nos. Toilet (for 1st and 2nd site) and laying of UPVC pipe line with providing House connection at Bholardabri WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000184/2021-2022 | 1313/ALD | 05/10/2021 | 60 | HARI CONSTRUCTION | 33.81 | 33.47 | 64
1090 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House Connection of Bholardabri WSS under Alipurduar Division, PHE Dte.Part-7 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000203/2021-2022 | 991/ALD | 13/09/2021 | 30 | MANORAMA ENTERPRISE | 4.3 | 3 | 63
1091 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of Damaged AC pipeline with UPVC pipeline of Bholardabri WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000204/2021-2022 | 992/ALD | 13/09/2021 | 30 | MANORAMA ENTERPRISE | 4.89 | 4.62 | 65
1092 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-8 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000274/2021-2022 | 1840/ALD | 10/12/2021 | 30 | HARI CONSTRUCTION | 5 | 4.72 | 66
1093 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-9 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000275/2021-2022 | 1841/ALD | 10/12/2021 | 30 | HARI CONSTRUCTION | 5.04 | 4.42 | 65
1094 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-10 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000276/2021-2022 | 1842/ALD | 10/12/2021 | 30 | HARIDAS GHOSH | 5.02 | 4.39 | 63
1095 | Alipurduar Division | Alipurduar Sadar Sub-Division | Drilling Rigbore tube well (ODEX-115 method) at Modakpara, Paschim Bholardabri under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000305/2022-2023 | 1943/ALD | 17/10/2022 | 30 | HARIDAS GHOSH | 2.77 | 0 | 0
1096 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2022 to 31.12.2022) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000307/2021-2022 | 2014/ALD | 29/12/2021 | 365 | KAMALESH ROY | 1.76 | 1.49 | 61
1097 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 450cum OHR for Bholardabri water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000311/2021-2022 | 2187/ALD | 11/01/2022 | 180 | HARIDAS GHOSH | 87.58 | 86.43 | 63
1098 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, supply of CIDF specials, land development works, construction of surface drain, pathway at 3rd TW site and other allied works in connection with the Augmentation of Bholardabri PWSS under Alipurduarn Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000318/2023-2024 | 2410/ALD | 09/11/2023 | 450 | HARI CONSTRUCTION | 30.3 | 16.52 | 100
1099 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-11 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000347/2021-2022 | 2140/ALD | 06/01/2022 | 30 | HARIDAS GHOSH | 5.04 | 5.04 | 64
1100 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bholardabri WSS under Alipurduar Division, PHE Dte. Part-12 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000348/2021-2022 | 2141/ALD | 06/01/2022 | 60 | HARIDAS GHOSH | 5.04 | 4.66 | 65
1101 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system and other allied works under Bholardabri PWSS, Alipurduar Division, PHE Dte. (SM/09883) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000353/2024-2025 | 3423/ALD | 26/09/2024 | 180 | TAPASH DAS | 20.57 | 0 | 70
1102 | Alipurduar Division | Alipurduar Sadar Sub-Division | soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-1 Places : 1)Uttar Kamakhyaguri 2)Uttar Majherdabri. 3)Bholardabri. 4) Narathali. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000356/2021-2022 | 2121/ALD | 05/01/2022 | 30 | MOYTEC | 4.9 | 4.9 | 69
1103 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and Providing FHTC including Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Bholardabri PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000382/2021-2022 | 2382/ALD | 31/01/2022 | 1080 | HARIDAS GHOSH | 82.3 | 46.48 | 80
1104 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Rig Machine Approach Road of Bholardabri 3rd TW Site under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000407/2022-2023 | 2792/ALD | 10/01/2023 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.33 | 0.32 | 64
1105 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC in school in Bholardabri PWSS under Alipurduar Division P.H.E Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2022-2023 | 3359/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.25 | 0.25 | 100
1106 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC Pipeline with UPVC pipeline of Bholardabri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000533/2021-2022 | 3107/ALD | 24/03/2022 | 60 | HARI CONSTRUCTION | 56.51 | 51.82 | 100
1107 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 10 | 0
1108 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway with paver block & land development of Loknathpur HW site WSS (Western part of GADA rivert) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000082/2022-2023 | 446/ALD | 13/05/2022 | 30 | MATARA CONSTRUCTION CO | 4.21 | 0 | 0
1109 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway with paver block & land development of Loknathpur HW site & 2nd site WSS (Western part of GADA rivet) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000083/2022-2023 | 447/ALD | 13/05/2022 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.19 | 0 | 0
1110 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main line HDPE PN10, horizontal boring by HDD method, bridge and culvert crossing, construction of pathway, surface drain and chatal, installation of paver block along with the others allied works at Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000393/2023-2024 | 204/ALD | 16/01/2024 | 450 | SOUVIK ROY PALADHI | 26.65 | 12.58 | 60
1111 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing, construction of RCC pillars for supporting DI Pipe, surface drain and others allied works in connection with the Augmentation of Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000408/2024-2025 | 4535/ALD | 26/12/2024 | 60 | SOUVIK ROY PALADHI | 80.87 | 0 | 0
1112 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1113 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC in school in Loknathpur PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000494/2022-2023 | 3358/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.22 | 0 | 100
1114 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline with DI/UPVC pipeline for JAL SWAPNO programme (FHTC for every household) for LOKNATHPUR WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000499/2021-2022 | 3004/ALD | 15/03/2022 | 60 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 20.09 | 16.34 | 0
1115 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC in school in Loknathpur PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000505/2022-2023 | .3358/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.22 | 0 | 100
1116 | Alipurduar Division | Alipurduar Sadar Sub-Division | Gap filling of HDPE pipeline at Nepania Division area under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000325/2023-2024 | 2422/ALD | 09/11/2023 | 60 | BHAGWATI BHUJEL | 5.01 | 5.01 | 100
1117 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-195 Method of drilling, Construction of 1no. of Pump house, boundary wall an distribution line with FHTC for Augmentation of NEPANIA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000348/2022-2023 | 2489/ALD | 13/12/2022 | 120 | BHAGWATI BHUJEL | 59.01 | 42.45 | 80
1118 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new HDPE pipeline in the balance portion distribution system of Raydak TG PWSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000008/2023-2024 | 92/ALD | 18/04/2023 | 60 | TILAK SHARMA | 12.11 | 0 | 0
1119 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new HDPE pile line in the balance portion distribution system at Sanialine & adj. Area of Raydak TG PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000031/2023-2024 | 362/ALD | 18/05/2023 | 60 | SUMAN CHAKRABORTY | 7.99 | 0 | 0
1120 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tubewell boring by ODEX-165 method of drilling, construction of Pump House, Boundary Wall at Proposed 3rd TW site of Raydak TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000032/2023-2024 | 363/ALD | 18/05/2023 | 360 | POLY CONSTRUCTION | 17.71 | 5.08 | 3
1121 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new HDPE pile line in the balance portion distribution system at khuruline & four line of Raydak TG PWSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000038/2023-2024 | 369/ALD | 18/05/2023 | 60 | PRAPTI DUTTA | 10 | 8.51 | 80
1122 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Raydak TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000207/2023-2024 | 1561/ALD | 23/08/2023 | 45 | BRAJA GOPAL SAHA | 6.69 | 0 | 0
1123 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Raydak TG WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000224/2023-2024 | 1595/ALD | 25/08/2023 | 30 | DAS CONSTRUCTION | 6.76 | 6.74 | 95
1124 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works for proposed overhead reservoir of RAYDAK TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000313/2022-2023 | 2222/ALD | 21/11/2022 | 30 | K S GROUP | 0.65 | 0.65 | 0
1125 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new HDPE pipe line, Construction of Pump House at Head Work Site and providing FHTC and other allied works for Raydak TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000320/2022-2023 | 2229/ALD | 21/11/2022 | 120 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 13.78 | 6.35 | 61
1126 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at 2nd site of RAYDAK TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000323/2022-2023 | 2232/ALD | 21/11/2022 | 90 | ALATYA CONSTRUCTION & CO. | 13.65 | 0 | 0
1127 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new HDPE and DI pipeline, Supply of necessary specials, construction of sluice valve chamber, boundary wall at Head work site of RAYDAK TG AREA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000325/2022-2023 | 2234/ALD | 21/11/2022 | 90 | HITANGSHU CHOUDHURY | 15.63 | 3.73 | 61
1128 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 method of drilling at 2nd TW Site, Construction of Pump house at 2nd site, laying of Rising Main and delivery line connection, providing FHTC and other allied works for RAYDAK Tea Garden PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000328/2022-2023 | 2237/ALD | 21/11/2022 | 600 | DAS CONSTRUCTION | 95.24 | 60.93 | 65
1129 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Construction of 300 cum OHR as per Departmental Design & drawing, Providing FHTC and other allied works for RAYDAK TEA GARDEN PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000457/2022-2023 | 2978/ALD | 02/02/2023 | 180 | CHINMOY BHATTACHARJEE | 233.78 | 161.96 | 54
1130 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of DI specials and CI Jeffy coupling for Raydak TG Water Supply Scheme(SM/12114) of Kumargram Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000516/2023-2024 | 835/ALD | 14/03/2024 | 360 | HARI CONSTRUCTION | 15.18 | 8.28 | 80
1131 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000010/2023-2024 | 207/ALD/2023-2024 | 02/05/2023 | 0 | Resource Division | 44.73 | 0 | 0
1132 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000105/2023-2024 | 129/ALD | 10/01/2024 | 0 | Resource Division | 12.31 | 0 | 0
1133 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000080/2025-2026 | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1134 | Alipurduar Division | Birpara Sub-Division | Construction of boulder apron for Dimdima PWSS in sishujhumra mouza for protection of existing HW site under Alipurduar Division. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000487/2023-2024 | 743/ALD | 12/03/2024 | 135 | SUBIR GHOSH | 4.03 | 1.08 | 10
1135 | Alipurduar Division | Birpara Sub-Division | 3 nos. of Tube well Boring by ODEX-165 Method of drilling at HW site, 2nd TW and 3rd site site and Constructions of 350 Cum OHR at HW site inclu. soil testing , construction of pump house and boundary wall at H/W, 2nd site and 3rd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for SISHA JUMRHA PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000555/2022-2023 | 3576/ALD | 27/03/2023 | 902 | DILIP MAHATO | 539.73 | 365.61 | 23
1136 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000030/2023-2024 | 1275/ALD | 11/08/2023 | 0 | Resource Division | 54.68 | 0 | 0
1137 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000089/2023-2024 | 113/ALD | 10/01/2024 | 0 | Resource Division | 16.53 | 0 | 0
1138 | Alipurduar Division | Alipurduar Sadar Sub-Division | NEW CONNECTION FOR TUTURIKHANDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00044/2022-2023 | 394/22-23/PFMS | 21/12/2022 | 0 | WBSEDCL | 0.08 | 0 | 0
1139 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1140 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kumargram Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000081/2025-2026 | 1049/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1141 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KUMARGRAM water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000141/2020-2021 | 857/ALD | 14/10/2020 | 30 | ASHIM KUMAR CHAKRABORTY | 4.98 | 4.98 | 8
1142 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of Laying distribution system by replacing of Damaged AC pipeline with UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000153/2022-2023 | 1004/ALD | 15/07/2022 | 30 | DILIP MAHATO | 4.92 | 4.65 | 8
1143 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Kumargram PWSS, Kumargram Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000170/2022-2023 | 1009/ALD | 15/07/2022 | 60 | DILIP MAHATO | 43.79 | 13.32 | 6
1144 | Alipurduar Division | Alipurduar Sadar Sub-Division | Preparation of detailed Additional cost Requirement D.P.R. booklets in connection to various PWSS under Kumargram and Kalchini Block under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000186/2023-2024 | 1204/ALD | 07/08/2023 | 30 | ANIK BHATTACHARJEE | 0.78 | 0.78 | 100
1145 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 150cum. OHR for KUMARGRAM ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000255/2022-2023 | 1486/ALD | 05/09/2022 | 180 | MATRI ENTERPRISE | 50.41 | 46.14 | 100
1146 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of OHR 200cum for KUMARGRAM ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000256/2022-2023 | 1487/ALD | 05/09/2022 | 180 | S.G ENTERPRISE | 55.09 | 46.61 | 100
1147 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of OHR 200cum for KUMARGRAM ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000257/2022-2023 | 1488/ALD | 05/09/2022 | 720 | UNIVERSAL ENTERPRISES | 55.33 | 47.63 | 100
1148 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 250cum OHR for KUMARGRAM ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000258/2022-2023 | 1489/ALD | 05/09/2022 | 720 | GOUTAM KUMAR DAS | 57.3 | 52.88 | 95
1149 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation work at 4 different places of Kumargram within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000264/2022-2023 | 1502/ALD | 05/09/2022 | 30 | MOYTEC | 4.88 | 4.88 | 7
1150 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing and renovation of pump house, boundary wall and construction of new toilet of 2nd T/W site at Kumargram Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000306/2022-2023 | 1944/ALD | 17/10/2022 | 60 | TAPASH DAS | 4.73 | 3.99 | 8
1151 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of Kumargram Rest Shed and other works at Kumargram PWSS, Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. (SM/11985) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000450/2024-2025 | 5062/ALD | 18/02/2025 | 45 | DULAL DAS | 3.09 | 0 | 0
1152 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-165, Construction of pump house and boundary wall including laying distribution system with new UPVC pipeline with rising and delivery line connection, Providing FHTC and other allied works for KUMARGRAM PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2022-2023 | 3000/ALD | 06/02/2023 | 180 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 1152.29 | 660 | 50
1153 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1154 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main line /distribution pipeline, supply of DI pipe and specials, horizontal boring by HDD method, bridge and culvert crossing, specials repair with trial run of pipeline and allied works at Aug. of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000471/2023-2024 | 689/ALD | 07/03/2024 | 270 | HARI CONSTRUCTION | 40.9 | 0 | 0
1155 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 11.6 | 60
1156 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte..(from 01.02.2024 to 31.01.2025) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000500/2023-2024 | 372/ALD | 31/01/2024 | 366 | CHANDAN KIRTONIA | 4.8 | 4.25 | 0
1157 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000016/2024-2025 | 3950/ALD | 26/11/2024 | 0 | Resource Division | 12.32 | 0 | 0
1158 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000028/2022-2023 | 1702/ALD | 21/09/2022 | 0 | Resource Division | 61.6 | 0 | 0
1159 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000041/2022-2023 | 3483/ALD | 23/03/2023 | 0 | Resource Division | 61.6 | 0 | 0
1160 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000059/2023-2024 | 2721/ALD | 13/12/2023 | 0 | Resource Division | 97.75 | 0 | 0
1161 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment of Net Present value( NPV) against proposal no:FP/WB/Others /443394/2023- Cornpensatory levies {demand rote) againstIn-principal (Stage-l) approval of Water Supply Scheme Buxa forest PWSS {Z-Il} Pampu Basty under,Jal Jeelan Mission at Pampu Basti Forest Village - reg"(Annexure- I) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00155/2024-2025 | 154/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0
1162 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment for compensatory afforestation under proposal no FP/WB/others/443394/2023-C0mpenatory Levies(demand note) against In- principal of water supply scheme Buxa forest pwss ( Z-II)Pampu Basty under Jal Jeevan misson at pampu basti forest village - reg as per annexture-2 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00156/2024-2025 | 153/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0
1163 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment for boundary demarcation and construction of boundary pillar for the principal ( stage-I) approval for diversion of the forest land of area 0.0232 ha for water supply scheme Buxa forest PWSS(Z-II) Pampu Basty under proposal No :FP/WB/Others/443394/2023 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00157/2024-2025 | 152/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0
1164 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment of Net Present value ( NPV) against proposal no : FP/WB/Others/443377/2023- Compensatory levies ( Demand Note ) against In Principal ( Stage-I) approval of water supply scheme for Buxa Forest PWSS ( Z-II)Garo Basty under JJM at Garo Basti Forest Village- reg | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00158/2024-2025 | 157/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 17.54 | 0 | 0
1165 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment for compensatory afforestation under proposal no : FP/WB/Others/443377/2023-Compensatory levies ( Demand note) against In - Principal ( Stage-I) approval of Water supply scheme for Buxa Forest PWSS ( Z-II) Garo Basty under jal Jeevan Mission at Garo Basti Forest Village- reg | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00159/2024-2025 | 155/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0
1166 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment for boundary demarcation and construction of boundary pillar for the principal ( stage-I) approval for diversion of forest land of area 0.157 ha for Buxa forest PwSS ( Z-II ) Garo BastyUnder Proposal No: FP/WB/Others/443377/2023 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00160/2024-2025 | 156/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.94 | 0 | 0
1167 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment of Net Present Value ( NPV) against proposal No : FP/WB/Others/ 443397/2023 - Compensatory Levies ( Demand Note) against in- Principal ( Stage-I) approval of water supply Scheme for Buxa Forest PWSS (Z-II) Panijhora under JJM at Panijhora forest village reg | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00161/2024-2025 | 158/24-25/PFMS | 09/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0
1168 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cost of raising and maintenance of the compensatory afforestation for Ca area 0.04 ha ( 100 trees plantation and maintenance for 10 years) against proposed diversion of forrest land for water supply scheme Buxa forest PWSS ( Z-II) panijhora under JJM at panijhora forest Village reg under proposal NO: FP/WB/Others/443397/2023 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00162/2024-2025 | 159/24-25/PFMS | 09/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0
1169 | Alipurduar Division | Alipurduar Sadar Sub-Division | payment for boundary demarcation and constuction of boundary pillar for the principal ( Stage - I ) approval for diversion of forest land of .0232 ha area for Buxa forest PWSS ( Z-II) Panijhora under JJM at Panijhora forest village - reg under Proposal No: FP/WB/Others /443397/2023 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00163/2024-2025 | 160/24-25/PFMS | 09/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0
1170 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment against proposal No : FP/WB/Others /442047/2023-compensatory Levies ( Demand Note)against in- principal ( stage-I) approval of Gravity based WSS for boundary demarcation and construction of boundary pillar for Buxa forest PWSS under JJM at Uttar Poro Forest village -reg | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00185/2024-2025 | 149/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 0.52 | 0 | 0
1171 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payement aginst proposal no : FP/WB/Others/ 442047/2023 of Net Present Value of 0.0232 ha ( As per Annexure-1) forest land for diversion for gravity base water supply scheme for Buxa forest PWSS at Uttor Poro under JJM under BTR(WEST) Diivision under WDPO range Poro7Compartment | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00186/2024-2025 | 150/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.59 | 0 | 0
1172 | Alipurduar Division | Alipurduar Sadar Sub-Division | Payment as per annexure -2 against proposal No : FP/WB/Others/442047/2023 for raising and maintenance of the compensatory afforestation ( 100 trees plantation and maintence for 1o years ) agaist proposed diversion of forest land forgravity based piped water supply scheme for Buxa forest PWSS under JJm at Uttar Poro | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00187/2024-2025 | 151/24-25/PFMS | 08/08/2024 | 0 | EXECUTIVE ENGINEER, ALIPURDUAR DIVISION | 2.13 | 0 | 0
1173 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. 4 nos Tube well boring by ODEX-165 Method of drilling at HW site including distribution system with new HDPE pipeline, Cons. of 250 cum OHR as per Departmental Design & drawing, Pump House , Boundary Wall, Path way, Providing FHTC, Soil Testing and other allied works for BUXA FOREST(RAJA BHATKHAWA) PIPED WATER SUPPLY SCHEME under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000176/2023-2024 | 1112/ALD | 28/07/2023 | 644 | CAPITAL ENGINEERS | 518.6 | 103.94 | 30
1174 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC from existing distribution system as per specification for BUXA FOREST (RAJABHATKHAWA) PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000321/2023-2024 | 2416/ALD | 09/11/2023 | 60 | SHIB RATAN BHOWMIK | 17.96 | 0 | 0
1175 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000021/2023-2024 | 1259/ALD | 10/08/2023 | 0 | Resource Division | 61.75 | 0 | 0
1176 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000039/2022-2023 | 3047/ALD | 08/02/2023 | 0 | Resource Division | 61.86 | 0 | 0
1177 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for Dakshin Rangalibazna PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000303/2023-2024 | 2134/ALD | 03/10/2023 | 30 | MANI PRADHAN | 3.25 | 0 | 0
1178 | Alipurduar Division | Birpara Sub-Division | Cons. of Rig bored TW(2nos) by ODEX-165 method of drilling at HW and 2nd site, cons of 100 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dakshin Rangalibazna PWSS under Birpara Sub-Division, Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000509/2022-2023 | 3396/ALD | 16/03/2023 | 180 | S.G. CONSTRUCTION | 247.26 | 77.23 | 32
1179 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000030/2024-2025 | 3988/ALD | 27/11/2024 | 0 | Resource Division | 4.89 | 0 | 0
1180 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000045/2022-2023 | 3487ALD | 23/03/2023 | 0 | Resource Division | 4.89 | 0 | 0
1181 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000056/2023-2024 | 2702 | 12/12/2023 | 0 | Resource Division | 68.94 | 0 | 0
1182 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000088/2023-2024 | 112/ALD | 10/01/2024 | 0 | Resource Division | 4.89 | 0 | 0
1183 | Alipurduar Division | Alipurduar RWS Sub-Division | Laying of new HDPE pipeline for providing FHTC and land filling at Headwork site & 2nd site at Foskadanga PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000030/2025-2026 | 439/ALD | 30/04/2025 | 60 | MADHAB SAHA | 52.23 | 0 | 0
1184 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC from existing distribution system as per specification for Foskadanga PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000272/2023-2024 | 1888/ALD | 07/09/2023 | 30 | MADHAB SAHA | 7 | 4.77 | 70
1185 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (100cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Foskadanga PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000549/2022-2023 | 3572/ALD | 27/03/2023 | 737 | MADHAB SAHA | 321.67 | 219.01 | 10
1186 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000028/2024-2025 | 3986/ALD | 27/11/2024 | 0 | Resource Division | 4.21 | 0 | 0
1187 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000042/2024-2025 | 4258/ALD | 13/12/2024 | 0 | Resource Division | 1.53 | 0 | 0
1188 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000092/2023-2024 | 116/ALD | 10/01/2024 | 0 | Resource Division | 4.21 | 0 | 0
1189 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC including Rising main and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00602/2023-2024 |  | 29/02/2024 | 0 | HARI CONSTRUCTION | 1.21 | 0 | 0
1190 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution line with UPVC pipe at PUTIMARI WSS under Alipurduar Division , PHE Dte(Part - III) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000069/2022-2023 | 434/ALD | 13/05/2022 | 30 | HARI CONSTRUCTION | 5.02 | 4.74 | 93
1191 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Putimari Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000106/2022-2023 | 698/ALD | 08/06/2022 | 30 | TAPASH DAS | 4.83 | 4.83 | 93
1192 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Putimari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000194/2022-2023 | 1221/ALD | 10/08/2022 | 1020 | HARI CONSTRUCTION | 38.9 | 25.91 | 100
1193 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for Putimari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000205/2023-2024 | 1558/ALD | 23/08/2023 | 30 | HARI CONSTRUCTION | 3.35 | 0 | 0
1194 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system for Putimari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000228/2022-2023 | 1104/ALD | 29/07/2022 | 30 | HARIDAS GHOSH | 2.92 | 2.92 | 95
1195 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at office of the Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000242/2022-2023 | 1152/ALD | 02/08/2022 | 7 | CYBER NET | 0.99 | 0.99 | 94
1196 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 350cum OHR for Putimari TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000312/2021-2022 | 2188/ALD | 11/01/2022 | 429 | TAPASH KUMAR BHOWMICK | 71.4 | 53.44 | 95
1197 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation work at 4 different places of Alipurduar District under Alipurduar Division PHE Dte. Part-4 Venue : Putimari 2)Mechpara 3)Mathura 4)Gangutia. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000362/2021-2022 | 2124/ALD | 05/01/2022 | 30 | MABCO CONSULTANT, | 4.86 | 4.86 | 94
1198 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Putimari PWSS, Alipurduar Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000364/2021-2022 | 2291/ALD | 24/01/2022 | 1200 | HARI CONSTRUCTION | 45.52 | 42.55 | 100
1199 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000386/2021-2022 | 2386/ALD | 31/01/2022 | 90 | TAPASH KUMAR BHOWMICK | 93.77 | 93.18 | 96
1200 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000387/2021-2022 | 2387/ALD | 31/01/2022 | 60 | TAPASH KUMAR BHOWMICK | 76.84 | 75.28 | 97
1201 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC including Rising main and laying distribution system for PUTIMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000388/2021-2022 | 2388/ALD | 31/01/2022 | 60 | HARI CONSTRUCTION | 71.64 | 68.88 | 94
1202 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of UPVC pipeline for Putimari WSS under Dakshin Shibkata Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000390/2021-2022 | 2304/ALD | 25/01/2022 | 30 | HARI CONSTRUCTION | 5.05 | 5.05 | 91
1203 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of UPVC pipeline for Putimari WSS under Dakshin Dhalkar Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000391/2021-2022 | 2305/ALD | 25/01/2022 | 30 | PRAPTI DUTTA | 5.04 | 4.55 | 95
1204 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of UPVC pipeline for Putimari WSS under Putimari Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000405/2021-2022 | 2312/ALD | 25/01/2022 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.04 | 5.04 | 94
1205 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of UPVC pipeline for Putimari WSS under Putimari Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000406/2021-2022 | 2313/ALD | 25/01/2022 | 30 | AASHIRBAD ENTERPRISE | 5.04 | 5.04 | 93
1206 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of UPVC pipeline for Putimari WSS under Uttar Dhalkar Mousa under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000407/2021-2022 | 2314/ALD | 25/01/2022 | 30 | PRAPTI DUTTA | 5.04 | 5.04 | 92
1207 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 100
1208 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing balance FHTC from existing distribution system as per specification for BHATPARA TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000315/2023-2024 | 2185/ALD | 06/10/2023 | 60 | MAHENDRA CHHETRI | 17.77 | 0 | 0
1209 | Alipurduar Division | Alipurduar RWS Sub-Division | T/W Boring by ODEX-165 Method of drilling at HW FIRST TW site including LDS with new HDPE P/L, Cons. of 250 Cum OHR as per Departmental Design and drawing including soil investigation works, 2nos. pumphouse and boundary wall, providing FHTC and others allied works for BHATPARA TG PWSS under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000452/2022-2023 | 2969/ALD | 31/01/2023 | 1080 | MAHENDRA CHHETRI | 362.78 | 251.6 | 90
1210 | Alipurduar Division | Alipurduar RWS Sub-Division | Laying of HDPE Pipeline for left out household connection, boundary wall, pump house, OHR, Land Development, Pathway Platform for FHTC and allied works at Bhatpara PWSS under Alipurduar Division, P.H.E. Dte. (SM/14212) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000510/2023-2024 | 828/ALD | 14/03/2024 | 70 | MAHENDRA CHHETRI | 47.4 | 42.11 | 28
1211 | Alipurduar Division | Alipurduar RWS Sub-Division | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.02.2023 to 30.04.2023) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000566/2022-2023 | 2952/ALD | 24/01/2023 | 90 | NIRANJAN KIRTANIA | 0.7 | 0.51 | 0
1212 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000025/2023-2024 | 1270/ALD | 11/08/2023 | 0 | Resource Division | 17.99 | 0 | 0
1213 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000032/2024-2025 | 4248/ALD | 13/12/2024 | 0 | Resource Division | 3.63 | 0 | 0
1214 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000075/2023-2024 | 99/ALD | 10/01/2024 | 0 | Resource Division | 14.3 | 0 | 0
1215 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000086/2023-2024 | 110/ALD | 10/01/2024 | 0 | Resource Division | 14.3 | 0 | 0
1216 | Alipurduar Division | Alipurduar Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1217 | Alipurduar Division | Alipurduar Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for KALCHINI TG ZONE-I PWSS Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000009/2022-2023 | 3230/ALD. | 27/02/2023 | 240 | SHREE RANISATI ENTERPRISE | 190.87 | 119.33 | 10
1218 | Alipurduar Division | Alipurduar Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd & 3rd site including laying distribution system , Rising main and providing FHTC for KALCHINI TG ZONE-I PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000014/2022-2023 | 3229/ALD. | 27/02/2023 | 120 | SHREE RANISATI ENTERPRISE | 143.22 | 63.43 | 30
1219 | Alipurduar Division | Alipurduar Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 3rd & 4th site including laying distribution system , Rising main and providing FHTC for KALCHINI TG ZONE-II PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000015/2022-2023 | 3227/ALD | 27/02/2023 | 120 | SHREE RANISATI ENTERPRISE | 179.1 | 0 | 0
1220 | Alipurduar Division | Alipurduar Division | Retrofitting and Extension of pipeline for Kalchini area under DIMA PWSS at Kalchini Block under Alipurduar Division. PHE Dte. Part-A | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000372/2020-2021 | 1768/ALD | 19/02/2021 | 60 | SUNDAR SING LAMA | 41.98 | 0 | 86
1221 | Alipurduar Division | Alipurduar Division | Retrofitting and Extension of pipeline for Kalchini area under DIMA PWSS at Kalchini Block under Alipurduar Division. PHE Dte. Part-B | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000373/2020-2021 | 1769/ALD | 19/02/2021 | 60 | RAMESH SHARMA | 49.52 | 0 | 93
1222 | Alipurduar Division | Alipurduar Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1223 | Alipurduar Division | Alipurduar Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site & 2nd site including laying distribution system and providing FHTC for KALCHINI TG ZONE-II PWSS Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000474/2022-2023 | 3228/ALD | 27/02/2023 | 120 | SHREE RANISATI ENTERPRISE | 179.69 | 0 | 0
1224 | Alipurduar Division | Alipurduar Division | Supply of CIDF/CIPE pipes and specials & CI Jeffy Coupling for Kalchini TG Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000483/2023-2024 | 739/ALD | 12/03/2024 | 30 | MADHAB SAHA | 13.81 | 0 | 0
1225 | Alipurduar Division | Alipurduar Division | Conceptualization, design and implementing mass awareness generation through Wall writing at 22 nos. villages (Block - Madarihat) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal.( SM/15482) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000497/2023-2024 | 753/ALD | 12/03/2024 | 30 | BARMAN ENTERPRISE | 5.27 | 5.27 | 100
1226 | Alipurduar Division | Alipurduar Division | Construction of 350cum OHR for Kalchini TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000564/2022-2023 | 3233/ALD | 27/02/2023 | 180 | Z STAR COMMOTRADE PVT LTD. | 71.41 | 0 | 0
1227 | Alipurduar Division | Alipurduar Division | Construction of 500cum OHR for Kalchini TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000565/2022-2023 | 3234ALD | 27/02/2023 | 360 | SHREE RANISATI ENTERPRISE | 91.81 | 41.04 | 40
1228 | Alipurduar Division | Alipurduar Division | Reparing of Pump House at Headwork site of Kalchini PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000592/2024-2025 | 5421/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.98 | 0 | 0
1229 | Alipurduar Division | Alipurduar Division | Reparing of Pump House at 3nd site of Kalchini PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000594/2024-2025 | 5423/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.98 | 0 | 0
1230 | Alipurduar Division | Alipurduar Division | Reparing of Pump House at 2nd site of Kalchini PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000601/2024-2025 | 5422/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0
1231 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000027/2023-2024 | 1272/ALD | 11/08/2023 | 0 | Resource Division | 77.78 | 0 | 0
1232 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000042/2022-2023 | 3484/ALD | 23/03/2023 | 0 | Resource Division | 36.96 | 0 | 0
1233 | Alipurduar Division | Birpara Sub-Division | Construction of 2nos pump house, boundary wall, TW boring by ODEX-195 method of drilling for Augmentation of Dhumchipara PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000389/2023-2024 | 200/ALD | 16/01/2024 | 480 | MITHUN DAS | 54.27 | 0 | 50
1234 | Alipurduar Division | Birpara Sub-Division | Construction of boulder apron for Dhumchipara PWSS for protection of existing Pump house under Alipurduar Division. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000488/2023-2024 | 744/ALD | 12/03/2024 | 45 | MANI PRADHAN | 3.59 | 3.58 | 50
1235 | Alipurduar Division | Birpara Sub-Division | Boring of TW, Construction of Pumphouse, Boundary wall, Laying of Distribution system for Augmentation of Dhumchipara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000502/2022-2023 | 3324/ALD | 13/03/2023 | 840 | GIRIRAJ ENTERPRISE | 22.78 | 18.97 | 70
1236 | Alipurduar Division | Birpara Sub-Division | Replacement of damaged pipeline with HDPE and DI pipes for Dhumchipara PWSS of Alipurduar RWS Sub-Division under Alipurduar Division, PHE Dte. (SM/09896) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000505/2023-2024 | 823/ALD | 14/03/2024 | 60 | MONORAMA ENTERPRISE | 5.73 | 0 | 5
1237 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline (parallel and balance line ) at Umacharanpur PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000194/2025-2026 | 2077/ALD | 19/09/2025 | 75 | TAPASH KUMAR BHOWMICK | 80.25 | 0 | 0
1238 | Alipurduar Division | Birpara Sub-Division | Laying of rising main DI (K7), interconnection work with HDPE pipe , Construction of sluice valve chamber for Umacharanpur PWSS under Birpara Sub- Division ,Alipurduar Division PHE Dte. under North Bengal Circle-I PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000210/2024-2025 | 2061/ALD | 12/07/2024 | 300 | TAPASH KUMAR BHOWMICK | 101.24 | 93.17 | 90
1239 | Alipurduar Division | Birpara Sub-Division | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site, Soil investigation at OHR site, constructions of 500 Cum OHR at HW, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Uma Charanpur PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000251/2023-2024 | 1873/ALD | 07/09/2023 | 270 | TAPASH KUMAR BHOWMICK | 608.41 | 242.55 | 37
1240 | Alipurduar Division | Birpara Sub-Division | Supply of CIDF Specials and Jeffy Coupling for Umacharanpur (SM/16114) WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000413/2024-2025 | 4591/ALD | 03/01/2025 | 30 | TAPASH KUMAR BHOWMICK | 19.81 | 0 | 0
1241 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1242 | Alipurduar Division | Birpara Sub-Division | Supply of CI Sluice Valve and Special & CI Jeffy Coupling for Umachndrapur Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000465/2023-2024 | 608/ALD | 29/02/2024 | 30 | MANSAROVAR CASTING | 11.95 | 11.95 | 85
1243 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000065/2023-2024 | 2775/ALD | 18/12/2023 | 0 | Resource Division | 18.81 | 0 | 0
1244 | Alipurduar Division | Alipurduar Sadar Sub-Division | Route surveying and revalidation of Household data with digitization of LDS for Lepchakha and Santalebari PWSS under Kalchini Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000096/2025-2026 | 1180/ALD | 26/06/2025 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.58 | 0 | 0
1245 | Alipurduar Division | Alipurduar Sadar Sub-Division | LAYING OF 25 MM DIA PP-R PIPES FROM TASHIGAON RIVER TO LEPCHAKHA AND LEPCHAKHA TO DUMBA AND OTHER ALLIED WORKS UNDER JJM PROGRAMME UNDER ALIPURDUAR DIVISION, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000439/2024-2025 | 5042/ALD | 17/02/2025 | 120 | S.D. PROJECT | 8.33 | 0 | 100
1246 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of RCC clear water Reservoir (CWR) of capacity 100 cum, laying distribution system and providing FHTC at Buxa PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000563/2022-2023 | 3506/ALD | 23/03/2023 | 180 | ASHOK SAPKOTA | 30.8 | 0 | 100
1247 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000022/2023-2024 | 1260/ALD | 10/08/2023 | 0 | Resource Division | 2.17 | 0 | 0
1248 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000078/2023-2024 | 102/ALD | 10/01/2024 | 0 | Resource Division | 16.34 | 0 | 0
1249 | Alipurduar Division | Alipurduar Division | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new UPVC pipeline , Constructions of 100 Cum OHR as per Departmental Design & drawing including soil investigation works, TWO nos. pump house & boundary wall, providing FHTC and others allied works for UTTAR BARAJHAR FOREST PWSS Under Alipurduar Division PHE DTE. (2nd call) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000011/2023-2024 | 134/ALD | 24/04/2023 | 180 | TAPASH DAS | 193.2 | 32.59 | 15
1250 | Alipurduar Division | Alipurduar Division | Providing FHTC from existing distribution system as per specification for Uttar Barajhar PWSS PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000270/2023-2024 | 1887/ALD | 07/09/2023 | 30 | TAPASH DAS | 4.24 | 0 | 0
1251 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000025/2024-2025 | 3983/ALD | 27/11/2024 | 0 | Resource Division | 3.49 | 0 | 0
1252 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000034/2022-2023 | 3014/ALD, | 07/02/2023 | 0 | Resource Division | 10.87 | 0 | 0
1253 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000079/2023-2024 | 103/ALD | 10/01/2024 | 0 | Resource Division | 3.49 | 0 | 0
1254 | Alipurduar Division | Birpara Sub-Division | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , soil investigation at OHR site, constructions of 300 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Lachhimandabri PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000183/2023-2024 | 1172/ALD | 03/08/2023 | 900 | M/S T M CONSTRUCTION | 433.46 | 174.73 | 35
1255 | Alipurduar Division | Birpara Sub-Division | Supply of CIDF/CIPE pipes and specials & CI Jeffy Coupling for Lachman Dabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000478/2023-2024 | 696/ALD | 07/03/2024 | 300 | HARIDAS GHOSH | 18.07 | 18.07 | 65
1256 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000018/2024-2025 | 3952/ALD | 26/11/2024 | 0 | Resource Division | 7.84 | 0 | 0
1257 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000038/2023-2024 | 1476/ALD | 16/08/2023 | 0 | Resource Division | 21.37 | 0 | 0
1258 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000054/2023-2024 | 2700/ALD | 12/12/2023 | 0 | Resource Division | 84.45 | 0 | 0
1259 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000063/2023-2024 | 2773/ALD | 18/12/2023 | 0 | Resource Division | 7.84 | 0 | 0
1260 | Alipurduar Division | Birpara Sub-Division | Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. Part-B | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000048/2023-2024 | 394/ALD | 19/05/2023 | 120 | TAPASH KUMAR BHOWMICK | 4.67 | 4.67 | 0
1261 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0
1262 | Alipurduar Division | Birpara Sub-Division | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Tasti Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE.(2nd call) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000170/2023-2024 | 975/ALD | 12/07/2023 | 659 | MADHAB SAHA | 298.87 | 95.05 | 15
1263 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1264 | Alipurduar Division | Birpara Sub-Division | Supply of CIDF/CIPE Pipes and Special & CI Jeffy Coupling for Tasati TG Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000485/2023-2024 | 741/ALD | 12/03/2024 | 30 | MADHAB SAHA | 12.19 | 0 | 0
1265 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000020/2024-2025 | 3954/ALD | 26/11/2024 | 0 | Resource Division | 7.29 | 0 | 0
1266 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000039/2023-2024 | 1478/ALD | 16/08/2023 | 0 | Resource Division | 40.6 | 0 | 0
1267 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000062/2023-2024 | 2772/ALD | 18/12/2023 | 0 | Resource Division | 7.29 | 0 | 0
1268 | Alipurduar Division | Birpara Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1269 | Alipurduar Division | Birpara Sub-Division | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000049/2023-2024 | 395/ALD | 19/05/2023 | 120 | TAPASH KUMAR BHOWMICK | 4.29 | 4.29 | 20
1270 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Falakata Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000130/2025-2026 | 1629/ALD | 04/08/2025 | 60 | NARENDRA BHADANI. | 18.13 | 0 | 0
1271 | Alipurduar Division | Birpara Sub-Division | Supply of DI/DIDF Specials for Dalgaon TG (SM/16823)WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000410/2024-2025 | 4582/ALD | 02/01/2025 | 30 | TAPASH KUMAR BHOWMICK | 16.98 | 0 | 0
1272 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1273 | Alipurduar Division | Birpara Sub-Division | "Supply of DIDF Special and CI Jeffy Coupling for Dalgaon TG Water Supply Scheme(SM/16823) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000527/2023-2024 | 846/ALD | 14/03/2024 | 90 | MADHAB SAHA | 16.41 | 16.41 | 62
1274 | Alipurduar Division | Birpara Sub-Division | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , constructions of 200 Cum OHR at HW including soil investigation , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Dalgaon Tea Garden PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000573/2022-2023 | 3634/ALD | 31/03/2023 | 1091 | M/S MRITYUNJAY PAUL AND SONS | 390.34 | 197.43 | 51
1275 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000046/2023-2024 | 1954/ALD | 12/09/2023 | 0 | Resource Division | 40.05 | 0 | 0
1276 | Alipurduar Division | Birpara Sub-Division | Laying of DI / UPVC Pipeline & other Misc. works for Bhutiya Basti area at PAITKAPARA PWSS under Alipurduar Division PHED. | Alipurduar RWS | Birpara Sub Division | ORD/000071/2020-2021 | 625/ALD | 03/09/2020 | 120 | DAS CONSTRUCTION | 16.33 | 7.8 | 99
1277 | Alipurduar Division | Birpara Sub-Division | Providing House connection for DHEKLAPARA PWSS at MADARIHAT-BIRPARA Block under Alipurduar Division PHED PART 1 | Alipurduar RWS | Birpara Sub Division | ORD/000082/2020-2021 | 634/ALD | 03/09/2020 | 90 | DILIP MAHATO | 21.8 | 18.74 | 0
1278 | Alipurduar Division | Birpara Sub-Division | Extension and Replacement of damaged pipeline under Patlakhawa PWSS under Alipurduar Division, P.H.E. Dte.(Part-C) | Alipurduar RWS | Birpara Sub Division | ORD/000183/2020-2021 | 1008/ALD | 12/11/2020 | 60 | JAI BHARAT COMMERCIAL CORPORATION | 14.4 | 17.22 | 100
1279 | Alipurduar Division | Birpara Sub-Division | Retrofitting work of pipeline of Madarihat PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000199/2021-2022 | 972/ALD | 13/09/2021 | 30 | MS DEYS CONSTRUCTION | 4.99 | 0 | 99
1280 | Alipurduar Division | Birpara Sub-Division | Providing House connection for PURBA KATHALBARI water supply scheme at Alipurduar -I Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar RWS | Birpara Sub Division | ORD/000222/2020-2021 | 1173/ALD | 15/12/2020 | 60 | MADHAB SAHA | 19.93 | 27.91 | 0
1281 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Alipurduar RWS | Birpara Sub Division | ORD/000268/2020-2021 | 1280/ALD | 05/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 30.9 | 28.62 | 98
1282 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 90 | ANUP GUPTA | 20.99 | 0 | 80
1283 | Alipurduar Division | Birpara Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 17 | 100
1284 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of old UPVC pipe line , FHTC and other misc. work related to DHAOLAJHORA PWSS Alipurduar - II Block under Alipurduar Division , PHE Dte | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000071/2022-2023 | 436/ALD | 13/05/2022 | 30 | MATARA CONSTRUCTION CO | 3.3 | 0 | 27
1285 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DHAOLAJHORA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000325/2021-2022 | 2226/ALD | 14/01/2022 | 90 | MADHAB SAHA | 20.99 | 17.04 | 100
1286 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000109/2022-2023 | 701/ALD | 08/06/2022 | 30 | HARIDAS GHOSH | 4.96 | 4.96 | 73
1287 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of UPVC pipeline for augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000197/2022-2023 | 1223/ALD | 10/08/2022 | 960 | DILIP MAHATO | 56.93 | 54.35 | 100
1288 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of UPVC pipeline for augmentation of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000198/2022-2023 | 1224/ALD | 10/08/2022 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 46.73 | 40.43 | 70
1289 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of boundary wall (H/W) Site, Toilet, Repairing of Pump House & 125 nos. house connection of Uttar Majherdabri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000275/2020-2021 | 1287/ALD | 05/01/2021 | 60 | TAPASH KUMAR BHOWMICK | 20.49 | 12.7 | 73
1290 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 450cum OHR for Augmentation of Uttar Majher Dabri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000413/2021-2022 | 2581/ALD | 17/02/2022 | 720 | M/S DUTTA AND CO | 87.59 | 87.15 | 99
1291 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for UTTAR MAJHERDABRI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000427/2021-2022 | 2611/ALD | 17/02/2022 | 90 | HIGHLIFE INTERNATIONAL | 44.39 | 43.93 | 100
1292 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000470/2021-2022 | 2870/ALD | 07/03/2022 | 1080 | DILIP MAHATO | 101.03 | 96.04 | 80
1293 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000471/2021-2022 | 2871/ALD | 07/03/2022 | 1200 | TAPAN CHANDA | 100.9 | 74.42 | 100
1294 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-C) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000472/2021-2022 | 2872/ALD | 07/03/2022 | 60 | MAHENDRA CHHETRI | 94.52 | 77.53 | 73
1295 | Alipurduar Division | Alipurduar Sadar Sub-Division | Balance work of construction of boundary wall & repairing of pump house at 2nd Tubewell site of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000483/2021-2022 | 2659/ALD | 21/02/2022 | 45 | TAPASH KUMAR BHOWMICK | 4.49 | 3.62 | 73
1296 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC in school in Uttar Majherdabri PWSS under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000496/2022-2023 | 3360/ALD | 14/03/2023 | 30 | HARIDAS GHOSH | 0.22 | 0.22 | 100
1297 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of Uttar Majherdabri WSS under Alipurduar Division, PHE Dte. (Part-D) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000497/2021-2022 | 3002/ALD | 15/03/2022 | 60 | M/S DUTTA AND CO | 95.57 | 74.72 | 71
1298 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000024/2022-2023 | 1589/ALD | 14/09/2022 | 0 | Resource Division | 12.3 | 0 | 0
1299 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000084/2023-2024 | 108/ALD | 10/01/2024 | 0 | Resource Division | 4.47 | 0 | 0
1300 | Alipurduar Division | Birpara Sub-Division | Construction of balance portion of boundary wall at CWR site under LANKAPARA (TULSHIPARA TG ) WSS under Alipurduar Division PHE Dte . | Birpara A.E | Birpara Sub Division | ORD/000084/2022-2023 | 448/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.91 | 4.8 | 97
1301 | Alipurduar Division | Birpara Sub-Division | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | Birpara A.E | Birpara Sub Division | ORD/000181/2020-2021 | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 0 | 97
1302 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE/DI pipe line at different area of flank of Lankapara road/village road and Lankapara Bazar Area under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000182/2020-2021 | 1007/ALD | 12/11/2020 | 60 | MADHAB SAHA | 33.79 | 13.5 | 99
1303 | Alipurduar Division | Birpara Sub-Division | Sinking of 1no. Tube Well for replacement and another 1no. new Tube Well near factory line by ODEX-195 method of drilling at Lankapara Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000205/2021-2022 | 1345/ALD | 08/10/2021 | 30 | SASANKA ROY | 33 | 32.32 | 96
1304 | Alipurduar Division | Birpara Sub-Division | Development of rig Bore TW by ODEX-165 method of drilling at Lankapara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000261/2021-2022 | 1608/ALD | 22/11/2021 | 20 | DILIP MAHATO | 0.66 | 0.5 | 99
1305 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Birpara A.E | Birpara Sub Division | ORD/000268/2020-2021 | 1280/ALD | 05/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 30.9 | 0 | 98
1306 | Alipurduar Division | Birpara Sub-Division | Construction of Boundary wall near head work site of Lankapara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000395/2021-2022 | 2309/ALD | 25/01/2022 | 45 | ASHOK SAPKOTA | 4.78 | 3.04 | 98
1307 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House with sanitary & plumbing arrangement near head work site of Lankapara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000396/2021-2022 | 2310/ALD | 25/01/2022 | 60 | ASHOK SAPKOTA | 5.03 | 4.68 | 98
1308 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Beltali Road and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000026/2022-2023 | 24/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 0 | 80
1309 | Alipurduar Division | Birpara Sub-Division | Extension of Distribution line with UPVC pipe line near Narendra Nath Sishu Siksha Kendra under Jateswar Water Supply Scheme under Alipurduar Division,PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000134/2020-2021 | 880/ALD | 14/10/2020 | 30 | NARAYAN CHANDRA SAHA | 2.02 | 3.71 | 0
1310 | Alipurduar Division | Birpara Sub-Division | Providing House connection for JATESWAR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. PART-1 | Birpara A.E | RWS Falakata Block | ORD/000155/2020-2021 | 867/ALD | 14/10/2020 | 30 | PARAMJYOTI ENTERPRISE | 4.93 | 9.87 | 0
1311 | Alipurduar Division | Birpara Sub-Division | Providing House connection for JATESWAR water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. PART-2 | Birpara A.E | RWS Falakata Block | ORD/000156/2020-2021 | 868/ALD | 14/10/2020 | 30 | NARAYAN CHANDRA SAHA & SONS | 4.93 | 9.87 | 0
1312 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI/MS Distribution pipe line and FHTC in connection with Jaldhara Jal Sapna and other misc. work for Jateswar WSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000239/2020-2021 | 1180/ALD | 15/12/2020 | 60 | SANJIT SAHA | 41.94 | 61.91 | 96
1313 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) | Birpara A.E | RWS Falakata Block | ORD/000320/2020-2021 | 1453/ALD | 25/01/2021 | 45 | PRAMESH LAMA | 33.97 | 5.88 | 100
1314 | Alipurduar Division | Birpara Sub-Division | Construction of roof truss, field development and other allied works at Headwork site of Old Jaigaon WSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000393/2021-2022 | 2307/ALD | 25/01/2022 | 30 | DILIP MAHATO | 4.17 | 0 | 75
1315 | Alipurduar Division | Birpara Sub-Division | Construction of 500cum OHR for Augmentation of Jateswar Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000409/2021-2022 | 2525/ALD | 11/02/2022 | 180 | ASHIT KUMAR SINGHA | 91.76 | 0 | 80
1316 | Alipurduar Division | Birpara Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 25 | 100
1317 | Alipurduar Division | Birpara Sub-Division | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-II | Birpara A.E | RWS Falakata Block | ORD/000450/2021-2022 | 2747/ALD | 24/02/2022 | 60 | TAPASH DAS | 49.62 | 8.38 | 59
1318 | Alipurduar Division | Birpara Sub-Division | Laying of distribution of UPVC/DI/GI pipeline including FHTC for JATESWAR PWSS under Alipurduar Division, PHE DTE. PART-I | Birpara A.E | RWS Falakata Block | ORD/000467/2021-2022 | 2812/ALD | 28/02/2022 | 60 | SOUVIK ROY PALADHI | 98.49 | 0.03 | 63
1319 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI/MS/CI distribution pipe line for gap filling and FHTC connection for Sahapara and adjoining area of Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000539/2021-2022 | 3191/ALD | 28/03/2022 | 60 | AASHIRBAD ENTERPRISE | 12.35 | 0 | 78
1320 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 3.2 | 0
1321 | Alipurduar Division | Birpara Sub-Division | Fuel bill for the month of August 2021 | Birpara A.E | RWS Falakata Block | VCH/000568/2021-2022 | 118/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.21 | 0 | 0
1322 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Boundary Wall at Dalda Bari of Jaigaon WSS, Zone-II under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000040/2021-2022 | 551/ALD | 14/07/2021 | 45 | TAPASH DAS | 4.9 | 0 | 0
1323 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for Putimari water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000104/2020-2021 | 725/ALD | 22/09/2020 | 30 | HIMALAYAN CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.02 | 10.04 | 0
1324 | Alipurduar Division | Alipurduar Sadar Sub-Division | Preparation of Augmentation D.P.R after investigation For Jateswar W/S scheme under Alipurduar Division. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000111/2021-2022 | 914/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.31 | 0.01 | 0
1325 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for SALSALABARI water supply scheme at ALIPURDUAR-II Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000166/2020-2021 | 910/ALD | 16/10/2020 | 30 | M/S BHOWMICK CONSTRUCTION | 4.96 | 9.91 | 0
1326 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for Jashodanga water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000205/2020-2021 | 1159/ALD | 15/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 29.89 | 25.43 | 98
1327 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for Purba Chepani water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte.(Part-IV | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000212/2020-2021 | 1132/ALD | 10/12/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.93 | 2.88 | 0
1328 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under SALSALABARI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000267/2020-2021 | 1279/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 45.43 | 30.3 | 97
1329 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for SALSALABARI water supply scheme at Alipurduar -II Block underAlipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | VCH/000945/2020-2021 | 572/20-21 | 26/03/2021 | 0 | TAPASH KUMAR BHOWMICK | 14 | 0 | 0
1330 | Alipurduar Division | Birpara Sub-Division | Providing FHTC and other allied works at Munshipara WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000161/2021-2022 | 1303/ALD | 05/10/2021 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 44.94 | 31.33 | 82
1331 | Alipurduar Division | Birpara Sub-Division | Laying of DI/UPVC pipeline along with PMGSY Road and other misc. works related to Munshipara PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000187/2020-2021 | 1012/ALD | 12/11/2020 | 60 | TAPASH DAS | 35.88 | 8.78 | 83
1332 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000196/2021-2022 | 1317/ALD | 05/10/2021 | 1560 | DILIP MAHATO | 58.07 | 0 | 85
1333 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Munshipara piped water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte.Part-II | Alipurduar RWS | Birpara Sub Division | ORD/000204/2020-2021 | 1158/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.93 | 0 | 82
1334 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS | Birpara Sub Division | ORD/000278/2021-2022 | 1845/ALD | 10/12/2021 | 30 | RATAN DUTTA | 4.35 | 2.57 | 82
1335 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar RWS | Birpara Sub Division | ORD/000279/2021-2022 | 1846/ALD | 10/12/2021 | 30 | AASHIRBAD ENTERPRISE | 4.34 | 0 | 80
1336 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 72
1337 | Alipurduar Division | Birpara Sub-Division | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000080/2020-2021 | 632/ALD | 03/09/2020 | 90 | HARIDAS GHOSH | 63.58 | 24.64 | 80
1338 | Alipurduar Division | Birpara Sub-Division | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 0 | 62
1339 | Alipurduar Division | Birpara Sub-Division | Preparation of Augmentation D.P.R after investigation For Salkumarhat W/S scheme under Alipurduar Division. | Birpara A.E | RWS Falakata Block | ORD/000115/2021-2022 | 921/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 1.08 | 2.15 | 0
1340 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Birpara A.E | RWS Falakata Block | ORD/000133/2021-2022 | 1243/ALD | 27/09/2021 | 60 | TAPASH DAS | 25.25 | 7.05 | 78
1341 | Alipurduar Division | Birpara Sub-Division | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | Birpara A.E | RWS Falakata Block | ORD/000181/2020-2021 | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 8.88 | 97
1342 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000197/2021-2022 | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 0 | 85
1343 | Alipurduar Division | Birpara Sub-Division | Providing House connection for CHOTO SALKUMAR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | Birpara A.E | RWS Falakata Block | ORD/000218/2020-2021 | 1169/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 43.77 | 70
1344 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line for retrofitting and providing functional household tap connection (FHTC) in connection with Jaldhara Jal Sapno of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000298/2020-2021 | 1378/ALD | 19/01/2021 | 45 | M/S PALIT ENTERPRISE | 43.75 | 30.3 | 68
1345 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line and other misc. work for retrofitting at Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000299/2020-2021 | 1379/ALD | 19/01/2021 | 45 | SASANKA ROY | 17.09 | 5.84 | 100
1346 | Alipurduar Division | Birpara Sub-Division | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | Birpara A.E | RWS Falakata Block | ORD/000397/2021-2022 | 2311/ALD | 25/01/2022 | 45 | AASHIRBAD ENTERPRISE | 5.01 | 3.88 | 62
1347 | Alipurduar Division | Birpara Sub-Division | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000445/2021-2022 | 2754/ALD | 24/02/2022 | 60 | KAJAL KUMAR DE | 34.67 | 19.28 | 45
1348 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000164/2021-2022 | 1305/ALD | 05/10/2021 | 60 | SASANKA ROY | 50.06 | 42.97 | 36
1349 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for CHANDIRJHAR water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000223/2020-2021 | 1174/ALD | 15/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 19.93 | 19.93 | 0
1350 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHANDIRJHAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000317/2021-2022 | 2193/ALD | 11/01/2022 | 90 | DULAL DAS | 21.92 | 8.72 | 100
1351 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Chandirjhar WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000345/2021-2022 | 2138/ALD | 06/01/2022 | 30 | SASANKA ROY | 5.04 | 5.04 | 49
1352 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Chandirjhar WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000346/2021-2022 | 2139/ALD | 06/01/2022 | 30 | SASANKA ROY | 5.04 | 5.04 | 49
1353 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Chandirjhar PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000475/2021-2022 | 2761/ALD | 25/02/2022 | 60 | MATRI ENTERPRISE | 58 | 45.22 | 49
1354 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 1.8 | 0
1355 | Alipurduar Division | Birpara Sub-Division | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000080/2020-2021 | 632/ALD | 03/09/2020 | 90 | HARIDAS GHOSH | 63.58 | 19.14 | 80
1356 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumarhat Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Alipurduar RWS | Birpara Sub Division | ORD/000087/2021-2022 | 983/ALD | 13/09/2021 | 60 | TAPASH DAS | 25.25 | 0 | 97
1357 | Alipurduar Division | Birpara Sub-Division | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 4.16 | 62
1358 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Alipurduar RWS | Birpara Sub Division | ORD/000133/2021-2022 | 1243/ALD | 27/09/2021 | 60 | TAPASH DAS | 25.25 | 11.36 | 78
1359 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000197/2021-2022 | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 23.09 | 85
1360 | Alipurduar Division | Birpara Sub-Division | Providing FHTC connection for AWC, School, Health Centre etc. of Salkumarhat WSS under Alipurduar Division, PHE Dte. Part-C | Alipurduar RWS | Birpara Sub Division | ORD/000263/2021-2022 | 1596/ALD | 22/11/2021 | 30 | DEBABRATA DUTTA | 4.92 | 3.03 | 98
1361 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Salkumarhat PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000479/2021-2022 | 2898/ALD | 08/03/2022 | 1381 | DILIP MAHATO | 48.52 | 6.4 | 65
1362 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline for the 'Jal Sapno' programme and providing FHTC Connection under Chandirjhar WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000164/2021-2022 | 1305/ALD | 05/10/2021 | 60 | SASANKA ROY | 50.06 | 6.75 | 36
1363 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHANDIRJHAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000317/2021-2022 | 2193/ALD | 11/01/2022 | 90 | DULAL DAS | 21.92 | 13.2 | 100
1364 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Chandirjhar PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000475/2021-2022 | 2761/ALD | 25/02/2022 | 60 | MATRI ENTERPRISE | 58 | 0 | 49
1365 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Loknathpur WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000282/2021-2022 | 1851/ALD | 13/12/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 0 | 63
1366 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of LOKNATHPUR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000319/2021-2022 | 2195/ALD | 11/01/2022 | 90 | GOUTAM KUMAR DAS | 20.89 | 0 | 0
1367 | Alipurduar Division | Alipurduar Sadar Sub-Division | Balance work of construction of boundary wall (2nd site) at Loknathpur WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000484/2021-2022 | .2657/ALD | 21/02/2022 | 45 | GOUTAM KUMAR DAS | 4.47 | 0 | 0
1368 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel vehicle maxi cab (at least 7 seater) for Executive Engineer, Alipurduar Division.(01.09.2020 to 31.03.2021) | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000191/2020-2021 | 600/ALD | 31/08/2020 | 212 | APSARI BHOWMICK | 1.25 | 0 | 0
1369 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system of Totpara PWSS by replacing of damaged AC pipeline with UPVC and DI pipeline including interconnection with Bakla Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000227/2021-2022 | 1573/ALD | 22/11/2021 | 120 | HARIDAS GHOSH | 55.38 | 25 | 100
1370 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under BAKLA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000271/2020-2021 | 1283/ALD | 05/01/2021 | 60 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 45.19 | 7.25 | 74
1371 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bakla WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000351/2021-2022 | 2150/ALD | 06/01/2022 | 30 | SHIB RATAN BHOWMIK | 4.99 | 4.99 | 73
1372 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Bakla WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000352/2021-2022 | 2151/ALD | 06/01/2022 | 30 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 5 | 5 | 73
1373 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Bakla PWSS Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000444/2021-2022 | 2753/ALD | 24/02/2022 | 1200 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 43.78 | 34.75 | 43
1374 | Alipurduar Division | Birpara Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1375 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at H/W site including laying distribution system and providing FHTC for MATHURA TG AREA PWSS Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000007/2022-2023 | 17/ALD | 01/04/2022 | 120 | M/S SURAJIT DEY & CO | 246.1 | 148.93 | 69
1376 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for MATHURA TG AREA PWSS Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000012/2022-2023 | 22/ALD | 01/04/2022 | 120 | TAPASH KUMAR BHOWMICK | 246.44 | 231.69 | 65
1377 | Alipurduar Division | Birpara Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Mathura Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000113/2022-2023 | 705/ALD | 08/06/2022 | 30 | SASANKA ROY | 4.79 | 4.79 | 65
1378 | Alipurduar Division | Birpara Sub-Division | Construction of 400cum OHR for Mathura Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000415/2021-2022 | 2583/ALD | 17/02/2022 | 180 | M/S SURAJIT DEY & CO | 77.51 | 58.47 | 63
1379 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 0
1380 | Alipurduar Division | Birpara Sub-Division | Supply of DI Special and CI Jeffy Coupling for Mathura TG Water Supply Scheme (SM/10172) of Alipurduar-I Block under Alipurduar Division P.H.E. Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000513/2023-2024 | 831/ALD | 14/03/2024 | 60 | TAPASH KUMAR BHOWMICK | 11.6 | 10.93 | 50
1381 | Alipurduar Division | Birpara Sub-Division | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Mathura Tea Garden Area Piped Water Supply Scheme (SM-10172) of Alipurduar - I Block under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000536/2023-2024 | 852/ALD | 14/03/2024 | 30 | GUHA ENTERPRISE | 11.62 | 11.62 | 75
1382 | Alipurduar Division | Birpara Sub-Division | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000585/2021-2022 | 1969/ALD | 24/12/2021 | 90 | TAPASH KUMAR BHOWMICK | 0.96 | 0.96 | 64
1383 | Alipurduar Division | Birpara Sub-Division | Entry of data of Functional Household Tap Connection (FHTC under JJM) of PWSS in Website under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000586/2021-2022 | 743/ALD | 11/08/2021 | 90 | TAPASH KUMAR BHOWMICK | 0.96 | 0.96 | 65
1384 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000003/2022-2023 | 395/ALD | 11/05/2022 | 0 | Resource Division | 3.16 | 0 | 0
1385 | Alipurduar Division | Birpara Sub-Division | Dismantling Concrete road and re -casting the same for providing FHTC at different area of BIRPARA (APD) PWSS AND Alipurduar - I Block under Alipurduar Division , PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000078/2022-2023 | 441/ALD | 13/05/2022 | 30 | R.K.CONSTRUCTION | 4.96 | 0 | 71
1386 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline of Birpara PWSS, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000295/2022-2023 | 1686/ALD | 20/09/2022 | 60 | KAMALESH ROY | 5.01 | 0 | 0
1387 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BIRPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000316/2021-2022 | 2192/ALD | 11/01/2022 | 90 | DAS CONSTRUCTION | 22.03 | 8.08 | 65
1388 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC / DI pipeline for filling of Gap in the distribution system and laying of delivery line connection, Land Development works, Construction of surface drain, supply of CIDF specials and other allied works in connection with the Birpara(APD) PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000348/2023-2024 | 2600/ALD | 04/12/2023 | 540 | DAS CONSTRUCTION | 38.1 | 0 | 30
1389 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Birpara PWSS (APD) Under Alipurduar Division, PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000443/2021-2022 | 2751/ALD | 24/02/2022 | 60 | R.K.CONSTRUCTION | 31.74 | 14.75 | 60
1390 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at HEADWORK site of BIRPARA (APD) PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000578/2024-2025 | 5392/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.94 | 0 | 0
1391 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 2nd site of BIRPARA (APD) PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000580/2024-2025 | 5394/ALD | 17/03/2025 | 60 | DAS CONSTRUCTION | 0.79 | 0 | 0
1392 | Alipurduar Division | Birpara Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1393 | Alipurduar Division | Birpara Sub-Division | Laying of DI pipe of Different Dia and other works For TAPSHIKHATA PWSS at Alipurduar -I Block under Alipurduar Division , PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000070/2022-2023 | 435/ALD | 13/05/2022 | 30 | KAMALESH ROY | 4.76 | 0 | 0
1394 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000349/2021-2022 | 2142/ALD | 06/01/2022 | 30 | DEBAJYOTI SUTRADHAR | 5.02 | 5.02 | 52
1395 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1396 | Alipurduar Division | Birpara Sub-Division | Laying of distribution line with HDPE,UPVC and CI/DI pipes, laying of paver block at pump house no-1 and 2 and providing FHTC for Aug. Of Tapshikhata PWSS under Alipurduar Division. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000469/2023-2024 | 675/ALD | 06/03/2024 | 180 | TAPASH DAS | 43.25 | 26.98 | 10
1397 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 2nd TW site of TAPSHIKHATA PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000572/2024-2025 | 5386/ALD | 17/03/2025 | 60 | CHANDAN DAS | 0.78 | 0 | 0
1398 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at HEADWORK site of TAPSHIKHATA PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000577/2024-2025 | 5391/ALD | 17/03/2025 | 60 | CHANDAN DAS | 0.94 | 0 | 0
1399 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000003/2024-2025 | 3608/ALD | 24/10/2024 | 0 | Resource Division | 4.11 | 0 | 0
1400 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of additional HDPE pipeline for Gap filling and providing FHTC at Hoasinbad TG under Hoasinbad PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000068/2025-2026 | 966/ALD | 12/06/2025 | 60 | SASANKA ROY | 26.04 | 0 | 0
1401 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 200 cum OHR as per Departmental Design and drawing in headwork site, Tube well Boring by ODEX-165 method of drilling 2nos. respectively at Headwork site and 2nd Tubewell site, Rising Main and distribution line (Part-1) for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000281/2022-2023 | 1635/ALD | 19/09/2022 | 929 | SASANKA ROY | 96.32 | 75.58 | 95
1402 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 2nos. Pump house, 2nos. Boundary wall at headwork site and 2nd Tubewell site including providing FHTC for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000282/2022-2023 | 1636/ALD | 19/09/2022 | 954 | RATAN DUTTA | 37.7 | 30.66 | 80
1403 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution system (Part-2) and providing FHTC for HOASINBAD TG AREA PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000283/2022-2023 | 1637/ALD | 19/09/2022 | 345 | SASANKA ROY | 81.64 | 75.12 | 92
1404 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation works at head works site for HOASINBAD TG AREA PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000309/2022-2023 | 2133/ALD | 10/11/2022 | 30 | MOYTEC | 0.7 | 0.64 | 0
1405 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of DI and HDPE pipeline, trenchless pipe laying by HDD process, providing FHTC and others for Hossainabad PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000472/2023-2024 | 690/ALD | 07/03/2024 | 270 | SASANKA ROY | 62.82 | 34.23 | 80
1406 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC pipeline including FHTC for KHOARDANGA AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE 2743/ALD DT:24/02/2022 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00599/2023-2024 | 447/23-24/PFMS | 30/03/2024 | 0 | HARIDAS GHOSH | 1.98 | 0 | 0
1407 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of boundary wall, repairing of pump house of 3rd T/W site and interconnection between 2nd and 3rd site by using DI pipe with pillar including supply of CI materials at Narathali Water Supply Scheme under Alipurduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000075/2021-2022 | 881/ALD | 03/09/2021 | 60 | SREE MAA CONSTRUCTION & CO. | 13.19 | 8.13 | 71
1408 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Narathali Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000108/2022-2023 | 700/ALD | 08/06/2022 | 30 | M/S SHIB RATAN BHOWMICK & CO | 4.88 | 4.88 | 70
1409 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of Laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and constructon of boundary wall, toilet and repairing of pump house (2nd site) at Narathali Water Supply Scheme under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000183/2021-2022 | 1312/ALD | 05/10/2021 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 11.97 | 3.92 | 69
1410 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing extension of distribution line, repair of water pipeline in 10/142 booth at Khoardanga 2 G.P from the commissioned NARATHALI PWSS (UID-APD-166) UNDER ALIPURDUAR DIVISION PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000309/2020-2021 | 1483/ALD | 27/01/2021 | 60 | TAPASH DAS | 15.73 | 1.42 | 70
1411 | Alipurduar Division | Alipurduar Sadar Sub-Division | Gap filling in laying distribution system by making culvert crossing and laying of DI and UPVC pipes under Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000317/2022-2023 | 2226/ALD | 21/11/2022 | 45 | MADHAB SAHA | 4.65 | 0 | 0
1412 | Alipurduar Division | Alipurduar Sadar Sub-Division | Gap filling in laying distribution system by making culvert crossing and laying of DI and UPVC pipes under Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000318/2022-2023 | 2227./ALD | 21/11/2022 | 45 | HARI CONSTRUCTION | 3.45 | 0 | 0
1413 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 550cum OHR for Augmentation of Narathali Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000408/2021-2022 | 2524/ALD | 11/02/2022 | 180 | TAPAN CHANDA | 98.12 | 89.52 | 72
1414 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for NARATHALI PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000410/2021-2022 | 2526/ALD | 11/02/2022 | 990 | TAPAN CHANDA | 41.03 | 27.14 | 100
1415 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC pipeline including FHTC for PASCHI NARATHALI MOUZA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000436/2021-2022 | 2742/ALD | 24/02/2022 | 60 | MADHAB SAHA | 87.55 | 78.76 | 71
1416 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC pipeline including FHTC for KHOARDANGA AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000437/2021-2022 | 2743/ALD | 24/02/2022 | 60 | HARIDAS GHOSH | 87.82 | 87.69 | 99
1417 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC pipeline including FHTC for MADHYA NARATHALI AREA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000438/2021-2022 | 2744/ALD | 24/02/2022 | 60 | DAS CONSTRUCTION | 87.58 | 66.41 | 68
1418 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution of UPVC pipeline including FHTC for NARATHALI MOUZA under NARATHALI PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000439/2021-2022 | 2745/ALD | 24/02/2022 | 60 | SASANKA ROY | 87.59 | 78.42 | 70
1419 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of pipeline at PASCHIM NARATHALI by extension of pipeline from Uttar Kamakhyaguri PWSS under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000440/2021-2022 | 2746/ALD | 24/02/2022 | 1020 | AKANSHA COMMERCIAL PRIVATE LTD. | 93.92 | 58.61 | 100
1420 | Alipurduar Division | Alipurduar Sadar Sub-Division | "Collectio of house hold details at prescribrd format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. (for the financial year 2022-2023 from 01/04/2022 onwards)" | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000578/2021-2022 | 3223/ALD | 31/03/2022 | 365 | DILIP MAHATO | 4.96 | 3.06 | 54
1421 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000011/2022-2023 | 716/ALD | 13/06/2022 | 0 | Resource Division | 51.21 | 0 | 0
1422 | Alipurduar Division | Alipurduar RWS Sub-Division | Procurement of Laptop,Tab .Assemble Deskton Printer VC accessories and Other related accessories Tor all Permanent & contractual JE. all Assistant Engineer and Divisional Staff at Alipurduar PHED. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | BILL/00098/2024-2025 | 77/24-25/PFMS | 21/06/2024 | 0 | CYBERNET | 31.34 | 0 | 0
1423 | Alipurduar Division | Alipurduar RWS Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1424 | Alipurduar Division | Alipurduar RWS Sub-Division | Laying HDPE pipeline from Dakshin Sonapur aath mile bazaar to head work site due to widening of NH and providing FHTC at Dakshin Sonapur PWSS Area, Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000003/2023-2024 | 06/ALD | 04/04/2023 | 450 | PINTU SAHA | 46.56 | 46.03 | 80
1425 | Alipurduar Division | Alipurduar RWS Sub-Division | CONSTRUCTION OF PUMP HOUSE & BOUNDARY WALL FOR ADDITIONAL TUBEWELL FOR PROVIDING FHTC AND LAND DEVELOPMENT AT HW SITE & 2ND SITE FOR AUGMENTATION OF DAKSHIN SONAPUR PWSS. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000026/2025-2026 | 435/ALD | 30/04/2025 | 60 | TAPASH DAS | 16.07 | 0 | 0
1426 | Alipurduar Division | Alipurduar RWS Sub-Division | Laying of distribution line with HDPE, UPVC & CI/DI Pipes at Kumarpara & adjoining areas and others allied works for Augmentation of Dakshin Sonapur PWSS within Alipurduar-I Block under Alipurduar Division, PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000055/2025-2026 | 706/ALD | 22/05/2025 | 75 | S.D. PROJECT | 150.21 | 0 | 0
1427 | Alipurduar Division | Alipurduar RWS Sub-Division | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dakshin Sonapur Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000057/2025-2026 | 785/ALD | 30/05/2025 | 30 | DILIP MAHATO (OPC) PRIVATE LIMITED | 11.09 | 0 | 0
1428 | Alipurduar Division | Alipurduar RWS Sub-Division | Extension and replacement of damaged pipeline and providing house connection at Dakshin Sonapur Area under Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000080/2021-2022 | 976/ALD | 13/09/2021 | 60 | MADHAB SAHA | 44.48 | 43.57 | 17
1429 | Alipurduar Division | Alipurduar RWS Sub-Division | Extension and replacement of damaged pipeline and providing house connection at Panchkolguri area under Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000081/2021-2022 | 977/ALD | 13/09/2021 | 1355 | M/S JHA CONSTRUCTION | 43.59 | 40.35 | 60
1430 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-I Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000082/2025-2026 | 1050/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1431 | Alipurduar Division | Alipurduar RWS Sub-Division | Laying of Different Dia pipeline And providing FHTC For Uttar Simlabari and adjoing area under Patlakhowa PWSS at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000121/2022-2023 | 1491/ALD | 05/09/2022 | 766 | SHREE RANISATI ENTERPRISE | 100.02 | 0 | 30
1432 | Alipurduar Division | Alipurduar RWS Sub-Division | Repairing of pump house at 2nd site of Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000205/2025-2026 | 2352/ALD | 10/11/2025 | 60 | DIPAK DAS | 2.29 | 0 | 0
1433 | Alipurduar Division | Alipurduar RWS Sub-Division | Repairing of pump house at headwork site of Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000206/2025-2026 | 2353/ALD | 10/11/2025 | 60 | DIPAK DAS | 2.62 | 0 | 0
1434 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. Part-1 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000261/2022-2023 | 1493/ALD | 05/09/2022 | 945 | MADHAB SAHA | 34.59 | 0 | 27
1435 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. Part-2 | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000262/2022-2023 | 1494/ALD | 05/09/2022 | 1080 | KAJAL KUMAR DE | 34.44 | 0 | 15
1436 | Alipurduar Division | Alipurduar RWS Sub-Division | Construction of 700cum OHR for Augmentation of DAKSHIN SONAPUR Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000263/2022-2023 | 1495/ALD | 05/09/2022 | 1080 | SHREE RANISATI ENTERPRISE | 123.17 | 52.09 | 5
1437 | Alipurduar Division | Alipurduar RWS Sub-Division | Construction of platform for FHTC laying of different dia. UPVC and DI pipe line at Dakshin Sonapur PWSS and adjoining mouzas under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000320/2023-2024 | 2415/ALD | 09/11/2023 | 60 | MADHAB SAHA | 31.16 | 6.37 | 15
1438 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC from existing distribution system as per specification for Augmentation of DAKSHIN SONAPUR PWSS at Uttar Sonapur and adjoining moujas under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000345/2023-2024 | 2546/ALD | 28/11/2023 | 90 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.34 | 0 | 0
1439 | Alipurduar Division | Alipurduar RWS Sub-Division | River crossing for laying DI pipe line, Extension and replacement of damaged pipeline and providing FHTC at Sonapur and surrounding area of Sonapur PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000357/2021-2022 | 2236/ALD | 14/01/2022 | 60 | M/S SIBU DEY AND CO | 38.07 | 34.93 | 91
1440 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC from existing distribution system as per specification for Augmentation of DAKSHIN SONAPUR PWSS at Kumarpara and adjoining moujas under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000360/2023-2024 | 2746/ALD | 14/12/2023 | 60 | KAMALESH ROY | 34 | 0 | 0
1441 | Alipurduar Division | Alipurduar RWS Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at Dakshin Kashigram area under Sonapur PWSS under Alipurduar Division, Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000366/2021-2022 | 2294/ALD | 24/01/2022 | 60 | SASANKA ROY | 50.15 | 47.18 | 18
1442 | Alipurduar Division | Alipurduar RWS Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at Uttar Kashigram area under Sonapur PWSS under Alipurduar Division, Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000367/2021-2022 | 2295/ALD | 24/01/2022 | 60 | NARENDRA BHADANI. | 45.29 | 24.47 | 18
1443 | Alipurduar Division | Alipurduar RWS Sub-Division | Road crossing and laying of different dia pipeline for Dakshin Sonapur WSS under Alipurduar-I Block under Alipurduar Division, P.H.E. Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000397/2022-2023 | 2664/ALD/ | 22/12/2022 | 610 | M/S AMIT KUMAR GUPTA | 31.75 | 28.1 | 88
1444 | Alipurduar Division | Alipurduar RWS Sub-Division | Soil investigation work for Augmentaion of Dakshin Sonapur PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000406/2022-2023 | 2791/ALD | 10/01/2023 | 30 | MOYTEC | 0.95 | 0.95 | 0
1445 | Alipurduar Division | Alipurduar RWS Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1446 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tube Well, Construction of Pump House, Boundary Wall, Laying Of Rising Main, Distribution System for Augmentation of Dakshin Sonapur PWSS under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000480/2022-2023 | 3197/ALD | 27/02/2023 | 900 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 171.88 | 83.31 | 35
1447 | Alipurduar Division | Alipurduar RWS Sub-Division | Continuation of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2024 to 29.02.2024) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000546/2023-2024 | 2907/ALD | 29/12/2023 | 62 | PARITOSH SUTRADHAR | 0.8 | 0.77 | 0
1448 | Alipurduar Division | Alipurduar RWS Sub-Division | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/02/2023 to 30/04/2023) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000567/2022-2023 | 2953/ALD | 24/01/2023 | 90 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 0
1449 | Alipurduar Division | Alipurduar RWS Sub-Division | Reparing of Pump House at 3nd site of DAKSHIN SONAPUR PWSS Under Alipurduar Division PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000574/2024-2025 | 5388/ALD | 17/03/2025 | 60 | CHANDAN DAS | 0.84 | 0 | 0
1450 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 250cum. OHR for Kumargram TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000139/2022-2023 | 976/ALD | 15/07/2022 | 180 | HARIDAS GHOSH | 57.62 | 47.61 | 100
1451 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC at Kumargram WSS under Alipurduar Division, PHE Dte. Part-3 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000146/2022-2023 | 1001/ALD | 15/07/2022 | 30 | DILIP MAHATO | 5.04 | 0 | 0
1452 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 150cum. OHR for KUMARGRAM ZONE-IV Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000147/2022-2023 | 983/ALD | 15/07/2022 | 180 | MATRI ENTERPRISE | 50.41 | 0 | 0
1453 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House Connection (FHTC) at Kumargram WSS under Alipurduar Division, PHE Dte. Part-4 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000148/2022-2023 | 1002/ALD | 15/07/2022 | 30 | DILIP MAHATO | 5.04 | 0 | 43
1454 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House Connection (FHTC) at Kumargram WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000150/2022-2023 | 1003/ALD | 15/07/2022 | 30 | DILIP MAHATO | 5.04 | 0 | 42
1455 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation work at 4 different places of Kumargram within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000156/2022-2023 | 1005/ALD | 15/07/2022 | 30 | MOYTEC | 4.88 | 0 | 0
1456 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for KUMARGRAM TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000205/2022-2023 | 1304/ALD | 22/08/2022 | 120 | GOUTAM KUMAR DAS | 94.63 | 57.55 | 80
1457 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for KUMARGRAM TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000210/2022-2023 | 1305/ALD | 22/08/2022 | 720 | HARIDAS GHOSH | 81.11 | 60.75 | 90
1458 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF special for Kumargram TG Pwss Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000239/2023-2024 | 1608/ALD | 25/08/2023 | 30 | HARI CONSTRUCTION | 7.67 | 7.65 | 95
1459 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for KUMARGRAM TG PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000245/2023-2024 | 1791/ALD | 29/08/2023 | 360 | HARI CONSTRUCTION | 13.16 | 11.1 | 81
1460 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land development, construction of pathway of HWS and culvert crossing with DI pipe under Kumargram TG WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000350/2022-2023 | 2492/ALD | 13/12/2022 | 90 | HARIDAS GHOSH | 12.45 | 12.33 | 43
1461 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000009/2023-2024 | 206/ALD/2023-2024 | 02/05/2023 | 0 | Resource Division | 5.44 | 0 | 0
1462 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000106/2023-2024 | 130/ALD | 10/01/2024 | 0 | Resource Division | 9.2 | 0 | 0
1463 | Alipurduar Division | Birpara Sub-Division | Continuation work order for the work of "Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/5/2024-EE(ALI_D) SEC-DPHE (Computer No-973264)) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick),RWS Falakata Block | ORD/000199/2024-2025 | 1913/ALD | 26/06/2024 | 60 | DILIP MAHATO | 14.57 | 14.37 | 90
1464 | Alipurduar Division | Birpara Sub-Division | Sinking of Rig bore T/W (4nos.) by Reverse Rotary method of drilling, cons. of 100 cum. OHR (2nos), cons. of P/H and B/W, Rising main, distribution line and providing FHTC at H/W and 2nd site inclu. Soil testing for KADAMBINI TG PWSS (ZONE-I and ZONE-II) under Birpara Sub-Division, Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick),RWS Falakata Block | ORD/000430/2022-2023 | 2857/ALD | 17/01/2023 | 874 | DILIP MAHATO | 498.42 | 452.83 | 95
1465 | Alipurduar Division | Birpara Sub-Division | "Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Kadambini TG Water Supply Scheme (SM/13239) of Falakata Block under Alipurduar Division P.H.E. Dte. " | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick),RWS Falakata Block | ORD/000526/2023-2024 | 845/ALD | 14/03/2024 | 30 | MANSAROVAR CASTING | 13.2 | 0 | 0
1466 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick),RWS Falakata Block | RTOR000029/2023-2024 | 1274/ALD | 11/08/2023 | 0 | Resource Division | 34.39 | 0 | 0
1467 | Alipurduar Division | Alipurduar Division | Providing FHTC from existing distribution system as per specification for Paschim Satali PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000261/2023-2024 | 1879/ALD | 07/09/2023 | 270 | SATYABRATA BHATTACHERJEE | 7.02 | 0 | 1
1468 | Alipurduar Division | Alipurduar Division | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL AND SECOND TUBE WELL site including laying distribution system with new HDPE pipeline (Part-B) CONSTRUCTION OF THREE (3) NOS PUMP HOUSES ,providing FHTC and others allied works for PASCHIM SATALI PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000432/2022-2023 | 2859/ALD | 17/01/2023 | 180 | MAHENDRA CHHETRI | 267.57 | 227.68 | 50
1469 | Alipurduar Division | Alipurduar Division | Constructions of 300 Cum OHR as per Departmental Design & drawing including laying distribution system with new HDPE pipeline (Part-A), RISING MAIN, CONSTRUCTION OF THREE(3) NOS OF BOUNDARY WALL, PATHWAY including soil test, providing FHTC and others allied works for PASCHIM SATALI PWSS Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000433/2022-2023 | 2860/ALD | 17/01/2023 | 1082 | DILIP MAHATO | 497.97 | 365.27 | 74
1470 | Alipurduar Division | Alipurduar Division | Balance portion of boundary wall and Gap joint of new HDPE/DI pipeline, and land development of HW Site,1st and 2nd site of Paschim Satali PWSS (Part) Kalchini Block Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000474/2023-2024 | 692/ALD | 07/03/2024 | 509 | DILIP MAHATO | 61.82 | 0 | 45
1471 | Alipurduar Division | Alipurduar Division | Supply of CIDF/CIPE pipes and specials & Sluice Valve for Paschim Satali Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000479/2023-2024 | 697/ALD | 07/03/2024 | 90 | SSPR VALVE MANUFACTURING PVT LTD | 18.08 | 18.08 | 80
1472 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons of PH AND TW Boring by ODEX-165 drilling at HW site and 2nd site , LDS with HDPE P/LINE INCL RM and delivery connection , CONS of 100 Cum OHR along with the Soil investigation works , providing FHTC and others for Jayanti Tea Garden-II PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000132/2023-2024 | 637/ALD | 06/06/2023 | 901 | ACHINTA SAHA | 170.77 | 85.86 | 70
1473 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tubewell boring by ODEX-195 method of drilling including rising main connection, repair & renovation of PH, B/wall and Main building of inspection bungalow including painting works, cons of pathway, surface drain, cons of balance civil works of annex building other allied works at Jayanti Inspection bungalow under Alipurduar Divn, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000327/2023-2024 | 2424/ALD | 10/11/2023 | 90 | TAPASH KUMAR BHOWMICK | 53.99 | 0 | 25
1474 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF/CIPE pipes and specials for Jayanti TG-II Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2023-2024 | 607/ALD | 29/02/2024 | 30 | BARMAN ENTERPRISE | 8.6 | 1.42 | 61
1475 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000108/2023-2024 | 132/ALD | 10/01/2024 | 0 | Resource Division | 3.47 | 0 | 0
1476 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1477 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for TELIPARA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000216/2023-2024 | 1570/ALD | 23/08/2023 | 30 | DHANENDRA SARKAR | 4.32 | 0 | 0
1478 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new additional pipeline opposite flanks of the higher dia UPVC pipeline and to connect the scattered house with the distribution system in view of providing FHTC, Construction of RCC pillars for supporting DI Pipe, trial run and others allied works in connection with the Telipara PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000421/2024-2025 | 4907/ALD | 31/01/2025 | 45 | MATRI ENTERPRISE | 39.9 | 0 | 0
1479 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1480 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of P/H and T/W Boring by ODEX-165 Method of drilling at HW and 2nd site , LDS with UPVC P/L including rising main and delivery connection, Cons. of 200 Cum OHR as per Departmental Design & drawing along with soil investigation works, providing FHTC and others allied works for TELIPARA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000579/2022-2023 | 3640/ALD | 31/03/2023 | 180 | MATRI ENTERPRISE | 225.29 | 167.75 | 85
1481 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000016/2023-2024 | 222/ALD | 03/05/2023 | 0 | Resource Division | 12.68 | 0 | 0
1482 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000048/2024-2025 | 4268/ALD | 13/12/2024 | 0 | Resource Division | 13.19 | 0 | 0
1483 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000050/2023-2024 | 2398/ALD | 08/11/2023 | 0 | Resource Division | 6.34 | 0 | 0
1484 | Alipurduar Division | Alipurduar RWS Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1485 | Alipurduar Division | Alipurduar RWS Sub-Division | Gap filling of distribution line river crossing and other allied works for Kalaberia village under Kalaberia PWSS within Alipurduar-I block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000070/2025-2026 | 968/ALD | 12/06/2025 | 90 | SASANKA ROY | 73.92 | 0 | 0
1486 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC from existing distribution system as per specification for Kalaberia PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000276/2023-2024 | 1890/ALD | 07/09/2023 | 30 | SASANKA ROY | 7.46 | 0 | 0
1487 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR, Laying Of Rising Main, Distribution System including soil test and providing FHTC for Kolaberia PWSS Under Alipurduar Division, PHE Dte | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000560/2022-2023 | 3578/ALD | 27/03/2023 | 900 | SASANKA ROY | 283.27 | 190.14 | 12
1488 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000094/2023-2024 | 118/ALD | 10/01/2024 | 0 | Resource Division | 6.56 | 0 | 0
1489 | Alipurduar Division | Alipurduar RWS Sub-Division | CONSTRUCTION OF PUMP HOUSE & BOUNDARY WALL FOR ADDITIONAL TUBEWELL FOR PROVIDING FHTC AND CONSTRUCTION OF RIVER BANK PROTECTION WALL WITH WIRE CREATE AND FILLING NEAR HWS AT PARARPAR PWSS WITHIN ALIPURDUAR-I BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000025/2025-2026 | 434/ALD | 30/04/2025 | 60 | SASANKA ROY | 21 | 0 | 0
1490 | Alipurduar Division | Alipurduar RWS Sub-Division | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Pararpar Water Supply Scheme TW No.-III (Additional) under NMD-II,PHE.Dte,Alipurduar. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000059/2025-2026 | 787/ALD | 30/05/2025 | 30 | SUBODH KUMAR BANIK | 11.09 | 0 | 0
1491 | Alipurduar Division | Alipurduar RWS Sub-Division | Gap filling of distribution line, land development and others allied works for augmentation of Pararpar PWSS within APD-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000073/2025-2026 | 971/ALD | 12/06/2025 | 90 | SASANKA ROY | 60.73 | 0 | 0
1492 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-I Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000082/2025-2026 | 1050/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1493 | Alipurduar Division | Alipurduar RWS Sub-Division | Sinking of Big dia Tube Well (250 x 200 mm dia) by R.C. drilling for Aug. of Pararpar PWSS within Alipurduar-I Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/14209) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000234/2024-2025 | 2294/ALD | 07/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 20.72 | 0 | 100
1494 | Alipurduar Division | Alipurduar RWS Sub-Division | Providing FHTC from existing distribution system as per specification for Pararpar PWSS PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000275/2023-2024 | 1889/ALD | 07/09/2023 | 30 | INDRAYOODH BHOWAL | 8.26 | 0 | 0
1495 | Alipurduar Division | Alipurduar RWS Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1496 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tube Well, Construction of Pump House, Boundary Wall, OHR (150 cum) including soil testing, Laying Of Rising Main, Distribution System and providing FHTC for Pararpar PWSS Under Alipurduar Division, PHE Dte. (2nd call) | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000510/2022-2023 | 3397/ALD | 16/03/2023 | 900 | SASANKA ROY | 324.42 | 219.59 | 3
1497 | Alipurduar Division | Alipurduar RWS Sub-Division | Gap filling and replacing lower dia pipe and FHTC connection at Pararpar PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000562/2022-2023 | 3505/ALD | 23/03/2023 | 180 | TAPASH DAS | 6.38 | 6.35 | 98
1498 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000038/2024-2025 | 4257/ALD | 13/12/2024 | 0 | Resource Division | 36.71 | 0 | 0
1499 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BHUTNIRGHAT water supply scheme at FALAKATA Block under Alipuduar Division, P.H.E. Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000153/2020-2021 | 865/ALD | 14/10/2020 | 30 | GOUTAM KUMAR DAS | 4.98 | 2.6 | 0
1500 | Alipurduar Division | Birpara Sub-Division | Providing FHTC and other allied works at Munshipara WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000161/2021-2022 | 1303/ALD | 05/10/2021 | 60 | BENGAL YOUTH UN EMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 44.94 | 7.94 | 82
1501 | Alipurduar Division | Birpara Sub-Division | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | Alipurduar RWS | Birpara Sub Division | ORD/000181/2020-2021 | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 9.4 | 97
1502 | Alipurduar Division | Birpara Sub-Division | Laying of DI/UPVC pipeline along with PMGSY Road and other misc. works related to Munshipara PWSS under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000187/2020-2021 | 1012/ALD | 12/11/2020 | 60 | TAPASH DAS | 35.88 | 47.5 | 83
1503 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000196/2021-2022 | 1317/ALD | 05/10/2021 | 1560 | DILIP MAHATO | 58.07 | 39.35 | 85
1504 | Alipurduar Division | Birpara Sub-Division | Providing House connection for Munshipara piped water supply scheme at Alipurduar-I Block under Alipuduar Division, P.H.E. Dte.Part-II | Alipurduar RWS | Birpara Sub Division | ORD/000204/2020-2021 | 1158/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.93 | 27.63 | 82
1505 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar RWS | Birpara Sub Division | ORD/000278/2021-2022 | 1845/ALD | 10/12/2021 | 30 | RATAN DUTTA | 4.35 | 0 | 82
1506 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Munshipara WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar RWS | Birpara Sub Division | ORD/000279/2021-2022 | 1846/ALD | 10/12/2021 | 30 | AASHIRBAD ENTERPRISE | 4.34 | 2.47 | 80
1507 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0.05 | 72
1508 | Alipurduar Division | Birpara Sub-Division | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 30 | DAS ENTERPRISE | 5.02 | 0.21 | 77
1509 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution system with HDPE/DI pipeline, Providing FHTC and others allied works for Chengmari PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000015/2023-2024 | 233/ALD | 04/05/2023 | 270 | HARIDAS GHOSH | 248.85 | 205.79 | 65
1510 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, Laying of distribution system with HDPE pipeline including rising main and delivery connection, Constructions of 200 Cum OHR as per Departmental Design and drawing along with the Soil investigation works, providing FHTC and others allied works for Chengmari PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000055/2023-2024 | 423/ALD | 24/05/2023 | 678 | HARIDAS GHOSH | 240.7 | 143.93 | 85
1511 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new HDPE pipeline for interconnection in the distributation system and bridge/culvert crossing and other allied works in connection with Chengmari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000078/2025-2026 | 976/ALD | 12/06/2025 | 90 | HARI CONSTRUCTION | 49.29 | 0 | 0
1512 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Paschim Chegmari WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000233/2023-2024 | 1597/ALD | 25/08/2023 | 30 | M/S SSB CONSTRUCTION CO. | 6.77 | 0 | 0
1513 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1514 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000014/2024-2025 | 3948/ALD | 26/11/2024 | 0 | Resource Division | 10.47 | 0 | 0
1515 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000050/2024-2025 | 4270/ALD | 13/12/2024 | 0 | Resource Division | 22.34 | 0 | 0
1516 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000052/2023-2024 | 2698/ALD | 12/12/2023 | 0 | Resource Division | 21.43 | 0 | 0
1517 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000100/2023-2024 | 214/ALD | 10/01/2024 | 0 | Resource Division | 10.47 | 0 | 0
1518 | Alipurduar Division | Birpara Sub-Division | Withdrawing & relaying & laying of pipeline and other misc. works for retrofitting of GARGENDA PWSS under Alipurduar Division PHED. | Birpara A.E | Birpara Sub Division | ORD/000092/2020-2021 | 698/ALD | 16/09/2020 | 120 | M/S SSB CONSTRUCTION | 30.51 | 5.88 | 60
1519 | Alipurduar Division | Birpara Sub-Division | Supply of fuel for Diesel Vehicle Maxi Cab(At least 7 seater ) (Preferably TUV) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 08/08/2022 to 31/12/2022) | Birpara A.E | Birpara Sub Division | ORD/000179/2022-2023 | 1185/ALD | 05/08/2022 | 153 | RATAN DUTTA | 1.27 | 0 | 0
1520 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, laying distribution system and providing FHTC for BHUTNIRGHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000379/2021-2022 | 2379/ALD | 31/01/2022 | 90 | DILIP MAHATO | 92.34 | 2.32 | 98
1521 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for GARGENDA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000400/2021-2022 | 2391/ALD | 31/01/2022 | 90 | MITHUN DAS | 27.16 | 25.52 | 100
1522 | Alipurduar Division | Birpara Sub-Division | Construction of 300cum OHR for Augmentation of Jagijhora Barabak Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000414/2021-2022 | 2582/ALD | 17/02/2022 | 180 | ASHIM KUMAR GHOSH | 63.76 | 12.04 | 43
1523 | Alipurduar Division | Birpara Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Birpara A.E | Birpara Sub Division | ORD/000417/2022-2023 | 2732/ALD | 30/12/2022 | 365 | PARITOSH SUTRADHAR | 4.8 | 2.27 | 90
1524 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI pipe line at flank of Asian Highway Road at Jateswar to towards Kazali Bazar under Jateswar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000454/2022-2023 | 2944/ALD | 20/01/2023 | 60 | TAPASH DAS | 16.1 | 4.72 | 95
1525 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 7.5 | 0
1526 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for LOKNATHPUR water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000152/2020-2021 | 864/ALD | 14/10/2020 | 30 | MATARA CONSTRUCTION CO | 4.98 | 9.97 | 0
1527 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Loknathpur WSS under Alipurduar Division, PHE Dte. Part-5 | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000282/2021-2022 | 1851/ALD | 13/12/2021 | 30 | GOUTAM KUMAR DAS | 5.04 | 4.86 | 63
1528 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of boundary wall at 2nd TW site at Loknathpur WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000333/2021-2022 | 2109/ALD | 05/01/2022 | 45 | GOUTAM KUMAR DAS | 4.67 | 4.7 | 62
1529 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the 'Jal Sapna' programme (FHTC for every house hold) under Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000368/2021-2022 | 2296/ALD | 24/01/2022 | 60 | GOUTAM KUMAR DAS | 45.8 | 22.25 | 94
1530 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of distribution pipeline with DI and UPVC pipes for interconnection of Dhaolajhora PWSS with Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000540/2021-2022 | 3192/ALD | 28/03/2022 | 60 | GOUTAM KUMAR DAS | 49.89 | 5.43 | 81
1531 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for CHANDIRJHAR water supply scheme at ALIPURDUAR-II Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000165/2020-2021 | 909/ALD | 16/10/2020 | 30 | SREE MAA CONSTRUCTION & CO. | 4.98 | 9.96 | 0
1532 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection and construction of different dia. sluice valve chamber including supply of CI materials for Jashodanga WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000192/2021-2022 | 1316/ALD | 05/10/2021 | 45 | HARI CONSTRUCTION | 12.88 | 12.83 | 99
1533 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for Jashodanga water supply scheme at Alipurduar -II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000205/2020-2021 | 1159/ALD | 15/12/2020 | 60 | TAPASH KUMAR BHOWMICK | 29.89 | 17.18 | 98
1534 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under JHOSHODANGA PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000272/2020-2021 | 1284/ALD | 05/01/2021 | 60 | MADHAB SAHA | 24.66 | 42.78 | 99
1535 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply delivery & installation of various machineries at Alipurduar Division Office & allied Sub-Division Offices and laboratories under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000303/2021-2022 | 1287/ALD | 01/10/2021 | 15 | MATRI ENTERPRISE | 1.75 | 1.75 | 97
1536 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 18 | 100
1537 | Alipurduar Division | Alipurduar Sadar Sub-Division | Preparation of Augmentation D.P.R after investigation For Bhatibari W/S scheme under Alipurduar Division. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000110/2021-2022 | 913/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.62 | 5.25 | 0
1538 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAMAKHYAGURI water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000149/2020-2021 | 861/ALD | 14/10/2020 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 4.94 | 4.94 | 98
1539 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte. (Part-4) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000162/2021-2022 | 1304/ALD | 05/10/2021 | 60 | DULAL MAJUMDER | 34.38 | 0 | 76
1540 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000167/2021-2022 | 1306/ALD | 05/10/2021 | 60 | GOUTAM KUMAR DAS | 25.34 | 21.65 | 74
1541 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline of Uttar Kamakhyaguri WSS under Alipurduar Division, PHE Dte.(Part-A) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000180/2021-2022 | 1307/ALD | 05/10/2021 | 60 | TAPASH DAS | 25.34 | 17.32 | 76
1542 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for KAMAKHYAGURI water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000209/2020-2021 | 1163/ALD | 15/12/2020 | 60 | TAPASH DAS | 19.94 | 8.85 | 77
1543 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and Providing House Connection of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000226/2021-2022 | 1574/ALD | 22/11/2021 | 60 | M/S PALIT ENTERPRISE | 48.63 | 6.78 | 78
1544 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of Kamakhyaguri PWSS, Kumargram Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000370/2021-2022 | 2289/ALD | 24/01/2022 | 60 | GOUTAM KUMAR DAS | 27.39 | 8.81 | 93
1545 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 400cum OHR for Augmentation of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000412/2021-2022 | 2580/ALD | 17/02/2022 | 180 | DILIP MAHATO | 77.31 | 18.21 | 74
1546 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall and laying distribution system for Uttar Kamkhyaguri Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000424/2021-2022 | 2608/ALD | 17/02/2022 | 90 | GOUTAM KUMAR DAS | 90.8 | 0 | 74
1547 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000196/2021-2022 | 1317/ALD | 05/10/2021 | 1560 | DILIP MAHATO | 58.07 | 0 | 85
1548 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHHOTO SALKUMAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000318/2021-2022 | 2194/ALD | 11/01/2022 | 90 | KAJAL KUMAR DE | 21.92 | 14.23 | 46
1549 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at Chhoto Salkumar WSS under Alipurduar Division, PHE Dte.Part-5 | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000389/2021-2022 | 2303/ALD | 25/01/2022 | 30 | AASHIRBAD ENTERPRISE | 5.03 | 0 | 61
1550 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000397/2021-2022 | 2311/ALD | 25/01/2022 | 45 | AASHIRBAD ENTERPRISE | 5.01 | 0 | 62
1551 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000445/2021-2022 | 2754/ALD | 24/02/2022 | 60 | KAJAL KUMAR DE | 34.67 | 3.29 | 45
1552 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC/DI/MS/CI distribution pipeline for Gap filling of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000577/2021-2022 | 3132/ALD | 25/03/2022 | 30 | PRITAM DAS | 5.04 | 0.82 | 71
1553 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1554 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of FHTCs and withdrawing and relaying a pipeline (125 mm) at Patotola area at 5th site Samuktala PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000052/2025-2026 | 678/ALD | 21/05/2025 | 45 | DULAL DAS | 4.5 | 0 | 0
1555 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply and installation of sign board at different PWSS site of Alipurduar-II Block under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000071/2025-2026 | 969/ALD | 12/06/2025 | 45 | HARI CONSTRUCTION | 4.92 | 0 | 0
1556 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of Pump House no1 at HW site of SAMUKTALA PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000153/2025-2026 | 1590/ALD | 31/07/2025 | 60 | PRITAM DAS | 0.97 | 0 | 0
1557 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway, surface drain and chatal, installation of paver block, land development along with the others allied works at Samuktala Zone-I head work site PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000197/2023-2024 | 1495/ALD | 16/08/2023 | 60 | DIPAK DAS | 13.04 | 5.1 | 25
1558 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 100cum. OHR for SAMUKTALA ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000265/2022-2023 | 1658/ALD | 19/09/2022 | 1140 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 43.9 | 28.97 | 100
1559 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation work at 3 different places of Samuktala within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000266/2022-2023 | 1657/ALD | 19/09/2022 | 30 | ASIS ENTERPRISE | 3.65 | 3.65 | 50
1560 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Boundary wall at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000267/2022-2023 | 1666/ALD | 19/09/2022 | 30 | PRITAM DAS | 4.74 | 4.74 | 47
1561 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Boundary wall at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000268/2022-2023 | 1668/ALD | 19/09/2022 | 270 | ROY & PANDIT CONSTRUCTIONS | 4.76 | 4.71 | 100
1562 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House at 1st TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000269/2022-2023 | 1669/ALD | 19/09/2022 | 60 | KOUSHIK BHOWMICK | 4.77 | 4.77 | 95
1563 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House at 3rd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000270/2022-2023 | 1671/ALD | 19/09/2022 | 60 | SWADESH DEV | 4.75 | 4.65 | 100
1564 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000271/2022-2023 | 1672/ALD | 19/09/2022 | 60 | PROJIT HALDER | 4.77 | 0 | 0
1565 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House at 5th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000272/2022-2023 | 1673/ALD | 19/09/2022 | 60 | CHITTA RANJAN DEY | 4.75 | 4.7 | 100
1566 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Boundary wall at 4th TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000273/2022-2023 | 1667/ALD | 19/09/2022 | 45 | DHANENDRA SARKAR | 4.77 | 4.74 | 100
1567 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 400cum OHR for SAMUKTALA ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000274/2022-2023 | 1659/ALD | 19/09/2022 | 180 | DILIP MAHATO | 77.32 | 77.29 | 100
1568 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 350cum OHR for SAMUKTALA ZONE-II Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000275/2022-2023 | 1661/ALD | 19/09/2022 | 180 | MATARA CONSTRUCTION CO | 71.41 | 69.83 | 100
1569 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000276/2022-2023 | 1662/ALD | 19/09/2022 | 180 | M/S SSB CONSTRUCTION CO. | 100.42 | 92.48 | 48
1570 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe of SAMUKTALA ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000277/2022-2023 | 1663/ALD | 19/09/2022 | 180 | MATARA CONSTRUCTION CO | 101.06 | 92.43 | 100
1571 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Samuktala Bazar Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000278/2022-2023 | 1664/ALD | 19/09/2022 | 180 | DILIP MAHATO | 100.58 | 92.15 | 46
1572 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe of Baniadabri and Garokhota Area under SAMUKTALA WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000279/2022-2023 | 1665/ALD | 19/09/2022 | 180 | GOUTAM KUMAR DAS | 101.2 | 95.1 | 47
1573 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution pipeline with UPVC pipe of Samuktala Zone-III Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000280/2022-2023 | 1660/ALD | 19/09/2022 | 60 | LONGLAST PIPES (INDIA)PVT.LTD. | 97.26 | 95.08 | 50
1574 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of boundary wall (remaining portion) at Headwork site under Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000289/2023-2024 | 1903/ALD | 07/09/2023 | 360 | SWAPAN MALAKAR | 6 | 5.93 | 100
1575 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House at 2nd TW site of Samuktalata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000293/2022-2023 | 1670/ALD | 19/09/2022 | 60 | M/S SADHAN SAHA & CO. | 4.76 | 4.6 | 100
1576 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-165 Method of drilling, Construction of Pump House, Boundary wall at proposed 6th site of SAMUKTALA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000324/2023-2024 | 2421/ALD | 09/11/2023 | 360 | DULAL DAS | 17.57 | 17.48 | 100
1577 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. Of pathway, surface drain and chatal, Installation of Paver block, land development along with the other allied works at Samuktala Zone-II H/W, 2nd site and 3rd Tube well Site under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000333/2023-2024 | 2519/ALD | 24/11/2023 | 60 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 23.26 | 0 | 0
1578 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main and delivery line connection, construction of boundary wall at headwork site of Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000340/2023-2024 | 2541/ALD | 28/11/2023 | 360 | DIPAK DAS | 28.74 | 18.77 | 100
1579 | Alipurduar Division | Alipurduar Sadar Sub-Division | 5 nos Tube well boring by ODEX - 165 Method of drilling for the works of augmentation of SAMUKTALA PWSS under Alipurduar Division ,PHE Dte | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000342/2022-2023 | 2221/ALD | 21/11/2022 | 30 | S.G. CONSTRUCTION | 32.14 | 25.17 | 50
1580 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing in connection with the FHTC, fixing of FHTC by means of PCC concrete block fixing of FHTC by mean of PCC concrete block at Samuktalata Zone-II PWSS under Alipurduar Division, PHE Dte. (SM/12561) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000352/2024-2025 | 3422/ALD | 26/09/2024 | 240 | KAMALESH ROY | 75.37 | 0 | 0
1581 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000355/2022-2023 | 2500/ALD | 13/12/2022 | 120 | TAPASH KUMAR BHOWMICK | 88.46 | 80.56 | 50
1582 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new UPVC pipeline, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000356/2022-2023 | 2501/ALD | 13/12/2022 | 120 | MADHAB SAHA | 93.21 | 81.56 | 49
1583 | Alipurduar Division | Alipurduar Sadar Sub-Division | Fabrication,Erection of Signage (127 nos) of Pump house/OHR site democration with in Alipurduar-I Block for Different PWSS of JJM Project Under Alipurduar Division P.H.E.Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000356/2024-2025 | 3443/ALD | 27/09/2024 | 15 | M/S SARKAR & CO | 13.95 | 13.73 | 100
1584 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for interconnection in the distribution system and bridge/culvert crossing in connection with the FHTC, fixing of FHTC by means of PCC concrete block fixing of FHTC by mean of PCC concrete block at Samuktalata Zone-III PWSS under Alipurduar Division, PHE Dte. (SM/12561) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000380/2024-2025 | 3774/ALD | 13/11/2024 | 90 | DAS CONSTRUCTION | 60.38 | 0 | 0
1585 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and others allied works for Samuktala Zone-II PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000393/2022-2023 | 2658/ALD | 22/12/2022 | 900 | HARIDAS GHOSH | 88.71 | 80.24 | 48
1586 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution system with new UPVC/DI pipeline along with rising and delivery line connection, providing FHTC and other allied works for Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000394/2022-2023 | 2659/ALD | 22/12/2022 | 120 | ESCON INDIA | 90.53 | 50.31 | 50
1587 | Alipurduar Division | Alipurduar Sadar Sub-Division | Interconnection of distribution system by laying of DI and HDPE pipes along with bridge/culvert crossing and other allied works at Shrinathpur TG Adjacent to Samuktala PWSS (Zone-I) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000462/2024-2025 | 5288/ALD | 07/03/2025 | 60 | DEBAJYOTI SUTRADHAR | 18.28 | 0 | 0
1588 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1589 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Samuktala Water Supply Scheme under Alipurduar Division P.H.E. Dte. (SM/12561) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000467/2023-2024 | 673/ALD | 06/03/2024 | 30 | BHAGWATI BHUJEL | 11.36 | 11.34 | 15
1590 | Alipurduar Division | Alipurduar Sadar Sub-Division | Land development works at headwork site and laying of new UPVC/DI pipeline for filling gap in distribution system Samuktala Zone-III PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000488/2022-2023 | 3320/ALD | 13/03/2023 | 60 | BHAGWATI BHUJEL | 9.19 | 9.15 | 100
1591 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC pipeline for filling of Gap in distribution system Samuktala Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000489/2022-2023 | 3321/ALD | 13/03/2023 | 60 | CHANDAN KIRTONIA | 5.37 | 5.37 | 0
1592 | Alipurduar Division | Alipurduar Sadar Sub-Division | Repairing of HW Site Boundary Wall (15M) Samuktala WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000556/2022-2023 | 3501/ALD | 23/03/2023 | 120 | PROGRESSIVE UNEMPLOYED CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 2.14 | 1.8 | 100
1593 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House no 2 at HW site of SAMUKTALA PWSS Under Alipurduar Division PHE DTE.(2nd call) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000611/2024-2025 | 5601/ALD | 27/03/2025 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.96 | 0 | 0
1594 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC pipeline at opposite flank of Higher dia in the distribution system and const. of culvert at front of HW site at Kayakhata PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000077/2025-2026 | 975/ALD | 12/06/2025 | 90 | HARI CONSTRUCTION | 22.06 | 0 | 0
1595 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1596 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Kayakhata WSS Under Alipurduar Division P.H.E Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000240/2023-2024 | 1775/ALD | 28/08/2023 | 30 | HARI CONSTRUCTION | 6.76 | 6.76 | 100
1597 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for KAYAKHATA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000242/2023-2024 | 1788/ALD | 29/08/2023 | 60 | HARI CONSTRUCTION | 11.22 | 0 | 0
1598 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1599 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIPE Special & CI Jeffy Coupling for Kayakhata Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000480/2023-2024 | 698/ALD | 07/03/2024 | 30 | HARI CONSTRUCTION | 15.33 | 15.33 | 85
1600 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of pump house and Sinking of 250 mm x 200 mm X 150 mtr. big dia. TW at HW site and 2nd site, LDS with UPVC pipeline, Cons. of 200 cum OHR as per Departmental Design & drawing including soil investigation works, providing FHTC and others allied works for KAYAKHATA PWSS Under Alipurduar Division PHE DTE. (2nd call) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000514/2022-2023 | 3395/ALD | 16/03/2023 | 1022 | GOUTAM KUMAR DAS | 316.2 | 243.76 | 43
1601 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000040/2022-2023 | 3048/ALD | 08/02/2023 | 0 | Resource Division | 29.21 | 0 | 0
1602 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000054/2024-2025 | 4274/ALD | 13/12/2024 | 0 | Resource Division | 11.82 | 0 | 0
1603 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000116/2023-2024 | 140/ALD | 10/01/2024 | 0 | Resource Division | 9.76 | 0 | 0
1604 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for PAKRIGURI PWSSunder Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000212/2023-2024 | 1566/ALD | 23/08/2023 | 30 | SREE MAA CONSTRUCTION | 3.43 | 0 | 15
1605 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF Specials & Jeffy Coupling for Pakriguri (SM/14223) under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000399/2024-2025 | 4265/ALD | 13/12/2024 | 60 | BARMAN ENTERPRISE | 19.64 | 3.38 | 51
1606 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pumphouse & boundary wall for 3rd site, laying of distribution system with UPVC and DI pipeline, providing FHTC, Rising main and other allied works for Pakriguri PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000422/2024-2025 | 4906/ALD | 31/01/2025 | 90 | DEBAJYOTI SUTRADHAR | 23.9 | 0 | 0
1607 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1608 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons of PH and Sinking of 250 mm x 200 mm X 150 mtr Big dia TW at HW site , 2nd site and 3rd TW site LDS with UPVC p/line , cons of 100 Cum OHR incl the Soil investigation works providing FHTC and others allied works for Pakriguri PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000576/2022-2023 | 3637/ALD | 31/03/2023 | 900 | DEBAJYOTI SUTRADHAR | 183.6 | 136.16 | 65
1609 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000015/2023-2024 | 221/ALD | 03/05/2023 | 0 | Resource Division | 9.77 | 0 | 0
1610 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000029/2024-2025 | 3987/ALD | 27/11/2024 | 0 | Resource Division | 3.71 | 0 | 0
1611 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000049/2024-2025 | 4269/ALD | 13/12/2024 | 0 | Resource Division | 25.24 | 0 | 0
1612 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000098/2023-2024 | 122/ALD | 10/01/2024 | 0 | Resource Division | 3.71 | 0 | 0
1613 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline (new and Parallel ) at Malsagaon PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000134/2025-2026 | 1625/ALD | 04/08/2025 | 75 | DILIP MAHATO | 65.97 | 0 | 0
1614 | Alipurduar Division | Birpara Sub-Division | Construction of tubewells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site, soil investigation at HW site, constructions of 350 Cum OHR at HW, construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Malsagaon PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000252/2023-2024 | 1874/ALD | 07/09/2023 | 991 | DILIP MAHATO | 517.3 | 494.44 | 90
1615 | Alipurduar Division | Birpara Sub-Division | Rising Main, Laying of DI (K7), gap filling of HDPE pipe, construction of sluice valve chamber for washout purpose in the command area of Malsagaon PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000341/2023-2024 | 2542/ALD | 28/11/2023 | 90 | BHAGWATI BHUJEL | 76.02 | 76 | 100
1616 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000066/2023-2024 | 2776/ALD | 18/12/2023 | 0 | Resource Division | 9.12 | 0 | 0
1617 | Alipurduar Division | Birpara Sub-Division | Construction of tube wells (2 nos.) by Reverse rotary method of drilling at HW site and 2nd TW site , soil investigation at OHR site, constructions of 400 Cum OHR at HW , construction of pump house and boundary wall at H/W and 2nd site, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Bengkandi PWSS Under Birpara Subdivision, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000178/2023-2024 | 1114/ALD | 28/07/2023 | 793 | M/S ELITE CONSTRUCTION | 655.41 | 402.25 | 51
1618 | Alipurduar Division | Birpara Sub-Division | Laying of different dia. HDPE Pipe line and other allied works in connection with Jal Jeevan Mission for Bengkandi PWSS under Alipurduar Division, PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000424/2024-2025 | 4948/ALD | 06/02/2025 | 90 | M/S ELITE CONSTRUCTION | 106.35 | 0 | 0
1619 | Alipurduar Division | Birpara Sub-Division | Supply of CI Sluice Valve and Special & CI Jeffy Coupling for Benkandi Water Supply Scheme under Alipurduar Division P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000541/2023-2024 | 754/ALD | 12/03/2024 | 90 | SSPR VALVE MANUFACTURING PVT LTD | 12.88 | 12.88 | 15
1620 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000043/2023-2024 | 1482/ALD | 16/08/2023 | 0 | Resource Division | 21.99 | 0 | 0
1621 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000053/2023-2024 | 2699/ALD | 12/12/2023 | 0 | Resource Division | 68.94 | 0 | 0
1622 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000069/2023-2024 | 2782/ALD | 18/12/2023 | 0 | Resource Division | 12.78 | 0 | 0
1623 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of pump house and Tube well Boring by ODEX-165 Method of drilling at HW site and 2nd site, LDS with HDPE pipeline including rising main and delivery connection, Cons. of 100 Cum OHR as per Dept. Design and drawing along with the Soil investigation works, providing FHTC and other allied works for Purba Majherdabri TG PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000050/2023-2024 | 406/ALD | 22/05/2023 | 680 | DAS CONSTRUCTION | 212.4 | 155.27 | 35
1624 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of DIDF Pipes and DI Special and CI Jeffy Coupling for Purba Majherdabri TG Water Supply Scheme (SM/18157) of Alipurduar-II Block under Alipurduar Division P.H.E. Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000217/2024-2025 | 2069/ALD | 12/07/2024 | 30 | GUHA ENTERPRISE | 8.02 | 8.02 | 100
1625 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | RTOR000023/2024-2025 | 39818/ALD | 27/11/2024 | 0 | Resource Division | 9.47 | 0 | 0
1626 | Alipurduar Division |  | Soil investigation work at 3 different places of Dalimpur within Alipurduar District under Alipurduar Division PHE Dte. |  |  | ORD/000160/2023-2024 | 965/ALD | 12/07/2023 | 30 | CITY ENGINEERING & TESTING LABORATORY | 3.67 | 3.67 | 100
1627 | Alipurduar Division |  | Construction of 400cum OHR for DALIMPUR ZONE-I Water Supply Scheme under Alipurduar Division, PHE Dte. |  |  | ORD/000161/2023-2024 | 968/ALD | 12/07/2023 | 360 | NARAYAN CHANDRA SAHA | 77.28 | 28.26 | 60
1628 | Alipurduar Division |  | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Dalimpur PWSS under Alipurduar Division, PHE Dte. Part-3 |  |  | ORD/000162/2023-2024 | 966/ALD | 12/07/2023 | 180 | TAPASH DAS | 34.77 | 4.52 | 15
1629 | Alipurduar Division |  | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site for Dalimpur Zone-III PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000164/2023-2024 | 967/ALD | 12/07/2023 | 750 | NARENDRA BHADANI. | 45.9 | 44.65 | 100
1630 | Alipurduar Division |  | Laying of distribution of UPVC/DI/GI pipeline including FHTC for DALIMPUR PWSS under Alipurduar Division, PHE DTE. PART-2 |  |  | ORD/000165/2023-2024 | 970/ALD | 12/07/2023 | 480 | MITHUN DAS | 67.93 | 63.74 | 65
1631 | Alipurduar Division |  | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of office godown for Dalimpur Zone-I PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000167/2023-2024 | 973/ALD | 12/07/2023 | 360 | NARAYAN CHANDRA SAHA | 48.31 | 48.23 | 65
1632 | Alipurduar Division |  | Construction of 150cum. OHR for DALIMPUR ZONE-III Water Supply Scheme under Alipurduar Division, PHE Dte. |  |  | ORD/000169/2023-2024 | 972/ALD | 12/07/2023 | 360 | UJJWAL ROY | 50.43 | 40.91 | 100
1633 | Alipurduar Division |  | Providing FHTC from existing distribution system as per specification for DALIMPUR PWSS under Alipurduar Division, PHE Dte. |  |  | ORD/000287/2023-2024 | 1995/ALD | 15/09/2023 | 780 | SREE MAA CONSTRUCTION | 28.8 | 9.96 | 45
1634 | Alipurduar Division |  | Laying of Rising Main, road and culvert crossing and distribution pipeline in DALIMPUR PWSS (Zone-III) under Alipurduar Division, PHE Dte |  |  | ORD/000319/2023-2024 | 2411/ALD | 09/11/2023 | 240 | NARENDRA BHADANI. | 17.66 | 16.47 | 10
1635 | Alipurduar Division |  | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-A) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. |  |  | ORD/000401/2024-2025 | 4537/ALD | 26/12/2024 | 120 | HITANGSHU CHOUDHURY | 55.82 | 0 | 80
1636 | Alipurduar Division |  | LAYING OF DISTRIBUTION PIPELINE AT DALIMPUR (ZONE-II, PART-B) PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. |  |  | ORD/000452/2024-2025 | 5169/ALD | 25/02/2025 | 240 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 55.35 | 0 | 10
1637 | Alipurduar Division |  | Construction of tubewells (2 nos.) by Reverse rotary method of drilling, constructions of 150 Cum OHR at HW, Cons. of pump house and Boundary wall at HW site and 2nd site, Laying of rising main, part of distribution line and providing FHTC for Dalimpur zone-II under Birpara Sub-division, Alipurduar Division of North Bengal Circle-I, PHE DTE. |  |  | ORD/000454/2023-2024 | 366/ALD | 31/01/2024 | 426 | HARIDAS GHOSH | 199.7 | 117.92 | 80
1638 | Alipurduar Division |  | Laying of rising Main,Road and Calvert crossing and Balance distribution pipeline in Dalimpur(Zone-I) under Alipurduar Division,PHE Dte of North Bengal Circle-I, PHE Dte. under JJM Programme. |  |  | ORD/000466/2023-2024 | 670/ALD | 06/03/2024 | 300 | UJJWAL ROY | 132.1 | 121.02 | 80
1639 | Alipurduar Division |  | Balance work of rising main, delivery main, bypass arrangement, land development, pipeline for left out household connection and other allied works at Augmentation of Dalimpur(Zone-3)(H/W site) of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/18254) |  |  | ORD/000502/2023-2024 | 820/ALD | 14/03/2024 | 480 | UJJWAL ROY | 41.61 | 0 | 40
1640 | Alipurduar Division |  | Road crossing, hume pipe culvert crossing, and bridge crossing by G.I. pipe at Dalimpur Zone-III PWSS including Laying of UPVC Pipeline for left out household connection of Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. (SM/18254) |  |  | ORD/000512/2023-2024 | 830/ALD | 14/03/2024 | 60 | MITHUN DAS | 9.04 | 8.79 | 10
1641 | Alipurduar Division |  | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 3947/ALD | 26/11/2024 | 0 | Resource Division | 25.05 | 0 | 0
1642 | Alipurduar Division | Birpara Sub-Division | Construction of balance portion of boundary wall at CWR site under LANKAPARA (TULSHIPARA TG ) WSS under Alipurduar Division PHE Dte . | Birpara A.E | Birpara Sub Division | ORD/000084/2022-2023 | 448/ALD | 13/05/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.91 | 0 | 97
1643 | Alipurduar Division | Birpara Sub-Division | Sinking of Rig Bore Tube well by Odex-165 method of drilling and installation of Raising Main and laying of DI/MS/HDPE pipe line for the Tulshipara and Lankapara Water Supply Scheme. | Birpara A.E | Birpara Sub Division | ORD/000181/2020-2021 | 1006/ALD | 12/11/2020 | 60 | UMWELT ENGINEER PVT. LTD. | 32.34 | 3.86 | 97
1644 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE/DI pipe line at different area of flank of Lankapara road/village road and Lankapara Bazar Area under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000182/2020-2021 | 1007/ALD | 12/11/2020 | 60 | MADHAB SAHA | 33.79 | 13.57 | 99
1645 | Alipurduar Division | Birpara Sub-Division | PROVIDING HOUSE CONNECTION FOR DIMDIMA Z-I PWSS AT MADARIHAT-BIRPARA BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. PART-2 | Birpara A.E | Birpara Sub Division | ORD/000194/2020-2021 | 1025/ALD | 18/11/2020 | 60 | DILIP MAHATO | 28.87 | 22.95 | 0
1646 | Alipurduar Division | Birpara Sub-Division | Sinking of 1no. Tube Well for replacement and another 1no. new Tube Well near factory line by ODEX-195 method of drilling at Lankapara Water Supply Scheme under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000205/2021-2022 | 1345/ALD | 08/10/2021 | 30 | SASANKA ROY | 33 | 0 | 96
1647 | Alipurduar Division | Birpara Sub-Division | Development of rig Bore TW by ODEX-165 method of drilling at Lankapara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000261/2021-2022 | 1608/ALD | 22/11/2021 | 20 | DILIP MAHATO | 0.66 | 0 | 99
1648 | Alipurduar Division | Birpara Sub-Division | Laying of DI/MS/HDPE Distribution pipe line for the LANKAPARA WSS (TULSHIPARA TG) under Alipurduar Division, PHE Dte. Dist-Alipurduar. | Birpara A.E | Birpara Sub Division | ORD/000268/2020-2021 | 1280/ALD | 05/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 30.9 | 22.49 | 98
1649 | Alipurduar Division | Birpara Sub-Division | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-1 | Birpara A.E | Birpara Sub Division | ORD/000317/2020-2021 | 1449/ALD | 25/01/2021 | 45 | MAHENDRA CHHETRI | 43.86 | 7.27 | 67
1650 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for PURBA CHEPANI water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000211/2020-2021 | 1165/ALD | 15/12/2020 | 60 | TAPAN CHANDA | 23.9 | 23.9 | 94
1651 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for PURBA CHEPANI water supply scheme at Alipurduar-II Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000215/2020-2021 | 1166/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 23.91 | 23.91 | 95
1652 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 0 | 94
1653 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Simlabari area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000078/2021-2022 | 876/ALD | 03/09/2021 | 60 | M/S AMIT KUMAR GUPTA | 35.43 | 25.8 | 75
1654 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline including new FHTC under Dakshin Chakoakhati mouza (Sonapur area) at Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000079/2021-2022 | 877/ALD | 03/09/2021 | 60 | M/S STAR INDIA CONSTRUCTION | 33.42 | 0 | 73
1655 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying of UPVC and DI pipeline due to damaged during bitumen road construction and other misc works at Tapshikhata PWSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000146/2020-2021 | 941/ALD | 19/10/2020 | 60 | KAMALESH ROY | 10.81 | 0 | 77
1656 | Alipurduar Division | Birpara Sub-Division | Providing extension of distribution line, AT TAPSHIKATHA G.P from the commissioned TAPSHIKATHA PWSS (UID-APD-022) UNDER ALIPURDUAR DIVISION PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000308/2020-2021 | 1481/ALD | 27/01/2021 | 60 | KAMALESH ROY | 12.16 | 2.26 | 76
1657 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of TAPSHIKHATA Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS | Birpara Sub Division | ORD/000321/2021-2022 | 2197/ALD | 11/01/2022 | 1116 | DEBABRATA DUTTA | 21.58 | 4.43 | 69
1658 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna at Tapshikhata WSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar RWS | Birpara Sub Division | ORD/000350/2021-2022 | 2143/ALD | 06/01/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 5.03 | 0 | 76
1659 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at surrounding area of North side of Pukuritola area under Tapshikatha PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000369/2021-2022 | 2292/ALD | 24/01/2022 | 60 | DEBAJYOTI SUTRADHAR | 26.52 | 24.9 | 78
1660 | Alipurduar Division | Birpara Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Tapshikhata PWSS Under Alipurduar Division, PHE DTE. | Alipurduar RWS | Birpara Sub Division | ORD/000442/2021-2022 | 2750/ALD | 24/02/2022 | 60 | AMBITIOUS ENTERPRISE | 36.94 | 4.68 | 68
1661 | Alipurduar Division | Alipurduar Sadar Sub-Division | New Laying of UPVC/DI pipeline, Providing FHTC and other allied works for Augmentation of Purba Chepani PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000193/2022-2023 | 1220/ALD | 10/08/2022 | 60 | SREE MAA CONSTRUCTION | 21.55 | 11.07 | 94
1662 | Alipurduar Division | Alipurduar Sadar Sub-Division | Retrofitting of pipeline etc. for the "Jal Swapno" Programme (FHTC for every house hold) under PURBA CHEPANI PWSS, Block- Alipurduar-II, Dist-Alipurduar. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000269/2020-2021 | 1281/ALD | 05/01/2021 | 60 | MATRI ENTERPRISE | 37.84 | 15.88 | 94
1663 | Alipurduar Division | Alipurduar Sadar Sub-Division | Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte.(from 01.01.2023 to 31.12.2023) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000415/2022-2023 | 2730/ALD | 30/12/2022 | 365 | MATRI ENTERPRISE | 4.8 | 4.76 | 10
1664 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 40 | 100
1665 | Alipurduar Division | Birpara Sub-Division | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000080/2020-2021 | 632/ALD | 03/09/2020 | 90 | HARIDAS GHOSH | 63.58 | 0 | 80
1666 | Alipurduar Division | Birpara Sub-Division | Repairing & renovation of Pump House, Pathway, Boundary wall (2nd site) & laying DI Pipe line at Salkumarhat WSS under Alipurduar Division PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000099/2021-2022 | 898/ALD | 03/09/2021 | 45 | TAPASH DAS | 4.82 | 0 | 62
1667 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC & Di Pipe , with providing FHTC Connection for the Salkumar Water Supply Scheme Under Alipurduar Division PHE DTE (PART-A) | Birpara A.E | RWS Falakata Block | ORD/000133/2021-2022 | 1243/ALD | 27/09/2021 | 60 | TAPASH DAS | 25.25 | 4.11 | 78
1668 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar and Munshipara Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000196/2021-2022 | 1317/ALD | 05/10/2021 | 1560 | DILIP MAHATO | 58.07 | 0 | 85
1669 | Alipurduar Division | Birpara Sub-Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000197/2021-2022 | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 3.16 | 85
1670 | Alipurduar Division | Birpara Sub-Division | Providing House connection for CHOTO SALKUMAR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | Birpara A.E | RWS Falakata Block | ORD/000218/2020-2021 | 1169/ALD | 15/12/2020 | 60 | SASANKA ROY | 29.9 | 5.13 | 70
1671 | Alipurduar Division | Birpara Sub-Division | Withdrawing and relaying and laying of UPVC/DI/MS/CI Distribution pipe line for retrofitting and providing functional household tap connection (FHTC) in connection with Jaldhara Jal Sapno of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000298/2020-2021 | 1378/ALD | 19/01/2021 | 45 | M/S PALIT ENTERPRISE | 43.75 | 0 | 68
1672 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of CHHOTO SALKUMAR Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Birpara A.E | RWS Falakata Block | ORD/000318/2021-2022 | 2194/ALD | 11/01/2022 | 90 | KAJAL KUMAR DE | 21.92 | 5.65 | 46
1673 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at Chhoto Salkumar WSS under Alipurduar Division, PHE Dte.Part-5 | Birpara A.E | RWS Falakata Block | ORD/000389/2021-2022 | 2303/ALD | 25/01/2022 | 30 | AASHIRBAD ENTERPRISE | 5.03 | 3.99 | 61
1674 | Alipurduar Division | Birpara Sub-Division | Laying distribution line of UPVC and providing FHTC connection for Chhoto Salkumar Water Supply Scheme Area under Alipurduar Division, P.H.E. Dte. | Birpara A.E | RWS Falakata Block | ORD/000397/2021-2022 | 2311/ALD | 25/01/2022 | 45 | AASHIRBAD ENTERPRISE | 5.01 | 0 | 62
1675 | Alipurduar Division | Birpara Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 20 | 100
1676 | Alipurduar Division | Birpara Sub-Division | Providing FHTC at surrounding area of Chhoto Salkumar Under Alipurduar Division, PHE DTE. | Birpara A.E | RWS Falakata Block | ORD/000445/2021-2022 | 2754/ALD | 24/02/2022 | 60 | KAJAL KUMAR DE | 34.67 | 0.03 | 45
1677 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 10 | 0
1678 | Alipurduar Division | Birpara Sub-Division | Laying of UPVC/DI/MS/CI distribution pipeline for Gap filling of Chhoto Salkumar PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | RWS Falakata Block | ORD/000577/2021-2022 | 3132/ALD | 25/03/2022 | 30 | PRITAM DAS | 5.04 | 4.19 | 71
1679 | Alipurduar Division | Alipurduar Division | Extension of pipeline from Santali TG connection line to upper line of Madhu TG area (booster line) under Hasimara TG PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000024/2022-2023 | 19/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 12.61 | 8.47 | 49
1680 | Alipurduar Division | Alipurduar Division | Extension of pipeline from Malangi TW to Bharnobari TG area (booster line) under Hasimara PWSS at Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000025/2022-2023 | 20/ALD | 01/04/2022 | 60 | AASHIRBAD ENTERPRISE | 14.64 | 11.92 | 50
1681 | Alipurduar Division | Alipurduar Division | PROVIDNG HOUSE CONNECTION FOR BHARNOBARI TG AREA NEAR DALSINGPARA AT KALCHINI BLOCK UNDER ALIPURDUAR DIVISION, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000034/2021-2022 | 582/ALD | 15/07/2021 | 30 | M/S BHOWMICK CONSTRUCTION | 20.03 | 20.03 | 96
1682 | Alipurduar Division | Alipurduar Division | Providing FHTC for Bharnobari / Santali TG area including supply of CI materials and other misc. works under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000073/2021-2022 | 880/ALD | 03/09/2021 | 60 | SOUVIK ROY PALADHI | 30.69 | 19.4 | 95
1683 | Alipurduar Division | Alipurduar Division | Construction of valve chamber, dismantling concrete road and other misc works at Malangi TG area within Hasimara W/S/S under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000077/2022-2023 | 442/ALD | 13/05/2022 | 30 | MADHAB SAHA | 4.9 | 4.55 | 49
1684 | Alipurduar Division | Alipurduar Division | Supply of CIPE Special & CI Jeffy Coupling for Augmentation of Hasimara Water Supply Scheme under Alipurduar Division P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000111/2022-2023 | 703/ALD | 08/06/2022 | 30 | MADHAB SAHA | 4.84 | 4.84 | 50
1685 | Alipurduar Division | Alipurduar Division | Extension of pipeline to Bharnabari TG area under Hasimara PWSS for providing at Kalchini Block under Alipurduar Division, P.H.E. Dte.(Part-A) | HQ-A.E | RWS Kalchini Block | ORD/000122/2020-2021 | 794/ALD | 01/10/2020 | 60 | TAPASH KUMAR BHOWMICK | 40.85 | 17.5 | 98
1686 | Alipurduar Division | Alipurduar Division | Providing House connection for BAROBISHA ZONE- III water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000148/2020-2021 | 860/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 2.15 | 79
1687 | Alipurduar Division | Alipurduar Division | Laying Distribution line of UPVC and DI with providing FHTC Connection for the Salkumar Water Supply Scheme Area under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000197/2021-2022 | 1318/ALD | 05/10/2021 | 60 | TAPASH KUMAR BHOWMICK | 35.38 | 5.13 | 85
1688 | Alipurduar Division | Alipurduar Division | Construction of Culvert at Hasimara WSS Head Work Site within Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000264/2021-2022 | 1597/ALD | 22/11/2021 | 45 | ALATYA CONSTRUCTION & CO. | 4.92 | 4.54 | 98
1689 | Alipurduar Division | Alipurduar Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of HASIMARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000294/2021-2022 | 1992/ALD | 27/12/2021 | 90 | MAHENDRA CHHETRI | 42.03 | 42.02 | 49
1690 | Alipurduar Division | Alipurduar Division | Providing House connection for KALCHINI water supply scheme at KALCHINI Block under Alipuduar Division, P.H.E. Dte.(Part-3) | HQ-A.E | RWS Kalchini Block | ORD/000327/2020-2021 | 1463/ALD | 25/01/2021 | 30 | HARI CONSTRUCTION | 4.98 | 2.15 | 97
1691 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipeline for Malangi Tea Garden Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000375/2021-2022 | 2375/ALD | 31/01/2022 | 60 | MADHAB SAHA | 74.82 | 69.57 | 94
1692 | Alipurduar Division | Alipurduar Division | Laying of HDPE pipeline for New Hasimara Area within Hasimara Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000376/2021-2022 | 2376/ALD | 31/01/2022 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 73.83 | 58.99 | 99
1693 | Alipurduar Division | Alipurduar Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 50 | 100
1694 | Alipurduar Division | Alipurduar Division | Providing FHTC at Northern side of Hasimara Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000434/2021-2022 | 2714/ALD | 23/02/2022 | 60 | ASHIM KUMAR GHOSH | 34.64 | 34.64 | 49
1695 | Alipurduar Division | Alipurduar Division | Providing FHTC at Southern side of Hasimara Piped Water Supply Scheme Under Alipurduar Division, PHE DTE. | HQ-A.E | RWS Kalchini Block | ORD/000466/2021-2022 | 2811/ALD | 28/02/2022 | 60 | MAHENDRA CHHETRI | 34.74 | 31.27 | 91
1696 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( Reverse Rotary Method) and Rising Main for Additional T/W of BANCHUKAMARI Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000315/2021-2022 | 2191/ALD | 11/01/2022 | 90 | HITANGSHU CHOUDHURY | 21.92 | 0 | 56
1697 | Alipurduar Division | Birpara Sub-Division | Extension and replacement of damaged pipeline and providing FHTC at Satkodali and surrounding area of Banchukamari PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000377/2021-2022 | 2377/ALD | 31/01/2022 | 60 | MATRI ENTERPRISE | 56.5 | 10.74 | 0
1698 | Alipurduar Division | Birpara Sub-Division | Laying balance portion pipeline and providing house connection at Jayanti Water Supply Scheme and Bhutiya Busty Area under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000202/2021-2022 | 975/ALD | 13/09/2021 | 30 | GHOSH & SAHA CONSTRUCTION | 5.04 | 5.03 | 54
1699 | Alipurduar Division | Birpara Sub-Division | Extension pipeline (HDPE) for providing FHTC at Santalbari area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000222/2021-2022 | 1619/ALD | 23/11/2021 | 60 | M/S BHOWMICK CONSTRUCTION | 24.53 | 0 | 60
1700 | Alipurduar Division | Birpara Sub-Division | Extension pipeline (HDPE) for providing FHTC at 28th and 29th mile busty area under Jainti Water Supply Scheme, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000224/2021-2022 | 1576/ALD | 22/11/2021 | 60 | DEBAJYOTI SUTRADHAR | 25.75 | 1.06 | 69
1701 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House Boundary Wall Land development & pathway TW Boring (2nd Suite of OHR-1 ODEX 165) Raising Main for Jainti TG PWSS at Kumargram under Alipurduar Division. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000335/2019-2020 | 2020/ALD | 20/03/2020 | 0 | DAS CONSTRUCTION | 17.19 | 4.28 | 0
1702 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline & other misc work related to Jayanti WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000354/2021-2022 | 2119/ALD | 05/01/2022 | 30 | TAPASH KUMAR BHOWMICK | 4.28 | 0 | 71
1703 | Alipurduar Division | Birpara Sub-Division | Tube well Boring by ODEX-195 method of drilling including Rising main for JAYANTI Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000401/2021-2022 | 2392/ALD | 31/01/2022 | 90 | TAPASH KUMAR BHOWMICK | 12.78 | 11.81 | 44
1704 | Alipurduar Division | Birpara Sub-Division | Balance work of Jainty Rest Shed along with laying of delivery line from CWR of Jainti WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000431/2021-2022 | 2629/ALD | 18/02/2022 | 60 | GHOSH & SAHA CONSTRUCTION | 13.4 | 1.53 | 64
1705 | Alipurduar Division | Alipurduar Sadar Sub-Division | Replacement of damaged pipeline in Madarihat Bazar Area PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000043/2023-2024 | 389/ALD | 19/05/2023 | 180 | KAMALESH ROY | 5.46 | 4.63 | 95
1706 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of UTTAR MADARIHAT Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000322/2021-2022 | 2198/ALD | 11/01/2022 | 90 | DILIP MAHATO | 20.99 | 15.11 | 72
1707 | Alipurduar Division | Alipurduar Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 72
1708 | Alipurduar Division | Alipurduar Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of MADHU TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000320/2021-2022 | 2196/ALD | 11/01/2022 | 90 | NARENDRA BHADANI. | 20.88 | 21.06 | 50
1709 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with DI and UPVC pipe of Kumargram WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000084/2021-2022 | 980/ALD | 13/09/2021 | 60 | DILIP MAHATO | 48.35 | 0 | 68
1710 | Alipurduar Division | Alipurduar Sadar Sub-Division | Preparation of Agumentation D.P.R after investigation For Kumargram W/Sscheme under Alipurduar Division. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000109/2021-2022 | 912/ALD | 06/09/2021 | 30 | BHAGWATI BHUJEL | 2.77 | 2.95 | 0
1711 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA ZONE- II water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000143/2020-2021 | 859/ALD | 14/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 9.96 | 0
1712 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA ZONE- II water supply scheme at KUMARGRAM Block under Alipuduar Division, P.H.E. Dte.(PART-2) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000168/2020-2021 | 912/ALD | 16/10/2020 | 30 | AKANSHA COMMERCIAL PRIVATE LTD. | 4.98 | 9.97 | 0
1713 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution line of UPVC, DI Pipe (with pillar) and cons. Of new toilet, repairing of pump house (2nd site), Land Development at Barobisa Zone-I Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000169/2021-2022 | 1319/ALD | 05/10/2021 | 60 | M/S SURAJIT DEY & CO | 81.49 | 0 | 70
1714 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA Zone-I water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-III | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000206/2020-2021 | 1160/ALD | 15/12/2020 | 60 | M/S SURAJIT DEY & CO | 29.98 | 47.09 | 69
1715 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House connection for BAROBISHA Zone-III water supply scheme at Kumargram Block under Alipuduar Division, P.H.E. Dte. Part-II | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000208/2020-2021 | 1162/ALD | 15/12/2020 | 60 | AKANSHA COMMERCIAL PRIVATE LTD. | 19.93 | 0 | 77
1716 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of rising main and delivery line connection, horizontal boring by HDD method with HDPE pipe, distribution gap filling with UPVC pipe and others allied works at Barobisha Zone-I PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000388/2023-2024 | 199/ALD | 16/01/2024 | 540 | SREE MAA CONSTRUCTION | 22.86 | 0 | 100
1717 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of pipeline (UPVC) and providing FHTC at surrounding area of Barobisha PWSS (Part-II) Under Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000474/2021-2022 | 2764/ALD | 25/02/2022 | 60 | TAPAN CHANDA | 50.32 | 1.08 | 60
1718 | Alipurduar Division | Alipurduar Sadar Sub-Division | Extension of Distribution pipe line (Barman Para and Beltala) with UPVC Connection of BAROBISA PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000555/2021-2022 | 3082/ALD | 22/03/2022 | 60 | AASHIRBAD ENTERPRISE | 13.46 | 2.56 | 70
1719 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC for MADARIHAT TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000008/2022-2023 | 18/ALD | 01/04/2022 | 120 | DILIP MAHATO | 216.89 | 197.43 | 100
1720 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd & 3rd site including laying distribution system , Rising main and providing FHTC for MADARIHAT TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000013/2022-2023 | 23/ALD | 01/04/2022 | 120 | DILIP MAHATO | 213.9 | 154.11 | 84
1721 | Alipurduar Division | Birpara Sub-Division | Replacement of damaged pipeline in Madarihat Bazar Area PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000043/2023-2024 | 389/ALD | 19/05/2023 | 180 | KAMALESH ROY | 5.46 | 0 | 95
1722 | Alipurduar Division | Birpara Sub-Division | Repair of Pump House with additional Toilet at 2nd Pump House site of Madarihat WSS under Alipuduar Division, P.H.E. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000131/2020-2021 | 877/ALD | 14/10/2020 | 45 | DILIP MAHATO | 2.13 | 0 | 91
1723 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for Govt office and other Institution under Madarihat WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000265/2021-2022 | 1830/ALD | 10/12/2021 | 30 | BHAGWATI BHUJEL | 5.04 | 5.04 | 61
1724 | Alipurduar Division | Birpara Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna for AWC and school under Madarihat WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000266/2021-2022 | 1831/ALD | 10/12/2021 | 30 | RATAN DUTTA | 5.04 | 0.97 | 59
1725 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of DIMA TG Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000293/2021-2022 | 1991/ALD | 27/12/2021 | 90 | GOBINDA BAGCHI | 20.87 | 0 | 72
1726 | Alipurduar Division | Birpara Sub-Division | Providing House connection for BIRPARA PWSS, MADARIHAT-BIRPARA Block under Alipuduar Division, P.H.E. Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000370/2020-2021 | 1766/ALD | 19/02/2021 | 60 | BILTU DAS | 39.46 | 33.54 | 83
1727 | Alipurduar Division | Birpara Sub-Division | Providing House connection for MADARIHAT PWSS under Alipuduar Division, P.H.E. Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000386/2020-2021 | 1806/ALD | 22/02/2021 | 60 | DILIP MAHATO | 20.13 | 2.01 | 90
1728 | Alipurduar Division | Birpara Sub-Division | Construction of 350cum OHR for Madarihat TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000417/2021-2022 | 2586/ALD | 17/02/2022 | 180 | DILIP MAHATO | 71.4 | 51.24 | 90
1729 | Alipurduar Division | Birpara Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 260 | 0
1730 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000009/2022-2023 | 491/ALD | 18/05/2022 | 0 | Resource Division | 149.46 | 0 | 0
1731 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000113/2023-2024 | 137/ALD | 10/01/2024 | 0 | Resource Division | 14.03 | 0 | 0
1732 | Alipurduar Division | Alipurduar Sadar Sub-Division | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 58
1733 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of Distribution Line (HDPE and DI) for retrofitting of FHTC for BIRPARA WSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000360/2020-2021 | 1754/ALD | 19/02/2021 | 45 | BILTU DAS | 47.98 | 0 | 61
1734 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of OHR 200cum for Jay Birpara TG Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000422/2021-2022 | 2601/ALD | 17/02/2022 | 180 | SUBHAS CHANDRA ROY | 55.36 | 46.9 | 80
1735 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling including providing FHTC and Rising main for JAY BIRPARA TG AREA PWSS under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000487/2021-2022 | 2911/ALD | 08/03/2022 | 120 | ALOK ENTERPRISE | 156.25 | 64.37 | 50
1736 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 100 | 0
1737 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000028/2023-2024 | 1273/ALD | 11/08/2023 | 0 | Resource Division | 20.82 | 0 | 0
1738 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at H/W site including laying distribution system and providing FHTC fo GOPALPUR TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000016/2022-2023 | 26/ALD | 01/04/2022 | 1320 | ASHIT KUMAR SINGHA | 136.46 | 60 | 95
1739 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by ODEX-165 Method of drilling at 2nd site including laying distribution system , Rising main and providing FHTC for GOPALPUR TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000017/2022-2023 | 27/ALD | 01/04/2022 | 840 | M/S DUTTA AND CO | 138.71 | 102.09 | 90
1740 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Tubewell by ODEX-165 method of drilling, construction of of pump house and boundary wall for Gopalpur PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000033/2023-2024 | 364/ALD | 18/05/2023 | 775 | SWAPAN KUMAR SAHA | 24.47 | 15.02 | 100
1741 | Alipurduar Division | Alipurduar Sadar Sub-Division | Carrying of different dia AC pipes from Alipurduar Stackyard and withdrawing CI pipes at Alipurduar Sadar Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000094/2022-2023 | 458/ALD | 13/05/2022 | 30 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 0.99 | 0 | 58
1742 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC from existing distribution system as per specification for Gopalpur TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000257/2023-2024 | 1875/ALD | 07/09/2023 | 300 | NARENDRA BHADANI. | 7.03 | 6.15 | 90
1743 | Alipurduar Division | Alipurduar Sadar Sub-Division | SUPPLY, INSTALLATION, COMMISSIONING AND TRIAL OPERATION OF ELECTRO MECHANICAL COMPONENTS OF RIGBORE T/W (1 NOS) FOR GOPALPUR TG ALONG WITH CONS. OF 1 NO. P/H OF SIZE 3.00M X 3.60M | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000336/2020-2021 | 1486/ALD | 27/01/2021 | 60 | DILIP MAHATO | 11 | 1.94 | 78
1744 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 250cum OHR for Gopalpur Tea Garden Water Supply Scheme under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000423/2021-2022 | 2602/ALD | 17/02/2022 | 180 | SASANKA ROY | 57.59 | 57.96 | 72
1745 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of different materials for Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000495/2021-2022 | 939/ALD | 08/09/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1200 | 200 | 0
1746 | Alipurduar Division | Alipurduar Sadar Sub-Division | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-B) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000584/2021-2022 | 1968/ALD | 24/12/2021 | 90 | TAPASH DAS | 0.96 | 0.96 | 78
1747 | Alipurduar Division | Alipurduar Sadar Sub-Division | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000588/2021-2022 | 745/ALD | 11/08/2021 | 90 | HARIDAS GHOSH | 0.96 | 0.96 | 74
1748 | Alipurduar Division | Alipurduar Sadar Sub-Division | Entry of data of Functional Household Tape Connection (FHTC under JJM) of PWSS in website under Alipurduar Division, PHE Dte. (Part-C) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000591/2021-2022 | 361/ALD | 08/06/2021 | 90 | TAPASH DAS | 0.96 | 0.96 | 77
1749 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000014/2022-2023 | 825/ALD | 28/06/2022 | 0 | Resource Division | 26.08 | 0 | 0
1750 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000017/2022-2023 | 828/ALD | 28/06/2022 | 0 | Resource Division | 34.42 | 0 | 0
1751 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000115/2023-2024 | 139/ALD | 10/01/2024 | 0 | Resource Division | 9.16 | 0 | 0
1752 | Alipurduar Division | Birpara Sub-Division | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Alipurduar RWS Sub-Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000460/2024-2025 | 4555/ALD | 30/12/2024 | 90 | SASANKA ROY | 1.2 | 1.19 | 0
1753 | Alipurduar Division | Birpara Sub-Division | Continuation of work of Hiring of Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte.(from 01.01.2025 to 31.03.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000461/2024-2025 | 4556/ALD | 30/12/2024 | 90 | BHAGWATI BHUJEL | 1.2 | 0 | 0
1754 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1755 | Alipurduar Division | Birpara Sub-Division | Construction of pump house, boundary wall and Rising main for 4th Tube well site at Paschim Khairbari PWSS of Birpara Sub-Division under Alipurduar Division, PHE Dte. (SM/10672) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000501/2023-2024 | 819/ALD | 14/03/2024 | 567 | TAPASH KUMAR BHOWMICK | 16.68 | 0 | 70
1756 | Alipurduar Division | Birpara Sub-Division | Laying of new HDPE/DI pipeline and replacement of Old distribution line and repairing of FHTC for Augmentation of paschim Khairbari PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000591/2024-2025 | 5504/ALD | 21/03/2025 | 60 | MONORAMA ENTERPRISE | 13.99 | 0 | 0
1757 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 350cum OHR for Madhya Parokata Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000313/2021-2022 | 2189/ALD | 11/01/2022 | 180 | SOUVIK ROY PALADHI | 71.4 | 32 | 96
1758 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House Connection (FHTC) at Parokata WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000340/2021-2022 | 2116/ALD | 05/01/2022 | 30 | SREE MAA CONSTRUCTION | 5.02 | 5.02 | 95
1759 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of UPVC pipeline and Tube well Boring by ODEX-165 Method of drilling for Madhya Parokata Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000384/2021-2022 | 2384/ALD | 31/01/2022 | 60 | SOUVIK ROY PALADHI | 96.14 | 101.62 | 95
1760 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC including Rising main for Madhya Parokata Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000385/2021-2022 | 2385/ALD | 31/01/2022 | 60 | SOUVIK ROY PALADHI | 74.19 | 64.79 | 94
1761 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 30 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 30 | 100
1762 | Alipurduar Division | Birpara Sub-Division | Laying of overground distribution system by using HDPE pipes under Augmentation of Totopara PWSS under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000001/2023-2024 | 04/ALD | 04/04/2023 | 60 | DULAL DAS | 39.82 | 39.61 | 100
1763 | Alipurduar Division | Birpara Sub-Division | Construction of intake structure ground level reservoir, boundary wall, Pump House, laying of distribution network and providing FHTC under Augmentation of Totopara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000352/2023-2024 | 2604/ALD | 04/12/2023 | 600 | DULAL DAS | 63.1 | 12.27 | 35
1764 | Alipurduar Division | Birpara Sub-Division | Route surveying and revalidation of Household data with digitization of LDS for Lankapara (Zone-I, Zone-II & Zone-III) PWSS under Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | ORD/000097/2025-2026 | 1181/ALD | 26/06/2025 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.65 | 0 | 0
1765 | Alipurduar Division | Birpara Sub-Division | Construction of river bank protection wall with wire create and land filling near 3 No. PHE pump house at SK Line under Lankapara GP within Madarihat-Birpara Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | ORD/000352/2022-2023 | 2496/ALD | 13/12/2022 | 90 | RATAN DUTTA | 1.31 | 1.17 | 100
1766 | Alipurduar Division | Birpara Sub-Division | Laying of DI & HDPE pipeline, construction of valve chamber and other works for Tulshipara TG at Lonkapara PWSS, Birpara Sub-Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | ORD/000366/2023-2024 | 82/ALD | 10/01/2024 | 135 | SUBIR GHOSH | 6.78 | 3.19 | 10
1767 | Alipurduar Division | Birpara Sub-Division | Laying of DI & HDPE pipeline, River and road crossing construction of valve chamber, community water tank and other misc. works for Lonkapara PWSS, Birpara Sub-Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | ORD/000370/2023-2024 | 86/ALD | 10/01/2024 | 90 | SUDDHYA SING LAMA | 27.7 | 0 | 0
1768 | Alipurduar Division | Birpara Sub-Division | Tube well Boring by ODEX-195 Method of drilling of Constructions of 1no. pump house, boundary wall, distribution line with FHTC for Lankapara 20no. Line for Augmentation of Lankapara TG for Lonkapara Hat Area PWSS Under Birpara Sub-Division, Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | ORD/000449/2022-2023 | 2920/ALD | 19/01/2023 | 240 | SUDDHYA SING LAMA | 40.15 | 32.23 | 51
1769 | Alipurduar Division | Birpara Sub-Division | Distribution line for Lankapara Sukundi line and adjoining areas for Augmentation of Lankapara TG for Lonkapara Hat PWSS under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, PHE(Md. Mahfuz) Dte. | ORD/000483/2022-2023 | 3318/ALD | 13/03/2023 | 714 | SHYAMAL ROY | 18.77 | 12.6 | 87
1770 | Alipurduar Division | Alipurduar Division | Continuation for the work of Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000023/2025-2026 | 343/ALD | 29/04/2025 | 180 | TAPASH KUMAR BHOWMICK | 4.29 | 0 | 0
1771 | Alipurduar Division | Alipurduar Division | Laying of DI & HDPE pipeline from Santali TG and Malangi TG to the existing OHR at Hasimara PWSS area, kalchini Block under Alipurduar division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000042/2023-2024 | 388/ALD | 19/05/2023 | 720 | D. K. & SONS | 26.33 | 13.59 | 100
1772 | Alipurduar Division | Alipurduar Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Kalchini Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000084/2025-2026 | 1052/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1773 | Alipurduar Division | Alipurduar Division | Construction of deep TW by ODEX-165 method of drilling for Subhashini TG under Hasimara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000099/2025-2026 | 1184/ALD | 26/06/2025 | 60 | SWARAN ENTERPRISE | 8.73 | 0 | 0
1774 | Alipurduar Division | Alipurduar Division | Reparing of Pump House at 2nd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000138/2025-2026 | 1575/ALD | 31/07/2025 | 60 | NARENDRA BHADANI. | 0.94 | 0 | 0
1775 | Alipurduar Division | Alipurduar Division | Reparing of Pump House at 3rd site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000139/2025-2026 | 1576/ALD | 31/07/2025 | 60 | NARENDRA BHADANI. | 0.78 | 0 | 0
1776 | Alipurduar Division | Alipurduar Division | Reparing of Pump House at Headwork site of MADHU TG PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000140/2025-2026 | 1577/ALD | 31/07/2025 | 60 | NARENDRA BHADANI. | 0.94 | 0 | 0
1777 | Alipurduar Division | Alipurduar Division | Continuation of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte..(from 01.08.2025 to 31.01.2026) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000176/2025-2026 | 1557/ALD | 30/07/2025 | 184 | CHANDAN KIRTONIA | 2.4 | 0 | 0
1778 | Alipurduar Division | Alipurduar Division | Restoration of pipeline and FHTC and allied works at Madhu TG under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000196/2025-2026 | 2103/ALD | 23/09/2025 | 60 | NARENDRA BHADANI. | 6.46 | 0 | 0
1779 | Alipurduar Division | Alipurduar Division | Painting of Old OHR of 300 cum at Madhu under Augmentation of Hasimara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000197/2025-2026 | 2104/ALD | 23/09/2025 | 60 | NARENDRA BHADANI. | 3.39 | 0 | 0
1780 | Alipurduar Division | Alipurduar Division | Continuation for the work of hiring of additional Diesel vehicle maxi cab (At least 7 seater) for Assistant Engineer, Birpara Sub-Division, P.H.E. Dte. (from 01.10.2025 to 31.12.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000204/2025-2026 | 2121/ALD | 24/09/2025 | 91 | PARITOSH SUTRADHAR | 1.2 | 0 | 0
1781 | Alipurduar Division | Alipurduar Division | Providing balance FHTC from existing distribution system as per specification for HASIMARA PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000283/2023-2024 | 1990/ALD | 15/09/2023 | 90 | BRAJA GOPAL SAHA | 73.9 | 0 | 0
1782 | Alipurduar Division | Alipurduar Division | Special repairing of road for providing of FHTC at Northen side of Hasimara PWSS under Alipurduar, Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000313/2023-2024 | 2178/ALD | 06/10/2023 | 30 | SHIB RATAN BHOWMIK | 0.93 | 0 | 0
1783 | Alipurduar Division | Alipurduar Division | Continuation order for the work of "Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same to PHE Dte. (in soft copy) Part-B" | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000346/2024-2025 | 3424/ALD | 26/09/2024 | 181 | TAPASH KUMAR BHOWMICK | 4.67 | 1.24 | 100
1784 | Alipurduar Division | Alipurduar Division | Soil investigation work at proposed OHR construction site of Hasimara PWSS under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000405/2022-2023 | 2790/ALD | 10/01/2023 | 30 | MOYTEC | 0.95 | 0.95 | 100
1785 | Alipurduar Division | Alipurduar Division | Restoration of pipeline for Gap filling and other allied works under Hasimara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000453/2024-2025 | 5170/ALD | 25/02/2025 | 60 | BRAJA GOPAL SAHA | 4.47 | 0 | 0
1786 | Alipurduar Division | Alipurduar Division | Construction of 1no. Pump House boundary wall, at new Hasimara PWSS Area under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000454/2024-2025 | 5171/ALD | 25/02/2025 | 120 | BRAJA GOPAL SAHA | 17.18 | 0 | 0
1787 | Alipurduar Division | Alipurduar Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1788 | Alipurduar Division | Alipurduar Division | Construction of 700cum OHR for Augmentation of HASIMARA Water Supply Scheme under Alipurduar Division, PHE Dte.(3rd call) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000479/2022-2023 | 3196/ALD | 27/02/2023 | 180 | BRAJA GOPAL SAHA | 121.92 | 85.66 | 90
1789 | Alipurduar Division | Alipurduar Division | Continuation of work of "Hiring of Diesel Vehicle Maxi Cab (At least 7 seater ) for Deputy Superintending Engineer, North Bengal Circle-I , P.H.E. Dte.(from 01.03.2024 to 31.07.2024)" | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000549/2023-2024 | 602/ALD | 27/02/2024 | 151 | MAHENDRA CHHETRI | 2 | 0 | 0
1790 | Alipurduar Division | Alipurduar Division | Continuation for the work of hiring of diesel vehicle maxi cab (At least 7 seater) for Deputy Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. (from 01.03.2024 to 31.10.2024) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000555/2023-2024 | 620/ALD | 29/02/2024 | 245 | MAHENDRA CHHETRI | 3.2 | 0 | 0
1791 | Alipurduar Division | Alipurduar Division | Reparing of Pump House at Headwork site of HASIMARA PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000598/2024-2025 | 5427/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.78 | 0 | 0
1792 | Alipurduar Division | Alipurduar Division | Continuation of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte..(from 01.02.2025 to 31.07.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000747/2024-2025 | 4920/ALD | 31/01/2025 | 181 | CHANDAN KIRTONIA | 2.4 | 0 | 0
1793 | Alipurduar Division | Alipurduar Division | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for Assistant Engineer ,Birpara Sub- Division ,P.H.E. Dte..(from 01.04.2025 to 30.09.2025) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000751/2024-2025 | 5760/ALD | 28/03/2025 | 184 | PARITOSH SUTRADHAR | 2.4 | 0 | 0
1794 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000004/2023-2024 | 185/ALD | 28/04/2023 | 0 | Resource Division | 33.51 | 0 | 0
1795 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000006/2024-2025 | 3611/ALD | 24/10/2024 | 0 | Resource Division | 9.89 | 0 | 0
1796 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC from existing distribution system as per specification for Ethelbari PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000260/2023-2024 | 1878/ALD | 07/09/2023 | 30 | NARENDRA BHADANI. | 3.87 | 0 | 0
1797 | Alipurduar Division | Alipurduar Sadar Sub-Division | Gap filling by HDPE/DI pipe in Ethelbari TG under Birpara Sub-Division, Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000392/2023-2024 | 203/ALD | 16/01/2024 | 60 | BHAGWATI BHUJEL | 14.02 | 13.28 | 85
1798 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Rig Bored tubewells (1 nos.) by Reverse rotary method of drilling at HW site , construction of pump house and boundary wall at H/W, laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for Ethelbari Tea Garden PWSS (zone-2) Under Birpara Subdivision, Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000395/2022-2023 | 2660/ALD | 22/12/2022 | 600 | M/S DUTTA AND CO | 87.73 | 39.95 | 26
1799 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of Rig bored TW(2nos) by Reverse Rotary method of drilling at HW and 2nd site, cons of 200 cum OHR at HW including soil testing, cons. of P/H and B/W at HW,2nd site, Laying of rising main, distribution line and providing FHTC as per Departmental Design & drawing for ETHELBARI TG PWSS (ZONE-I)under Birpara Sub-Division, Alipurduar Division, PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | ORD/000434/2022-2023 | 2861/ALD | 17/01/2023 | 180 | DILIP MAHATO | 385.44 | 323.42 | 90
1800 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000044/2022-2023 | 3486/ALD | 23/03/2023 | 0 | Resource Division | 11.43 | 0 | 0
1801 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000057/2023-2024 | 2719/ALD | 13/12/2023 | 0 | Resource Division | 60.01 | 0 | 0
1802 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, PHE Dte.(Gourab Mallick) | RTOR000068/2023-2024 | 2781/ALD | 18/12/2023 | 0 | Resource Division | 11.43 | 0 | 0
1803 | Alipurduar Division | Alipurduar RWS Sub-Division | Laying of DI/HDPE distribution line, land filling at HW site, trial run and allied works at Dakshin Barajhar Forest under Aipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000343/2024-2025 | 3231/ALD | 10/09/2024 | 60 | DILIP MAHATO (OPC) PRIVATE LIMITED | 19.62 | 7.92 | 5
1804 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tube Well, Construction of Pump House, Boundary Wall, Laying Of Rising Main, Distribution System and providing FHTC for Dakshin Barajhar Forest PWSS Under Alipurduar Division, PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000450/2022-2023 | 2921/ALD | 19/01/2023 | 120 | BHAGWATI BHUJEL | 85.2 | 74.21 | 33
1805 | Alipurduar Division | Alipurduar RWS Sub-Division | Material Requisition To Resource Division | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | RTOR000040/2024-2025 | 4255/ALD | 13/12/2024 | 0 | Resource Division | 20.1 | 0 | 0
1806 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1807 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of concrete platform, pathway and drain along with the repairing of existing boundary wall and drain for effectively stacking the various pipe/ specials items at Alipurduar Sadar Sub-Division Stackyard under the head of augmentation of Bhatibari PWSS under Alipurduar, Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000006/2023-2024 | 03/ALD | 04/04/2023 | 90 | HARIDAS GHOSH | 6.38 | 6.02 | 100
1808 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/05/2023 to 31/07/2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000052/2023-2024 | 180/ALD | 27/04/2023 | 91 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 85
1809 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.05.2023 to 31.07.2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000054/2023-2024 | 181/ALD | 27/04/2023 | 91 | NIRANJAN KIRTANIA | 0.7 | 0.58 | 0
1810 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing house connection from Bhatibari Water Supply Scheme (Specially for schools & FHTC) under Alipurduar Division P.H.E. Dte.Part-1 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000088/2021-2022 | 887/ALD | 03/09/2021 | 30 | SREE MAA CONSTRUCTION | 4.87 | 4.87 | 21
1811 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing house connection from Bhatibari Water Supply Scheme (Specially for ICDS & FHTC) under Alipurduar Division P.H.E. Dte.Part-2 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000089/2021-2022 | 888/ALD | 03/09/2021 | 30 | SREE MAA CONSTRUCTION | 4.86 | 4.86 | 20
1812 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of Laying distribution system by replacing of damaged AC pipeline with UPVC pipeline & constructon of boundary wall, new toilet, repairing of pump house (H/W site) at Bhatibari Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000182/2021-2022 | 1311/ALD | 05/10/2021 | 60 | DEBAJYOTI SUTRADHAR | 14.02 | 12 | 21
1813 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 250cum OHR as per Departmental Design, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-III PWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000196/2024-2025 | 1766/ALD | 07/06/2024 | 573 | HARIDAS GHOSH | 103.38 | 37.39 | 50
1814 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 300 cum OHR as per Departmental Design, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-IPWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000202/2024-2025 | 1931/ALD | 28/06/2024 | 300 | TAPASH KUMAR BHOWMICK | 114.7 | 17.27 | 45
1815 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for filling of left out portion in the distribution system and other allied works in connection with the Augmentation of Bhatibari (Zone-III) PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000222/2024-2025 | 2275/ALD | 05/08/2024 | 360 | HARI CONSTRUCTION | 37.43 | 0 | 65
1816 | Alipurduar Division | Alipurduar Sadar Sub-Division | Constructions of pump house, Boundary wall, laying of UPVC pipeline & Rising main connection for Purba Barachouki area under Bhatibari PWSS proposed Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000224/2024-2025 | 2277/ALD | 05/08/2024 | 360 | HARI CONSTRUCTION | 32.72 | 0 | 35
1817 | Alipurduar Division | Alipurduar Sadar Sub-Division | Balance work of construction of boundary wall of 2nd Site at Bhatibari WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000251/2021-2022 | 1598/ALD | 22/11/2021 | 45 | SREE MAA CONSTRUCTION | 4.79 | 4.77 | 19
1818 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.08.2023 to 31.10.2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000253/2023-2024 | 1109/ALD | 28/07/2023 | 92 | NIRANJAN KIRTANIA | 0.7 | 0.51 | 0
1819 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/08/2023 to 31/10/2023) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000254/2023-2024 | 1108/ALD | 28/07/2023 | 92 | NIRANJAN KIRTANIA | 0.5 | 0.5 | 0
1820 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of new UPVC/DI pipeline for filling of left out portion in the distribution system and other allied works in connection with the Augmentation of Bhatibari (Zone-I) PWSS Alipurduar Sadar Sub-Division, under Alipurduar Division PHE DTE. .(SM/14096) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000254/2024-2025 | 3117/ALD | 30/08/2024 | 225 | M/S MAA ELECTRIC ELECTRONIC | 6.45 | 0 | 70
1821 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-II PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000271/2023-2024 | 1948/ALD | 12/09/2023 | 60 | SWAPAN MALAKAR | 13 | 0 | 100
1822 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-III PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000273/2023-2024 | 1949/ALD | 12/09/2023 | 60 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 9.75 | 0 | 0
1823 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-I PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000279/2023-2024 | 1947/ALD | 12/09/2023 | 60 | SAHA ENTERPRISE | 12.4 | 0 | 0
1824 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pathway, surface drain and chatal, land development, along with the other allied works at Bhatibari Zone-IV PWSS under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000280/2023-2024 | 1950/ALD | 12/09/2023 | 60 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 13.54 | 0 | 0
1825 | Alipurduar Division | Alipurduar Sadar Sub-Division | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipe at Bhatibari WSS under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000355/2021-2022 | 2120/ALD | 05/01/2022 | 30 | SREE MAA CONSTRUCTION | 4.95 | 4.66 | 0
1826 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at Bhatibari Zone-II PWSS Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000367/2022-2023 | 2611/ALD/ | 21/12/2022 | 630 | RATAN DUTTA | 24.73 | 18.96 | 60
1827 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 1no. Boundary Wall and 2nos. Tube well Boring by Reverse Rotary Method of drilling for BHATIBARI ZONE-III and ZONE-IV PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000368/2022-2023 | 2612/ALD | 21/12/2022 | 540 | AASHIRBAD ENTERPRISE | 24.63 | 23.93 | 100
1828 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-6 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000369/2022-2023 | 2613/ALD | 21/12/2022 | 211 | TAPASH KUMAR BHOWMICK | 34.47 | 24.13 | 70
1829 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-7 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000370/2022-2023 | 2614/ALD | 21/12/2022 | 45 | HARIDAS GHOSH | 34.76 | 13.04 | 21
1830 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-8 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000371/2022-2023 | 2615/ALD | 21/12/2022 | 45 | GOUTAM KUMAR DAS | 34.6 | 0 | 0
1831 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Bhatibari PWSS under Alipurduar Division, PHE Dte. Part-9 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000372/2022-2023 | 2616/ALD | 21/12/2022 | 45 | TAPASH KUMAR BHOWMICK | 34.47 | 0 | 0
1832 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House Connection (FHTC) at Bhatibari WSS under Alipurduar Division, PHE Dte.Part-4 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000373/2022-2023 | 2619/ALD | 21/12/2022 | 30 | SREE MAA CONSTRUCTION | 5.02 | 4.88 | 21
1833 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing House Connection (FHTC) at Bhatibari WSS under Alipurduar Division, PHE Dte.Part-5 | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000374/2022-2023 | 2620/ALD | 21/12/2022 | 30 | DEBAJYOTI SUTRADHAR | 5.02 | 5.02 | 22
1834 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution pipe line by DI pipe (with pillar) along the flank of Alipurduar-Bhatibari PWD Road (From Charmile to Bhatibari) of Bhatibari WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000375/2022-2023 | 2621/ALD | 21/12/2022 | 553 | DEBAJYOTI SUTRADHAR | 28.2 | 23.43 | 83
1835 | Alipurduar Division | Alipurduar Sadar Sub-Division | Soil investigation work at 4 different places of Bhatibari within Alipurduar District under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000376/2022-2023 | 2622/ALD | 21/12/2022 | 30 | R B TESTING | 4.86 | 0 | 0
1836 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-I WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000381/2022-2023 | 2627/ALD/ | 21/12/2022 | 60 | SHIBA ENTERPRISE | 100.55 | 73.39 | 72
1837 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000382/2022-2023 | 2628/ALD/ | 21/12/2022 | 148 | TAPASH KUMAR BHOWMICK | 100.89 | 76.17 | 50
1838 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-I WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000383/2022-2023 | 2629/ALD/ | 21/12/2022 | 60 | MATRI ENTERPRISE | 100.29 | 92.25 | 87
1839 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-II WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000384/2022-2023 | 2630/ALD | 21/12/2022 | 840 | HARIDAS GHOSH | 98.45 | 80.75 | 18
1840 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-IV WSS under Alipurduar Division, PHE Dte. (Part-A) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000385/2022-2023 | 2631/ALD | 21/12/2022 | 60 | DEBAJYOTI SUTRADHAR | 75.53 | 61.22 | 20
1841 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying Distribution pipe with DI and UPVC pipe along with FHTC Connection of BHATIBARI ZONE-IV WSS under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000386/2022-2023 | 2632/ALD | 21/12/2022 | 780 | KAMALESH ROY | 74.77 | 65.08 | 87
1842 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution pipe with DI and UPVC pipe of Chilurghat, Bhatibari area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-I) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000387/2022-2023 | 2633/ALD | 21/12/2022 | 60 | DAS CONSTRUCTION | 98.5 | 86.88 | 88
1843 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution pipe with DI and UPVC pipe of Chilurghat, Kumarijan area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-II) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000388/2022-2023 | 2634/ALD | 21/12/2022 | 60 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 83.66 | 62.39 | 19
1844 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying distribution pipe with DI and UPVC pipe of Chikliguri area under Bhatibari Zone-III WSS under Alipurduar Division, PHE Dte.(Part-III) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000389/2022-2023 | 2635/ALD | 21/12/2022 | 60 | TAPASH DAS | 74.46 | 43.73 | 21
1845 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House, Boundary Wall, Tube well Boring by Reverse Rotary Method of drilling including Rising Main at H/W site and 2nd site along with repairing of office godown for Bhatibari Zone-I PWSS Under Alipurduar Division PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000390/2022-2023 | 2636/ALD | 21/12/2022 | 180 | DULAL DAS | 51.35 | 35.53 | 85
1846 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 1no. Boundary Wall and 2nos. Pump House for BHATIBARI ZONE-III and ZONE-IV PWSS Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000391/2022-2023 | 2637/ALD | 21/12/2022 | 810 | CREATIVE UN EMPLOYED ENGINEERSCO OPER SOCYLIMITED | 17.67 | 0 | 100
1847 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 150 cum OHR as per Departmental Design & drawing, laying of rising main & delivery connection . Supply of CIDF Specials and others allied works for Bhatibari Z-II PWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000423/2024-2025 | 4898/ALD | 30/01/2025 | 180 | MATRI ENTERPRISE | 95.67 | 0 | 0
1848 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of 150cum OHR as per Departmental Design & drawing, laying of rising main & delivery connection, Supply of CIDF specials and others allied works for Bhatibari Zone -IV PWSS Under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000537/2023-2024 | 895/ALD | 15/03/2024 | 690 | KAMALESH ROY | 98.47 | 50.36 | 50
1849 | Alipurduar Division | Alipurduar Sadar Sub-Division | Reparing of Pump House at 3nd site of BHATIBARI PWSS Under Alipurduar Division PHE DTE.(2nd call) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - II Block | ORD/000613/2024-2025 | 5603/ALD | 27/03/2025 | 60 | SREE MAA CONSTRUCTION | 0.97 | 0 | 0
1850 | Alipurduar Division | Birpara Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1851 | Alipurduar Division | Birpara Sub-Division | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Madhya Khairbari Water Supply Scheme TW No.-IV (Additional) under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000060/2025-2026 | 788/ALD | 30/05/2025 | 30 | M/S. BHOWMIK & CO | 10.78 | 0 | 0
1852 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Madarihat-Birpara Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000080/2025-2026 | 1048/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1853 | Alipurduar Division | Birpara Sub-Division | Continuation work order of the work of "Boring of TW, Cons. Of Pump House, boundary wall, OHR (300 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for MADHYA KHAIRBARI PWSS under Alipurduar Division PHE DTE." (As per approval of SE NBC-I P.H.E. Dte. vide e-file no-DPHE-33014/10/2024-EE(ALI_D) SEC-DPHE (Computer No-974292)) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000200/2024-2025 | 1914/ALD | 26/06/2024 | 60 | DILIP MAHATO | 26.54 | 26.16 | 90
1854 | Alipurduar Division | Birpara Sub-Division | Sinking of Big dia Tube Well (250 x 200 x 150 mm dia) by Modified DTH - ODEX of drilling at Madhya Khairbari PWSS within Madarihat-Birpara Block of RWS SUB-Division under Alipurduar Division, PHE Dte. (SM/13248) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000237/2024-2025 | 2297/ALD | 07/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 18.06 | 0 | 80
1855 | Alipurduar Division | Birpara Sub-Division | Providing FHTC from existing distribution system as per specification for MADHYA KHAIRBARI PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000285/2023-2024 | 1992/ALD | 15/09/2023 | 360 | DINABANDHU RAY | 16.91 | 0 | 0
1856 | Alipurduar Division | Birpara Sub-Division | CONSTRUCTION OF PUMP HOUSE and BOUNDARY WALL FOR ADDITIONAL TUBEWELL and LAYING DISTRIBUTION SYSTEM FOR PROVIDING FHTC AND LAND DEVELOPMENT AT HW SITE and 2ND SITE AT MADHYA KHAIRBARI PWSS WITHIN MADARIHAT-BIRPARA BLOCK. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000349/2024-2025 | 3419/ALD | 26/09/2024 | 240 | MITHUN DAS | 64.12 | 0 | 50
1857 | Alipurduar Division | Birpara Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1858 | Alipurduar Division | Birpara Sub-Division | Conceptualization, design and implementing mass awareness generation through Wall writing at 20 nos. villages (Block - Kalchini) by dissemination of awareness generation IEC messages FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Alipurduar district under Alipurduar Division, PHE Dte, Govt. of West Bengal. (SM/13248) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000496/2023-2024 | 752/ALD | 12/03/2024 | 60 | M/S SARKAR & CO | 4.76 | 4.68 | 100
1859 | Alipurduar Division | Birpara Sub-Division | Boring of TW, Cons. Of Pump House, boundary wall, OHR (300 cum) inclu. Soil investigation works, Laying of rising main, distribution system and providing FHTC for MADHYA KHAIRBARI PWSS under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | ORD/000553/2022-2023 | 3575/ALD | 27/03/2023 | 900 | DILIP MAHATO | 553.32 | 428.63 | 85
1860 | Alipurduar Division | Birpara Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Madarihat - Birpara Block | RTOR000091/2023-2024 | 115/ALD | 10/01/2024 | 0 | Resource Division | 15.17 | 0 | 0
1861 | Alipurduar Division | Alipurduar Division | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 100 Cum OHR as per Departmental Design & drawing , TWO nos. pump house & boundary wall, providing FHTC, Soil Investigation work and others allied works for NIMTIJHORA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000578/2022-2023 | 3639/ALD | 31/03/2023 | 720 | SAMIRON PODDER | 207.36 | 166.43 | 95
1862 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000036/2024-2025 | 4252/ALD | 13/12/2024 | 0 | Resource Division | 1.61 | 0 | 0
1863 | Alipurduar Division | Alipurduar Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | RTOR000071/2023-2024 | 2784/ALD | 18/12/2023 | 0 | Resource Division | 6.17 | 0 | 0
1864 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna for Alipurduar-II Block under Alipurduar Division, PHE Dte. (Pin point site of the FHTC will be given at the time of issue of work order) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000083/2025-2026 | 1051/ALD | 17/06/2025 | 60 | MOTI INDUSTRIES | 18.14 | 0 | 0
1865 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing balance FHTC for TURTURI PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000217/2023-2024 | 1571/ALD | 23/08/2023 | 496 | TAPASH KUMAR BHOWMICK | 6.81 | 0 | 0
1866 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF & CISS Pipes and specials for Turturi Water Supply Scheme under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000219/2023-2024 | 1579/ALD | 24/08/2023 | 30 | TAPASH KUMAR BHOWMICK | 11.27 | 11.27 | 85
1867 | Alipurduar Division | Alipurduar Sadar Sub-Division | Continuation for the work of Collection of house hold details at prescribed format through mobile app/Hard Copy including Geo-reference as directed by the E.I.C. and submission the same (soft copy) to P.H.E. Dte. Part-B | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000255/2023-2024 | 1107/ALD | 28/07/2023 | 120 | TAPASH KUMAR BHOWMICK | 4.67 | 4.67 | 100
1868 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well boring by ODEX-165 Method of drilling, Construction of Pump House, Boundary wall at proposed 3rd site of Turturi under Alipurduar Division, PHE Dte | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000323/2023-2024 | 2420/ALD | 09/11/2023 | 431 | TAPASH KUMAR BHOWMICK | 17.4 | 11.8 | 70
1869 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply of CIDF Specials & Jeffy Coupling for Turturi (SM/14219) WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000403/2024-2025 | 4539/ALD | 26/12/2024 | 30 | SOUVIK ROY PALADHI | 19.99 | 0 | 0
1870 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE/DI Pipeline, horizontal boring by HDD method, bridge and culvert crossing, providing FHTC, specials repair with trial run of pipeline and allied works at Chuniajhora PWSS under Alipurduar Division, PHE Dte.(SM/14219 & SM/10179) | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000460/2023-2024 | 672/ALD | 06/03/2024 | 240 | ASHOK SAPKOTA | 19.39 | 0 | 100
1871 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supplying and Laying of Water supply line (using HDD/micro tunneling machine) for supply of drinking water in different areas of Alipurduar district under Alipurduar Division PHE Dte. | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000464/2024-2025 | 5287/ALD | 07/03/2025 | 240 | APEX ENGINEERING | 74.36 | 0 | 65
1872 | Alipurduar Division | Alipurduar Sadar Sub-Division | Cons. of Pump House & Tube well Boring by ODEX-165 Method drilling at HW Site & 2nd Site, laying distribution system with UPVC pipeline including rising main & delivery connection, Cons. of 150cum OHR as per departmental Design & drawing along with soil investigation works, providing FHTC including cons. of platform and others allied works for TURTURI PWSS Under Alipurduar Division, PHE DTE | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000551/2022-2023 | 3574/ALD | 27/03/2023 | 720 | TAPASH KUMAR BHOWMICK | 399.05 | 350.21 | 90
1873 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000015/2024-2025 | 3949/ALD | 26/11/2024 | 0 | Resource Division | 6.18 | 0 | 0
1874 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000038/2022-2023 | 3046/ALD | 08/02/2023 | 0 | Resource Division | 25.4 | 0 | 0
1875 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000049/2023-2024 | 2397/ALD | 08/11/2023 | 0 | Resource Division | 6.18 | 0 | 0
1876 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Alipurduar Sadar Sub Division,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000056/2024-2025 | 4276/ALD | 13/12/2024 | 0 | Resource Division | 7.63 | 0 | 0
1877 | Alipurduar Division | Alipurduar RWS Sub-Division | Laying of remaining Distribution Line and providing FHTC at different areas under Torsha FOREST PWSS under Alipurduar Division, PHE Dte | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000221/2023-2024 | 1581/ALD | 24/08/2023 | 60 | KAMALESH ROY | 10.84 | 10.84 | 100
1878 | Alipurduar Division | Alipurduar RWS Sub-Division | Boring of Tubewell, Construction of pump house, boundary wall, Laying of Rising main, distribution system and providing FHTC for Torsha Forest PWSS under Alipurduar Division PHE Dte. | Alipurduar RWS,Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte. | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Alipurduar - I Block | ORD/000448/2022-2023 | 2919/ALD | 19/01/2023 | 600 | KAMALESH ROY | 79.66 | 71.83 | 94
1879 | Alipurduar Division | Alipurduar Sadar Sub-Division | RESTORATION OF PIPELINE DAMAGED DUE TO CONSTRUCTION ACTIVITY WBSRDA | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | BILL/00501/2024-2025 | 321/24-25/PFMS | 14/11/2024 | 0 | EXECUTIVE ENGINEER WBSRDA | 64.01 | 0 | 0
1880 | Alipurduar Division | Alipurduar Sadar Sub-Division | Supply and installation of scheme information board at different PWSS site of Kalchini Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000112/2025-2026 | 1394/ALD | 16/07/2025 | 60 | M/S SARKAR & CO | 3.64 | 0 | 0
1881 | Alipurduar Division | Alipurduar Sadar Sub-Division | Expenditure for different PWSS land registration and subsequent mutation process as compliance for PHED and Land commissioner authorise to overcome the stalemate and initiation of due diligence process in Kalchini Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000113/2025-2026 | 1395/ALD | 16/07/2025 | 45 | M/S SARKAR & CO | 2 | 0 | 0
1882 | Alipurduar Division | Alipurduar Sadar Sub-Division | Laying of HDPE (PN-6) bring crossing work including land development and allied work at Bhatkhawa Tea Garden Piped Water Supply Scheme Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000181/2025-2026 | 1884/ALD | 27/08/2025 | 90 | PRITAM DAS | 21.91 | 0 | 0
1883 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing FHTC from existing distribution system as per specification for Bhatkhawa TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000265/2023-2024 | 1883/ALD | 07/09/2023 | 240 | PRANAB GHOSH | 7.16 | 7.1 | 100
1884 | Alipurduar Division | Alipurduar Sadar Sub-Division | Tube well Boring by ODEX-165 Method of drilling at HW, FIRST TUBE WELL site including laying distribution system with new HDPE pipeline , Constructions of 150 Cum OHR as per Departmental Design & drawing , TWO nos pump house & boundary wall, providing FHTC, Soil Investigation work and other allied works for BHATKHAWA TEA GARDEN AREA PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000475/2022-2023 | 3193/ALD | 27/02/2023 | 673 | S.G. CONSTRUCTION | 325.36 | 147.41 | 60
1885 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000033/2024-2025 | 4249/ALD | 13/12/2024 | 0 | Resource Division | 29.54 | 0 | 0
1886 | Alipurduar Division | Alipurduar Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Alipurduar Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | RTOR000070/2023-2024 | 2783/ALD | 18/12/2023 | 0 | Resource Division | 9.88 | 0 | 0
1887 | Alipurduar Division | Alipurduar Sadar Sub-Division | LAYING DISTRIBUTION LINE FOR RETROFITTING OF FHTC AT KHASRU LINE UNDER RAHIMABAD TG PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000032/2021-2022 | 580/ALD | 15/07/2021 | 30 | M/S BHOWMICK CONSTRUCTION | 12.75 | 0 | 71
1888 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing house connection from Rahimabad Water Supply Scheme (Specially for School & FHTC) under Alipurduar Division P.H.E. Dte.Part-3 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000090/2021-2022 | 889/ALD | 03/09/2021 | 30 | POLY CONSTRUCTION | 4.3 | 8.6 | 0
1889 | Alipurduar Division | Alipurduar Sadar Sub-Division | Providing house connection from Rahimabad Water Supply Scheme (Specially for School & FHTC) under Alipurduar Division P.H.E. Dte.Part-4 | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000091/2021-2022 | 890/ALD | 03/09/2021 | 30 | SOUVIK ROY PALADHI | 4.3 | 3.54 | 71
1890 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of pump house, Boundary Wall, Tube well Boring (ODEX-165 method), rising main of 3rd TW site of Rahimabad WSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000347/2022-2023 | 2493/ALD | 13/12/2022 | 120 | DULAL DAS | 23.52 | 14.88 | 27
1891 | Alipurduar Division | Birpara Sub-Division | Renovation of Pump house and boundary wall at H/W site of Hantapara TG PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000088/2025-2026 | 1172/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.28 | 0 | 0
1892 | Alipurduar Division | Birpara Sub-Division | Renovation of Pump house and boundary wall at 2nd site of Hantapara TG PWSS under Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000089/2025-2026 | 1173/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.07 | 0 | 0
1893 | Alipurduar Division | Birpara Sub-Division | Renovation of Pump house and boundary wall at 3rd site of Hantapara TG PWSS under Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000090/2025-2026 | 1174/ALD | 26/06/2025 | 90 | MANI PRADHAN | 1.05 | 0 | 0
1894 | Alipurduar Division | Birpara Sub-Division | Boring of TW, Construction of Pumphouse, Boundary wall, Laying of Distribution system for Augmentation of Hantupara PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000517/2022-2023 | 3317/ALD | 13/03/2023 | 585 | DULAL DAS | 23.8 | 20.28 | 98
1895 | Alipurduar Division | Birpara Sub-Division | Renovation of Pump house and boundary wall at 3rd Pump house site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000093/2025-2026 | 1177/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.04 | 0 | 0
1896 | Alipurduar Division | Birpara Sub-Division | Renovation of Pump house and boundary wall at 2nd Pump house site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000094/2025-2026 | 1178/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.04 | 0 | 0
1897 | Alipurduar Division | Birpara Sub-Division | Renovation of Pump house and boundary wall at H/W site of Gargenda TG PWSS under Alipurduar Division, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000095/2025-2026 | 1179/ALD | 26/06/2025 | 90 | AVNI CONSTRUCTION | 1.3 | 0 | 0
1898 | Alipurduar Division | Birpara Sub-Division | Supply of MSREW Pipe for modified DTH - ODEX of drilling at Site no. 01 of GARGENDA TE of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/16824) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000232/2024-2025 | 2292/ALD | 06/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 8.77 | 7.43 | 100
1899 | Alipurduar Division | Birpara Sub-Division | Supply of MSREW Pipe for modified DTH - ODEX of drilling at 2 different locations under Madarihat-Birpara Block of RWS SUB-Division under Alipurduar Division, PHE Dte.(SM/16824) | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000233/2024-2025 | 2293/ALD | 06/08/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 14.15 | 8.09 | 100
1900 | Alipurduar Division | Birpara Sub-Division | Construction of boundary wall, Pump house, TW, Rising main for Gargenda PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000384/2023-2024 | 196/ALD | 16/01/2024 | 120 | DILIP MAHATO | 27.12 | 0 | 0
1901 | Alipurduar Division | Birpara Sub-Division | Construction of boundary wall, Pump house, TW, Rising main for Gargenda (Near Dukhiya Line) PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000386/2023-2024 | 197/ALD | 16/01/2024 | 600 | MANI PRADHAN | 27.78 | 0 | 70
1902 | Alipurduar Division | Birpara Sub-Division | Boring of TW, Construction of PH, B/Wall and LDS for Augmentation of Gargenda PWSS under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000520/2022-2023 | 3473/ALD | 22/03/2023 | 480 | SHYAMAL ROY | 36.57 | 18.74 | 60
1903 | Alipurduar Division | Birpara Sub-Division | Sinking of Big dia. Tubewell (200 x 150 mm dia.)by modified DTH -ODEX method of drilling at Gargenda-1 no site (SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000532/2023-2024 | 890/ALD | 15/03/2024 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 17.23 | 15.62 | 5
1904 | Alipurduar Division | Birpara Sub-Division | Sinking of Big dia. Tubewell (200 x 150 mm dia.)By modified DTH -ODEX method of drilling at Dhumchipara-2nos. site (SM/09896 & SM/16824) of Birpara Sub-Division under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,Birpara A.E | Birpara Sub Division,Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda) | ORD/000533/2023-2024 | 891/ALD | 15/03/2024 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT LTD | 34.47 | 14.79 | 10
1905 | Alipurduar Division | Alipurduar Division | Tube well Boring by ODEX-165 Method of drilling at TUBE WELL site including laying distribution system with new HDPE pipeline ,One nos pump house & boundary wall, providing FHTC and others allied works for Bhutri Forest PWSS Under Alipurduar Division PHE DTE. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000010/2023-2024 | 94/ALD | 18/04/2023 | 120 | FAUDA SINGH CHHETRI | 34.7 | 4.07 | 100
1906 | Alipurduar Division | Alipurduar Division | Gap joint and restoration of HDPE line and repairing of FHTC and allied works at Radharani and Chuapara village under Radharani under Bhutri Forest PWSS within Kalchini Block under Alipurduar Division, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,PHE Dte.,HQ-A.E | Junior Engineer 2,Alipurduar Mechanical sub-division,PHE Dte (Md. saquib Hoda),RWS Kalchini Block | ORD/000065/2025-2026 | 817/ALD | 03/06/2025 | 75 | PRAPTI DUTTA | 23.32 | 0 | 50
1907 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Latabari PWSS under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | Birpara Sub Division | ORD/000102/2022-2023 | 406/ALD | 11/05/2022 | 45 | ASHOK SAPKOTA | 24.2 | 20.74 | 42
1908 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection (FHTC) in connection with Jaldhara/JalSwapna (Schools, AWC and others) for Uttar Latabari PWSS under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | Birpara Sub Division | ORD/000103/2022-2023 | 407/ALD | 11/05/2022 | 45 | SHIB RATAN BHOWMIK | 24.21 | 8.68 | 46
1909 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline for providing FHTC at Uttar Latabari PWSS area, Kalchini Block under Alipurduar Division PHE DTE. | HQ-A.E | Birpara Sub Division | ORD/000238/2022-2023 | 1330/ALD | 24/08/2022 | 60 | DIPANKAR DUTTA | 47.46 | 47.24 | 46
1910 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection from existing pipeline to the schools, AWC, Community centres, Govt. Office Buildings and Households at Southern Part of Uttar Latabari Area under Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000249/2021-2022 | 1594/ALD | 22/11/2021 | 30 | M/S SHIB RATAN BHOWMICK & CO | 4.99 | 4.99 | 76
1911 | Alipurduar Division | Birpara Sub-Division | Providing Functional Tap Connection from existing pipeline to the schools, AWC, Community centres, Govt. Office Buildings and Households at Northern Part of Uttar Latabari Area under Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000250/2021-2022 | 1595/ALD | 22/11/2021 | 30 | M/S SHIB RATAN BHOWMICK & CO | 4.99 | 4.99 | 75
1912 | Alipurduar Division | Birpara Sub-Division | Construction of RCC boundary wall for Uttar Latabari WSS Pump House (rabindra nagar) at Uttar Latabari PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000268/2021-2022 | 1834/ALD | 10/12/2021 | 45 | SHIB RATAN BHOWMIK | 4.9 | 4.48 | 75
1913 | Alipurduar Division | Birpara Sub-Division | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-A | HQ-A.E | Birpara Sub Division | ORD/000273/2020-2021 | 1285/ALD | 05/01/2021 | 60 | ASHOK SAPKOTA | 22.45 | 3.32 | 46
1914 | Alipurduar Division | Birpara Sub-Division | Retrofitting of pipeline for UTTAR LATABARAI PWSS (Rabindranagar & surroundings) area at Kalchini Block under Alipurduar Division, PHE Dte. Part-B | HQ-A.E | Birpara Sub Division | ORD/000274/2020-2021 | 1286/ALD | 05/01/2021 | 60 | ASHOK SAPKOTA | 19.09 | 6.87 | 45
1915 | Alipurduar Division | Birpara Sub-Division | Laying of DI and HDPE pipeline from Kalchini BDO Office towards Hamiltonganj Bazar at Uttar Latabari PWSS area under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000294/2022-2023 | 1685/ALD | 20/09/2022 | 60 | SUNDAR SING LAMA | 24.01 | 23.09 | 45
1916 | Alipurduar Division | Birpara Sub-Division | Providing balance FHTC from existing distribution system as per specification for UTTAR LATABARI PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | Birpara Sub Division | ORD/000295/2023-2024 | 2104/ALD | 29/09/2023 | 90 | DIPANKAR DUTTA | 65.07 | 0 | 0
1917 | Alipurduar Division | Birpara Sub-Division | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling Near House of Lt. Jhagru Rai, East Hirdaypur of Angrabhasa GP-I under Nagrakata Block under Jalpaiguri District. | HQ-A.E | Birpara Sub Division | ORD/000406/2020-2021 | 1827/ALD | 23/02/2021 | 15 | RAMESH SHARMA | 4.08 | 0 | 40
1918 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at Headwork site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | Birpara Sub Division | ORD/000595/2024-2025 | 5424/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0
1919 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 4th site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE | HQ-A.E | Birpara Sub Division | ORD/000596/2024-2025 | 5425/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0
1920 | Alipurduar Division | Birpara Sub-Division | Reparing of Pump House at 2nd site of Uttar Latabari PWSS Under Alipurduar Division PHE DTE. | HQ-A.E | Birpara Sub Division | ORD/000597/2024-2025 | 5426/ALD | 19/03/2025 | 60 | DOOARS SOCIAL WELFARE ORGANISATION | 0.93 | 0 | 0
1921 | Alipurduar Division | Alipurduar Sadar Sub-Division | Construction of Pump House ,Boundary Wall, and Tube well Boring by Reverse Rotary method of drilling including Rising main for JASHODANGA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar Sadar Sub Division,Assistant Engineer,Cooch-Behar Mechanical Sub-Division, PHE Dte. | Alipurduar Sub Division,Junior Engineer 1, Northern Mechanical Division-II,PHE Dte. | ORD/000403/2021-2022 | 2394/ALD | 31/01/2022 | 90 | MATRI ENTERPRISE | 24.02 | 17.8 | 44
1922 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE / DI Pipeline at different area of MAKRAPARA PWSS under Alipurduar Division PHED. | Birpara A.E | Birpara Sub Division | ORD/000070/2020-2021 | 624/ALD | 03/09/2020 | 120 | DILIP MAHATO | 14.63 | 8.7 | 84
1923 | Alipurduar Division | Birpara Sub-Division | Construction of Balance boundary wall at CWR under Makrapara WSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000093/2021-2022 | 892/ALD | 03/09/2021 | 45 | DILIP MAHATO | 4.76 | 4.9 | 0
1924 | Alipurduar Division | Birpara Sub-Division | Laying of balance DI/MS/HDPE pipeline for Makrapara WSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000325/2020-2021 | 1457/ALD | 25/01/2021 | 45 | DILIP MAHATO | 13.65 | 8.83 | 85
1925 | Alipurduar Division | Birpara Sub-Division | Construction of Pump House, Boundary Wall, and Tube well Boring by ODEX-195 method of drilling including Rising main for MAKRAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000398/2021-2022 | 2389/ALD | 31/01/2022 | 90 | INDRAYOODH BHOWAL | 27.18 | 0 | 0
1926 | Alipurduar Division | Birpara Sub-Division | Laying of distribution of HDPE pipeline and providing FHTC for Garochira area, Makrapara PWSS under Alipurduar Division, PHE DTE. | Birpara A.E | Birpara Sub Division | ORD/000478/2021-2022 | 2897/ALD | 08/03/2022 | 60 | DILIP MAHATO | 33.9 | 19.97 | 42
1927 | Alipurduar Division | Birpara Sub-Division | Laying of HDPE pipeline near existing PH No-01 village for the Makrapara PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000554/2021-2022 | 3046/ALD | 21/03/2022 | 30 | DILIP MAHATO | 4.95 | 2.22 | 42
1928 | Alipurduar Division | Birpara Sub-Division | Water supply for Makrapara Kali Mandir at Makarapara within Birpara Sub-Division under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000558/2021-2022 | 3216/ALD | 30/03/2022 | 45 | RATAN DUTTA | 4.4 | 0 | 0
1929 | Alipurduar Division | Birpara Sub-Division | Fuel bill for the month of August 2021 | Birpara A.E | Birpara Sub Division | VCH/000568/2021-2022 | 118/21-22/PFMS | 08/09/2021 | 0 | SHIVAM SERVICE STATION | 0.21 | 0 | 0
Total | [10 empty] | 129858.35 | 41109.66