## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Chenchurgerya water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00233/2024-2025 | 114/JMD | 13/05/2024 | 0 | WBSEDCL | 8.71 | 0 | 0
2 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chenchur Geria & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | ORD/000043/2023-2024 | 1246/JMD | 26/05/2023 | 180 | M/S. SAMRIDDHI ENTERPRISE | 21.88 | 16.2 | 50
3 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Kanduana T/W - II water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00175/2024-2025 | 102/JMD | 08/05/2024 | 0 | WBSEDCL | 5.18 | 0 | 0
4 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection charges. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00414/2024-2025 | 200/JMD | 14/06/2024 | 0 | WBSEDCL | 2.93 | 0 | 0
5 | Jhargram Mechanical Division | Jhargram Division | For new service connection charges for Goyaldanga, t/w-II w/s scheme. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00006/2022-2023 | 6/JMD/PFMS/DEC | 01/12/2022 | 0 | WBSEDCL | 0.21 | 0 | 0
6 | Jhargram Mechanical Division | Jhargram Division | Charges for WBSEDCL new service connection. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00007/2022-2023 | 7/JMD/PFMS/DEC | 07/12/2022 | 0 | WBSEDCL | 3.54 | 0 | 0
7 | Jhargram Mechanical Division | Jhargram Division | New service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00013/2022-2023 | 13/JMD/PFMS/DEC | 17/12/2022 | 0 | WBSEDCL | 0.62 | 0 | 0
8 | Jhargram Mechanical Division | Jhargram Division | New service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00027/2022-2023 | 27/JMD/PFMS/DEC | 20/12/2022 | 0 | WBSEDCL | 0.21 | 0 | 0
9 | Jhargram Mechanical Division | Jhargram Division | WBSEDCL payment for new service connection | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00039/2022-2023 | 39/JMD/PFMS/DEC | 29/12/2022 | 0 | WBSEDCL | 19.57 | 0 | 0
10 | Jhargram Mechanical Division | Jhargram Division | New service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00047/2022-2023 | 8/JMD//PFMS/JAN | 11/01/2023 | 0 | WBSEDCL | 2.5 | 0 | 0
11 | Jhargram Mechanical Division | Jhargram Division | New service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00058/2022-2023 | 17JMD//PFMS/JAN | 20/01/2023 | 0 | WBSEDCL | 0.21 | 0 | 0
12 | Jhargram Mechanical Division | Jhargram Division | New service connection charges | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00264/2022-2023 | 15/JMD/PFMS/MAR | 06/03/2023 | 0 | WBSEDCL | 1.46 | 0 | 0
13 | Jhargram Mechanical Division | Jhargram Division | New service connection charges under 269 mini pwss (Scheme code:- SM/09915) | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00280/2022-2023 | 16/JMD/PFMS/MAR | 06/03/2023 | 0 | WBSEDCL | 3.15 | 0 | 0
14 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00387/2023-2024 | 22/AUG | 25/08/2023 | 0 | WBSEDCL | 0.21 | 0 | 0
15 | Jhargram Mechanical Division | Jhargram Division | New service connection. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00627/2023-2024 | 10/JMD | 11/10/2023 | 0 | WBSEDCL | 0.21 | 0 | 0
16 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sankarbani Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000005/2023-2024 | 953/JMD | 25/04/2023 | 120 | SRI KRISHNA NIRMAN | 5.78 | 5.76 | 100
17 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paira Kuli, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000006/2023-2024 | 954/JMD | 25/04/2023 | 120 | SINHA ELECTRICALS | 5.62 | 5.56 | 95
18 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paira Kuli, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000007/2023-2024 | 955/JMD | 25/04/2023 | 120 | A.K. SIKDAR | 5.77 | 5.68 | 100
19 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000008/2023-2024 | 956/JMD | 25/04/2023 | 120 | P.K. ENGINEERING | 5.78 | 5.75 | 95
20 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000009/2023-2024 | 957/JMD | 25/04/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 5.74 | 95
21 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Patina, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000010/2023-2024 | 958/JMD | 25/04/2023 | 598 | SUJOY RANJAN BHOWMICK | 5.78 | 4.11 | 100
22 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Deulbar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000011/2023-2024 | 959/JMD | 25/04/2023 | 120 | DEB KUMAR BASU | 5.78 | 5.75 | 95
23 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000012/2023-2024 | 960/JMD | 25/04/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 5.15 | 95
24 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Thuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000013/2023-2024 | 961/JMD | 25/04/2023 | 120 | GOENKA ENTERPRISE | 5.78 | 4.01 | 90
25 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Thuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000014/2023-2024 | 962/JMD | 25/04/2023 | 120 | A.S. ENGINEERING | 5.78 | 3.78 | 90
26 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadam Diha, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000015/2023-2024 | 963/JMD | 25/04/2023 | 120 | M/S. P.P. ELECTRICALS | 5.77 | 5.73 | 95
27 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadam Diha, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000016/2023-2024 | 964/JMD | 25/04/2023 | 120 | TAPAN BISWAS | 5.77 | 5.1 | 95
28 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000017/2023-2024 | 965/JMD | 25/04/2023 | 120 | SUBHASIS ROY | 5.77 | 4.96 | 95
29 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000018/2023-2024 | 966/JMD | 25/04/2023 | 120 | M/S. EMMESS | 5.78 | 4.13 | 95
30 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ramkrishnapur, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000019/2023-2024 | 967/JMD | 25/04/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 5.75 | 100
31 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jagannathpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000028/2023-2024 | 1206/JMD | 25/05/2023 | 120 | MASSK ENGINEERING WORKS | 5.78 | 5.72 | 95
32 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chandabila, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000029/2023-2024 | 1207/JMD | 25/05/2023 | 120 | M/S. EMMESS | 5.78 | 4.13 | 95
33 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chandabila, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000038/2023-2024 | 1293/JMD | 30/05/2023 | 120 | S.S. GHORAI | 5.78 | 5.06 | 95
34 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Andharisol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000053/2023-2024 | 987/JMD | 26/04/2023 | 120 | SHOVAN KUMAR DAS | 5.78 | 5.76 | 95
35 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Birbhanpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000054/2023-2024 | 1349/JMD | 06/06/2023 | 120 | JAGANNATH ENTERPRISE | 5.78 | 5.17 | 95
36 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kandnashol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000055/2023-2024 | 1359/JMD | 06/06/2023 | 120 | MONORANJAN DEY | 5.77 | 5.74 | 95
37 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amadubi T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000077/2023-2024 | 985/JMD | 26/04/2023 | 180 | ABHIJIT BASU | 6.89 | 6.78 | 95
38 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000078/2023-2024 | 986/JMD | 24/04/2023 | 120 | DEB KUMAR BASU | 5.98 | 5.85 | 95
39 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gohalberya T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000083/2023-2024 | 1706/JMD | 13/07/2023 | 180 | DEBJYOTI BASU | 6.89 | 6.84 | 100
40 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gohalberya T/W no. -III & IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000084/2023-2024 | 1707/JMD | 13/07/2023 | 180 | SUJOY RANJAN BHOWMICK | 6.89 | 0 | 0
41 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rupai T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000085/2023-2024 | 1708/JMD | 13/07/2023 | 180 | DEBJYOTI BASU | 6.89 | 0 | 0
42 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nischintapur T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000086/2023-2024 | 1709/JMD | 13/07/2023 | 180 | M/S. EMMESS | 6.89 | 2.94 | 80
43 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pukhuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000087/2023-2024 | 1727/JMD | 14/07/2023 | 120 | SAMARPITA ENGINEERING | 5.78 | 5.75 | 95
44 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pukhuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000088/2023-2024 | 1728/JMD | 14/07/2023 | 120 | M/S. SAMRIDDHI ENTERPRISE | 5.78 | 5.03 | 100
45 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sanuningui, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000089/2023-2024 | 1729/JMD | 14/07/2023 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 5.03 | 95
46 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sanuningui, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000090/2023-2024 | 1730/JMD | 14/07/2023 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 5.76 | 95
47 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhansol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000091/2023-2024 | 1731/JMD | 14/07/2023 | 120 | M/S. SAMRIDDHI ENTERPRISE | 5.78 | 0 | 0
48 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhansol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000092/2023-2024 | 1732/JMD | 14/07/2023 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 5.78 | 0 | 0
49 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Metyalsol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000093/2023-2024 | 1733/JMD | 14/07/2023 | 120 | SAMARPITA ENGINEERING | 5.78 | 0 | 0
50 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kundal Pahari T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000094/2023-2024 | 1710/JMD | 13/07/2023 | 180 | DAS CONSTRUCTION | 6.89 | 0 | 0
51 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000095/2023-2024 | 1711/JMD | 13/07/2023 | 180 | MASSK ENGINEERING WORKS | 5.98 | 5.26 | 100
52 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhararu T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000096/2023-2024 | 1712/JMD | 13/07/2023 | 120 | SOUMEN ELECTRIC | 5.98 | 5.94 | 100
53 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000097/2023-2024 | 1713/JMD | 13/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0
54 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Panisol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000098/2023-2024 | 1758/JMD | 19/07/2023 | 120 | K.S.P. ENTERPRISE | 5.74 | 3.89 | 75
55 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rai Gani, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000099/2023-2024 | 1759/JMD | 19/07/2023 | 120 | DEBJYOTI BASU | 5.77 | 5.1 | 92
56 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rai Gani, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000100/2023-2024 | 1760/JMD | 19/07/2023 | 120 | ABHIJIT BASU | 5.78 | 5.74 | 100
57 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumaria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000101/2023-2024 | 1761/JMD | 19/07/2023 | 120 | S. PATHAK & CO. | 5.76 | 5.18 | 95
58 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpahari Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000102/2023-2024 | 1762/JMD | 19/07/2023 | 120 | ASHOKE ADHIKARY | 5.76 | 5.08 | 95
59 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Damodarpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000103/2023-2024 | 1763/JMD | 19/07/2023 | 120 | RS ELECTROMECHANICAL CORPORATION | 5.78 | 3.78 | 90
60 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Taldangra Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000104/2023-2024 | 1764/JMD | 19/07/2023 | 650 | DAS CONSTRUCTION | 5.78 | 0 | 0
61 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Phulbani, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000105/2023-2024 | 1765/JMD | 19/07/2023 | 651 | M/S D.G.B. ENTERPRISE | 5.78 | 3.78 | 70
62 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Phulbani, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000107/2023-2024 | 1766/JMD | 19/07/2023 | 120 | JAL PRAVAHIKA PVT. LTD. | 5.78 | 3.78 | 80
63 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000108/2023-2024 | 1767/JMD | 19/07/2023 | 120 | PRANAB KUMAR DAS | 5.78 | 0 | 0
64 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-V Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000109/2023-2024 | 1768/JMD | 19/07/2023 | 120 | RITESH ENTERPRISE | 5.78 | 0 | 0
65 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-VI Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000110/2023-2024 | 1769/JMD | 19/07/2023 | 120 | ECO ENTERPRISE | 5.77 | 0 | 0
66 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Patina, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000111/2023-2024 | 1770/JMD | 19/07/2023 | 514 | SUJOY RANJAN BHOWMICK | 5.78 | 3.78 | 70
67 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Deulbar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000112/2023-2024 | 1771/JMD | 19/07/2023 | 120 | ABHIJIT BASU | 5.78 | 5.75 | 100
68 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Narda, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000113/2023-2024 | 1772/JMD | 19/07/2023 | 120 | MAA BHABOTARINE ENTERPRISE | 5.78 | 0 | 0
69 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dulki, Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000114/2023-2024 | 1795/JMD | 24/07/2023 | 120 | BHABANI PRASAD MANNA | 5.78 | 0 | 0
70 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gorur Ghata Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000115/2023-2024 | 1796/JMD | 24/07/2023 | 240 | BEE GEE CONSTRUCTION | 5.78 | 5.19 | 96
71 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gokhur Pal Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000116/2023-2024 | 1797/JMD | 24/07/2023 | 120 | BUSR ENGINEERING | 5.77 | 5.15 | 95
72 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Jharia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000117/2023-2024 | 1798/JMD | 24/07/2023 | 120 | SWAPAN ENTERPRISE | 5.78 | 0 | 0
73 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bans Pat Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000118/2023-2024 | 1799/JMD | 24/07/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 4.15 | 70
74 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nara Singha Pur, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000119/2023-2024 | 1801/JMD | 24/07/2023 | 120 | M/S. SAJAHAN CHOWDHURY | 5.78 | 0 | 0
75 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nara Singha Pur, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000120/2023-2024 | 1802/JMD | 24/07/2023 | 120 | DAS CONSTRUCTION | 5.78 | 0 | 0
76 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jadabpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000121/2023-2024 | 1803/JMD | 24/07/2023 | 120 | PADMA ENGINEERING CO. | 5.78 | 3.78 | 80
77 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000122/2023-2024 | 1804/JMD | 24/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0
78 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000123/2023-2024 | 1805/JMD | 24/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0
79 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000124/2023-2024 | 1806/JMD | 24/07/2023 | 120 | M/S. EMMESS | 5.78 | 3.78 | 90
80 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalma Pukhuria, Tube Well no.-V Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000125/2023-2024 | 1807/JMD | 24/07/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 5.2 | 100
81 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Malam, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000127/2023-2024 | 1819/JMD | 24/07/2023 | 120 | DEBJYOTI BASU | 5.77 | 0 | 0
82 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Malam, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000128/2023-2024 | 1820/JMD | 24/07/2023 | 120 | ABHIJIT BASU | 5.78 | 4.15 | 70
83 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tikra Para Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000129/2023-2024 | 1821/JMD | 24/07/2023 | 120 | JIBON GHOSH | 5.78 | 3.78 | 80
84 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Bandh, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000130/2023-2024 | 1822/JMD | 24/07/2023 | 599 | ECO ENTERPRISE | 5.77 | 0 | 80
85 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Bandh, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000131/2023-2024 | 1823/JMD | 24/07/2023 | 120 | CHAKRABORTY MINING & ENGINEERING | 5.77 | 5.11 | 100
86 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Kati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000132/2023-2024 | 1824/JMD | 24/07/2023 | 120 | PRANAB KUMAR DAS | 5.78 | 0 | 0
87 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kadokota Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000133/2023-2024 | 1825/JMD | 24/07/2023 | 120 | BHABANI PRASAD MANNA | 5.78 | 0 | 0
88 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kukrasole, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000134/2023-2024 | 1826/JMD | 24/07/2023 | 120 | SWAPAN ENTERPRISE | 5.78 | 0 | 0
89 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chanda Bila stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000135/2022-2023 | 1409/JMD | 14/07/2022 | 120 | DEBJYOTI BASU | 6.84 | 6.83 | 85
90 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000135/2023-2024 | 1827/JMD | 24/07/2023 | 120 | RITESH ENTERPRISE | 5.78 | 0 | 0
91 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Madhabpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000136/2022-2023 | 1410/JMD | 14/07/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 5.56 | 95
92 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000136/2023-2024 | 1828/JMD | 24/07/2023 | 704 | B. P. TRADING CORPORATION | 5.78 | 3.78 | 90
93 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narcha stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000137/2022-2023 | 1411/JMD | 14/07/2022 | 120 | ABHIJIT BASU | 6.86 | 6.85 | 50
94 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Arra, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000137/2023-2024 | 1829/JMD | 24/07/2023 | 120 | SRI KRISHNA NIRMAN | 5.78 | 5.04 | 80
95 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000138/2022-2023 | 1412/JMD | 14/07/2022 | 120 | DEBJYOTI BASU | 6.84 | 4.05 | 98
96 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumuria, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000138/2023-2024 | 1830/JMD | 24/07/2023 | 120 | A.S. ENTERPRISE | 5.78 | 0 | 0
97 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kumarbandh stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000139/2022-2023 | 1413/JMD | 14/07/2022 | 120 | BHABANI PRASAD MANNA | 6.86 | 4.79 | 95
98 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dumuria, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000139/2023-2024 | 1831/JMD | 24/07/2023 | 120 | ARATI ENGINEERING | 5.78 | 0 | 0
99 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Lakshanpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000140/2022-2023 | 1414/JMD | 14/07/2022 | 120 | M/S. EMMESS | 6.83 | 4.83 | 100
100 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jari Ghati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000140/2023-2024 | 1832/JMD | 24/07/2023 | 453 | SUJOY RANJAN BHOWMICK | 5.78 | 4.15 | 80
101 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kank Para stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000141/2022-2023 | 1415/JMD | 14/07/2022 | 120 | KAMAKHYA ENTERPRISE | 6.8 | 4.69 | 0
102 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sal Bani Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000141/2023-2024 | 1833/JMD | 24/07/2023 | 120 | JAGANNATH ENTERPRISE | 5.78 | 5.11 | 96
103 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kank Para stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000142/2022-2023 | 1416/JMD | 14/07/2022 | 120 | SHOVAN KUMAR DAS | 6.86 | 4.73 | 0
104 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000142/2023-2024 | 1834/JMD | 24/07/2023 | 120 | P.K. ENGINEERING | 5.78 | 0 | 0
105 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Damujana stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000143/2022-2023 | 1417/JMD | 14/07/2022 | 120 | SUBHASIS ROY | 6.87 | 6.84 | 100
106 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000143/2023-2024 | 1835/JMD | 24/07/2023 | 120 | AMIT DAS | 5.77 | 0 | 0
107 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Goal Danga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000144/2022-2023 | 1418/JMD | 14/07/2022 | 120 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 7.02 | 7.02 | 100
108 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bardhan Sola (G.P.- Kharikamathani), Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000144/2023-2024 | 1836/JMD | 24/07/2023 | 120 | M.D. ENTERPRISE | 5.77 | 0 | 0
109 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000145/2022-2023 | 1419/JMD | 14/07/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 6.31 | 100
110 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nandalalpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000145/2023-2024 | 1837/JMD | 24/07/2023 | 120 | SUBHASIS ROY | 5.77 | 0 | 0
111 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bankisol Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000146/2023-2024 | 1838/JMD | 24/07/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 5.19 | 100
112 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jarkasol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000147/2022-2023 | 1452/JMD | 19/07/2022 | 120 | BUSR ENGINEERING | 6.86 | 6.83 | 100
113 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bankati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000147/2023-2024 | 1839/JMD | 24/07/2023 | 120 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD | 5.77 | 0 | 0
114 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Phul Berya stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000148/2022-2023 | 1453/JMD | 19/07/2022 | 120 | DEB KUMAR BASU | 6.86 | 6.83 | 100
115 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Swarup Narayanpur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000148/2023-2024 | 1840/JMD | 24/07/2023 | 120 | ECO ENTERPRISE | 5.78 | 3.78 | 95
116 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bankra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000149/2022-2023 | 1454/JMD | 19/07/2022 | 120 | MONORANJAN DEY | 6.86 | 5.04 | 10
117 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dingla Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000149/2023-2024 | 1841/JMD | 24/07/2023 | 120 | A.M.S. ENTERPRISE | 5.75 | 5.72 | 100
118 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000150/2022-2023 | 1455/JMD | 19/07/2022 | 120 | SUBHAM ENTERPRISE | 6.86 | 5.04 | 0
119 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhadai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000151/2022-2023 | 1456/JMD | 19/07/2022 | 120 | P.K. ENGINEERING | 6.86 | 6.83 | 100
120 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Rai Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000152/2022-2023 | 1457/JMD | 19/07/2022 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 6.87 | 6.84 | 100
121 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narda stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000153/2022-2023 | 1458/JMD | 19/07/2022 | 120 | ECO ENTERPRISE | 6.87 | 6.85 | 100
122 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000154/2022-2023 | 1459/JMD | 19/07/2022 | 120 | M/S D.G.B. ENTERPRISE | 6.87 | 5.03 | 0
123 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Muniada T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000156/2023-2024 | 1967/JMD | 31/07/2023 | 220 | RUBY ENTERPRISE | 5.78 | 5.17 | 100
124 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Andharisol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000157/2023-2024 | 1968/JMD | 31/07/2023 | 306 | BALAJI CONSTRUCTION | 5.78 | 5.07 | 100
125 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khasjangal, Tube Well no.-III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000158/2023-2024 | 1969/JMD | 31/07/2023 | 120 | M/S B.M. ELECTRICAL | 5.78 | 0 | 0
126 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tiyakati, Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000159/2023-2024 | 1970/JMD | 31/07/2023 | 120 | SUBHAM ENTERPRISE | 5.78 | 2.76 | 60
127 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000160/2022-2023 | 1460/JMD | 19/07/2022 | 120 | JAL PRAVAHIKA PVT. LTD. | 6.87 | 5.03 | 0
128 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nagri Pada, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000160/2023-2024 | 1971/JMD | 31/07/2023 | 120 | SHOVAN KUMAR DAS | 5.78 | 5.09 | 95
129 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garkhelar stand alone piped water supply scheme, tube well no.-III of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000161/2022-2023 | 1461/JMD | 19/07/2022 | 120 | BALAJI CONSTRUCTION | 6.86 | 0 | 0
130 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nagri Pada, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000161/2023-2024 | 1972/JMD | 31/07/2023 | 773 | S.S. GHORAI | 5.78 | 0 | 100
131 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sri Ram Pur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000162/2022-2023 | 1462/JMD | 19/07/2022 | 120 | MENAKA ENTERPRISE | 6.87 | 6.85 | 100
132 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kul Diha, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000162/2023-2024 | 1973/JMD | 31/07/2023 | 598 | SOUMEN ELECTRIC | 5.78 | 4.15 | 100
133 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Arra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000163/2022-2023 | 1463/JMD | 19/07/2022 | 120 | M/S B.M. ELECTRICAL | 6.86 | 5.04 | 95
134 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khas Jangal (G.P. - Malam) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000163/2023-2024 | 1974/JMD | 31/07/2023 | 120 | J.K. ENGINEERING CO. | 5.78 | 3.91 | 90
135 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Hanri Bhanga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000164/2022-2023 | 1464/JMD | 19/07/2022 | 120 | PRANAB KUMAR DAS | 6.86 | 6.78 | 100
136 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kulghagri stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000165/2022-2023 | 1465/JMD | 19/07/2022 | 120 | SOUMEN ELECTRIC | 6.86 | 5.04 | 100
137 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangua T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000165/2023-2024 | 2021/JMD | 02/08/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 5.44 | 100
138 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Tungadhua stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000166/2022-2023 | 1466/JMD | 19/07/2022 | 120 | T.N. BANERJEE | 6.86 | 6.81 | 100
139 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhalia Chati Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000166/2023-2024 | 2022/JMD | 02/08/2023 | 120 | A. G. ENTERPRISE | 5.78 | 0 | 0
140 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Tungadhua stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000167/2022-2023 | 1467/JMD | 19/07/2022 | 120 | DEY ENTERPRISE | 6.79 | 6.25 | 95
141 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kuldiha Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000167/2023-2024 | 2032/JMD | 02/08/2023 | 120 | EASTERN INDIA SALES AND SERVICE | 5.77 | 0 | 0
142 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000168/2022-2023 | 1468/JMD | 19/07/2022 | 120 | S.S. GHORAI | 6.86 | 6.81 | 100
143 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000169/2022-2023 | 1469/JMD | 19/07/2022 | 120 | RITESH ENTERPRISE | 6.89 | 6.34 | 95
144 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhalki Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000170/2022-2023 | 1470/JMD | 19/07/2022 | 120 | M/S. EMMESS | 6.83 | 4.83 | 100
145 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000171/2022-2023 | 1471/JMD | 19/07/2022 | 120 | SOUMEN ELECTRIC | 6.86 | 5.04 | 100
146 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000172/2022-2023 | 1472/JMD | 19/07/2022 | 120 | MAA BHABOTARINE ENTERPRISE | 6.86 | 5.03 | 0
147 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Paschim Gholai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000173/2022-2023 | 1473/JMD | 19/07/2022 | 120 | M/S. NABIN GOPAL SENGUPTA | 6.87 | 6.79 | 100
148 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Amtalia stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000180/2022-2023 | 1585/JMD | 27/07/2022 | 120 | MENAKA ENTERPRISE | 6.87 | 6.84 | 90
149 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghakhondar stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000181/2022-2023 | 1586/JMD | 27/07/2022 | 120 | ABHIJIT BASU | 6.86 | 6.83 | 90
150 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sankisol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000182/2022-2023 | 1587/JMD | 27/07/2022 | 120 | DEB KUMAR BASU | 6.86 | 6.83 | 100
151 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chilkigar stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000183/2022-2023 | 1588/JMD | 27/07/2022 | 120 | DIPALI CONSTRUCTION | 6.79 | 6.77 | 95
152 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sonamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000184/2022-2023 | 1589/JMD | 27/07/2022 | 120 | P.K. ENGINEERING | 6.86 | 6.31 | 10
153 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Purna Pani stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000185/2022-2023 | 1590/JMD | 27/07/2022 | 120 | SUBHASIS ROY | 6.86 | 6.85 | 100
154 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghjhapa stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000186/2022-2023 | 1591/JMD | 27/07/2022 | 120 | M/S. SAMRIDDHI ENTERPRISE | 7.02 | 7.01 | 100
155 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhurkundi stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000187/2022-2023 | 1592/JMD | 27/07/2022 | 120 | M/S. SAJAHAN CHOWDHURY | 6.82 | 6.77 | 100
156 | Jhargram Mechanical Division | Jhargram Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Kuldiha under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000219/2023-2024 | 2286/JMD | 10/08/2023 | 510 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 100
157 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Shutpipal stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000261/2022-2023 | 1728/JMD | 17/08/2022 | 120 | DEBJYOTI BASU | 6.84 | 6.82 | 100
158 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kargonala stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000262/2022-2023 | 1729/JMD | 17/08/2022 | 120 | ECO ENTERPRISE | 6.87 | 6.85 | 100
159 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bag Doba stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000263/2022-2023 | 1730/JMD | 17/08/2022 | 120 | SHOVAN KUMAR DAS | 6.87 | 6.84 | 100
160 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kalma Pukhuria stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000264/2022-2023 | 1731/JMD | 17/08/2022 | 120 | S.S. GHORAI | 6.86 | 6.84 | 100
161 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bara Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000265/2022-2023 | 1732/JMD | 17/08/2022 | 120 | M/S. EMMESS | 6.83 | 6.82 | 0
162 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dhobani Sol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000266/2022-2023 | 1735/JMD | 17/08/2022 | 120 | DAS CONSTRUCTION | 6.85 | 6.24 | 0
163 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chhota Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000267/2022-2023 | 1733/JMD | 17/08/2022 | 120 | A. G. ENTERPRISE | 6.85 | 6.81 | 95
164 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chhota Tal Pada stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000268/2022-2023 | 1734/JMD | 17/08/2022 | 120 | GOENKA ENTERPRISE | 6.86 | 5.02 | 0
165 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jamda Hara stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000269/2022-2023 | 1736/JMD | 17/08/2022 | 120 | MASSK ENGINEERING WORKS | 6.86 | 6.84 | 100
166 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jhaurishol stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000270/2022-2023 | 1737/JMD | 17/08/2022 | 120 | S.K. ENTERPRISE | 6.85 | 6.83 | 100
167 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Jhaurishol stand alone piped water supply scheme, tube well no.-II of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000271/2022-2023 | 1738/JMD | 17/08/2022 | 120 | M/S. P.P. ELECTRICALS | 6.85 | 6.27 | 0
168 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khatkura Jr. High School Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000294/2023-2024 | 2633/JMD | 29/08/2023 | 120 | MOUSUMI BANERJEE | 5.77 | 5.74 | 100
169 | Jhargram Mechanical Division | Jhargram Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Dhengabahara, Tube Well no.-II under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000295/2023-2024 | 2634/JMD | 29/08/2023 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 2.31 | 100
170 | Jhargram Mechanical Division | Jhargram Division | Supply and delivery of Bentonite Powder sodium based (Rajasthan Varity) at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000296/2023-2024 | 2635/JMD | 29/08/2023 | 10 | DEBJYOTI BASU | 2.24 | 2.24 | 100
171 | Jhargram Mechanical Division | Jhargram Division | Supply and Delivery of Ø 7-7/8 " Drag Bit with Tungsten Carbide insert for Mud Rotary Drilling at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000297/2023-2024 | 2636/JMD | 29/08/2023 | 10 | B. P. TRADING CORPORATION | 2.77 | 2.77 | 100
172 | Jhargram Mechanical Division | Jhargram Division | Supply and Delivery of Ø 9 " Drag Bit with Tungsten Carbide insert for Mud Rotary Drilling at MMSD(D) store room for sinking of Rig Bored Tube Wells under MMSD(D) under JMD PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000298/2023-2024 | 2637/JMD | 29/08/2023 | 10 | SUDIP ENGINEERING CO. | 1.5 | 1.5 | 100
173 | Jhargram Mechanical Division | Jhargram Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Khatkura Junior High School under Jamboni Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000357/2023-2024 | 2785/JMD | 07/09/2023 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 2.1 | 100
174 | Jhargram Mechanical Division | Jhargram Division | Dismantling the differential gear portion of HALCO Rig unit under Bankura Mechanical Division (BMD) and carrying the same from BMD to Jhargram Mechanical Division (JMD) for fitting fixing in 238/AR/HALCO Rig unit under MMSD(D) under JMD, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000433/2021-2022 | 350/JMD | 04/03/2022 | 10 | CHAKRABORTY MINING & ENGINEERING | 0.14 | 0.14 | 100
175 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Aguibil T/W no. I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000516/2022-2023 | 3064/JMD | 28/09/2022 | 120 | MENAKA ENTERPRISE | 6.79 | 0 | 0
176 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amlasol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000517/2022-2023 | 3065/JMD | 28/09/2022 | 120 | P.K. ENGINEERING | 6.79 | 6.09 | 0
177 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000518/2022-2023 | 3066/JMD | 28/09/2022 | 682 | DEBJYOTI BASU | 6.79 | 4.4 | 100
178 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kendisol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000519/2022-2023 | 3067/JMD | 28/09/2022 | 120 | SOUMEN ELECTRIC | 6.79 | 4.86 | 0
179 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Hudhudi T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000521/2022-2023 | 3069/JMD | 28/09/2022 | 120 | RMD TRADING | 5.7 | 5.69 | 100
180 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shibanandapur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000522/2022-2023 | 3070/JMD | 28/09/2022 | 120 | BALAJI CONSTRUCTION | 5.71 | 5.68 | 100
181 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara (School) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000523/2022-2023 | 3071/JMD | 28/09/2022 | 120 | MONORANJAN DEY | 5.71 | 5.68 | 100
182 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (Pal) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000524/2022-2023 | 3072/JMD | 28/09/2022 | 120 | M/S. EMMESS | 5.71 | 5.68 | 100
183 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Village) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000526/2022-2023 | 3093/JMD | 28/09/2022 | 120 | CHATTERJEE CONSTRUCTION | 5.71 | 5.69 | 100
184 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khanakul T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000527/2022-2023 | 3085/JMD | 28/09/2022 | 120 | RSA ENTERPRISE | 5.71 | 5.68 | 0
185 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Chakri T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000528/2022-2023 | 3084/JMD | 28/09/2022 | 120 | B. P. TRADING CORPORATION | 5.71 | 5.7 | 100
186 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Mahuli T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000529/2022-2023 | 3073/JMD | 28/09/2022 | 120 | SUBHASIS ROY | 5.7 | 5.12 | 0
187 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000530/2022-2023 | 3074/JMD | 28/09/2022 | 120 | SWAPAN ENTERPRISE | 5.71 | 4.99 | 0
188 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Topoban T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000531/2022-2023 | 3075/JMD | 28/09/2022 | 120 | M/S D.G.B. ENTERPRISE | 5.71 | 5.7 | 0
189 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Topoban T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000532/2022-2023 | 3076/JMD | 28/09/2022 | 120 | JAL PRAVAHIKA PVT. LTD. | 5.71 | 5.7 | 0
190 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murakati T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000533/2022-2023 | 3077/JMD | 28/09/2022 | 120 | A. G. ENTERPRISE | 5.7 | 5.68 | 100
191 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bam Diha T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000534/2022-2023 | 3078/JMD | 28/09/2022 | 120 | BIJAN ENTERPRISE | 5.7 | 3.78 | 80
192 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rangamatia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000536/2022-2023 | 3079/JMD | 28/09/2022 | 120 | J.K. ENGINEERING CO. | 5.7 | 5.67 | 100
193 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Choto Jharia T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000537/2022-2023 | 3080/JMD | 28/09/2022 | 120 | ASHUTOSH DAS & CO. | 5.63 | 5.02 | 0
194 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amla Kora T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000538/2022-2023 | 3081/JMD | 28/09/2022 | 120 | A.M.S. ENTERPRISE | 5.7 | 0 | 0
195 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amla Kora T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000539/2022-2023 | 3082/JMD | 28/09/2022 | 120 | MAA BHABOTARINE ENTERPRISE | 5.71 | 4.13 | 0
196 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nuagarh T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000540/2022-2023 | 3083/JMD | 28/09/2022 | 120 | CHAKRABORTY MINING & ENGINEERING | 5.7 | 5.69 | 100
197 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Didiha T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000541/2022-2023 | 3086/JMD | 28/09/2022 | 120 | BEE GEE CONSTRUCTION | 5.7 | 5.7 | 100
198 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000542/2022-2023 | 3087/JMD | 28/09/2022 | 120 | S.K. ENTERPRISE | 5.71 | 5.68 | 100
199 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Brindabanpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000543/2022-2023 | 3088/JMD | 28/09/2022 | 120 | A.S. ENTERPRISE | 5.7 | 5.7 | 100
200 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near Club) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000544/2022-2023 | 3089/JMD | 28/09/2022 | 120 | SAMARPITA ENGINEERING | 5.72 | 5.68 | 100
201 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000545/2022-2023 | 3090/JMD | 28/09/2022 | 120 | SUBHASIS ROY | 5.7 | 5.64 | 100
202 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000546/2022-2023 | 3091/JMD | 28/09/2022 | 120 | M/S. SAMRIDDHI ENTERPRISE | 5.71 | 5.69 | 100
203 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000547/2022-2023 | 3092/JMD | 28/09/2022 | 120 | ECO ENTERPRISE | 5.71 | 5.69 | 100
204 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Purba Para) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000548/2022-2023 | 3094/JMD | 28/09/2022 | 120 | DEB KUMAR BASU | 5.71 | 5.69 | 100
205 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000549/2022-2023 | 3156/JMD | 19/10/2022 | 120 | DEBJYOTI BASU | 5.71 | 5.68 | 100
206 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Balia Geria T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000550/2022-2023 | 3157/JMD | 19/10/2022 | 120 | BUSR ENGINEERING | 5.7 | 5.1 | 0
207 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khanderpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000551/2022-2023 | 3098/JMD | 28/09/2022 | 120 | SANJIB SAHA | 5.72 | 4.79 | 90
208 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000552/2022-2023 | 3097/JMD | 28/09/2022 | 120 | DEB KUMAR BASU | 5.75 | 5.74 | 100
209 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Ramchandrapur) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000553/2022-2023 | 3158/JMD | 19/10/2022 | 120 | DEB KUMAR BASU | 5.71 | 5.69 | 0
210 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Kutisai) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000554/2022-2023 | 3159/JMD | 19/10/2022 | 120 | ABHIJIT BASU | 5.71 | 5.69 | 100
211 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000555/2022-2023 | 3160/JMD | 19/10/2022 | 120 | M/S MANABESH ROY | 5.71 | 5.68 | 0
212 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000556/2022-2023 | 3161/JMD | 19/10/2022 | 120 | KAMAKHYA ENTERPRISE | 5.71 | 4.82 | 0
213 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhirighutu T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000557/2022-2023 | 3162/JMD | 19/10/2022 | 120 | JAGANNATH ENTERPRISE | 5.72 | 5.08 | 0
214 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kiajharia T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000558/2022-2023 | 3163/JMD | 19/10/2022 | 120 | M/S. CHANDRANATH MUKHERJEE | 5.71 | 5.67 | 95
215 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Pry. School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000559/2022-2023 | 3164/JMD | 19/10/2022 | 120 | S.S. GHORAI | 5.71 | 5.11 | 0
216 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bag Doba T/W no. II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000565/2022-2023 | 3165/JMD | 19/10/2022 | 120 | M/S. NABIN GOPAL SENGUPTA | 5.71 | 5.14 | 0
217 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baradhan Sola T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000566/2022-2023 | 3166/JMD | 19/10/2022 | 120 | M.D. ENTERPRISE | 5.7 | 5.67 | 0
218 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tiakati T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000567/2022-2023 | 3167/JMD | 19/10/2022 | 120 | AMIT DAS | 5.71 | 5.68 | 0
219 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Antapati T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000568/2022-2023 | 3168/JMD | 19/10/2022 | 120 | R.K. ENTERPRISES | 5.7 | 5.69 | 0
220 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kalinagar T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000569/2022-2023 | 3169/JMD | 19/10/2022 | 120 | SHIVAM ENTERPRISE | 5.7 | 5.69 | 0
221 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (A.W.C.) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000570/2022-2023 | 3170/JMD | 19/10/2022 | 120 | M/S. EMMESS | 5.7 | 5.68 | 100
222 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jamboni T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000578/2022-2023 | 3192/JMD | 28/10/2022 | 120 | ARATI ENGINEERING | 5.72 | 5.7 | 100
223 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dubrajpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000579/2022-2023 | 3193/JMD | 28/10/2022 | 120 | BOSE AND CHATTERJEE INDUSTRIES | 5.68 | 5.11 | 0
224 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Bardanga) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000580/2022-2023 | 3194/JMD | 28/10/2022 | 120 | SUJOY RANJAN BHOWMICK | 5.71 | 5.7 | 100
225 | Jhargram Mechanical Division | Jhargram Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary / Combination Method at Panisol Primary School under Gopiballavpur-I Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000583/2023-2024 | 2984/JMD | 16/10/2023 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.37 | 0 | 100
226 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhulaburari T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000591/2022-2023 | 3324/JMD | 14/11/2022 | 120 | SUJOY RANJAN BHOWMICK | 5.71 | 5.7 | 100
227 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Niramishpur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000610/2022-2023 | 3620/JMD | 07/12/2022 | 120 | BUSR ENGINEERING | 5.7 | 5.68 | 100
228 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Goal Danga T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000611/2022-2023 | 3621/JMD | 07/12/2022 | 120 | MAA TARA ENTERPRISE | 5.72 | 5.69 | 100
229 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000612/2022-2023 | 3622/JMD | 07/12/2022 | 120 | PRANAB KUMAR DAS | 5.7 | 5.68 | 95
230 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000613/2022-2023 | 3623/JMD | 07/12/2022 | 120 | BHABANI PRASAD MANNA | 5.72 | 5.7 | 100
231 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000614/2022-2023 | 3624/JMD | 07/12/2022 | 120 | M/S B.M. ELECTRICAL | 5.7 | 5.01 | 0
232 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000615/2022-2023 | 3625/JMD | 07/12/2022 | 120 | RITESH ENTERPRISE | 5.71 | 5.69 | 100
233 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Muniada T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000620/2022-2023 | 3626/JMD | 07/12/2022 | 480 | R.N.S. TRADING | 5.73 | 0 | 100
234 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Khatkhura T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000621/2022-2023 | 3627/JMD | 07/12/2022 | 120 | SHOVAN KUMAR DAS | 5.72 | 4.15 | 10
235 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jugi Bandh T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000622/2022-2023 | 3628/JMD | 07/12/2022 | 120 | SUBHAM ENTERPRISE | 5.73 | 5.71 | 100
236 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jugi Bandh T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000623/2022-2023 | 3629/JMD | 07/12/2022 | 480 | COMBINE ENTERPRISES | 5.71 | 5.1 | 100
237 | Jhargram Mechanical Division | Jhargram Division | Hiring of Diesel driven Commercial Covered four wheeler vehicle on daily basis along with LMV licensed driver for official purpose of Assistant Engineer, Jhargram Mechanical Division under office of Executive Engineer, Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000645/2021-2022 | 340/JMD | 03/03/2022 | 362 | SUBHASIS ROY | 1.68 | 1.22 | 100
238 | Jhargram Mechanical Division | Jhargram Division | Supply,delivery, installation, commisioning & trial run of submersible pumping machinary and other Electro Mechanical accessories for Chandabila Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000655/2022-2023 | 4194/JMD | 28/12/2022 | 120 | BINAPANI ENTERPRISE | 5.78 | 5.04 | 80
239 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhadka Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000656/2022-2023 | 4195/JMD | 28/12/2022 | 735 | J.K. ENGINEERING CO. | 5.78 | 3.92 | 100
240 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Degaria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000657/2022-2023 | 4196/JMD | 28/12/2022 | 120 | CHATTERJEE CONSTRUCTION | 5.78 | 5.75 | 100
241 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Rajgram Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000658/2022-2023 | 4197/JMD | 28/12/2022 | 120 | DIPALI CONSTRUCTION | 5.78 | 5.16 | 0
242 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salika Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000659/2022-2023 | 4198/JMD | 28/12/2022 | 120 | DIPALI CONSTRUCTION | 5.78 | 5.16 | 80
243 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tukurya Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000660/2022-2023 | 4199/JMD | 28/12/2022 | 120 | RADHARANI ENTERPRISE | 5.77 | 5.16 | 100
244 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Nargi Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000661/2022-2023 | 4200/JMD | 28/12/2022 | 120 | A. G. ENTERPRISE | 5.77 | 0 | 75
245 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Gaida Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000662/2022-2023 | 4201/JMD | 28/12/2022 | 120 | A.S. ENTERPRISE | 5.78 | 5.75 | 100
246 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhengbahara Stand Alone piped water supply scheme, tube well no-I of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000663/2022-2023 | 4202/JMD | 28/12/2022 | 765 | SUBHRA ENTERPRISE | 5.78 | 3.78 | 100
247 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Sahari Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000664/2022-2023 | 4203/JMD | 28/12/2022 | 120 | PINTU DEY | 5.78 | 5.75 | 100
248 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhengbahara Stand Alone piped water supply scheme, tube well no-II of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000665/2022-2023 | 4204/JMD | 28/12/2022 | 643 | M/S. NABIN GOPAL SENGUPTA | 5.78 | 0 | 100
249 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluka Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000666/2022-2023 | 4205/JMD | 28/12/2022 | 459 | COMBINE ENTERPRISES | 5.78 | 5.17 | 95
250 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chilkigarh Stand Alone piped water supply scheme, tube well no-II of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000667/2022-2023 | 4206/JMD | 28/12/2022 | 120 | BUSR ENGINEERING | 5.77 | 5.73 | 100
251 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chilkigarh Stand Alone piped water supply scheme, tube well no-III of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000668/2022-2023 | 4207/JMD | 28/12/2022 | 120 | KAMAKHYA ENTERPRISE | 5.76 | 0 | 0
252 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chilkigarh Stand Alone piped water supply scheme, tube well no-IV of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000669/2022-2023 | 4208/JMD | 28/12/2022 | 120 | KAMAKHYA ENTERPRISE | 5.75 | 0 | 0
253 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jirapara Stand Alone piped water supply scheme, tube well no-I of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000670/2022-2023 | 4209/JMD | 28/12/2022 | 120 | ABHIJIT BASU | 5.78 | 5.21 | 0
254 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Barighati T/W no. I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000671/2022-2023 | 4210/JMD | 28/12/2022 | 120 | MAA BHABOTARINE ENTERPRISE | 6.84 | 0 | 0
255 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lekraanchra T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000672/2022-2023 | 4211/JMD | 28/12/2022 | 120 | MANAS KUMAR SAHA | 6.84 | 0 | 0
256 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Naharia, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000684/2022-2023 | 136/JMD | 18/01/2023 | 120 | SOUMEN ELECTRIC | 5.78 | 5.76 | 0
257 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Harki Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000685/2022-2023 | 137/JMD | 18/01/2023 | 120 | PADMA ENGINEERING CO. | 5.78 | 5.76 | 100
258 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tentulia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000686/2022-2023 | 142/JMD | 19/01/2023 | 718 | SOUMEN ELECTRIC | 5.78 | 4.15 | 70
259 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Marchi Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000687/2022-2023 | 143/JMD | 19/01/2023 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 5.78 | 0 | 0
260 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Ram Chandra Pur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000688/2022-2023 | 144/JMD | 19/01/2023 | 120 | SUJOY RANJAN BHOWMICK | 5.78 | 5.17 | 10
261 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000689/2022-2023 | 145/JMD | 19/01/2023 | 120 | DEBJYOTI BASU | 5.77 | 5.1 | 97
262 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Murar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000690/2022-2023 | 146/JMD | 19/01/2023 | 120 | MAA BHABOTARINE ENTERPRISE | 5.77 | 5.75 | 100
263 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shutpipal, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000691/2022-2023 | 147/JMD | 19/01/2023 | 120 | M/S. NABIN GOPAL SENGUPTA | 5.78 | 4.21 | 95
264 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Narendrapur Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000692/2022-2023 | 148/JMD | 19/01/2023 | 120 | CHATTERJEE CONSTRUCTION | 5.77 | 5.75 | 100
265 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Benachapra Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000693/2022-2023 | 149/JMD | 19/01/2023 | 792 | ABHIJIT MUKHERJEE | 5.78 | 0 | 100
266 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Naharia, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000695/2022-2023 | 150/JMD | 19/01/2023 | 120 | SUBHASIS ROY | 5.77 | 5.77 | 100
267 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narcha stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000700/2022-2023 | 3432/JMD | 29/11/2022 | 763 | ABHIJIT BASU | 0.07 | 0 | 100
268 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Ramchandrapur) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000701/2022-2023 | 3490/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0
269 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sankisol stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000702/2022-2023 | 3541/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0
270 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Phul Berya stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000703/2022-2023 | 3538/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 100
271 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Purba Para) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000704/2022-2023 | 3486/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0
272 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Maubhandar, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000705/2022-2023 | 255/JMD | 03/02/2023 | 120 | DEY ENTERPRISE | 5.78 | 5.75 | 100
273 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Menia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000706/2022-2023 | 256/JMD | 03/02/2023 | 120 | M/S A.D. CONCERN | 5.78 | 5.71 | 95
274 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kandnashol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000707/2022-2023 | 257/JMD | 03/02/2023 | 120 | M/S. EMMESS | 5.78 | 5.76 | 100
275 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Biriberia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000708/2022-2023 | 258/JMD | 03/02/2023 | 120 | MAA TARA ENTERPRISE | 5.78 | 5.75 | 100
276 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Jamboni Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000709/2022-2023 | 259/JMD | 03/02/2023 | 120 | DEB KUMAR BASU | 5.78 | 5.75 | 95
277 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Sol, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000710/2022-2023 | 260/JMD | 03/02/2023 | 451 | M/S D.G.B. ENTERPRISE | 5.78 | 5.19 | 0
278 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Sol, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000711/2022-2023 | 261/JMD | 03/02/2023 | 120 | JAL PRAVAHIKA PVT. LTD. | 5.78 | 0 | 0
279 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Parashia, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000712/2022-2023 | 262/JMD | 03/02/2023 | 120 | RSA ENTERPRISE | 5.78 | 5.75 | 100
280 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Parashia, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000713/2022-2023 | 263/JMD | 03/02/2023 | 120 | RSA ENTERPRISE | 5.78 | 5.75 | 100
281 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bali Muri Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000714/2022-2023 | 264/JMD | 03/02/2023 | 120 | P.K. ENGINEERING | 5.78 | 4.15 | 80
282 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai, Tube Well no.-IV Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000715/2022-2023 | 266/JMD | 03/02/2023 | 120 | ABHIJIT BASU | 5.78 | 5.75 | 100
283 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000716/2022-2023 | 267/JMD | 03/02/2023 | 120 | DEBJYOTI BASU | 5.77 | 5.15 | 10
284 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Mura Kati (G.P. - Barakhankri) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000717/2022-2023 | 268/JMD | 03/02/2023 | 120 | DAS CONSTRUCTION | 5.76 | 5.07 | 95
285 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Kutisai) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000718/2022-2023 | 3491/JMD | 29/11/2022 | 7 | ABHIJIT BASU | 0.07 | 0 | 0
286 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Purna Pani stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000719/2022-2023 | 3516/JMD | 29/11/2022 | 7 | SUBHASIS ROY | 0.07 | 0 | 0
287 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghakhondar stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000720/2022-2023 | 3542/JMD | 29/11/2022 | 7 | ABHIJIT BASU | 0.07 | 0 | 100
288 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rajpara T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000721/2022-2023 | 3519/JMD | 29/11/2022 | 7 | DEB KUMAR BASU | 0.07 | 0 | 0
289 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhansola Chhota Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000728/2022-2023 | 311/JMD | 09/02/2023 | 120 | RADHARANI ENTERPRISE | 5.77 | 5.75 | 95
290 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Maubhandar, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000731/2022-2023 | 462/JMD | 09/03/2023 | 120 | DEY ENTERPRISE | 5.78 | 3.92 | 100
291 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Madhabpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000733/2022-2023 | 3431/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0.07 | 100
292 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000734/2022-2023 | 3444/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0.07 | 100
293 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bachhur Khoyar (Bardanga) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000735/2022-2023 | 3488/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0
294 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhulaburari T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000736/2022-2023 | 3529/JMD | 29/11/2022 | 7 | SUJOY RANJAN BHOWMICK | 0.07 | 0 | 0
295 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Paika T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000738/2022-2023 | 3487/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0 | 0
296 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Shutpipal stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000739/2022-2023 | 3435/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0.07 | 100
297 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Garra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000740/2022-2023 | 3433/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0.07 | 100
298 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Chanda Bila stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000741/2022-2023 | 3443/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0.07 | 100
299 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kankrajhor T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000742/2022-2023 | 3446/JMD | 29/11/2022 | 7 | DEBJYOTI BASU | 0.07 | 0 | 0
300 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Hanri Bhanga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000743/2022-2023 | 3504/JMD | 29/11/2022 | 7 | PRANAB KUMAR DAS | 0.07 | 0 | 0
301 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Khankri T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000744/2022-2023 | 3500/JMD | 29/11/2022 | 7 | PRANAB KUMAR DAS | 0.07 | 0.07 | 100
302 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bihankuria Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000751/2022-2023 | 657/JMD | 24/03/2023 | 120 | SHIVAM ENTERPRISE | 5.75 | 5.72 | 100
303 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000752/2022-2023 | 658/JMD | 24/03/2023 | 120 | DEBJYOTI BASU | 5.77 | 5.75 | 95
304 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Ningui, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000753/2022-2023 | 659/JMD | 24/03/2023 | 120 | DEBJYOTI BASU | 5.77 | 5.75 | 95
305 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhalia Ghati, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000754/2022-2023 | 660/JMD | 24/03/2023 | 120 | P.K. ENGINEERING | 5.78 | 5.75 | 95
306 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Totasai, Tube Well no.-I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000755/2022-2023 | 661/JMD | 24/03/2023 | 285 | AMIT DAS | 5.77 | 3.78 | 70
307 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Totasai, Tube Well no.-II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000756/2022-2023 | 662/JMD | 24/03/2023 | 120 | M.D. ENTERPRISE | 5.78 | 5.76 | 80
308 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Ghara Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000757/2022-2023 | 663/JMD | 24/03/2023 | 120 | T.N. BANERJEE | 5.77 | 0 | 0
309 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Astia Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000758/2022-2023 | 664/JMD | 24/03/2023 | 120 | B. P. TRADING CORPORATION | 5.78 | 5.76 | 100
310 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Baksa Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000759/2022-2023 | 665/JMD | 24/03/2023 | 120 | MENAKA ENTERPRISE | 5.78 | 5.16 | 95
311 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bara Mara Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000760/2022-2023 | 666/JMD | 24/03/2023 | 120 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 5.78 | 5.21 | 95
312 | Jhargram Mechanical Division | Jhargram Division | Supply and delivery of Silpaulin for Drilling works at Rig Store of MMSD(D) in Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000771/2022-2023 | 1011/JMD | 26/05/2022 | 7 | MONORANJAN DEY | 1.84 | 0 | 0
313 | Jhargram Mechanical Division | Jhargram Division | Supply, Delivery & fitting fixing of fast moving spares (Air filter, ELGI Air lube plus) for preventive maintenance of compressor unit (Model:- 600-200, Make:- ELGI) attached with DR/DTH -500 (make:- KLR) rig unit under MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000785/2022-2023 | 363/JMD | 23/02/2023 | 7 | B. P. TRADING CORPORATION | 0.82 | 0 | 0
314 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Paschim Gholai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000805/2022-2023 | 3513/JMD | 29/11/2022 | 7 | M/S. NABIN GOPAL SENGUPTA | 0.07 | 0 | 0
315 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bag Doba T/W no. II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000806/2022-2023 | 3497/JMD | 29/11/2022 | 7 | M/S. NABIN GOPAL SENGUPTA | 0.07 | 0 | 0
316 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghjhapa stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000807/2022-2023 | 3517/JMD | 29/11/2022 | 7 | M/S. SAMRIDDHI ENTERPRISE | 0.07 | 0 | 0
317 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000808/2022-2023 | 3483/JMD | 29/11/2022 | 7 | M/S. SAMRIDDHI ENTERPRISE | 0.07 | 0 | 0
318 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Salgaria (Near Club) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000809/2022-2023 | 3481/JMD | 29/11/2022 | 7 | SAMARPITA ENGINEERING | 0.07 | 0 | 0
319 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Sonamui stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000810/2022-2023 | 3515/JMD | 29/11/2022 | 7 | P.K. ENGINEERING | 0.07 | 0 | 0
320 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Amlasol T/W no. -I & II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000811/2022-2023 | 3445/JMD | 29/11/2022 | 7 | P.K. ENGINEERING | 0.07 | 0 | 0
321 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bhadai stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000812/2022-2023 | 3535/JMD | 29/11/2022 | 7 | P.K. ENGINEERING | 0.07 | 0 | 0
322 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Baghmari stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000813/2022-2023 | 3511/JMD | 29/11/2022 | 7 | SOUMEN ELECTRIC | 0.07 | 0.07 | 100
323 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Kiajharia T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000814/2022-2023 | 3495/JMD | 29/11/2022 | 7 | M/S. CHANDRANATH MUKHERJEE | 0.07 | 0 | 0
324 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Bhaluk Chua T/W no. I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000817/2022-2023 | 3493/JMD | 29/11/2022 | 7 | KAMAKHYA ENTERPRISE | 0.07 | 0 | 0
325 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kulghagri stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000818/2022-2023 | 3505/JMD | 29/11/2022 | 7 | SOUMEN ELECTRIC | 0.07 | 0.07 | 100
326 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Goal Danga stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000819/2022-2023 | 3440/JMD | 29/11/2022 | 7 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.07 | 0.07 | 100
327 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Panchami Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000840/2022-2023 | 265/JMD | 03/02/2023 | 331 | BALAJI CONSTRUCTION | 5.78 | 5 | 100
328 | Jhargram Mechanical Division | Jhargram Division | Providing one no. 10 MT capacity truck & one no 32 BHP Capacity Tractor along with licensed driver on daily basis for Rig unit no. 41D/LMP/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000841/2022-2023 | 366/JMD | 23/02/2023 | 20 | M/S. SAMRIDDHI ENTERPRISE | 0.97 | 0 | 0
329 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Arra , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000854/2022-2023 | 1058/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 2.78 | 1.97 | 100
330 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Arra, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000855/2022-2023 | 1059/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0.26 | 100
331 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Lakshanpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000871/2022-2023 | 3436/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0.07 | 100
332 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kargonala stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000872/2022-2023 | 3442/JMD | 29/11/2022 | 7 | ECO ENTERPRISE | 0.07 | 0 | 0
333 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Narda stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000873/2022-2023 | 3450/JMD | 29/11/2022 | 7 | ECO ENTERPRISE | 0.07 | 0 | 0
334 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bara Khankri stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000874/2022-2023 | 3458/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0 | 0
335 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Shahari mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000875/2021-2022 | 575/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0
336 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Lakhipara (School) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000875/2022-2023 | 3466/JMD | 29/11/2022 | 7 | MONORANJAN DEY | 0.07 | 0 | 0
337 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tukurya mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000876/2021-2022 | 567/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0
338 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (Pal) T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000876/2022-2023 | 3467/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0 | 0
339 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nargi mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000877/2021-2022 | 569/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 100
340 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Dhumsai T/W no. -III Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000877/2022-2023 | 3484/JMD | 29/11/2022 | 7 | ECO ENTERPRISE | 0.07 | 0 | 0
341 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Dhadka mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000878/2021-2022 | 544/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0
342 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Koima (A.W.C.) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000878/2022-2023 | 3499/JMD | 29/11/2022 | 7 | M/S. EMMESS | 0.07 | 0 | 0
343 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Shahari mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000879/2021-2022 | 576/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0
344 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Bankra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000879/2022-2023 | 3537/JMD | 29/11/2022 | 7 | MONORANJAN DEY | 0.07 | 0 | 0
345 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Nargi mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000880/2021-2022 | 570/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 100
346 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000881/2021-2022 | 143/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0
347 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000882/2021-2022 | 144/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.15 | 0 | 0
348 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Salika mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000883/2021-2022 | 557/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.77 | 0 | 0
349 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Salika mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000884/2021-2022 | 558/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0
350 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tukurya mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000885/2021-2022 | 568/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0
351 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dhadka mouza of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000886/2021-2022 | 543/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.59 | 0 | 0
352 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria , tube well no. 6 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000886/2022-2023 | 1056/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.78 | 0 | 0
353 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000887/2022-2023 | 1419./JMD | 14/06/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0.53 | 100
354 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Rangua mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000888/2021-2022 | 485/JMD | 23/12/2021 | 4 | SUJOY RANJAN BHOWMICK | 2.62 | 0 | 0
355 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000888/2022-2023 | 1429./JMD | 14/06/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0.53 | 100
356 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Rangua mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000889/2021-2022 | 486/JMD | 23/12/2021 | 4 | SUJOY RANJAN BHOWMICK | 0.33 | 0 | 0
357 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Kalma Pukhuria stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000890/2022-2023 | 3457/JMD | 29/11/2022 | 7 | S.S. GHORAI | 0.07 | 0 | 0
358 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000891/2021-2022 | 94/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.15 | 0 | 0
359 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Shibanandapur T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000891/2022-2023 | 3465/JMD | 29/11/2022 | 7 | BALAJI CONSTRUCTION | 0.07 | 0 | 0
360 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Rukhni Mara (Pry. School) Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000892/2022-2023 | 3496/JMD | 29/11/2022 | 7 | S.S. GHORAI | 0.07 | 0 | 0
361 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000893/2021-2022 | 707/JMD | 31/12/2021 | 4 | M/S. BIKASH DE | 2.6 | 0 | 0
362 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Nischinta stand alone piped water supply scheme, tube well no.-I of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000893/2022-2023 | 3508/JMD | 29/11/2022 | 7 | S.S. GHORAI | 0.07 | 0 | 0
363 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000894/2021-2022 | 93/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.71 | 0 | 0
364 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 6 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000894/2022-2023 | 1057/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0
365 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000895/2021-2022 | 95/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.71 | 0 | 0
366 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria , tube well no. 5 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000895/2022-2023 | 1054/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.78 | 0 | 100
367 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Amadubi mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000896/2021-2022 | 96/JMD | 31/01/2022 | 2 | DEBJYOTI BASU | 0.15 | 0 | 0
368 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 5 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000896/2022-2023 | 1055/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0
369 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria , tube well no. 4 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000897/2022-2023 | 1052/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.78 | 1.77 | 100
370 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 4 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000898/2022-2023 | 1053/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 100
371 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Dubrajpur stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000899/2022-2023 | 1419../JMD | 14/07/2022 | 120 | SUJOY RANJAN BHOWMICK | 6.86 | 0.74 | 70
372 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Sal Bani mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000900/2021-2022 | 722/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0
373 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Sal Bani mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000901/2021-2022 | 723/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0
374 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bihankuria mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000902/2021-2022 | 645/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0
375 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kadokata, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000902/2022-2023 | 1066/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0
376 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bihankuria mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000903/2021-2022 | 646/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0
377 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhan Sola, tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000903/2022-2023 | 1082/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0
378 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bara Mara mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000904/2021-2022 | 720/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.6 | 0 | 0
379 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhan Sola, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000904/2022-2023 | 1077/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.8 | 0 | 0
380 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bara Mara mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000905/2021-2022 | 721/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0
381 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhan Sola, tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000905/2022-2023 | 1081/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 2.8 | 0 | 0
382 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bali Muri mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000906/2021-2022 | 708/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0
383 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhan Sola, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000906/2022-2023 | 1079/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.8 | 0 | 0
384 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chilkigar mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000907/2021-2022 | 563/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.6 | 0 | 0
385 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000907/2022-2023 | 1072/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 2.8 | 0 | 0
386 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Chilkigar mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000908/2021-2022 | 564/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0 | 0
387 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kadokata, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000908/2022-2023 | 1065/JMD | 01/06/2022 | 5 | M/S. SAMRIDDHI ENTERPRISE | 2.8 | 0 | 0
388 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000909/2022-2023 | 1074/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 2.8 | 0 | 0
389 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000910/2022-2023 | 1075/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 0.33 | 0 | 0
390 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.3 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000911/2021-2022 | 121/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.71 | 0 | 100
391 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhan Sola, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000911/2022-2023 | 1078/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0
392 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.3 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000912/2021-2022 | 122/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.15 | 0 | 100
393 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kukrasol, tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000912/2022-2023 | 1073/JMD | 01/06/2022 | 5 | SAMARPITA ENGINEERING | 0.33 | 0 | 0
394 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000913/2021-2022 | 123/JMD | 31/01/2022 | 1048 | DEBJYOTI BASU | 0.71 | 0 | 100
395 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhan Sola, tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000913/2022-2023 | 1080/JMD | 01/06/2022 | 5 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0 | 0
396 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Gohalberya mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000914/2021-2022 | 124/JMD | 31/01/2022 | 1148 | DEBJYOTI BASU | 0.15 | 0 | 100
397 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bankisol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000915/2021-2022 | 493/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 1.59 | 100
398 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bankati mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000916/2021-2022 | 508/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0
399 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Dingla mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000917/2021-2022 | 528/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0.33 | 100
400 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000918/2021-2022 | 698/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 100
401 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000919/2021-2022 | 676/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 100
402 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000920/2021-2022 | 699/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.76 | 100
403 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tikra Para mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000921/2021-2022 | 705/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.86 | 100
404 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Jadabpur mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000923/2021-2022 | 664/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 100
405 | Jhargram Mechanical Division | Jhargram Division | Continuation work order for Providing one no. 10 MT capacity truck & one no 32 BHP Capacity Tractor along with licensed driver on daily basis for Rig unit no. 41D/LMP/500 of MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000923/2022-2023 | 716/JMD | 28/03/2023 | 20 | M/S. SAMRIDDHI ENTERPRISE | 0.97 | 0 | 0
406 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000924/2021-2022 | 700/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 100
407 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tikra Para mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000925/2021-2022 | 706/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 0.33 | 0.26 | 100
408 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bankisol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000926/2021-2022 | 494/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0.33 | 100
409 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Bankati mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000927/2021-2022 | 507/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0
410 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Dingla mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000928/2021-2022 | 527/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 1.58 | 100
411 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Malam mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000929/2021-2022 | 697/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.75 | 100
412 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 3 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000930/2021-2022 | 675/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 2 | 100
413 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000931/2021-2022 | 659/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 0 | 0
414 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Tiyakati mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000932/2021-2022 | 647/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 1.68 | 100
415 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000933/2021-2022 | 657/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 0 | 0
416 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000934/2021-2022 | 673/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 2.6 | 0 | 0
417 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Jadabpur mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000936/2021-2022 | 663/JMD | 31/12/2021 | 4 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 2.6 | 1.76 | 100
418 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Kalma Pukhuria mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000938/2021-2022 | 674/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0 | 0
419 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 1 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000939/2021-2022 | 658/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0 | 0
420 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Tiyakati mouza of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000940/2021-2022 | 648/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0.26 | 100
421 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nara Singha Pur mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000941/2021-2022 | 660/JMD | 31/12/2021 | 4 | SAMARPITA ENGINEERING | 0.33 | 0 | 0
422 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000942/2021-2022 | 126/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.16 | 0 | 100
423 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Kankrajhor mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000943/2021-2022 | 92/JMD | 31/01/2022 | 608 | DEBJYOTI BASU | 0.16 | 0 | 100
424 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Lekraanchra mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000944/2021-2022 | 108/JMD | 31/01/2022 | 475 | DEBJYOTI BASU | 0.16 | 0 | 100
425 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000945/2021-2022 | 128/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.16 | 0 | 100
426 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories for Arra stand alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000945/2022-2023 | 3455/JMD | 29/11/2022 | 7 | M/S B.M. ELECTRICAL | 0.07 | 0.04 | 100
427 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Chandabila mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000946/2021-2022 | 140/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0
428 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000946/2022-2023 | 3501/JMD | 29/11/2022 | 7 | M/S B.M. ELECTRICAL | 0.07 | 0 | 100
429 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Lekraanchra mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000947/2021-2022 | 107/JMD | 31/01/2022 | 475 | DEBJYOTI BASU | 0.71 | 0 | 100
430 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Chhota Jharia T/W no. -II Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000947/2022-2023 | 3502/JMD | 29/11/2022 | 7 | RITESH ENTERPRISE | 0.07 | 0.07 | 100
431 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Kankrajhor mouza, tube well no.4 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000948/2021-2022 | 91/JMD | 31/01/2022 | 608 | DEBJYOTI BASU | 0.71 | 0 | 100
432 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Pathar Chakri T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000948/2022-2023 | 3521/JMD | 29/11/2022 | 7 | B. P. TRADING CORPORATION | 0.07 | 0 | 100
433 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.2 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000949/2021-2022 | 127/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.71 | 0 | 100
434 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Nischintapur mouza, tube well no.1 of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000950/2021-2022 | 125/JMD | 31/01/2022 | 1125 | DEBJYOTI BASU | 0.71 | 0 | 100
435 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Chandabila mouza, tube well no.2 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000951/2021-2022 | 139/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0
436 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000952/2021-2022 | 145/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0
437 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Chilkigar mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000953/2021-2022 | 565/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 2.62 | 1.56 | 100
438 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Chilkigar mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000954/2021-2022 | 566/JMD | 23/12/2021 | 4 | CHAKRABORTY MINING & ENGINEERING | 0.33 | 0.33 | 100
439 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Narda mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000955/2021-2022 | 652/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 0.33 | 0 | 0
440 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Narda mouza , tube well no. 2 of Nayagram block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000956/2021-2022 | 651/JMD | 31/12/2021 | 4 | M/S. SAMRIDDHI ENTERPRISE | 2.62 | 0 | 0
441 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhansol mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000957/2021-2022 | 503/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0
442 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Swarup Narayanpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000958/2021-2022 | 515/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0
443 | Jhargram Mechanical Division | Jhargram Division | Additional work for supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Hudhudi T/W no. -I Stand Alone piped water supply scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000958/2022-2023 | 3518/JMD | 29/11/2022 | 7 | RMD TRADING | 0.07 | 0 | 0
444 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Baradhansol mouza, tube well no.1 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000959/2021-2022 | 501/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0
445 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Nandalalpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000960/2021-2022 | 481/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0
446 | Jhargram Mechanical Division | Jhargram Division | Sinking of (150 mmX 100 mmX 135mtr) RBTW by Rotary Method at Metyalsol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000961/2021-2022 | 505/JMD | 30/12/2021 | 4 | RSA ENTERPRISE | 2.62 | 0 | 0
447 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Baradhansol mouza, tube well no.1 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000962/2021-2022 | 502/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0
448 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Nandalalpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000963/2021-2022 | 482/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0
449 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Swarup Narayanpur mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000964/2021-2022 | 516/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0
450 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Metyalsol mouza of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000965/2021-2022 | 506/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0
451 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Baradhansol mouza, tube well no.2 of Binpur-I block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000966/2021-2022 | 504/JMD | 23/12/2021 | 4 | RSA ENTERPRISE | 0.33 | 0 | 0
452 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000967/2021-2022 | 135/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0
453 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000968/2021-2022 | 133/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0
454 | Jhargram Mechanical Division | Jhargram Division | Sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000969/2021-2022 | 147/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.71 | 0 | 0
455 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000970/2021-2022 | 148/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0
456 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Dhengbahara mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000971/2021-2022 | 146/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0
457 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.3 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000972/2021-2022 | 134/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0
458 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH method at Muniada mouza, tube well no.4 of Jamboni block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000973/2021-2022 | 136/JMD | 31/01/2022 | 2 | CHAKRABORTY MINING & ENGINEERING | 0.16 | 0 | 0
459 | Jhargram Mechanical Division | Jhargram Division | Providing different manpower for Sinking of (150 mmX 100 mmX 135 mtr.) RBTW by Rotary Method at Bhararu mouza of Binpur-II block under stand alone piped water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000975/2021-2022 | 542/JMD | 23/12/2021 | 4 | DEBJYOTI BASU | 0.33 | 0 | 0
460 | Jhargram Mechanical Division | Jhargram Division | Payment for new service connection of WBSEDCL. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000726/2022-2023 | 23/JMD/PFMS/SEP | 09/09/2022 | 0 | WBSEDCL | 6.27 | 0 | 0
461 | Jhargram Mechanical Division | Jhargram Division | Payment for new service connection of WBSEDCL. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000846/2022-2023 | 22/JMD/PFMS/SEP | 29/09/2022 | 0 | WBSEDCL | 1.87 | 0 | 0
462 | Jhargram Mechanical Division | Jhargram Division | WBSEDCL Payment for New service connection. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000856/2022-2023 | 1/JMD/PFMS/OCT | 18/10/2022 | 0 | WBSEDCL | 4.58 | 0 | 0
463 | Jhargram Mechanical Division | Jhargram Division | WBSEDCL payment for new Service Connection. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000878/2022-2023 | 2/JMD/PFMS/OCT | 25/10/2022 | 0 | WBSEDCL | 6.46 | 0 | 0
464 | Jhargram Mechanical Division | Jhargram Division | new service connection charges for Metal-2 | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01965/2023-2024 | 182/JMD | 30/03/2024 | 0 | WBSEDCL | 5.04 | 0 | 0
465 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES FOR METAL-1 | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01966/2023-2024 | 183/JMD | 30/03/2024 | 0 | WBSEDCL | 6.68 | 0 | 0
466 | Jhargram Mechanical Division | Jhargram Division | New service connection charges at Ramchandrapur-II water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00403/2024-2025 | 192/JMD | 14/06/2024 | 0 | WBSEDCL | 6.9 | 0 | 0
467 | Jhargram Mechanical Division | Jhargram Division | New service connection charges at Ramchandrapur-I water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00404/2024-2025 | 193/JMD | 14/06/2024 | 0 | WBSEDCL | 2.85 | 0 | 0
468 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00406/2023-2024 | 1/JMD | 07/09/2023 | 0 | WBSEDCL | 1.38 | 0 | 0
469 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00663/2023-2024 | 12/JMD | 10/11/2023 | 0 | WBSEDCL | 1.26 | 0 | 0
470 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Additional service connection chargers at Mahishamura-I water supply scheme | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01043/2024-2025 | 378/JMD | 30/09/2024 | 0 | WBSEDCL | 2.48 | 0 | 0
471 | Jhargram Mechanical Division | Jhargram RWS Sub Division | new service connection charges at Mahisamura tw-II | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01166/2024-2025 | 386/JMD | 04/10/2024 | 0 | WBSEDCL | 3.56 | 0 | 0
472 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection charges. | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00650/2023-2024 | 31/JMD | 31/10/2023 | 0 | WBSEDCL | 3.37 | 0 | 0
473 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00658/2023-2024 | 9/JMD | 10/11/2023 | 0 | WBSEDCL | 4.03 | 0 | 0
474 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Noagaon & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer | JE (M),Junior Engineer-II | ORD/000204/2023-2024 | 2265/JMD | 09/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.08 | 18.75 | 94
475 | Jhargram Mechanical Division | Jhargram Division | WBSEDCL New connection payment for Benakharanga | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00158/2024-2025 | 85/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
476 | Jhargram Mechanical Division | Jhargram Division | New service connection payment towards WBSEDCL for Shiyartola | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00160/2024-2025 | 86/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
477 | Jhargram Mechanical Division | Jhargram Division | Payment of New connection of WBSEDCL for Jualbhanga | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00161/2024-2025 | 87/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
478 | Jhargram Mechanical Division | Jhargram Division | Payment of New connection of WBSEDCL for Melkharia | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00162/2024-2025 | 88/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
479 | Jhargram Mechanical Division | Jhargram Division | New service connection payment towards WBSEDCL for Mohanpur | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00508/2024-2025 | 231/JMD | 28/06/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
480 | Jhargram Mechanical Division | Jhargram Division | WBSEDCL New connection payment for Bara Brindabanpur | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00509/2024-2025 | 232/JMD | 28/06/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
481 | Jhargram Mechanical Division | Jhargram Division | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE ALAMDANGA ( scheme code SM/11475) | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00712/2024-2025 | 277/JMD | 31/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
482 | Jhargram Mechanical Division | Jhargram Division | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE OF MOHANPUR (scheme code SM/11475 ) | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00713/2024-2025 | 278/JMD | 31/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
483 | Jhargram Mechanical Division | Jhargram Division | PAYMENT FOR NEW SERVICE CONNECTION OF WBSEDCL AT SITE NAMBANSHBER ( scheme code SM/11475) | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00714/2024-2025 | 279/JMD | 31/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
484 | Jhargram Mechanical Division | Jhargram Division | New service connection at Dhabani,Andharia GP | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01209/2023-2024 | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
485 | Jhargram Mechanical Division | Jhargram Division | New service connection charge at Bagghara,Dharampur GP | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01210/2023-2024 | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
486 | Jhargram Mechanical Division | Jhargram Division | New service connection at Chantukasda,Ramgarh GP | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01211/2023-2024 | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
487 | Jhargram Mechanical Division | Jhargram Division | New service connection charge at Padiha | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01212/2023-2024 | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
488 | Jhargram Mechanical Division | Jhargram Division | New service connection charge at Harulia | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01213/2023-2024 | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
489 | Jhargram Mechanical Division | Jhargram Division | New service connection charges | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01214/2023-2024 | 50/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
490 | Jhargram Mechanical Division | Jhargram Division | New service connection at manpur under 179 Scheme.(Scheme code:- SM/11475) | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01416/2024-2025 | 427/JMD | 28/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
491 | Jhargram Mechanical Division | Jhargram Division | New service connection at Baita under 179 Scheme.(Scheme code:- SM/11475) | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01417/2024-2025 | 428/JMD | 28/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
492 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Bandhagora at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | ORD/000600/2024-2025 | 6760/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0
493 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Chunpara at Binpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | ORD/000614/2024-2025 | 6774/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 3.49 | 0 | 100
494 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Nalbona T/W-I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00062/2024-2025 | 36/JMD | 29/04/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
495 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection atNalbona T/W-I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00063/2024-2025 | 37/JMD | 29/04/2024 | 0 | WBSEDCL | 3.3 | 0 | 0
496 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for peruabad t/w 1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00088/2024-2025 | 62/JMD | 29/04/2024 | 0 | WBSEDCL | 5.52 | 0 | 0
497 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Peruabad t/w 2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00089/2024-2025 | 63/JMD | 29/04/2024 | 0 | WBSEDCL | 5.59 | 0 | 0
498 | Jhargram Mechanical Division | Ghatal Subdivision | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at newly proposed T/W no. II of Gohaldanga water supply scheme in the district of Paschim Medinipur under Jhargram Mechanical Division, P.H.E. Dte. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000739/2024-2025 | 6941/JMD | 13/09/2024 | 241 | R S ENTERPRISE | 11.26 | 8.08 | 60
499 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Harinasuli TW-II water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00459/2024-2025 | 217/JMD | 21/06/2024 | 0 | WBSEDCL | 3.65 | 0 | 0
500 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Harinasuli TW-I water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00460/2024-2025 | 218/JMD | 21/06/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
501 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Simli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000070/2023-2024 | 1241/JMD | 26/05/2023 | 180 | T.N. BANERJEE | 20.82 | 0 | 0
502 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES AT DUDHKUNDI TW-I PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00892/2024-2025 | 320/JMD | 28/08/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
503 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES AT DUDHKUNDI TW-II PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00893/2024-2025 | 321/JMD | 28/08/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
504 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dud Kundi & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000041/2023-2024 | 1243/JMD | 26/05/2023 | 617 | DEBJYOTI BASU | 21.76 | 0 | 50
505 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection at Barabolbandi T/W-1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00260/2024-2025 | 115/JMD | 13/05/2024 | 0 | WBSEDCL | 9.67 | 0 | 0
506 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Amsol T/W -I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00071/2024-2025 | 45/JMD | 29/04/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
507 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at AMSOL T/W-II water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00230/2024-2025 | 113/JMD | 13/05/2024 | 0 | WBSEDCL | 6.12 | 0 | 0
508 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01301/2023-2024 | 72/JMD | 12/02/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
509 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01302/2023-2024 | 73/JMD | 12/02/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
510 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection for Dukhi T/W - 1 water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01381/2023-2024 | 44/JMD | 11/03/2024 | 0 | WBSEDCL | 5.24 | 0 | 0
511 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection for Dukhi T/W-2 water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01382/2023-2024 | 45/JMD | 11/03/2024 | 0 | WBSEDCL | 4.77 | 0 | 0
512 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01299/2023-2024 | 70/JMD | 12/02/2024 | 0 | WBSEDCL | 4.59 | 0 | 0
513 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01300/2023-2024 | 71/JMD | 12/02/2024 | 0 | WBSEDCL | 3.5 | 0 | 0
514 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection charges Barakadra T/W-2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00087/2024-2025 | 61/JMD | 29/04/2024 | 0 | WBSEDCL | 4.04 | 0 | 0
515 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for WBSEDCL new connection at BARAKADRA 1 (SM/14991. BARAKADRA AND ADJOINING MOUJAS PWSS ) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00370/2024-2025 | 171/JMD | 07/06/2024 | 0 | WBSEDCL | 11.23 | 0 | 0
516 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT KADRA TW-II WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00570/2024-2025 | 249/JMD | 10/07/2024 | 0 | WBSEDCL | 6.94 | 0 | 0
517 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01396/2023-2024 | 59/JMD | 13/03/2024 | 0 | WBSEDCL | 6.27 | 0 | 0
518 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charge at Krishnasole ( Mansingha-I) water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00973/2024-2025 |  | 03/09/2024 | 0 | WBSEDCL | 5.4 | 0 | 0
519 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01397/2023-2024 | 60/JMD | 13/03/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
520 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01398/2023-2024 | 61/JMD | 13/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0
521 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT POCHADOHARA TW-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00568/2024-2025 | 247/JMD | 10/07/2024 | 0 | WBSEDCL | 7.16 | 0 | 0
522 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges for Pirrakuli w/s scheme, t/w no.-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01969/2023-2024 | 187/JMD | 30/03/2024 | 0 | WBSEDCL | 7.79 | 0 | 0
523 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges for Pirrakuli w/s scheme, t/w no.-I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01970/2023-2024 | 188/JMD | 30/03/2024 | 0 | WBSEDCL | 9.29 | 0 | 0
524 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Dismantling the existing damaged voltage stabilizer and supply, delivery & installation of newly supplied single phase 20 KVA oil cooled type voltage stabilizer with other allied works at tube well no.-II of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000245/2022-2023 | 924/JMD | 12/05/2022 | 7 | PRANAB KUMAR DAS | 2.62 | 2.57 | 0
525 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, Delivery of multicore copper control cable for actuator connection at tube well no.I of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000507/2022-2023 | 2824/JMD | 16/09/2022 | 7 | SWAPAN ENTERPRISE | 0.08 | 0.06 | 0
526 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply , Delivery of multicore copper control cable for actuator connection at tube well no.II of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000508/2022-2023 | 2825/JMD | 16/09/2022 | 7 | ORIENTAL ENGINEERING CO. | 0.16 | 0.12 | 0
527 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Dismantling the existing damaged voltage stabilizer and supply, delivery & installation of newly supplied three phase 15 KVA oil cooled type voltage stabilizer with other allied works at tube well no.II of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000603/2021-2022 | 525/JMD | 22/03/2022 | 7 | BEE GEE CONSTRUCTION | 2.28 | 2.24 | 0
528 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no.II of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000769/2021-2022 | 523/JMD | 22/03/2022 | 7 | ORIENTAL ENGINEERING CO. | 4.55 | 4.55 | 0
529 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Making compound lighting arrangement and allied works at tube well no.I (Head work site) of Rohini water supply scheme of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000802/2021-2022 | 526/JMD | 22/03/2022 | 7 | SUBHRA ENTERPRISE | 2.96 | 2.84 | 0
530 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tube well no.I of Rohini water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000814/2021-2022 | 522/JMD | 22/03/2022 | 7 | SWAPAN ENTERPRISE | 4.42 | 4.4 | 0
531 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at proposed additional T/Well as part of augmentation of Junsola W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-II block | ORD/000172/2023-2024 | 2098/JMD | 03/08/2023 | 30 | DAS CONSTRUCTION | 9.41 | 0 | 0
532 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories for proposed additional T/Well at head work site as part of augmentation of Balibandh W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000021/2023-2024 | 1128/JMD | 18/05/2023 | 120 | SAMARPITA ENGINEERING | 10.42 | 10.33 | 100
533 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01362/2023-2024 | 25/JMD | 06/03/2024 | 0 | WBSEDCL | 7.47 | 0 | 0
534 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for Bagchori T/W - I water supply scheme. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01366/2023-2024 | 29/JMD | 11/03/2024 | 0 | WBSEDCL | 7.47 | 0 | 0
535 | Jhargram Mechanical Division | Ghatal Subdivision | Quotaton for new service connection charges for Maheshpur tw-II water supply scheme. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00813/2024-2025 | 295/JMD | 09/08/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
536 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01251/2023-2024 | 49/JMD | 06/02/2024 | 0 | WBSEDCL | 4.07 | 0 | 0
537 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Saldahara pwss, t/w no. II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00076/2024-2025 | 50/JMD | 29/04/2024 | 0 | WBSEDCL | 7.59 | 0 | 0
538 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Saldahara pwss, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01371/2023-2024 | 34/JMD | 11/03/2024 | 0 | WBSEDCL | 3.32 | 0 | 0
539 | Jhargram Mechanical Division | Jhargram Division | NEW METER CONNECTION CHARGES AT GOBINDAPUR T/W-1 WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00096/2024-2025 | 69/JMD | 29/04/2024 | 0 | WBSEDCL | 9.92 | 0 | 0
540 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES AT GOBINDAPUR T/W-2 WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00097/2024-2025 | 70/JMD | 29/04/2024 | 0 | WBSEDCL | 4.78 | 0 | 0
541 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block-Jhargram in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | ORD/000039/2023-2024 | 1236/JMD | 26/05/2023 | 890 | DAS CONSTRUCTION | 20.78 | 0 | 50
542 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. | DIC(D)_MMSD(D) | JE (M) | BILL/00318/2024-2025 | 134/JMD | 24/05/2024 | 0 | SURAJ SERVICE STATION | 1.01 | 0 | 0
543 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charges | DIC(D)_MMSD(D) | JE (M) | BILL/00852/2023-2024 | 32/JMD | 19/12/2023 | 0 | WBSEDCL | 1.68 | 0 | 0
544 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service connection | DIC(D)_MMSD(D) | JE (M) | BILL/00871/2023-2024 | 44/JMD | 29/12/2023 | 0 | WBSEDCL | 1.26 | 0 | 0
545 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service connection charges. | DIC(D)_MMSD(D) | JE (M) | BILL/01347/2023-2024 | 10/JMD | 01/03/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
546 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Jamirdiha & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000056/2023-2024 | 1350/JMD | 06/06/2023 | 40 | SUBHASIS ROY | 22 | 6.3 | 30
547 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 148 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 88.77 | 100
548 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Erection & commissioning of 37 (thirty seven) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000227/2023-2024 | 2303/JMD | 14/08/2023 | 870 | CONCORD ENGINEERING | 1025.92 | 80.75 | 12
549 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000961/2024-2025 | 193/JMD | 30/01/2025 | 352 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 20
550 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Charchita T/W I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00106/2024-2025 | 79/JMD | 29/04/2024 | 0 | WBSEDCL | 7.46 | 0 | 0
551 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no. I of Sasrah water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | ORD/000616/2022-2023 | 3634/JMD | 07/12/2022 | 30 | SUJOY RANJAN BHOWMICK | 6.62 | 6.49 | 0
552 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery & installation of submersible pumping machinery and other electro mechanical accessories at tubewell no. II of Sasrah water supply scheme in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | ORD/000617/2022-2023 | 3635/JMD | 07/12/2022 | 30 | SUJOY RANJAN BHOWMICK | 5.78 | 5.63 | 0
553 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bagmuri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000213/2023-2024 | 1228/JMD | 26/05/2023 | 180 | ARATI ENGINEERING | 20.76 | 0 | 0
554 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00340/2023-2024 | 19/AUG | 24/08/2023 | 0 | WBSEDCL | 2.95 | 0 | 0
555 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00341/2023-2024 | 20/AUG | 24/08/2023 | 0 | WBSEDCL | 4.72 | 0 | 0
556 | Jhargram Mechanical Division |  | Supply, delivery and laying of additional Cable, pipe & erection of fencing arrangement with other allied accessories at T/W no.-II of Khasjungle W/S Scheme at Binpur-I Block in the district of Jhargram under Jhargram Mechanical Division P.H.E Dte. |  |  | ORD/000055/2025-2026 | 1240/JMD | 02/06/2025 | 45 | SOUMEN ELECTRIC | 3.39 | 0 | 100
557 | Jhargram Mechanical Division |  | Withdrawing the damaged sub-mersible pumping machinery and installation of same capacity departmentally supplied pump motor set with other allied works at Khasjangle water supply scheme, tube well no.-1 at Binpur-I block in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. |  |  | ORD/000915/2022-2023 | 1572/JMD | 26/07/2022 | 5 | M/S. EMMESS | 4.18 | 4.18 | 100
558 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply delivery & installation of pumping machinery and other electro mechanical accessories for the newly sunk replacement tube well no -II at Chichira w/s scheme to accommodate FHTC at Jamboni block of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000520/2022-2023 | 3068/JMD | 28/09/2022 | 30 | SHOVAN KUMAR DAS | 9.89 | 9.71 | 0
559 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00339/2023-2024 | 18/AUG | 24/08/2023 | 0 | WBSEDCL | 2.94 | 0 | 0
560 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00386/2023-2024 | 25/AUG | 25/08/2023 | 0 | WBSEDCL | 5.64 | 0 | 0
561 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belia & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | ORD/000205/2023-2024 | 2266/JMD | 09/08/2023 | 180 | CHAKRABORTY MINING & ENGINEERING | 22.09 | 18.06 | 65
562 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Tentulia tw-II water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00346/2024-2025 | 149/JMD | 31/05/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
563 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Tentulia T/W -I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00347/2024-2025 | 150/JMD | 31/05/2024 | 0 | WBSEDCL | 3.04 | 0 | 0
564 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00407/2023-2024 | 2/JMD | 07/09/2023 | 0 | WBSEDCL | 3.1 | 0 | 0
565 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00408/2023-2024 | 3/JMD | 07/09/2023 | 0 | WBSEDCL | 4.75 | 0 | 0
566 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Junsola & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000030/2023-2024 | 1227/JMD | 26/05/2023 | 180 | CREATIVE WATER AND PROCESS TECHNOLOGIES PVT LTD | 20.73 | 0 | 0
567 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Andharnayan T/W-III water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00065/2024-2025 | 39/JMD | 29/04/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
568 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Anadarnyan T/W-I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00066/2024-2025 | 40/JMD | 29/04/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
569 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Andharnayan T/W-II water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00067/2024-2025 | 41/JMD | 29/04/2024 | 0 | WBSEDCL | 4.78 | 0 | 0
570 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Karnagarg, tw-I w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01305/2023-2024 | 76/JMD | 12/02/2024 | 0 | WBSEDCL | 3.23 | 0 | 0
571 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Karnagarh, tw-II w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01306/2023-2024 | 77/JMD | 14/02/2024 | 0 | WBSEDCL | 2.99 | 0 | 0
572 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00338/2023-2024 | 17/AUG | 24/08/2023 | 0 | WBSEDCL | 3.06 | 0 | 0
573 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at Barsole T/W -I water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00507/2024-2025 | 230/JMD | 28/06/2024 | 0 | WBSEDCL | 5.37 | 0 | 0
574 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection for Kantal T/W- 1 water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00077/2024-2025 | 51/JMD | 29/04/2024 | 0 | WBSEDCL | 12.47 | 0 | 0
575 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Murakati t/w 1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00082/2024-2025 | 56/JMD | 29/04/2024 | 0 | WBSEDCL | 8.25 | 0 | 0
576 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for WBSEDCL new connection at MURAKATI 2 (SM/14004. MURAKATI AND ADJOINING MOUJAS PWSS ) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00369/2024-2025 | 170/JMD | 07/06/2024 | 0 | WBSEDCL | 4.23 | 0 | 0
577 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Shakhabai T/W-II water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00070/2024-2025 | 44/JMD | 29/04/2024 | 0 | WBSEDCL | 4.18 | 0 | 0
578 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00416/2024-2025 | 196/JMD | 14/06/2024 | 0 | WBSEDCL | 10.32 | 0 | 0
579 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00409/2023-2024 | 4/JMD | 07/09/2023 | 0 | WBSEDCL | 3.15 | 0 | 0
580 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00411/2023-2024 | 6/JMD | 07/09/2023 | 0 | WBSEDCL | 1.23 | 0 | 0
581 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection atRaghunathpur water supply scheme T/W -1 | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00027/2024-2025 | 26/JMD | 22/04/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
582 | Jhargram Mechanical Division | Jhargram Sub-Division | New service connection charges for Belatikri, t/w no.-II | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01391/2023-2024 | 54/JMD | 12/03/2024 | 0 | WBSEDCL | 3.34 | 0 | 0
583 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service Connection Charges for Abhaya T/W - I PWSS | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01258/2024-2025 |  | 04/10/2024 | 0 | WBSEDCL | 4.99 | 0 | 0
584 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges. | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00263/2023-2024 | 2/JMD/AUG | 17/08/2023 | 0 | WBSEDCL | 3.2 | 0 | 0
585 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Additional Service Connection Charges for Andhari P.H - II PWSS | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00440/2024-2025 | 208/JMD | 20/06/2024 | 0 | WBSEDCL | 5.7 | 0 | 0
586 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00670/2023-2024 | 18/JMD | 20/11/2023 | 0 | WBSEDCL | 2.9 | 0 | 0
587 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00699/2023-2024 | 25/JMD | 29/11/2023 | 0 | WBSEDCL | 0.05 | 0 | 0
588 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Dhadangri T/W-II water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00262/2024-2025 | 117/JMD | 13/05/2024 | 0 | WBSEDCL | 3.86 | 0 | 0
589 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dhadangiri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000300/2023-2024 | 1251/JMD | 26/05/2023 | 885 | BHABANI PRASAD MANNA | 22.08 | 0 | 90
590 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00249/2023-2024 | 12/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 2.83 | 0 | 0
591 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00251/2023-2024 | 14/JMD/PFMS/APR | 27/07/2023 | 0 | WBSEDCL | 3.3 | 0 | 0
592 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dhansol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M),Junior Engineer-II | ORD/000201/2023-2024 | 2262/JMD | 09/08/2023 | 180 | RS ELECTROMECHANICAL CORPORATION | 21.96 | 18.53 | 91
593 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00264/2023-2024 | 3/JMD/AUG | 17/08/2023 | 0 | WBSEDCL | 2.83 | 0 | 0
594 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00649/2023-2024 | 30/JMD | 31/10/2023 | 0 | WBSEDCL | 4.73 | 0 | 0
595 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Anandapur & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M),Junior Engineer-II | ORD/000198/2023-2024 | 2259/JMD | 09/08/2023 | 180 | DAS ENTERPRISE | 20.74 | 17.88 | 94
596 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Kuliana T/W-I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00107/2024-2025 | 80/JMD | 29/04/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
597 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Kuliana T/W-II water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00108/2024-2025 | 81/JMD | 29/04/2024 | 0 | WBSEDCL | 2.99 | 0 | 0
598 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charges | DIC(D)_MMSD(D) | JE (M) | BILL/01076/2023-2024 | 11/JMD | 05/01/2024 | 0 | WBSEDCL | 1.05 | 0 | 0
599 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New connection bill for Jagannathpur in Bheliadiha GP | DIC(D)_MMSD(D) | JE (M) | BILL/01473/2023-2024 | 75/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
600 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New connection bill for Mahulbani in Bheliadiha GP | DIC(D)_MMSD(D) | JE (M) | BILL/01474/2023-2024 | 76/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
601 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000322/2023-2024 | 3015/JMD | 20/10/2023 | 794 | CONCORD ENGINEERING | 621.67 | 89.37 | 25
602 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. III & IV as part of augmentation of Rohini W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | ORD/000171/2023-2024 | 2095/JMD | 03/08/2023 | 180 | WEST BENGAL ENGINEERING CO. | 19.76 | 0 | 0
603 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges for Rampura w/s scheme, t/w no.- II | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00285/2024-2025 | 123/JMD | 20/05/2024 | 0 | WBSEDCL | 10.17 | 0 | 0
604 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection Charges for Rampura P.H - I PWSS | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00429/2024-2025 | 203/JMD | 14/06/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
605 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges | Assistant Engineer | Junior Engineer-II | BILL/00869/2023-2024 | 42/JMD | 29/12/2023 | 0 | WBSEDCL | 0.21 | 0 | 0
606 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM.(scheme code -TSM/015566 ) | Assistant Engineer | Junior Engineer-II | BILL/01023/2024-2025 | 355/JMD | 13/09/2024 | 0 | SURAJ SERVICE STATION | 0.53 | 0 | 0
607 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Providing fuel & lubricant for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Jamirdiha & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | BILL/01135/2023-2024 | 16/JMD | 10/01/2024 | 0 | SURAJ SERVICE STATION | 5 | 0 | 0
608 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection charges. | Assistant Engineer | Junior Engineer-II | BILL/01148/2023-2024 | 31/JMD | 18/01/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
609 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer | Junior Engineer-II | BILL/01297/2023-2024 | 68/JMD | 12/02/2024 | 0 | WBSEDCL | 0.84 | 0 | 0
610 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection charges. | Assistant Engineer | Junior Engineer-II | BILL/01346/2023-2024 | 9/JMD | 01/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
611 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection Charges for Baramsol PWSS. CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | Assistant Engineer | Junior Engineer-II | BILL/01351/2024-2025 | 415/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
612 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection Charges for Pakurasol PWSS.CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | Assistant Engineer | Junior Engineer-II | BILL/01352/2024-2025 | 416/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
613 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection Charges for Jhatiara PWSS | Assistant Engineer | Junior Engineer-II | BILL/01353/2024-2025 | 417/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
614 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection Charges for Srinathpur PWSS. CHAINBERA ZONE-III JOYPUR & ADJOINING MOUJAS PWSS | Assistant Engineer | Junior Engineer-II | BILL/01354/2024-2025 | 418/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
615 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Conducting Geophysical investigation of twenty two (22) nos. sites in Bhelaidiha GP in Binpur-2 Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | Junior Engineer-II | ORD/000222/2023-2024 | 2288/JMD | 10/08/2023 | 44 | SUBHASIS ROY | 4.12 | 3.93 | 97
616 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 148 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 100
617 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Erection & commissioning of 37 (thirty seven) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000227/2023-2024 | 2303/JMD | 14/08/2023 | 870 | CONCORD ENGINEERING | 1025.92 | 0 | 12
618 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Erection & commissioning of 30 (thirty) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Ergoda G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur- II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000228/2023-2024 | 2304/JMD | 14/08/2023 | 770 | CONCORD ENGINEERING | 810.97 | 64.19 | 10
619 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000322/2023-2024 | 3015/JMD | 20/10/2023 | 794 | CONCORD ENGINEERING | 621.67 | 0 | 25
620 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Srinathpur & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000373/2023-2024 | 2790/JMD | 08/09/2023 | 502 | RSA ENTERPRISE | 22 | 18.45 | 91
621 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000961/2024-2025 | 193/JMD | 30/01/2025 | 352 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 20
622 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Jangalkhash TW-I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00321/2024-2025 | 140/JMD | 24/05/2024 | 0 | WBSEDCL | 11.72 | 0 | 0
623 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection charges. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01480/2023-2024 | 85/JMD | 21/03/2024 | 0 | WBSEDCL | 2.59 | 0 | 0
624 | Jhargram Mechanical Division | Jhargram Sub-Division | Meter shifting bill for Lalgarh pwss, P/H/ no.-II | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/01143/2023-2024 | 25/JMD | 15/01/2024 | 0 | WBSEDCL | 0.11 | 0 | 0
625 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of electro-mechanical components at T/W no. I, II and renovation of existing compound lighting arrangement with other allied works at Lalgarh water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000154/2023-2024 | 1941/JMD | 28/07/2023 | 30 | M/S. EMMESS | 21.22 | 20.63 | 100
626 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of electro-mechanical components at T/W no. III of Lalgarh water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000155/2023-2024 | 1942/JMD | 28/07/2023 | 15 | M/S. CHANDRANATH MUKHERJEE | 9.27 | 9.23 | 100
627 | Jhargram Mechanical Division |  | New Service connection |  |  | BILL/00614/2023-2024 | 5/JMD | 11/10/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
628 | Jhargram Mechanical Division |  | New Service connection |  |  | BILL/00669/2023-2024 | 17/JMD | 10/11/2023 | 0 | WBSEDCL | 0.26 | 0 | 0
629 | Jhargram Mechanical Division |  | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Tube well no. II of Odalchua piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. |  |  | ORD/000585/2023-2024 | 2986/JMD | 16/10/2023 | 120 | DEBJYOTI BASU | 7.08 | 6.98 | 100
630 | Jhargram Mechanical Division |  | Supply, delivery& installation of submersible pumping machinary and other Electro-Mechanical accessories for newly sunk tube well under JJM programme at Odolchua water Supply scheme T/w no-1 (Chirakuti Mouza ,JL No-91) t under Jhargram Mechanical Division P.H.E Dte. in the district of Jhargram. |  |  | ORD/000593/2022-2023 | 3326/JMD | 14/11/2022 | 30 | DEBJYOTI BASU | 5.42 | 5.39 | 0
631 | Jhargram Mechanical Division |  | Supply delivery & Installation of on-line booster pumping machinery at Odalchua PWSS of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. |  |  | ORD/001367/2023-2024 | 2984/JMD | 13/03/2024 | 15 | DEBJYOTI BASU | 3.12 | 3 | 100
632 | Jhargram Mechanical Division |  | Providing solarization of WBSEDCL energised pumping installation at tube well no.-I & II of Odalchua w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. |  |  | ORD/001368/2023-2024 | 2985/JMD | 13/03/2024 | 30 | DEBJYOTI BASU | 6.26 | 0 | 0
633 | Jhargram Mechanical Division |  | Payment for new service connection of WBSEDCL. |  |  | VCH/000848/2022-2023 | 20/JMD/PFMS/SEP | 29/09/2022 | 0 | WBSEDCL | 0.21 | 0 | 0
634 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro-mechanical accessories at T/W no. III & IV as part of augmentation of Rantua W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. |  | Junior Engineer-III | ORD/000169/2023-2024 | 2093/JMD | 03/08/2023 | 180 | RSA ENTERPRISE | 19.73 | 0 | 0
635 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery and Installation of new pumping machinery and other electro mechanical accessories at Rantua T/W no -II water supply scheme at Gopiballavpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. |  | Junior Engineer-III | ORD/000597/2022-2023 | 1661/JMD | 01/08/2022 | 15 | BUSR ENGINEERING | 4.54 | 4.39 | 0
636 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of voltage stabilizer, chlorine machine and other allied works at Rantua tubewell no. 2 water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. |  | Junior Engineer-III | ORD/000618/2022-2023 | 3636/JMD | 07/12/2022 | 30 | BUSR ENGINEERING | 5.67 | 5.56 | 0
637 | Jhargram Mechanical Division | Jhargram Sub-Division | New service connection | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00644/2023-2024 | 26/JMD | 17/10/2023 | 0 | WBSEDCL | 5.63 | 0 | 0
638 | Jhargram Mechanical Division | Jhargram Sub-Division | Excess quotation payment for Jhitka-1 ,Binpur-1. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/01315/2023-2024 | 66/JMD | 12/02/2024 | 0 | WBSEDCL | 0.93 | 0 | 0
639 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories for additional T/Well at head work site as part of augmentation of Jhitka W/S scheme under Jhargram Mechanical Division, PHE. Dte. in the dist. of Jhargram. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000291/2023-2024 | 2516/JMD | 25/08/2023 | 30 | SHOVAN KUMAR DAS | 9.41 | 9.36 | 80
640 | Jhargram Mechanical Division | Jhargram Division | New service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00261/2023-2024 | 18/JMD/PFMS/JUL | 31/07/2023 | 0 | WBSEDCL | 3.02 | 0 | 0
641 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I of Manikpara piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000051/2023-2024 | 1256/JMD | 26/05/2023 | 180 | K.S.P. ENTERPRISE | 10.81 | 10.77 | 95
642 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning of pumping machinery and allied electro-mechanical works for Augmentation of t/w no. II of Manikpara water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/001045/2023-2024 | 2123/JMD | 22/02/2024 | 30 | SUBHRA ENTERPRISE | 9.73 | 9.44 | 100
643 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection charges. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00415/2024-2025 | 201/JMD | 14/06/2024 | 0 | WBSEDCL | 13.6 | 0 | 0
644 | Jhargram Mechanical Division | Jhargram Sub-Division | Qutation for new service connection at Balishira T/W -2 WATER SUPPLY SCHEME. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01502/2023-2024 | 92/JMD | 22/03/2024 | 0 | WBSEDCL | 2.92 | 0 | 0
645 | Jhargram Mechanical Division | Jhargram Division | New Service Connection Charges for Brahmandana T/W-II PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01971/2023-2024 | 189/JMD | 30/03/2024 | 0 | WBSEDCL | 5.88 | 0 | 0
646 | Jhargram Mechanical Division | Jhargram Division | New Service Connection Charges for Brahmandana T/W - I PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01972/2023-2024 | 190/JMD | 30/03/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
647 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Khasjangal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000035/2023-2024 | 1233/JMD | 26/05/2023 | 180 | AVIK KUMAR GHOSH | 20.78 | 0 | 0
648 | Jhargram Mechanical Division | Jhargram Sub-Division | NEW SERVICE CONNECTION CHARGES FOR SIJUA T/W - I PWSS | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01386/2023-2024 | 50/JMD | 12/03/2024 | 0 | WBSEDCL | 4.98 | 0 | 0
649 | Jhargram Mechanical Division | Jhargram Sub-Division | NEW SERICE CONNECTION CHARGES FOR SIJUA T/W -II PWSS | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01387/2023-2024 | 51/JMD | 12/03/2024 | 0 | WBSEDCL | 5.28 | 0 | 0
650 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for singla t/w 1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00078/2024-2025 | 52/JMD | 29/04/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
651 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for singla t/w 2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00079/2024-2025 | 53/JMD | 29/04/2024 | 0 | WBSEDCL | 3.13 | 0 | 0
652 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Benucha pwss, t/w no.II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01372/2023-2024 | 35/JMD | 11/03/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
653 | Jhargram Mechanical Division | Jhargram Division | Additional service connection charges of Panchami-1 water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00026/2024-2025 | 25/JMD | 24/04/2024 | 0 | WBSEDCL | 4.12 | 0 | 0
654 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00388/2023-2024 | 26/Aug | 29/08/2023 | 0 | WBSEDCL | 11.35 | 0 | 0
655 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00390/2023-2024 | 28/AUG | 29/08/2023 | 0 | WBSEDCL | 2.83 | 0 | 0
656 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Panchami & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000031/2023-2024 | 1229/JMD | 26/05/2023 | 180 | JAGANNATH ENTERPRISE | 20.76 | 17.12 | 70
657 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Burimole-2 water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00100/2024-2025 | 73/JMD | 29/04/2024 | 0 | WBSEDCL | 3.72 | 0 | 0
658 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Burimol-1 water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00101/2024-2025 | 74/JMD | 29/04/2024 | 0 | WBSEDCL | 5.38 | 0 | 0
659 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection for Kadambandi t/w-1 water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01380/2023-2024 | 43/JMD | 11/03/2024 | 0 | WBSEDCL | 5.01 | 0 | 0
660 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection for Nayabasat T/W-1 water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01383/2023-2024 | 46/JMD | 11/03/2024 | 0 | WBSEDCL | 4.58 | 0 | 0
661 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01471/2023-2024 | 80/JMD | 20/03/2024 | 0 | WBSEDCL | 6.26 | 0 | 0
662 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT BALADGHATA TW-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00575/2024-2025 | 254/JMD | 10/07/2024 | 0 | WBSEDCL | 5.02 | 0 | 0
663 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT BALADGHATA TW-II WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00576/2024-2025 | 255/JMD | 10/07/2024 | 0 | WBSEDCL | 5.07 | 0 | 0
664 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT JADABBATI-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00650/2024-2025 | 263/JMD | 23/07/2024 | 0 | WBSEDCL | 11.68 | 0 | 0
665 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Kankrisole t/w 1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00095/2024-2025 | 68/JMD | 29/04/2024 | 0 | WBSEDCL | 5.11 | 0 | 0
666 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01287/2023-2024 | 58/JMD | 08/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0
667 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01288/2023-2024 | 59/JMD | 08/02/2024 | 0 | WBSEDCL | 5.04 | 0 | 0
668 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Piasala & adjacent water supply schemes of Garhbeta-II block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000158/2024-2025 | 4293/JMD | 24/07/2024 | 30 | P.K. ENGINEERING | 3.05 | 0 | 0
669 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01281/2023-2024 | 52/JMD | 06/02/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
670 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection for Pursuri T/W -1 water supply scheme. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01331/2023-2024 | 98/JMD | 23/02/2024 | 0 | WBSEDCL | 7.84 | 0 | 0
671 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection for Pursuri T/W-2 water supply scheme | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01332/2023-2024 | 99/JMD | 23/02/2024 | 0 | WBSEDCL | 4.69 | 0 | 0
672 | Jhargram Mechanical Division | Midnapur Mechanical Sub Division-I | Repairing & rejuvenation of electro-mechanical accessories for Ukhla W/S scheme Pump house no -2 in Garbeta II block under Jhargram Mechanical Division, PHE. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000794/2024-2025 | 7246/JMD | 05/11/2024 | 188 | ABHIJIT MUKHERJEE | 4.43 | 0 | 100
673 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01282/2023-2024 | 53/JMD | 06/02/2024 | 0 | WBSEDCL | 3.82 | 0 | 0
674 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01359/2023-2024 | 23/JMD | 04/03/2024 | 0 | WBSEDCL | 9.72 | 0 | 0
675 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01283/2023-2024 | 54/JMD | 07/02/2024 | 0 | WBSEDCL | 4.29 | 0 | 0
676 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01405/2023-2024 | 69/JMD | 13/03/2024 | 0 | WBSEDCL | 5.25 | 0 | 0
677 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Saiyadpur pwss, t/w no. II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00074/2024-2025 | 48/JMD | 29/04/2024 | 0 | WBSEDCL | 7.54 | 0 | 0
678 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Saiyadpur pwss, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00075/2024-2025 | 49/JMD | 29/04/2024 | 0 | WBSEDCL | 8.15 | 0 | 0
679 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charges | DIC(D)_MMSD(D) | JE (M) | BILL/01075/2023-2024 | 10/JMD | 05/01/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
680 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New connection bill for Barsole in Bheliadiha GP | DIC(D)_MMSD(D) | JE (M) | BILL/01475/2023-2024 | 77/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
681 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New connection bill for Banksole in Bheliadiha GP | DIC(D)_MMSD(D) | JE (M) | BILL/01476/2023-2024 | 78/JMD | 20/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
682 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000322/2023-2024 | 3015/JMD | 20/10/2023 | 794 | CONCORD ENGINEERING | 621.67 | 0 | 25
683 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges at Dhobakuria TW-I water supply scheme | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00506/2024-2025 | 229/JMD | 28/06/2024 | 0 | WBSEDCL | 3.06 | 0 | 0
684 | Jhargram Mechanical Division | Jhargram RWS Sub Division | new service connection chargers at Dhobakurya-II water supply scheme | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01042/2024-2025 | 387/JMD | 04/10/2024 | 0 | WBSEDCL | 7.06 | 0 | 0
685 | Jhargram Mechanical Division | Gopiballavpur Sub Division | NEW SERVICE CONNECTION CHARGES AT SASRA T/W-I WATER SUPPLY SCHEME | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01006/2024-2025 | 346/JMD | 11/09/2024 | 0 | WBSEDCL | 6.65 | 0 | 0
686 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Nonasole w/s scheme, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01375/2023-2024 | 38/JMD | 11/03/2024 | 0 | WBSEDCL | 5.62 | 0 | 0
687 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Nonasol w/s scheme, t/w no.II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01376/2023-2024 | 39/JMD | 11/03/2024 | 0 | WBSEDCL | 2.29 | 0 | 0
688 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | new service connection charges at Kuilabad TW-I water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00976/2024-2025 | 338/JMD | 05/09/2024 | 0 | WBSEDCL | 12.35 | 0 | 0
689 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | new service connection charges at Kuilabad T/W-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01415/2024-2025 | 426/JMD | 28/11/2024 | 0 | WBSEDCL | 5.59 | 0 | 0
690 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00412/2023-2024 | 7/JMD | 07/09/2023 | 0 | WBSEDCL | 3.25 | 0 | 0
691 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer | Junior Engineer-II | BILL/00254/2023-2024 | 17/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 2.02 | 0 | 0
692 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection | Assistant Engineer | Junior Engineer-II | BILL/00671/2023-2024 | 2/JMD | 20/11/2023 | 0 | WBSEDCL | 5.68 | 0 | 0
693 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection | Assistant Engineer | Junior Engineer-II | BILL/00701/2023-2024 | 26/JMD | 29/11/2023 | 0 | WBSEDCL | 0.12 | 0 | 0
694 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bakra & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000202/2023-2024 | 2263/JMD | 09/08/2023 | 180 | DEY ENTERPRISE | 22.09 | 19.2 | 92
695 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation payment for Chandalbandh-III. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00024/2024-2025 | 23/JMD | 24/04/2024 | 0 | WBSEDCL | 3.17 | 0 | 0
696 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at proposed additional T/Well as a part of augmentation of Chandalbandh W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000168/2023-2024 | 2092/JMD | 03/08/2023 | 837 | BUSR ENGINEERING | 12.08 | 0 | 100
697 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Repairing & rejuvenation of various installed electro mechanical accessories for augmentation of ground water based water supply scheme for Laudaha Pump house no. II to accommodate FHTC at Sankrail block in Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | ORD/000068/2022-2023 | 1126/JMD | 10/06/2022 | 30 | MENAKA ENTERPRISE | 8.33 | 8.26 | 0
698 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation of various electro-mechanical accessories for Laudaha W/S scheme, T/W no. I to accommodate FHTC at Sankrail block in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | ORD/000173/2023-2024 | 2099/JMD | 03/08/2023 | 30 | P.K. ENGINEERING | 2.37 | 2.29 | 100
699 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply & delivery of stand by submersible pumping machinery at pump house no. II of Laudaha ground water based water supply scheme of Sankrail block of Jhargram Dist. under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | ORD/000750/2022-2023 | 163/JMD | 27/01/2023 | 7 | MENAKA ENTERPRISE | 0.5 | 0.49 | 0
700 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Payment for new service connection of WBSEDCL. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | VCH/000725/2022-2023 | 24/JMD/PFMS/SEP | 14/09/2022 | 0 | WBSEDCL | 0.35 | 0 | 0
701 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00429/2023-2024 | 9/JMD | 28/09/2023 | 0 | WBSEDCL | 6.52 | 0 | 0
702 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00433/2023-2024 | 14/JMD | 28/09/2023 | 0 | WBSEDCL | 3.98 | 0 | 0
703 | Jhargram Mechanical Division | Jhargram Division | new meter connection charges of Dalkati-I water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00017/2024-2025 | 16/JMD | 15/04/2024 | 0 | WBSEDCL | 3.03 | 0 | 0
704 | Jhargram Mechanical Division | Jhargram Division | new meter connection charges of Dalkati T/W-II water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00018/2024-2025 | 17/JMD | 15/04/2024 | 0 | WBSEDCL | 9.97 | 0 | 0
705 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dalkati & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000040/2023-2024 | 1239/JMD | 26/05/2023 | 180 | CHATTERJEE CONSTRUCTION | 20.81 | 4.54 | 60
706 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00248/2023-2024 | 11/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 2.31 | 0 | 0
707 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00673/2023-2024 | 20/JMD | 20/11/2023 | 0 | WBSEDCL | 3.13 | 0 | 0
708 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00704/2023-2024 | 28/JMD | 29/11/2023 | 0 | WBSEDCL | 0.05 | 0 | 0
709 | Jhargram Mechanical Division | Jhargram Division | New service connection charges at Champasole water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00402/2024-2025 | 191/JMD | 14/06/2024 | 0 | WBSEDCL | 11.57 | 0 | 0
710 | Jhargram Mechanical Division | Jhargram Division | New service connection payment towards WBSEDCL for Sankhuliya | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | BILL/00159/2024-2025 | 89/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
711 | Jhargram Mechanical Division | Jhargram Division | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM.(scheme code.- SM/11476) | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | BILL/01024/2024-2025 | 356/JMD | 13/09/2024 | 0 | SURAJ SERVICE STATION | 1.04 | 0 | 0
712 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | BILL/01150/2023-2024 | 33/JMD | 18/01/2024 | 0 | WBSEDCL | 2.1 | 0 | 0
713 | Jhargram Mechanical Division | Jhargram Division | New service connection charge at Dubrajpur. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | BILL/01208/2023-2024 | 48/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
714 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Dhobajan at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | ORD/000597/2024-2025 | 6757/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 1.56 | 0 | 100
715 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Jabarpur at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | ORD/000598/2024-2025 | 6758/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 1.56 | 0 | 100
716 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Ergoda at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | ORD/000599/2024-2025 | 6759/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0
717 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Mujrakanali at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | ORD/000601/2024-2025 | 6761/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0
718 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Baharabani at Binpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer-II | ORD/000613/2024-2025 | 6773/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 3.49 | 0 | 100
719 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Thakurpara TW-III water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00390/2024-2025 | 186/JMD | 11/06/2024 | 0 | WBSEDCL | 6.61 | 0 | 0
720 | Jhargram Mechanical Division | Jhargram Sub-Division | New service connection charges | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00876/2023-2024 | 49/JMD | 29/12/2023 | 0 | WBSEDCL | 4.78 | 0 | 0
721 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection charges. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01479/2023-2024 | 84/JMD | 21/03/2024 | 0 | WBSEDCL | 5.52 | 0 | 0
722 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00657/2023-2024 | 8/JMD | 08/11/2023 | 0 | WBSEDCL | 2.97 | 0 | 0
723 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges for Haripurbirua, t/w no.II pwss | Assistant Engineer | JE (M),Junior Engineer-II | BILL/01369/2023-2024 | 32/JMD | 11/03/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
724 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00250/2023-2024 | 13/JMD/PFMS/JUL | 27/07/2023 | 0 | WBSEDCL | 10.44 | 0 | 0
725 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00265/2023-2024 | 4/JMD/AUG | 17/08/2023 | 0 | WBSEDCL | 2.93 | 0 | 0
726 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Additional Service Connection Charges for Karkatasola P.H - I PWSS | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00441/2024-2025 | 209/JMD | 20/06/2024 | 0 | WBSEDCL | 8.66 | 0 | 0
727 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Karkatasol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M),Junior Engineer-II | ORD/000199/2023-2024 | 2260/JMD | 09/08/2023 | 180 | DAS ENTERPRISE | 20.74 | 17.88 | 94
728 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Darkhuli | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | BILL/00003/2024-2025 | 7/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
729 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Bhaliadiha. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | BILL/00004/2024-2025 | 8/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
730 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Jangal Khas | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | BILL/00005/2024-2025 | 9/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
731 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Krishnanagar water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | BILL/00184/2024-2025 | 104/JMD | 08/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
732 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Salgeria PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | BILL/00705/2024-2025 | 269/JMD | 26/07/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
733 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | BILL/01132/2023-2024 | 13/JMD | 09/01/2024 | 0 | WBSEDCL | 1.47 | 0 | 0
734 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block | BILL/01216/2023-2024 | 47/JMD | 06/02/2024 | 0 | WBSEDCL | 2.1 | 0 | 0
735 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pindra Kuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000032/2023-2024 | 1230/JMD | 26/05/2023 | 180 | RSA ENTERPRISE | 20.71 | 0 | 0
736 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection charges Kantore T/W-2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00084/2024-2025 | 58/JMD | 29/04/2024 | 0 | WBSEDCL | 8.63 | 0 | 0
737 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new connection at Kantore t/w-1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00085/2024-2025 | 59/JMD | 29/04/2024 | 0 | WBSEDCL | 4.07 | 0 | 0
738 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Bishnupur pwss, t/w no. I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00073/2024-2025 | 47/JMD | 29/04/2024 | 0 | WBSEDCL | 3.92 | 0 | 0
739 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Damodarpur & adjacent water supply schemes of Garhbeta-III block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000139/2024-2025 | 3784/JMD | 12/07/2024 | 30 | MONORANJAN DEY | 2.83 | 0 | 30
740 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges for Pathri w/s scheme, t/w no.-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01967/2023-2024 | 184/JMD | 30/03/2024 | 0 | WBSEDCL | 8.52 | 0 | 0
741 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges for Pathri w/s scheme, t/w no.-I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01968/2023-2024 | 185/JMD | 30/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0
742 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Mahasol, t/w-II w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01307/2023-2024 | 78/JMD | 12/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0
743 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Mahasol, t/w-I w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01309/2023-2024 | 80/JMD | 12/02/2024 | 0 | WBSEDCL | 3.03 | 0 | 0
744 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01355/2023-2024 | 19/JMD | 04/03/2024 | 0 | WBSEDCL | 5.33 | 0 | 0
745 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01356/2023-2024 | 20/JMD | 04/03/2024 | 0 | WBSEDCL | 4.23 | 0 | 0
746 | Jhargram Mechanical Division | Jhargram Division | New service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00781/2023-2024 | 21/JMD | 08/12/2023 | 0 | WBSEDCL | 8.86 | 0 | 0
747 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01337/2023-2024 | 104/JMD | 27/02/2024 | 0 | WBSEDCL | 4.52 | 0 | 0
748 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gramohan & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000072/2023-2024 | 1244/JMD | 26/05/2023 | 180 | MAA BHABOTARINE ENTERPRISE | 21.76 | 18.14 | 65
749 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service Connection Charges for Garmal T/W - I PWSS | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01028/2024-2025 | 359/JMD | 20/09/2024 | 0 | WBSEDCL | 8.11 | 0 | 0
750 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service Connection Charges for Pathrajuri-I PWSS | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01543/2024-2025 |  | 12/12/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
751 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-VII, Damsole & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000218/2023-2024 | 2284/JMD | 10/08/2023 | 180 | SUBHASIS ROY | 21.03 | 0 | 0
752 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at replacement T/W no. II of Domsol water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000836/2023-2024 | 1652/JMD | 08/02/2024 | 120 | MAA BHABOTARINE ENTERPRISE | 9.42 | 7.98 | 100
753 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00420/2024-2025 | 199/JMD | 14/06/2024 | 0 | WBSEDCL | 4.72 | 0 | 0
754 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at Kenchkapur T/W-II water supply scheme. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01041/2024-2025 | 377/JMD | 30/09/2024 | 0 | WBSEDCL | 5.3 | 0 | 0
755 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00625/2023-2024 | 8/JMD | 11/10/2023 | 0 | WBSEDCL | 11.96 | 0 | 0
756 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00626/2023-2024 | 9/JMD | 11/10/2023 | 0 | WBSEDCL | 7.31 | 0 | 0
757 | Jhargram Mechanical Division | Jhargram Division | New Service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00661/2023-2024 | 1/JMD | 20/11/2023 | 0 | WBSEDCL | 5.34 | 0 | 0
758 | Jhargram Mechanical Division | Jhargram Division | New Service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00662/2023-2024 |  | 09/11/2023 | 0 | WBSEDCL | 0.16 | 0 | 0
759 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00676/2023-2024 | 23/JMD | 24/11/2023 | 0 | WBSEDCL | 1.43 | 0 | 0
760 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Saftaldiha & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000067/2023-2024 | 1237/JMD | 26/05/2023 | 180 | MAA BHABOTARINE ENTERPRISE | 20.78 | 17.06 | 86
761 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service Connection Charges for Bhamal P.H -II PWSS | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00428/2024-2025 | 202/JMD | 14/06/2024 | 0 | WBSEDCL | 3.43 | 0 | 0
762 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00656/2023-2024 | 7/JMD | 08/11/2023 | 0 | WBSEDCL | 2.85 | 0 | 0
763 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhamal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | ORD/000071/2023-2024 | 1242/JMD | 26/05/2023 | 180 | M/S A.D. CONCERN | 21.75 | 0 | 0
764 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT DHENGADAHA TW-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00571/2024-2025 | 250/JMD | 10/07/2024 | 0 | WBSEDCL | 5.32 | 0 | 0
765 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT DHENGADAHA TW-II WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00572/2024-2025 | 251/JMD | 10/07/2024 | 0 | WBSEDCL | 5.83 | 0 | 0
766 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00432/2023-2024 | 13/JMD | 28/09/2023 | 0 | WBSEDCL | 5.08 | 0 | 0
767 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Barashol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | ORD/000208/2023-2024 | 2269/JMD | 09/08/2023 | 180 | M/S B.M. ELECTRICAL | 22.53 | 19.06 | 80
768 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00667/2023-2024 | 15/JMD | 10/11/2023 | 0 | WBSEDCL | 2.99 | 0 | 0
769 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Replacement Tube Well no. II of Banspahari piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. |  | Junior Engineer-II | ORD/000152/2023-2024 | 1940/JMD | 28/07/2023 | 30 | ECO ENTERPRISE | 8.35 | 8.26 | 98
770 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dahatmal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000034/2023-2024 | 1232/JMD | 26/05/2023 | 180 | M/S. NABIN GOPAL SENGUPTA | 20.79 | 0 | 75
771 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Quotation for new servcie connection at PITHAPURA TW-II water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00168/2024-2025 | 95/JMD | 08/05/2024 | 0 | WBSEDCL | 8.22 | 0 | 0
772 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00874/2023-2024 | 47/JMD | 29/12/2023 | 0 | WBSEDCL | 5.49 | 0 | 0
773 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00384/2023-2024 | 23/AUG | 25/08/2023 | 0 | WBSEDCL | 7.91 | 0 | 0
774 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00385/2023-2024 | 24/AUG | 25/08/2023 | 0 | WBSEDCL | 2.81 | 0 | 0
775 | Jhargram Mechanical Division | Jhargram Division | new service connection for Kaliam water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00001/2024-2025 | 01/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
776 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Juasole,Parsuli water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00002/2024-2025 | 02/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
777 | Jhargram Mechanical Division | Jhargram Division | New Service Connection Charges for Kapashi PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00163/2024-2025 | 82/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
778 | Jhargram Mechanical Division | Jhargram Division | New Service Connection Charges for Chirkundihi PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00164/2024-2025 | 83/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
779 | Jhargram Mechanical Division | Jhargram Division | New Service Connection Charges for Bhalukhuliya PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00165/2024-2025 | 84/JMD | 07/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
780 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/01294/2023-2024 | 65/JMD | 12/02/2024 | 0 | WBSEDCL | 0.84 | 0 | 0
781 | Jhargram Mechanical Division | Jhargram Division | Fuel & lubricant charges which is used at Rig unit HALCO for boring purpose at the site of Balidiha under 179 scheme(SM/11478) under Jamboni block | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/01367/2024-2025 | 424/JMD | 27/11/2024 | 0 | SURAJ SERVICE STATION | 0.53 | 0 | 0
782 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Balidiha at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | ORD/000608/2024-2025 | 6768/JMD | 27/08/2024 | 34 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 100
783 | Jhargram Mechanical Division | Jhargram Division | Supply , Delivery of Hydraulic pump for rotation motor of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | ORD/001031/2024-2025 | 16/W/MMSD(D) | 13/01/2025 | 10 | CHAKRABORTY MINING & ENGINEERING | 0.97 | 0 | 100
784 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at Tikayetpur T/W-I water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00598/2024-2025 | 259/JMD | 15/07/2024 | 0 | WBSEDCL | 6.86 | 0 | 0
785 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service Connection Charges for Tikayetpur tw-I pwss | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01200/2023-2024 | 41/JMD | 01/02/2024 | 0 | WBSEDCL | 2.88 | 0 | 0
786 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00337/2023-2024 | 16/AUG | 24/08/2023 | 0 | WBSEDCL | 2.83 | 0 | 0
787 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00342/2023-2024 | 21/AUG | 24/08/2023 | 0 | WBSEDCL | 4.82 | 0 | 0
788 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belda & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | ORD/000197/2023-2024 | 2258/JMD | 09/08/2023 | 180 | AMIT DAS | 20.75 | 14.14 | 75
789 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection charges Ruparghagra T/W-1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00090/2024-2025 | 64/JMD | 29/04/2024 | 0 | WBSEDCL | 8.29 | 0 | 0
790 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection charges Ruparghagra T/W-2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00091/2024-2025 | 65/JMD | 29/04/2024 | 0 | WBSEDCL | 7.43 | 0 | 0
791 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at BARAKURA T/W -I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00229/2024-2025 | 112/JMD | 13/05/2024 | 0 | WBSEDCL | 12.13 | 0 | 0
792 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Barakeundi w/s scheme, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01373/2023-2024 | 36/JMD | 11/03/2024 | 0 | WBSEDCL | 3.51 | 0 | 0
793 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Barakeundi w/s scheme, t/w no.II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01374/2023-2024 | 37/JMD | 11/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
794 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Baranagora t/w 1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00080/2024-2025 | 54/JMD | 29/04/2024 | 0 | WBSEDCL | 6.85 | 0 | 0
795 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Baranagora t/w 2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00081/2024-2025 | 55/JMD | 29/04/2024 | 0 | WBSEDCL | 10.04 | 0 | 0
796 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Karsa T/W-II water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00068/2024-2025 | 42/JMD | 29/04/2024 | 0 | WBSEDCL | 3.15 | 0 | 0
797 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00419/2024-2025 | 198/JMD | 14/06/2024 | 0 | WBSEDCL | 6.87 | 0 | 0
798 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service Connection Charges for Kakridahi t/w-II pwss | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01194/2023-2024 | 35/JMD | 01/02/2024 | 0 | WBSEDCL | 2.67 | 0 | 0
799 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service Connection Charges for Kakridahi tw-I pwss | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01195/2023-2024 | 36/JMD | 01/02/2024 | 0 | WBSEDCL | 3.2 | 0 | 0
800 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00389/2023-2024 | 27/AUG | 29/08/2023 | 0 | WBSEDCL | 6.24 | 0 | 0
801 | Jhargram Mechanical Division | Jhargram Division | New Service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00668/2023-2024 | 16/JMD | 10/11/2023 | 0 | WBSEDCL | 6.88 | 0 | 0
802 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01766/2023-2024 | 125/JMD | 29/03/2024 | 0 | WBSEDCL | 0.82 | 0 | 0
803 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Radhanagar & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000045/2023-2024 | 1248/JMD | 26/05/2023 | 180 | BEE GEE CONSTRUCTION | 21.86 | 17.9 | 100
804 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Agra-II water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00387/2024-2025 | 183/JMD | 11/06/2024 | 0 | WBSEDCL | 3.34 | 0 | 0
805 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01399/2023-2024 | 62/JMD | 13/03/2024 | 0 | WBSEDCL | 5.26 | 0 | 0
806 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT PATHRISOLE TW-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00565/2024-2025 | 244/JMD | 10/07/2024 | 0 | WBSEDCL | 7.8 | 0 | 0
807 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT PATHRISOLE TW-II WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00566/2024-2025 | 245/JMD | 10/07/2024 | 0 | WBSEDCL | 3.93 | 0 | 0
808 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection charges Dumuria T/W-1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00086/2024-2025 | 60/JMD | 29/04/2024 | 0 | WBSEDCL | 3.59 | 0 | 0
809 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection at Dumuria T/W-2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00261/2024-2025 | 116/JMD | 13/05/2024 | 0 | WBSEDCL | 4.95 | 0 | 0
810 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for WBSEDCL new connection at KADAMDIHA 1 (SM/15012. KADAMDIHA AND ADJOINING MOUJAS PWSS ) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00373/2024-2025 | 174/JMD | 07/06/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
811 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Kadamdiha t/w 2 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00510/2024-2025 | 228/JMD | 28/06/2024 | 0 | WBSEDCL | 7.12 | 0 | 0
812 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection | AE Ghatal Sub-division,Assistant Engineer,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Junior Engineer,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00623/2023-2024 | 6/JMD | 11/10/2023 | 0 | WBSEDCL | 5.63 | 0 | 0
813 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection | AE Ghatal Sub-division,Assistant Engineer,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Junior Engineer,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00624/2023-2024 | 7/JMD | 11/10/2023 | 0 | WBSEDCL | 6.36 | 0 | 0
814 | Jhargram Mechanical Division | Jhargram Division | New service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00780/2023-2024 | 20/JMD | 08/12/2023 | 0 | WBSEDCL | 9.92 | 0 | 0
815 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01361/2023-2024 | 24/JMD | 04/03/2024 | 0 | WBSEDCL | 3 | 0 | 0
816 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Barabari & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000033/2023-2024 | 1231/JMD | 26/05/2023 | 180 | KAMAKHYA ENTERPRISE | 20.79 | 17.32 | 87
817 | Jhargram Mechanical Division | Jhargram Division | Supply delivery & Installation of actuator operated double flanged type Sluice Valve at three different locations in the delivery pipeline with other allied works at Barabari PWSS of Jhargram block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000033/2025-2026 | 1115/JMD | 27/05/2025 | 60 | DEBJYOTI BASU | 11.06 | 0 | 0
818 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Telijhant TW-II water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00461/2024-2025 | 219/JMD | 21/06/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
819 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Telijhant TW-I water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00462/2024-2025 | 220/JMD | 21/06/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
820 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT Dhobaberia TW-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00573/2024-2025 | 252/JMD | 10/07/2024 | 0 | WBSEDCL | 4.02 | 0 | 0
821 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT Dhobaberia TW-II WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00574/2024-2025 | 253/JMD | 10/07/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
822 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service Connection Charges for Amlatora T/W-I PWSS | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01020/2024-2025 | 353/JMD | 13/09/2024 | 0 | WBSEDCL | 3.56 | 0 | 0
823 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service Connection Charges for Amlatora T/W - II PWSS | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01031/2024-2025 | 368/JMD | 24/09/2024 | 0 | WBSEDCL | 6.51 | 0 | 0
824 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-V, Bashajuri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | Junior Engineer RWS, Binpur-II Devlopment Block.,JE (M) | ORD/000217/2023-2024 | 2283/JMD | 10/08/2023 | 180 | SUJOY RANJAN BHOWMICK | 21.04 | 0 | 0
825 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01284/2023-2024 | 55/JMD | 08/02/2024 | 0 | WBSEDCL | 5.67 | 0 | 0
826 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01285/2023-2024 | 56/JMD | 08/02/2024 | 0 | WBSEDCL | 5.67 | 0 | 0
827 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01286/2023-2024 | 57/JMD | 08/02/2024 | 0 | WBSEDCL | 3.49 | 0 | 0
828 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection for Bandipur W/S Scheme | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | BILL/01039/2024-2025 | 379/JMD | 30/09/2024 | 0 | WBSEDCL | 6.77 | 0 | 0
829 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery and installation of pumping machineries and allied electro-mechanical accessories for Low lift and High lift pumping operations for augmentation of pond based Silda and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/001048/2024-2025 | 480/JMD | 20/03/2025 | 150 | B. T. PROJECTS PVT. LTD. | 86.7 | 0 | 0
830 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Gangani TW-I | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00463/2024-2025 | 221/JMD | 21/06/2024 | 0 | WBSEDCL | 4.57 | 0 | 0
831 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Gangani TW-II | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00464/2024-2025 | 222/JMD | 21/06/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
832 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Dharampur zone-VI, Chandpara & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000216/2023-2024 | 2282/JMD | 10/08/2023 | 180 | DEBJYOTI BASU | 30.67 | 0 | 0
833 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Gohalmara water supply scheme T/W - I | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00022/2024-2025 | 21/JMD | 19/04/2024 | 0 | WBSEDCL | 3.41 | 0 | 0
834 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Gohalmara water supply scheme T/W-II | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00023/2024-2025 | 22/JMD | 19/04/2024 | 0 | WBSEDCL | 4 | 0 | 0
835 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at Jhakra T/W-II water supply scheme. | AE Ghatal Sub-division |  | BILL/00877/2024-2025 | 305/JMD | 14/08/2024 | 0 | WBSEDCL | 8.95 | 0 | 0
836 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division |  | BILL/01495/2023-2024 | 88/JMD | 22/03/2024 | 0 | WBSEDCL | 7.03 | 0 | 0
837 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection for Kuapur W/S Scheme. | AE Ghatal Sub-division |  | BILL/01040/2024-2025 | 380/JMD | 30/09/2024 | 0 | WBSEDCL | 3.81 | 0 | 0
838 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Chakua water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00020/2024-2025 | 19/JMD | 15/04/2024 | 0 | WBSEDCL | 5.29 | 0 | 0
839 | Jhargram Mechanical Division | Jhargram Division | New meter connection charges of Chakua-2 water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00025/2024-2025 | 24/JMD | 22/04/2024 | 0 | WBSEDCL | 9.92 | 0 | 0
840 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chakkua & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000068/2023-2024 | 1238/JMD | 26/05/2023 | 180 | DEB KUMAR BASU | 20.83 | 14.18 | 50
841 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection atSONAKUNIA TW-I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00173/2024-2025 | 100/JMD | 08/05/2024 | 0 | WBSEDCL | 5.02 | 0 | 0
842 | Jhargram Mechanical Division | Jhargram Sub-Division | Qutation for new service connection at Sonakunia T/W-II water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00350/2024-2025 | 153/JMD | 31/05/2024 | 0 | WBSEDCL | 7.11 | 0 | 0
843 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | BILL/00417/2024-2025 | 194/JMD | 14/06/2024 | 0 | WBSEDCL | 5.62 | 0 | 0
844 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | BILL/00418/2024-2025 | 197/JMD | 14/06/2024 | 0 | WBSEDCL | 10.09 | 0 | 0
845 | Jhargram Mechanical Division | Jhargram RWS Sub Division | new service connection charges at Gidhni water supply scheme | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00317/2024-2025 | 136/JMD | 24/05/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
846 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Providing fuel and lubricant for rig unit 238/AR/HALCO for boring purpose, augmentation of Ground water based water supply scheme for Gidhni (SM/09374) of two sites in Jamboni Block under Jhargram Division PHE Dte | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00709/2024-2025 | 274/JMD | 26/07/2024 | 0 | SURAJ SERVICE STATION | 1.01 | 0 | 0
847 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00850/2023-2024 | 30/JMD | 19/12/2023 | 0 | WBSEDCL | 0.21 | 0 | 0
848 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for newly sunk tubewell for augmentation of Gidhni (Zone-I) water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000727/2022-2023 | 308/JMD | 09/02/2023 | 120 | SUBHASIS ROY | 7.27 | 6.44 | 75
849 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other Electro Mechanical accessories for Charichaka ICDS water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/001399/2023-2024 | 3081/JMD | 14/03/2024 | 120 | DAS CONSTRUCTION | 5.82 | 0 | 0
850 | Jhargram Mechanical Division | Jhargram Division | WBSEDCL new service connection. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00008/2022-2023 | 8/JMD/PFMS/DEC | 07/12/2022 | 0 | WBSEDCL | 0.34 | 0 | 0
851 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation & commisioning of pumping machinery and other electro mechanical accessories at newly sunk replacement tubwell no.I at Pukuria W/S scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000581/2022-2023 | 3195/JMD | 28/10/2022 | 30 | DEBJYOTI BASU | 10.07 | 9.7 | 95
852 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of pumping machinery and other electro mechanical accessories at newly sunk replacement tubwell no.II (Near Primary School) of Pukuria W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000724/2022-2023 | 305/JMD | 09/02/2023 | 120 | RSA ENTERPRISE | 9.76 | 9.16 | 0
853 | Jhargram Mechanical Division |  | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM for scheme (SM/09380) KECHENDA PWSS |  |  | BILL/00898/2024-2025 | 329/JMD | 29/08/2024 | 0 | SURAJ SERVICE STATION | 0.93 | 0 | 0
854 | Jhargram Mechanical Division |  | New Service Connection Charges for Kechanda T/W - III PWSS |  |  | BILL/01032/2024-2025 | 369/JMD | 24/09/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
855 | Jhargram Mechanical Division |  | Supply, delivery, installation, commissioning of submersible pumping machinery and other Electro Mechanical accessories at newly sunk tube well at Kechenda of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. |  |  | ORD/000802/2024-2025 | 7305/JMD | 13/11/2024 | 30 | M/S. NABIN GOPAL SENGUPTA | 2.12 | 0 | 100
856 | Jhargram Mechanical Division |  | Sinking tubewell (200 mm X 165 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works near Kechenda PWSS at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. |  |  | ORD/001397/2023-2024 | 3079/JMD | 14/03/2024 | 5 | SUJOY RANJAN BHOWMICK | 3.32 | 3.22 | 100
857 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Ichhapura | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block,Junior Engineer Sankrail block | BILL/00006/2024-2025 | 03/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
858 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Rangamatia | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block,Junior Engineer Sankrail block | BILL/00009/2024-2025 | 10/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
859 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block,Junior Engineer Sankrail block | BILL/01215/2023-2024 | 46/JMD | 06/02/2024 | 0 | WBSEDCL | 1.26 | 0 | 0
860 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES FOR SHIYALIA PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block,Junior Engineer Sankrail block | BILL/01384/2023-2024 | 47/JMD | 11/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
861 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES FOR CHOTOKANYADIHA PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Nayagram block,Junior Engineer Sankrail block | BILL/01385/2023-2024 | 48/JMD | 11/03/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
862 | Jhargram Mechanical Division | Jhargram Division | New Service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00659/2023-2024 | 10/JMD | 10/11/2023 | 0 | WBSEDCL | 3.12 | 0 | 0
863 | Jhargram Mechanical Division | Jhargram Division | New Service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | BILL/00660/2023-2024 | 11/JMD | 10/11/2023 | 0 | WBSEDCL | 3.25 | 0 | 0
864 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Murabani & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-I | ORD/000069/2023-2024 | 1240/JMD | 26/05/2023 | 180 | R.K. ENTERPRISES | 20.82 | 4.24 | 60
865 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection for Bandarboni T/W-2 water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00105/2024-2025 | 78/JMD | 29/04/2024 | 0 | WBSEDCL | 2.72 | 0 | 0
866 | Jhargram Mechanical Division | Jhargram Sub-Division | Qutation for new service connection at Bandarboni T/W-1 water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01497/2023-2024 | 89/JMD | 22/03/2024 | 0 | WBSEDCL | 2.87 | 0 | 0
867 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Mirga w/s scheme, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01377/2023-2024 | 40/JMD | 11/03/2024 | 0 | WBSEDCL | 5.86 | 0 | 0
868 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Mirga w/s scheme, t/w no.II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01378/2023-2024 | 41/JMD | 11/03/2024 | 0 | WBSEDCL | 5.09 | 0 | 0
869 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT PATHARTORIA TW-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00567/2024-2025 | 246/JMD | 10/07/2024 | 0 | WBSEDCL | 3.53 | 0 | 0
870 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for new service connection at Keshia T/W-1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00083/2024-2025 | 57/JMD | 29/04/2024 | 0 | WBSEDCL | 3.45 | 0 | 0
871 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for WBSEDCL new connection at KESIA 2 (SM/13124. KESIA AND ADJOINING MOUJAS PWSS ) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00372/2024-2025 | 173/JMD | 07/06/2024 | 0 | WBSEDCL | 7.69 | 0 | 0
872 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Chandri T/W-1,water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00102/2024-2025 | 75/JMD | 29/04/2024 | 0 | WBSEDCL | 9.35 | 0 | 0
873 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Chandri-II water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/01029/2024-2025 | 360/JMD | 20/09/2024 | 0 | WBSEDCL | 5.33 | 0 | 0
874 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chandri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000047/2023-2024 | 1250/JMD | 26/05/2023 | 180 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.95 | 12.63 | 50
875 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new sevice connection at Nepura tw-I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00322/2024-2025 | 141/JMD | 24/05/2024 | 0 | WBSEDCL | 9.91 | 0 | 0
876 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Fatesingpur TW-I water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00458/2024-2025 | 216/JMD | 21/06/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
877 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at BAGHUASOLE T/W-I water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00011/2024-2025 | 11/JMD | 05/04/2024 | 0 | WBSEDCL | 2.7 | 0 | 0
878 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at BAGHUASOLE T/W-II water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00012/2024-2025 | 12/JMD | 05/04/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
879 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service Connection Charges for Rautara T/W - I PWSS | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01027/2024-2025 | 358/JMD | 20/09/2024 | 0 | WBSEDCL | 5.17 | 0 | 0
880 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Madhupur w/s scheme, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00353/2024-2025 | 156/JMD | 31/05/2024 | 0 | WBSEDCL | 6.6 | 0 | 0
881 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service charges for Madhupur w/s scheme, t/w no.II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00354/2024-2025 | 157/JMD | 31/05/2024 | 0 | WBSEDCL | 5.91 | 0 | 0
882 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Godapiasal, tw-II w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01304/2023-2024 | 75/JMD | 12/02/2024 | 0 | WBSEDCL | 3.58 | 0 | 0
883 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Godapiasal, tw-I w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01310/2023-2024 | 81/JMD | 12/02/2024 | 0 | WBSEDCL | 3.18 | 0 | 0
884 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Barbaria & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-II block | ORD/000049/2023-2024 | 1253/JMD | 26/05/2023 | 180 | SAMARPITA ENGINEERING | 31.73 | 0 | 0
885 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT BAGDOBA-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00648/2024-2025 | 261/JMD | 23/07/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
886 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Murari w/s scheme, t/w no.-I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00357/2024-2025 | 160/JMD | 31/05/2024 | 0 | WBSEDCL | 3.76 | 0 | 0
887 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Murari w/s scheme, t/w no.-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00358/2024-2025 | 161/JMD | 31/05/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
888 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service Connection Charges for Murari T/W - III PWSS | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01017/2024-2025 | 350/JMD | 13/09/2024 | 0 | WBSEDCL | 3.48 | 0 | 0
889 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES AT RAJABASA TW-II PWSS | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00894/2024-2025 | 322/JMD | 28/08/2024 | 0 | WBSEDCL | 4.04 | 0 | 0
890 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Rajabasa-I water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01030/2024-2025 | 361/JMD | 20/09/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
891 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II, III & IV and making compound lighting arrangement at T/W no. I of Rajabasa & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000050/2023-2024 | 1255/JMD | 26/05/2023 | 180 | DEBJYOTI BASU | 43.9 | 0 | 0
892 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Sukhnator T/W-I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00069/2024-2025 | 43/JMD | 29/04/2024 | 0 | WBSEDCL | 14.15 | 0 | 0
893 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no. II under JJM programme at Telidanga W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000174/2023-2024 | 2100/JMD | 03/08/2023 | 90 | JAGANNATH ENTERPRISE | 1.23 | 0 | 0
894 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Amlagura W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000175/2023-2024 | 2101/JMD | 03/08/2023 | 90 | MONORANJAN DEY | 1.23 | 0 | 0
895 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Bhaliadiha W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000176/2023-2024 | 2102/JMD | 03/08/2023 | 90 | DEBJYOTI BASU | 1.23 | 0 | 0
896 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Natundihi W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000177/2023-2024 | 2096/JMD | 03/08/2023 | 90 | RMD TRADING | 1.23 | 0 | 0
897 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of submersible pumping machinery and other Electro-Mechanical accessories for newly sunk tube well no.-II under JJM programme at Dakisole SSK W/S scheme in the dist. of Jhargram under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000299/2023-2024 | 2640/JMD | 29/08/2023 | 90 | BHABANI PRASAD MANNA | 1.23 | 0 | 0
898 | Jhargram Mechanical Division | Jhargram Sub-Division | Providing UPVC materials including other drilling related works for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000795/2022-2023 | 80/JMD | 03/01/2023 | 3 | DEBJYOTI BASU | 0.75 | 0 | 100
899 | Jhargram Mechanical Division | Jhargram Sub-Division | Providing different manpower for construction of (125 mm X 115 mm X 200 mtr) RBTW by DTH Method by departmental rig unit under JJM programme at Dakisole SSK ( T/W-2) water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | Junior Engineer Jhargram Dev. Block, Junior Engineer RWS, Binpur-II Devlopment Block., The Junior Engineer-IV Jhargram Sub-Division,JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000815/2022-2023 | 81/JMD | 03/01/2023 | 3 | DEBJYOTI BASU | 0.15 | 0 | 100
900 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. II of Lakat W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000183/2023-2024 | 2107/JMD | 03/08/2023 | 30 | DEBJYOTI BASU | 9.62 | 9.56 | 100
901 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at RAMKRISHNAPUR T/W-II water supply scheme. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/00286/2024-2025 | 124/JMD | 20/05/2024 | 0 | WBSEDCL | 3.17 | 0 | 0
902 | Jhargram Mechanical Division | Ghatal Subdivision | SHIFTING OF 11 KV HTOH LINE HATPUKUR FEEDER FOR CONSTRUCTION OF RAMKRISHNAPUR T/W-I P.H. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/00517/2024-2025 | 234/JMD | 09/07/2024 | 0 | WBSEDCL | 2.52 | 0 | 0
903 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/01478/2023-2024 | 83/JMD | 21/03/2024 | 0 | WBSEDCL | 3.28 | 0 | 0
904 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/01358/2023-2024 | 22/JMD | 04/03/2024 | 0 | WBSEDCL | 6.8 | 0 | 0
905 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation of pumping machinery and other electro-mechanical components at replacement T/W no. I of Zone-1 at Ramgarh water supply scheme in Binpur-1 Block under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000015/2025-2026 | 925/JMD | 13/05/2025 | 111 | M/S. CHANDRANATH MUKHERJEE | 3.27 | 0 | 100
906 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. I (Zone-II) of Ramgarh W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000180/2023-2024 | 2104/JMD | 03/08/2023 | 30 | A.K. INDUSTRIES | 9.61 | 0 | 100
907 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT KADABONI TW-I WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00569/2024-2025 | 248/JMD | 10/07/2024 | 0 | WBSEDCL | 7.78 | 0 | 0
908 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at Krishnapur T/W-II water supply scheme. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | BILL/00880/2024-2025 | 308/JMD | 14/08/2024 | 0 | WBSEDCL | 3.11 | 0 | 0
909 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | BILL/01363/2023-2024 | 26/JMD | 06/03/2024 | 0 | WBSEDCL | 3.38 | 0 | 0
910 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for Krishnapur T/W - I water supply scheme. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | BILL/01367/2023-2024 | 30/JMD | 11/03/2024 | 0 | WBSEDCL | 3.38 | 0 | 0
911 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Shaluka TW-I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00388/2024-2025 | 184/JMD | 11/06/2024 | 0 | WBSEDCL | 2.92 | 0 | 0
912 | Jhargram Mechanical Division | Ghatal Subdivision | Aditional quotation of new service connection at Mangrul T/W-I due to way leave problem under Ramjibanpur C.C.C. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/00817/2024-2025 | 296/JMD | 09/08/2024 | 0 | WBSEDCL | 0.49 | 0 | 0
913 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for Mangrul T/W - 2 water supply scheme. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/01407/2023-2024 | 67/JMD | 13/03/2024 | 0 | WBSEDCL | 2.79 | 0 | 0
914 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/01470/2023-2024 | 79/JMD | 20/03/2024 | 0 | WBSEDCL | 3.69 | 0 | 0
915 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00252/2023-2024 | 15/JMD/PFMS/APR | 27/07/2023 | 0 | WBSEDCL | 2.89 | 0 | 0
916 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dumri Nakrasuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M),Junior Engineer-II | ORD/000203/2023-2024 | 2264/JMD | 09/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 22.08 | 9.39 | 55
917 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Qutation for new service connection at MAHULBONI TW-II water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00169/2024-2025 | 96/JMD | 08/05/2024 | 0 | WBSEDCL | 10.75 | 0 | 0
918 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for Mahulboni T/W - I water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01423/2023-2024 | 72/JMD | 15/03/2024 | 0 | WBSEDCL | 4.3 | 0 | 0
919 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service Connection Charges for Chhayhazari Humita tw-I PWSS | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01196/2023-2024 | 37/JMD | 01/02/2024 | 0 | WBSEDCL | 4.24 | 0 | 0
920 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at GOBINDDPUR TW-II water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00171/2024-2025 | 98/JMD | 08/05/2024 | 0 | WBSEDCL | 2.73 | 0 | 0
921 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at GOBINDAPUR T/W -I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00172/2024-2025 | 99/JMD | 08/05/2024 | 0 | WBSEDCL | 3.29 | 0 | 0
922 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block- Gopiballavpur-II in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000036/2023-2024 | 1234/JMD | 26/05/2023 | 180 | GOENKA ENTERPRISE | 20.77 | 0 | 0
923 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply of Fuel and lubricants for KLR/DR/DTH-500 for the month of March 2023 during construction of RBT works under JMD,PHE dte | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00320/2024-2025 | 135/JMD | 24/05/2024 | 0 | SURAJ SERVICE STATION | 0.43 | 0 | 0
924 | Jhargram Mechanical Division | Jhargram Sub-Division | Sinking tubewell (125 mm X 115 mm X 200 mtr) by DTH / Combination Method with supply and delivery of UPVC consumables with drilling related works at Tamajuri at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/001396/2023-2024 | 3078/JMD | 14/03/2024 | 2 | SUJOY RANJAN BHOWMICK | 1.27 | 0.9 | 100
925 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Beliaberya W/S scheme under Jhargram Mechanical Division, PHE Dte. in the dist. of Jhargram. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000170/2023-2024 | 2094/JMD | 03/08/2023 | 30 | S.S. GHORAI | 13.82 | 10.05 | 90
926 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of various electro-mechanical accessories at tube well no.-I of Beliabera w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/001372/2023-2024 | 2989/JMD | 13/03/2024 | 30 | S.S. GHORAI | 1.39 | 1.36 | 100
927 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation of electro-mechanical components for tube well no. II of Beliabera water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/001401/2023-2024 | 113/W/MMSD(D) | 12/03/2024 | 30 | S.S. GHORAI | 1.39 | 1.37 | 100
928 | Jhargram Mechanical Division | Jhargram Sub-Division | New service connection charges |  | Junior Engineer-II | BILL/00265/2022-2023 | 17/JMD/PFMS/MAR | 06/03/2023 | 0 | WBSEDCL | 0.21 | 0 | 0
929 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning of Electro Mechanical accessories for newly constructed Pump house for newly sunk Rig bore T/W at Khamar piped water supply scheme of Jhargram District under Jhargram Mechanical Division P.H.E Dte. |  | Junior Engineer-II | ORD/000195/2023-2024 | 2110/JMD | 03/08/2023 | 60 | DEBJYOTI BASU | 4.46 | 4.45 | 100
930 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning of submersible pumping machinery and other Electro Mechanical accessories for two (02) nos. newly sunk Rig bore Tube well at Khamar piped water supply scheme at Binpur -II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. |  | Junior Engineer-II | ORD/000673/2022-2023 | 4212/JMD | 28/12/2022 | 30 | AMIT DAS | 7.38 | 6.57 | 0
931 | Jhargram Mechanical Division | Jhargram Sub-Division | Sinking of (200 mmX 165 mm) RBTW by DTH Method at Khamar PWSS, tube well no.-1 of Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. |  | Junior Engineer-II | ORD/000890/2021-2022 | 593/JMD | 23/12/2021 | 4 | SUJOY RANJAN BHOWMICK | 0.62 | 0 | 0
932 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for Dedicated Transformer for C.K Road Z - I P.H - III water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00942/2024-2025 | 331/JMD | 29/08/2024 | 0 | WBSEDCL | 4.42 | 0 | 0
933 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-II of Dahijuri w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/001371/2023-2024 | 2988/JMD | 13/03/2024 | 30 | SUJOY RANJAN BHOWMICK | 9.57 | 6.08 | 50
934 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery and installation of Vinyl Sign board for depicting the scheme details of Dahijuri and adjacent water supply schemes for ongoing Solarisation works for the purpose of Geotagging under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/001379/2023-2024 | 3061/JMD | 14/03/2024 | 15 | MUKHERJEE ART CENTRE | 9.68 | 9.66 | 100
935 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for Bhila T/W - I water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | BILL/01424/2023-2024 | 73/JMD | 15/03/2024 | 0 | WBSEDCL | 2.86 | 0 | 0
936 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for Bhila T/W - 2 water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | BILL/01425/2023-2024 | 74/JMD | 15/03/2024 | 0 | WBSEDCL | 3.96 | 0 | 0
937 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Tilaboni TW-III water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00391/2024-2025 | 187/JMD | 11/06/2024 | 0 | WBSEDCL | 4.43 | 0 | 0
938 | Jhargram Mechanical Division | Jhargram Sub-Division | New service connection | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01313/2023-2024 | 84/JMD | 12/02/2024 | 0 | WBSEDCL | 3.14 | 0 | 0
939 | Jhargram Mechanical Division | Jhargram Sub-Division | New service connection | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01314/2023-2024 | 85/JMD | 12/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
940 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00430/2023-2024 | 11/JMD | 28/09/2023 | 0 | WBSEDCL | 2.96 | 0 | 0
941 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00431/2023-2024 | 12/JMD | 28/09/2023 | 0 | WBSEDCL | 4.71 | 0 | 0
942 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Par Shuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | ORD/000207/2023-2024 | 2268/JMD | 09/08/2023 | 360 | JIBON GHOSH | 22.53 | 18.95 | 80
943 | Jhargram Mechanical Division | Jhargram Sub-Division | NEW SERVICE CONNECTION CHARGRES FOR BANKATI T/W -I PWSS | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01389/2023-2024 | 52/JMD | 12/03/2024 | 0 | WBSEDCL | 11.31 | 0 | 0
944 | Jhargram Mechanical Division | Jhargram Sub-Division | NEW SERVICE CONNECTION CHARGES FOR BANKATI T/W - II PWSS | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01390/2023-2024 | 53/JMD | 12/03/2024 | 0 | WBSEDCL | 5.32 | 0 | 0
945 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00872/2023-2024 | 45/JMD | 29/12/2023 | 0 | WBSEDCL | 3.44 | 0 | 0
946 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00873/2023-2024 | 46/JMD | 29/12/2023 | 0 | WBSEDCL | 2.73 | 0 | 0
947 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Phulakendu mini pwss | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | BILL/00015/2024-2025 | 15/JMD | 18/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
948 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges for Muchinala mini pwss | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | BILL/00099/2024-2025 | 72/JMD | 29/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
949 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | BILL/01138/2023-2024 | 19/JMD | 11/01/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
950 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | BILL/01149/2023-2024 | 32/JMD | 18/01/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
951 | Jhargram Mechanical Division | Jhargram Division | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. (scheme code:- SM/11477) | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | BILL/01366/2024-2025 | 423/JMD | 27/11/2024 | 0 | SURAJ SERVICE STATION | 0.12 | 0 | 0
952 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Kamarbandi at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000596/2024-2025 | 6756/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0
953 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 135 mtr.) RBTW by DTH /combination method for Matihana at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000602/2024-2025 | 6762/JMD | 27/08/2024 | 4 | RSA ENTERPRISE | 1.56 | 0 | 0
954 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Kachmabila at Gopiballavpur-I block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000603/2024-2025 | 6763/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0
955 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Dahi at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000604/2024-2025 | 6764/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0
956 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Ranjia at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000605/2024-2025 | 6765/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0
957 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Chaqua at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000606/2024-2025 | 6766/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0
958 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Mahupal at Gopiballavpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000607/2024-2025 | 6767/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0
959 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Jamdahari at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000609/2024-2025 | 6769/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0
960 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Panchberia at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000610/2024-2025 | 6770/JMD | 27/08/2024 | 127 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 100
961 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Banbhum at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000611/2024-2025 | 6771/JMD | 27/08/2024 | 127 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 100
962 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Madhabpur at Binpur-II block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block,Junior Engineer-II | ORD/000615/2024-2025 | 6775/JMD | 27/08/2024 | 127 | RSA ENTERPRISE | 3.49 | 0 | 100
963 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00410/2023-2024 | 5/JMD | 07/09/2023 | 0 | WBSEDCL | 3.32 | 0 | 0
964 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00666/2023-2024 | 14/JMD | 10/11/2023 | 0 | WBSEDCL | 3.16 | 0 | 0
965 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Rautrapur t/w-2 water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00103/2024-2025 | 76/JMD | 29/04/2024 | 0 | WBSEDCL | 6.82 | 0 | 0
966 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Rautarapur, T/W-1 water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00104/2024-2025 | 77/JMD | 29/04/2024 | 0 | WBSEDCL | 9.06 | 0 | 0
967 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rautarapur & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | ORD/000046/2023-2024 | 1249/JMD | 26/05/2023 | 180 | MAA BHABOTARINE ENTERPRISE | 21.88 | 16.48 | 50
968 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service Connection charges for Sumitrapur tw-II pwss | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01197/2023-2024 | 38/JMD | 01/02/2024 | 0 | WBSEDCL | 3.83 | 0 | 0
969 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service Connection charges for Sumitrapur, Tw-I pwss | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01198/2023-2024 | 39/JMD | 01/02/2024 | 0 | WBSEDCL | 4.28 | 0 | 0
970 | Jhargram Mechanical Division | Jhargram Sub-Division | New service connection charges | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00875/2023-2024 | 48/JMD | 29/12/2023 | 0 | WBSEDCL | 3.67 | 0 | 0
971 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new cesvice connection at Harda tw-1 water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01503/2023-2024 | 93/JMD | 22/03/2024 | 0 | WBSEDCL | 11.49 | 0 | 0
972 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Simladanga tw-III water supply scheme. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/00389/2024-2025 | 185/JMD | 11/06/2024 | 0 | WBSEDCL | 5.94 | 0 | 0
973 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Parbatipur TW-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00467/2024-2025 | 225/JMD | 21/06/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
974 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Parbatipur TW-I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00468/2024-2025 | 226/JMD | 21/06/2024 | 0 | WBSEDCL | 3.52 | 0 | 0
975 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Parbotipur & adjacent water supply schemes of Garhbeta-I block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000159/2024-2025 | 4294/JMD | 24/07/2024 | 30 | P.K. ENGINEERING | 3.31 | 0 | 0
976 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00664/2023-2024 | 13/JMD | 10/11/2023 | 0 | WBSEDCL | 8.33 | 0 | 0
977 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00675/2023-2024 | 22/JMD | 20/11/2023 | 0 | WBSEDCL | 2.64 | 0 | 0
978 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Palasbani & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000206/2023-2024 | 2267/JMD | 09/08/2023 | 180 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 22.55 | 20.18 | 85
979 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Benachapra pwss, t/w no. II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00072/2024-2025 | 46/JMD | 29/04/2024 | 0 | WBSEDCL | 3.44 | 0 | 0
980 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Benachapra pwss, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01370/2023-2024 | 33/JMD | 11/03/2024 | 0 | WBSEDCL | 5.66 | 0 | 0
981 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Goatsingla t/w 1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00093/2024-2025 | 67/JMD | 29/04/2024 | 0 | WBSEDCL | 3.68 | 0 | 0
982 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at Khandanga TW-I water supply scheme. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00878/2024-2025 | 306/JMD | 14/08/2024 | 0 | WBSEDCL | 6.54 | 0 | 0
983 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at Khandanga T/W-II water supply scheme. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00879/2024-2025 | 307/JMD | 14/08/2024 | 0 | WBSEDCL | 5.56 | 0 | 0
984 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01395/2023-2024 | 58/JMD | 13/03/2024 | 0 | WBSEDCL | 7.09 | 0 | 0
985 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Gobindapur T/W -2 water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01498/2023-2024 | 90/JMD | 22/03/2024 | 0 | WBSEDCL | 4.53 | 0 | 0
986 | Jhargram Mechanical Division | Jhargram Sub-Division | Qutation for new service connection at Gobindapur T/W-1 water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | BILL/01499/2023-2024 | 91/JMD | 22/03/2024 | 0 | WBSEDCL | 4.74 | 0 | 0
987 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Gilabani TW-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00465/2024-2025 | 223/JMD | 21/06/2024 | 0 | WBSEDCL | 3.22 | 0 | 0
988 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges at Gilabani TW-I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00466/2024-2025 | 224/JMD | 21/06/2024 | 0 | WBSEDCL | 5.08 | 0 | 0
989 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Bagbasa tw-I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01303/2023-2024 | 74/JMD | 12/02/2024 | 0 | WBSEDCL | 3.54 | 0 | 0
990 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Bagbasa tw-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01311/2023-2024 | 82/JMD | 12/02/2024 | 0 | WBSEDCL | 6.09 | 0 | 0
991 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service Connection Charges for Palaiboni T/W -I PWSS | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01018/2024-2025 | 351/JMD | 13/09/2024 | 0 | WBSEDCL | 8.03 | 0 | 0
992 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service Connection Charges for Palaiboni-II PWSS | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01019/2024-2025 | 352/JMD | 13/09/2024 | 0 | WBSEDCL | 7.97 | 0 | 0
993 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Pukuriasole w/s scheme, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01379/2023-2024 | 42/JMD | 11/03/2024 | 0 | WBSEDCL | 8.33 | 0 | 0
994 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery and installation of horizontal split casing type centrifugal pumping machineries with suitable rated horizontal foot mounted Induction motor sets and allied electro-mechanical accessories for low lift and high lift pumping operations at Dharampur Zone-IV (Madhabpur) and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000164/2023-2024 | 2009/JMD | 02/08/2023 | 180 | M/S. EMMESS | 50.21 | 0 | 0
995 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01330/2023-2024 | 97/JMD | 22/02/2024 | 0 | WBSEDCL | 4.13 | 0 | 0
996 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01472/2023-2024 | 81/JMD | 20/03/2024 | 0 | WBSEDCL | 6.88 | 0 | 0
997 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | BILL/01134/2023-2024 | 17/JMD | 10/01/2024 | 0 | SURAJ SERVICE STATION | 0.89 | 0 | 0
998 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service connection charges. | DIC(D)_MMSD(D) | JE (M) | BILL/01140/2023-2024 | 21/JMD | 11/01/2024 | 0 | WBSEDCL | 1.47 | 0 | 0
999 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charge in Nachna, Kanko GP, Binpur-1 | DIC(D)_MMSD(D) | JE (M) | BILL/01206/2023-2024 | 44/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1000 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charge in Salpatra, Kanko GP, Binpur-1 | DIC(D)_MMSD(D) | JE (M) | BILL/01207/2023-2024 | 44/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1001 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charges for Bankrasol, Kanko GP ,Jhargram | DIC(D)_MMSD(D) | JE (M) | BILL/01316/2023-2024 | 67/JMD | 12/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1002 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charges for Jadabpur, Kanko GP ,Jhargram | DIC(D)_MMSD(D) | JE (M) | BILL/01317/2023-2024 | 67/JMD | 12/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1003 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | BILL/01323/2023-2024 | 91/JMD | 16/02/2024 | 0 | SURAJ SERVICE STATION | 1.25 | 0 | 0
1004 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Kanko G.P. in place of {Dharampur Zone-III Kanko } w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | BILL/01349/2023-2024 | 12/JMD | 01/03/2024 | 0 | SURAJ SERVICE STATION | 1.23 | 0 | 0
1005 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Payment for new service connection at Korkora laldanga school(H.S),Kanko under 130 PWSS scheme. | DIC(D)_MMSD(D) | JE (M) | BILL/01554/2024-2025 |  | 18/12/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1006 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000022/2023-2024 | 1126/JMD | 18/05/2023 | 613 | RSA ENTERPRISE | 27 | 23.93 | 85
1007 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Bankrasol & adjacent eight (08) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000023/2023-2024 | 1127/JMD | 18/05/2023 | 611 | RSA ENTERPRISE | 30.38 | 21.76 | 83
1008 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Erection & commissioning of 23 (twenty three) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Kanko G.P. in place of (Dharampur Zone-III Kanko (TSM/015873) and Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000323/2023-2024 | 3016/JMD | 20/10/2023 | 675 | MONDAL PRECISION PRIVATE LIMITED | 616.83 | 224.71 | 65
1009 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Material Requisition To Resource Division | DIC(D)_MMSD(D) | JE (M) | RTOR000001/2023-2024 | 2867/JMD | 07/03/2024 | 0 | Resource Division | 4.8 | 0 | 0
1010 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charges | DIC(D)_MMSD(D) | JE (M) | BILL/00851/2023-2024 | 31/JMD | 19/12/2023 | 0 | WBSEDCL | 0.84 | 0 | 0
1011 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service connection | DIC(D)_MMSD(D) | JE (M) | BILL/00870/2023-2024 | 43/JMD | 29/12/2023 | 0 | WBSEDCL | 0.42 | 0 | 0
1012 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service connection charges. | DIC(D)_MMSD(D) | JE (M) | BILL/01348/2023-2024 | 11/JMD | 01/03/2024 | 0 | WBSEDCL | 0.63 | 0 | 0
1013 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 148 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 100
1014 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Erection & commissioning of 37 (thirty seven) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000227/2023-2024 | 2303/JMD | 14/08/2023 | 870 | CONCORD ENGINEERING | 1025.92 | 100.34 | 12
1015 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000961/2024-2025 | 193/JMD | 30/01/2025 | 352 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 20
1016 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01189/2023-2024 | 31/JMD | 01/02/2024 | 0 | WBSEDCL | 4.69 | 0 | 0
1017 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at Amarda T/W-I water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01005/2024-2025 | 347/JMD | 11/09/2024 | 0 | WBSEDCL | 3.77 | 0 | 0
1018 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at Jadavpur T/W-III water supply scheme. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/00812/2024-2025 | 294/JMD | 09/08/2024 | 0 | WBSEDCL | 6.84 | 0 | 0
1019 | Jhargram Mechanical Division | Ghatal Subdivision | Quotation for new service connection at Jadavpur T/W-I water supply scheme. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/00876/2024-2025 | 304/JMD | 14/08/2024 | 0 | WBSEDCL | 7.79 | 0 | 0
1020 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | BILL/01404/2023-2024 | 68/JMD | 13/03/2024 | 0 | WBSEDCL | 3.67 | 0 | 0
1021 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Service Connection Charges for Ragra tw-I pwss | Assistant Engineer | JE (M),Junior Engineer-II | BILL/01199/2023-2024 | 40/JMD | 01/02/2024 | 0 | WBSEDCL | 5.66 | 0 | 0
1022 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection charges for Ragra w/s scheme, t/w no.II | Assistant Engineer | JE (M),Junior Engineer-II | BILL/01368/2023-2024 | 31/JMD | 11/03/2024 | 0 | WBSEDCL | 10.96 | 0 | 0
1023 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Darkuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000196/2023-2024 | 2111/JMD | 03/08/2023 | 180 | S.K. ENTERPRISE | 15.64 | 0 | 0
1024 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at Ghorapitcha T/W-I water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00518/2024-2025 | 235/JMD | 09/07/2024 | 0 | WBSEDCL | 7.07 | 0 | 0
1025 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at Ghorapitcha T/W-II water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00519/2024-2025 | 236/JMD | 09/07/2024 | 0 | WBSEDCL | 3.04 | 0 | 0
1026 | Jhargram Mechanical Division | Jhargram Division | new service connection charge for Uransole water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00019/2024-2025 | 18/JMD | 18/04/2024 | 0 | WBSEDCL | 7.1 | 0 | 0
1027 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uransoal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000042/2023-2024 | 1245/JMD | 26/05/2023 | 705 | MANAS KUMAR SAHA | 21.75 | 0 | 40
1028 | Jhargram Mechanical Division | Jhargram RWS Sub Division | Supply, delivery and installation of horizontal split casing type centrifugal pumping machineries with suitable rated horizontal foot mounted Induction motor sets and allied electro-mechanical accessories for low lift and high lift pumping operations at Chianbera Zone-IV (Malabati) and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer | Junior Engineer-II | ORD/000214/2023-2024 | 2280/JMD | 10/08/2023 | 180 | DIPALI CONSTRUCTION | 62.3 | 0 | 0
1029 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery and Installation of new pumping machinery and other electro mechanical accessories at Naupara T/W no -II water supply scheme at Gopiballavpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | JE (M),Junior Engineer-III | ORD/000412/2022-2023 | 1653/JMD | 01/08/2022 | 15 | SHOVAN KUMAR DAS | 4.59 | 4.46 | 0
1030 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery & installation of voltage stabilizer and other allied works at Naupara tubewell no.1 water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | JE (M),Junior Engineer-III | ORD/000619/2022-2023 | 3638/JMD | 07/12/2022 | 30 | SOUMEN ELECTRIC | 4.41 | 4.37 | 0
1031 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation of pumping machinery and allied electro-mechanical accessories within newly sunk replacement tube well at P/H no. I of Naupara water supply scheme in the district of Jhargram under Jhargram Mechanical Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | JE (M),Junior Engineer-III | ORD/001044/2023-2024 | 2122/JMD | 22/02/2024 | 183 | JAGANNATH ENTERPRISE | 5.13 | 0 | 0
1032 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at PETBINDHI TW-II watyer supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00170/2024-2025 | 97/JMD | 08/05/2024 | 0 | WBSEDCL | 5.02 | 0 | 0
1033 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Petbindhi tw-I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00176/2024-2025 | 103/JMD | 08/05/2024 | 0 | WBSEDCL | 3.24 | 0 | 0
1034 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Petbindhi & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000048/2023-2024 | 1252/JMD | 26/05/2023 | 180 | M/S B.M. ELECTRICAL | 22.09 | 0 | 0
1035 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Kumari water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00008/2024-2025 | 2/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1036 | Jhargram Mechanical Division | Jhargram Division | new service connection for Ashanbani water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00010/2024-2025 | 4/JMD | 04/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1037 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Chhota Ektal water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00098/2024-2025 | 71/JMD | 29/04/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1038 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES AT KISMAT BAGJHAPA WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00263/2024-2025 | 118/JMD | 13/05/2024 | 0 | WBSEDCL | 2.98 | 0 | 0
1039 | Jhargram Mechanical Division | Jhargram Division | new service connection charges at Kasitoria water supply scheme | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/00264/2024-2025 | 119/JMD | 13/05/2024 | 0 | WBSEDCL | 2.44 | 0 | 0
1040 | Jhargram Mechanical Division | Jhargram Division | New Service connection charges | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/01131/2023-2024 | 12/JMD | 09/01/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1041 | Jhargram Mechanical Division | Jhargram Division | Fuel & lubricant charges which is used at Rig unit HALCO for boring purpose at the site of Parihati under 179 scheme(SM/11479) under Jamboni block | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | BILL/01365/2024-2025 | 422/JMD | 27/11/2024 | 0 | SURAJ SERVICE STATION | 0.54 | 0 | 0
1042 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Parihati at Jamboni block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | ORD/000531/2024-2025 | 6717/JMD | 23/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 100
1043 | Jhargram Mechanical Division | Jhargram Division | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (150 mm x 100 mm x 135 mtr.) RBTW by Rotary /combination method for Kismat Balibhasa at Jhargram block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M) | ORD/000612/2024-2025 | 6772/JMD | 27/08/2024 | 4 | CHAKRABORTY MINING & ENGINEERING | 3.42 | 0 | 0
1044 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Mahapal tw-II water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00348/2024-2025 | 151/JMD | 31/05/2024 | 0 | WBSEDCL | 3.6 | 0 | 0
1045 | Jhargram Mechanical Division | Jhargram Sub-Division | Quotation for new service connection at Mahapal tw-I water supply scheme. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00349/2024-2025 | 152/JMD | 31/05/2024 | 0 | WBSEDCL | 3.42 | 0 | 0
1046 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mahapal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000073/2023-2024 | 1254/JMD | 26/05/2023 | 180 | SUBHASIS ROY | 22.71 | 0 | 0
1047 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00336/2023-2024 | 15/Aug | 24/08/2023 | 0 | WBSEDCL | 3.04 | 0 | 0
1048 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00665/2023-2024 |  | 09/11/2023 | 0 | WBSEDCL | 13.78 | 0 | 0
1049 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Quotation for new service connection at BHALUKASOLE T/W-II water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/00013/2024-2025 | 13/JMD | 05/04/2024 | 0 | WBSEDCL | 2.56 | 0 | 0
1050 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection charges | Assistant Engineer,DIC(D)_MMSD(D) | The Junior Engineer-IV Jhargram Sub-Division,JE (M) | BILL/01193/2023-2024 | 34/JMD | 01/02/2024 | 0 | WBSEDCL | 4.62 | 0 | 0
1051 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service Connection Charges for Satkuli P.H - II PWSS | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00577/2024-2025 | 256/JMD | 10/07/2024 | 0 | WBSEDCL | 6.79 | 0 | 0
1052 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00674/2023-2024 | 21/JMD | 20/11/2023 | 0 | WBSEDCL | 5.65 | 0 | 0
1053 | Jhargram Mechanical Division | Jhargram RWS Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00706/2023-2024 | 29/JMD | 29/11/2023 | 0 | WBSEDCL | 0.11 | 0 | 0
1054 | Jhargram Mechanical Division | Jhargram Division | New Service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00773/2023-2024 | 13/JMD | 07/12/2023 | 0 | WBSEDCL | 2.82 | 0 | 0
1055 | Jhargram Mechanical Division | Jhargram Division | New Service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00774/2023-2024 | 14/JMD | 07/12/2023 | 0 | WBSEDCL | 6.12 | 0 | 0
1056 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Amlachati & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000037/2023-2024 | 1235/JMD | 26/05/2023 | 180 | S.S. GHORAI | 20.79 | 17.03 | 70
1057 | Jhargram Mechanical Division | Jhargram Division | New service connection charges for Bhaudit-1 | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01964/2023-2024 | 186/JMD | 30/03/2024 | 0 | WBSEDCL | 7.55 | 0 | 0
1058 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES AT MANTIPA-1 WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00351/2024-2025 | 154/JMD | 31/05/2024 | 0 | WBSEDCL | 7.08 | 0 | 0
1059 | Jhargram Mechanical Division | Jhargram Division | NEW SERVICE CONNECTION CHARGES AT MANTIPA-II WATER SUPPLY SCHEME | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00352/2024-2025 | 155/JMD | 31/05/2024 | 0 | WBSEDCL | 3.5 | 0 | 0
1060 | Jhargram Mechanical Division | Jhargram Division | New service connection | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00391/2023-2024 | 29/AUG | 29/08/2023 | 0 | WBSEDCL | 3.49 | 0 | 0
1061 | Jhargram Mechanical Division | Jhargram Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pathar Nala & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000044/2023-2024 | 1247/JMD | 26/05/2023 | 180 | DEY ENTERPRISE | 21.88 | 16.49 | 55
1062 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for WBSEDCL new connection at MAKLI 2 (SM/13096. MAKLI AND ADJOINING MOUJAS PWSS ) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00371/2024-2025 | 172/JMD | 07/06/2024 | 0 | WBSEDCL | 10.13 | 0 | 0
1063 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | WBSEDCL new connection payment for Manikdipa t/w 1 | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00092/2024-2025 | 66/JMD | 29/04/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
1064 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Payment for WBSEDCL new connection at Manikdipa 2 (SM/13097. MANIKDIPABARA AND ADJOINING MOUJAS PWSS ) | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00368/2024-2025 | 169/JMD | 07/06/2024 | 0 | WBSEDCL | 3.55 | 0 | 0
1065 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New service connection charges | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00253/2023-2024 | 16/JMD/PFMS/APR | 27/07/2023 | 0 | WBSEDCL | 6.48 | 0 | 0
1066 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Revused Quotation for New service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00392/2023-2024 | 30/AUG | 29/08/2023 | 0 | WBSEDCL | 0 | 0 | 0
1067 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00672/2023-2024 | 19/JMD | 20/11/2023 | 0 | WBSEDCL | 5.55 | 0 | 0
1068 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection | Assistant Engineer | JE (M),Junior Engineer-II | BILL/00703/2023-2024 | 27/JMD | 29/11/2023 | 0 | WBSEDCL | 0.12 | 0 | 0
1069 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block- Sankrail in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M),Junior Engineer-II | ORD/000200/2023-2024 | 2261/JMD | 09/08/2023 | 180 | M/S. EMMESS | 21.77 | 9.24 | 90
1070 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Babuibasa w/s scheme, t/w no.I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00355/2024-2025 | 158/JMD | 31/05/2024 | 0 | WBSEDCL | 6.05 | 0 | 0
1071 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Supply, delivery & fitting fixing of wooden board & Porcelain fuse unit for receiving power from WBSEDCL at Babaibasa & adjacent water supply schemes of Salboni block under JJM progamme under Jhargram Mechanical Division, P.H.E Dte. in the district of Paschim Medinipur. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000138/2024-2025 | 3783/JMD | 12/07/2024 | 30 | MONORANJAN DEY | 3.85 | 0 | 0
1072 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | new service connection charges at Chandabila-II water supply scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00597/2024-2025 | 258/JMD | 15/07/2024 | 0 | WBSEDCL | 3.61 | 0 | 0
1073 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01400/2023-2024 | 63/JMD | 13/03/2024 | 0 | WBSEDCL | 6.83 | 0 | 0
1074 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01401/2023-2024 | 64/JMD | 13/03/2024 | 0 | WBSEDCL | 6.33 | 0 | 0
1075 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01402/2023-2024 | 65/JMD | 13/03/2024 | 0 | WBSEDCL | 3.09 | 0 | 0
1076 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service Connection Charges for Domsole-II PWSS | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00895/2024-2025 | 323/JMD | 28/08/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
1077 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service Connection Charges for Domsole T/W-I PWSS | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/00896/2024-2025 | 324/JMD | 28/08/2024 | 0 | WBSEDCL | 3.7 | 0 | 0
1078 | Jhargram Mechanical Division | Jhargram Sub-Division | New Service connection charges. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | BILL/01157/2023-2024 | 37/JMD | 23/01/2024 | 0 | WBSEDCL | 3 | 0 | 0
1079 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at Bhaturbandi T/W-I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00064/2024-2025 | 38/JMD | 29/04/2024 | 0 | WBSEDCL | 4.02 | 0 | 0
1080 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Jharbhanga, t/w-I w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01308/2023-2024 | 79/JMD | 12/02/2024 | 0 | WBSEDCL | 3.39 | 0 | 0
1081 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Jharbhanga, t/w-II w/s scheme | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01320/2023-2024 | 88/JMD | 12/02/2024 | 0 | WBSEDCL | 3.4 | 0 | 0
1082 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection at Gohaldanga T/W-II water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00930/2024-2025 | 327/JMD | 29/08/2024 | 0 | WBSEDCL | 3.37 | 0 | 0
1083 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01298/2023-2024 | 69/JMD | 12/02/2024 | 0 | WBSEDCL | 4.49 | 0 | 0
1084 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01357/2023-2024 | 21/JMD | 04/03/2024 | 0 | WBSEDCL | 4.68 | 0 | 0
1085 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New Service connection charges. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/01481/2023-2024 | 86/JMD | 21/03/2024 | 0 | WBSEDCL | 11.56 | 0 | 0
1086 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at BARDIHA T/W-I water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00231/2024-2025 | 371/JMD | 25/09/2024 | 0 | WBSEDCL | 5.38 | 0 | 0
1087 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | Quotation for new service connection at BARDIHA T/W-II water supply scheme. | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00232/2024-2025 | 370/JMD | 25/09/2024 | 0 | WBSEDCL | 7.27 | 0 | 0
1088 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Patajhariya w/s scheme, t/w no.-II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00356/2024-2025 | 159/JMD | 31/05/2024 | 0 | WBSEDCL | 8.54 | 0 | 0
1089 | Jhargram Mechanical Division | Ghatal Subdivision | New Service connection charges. | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01137/2023-2024 | 22/JMD | 11/01/2024 | 0 | WBSEDCL | 2.79 | 0 | 0
1090 | Jhargram Mechanical Division | Ghatal Subdivision | New service connection | AE Ghatal Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/01312/2023-2024 | 83/JMD | 12/02/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
1091 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. I of Kantapahari W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | ORD/000182/2023-2024 | 2106/JMD | 03/08/2023 | 30 | SUBHASIS ROY | 9.62 | 0 | 100
1092 | Jhargram Mechanical Division | Jhargram Sub-Division | Supply, delivery, installation & commissioning of submersible pumping machinery and other electro-mechanical accessories at replacement T/W no. II of Netai W/S scheme under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000181/2023-2024 | 2105/JMD | 03/08/2023 | 30 | P.K. ENGINEERING | 9.62 | 7.3 | 17
1093 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Satpati w/s scheme, t/w no.-I | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00359/2024-2025 | 162/JMD | 31/05/2024 | 0 | WBSEDCL | 3.36 | 0 | 0
1094 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | New service connection charges for Satpati w/s scheme, t/w no.II | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00360/2024-2025 | 163/JMD | 31/05/2024 | 0 | WBSEDCL | 3.95 | 0 | 0
1095 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Siarkatia & Beniadihi),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte. upto 21.03.2024 | DIC(D)_MMSD(D) | JE (M) | BILL/00268/2024-2025 | 126/JMD | 20/05/2024 | 0 | SURAJ SERVICE STATION | 1.04 | 0 | 0
1096 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel & lubricant for rig unit 238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Birgeria)(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division PHE Dte. upto 05.04.2024 | DIC(D)_MMSD(D) | JE (M) | BILL/00319/2024-2025 | 133/JMD | 24/05/2024 | 0 | SURAJ SERVICE STATION | 0.54 | 0 | 0
1097 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. Dharampur zone-II Barbasuli and adjoining moujas PWSS (SM/17924). | DIC(D)_MMSD(D) | JE (M) | BILL/00675/2024-2025 | 266/JMD | 26/07/2024 | 0 | SURAJ SERVICE STATION | 0.82 | 0 | 0
1098 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Amakuli),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte | DIC(D)_MMSD(D) | JE (M) | BILL/00708/2024-2025 | 273/JMD | 26/07/2024 | 0 | SURAJ SERVICE STATION | 0.54 | 0 | 0
1099 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM for Scheme(SM/17924) Bibarda & Baramsol in Ergoda GP, Binpur -2 | DIC(D)_MMSD(D) | JE (M) | BILL/00899/2024-2025 | 330/JMD | 29/08/2024 | 0 | SURAJ SERVICE STATION | 1.12 | 0 | 0
1100 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service connection charges. | DIC(D)_MMSD(D) | JE (M) | BILL/01139/2023-2024 | 20/JMD | 11/01/2024 | 0 | WBSEDCL | 0.63 | 0 | 0
1101 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New service connection charge in Ratanpur, Kanko GP, Binpur-1 | DIC(D)_MMSD(D) | JE (M) | BILL/01205/2023-2024 | 45/JMD | 06/02/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1102 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service connection charges. | DIC(D)_MMSD(D) | JE (M) | BILL/01345/2023-2024 | 8/JMD | 01/03/2024 | 0 | WBSEDCL | 0.42 | 0 | 0
1103 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | BILL/01350/2023-2024 | 13/JMD | 01/03/2024 | 0 | SURAJ SERVICE STATION | 1.68 | 0 | 0
1104 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service Connection Charges for Birgeria PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS | DIC(D)_MMSD(D) | JE (M) | BILL/01355/2024-2025 | 419/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1105 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service Connection Charges for Kharipahari PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS | DIC(D)_MMSD(D) | JE (M) | BILL/01356/2024-2025 | 420/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1106 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | New Service Connection Charges for Beniadihi PWSS | DIC(D)_MMSD(D) | JE (M) | BILL/01357/2024-2025 | 421/JMD | 22/11/2024 | 0 | WBSEDCL | 0.21 | 0 | 0
1107 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | BILL/01773/2023-2024 | 126/JMD | 29/03/2024 | 0 | SURAJ SERVICE STATION | 1.1 | 0 | 0
1108 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | BILL/01962/2023-2024 | 28/JMD | 26/04/2024 | 0 | SURAJ SERVICE STATION | 1.04 | 0 | 0
1109 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Pusda & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000057/2023-2024 | 1351/JMD | 06/06/2023 | 40 | CHAKRABORTY MINING & ENGINEERING | 21.95 | 1 | 30
1110 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Additional work for Washing and development including determination of yield of Rig Bored Tube Wells at different locations in Ergoda GP under MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000084/2024-2025 | 3490/JMD | 21/06/2024 | 120 | RSA ENTERPRISE | 6.83 | 1.37 | 25
1111 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of pneumatically air hammer & 165 mm dia Button Bit at MMSD (D) store for DTH drilling works under Midnapore Mechanical Sub-Division (D) in the district of Jhargram. | DIC(D)_MMSD(D) | JE (M) | ORD/000089/2024-2025 | 551/W/MMSD(D) | 21/06/2024 | 30 | SUDIP ENGINEERING CO. | 6.06 | 6.06 | 100
1112 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000148/2024-2025 | 3871/JMD | 22/07/2024 | 406 | RSA ENTERPRISE | 8.14 | 0 | 40
1113 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Jamirdiha & its adjacent nine (09) nos villages under Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000160/2024-2025 | 4295/JMD | 24/07/2024 | 40 | SUBHASIS ROY | 15.61 | 0 | 0
1114 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Erection & commissioning of 30 (thirty) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Ergoda G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur- II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000228/2023-2024 | 2304/JMD | 14/08/2023 | 770 | CONCORD ENGINEERING | 810.97 | 70.24 | 10
1115 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Erection & commissioning of 23 (twenty three) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Kanko G.P. in place of (Dharampur Zone-III Kanko (TSM/015873) and Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000323/2023-2024 | 3016/JMD | 20/10/2023 | 675 | MONDAL PRECISION PRIVATE LIMITED | 616.83 | 167.07 | 65
1116 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of different spare parts for LMP-500 and other departmental Rig unit at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000729/2024-2025 | 572/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.97 | 0.97 | 100
1117 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of Hydraulic house and other essential spare parts at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000730/2024-2025 | 573/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.97 | 0.97 | 100
1118 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of essential drilling tools and Mud pump spare parts for 21D/ LT-500 and KLR/DR/DTH-500 under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000731/2024-2025 | 574/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.99 | 0.99 | 100
1119 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply & delivery of Mud Rotary Drilling tools at MMSD(D) store of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000733/2024-2025 | 576/W/MMSD(D) | 04/07/2024 | 7 | B. P. TRADING CORPORATION | 0.77 | 0.77 | 100
1120 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply, delivery of batteries for Rig unit Halco/238/V-596 under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000993/2024-2025 | 705/W/MMSD(D) | 13/12/2024 | 7 | CHAKRABORTY MINING & ENGINEERING | 0.47 | 0 | 100
1121 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Kishda & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001355/2023-2024 | 2968/JMD | 12/03/2024 | 12 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 4.52 | 65
1122 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Siarkatia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001356/2023-2024 | 2969/JMD | 12/03/2024 | 12 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 4.35 | 100
1123 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Parulia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001357/2023-2024 | 2970/JMD | 12/03/2024 | 12 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 3.69 | 65
1124 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply and Delivery of Bucket Holder for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001645/2023-2024 | 119/W/MMSD(D) | 15/03/2024 | 7 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0.96 | 100
1125 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Supply and Delivery of Piston Rod for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001646/2023-2024 | 120/W/MMSD(D) | 15/03/2024 | 7 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0.96 | 100
1126 | Jhargram Mechanical Division | Midnapur Mechanical (Drill.) Sub-Division | Material Requisition To Resource Division | DIC(D)_MMSD(D) | JE (M) | RTOR000002/2023-2024 | 2868/JMD | 07/03/2024 | 0 | Resource Division | 2.16 | 0 | 0
1127 | Jhargram Mechanical Division | Gopiballavpur Sub Division | ADDITIONAL Quotation for new service connection at GOHALBURA T/W-II water supply scheme. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00174/2024-2025 | 101/JMD | 08/05/2024 | 0 | WBSEDCL | 3.32 | 0 | 0
1128 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM ( scheme code SM/17585 ) | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/01025/2024-2025 | 357/JMD | 13/09/2024 | 0 | SURAJ SERVICE STATION | 0.8 | 0 | 0
1129 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection charges. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/01328/2023-2024 | 95/JMD | 22/02/2024 | 0 | WBSEDCL | 2.86 | 0 | 0
1130 | Jhargram Mechanical Division | Gopiballavpur Sub Division | New Service connection charges. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/01329/2023-2024 | 96/JMD | 22/02/2024 | 0 | WBSEDCL | 5.85 | 0 | 0
1131 | Jhargram Mechanical Division | Midnapur Mechanical Sub Division-I | Repairing & rejuvenation of electro-mechanical accessories for Suktajuri W/S scheme Pump house no -2 in Garbeta II block under Jhargram Mechanical Division, PHE. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000808/2024-2025 | 7332/JMD | 19/11/2024 | 102 | TAPAN KUMAR SARKAR | 4.86 | 0 | 100
1132 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro mechanical accessories at newly sunk tube well no. I as part of augmentation of Gopiballavpur w/s scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000589/2022-2023 | 3322/JMD | 14/11/2022 | 120 | ORIENTAL ENGINEERING CO. | 11.03 | 10.97 | 100
1133 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery, installation, commissioning & trial run of submersible pumping machinery and other electro mechanical accessories at newly sunk tube well no. II as part of augmentation of Gopiballavpur w/s scheme of Jhargram District under Jhargram Mechanical Division, P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000590/2022-2023 | 3323/JMD | 14/11/2022 | 120 | DEBJYOTI BASU | 11.04 | 10.9 | 100
1134 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Continuation work order for Hiring of Diesel driven Commercial Covered four wheeler vehicle on daily basis along with LMV licensed driver for official purpose of Executive Engineer, Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000793/2022-2023 | 641/JMD | 22/03/2023 | 366 | SUJOY RANJAN BHOWMICK | 1.74 | 0.87 | 100
1135 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Providing solarization of WBSEDCL energised pumping installation at Gopiballavpur w/s schemes under JJM programme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/001369/2023-2024 | 2986/JMD | 13/03/2024 | 30 | SAMARPITA ENGINEERING | 6.26 | 0 | 0
1136 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-II of Gopiballavpur w/s scheme in the dist. of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/001370/2023-2024 | 2987/JMD | 13/03/2024 | 30 | SOUMEN ELECTRIC | 8.81 | 8.51 | 100
1137 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Supply, delivery & installation of various electro-mechanical accessories for repairing & rejuvenation of pump house no.-I of Gopiballavpur w/s scheme in the dist. of Jhargram under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/001376/2023-2024 | 3058/JMD | 14/03/2024 | 30 | S.S. GHORAI | 8.81 | 8.41 | 100
1138 | Jhargram Mechanical Division | Gopiballavpur Sub Division | Payment for new service connection of WBSEDCL. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | VCH/000847/2022-2023 | 21/JMD/PFMS/SEP | 29/09/2022 | 0 | WBSEDCL | 1.63 | 0 | 0
1139 | Jhargram Mechanical Division | Midnapur Sadar Sub-Division | NEW SERVICE CONNECTION CHARGES AT NERASOLE-II WATER SUPPLY SCHEME | AE Sadar Sub-division,Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00649/2024-2025 | 262/JMD | 23/07/2024 | 0 | WBSEDCL | 5.29 | 0 | 0
Total | [10 empty] | 14256.67 | 2909.69