## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Birsing mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 11. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000050/2021-2022 | 1221/SWSD | 01/11/2021 | 35 | M/S MATRI CONSTRUCTION | 31.13 | 0 | 100
2 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Huchaimallick mouza and remaining part of Fakna mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 12 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000051/2021-2022 | 1222/SWSD | 01/11/2021 | 20 | PRADIP GUHA | 16.83 | 0 | 68
3 | Siliguri W/S Division | Siliguri W/S Division | Extension of distribution pipeline within the command area for providing 100% Functional House Hold Tap Connections under Jal Jeevan Mission & Jal Swapno Programme of Mangalsing PWWS at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 06 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000034/2021-2022 | 987/SWSD | 06/09/2021 | 25 | NARAYAN CH GHOSH | 4.3 | 0 | 100
4 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Paschim Madati twenty six point sixty three percent Habitation Alim Ganj Chowdhry Gach and Gava Ganga of Purba Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000065/2020-2021 | 1079/SWSD | 18/12/2020 | 40 | SHRI ANUP BASU | 35.92 | 0 | 65
5 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF UTTAR RAMDHAN PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000053/2023-2024 | 246/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 100
6 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area village Madan habitation Madan and village Uttar Ramdhan habitation Goursing and Wairish of Uttar Ramdhan and adjoining Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000054/2020-2021 | 1010/SWSD | 11/12/2020 | 35 | M/S DEBRAJ ENTERPRISE | 37.87 | 21.13 | 100
7 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Gandagal village habitation Dil saram Dulal Gandogle and village Jibansing habitation Babuchhan Dilsaram and Jiban sing of Uttar Ramdhan and adjoining mouzas Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000055/2020-2021 | 1011/SWSD | 11/12/2020 | 40 | M/S DEBRAJ ENTERPRISE | 37.92 | 0 | 100
8 | Siliguri W/S Division | Siliguri W/S Division | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2022 TO 31.08.2022. (FOR EXECUIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) (i.e. SIX MONTHS) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000162/2021-2022 | 2301/SWSD | 28/02/2022 | 184 | SUBIR CH. CHOWDHURY | 0.88 | 0 | 100
9 | Siliguri W/S Division | Siliguri W/S Division | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 100
10 | Siliguri W/S Division | Siliguri Sub-Division | Continuation order for Hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of The Chief Engineer (Civil), Northern Zone, P.H.E. Dte. Vivekananda Bhawan (2nd floor), Hill Cart Road, Siliguri for the period from 01.08.2023 to 31.12.2023 (for Chief Engineer (Civil), Northern Zone, P.H.E. Dte.) i.e. 05 (Five) months. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000150/2023-2024 | 1051/SWSD | 28/07/2023 | 153 | PINKI DAM | 0.74 | 0 | 100
11 | Siliguri W/S Division | Siliguri Sub-Division | HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 28.02.2023 (FOR EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. SIX MONTHS. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000195/2022-2023 | 1227/SWSD | 31/08/2022 | 6 | SUBIR CH. CHOWDHURY | 0.88 | 0 | 100
12 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Fulbar Habitation Fulbar and village Bhalamanshi Habitation Charge more of Bhalamanshi Piped Water Supply Scheme and Allied works at Phansidewa block under Siliguri Sub Division PHE Dte (3rd CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000009/2021-2022 | 695/SWSD | 02/08/2021 | 45 | SHRI ANUP BASU | 36.74 | 0 | 30
13 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Churaman Habitation Churaman, village Thuna Habitation Thuna village Thuna Chhat Habitation Thunar Chhat and village Baramala Habitation Baramala of Bhalamanshi Piped Water Supply Scheme and Allied works at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000076/2020-2021 | 1090/SWSD | 18/12/2020 | 45 | SHRI ANUP BASU | 37.37 | 0 | 100
14 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum work order for installation of the Iron removal filtration plant including platform and drain with necessary connection and blower room 01 No. at Bhalamanshi Piped water supply Scheme H/W Site within Phansidewa Block under Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000189/2024-2025 | 3155/SWSD | 25/11/2024 | 30 | PALLAB BHOWAL | 26.07 | 0 | 0
15 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Danra Goan, Soom 1st Division, Gram Panchyat -Soom Singtam, Block Bijanbari -PullBazar. TSM No. 009476 SM Code-SM/08937 |  | Sub-Assistant Engineer | ORD/000060/2022-2023 | 556/NKWSMD | 26/05/2022 | 60 | NAVRATNA CONSTRUCTION CO | 16.53 | 0 | 100
16 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000124/2022-2023 | 1900/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.36 | 0 | 0
17 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000184/2022-2023 | 2579/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.36 | 0 | 0
18 | Siliguri W/S Division | Siliguri Sub-Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
19 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 200 cu.m. capacity RCC Elevated Reservoir, 20 mtrs Staging height at the head works site including rising mains and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of Pauchakelguri and adjoining mouzas water supply scheme within Matigara block under Siliguri Sub Division, PHE Dte. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000007/2022-2023 | 176/SWSD | 22/04/2022 | 180 | S.K. BANIK | 126 | 0 | 35
20 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House (5.4 X 3.60) size with (1.35 X 2.10 M) size toilet, plinth protection etc. and boundary wall at Khopalasi of PAUCHAKELGURI Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000038/2023-2024 | 642/SWSD | 15/06/2023 | 45 | U.K CONSTRUCTIONS | 12.89 | 0 | 50
21 | Siliguri W/S Division | Siliguri Sub-Division | Laying Distribution System (Part-E) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-E) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 09. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000063/2022-2023 | 868/SWSD | 21/07/2022 | 985 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 81.94 | 0 | 70
22 | Siliguri W/S Division | Siliguri Sub-Division | Soil Investigation of Pauchkelguri PWSS for Construction of 200 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000091/2022-2023 | 388/SSD | 20/07/2022 | 20 | R.B.TESTING | 1.02 | 0 | 100
23 | Siliguri W/S Division | Siliguri Sub-Division | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-B) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 08. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000137/2021-2022 | 2434//SWSD | 21/03/2022 | 60 | S.K. BANIK | 68.28 | 0 | 65
24 | Siliguri W/S Division | Siliguri Sub-Division | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-C) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 09. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000138/2021-2022 | 2435/SWSD | 21/03/2022 | 50 | S.K. BANIK | 53.92 | 0 | 25
25 | Siliguri W/S Division | Siliguri Sub-Division | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connecetion (FHTC) under Jal Swapno and Jal Jeevan Mission at Distribution Pipeline (Part-D) of Pauchakelguri and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 10. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000139/2021-2022 | 2436/SWSD | 21/03/2022 | 1561 | U.K CONSTRUCTIONS | 73.9 | 0 | 65
26 | Siliguri W/S Division | Siliguri Sub-Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000166/2022-2023 | 1326/SWSD | 14/09/2022 | 45 | M/S NIRANJAN SARKAR | 46.36 | 0 | 100
27 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. and Boundary Wall at Jhaguri of Pauchakelguri Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000175/2023-2024 | 1203/SWSD | 10/08/2023 | 45 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 13.45 | 0 | 100
28 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum work order "Construction of Pump House (3 NOS) (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. Rising Main and Boundary Wall at Pauchakelguri ,Khopalasi and Jhauguri of Pauchakelguri Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling". | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000321/2023-2024 | 604/SWSD | 06/03/2024 | 280 | M/S JAYDEV JHA | 28.86 | 0 | 60
29 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000017/2021-2022 | 2172/SWSD | 11/02/2022 | 0 | Resource Division | 39.61 | 0 | 0
30 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000018/2022-2023 | 1448/SWSD | 29/09/2022 | 0 | Resource Division | 9.74 | 0 | 0
31 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000304/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 9.73 | 0 | 0
32 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000892/2021-2022 | BP-2021-22-110 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 28.3 | 0 | 0
33 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PAUCHAKULGURI W/S Scheme, T/W No. II under MATIGARA CCC [APPLICATION NO. 4003058421 ; Reference ID : 402932706] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00002/2023-2024 | BP/23-24/05 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0
34 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PAUCHAKULGURI W/S Scheme, T/W No. I under MATIGARA CCC [APPLICATION NO. 4003058425 ; Reference ID : 402932707] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00003/2023-2024 | BP/23-24/05 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0
35 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PACHKELGURI, T/W I, under MATIGARA CCC, [APPLICATION NO. 4003199222, Reference ID : 403050473] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00582/2023-2024 | BP/23-24/67 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4 | 0 | 0
36 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for PACHKELGURI, T/W No. I, under MATIGARA CCC [APPLICATION NO. 100000084014 , Reference ID : 860275184] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01785/2023-2024 | BP/23-24/286 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 27.56 | 0 | 0
37 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PAUCHAKULGURI PIPED WATER SUPPLY SCHEME ,TW No. I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000054/2023-2024 | 547/NMD | 15/05/2023 | 688 | ALPHA ENTERPRISE | 23.49 | 0 | 90
38 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PAUCHAKULGURI PWSS at TW NO II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000246/2024-2025 | 1524/NMD | 03/09/2024 | 408 | ALPHA ENTERPRISE | 11.91 | 0 | 75
39 | Siliguri W/S Division | Siliguri W/S Division | Hiring of 1(one) no. Mariti van (non A/C) for the office of the Superintending Engineer, NBC-I , PHE Dte. period from Septenber,October & November 2022 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00041/2022-2023 | BP-2022-23-114 | 09/02/2023 | 0 | RUPA PRASAD | 0.8 | 0 | 0
40 | Siliguri W/S Division | Siliguri W/S Division | Hiring 1 no. diesel consumed luxury vehicle on monthly basis preferably Maxi Cab (with A/C) for Deputy Superintending Engineer, NBC-I, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00068/2022-2023 | BP-2022-23-132 | 20/02/2023 | 0 | OM TRAVELS | 1.95 | 0 | 0
41 | Siliguri W/S Division | Siliguri W/S Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
42 | Siliguri W/S Division | Siliguri W/S Division | Repair and renovation of the Head Work site Pump House (3.65 m X 2.45 m) size and boundary wall at Head work site allied with additional works like shifting of Rising Main and drain under Augmentation of SALBARI W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000002/2023-2024 | 53/SWSD | 10/04/2023 | 30 | SUBIR CH. CHOWDHURY | 9.84 | 0 | 75
43 | Siliguri W/S Division | Siliguri W/S Division | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-B) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000092/2021-2022 | 2077/SWSD | 03/02/2022 | 60 | SUDIP BASAK | 66.67 | 0 | 52
44 | Siliguri W/S Division | Siliguri W/S Division | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-C) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000093/2021-2022 | 2078/SWSD | 03/02/2022 | 60 | M/S G.C. CONSTRUCTION & CO. | 65.37 | 0 | 80
45 | Siliguri W/S Division | Siliguri W/S Division | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-D) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000094/2021-2022 | 2079/SWSD | 03/02/2022 | 40 | BUDDHADEV NAG | 30.7 | 0 | 60
46 | Siliguri W/S Division | Siliguri W/S Division | Laying Distribution System (Part-E) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-E) of Salbarir Chhat Pratham khanda , Panchanai, Nunu Bairagi, Mahatram, Udaysing Mouza's (Partially) of Salbari and Adjoining Moujas Water Supply Scheme under Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000095/2021-2022 | 2080/SWSD | 03/02/2022 | 75 | HIMADRI DAM & CO. | 70.68 | 0 | 50
47 | Siliguri W/S Division | Siliguri W/S Division | Construction of 300 cu.m. capacity RCC Elevated Reservoir, 20 mtrs. staging height at the head works site including rising main and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of SALBARI CHHAT, PRATHAM KHANDA, PANCHANAI, NUNU BAIRAGI, MAHATRAM, UDAYSING MOUZA'S (Partially) of SALBARI and adjoining mouza's Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000105/2021-2022 | 2202/SWSD | 17/02/2022 | 180 | SUBIR CH. CHOWDHURY | 125.67 | 0 | 100
48 | Siliguri W/S Division | Siliguri W/S Division | Soil Investigation of Salbari PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000108/2022-2023 | 392/SSD | 20/07/2022 | 20 | SUBIR CH. CHOWDHURY | 1.03 | 0 | 100
49 | Siliguri W/S Division | Siliguri W/S Division | Continuation order for hiring of 1 (one) No. Maruti Van (Non A/C) for the Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. period from 01.04.2022 to 31.03.2023 i.e. 12 (twelve) months. VEHICLE NO. WB 73B/1911. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000149/2021-2022 | 2534/SWSD | 29/03/2022 | 12 | RUPA PRASAD | 1.48 | 0 | 100
50 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000165/2022-2023 | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 100
51 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000170/2022-2023 | 1330/SWSD | 14/09/2022 | 25 | M/S K. R. S. CONSTRUCTION | 15.45 | 0 | 0
52 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for construction of 4th Tubewell Pump House (3.60 m X 2.40 m) allied with rising main and boundary wall under Augmentation of Salbari W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000181/2023-2024 | 1793/SWSD | 29/09/2023 | 352 | M/S UNIQUE13 | 14.26 | 0 | 70
53 | Siliguri W/S Division | Siliguri W/S Division | Acceptance Cum Work Order for Repair and Renovation of the 2nd & 3rd Pump House (3.65 m X 2.45 m) site allied with additional works under Augmentation of Salbari W/S Scheme under Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000220/2023-2024 | 2036/SWSD | 06/11/2023 | 473 | SEBU CHAKRABORTY | 6.38 | 0 | 90
54 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000016/2022-2023 | 1446/SWSD | 29/09/2022 | 0 | Resource Division | 9.7 | 0 | 0
55 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000021/2021-2022 | 2176/SWSD | 11/02/2022 | 0 | Resource Division | 73.29 | 0 | 0
56 | Siliguri W/S Division | Siliguri W/S Division | SHIFTING OF EXISTING TRANSFORMER ALONG WITH 11 KV HOTH LINE. ( REF ID: 860242115 AND APPLICATION ID : 100000052425 ) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | VCH/000185/2022-2023 |  | 22/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.85 | 0 | 0
57 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | VCH/000302/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 12.12 | 0 | 0
58 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | VCH/000894/2021-2022 | BP-2021-22-112 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 62.77 | 0 | 0
59 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for SALBARI, T.W. No. IV under MATIGARA CCC [APPLICATION NO. 4003194765 ; Reference ID : 403046874] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/02009/2023-2024 | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.21 | 0 | 0
60 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SALBARI PIPED WATER SUPPLY SCHEME , TW No III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000612/2023-2024 | 1395/NMD | 09/08/2023 | 512 | M/S SAJAHAN CHOWDHURY | 12.99 | 0 | 100
61 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan M is si on.an d Jal Swapno Programme for Pipe Water Supply Sche me Scheme for 5th mile upper Kotwali Gaon. from Boka Jhora Source under Jorebanglow- Sukhiapokhri Block Darj eeling" |  | Sub-Assistant Engineer | VCH/000055/2022-2023 | BP-2022-23-41 | 06/05/2022 | 0 | KAMAKHYA ENTERPRISES | 3.63 | 0 | 0
62 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connect ion under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Sch eme for Pokhriabong Bazar from Nursery Fatak Source under Jorebanglow- Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000063/2022-2023 | BP-2022-23-54 | 20/05/2022 | 0 | RISHI KESH THAKURI | 7.36 | 0 | 0
63 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Jai Jeevan Mi ssion and Jal Swapno Programme for Pipe Water Su pply Scheme for Minzu Pussimbing from Bethany Khop Source under Jorebanglow Sukhiapokhri Block Darjeeling ." |  | Sub-Assistant Engineer | VCH/000064/2022-2023 | BP-2022-23-53 | 20/05/2022 | 0 | KESHAR CHETTRI | 4.91 | 0 | 0
64 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Pipe Water Supply Scheme for Chotta Pubong ward No 3 & 4 from Singadevi Khela Source Under Jorebanglow - Su khiapokhri Block Dar je elin g under Darje eling Division PHED, GTA." |  | Sub-Assistant Engineer | VCH/000068/2022-2023 | BP-2022-23-49 | 20/05/2022 | 0 | KIRAN NIROLA | 3.11 | 0 | 0
65 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Conne ct ion under Jal Jee van Missi on and Jal Swapno Programme for Prpe Water Supply Sch eme for Tar zum under Jorebanglow Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000112/2022-2023 | BP-2022-23-90 | 14/07/2022 | 0 | SONAM TAMANG | 4.1 | 0 | 0
66 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Funct ional House hold Tap Connection under Jal Jeevan Mission an d Jal Swapno Programme for Pipe Water Supply Sc heme for Mazidhura Lower Parment Busty from Bhir Khola Sou rc e under Jorebanglow- Sukhiapokhri Block Darjeelin g under Darjeeling Division PH ED, GTA." |  | Sub-Assistant Engineer | VCH/000156/2022-2023 | BP-2022-23-111 | 12/08/2022 | 0 | KAMAKHYA ENTERPRISES | 3.68 | 0 | 0
67 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JAL Jeeva n Mission and Jal Swapno Programme for Pipe Water Su pply Scheme for Chamong Maleteneya And Pari Gaon from Paa Khola and Kera Bari Source under Jorebangiow Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000161/2022-2023 | BP-2022-23-105 | 08/08/2022 | 0 | RISHI KESH THAKURI | 3.54 | 0 | 0
68 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functionai Household Tap Connection under Jal Jeevan Mission and Jal Swapno Pro grarnme for Pipe Water Supply Sch eme for Pokhriabong Busty No 4. from Ghimiray Jhora an Thulung Pakha Source under Jorebanglow - Sukhiapokhi" |  | Sub-Assistant Engineer | VCH/000283/2022-2023 | BP-2022-23-170 | 20/10/2022 | 0 | RISHI KESH THAKURI | 2.56 | 0 | 0
69 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jee van Mission and Jal Swapno Pro gramme for Pipe Water Supply Scheme for Lepcha Tribal Gaon Pokhriabong Busty from Gardinay Sim Source under Jorebanglow- Sukhiapokhri Block Darjeeling" |  | Sub-Assistant Engineer | VCH/000284/2022-2023 | BP-2022-23-171 | 20/10/2022 | 0 | RISHI KESH THAKURI | 3.13 | 0 | 0
70 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000001/2020-2021 | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0
71 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Providing Fun ctional Household Tap Connection under Jal .Jeevan Mission and Jal Swapno Programme for Pipe Water Supp ly Scheme for Bhutia Gaon Plundung from Khodaydhura Khola Source unde r Jorebanglow- Sukhia.pokhri Block Darj eeling |  | Sub-Assistant Engineer | ORD/000002/2020-2021 | 117/EE/DD/PHED | 10/02/2021 | 120 | ROMAN SHERPA | 3.69 | 0 | 0
72 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000003/2020-2021 | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0
73 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal jeevan Mission and Jal Swapno Programrne for Pipe Water Supply Scheme for upper Sirubari and Beech Gaon. Sungma T .E from Bara ReyangKhola Source under Jorebanglow Sukhiapokhri Block Darjeeling |  | Sub-Assistant Engineer | ORD/000004/2020-2021 | 114/EE/DD/PHED | 10/02/2021 | 120 | SONAM TAMANG | 11.12 | 0 | 0
74 | Siliguri W/S Division | Siliguri W/S Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
75 | Siliguri W/S Division | Siliguri W/S Division | Hiring of vehicle for the office of the Siliguri Sub Division PHE Dte. Assistant Engineer | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00199/2023-2024 | BP-2023-24-120 | 19/10/2023 | 0 | SUDIP BASAK | 0.74 | 0 | 0
76 | Siliguri W/S Division | Siliguri W/S Division | Construction of Pump House (5.40 m X 3.60 m) size with Sanitary & Plumbing arrangement as per Model Approved Drawing at Tubewell site for different Water Supply Scheme under Siliguri W/S Division, P. H. Engineering Dte. (Name of Scheme : Kharibari Zone-I & II PWSS (Two Nos.) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000016/2023-2024 | 334/SWSD | 08/05/2023 | 45 | SWAPAN CHANDRA DAS | 11.67 | 0 | 100
77 | Siliguri W/S Division | Siliguri W/S Division | Construction of 450 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site including rising main and distribution system (Paret-A) allied with providing functional household connection (FHTC) at distribution pipeline of Kharibari Zone-I of the Kharibari Piped Water Supply Scheme and allied works Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 14. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000067/2022-2023 | 872/SWSD | 21/07/2022 | 1160 | PALLAB BHOWAL | 232.84 | 0 | 20
78 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system (Part-B) and allied works with providing functional household connection (FHTC) at distribution pipeline of Kharibari Zone-I of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 15. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000068/2022-2023 | 873/SWSD | 21/07/2022 | 85 | PALLAB BHOWAL | 91 | 0 | 73
79 | Siliguri W/S Division | Siliguri W/S Division | Construction of 300 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site including distribution system with Providing Functional Household Connection (FHTC) and allied works at distribution pipe line of Kharibari Zone -II of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 01. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000088/2022-2023 | 911/SWSD | 25/07/2022 | 891 | ARUN KUMAR SHRIVASTAVA | 240.16 | 0 | 2
80 | Siliguri W/S Division | Siliguri W/S Division | Soil Investigation of Kharibari Zone -II PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000090/2022-2023 | 387/SSD | 20/07/2022 | 20 | G. TECH INDIA | 1.03 | 0 | 100
81 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Kharibari W/S Scheme at Kharibari block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000108/2021-2022 | 818/SWSD | 13/08/2021 | 21 | ENVIROTECH SOLUTIONS | 3.08 | 0 | 100
82 | Siliguri W/S Division | Siliguri W/S Division | Sinking of Tubewell By Reverse Rotary Method at 2nd site(KESORDOBA) in replacsmenil of damaged Tube well,KHARIBARI PWSS (ZONE-II) Block: Khoribari, Dist: Darjeeling Under Siliguri W/S Division P.H.E.Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000139/2024-2025 | 2533/swsd | 18/09/2024 | 151 | NARENDRA KUMAR | 8.71 | 0 | 85
83 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000165/2022-2023 | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 100
84 | Siliguri W/S Division | Siliguri W/S Division | Part work order for construction of blower room (3.60 m X 3.00 m) size as per Model Approved drawings at tubewell site including IEP and boundary walls for Kharibari Zone I & II water supply scheme under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000168/2024-2025 | 2931/SWSD | 30/10/2024 | 45 | ARUN KUMAR SHRIVASTAVA | 49.08 | 0 | 0
85 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000018/2021-2022 | 2175/SWSD | 11/02/2022 | 0 | Resource Division | 51.57 | 0 | 0
86 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000021/2022-2023 | 1451/SWSD | 29/09/2022 | 0 | Resource Division | 26.79 | 0 | 0
87 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000299/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 19.19 | 0 | 0
88 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000887/2021-2022 | BP-2021-22-105 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 49.61 | 0 | 0
89 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for GURUDAYALJOTE W/S Scheme, T/W No. I, Zone-I under KHARIBARI CCC, [APPLICATION NO. 4003055480, Reference ID : 402933291] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00046/2022-2023 | BP/22-23/122 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.75 | 0 | 0
90 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for PWD MORE W/S Scheme, T/W No. I, Zone-II under KHARIBARI CCC, [APPLICATION NO. 4003055466, Reference ID : 402933292] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00047/2022-2023 | BP/22-23/122 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.75 | 0 | 0
91 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KHARIBARI ZONE - I (TW No. I) and ZONE - II (TW No. I) PIPED WATER SUPPLY SCHEME , in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000039/2023-2024 | 493/NMD | 28/04/2023 | 30 | SARKAR ELECTRIC | 22.33 | 0 | 80
92 | Neorakhola W/S & Mtc.Div. |  | Providing Functional House hold Tap Connection under Jal Jeev an Mission and Jal Swapna Programme for Piped water Supply Scheme for Longview Tarai 34 & satt Ghurnt, St Mary's GP-Ill under Kurseong Sub-Division PHED. GTA. |  |  | VCH/000020/2022-2023 | BP-2022-23-19 | 20/04/2022 | 0 | SURAJ LAMA | 6.2 | 0 | 0
93 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000144/2022-2023 |  | 26/08/2022 | 0 | SHREE VAISHNO ENTERPRISES | 14.05 | 0 | 0
94 | Neorakhola W/S & Mtc.Div. |  | Providing Functional HouseholdTap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for for Hilay Jhora and Manju ak number Dara under Kurseong Sub-Division PHED, GTA |  |  | VCH/000154/2022-2023 | BP-2022-23-112 | 12/08/2022 | 0 | CHARDHAM CONSTRUCTION | 3.7 | 0 | 0
95 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Khoprail sakha under Kurseong Sub-Division PHED. GTA |  |  | VCH/000155/2022-2023 | BP-2022-23-113 | 12/08/2022 | 0 | CHARDHAM CONSTRUCTION | 3.83 | 0 | 0
96 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Conne ction under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Mandir Busty, Giddhapa har underKurseong Sub-Division PHED, GTA |  |  | VCH/000159/2022-2023 | BP-2022-23-122 | 23/08/2022 | 0 | NAVRATNA CONSTRUCTION CO | 6.08 | 0 | 0
97 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
98 | Siliguri W/S Division | Siliguri Sub-Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
99 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 350 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height including laying distribution system, 400 Nos. FHTC (Part-A) for Chamta and adjoining mouza¿s Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000014/2022-2023 | 274/SWSD | 06/05/2022 | 180 | ANUP BASU | 170.09 | 0 | 0
100 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system of pipeline (Part-D) at Chamta & adjoining mouza¿s Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-D). Sl. No. 13. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000066/2022-2023 | 871/SWSD | 21/07/2022 | 80 | NARENDRA KUMAR | 89.17 | 0 | 80
101 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system of pipeline (Part-B) at Chamta and adjoining mouzas Water Supply Scheme withinMatigara block under Siliguri Sub Division, P.H.E. Dte. (Part-B). (2ND CALL). Sl. No. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000069/2022-2023 | 874/SWSD | 21/07/2022 | 85 | DEBASHIS SINHA | 109.33 | 0 | 75
102 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system of pipeline (Part-C) at Chamta and adjoining mouzas Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-C). (2ND CALL). Sl. No. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000070/2022-2023 | 875/SWSD | 21/07/2022 | 75 | M/S UTPAL CHAKRABORTY & CO. | 78.93 | 0 | 70
103 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system of pipeline (Part-E) at Chamta and adjoining mouzas Water Supply Scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-E). (2ND CALL) Sl. No. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000071/2022-2023 | 876/SWSD | 21/07/2022 | 1043 | SUBIR CH. CHOWDHURY | 104.02 | 0 | 92
104 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system of pipeline at Jhauguri at Chamta and adjoining mouzas Water Supply Scheme under Matigara block under Siliguri Sub Division, P.H.E Dte.(Part E). Sl. No. 17. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000087/2022-2023 | 860/SWSD | 21/07/2022 | 75 | BISWADEEP CONSTRUCTION | 71.84 | 0 | 92
105 | Siliguri W/S Division | Siliguri Sub-Division | Soil Investigation of Champta PWSS for Construction of 350 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000107/2022-2023 | 391/SSD | 20/07/2022 | 20 | G. MITRA & ASSOCIATES | 1.03 | 0 | 90
106 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Chamta W/S Scheme at Matigara block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 04. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000111/2021-2022 | 831/SWSD | 13/08/2021 | 21 | ENVIROTECH SOLUTIONS | 1.97 | 0 | 100
107 | Siliguri W/S Division | Siliguri Sub-Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000166/2022-2023 | 1326/SWSD | 14/09/2022 | 45 | M/S NIRANJAN SARKAR | 46.36 | 0 | 100
108 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000019/2021-2022 | 2177/SWSD | 11/02/2022 | 0 | Resource Division | 43.55 | 0 | 0
109 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000024/2022-2023 | 1454/SWSD | 29/09/2022 | 0 | Resource Division | 14.43 | 0 | 0
110 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | VCH/000297/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 2.52 | 0 | 0
111 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | VCH/000895/2021-2022 | BP-2021-22-113 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 32.46 | 0 | 0
112 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for CHAMTA W/S Scheme, T/W No. I under MATIGARA CCC, [APPLICATION NO. 4003058415, Reference ID : 402932670] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00042/2022-2023 | BP/22-23/124 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0
113 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for CHAMTA W/S Scheme, T/W No. II under MATIGARA CCC, [APPLICATION NO. 4003049182, Reference ID : 402926291] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00043/2022-2023 | BP/22-23/124 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0
114 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMTA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000795/2022-2023 | 109/NMD | 03/02/2023 | 30 | MAA ENTERPRISES | 10.96 | 0 | 100
115 | Siliguri W/S Division | Siliguri W/S Division | Hiring 1 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (WITH AIR CONDITION ) fore office of the Executive Engineer, Siliguri W/S division PHE Dte. for the period from 01.09.2021 to 28.02.2022 | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00051/2022-2023 | BP-2022-23-119 | 20/02/2023 | 0 | SUBIR CH. CHOWDHURY | 1.5 | 0 | 0
116 | Siliguri W/S Division | Siliguri W/S Division | Resources payment for Different Water Supply Scheme | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
117 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Bairatisal W/S Scheme at Matigara block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 06. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000113/2021-2022 | 833/SWSD | 13/08/2021 | 25 | ENVIROTECH SOLUTIONS | 4.85 | 0 | 100
118 | Siliguri W/S Division | Siliguri W/S Division | Construction of 550 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, laying Rising Main, laying distribution pipeline with Functional household tap connection (FHTC), construction of 2 (two) nos. Pump House (5.40 X 3.60 m), Iron elimination plant (IEP) with blower room, sinking of 2 (two) nos tube well (ODEX-165 method) and boundary wall for BAIRATISAL PWSS (Zone-II), Block Matigara Dist. Darjeeling under Siliguri W/S Division, PHE | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000118/2023-2024 | 1204/SWSD | 11/08/2023 | 767 | BRM DEVELOPERS | 527.89 | 0 | 20
119 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000168/2022-2023 | 1328/SWSD | 14/09/2022 | 25 | RANJEET SINGH BENIWAL | 15.46 | 0 | 88
120 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000170/2022-2023 | 1330/SWSD | 14/09/2022 | 25 | M/S K. R. S. CONSTRUCTION | 15.45 | 0 | 0
121 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000003/2022-2023 | 130/SWSD | 13/04/2022 | 0 | Resource Division | 14.63 | 0 | 0
122 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000015/2021-2022 | 2173/SWSD | 11/02/2022 | 0 | Resource Division | 34.95 | 0 | 0
123 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000023/2022-2023 | 1453/SWSD | 29/09/2022 | 0 | Resource Division | 27.72 | 0 | 0
124 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | VCH/000296/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 9.3 | 0 | 0
125 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | VCH/000893/2021-2022 | BP-2021-22-111 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 38.2 | 0 | 0
126 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for AUG OF BAIRATISAL, T/W No. I, ZONE-II, under SHEVMANDIR CCC [APPLICATION NO. 4003312877 , Reference ID : 403140528] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01916/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.29 | 0 | 0
127 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for AUG BAIRATISAL,T/W No. II,ZONE-II under SHIVMANDIR CCC [APPLICATION NO. 4003312875 , Reference ID : 403140527] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01917/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.31 | 0 | 0
128 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - II (TW No. I and II) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000797/2022-2023 | 111/NMD | 03/02/2023 | 910 | CHOWDHURY AND BASU ENTERPRISE | 20.36 | 0 | 100
129 | Siliguri W/S Division | Siliguri Sub-Division | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of July (16/07/24 to 26/07/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00354/2024-2025 | BP-2024-25-129 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.32 | 0 | 0
130 | Siliguri W/S Division | Siliguri Sub-Division | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of August(20/08/24 to 29/08/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00357/2024-2025 | BP-2024-25-128 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.35 | 0 | 0
131 | Siliguri W/S Division | Siliguri Sub-Division | Soil Investigation of Kharibari Zone -I PWSS for Construction of 450 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000089/2022-2023 | 386/SSD | 20/07/2022 | 20 | GLORY ENGINEERS SYNDICATE | 1.03 | 0 | 100
132 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 02 (Two) nos. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2023 to 31.07.2023. |  | Sub-Assistant Engineer | ORD/000068/2023-2024 | 377/NKWSMD | 31/05/2023 | 61 | THE ELECTRIC SPHERE | 0.79 | 0 | 100
133 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 01 (one) no. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Superintending Engineer, GTA, P.H.E. Dte from 01.06.2023 to 31.07.2023. |  | Sub-Assistant Engineer | ORD/000069/2023-2024 | 378/NKWSMD | 31/05/2023 | 61 | THE ELECTRIC SPHERE | 0.39 | 0 | 100
134 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR KOLBONG UNDER JAL SWAPNO PROGRAMME. (BLOCK-DARJEELING-PULBAZAR) |  | Sub-Assistant Engineer | ORD/000091/2022-2023 | 610/NKWSMD | 26/05/2022 | 180 | HEMRAJ NIROLA | 80.89 | 0 | 0
135 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 |  | Sub-Assistant Engineer | ORD/000150/2022-2023 | 680/NKWSMD | 31/05/2022 | 12 | THE ELECTRIC SPHERE | 4.98 | 0 | 95
136 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1(One) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the S.E. GTA, P.H.E. Dte from 01.06.2022 to 31.05.2023 |  | Sub-Assistant Engineer | ORD/000152/2022-2023 | 681/NKWSMD | 31/05/2022 | 365 | THE ELECTRIC SPHERE | 2.47 | 0 | 45
137 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/09/2023. |  | Sub-Assistant Engineer | ORD/000205/2023-2024 | 848/NKWSMD | 28/07/2023 | 62 | THE ELECTRIC SPHERE | 0.93 | 0 | 100
138 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 |  | Sub-Assistant Engineer | ORD/000207/2023-2024 | 851/NKWSMD | 28/07/2023 | 123 | THE ELECTRIC SPHERE | 0.87 | 0 | 90
139 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000044/2022-2023 | 1271/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.66 | 0 | 0
140 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Teesta Valley, GP - Rungli, Block - Rungli Rungliot. |  | Sub-Assistant Engineer | ORD/000176/2022-2023 | 952/NKWSMD | 12/07/2022 | 658 | NAVRATNA CONSTRUCTION CO | 167.77 | 0 | 92
141 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000133/2022-2023 | 1909/NKWSMD | 15/12/2022 | 0 | Resource Division | 8.41 | 0 | 0
142 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000197/2022-2023 | 2593/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.41 | 0 | 0
143 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR ROLAK KHASMAHAL & LONKU KHASMAHAL UNDER KURSEONG BLOCK DISTRICT-DARJEELING UNDER KURSEONG DIVISION. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000041/2025-2026 | 656/NKWSMD | 05/05/2025 | 180 | DAJUBHAI CONSTRUCTION | 83.76 | 0 | 0
144 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Rolak Khasmahal & Lonku Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kurseong Block within Darjeeling District. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000314/2022-2023 | 2494/NKWSMD | 09/02/2023 | 1405 | VINAYAK CONSTRUCTION | 1016.14 | 0 | 100
145 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000151/2022-2023 | 2071/NKWSMD | 05/01/2023 | 0 | Resource Division | 8.37 | 0 | 0
146 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000208/2022-2023 | 2556/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.37 | 0 | 0
147 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000238/2022-2023 | 2723/NKWSMD | 03/03/2023 | 0 | Resource Division | 8.37 | 0 | 0
148 | Siliguri W/S Division | Siliguri W/S Division | Continuation order for hiring of 1 (one) no. Maxi Cab with engine capacity less than or Equal to 2000 CC (with Air Condition) for the office of the Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022 (for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte.) | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00052/2022-2023 | BP-2022-23-118 | 20/02/2023 | 0 | HIMADRI DAM | 1.45 | 0 | 0
149 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Uttar Ramdhan Zone I of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 13 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000083/2022-2023 | 856/SWSD | 21/07/2022 | 100 | PALLAB BHOWAL | 162.34 | 0 | 30
150 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Uttar Ramdhan Zone II of the Kharibari Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 14. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000084/2022-2023 | 857/SWSD | 21/07/2022 | 30 | TUSHAR KANTI SEAL | 29.64 | 0 | 90
151 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000165/2022-2023 | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 100
152 | Siliguri W/S Division | Siliguri W/S Division | Continuation of hiring of 1 (one) no. diesel consumed on monthly basis preferably Maxi Cab (With A/C) for O/O the assistant Engineer Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000813/2020-2021 | 308/SSD | 13/08/2020 | 0 | SUDIP BASAK | 0.88 | 0 | 0
153 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000037/2022-2023 | 1467/SWSD | 29/09/2022 | 0 | Resource Division | 20.24 | 0 | 0
154 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000044/2022-2023 | 2024/SWSD | 16/12/2022 | 0 | Resource Division | 17.86 | 0 | 0
155 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for CHOTO DILSARAMJOTE W/S Scheme, T/W No. III, Zone-II under UTTAR RAMDHAN CCC, [APPLICATION NO. 4003055461, Reference ID : 402933290] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00048/2022-2023 | BP/22-23/137 | 01/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.54 | 0 | 0
156 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for UTTAR RAMDHAN, ZONE-I,T/W -I, under NAXALBARI CCC, [APPLICATION NO. 4003079475, Reference ID : 402958536] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00583/2022-2023 | BP/22-23/137 | 01/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0
157 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF UTTAR RAMDHAN WATER SUPPLY SCHEME, (ZONE-I) TW No. I AND II , (ZONE-II) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000792/2022-2023 | 106/NMD | 03/02/2023 | 30 | S.P. ENTERPRISE | 32.98 | 0 | 50
158 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Additional Work (F.H.T.C , Paverblock Pavement etc ), under JJM/Jal Swapna in connection with rejuvenation of DAMDAMA PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri W/S Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000006/2025-2026 | 1233/SWSD | 24/04/2025 | 45 | KAMAL GHOSH | 4.73 | 0 | 0
159 | Siliguri W/S Division | Siliguri Sub-Division | Repairing Of Damaged Pipe Line alongwith House Connections at Airport More Sansad, Lokhnath nagar, Bhujiyapani under Dumriguri Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2023-2024 | 962/SWSD | 24/07/2023 | 15 | U.K CONSTRUCTIONS | 4.47 | 0 | 100
160 | Siliguri W/S Division | Siliguri Sub-Division | Work Order for Repairing of 350 Cu.M. R.C.C Elevated Reservoir, 20 mtrs. Staging Height at the Head Work Site, Laying Rising Main, Laying distribution pipe line with Functional House Hold Tap Connection (FHTC), Construction of one number pump house (3.00 X 3.60m), Sinking of 01 (one) no tubewell (ODEX-165 method) and Boundary wall for Dumriguri PWSS, Block Naxalbari, Dist- Darjeeling under Siliguri Water Supply Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000198/2023-2024 | 1978/SWSD | 26/10/2023 | 767 | DRISHTI CONSTRUCTION | 529.56 | 0 | 80
161 | Siliguri W/S Division | Siliguri Sub-Division | Sinking of 01(one) No Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at 3rd Tube well site for Augmentation of Dumriguri Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000252/2022-2023 | 2166/SWSD | 30/12/2022 | 10 | M/S K. R. S. CONSTRUCTION | 8.14 | 0 | 100
162 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000029/2022-2023 | 1459/SWSD | 29/09/2022 | 0 | Resource Division | 19.64 | 0 | 0
163 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000061/2022-2023 | 2041/SWSD | 16/12/2022 | 0 | Resource Division | 111.41 | 0 | 0
164 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for DUMRIGURI, TW No. I, (REJU) BAGDOGRA CCC [APPLICATION NO.4003151289 , Reference ID : 403013234] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00250/2023-2024 | BP/23-24/28 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
165 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for DUMRIGURI (REJU) , under BAGDOGRA CCC , [APPLICATION NO. 100000094733, Reference ID : 860287023] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02024/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.72 | 0 | 0
166 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DUMRIGURI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000661/2023-2024 | 1475/NMD | 17/08/2023 | 30 | RAJEEV RANJAN OJHA | 23 | 0 | 30
167 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED SANTA BHAWAN & RAJBARI LOWER PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000219/2022-2023 | 1117/NKWSMD | 05/08/2022 | 1195 | BOBBY PRADHAN | 117.24 | 0 | 50
168 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000148/2022-2023 | 2068/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.04 | 0 | 0
169 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MANI KHOPE PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | ORD/000268/2022-2023 | 1749/NKWSMD | 25/11/2022 | 265 | ROSHAN BISWAKARMA | 78.65 | 0 | 100
170 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | RTOR000114/2023-2024 | 1066/NKWSMD | 13/09/2023 | 0 | Resource Division | 0.42 | 0 | 0
171 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LAPCHER (ROHINI) PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000082/2022-2023 | 603/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 63.44 | 0 | 100
172 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000073/2022-2023 | 1317/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.52 | 0 | 0
173 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000138/2022-2023 | 1258/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.52 | 0 | 0
174 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MARCHEBUNG PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000079/2022-2023 | 602/NKWSMD | 26/05/2022 | 622 | ROSHAN BISWAKARMA | 60.38 | 0 | 100
175 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000071/2022-2023 | 1315/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.57 | 0 | 0
176 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000136/2022-2023 | 2056/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.57 | 0 | 0
177 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Lower Lonku under Kurseong Sub-Division, P.H.E.D. GTA. | Assistant Engineer | Sub-Assistant Engineer | ORD/000140/2022-2023 | 831/NKWSMD | 30/06/2022 | 607 | BIKRAM RAI | 79.8 | 0 | 100
178 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/01/2025 TO 31/03/2025 (3 MONTHS). | Assistant Engineer | Sub-Assistant Engineer | ORD/000163/2024-2025 | 2410/NKWSMD | 31/12/2024 | 90 | NIM TSHERING LEPCHA | 2.17 | 0 | 0
179 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000142/2022-2023 | 2062/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.46 | 0 | 0
180 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000264/2022-2023 | 2812 | 14/03/2023 | 0 | Resource Division | 0.46 | 0 | 0
181 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000030/2022-2023 | 1460/SWSD | 29/09/2022 | 0 | Resource Division | 4.89 | 0 | 0
182 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rungbull (Gorkha Busty habitation) under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000144/2022-2023 | 835/NKWSMD | 30/06/2022 | 1260 | SAMIR THAPA | 10.11 | 0 | 80
183 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000049/2022-2023 | 1293/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.87 | 0 | 0
184 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Work for Providing FHTC under Jal Jeevan Mission for balance Household at Maneybhanjang Forest Village Gram Panchayat: Sukhia Simana Block: Jorebunglow Sukhiapokhri. |  | Sub-Assistant Engineer | ORD/000200/2023-2024 | 1082/NKWSMD | 19/09/2023 | 210 | MOHAN MUKHIA | 55.31 | 0 | 75
185 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SUKHIA POKHARI PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000253/2022-2023 | 1525/NKWSMD | 17/10/2022 | 960 | SUMAN PRADHAN | 317.2 | 0 | 100
186 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000014/2024-2025 | 979/NKWSMD | 18/06/2024 | 60 | SUNRISE ENTERPRISES | 24.35 | 0 | 100
187 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Kurseong Division, P.H.E.D., GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000262/2023-2024 | 160/AE-II/NKWSMD | 10/01/2024 | 357 | MS JAGANNATH PRASAD | 12.44 | 0 | 100
188 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme in Kurseong Under Darjeeling District. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000286/2022-2023 | 2081/NKWSMD | 10/01/2023 | 348 | SUNRISE ENTERPRISES | 185.86 | 0 | 100
189 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0
190 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Aringalae with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000179/2022-2023 | 955/NKWSMD | 12/07/2022 | 790 | LAL BAHADUR THAPA | 27.77 | 0 | 75
191 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000075/2022-2023 | 1319/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.74 | 0 | 0
192 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000146/2022-2023 | 2066/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.74 | 0 | 0
193 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 2 (two) Nos. Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size toilet, Rig bore 2 (two) Nos. big dia deep T/W by Odex-165 method of drilliig, boundary wall at 2 (two) sites. laying distribution system, providing functional house hold tap connection (FHTC) and supplying, fabrication, erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (40 cum/hr. at SATHBIL PASCHIM MADATI Mouza and 20 cu.m./hr opposite of MADATI HIGH SCHOOL) required platform and drain etc. for Rejuvenation at PURBA MADATI Piped Water Supply Scheme at Phanshidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000133/2023-2024 | 1372/SWSD | 18/08/2023 | 948 | M/S G.C. CONSTRUCTION & CO. | 117.74 | 0 | 35
194 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000052/2022-2023 | 2032/SWSD | 16/12/2022 | 0 | Resource Division | 1.97 | 0 | 0
195 | Central Drilling | Siliguri Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
196 | Northern Mechanical | Siliguri Sub-Division | Quotation Charges New service Connection at Purba Madati PWSS under NMD,PHE Dte. Application No - 4003339413 Ref Id- 403162854 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00835/2024-2025 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.97 | 0 | 0
197 | Northern Mechanical | Siliguri Sub-Division | Charges for New Service connection at Purba Madati PWSS,TW No- II under NMD , PHEW Dte. Application No- 4003498842 Ref ID- 403286657 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01403/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.19 | 0 | 0
198 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PURBA MADATI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000665/2023-2024 | 1479/NMD | 17/08/2023 | 805 | RIPON DAS | 23.26 | 0 | 90
199 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 200 Cu.M. capacity RCC Elevated Reservoir of 20 mtr. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells by ODEX-165, construction of pump houses with toilet, boundary wall at head works 2nd tubewell & 3rd Tubewell sites with necessary interconnection, providing FHTC with platform with other allied works under Jal Jeevan Mission for PATHAR HIRHIRAR CHHAT piped W/S scheme of Phansidewa Block under Siliguri Sub Division PHE Dte. ( Sl No. 08) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000075/2023-2024 | 859/SWSD | 12/07/2023 | 1131 | SUBIR CH. CHOWDHURY | 403.68 | 0 | 70
200 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Pathar Hirhirar Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000161/2022-2023 | 307/SSD | 09/06/2022 | 20 | SUBHANKAR GHOSH | 3.09 | 0 | 100
201 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000043/2023-2024 | 68/SWSD | 10/01/2024 | 0 | Resource Division | 8.57 | 0 | 0
202 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000064/2022-2023 | 2044/SWSD | 16/12/2022 | 0 | Resource Division | 30.96 | 0 | 0
203 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
204 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PATHAR HARHARIAR CHHAT, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003299733 ; Reference ID : 403131317] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01739/2023-2024 | BP/23-24/224 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.72 | 0 | 0
205 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PATHAR HARHARIAR CHHAT, T/W No. II, under NAXALBARI CCC [APPLICATION NO. 4003300848 ; Reference ID : 403131314] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01740/2023-2024 | BP/23-24/225 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.46 | 0 | 0
206 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PATHAR HIRHIRAR CHHAT , T/W No. III, under NAXALBARI CCC, [APPLICATION NO. 4003313525, Reference ID : 403145696] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01954/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.79 | 0 | 0
207 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
208 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHAR HIRHIRAR CHHAT PIPED WATER SUPPLY SCHEME, TW No. I, II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000780/2023-2024 | 1644/NMD | 29/09/2023 | 562 | PADMA ENGINEERING CO. | 20.85 | 0 | 90
209 | Northern Mechanical | Siliguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000996/2024-2025 | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0
210 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001071/2024-2025 | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0
211 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for IMPROVEMENT OF EXISTING PIPELINE & FHTC DUE TO ROAD & DRAIN CONSTRUCTION at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under JJM/Jal Swapna in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri Sub Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000010/2025-2026 | 1236/SWSD | 24/04/2025 | 30 | KAMAL GHOSH | 16.83 | 0 | 0
212 | Siliguri W/S Division | Siliguri Sub-Division | Additional work (Including repairing of damaged house connection , Pipeline extention of existing pipeline etc) at Singbhita, Dhulia, Dhuliar Chhat, Dakua, Tharu Bhita, Dagdhu mouza under Jal Jeevan Mission in connection with rejuvenation of DHULIA PIPED WATER SUPPLY SCHEME under Kharibari block, Darjeeling District under Siliguri W/S Division, PHD Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000142/2024-2025 | 2536/SWSD | 18/09/2024 | 137 | KAMAL GHOSH | 7.7 | 0 | 80
213 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000048/2022-2023 | 2028/SWSD | 16/12/2022 | 0 | Resource Division | 0.98 | 0 | 0
214 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for rrjuvenation of Dhulia PWSS, TW No. I, NAXALBARI CCC [APPLICATION NO. 4003144973 ; Reference ID : 403013028] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00040/2023-2024 | BP/23-24/11 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
215 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DHULIA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000799/2022-2023 | 164/NMD | 17/02/2023 | 30 | MAA BHABOTARINE ENTERPRISE | 10.76 | 0 | 70
216 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED ROHINI TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | ORD/000011/2023-2024 | 100/NKWSMD | 28/04/2023 | 180 | RUKMANI ENGINEERING WORKS | 324.1 | 0 | 80
217 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | RTOR000043/2023-2024 | 322/NKWSMD | 24/05/2023 | 0 | Resource Division | 1.69 | 0 | 0
218 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | RTOR000152/2022-2023 | 2072/NKWSMD | 05/01/2023 | 0 | Resource Division | 8.37 | 0 | 0
219 | Siliguri W/S Division | Siliguri Sub-Division | Issue of fuel for office Executive Engineer and Assistant Engineer Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00295/2023-2024 | BP-2023-24-141 | 15/12/2023 | 0 | SONA PETROL PUMP | 0.2 | 0 | 0
220 | Siliguri W/S Division | Siliguri Sub-Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF UTTAR BANSGAON KISMAT PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000062/2023-2024 | 255/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.31 | 0 | 100
221 | Siliguri W/S Division | Siliguri Sub-Division | Construction Of 150 Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site along with distribution system, functional household tap connection ,rising main ,pump house (3 nos),IEP (2 nos.),Boundry wall, tube well and soil investigation test under Jal Jeevan Mission of UTTAR BANSGAON KISMAT Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte.. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000083/2023-2024 | 976/SWSD | 25/07/2023 | 963 | MANAS KUMAR SAHA | 391.69 | 0 | 12
222 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000040/2022-2023 | 1952/SWSD | 07/12/2022 | 0 | Resource Division | 13.74 | 0 | 0
223 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
224 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for UTTAR BANSGAON, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003303453 ; Reference ID : 403135383] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01814/2023-2024 | BP/23-24/274 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.16 | 0 | 0
225 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for UTTAR BANSGAON KISMAT, T/W No.I, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003320164, Reference ID : 403149648] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01948/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.01 | 0 | 0
226 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for UTTAR BANSGAON KISMAT, T/W No. I, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320186, Reference ID : 403148656] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01949/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.11 | 0 | 0
227 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
228 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR BANSGAON KISMAT (ZONE-I) TW No. I and II , (ZONE-II) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000781/2023-2024 | 1645/NMD | 29/09/2023 | 30 | SARKAR ELECTRIC | 20.65 | 0 | 85
229 | Northern Mechanical | Siliguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000996/2024-2025 | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0
230 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/001071/2024-2025 | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0
231 | Siliguri W/S Division | Siliguri W/S Division | Construction of Pump House 2 Nos., Rig bore 2 Nos. big dia T/W by Odex- 165 method, boundary walls, laying distribution system (HDPE pipe), rising main, providing FHTC & supplying fabrication on suitable RCC foundation & commissioning with 3 (three) months trial run IEP (20 m cum/hr) and allied works at Augmentation of Buraganj & Jatru PWSS at Kharibari block under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000010/2023-2024 | 335/SWSD | 08/05/2023 | 635 | DEBRAJ ENTERPRISE | 228.26 | 0 | 100
232 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BURAGANJ & JATUR PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000060/2023-2024 | 253/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.22 | 0 | 100
233 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000055/2022-2023 | 2035/SWSD | 16/12/2022 | 0 | Resource Division | 16.3 | 0 | 0
234 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. I, under KHARIBARI CCC [APPLICATION NO. 4003291396 ; Reference ID : 403123842] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01712/2023-2024 | BP/23-24/202 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0
235 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BURAGANJ AND JATRU, T/W No. II, under KHARIBARI CCC [APPLICATION NO. 4003291407 ; Reference ID : 403123844] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01713/2023-2024 | BP/23-24/203 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.06 | 0 | 0
236 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
237 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BURAGANJA and JATRU PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000783/2023-2024 | 1647/NMD | 29/09/2023 | 641 | SANJIB SAHA | 11.85 | 0 | 100
238 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0
239 | Neorakhola W/S & Mtc.Div. | Kurseong Division | GRAVITY BASED WATER SUPPLY SCHEME FOR LATPANCHAR FOREST, UNDER JAL JEEVAN MISSION | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | BILL/00396/2024-2025 | BP-2024-25-281 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.3 | 0 | 0
240 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR LATPANICHAR FOREST PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | ORD/000021/2023-2024 | 120/NKWSMD | 28/04/2023 | 905 | MS. SURYA I PVT. LTD COMPANY | 239.52 | 0 | 80
241 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | RTOR000018/2023-2024 | 203/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.03 | 0 | 0
242 | Siliguri W/S Division | Siliguri W/S Division | Laying of additional pipeline installation of FHTC and Others allied Works at command area of Augmentation of Birsing Piped Water Supply Scheme inconnection with JJM under Siliguri W/S Division P.H.E. Dte.. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000143/2024-2025 | 2537/SWSD | 18/09/2024 | 151 | NARAYAN CH GHOSH | 4.81 | 0 | 100
243 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum Work order Laying distribution system along with boring of new tubewells by ODEX-165, construction of pump houses, boundary walls at 3rd and 4th tubewell site and other allied works inconnection with Augmentation of BIRSING Piped Water Supply Scheme at Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000190/2024-2025 | 3324/SWSD | 09/12/2024 | 403 | M/S G.C. CONSTRUCTION & CO. | 53.95 | 0 | 12
244 | Siliguri W/S Division | Siliguri W/S Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 50
245 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000006/2023-2024 | 204/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0
246 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
247 | Central Drilling | Siliguri W/S Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
248 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BIRSING, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003300023 ; Reference ID : 403131327] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01741/2023-2024 | BP/23-24/228 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0
249 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
250 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BIRSING PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000809/2023-2024 | 1666/NMD | 29/09/2023 | 30 | MAA ENTERPRISES | 10.31 | 0 | 0
251 | Northern Mechanical | Siliguri W/S Division | Installation of two tank chlorination system at BIRSING and other adjacent water supply scheme UNDER JJM under NAXALBARI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000890/2024-2025 | 82/SMSD | 07/02/2025 | 10 | CHOWDHURY AND BASU ENTERPRISE | 1.26 | 0 | 0
252 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/001067/2024-2025 | 35/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0
253 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for installation of the Iron removal filtration plant including platform and drain with necessary connection and blower room 01 No. at Bhalamanshi Piped water supply Scheme H/W Site within Phansidewa Block under Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000189/2024-2025 | 3155/SWSD | 25/11/2024 | 30 | PALLAB BHOWAL | 26.07 | 0 | 0
254 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000016/2023-2024 | 1800/SWSD | 30/09/2023 | 0 | Resource Division | 0.85 | 0 | 0
255 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000089/2022-2023 | 2231/SWSD | 06/01/2023 | 0 | Resource Division | 1.97 | 0 | 0
256 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
257 | Northern Mechanical | Siliguri W/S Division | Charges for New service Connection at Bhalomanshi TW-II Under NMD,PHE Dte. Application No- 4003425977 Ref. ID- 403232535 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00434/2024-2025 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.54 | 0 | 0
258 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
259 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BHALAMANSHI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000803/2023-2024 | 1660/NMD | 29/09/2023 | 30 | M/S ANJALI ENTERPRISE | 10.08 | 0 | 0
260 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0
261 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
262 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR LODHOMA PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000004/2023-2024 | 88/NKWSMD | 27/04/2023 | 600 | KAMAL AND COMPANY | 157.57 | 0 | 80
263 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000041/2023-2024 | 329/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.28 | 0 | 0
264 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR JAMADAR BHITA KHASMAHAL (PART-1 & 2) PIPED WATER SUPPLY SCHEME IN KURSEONG, UNDER DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000094/2023-2024 | 718/NKWSMD | 18/07/2023 | 665 | GARGO TRADERS | 976.84 | 0 | 70
265 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000063/2023-2024 | 759/NKWSMD | 19/07/2023 | 0 | Resource Division | 4.38 | 0 | 0
266 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00708/2023-2024 | BP-2023-24-477 | 28/01/2024 | 0 | WBSEDCL | 4.54 | 0 | 0
267 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00709/2023-2024 | BP-2023-24-478 | 28/01/2024 | 0 | WBSEDCL | 6.1 | 0 | 0
268 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR PANIGHATA PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000014/2023-2024 | 110/NKWSMD | 28/04/2023 | 900 | YAMA CONSTRUCTIONS LLP | 282.78 | 0 | 85
269 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR PANIGHATA PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT DARJEELING, KURSEONG DIVISION PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000171/2024-2025 | 161/NKWSMD | 04/02/2025 | 180 | S S CONSTRUCTIONS | 52.49 | 0 | 80
270 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000009/2023-2024 | 156/NKWSMD | 03/05/2023 | 0 | Resource Division | 7.53 | 0 | 0
271 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000119/2023-2024 | 1188/NKWSMD | 06/10/2023 | 0 | Resource Division | 7.53 | 0 | 0
272 | Siliguri W/S Division | Siliguri Sub-Division | Part Work order for 150 cu.m capacity R.C.C. elevated reservoir, 20 mtrs staging height at the head works site along with distribution system, functional household tap connection, rising main, pump house (2 nos), IEP, boundary wall and tubewell under Jal Jeevan Mission for Jogibhita Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000226/2023-2024 | 1979/SWSD | 26/10/2023 | 979 | M/S UTPAL CHAKRABORTY & CO. | 271.29 | 0 | 25
273 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Jogibhita Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000329/2022-2023 | 411/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 2.76 | 0 | 0
274 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000010/2023-2024 | 209/SWSD | 25/04/2023 | 0 | Resource Division | 23.71 | 0 | 0
275 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000056/2023-2024 | 81/SWSD | 10/01/2024 | 0 | Resource Division | 6.67 | 0 | 0
276 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
277 | Central Drilling | Siliguri Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
278 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for JOGIBHITA T/W No. I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003323751, Reference ID : 403152325] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/02034/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.32 | 0 | 0
279 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for JOGIBHITA T/W No. II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003323752, Reference ID : 403152314] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/02035/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.1 | 0 | 0
280 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAHAL DHIRAM FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000023/2023-2024 | 122/NKWSMD | 28/04/2023 | 630 | MS. SURYA I PVT. LTD COMPANY | 250.28 | 0 | 85
281 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000019/2023-2024 | 204/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.59 | 0 | 0
282 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM - 15895] | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00231/2024-2025 | BP-2024-25-234 | 03/09/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
283 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR SEVOKE HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT [SM NO - 15895] | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00232/2024-2025 | BP-2024-25-235 | 03/09/2024 | 0 | WBSEDCL | 4.17 | 0 | 0
284 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR SEVOK HILL FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000062/2023-2024 | 434/NKWSMD | 06/06/2023 | 605 | SRINIWAS AGARWAL | 216.18 | 0 | 85
285 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000056/2023-2024 | 441/NKWSMD | 07/06/2023 | 0 | Resource Division | 1.15 | 0 | 0
286 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0
287 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR JUNGPANA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | ORD/000029/2023-2024 | 107/NKWSMD | 28/04/2023 | 605 | SRINIWAS AGARWAL | 690.58 | 0 | 100
288 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | RTOR000027/2023-2024 | 247/NKWSMD | 12/05/2023 | 0 | Resource Division | 4.4 | 0 | 0
289 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR ALOOBARI PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-VI | ORD/000015/2023-2024 | 115/NKWSMD | 28/04/2023 | 840 | P. D. COMPANY | 577.74 | 0 | 100
290 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-VI | RTOR000004/2023-2024 | 156/NKWSMD | 03/05/2023 | 0 | Resource Division | 1.77 | 0 | 0
291 | Siliguri W/S Division | Siliguri W/S Division | Hiring of (one) no. Disel Motor Cab on daily basis for the Assistant Engineer-II, office of the Executive Engineer, Siliguri W/S Division, P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00353/2023-2024 | BP-2023-24-154 | 09/01/2024 | 0 | SUDIP BASAK | 0.99 | 0 | 0
292 | Siliguri W/S Division | Siliguri W/S Division | ISSUE OF FULE FOR OFFICE VEHICLES OF EXECUTIVE ENGINEER SILIGURI W/S DIVISION AND ASSISTANT ENGINEER PHE DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00354/2023-2024 | BP-2023-24-147 | 09/01/2024 | 0 | SONA PETROL PUMP | 0.53 | 0 | 0
293 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BARSADBHITA PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000052/2023-2024 | 245/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 3.87 | 0 | 100
294 | Siliguri W/S Division | Siliguri W/S Division | Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site (Zn-II) including distribution system all zones (HDPE) with Rising Main, Rig bore 3 nos. big dia T/W by Odex-165 method (Zn-II, III), Providing Functional Household Connection (FHTC), Pump House 3 Nos., Blower Room, IEP (Zone-III-30, Zn-II 30) cu.m/hr, Boundary Walls, Soil Testing & all repair works at Zone-I & Zn-II and allied works for Augmentation of BARSADVITA PWSS Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000113/2023-2024 | 1192/SWSD | 10/08/2023 | 753 | RAMESH AGARWAL | 572.07 | 0 | 60
295 | Siliguri W/S Division | Siliguri W/S Division | Continuation of Hiring of 1 (one) no. diesel consumed vehicle on monthly basis preferably Maxi Cab (with A/C) for O/O the Assistant Engineer, Siliguri Sub Division, P.H.E. Dte. from 01.09.2022 to 30.11.2022 (With Engine Capacity less than or equal to 2000 CC) (Vehicle no. WB 76A4921) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000270/2022-2023 | 439/SSD | 31/08/2022 | 91 | SUDIP BASAK | 0.44 | 0 | 100
296 | Siliguri W/S Division | Siliguri W/S Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 50
297 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000015/2023-2024 | 1799/SWSD | 30/09/2023 | 0 | Resource Division | 33.55 | 0 | 0
298 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000082/2022-2023 | 2199/SWSD | 04/01/2023 | 0 | Resource Division | 31.91 | 0 | 0
299 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
300 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BARSADBHITA Zone-III,TW- I under KHARIBARI CCC | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00382/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.5 | 0 | 0
301 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BARSADBHITA, T/W No. II, ZONE- II, under KHARIBARI CCC, [APPLICATION NO. 4003319623, Reference ID : 403147073] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01968/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.54 | 0 | 0
302 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BARSADBHITA, T/W No. I, ZONE-II, under KHARIBARI CCC, [APPLICATION NO. 4003319471, Reference ID : 403145974] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01969/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.56 | 0 | 0
303 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
304 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BARSADBHITA PIPED, (Zone-II) TW No. I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000749/2023-2024 | 1577/NMD | 08/09/2023 | 530 | DIPALI CONSTRUCTION | 25.01 | 0 | 100
305 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0
306 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0
307 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Piped Water Supply Scheme for Sukna under Kurseong Division. Scheme Code - 15653 TSM/017746 | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00093/2024-2025 | BP-2024-25-98 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0
308 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SUKNA PWSS TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000378/2022-2023 | 2874/NKWSMD | 23/03/2023 | 635 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 241.94 | 0 | 43
309 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000268/2022-2023 | 2893/NKWSMD | 29/03/2023 | 0 | Resource Division | 2.48 | 0 | 0
310 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
311 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR NAMLA TEA GARDEN PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000019/2023-2024 | 119/NKWSMD | 28/04/2023 | 728 | SAGARMATHA CONSTRUCTION CO. | 228.41 | 0 | 80
312 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR NAMLA BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK-DARJEELING PULBAZAR DISTRICT-DARJEELING. |  | Sub-Assistant Engineer | ORD/000154/2024-2025 | 2357/NKWSMD | 19/12/2024 | 60 | SAGARMATHA CONSTRUCTION CO. | 10.39 | 0 | 0
313 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Piped water supply scheme for Rimbick & Namla under Darjeeling Pulbazar Block, Darjeeling Division, PHED, G.T.A. |  | Sub-Assistant Engineer | ORD/000247/2023-2024 | 87/NKWSMD | 11/01/2024 | 90 | NIMA SHERPA | 27.05 | 0 | 100
314 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000005/2023-2024 | 152/NKWSMD | 03/05/2023 | 0 | Resource Division | 2.37 | 0 | 0
315 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR AMBOOTIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | ORD/000096/2023-2024 | 719/NKWSMD | 18/07/2023 | 1036 | SRINIWAS AGARWAL | 1473.72 | 0 | 65
316 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer6,Sub-Assistant Engineer | RTOR000087/2023-2024 | 815/NKWSMD | 24/07/2023 | 0 | Resource Division | 7.71 | 0 | 0
317 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00815/2023-2024 | BP-2023-24-531 | 26/02/2024 | 0 | WBSEDCL | 6.19 | 0 | 0
318 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00816/2023-2024 | BP-2023-24-532 | 26/02/2024 | 0 | WBSEDCL | 5.88 | 0 | 0
319 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00817/2023-2024 | BP-2023-24-533 | 26/02/2024 | 0 | WBSEDCL | 6.18 | 0 | 0
320 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000023/2025-2026 | 591/NKWSMD | 29/04/2025 | 180 | ALLIED INSTRUMENTS | 55.54 | 0 | 0
321 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR NEW FALLODI TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000155/2023-2024 | 883/NKWSMD | 03/08/2023 | 365 | GARGO TRADERS | 1359.83 | 0 | 80
322 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00820/2023-2024 | BP-2023-24-536 | 26/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0
323 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK: UNDER DARJEELING DISTRICT.UNDER KURSEONG DIVISION PHED-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000025/2025-2026 | 593/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 64.04 | 0 | 0
324 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SAURENA TEA ESTATE PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000156/2023-2024 | 884/NKWSMD | 03/08/2023 | 975 | GARGO TRADERS | 1832.72 | 0 | 75
325 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 31/11/2023. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000206/2023-2024 | 1153/NKWSMD | 29/09/2023 | 61 | THE ELECTRIC SPHERE | 0.94 | 0 | 0
326 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TUKDAH, LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000148/2024-2025 | 2351/NKWSMD | 19/12/2024 | 180 | THUPDEN BHUTIA | 117.43 | 0 | 0
327 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TUKDAH,LAPCHU KHASMAHAL & LAPCHU TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000176/2023-2024 | 935/NKWSMD | 16/08/2023 | 365 | THUPDEN BHUTIA | 1654.3 | 0 | 80
328 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000099/2023-2024 | 962/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.29 | 0 | 0
329 | Siliguri W/S Division | Siliguri W/S Division | FUEL FOR OFFICE VECHILE OF EXECUTIVE ENGINEER SILIGURI W/S DIVISION PHE DTE | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00400/2023-2024 | BP-2023-24-161 | 29/01/2024 | 0 | SONA PETROL PUMP | 0.3 | 0 | 0
330 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for providing functional house hold tap connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara block under Siliguri Sub Division, P.H.E. Dte. (Part-I). | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000010/2024-2025 | 1779/SWSD | 12/07/2024 | 45 | SWAPAN CHANDRA DAS | 19.86 | 0 | 0
331 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) under Augmentation of Kalkut PWSS (Zone-II) under Matigara Block in connection with JJM under Siliguri W/S Division P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000013/2025-2026 | 1239/SWSD | 24/04/2025 | 30 | BUDDHADEV NAG | 36.69 | 0 | 0
332 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum Work Order for Construction of Pump House, Boundary wall, IEP and Blower room and allied work for Augmentation Kalkut Zone-1within Matigara block in connection with JJM under Siliguri W/S Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000016/2025-2026 | 1349/SWSD | 02/05/2025 | 45 | BRM DEVELOPERS | 28.42 | 0 | 0
333 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-III) within Matigara Block under Siliguri Sub Division, P.H.E.Dte. (Part ¿ B). | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000020/2025-2026 | 1094/SWSD | 11/04/2025 | 60 | SAFTI PRIVATE LIMITED | 58.79 | 0 | 0
334 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-III) under Matigara Block under Siliguri Sub Division, P.H.E.Dte. (Part A). | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000021/2025-2026 | 1403/SWSD | 08/05/2025 | 60 | SAFTI PRIVATE LIMITED | 53.44 | 0 | 0
335 | Siliguri W/S Division | Siliguri W/S Division | Work order for Laying distribution system at Kalkut Piped Water Supply Scheme (Zone-II) Part-B under JJM at Matigara Block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000031/2024-2025 | 2026/SWSD | 06/08/2024 | 180 | NARENDRA KUMAR | 128.48 | 0 | 30
336 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PIPED KALKUT WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000068/2023-2024 | 261/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 4.68 | 0 | 100
337 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000085/2023-2024 | 1023/SWSD | 26/07/2023 | 615 | S.G.CONSTRUCTION | 7.63 | 0 | 0
338 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Construction of boundary wall at 3rd tubewell site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000087/2023-2024 | 1024/SWSD | 26/07/2023 | 60 | SHREYANSH AUTOMOBILE | 7.63 | 0 | 0
339 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum Work Order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-II) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000088/2023-2024 | 1025/SWSD | 26/07/2023 | 60 | A.B. GANAPATI CONSTRUCTION | 7.63 | 0 | 75
340 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum Work Order for Construction of boundary wall at 2nd tubewell site of Kalkut Piped Water Supply Scheme (Zone-III) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000089/2023-2024 | 1026/SWSD | 26/07/2023 | 60 | M/S SHIB ENTERPRISE | 7.72 | 0 | 0
341 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Construction of boundary wall at 3rd tubewell site of Kalkut Piped Water Supply Scheme (Zone-III) with site development and other allied works under JJM within Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000090/2023-2024 | 1027/SWSD | 26/07/2023 | 60 | S.K. BANIK | 7.63 | 0 | 0
342 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Construction of pump house with toilet at Head Works site of Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigaraa Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000091/2023-2024 | 1028/SWSD | 26/07/2023 | 60 | PANKAJ KUNDU | 5.63 | 0 | 90
343 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Construction of pump house (3.60 m X 2.40 m) size with sanitary and plumbing arrangement at 2nd tubewell site for Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigara Block, Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000094/2023-2024 | 1029/SWSD | 26/07/2023 | 60 | PANKAJ KUNDU | 4.58 | 0 | 0
344 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Construction of pump house (3.60 m X 2.40 m) size with sanitary and plumbing arrangement at 3rd tubewell site for Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara Block, Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000095/2023-2024 | 1030/SWSD | 26/07/2023 | 60 | CHOWDHURY & BASU ENTERPRISE | 4.74 | 0 | 0
345 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-A). | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000100/2023-2024 | 1031/SWSD | 26/07/2023 | 675 | A.B. GANAPATI CONSTRUCTION | 4.85 | 0 | 100
346 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-E) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000101/2023-2024 | 1032/SWSD | 26/07/2023 | 1027 | S.G.CONSTRUCTION | 9.71 | 0 | 100
347 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-F) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000102/2023-2024 | 1033/SWSD | 26/07/2023 | 45 | S.K. BANIK | 9.71 | 0 | 0
348 | Siliguri W/S Division | Siliguri W/S Division | Construction of 450 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site at KALKUT Piped W/S Scheme (Zone-2) and FHTC Part-J under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000121/2023-2024 | 1226/SWSD | 14/08/2023 | 535 | BUDDHADEV NAG | 164.68 | 0 | 1
349 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Sche me (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-D). | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000124/2023-2024 | 1233/SWSD | 14/08/2023 | 45 | ROYAL ENTERPRISE | 9.81 | 0 | 0
350 | Siliguri W/S Division | Siliguri W/S Division | Construction of 550 cu.m. capacity R.C.C. Elevated, 20 mtrs. Staging height at the head works site and FHTC (Part-C) at KALKUT Piped W/S Scheme (Zone-3) under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte. (SL No.01) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000127/2024-2025 | 2616/SWSD | 23/09/2024 | 225 | BUDDHADEV NAG | 205.05 | 0 | 60
351 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system along with laying of rising main with interconnection at Kalkut Piped Water Supply Scheme (Zone-III) under JJM at Matigara Block, Darjeeling District, under Siliguri Sub Division, PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000128/2023-2024 | 1241/SWSD | 16/08/2023 | 1013 | MANAS KUMAR SAHA | 358.73 | 0 | 29
352 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system Part-B and allied works at Kalkut Piped W/S Scheme (Zone-I) undere JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000134/2023-2024 | 1373/SWSD | 18/08/2023 | 310 | DEBASHIS SINHA | 226.29 | 0 | 60
353 | Siliguri W/S Division | Siliguri W/S Division | Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, Rising main and laying distribution system Part-A at KALKUT Piped W/S Scheme (Zone-I) under JJM of Matigara Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000136/2023-2024 | 1404/SWSD | 21/08/2023 | 497 | M/S G.C. CONSTRUCTION & CO. | 152.43 | 0 | 90
354 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for construction of Rig bore big dia deep tubewell by Odex-165 method of drilling at head works, 2nd TW and 3rd TW site of Kalkut Piped Water Supply Scheme (Zone-II) under JJM within Matigara block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000173/2023-2024 | 1735/SWSD | 22/09/2023 | 45 | ABHIJIT CHANDA | 21.28 | 0 | 31
355 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for construction of Rig bore big dia deep tubewell by Odex-165 method of drilling at head works, 2nd TW and 3rd TW site of Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000174/2023-2024 | 1736/SWSD | 22/09/2023 | 45 | ABHIJIT CHANDA | 21.28 | 0 | 0
356 | Siliguri W/S Division | Siliguri W/S Division | Work Order for laying distribution system along with laying of rising main with interconnection at Kalkut Piped Water Supply Scheme (Zone-II) Part-A under JJM Matigara Block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000179/2023-2024 | 1730/SWSD | 21/09/2023 | 90 | ARUN KUMAR SHRIVASTAVA | 111.73 | 0 | 0
357 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum Work Order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped water Supply Scheme (Zone-II) with Matigara Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000184/2023-2024 | 1830/SWSD | 03/10/2023 | 45 | KULENDRA NATH BARMAN | 19.02 | 0 | 0
358 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-B) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000186/2023-2024 | 1883/SWSD | 09/10/2023 | 30 | M/S S.P. BISWAS | 4.85 | 0 | 0
359 | Siliguri W/S Division | Siliguri W/S Division | Acceptance Cum Work Order for Construction of boundary wall at head work site of Kalkut Piped Water Supply Scheme (Zone-I) with site development and other allied works under JJM within Matigara block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000218/2023-2024 | 2034/SWSD | 06/11/2023 | 60 | SANJIB SAHA | 18.35 | 0 | 0
360 | Siliguri W/S Division | Siliguri W/S Division | Acceptance Cum Work Order for Providing Functional Household Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000219/2023-2024 | 2035/SWSD | 06/11/2023 | 45 | M/S DIBYA CONSTRUCTION | 19.86 | 0 | 0
361 | Siliguri W/S Division | Siliguri W/S Division | Acceptance Cum Work Order for Providing Functional House Hold Tap Connection along with platform under Jal Jeevan Mission for Kalkut Piped Water Supply Scheme (Zone-II) within Matigara Block under Siliguri Sub Division, P.H.E. Dte. (Part-C) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000221/2023-2024 | 2050/SWSD | 07/11/2023 | 30 | CHOWDHURY & BASU ENTERPRISE | 4.85 | 0 | 0
362 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House Hold Tap Connection (FHTC) at Kalkut Zone-1 Command area of Augmentation of Kalkut PWSS inconnection with JJM under Siliguri W/S Division P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000236/2024-2025 | 243/SWSD | 22/01/2025 | 30 | M/S G.C. CONSTRUCTION & CO. | 15.2 | 0 | 0
363 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House Hold Tap Connection (FHTC) at Kalkut Zone-3 Command area of Augmentation of Kalkut PWSS in connection with JJM under Siliguri W/S Division P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000242/2024-2025 | 483/SWSD | 12/02/2025 | 30 | DEBASHIS SINHA | 15.2 | 0 | 0
364 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for construction of pump house (3.6 m X 2.40 m) size with sanitary and plumbing arrangement at 2nd tubewell site for Kalkut Piped Water Supply Scheme (Zone-III) under JJM within Matigara Block, Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000256/2023-2024 | 102/SWSD | 15/01/2024 | 383 | ARATI SAHA | 4.82 | 0 | 88
365 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000017/2023-2024 | 1801/SWSD | 30/09/2023 | 0 | Resource Division | 142.4 | 0 | 0
366 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000026/2023-2024 | 2285 | 11/12/2023 | 0 | Resource Division | 4.28 | 0 | 0
367 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
368 | Northern Mechanical | Siliguri W/S Division | Charges for new service connection at T.W No-III,zone-II of Kalkut (Aug) w/s scheme in the dist of Darjeeling under NMD PHE dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00491/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.84 | 0 | 0
369 | Northern Mechanical | Siliguri W/S Division | Charges for new service connection at T.W No-I,zone-III of Kalkut (Aug) w/s scheme in the dist of Darjeeling under NMD PHE dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00492/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.35 | 0 | 0
370 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KALKUT, T/W No. II, ZONE-II, under PRADHAN NAGAR CCC [APPLICATION NO. 4003302722 ; Reference ID : 4003132350] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01818/2023-2024 | BP/23-24/278 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 17.36 | 0 | 0
371 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KALKUT, T/W No. I, ZONE-II, under PRADHAN NAGAR CCC [APPLICATION NO. 4003302654 ; Reference ID : 403132349] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01819/2023-2024 | BP/23-24/279 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.49 | 0 | 0
372 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
373 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KALKUT PIPED WATER SUPPLY SCHEME, (ZONE-II) TW NO I, II, III AND (ZONE-III) TW NO I, II, III in the district of DARJEELING under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000808/2023-2024 | 1665/NMD | 29/09/2023 | 30 | ORIENTAL ENGINEERING CO. | 57.97 | 0 | 30
374 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0
375 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/001065/2024-2025 | 33/NMD | 06/01/2025 | 30 | SAIKAT SINHA | 12.3 | 0 | 0
376 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAHAL DIRAM TEA GARDEN PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000324/2022-2023 | 2655/NKWSMD | 28/02/2023 | 630 | MS. SURYA I PVT. LTD COMPANY | 212.76 | 0 | 85
377 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000133/2023-2024 | 263/NKWSMD | 20/02/2024 | 0 | Resource Division | 2.17 | 0 | 0
378 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000245/2022-2023 | 2720/NKWSMD | 03/03/2023 | 0 | Resource Division | 1.02 | 0 | 0
379 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR KANKIBONG PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000228/2023-2024 | 1290/NKWSMD | 17/10/2023 | 365 | SAGARMATHA CONSTRUCTION CO. | 785.44 | 0 | 10
380 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA. |  |  | ORD/000039/2025-2026 | 654/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 142.77 | 0 | 0
381 | Neorakhola W/S & Mtc.Div. |  | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.08.2024 to 31.08.2024. |  |  | ORD/000096/2024-2025 | 1346/NKWSMD | 31/07/2024 | 31 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
382 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR KALEJ VALLEY PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000202/2023-2024 | 1100/NKWSMD | 21/09/2023 | 365 | VINAYAK CONSTRUCTION | 1970.49 | 0 | 50
383 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 1174/NKWSMD | 05/10/2023 | 0 | Resource Division | 3.2 | 0 | 0
384 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | i)Hydrological study of Rungdong Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-I ii) Hydrological study of Jamboni River under Water Supply Scheme for Darjeeling Pulbazar Pumping-II iii) Hydrological study of Jhepi Khola River under Water Supply Scheme for Darjeeling Pulbazar Pumping-III iv)Hydrological study of Balason Khola River (locally khown as Rangbhang Khola) under Water Supply Scheme for Mangarjung Tea Garden and other three villages (MVS), Block- Jorebunglow Sukhiapokhari. v) Hydrological study of Rangbhang River (Khola) Pumping water Supply Scheme for Mirik Municipal Town and EN-Route villages District- Darjeeling (under AMRUT) | Assistant Engineer 1 | Sub-Assistant Engineer | BILL/00218/2024-2025 | BP-2024-25-179 | 01/08/2024 | 0 | JADAVPUR UNIVERSITY | 17.51 | 0 | 0
385 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000113/2025-2026 | 942/NKWSMD | 30/06/2025 | 92 | NIM TSHERING LEPCHA | 2.17 | 0 | 0
386 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/07/2025 TO 30/09/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000114/2025-2026 | 943/NKWSMD | 30/06/2025 | 92 | NIM TSHERING LEPCHA | 3.61 | 0 | 0
387 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - II SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000169/2024-2025 | 134/NKWSMD | 28/01/2025 | 546 | SSN DEVELOPERS | 8170.65 | 0 | 15
388 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months for G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000218/2024-2025 | 146/NKWSMD | 31/01/2025 | 150 | YAMA CONSTRUCTIONS LLP | 0.83 | 0 | 0
389 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES FROM 5 BLOCKS OF DARJEELING HILLS UNDER SINDHAP SUB DISTRICT LABORATORY UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000234/2024-2025 | 413/NKWSMD | 28/03/2025 | 92 | NIM TSHERING LEPCHA | 2.17 | 0 | 0
390 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/04/2025 TO 30/06/2025 (3 MONTHS). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000235/2024-2025 | 414/NKWSMD | 28/03/2025 | 92 | NIM TSHERING LEPCHA | 3.61 | 0 | 0
391 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000128/2023-2024 | 52/NKWSMD | 09/01/2024 | 0 | Resource Division | 13.36 | 0 | 0
392 | Neorakhola W/S & Mtc.Div. |  | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake,WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites),GLRs,Chlorine cum switch room , Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR DARJEELING PULBAZAR PUMPING - III SPRING WATER SUPPLY SCHEME followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000107/2024-2025 | 1653/NKWSMD | 11/09/2024 | 546 | YATERI CONSTRUCTIONS,JV OF YAMA CONSTRUCTIONS LLP(LEAD PARTNER),AROGYA ENT & BALAJI CONS. | 6744.68 | 0 | 40
393 | Neorakhola W/S & Mtc.Div. |  | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/08/2024 to 31/01/2025. Note: With effect from the date of issuing work order. |  |  | ORD/000118/2024-2025 | 1349/NKWSMD | 31/07/2024 | 180 | SUJIT DEB | 0.99 | 0 | 100
394 | Neorakhola W/S & Mtc.Div. |  | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 5 (Five) Months, other than G.T.A Area from 01/02/2025 to 30/06/2025. Note: With effect from the date of issuing work order. |  |  | ORD/000219/2024-2025 | 147/NKWSMD | 31/01/2025 | 150 | SUJIT DEB | 0.83 | 0 | 0
395 | Neorakhola W/S & Mtc.Div. |  | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
396 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 53/NKWSMD | 09/01/2024 | 0 | Resource Division | 9.98 | 0 | 0
397 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 350 cu.m. Capacity Elevated Reservoir 20 m staging height allied with laying of distribution pipeline, Rising Main,construction of 3 nos. Big dia rig bore tube well by ODEX-165, Pump House, Iron Elemination Plant, Boundary Wall including Functiopnal Household Tap Connection at KASHIRAM Piped Water Supply Scheme (Zone I & II) undere Phansidewa block, Darjeeling dist. in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000131/2023-2024 | 1366/SWSD | 18/08/2023 | 606 | UNIBRO INFRASERV PRIVATE LIMITED | 676.79 | 0 | 35
398 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kashiram Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000319/2022-2023 | 255/SSD | 17/05/2022 | 20 | ENVIROTECH SOLUTIONS | 4.05 | 0 | 100
399 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000021/2023-2024 | 1805/SWSD | 30/09/2023 | 0 | Resource Division | 7 | 0 | 0
400 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000032/2023-2024 | 2291/SWSD | 11/12/2023 | 0 | Resource Division | 1.63 | 0 | 0
401 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000053/2023-2024 | 78/SWSD | 10/01/2024 | 0 | Resource Division | 22.19 | 0 | 0
402 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
403 | Northern Mechanical | Siliguri Sub-Division | Quotation Charges New service Connection at Kashiram PWSS,TW-III under NMD,PHE Dte. Application No - 4003458955 Ref Id- 403256880 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00832/2024-2025 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 20.61 | 0 | 0
404 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for KASHIRAM , T/W No. I under PHANSIDAWA CCC, [APPLICATION NO. 4003317755, Reference ID : 403145742] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01981/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.28 | 0 | 0
405 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for KASHIRAM , T/W No. II under PHANSIDAWA CCC, [APPLICATION NO. 4003317760, Reference ID : 403145866] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01982/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.26 | 0 | 0
406 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KASHIRAM PIPED WATER SUPPLY SCHEME, TW No.- I,II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000789/2023-2024 | 1653/NMD | 29/09/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 23 | 0 | 0
407 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART), OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 1 - Sonada Khasmahal part 1] | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000171/2023-2024 | 915/NKWSMD | 11/08/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1177.68 | 0 | 80
408 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 2 - Sonada Khasmahal part 2] | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000173/2023-2024 | 916/NKWSMD | 11/08/2023 | 605 | M/S. ASHOK KUMAR PERIWAL | 1167.7 | 0 | 80
409 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (SURFACE WATER BASED SONADA KHASMAHAL, RONGMOOK CEDER TEA GARDEN (PART) ,OAKS TEA GARDEN (PART), & RINGTONG TEA GARDEN (PART) PWSS TO ACCOMODATE FHTC IN JORE BUNGLOW SUKHIA POKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE.) [ZONE - 3 - Rongmook ceder (part), Oaks (part) & Ringtong tea garden (part)] | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000174/2023-2024 | 917/NKWSMD | 11/08/2023 | 365 | TIKARAM SHARMA | 1263.3 | 0 | 85
410 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000106/2023-2024 | 972/NKWSMD | 21/08/2023 | 0 | Resource Division | 10.32 | 0 | 0
411 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED RANGMOOK CEDER TEA GARDEN (PART) AND OAKS TEA GARDEN (PART) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN JOREBUNGLOW SUKHIAPOKHARI BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.DTE. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000164/2023-2024 | 912/NKWSMD | 11/08/2023 | 1025 | M/S. ASHOK KUMAR PERIWAL | 2166.21 | 0 | 80
412 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000109/2023-2024 | 975/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.24 | 0 | 0
413 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00760/2023-2024 |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0
414 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | FOREST PAYMENT | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00905/2023-2024 | BP-2023-24-497 | 17/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0
415 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR TINDHARIA & NORBUNG TEA GARDEN WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000010/2025-2026 | 496/NKWSMD | 09/04/2025 | 90 | SUNIT DEEP RAI | 17.57 | 0 | 0
416 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED TINDHARIA & NARBUNG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSOENG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000166/2023-2024 | 919/NKWSMD | 11/08/2023 | 605 | SUNIT DEEP RAI | 1161.89 | 0 | 100
417 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000105/2023-2024 | 967/NKWSMD | 21/08/2023 | 0 | Resource Division | 2.14 | 0 | 0
418 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BHIRGAON DHARAGAON PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000159/2023-2024 | 893/NKWSMD | 07/08/2023 | 180 | RINZI SHERPA | 152.77 | 0 | 60
419 | Siliguri W/S Division | Siliguri Sub-Division | Laying of new pipe line in connection with providing functional household tap connection (FHTC) at Mingharer Chhat, Nimubhitar Chhat, Atal of Damdama W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000122/2021-2022 | 2363/SWSD | 08/03/2022 | 25 | ARUN KUMAR SHRIVASTAVA | 19.04 | 0 | 100
420 | Siliguri W/S Division | Siliguri Sub-Division | Laying of new pipe line in connection with providing functional household tap connection (FHTC) at Damdama, Grammani, Grammanir Chhat of Damdama W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000125/2021-2022 | 2364/SWSD | 08/03/2022 | 20 | DEBOL,S ENTERPRISE | 9.63 | 0 | 100
421 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Bairbhita Habitation Bairvita Madanjote village Atal Habitation Atal village Nimubhita chat Habitation Nimuvita, village Minghara chat Habitation Minghar chhat of Damdama Piped Water Supply Scheme and Allied works at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 04 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000205/2020-2021 | 1525/SWSD | 22/02/2021 | 25 | ARUN KUMAR SHRIVASTAVA | 20.95 | 0 | 75
422 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapno under Shyamdhan and adjoining mouas WS Scheme command area at Badra and Balijhora and laying wash out pipeline from 2nd T W IEP upto nearest culvert and also laying HDPE piped at Shyamdhan command area of the Shyamdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000048/2021-2022 | 1219/SWSD | 01/11/2021 | 20 | M/S SHIVAJI ROY | 12.99 | 0 | 100
423 | Siliguri W/S Division | Siliguri Sub-Division | Providing functional household tap connection FHTC and laying 90 mm OD HDPE pipe from house of Dulal Biswas to house of Sunil Sikdar and house of Kalipada Mondal to Zamatulla SSK at village Shyamdhan and habitation Shyamdhan and allied worksw of the Shyamdhan piped WS scheme under Siliguri Sub Division PHE Dte Kharibari block. SL. NO. 08. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000082/2021-2022 | 1830/SWSD | 13/01/2022 | 15 | BUDDHADEV NAG | 6.5 | 0 | 100
424 | Siliguri W/S Division | Siliguri Sub-Division | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 100
425 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000011/2021-2022 | 1672/SWSD | 28/12/2021 | 0 | Resource Division | 0.05 | 0 | 0
426 | Siliguri W/S Division | Siliguri Sub-Division | Shifting of LT POLE FOR CONSTRUCTION OF PHE WATER TANK | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00113/2022-2023 | BP-2022-23-142 | 16/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.19 | 0 | 0
427 | Siliguri W/S Division | Siliguri Sub-Division | Laying 15 mm O.D. HDPE and 15 mm dia G.I. Pipe (excess quantity estimate) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapno under command area (village-Shyamdhan habitation-Shyamdhan (Part-B) of Shyamdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000017/2022-2023 | 304/SWSD | 10/05/2022 | 25 | SHIVNATH DEY | 1.55 | 0 | 100
428 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Providing Functional House Hold Tap Connection under Jal Jeevan Mission Programme for PELKU (JL No. 71) and TIKNIKATA (JL No. 74) mouzas of KAWAKHALI Piped Water Supply Scheme at Matigara block under Siliguri W/S Division, P.H.E. Dte.(1st CALL) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000117/2023-2024 | 1196/SWSD | 10/08/2023 | 75 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 74.02 | 0 | 0
429 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection under Jal Swapna Programme for Purba Bansgaon Village of PURBA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART A | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000002/2021-2022 | 696/SWSD | 02/08/2021 | 35 | AKASH ENTERPRISE | 30.21 | 23.08 | 100
430 | Siliguri W/S Division | Siliguri Sub-Division | Laying of new PVC line at along with other repairing works at Matigara Habitation, Purba Bansgaon water supply scheme Phansidewa Block, Siliguri W/S Division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000233/2022-2023 | 512/SSD | 16/11/2022 | 10 | SHIVNATH DEY | 0.36 | 0 | 100
431 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000006/2021-2022 | 1667/SWSD | 28/12/2021 | 0 | Resource Division | 2.13 | 0 | 0
432 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil) | VCH/000761/2021-2022 | 512/DW/21-22 | 18/02/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0
433 | Siliguri W/S Division | Siliguri Sub-Division | ISSUE OF FULE FOR OFFICE VEHICLES OF EXECUTIVWE ENGINEER SILIGURI W/S DIVISION PHE DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00539/2023-2024 | BP-2023-24-184 | 13/03/2024 | 0 | SONA PETROL PUMP | 1.4 | 0 | 0
434 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeevan Mission & Jal Swapno Programme for bharatsing & Putimari of Lalman Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub-Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000014/2021-2022 | 708/SWSD | 03/08/2021 | 90 | M/S UTPAL CHAKRABORTY & CO. | 21.03 | 0 | 100
435 | Siliguri W/S Division | Siliguri Sub-Division | Additional work in connection with Providing FHTC under Jal Jeevan Mission and Jal Swapno Programme for Bharatsing and Putimari of Lalman Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 01. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000121/2021-2022 | 2362/SWSD | 08/03/2022 | 15 | M/S UTPAL CHAKRABORTY & CO. | 6.9 | 0 | 0
436 | Siliguri W/S Division | Siliguri Sub-Division | Continuation order of Hiring of 01 (one) nos Disel Motor CAB on monthly basis for the Assistant Engineer-II, Office of the Executive Engineer under Siliguri W/S Division, P.H.E. Dte. for the month of 01.09.2024 to 28.02.2025. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000184/2024-2025 | 2161/SWSD | 21/08/2024 | 180 | BUDDHADEV NAG | 0.88 | 0 | 0
437 | Siliguri W/S Division | Siliguri Sub-Division | Hiring of I (one) nos Disel Motor CAB on monthly besis for the Assistant Engineer II ,Office of Executive Engineer under Siligui W/S Division, P.H.E Dte..With effect from 25.08.2023 to 24.02.2024 .Total 184 days. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000195/2023-2024 | 1427/SWSD | 24/08/2023 | 184 | BUDDHADEV NAG | 0.88 | 0 | 100
438 | Siliguri W/S Division | Siliguri Sub-Division | Further continuation order for hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of the Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.01.2024 to 31.07.2024 for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte. i.e. 07 (seven) months. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000325/2023-2024 | 2398/SWSD | 16/12/2023 | 213 | HIMADRI DAM | 1.03 | 0 | 0
439 | Siliguri W/S Division | Siliguri Sub-Division | Continuation order of Hiring of I (one) nos Diesel Motor CAB on monthly basis for the Assistant Engineer II ,Office of Executive Engineer under Siligui W/S Division, P.H.E Dte..for the month of 25/02/2024 to 22/08/2024 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000400/2023-2024 | 225/SWSD | 30/01/2024 | 180 | BUDDHADEV NAG | 0.88 | 0 | 0
440 | Siliguri W/S Division |  | Providing Functional Household Tap Connection under Jal Swapno Programme for Rupandighi and Sahananda village of Guabari Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. (Part B). |  |  | ORD/000052/2020-2021 | 1008/SWSD | 11/12/2020 | 30 | UJJWAL ROY | 35.77 | 32.75 | 100
441 | Siliguri W/S Division |  | Providing functional house hold tap connection under Jal Swapno programme for Guabari village of Guabari piped water supply scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. SL. No. 05. |  |  | ORD/000079/2021-2022 | 1827/SWSD | 13/01/2022 | 30 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 23.24 | 0 | 30
442 | Siliguri W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000008/2021-2022 | 1669/SWSD | 28/12/2021 | 0 | Resource Division | 1.87 | 0 | 0
443 | Siliguri W/S Division |  | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. |  |  | VCH/000761/2021-2022 | 512/DW/21-22 | 18/02/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0
444 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional House hold Tap Connection under Jal Swapna Programme for Madhya Bansgaon of MADHYA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART C | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000006/2021-2022 | 692/SWSD | 02/08/2021 | 45 | M/S G.C. CONSTRUCTION & CO. | 38.43 | 0 | 0
445 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional House hold Tap Connection under Jal Swapna Programme for Madhya Bansgaon of MADHYA BANSGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte PART D | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000007/2021-2022 | 693/SWSD | 02/08/2021 | 35 | KAMAL GHOSH | 30.83 | 0 | 35
446 | Siliguri W/S Division | Siliguri Sub-Division | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 100
447 | Neorakhola W/S & Mtc.Div. | Kurseong Division | FOREST PAYMENT | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00760/2023-2024 |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0
448 | Neorakhola W/S & Mtc.Div. | Kurseong Division | FOREST PAYMENT | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00905/2023-2024 | BP-2023-24-497 | 17/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 7.43 | 0 | 0
449 | Neorakhola W/S & Mtc.Div. | Kurseong Division | LOHAGARH WATER SUPPLY SCHEME FROM MANAY KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DARJEELING | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000069/2021-2022 | 459/NKWSMD | 14/01/2022 | 2404 | SHREE VAISHNO ENTERPRISES | 153.57 | 0 | 80
450 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000003/2021-2022 | 637/NKWSMD | 23/02/2022 | 0 | Resource Division | 2.36 | 0 | 0
451 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Soom 2nd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009296 SM Code-SM/08936 |  | Sub-Assistant Engineer | ORD/000059/2022-2023 | 555/NKWSMD | 26/05/2022 | 60 | NAVRATNA CONSTRUCTION CO | 16.91 | 0 | 100
452 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000034/2022-2023 | 1261/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.84 | 0 | 0
453 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000183/2022-2023 | 2575/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.84 | 0 | 0
454 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under JJM & JSP Programme including extension work for PWS Scheme for Dhupi gare, Bloomfield, Gram Panchyat -Rishihat Bloomfield, Block Bijanbari -PullBazar. TSM No. 009472 SM Code-SM/08930 |  | Sub-Assistant Engineer | ORD/000034/2022-2023 | 497/NKWSMD | 24/05/2022 | 222 | KIRAN SUBBA | 13.14 | 0 | 100
455 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000080/2022-2023 | 1362/NKWSMD | 21/09/2022 | 0 | Resource Division | 0.59 | 0 | 0
456 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000182/2022-2023 | 2614/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.59 | 0 | 0
457 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household Tap Connection under JJM & JSP Programme for 8th & 9th M ile , Peshoke Road GP Lamahatta under DARJEELING Division PHED, GTA |  | Sub-Assistant Engineer | VCH/000069/2022-2023 | BP-2022-23-50 | 20/05/2022 | 0 | KIRAN NIROLA | 5.7 | 0 | 0
458 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000001/2020-2021 | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0
459 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000003/2020-2021 | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0
460 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer I,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | BILL/00174/2023-2024 | BP-2023-24-129 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
461 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TWO NOS OF VILLAGES UNDER BLOCK KURSEONG DISTRICT OF DARJEELING [TSM NO - 10476 / 10473] 1. Septiguri Khelaghar tea garden 2. Pairikumari | Assistant Engineer I,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000084/2022-2023 | 608/NKWSMD | 26/05/2022 | 240 | M/S KAMAK ENGINEERS AND CO. | 199.42 | 0 | 100
462 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000158/2022-2023 | 2374/NKWSMD | 03/02/2023 | 0 | Resource Division | 1.8 | 0 | 0
463 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection by Strengthening mainline under Jal Jeevan Mission and Jal Swapno Programme for P.W.S Scheme at Sukhia Bazar, G.P - Sukhia Simana, Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000162/2022-2023 | 938/NKWSMD | 12/07/2022 | 60 | KAMAKHYA ENTERPRISES | 33.83 | 0 | 0
464 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000118/2022-2023 | 1895/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.4 | 0 | 0
465 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000177/2022-2023 | 2577/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.4 | 0 | 0
466 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Marybong GP - Lingia Marybong, Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000167/2022-2023 | 943/NKWSMD | 12/07/2022 | 903 | MANI KUMAR CHHETRI | 18.47 | 0 | 100
467 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000041/2022-2023 | 1268/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.48 | 0 | 0
468 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000130/2022-2023 | 1906/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.48 | 0 | 0
469 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000190/2022-2023 | 2590/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.48 | 0 | 0
470 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Bijuwa Gaon Pulundung GP - Pulundung, Block - Jorebungalow Sukhia |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000163/2022-2023 | 939/NKWSMD | 12/07/2022 | 60 | KIRAN NIROLA | 12.21 | 0 | 0
471 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000040/2022-2023 | 1267/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.39 | 0 | 0
472 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000132/2022-2023 | 1908/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.39 | 0 | 0
473 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000194/2022-2023 | 2591/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.39 | 0 | 0
474 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
475 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface Water Based Upper Mamring Piped Water Supply Scheme to accmmodate FHTC in Kurseong Block within Darjeeling District under Kurseong Sub-Division, P.H.E.D-G.T.A | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000145/2022-2023 | 836/NKWSMD | 30/06/2022 | 90 | AJAY RAI | 89.52 | 0 | 85
476 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000141/2022-2023 | 2061/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.94 | 0 | 0
477 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Deorali Chimney (North Shibkhola habitation) under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000147/2022-2023 | 838/NKWSMD | 30/06/2022 | 60 | SONAM LAMA | 9.28 | 0 | 45
478 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000046/2022-2023 | 1290/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.77 | 0 | 0
479 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Siresay Ambotia (Sirasay habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000117/2022-2023 | 797/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 9.35 | 0 | 100
480 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000056/2022-2023 | 1300/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.74 | 0 | 0
481 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Malotar T.E. Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000130/2022-2023 | 810/NKWSMD | 30/06/2022 | 60 | NARESH RAI | 17.84 | 0 | 0
482 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000059/2022-2023 | 1303/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.96 | 0 | 0
483 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for Piped Water Supply Scheme at Chandraman Gaon Gram Panchyat Paila Goan S D- 2 Block- Mirik TSM No. 009302 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000125/2022-2023 | 805/NKWSMD | 30/06/2022 | 915 | MS. SURYA I PVT. LTD COMPANY | 18.95 | 0 | 100
484 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000069/2022-2023 | 1313/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.34 | 0 | 0
485 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Krish Kunj: Gram Panchyat Duptin 10, Block - Mirik TSM No. 009481 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000127/2022-2023 | 807/NKWSMD | 30/06/2022 | 60 | BIKASH LAMA | 5.52 | 0 | 0
486 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Chotta Tingling: Gram Panchyat- Soureni-II , Block Mirik TSM No. 009480 | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000017/2022-2023 | 787/NKWSMD | 30/06/2022 | 60 | MAHENDRA ADHIKARI | 7.72 | 0 | 100
487 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SINGLA PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKHIAPOKRI DISTRICT-DARJEELING. |  | Sub-Assistant Engineer | ORD/000009/2025-2026 | 495/NKWSMD | 09/04/2025 | 180 | DAJUBHAI CONSTRUCTION | 88.19 | 0 | 0
488 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FROM SINGLA TEA GARDEN UNDER DARJEELING DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, G.T.A |  | Sub-Assistant Engineer | ORD/000226/2022-2023 | 1289/NKWSMD | 08/09/2022 | 995 | VINAYAK CONSTRUCTION | 280.33 | 0 | 100
489 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000109/2022-2023 | 1886/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.6 | 0 | 0
490 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000168/2022-2023 | 2605/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.6 | 0 | 0
491 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Rangaroong T.G water supply scheme Under Jal Jeewan Mission Detail - (SW No. : SW/111753/2022) |  | Sub-Assistant Engineer | BILL/00393/2024-2025 | "BP-2024-25-293 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.38 | 0 | 0
492 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Rageroong Tea Estate for water supply scheme under Darjeeling Division,PHED-GTA. |  | Sub-Assistant Engineer | ORD/000121/2023-2024 | 862/NKWSMD | 31/07/2023 | 790 | KUNCHAN JUNGA ENTERPRISES | 30.33 | 0 | 100
493 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RANGAROONG TEA GARDEN PWSS, BLOCK: JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT: DARJEELING.(TSM/012508) |  | Sub-Assistant Engineer | ORD/000251/2022-2023 | 1529/NKWSMD | 18/10/2022 | 830 | KUNCHAN JUNGA ENTERPRISES | 272.77 | 0 | 100
494 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000115/2022-2023 | 1892/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.64 | 0 | 0
495 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000174/2022-2023 | 2611/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.64 | 0 | 0
496 | Siliguri W/S Division | Siliguri Sub-Division | Issue of fuel for Office of the Executive Engineer and Assistant Engineers of Siliguri W/S Division, PHE Dte. from 17th March 2024 to 30th May 2024 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00124/2024-2025 | BP-2024-25-41 | 08/07/2024 | 0 | SONA PETROL PUMP | 1.87 | 0 | 0
497 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeeven Mission & Jal SWapno Programme for Lalman Mouza (Part) of Lalman Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub-Division, P.H.E. Dte. (Part-A) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000012/2021-2022 | 706/SWSD | 03/08/2021 | 120 | RAJEEV RANJAN OJHA | 32.5 | 13.11 | 43
498 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional House Hold Tap Connection under Jal Jeevan Mission & Jal Swapno Programme for Lalman mouza (Part) of Lalman W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000128/2021-2022 | 1009/SWSD | 10/09/2021 | 15 | SEBU CHAKRABORTY | 4.84 | 0 | 100
499 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Improvement of Existing FHTC with existing pipelines for Rejuvenation of Paschim Madati PWSS under Jal Jeeban Mission (JJM) at Phansidewa Block within Siliguri Sub- Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000015/2025-2026 | 1241/SWSD | 24/04/2025 | 30 | AKASH ENTERPRISE | 16.03 | 0 | 0
500 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, Rig bored big dia deep T/W by Odex-165 method of drilling, boundary wall, laying distribution system, providing functional house hold tap connection (FHTC) and supplying, fabrication, erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (40 cum./hr) required platform and drain etc. for rejuvenation of Paschim Madati Piped Water Supply Scheme at Phanshidewa block under Siliguri Sub Division, PHE Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000268/2022-2023 | 2366/SWSD | 24/01/2023 | 799 | AKASH ENTERPRISE | 67.76 | 0 | 100
501 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000051/2022-2023 | 2031/SWSD | 16/12/2022 | 0 | Resource Division | 0.98 | 0 | 0
502 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for Rejuvenation of Paschim Madati, TW No. I, BIDHANNAGAR CCC, [APPLICATION NO. 4003143720, Reference ID : 803008623] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00031/2023-2024 | BP/23-24/08 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0
503 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PASCHIM MADATI PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000050/2023-2024 | 529/NMD | 10/05/2023 | 30 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 11.64 | 0 | 90
504 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCEME FOR TAMSANG TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING (TSM/011759). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000043/2025-2026 | 648/NKWSMD | 05/05/2025 | 60 | DAJUBHAI HARDWARE | 23.02 | 0 | 0
505 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000052/2024-2025 | 386/NKWSMD | 31/05/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 100
506 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme for Tamsang Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000264/2022-2023 | 1562/NKWSMD | 21/10/2022 | 845 | VINAYAK CONSTRUCTION | 736.38 | 0 | 100
507 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000120/2022-2023 | 1897/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.25 | 0 | 0
508 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000179/2022-2023 | 2578/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.25 | 0 | 0
509 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum Work Order for Construction of Boundary Wall at H/W & 2nd T/W Site Augmentation RANGALI PWSS SCHEME Block Kharibari under Siliguri W/S Division PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000019/2025-2026 | 1361/SWSD | 05/05/2025 | 30 | S.G.CONSTRUCTION | 18.14 | 0 | 0
510 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF RANGALI PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000061/2023-2024 | 254/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.77 | 0 | 100
511 | Siliguri W/S Division | Siliguri W/S Division | Construction of l00 cu.m. capacity RCC Elevated Reseervoir, 20 mtrs. Staging height at the head works site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of 2 (two) nos. pump house (5.40 X 3.60 m), Iron elimination plant (IEP) with blower room, sinking of 2 (two) nos. tubewell (ODEX-165 method) and soil investigation at H/W site for RANGALI PWSS, block : Kharibari, Dist. Darjeeling under Siliguri W/S Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000316/2022-2023 | 2918/SWSD | 24/03/2023 | 739 | M/S BIRAT CONSTRUCTION | 217.11 | 0 | 10
512 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000057/2022-2023 | 2037/SWSD | 16/12/2022 | 0 | Resource Division | 13.5 | 0 | 0
513 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for RANGALI, T/W II, under KHARIBARI CCC [APPLICATION NO. 4003208340 ; Reference ID : 403057204] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00992/2023-2024 | BP/23-24/95 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.16 | 0 | 0
514 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for RANGALI, T/W I, under KHARIBARI CCC [APPLICATION NO. 4003208350 ; Reference ID : 403057203] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00994/2023-2024 | BP/23-24/95 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.11 | 0 | 0
515 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
516 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RANGALI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000782/2023-2024 | 1646/NMD | 29/09/2023 | 498 | TAPAN BISWAS | 10.99 | 0 | 100
517 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0
518 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/001069/2024-2025 | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0
519 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution of HDPE pipe line, sluice valve chamber, construction of boundary wall including drain & paver block pathway for Augmentation at Bairagi Water Supply Scheme, 2nd tubewell site of Khoribari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000040/2023-2024 | 644/SWSD | 15/06/2023 | 690 | M/S SHIVAJI ROY | 22.4 | 0 | 40
520 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000007/2023-2024 | 206/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0
521 | Northern Mechanical | Siliguri W/S Division | Quotation Charges for New Service Connection at Bairagi PWSS,TW-I under NMD PHE Dte. Application No- 4003340167 Ref ID- 403162856 | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | BILL/01009/2024-2025 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.69 | 0 | 0
522 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRAGI PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000450/2023-2024 | 1389/NMD | 09/08/2023 | 581 | M/S ANJALI ENTERPRISE | 12.38 | 0 | 100
523 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Base Water Supply Scheme for Senchal-I under Jal Jeevan Mission Detail - (SW No. : SW/145710/2023) |  | Junior Engineer-V | BILL/00389/2024-2025 | BP-2024-25-452 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 5.7 | 0 | 0
524 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Based water supply scheme for Senchal-2 under JAl JEEWAN MISSION. Detail - (SW No. : SW/145709/2023) |  | Junior Engineer-V | BILL/00390/2024-2025 |  | 20/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0
525 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission Detail - (SW No. : SW/145713/2023) WEST BENGAL , DARJEELING |  | Junior Engineer-V | BILL/00391/2024-2025 |  | 20/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0
526 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Base Water Supply Scheme for Senchal III under Jal Jeevan Mission |  | Junior Engineer-V | BILL/00645/2024-2025 | BP-2024-25-454 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.86 | 0 | 0
527 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity based water supply scheme for Senchal - 2 under JAL JEEWAN MISSION DETAILS (SW/145709/2023) |  | Junior Engineer-V | BILL/00646/2024-2025 | BP-2024-25-456 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.24 | 0 | 0
528 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | DETAILED PROJECT REPORT FOR GRAVITY BASED WATER SUPPLY SCHEME FOR SENCHAL FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-V | ORD/000018/2023-2024 | 118/NKWSMD | 28/04/2023 | 974 | SUMAN THAKURI | 483 | 0 | 70
529 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-V | RTOR000006/2023-2024 | 153/NKWSMD | 03/05/2023 | 0 | Resource Division | 2.42 | 0 | 0
530 | Neorakhola W/S & Mtc.Div. |  | PAYMENT FOR WBSEDCL |  |  | BILL/00758/2023-2024 | BP-2023-24-503 | 17/02/2024 | 0 | WBSEDCL | 5.5 | 0 | 0
531 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR GOPALDHARA TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000040/2023-2024 | 223/NKWSMD | 10/05/2023 | 842 | GREENPRO ENGINEERING | 1051.51 | 0 | 100
532 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 326/NKWSMD | 24/05/2023 | 0 | Resource Division | 4.87 | 0 | 0
533 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme For Lower Bansbotay & Lower Lingsay Bong Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000057/2023-2024 | 415/NKWSMD | 05/06/2023 | 180 | HARI PRASAD CHETTRI | 287.97 | 0 | 80
534 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000048/2023-2024 | 443/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.38 | 0 | 0
535 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Additional work (F.H.T.C & LDS) at adjoining mouzas under JJM/Jal Swapna in connection with AUGMENTATION of OMI PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri W/S Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000008/2025-2026 | 1234/SWSD | 24/04/2025 | 30 | NARAYAN CH GHOSH | 2.72 | 0 | 0
536 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum work order for laying of rising main, distribution system of pipeline, construction of pump houses, boundary wall, sinking of Rig bore deep tube well by Odex-165 method of drilling, development of land and other allied works for Augmentation of OMI Piped W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Dist-Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000172/2023-2024 | 1734/SWSD | 22/09/2023 | 551 | NARAYAN CH GHOSH | 65.91 | 0 | 80
537 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
538 | Central Drilling | Siliguri Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). (Phase-X) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000031/2024-2025 | 563/CDD | 07/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0
539 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for OMI, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003299978 ; Reference ID : 403131329] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01743/2023-2024 | BP/23-24/226 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.15 | 0 | 0
540 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for OMI, T/W No. II, under NAXALBARI CCC [APPLICATION NO. 4003300005 ; Reference ID : 403131330] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01744/2023-2024 | BP/23-24/227 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.79 | 0 | 0
541 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF OMI PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000817/2023-2024 | 1672/NMD | 29/09/2023 | 395 | M/S MATRI CONSTRUCTION | 10.37 | 0 | 100
542 | Siliguri W/S Division | Siliguri Sub-Division | Part work order for construction the boring of ODEX 165 tubewell, laying distribution, iron elimination plant, pump house, boundary wall, TW all complete under Augmentation of Guabari Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000329/2023-2024 | 676/SWSD | 14/03/2024 | 746 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 52.8 | 0 | 45
543 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000008/2023-2024 | 207/SWSD | 25/04/2023 | 0 | Resource Division | 0.79 | 0 | 0
544 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for GUABARI, T/W No. I, under PHANSIDAWA CCC, [APPLICATION NO. 4003325453, Reference ID : 403153288] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | BILL/01964/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.39 | 0 | 0
545 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF GUABARI PIPED WATER SUPPLY SCHEME, TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000462/2023-2024 | 1438/NMD | 10/08/2023 | 752 | S.D. CONCERN | 10.38 | 0 | 90
546 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0
547 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RIMBICK PIPED WATER SUPPLY SCHEME IN DARJEELING-PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000082/2023-2024 | 681/NKWSMD | 12/07/2023 | 781 | NIMA SHERPA | 699.58 | 0 | 90
548 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Piped water supply scheme for Rimbick & Namla under Darjeeling Pulbazar Block, Darjeeling Division, PHED, G.T.A. |  | Sub-Assistant Engineer | ORD/000247/2023-2024 | 87/NKWSMD | 11/01/2024 | 90 | NIMA SHERPA | 27.05 | 0 | 100
549 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000074/2023-2024 | 757/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.77 | 0 | 0
550 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHAINPURAY PIPED WATER SUPPLY SUPPLY IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000081/2023-2024 | 680/NKWSMD | 12/07/2023 | 797 | VAISHNO CONSTRUCTION | 80.25 | 0 | 100
551 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000068/2023-2024 | 755/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.86 | 0 | 0
552 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000025/2023-2024 | 124/NKWSMD | 28/04/2023 | 360 | DENDUP BHUTIA AND COMPANY | 255.41 | 0 | 100
553 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Strengthening of mainline of water supply scheme at Majua (Singhbumdera) under Darjeeling Division, PHED-GTA. |  | Sub-Assistant Engineer | ORD/000118/2023-2024 | 861/NKWSMD | 31/07/2023 | 60 | RISHI KESH THAKURI | 28.53 | 0 | 100
554 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000024/2023-2024 | 243/NKWSMD | 12/05/2023 | 0 | Resource Division | 1.08 | 0 | 0
555 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | ORD/000017/2023-2024 | 117/NKWSMD | 28/04/2023 | 815 | VINAYAK CONSTRUCTION | 1144.27 | 0 | 5
556 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR MAKAIBARI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK- KURSEONG DISTRICT-DARJEELING KURSEONG DIVISION PHED/GTA | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | ORD/000036/2025-2026 | 652/NKWSMD | 05/05/2025 | 90 | MAGMA CONSORTIUM | 30.47 | 0 | 0
557 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Junior Engineer7,Sub-Assistant Engineer | RTOR000008/2023-2024 | 155/NKWSMD | 03/05/2023 | 0 | Resource Division | 4.98 | 0 | 0
558 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED NAHORI TEA GARDEN (BALASOM) (PART) PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7 | ORD/000339/2022-2023 | 2736/NKWSMD | 03/03/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 659.52 | 0 | 85
559 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7 | RTOR000261/2022-2023 | 2772/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.03 | 0 | 0
560 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000055/2025-2026 | 820/NKWSMD | 09/06/2025 | 60 | M/S S S CONSTRUCTION | 14.61 | 0 | 0
561 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SIMRING TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK KURSEONG UNDER DISTRICT DARJEELING. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000084/2023-2024 | 683/NKWSMD | 12/07/2023 | 420 | M/S S S CONSTRUCTION | 417.8 | 0 | 50
562 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000076/2023-2024 | 764/NKWSMD | 19/07/2023 | 0 | Resource Division | 1.84 | 0 | 0
563 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA. SCHEME CODE - 15647 TSM/017747 | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00091/2024-2025 | "BP-2024-25-100 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 13.99 | 0 | 0
564 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SUKNA PRATHAM KHANDA TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000377/2022-2023 | 2873/NKWSMD | 23/03/2023 | 695 | RESILIENCE INFRASTRUCTURE PRIVATE LIMITED | 488.43 | 0 | 52
565 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000269/2022-2023 | 2892/NKWSMD | 29/03/2023 | 0 | Resource Division | 6.38 | 0 | 0
566 | Kurseong Division | Kurseong Division | Work Order for proposals to frame and put up for Forest land clearance for land parcels through PARIVESH portal of MOEF GOI, Kurseong under Kurseong division, PHED,GTA | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000001/2023-2024 | 515/EE/KD/PHED | 22/11/2023 | 10 | HILL GROUND CONSULTANCY | 0.96 | 0 | 100
567 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
568 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED NORTH & SOUTH SHIBKHOLA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000162/2023-2024 | 910/NKWSMD | 11/08/2023 | 570 | AROGYA ENTERPRISES | 1336.08 | 0 | 95
569 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000094/2023-2024 | 958/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.92 | 0 | 0
570 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-RANGLI RANGLIOT DISTRICT-DARJEELING. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000034/2025-2026 | 649/NKWSMD | 05/05/2025 | 180 | MAGMA CONSORTIUM | 74.02 | 0 | 0
571 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROVIDING FHTC UNDER JAL JEEVAN MISSION FOR BALANCE HOUSEHOLD AT 9TH MILE (MAMTA PARK LAMAHATTA) PESHOKE ROAD, LAMAHATTA UNDER DARJEELING DIVISION, P.H.E DEPTT, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000175/2023-2024 | 934/NKWSMD | 16/08/2023 | 60 | PUSHKAR GURUNG | 13.64 | 0 | 100
572 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PESHOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000185/2023-2024 | 949/NKWSMD | 17/08/2023 | 1095 | VINAYAK CONSTRUCTION | 956.42 | 0 | 80
573 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000097/2023-2024 | 961/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.15 | 0 | 0
574 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF KAWAKHALI PIPED WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000069/2023-2024 | 262/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 4.02 | 0 | 100
575 | Siliguri W/S Division | Siliguri W/S Division | Construction of 250 cu.m. Capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site (Zone-II), including Rising Mains, Distribution System Providing Functional household Tapn Connection (FHTC), Iron Elimination Plant (IEP) with Blower Room, Boundary wall & Soil Investigation at H/W site (Zone-II) for Augmentation of KAWAKHALI (Zone-I, II & III) Piped Water Supply Scheme Block : Matigara under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000122/2023-2024 | 1230/SWSD | 14/08/2023 | 687 | FAIRDEAL ASSOCIATES | 827.38 | 0 | 25
576 | Siliguri W/S Division | Siliguri W/S Division | CONSTRUCTION OF PATHWAY & LAND DEVOLOPMENT FOR KAWAKHALI ZONE-I , II & III PIPED WATER SUPPLY SCHEME (H/W SITE & 2ND T/W SITE) BLOCK MATIGARA DISTRICT : DARJEELING UNDER SILIGURI W/S DIVISION P.H.E.Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000155/2024-2025 | 2846/SWSD | 23/10/2024 | 30 | FAIRDEAL ASSOCIATES | 19.13 | 0 | 0
577 | Siliguri W/S Division | Siliguri W/S Division | ACCEPTANCE CUM WORK ORDER FOR CONSTRUCTION OF BOUNDARY WALL AT EXISTING PUMP HOUSE (two nos)FOR KAWA KHALI W/S SCHEME UNDER SILIGURI WATER SUPPLY DIVISION PHE DTE.(CONSIDERING A LENGTH OF 70 METRE) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000239/2024-2025 | 193/SWSD | 16/01/2025 | 45 | RAJEEV RANJAN OJHA | 8.04 | 0 | 0
578 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000018/2023-2024 | 1802/SWSD | 30/09/2023 | 0 | Resource Division | 59.09 | 0 | 0
579 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for AUG. OF KAWAKHALI, T/W No. III, under PHANSIDEWA CCC, [APPLICATION NO. 4003317469, Reference ID : 403145877] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01975/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.98 | 0 | 0
580 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for AUG KAWAKHALI, T/W No. I, under PHANSIDAWA CCC, [APPLICATION NO. 4003320233, Reference ID : 403148653] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01976/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.61 | 0 | 0
581 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for AUG KAWAKHALI, T/W No.II, under PHANSIDAWA CCC, [APPLICATION NO. 4003320218, Reference ID : 403148651] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01977/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.1 | 0 | 0
582 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KAWAKHALI PIPED WATER SUPPLY SCHEME, (Zone-II) TW No. I, II and (Zone-III) TW-I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000463/2023-2024 | 1439/NMD | 10/08/2023 | 604 | ALPHA ENTERPRISE | 47.79 | 0 | 75
583 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0
584 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/001066/2024-2025 | 34/NMD | 06/01/2025 | 30 | PRATIK ROY | 9.2 | 0 | 0
585 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection with retrofitting the existing distribution networks under Jal Swapno Programme for PWS scheme at Kataray forest Busty Gram Panchyat-Soureni-II, Block- Mirik TSM No. 009305 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000013/2022-2023 | 785/NKWSMD | 30/06/2022 | 60 | MAHENDRA ADHIKARI | 7.66 | 0 | 100
586 | Neorakhola W/S & Mtc.Div. |  | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical works like Intake, WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for Water Supply Scheme for Darjeeling Pulbazar Pumping - I Spring Water Supply Scheme followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000101/2024-2025 | 1567/NKWSMD | 03/09/2024 | 546 | DARA ENGINEERING & INFRASTRUCTURES PRIVATE LIMITED | 15881.1 | 0 | 5
587 | Neorakhola W/S & Mtc.Div. |  | (Continuation) Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate for the period from January 2025 to June 2025. |  |  | ORD/000217/2024-2025 | 2412/NKWSMD | 31/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 0
588 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000127/2023-2024 | 51/NKWSMD | 09/01/2024 | 0 | Resource Division | 22.53 | 0 | 0
589 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
590 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00096/2024-2025 | BP-2024-25-88 | 08/07/2024 | 0 | WBSEDCL | 17.08 | 0 | 0
591 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00280/2024-2025 | BP-2024-25-220 | 28/08/2024 | 0 | WBSEDCL | 5.43 | 0 | 0
592 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK P.H.E-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000030/2025-2026 | 639/NKWSMD | 05/05/2025 | 180 | SHAKTI CONSTRUCTION | 87.36 | 0 | 0
593 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED MARMA TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000168/2023-2024 | 921/NKWSMD | 11/08/2023 | 365 | SHAKTI CONSTRUCTION | 1126.3 | 0 | 90
594 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000092/2023-2024 | 971/NKWSMD | 21/08/2023 | 0 | Resource Division | 7.21 | 0 | 0
595 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SINGEL TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000172/2023-2024 | 914/NKWSMD | 11/08/2023 | 815 | M/S. ASHOK KUMAR PERIWAL | 958.42 | 0 | 80
596 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000107/2023-2024 | 968/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.15 | 0 | 0
597 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 150 cu.m. Overhead reservoir, 2 nos. Odex-165 Tubewell, laying distribution, Iron Elimination Plant, Pump House, boundary wall, TW and FHTC all complete under Augmentation of MADHYA BANSGAON (Zone-I) Piped Water Supply Scheme and Construction of 350 cu.m. overhead reservoir, 1 no. Odex-165 Tubewell, laying distribution, Iron Elimination Plant, Pump House, boundary wall, TW and FHTC all complete under Augmentation work of MADHYA BANSGAON (Zone-II) Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000104/2023-2024 | 1130/SWSD | 07/08/2023 | 482 | UNIBRO INFRASERV PRIVATE LIMITED | 869.38 | 0 | 19
598 | Siliguri W/S Division | Siliguri Sub-Division | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 100
599 | Siliguri W/S Division | Siliguri Sub-Division | FURTHER ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2023 TO 31.08.2023 (FOR ASSISTANT ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. 6 (SIX) MONTHS. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000336/2022-2023 | 2642/SWSD | 01/03/2023 | 184 | HIMADRI DAM | 0.88 | 0 | 100
600 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000028/2022-2023 | 1458/SWSD | 29/09/2022 | 0 | Resource Division | 6.05 | 0 | 0
601 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000081/2022-2023 | 2060/SWSD | 16/12/2022 | 0 | Resource Division | 65.06 | 0 | 0
602 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
603 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MADHYA BANSGAON, T/W No. I, ZONE-I, under PHANSIDEWA CCC [APPLICATION NO. 4003305873 ; Reference ID : 403135372] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01815/2023-2024 | BP/23-24/275 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.96 | 0 | 0
604 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MADHYA BANSGAON , T/W No. I , ZONE-II, under PHANSIDAWA CCC, [APPLICATION NO. 4003317715, Reference ID : 403145870] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01940/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.84 | 0 | 0
605 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MADHYA BANSGAON , T/W No. II , ZONE-I, under PHANSIDAWA CCC, [APPLICATION NO. 4003317696, Reference ID : 403145882] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01941/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.53 | 0 | 0
606 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MADHYA BANSGAON PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,II and (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000788/2023-2024 | 1652/NMD | 29/09/2023 | 702 | M/S SWAPAN BANERJEE | 22.53 | 0 | 100
607 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR MALDIRAM FOREST PART, ST MARYS PART, UPPER LANKU & UPPER ROLAK PART, SIMRING TEA GARDEN PART, CHANDU BUSTY GIDHE PAHAR PART PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. |  |  | ORD/000108/2024-2025 | 1746/NKWSMD | 19/09/2024 | 365 | DAJUBHAI CONSTRUCTION | 861.59 | 0 | 80
608 | Neorakhola W/S & Mtc.Div. |  | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
609 | Siliguri W/S Division | Siliguri Sub-Division | Issue of fuel for office vehicles of Executive Engineer and Assistant Engineers of Siliguri W/S Division and Siliguri Sub division, PHE Dte. for the period form 01.06.2024 to 13.07.2024 | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00158/2024-2025 | BP-2024-25-62 | 02/08/2024 | 0 | SONA PETROL PUMP | 0.98 | 0 | 0
610 | Siliguri W/S Division | Siliguri Sub-Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
611 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Badang, Pakridhuka, Sapti and Jayantyika 318 Nos house hold) of Purba Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000066/2020-2021 | 1080/SWSD | 18/12/2020 | 35 | SUBIR CH. CHOWDHURY | 30.22 | 24.34 | 100
612 | Siliguri W/S Division | Siliguri Sub-Division | Providing functional house hold tasp connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapno) under command area (Habitation Badang Jayantika Sapti Alim Ganj & Chowdhury Gachh) due to Y.D.U of Purba Madati Piped water supply scheme at Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000080/2021-2022 | 1828/SWSD | 13/01/2022 | 25 | BIMAN DUTTA | 10.38 | 0 | 20
613 | Siliguri W/S Division | Siliguri Sub-Division | Continuation order for Supply of 01 (one) no. Maxi Cab with Engine Capacity less than or equal to 2000 C.C. with Air Condition on hire basis (for monthly hiring) including driver under Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte. (With valid Taxi permit and other necessary documents as per norms of Zonal R.T.O) For 03 (three months) with effect from 01.01.2025 to 31.03.2025. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000264/2024-2025 | 3610/SWSD | 31/12/2024 | 90 | S S CONSTRUCTIONS | 0.47 | 0 | 0
614 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000009/2021-2022 | 1670/SWSD | 28/12/2021 | 0 | Resource Division | 1.42 | 0 | 0
615 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil) | VCH/000307/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 0.56 | 0 | 0
616 | Siliguri W/S Division | Siliguri Sub-Division | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 100
617 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000031/2022-2023 | 1461/SWSD | 29/09/2022 | 0 | Resource Division | 6.01 | 0 | 0
618 | Siliguri W/S Division | Siliguri W/S Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
619 | Siliguri W/S Division | Siliguri W/S Division | Laying Distribution System (Part-B) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-B) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000002/2022-2023 | 36/SWSD | 07/04/2022 | 100 | VIJAY KUMAR ARORA | 198.7 | 0 | 95
620 | Siliguri W/S Division | Siliguri W/S Division | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) of Distribution Pipeline (Part-D) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000003/2022-2023 | 35/SWSD | 07/04/2022 | 90 | ANUP BASU | 123.58 | 0 | 0
621 | Siliguri W/S Division | Siliguri W/S Division | Construction of Pump House(3.6 X 3.0 m), at Kalam 4th Site under Augmentation of Kalam piped water supply Scheme under Matigara Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000017/2023-2024 | 194/SSD | 04/05/2023 | 45 | K.K.GHOSH & CO. | 4.75 | 0 | 95
622 | Siliguri W/S Division | Siliguri W/S Division | Constuction of Pump House (3.6*3.0m) at Kalam 3rd site under Augmentation of Kalam piped water supply scheme under Matigara Block Darjeeling district in connection with Jal jeevan Mission under Siliguri Sub-division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000021/2023-2024 | 268/SSD | 05/06/2023 | 45 | K.K.GHOSH & CO. | 4.75 | 0 | 100
623 | Siliguri W/S Division | Siliguri W/S Division | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connecetion (FHTC) at Distribution Pipeline (Part-C) of Kalam and Adjoining Moujas Water Supply Scheme within Matigara Block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000103/2021-2022 | 2081/SWSD | 03/02/2022 | 336 | KAMAL GHOSH | 63.4 | 0 | 92
624 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000166/2022-2023 | 1326/SWSD | 14/09/2022 | 45 | M/S NIRANJAN SARKAR | 46.36 | 0 | 100
625 | Siliguri W/S Division | Siliguri W/S Division | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 28.02.2023 (FOR ASSISTANT ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. SIX MONTHS. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000197/2022-2023 | 1236/SWSD | 31/08/2022 | 181 | HIMADRI DAM | 0.88 | 0 | 100
626 | Siliguri W/S Division | Siliguri W/S Division | `Continuation of Hiring of 1(one) no. diesel consumed vehicle on monthly basis preferably Maxi Cab (with A/C) for O/O the Assistant Engineer, Siliguri Sub Division, P.H.E Dte. from 1.03.2022 to 31.08.2022 (with Engine Capacity less than or equal to 2000 CC) Vehicle no. WB76A 4921) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000220/2021-2022 | 112/SSD | 28/02/2022 | 184 | SUDIP BASAK | 0.88 | 0 | 100
627 | Siliguri W/S Division | Siliguri W/S Division | Work Order for Construction of 200 Cu.M capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head works site including rising mains and distribution system (Part-A) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-A) of Kalam & adjoining mouza's water supply scheme within Matigara block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000236/2023-2024 | 2354/SWSD | 15/12/2023 | 807 | SHRI ANNAPURNA DISTRIBUTORS | 156.84 | 0 | 50
628 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for construction of blower room, iron elimination plant, boundary wall at Kalam Piped Water Supply Scheme under Matigara block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000250/2023-2024 | 35/SWSD | 08/01/2024 | 754 | SUBIR CH. CHOWDHURY | 63.98 | 0 | 60
629 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000017/2022-2023 | 1447/SWSD | 29/09/2022 | 0 | Resource Division | 13.8 | 0 | 0
630 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000020/2021-2022 | 2178/SWSD | 11/02/2022 | 0 | Resource Division | 84.79 | 0 | 0
631 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | VCH/000303/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 18.84 | 0 | 0
632 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | VCH/000896/2021-2022 | BP-2021-22-114 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 64.05 | 0 | 0
633 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KALAM, T/W III, under SHIVMANDIR CCC [APPLICATION NO. 4003119111 ; Reference ID : 402986652] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00004/2023-2024 | BP/23-24/03 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0
634 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KALAM, T/W II, under SHIVMANDIR CCC [APPLICATION NO. 4003119079 ; Reference ID : 402986632] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00005/2023-2024 | BP/23-24/03 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.79 | 0 | 0
635 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KALAM PIPED WATER SUPPLY SCHEME , TW No II & III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000056/2023-2024 | 551/NMD | 15/05/2023 | 30 | SARKAR ELECTRIC | 23.37 | 0 | 100
636 | Northern Mechanical | Siliguri W/S Division | Supply & delivery of CIDF Specials Under JJM project at Kalam W/S Scheme in the dist of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/001643/2023-2024 | 383/SMSD | 07/03/2024 | 7 | B.B. CONCERNED | 0.9 | 0 | 100
637 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional House hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Fakna mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000047/2021-2022 | 1218/SWSD | 01/11/2021 | 20 | U.K CONSTRUCTIONS | 14.99 | 0 | 80
638 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Birsing mouza of Birsing Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte. Sl. No. 11. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000050/2021-2022 | 1221/SWSD | 01/11/2021 | 35 | M/S MATRI CONSTRUCTION | 31.13 | 0 | 100
639 | Siliguri W/S Division | Siliguri Sub-Division | HIRING OF 1 (ONE) NO. WELL MAINTAINED DIESEL CONSUMED LUXURY CAB ON MONTHLY HIRED BASIS PREFERABLY MAXI CAB (A/C) WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC FOR OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHER ZONE, P.H.E. DTE. VIVEKANANDA BHAWAN (2ND FLOOR) HILL CART ROAD, SILIGURI (FOR ASSISTANT CHIEF ENGINEER, NORTHERN ZONE (CIVIL), P.H.E. DTE. FOR THE PERIOD FROM 01.09.2022 TO 31.10.2022 i.e. 2 (TWO) MONTHS. | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00067/2022-2023 | BP-2022-23-131 | 20/02/2023 | 0 | OM TRAVELS | 1.08 | 0 | 0
640 | Siliguri W/S Division | Siliguri Sub-Division | Continuation of hiring of 1 (one) no. diesel consumed on monthly basis preferably Maxi Cab (With A/C) for O/O the assistant Engineer Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00110/2023-2024 | BP-2023-24-41 | 28/07/2023 | 0 | SUDIP BASAK | 2.24 | 0 | 0
641 | Siliguri W/S Division | Siliguri Sub-Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
642 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 400 cu.m. capacity RCC Over Head Reservoir, 20 mtrs Staging height and rising mains with laying distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-A) of Lohugaon (Zone-I) and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. Sl. No. 07. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000062/2022-2023 | 867/SWSD | 21/07/2022 | 1218 | PALLAB BHOWAL | 159.67 | 0 | 70
643 | Siliguri W/S Division | Siliguri Sub-Division | Soil Investigation of Lahugaon Z I PWSS for Construction of 400 cum OHR under Siliguri Sub-Division P.H.E. Dte under Phansidewa Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000092/2022-2023 | 389/SSD | 20/07/2022 | 20 | M/S PRANTIK ASSOCIATES | 1.02 | 0 | 100
644 | Siliguri W/S Division | Siliguri Sub-Division | Soil Investigation of Lahugaon Z II PWSS for Construction of 300 cum OHR under Siliguri Sub-Division P.H.E. Dte under Phansidewa Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000093/2022-2023 | 390/SSD | 20/07/2022 | 20 | D.P. ENTERPRISE | 1.03 | 0 | 100
645 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-B) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-B) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000133/2021-2022 | 2430/SWSD | 21/03/2022 | 1427 | SUBIR CH. CHOWDHURY | 64.88 | 0 | 65
646 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-C) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-C) of Lahugaon (Zone-1) and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 03. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000134/2021-2022 | 2431/SWSD | 21/03/2022 | 1382 | AKASH ENTERPRISE | 53.99 | 0 | 60
647 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-D) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-D) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000135/2021-2022 | 2432/SWSD | 21/03/2022 | 50 | M/S FULBARI CONSTRUCTION CO. | 53.41 | 0 | 65
648 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-F) allied with providing functional household tap connection (FHTC) under Jal Swapno and Jal Jeevan Mission at distribution pipeline (Part-F) of Lahugaon and adjoining mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000136/2021-2022 | 2433/SWSD | 21/03/2022 | 45 | BUDDHADEV NAG | 49.84 | 0 | 60
649 | Siliguri W/S Division | Siliguri Sub-Division | Supplying. Fabrication, Erection of IRON ELEMINATION PLANT at Lohugaon (Z-1) and construction of Blower Room at pump house site at Lohugaon water Supply Scheme Under Siliguri Sub division, P.H.E DTE. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000138/2024-2025 | 2532/SWSD | 13/09/2024 | 30 | PALLAB BHOWAL | 15.2 | 0 | 0
650 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 300 cum capacity Over Head Reservoir, Laying Distribution System with Providing Functional Household Tap Connection (FHTC), construction of Rig Bore Big Dia Deep Tubewells (H/W, 2nd & 3rd sites) by ODEX-165 method of drilling under Augmentation of Lohugaon (Zone-II) piped water supply scheme under Jal Swapna/JJM works within Phansidewa Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000269/2022-2023 | 2376/SWSD | 24/01/2023 | 829 | FAIRDEAL ASSOCIATES | 400.24 | 0 | 70
651 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum work order "Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. and two nos Pump House (3600mm x 2400mm x 3300mm height) with toilet (2100mm x 1350mm) sanitary and plumbing arrangement along with verandah (3975mm x 1500mm) having plinth height 600m m. and construction of Boundary Wall at Three Different Site Pump House Site and Iron Elemination Plant Under Lohugaon (Z-II) at Lahugaon (Z-II) Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling". | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000320/2023-2024 | 603/SWSD | 06/03/2024 | 667 | SHYAMAL NATH | 68.77 | 0 | 60
652 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000012/2021-2022 | 2169/SWSD | 11/02/2022 | 0 | Resource Division | 313.89 | 0 | 0
653 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000019/2022-2023 | 1449/SWSD | 29/09/2022 | 0 | Resource Division | 25.7 | 0 | 0
654 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000301/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 1.32 | 0 | 0
655 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000890/2021-2022 | BP-2021-22-108 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 230.79 | 0 | 0
656 | Central Drilling | Siliguri Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23) (Phase-IX). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000030/2024-2025 | 560/CDD | 06/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 10
657 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for LAHUGAON, KUMARTULI, T.W. No. I under BIDHANNAGAR CCC, [APPLICATION NO. 4003194405, Reference ID : 403046890] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00590/2023-2024 | BP/23-24/74 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.22 | 0 | 0
658 | Northern Mechanical | Siliguri Sub-Division | Charges for additional quotation For lahugaon PWSS (Near Kumar tuli),Z-II,Tw-II under NMD PHE dte. Application no- 4003320704 Ref ID- 403147041 For Additional Quotation Application ID- 100000114620 Ref ID- 860308530 | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00643/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.88 | 0 | 0
659 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for LAHUGAON T/W No.II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003320700, Reference ID : 403147042] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/02022/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0
660 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for LAHUGAON T/W No. II, ZONE-II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003320704, Reference ID : 403147041] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/02023/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.35 | 0 | 0
661 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LAHUGAON PIPED WATER SUPPLY SCHEME, TW No. III (Zone-I), TW-I and II (Zone-II) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000666/2023-2024 | 1480/NMD | 17/08/2023 | 776 | ANUP BASU | 34.42 | 0 | 70
662 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SHIVKHOLA FOREST PAGLAJHORA PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000013/2025-2026 | 499/NKWSMD | 09/04/2025 | 90 | SWAD CONSTRUCTION | 55.85 | 0 | 0
663 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED SHIVAKHOLA FOREST PAGLA JHORA PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITH IN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000284/2022-2023 | 2082/NKWSMD | 10/01/2023 | 180 | SWAD CONSTRUCTION | 168.21 | 0 | 100
664 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000225/2022-2023 | 2566/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.65 | 0 | 0
665 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Rupsing Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000152/2022-2023 | 268/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.73 | 0 | 100
666 | Siliguri W/S Division | Siliguri W/S Division | Part Work order for Construction of 200 cu.m. capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head work site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of one number pump house (5.40 X 3.60 m), one number pump house (3.00 X 3.60 m), iron elimination plant (IEP) with blower room, sinking of two (2) nos. tube well (ODEX-165 method), soil investigation at HW site and boundary wall for Rupsing PWSS, Block Naxalbari, Dist- Darjeeling under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000253/2023-2024 | 84/SWSD | 10/01/2024 | 240 | YAMA CONSTRUCTIONS LLP | 255.16 | 0 | 0
667 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000033/2022-2023 | 1463/SWSD | 29/09/2022 | 0 | Resource Division | 6.38 | 0 | 0
668 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000074/2022-2023 | 2053/SWSD | 16/12/2022 | 0 | Resource Division | 45.28 | 0 | 0
669 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
670 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RUPSING PIPED WATER SUPPLY SCHEME, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000800/2023-2024 | 1657/NMD | 29/09/2023 | 30 | TALUKDER ENTERPRISE | 11.5 | 0 | 50
671 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MIDDLE MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT, UNDER KURSEONG DIVISION, P.H.E-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000223/2022-2023 | 1121/NKWSMD | 05/08/2022 | 1151 | PREM CHANDRA RAI | 96.87 | 0 | 100
672 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000267/2022-2023 | 2839/NKWSMD | 17/03/2023 | 0 | Resource Division | 1.03 | 0 | 0
673 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LOWER MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000090/2022-2023 | 609/NKWSMD | 26/05/2022 | 948 | NAVRATNA CONSTRUCTION CO | 125.37 | 0 | 80
674 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000140/2022-2023 | 2060/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.21 | 0 | 0
675 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR THULUNG GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000088/2022-2023 | 612/NKWSMD | 26/05/2022 | 60 | SEWARO CONSTRUCTION COMPANY | 75.88 | 0 | 95
676 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000077/2022-2023 | 1321/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.66 | 0 | 0
677 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | PIPED WATER SUPPLY SCHEME FOR POKHRIABONG BUSTY NO. 5 UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000107/2022-2023 | 628/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 85.92 | 0 | 100
678 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000085/2022-2023 | 1367/NKWSMD | 21/09/2022 | 0 | Resource Division | 0.52 | 0 | 0
679 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000107/2022-2023 | 1884/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.52 | 0 | 0
680 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000166/2022-2023 | 2571/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.52 | 0 | 0
681 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Upper Naya Busty under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000121/2022-2023 | 801/NKWSMD | 30/06/2022 | 60 | PRASANT NIROLA | 19.84 | 0 | 100
682 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000047/2022-2023 | 1323/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.66 | 0 | 0
683 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Rajbari Tindharay Gayabari-II GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000132/2022-2023 | 812/NKWSMD | 30/06/2022 | 60 | HIMALI CONSTRUCTION COMPANY | 22.13 | 0 | 100
684 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000058/2022-2023 | 1302/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.36 | 0 | 0
685 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SUPPLEMENTARY ITEMS IN ONGOING SPRING SIDI PIPED WATER SUPPLY SCHEMES UNDER KURSEONG DIVISION, PHED, GTA | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Sub-Assistant Engineer | ORD/000053/2025-2026 | 776/NKWSMD | 28/05/2025 | 60 | HIMALAYAN CONSTRUCTION | 11.53 | 0 | 0
686 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Water Supply Scheme for Spring Sidi Tea Garden village Piped Water Supply Scheme In Kurseong Under Darjeeling District. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Sub-Assistant Engineer | ORD/000320/2022-2023 | 2644/NKWSMD | 24/02/2023 | 770 | HIMALAYAN CONSTRUCTION | 217.45 | 0 | 100
687 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer5,Sub-Assistant Engineer | RTOR000134/2023-2024 | 700/NKWSMD | 22/03/2024 | 0 | Resource Division | 1.52 | 0 | 0
688 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation of source and provding FHTC at Bijanbari Bazar under Jal Swapno Programme for Balance household at Bijanbari Bazar, Gram panchyat- Bijanabari, Block- Bijanbari-Pullbazaar TSM No. 009478 |  | Sub-Assistant Engineer | ORD/000124/2022-2023 | 804/NKWSMD | 30/06/2022 | 60 | PROSENJIT BASAK | 35.85 | 0 | 85
689 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Gothals Siding and Upper Kharay Busty with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000231/2022-2023 | 1445/NKWSMD | 28/09/2022 | 60 | NIPENDRA TAMANG | 31.04 | 0 | 30
690 | Siliguri W/S Division | Siliguri W/S Division | Laying Rising Main, laying distribution pipe line with Functional Household Tap Connection (FHTC), construction of two number Pump Houses (5.40 X 3.60 M), Iron Elimination Plant (IEP) with Blower Room and sinking of 2 (two) Nos. Tube well (ODEX-165 method) for HATIDOBA PWSS, Block - Kharibari, Dist. Darjeeling under Siliguri W/S Division P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000046/2023-2024 | 654/SWSD | 15/06/2023 | 775 | M/S DOLPHIN CONSTRUCTION CO | 178.07 | 0 | 25
691 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF HATIDOBA PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000058/2023-2024 | 251/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.8 | 0 | 100
692 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000067/2022-2023 | 2046/SWSD | 16/12/2022 | 0 | Resource Division | 13.77 | 0 | 0
693 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
694 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for HATIDOBA, T/W No. I, under KHORIBARI CCC [APPLICATION NO. 4003296374 ; Reference ID : 403127440] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01745/2023-2024 | BP/23-24/223 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.71 | 0 | 0
695 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for HATIDOBA, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003321646, Reference ID : 403147923] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01947/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.02 | 0 | 0
696 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
697 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF HATIDOBA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000779/2023-2024 | 1643/NMD | 29/09/2023 | 713 | M/S SIMARR | 11.92 | 0 | 100
698 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0
699 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/001069/2024-2025 | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0
700 | Siliguri W/S Division | Siliguri W/S Division | Laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of two numbers pump house (5.40 X 3.60 m), iron elimination plant (IEP) with blower room, sinking of 2 (two) nos. tubewell (ODEX-165 method) and boundary wall for ARJUNMAHAL PWSS, Block : Kharibari, Dist. Darjeeling under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000003/2023-2024 | 58/SWSD | 10/04/2023 | 120 | M/S UTPAL CHAKRABORTY & CO. | 180.13 | 0 | 30
701 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF ARJUN MAHAL PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000056/2023-2024 | 249/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.83 | 0 | 100
702 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000065/2022-2023 | 2043/SWSD | 16/12/2022 | 0 | Resource Division | 14.57 | 0 | 0
703 | Northern Mechanical | Siliguri W/S Division | Quotation For New service Connection at Arjun Mahal Piped Water Supply Scheme, PH-II under Northern Mechanical Division ,PHE dte. siliguri. APPLICATION NO:- 4003208346 Reference ID :- 403057205 | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00183/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0
704 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for ARJUN MAHAL, T.W. No. I under KHARIBARI CCC, [APPLICATION NO. 4003193675, Reference ID : 403046163] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00597/2023-2024 | BP/23-24/77 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0
705 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for ARJUN MAHAL, T/W II, under KHARIBARI CCC [APPLICATION NO. 4003208346 ; Reference ID : 403057205] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00993/2023-2024 | BP/23-24/94 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0
706 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
707 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ARJUNMAHAL PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000785/2023-2024 | 1649/NMD | 29/09/2023 | 30 | M/S UTPAL CHAKRABORTY & CO. | 11.85 | 0 | 100
708 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0
709 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0
710 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000022/2025-2026 | 590/NKWSMD | 29/04/2025 | 90 | M/S BRM DEVELOPERS | 35.22 | 0 | 0
711 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR PLUNGDUNG KHASMAHAL PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000317/2022-2023 | 2521/NKWSMD | 15/02/2023 | 545 | GARGO TRADERS | 1596.98 | 0 | 85
712 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
713 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000211/2022-2023 | 2559/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.78 | 0 | 0
714 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000241/2022-2023 | 2717/NKWSMD | 03/03/2023 | 0 | Resource Division | 6.78 | 0 | 0
715 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR PUSSINGBONG TEA GARDEN WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000045/2025-2026 | 632/NKWSMD | 05/05/2025 | 180 | VAJRA ENTERPRISES | 45.26 | 0 | 0
716 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR PUSSINGBONG PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000222/2023-2024 | 1279/NKWSMD | 17/10/2023 | 605 | SHAKTI CONSTRUCTION | 1586.35 | 0 | 95
717 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000271/2023-2024 | 1592/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
718 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR SAGMARU TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000086/2023-2024 | 685/NKWSMD | 12/07/2023 | 605 | GARGO TRADERS | 2047.06 | 0 | 50
719 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000077/2023-2024 | 765/NKWSMD | 19/07/2023 | 0 | Resource Division | 5.61 | 0 | 0
720 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum work order for construction of pump house, boundary wall, drain under Augmentation of Purba Bansgaon Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000182/2023-2024 | 1811/SWSD | 03/10/2023 | 695 | AKASH ENTERPRISE | 32.21 | 0 | 100
721 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Construction the boring of ODEX-165 tubewell, laying distribution, iron elimination plant under Augmentation of Purba Bansgaon Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000229/2023-2024 | 2033/SWSD | 06/11/2023 | 45 | BUDDHADEV NAG | 55.04 | 0 | 17
722 | Siliguri W/S Division | Siliguri Sub-Division | Sinking of Rig bored Tubewell by Odex-165 method of drilling & Erection of Iron Elimination Plant of 40 Cum/Hr at 4th TW Site and Construction of Pump House ( 5.40M X 3.65M ) Size with sanitary & plumbing arrangement including Boundary wall along with other anciellary works at 3rd T/W Site for Augmentation of Purba Basgaon Piped Water Supply Scheme within Phansidewa Block under Siliguri W/S Division, related to Jal Jeevan Mission (JJM) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000237/2024-2025 | 350/SWSD | 30/01/2025 | 45 | BUDDHADEV NAG | 33.94 | 0 | 0
723 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000003/2023-2024 | 203/SWSD | 25/04/2023 | 0 | Resource Division | 0.79 | 0 | 0
724 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
725 | Northern Mechanical | Siliguri Sub-Division | Quotation Charges for new Service connection at Purba Bansgaon PWSS , TW-I under NMD PHE Dte. Application No- 4003510209 Ref ID- 403289913 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01413/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.77 | 0 | 0
726 | Northern Mechanical | Siliguri Sub-Division | Quotation Charges for new Service connection at Purba Bansgaon PWSS , TW-I under NMD PHE Dte. Application No- 4003510161 Ref ID- 403289908 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01414/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.02 | 0 | 0
727 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PURBA BANSGAON , T/W No. I, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320146, Reference ID : 403147647] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01965/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.49 | 0 | 0
728 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PURBA BANSGAON , T/W No. II, ZONE-II under PHANSIDAWA CCC, [APPLICATION NO. 4003320129, Reference ID : 403147638] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01966/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.88 | 0 | 0
729 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA BANSGAON PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000807/2023-2024 | 1664/NMD | 29/09/2023 | 30 | THE BANERJEE CONCERN | 10.22 | 0 | 0
730 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 0 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0
731 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR KALIJHORA BAZAR PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000026/2023-2024 | 125/NKWSMD | 28/04/2023 | 810 | GREEN VALLEY CONSTRUCTION | 155.27 | 0 | 82
732 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000017/2023-2024 | 213/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.82 | 0 | 0
733 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
734 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DANGIA PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000033/2023-2024 | 183/NKWSMD | 04/05/2023 | 240 | HARI PRASAD CHETTRI | 480.88 | 0 | 55
735 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission for Balance Household at upper Kolbong in connection with Dangia under Darjeeling Division, P.H.E-G.T.A. |  | Sub-Assistant Engineer | ORD/000246/2023-2024 | 164/NKWSMD | 30/01/2024 | 120 | TULSI NIROLA | 23.65 | 0 | 100
736 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.01.2024 TO 30.04.2024. |  | Sub-Assistant Engineer | ORD/000258/2023-2024 | 1576/NKWSMD | 29/12/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 100
737 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000012/2023-2024 | 209/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.98 | 0 | 0
738 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000130/2023-2024 | 163/NKWSMD | 30/01/2024 | 0 | Resource Division | 0.22 | 0 | 0
739 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000263/2022-2023 | 2777/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.44 | 0 | 0
740 | Siliguri W/S Division | Siliguri Sub-Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
741 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Additional Work for functional house hold tap connection (FHTC) at Agumentation Thakurganj and Adjoining Mouzas water Supply Scheme under Phansidewa Block under Siliguri Sub Division , P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000012/2025-2026 | 1238/SWSD | 24/04/2025 | 30 | VIJAY KUMAR ARORA | 13.11 | 0 | 0
742 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 350 cu.m. capacity RCC Elevated Reservoir, 20 mtrs Staging Height at the head works site including rising mains and distribution system (Part-A) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-A) of Thakurganj at Thakurganj and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL.NO. 01. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000013/2022-2023 | 273/SWSD | 06/05/2022 | 1122 | HIMADRI DAM & CO. | 158.69 | 0 | 60
743 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-G) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-G) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 04. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000025/2022-2023 | 536/SWSD | 16/06/2022 | 35 | SHIVNATH DEY | 25.22 | 0 | 0
744 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House with toilet, plinth protection etc. installation of IEP and Boundary Wall at Thakurganj of THAKURGANJ Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000037/2023-2024 | 646/SWSD | 15/06/2023 | 226 | HIMADRI DAM & CO. | 49.26 | 0 | 35
745 | Siliguri W/S Division | Siliguri Sub-Division | Laying Distribution System (Part-C) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-C) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 02 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000057/2022-2023 | 862/SWSD | 21/07/2022 | 75 | M/S UTPAL CHAKRABORTY & CO. | 82.68 | 0 | 83
746 | Siliguri W/S Division | Siliguri Sub-Division | Laying Distribution System (Part-D) allied with Providing Functional Household Tap Connection (FHTC) at Distribution Pipeline (Part-D) and rising main at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 03. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000058/2022-2023 | 863/SWSD | 21/07/2022 | 1200 | AKASH ENTERPRISE | 122.09 | 0 | 2
747 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-G) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-G) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 04. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000059/2022-2023 | 864/SWSD | 21/07/2022 | 35 | SHIVNATH DEY | 25.22 | 0 | 90
748 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-E) Erection of Iron Elimination Plant allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-E) at Thakurganj and adjoining mouzas water supply scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 05. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000143/2021-2022 | 2439/SWSD | 21/03/2022 | 75 | M/S DEBRAJ ENTERPRISE | 85.61 | 0 | 85
749 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system (Part-F) allied with Providing Functional Household Tap Connection (FHTC) at distribution pipeline (Part-F) at Thakurganj and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, PHE Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000144/2021-2022 | 2440/SWSD | 21/03/2022 | 40 | M/S ASHIRBAD ENTERPRISE | 33.08 | 0 | 60
750 | Siliguri W/S Division | Siliguri Sub-Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000165/2022-2023 | 1325/SWSD | 14/09/2022 | 45 | GANPATI CONSTRUCTION CO | 46.34 | 0 | 100
751 | Siliguri W/S Division | Siliguri Sub-Division | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 100
752 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000014/2021-2022 | 2171/SWSD | 11/02/2022 | 0 | Resource Division | 42.81 | 0 | 0
753 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000015/2022-2023 | 1445/SWSD | 29/09/2022 | 0 | Resource Division | 12.16 | 0 | 0
754 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000305/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 10.86 | 0 | 0
755 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000891/2021-2022 | BP-2021-22-109 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 31.44 | 0 | 0
756 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for AUGUMENTATION OF THAKURGANJ,T/W No - I W/S Scheme, under BIDHANNAGAR CCC, [APPLICATION NO. 4003058220, Reference ID : 402933259] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00752/2022-2023 | BP/22-23/156 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0
757 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF THAKURGANJ PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000793/2022-2023 | 107/NMD | 03/02/2023 | 30 | M/S MATRI CONSTRUCTION | 10.95 | 0 | 100
758 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site along with distribution system, functional household tap connection, rising main, pump house (2 nos.), IEP, boundary wall and tubewell under Jal Jeevan Mission of PURBA BANSGAON CHAKLA Piped Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000108/2023-2024 | 1148/SWSD | 08/08/2023 | 420 | UNIBRO INFRASERV PRIVATE LIMITED | 497.64 | 0 | 10
759 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Purba Bansgaon Chakla Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000330/2022-2023 | 412/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.69 | 0 | 0
760 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000014/2023-2024 | 212/SWSD | 25/04/2023 | 0 | Resource Division | 23.82 | 0 | 0
761 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000057/2023-2024 | 83/SWSD | 10/01/2024 | 0 | Resource Division | 12.11 | 0 | 0
762 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
763 | Northern Mechanical | Siliguri Sub-Division | Additional Charges for New Service Connection at Purba Bansgaon Chakla PWSS ,Zone-II,TW-II under NMD PHEdte. Ref ID- 860316628 Application ID- 100000122188 | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01455/2024-2025 | BP/24-25/245 | 26/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 22.22 | 0 | 0
764 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for PURBBA BANSGAON CHAKLA T/W No. I, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003326733, Reference ID : 403152619] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/02036/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.64 | 0 | 0
765 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for PURBBA BANSGAON CHAKLA T/W No. II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003326724, Reference ID : 403152618] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/02037/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.12 | 0 | 0
766 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBBA BANSGAON CHAKLA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000754/2023-2024 | 1582/NMD | 08/09/2023 | 723 | M/S SAJAHAN CHOWDHURY | 34.01 | 0 | 70
767 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional estimate for water supply scheme for Pumong Tea Garden piped water supply scheme in rangli-rangliot Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000019/2024-2025 | 983/NKWSMD | 18/06/2024 | 60 | RAMESH AGARWAL | 48.79 | 0 | 100
768 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PUMONG TEA GARDEN PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000083/2023-2024 | 682/NKWSMD | 12/07/2023 | 455 | RAMESH AGARWAL | 701.65 | 0 | 50
769 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000075/2023-2024 | 764/NKWSMD | 19/07/2023 | 0 | Resource Division | 7.38 | 0 | 0
770 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHEWARIBOTAY PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000048/2023-2024 | 261/NKWSMD | 15/05/2023 | 120 | NIMA SHERPA | 132.89 | 0 | 100
771 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.06.2024 to 31.07.2024 |  | Sub-Assistant Engineer | ORD/000051/2024-2025 | 385/NKWSMD | 31/05/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
772 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000040/2023-2024 | 327/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.21 | 0 | 0
773 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BARBATIA KHASMAHAL PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000032/2023-2024 | 182/NKWSMD | 04/05/2023 | 330 | MS. SURYA I PVT. LTD COMPANY | 194.76 | 0 | 95
774 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000014/2023-2024 | 211/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.77 | 0 | 0
775 | Neorakhola W/S & Mtc.Div. |  | Surface water based Toryak Khasmahal Piped Water Supply Scheme to accommodate FHTC in Kurseong Block within Darjeeling District |  |  | ORD/000233/2023-2024 | 1328/NKWSMD | 03/11/2023 | 365 | SHAKTI CONSTRUCTION | 1230.38 | 0 | 100
776 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Estimate for Water Supply Scheme for Ginglam & Gielle Tea Garden Piped Water Supply Scheme in Rangli-Rangliot Block under Darjeeling District. (SM/18721) | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000021/2024-2025 | 985/NKWSMD | 18/06/2024 | 60 | RAMESH AGARWAL | 32.15 | 0 | 100
777 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GINGLAM & GIELLE TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000182/2023-2024 | 907/NKWSMD | 11/08/2023 | 415 | RAMESH AGARWAL | 1031.49 | 0 | 100
778 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000103/2023-2024 | 976/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.58 | 0 | 0
779 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | BILL/00490/2023-2024 | BP-2023-24-294 | 02/11/2023 | 0 | WBSEDCL | 2.71 | 0 | 0
780 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | BILL/00491/2023-2024 | BP-2023-24-293 | 02/11/2023 | 0 | WBSEDCL | 5.02 | 0 | 0
781 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 100
782 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
783 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000156/2022-2023 | 2368/NKWSMD | 03/02/2023 | 0 | Resource Division | 6.09 | 0 | 0
784 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Rongchong and Labda under Kurseong Division. Scheme code - 18729 TSM/018103 | Assistant Engineer | Sub-Assistant Engineer | BILL/00090/2024-2025 | BP-2024-25-97 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 5.04 | 0 | 0
785 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR RONGCHONG AND LABDA IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION. PHED/GTA. | Assistant Engineer | Sub-Assistant Engineer | ORD/000040/2025-2026 | 655/NKWSMD | 05/05/2025 | 180 | DAJUBHAI CONSTRUCTION | 107.78 | 0 | 0
786 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RANGCHONG & LABDA PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT | Assistant Engineer | Sub-Assistant Engineer | ORD/000177/2023-2024 | 936/NKWSMD | 16/08/2023 | 605 | VINAYAK CONSTRUCTION | 1186.16 | 0 | 100
787 | Neorakhola W/S & Mtc.Div. |  | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-I) (MARGARET HOPE) |  |  | ORD/000218/2023-2024 | 1207/NKWSMD | 10/10/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1076.48 | 0 | 90
788 | Neorakhola W/S & Mtc.Div. |  | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-II) (MARGARET HOPE) |  |  | ORD/000224/2023-2024 | 1286/NKWSMD | 17/10/2023 | 365 | M/S. ASHOK KUMAR PERIWAL | 1084.55 | 0 | 80
789 | Neorakhola W/S & Mtc.Div. |  | Piped Water Supply Scheme with FHTC for Ringtong Tea Garden (Margaret Hope), Part of Ringtong Tea Garden (Gunawar) & Nahori Tea Garden (Balason) under Kurseong Division, P.H.E.D-GTA (ZONE-III) |  |  | ORD/000225/2023-2024 | 1287/NKWSMD | 17/10/2023 | 365 | TIKARAM SHARMA | 973.97 | 0 | 85
790 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 1285/NKWSMD | 17/10/2023 | 0 | Resource Division | 6.92 | 0 | 0
791 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Home Dara(Tower Dara) Gram Panchyat -Relling , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009299 SM Code-SM/08927 GO2223000391PH |  | Sub-Assistant Engineer | ORD/000025/2022-2023 | 258/NKWSMD | 10/05/2022 | 60 | M/S DIVYA ENTERPRISES | 13.79 | 0 | 0
792 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000031/2022-2023 | 1258/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.68 | 0 | 0
793 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Sub-Assistant Engineer | ORD/000052/2025-2026 | 775/NKWSMD | 28/05/2025 | 180 | HIMALAYAN CONSTRUCTION | 122.95 | 0 | 0
794 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SITTONG KHASMAHAL PIPED WATER SUPPLY SCHEME KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Sub-Assistant Engineer | ORD/000113/2023-2024 | 850/NKWSMD | 27/07/2023 | 715 | HIMALAYAN CONSTRUCTION | 921.25 | 0 | 85
795 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part B) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 10. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000080/2022-2023 | 853/SWSD | 21/07/2022 | 30 | PRADIP GUHA | 26.69 | 0 | 40
796 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part C) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 11 | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000081/2022-2023 | 854/SWSD | 21/07/2022 | 25 | M/S SHIVAJI ROY | 18.45 | 0 | 40
797 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system and allied works with Providing Functional Household Connection (FHTC) at distribution pipeline of Shyamdhan Zone I (Part D) of the Shyamdhan Piped Water Supply Scheme, Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 12. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000082/2022-2023 | 855/SWSD | 21/07/2022 | 25 | SWAPAN CHANDRA DAS | 24.77 | 0 | 40
798 | Siliguri W/S Division | Siliguri W/S Division | Construction of 300 Cu.M. capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site including distribution system with Providing Functional Household Tap Connection (FHTC), construction of Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at 3rd TW site and allied works at distribution pipe line under Jal Swapna/JJM works for Augmentation of Shyamdhan (ZONE-I) Piped Water Supply Scheme (PART-A), Kharibari block under Siliguri Sub Division.P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000082/2023-2024 | 1049/SWSD | 28/07/2023 | 787 | M/S BIRAT CONSTRUCTION | 319.92 | 0 | 40
799 | Siliguri W/S Division | Siliguri W/S Division | Construction of Pump House 2 Nos. (3.65 X 2.45, Zn-II 2nd and 3rd T/W Zn-I) size with (1.20 X 2.10 M) size toilet, plinth protection, 3 nos. Boundary Wall and IEP (40 cu.m/hr. Zn-II H/W, 20 cu.m/hr Zn-I H/W) Supplying, fabrication eretion on suitable RCC foundation and Commissioning with 3 (three) month trial run of pressure type Iron Removal Plant with Blower cum Compressure Room 2 nos. (Zn-II and I, H/W) with required size platform, surface drain at SHYAMDHAN Piped Water Supply Scheme at kharibari block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000146/2023-2024 | 1414/SWSD | 22/08/2023 | 541 | KOHINOOR ALAM | 84.29 | 0 | 40
800 | Siliguri W/S Division | Siliguri W/S Division | CONSTRUCTION OF BOUNDARY WALL, DRAIN, PATHWAY INCLUDING LAND DEVELOPMENT AT HEAD WORK SITE OF SHYAMDHAN ZONE-II AND RENOVATION OF BOUNDARY WALLS, PUMP HOUSES AT H/W SITE AND 2ND SITE OF SHYAMDHAN ZONE-I INCLUDING WASHOUT LINES ICW AUGMENTATION OF SHYAMDHAN PWSS RELATED TO JAL JEEVAN MISSION (JJM) AT KHARIBARI BLOCK WITHIN SILIGURI W/S DIVISION, PHE DTE. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000147/2024-2025 | 2845/SWSD | 23/10/2024 | 330 | D S ENTERPRISE | 43.07 | 0 | 30
801 | Siliguri W/S Division | Siliguri W/S Division | Soil investigation of Shyamdhan Zone- II PWSS for Construction of 200 Cum OHR under Siliguri Sub Division, PHE Dte. under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000168/2023-2024 | 436/SSD | 12/09/2023 | 20 | MABCO CONSULTANT | 1.03 | 0 | 100
802 | Siliguri W/S Division | Siliguri W/S Division | Soil investigation of Shyamdhan Zone- I PWSS for Construction of 300 cum OHR under Siliguri Sub Division, PHE Dte. under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000170/2023-2024 | 435/SSD | 12/09/2023 | 20 | GEOCON INDIA | 1.03 | 0 | 100
803 | Siliguri W/S Division | Siliguri W/S Division | Work order for Construction of 200 cu.m capacity R.C.C. Elevated Reservoir, 20 mtrs. staging height at the head work site including pump house (H/W site), rising main and distribution system with providing household tap connection (FHTC), construction of rig bored big dia deep tubewells (H/W & 2nd sites) by ODEX-165 method of drilling and allied works at distribution pipe line under Jal Swapna/JJM works for Augmentation of Shyamdhan Piped Water Supply Scheme (Zone-II), Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000257/2023-2024 | 107/SWSD | 15/01/2024 | 580 | M/S YOUNG ASSOCIATES | 329.38 | 0 | 35
804 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000025/2023-2024 | 1809/SWSD | 30/09/2023 | 0 | Resource Division | 193.96 | 0 | 0
805 | Central Drilling | Siliguri W/S Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
806 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for SHYAMDHAN, T/W No. III, ZONE-I under KHARIBARI CCC, [APPLICATION NO. 4003320066, Reference ID : 403147080] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01978/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.42 | 0 | 0
807 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for SHYAMDHAN, T/W No. I, ZONE-II under KHARIBARI CCC, [APPLICATION NO. 4003320289, Reference ID : 403147077] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01979/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.07 | 0 | 0
808 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for SHYAMDHAN, T/W No. II, ZONE-II under KHARIBARI CCC, [APPLICATION NO. 4003320230, Reference ID : 403147069] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01980/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.41 | 0 | 0
809 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SHYAMDHAN PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. III ,& (Zone-II) TW-I,II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000455/2023-2024 | 1394/NMD | 09/08/2023 | 753 | WEST BENGAL ENGINEERING CO. | 34.92 | 0 | 90
810 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Gitangay T.E. Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000123/2022-2023 | 803/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 11.87 | 0 | 100
811 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000066/2022-2023 | 1310/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.44 | 0 | 0
812 | Siliguri W/S Division | Siliguri Sub-Division | Work Order for Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height at the head work site including distribution system (HDPE) with rising main, Rig bore 2 nos. big dia T/W by Odex-165 method, providing functional household tap connection (FHTC), pump house 2 nos., blower room, IEP 60 cu.m./hr., boundary walls, soil testing and allied works at Mandilajhar PWSS Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000183/2023-2024 | 1812/SWSD | 03/10/2023 | 393 | KRISHNA TRADING CO. | 509.14 | 0 | 60
813 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000023/2023-2024 | 1807/SWSD | 30/09/2023 | 0 | Resource Division | 18.81 | 0 | 0
814 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000051/2023-2024 | 76/SWSD | 10/01/2024 | 0 | Resource Division | 9.49 | 0 | 0
815 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
816 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for MANDILA JHAR T/W No. I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322513, Reference ID : 403149165] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/02043/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.51 | 0 | 0
817 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for MANDILA JHAR T/W No. II, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322508, Reference ID : 403149170] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/02044/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.46 | 0 | 0
818 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANDILA JHAR PIPED WATER SUPPLY SCHEME, TW No. I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000938/2023-2024 | 1671/NMD | 29/09/2023 | 460 | SAIKAT SINHA | 11.58 | 0 | 100
819 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000054/2023-2024 | 247/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.53 | 0 | 100
820 | Siliguri W/S Division | Siliguri W/S Division | Construction of 200 cum capacity RCC Elevated Reservoir, 20 mtrs. Staging height at the head works site along with distribution system rising main, iron elimination plant, pump houses, boundary walls, functional house hold tap connection (FHTC), soil investigation and other allied works under Jal Jeevan Mission (JJM) for Augmentation of ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME under Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000277/2022-2023 | 2655/SWSD | 02/03/2023 | 841 | VIJAY KUMAR ARORA | 209.89 | 0 | 65
821 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000054/2022-2023 | 2033/SWSD | 16/12/2022 | 0 | Resource Division | 15.89 | 0 | 0
822 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for ORD TERAI, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003291503 ; Reference ID : 403124697] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01746/2023-2024 | BP/23-24/222 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.07 | 0 | 0
823 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for ORD TERAI, T/W No. II under NAXALBARI CCC [APPLICATION NO. 4003312826 , Reference ID : 4031141988] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01918/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0
824 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
825 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ORD TERAI TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000664/2023-2024 | 1478/NMD | 17/08/2023 | 30 | SAIKAT SINHA | 12.5 | 0 | 100
826 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (NAXALBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000998/2024-2025 | 17/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 11.76 | 0 | 0
827 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001068/2024-2025 | 36/NMD | 06/01/2025 | 30 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0
828 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for BHAKTARAM UTTAM CHAND UTTAM CHANDER CHHAT HODUVITA and MUDIR JANGAL mouza of GHUSURU Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division PHE Dte SL. NO. 03 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000044/2021-2022 | 1215/SWSD | 01/11/2021 | 45 | ARUN KUMAR SHRIVASTAVA | 36.04 | 0 | 100
829 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional Household Tap Connection (FHTC) in connection under Jal Jeeven Mission & Jal Swapno Programme for Kawakhali Piped Water Supply Scheme at Matigar Block under Siliguri Sub-Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000013/2021-2022 | 707/SWSD | 03/08/2021 | 120 | DEBASHIS SINHA | 34.96 | 0 | 100
830 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House Hold Top Connection under Jal Jeevan Mission & Jal Swapno Programme for AWC¿s , Schools etc. under Kawakhali Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 12 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000036/2021-2022 | 996/SWSD | 08/09/2021 | 15 | S.G.CONSTRUCTION | 4.71 | 0 | 0
831 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House Hold Top Connection under Jal Jeevan Mission & Jal Swapno Programme for AWC¿s , Schools etc. under Bairagi Piped Water Supply Scheme at Kharibari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 13 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000037/2021-2022 | 1002/SWSD | 09/09/2021 | 15 | M/S ROYAL ENTERPRISE | 4.71 | 0 | 100
832 | Siliguri W/S Division | Siliguri W/S Division | Providing functional household tap connection under Jal Jeevan Mission & Jal Swapno programme for Kawakhali Piped Water Supply Scheme at Matigara block under Siliguri Sub Division, P.H.E. Dte. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000087/2021-2022 | 1637/SWSD | 28/12/2021 | 15 | KAMAL GHOSH | 4.31 | 0 | 100
833 | Siliguri W/S Division | Siliguri W/S Division | Minor repairing works in connection with functional household tap connection at Kawakhali piped W/S Scheme at Matigara Blockunder siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000229/2022-2023 | 543/SSD | 19/12/2022 | 15 | KAMAL GHOSH | 0.77 | 0 | 100
834 | Siliguri W/S Division | Siliguri W/S Division | Additional work of providing functional household tap connection under Jal jeevan Mission and Jal Swapno for Kawakhali piped water supply scheme at Matigara Block under Siliguri Sub division,P.H.Engineering Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000253/2022-2023 | 508/SSD | 16/11/2022 | 15 | DEBASHIS SINHA | 1.1 | 0 | 0
835 | Siliguri W/S Division | Siliguri W/S Division | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHERN ZONE, PHE DTE., VIVEKANANDA BHAWAN (2ND FLOOR), HILL CART, ROAD, SILIGURI FOR THE PERIOD FROM 01.04.2022 TO 30.09.2022 (FOR CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE.). (i.e. 6 months) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00050/2022-2023 | BP-2022-23-120 | 20/02/2023 | 0 | PINKI DAM | 1.72 | 0 | 0
836 | Siliguri W/S Division | Siliguri W/S Division | Construction of 350 Cum. capacity R.C.C Elevated Reservoir , 20 Mtrs. Staging Height at the head works site including Rising Main, distribution system and providing functional household tap connection (FHTC) & IEP, boundary wall and sub soil investigation for Augmentation of BAIRATISAL & ADJ. Mouza's (Zone-I) Water Supply Scheme under Matigara block under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000031/2023-2024 | 652/SWSD | 15/06/2023 | 1077 | FAIRDEAL ASSOCIATES | 476.26 | 0 | 70
837 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000169/2022-2023 | 1329/SWSD | 14/09/2022 | 25 | RANJEET SINGH BENIWAL | 15.47 | 0 | 100
838 | Siliguri W/S Division | Siliguri W/S Division | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE., VIVEKANANDA BHAWAN (2ND FLOOR), HILL CART ROAD, SILIGURI FOR THE PERIOD FROM 01.10.2022 TO 28.02.2023 (FOR CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE.) i.e. 5 (FIVE) MONTHS. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000216/2022-2023 | 1435/SWSD | 28/09/2022 | 153 | PINKI DAM | 0.74 | 0 | 100
839 | Siliguri W/S Division | Siliguri W/S Division | Continuation order for hiring of 1 (one) no. well maintained diesel consumed luxury cab on monthly hired basis preferably MAXI CAB (A/C) with engine capacity less than or equal to 2000 CC for office of the Chief Engineer (Civil), Northern Zone, P.H.E. Dte., Vivekananda Bhawan (2nd floor) Hill Cart Road, Siliguri (for Assistant Chief Engineer, Northern Zone (Civil), P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000262/2021-2022 | 2269/SWSD | 24/02/2022 | 6 | OM TRAVELS | 0.88 | 0 | 100
840 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000026/2022-2023 | 1456/SWSD | 29/09/2022 | 0 | Resource Division | 13.34 | 0 | 0
841 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000045/2022-2023 | 2025/SWSD | 16/12/2022 | 0 | Resource Division | 134.96 | 0 | 0
842 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BAIRATISAL,ZONE-I TW No. I, SHIVMANDIR CCC, [APPLICATION NO.4003158519, Reference ID : 403021368] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00468/2023-2024 | BP/23-24/29 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.67 | 0 | 0
843 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - I PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000679/2023-2024 | 1491/NMD | 17/08/2023 | 442 | M/S MATRI CONSTRUCTION | 12.5 | 0 | 100
844 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0
845 | Siliguri W/S Division | Siliguri Sub-Division | Hiring of Vehicle for the office of the Assistant Engineer under Siliguri Sub-division ,P.H.E dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00026/2022-2023 | BP-2022-23-109 | 18/01/2023 | 0 | SUDIP BASAK | 0.38 | 0 | 0
846 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Kamala (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Tutaram Zone) under Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. SL. NO. 15. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000004/2022-2023 | 38/SWSD | 07/04/2022 | 377 | ARUN KUMAR SHRIVASTAVA | 137.11 | 0 | 60
847 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Budhkraran (Part) & Geni (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Roypara Zone) under Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. SL. NO. 17. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000005/2022-2023 | 37/SWSD | 07/04/2022 | 1365 | SUBIR CH. CHOWDHURY | 138.01 | 0 | 100
848 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House (3.65 X 2.45) size with (1.20 X 2.10 M) size with toilet, plinth protection etc. at Kamala zone of Naxalbari Piped Water Supply Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. SL. NO. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000019/2022-2023 | 307/SWSD | 10/05/2022 | 50 | S.G.CONSTRUCTION | 4.15 | 0 | 100
849 | Siliguri W/S Division | Siliguri Sub-Division | Supplying, fabrication, erection on suitable RCC foundation and commissioning with 3(three) months trial run of pressure type Iron Removal Plant with blower cum compressor room of internal size (3.6 M X 3.00 M) and platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Tutaram zone of Naxalbari W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. (Capacity : 30 cu.m./hr.) SL. NO. 11. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000030/2022-2023 | 542/SWSD | 16/06/2022 | 45 | MAA ENTERPRISE | 16.52 | 0 | 0
850 | Siliguri W/S Division | Siliguri Sub-Division | Laying Distribution System and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno Programme at Dayaram (Part), Kamala (Part) & Naxalbari (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kamala Zone) within Naxalbari block, Darjeeling Dist. under Siliguri Sub Division, P.H.E. Dte. Sl. No. 10. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000064/2022-2023 | 869/SWSD | 21/07/2022 | 170 | NARAYAN CH GHOSH | 69.9 | 0 | 90
851 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dayaram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Dayaram Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000074/2022-2023 | 847/SWSD | 21/07/2022 | 198 | M/S G.C. CONSTRUCTION & CO. | 83.65 | 0 | 2
852 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dhakna (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Dhakna Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 04. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000075/2022-2023 | 848/SWSD | 21/07/2022 | 70 | BUDDHADEV NAG | 67.02 | 0 | 100
853 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Chhoto Maniram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Chhota Maniram Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000077/2022-2023 | 850/SWSD | 21/07/2022 | 75 | UJJWAL ROY | 81.01 | 0 | 100
854 | Siliguri W/S Division | Siliguri Sub-Division | Supplying, Fabrication, Erection on suitable RCC foundation and Commissioning with 3 (three) months Trial Run of pressure type Iron removal plant with Blower cum Compressor room of internal size ( 3.6 M X 3.00 M ) and Platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Rathkhola Bhimram Zone of Naxalbari WS scheme at Naxalbari Block under Siliguri Sub Division, P. H. Engg. Dte. (Capacity: 15 Cu.M./hr.) Sl. No. 08. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000078/2022-2023 | 851/SWSD | 21/07/2022 | 45 | DEBRAJ ENTERPRISE | 13.82 | 0 | 0
855 | Siliguri W/S Division | Siliguri Sub-Division | Supplying, Fabrication, Erection on suitable RCC foundation and Commissioning with 3 (three) months Trial Run of pressure type Iron removal plant with Blower cum Compressor room of internal size ( 3.6 M X 3.00 M ) and Platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E.Plant with surface drain of required length at Dhakna Zone of Naxalbari WS scheme at Naxalbari Block under Siliguri Sub Division, P. H. Engg. Dte. (Capacity: 20 Cu.M./hr.) Sl. No. 09. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000079/2022-2023 | 852/SWSD | 21/07/2022 | 45 | SUBIR CH. CHOWDHURY | 14.66 | 0 | 0
856 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Geni (Part) and Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Rathkhola Bhimram Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 15. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000085/2022-2023 | 858/SWSD | 21/07/2022 | 233 | M/S G.C. CONSTRUCTION & CO. | 90 | 0 | 50
857 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Geni (Part) Kamala (Part) and Naxalbari (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kalibari Zone) under Naxalbari Block Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 16. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000086/2022-2023 | 859/SWSD | 21/07/2022 | 1086 | PALLAB BHOWAL | 129.79 | 0 | 90
858 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (D.P.R.) in connection with the augmentation of Naxalbari W/S Scheme at Naxalbari block of Siliguri Sub Division under Siliguri W/S Division, PHE Dte. in connection with Jal Jeevan Mission and Jal Swapno Programme. SL. NO. 02. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000109/2021-2022 | 819/SWSD | 13/08/2021 | 25 | ENVIROTECH SOLUTIONS | 4.85 | 0 | 100
859 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Rathkhola - Bhimram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000110/2022-2023 | 280/SSD | 26/05/2022 | 60 | M/S S.P. BISWAS | 4.18 | 0 | 60
860 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Chhota Maniram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000111/2022-2023 | 281/SSD | 26/05/2022 | 60 | A.B. GANAPATI CONSTRUCTION | 4.17 | 0 | 100
861 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Dhakna zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000112/2022-2023 | 282/SSD | 26/05/2022 | 60 | M/S S.P. BISWAS | 4.18 | 0 | 100
862 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House ( 3.65 X 2.45 ) Size with ( 1.20 X 2.10 M. ) size with Toilet, plinth protection etc. at Dayaram zone of Naxalbari Piped Water Supply Scheme at Naxalbari Block under Siliguri Sub -Division , P.H.E. Dte. in the dist.of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000113/2022-2023 | 283/SSD | 26/05/2022 | 60 | SHREYANSH AUTOMOBILE | 4.17 | 0 | 100
863 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and providing functional household tap connection under Jal Jeevan Mission and Jal Swapno Programme at Dayaram (Part) & Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Kotia Zone) under Naxalbari block, Darjeeling District, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000137/2023-2024 | 1405/SWSD | 21/08/2023 | 573 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 127.6 | 0 | 70
864 | Siliguri W/S Division | Siliguri Sub-Division | Supplying, fabrication, erection on subitable RCC foundation and commissioning with 3 (three) months trial run of pressure type Iron Removal Plant with bower cum compressor room of internal size (3.6 M X 3.00 M) and platform of size (9.00 m X 4.50 m) for resting the cylinders of I.E. Plant with surface drain of required length at Budhkaran Zone of Naxalbari W/S Scheme at Naxalbari block under Siliguri Sub Division, P.H.E. Dte. (Capacity : 15 cu.m./hr.). SL. NO. 13. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000140/2021-2022 | 2437/SWSD | 21/03/2022 | 45 | SUBIR CH. CHOWDHURY | 13.81 | 0 | 0
865 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and providing functional house hold tap connection under Jal Jeevan Mission & Jal Swapno programme at Budhkaran (Part) & Geni (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Budhkaran Zone) within Naxalbari block, Darjeeling dist. under Siliguri Sub Division, PHE Dte. SL. NO. 16. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000141/2021-2022 | 2438/SWSD | 21/03/2022 | 1412 | DEBRAJ ENTERPRISE | 92.59 | 0 | 81
866 | Siliguri W/S Division | Siliguri Sub-Division | CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60 M) SIZE WITH SANITARY & PLUMBING ARRANGEMENT AS PER MODEL APPROVED DRAWING AT BUDHKARAN TUBEWELL SITE FOR NAXALBARI PIPED WATER SUPPLY SCHEME UNDER SILIGURI W/S DIVISION, P. H. ENGINEERING DTE. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000145/2024-2025 | 2540/SWSD | 18/09/2024 | 106 | NARAYAN CH GHOSH | 5.83 | 0 | 100
867 | Siliguri W/S Division | Siliguri Sub-Division | Continuation order for hiring of 1 (one) No. Maruti Van (Non A/C) for the Superintending Engineer, North Bengal Circle-I, P.H.E. Dte. period from 01.04.2022 to 31.03.2023 i.e. 12 (twelve) months. VEHICLE NO. WB 73B/1911. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000149/2021-2022 | 2534/SWSD | 29/03/2022 | 12 | RUPA PRASAD | 1.48 | 0 | 100
868 | Siliguri W/S Division | Siliguri Sub-Division | Sinking of 06(six) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000167/2022-2023 | 1327/SWSD | 14/09/2022 | 99 | NORTH EAST CO-OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 46.37 | 0 | 100
869 | Siliguri W/S Division | Siliguri Sub-Division | Balanced work of laying distribution system along with pump connection in connection with Augmentation of Naxalbari piped water supply scheme (chhota Maniram ZOne) under Naxalbari Block, Darjeeling District under siliguri Sub-division ,P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000239/2023-2024 | 523/SSD | 18/12/2023 | 31 | UJJWAL ROY | 1.91 | 0 | 100
870 | Siliguri W/S Division | Siliguri Sub-Division | Supply installation commissioning and trial operation of electro mechanical components along with copper wound line voltage corrector for AUGMENTATION OF NAXALBARI ZONE -I and II ( Rathkhola Bhimram, Kamola Jote Budhkaran) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000255/2023-2024 | 2161/SWSD | 29/11/2023 | 30 | CHOWDHURY & BASU ENTERPRISE | 34.09 | 0 | 90
871 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system and Providing Functional House Hold Tap Connection under Jal Jeevan Mission and Jal Swapno Programme at Dhakna (Part) and Bhimram (Part) mouza in connection with Augmentation of Naxalbari Piped Water Supply Scheme (Bengaijote Zone) under Naxalbari Block, Darjeeling District under Siliguri Sub Division, P.H.E Dte. Sl. No. 03. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000265/2022-2023 | 2074/SWSD | 13/01/2023 | 85 | KAMIRUL SK & CO | 91.79 | 0 | 100
872 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000025/2022-2023 | 1455/SWSD | 29/09/2022 | 0 | Resource Division | 53.04 | 0 | 0
873 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000063/2022-2023 | 2042/SWSD | 16/12/2022 | 0 | Resource Division | 131.38 | 0 | 0
874 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for NAXALBARI PWSS (KAMALA JOTE), under NAXALBARI CCC [APPLICATION NO. 4003105316 ; Reference ID : 402974351] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00008/2023-2024 | BP/23-24/04 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
875 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for NAXALBARI PWSS (DHAKNA JOTE), under NAXALBARI CCC [APPLICATION NO. 4003105319 ; Reference ID : 402974350] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00009/2023-2024 | BP/23-24/04 | 26/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
876 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for CHHOTO MONIRAM KALUAJOTE W/S Scheme, T/W No. II, Zone-II under NAXALBARI CCC, [APPLICATION NO. 4003049226, Reference ID : 402926293] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00044/2022-2023 | BP/22-23/125 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0
877 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for RATHKHOLA BHIMRAM W/S Scheme, T/W No. III, Zone-II under NAXALBARI CCC, [APPLICATION NO. 4003049742, Reference ID : 402926292] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00045/2022-2023 | BP/22-23/125 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0
878 | Northern Mechanical | Siliguri Sub-Division | Quotation Charges New service Connection at Naxalbari PWSS,TW-VI, Near Budhkaran under NMD,PHE Dte. Application No - 4003462594 Ref Id- 403258323 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00833/2024-2025 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.34 | 0 | 0
879 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF NAXALBARI ZONE - I AND ZONE - II PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000798/2022-2023 | 112/NMD | 03/02/2023 | 30 | CHOWDHURY AND BASU ENTERPRISE | 32.88 | 0 | 100
880 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Balance work for water supply scheme for Murmudang, Kom Busty, & Lower Kolbong under Jal Jeevan Mission & JSP programme under Pull Bijanbari Block PHED-GTA. |  | Sub-Assistant Engineer | ORD/000152/2023-2024 | 880/NKWSMD | 03/08/2023 | 60 | AMRIT KUMAR SUBBA | 96.3 | 0 | 50
881 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR MURMIDANG, KOM BUSTY & LOWER KOLBONG UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  | Sub-Assistant Engineer | ORD/000221/2022-2023 | 1119/NKWSMD | 05/08/2022 | 180 | AMRIT KUMAR SUBBA | 107.92 | 0 | 50
882 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000084/2022-2023 | 1366/NKWSMD | 21/09/2022 | 0 | Resource Division | 1.49 | 0 | 0
883 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000106/2022-2023 | 1883/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.49 | 0 | 0
884 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000196/2022-2023 | 2592/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.49 | 0 | 0
885 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Relling-I & II, GP - Rungli, Block - Bijanbari Pullbazar |  | Sub-Assistant Engineer | ORD/000229/2022-2023 | 1443/NKWSMD | 28/09/2022 | 60 | SUMAN PRADHAN | 60.32 | 0 | 100
886 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000129/2022-2023 | 1905/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.94 | 0 | 0
887 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000189/2022-2023 | 2589/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.94 | 0 | 0
888 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Bhir Gaon & Dhar Gaon Gram, GP - Majua, Block - Bijanbari Pulbazar. |  | Sub-Assistant Engineer | ORD/000168/2022-2023 | 944/NKWSMD | 12/07/2022 | 120 | SUVASH RAI | 40.11 | 0 | 100
889 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000127/2022-2023 | 1903/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.05 | 0 | 0
890 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000187/2022-2023 | 2615/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.05 | 0 | 0
891 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme for balance household at Sumbuck & Kankeybong, GP - Jhepi, Block - Bijanbari Pulbazar. |  | Sub-Assistant Engineer | ORD/000175/2022-2023 | 951/NKWSMD | 12/07/2022 | 180 | SACHIN PRADHAN | 114.36 | 0 | 100
892 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000082/2022-2023 | 1364/NKWSMD | 21/09/2022 | 0 | Resource Division | 2.92 | 0 | 0
893 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000128/2022-2023 | 1904/NKWSMD | 15/12/2022 | 0 | Resource Division | 2.92 | 0 | 0
894 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000188/2022-2023 | 2616/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.92 | 0 | 0
895 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  | Sub-Assistant Engineer | BILL/00011/2023-2024 |  | 18/04/2023 | 0 | KASHYAP COMPUTERS | 0.85 | 0 | 0
896 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  | Sub-Assistant Engineer | BILL/00078/2023-2024 | BP-2023-24-40 | 11/05/2023 | 0 | KASHYAP COMPUTERS | 0.34 | 0 | 0
897 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | computer operator payment |  | Sub-Assistant Engineer | BILL/00484/2023-2024 | BP-2023-24-193 | 30/09/2023 | 0 | KASHYAP COMPUTERS | 0.51 | 0 | 0
898 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at 6th Mile Bazar Gram GP - Rampuria & Mineral Spring, Block - Pull Bijanbari |  | Sub-Assistant Engineer | ORD/000171/2022-2023 | 947/NKWSMD | 12/07/2022 | 60 | PUSHKAR GURUNG | 29.98 | 0 | 0
899 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
900 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED GHAYABARI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000080/2022-2023 | 605/NKWSMD | 26/05/2022 | 1010 | NAVRATNA CONSTRUCTION CO | 125.67 | 0 | 90
901 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
902 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00492/2023-2024 | BP-2023-24-291 | 02/11/2023 | 0 | WBSEDCL | 0.36 | 0 | 0
903 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00493/2023-2024 | BP-2023-24-292 | 02/11/2023 | 0 | WBSEDCL | 0.46 | 0 | 0
904 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00706/2023-2024 | BP-2023-24-475 | 28/01/2024 | 0 | WBSEDCL | 4.15 | 0 | 0
905 | Neorakhola W/S & Mtc.Div. | Kurseong Division | payment for wbsedcl | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00707/2023-2024 | BP-2023-24-476 | 28/01/2024 | 0 | WBSEDCL | 5.49 | 0 | 0
906 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 100
907 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
908 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000010/2024-2025 | 1781/NKWSMD | 23/09/2024 | 0 | Resource Division | 0.54 | 0 | 0
909 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000155/2022-2023 | 2373/NKWSMD | 03/02/2023 | 0 | Resource Division | 4.21 | 0 | 0
910 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Dilaram TE (Dilaram Bazar habitation) under Kurseong Sub-Division PHED, GTA. |  |  | ORD/000111/2022-2023 | 791/NKWSMD | 30/06/2022 | 60 | JIWAN TAMANG | 5.96 | 0 | 0
911 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 1294/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.4 | 0 | 0
912 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Gothals siding (Kopchey and Paglabung Gothals Siding habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | ORD/000113/2022-2023 | 793/NKWSMD | 30/06/2022 | 60 | NAVRATNA CONSTRUCTION CO | 14.52 | 0 | 98
913 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | RTOR000052/2022-2023 | 1296/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.19 | 0 | 0
914 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer 4,Assistant Engineer4 |  | ORD/000122/2022-2023 | 802/NKWSMD | 30/06/2022 | 60 | PHURBA RUMBA | 20.05 | 0 | 100
915 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer 4,Assistant Engineer4 |  | RTOR000054/2022-2023 | 1298/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.66 | 0 | 0
916 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under Jal Jeevan Mission & JSP Programme including Retrofitting work for PWS scheme for Cricket Bazar Tindharay Mahanadi GP Block - Kurseong Block. | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000115/2022-2023 | 795/NKWSMD | 30/06/2022 | 610 | BIKASH TAMANG | 12.59 | 0 | 1
917 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000057/2022-2023 | 1301/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.83 | 0 | 0
918 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Bagmara Mahanadi GP Block - Kurseong Block. | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000216/2022-2023 | 1110/NKWSMD | 05/08/2022 | 60 | MS. SURYA I PVT. LTD COMPANY | 9.17 | 0 | 0
919 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000070/2022-2023 | 1314/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.36 | 0 | 0
920 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for 14 Mile Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000120/2022-2023 | 800/NKWSMD | 30/06/2022 | 60 | PREM KUMAR PRADHAN | 10.87 | 0 | 100
921 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000065/2022-2023 | 1309/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.63 | 0 | 0
922 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR SALU TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000252/2022-2023 | 1530/NKWSMD | 18/10/2022 | 840 | VINAYAK CONSTRUCTION | 318.85 | 0 | 100
923 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000121/2022-2023 | 1898/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.32 | 0 | 0
924 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000180/2022-2023 | 2574/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.32 | 0 | 0
925 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at 3 Nos Montiviote TE with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer4,Sub-Assistant Engineer | ORD/000211/2022-2023 | 984/NKWSMD | 12/07/2022 | 60 | PRASANT NIROLA | 17.52 | 0 | 100
926 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer4,Sub-Assistant Engineer | RTOR000057/2023-2024 | 530/NKWSMD | 13/06/2023 | 0 | Resource Division | 2.05 | 0 | 0
927 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer4,Sub-Assistant Engineer | RTOR000149/2022-2023 | 2069/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.22 | 0 | 0
928 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | permission fro laying 80mm dia GI Pipeline along the hill side of Darjeeling Ghoom Bhanjang Bijanbari Road |  | Junior Engineer-IV,Sub-Assistant Engineer | BILL/00206/2022-2023 | BP-2022-23-426 | 30/03/2023 | 0 | NEORAKHOLA W/S & MTC. DIV. | 10.35 | 0 | 0
929 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Proposed Gravity Based Water Supply Scheme for Mariabong Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000236/2022-2023 | 1451/NKWSMD | 29/09/2022 | 1000 | GARGO TRADERS | 973.62 | 0 | 100
930 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000114/2022-2023 | 1891/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.68 | 0 | 0
931 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000173/2022-2023 | 2609/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.68 | 0 | 0
932 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum work order for Construction of 250 Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site of Ghusuru Piped Water Supply Scheme under Naxalbari Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000183/2024-2025 | 3026/SWSD | 13/11/2024 | 618 | M/S G.C. CONSTRUCTION & CO. | 89.68 | 0 | 25
933 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system along with boring of new tubewells, construction of pump house, boundary walls at 3rd and 4th tubewell site and providing FHTC at Uttam Chand, Hoda Bhitar Chhat, Uttam Chander Chhat, Mudir Jangal, Satbhaiya, Ghusuru, Raghuram, Raghuramer Chhat, Bhaktaram mouza in connection with rejuvenation of GHUSURU PIPED WATER SUPPLY SCHEME under JJM at Naxalbari block, Darjeeling District under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000267/2022-2023 | 2365/SWSD | 24/01/2023 | 90 | SUBIR CH. CHOWDHURY | 142.14 | 0 | 91
934 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000024/2023-2024 | 1808/SWSD | 30/09/2023 | 0 | Resource Division | 9.89 | 0 | 0
935 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000049/2022-2023 | 2029/SWSD | 16/12/2022 | 0 | Resource Division | 1.97 | 0 | 0
936 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for rrjuvenation of Ghusuri PWSS, TW No. I, NAXALBARI CCC [APPLICATION NO. 4003144975 ; Reference ID : 403013463] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00041/2023-2024 | BP/23-24/10 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
937 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for Rejuvenation of Ghusuri PWSS, TW No. II, NAXALBARI CCC [APPLICATION NO. 4003144980 ; Reference ID : 403013029] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00042/2023-2024 | BP/23-24/10 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
938 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GHUSURU PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000055/2023-2024 | 549/NMD | 15/05/2023 | 30 | M/S B.ENTERPRISE | 23.18 | 0 | 100
939 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Mohorgaon Tea Garden Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000159/2022-2023 | 289/SSD | 26/05/2022 | 20 | SUBHANKAR GHOSH | 3.3 | 0 | 100
940 | Siliguri W/S Division | Siliguri W/S Division | Work Order for Construction of 200 cu.m capacity Elevated Reservoir 20 m staging height allied with laying of distribution pipeline, Rising Main, Construction of 3 nos Big dia rig bore tube well by ODEX 165, Pump House (5.4 X 3.60 m), Iron Elemination Plant, Boundary Wall including Functional Household Tap Connection at MOHORGAON TEA GARDEN Piped Water Supply Scheme (Zone I & II) under Matigara Block, Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000197/2023-2024 | 1977/SWSD | 26/10/2023 | 885 | EASHAN POLYMERS PRIVATE LIMITED | 492.88 | 0 | 35
941 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000036/2023-2024 | 2303/SWSD | 12/12/2023 | 0 | Resource Division | 2.72 | 0 | 0
942 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000041/2023-2024 | 62/SWSD | 09/01/2024 | 0 | Resource Division | 6.3 | 0 | 0
943 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000071/2022-2023 | 2050/SWSD | 16/12/2022 | 0 | Resource Division | 24.61 | 0 | 0
944 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
945 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for MOHORGON TEA GARDEN, T/W No.II, under MATIGARA CCC, [APPLICATION NO. 4003316001, Reference ID : 403143726] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01944/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.06 | 0 | 0
946 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for MOHORGON TEA GARDEN, T/W No. I, under MATIGARA CCC, [APPLICATION NO. 4003315986, Reference ID : 403143724] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01945/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.4 | 0 | 0
947 | Northern Mechanical | Siliguri W/S Division | Infrastructure Cost for MOHORGAON T/W-III, under PRADHAN NAGAR CCC , [APPLICATION NO. 4003337401, Reference ID : 403161193] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02025/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.02 | 0 | 0
948 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MOHORGON TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I,IIand (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000787/2023-2024 | 1651/NMD | 29/09/2023 | 30 | M/S SAJAHAN CHOWDHURY | 23.8 | 0 | 100
949 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR KARBIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000291/2022-2023 | 2148/NKWSMD | 20/01/2023 | 240 | M/S. ASHOK KUMAR PERIWAL | 390.86 | 0 | 50
950 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000202/2022-2023 | 2551/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.08 | 0 | 0
951 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR GITINGYA TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000277/2022-2023 | 2004/NKWSMD | 23/12/2022 | 912 | ABHINAY CHETTRI | 306.39 | 0 | 100
952 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000229/2022-2023 | 2584/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.05 | 0 | 0
953 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SONADA FOREST UNDER KURSEONG DIVISION. SCHEME CODE - 12983 TSM/012820 | Assistant Engineer 4 |  | BILL/00089/2024-2025 | BP-2024-25-96 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 8.41 | 0 | 0
954 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Continuation Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 | Assistant Engineer 4 |  | ORD/000252/2023-2024 | 1469/NKWSMD | 01/12/2023 | 62 | THE ELECTRIC SPHERE | 0.41 | 0 | 0
955 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SONADA FOREST PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4 |  | ORD/000308/2022-2023 | 2472/NKWSMD | 06/02/2023 | 1005 | M/S. ASHOK KUMAR PERIWAL | 1198.11 | 0 | 85
956 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 |  | RTOR000061/2023-2024 | 571/NKWSMD | 22/06/2023 | 0 | Resource Division | 7.02 | 0 | 0
957 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 |  | RTOR000203/2022-2023 | 2595/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.26 | 0 | 0
958 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system along with construction of pump houses with toilet, boundary walls at tube well sites, laying of rising main, providing FHTC with platform and other allied works under Jal Jeevan Mission (JJM) for MANJHA TEA GARDEN Piped Water Supply Scheme under Naxalbari block, Darjeeling District under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000271/2022-2023 | 2504/SWSD | 10/02/2023 | 324 | BUDDHADEV NAG | 154.25 | 0 | 90
959 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Manja Tea Garden Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000322/2022-2023 | 312/SSD | 14/06/2022 | 20 | ENVIROTECH SOLUTIONS | 2.28 | 0 | 100
960 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000042/2022-2023 | 2021/SWSD | 15/12/2022 | 0 | Resource Division | 2.39 | 0 | 0
961 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000059/2023-2024 | 87/SWSD | 10/01/2024 | 0 | Resource Division | 3.3 | 0 | 0
962 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MANJHA T.G., T.W. No. III under NAXALBARI CCC, [APPLICATION NO. 4003194667, Reference ID : 403046932] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00594/2023-2024 | BP/23-24/79 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.87 | 0 | 0
963 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MANJHA T.G., T.W. No. I under NAXALBARI CCC, [APPLICATION NO. 4003194643, Reference ID : 403046929] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00595/2023-2024 | BP/23-24/79 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.19 | 0 | 0
964 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MANJHA T.G., T.W. No. II under NAXALBARI CCC, [APPLICATION NO. 4003194663, Reference ID : 403046923] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00596/2023-2024 | BP/23-24/79 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0
965 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MANJA TEA GARDEN PIPED WATER SUPPLY SCHEME ,(Zone-I) TW No. I and (Zone-II) TW No. I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000168/2023-2024 | 1210/NMD | 26/07/2023 | 30 | M/S PALIDEB ENGINEERING WORKS | 23.21 | 0 | 100
966 | Siliguri W/S Division | Siliguri Sub-Division | QUOTATION IVO SHIFTING OF A PART OF HNSQUA 11 KV FEEDER EMANETED FRAM BAGDOGRA 33/11 KV SUBSTATION IN THE AREA OF PHE DTE HANSQUA WATER PUMP HOUSE | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00352/2023-2024 | BP-2023-24-146 | 03/01/2024 | 0 | WBSEDCL | 2.59 | 0 | 0
967 | Siliguri W/S Division | Siliguri Sub-Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF HANSQUA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000065/2023-2024 | 258/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.01 | 0 | 100
968 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 100 cu.m. capacity R.C.C. Elevated Reservoir of 20 Mtrs. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells by ODEX-165 method, construction of pump house with toilet, boundary wall at head works and 2nd tubewell site with necessary interconnection, providing FHTC with platform and other allied works under Jal Jeevan Mission for Augmentation of HANSQUA TEA GARDEN Piped WS Scheme of Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000315/2022-2023 | 2919/SWSD | 24/03/2023 | 882 | SUBIR CH. CHOWDHURY | 296.64 | 0 | 90
969 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000069/2022-2023 | 2048/SWSD | 16/12/2022 | 0 | Resource Division | 16.99 | 0 | 0
970 | Northern Mechanical | Siliguri Sub-Division | "New Service Connection Charge for HANSQUA TEA GARDEN TW-I " APPLICATION NO.4003194521 Reference ID : 403046887 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00448/2024-2025 | BP/24-25/99 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0
971 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for HANSQUA TEA GARDEN, T.W. No. I under BAGDOGRA CCC, [APPLICATION NO. 4003194521, Reference ID : 403046887] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00591/2023-2024 | BP/23-24/76 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.64 | 0 | 0
972 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for HANSQUA TEA GARDEN, T/W No. II, under BAGDOGRA CCC [APPLICATION NO. 4003291262 ; Reference ID : 403123837] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01671/2023-2024 | BP/23-24/201 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.1 | 0 | 0
973 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for HANSQUA, T/W No. I, under KADAMTALA CCC, [APPLICATION NO. 100000095265, Reference ID : 860287415] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01946/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.59 | 0 | 0
974 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
975 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF HANSQUA TEA GARDEN AREA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000811/2023-2024 | 1668/NMD | 29/09/2023 | 30 | M/S SIMARR | 10.31 | 0 | 100
976 | Northern Mechanical | Siliguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000996/2024-2025 | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0
977 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001071/2024-2025 | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0
978 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BAGULAHAGI & BHATTAGACHH PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000057/2023-2024 | 250/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.92 | 0 | 100
979 | Siliguri W/S Division | Siliguri W/S Division | Laying Rising main, laying distribution pipeline with functional household Tap connection (FHTC), construction of two number pump house (5.40 X 3.60 m), Iron Elimination plant (IEP) with Blower Room and sinking of 2 (two) Nos.Tube Well (ODEX- 165 method) and boundary wall for BAGULAHAGI and BHATTAGACHH PWSS Block - Kharibari, Dist : Darjeeling under Siliguri Sub Division , P.H.E. Dte. Sl No 07. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000076/2023-2024 | 867/SWSD | 14/07/2023 | 120 | NARENDRA KUMAR | 197.75 | 0 | 25
980 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000066/2022-2023 | 2045/SWSD | 16/12/2022 | 0 | Resource Division | 16.3 | 0 | 0
981 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
982 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BAGULAHAGI & BHATTAGACHH, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003319706, Reference ID : 403147081] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01933/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.67 | 0 | 0
983 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BAGULAHAGI & BHATTAGACHH, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319825, Reference ID : 403147074] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/01934/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.77 | 0 | 0
984 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
985 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAGULAHAGI and BHATTAGACHH PWSS, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000810/2023-2024 | 1667/NMD | 29/09/2023 | 531 | MALAY KUMAR SAHA | 11.86 | 0 | 100
986 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0
987 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/001070/2024-2025 | 38/NMD | 06/01/2025 | 30 | DEY ENTERPRISE(MALDA) | 15.33 | 0 | 0
988 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | TAKDAH FOREST WATER SUPPLY SCHEME UNDER JAL JEEWAN MISSION |  | Sub-Assistant Engineer | BILL/00388/2024-2025 | BP-2024-25-283 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 7 | 0 | 0
989 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TUKDAH FOREST PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000030/2023-2024 | 108/NKWSMD | 28/04/2023 | 1347 | RAMESH AGARWAL | 108.34 | 0 | 95
990 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000025/2023-2024 | 244/NKWSMD | 12/05/2023 | 0 | Resource Division | 0.77 | 0 | 0
991 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR KOLBONG KHASMAHAL PIPED WATER SUPPLY SCHEME UNDER BLOCK : RANGLI RANGLIOT, DISTRICT: DARJEELING. |  | Sub-Assistant Engineer | ORD/000045/2023-2024 | 189/NKWSMD | 04/05/2023 | 772 | SRINIWAS AGARWAL | 212.21 | 0 | 100
992 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000037/2023-2024 | 324/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.88 | 0 | 0
993 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme For Upper & Lower Sumbuk Piped Water Supply Scheme in Pulbazar Block Under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000059/2023-2024 | 418/NKWSMD | 05/06/2023 | 360 | HARI PRASAD CHETTRI | 278.38 | 0 | 100
994 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000049/2023-2024 | 444/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.74 | 0 | 0
995 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAHARANI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000047/2025-2026 | 636/NKWSMD | 05/05/2025 | 120 | SURAJMULL PRABHUDAYAL | 16.26 | 0 | 100
996 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MAHARANI TEA GARDEN PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000340/2022-2023 | 2737/NKWSMD | 03/03/2023 | 805 | SRINIWAS AGARWAL | 440.47 | 0 | 65
997 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | RTOR000262/2022-2023 | 2773/NKWSMD | 10/03/2023 | 0 | Resource Division | 3.01 | 0 | 0
998 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
999 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BIJANBARI PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000006/2023-2024 | 89/NKWSMD | 27/04/2023 | 817 | VAISHNO CONSTRUCTION | 339.14 | 0 | 90
1000 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000038/2023-2024 | 325/NKWSMD | 24/05/2023 | 0 | Resource Division | 1.84 | 0 | 0
1001 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SINGALILA FOREST PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000003/2023-2024 | 87/NKWSMD | 27/04/2023 | 858 | NIMA SHERPA | 364.9 | 0 | 100
1002 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SINGALILA UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PUL BIJANBARI BLOCK. |  | Sub-Assistant Engineer | ORD/000158/2024-2025 | 2368/NKWSMD | 20/12/2024 | 90 | RINZI SHERPA | 29 | 0 | 0
1003 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000003/2023-2024 | 151/NKWSMD | 03/05/2023 | 0 | Resource Division | 0.47 | 0 | 0
1004 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000015/2023-2024 | 212/NKWSMD | 10/05/2023 | 0 | Resource Division | 0.47 | 0 | 0
1005 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1006 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme For St Marys and Geothals | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00647/2024-2025 | BP-2024-25-458 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 2.52 | 0 | 0
1007 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED ST. MARYS AND GOETHALS PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000331/2022-2023 | 2670/NKWSMD | 01/03/2023 | 180 | SITA SHARMA | 300.54 | 0 | 60
1008 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000258/2022-2023 | 2770/NKWSMD | 10/03/2023 | 0 | Resource Division | 4.4 | 0 | 0
1009 | Neorakhola W/S & Mtc.Div. |  | Augmentation of Water Supply Scheme for Montiviot Tea Garden Piped Water Supply Scheme, Block: Kurseong, District: Darjeeling. |  |  | ORD/000014/2024-2025 | 979/NKWSMD | 18/06/2024 | 60 | SUNRISE ENTERPRISES | 24.35 | 0 | 100
1010 | Neorakhola W/S & Mtc.Div. |  | Augmentation for ground water Reservoir of capacity 20 ML at Sepoydhura (Near Woodcut) Kurseong under PHED, Kusseong Sub- Division, GTA. |  |  | ORD/000056/2025-2026 | 824/NKWSMD | 09/06/2025 | 365 | INTERIOR'S NEST | 411.05 | 0 | 0
1011 | Neorakhola W/S & Mtc.Div. |  | Ground Water Reservoir of 20 ML At Sepoydhura Near Woodcut Under Kurseong Division, P.H.E.D-GTA. |  |  | ORD/000227/2023-2024 | 1288/NKWSMD | 17/10/2023 | 928 | INTERIOR'S NEST | 2445.49 | 0 | 35
1012 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1013 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR HUM TUKDAH KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000076/2023-2024 | 674/NKWSMD | 12/07/2023 | 515 | RAMESH AGARWAL | 1210.81 | 0 | 100
1014 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000275/2023-2024 | 1595/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1015 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000064/2023-2024 | 760/NKWSMD | 19/07/2023 | 0 | Resource Division | 9.95 | 0 | 0
1016 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bara Gharia Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000160/2022-2023 | 298/SSD | 01/06/2022 | 20 | SUBHANKAR GHOSH | 3.03 | 0 | 100
1017 | Siliguri W/S Division | Siliguri Sub-Division | Work order construction of 200 cu.m capacity R.C.C. elevated reservoir, 20 mtrs. staging height at the head works site, laying rising main, laying distribution pipe line with functional household tap connection (FHTC), construction of pump house (5.40 X 3.60m) and pump house (3.60 X 3.00m) without sanitary and plumbing arrangement, iron elemination plant (IEP) with blower room and soil investigation at H/W site for Bara Gharia PWSS, block Matigara, Dist - Darjeeling under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000180/2023-2024 | 1731/SWSD | 21/09/2023 | 225 | CAPITAL ENGINEERS | 338.72 | 0 | 0
1018 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000013/2022-2023 | 1376/SWD | 21/09/2022 | 0 | Resource Division | 6.69 | 0 | 0
1019 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000030/2023-2024 | 2289/SWSD | 11/12/2023 | 0 | Resource Division | 5 | 0 | 0
1020 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000076/2022-2023 | 2055/SWSD | 16/12/2022 | 0 | Resource Division | 54.77 | 0 | 0
1021 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1022 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PIPED WATER SUPLY SCHEME, TW No.- I AND II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000792/2023-2024 | 1656/NMD | 29/09/2023 | 30 | M/S PARITOSH BHOWMICK AND CO. | 11.49 | 0 | 50
1023 | Siliguri W/S Division | Siliguri Sub-Division | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division. Month of september 2024 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00299/2024-2025 | BP-2024-25-109 | 04/10/2024 | 0 | SONA PETROL PUMP | 0.32 | 0 | 0
1024 | Siliguri W/S Division | Siliguri Sub-Division | Additional laying of 90mm dia pipeline for FHTC Jal swapno programme of Madhya Bansgaon w/s scheme under Siliguri subdivision, PHE. Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000261/2022-2023 | 2064/SWSD | 11/01/2023 | 30 | NARENDRA KUMAR | 4.42 | 0 | 100
1025 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection under JAl Swapno Programme for Uttar Palash & Dakshin Palash area of Palash mouza of Kalkut Piped Water Supply Scheme at Matigar Block under Siliguri Sub-Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000015/2021-2022 | 711/SWSD | 03/08/2021 | 40 | ARUN KUMAR SHRIVASTAVA | 19.62 | 0 | 100
1026 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009297 SM Code-SM/08931 |  | Sub-Assistant Engineer | ORD/000042/2022-2023 | 524/NKWSMD | 25/05/2022 | 60 | RAMESH PRADHAN AND CO. | 6.23 | 0 | 100
1027 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000037/2022-2023 | 1264/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.22 | 0 | 0
1028 | Siliguri W/S Division | Siliguri W/S Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
1029 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system (Part-A) at Tari habitation for Augmentation of Bairatisal and adjoining mouzas (Zone-III) Water Supply Scheme within Matigara block under Siliguri W/S Division, P.H.E. Dte. Sl. No. 12. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000065/2022-2023 | 870/SWSD | 21/07/2022 | 85 | M/S G.C. CONSTRUCTION & CO. | 92.37 | 0 | 90
1030 | Siliguri W/S Division | Siliguri W/S Division | Soil Investigation of Bairatisal Zone III PWSS for Construction of 600 cum OHR under Siliguri Sub-Division P.H.E. Dte under Matigara Block. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000109/2022-2023 | 393/SSD | 20/07/2022 | 20 | SUBIR CH. CHOWDHURY | 1.03 | 0 | 100
1031 | Siliguri W/S Division | Siliguri W/S Division | Construction of 600 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site including rising mains, distribution system, pump house (3.65 X 2.45) size, IEP, boundary wall and providing Functional Household Tap Connection (FHTC) for augmentation of BAIRATISAL and adjoining mouzas (Zone-III) Water Supply Scheme within Matigara block under Siliguri W/S Division, P.H.E. Dte. SL. NO. B. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000149/2022-2023 | 970/SWSD | 01/08/2022 | 1095 | M/S KAMAK ENGINEERS & CO | 584.1 | 0 | 90
1032 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 02(Two) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different TW Sites as mentioned in ANNEXURE-A under different Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000168/2022-2023 | 1328/SWSD | 14/09/2022 | 25 | RANJEET SINGH BENIWAL | 15.46 | 0 | 88
1033 | Siliguri W/S Division | Siliguri W/S Division | Continuation order for hiring of 1 (one) no. well maintained diesel consumed luxury cab on monthly hired basis preferably MAXI CAB (A/C) with engine capacity less than or equal to 2000 CC for office of the Chief Engineer (Civil), Northern Zone, P.H.E. Dte., Vivekananda Bhawan (2nd floor) Hill Cart Road, Siliguri (for Assistant Chief Engineer, Northern Zone (Civil), P.H.E. Dte. for the period from 01.03.2022 to 31.08.2022. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000262/2021-2022 | 2269/SWSD | 24/02/2022 | 6 | OM TRAVELS | 0.88 | 0 | 100
1034 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000016/2021-2022 | 2174/SWSD | 11/02/2022 | 0 | Resource Division | 112.07 | 0 | 0
1035 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000022/2022-2023 | 1452/SWSD | 29/09/2022 | 0 | Resource Division | 28.55 | 0 | 0
1036 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000041/2022-2023 | 2012/SWSD | 14/12/2022 | 0 | Resource Division | 7.18 | 0 | 0
1037 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000298/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 38.4 | 0 | 0
1038 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer(Civil) | VCH/000888/2021-2022 | BP-2021-22-106 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.99 | 0 | 0
1039 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for PURBA RANGIA W/S Scheme, T/W No. I, Zone-III under BAIRATISAL CCC, [APPLICATION NO. 4003058151, Reference ID : 402932775] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00049/2022-2023 | BP/22-23/123 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0
1040 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for PURBA RANGIA W/S Scheme, T/W No. II, Zone-III under BAIRATISAL CCC, [APPLICATION NO. 4003058171, Reference ID : 402932779] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00050/2022-2023 | BP/22-23/123 | 16/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0
1041 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BAIRATISAL ZONE - III (TW No. I and II) PIPED WATER SUPPLY SCHEME, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000796/2022-2023 | 110/NMD | 03/02/2023 | 30 | B.B. CONCERNED | 23.55 | 0 | 100
1042 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Engagement of 1no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna , | Assistant Engineer | Sub-Assistant Engineer | BILL/00288/2023-2024 |  | 27/09/2023 | 0 | RAJ BUILDERS | 0.85 | 0 | 0
1043 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | computer operator payment | Assistant Engineer | Sub-Assistant Engineer | BILL/00485/2023-2024 | BP-2023-24-192 | 30/09/2023 | 0 | RAJ BUILDERS | 0.85 | 0 | 0
1044 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000216/2022-2023 | 2563/NKWSMD | 17/02/2023 | 0 | Resource Division | 12.04 | 0 | 0
1045 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JaL Jeevan Mission and Jal Swapna Programme for Piped Wat¿r Supply Scheme for Ringtong godam dhura gorabari margret's hope GP under Kurseong Sub-Division P HED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000015/2022-2023 | BP-2022-23-14 | 11/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 5.35 | 0 | 0
1046 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JaL Jeevan Mission and Jal Swapna Programme for Piped Water Supply Scheme for Upper Pachang lower Sonada GP-II under Kurseong Sub-Division P HED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000016/2022-2023 | BP-2022-23-15 | 11/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 4.67 | 0 | 0
1047 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Pankhabari & sorroundingarea St Mary's GP-Ill under Kurseong Sub-Division PHED, GTA. | Assistant Engineer | Sub-Assistant Engineer | VCH/000019/2022-2023 | BP-2022-23-18 | 20/04/2022 | 0 | SURAJ LAMA | 9.17 | 0 | 0
1048 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional House hold Tap Connection under Jal Jeev an Mission and Jal Swapna Programme for Piped water Supply Scheme for Longview Tarai 34 & satt Ghurnt, St Mary's GP-Ill under Kurseong Sub-Division PHED. GTA. | Assistant Engineer | Sub-Assistant Engineer | VCH/000021/2022-2023 | BP-2022-23-20 | 20/04/2022 | 0 | SURAJ LAMA | 6.21 | 0 | 0
1049 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programe for Piped Water Supply Scheme for Upper Prashanti Gram & Chatakpur Upper Sonada GP under Kurseong Sub-Division PHED, | Assistant Engineer | Sub-Assistant Engineer | VCH/000025/2022-2023 | BP-2022-23-24 | 20/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 6.92 | 0 | 0
1050 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission an.d Jal Swapno Programme for Piped Water Supply Scheme for D.B Road Ekta Valley Lowe r Sonada GP II under Kurseong Sub-Division PHED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000027/2022-2023 | BP-2022-23-26 | 20/04/2022 | 0 | KAMAKHYA CONSTRUCTION | 6.46 | 0 | 0
1051 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Longview T.E, St. Mary - Ill GP under Kurseong Sub-Divisi on PHED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000051/2022-2023 | BP-2022-23-39 | 06/05/2022 | 0 | SURAJ LAMA | 21.74 | 0 | 0
1052 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for upper Sirubari, Ghyabari GP I under Kurseong Sub-Division PHED, GTA | Assistant Engineer | Sub-Assistant Engineer | VCH/000160/2022-2023 | BP-2022-23-123 | 23/08/2022 | 0 | NAVRATNA CONSTRUCTION CO | 14.53 | 0 | 0
1053 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling | Assistant Engineer | Sub-Assistant Engineer | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
1054 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Mini Piped Water Supply Scheme for South Sukna and Choklong under Kurseong Division. Scheme Code - 10788 TSM/010472 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00092/2024-2025 | "BP-2024-25-99 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.91 | 0 | 0
1055 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00167/2023-2024 | BP-2023-24-123 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1056 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00168/2023-2024 | BP-2023-24-124 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1057 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00169/2023-2024 | BP-2023-24-125 | 28/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1058 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00170/2023-2024 | BP-2023-24-126 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1059 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00171/2023-2024 | BP-2023-24-122 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1060 | Neorakhola W/S & Mtc.Div. | Kurseong Division | MINI PIPED WATER SUPPLY SCHEME FOR FIVE NUMBER OF VILLAGES UNDER KURSEONG, MIRIK BLOCK, DISTRICT OF DARJEELING. [TSM NO -10472] 1. Sukna Forest(Sukna Forest South). 2. Choklong Forest. 3. Panighata(panighata 14 number ward, 10 number line). 4. PanthabariForest(Naya Basti 1). 5. Panthabari Forest(Naya Basti 3). | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000085/2022-2023 | 607/NKWSMD | 26/05/2022 | 1203 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 242.87 | 0 | 100
1061 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000079/2022-2023 | 1291/NKWSMD | 09/09/2022 | 0 | Resource Division | 2.35 | 0 | 0
1062 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000154/2022-2023 | 2372/NKWSMD | 03/02/2023 | 0 | Resource Division | 2.35 | 0 | 0
1063 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Piped Water Supply Scheme for Jhepi & Gurdung under Jal Jeevan Mission and Jal Swapno Programme. |  | Sub-Assistant Engineer | ORD/000138/2022-2023 | 818/NKWSMD | 30/06/2022 | 240 | VINAYAK CONSTRUCTION | 303.13 | 0 | 100
1064 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000083/2022-2023 | 1365/NKWSMD | 21/09/2022 | 0 | Resource Division | 1.9 | 0 | 0
1065 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000105/2022-2023 | 1882/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.9 | 0 | 0
1066 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000165/2022-2023 | 2570/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.9 | 0 | 0
1067 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Manebhanjyang Bazar, Panchyat - Sukhia Simana Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000170/2022-2023 | 946/NKWSMD | 12/07/2022 | 60 | MOHAN MUKHIA | 48.83 | 0 | 0
1068 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000102/2022-2023 | 1911/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.54 | 0 | 0
1069 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under JJM & JSP Programme including extension work for PWS Scheme for Upper & Lower Barbotia, Gram Panchyat -Rishihat Bloomfield, Block Bijanbari -PullBazar. TSM No. 009473 SM Code-SM/08932 |  | Sub-Assistant Engineer | ORD/000035/2022-2023 | 498/NKWSMD | 24/05/2022 | 60 | PROSENJIT BASAK | 18.21 | 0 | 100
1070 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000125/2022-2023 | 1901/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.86 | 0 | 0
1071 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000185/2022-2023 | 2580/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.86 | 0 | 0
1072 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED RONG TONG 12 MILE PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000077/2022-2023 | 600/NKWSMD | 26/05/2022 | 825 | NARAYAN THAPA | 83.04 | 0 | 51
1073 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1074 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00488/2023-2024 | BP-2023-24-295 | 02/11/2023 | 0 | WBSEDCL | 6.14 | 0 | 0
1075 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00489/2023-2024 | BP-2023-24-296 | 02/11/2023 | 0 | WBSEDCL | 4.87 | 0 | 0
1076 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation Of ODEX Tube Well based 02(Two) number of pipe water supply Scheme having provision of 2(Two) number of RCC OHR viz 300 Cum & 200Cum and other related works for 6(Six) villages in GTA Area. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000094/2022-2023 | 825/NKWSMD | 30/06/2022 | 900 | M/S KAMAK ENGINEERS AND CO. | 783.01 | 0 | 100
1077 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
1078 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000161/2022-2023 | 2375/NKWSMD | 03/02/2023 | 0 | Resource Division | 9.18 | 0 | 0
1079 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | :Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Linseybong, Gram Panchyat -Lodhuma-I, Block Bijanbari -PullBazar. TSM No. 009471 SM Code-SM/08926 |  | Sub-Assistant Engineer | ORD/000108/2022-2023 | 629/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 16.59 | 0 | 70
1080 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000039/2022-2023 | 1269/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.17 | 0 | 0
1081 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | ADDITIONAL WORK FOR GRAVITY BASED WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PIPED WATER SUPPLY SCHEME, BLOCK: JORE BUNGALOW SUKHIAPOKHRI, DISTRICT: DARJEELING UNDER DARJEELING DIVISION, P.H.E-GTA. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000042/2025-2026 | 647/NKWSMD | 05/05/2025 | 60 | DAJUBHAI HARDWARE | 22.9 | 0 | 0
1082 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR LINGIA TEA GARDEN PWSS, BLOCK : JORE BUNGALOW-SUKHIAPOKHRI, DISTRICT : DARJEELING |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000259/2022-2023 | 1622/NKWSMD | 03/11/2022 | 815 | VINAYAK CONSTRUCTION | 633.65 | 0 | 100
1083 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000193/2022-2023 | 2581/NKWSMD | 17/02/2023 | 0 | Resource Division | 2.75 | 0 | 0
1084 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden (Khundrukey Busty, Lower Chimney, Majuwa Busty, Mohan Majuwa, Titney Busty habitation) under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000114/2022-2023 | 794/NKWSMD | 30/06/2022 | 960 | MS JAGANNATH PRASAD | 11.97 | 0 | 55
1085 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000053/2022-2023 | 1297/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.07 | 0 | 0
1086 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Kalimati Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | ORD/000134/2022-2023 | 814/NKWSMD | 30/06/2022 | 60 | SWAD CONSTRUCTION | 12.14 | 0 | 0
1087 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer5 |  | RTOR000060/2022-2023 | 1304/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.34 | 0 | 0
1088 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS scheme fro Soureni Bazar: Gram Panchyat- Soureni-I, Block -Mirik TSM No. 009309 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000016/2022-2023 | 782/NKWSMD | 30/06/2022 | 60 | KAMAL PRADHAN | 22.21 | 0 | 100
1089 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS scheme at Chowandhura Gram Panchyat Soureni-I Block Mirik TSM No. 009303 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000011/2022-2023 | 789/NKWSMD | 30/06/2022 | 915 | KAMAL PRADHAN | 11.04 | 0 | 100
1090 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PULUNGDONG TEA ESTATE VILLAGE WATER SUPPLY SCHEME UNDER JOREBUNGLOW SUKHIAPOKHARI BLOCK. |  | Junior Engineer-VI | ORD/000078/2023-2024 | 677/NKWSMD | 12/07/2023 | 180 | SATHI CONSTRUCTION COMPANY | 239.24 | 0 | 100
1091 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PULUNGDUNG TEA ESTATE PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING. |  | Junior Engineer-VI | ORD/000146/2024-2025 | 2349/NKWSMD | 19/12/2024 | 90 | SATHI CONSTRUCTION COMPANY | 47.86 | 0 | 0
1092 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-VI | RTOR000067/2023-2024 | 762/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.62 | 0 | 0
1093 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 200 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Main construction of 4 nos big dia rig bore tube well by ODEX - 165, Pump House (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plant , Boundary Wall including Functional Household Tap Connection at HETMURI Piped Water Supply Scheme (ZONE I , II & III) under Phansidewa Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000116/2023-2024 | 1212/SWSD | 11/08/2023 | 867 | K.R.ENTERPRISE | 577.26 | 0 | 10
1094 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Hetmuri Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000157/2022-2023 | 287/SSD | 26/05/2022 | 20 | SUBHANKAR GHOSH | 3.54 | 0 | 100
1095 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000050/2023-2024 | 75/SWSD | 10/01/2024 | 0 | Resource Division | 11.05 | 0 | 0
1096 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000077/2022-2023 | 2056/swsd | 16/12/2022 | 0 | Resource Division | 23.32 | 0 | 0
1097 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1098 | Central Drilling | Siliguri Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
1099 | Northern Mechanical | Siliguri Sub-Division | New service connection at Hetmuri Z-II ,TW-II under NMD, PHE dte. Application No- 4003425299 Ref. Id- 403230924 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00417/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.45 | 0 | 0
1100 | Northern Mechanical | Siliguri Sub-Division | New service connection at Hetmuri Z-II ,TW-I under NMD, PHE dte. Application No- 4003425334 Ref. Id- 403230933 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00418/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.63 | 0 | 0
1101 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for HETMURII, T/W No. I, under PHANSIDEWAI CCC [APPLICATION NO. 4003293269 , Reference ID : 403129587] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01781/2023-2024 | BP/23-24/259 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.57 | 0 | 0
1102 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for HETMURII, T/W No. II, under PHANSIDEWAI CCC [APPLICATION NO. 4003293284 , Reference ID : 403129595] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01782/2023-2024 | BP/23-24/258 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5 | 0 | 0
1103 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for HETMURI PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II, (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000746/2023-2024 | 1576/NMD | 08/09/2023 | 30 | ALPHA ENTERPRISE | 31.45 | 0 | 0
1104 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.09.2024 to 31.10.2024. |  | Sub-Assistant Engineer | ORD/000105/2024-2025 | 1551/NKWSMD | 30/08/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 100
1105 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation of source for lower takbia under Jal Swapno Programme for Goke-1, Block-Bijanbari-Pullbazar TSM No. 009479 |  | Sub-Assistant Engineer | ORD/000126/2022-2023 | 806/NKWSMD | 30/06/2022 | 60 | SAILESH RAI | 23.93 | 0 | 65
1106 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | GRAVITY BASED WATER SUPPLY SCHEME FOR SOOLBONG TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000232/2022-2023 | 1146/NKWSMD | 29/09/2022 | 665 | GARGO TRADERS | 852.89 | 0 | 95
1107 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000113/2022-2023 | 1890/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.04 | 0 | 0
1108 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000172/2022-2023 | 2610/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.04 | 0 | 0
1109 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Forest Busty, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | ORD/000180/2022-2023 | 956/NKWSMD | 12/07/2022 | 970 | RAMESH THAPA | 23.61 | 0 | 100
1110 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer4,Sub-Assistant Engineer | RTOR000074/2022-2023 | 1318/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.32 | 0 | 0
1111 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000055/2023-2024 | 248/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.5 | 0 | 100
1112 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Acceptance cum Work order Construction of boundary wall at head work site allied with Functional Household Tap Connection (FHTC) for Augmentation Trihana Tea Garden Area PWSS under Naxalbari Block under Siliguri Water Supply Division ,P.H.E,Dte.. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000177/2023-2024 | 1690/SWSD | 19/09/2023 | 45 | S.K. BANIK | 30.58 | 0 | 40
1113 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Construction of 2 Nos. Pump House (5.4 X 3.60) size, boundary wall allied with laying of rising main, distribution system & providing functional household tap connection (FHTC) for Augmentation TRIHANA TEA GARDEN Area Piped Water Supply Scheme under Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000202/2022-2023 | 1675/SWSD | 10/11/2022 | 75 | S.K. BANIK | 94.26 | 0 | 80
1114 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Sinking of 02(Two) Nos. Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at Tube Well Sites for Augmentation of TRIHANA TEA GARDEN Area Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000236/2022-2023 | 2092/SWSD | 22/12/2022 | 25 | SUBHADEEP ENTERPRISE | 16.28 | 0 | 100
1115 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Continuation order for Hiring of (one) no. Disel Motor Cab on daily basis for the Assistant Engineer-II, office of the Executive Engineer, Siliguri W/S Division, P.H.E Dte | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000353/2022-2023 | 1834/SWSD | 25/11/2022 | 182 | SUDIP BASAK | 0.89 | 0 | 0
1116 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000038/2022-2023 | 1949/SWSD | 07/12/2022 | 0 | Resource Division | 11.72 | 0 | 0
1117 | Northern Mechanical | Siliguri Mechanical Sub-Division | New Service Connection Charge for TRIHANA TEA GARDEN, under NAXALBARI CCC, [APPLICATION NO. 4003079478, Reference ID : 402958535] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | BILL/00582/2022-2023 | BP/22-23/145 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0
1118 | Northern Mechanical | Siliguri Mechanical Sub-Division | New Service Connection Charge for TRIHANA W/S SCHEME, T/W II, under NAXALBARI CCC, [APPLICATION NO. 4003210228, Reference ID : 403058760] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | BILL/01163/2023-2024 | BP/23-24/142 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.75 | 0 | 0
1119 | Northern Mechanical | Siliguri Mechanical Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
1120 | Northern Mechanical | Siliguri Mechanical Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000794/2022-2023 | 108/NMD | 03/02/2023 | 30 | MAA ENTERPRISES | 11.55 | 0 | 80
1121 | Northern Mechanical | Siliguri Mechanical Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TRIHANA TEA GARDEN PIPED WATER SUPPLY SCHEME , TW No II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000848/2023-2024 | 1753/NMD | 31/10/2023 | 460 | SUBODH KUMAR BANIK | 11.07 | 0 | 100
1122 | Northern Mechanical | Siliguri Mechanical Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (NAXALBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000998/2024-2025 | 17/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 11.76 | 0 | 0
1123 | Northern Mechanical | Siliguri Mechanical Sub-Division | Supplementary work for supply & delivery of column pipe & cable for AUGMENTATION OF TRIHANA TEA GARDEN,TW-I in the dist of Darjeeling under Northern Mechanical Division., PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/001029/2023-2024 | 366/SMSD | 06/12/2023 | 10 | MAA ENTERPRISES | 1.23 | 0 | 100
1124 | Northern Mechanical | Siliguri Mechanical Sub-Division | Supply & delivery of Column pipe under JJM project at Trihana Tea Garden PWSS in the dist of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/001038/2023-2024 | 421/SMSD | 19/12/2023 | 10 | B.B. CONCERNED | 0.94 | 0 | 100
1125 | Northern Mechanical | Siliguri Mechanical Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/001068/2024-2025 | 36/NMD | 06/01/2025 | 30 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0
1126 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system along with construction of pump house with toilet (2 nos. at each zone), boundary walls ( 2 nos.at each zone ), boring of new tubewells by ODEX-165 ( 2 nos.at each zone) , providing FHTC With platform & other allied works under Jal Jeevan Mission Programme for FULBARI Piped water supply Scheme (zone-I,II & III ) under Kharibari Block ,Darjeeling District , under Siliguri Sub Division ,P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000032/2023-2024 | 651/SWSD | 15/06/2023 | 960 | AKASH ENTERPRISE | 341.56 | 0 | 80
1127 | Siliguri W/S Division | Siliguri Sub-Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000319/2023-2024 | 641/SWSD | 11/03/2024 | 15 | BUDDHADEV NAG | 11.93 | 0 | 55
1128 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Fulbari Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000331/2022-2023 | 413/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 2.85 | 0 | 0
1129 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000034/2023-2024 | 2294/SWSD | 11/12/2023 | 0 | Resource Division | 0.31 | 0 | 0
1130 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000040/2023-2024 | 60/SWSD | 09/01/2024 | 0 | Resource Division | 5.67 | 0 | 0
1131 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000070/2022-2023 | 2049/SWSD | 16/12/2022 | 0 | Resource Division | 30.25 | 0 | 0
1132 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1133 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for FULBARI, T/W No. I, under KHARIBARI CCC [APPLICATION NO. 4003293300 ; Reference ID : 403125590] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01710/2023-2024 | BP/23-24/205 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.93 | 0 | 0
1134 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for FULBARI, T/W No. II, under KHARIBARI CCC [APPLICATION NO. 4003293292 ; Reference ID : 403125589] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01711/2023-2024 | BP/23-24/204 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.87 | 0 | 0
1135 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for FULBARI, T/W No. IV, under KHARIBARI CCC, [APPLICATION NO. 4003320577, Reference ID : 403147082] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01955/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.35 | 0 | 0
1136 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for FULBARI, T/W No. V, under KHARIBARI CCC, [APPLICATION NO. 4003320539, Reference ID : 403147071] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01956/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.01 | 0 | 0
1137 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for FULBARI, T/W No. VI, under KHARIBARI CCC, [APPLICATION NO. 4003320625, Reference ID : 403147079] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01957/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.94 | 0 | 0
1138 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for FULBARI, T/W No. III, under KHARIBARI CCC [APPLICATION NO.4003303307 ; Reference ID : 403132403] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02016/2023-2024 | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.85 | 0 | 0
1139 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for FULBARI PIPED WATER SUPPLY SCHEME( ZONE-I) TW No. I, II, (ZONE-II) TW No. I , II and (ZONE-III) TW No. I , II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000802/2023-2024 | 1659/NMD | 29/09/2023 | 754 | DAS ENTERPRISE | 57.06 | 0 | 100
1140 | Northern Mechanical | Siliguri Sub-Division | Supply and Delivery of C.I.D.F special ( 90 degree Bend) for using pumping machinery installation purpose at FULBARI W/S/S under JJM in the dist. of Siliguri under, Northern Mechanical Division ,PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001039/2023-2024 | 424/SMSD | 20/12/2023 | 376 | THE BANERJEE CONCERN | 0.44 | 0 | 100
1141 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House 2 Nos. (5.4 X 3.6) with toilet (2.1 X 1.2), Rig bore 2 Nos. Big Dia T/W by Odex-165 method, Boundary Walls, Laying distribution system (HDPE pipe), Rising Main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with 3 (three) months trial run IEP (25 cu.m./hr. for Zone-II & 50 cu.m./hr. for Zone-III), all repair works Zone-I and allied works at Augmentation of BUDHARUGAON PWSS at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000045/2023-2024 | 655/SWSD | 15/06/2023 | 1125 | NETWAY SOLUTION | 371.47 | 0 | 16
1142 | Siliguri W/S Division | Siliguri Sub-Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000051/2023-2024 | 244/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 4.02 | 0 | 100
1143 | Siliguri W/S Division | Siliguri Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 50
1144 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000068/2022-2023 | 2047/SWSD | 16/12/2022 | 0 | Resource Division | 26.07 | 0 | 0
1145 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for BUDHARUGAON T/W No. II, ZONE-I, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322531, Reference ID : 403149186] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02026/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.85 | 0 | 0
1146 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for BUDHARUGAON T/W No. II, ZONE-III, under BIDHANNAGAR CCC , [APPLICATION NO. 4003322541, Reference ID : 403149161] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02027/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5 | 0 | 0
1147 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
1148 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BUDHARUGAON PIPED WATER SUPPLY SCHEME , TW No I (Zone-II) and TW No. I (Zone-III) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000439/2023-2024 | 1378/NMD | 09/08/2023 | 721 | NIRMAN | 23.67 | 0 | 30
1149 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001071/2024-2025 | 39/NMD | 06/01/2025 | 30 | M/S P.P. ELECTRICALS | 15.34 | 0 | 0
1150 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0
1151 | Siliguri W/S Division | Siliguri Sub-Division | Construction Of 500 -1no & & 600 -1 No & 450 -1 No Cu.M. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site ( Zn-I, Zn-II & Zn-III) including distribution system (UPVC) with Rising Main,Providing Functional Household Connection (FHTC) , Pump House 4 Nos, ,Boundary Walls , Horizontal boring and allied works for Augmentation of MATIGARAHAT PWSS, Matigara block under Siliguri Sub Division.P.H.E.Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000099/2023-2024 | 1082/SWSD | 02/08/2023 | 730 | SRINIWAS AGARWAL | 2266.88 | 0 | 70
1152 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000027/2023-2024 | 2286/SWSD | 11/12/2023 | 0 | Resource Division | 5.18 | 0 | 0
1153 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000083/2022-2023 | 2198/SWSD | 04/01/2023 | 0 | Resource Division | 124.88 | 0 | 0
1154 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MATIGARAHAT, T/W No. II, ZONE-III under MATIGARA CCC, [APPLICATION NO. 4003316072, Reference ID : 403143728] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01960/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.65 | 0 | 0
1155 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for MATIGARAHAT, T/W No.I,ZONE-III under MATIGARA CCC, [APPLICATION NO. 4003316052, Reference ID : 403143727] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01961/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.19 | 0 | 0
1156 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MATIGARAHAT PIPED WATER SUPPLY SCHEME, (Zone-II) TW No. I and (Zone-III) TW No. I, II and III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000755/2023-2024 | 1583/NMD | 08/09/2023 | 754 | ANUP BASU | 50.02 | 0 | 25
1157 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/001066/2024-2025 | 34/NMD | 06/01/2025 | 30 | PRATIK ROY | 9.2 | 0 | 0
1158 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00194/2024-2025 | BP-2024-25-171 | 30/07/2024 | 0 | WBSEDCL | 0.95 | 0 | 0
1159 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | payment for WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00767/2023-2024 | BP-2023-24-505 | 17/02/2024 | 0 | WBSEDCL | 4.8 | 0 | 0
1160 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00768/2023-2024 | BP-2023-24-506 | 17/02/2024 | 0 | WBSEDCL | 10.62 | 0 | 0
1161 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00769/2023-2024 | BP-2023-24-507 | 17/02/2024 | 0 | WBSEDCL | 0.96 | 0 | 0
1162 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BUKIM TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000074/2023-2024 | 675/NKWSMD | 12/07/2023 | 425 | YAMA CONSTRUCTIONS LLP | 2035.87 | 0 | 75
1163 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000065/2023-2024 | 770/NKWSMD | 19/07/2023 | 0 | Resource Division | 10.27 | 0 | 0
1164 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1165 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000066/2023-2024 | 362/NKWSMD | 29/05/2023 | 365 | YAMA CONSTRUCTIONS LLP | 1365.56 | 0 | 90
1166 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MAJUA TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | ORD/000222/2024-2025 | 408/NKWSMD | 26/03/2025 | 90 | NIM TSHERING LEPCHA | 35.96 | 0 | 0
1167 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer7,Sub-Assistant Engineer | RTOR000059/2023-2024 | 532/NKWSMD | 13/06/2023 | 0 | Resource Division | 6.53 | 0 | 0
1168 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RISHIHAT KHASMAHAL PIPED WATER SUPPLY SCHEME IN DARJEELING PHULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000022/2023-2024 | 121/NKWSMD | 28/04/2023 | 240 | MS. SURYA I PVT. LTD COMPANY | 196.43 | 0 | 70
1169 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000013/2023-2024 | 210/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.21 | 0 | 0
1170 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR JAMADARBHITTA KHASMAHAL (PART-1 & 2) IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000024/2025-2026 | 592/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 45.62 | 0 | 0
1171 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR JAMADAR BHITA KHASMAHAL (PART-1 & 2) PIPED WATER SUPPLY SCHEME IN KURSEONG, UNDER DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000094/2023-2024 | 718/NKWSMD | 18/07/2023 | 665 | GARGO TRADERS | 976.84 | 0 | 70
1172 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000086/2023-2024 | 797/NKWSMD | 20/07/2023 | 0 | Resource Division | 3.43 | 0 | 0
1173 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR GOKE UNDER PULL BIJANIARI BLOCK DARJEELING DIVISION, PHED TO ACCOMMODATE FHTC IN PULL BIJANBARI BLOCK |  | Sub-Assistant Engineer | ORD/000140/2024-2025 | 2331/NKWSMD | 17/12/2024 | 180 | MS. SURYA I PVT. LTD COMPANY | 66.7 | 0 | 0
1174 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR GOKE-I PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT |  | Sub-Assistant Engineer | ORD/000226/2023-2024 | 1293/NKWSMD | 17/10/2023 | 365 | VAISHNO CONSTRUCTION | 839.28 | 0 | 68
1175 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000089/2023-2024 | 813/NKWSMD | 24/07/2023 | 0 | Resource Division | 6.67 | 0 | 0
1176 | Siliguri W/S Division | Siliguri W/S Division | Construction of 250 cu.m. capacity R.C.C. Elevated Reservosir, 20 mtrs. Staging Height at the head works site including distribution system (HDPE) with Rising Main, Rig bore 2 nos. big dia T/W by Odex-165 method, Providing Functional Household Connection (FHTC), Pump House 2 Nos., Blower Room, I.E.P. 50 cu.m./hr, Boundary Walls, Soil Testing and allied works at DEBIGANJA PWSS, Kharibari block under Siliguri Sub Division, P.H.E. Dte. . (3rd Call) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000139/2023-2024 | 1411/SWSD | 22/08/2023 | 548 | SANJEEV KUMAR | 430.31 | 0 | 25
1177 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Debiganja Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000320/2022-2023 | 261/SSD | 17/05/2022 | 20 | ENVIROTECH SOLUTIONS | 3.48 | 0 | 0
1178 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000019/2023-2024 | 1803/SWSD | 30/09/2023 | 0 | Resource Division | 31.55 | 0 | 0
1179 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000055/2023-2024 | 80/SWSD | 10/01/2024 | 0 | Resource Division | 13 | 0 | 0
1180 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000090/2022-2023 | 2232/SWSD | 06/01/2023 | 0 | Resource Division | 23.09 | 0 | 0
1181 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1182 | Northern Mechanical | Siliguri W/S Division | Quotation For New Service Connection charges under DEBIGANJA PWSS Tw-II under NMD PHE dte. Application no- 4003456575 Ref ID- 403252077 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00619/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0
1183 | Northern Mechanical | Siliguri W/S Division | Quotation For New Service Connection charges under DEBIGANJA PWSS Tw-I under NMD PHE dte. Application no- 4003456573 Ref ID- 403252078 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00834/2024-2025 | BP/24-25/157 | 07/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.08 | 0 | 0
1184 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DEBIGANJA PIPED WATER SUPPLY SCHEME, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000805/2023-2024 | 1662/NMD | 29/09/2023 | 641 | PRATIK ROY | 12.92 | 0 | 90
1185 | Neorakhola W/S & Mtc.Div. | Kurseong Division | AUGMENTATION OF LEFT OUT HABITATION OF CART ROAD GHAYABARI-II G.P. UNDER KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer5,Sub-Assistant Engineer | ORD/000008/2025-2026 | 494/NKWSMD | 09/04/2025 | 180 | SHAKTI CONSTRUCTION | 93.45 | 0 | 0
1186 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR LIZZIPUR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer5,Sub-Assistant Engineer | ORD/000229/2023-2024 | 1291/NKWSMD | 17/10/2023 | 365 | SHAKTI CONSTRUCTION | 1461.53 | 0 | 100
1187 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Preparation of Re-draft of proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 03 (three) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer5 | Junior Engineer5,Sub-Assistant Engineer | ORD/000274/2023-2024 | 1594/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.57 | 0 | 100
1188 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer7,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1189 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MAHANADI TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Junior Engineer7,Sub-Assistant Engineer | ORD/000005/2023-2024 | 92/NKWSMD | 27/04/2023 | 605 | VINAYAK CONSTRUCTION | 1041.6 | 0 | 100
1190 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer7,Sub-Assistant Engineer | RTOR000007/2023-2024 | 154/NKWSMD | 03/05/2023 | 0 | Resource Division | 6.37 | 0 | 0
1191 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR KARMAT BUSTY PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Sub-Assistant Engineer | ORD/000091/2023-2024 | 712/NKWSMD | 17/07/2023 | 300 | SRINIWAS AGARWAL | 128.73 | 0 | 100
1192 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer | Sub-Assistant Engineer | RTOR000062/2023-2024 | 776/NKWSMD | 19/07/2023 | 0 | Resource Division | 0.26 | 0 | 0
1193 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SAURINI BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK-MIRIK DISTRICT-DARJEELING, KURSEONG DIVISION PHE-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000026/2025-2026 | 594/NKWSMD | 29/04/2025 | 90 | ALLIED INSTRUMENTS | 22.62 | 0 | 0
1194 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000035/2023-2024 | 278/NKWSMD | 17/05/2023 | 0 | Resource Division | 4.55 | 0 | 0
1195 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection under Jal Swapna Programme for Budharugaon of BUDHARUGAON Piped Water Supply Scheme at Phansidewa block under Siliguri Sub-Division PHE Dte PART A | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000005/2021-2022 | 691/SWSD | 02/08/2021 | 50 | SUDIP BASAK | 41.87 | 0 | 100
1196 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Piped Water Supply Scheme for Mahanadi Forest under Kurseong Division. Scheme Code - 15648 TSM/017745 | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00094/2024-2025 | BP-2024-25-95 | 08/07/2024 | 0 | DIVISIONAL FOREST OFFICER | 15.27 | 0 | 0
1197 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1198 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR MAHANADI FOREST TO ACCOMMODATE FHTC UNDER KURSEONG DIVISION, PHE DTE, GTA, DARJEELING. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000065/2023-2024 | 439/NKWSMD | 07/06/2023 | 830 | RUKMANI ENGINEERING WORKS | 157.77 | 0 | 100
1199 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00854/2023-2024 | BP-2024-25-56 | 07/06/2024 | 0 | WBSEDCL | 51.83 | 0 | 0
1200 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED PATONG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION IN MIRIK BLOCK. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000016/2023-2024 | 116/NKWSMD | 28/04/2023 | 1193 | SRINIWAS AGARWAL | 677.35 | 0 | 90
1201 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000020/2023-2024 | 205/NKWSMD | 10/05/2023 | 0 | Resource Division | 4.29 | 0 | 0
1202 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 250 cu.m. (1 No.) & 150 Cum (2Nos) capacity R.C.C Elevated Reservoir , 20 Mtrs. Stagging Height at the head work site ( Zn-l,Zn-ll & Zn-lll) including distribution system (HDPE) with Rising Main , Rig bore 6 nos big dia T/W by ODEX-165method, Providing Functional Household Connection (FHTC) , Construction of 6 nos. Pump Houses, 3 Nos. Blower Rooms, Boundary walls, Installation of I.E. Plants (Capacity 30,50 & 30 cu.m./hr), Horizontal boring, Soil Testing and allied works at BARA PATHURAM Piped WS Scheme within Phansidewa block, under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000105/2023-2024 | 1131/SWSD | 07/08/2023 | 807 | UNIBRO INFRASERV PRIVATE LIMITED | 1076.34 | 0 | 30
1203 | Siliguri W/S Division | Siliguri Sub-Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000319/2023-2024 | 641/SWSD | 11/03/2024 | 15 | BUDDHADEV NAG | 11.93 | 0 | 55
1204 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Barapathuram Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000326/2022-2023 | 407/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.99 | 0 | 100
1205 | Siliguri W/S Division | Siliguri Sub-Division | CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE., VIVEKANANDA BHAWAN (2ND FLOOR), HILL CART ROAD, SILIGURI FOR THE PERIOD FROM 01.03.2023 TO 31.07.2023 (FOR CHIEF ENGINEER (CIVIL), NORTHERN ZONE, P.H.E. DTE.) i.e. 5 (FIVE) MONTHS. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000341/2022-2023 | 2645/SWSD | 01/03/2023 | 153 | PINKI DAM | 0.74 | 0 | 40
1206 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000039/2023-2024 | 59/SWSD | 09/01/2024 | 0 | Resource Division | 22.92 | 0 | 0
1207 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000085/2022-2023 | 2200/SWSD | 04/01/2023 | 0 | Resource Division | 85.16 | 0 | 0
1208 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1209 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for BARA PATHURAM, T/W No. I, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003321578, Reference ID : 403148659] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01973/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.26 | 0 | 0
1210 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for BARA PATHURAM, T/W No. II, ZONE-I under PHANSIDAWA CCC, [APPLICATION NO. 4003321619, Reference ID : 403148640] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01974/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.62 | 0 | 0
1211 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for BARA PATHURAM, T/W-I,ZONE-I under PHASIDAWA CCC [APPLICATION NO. 4003340866 , Reference ID : 403163866] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02062/2023-2024 | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.33 | 0 | 0
1212 | Northern Mechanical | Siliguri Sub-Division | Infrastructure Cost for BARA PATHURAM, T/W-I,ZONE-II under PHASIDAWA CCC [APPLICATION NO. 4003340843 ; Reference ID : 403163867] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02063/2023-2024 | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.55 | 0 | 0
1213 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA PATHURAM PIPED WATER SUPPLY SCHEME, ( ZONE-I) TW No. I, II, (ZONE-II) TW No. I, II and (ZONE-III) TW No. I, II, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000791/2023-2024 | 1655/NMD | 29/09/2023 | 712 | ALPHA ENTERPRISE | 45.3 | 0 | 24
1214 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Selim Hill T .E.under Kurseong Division PHED), GTA |  |  | VCH/000014/2022-2023 | BP-2022-23-13 | 11/04/2022 | 0 | SWAD CONSTRUCTION | 7.27 | 0 | 0
1215 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection unde.r Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Makaibari Tea Estate under Kurseong Sub-DIvision PHED, GTA |  |  | VCH/000022/2022-2023 | BP-2022-23-21 | 20/04/2022 | 0 | NIPENDRA TAMANG | 10.07 | 0 | 0
1216 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Sittong-1 & Sittong-111 under Kurseong Sub-Division PHED, GTA. |  |  | VCH/000026/2022-2023 | BP-2022-23-25 | 20/04/2022 | 0 | BIKRAM RAI | 21.12 | 0 | 0
1217 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Schem e for Dudhia Bazaar & its sorrounding area under Kurseong Sub-Division PHED, G1A |  |  | VCH/000037/2022-2023 | BP-2022-23-37 | 20/04/2022 | 0 | SUN SHINE GROUP | 19.39 | 0 | 0
1218 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000143/2022-2023 |  | 26/08/2022 | 0 | SHREE VAISHNO ENTERPRISES | 14.73 | 0 | 0
1219 | Neorakhola W/S & Mtc.Div. |  | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  |  | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
1220 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SAMALBONG PIPED WATER SUPPLY SCHEME UNDER BLOCK-PULBAZAR DISTRICT-DARJEELING. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000028/2025-2026 | 596/NKWSMD | 29/04/2025 | 180 | GARGO TRADERS | 98.47 | 0 | 0
1221 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SAMALBONG PIPED WATER SUPPLY SCHEME DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000178/2023-2024 | 937/NKWSMD | 16/08/2023 | 605 | GARGO TRADERS | 1200.76 | 0 | 80
1222 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000100/2023-2024 | 963/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.35 | 0 | 0
1223 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR MOLATEY AND AVONGRAVE TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHRI UNDER DARJEELING DISTRICT |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000235/2022-2023 | 1452/NKWSMD | 29/09/2022 | 850 | SHAKTI CONSTRUCTION | 926.69 | 0 | 99
1224 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000112/2022-2023 | 1889/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.41 | 0 | 0
1225 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000171/2022-2023 | 2572/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.41 | 0 | 0
1226 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00957/2023-2024 | BP-2023-24-657 | 23/03/2024 | 0 | WBSEDCL | 11.34 | 0 | 0
1227 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Balance work for Surface water based Purba & Paschim Phuguri Tea Garden Phuguri Forest and its Surrounding under Kurseong Division, P.H.E-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000057/2025-2026 | 874/NKWSMD | 16/06/2025 | 365 | INTERIOR'S NEST | 312.15 | 0 | 0
1228 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST AND ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000059/2025-2026 | 829/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 93.84 | 0 | 0
1229 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED PURBA AND PASCHIM PHUGURI TEA GARDEN PHUGURI FOREST & ITS SURROUNDING VILLAGE PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000169/2023-2024 | 913/NKWSMD | 11/08/2023 | 545 | INTERIOR'S NEST | 2568.72 | 0 | 75
1230 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000110/2023-2024 | 970/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.04 | 0 | 0
1231 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR ACHHALAL HATTA PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT DARJEELING. |  | Sub-Assistant Engineer | ORD/000126/2024-2025 | 2203/NKWSMD | 02/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 114.92 | 0 | 80
1232 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR ACHHALAL HATTA PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000151/2023-2024 | 879/NKWSMD | 03/08/2023 | 365 | YAMA CONSTRUCTIONS LLP | 2563.35 | 0 | 50
1233 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000132/2023-2024 | 174/NKWSMD | 08/02/2024 | 0 | Resource Division | 12.22 | 0 | 0
1234 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4 | Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1235 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000095/2023-2024 | 959/NKWSMD | 21/08/2023 | 0 | Resource Division | 5.46 | 0 | 0
1236 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 250 cu.m. capacity R.C.C. Elevated Reservoir, 20 Mtrs. Staging Height at the head works site along with distribution system, functional household tap connection, rising main, pump house (4 nos.), IEP, Bounary wall, tubewell and soil investigation under Jal Jeevan Mission at MEHERULLA Piped Water Supply Scheme under Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000314/2023-2024 | 545/SWSD | 01/03/2024 | 390 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 626.06 | 0 | 25
1237 | Siliguri W/S Division | Siliguri Sub-Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6'00X4'00 size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete(1:2:4) footing size 250X250X600 mm. under ground.The board for display to be made on self-adhesive latex venyle print (UVray protected) 100 micron as per standard format given from department to be pasted over M.S. sheet ( size-6'X4') including carriage , loading ,unloading at different sites under the area of four nos. Blocks under Siliguri Mahakuma Parishad area. Total nos of board -84 nos. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000319/2023-2024 | 641/SWSD | 11/03/2024 | 15 | BUDDHADEV NAG | 11.93 | 0 | 55
1238 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Meherulla Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000325/2022-2023 | 403/SSD | 27/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 100
1239 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000022/2023-2024 | 1806/SWSD | 30/09/2023 | 0 | Resource Division | 77.11 | 0 | 0
1240 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000058/2023-2024 | 82/SWSD | 10/01/2024 | 0 | Resource Division | 10.77 | 0 | 0
1241 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1242 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MEHERULLA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II & (Zone-II) TW No. I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000752/2023-2024 | 1580/NMD | 08/09/2023 | 30 | B.B. CONCERNED | 34.74 | 0 | 70
1243 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR DAWAIPANI & TUKDAH TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000037/2025-2026 | 650/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 130.55 | 0 | 0
1244 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DAWAIPANI & TUKDAH TEA GARDEN PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000191/2023-2024 | 988/NKWSMD | 23/08/2023 | 815 | VINAYAK CONSTRUCTION | 992.81 | 0 | 100
1245 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000113/2023-2024 | 999/NKWSMD | 24/08/2023 | 0 | Resource Division | 8.16 | 0 | 0
1246 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
1247 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Antaram village habitation Vulka Bajarur Chhat village habitation Bazarir chat Bhulka and Gandagal village habitation Barodil Saram and Chhoto Dil saran of Uttar Ramdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000053/2020-2021 | 1009/SWSD | 11/12/2020 | 30 | M/S DEBRAJ ENTERPRISE | 24.49 | 5.42 | 100
1248 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Gandagal village habitation Dil saram Dulal Gandogle and village Jibansing habitation Babuchhan Dilsaram and Jiban sing of Uttar Ramdhan and adjoining mouzas Piped Water Supply Scheme and allied works at Kharibari block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000055/2020-2021 | 1011/SWSD | 11/12/2020 | 40 | M/S DEBRAJ ENTERPRISE | 37.92 | 22 | 100
1249 | Siliguri W/S Division | Siliguri W/S Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Uttar Ramdhan habitation Projote of Uttar Ramdhan and adjoining mouzas piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000057/2020-2021 | 1013/SWSD | 11/12/2020 | 35 | NARENDRA KUMAR | 32.96 | 0 | 0
1250 | Siliguri W/S Division | Siliguri W/S Division | Repair of functional house hold tap connection (FHTC) and UPVC pipeline and allied work in command area of Uttar Ramdhan pipe water supply scheme under siliguri sub division,P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000238/2022-2023 | 550/SSD | 22/12/2022 | 15 | DEBRAJ ENTERPRISE | 1.63 | 0 | 100
1251 | Siliguri W/S Division | Siliguri W/S Division | FURTHER CONTINUATION HIRING OF 1 (ONE) NO. MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 CC (WITH AIR CONDITION) FOR THE OFFICE OF THE EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE. FOR THE PERIOD FROM 01.03.2023 TO 31.08.2023 (FOR EXECUTIVE ENGINEER, SILIGURI W/S DIVISION, P.H.E. DTE.) i.e. 06 (Six) months. |  | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000365/2022-2023 | 2576-31(A)/SWSD | 23/02/2023 | 181 | SUBIR CH. CHOWDHURY | 0.88 | 0 | 100
1252 | Siliguri W/S Division | Siliguri W/S Division | Soil Investigation of Kharibari Zone -I PWSS for Construction of 450 cum OHR under Siliguri Sub-Division P.H.E. Dte under Kharibari Block | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000089/2022-2023 | 386/SSD | 20/07/2022 | 20 | GLORY ENGINEERS SYNDICATE | 1.03 | 0 | 100
1253 | Siliguri W/S Division | Siliguri W/S Division | Part work order for construction of blower room (3.60 m X 3.00 m) size as per Model Approved drawings at tubewell site including IEP and boundary walls for Kharibari Zone I & II water supply scheme under Siliguri W/S Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000168/2024-2025 | 2931/SWSD | 30/10/2024 | 45 | ARUN KUMAR SHRIVASTAVA | 49.08 | 0 | 0
1254 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection under JJM & JSP Programme for PWS Scheme Raman Forest Village Source mahabir Jhora Gram Panchyat -Srikhola, Block Darjeeling - Pullbazaar. TSM No. 009295 SM Code-SM/08925 |  | Sub-Assistant Engineer | ORD/000029/2022-2023 | 492/NKWSMD | 24/05/2022 | 60 | NIMA SHERPA | 20.35 | 0 | 100
1255 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000036/2022-2023 | 1263/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.37 | 0 | 0
1256 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Gorkata Gram Panchyat -Goke-II , Block Darjeeling -Pull-Bijanbari Block. TSM No. 009301 SM Code-SM/08933 |  | Sub-Assistant Engineer | ORD/000031/2022-2023 | 494/NKWSMD | 24/05/2022 | 60 | MS D.R ENTERPRISES | 24.24 | 0 | 100
1257 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000032/2022-2023 | 1259/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.78 | 0 | 0
1258 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Upper Lamagoan, Gram Panchyat -Kaijiliya, Block Bijanbari -PullBazar. TSM No. 009097 SM Code-SM/04601 |  | Sub-Assistant Engineer | ORD/000043/2022-2023 | 525/NKWSMD | 25/05/2022 | 60 | M/S DIVYA ENTERPRISES | 18.55 | 0 | 0
1259 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000030/2022-2023 | 1272/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.47 | 0 | 0
1260 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Gorkhey Forest Villa, Gram Panchyat -Sirkhola Danra Gaon, Block Bijanbari -PullBazar. TSM No. 009469 SM Code-SM/08929 |  | Sub-Assistant Engineer | ORD/000032/2022-2023 | 495/NKWSMD | 24/05/2022 | 60 | NIMA SHERPA | 16.74 | 0 | 100
1261 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000035/2022-2023 | 1262/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.24 | 0 | 0
1262 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection und er JJM & JSP Programme for PWS Schem e for Lama goan GP Jhepi Kaijiliya under Darjeeling Division PHED GTA |  | Sub-Assistant Engineer | VCH/000017/2022-2023 | BP-2022-23-16 | 11/04/2022 | 0 | HARI PRASAD CHETTRI | 9.27 | 0 | 0
1263 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Relling Bhibaray & Lr Relling GP Relling under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000018/2022-2023 | BP-2022-23-17 | 11/04/2022 | 0 | HARI PRASAD CHETTRI | 8.03 | 0 | 0
1264 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Singhbhumdera GP Mazua under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000023/2022-2023 | BP-2022-23-22 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 13.75 | 0 | 0
1265 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Gairigoan Fatingtar GP Lodhoma II under Darjeeling Division PHED GTA |  | Sub-Assistant Engineer | VCH/000024/2022-2023 | BP-2022-23-23 | 20/04/2022 | 0 | BIRAJ RAI | 6.44 | 0 | 0
1266 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap ·connection under JJM & JSP Programme for PWS Scheme for Samsu (Lower) Relling GP under Darjeeling Division PHED GTA |  | Sub-Assistant Engineer | VCH/000028/2022-2023 | BP-2022-23-27 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 4.03 | 0 | 0
1267 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM &. .JSP Programme for PWSS Scheme for Dhotrey Forest fV GP Lodhoma 1 under DarJeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000033/2022-2023 | BP-2022-23-33 | 20/04/2022 | 0 | PASSANG TAMANG | 3.13 | 0 | 0
1268 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Kankeybong GP Lodhoma under Darjeellng Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000034/2022-2023 | BP-2022-23-34 | 20/04/2022 | 0 | SACHIN PRADHAN | 13.66 | 0 | 0
1269 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household d Tap Connection under JJM & JSP Programme for PWS Scheme for Lungtham Happy Valley under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000035/2022-2023 | BP-2022-23-35 | 20/04/2022 | 0 | SAMDEN DUKPA | 6.07 | 0 | 0
1270 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional .Household Tap Connection under JJM & JSP Programme for PWS Scheme for Takbia (Lower ) GP Goke 1 under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000036/2022-2023 | BP-2022-23-36 | 20/04/2022 | 0 | SAILESH RAI | 7.3 | 0 | 0
1271 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM & JSP Programme for PWS Scheme for Tukvar TG GP Tukvar under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000066/2022-2023 | BP-2022-23-51 | 20/05/2022 | 0 | VINAYAK CONSTRUCTION | 47.99 | 0 | 0
1272 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connecti on under JJM & JSP Pro gramme for PWS Scheme for Bijanbari Bazar GP Pull Bijnabari under Darjeeling Division PHED GTA" |  | Sub-Assistant Engineer | VCH/000067/2022-2023 | BP-2022-23-52 | 20/05/2022 | 0 | AROGYA ENTERPRISES | 24.75 | 0 | 0
1273 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | VCH/000234/2022-2023 | BP-2022-23-131 | 05/09/2022 | 0 | SHREE VAISHNO ENTERPRISES | 73.45 | 0 | 0
1274 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000001/2020-2021 | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0
1275 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000003/2020-2021 | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0
1276 | Darjeeling Division I | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under JJM &. .JSP Programme for PWSS Scheme for Dhotrey Forest fV GP Lodhoma 1 under DarJeeling Division PHED GTA" |  | Sub-Assistant Engineer | ORD/000005/2020-2021 | 110/EE/DD/PHED | 10/02/2021 | 120 | PASSANG TAMANG | 5.58 | 0 | 0
1277 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer I,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | BILL/00175/2023-2024 | BP-2023-24-130 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1278 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer I,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000159/2022-2023 | 2370/NKWSMD | 03/02/2023 | 0 | Resource Division | 1.81 | 0 | 0
1279 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR DARAGOAN UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PULL BIJANBARI BLOCK |  | Sub-Assistant Engineer | ORD/000077/2025-2026 | 967/NKWSMD | 03/07/2025 | 60 | SUNIL SHARMA | 6.93 | 0 | 0
1280 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR DARAGOAN LEKHARGA UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  | Sub-Assistant Engineer | ORD/000086/2022-2023 | 613/NKWSMD | 26/05/2022 | 60 | SUNIL SHARMA | 58.05 | 0 | 100
1281 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000104/2022-2023 | 1881/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.52 | 0 | 0
1282 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000164/2022-2023 | 2569/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.52 | 0 | 0
1283 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Fatinagar Gram, G.P. - Lodhama-I, Block - Bijanbari Pulbazar. |  | Sub-Assistant Engineer | ORD/000112/2023-2024 | 849/NKWSMD | 27/07/2023 | 60 | BIJAY CHETTRI | 25.37 | 0 | 100
1284 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Takdah Bazar GP - Takdah Block - Rungli Rungliot. |  | Sub-Assistant Engineer | ORD/000174/2022-2023 | 950/NKWSMD | 12/07/2022 | 253 | NAVRATNA CONSTRUCTION CO | 150.61 | 0 | 100
1285 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000134/2022-2023 | 1910/NKWSMD | 15/12/2022 | 0 | Resource Division | 5.85 | 0 | 0
1286 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000192/2022-2023 | 2618/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.85 | 0 | 0
1287 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Upper Mamring Khasmahal in Kurseong Block within Darjeeling District. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | ORD/000042/2023-2024 | 186/NKWSMD | 04/05/2023 | 870 | PREM CHANDRA RAI | 267.92 | 0 | 85
1288 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | RTOR000042/2023-2024 | 328/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.74 | 0 | 0
1289 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2023 TO 31.12.2023 |  | Sub-Assistant Engineer | ORD/000220/2023-2024 | 1023/NKWSMD | 31/08/2023 | 122 | QRT SECURITY AND MANPOWER SERVICE | 0.79 | 0 | 100
1290 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | CHOONGTOONG & LIZAHILL TEA GARDEN WATER SUPPLY SCHEME UNDER DARJEELING DIVISION I, PHED, GTA |  | Sub-Assistant Engineer | ORD/000239/2022-2023 | 1447/NKWSMD | 29/09/2022 | 300 | SUDESH RAYA MAJHI | 1203.75 | 0 | 80
1291 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000108/2022-2023 | 1885/NKWSMD | 15/12/2022 | 0 | Resource Division | 16.58 | 0 | 0
1292 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000167/2022-2023 | 2604/NKWSMD | 17/02/2023 | 0 | Resource Division | 16.58 | 0 | 0
1293 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Construction of 200 cu.m. Capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging height at the head works site, laying rising main, laying distribution pipeline with functional household tap connection (FHTC), construction of pump house (5.40 X 3.6 m) and pump house (3.60 X 3.00 m) with sanitary and plumbing arrangement, iron elimination plant (IEP) with blower room and soil investingation at head work site for DAKSHIN BAGDOGRA PWSS, Block Naxalbari Dist. Darjeeling under Siliguri W/S Division, PHE Dte | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000125/2023-2024 | 1200/SWSD | 10/08/2023 | 966 | NETWAY SOLUTION | 332.54 | 0 | 30
1294 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dakhshin Bagdogra Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000156/2022-2023 | 278/SSD | 25/05/2022 | 20 | SUBHANKAR GHOSH | 3.09 | 0 | 100
1295 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000032/2022-2023 | 1462/SWSD | 29/09/2022 | 0 | Resource Division | 7.47 | 0 | 0
1296 | Siliguri W/S Division | Siliguri Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000075/2022-2023 | 2054/SWSD | 16/12/2022 | 0 | Resource Division | 65.62 | 0 | 0
1297 | Central Drilling | Siliguri Mechanical Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1298 | Northern Mechanical | Siliguri Mechanical Sub-Division | Quotation for new service connection at T.W No-I of DAKSHIN BAGDOGRA PWSS in the dist. Darjeeling | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | BILL/00293/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.06 | 0 | 0
1299 | Northern Mechanical | Siliguri Mechanical Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at DAKSHIN BAGDOGRA PWSS for T/W No. II in the district of Darjeeling under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000845/2024-2025 | 583/NMD | 07/02/2025 | 30 | SAIKAT SINHA | 12.1 | 0 | 0
1300 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED RATNA DYANG PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA, DISTRICT DARJEELING. | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | ORD/000280/2022-2023 | 1988/NKWSMD | 23/12/2022 | 180 | KUMAR CHHETRI | 75.55 | 0 | 100
1301 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer6,Sub-Assistant Engineer | RTOR000226/2022-2023 | 2567/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.94 | 0 | 0
1302 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED JOGMAYA TEA ESTATE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000285/2022-2023 | 2083/NKWSMD | 10/01/2023 | 180 | MS CHAMLING CONSTRUCTION | 66.72 | 0 | 80
1303 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000224/2022-2023 | 2602/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.89 | 0 | 0
1304 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME FOR SINGBULLI FACTORY GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000089/2022-2023 | 611/NKWSMD | 26/05/2022 | 60 | M/S JAI BHAWANI CONSTRUCTION CO | 63.19 | 0 | 97
1305 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000078/2022-2023 | 1322/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.3 | 0 | 0
1306 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | BILL/00172/2023-2024 | BP-2023-24-127 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1307 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of wbsedcl for electrical service connection | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | BILL/00173/2023-2024 | BP-2023-24-128 | 27/07/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1308 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | BILL/00494/2023-2024 | BP-2023-24-290 | 02/11/2023 | 0 | WBSEDCL | 0.09 | 0 | 0
1309 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. | Assistant Engineer5 | Junior Engineer4,Sub-Assistant Engineer | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 1530 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 0 | 100
1310 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Proposed Gravity Based Water Supply Scheme for Tumsung Khasmahal PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000240/2022-2023 | 1494/NKWSMD | 14/10/2022 | 1000 | ALLIED INSTRUMENTS | 587.51 | 0 | 100
1311 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000110/2022-2023 | 1887/NKWSMD | 15/12/2022 | 0 | Resource Division | 1.74 | 0 | 0
1312 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000169/2022-2023 | 2606/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.74 | 0 | 0
1313 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000116/2022-2023 | 796/NKWSMD | 30/06/2022 | 60 | PREM KUMAR PRADHAN | 27.69 | 0 | 100
1314 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000055/2022-2023 | 1299/NKWSMD | 09/09/2022 | 0 | Resource Division | 2.61 | 0 | 0
1315 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation for work for PWS Scheme for Dara Goan, Khoprail: Gram Panchyat -Soureni-II, Block Mirik TSM No. 009308 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000015/2022-2023 | 783/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 12.59 | 0 | 100
1316 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Continuation Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for the period of 6 (Six) months. Note: With effect from date of issuing work order. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000248/2023-2024 | 1141/NKWSMD | 29/09/2023 | 182 | S S CONSTRUCTIONS | 0.99 | 0 | 100
1317 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for bada Kothi: Gram Panchyat Soureni- II, Block - Mirik TSM No. 009482 SM Code-SM/08949 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000019/2022-2023 | 781/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 3.78 | 0 | 100
1318 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap Connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Ghoomti T.E. Mahanadi GP Block Kurseong | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000131/2022-2023 | 811/NKWSMD | 30/06/2022 | 60 | MS CHAMLING CONSTRUCTION | 26.4 | 0 | 100
1319 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000061/2022-2023 | 1305/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.91 | 0 | 0
1320 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Sivitar T.E. Mahanadi GP Block - Kurseong Block | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000119/2022-2023 | 798/NKWSMD | 30/06/2022 | 60 | ABHINAY CHETTRI | 24.02 | 0 | 100
1321 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000063/2022-2023 | 1307/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.68 | 0 | 0
1322 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000079/2023-2024 | 767/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.82 | 0 | 0
1323 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION P.H.E DTE. |  |  | ORD/000145/2024-2025 | 2347/NKWSMD | 19/12/2024 | 365 | YAMA CONSTRUCTIONS LLP | 1156.69 | 0 | 75
1324 | Neorakhola W/S & Mtc.Div. |  | SURFACE WATER BASED FOR MANGPUU CINCHONA PLANTATION PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN RANGLI RANGLIOT BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E. DTE. |  |  | ORD/000249/2023-2024 | 3/NKWSMD | 03/01/2024 | 455 | YAMA CONSTRUCTIONS LLP | 5612.47 | 0 | 95
1325 | Siliguri W/S Division | Siliguri Sub-Division | Providing functional house hold tap connection under Jal Swapno programme for Bairagi village of Duba & Gayen village of Bairagi piped water supply scheme at Khoribari block under Siliguri Sub Division, PHE Dte. SL. No. 04. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000078/2021-2022 | 1826/SWSD | 13/01/2022 | 45 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 35.33 | 0 | 100
1326 | Siliguri W/S Division | Siliguri Sub-Division | Providing functional house hold tap connection (FHTC) in connection with jal Jeevan Mission ( JJM and Jal Swapna Programme ) for Bairagi Village of Bairagi piped water supply scheme at Kharibari | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000171/2020-2021 | 1275/SWSD | 14/08/2020 | 1826 | THE HINDUSTHAN CO-OPERTIVE LABO. CONT. & CONSTRACTION SOCIETY LTD. | 32.19 | 29.04 | 0
1327 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000007/2021-2022 | 1668/SWSD | 28/12/2021 | 0 | Resource Division | 2.68 | 0 | 0
1328 | Siliguri W/S Division | Siliguri Sub-Division | Laying of pipeline for distribution system, rising main, construction of Pump House, Installation of I.E. Plant with blower room construction of boundary wall for Zone-I & Zone-II for Augmentation of LALMAN W/S Scheme under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000047/2023-2024 | 649/SWSD | 15/06/2023 | 240 | S.G.CONSTRUCTION. | 453.84 | 0 | 65
1329 | Siliguri W/S Division | Siliguri Sub-Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000048/2023-2024 | 241/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.76 | 0 | 100
1330 | Siliguri W/S Division | Siliguri Sub-Division | Repairing Of Damaged House Connection Under Lalman Water Supply Scheme Under Siliguri Sub Division, Phe Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000188/2023-2024 | 1948/SWSD | 16/10/2023 | 10 | SEBU CHAKRABORTY | 1.62 | 0 | 100
1331 | Siliguri W/S Division | Siliguri Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 50
1332 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000080/2022-2023 | 2059/SWSD | 16/12/2022 | 0 | Resource Division | 23.85 | 0 | 0
1333 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1334 | Central Drilling | Siliguri Sub-Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
1335 | Northern Mechanical | Siliguri Sub-Division | ELECTRIC QUOTATION FOR NEW SERVICE CONNECTION AT LALMON T.W NO:- IV UNDER NMD, PHE DTE. | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01030/2024-2025 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.53 | 0 | 0
1336 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for LALMAN (AUG), T/W-I, under BAGDOGRA CCC, [APPLICATION NO. 4003347057, Reference ID : 403169281] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02178/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.29 | 0 | 0
1337 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
1338 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LALMAN PIPED WATER SUPPLY SCHEME , TW No I (Zone-I) and TW No. I (Zone-II) in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000786/2023-2024 | 1650/NMD | 29/09/2023 | 30 | SUBHRANGSHU GUHARAJA | 11.58 | 0 | 50
1339 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001067/2024-2025 | 35/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0
1340 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Construction of Pump House (5.4 X 3.65) size with (1.20 X 2.10 M) size with toilet, Rig bored big dia Deep T/W by Odex-165 method of drilling, boundary wall, laying distribution system, providing functional house hold tap connection (FHTC) and Supplying, Fabrication, Erection on suitable RCC foundation and commissioning with 3 (three) months trial run of pressure type IEP (20 cu.m./hour) required platform and drain etc. for Rejuvenation of Dangarvita Piped Water Supply Scheme at Kharibari block under under Siliguri Sub Division.P.H.E.Dte.in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000182/2024-2025 | 3025/SWSD | 13/11/2024 | 90 | BUDDHADEV NAG | 66.21 | 0 | 0
1341 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000050/2022-2023 | 2030/SWSD | 16/12/2022 | 0 | Resource Division | 0.98 | 0 | 0
1342 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000092/2022-2023 | 2234/SWSD | 06/01/2023 | 0 | Resource Division | 0.98 | 0 | 0
1343 | Central Drilling | Siliguri W/S Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
1344 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for DANGARVITA, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003321689, Reference ID : 403147924] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01943/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.46 | 0 | 0
1345 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DANGARBHITA PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000663/2023-2024 | 1477/NMD | 17/08/2023 | 30 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 12.44 | 0 | 0
1346 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Milan Dhura, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000182/2022-2023 | 958/NKWSMD | 12/07/2022 | 970 | NABIN RAI | 20.04 | 0 | 100
1347 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000143/2022-2023 | 2063/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.28 | 0 | 0
1348 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Piped Water Supply Scheme at Chimney Simanatar with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED-GTA, Darjeeling. | Assistant Engineer 4,Assistant Engineer4 |  | ORD/000188/2023-2024 | 986/NKWSMD | 23/08/2023 | 60 | PHURBA RUMBA | 77.11 | 0 | 0
1349 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 |  | RTOR000111/2023-2024 | 1000/NKWSMD | 24/08/2023 | 0 | Resource Division | 1.08 | 0 | 0
1350 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHAMU TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000257/2022-2023 | 1620/NKWSMD | 03/11/2022 | 545 | GARGO TRADERS | 874.98 | 0 | 90
1351 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000116/2022-2023 | 1893/NKWSMD | 15/12/2022 | 0 | Resource Division | 4.72 | 0 | 0
1352 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000175/2022-2023 | 2573/NKWSMD | 17/02/2023 | 0 | Resource Division | 4.72 | 0 | 0
1353 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH PROPOSED KHOKLONG PIPED WATER SUPPLY SCHEMES AT THE UNCOVERED MOUZAS UNDER MATIGARA BLOCK OF SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000066/2023-2024 | 259/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.02 | 0 | 100
1354 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000054/2023-2024 | 79/SWSD | 10/01/2024 | 0 | Resource Division | 1.08 | 0 | 0
1355 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000058/2022-2023 | 2038/SWSD | 16/12/2022 | 0 | Resource Division | 12.83 | 0 | 0
1356 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1357 | Northern Mechanical | Siliguri W/S Division | Power Service connection charges at T.W No-II of Khoklong PWSS under Northern Mechanical Division dist. Darjeeling CONSUMER ID:- 403230623 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00528/2024-2025 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.9 | 0 | 0
1358 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 4003460490 Reference ID : 403255264 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00973/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
1359 | Northern Mechanical | Siliguri W/S Division | Infrastructure development cost for new service connection at KHUKHLUNG PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 100000115666 Reference ID : 860308376 | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00980/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.39 | 0 | 0
1360 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KHOKLONG, T/W No.I, under MATIGARA CCC, [APPLICATION NO. 4003316039, Reference ID : 403143725] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01952/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.35 | 0 | 0
1361 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
1362 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOKLONG PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000819/2023-2024 | 1674/NMD | 29/09/2023 | 30 | B.B. CONCERNED | 11.43 | 0 | 70
1363 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0
1364 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/001065/2024-2025 | 33/NMD | 06/01/2025 | 30 | SAIKAT SINHA | 12.3 | 0 | 0
1365 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Additional work (F.H.T.C & LDS) at adjoining mouzas under JJM/Jal Swapna in connection with Augmentation of Gangaram PIPED WATER SUPPLY SCHEME under Phansidewa block, Darjeeling District under Siliguri W/S Division, PHD Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000011/2025-2026 | 1237/SWSD | 24/04/2025 | 30 | RAJEEV RANJAN OJHA | 11.94 | 0 | 0
1366 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 100 Cu.M. capacity R.C.C. Elevated Reservoir of 20 Mtrs. Staging Height with laying distribution system, soil investigation, rising main, boring of deep tubewells, construction of pump houses with toilet, boundary wall at head works and 2nd tubewell site with necessary interconnection, providing FHTC with platform and other allied works under Jal Jeevan Mission for Augmentation of GANGARAM TEA GARDEN PIPED WATER SUPPLY SCHEME of Phansidewa Block under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000044/2023-2024 | 670/SWSD | 16/06/2023 | 771 | RAJEEV RANJAN OJHA | 224.95 | 0 | 70
1367 | Siliguri W/S Division | Siliguri Sub-Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF GANGARAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER PHANSIDEWA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000063/2023-2024 | 256/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.65 | 0 | 100
1368 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000053/2022-2023 | 2034/SWSD | 16/12/2022 | 0 | Resource Division | 15.33 | 0 | 0
1369 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for GANGARAM TEA GARDEN, T/W I, under BAGDOGRA CCC [APPLICATION NO. 4003221633, Reference ID : 403068165] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01117/2023-2024 | BP/23-24/122 | 10/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0
1370 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for GANGARAM TG, T/W No. II (AUG), under BAGDOGRA CCC [APPLICATION NO. 4003263578, Reference ID : 403103790] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01653/2023-2024 | 23-24/173&174 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.75 | 0 | 0
1371 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
1372 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF GANGARAM TEA GARDEN AREA PIPED WATER SUPPLY SCHEM , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000436/2023-2024 | 1375/NMD | 09/08/2023 | 30 | NIRMAN | 20.9 | 0 | 0
1373 | Northern Mechanical | Siliguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (PHANSIDEWA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000996/2024-2025 | 15/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 23.02 | 0 | 0
1374 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0
1375 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00614/2023-2024 | BP-2023-24-412 | 12/01/2024 | 0 | WBSEDCL | 0.82 | 0 | 0
1376 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR PANTHABARI PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000001/2023-2024 | 32/NKWSMD | 17/04/2023 | 90 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 91.41 | 0 | 100
1377 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
1378 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) COLLECTION OF WATER SAMPLES FROM DIFFERENT SOURCES UNDER KALIMPONG DISTRICT UNDER NEORAKHOLA WATER SUPPLY & MAINTENANCE DIVISION P.H.E DIRECTORATE, KALIMPONG FROM 01/01/2025 TO 31/03/2025 (3 MONTHS). | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000164/2024-2025 | 2411/NKWSMD | 31/12/2024 | 90 | NIM TSHERING LEPCHA | 1.45 | 0 | 0
1379 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000002/2023-2024 | 58/NKWSMD | 24/04/2023 | 0 | Resource Division | 0.83 | 0 | 0
1380 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme For Hatta Piped Water Supply Scheme in Darjeeling Pulbazar Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000058/2023-2024 | 413/NKWSMD | 05/06/2023 | 938 | SAGARMATHA CONSTRUCTION CO. | 278.82 | 0 | 80
1381 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000047/2023-2024 | 442/NKWSMD | 07/06/2023 | 0 | Resource Division | 0.83 | 0 | 0
1382 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1383 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional estimate for water supply scheme for Manedara piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. (SM/15885) |  | Sub-Assistant Engineer | ORD/000017/2024-2025 | 981/NKWSMD | 18/06/2024 | 60 | ALLIED INSTRUMENTS | 13.06 | 0 | 100
1384 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MANEDARA PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000063/2023-2024 | 437/NKWSMD | 07/06/2023 | 690 | ALLIED INSTRUMENTS | 413.06 | 0 | 50
1385 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1386 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation with new source with laying of HDPE pipes for Soring Khasmahal Piped Water Supply Scheme under Rangli Rangliot Block District Darjeeling. |  | Sub-Assistant Engineer | ORD/000323/2023-2024 | 720/NKWSMD | 29/03/2024 | 278 | SRINIWAS AGARWAL | 22.64 | 0 | 100
1387 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kuchia Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000328/2022-2023 | 410/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 4.2 | 0 | 0
1388 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000013/2023-2024 | 213/SWSD | 25/04/2023 | 0 | Resource Division | 23.24 | 0 | 0
1389 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000033/2023-2024 | 2292/SWSD | 11/12/2023 | 0 | Resource Division | 1.05 | 0 | 0
1390 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000052/2023-2024 | 77/SWSD | 10/01/2024 | 0 | Resource Division | 9.93 | 0 | 0
1391 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1392 | Northern Mechanical | Siliguri Sub-Division | Quotation For New Service Connection charges under KUCHIA PWSS Tw-I under NMD PHE dte. Application no- 4003455839 Ref ID-403251521 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00620/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0
1393 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for KUCHIA, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319982, Reference ID : 403147083] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01967/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.61 | 0 | 0
1394 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KUCHIA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, & (Zone-II) TW-I, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000813/2023-2024 | 1670/NMD | 29/09/2023 | 30 | DIAMOND ELECTRICAL WORKS | 11.6 | 0 | 60
1395 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1396 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SORIANG KHASMAHAL & TAKLING BUSTY PIPED WATER SUPPLY SCHEME UNDER BLOCK- RANGLI RANGLIONT ; DISTRICT- DARJEELING. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000077/2023-2024 | 676/NKWSMD | 12/07/2023 | 515 | SRINIWAS AGARWAL | 531.05 | 0 | 100
1397 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Augmentation with new source with laying of HDPE pipes for Soring Khasmahal Piped Water Supply Scheme under Rangli Rangliot Block District Darjeeling. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000323/2023-2024 | 720/NKWSMD | 29/03/2024 | 278 | SRINIWAS AGARWAL | 22.64 | 0 | 100
1398 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000066/2023-2024 | 761/NKWSMD | 19/07/2023 | 0 | Resource Division | 2.74 | 0 | 0
1399 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00855/2023-2024 | BP-2023-24-656 | 23/03/2024 | 0 | WBSEDCL | 18.95 | 0 | 0
1400 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR DUPTIN BUSTY PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000028/2023-2024 | 104/NKWSMD | 28/04/2023 | 758 | SHAKTI CONSTRUCTION | 830.5 | 0 | 100
1401 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000026/2023-2024 | 251/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.42 | 0 | 0
1402 | Neorakhola W/S & Mtc.Div. |  | SURFACE WATER BASED RINGTONG TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000208/2023-2024 | 1289/NKWSMD | 17/10/2023 | 605 | SHAKTI CONSTRUCTION | 605.39 | 0 | 50
1403 | Neorakhola W/S & Mtc.Div. | Kurseong Division | GRAVITY BASED WATER SUPPLYSCHEME FORUNDER SELIM HILL UNDER JAL JEEWAN MISSION | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | BILL/00398/2024-2025 | "BP-2024-25-289 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.2 | 0 | 0
1404 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED SELIM HILL TEA GARDEN TO ACCOMODATE FHTC IN KURSEONG BLOCK | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000341/2022-2023 | 2756/NKWSMD | 09/03/2023 | 365 | SHAKTI CONSTRUCTION | 910.25 | 0 | 85
1405 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000259/2022-2023 | 2771/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.37 | 0 | 0
1406 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution pipeline and Rising Main allied with construction of 2 nos. big dia rig bore tube well by ODEX-165, Pump House (5.4 X 3.65 m), Iron Elimination Plant (10 cu.m/hr.), Boundary Wall including FHTC at NICHITPUR Piped Water Supply Scheme under Matigara Block, Darjeeling Dist. in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E. Dte. (2ND CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000039/2023-2024 | 643/SWSD | 15/06/2023 | 696 | U.K CONSTRUCTIONS | 108.96 | 0 | 30
1407 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH PROPOSED NICHITPUR PIPED WATER SUPPLY SCHEMES AT THE UNCOVERED MOUZAS UNDER MATIGARA BLOCK OF SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000067/2023-2024 | 260/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.05 | 0 | 100
1408 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000037/2023-2024 | 2302/SWSD | 12/12/2023 | 0 | Resource Division | 2.75 | 0 | 0
1409 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000046/2023-2024 | 71/SWSD | 10/01/2024 | 0 | Resource Division | 1.29 | 0 | 0
1410 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000059/2022-2023 | 2039/SWSD | 16/12/2022 | 0 | Resource Division | 15.3 | 0 | 0
1411 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1412 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for NICHINTAPUR, T/W No. I, under MATIGARA CCC [APPLICATION NO. 4003299595 ; Reference ID : 403130071] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01816/2023-2024 | BP/23-24/276 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.83 | 0 | 0
1413 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for NICHITPUR, T/W No. II, under NAXALBARI CCC, [APPLICATION NO. 4003299652, Reference ID : 403130074] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01953/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.95 | 0 | 0
1414 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
1415 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NICHITPUR PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000818/2023-2024 | 1673/NMD | 29/09/2023 | 30 | M/S UTPAL CHAKRABORTY & CO. | 11.43 | 0 | 85
1416 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (MATIGARA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000995/2024-2025 | 14/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 33.77 | 0 | 0
1417 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR BADAMTAM TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK: DARJEELING PULBAZAR DISTRICT DARJEELNG UNDER DARJEELING DIVISION PHED GTA. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000054/2025-2026 | 817/NKWSMD | 05/06/2025 | 90 | ASHIRWAD CONSTRUCTION CO | 29.04 | 0 | 0
1418 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BADAMTAM TEA GARDEN PWSS IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000184/2023-2024 | 947/NKWSMD | 17/08/2023 | 815 | ASHIRWAD CONSTRUCTION CO. | 1087.52 | 0 | 100
1419 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000270/2023-2024 | 1590/NKWSMD | 29/12/2023 | 10 | MANOMITA CIVIL ENGINEERING CONSULTANCY PVT LTD | 0.95 | 0 | 100
1420 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000104/2023-2024 | 966/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.07 | 0 | 0
1421 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00818/2023-2024 | BP-2023-24-534 | 26/02/2024 | 0 | WBSEDCL | 6.22 | 0 | 0
1422 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00819/2023-2024 | BP-2023-24-535 | 26/02/2024 | 0 | WBSEDCL | 4.83 | 0 | 0
1423 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000075/2023-2024 | 671/NKWSMD | 12/07/2023 | 635 | YAMA CONSTRUCTIONS LLP | 1111.51 | 0 | 100
1424 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TINGLING TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000170/2024-2025 | 160/NKWSMD | 04/02/2025 | 180 | S S CONSTRUCTIONS | 98.42 | 0 | 100
1425 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000118/2023-2024 | 1189/NKWSMD | 06/10/2023 | 0 | Resource Division | 5.08 | 0 | 0
1426 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Piped Water Supply Scheme for Lebong & Mineral Tea Garden (SM/18726) under Darjeeling Division, PHED, GTA | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000020/2024-2025 | 984/NKWSMD | 18/06/2024 | 60 | KUNCHAN JUNGA ENTERPRISES | 49.4 | 0 | 0
1427 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/18726) | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000149/2024-2025 | 2352/NKWSMD | 19/12/2024 | 60 | KUNCHAN JUNGA ENTERPRISES | 19.15 | 0 | 0
1428 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR LEBONG & MINERAL TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 1 | Sub-Assistant Engineer | ORD/000183/2023-2024 | 946/NKWSMD | 17/08/2023 | 866 | KUNCHAN JUNGA ENTERPRISES | 1046.33 | 0 | 85
1429 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 1 | Sub-Assistant Engineer | RTOR000102/2023-2024 | 965/NKWSMD | 21/08/2023 | 0 | Resource Division | 7.65 | 0 | 0
1430 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | RUNGBUL & HILL CART ROAD PIPED WATER SUPPLY SCHEME UNDER KURSEONG DIVISION. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000189/2023-2024 | 987/NKWSMD | 23/08/2023 | 755 | GARGO TRADERS | 1927.74 | 0 | 95
1431 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000112/2023-2024 | 998/NKWSMD | 24/08/2023 | 0 | Resource Division | 10.36 | 0 | 0
1432 | Siliguri W/S Division | Siliguri W/S Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
1433 | Siliguri W/S Division | Siliguri W/S Division | Laying rising main and distribution system (Part-A) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000026/2022-2023 | 537/SWSD | 16/06/2022 | 45 | M/S G.C. CONSTRUCTION & CO. | 47.93 | 0 | 0
1434 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system (Part-B) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000027/2022-2023 | 538/SWSD | 16/06/2022 | 40 | M/S G.C. CONSTRUCTION & CO. | 43.25 | 0 | 0
1435 | Siliguri W/S Division | Siliguri W/S Division | Laying rising main and distribution system (Part-A) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. Sl. No. 05. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000060/2022-2023 | 865/SWSD | 21/07/2022 | 45 | M/S G.C. CONSTRUCTION & CO. | 47.93 | 0 | 0
1436 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system (Part-B) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. Sl. No. 06. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000061/2022-2023 | 866/SWSD | 21/07/2022 | 40 | M/S G.C. CONSTRUCTION & CO. | 43.25 | 0 | 0
1437 | Siliguri W/S Division | Siliguri W/S Division | Construction of 400 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Mains, construction of Big dia rig bore tube wells by ODEX - 165, Pump Houses (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plants ,Boundary Walls including Functional Household Tap Connections for Augmentation of UTTAR BAGDOGRA Piped Water Supply Scheme (Zone - I & II) under Naxalbari Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000110/2023-2024 | 1155/SWSD | 09/08/2023 | 960 | MAHADEO PRASAD AGARWAL & CO | 495.4 | 0 | 0
1438 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system (Part-C) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 10. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000145/2021-2022 | 2441/SWSD | 21/03/2022 | 50 | NARAYAN CH GHOSH | 57.37 | 0 | 60
1439 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system (Part-D) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 11. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000146/2021-2022 | 2442/SWSD | 21/03/2022 | 40 | AKASH ENTERPRISE | 41.47 | 0 | 80
1440 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system (Part-E) for Augmentation of Uttar Bagdogra Zone-I Water Supply Scheme within Naxalbari Block under Siliguri W/S Division, P..H.E. Dte. SL. NO. 12. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000147/2021-2022 | 2443/SWSD | 21/03/2022 | 60 | KAMAL GHOSH | 60.01 | 0 | 0
1441 | Siliguri W/S Division | Siliguri W/S Division | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 100
1442 | Siliguri W/S Division | Siliguri W/S Division | Sinking of 04(four) Nos Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling at different Zones (as mentioned in ANNEXURE-A) of Uttar Bagdogra Piped Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000249/2022-2023 | 2164/SWSD | 30/12/2022 | 30 | K.R.ENTERPRISE | 32.57 | 0 | 0
1443 | Siliguri W/S Division | Siliguri W/S Division | FURTHER CONTINUATION ORDER FOR HIRING OF 1 (ONE) NO. MARUTI VAN (NON A/C) FOR THE SUPERINTENDING ENGINEER, NORTH BENGAL CIRCLE-I, P.H.E. DTE. PERIOF FROM 01.04.2023 TO 30.04.2023 i.e. 1 (ONE) MONTHS. VEHICLE NO. WB 73 B/1911. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000332/2022-2023 | 2987/SWSD | 28/03/2023 | 31 | RUPA PRASAD | 0.12 | 0 | 100
1444 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000013/2021-2022 | 2170/SWSD | 11/02/2022 | 0 | Resource Division | 225.89 | 0 | 0
1445 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000020/2022-2023 | 1450/SWSD | 29/09/2022 | 0 | Resource Division | 9.68 | 0 | 0
1446 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil) | VCH/000300/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 2.92 | 0 | 0
1447 | Siliguri W/S Division | Siliguri W/S Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil) | VCH/000889/2021-2022 | BP-2021-22-107 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 162.17 | 0 | 0
1448 | Northern Mechanical | Siliguri W/S Division | Electric quotation for new service connection at t.w no- i,z-ii of Uttar Bagdogra w/s scheme, in the dist. Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01348/2024-2025 | BP/24-25/217 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.91 | 0 | 0
1449 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF UTTAR BAGDOGRA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. III, IV and (Zone-II) TW-I,III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000756/2023-2024 | 1584/NMD | 08/09/2023 | 30 | SUMON ELECTRICAL | 46.7 | 0 | 75
1450 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00759/2023-2024 | BP-2023-24-504 | 26/02/2024 | 0 | WBSEDCL | 7.09 | 0 | 0
1451 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | STRENGHTENING OF LAYING DISTRIBUTION SYSTEM FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION,PHE.DTE. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000060/2025-2026 | 831/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 253.18 | 0 | 0
1452 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADITIONAL WORK FOR SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000061/2025-2026 | 830/NKWSMD | 09/06/2025 | 180 | MAA DURGA ENTERPRISE | 54.17 | 0 | 0
1453 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SINGBULLI TEA GARDEN, MANJUA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMODTE FHTC IN MIRIK BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000163/2023-2024 | 911/NKWSMD | 11/08/2023 | 365 | INTERIOR'S NEST | 1516.55 | 0 | 65
1454 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000096/2023-2024 | 960/NKWSMD | 21/08/2023 | 0 | Resource Division | 11.68 | 0 | 0
1455 | Siliguri W/S Division | Siliguri Sub-Division | Issue of fuel for office vehicles of Executive Engineer Siliguri W/S division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/00571/2023-2024 | BP-2023-24-196 | 28/03/2024 | 0 | SONA PETROL PUMP | 0.35 | 0 | 0
1456 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Barsadvita habitation Adhikari Barsadvita and village Mayanaguri habitation Moynaguri of Barsadvita piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000058/2020-2021 | 1014/SWSD | 11/12/2020 | 40 | VIJAY KUMAR ARORA | 33.45 | 28.95 | 100
1457 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission JJM and Jal Swapna under Command area village Maynaguri habitation Pitha bachi Ramchndra village Kelabari habitation Damravita Kalabari and village Alokjhari habitation Surya Mohan of Barsadvita piped water supply scheme and allied works at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000059/2020-2021 | 1015/SWSD | 11/12/2020 | 40 | M/S G.C. CONSTRUCTION & CO. | 35.14 | 7.44 | 20
1458 | Neorakhola W/S & Mtc.Div. |  | Surveying, planning, designing, delivery, erection, construction, commissioning and completion in all respect of all CIVIL, ELECTRICAL and MECHANICAL works like Intake, WTP, Raw Water rising main, Clear Water rising main (CWR at WTP to different GLR sites), GLRs, Chlorine cum switch room, Boundary Wall etc. including all allied related and enabling works for WATER SUPPLY SCHEME FOR MANGARJUNG AND OTHER 3 VILLAGES followed by 03 (three) months of Trial Run and subsequent Operation and maintenance of 03 (Three) years. |  |  | ORD/000114/2024-2025 | 1612/NKWSMD | 09/09/2024 | 546 | GARGO TRADERS | 8505.63 | 0 | 25
1459 | Neorakhola W/S & Mtc.Div. |  | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  |  | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1460 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Village Mahasing Habitation Fokira jote Mahasing village Deomani Habitation Deomani village Nandalal Habitation Jaban jote and Mouri jote of OMI Piped Water Supply Scheme and Allied works at Naxalbari block under Siliguri Sub Division PHE Dte (3rd CALL) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000008/2021-2022 | 694/SWSD | 02/08/2021 | 30 | S.K. BANIK | 27.18 | 0 | 100
1461 | Siliguri W/S Division | Siliguri Sub-Division | Laying of new pipe line inconnection with providing functional household tap connection (FHTC) at OMI village of OMI Piped W/S Scheme within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. Sl. No. 07. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000100/2022-2023 | 333/SWSD | 18/05/2022 | 10 | UJJWAL ROY | 4.39 | 0 | 100
1462 | Siliguri W/S Division | Siliguri Sub-Division | Laying bye-pass pipeline along with construction of boundary wall, development of land at head work site of OMI & adjoining w/s scheme under Siliguri Sub Division PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000791/2020-2021 | 1429/SWSD | 14/08/2020 | 0 | S.K. BANIK | 24.87 | 0 | 75
1463 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Motidhar Bijmillini T E Part A of Paschim Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000067/2020-2021 | 1081/SWSD | 18/12/2020 | 40 | M/S G.C. CONSTRUCTION & CO. | 33.72 | 0 | 85
1464 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Providing of Functional Household Tap Connection (FHTC) at Budharugaon & Dhakpara Mouza's under under Jal Jeevan & Jal Swapno programme of Budharugaon Water Supply Scheme under Phansidewa Block under Siliguri W/S Division , P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000014/2025-2026 | 1240/SWSD | 24/04/2025 | 45 | SUBIR CH. CHOWDHURY | 54.23 | 0 | 0
1465 | Siliguri W/S Division | Siliguri Sub-Division | Supply of 01 (one) no. Maxi Cab with Engine Capacity less than or equal to 2000 C.C. with Air Condition on hire basis (for monthly hiring) including driver under Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte. (With valid Taxi permit and other necessary documents as per norms of Zonal R.T.O) For 06 (six months) with effect from 01.07.2024 to 31.12.2024. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000037/2024-2025 | 1656/SWSD | 28/06/2024 | 180 | S S CONSTRUCTIONS | 0.95 | 0 | 0
1466 | Siliguri W/S Division | Siliguri W/S Division | Survey for existing water source electric connection nature of building etc. of schools,AWCs,health centres within different blocks under Siliguri Sub-Division,P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000230/2022-2023 | 544/SSD | 19/12/2022 | 15 | ROYAL ENTERPRISE | 1.02 | 0 | 100
1467 | Siliguri W/S Division | Siliguri W/S Division | Further continuation order for hiring of 01 (one) no maxi cab with engine capacity less than or equal to 2000 CC with air condition for the Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte for the period from 01.09.2023 to 31.12.2023 (For Executive Engineer, Siliguri W/S Division, P.H.E. Dte. i.e 04 (four) months. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000259/2023-2024 | 1492/SWSD | 31/08/2023 | 122 | SUBIR CH. CHOWDHURY | 0.59 | 0 | 0
1468 | Siliguri W/S Division | Siliguri W/S Division | Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C.on hire basis including driver for Assistant Engineer-I , Siliguri W/S Division, P.H.E. Dte. Dist. Darjeeling (with valid Taxi permit ). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000411/2023-2024 | 284/SWSD | 06/02/2024 | 182 | SUDIP BASAK | 0.88 | 0 | 0
1469 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation work for PWS Scheme for Bhotay Goth, Soom 3rd Division Gram Panchyat -Soom T.G., Block Darjeeling -Pull-Bijanbari Block. TSM No. 009298 SM Code-SM/08938 |  | Sub-Assistant Engineer | ORD/000030/2022-2023 | 493/NKWSMD | 24/05/2022 | 60 | MS JAGANNATH PRASAD | 14.04 | 0 | 98
1470 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000033/2022-2023 | 1260/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.8 | 0 | 0
1471 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including augmentation & extension for PWS Scheme for Samadhin Forest Villa, Gram Panchyat -Sirkhola Danra Gaon, Block Bijanbari -PullBazar. TSM No. 009470 SM Code-SM/08924 |  | Sub-Assistant Engineer | ORD/000033/2022-2023 | 496/NKWSMD | 24/05/2022 | 60 | SUNIL SHARMA | 13.76 | 0 | 50
1472 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000038/2022-2023 | 1265/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.14 | 0 | 0
1473 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000126/2022-2023 | 1902/NKWSMD | 15/12/2022 | 0 | Resource Division | 0.14 | 0 | 0
1474 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000186/2022-2023 | 2576/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.14 | 0 | 0
1475 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at 3rd Mile Simkuna Gram GP - Rungbull, Block - Jorebungalow Sukhia. |  | Sub-Assistant Engineer | ORD/000165/2022-2023 | 941/NKWSMD | 12/07/2022 | 60 | BIMLA GURUNG | 9.29 | 0 | 0
1476 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000195/2022-2023 | 2619/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.28 | 0 | 0
1477 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Pokhriabong Turzum Panchyat - Pokhriabong-II Block - Jorebungalow Sukhia. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000169/2022-2023 | 945/NKWSMD | 12/07/2022 | 60 | MOHAN MUKHIA | 67.07 | 0 | 100
1478 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000081/2022-2023 | 1363/NKWSMD | 21/09/2022 | 0 | Resource Division | 3.2 | 0 | 0
1479 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000131/2022-2023 | 1907/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.2 | 0 | 0
1480 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000191/2022-2023 | 2617/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.2 | 0 | 0
1481 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at New Fallodi Tea Garden GP - Soureni I, Block-Mirik. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000166/2022-2023 | 942/ NKWSMD | 12/07/2022 | 60 | ROHIT KUMAR DEWAN | 9.11 | 0 | 90
1482 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Lower Mamring Khasmahal in Kurseong Block within Darjeeling District. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | ORD/000043/2023-2024 | 187/NKWSMD | 04/05/2023 | 690 | PREM CHANDRA RAI | 356.26 | 0 | 85
1483 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Junior Engineer7,Sub-Assistant Engineer | RTOR000044/2023-2024 | 321/NKWSMD | 24/05/2023 | 0 | Resource Division | 0.69 | 0 | 0
1484 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed M.M TERAI Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000153/2022-2023 | 272/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.35 | 0 | 100
1485 | Siliguri W/S Division | Siliguri W/S Division | Construction of Pump House (5.4 X 3.65) size, Rig Bore Big Dia Deep Tubewell by ODEX-165 method of drilling, boundary wall allied with laying of rising main, distribution system and providing functional household tap connection (FHTC) under JJM for M.M. TERAI PIPED WATER SUPPLY SCHEME within Naxalbari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000245/2022-2023 | 2094/SWSD | 22/12/2022 | 75 | SUDIP BASAK | 88.33 | 0 | 60
1486 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000034/2022-2023 | 1464/SWSD | 29/09/2022 | 0 | Resource Division | 2.16 | 0 | 0
1487 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000046/2022-2023 | 2026/SWSD | 16/12/2022 | 0 | Resource Division | 1.45 | 0 | 0
1488 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for M.M TERAI, T/W No. I under NAXALBARI CCC [APPLICATION NO. 4003312828 ; Reference ID : 403142027] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01919/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.57 | 0 | 0
1489 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for M.M.TERAI PIPED WATER SUPPLY SCHEME, TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000353/2023-2024 | 1314/NMD | 04/08/2023 | 562 | HARAGOURI ENTERPRISE | 11.5 | 0 | 100
1490 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SURFACE WATER BASED NAYA KAMAN PWSS TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE-GTA. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | ORD/000012/2025-2026 | 498/NKWSMD | 09/04/2025 | 60 | ABHINAY CHETTRI | 19.79 | 0 | 0
1491 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED NAYA KAMAN PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | ORD/000261/2022-2023 | 1653/NKWSMD | 04/11/2022 | 1062 | ABHINAY CHETTRI | 86.11 | 0 | 80
1492 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer6,Sub-Assistant Engineer | RTOR000233/2022-2023 | 2587/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.81 | 0 | 0
1493 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED TINDHURIA GOLIAPAKHA PIPED WATER SUPPLY SCHEME TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000220/2022-2023 | 1118/NKWSMD | 05/08/2022 | 270 | PREM CHANDRA RAI | 99.95 | 0 | 90
1494 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000266/2022-2023 | 2838/NKWSMD | 17/03/2023 | 0 | Resource Division | 0.92 | 0 | 0
1495 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Ringtong Tinghare (Gorabari Margetshop GP) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer1,Assistant Engineer4 | Sub-Assistant Engineer | ORD/000112/2022-2023 | 792/NKWSMD | 30/06/2022 | 1360 | SAMIR THAPA | 6.78 | 0 | 70
1496 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1,Assistant Engineer4 | Sub-Assistant Engineer | RTOR000048/2022-2023 | 1292/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.31 | 0 | 0
1497 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household Tap connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Seepoydhura T.E. Mahanadi GP Block - Kurseong Block. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000133/2022-2023 | 813/NKWSMD | 30/06/2022 | 90 | HIMALI CONSTRUCTION COMPANY | 26.66 | 0 | 100
1498 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000064/2022-2023 | 1308/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.51 | 0 | 0
1499 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Additional work piped water supply scheme for Pokhriabong Busty No. 5 under Jal Jiwan Mission and Jal Swapno Programme. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000179/2023-2024 | 940/NKWSMD | 16/08/2023 | 510 | RISHI KESH THAKURI | 12.62 | 0 | 100
1500 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR POKHRIBONG KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000256/2022-2023 | 1619/NKWSMD | 03/11/2022 | 180 | YAMA CONSTRUCTIONS LLP | 897.18 | 0 | 0
1501 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Supply and erection of scheme information board made of 50X50X6 mm. M.S. angle frame 6¿00¿X4¿00¿ size at a height over 1.5M. over ground including ties and bracing made of 32X32X6 mm. M.S. Angle and legs(50X50X6mm) are embedded at a depth of 600 mm. and to be fixed in Cement Concrete (1:2:4) footing size 250X250X600 mm. underground. The board for display to be made on latex venyle print as per standard format given from department to be pasted over M.S. sheet (size-6¿X4¿) including carriage, loading, unloading at different sites for different JJM works under Darjeeling Division-I, P.H.E.D., GTA |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000261/2023-2024 | 159/AE-II/NKWSMD | 10/01/2024 | 15 | MADAN KUMAR CHHETRI | 23.94 | 0 | 100
1502 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000101/2023-2024 | 964/NKWSMD | 21/08/2023 | 0 | Resource Division | 3.58 | 0 | 0
1503 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LONGVIEW PWSS TO ACCOMODTE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | ORD/000307/2022-2023 | 2471/NKWSMD | 06/02/2023 | 455 | SHAKTI CONSTRUCTION | 1742.62 | 0 | 100
1504 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | RTOR000213/2022-2023 | 2561/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.11 | 0 | 0
1505 | Neorakhola W/S & Mtc.Div. | Kurseong Division | FOREST PAYMENT | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | BILL/00760/2023-2024 |  | 15/02/2024 | 0 | DIVISIONAL FOREST OFFICER | 10.71 | 0 | 0
1506 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest payment | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | BILL/01003/2023-2024 | BP-2023-24-601 | 18/03/2024 | 0 | DIVISIONAL FOREST OFFICER | 3.28 | 0 | 0
1507 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SURFACE WATER BASED BARASITTONG KHASMAHAL & SELPU KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000128/2024-2025 | 2205/NKWSMD | 02/12/2024 | 180 | YAMA CONSTRUCTIONS LLP | 246.9 | 0 | 80
1508 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Surface water based Barasitting Khasmahal & Selpu Khasmahal PWSS to accommodate FHTC in Kurseong Block within Darjeeling District | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000305/2022-2023 | 2362/NKWSMD | 01/02/2023 | 585 | YAMA CONSTRUCTIONS LLP | 1751.75 | 0 | 100
1509 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000150/2022-2023 | 2070/NKWSMD | 05/01/2023 | 0 | Resource Division | 10.71 | 0 | 0
1510 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000198/2022-2023 | 2594/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.35 | 0 | 0
1511 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME UNDER MATIGARA BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000049/2023-2024 | 242/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.19 | 0 | 100
1512 | Siliguri W/S Division | Siliguri W/S Division | Renovation of the pump House and Others allied Works at Mandalaguri (H/W) site of Mandalaguri Piped Water Supply Scheme under Siliguri W/S Division P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000144/2024-2025 | 2538/SWSD | 18/09/2024 | 45 | K.K.GHOSH & CO. | 3.2 | 0 | 0
1513 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000079/2022-2023 | 2058/SWSD | 16/12/2022 | 0 | Resource Division | 23.57 | 0 | 0
1514 | Central Drilling | Siliguri W/S Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). (Phase-X) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000031/2024-2025 | 563/CDD | 07/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 0
1515 | Central Drilling | Siliguri W/S Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000217/2023-2024 | 2292/CDD | 19/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 67.69 | 0 | 10
1516 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for MANDALAGURI, T/W-I, under MATIGARA CCC, [APPLICATION NO. 4003340645, Reference ID : 403163196] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/02138/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.1 | 0 | 0
1517 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANDALAGURI PIPED WATER SUPPLY SCHEME , (Zone-II) TW No III in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000438/2023-2024 | 1377/NMD | 09/08/2023 | 30 | BHAGIRATHI JUTE & HOLDINGS PVT. LTD. | 10.6 | 0 | 0
1518 | Northern Mechanical | Siliguri W/S Division | Installation of two tank chlorination system at MANDALAGURI and other adjacent water supply scheme UNDER JJM under MATIGARA Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Darjeeling. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000889/2024-2025 | 81/SMSD | 07/02/2025 | 10 | CHOWDHURY AND BASU ENTERPRISE | 1.1 | 0 | 0
1519 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MATIGARA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/001065/2024-2025 | 33/NMD | 06/01/2025 | 30 | SAIKAT SINHA | 12.3 | 0 | 0
1520 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Pokhari Tar with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer 2,Assistant Engineer 4,Assistant Engineer2,Assistant Engineer4 |  | ORD/000181/2022-2023 | 957/NKWSMD | 12/07/2022 | 60 | PHURBA RUMBA | 25.37 | 0 | 0
1521 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer 4,Assistant Engineer2,Assistant Engineer4 |  | RTOR000076/2022-2023 | 1320/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.22 | 0 | 0
1522 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer 4,Assistant Engineer2,Assistant Engineer4 |  | RTOR000147/2022-2023 | 2067/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.22 | 0 | 0
1523 | Siliguri W/S Division | Siliguri W/S Division | Construction of 200 Cu.M & 150 cum capacity RCC Elevated Reservoir each of 20 mtrs Staging Height at the head works sites,laying rising main,Laying distribution pipeline with Functional Household Tap Connection (FHTC), construction of Two number pump houses(5.40 X 3.60 m),Two number pump houses (3.00 X 3.60 m), Iron Elimination Plant (IEP) with Blower room ,Sinking of four (4) nos Tube well (ODEX-165 method),Soil Investigation at H/W sites and Boundary wall for BARA ADALPUR DWITYA KHANDA PWSS (ZONE I & II) Block:Matigara,Dist: Darjeeling under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000109/2023-2024 | 1150/SWSD | 08/08/2023 | 783 | MAHADEO PRASAD AGARWAL & CO | 510.38 | 0 | 80
1524 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bara Adalpur Dwitiyo Khanda Piped water supply schemes at the uncovered mouzas under Matigara Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000158/2022-2023 | 288/SSD | 26/05/2022 | 20 | SUBHANKAR GHOSH | 2.82 | 0 | 100
1525 | Siliguri W/S Division | Siliguri W/S Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and writing the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour sample as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within 328 Villages in Different Block( Matigara,Phansidewa, KharibarI,Naxalbari Block) under Siliguri W/S Division all complete as per direction of EIC.In Each Villge in 4 Locations tentatively, In Each Location (8 X 5= 40 Sq.Ft) Writing Area Required or as per the Dimension given by PHE Dte.), Writing area should be Geo Tagged in appropriate portal as guided by PHE Department | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000288/2023-2024 | 382/SWSD | 15/02/2024 | 30 | PHANSIDEWA SOCIAL & RURAL WELFARE SOCIETY | 21.57 | 0 | 50
1526 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000012/2022-2023 | 1375/SWSD | 21/09/2022 | 0 | Resource Division | 10.86 | 0 | 0
1527 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000028/2023-2024 | 2288/SWSD | 11/12/2023 | 0 | Resource Division | 3.57 | 0 | 0
1528 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000072/2022-2023 | 2051/SWSD | 16/12/2022 | 0 | Resource Division | 31.66 | 0 | 0
1529 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1530 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BARAADALPUR DWITYAKHANDA, T/W No. I, ZONE-II, under SHIVMANDIR CCC [APPLICATION NO. 4003300574 ; Reference ID : 403130566] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01737/2023-2024 | BP/23-24/220 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.47 | 0 | 0
1531 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BARAADALPUR DWITYAKHANDA, T/W No. II, ZONE-II, under SHIVMANDIR CCC [APPLICATION NO. 4003300577 ; Reference ID : 403130594] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01738/2023-2024 | BP/23-24/221 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.17 | 0 | 0
1532 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BARAADALPUR, T/W No. II, ZONE-I, under MATIGARA CCC [APPLICATION NO. 4003299635 ; Reference ID : 403130072] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01817/2023-2024 | BP/23-24/277 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.16 | 0 | 0
1533 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for BARAADALPUR, T/W No. I, ZONE-I, under MATIGARA CCC [APPLICATION NO. 4003299617 ; Reference ID : 403130073] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01820/2023-2024 | BP/23-24/280 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0
1534 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA ADALPUR DWITIYA KHANDA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000751/2023-2024 | 1579/NMD | 08/09/2023 | 694 | CHOWDHURY AND BASU ENTERPRISE | 23.46 | 0 | 100
1535 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Khalingdhura & Vahtukvar TG (Bhuttakheti) GP - Rangit-I, Block - Bijanbari Pullbazar |  | Sub-Assistant Engineer | ORD/000254/2022-2023 | 1617/NKWSMD | 03/11/2022 | 1060 | MANI KUMAR CHHETRI | 48.48 | 0 | 85
1536 | Siliguri W/S Division | Siliguri W/S Division | Acceptance cum work order for Repair and Renovation of Boundary wall( Zn-II ) ,Approach road & Drain (Zn-III) , Boosting Pump Connection(Zn-I) and allied works for the Augmentation of Mangalsing Piped Water Supply Scheme in connection with JJM under Siliguri W/S Division P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000009/2025-2026 | 1235/SWSD | 24/04/2025 | 45 | NARAYAN CH GHOSH | 8.25 | 0 | 0
1537 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME UNDER NAXALBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000050/2023-2024 | 243/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 3.34 | 0 | 100
1538 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution of pipeline, construction of boundary wall, pump house, installation of I.E.Plant ,Providing functional House hold Tap Connection (FHTC) at ( Zone -I) , ( Zone-II ) & ( Zone-III ) for augmentation of Mangalsing PWSS under JJM within Naxalbari block under Siliguri WS Division, PHE Dte. Sl No. 09 | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000077/2023-2024 | 868/SWSD | 14/07/2023 | 180 | M/S DOLPHIN CONSTRUCTION CO | 396.62 | 0 | 40
1539 | Siliguri W/S Division | Siliguri W/S Division | Shifting of existing pipeline to new pipeline ,house connection along with laying of additional pipeline at Sebdella Mouza and Mangalsingh Mouza under Mangalsingh Water supply scheme under Siliguri w/s Division, PHE Dte | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000141/2024-2025 | 2535/SWSD | 18/09/2024 | 30 | NARAYAN CH GHOSH | 4.92 | 0 | 100
1540 | Siliguri W/S Division | Siliguri W/S Division | Laying New HDPE Pipe Line Under Mangalsingh Pwss From Second Tubewell Site To Sebdullhajote Mouza ( Kanu Sanyal Basti) , Under Siliguri Sub Division, Under Siliguri W/S Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000189/2023-2024 | 1949/SWSD | 16/10/2023 | 15 | NARAYAN CH GHOSH | 7.12 | 0 | 95
1541 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000078/2022-2023 | 2057/SWSD | 16/12/2022 | 0 | Resource Division | 45.97 | 0 | 0
1542 | Central Drilling | Siliguri W/S Division | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23) (Phase-IX). | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000030/2024-2025 | 560/CDD | 06/08/2024 | 61 | JHARGRAM SPV PRIVATE LIMITED | 15.04 | 0 | 10
1543 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for MANGALSING, T/W No. I,ZONE-II under NAXALBARI CCC [APPLICATION NO. 4003289754 ; Reference ID : 403122959] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01708/2023-2024 |  | 22/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.63 | 0 | 0
1544 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANGALSING PIPED WATER SUPPLY SCHEME , (Zone-III) TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000445/2023-2024 | 1384/NMD | 09/08/2023 | 30 | BONANZA ENTERPRISE | 12.99 | 0 | 100
1545 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/001068/2024-2025 | 36/NMD | 06/01/2025 | 30 | M/S PALIDEB ENGINEERING WORKS | 9.21 | 0 | 0
1546 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme for Samarik Pani Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000265/2022-2023 | 1560/NKWSMD | 21/10/2022 | 965 | SRINIWAS AGARWAL | 1158.25 | 0 | 95
1547 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000122/2022-2023 | 1899/NKWSMD | 15/12/2022 | 0 | Resource Division | 5.24 | 0 | 0
1548 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000181/2022-2023 | 2609/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.24 | 0 | 0
1549 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PWSS IN JORE BUNGLOW SUKHIAPOKHARI BLOCK UNDER DARJEELING DISTRICT.(SM/13955) | Assistant Engineer 4 |  | BILL/00644/2024-2025 | BP-2024-25-450 | 09/12/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.58 | 0 | 0
1550 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR DOOTERIA FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 4 |  | ORD/000294/2022-2023 | 2152/NKWSMD | 20/01/2023 | 1065 | VINAYAK CONSTRUCTION | 229.98 | 0 | 80
1551 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 |  | RTOR000207/2022-2023 | 2555/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.48 | 0 | 0
1552 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1553 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Water Supply Scheme for Bamon Pokhari Forest Piped Water Supply Scheme in Kurseong Block Under Darjeeling District | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | ORD/000278/2022-2023 | 1879/NKWSMD | 14/12/2022 | 980 | ROSHAN BISWAKARMA | 211.2 | 0 | 60
1554 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 4,Assistant Engineer4 | Junior Engineer4,Sub-Assistant Engineer | RTOR000228/2022-2023 | 2583/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.02 | 0 | 0
1555 | Siliguri W/S Division | Siliguri W/S Division | Construction of Pump House 2 nos, Rig bord 2 nos big dia T/W by Odex -165 method, Boundary walls, Laying distribution system (HDPE pipe), rising main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with (Three) month trial run IEP (25 cum/hr) and allied works for Augmentation of Sona Chandi PWSS at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 09/SWSD | 05/04/2023 | 105 | A.K.CONSTRUCTION | 115.86 | 0 | 60
1556 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF SONA CHANDI PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000064/2023-2024 | 257/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.56 | 0 | 100
1557 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000044/2023-2024 | 69/SWSD | 10/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
1558 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000060/2022-2023 | 2040/SWSD | 16/12/2022 | 0 | Resource Division | 16.12 | 0 | 0
1559 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for SONA CHANDI, T/W No. I, under KHARIBARI CCC, [APPLICATION NO. 4003319880, Reference ID : 403147076] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01950/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.9 | 0 | 0
1560 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for SONA CHANDI, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003319753, Reference ID : 403147078] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01951/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.2 | 0 | 0
1561 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
1562 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Sona Chandi Piped Water Supply Scheme, TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000662/2023-2024 | 1476/NMD | 17/08/2023 | 776 | T S CONSTRUCTION | 24.83 | 0 | 90
1563 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0
1564 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001069/2024-2025 | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0
1565 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme For Ghoom Pahar Forest under JAL JEEWAN MISSION within Jorebunglow Sukhia Pokhri Block,District-Darjeeling Detail - (SW No. : SW/140971/2023) |  | Junior Engineer-IV,Sub-Assistant Engineer | BILL/00392/2024-2025 | BP-2024-25-291 | 24/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 6.45 | 0 | 0
1566 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | External Water Supply Works at 10 Bedded Hospital, Ghoom, Darjeeling, GTA |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000241/2023-2024 | 1507/NKWSMD | 06/12/2023 | 210 | DHIRAJ TAMANG | 17.88 | 0 | 100
1567 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Preparation of draft proposal including preparation of maps in KML file, DGPS Map, SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 05 (five) number of scheme under JJM (Jal Jeevan Mission). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000273/2023-2024 | 1591/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1568 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR GHOOM PAHAR FOREST PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW SUKIAPAKHRI BLOCK UNDER DARGEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000315/2022-2023 | 2519/NKWSMD | 15/02/2023 | 815 | GARGO TRADERS | 1586.68 | 0 | 85
1569 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1570 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/10/2023 to 30/11/2023 (2 Months). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000325/2023-2024 | 1139/NKWSMD | 29/09/2023 | 61 | THE ELECTRIC SPHERE | 0.79 | 0 | 100
1571 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | (Continuation) Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/12/2023 to 31/01/2024 (2 Months). |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000326/2023-2024 | 1457/NKWSMD | 30/11/2023 | 62 | THE ELECTRIC SPHERE | 0.79 | 0 | 100
1572 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000209/2022-2023 | 2557/NKWSMD | 17/02/2023 | 0 | Resource Division | 8.43 | 0 | 0
1573 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000240/2022-2023 | 2714/NKWSMD | 03/03/2023 | 0 | Resource Division | 8.43 | 0 | 0
1574 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 300 - 1 No. & 150 - 2 Nos. cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging Height at the head works site (Zone - I, II & III) including distribution system (HDPE) with Rising Main, Rig bore 6 Nos. big dia T/W by Odex-165 method, Providing Functional Household Tap Connection (FHTC), Pump House 6 Nos., Blower Room 3 Nos., IEP 70, 35 & 35 cu.m./hr, Boundary Walls, Horizontal Boring, Soil Testing and allied works at SINGHIJHOR PWSS Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000107/2023-2024 | 1147/SWSD | 08/08/2023 | 693 | UNIBRO INFRASERV PRIVATE LIMITED | 1080.94 | 0 | 50
1575 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Singijhor Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000327/2022-2023 | 409/SSD | 28/07/2022 | 20 | ENVIROTECH SOLUTIONS | 3.6 | 0 | 0
1576 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000038/2023-2024 | 58/SWSD | 09/01/2024 | 0 | Resource Division | 22.63 | 0 | 0
1577 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000084/2022-2023 | 2201/SWSD | 04/01/2023 | 0 | Resource Division | 74.03 | 0 | 0
1578 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1579 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for SINGIJHOR Zone-II,TW- II under BAGDOGRA CCC | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00383/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.76 | 0 | 0
1580 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for SINGIJHOR Zone-II,TW- I under BAGDOGRA CCC | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00384/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 17.12 | 0 | 0
1581 | Northern Mechanical | Siliguri Sub-Division | New service connection at singijhora PWSS,Z-I,TW-II under NMD PHE Dte. Application no- 4003417642 Ref id- 403224817 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00386/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.19 | 0 | 0
1582 | Northern Mechanical | Siliguri Sub-Division | New service connection at singijhora PWSS,Z-I,TW-I under NMD PHE Dte. Application no- 4003417637 Ref id- 403224816 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00387/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.08 | 0 | 0
1583 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for SINGIJHORA, T/W No.I, ZONE-III under BAGDOGRA CCC, [APPLICATION NO. 4003326146, Reference ID : 403152620] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01958/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0
1584 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for SINGIJHORA, T/W No.II, ZONE-III under BAGDOGRA CCC, [APPLICATION NO. 4003326171, Reference ID : 403152622] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01959/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.05 | 0 | 0
1585 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SINGIJHOR PIPED WATER SUPPLY SCHEME, ( ZONE-I) TW No. I and II, (ZONE-II) TW No. I and II, (ZONE-III) TW No. I and II, in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000790/2023-2024 | 1654/NMD | 29/09/2023 | 701 | M/S P.P. ELECTRICALS | 45.94 | 0 | 75
1586 | Northern Mechanical | Siliguri Sub-Division | Supply and Delivery of C.I.D.F specials for using pumping machinery installation purpose at SINGIJHORA W/S/S under JJM in the dist. of Siliguri under, Northern Mechanical Division ,PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001437/2023-2024 | 425/SMSD | 20/12/2023 | 377 | SARKAR ELECTRIC | 0.58 | 0 | 100
1587 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000012/2023-2024 | 101/NKWSMD | 28/04/2023 | 999 | HARI PRASAD CHETTRI | 258.75 | 0 | 70
1588 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR RISHIHAT TEA GARDEN PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. (SM/16161) |  | Sub-Assistant Engineer | ORD/000150/2024-2025 | 2353/NKWSMD | 19/12/2024 | 180 | HARI PRASAD CHETTRI | 53.29 | 0 | 0
1589 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000011/2023-2024 | 208/NKWSMD | 10/05/2023 | 0 | Resource Division | 2.42 | 0 | 0
1590 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system along with boring of new tubewells by ODEX-165, construction of pump houses, boundary walls at 3rd and 4th tubewell site, installation of I.E.P. at both sites and other allied works in connection with augmentation of TARBANDHA Piped Water Supply Scheme at Phansidewa block, Darjeeling dist. under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000013/2023-2024 | 336/SWSD | 08/05/2023 | 620 | UJJWAL ROY | 90.32 | 0 | 75
1591 | Siliguri W/S Division | Siliguri Sub-Division | Additional work (Including repairing of damaged house connection , Pipeline extention of existing pipeline etc) & other allied works(laying of pipeline , cleaning the chokage of pipe line and ferrule , repair of pump house , Drain and boundary wall) in connection with augmentation of TARBANDHA Piped Water Supply Scheme at Phansidewa block, Darjeeling dist. under Siliguri Sub Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000244/2024-2025 | 484/SWSD | 12/02/2025 | 301 | UJJWAL ROY | 17.38 | 0 | 90
1592 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000002/2023-2024 | 201/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0
1593 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1594 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for TARBANDHA, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003303453 ; Reference ID : 403135383] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01813/2023-2024 | BP/23-24/273 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.33 | 0 | 0
1595 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for TARBANDHA, T/W No. II, under BAGDOGRA CCC, [APPLICATION NO.4003308985, Reference ID : 403137427] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02033/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.92 | 0 | 0
1596 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000084/2025-2026 | 1074/NMD | 14/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 148.48 | 0 | 0
1597 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF TARBANDHA PIPED WATER SUPPLY SCHEME , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000806/2023-2024 | 1663/NMD | 29/09/2023 | 30 | SARKAR ELECTRIC | 10.38 | 0 | 100
1598 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: PHANSIDEWA, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001072/2024-2025 | 40/NMD | 06/01/2025 | 30 | B.B. CONCERNED | 15.33 | 0 | 0
1599 | Neorakhola W/S & Mtc.Div. | Kurseong Division | GRAVITY BASED WATER SUPPLY SCHEME FOR RANGAMOHAN UNDER JAL JEEVAN MISSION. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00395/2024-2025 | BP-2024-25-287 | 25/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 2.7 | 0 | 0
1600 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED RANGMOHAN PWSS TO ACCOMODATE FHTC IN MIRIK BLOCK | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000330/2022-2023 | 2669/NKWSMD | 01/03/2023 | 670 | MAHENDRA ADHIKARI | 304.14 | 0 | 85
1601 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000257/2022-2023 | 2776/NKWSMD | 10/03/2023 | 0 | Resource Division | 1.06 | 0 | 0
1602 | Siliguri W/S Division | Siliguri Sub-Division | Part Work order for Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height with Laying distribution system, Soil investigation, Rising main, Boring of deep tubewell by ODEX-165 method, Construction of Pump House with Toilet, Boundary Wall at Head Works and 2nd Tube Well site with necessary interconnection and Providing FHTC and Other allied works under Jal Jeevan Mission for Lohasing Piped water Supply Scheme within Matigara Block under Siliguri W/S Division, P.H.E. Dte. (Part - II) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000196/2024-2025 | 3485/SWSD | 19/12/2024 | 60 | CAPITAL ENGINEERS | 87.1 | 0 | 0
1603 | Siliguri W/S Division | Siliguri Sub-Division | Part Work order for Construction of 200 cu.m. capacity R.C.C. Elevated Reservoir , 20 Mtrs. Staging height with Laying distribution system, Soil investigation, Rising main, Boring of deep tubewell by ODEX-165 method, Construction of Pump House with Toilet, Boundary Wall at Head Works and 2nd Tube Well site with necessary interconnection and Providing FHTC and Other allied works under Jal Jeevan Mission for Lohasing Piped water Supply Scheme within Matigara Block under Siliguri W/S Division, P.H.E. Dte. (Part - I) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000258/2023-2024 | 109/SWSD | 15/01/2024 | 112 | CAPITAL ENGINEERS | 161.7 | 0 | 0
1604 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Lohasing Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000324/2022-2023 | 402/SSD | 25/07/2022 | 20 | ENVIROTECH SOLUTIONS | 2.64 | 0 | 30
1605 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000004/2023-2024 | 202/SWSD | 25/04/2023 | 0 | Resource Division | 23.39 | 0 | 0
1606 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000035/2023-2024 | 2293/SWSD | 11/12/2023 | 0 | Resource Division | 1.88 | 0 | 0
1607 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000047/2023-2024 | 72/SWSD | 10/01/2024 | 0 | Resource Division | 7.61 | 0 | 0
1608 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1609 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for LOHASING, T/W No. I, under NAXALBARI CCC [APPLICATION NO. 4003301385 ; Reference ID : 403131311] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01742/2023-2024 | BP/23-24/229 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.31 | 0 | 0
1610 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for LOHASING Piped Water Supply Scheme, TW No.- I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000812/2023-2024 | 1669/NMD | 29/09/2023 | 30 | ALPHA ENTERPRISE | 12.03 | 0 | 0
1611 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House with toilet , laying distribution system, Rising Main, boring of deep tube well by ODEX-165 method, construction of Blower Room with IEP, Boundary Wall at H/W and second tube well site with necessary interconnection and providng FHTC and other allied work under Jal Jeevan Mission for DHEMAL Piped Water Supply Scheme Block : Naxalbari under Siliguri W/S Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000120/2023-2024 | 1225/SWSD | 14/08/2023 | 871 | K.R.ENTERPRISE | 349.22 | 0 | 10
1612 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dhemal Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000323/2022-2023 | 319/SSD | 20/06/2022 | 20 | ENVIROTECH SOLUTIONS | 2.4 | 0 | 30
1613 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000020/2023-2024 | 1804/SWSD | 30/09/2023 | 0 | Resource Division | 11.72 | 0 | 0
1614 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000029/2023-2024 | 2287/SWSD | 11/12/2023 | 0 | Resource Division | 4.4 | 0 | 0
1615 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000048/2023-2024 | 73/SWSD | 10/01/2024 | 0 | Resource Division | 9.99 | 0 | 0
1616 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | RTOR000088/2022-2023 | 2212/SWSD | 05/01/2023 | 0 | Resource Division | 11.92 | 0 | 0
1617 | Central Drilling | Siliguri Sub-Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1618 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1619 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR TAKLING KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000031/2025-2026 | 631/NKWSMD | 05/05/2025 | 60 | SRINIWAS AGARWAL | 12.88 | 0 | 0
1620 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000036/2023-2024 | 323/NKWSMD | 24/05/2023 | 0 | Resource Division | 2.37 | 0 | 0
1621 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional estimate for water supply scheme for Bara Mungwa piped water supply scheme in Rangli-Rangliot Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000016/2024-2025 | 980/NKWSMD | 18/06/2024 | 60 | GARGO TRADERS | 12.72 | 0 | 100
1622 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BARA MUNGWA PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000064/2023-2024 | 438/NKWSMD | 07/06/2023 | 690 | GARGO TRADERS | 455.08 | 0 | 100
1623 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PROPOSED PUMPING BASED PIPED WATER SUPPLY SCHEME FOR RAMBI BAZAR DIF UNDER TEESTA G.P, BLOCK : KALIMPONG - I, DISTRICT:KALIMPONG |  | Sub-Assistant Engineer | ORD/000322/2022-2023 | 2652/NKWSMD | 28/02/2023 | 605 | KAMAKHAYA CONSTRUCTION | 179.69 | 0 | 80
1624 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1625 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Gravity Based Water Supply Scheme For Pubong Thulokhola under JAL JEEWAN MISSION under RR Block, District- Darjeeling Detail - (SW No. : SW/140500/2023) |  | Sub-Assistant Engineer | BILL/00394/2024-2025 | BP-2024-25-285 | 25/09/2024 | 0 | DIVISIONAL FOREST OFFICER | 4.35 | 0 | 0
1626 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work for Water supply Pubong Khasmahal Piped Water Supply Scheme Block Rangli-Rangliot District: Darjeeling. |  | Sub-Assistant Engineer | ORD/000003/2024-2025 | 967/NKWSMD | 14/06/2024 | 60 | RAMESH AGARWAL | 14.12 | 0 | 95
1627 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Water Supply Scheme for Pubong Khasmahal Piped Water Supply Scheme In Rangli Rangliot Block Under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000056/2023-2024 | 411/NKWSMD | 05/06/2023 | 447 | RAMESH AGARWAL | 513.34 | 0 | 100
1628 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000050/2023-2024 | 445/NKWSMD | 07/06/2023 | 0 | Resource Division | 3.46 | 0 | 0
1629 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SOIL TESTING FOR WATER STORAGE STRUCTURE (1) BIJANBARI PIPED WATER SUPPLY SCHEME.(2) DANGIA PIPED WATER SUPPLY SCHEME (3) NAMLA BUSTY PIPED WATER SUPPLY SCHEME (4) LAMAGAON PIPED WATER SUPPLY SCHEME (5) PUBONG KHASHMAHAL PIPED WATER SUPPLY SCHEME (6) HUM TUKDAH KHASMAHAL PWSS (7) MANEDARA PIPED WATER SUPPLY SCHEME (8) SORIANG KHASMAHAL & TAKLING BUSTY Piped Water Supply Scheme (9) TODAY TANGTA KHASMAHAL PWSS (10) UPPER FAGU PIPED WATER SUPPLY SCHEME. (11) PATEN GODAK KHASMAHAL PWSS (12) SAMSING MIDDLE & UPPER PIPED WATER SUPPLY SCHEME. (13) LODHAMA PIPED WATER SUPPLY SCHEME. (14) TAKLING KHASMAHAL & CHOTA MANGWA Piped Water Supply Scheme FOR PWSS, DARJEELING, GTA |  | Sub-Assistant Engineer | BILL/00194/2023-2024 | BP-2023-24-155 | 23/08/2023 | 0 | JALPAIGURI GOVERNMENT ENGINEERING COLLEGE | 8.4 | 0 | 0
1630 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR LAMAGAON PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000038/2023-2024 | 221/NKWSMD | 10/05/2023 | 515 | TULSI NIROLA | 679.13 | 0 | 50
1631 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional Estimate for Construction of platform at Lamagaon Piped Water Supply Scheme under Pulbazar Bijanbari Block, PHED, Darjeeling Division, GTA. |  | Sub-Assistant Engineer | ORD/000099/2024-2025 | 976/NKWSMD | 18/06/2024 | 60 | TULSI NIROLA | 32.99 | 0 | 100
1632 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household tap Connection under JJM & JSP Programme for Balance Household at Jhepi & Gurdung in Lamagaon under Darjeeling Division : PHED-GTA. |  | Sub-Assistant Engineer | ORD/000150/2023-2024 | 878/NKWSMD | 03/08/2023 | 350 | NARAYAN SUBBA | 33.7 | 0 | 100
1633 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000023/2023-2024 | 242/NKWSMD | 12/05/2023 | 0 | Resource Division | 3.87 | 0 | 0
1634 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR CHEGRA KHASMAHAL PIPED WATER SUPPLY SCHEME IN RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-VI | ORD/000034/2023-2024 | 184/NKWSMD | 04/05/2023 | 540 | GREEN VALLEY CONSTRUCTION | 323.03 | 0 | 50
1635 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (CONTINUATION) ADDITIONAL ENGAGEMENT OF 01 (ONE) NUMBER COMPUTER OPERATOR (GRADUATE WITH CERTIFICATE IN COMPUTER APPLICATION) FOR THE WORKS RELATED TO JAL JEEVAN MISSION / JAL SWAPNO AT THE OFFICE OF THE SUPERINTENDING ENGINEER, GTA-CIRCLE, PUBLIC HEALTH ENGINEERING DIRECTORATE FROM 01.09.2024 TO 31.10.2024. |  | Junior Engineer-VI | ORD/000103/2024-2025 | 1537/NKWSMD | 30/08/2024 | 61 | QRT SECURITY AND MANPOWER SERVICE | 0.39 | 0 | 80
1636 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Junior Engineer-VI | RTOR000010/2023-2024 | 202/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.46 | 0 | 0
1637 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR RELLING PIPED WATER SUPPLY SCHEME IN DARJEELING PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000061/2023-2024 | 426/NKWSMD | 06/06/2023 | 365 | NIMA SHERPA | 857.26 | 0 | 55
1638 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Laying of additional pipeline for Augmentation scheme for Bijanbari Bazar under Darjeeling Division: PHED-GTA. |  | Sub-Assistant Engineer | ORD/000149/2023-2024 | 877/NKWSMD | 03/08/2023 | 60 | TULSI NIROLA | 40.01 | 0 | 50
1639 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000051/2023-2024 | 446/NKWSMD | 07/06/2023 | 0 | Resource Division | 4.21 | 0 | 0
1640 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW-SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | BILL/00097/2024-2025 | BP-2024-25-87 | 08/07/2024 | 0 | WBSEDCL | 7.65 | 0 | 0
1641 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR SEYOK TEA GARDEN PIPED WATER SUPPLY SCHEME IN JOREBUNGLOW-SUKIAPOKHRI BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000158/2023-2024 | 892/NKWSMD | 07/08/2023 | 545 | M/S BALAJI CONSTRUCTIONS | 1180.95 | 0 | 96
1642 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000098/2023-2024 | 974/NKWSMD | 21/08/2023 | 0 | Resource Division | 6.01 | 0 | 0
1643 | Siliguri W/S Division | Siliguri W/S Division | Construction of 2 Nos. 250 Cu.M capacity Elevated Reservoir 20m staging height allied with laying of distribution pipeline, Rising Mains, construction of Big dia rig bore tube wells by ODEX - 165, Pump Houses (5.4 x 3.60 m & 3.6 x 3.0 m ) , Iron Elemination Plants , Boundary Walls including Functional Household Tap Connections for Augmentation of RANIDANGA AND RANGAPANI Piped Water Supply Scheme (Zone -I and Zone - II) under Naxalbari Block Darjeeling district in connection with Jal Jeevan Mission under Siliguri Sub Division, P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000127/2023-2024 | 1240/SWSD | 16/08/2023 | 535 | THE MAHADEV CONSTRUCTION | 1148.16 | 0 | 42
1644 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | RTOR000091/2022-2023 | 2233/SWSD | 06/01/2023 | 0 | Resource Division | 199.97 | 0 | 0
1645 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1646 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for AUG. OF RANIDANGA RANGAPANI, T/W No. II, under PHANSIDEWA CCC [APPLICATION NO. 4003314400 ; Reference ID : 403144139] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/01812/2023-2024 | BP/23-24/281 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.2 | 0 | 0
1647 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for RANIDANGA RANGAPANI (AUG), T under PHANSIDEWA CCC , [APPLICATION NO. 4003282303, Reference ID : 403118284] | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | BILL/02042/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.85 | 0 | 0
1648 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RANIDANGA RANGAPANI PIPED W/S SCHEME, (Zone-I) TW No. I,II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil),Junior Engineer(Civil) | ORD/000750/2023-2024 | 1578/NMD | 08/09/2023 | 30 | M/S RATAN KUMAR DASGUPTA AND CO. | 34.71 | 0 | 85
1649 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | HATTA WATER SUPPLY SCHEME FROM PAL MAJUA KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT- DARJEELING. |  | Sub-Assistant Engineer | ORD/000106/2021-2022 | 621/NKWSMD | 21/02/2022 | 150 | HARI PRASAD CHETTRI | 303.02 | 0 | 100
1650 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | Additional work for Hatta water supply scheme under Darjeeling Pulbazar Block, P.H.E. Dte. Darjeeling Division, G.T.A. |  | Sub-Assistant Engineer | ORD/000245/2023-2024 | 1530/NKWSMD | 14/12/2023 | 270 | MADAN KUMAR CHHETRI | 9.15 | 0 | 100
1651 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000029/2021-2022 | 828/NKWSMD | 21/03/2022 | 0 | Resource Division | 1.9 | 0 | 0
1652 | Neorakhola W/S & Mtc.Div. | Darjeeling Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000042/2022-2023 | 1266/NKWSMD | 05/09/2022 | 0 | Resource Division | 1.91 | 0 | 0
1653 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR PUBUNG PIPED WATER SUPPLY SCHEME UNDER BLOCK- JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING |  |  | ORD/000044/2025-2026 | 630/NKWSMD | 05/05/2025 | 90 | MAHAKAL ENTERPRISES | 28.61 | 0 | 95
1654 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR PUBONG PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKHIAPOKHRI UNDER DISTRICT DARJEELING. |  |  | ORD/000234/2023-2024 | 1372/NKWSMD | 22/11/2023 | 605 | SHAKTI CONSTRUCTION | 1221.09 | 0 | 100
1655 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING, KURSEONG DIVISION PHED/GTA. |  |  | ORD/000038/2025-2026 | 653/NKWSMD | 05/05/2025 | 180 | VINAYAK CONSTRUCTION | 263.39 | 0 | 0
1656 | Neorakhola W/S & Mtc.Div. |  | WATER SUPPLY SCHEME FOR DOOTERIA TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  |  | ORD/000201/2023-2024 | 1099/NKWSMD | 21/09/2023 | 455 | VINAYAK CONSTRUCTION | 3433.58 | 0 | 50
1657 | Neorakhola W/S & Mtc.Div. |  | Preparation of draft proposal including preparation of maps in KML file , DGPS Map ,SOI Map, uploading of proposal in PARIVESH PORTAL for forest land diversion in 02 (two) number of scheme under JJM (Jal Jeevan Mission). |  |  | ORD/000276/2023-2024 | 1596/NKWSMD | 29/12/2023 | 10 | CIVIL ENGINEERING CONSULTANCY | 0.95 | 0 | 100
1658 | Neorakhola W/S & Mtc.Div. |  | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1172/NKWSMD | 05/10/2023 | 0 | Resource Division | 14.44 | 0 | 0
1659 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
1660 | Siliguri W/S Division | Siliguri Sub-Division | Resources payment for Different Water Supply Scheme | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00121/2022-2023 | BP-2022-23-141 | 13/03/2023 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 131.28 | 0 | 0
1661 | Siliguri W/S Division | Siliguri Sub-Division | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of OCTOBER(18/10/24 to 29/10/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00352/2024-2025 | BP-2024-25-127 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.26 | 0 | 0
1662 | Siliguri W/S Division | Siliguri Sub-Division | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of August (01/08/24 to 13/08/24) 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00353/2024-2025 | BP-2024-25-126 | 25/11/2024 | 0 | SONA PETROL PUMP | 0.34 | 0 | 0
1663 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000005/2021-2022 | 895/SWSD | 24/08/2021 | 0 | Resource Division | 5.77 | 0 | 0
1664 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil) | VCH/000306/2022-2023 |  | 08/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 5.53 | 0 | 0
1665 | Siliguri W/S Division | Siliguri Sub-Division | Providing Functional House hold Tap Connection FHTC in connection with Jal Jeevan Mission JJM and Jal Swapna under command area Habitation Pathoria Ramprasad Sing Rup Sing and Sat of Paschim Madati Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division PHE Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000068/2020-2021 | 1082/SWSD | 18/12/2020 | 30 | M/S G.C. CONSTRUCTION & CO. | 28.59 | 0 | 89
1666 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000010/2021-2022 | 1671/SWSD | 28/12/2021 | 0 | Resource Division | 3.17 | 0 | 0
1667 | Siliguri W/S Division | Siliguri Sub-Division | Procurement of material from Resource Division P.H.E Dte. for the works of different water supply scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil) | VCH/000761/2021-2022 | 512/DW/21-22 | 18/02/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION,PHE DTE. | 100.36 | 0 | 0
1668 | Siliguri W/S Division | Siliguri Sub-Division | Providing functional household tap connection under Jal Swapno Programme for Bansgaon village of Purba Bansgaon Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. (Part-B). | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000051/2020-2021 | 1007/SWSD | 11/12/2020 | 30 | KAMAL GHOSH | 37.26 | 35.86 | 100
1669 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | RIMBICK WATER SUPPLY SCHEME FROM PARTHAM KHOLA SOURCE UNDER JAL SWAPNO PROGRAMME, DISTRICT-DARJEELING |  | Sub-Assistant Engineer | ORD/000001/2022-2023 | 8/NKWSMD | 04/04/2022 | 180 | NIMA SHERPA | 598.72 | 0 | 95
1670 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000043/2022-2023 | 1270/NKWSMD | 05/09/2022 | 0 | Resource Division | 10.06 | 0 | 0
1671 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000103/2022-2023 | 1880/NKWSMD | 15/12/2022 | 0 | Resource Division | 10.08 | 0 | 0
1672 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000163/2022-2023 | 2568/NKWSMD | 17/02/2023 | 0 | Resource Division | 10.08 | 0 | 0
1673 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | RESTORATION OF ROAD SIDE DRAIN UNDER PWD |  | Sub-Assistant Engineer | BILL/00056/2022-2023 | BP-2022-23-234 | 20/12/2022 | 0 | PWD | 3.95 | 0 | 0
1674 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan M ission and Jal Swapno Pro gramme for Pip e Water Supply Scheme for Sukhia Pokhri Bajar and adjoining area (Augmentation, Extension and Reparing) Darjeeling Div ision.P HED.G .T.A" |  | Sub-Assistant Engineer | VCH/000032/2022-2023 | BP-2022-23-32 | 20/04/2022 | 0 | KAMAKHYA ENTERPRISES | 41.26 | 0 | 0
1675 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | "Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme for upper and lower Majuwa, Rangbhang from GairiBass and Gairi Jhora source under Jorebunglo w Su khiapo lhri Block under Darjeeling PHED" |  | Sub-Assistant Engineer | VCH/000111/2022-2023 | BP-2022-23-89 | 14/07/2022 | 0 | MOHAN MUKHIA | 4.34 | 0 | 0
1676 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000001/2020-2021 | 123/EE/DD/PHED | 10/02/2021 | 365 | SHREE VAISHNO ENTERPRISES | 110.23 | 0 | 0
1677 | Darjeeling Division I | Neorakhola W/S Mnt. Division | Work order for supply of GI pipes/ specials of medium quality tata make, pvc pipe, hdpe, pipe for functional household tap connection schemes under jal jeevan mission and jal swapno progeame under phed, kurseong division, GTA , darjeeling |  | Sub-Assistant Engineer | ORD/000003/2020-2021 | 123/EE/DD | 10/02/2021 | 40 | SHREE VAISHNO ENTERPRISES | 40 | 0 | 0
1678 | Siliguri W/S Division | Siliguri Sub-Division | Temporary hiring 01 (one) nos. maxi cab with driver for official screening cum enquiry at Kalimpong in favour of Deputy Superintending Engineer, North Bengal Circle-I PHE Dte.& his team | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/00201/2023-2024 | BP-2023-24-64 | 28/09/2023 | 0 | SUDIP BASAK | 0.07 | 0 | 0
1679 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum Work Order for Additional Laying distribution system for (Z-V) allied with functional house hold tap connection (FHTC) at Augmentation of Bandargachh and Adjoining Mouzas Water Supply Scheme under Phansidewa Block under Siliguri Sub Division, P.H.E. Dte.. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000017/2025-2026 | 1243/SWSD | 24/04/2025 | 45 | SHRI ANNAPURNA DISTRIBUTORS | 48.42 | 0 | 0
1680 | Siliguri W/S Division | Siliguri Sub-Division | Construction of Pump House (4 Nos.) (5.4 X 3.60) size with (1.35 X 2.10 m) size with toilet. Plinth protection etc. installation of IEP and boundary wall at Zone-II, Zone-III, Zone-IV & Zone-V of BANDARGACHH Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000034/2023-2024 | 647/SWSD | 15/06/2023 | 1021 | BUDDHADEV NAG | 91.93 | 0 | 30
1681 | Siliguri W/S Division | Siliguri Sub-Division | Construction of rig bore big dia deep tube well 4 (four) nos. by ODEX-165 method of drilling of BANDARGACHH Piped Water Supply Scheme at Phansidewa block under Siliguri Sub Division, P.H.E. Dte. in the dist. of Darjeeling. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000036/2023-2024 | 648/SWSD | 15/06/2023 | 30 | BUDDHADEV NAG | 30.05 | 0 | 75
1682 | Siliguri W/S Division | Siliguri Sub-Division | Construction of 250 cu.m. capacity R.C.C. Overhead Reservoir, 20 mtrs. Staging height including laying distribution system and allied with providing functional household tap connection (FHTC) at distribution pipeline of BANDARGACHH and adjoining mouza's water supply scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. Sl. No. A. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000055/2022-2023 | 817/SWSD | 19/07/2022 | 1321 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 441.79 | 0 | 25
1683 | Siliguri W/S Division | Siliguri Sub-Division | 05 (Five) Nos. Soil Investigation for the construction of different Capacity Over Head Reservoir as mentioned in ANNEXURE-A under different Water Supply Scheme under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000228/2022-2023 | 2091/SWSD | 22/12/2022 | 20 | G. TECH INDIA | 3.21 | 0 | 100
1684 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000027/2022-2023 | 1457/SWSD | 29/09/2022 | 0 | Resource Division | 2.35 | 0 | 0
1685 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer(Civil) | RTOR000043/2022-2023 | 2023/SWSD | 16/12/2022 | 0 | Resource Division | 52.56 | 0 | 0
1686 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for BANDARGACHA, under PHANSIDEWA CCC [APPLICATION NO. 4003289610 ; Reference ID : 403124950] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01672/2023-2024 | BP/23-24/200 | 27/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0
1687 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for BANDARGACHA, T/W No. III, under PHANSIDEWAI CCC [APPLICATION NO.4003294308 ; Reference ID : 403128805] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01783/2023-2024 | BP/23-24/218 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.3 | 0 | 0
1688 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for BANDARGACHA, T/W No. II, under PHANSIDEWAI CCC [APPLICATION NO.4003298928 ; Reference ID : 403128850] | Assistant Engineer(Civil) | Junior Engineer(Civil) | BILL/01784/2023-2024 | BP/23-24/219 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.75 | 0 | 0
1689 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BANDARGACHA PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II & (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer(Civil) | ORD/000849/2023-2024 | 1752/NMD | 31/10/2023 | 530 | SUBODH KUMAR BANIK | 32.74 | 0 | 100
1690 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional household tap connection underJJM & JSP Programme including extension work for PWS Scheme for Upper Bansbotay, Gram Panchyat -Lodhuma-I, Block Bijanbari -PullBazar. TSM No. 009477 SM Code-SM/08923 |  | Sub-Assistant Engineer | ORD/000076/2022-2023 | 592/NKWSMD | 26/05/2022 | 60 | HARI PRASAD CHETTRI | 16.66 | 0 | 100
1691 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000029/2022-2023 | 1256/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.17 | 0 | 0
1692 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WBSEDCL4003424527 |  | Sub-Assistant Engineer | BILL/00643/2024-2025 | BP-2024-25-447 | 28/11/2024 | 0 | WBSEDCL | 0 | 0 | 0
1693 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | PIPED WATER SUPPLY SCHEME FOR 4th DIVISION: PHUBTSHERING TEA GARDEN UNDER JAL SWAPNO PROGRAMME. |  | Sub-Assistant Engineer | ORD/000087/2022-2023 | 614/NKWSMD | 26/05/2022 | 814 | KAMAKHYA ENTERPRISES | 92.66 | 0 | 100
1694 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000045/2022-2023 | 1257/NKWSMD | 05/09/2022 | 0 | Resource Division | 0.98 | 0 | 0
1695 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Bungkulung G.P - Dhuptin, Block-Mirik. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000164/2022-2023 | 940 /NKWSMD | 12/07/2022 | 716 | KAMAL PRADHAN | 27.91 | 0 | 98
1696 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Glenburn Singritam, Gram Panchayat - Singritam, Block - Rangli Rangliot. |  | Sub-Assistant Engineer | ORD/000087/2023-2024 | 686/NKWSMD | 12/07/2023 | 269 | PUSHKAR GURUNG | 166.03 | 0 | 92
1697 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000078/2023-2024 | 766/NKWSMD | 19/07/2023 | 0 | Resource Division | 8.61 | 0 | 0
1698 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR GAYABARI BISHACRE (LOWER) UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000275/2022-2023 | 2002/NKWSMD | 23/12/2022 | 930 | KAMAL PRADHAN | 65.73 | 0 | 100
1699 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000153/2022-2023 | 2073/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.28 | 0 | 0
1700 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000231/2022-2023 | 2585/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.49 | 0 | 0
1701 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Augmentation of Surface Water Based Piped Water Supply Scheme to accommodate Functional Household Tap Connection (FHTC) in Kurseong Block in Functional Household Tap Connection in Kurseong Block within Darjeeling District under Kurseong Division, PHED-G.T.A. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | ORD/000030/2024-2025 | 1167/NKWSMD | 04/07/2024 | 210 | SHAKTI CONSTRUCTION | 36.03 | 0 | 100
1702 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED PUNKHABARI PWSS TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | ORD/000300/2022-2023 | 2351/NKWSMD | 01/02/2023 | 700 | SHAKTI CONSTRUCTION | 298.42 | 0 | 100
1703 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer6,Sub-Assistant Engineer | RTOR000212/2022-2023 | 2560/NKWSMD | 17/02/2023 | 0 | Resource Division | 1.39 | 0 | 0
1704 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bhujia Banir Chhat Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000155/2022-2023 | 275/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.35 | 0 | 100
1705 | Siliguri W/S Division | Siliguri W/S Division | Laying distribution system along with boring of new tubewell, construction of pump house, boundary wall and providing FHTC under JJM/Jal Swapna for BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME under Naxalbari block, Darjeeling District under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000244/2022-2023 | 2093/SWSD | 22/12/2022 | 75 | THE HINDUSTHAN CO. OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 91.05 | 0 | 0
1706 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000035/2022-2023 | 1465/SWSD | 29/09/2022 | 0 | Resource Division | 4.02 | 0 | 0
1707 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000047/2022-2023 | 2027/SWSD | 16/12/2022 | 0 | Resource Division | 2.18 | 0 | 0
1708 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BHUJIA BANIR CHHAT PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000440/2023-2024 | 1379/NMD | 09/08/2023 | 30 | TAPAN BISWAS | 11.64 | 0 | 70
1709 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED KOPCHI GAON PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer1,Assistant Engineer5 | Junior Engineer1 | ORD/000078/2022-2023 | 601/NKWSMD | 26/05/2022 | 778 | HIMALI CONSTRUCTION COMPANY | 47.25 | 0 | 100
1710 | Neorakhola W/S & Mtc.Div. | Kurseong Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.11.2024 to 31.12.2024. | Assistant Engineer1,Assistant Engineer5 | Junior Engineer1 | ORD/000116/2024-2025 | 2047/NKWSMD | 28/10/2024 | 65 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
1711 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED LOWER CHISOPANI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000083/2022-2023 | 606/NKWSMD | 26/05/2022 | 930 | NARESH RAI | 69.92 | 0 | 100
1712 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000072/2022-2023 | 1316/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.52 | 0 | 0
1713 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000137/2022-2023 | 2057/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.52 | 0 | 0
1714 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR TINDHARIA TEA ESTATE WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000011/2025-2026 | 497/NKWSMD | 09/04/2025 | 180 | SUNIT DEEP RAI | 65.5 | 0 | 0
1715 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED TINDHARIA TEA ESTATE PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | ORD/000081/2022-2023 | 604/NKWSMD | 26/05/2022 | 240 | KARUNAMAYA ENTERPRISES | 108.97 | 0 | 80
1716 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer5 | Junior Engineer1,Sub-Assistant Engineer | RTOR000139/2022-2023 | 1259/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.47 | 0 | 0
1717 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00588/2023-2024 | BP-2023-24-381 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1718 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00589/2023-2024 | BP-2023-24-382 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1719 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00590/2023-2024 | BP-2023-24-383 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1720 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00591/2023-2024 | BP-2023-24-384 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1721 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Quotation of WBSEDCL for electrical service connection | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | BILL/00592/2023-2024 | BP-2023-24-385 | 03/01/2024 | 0 | WBSEDCL | 0.07 | 0 | 0
1722 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Implementation Of ODEX Tube Well based 02(Two) number of pipe water supply Scheme having provision of 2(Two) number of RCC OHR viz 300 Cum & 200Cum and other related works for 6(Six) villages in GTA Area. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000094/2022-2023 | 825/NKWSMD | 30/06/2022 | 900 | M/S KAMAK ENGINEERS AND CO. | 783.01 | 0 | 100
1723 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 360 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 10
1724 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer5,Sub-Assistant Engineer | RTOR000160/2022-2023 | 2371/NKWSMD | 03/02/2023 | 0 | Resource Division | 3.6 | 0 | 0
1725 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR SURFACE WATER BASED TOROYOK KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION ((FHTC) IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000049/2025-2026 | 638/NKWSMD | 05/05/2025 | 90 | SURAJMULL PRABHUDAYAL | 22.11 | 0 | 100
1726 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000001/2023-2024 | 59/NKWSMD | 24/04/2023 | 0 | Resource Division | 0.5 | 0 | 0
1727 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty (Lower kharaya and upper Kharaya Busty habitaion) under Kurseong Sub-Division PHED, GTA. | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | ORD/000118/2022-2023 | 799/NKWSMD | 30/06/2022 | 60 | SAI ENTERPRISE | 16.5 | 0 | 100
1728 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer 4,Assistant Engineer1,Assistant Engineer4 |  | RTOR000051/2022-2023 | 1295/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.44 | 0 | 0
1729 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme for including augmentatin work for PWS scheme for okaity ward no. 03 Gram panchyat PGSD-I, Block-Mirik TSM No. 009304 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000012/2022-2023 | 784/NKWSMD | 30/06/2022 | 60 | ROSHAN BISWAKARMA | 7.58 | 0 | 0
1730 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000068/2022-2023 | 1312/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.28 | 0 | 0
1731 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Ektis Goan: Gram Panchyat-Paila Goan School Dara-I, Block- Mirik TSM No. 009307 SM Code-SM/08942 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000014/2022-2023 | 786/NKWSMD | 30/06/2022 | 60 | PUSHKAR GURUNG | 20.13 | 0 | 0
1732 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000067/2022-2023 | 1311/NKWSMD | 09/09/2022 | 0 | Resource Division | 0.27 | 0 | 0
1733 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Manju Dara Gaon: Gram Panchyat- Soureni-II , Block Mirik TSM No. 009483 SM Code-SM/08950 | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000018/2022-2023 | 780/NKWSMD | 30/06/2022 | 60 | RAMESH PRADHAN AND CO. | 5.33 | 0 | 100
1734 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong Sub-Division P.H.E.D GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000146/2022-2023 | 837/KWSMD | 30/06/2022 | 60 | MS JAGANNATH PRASAD | 23.75 | 0 | 100
1735 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000062/2022-2023 | 1306/NKWSMD | 09/09/2022 | 0 | Resource Division | 1.5 | 0 | 0
1736 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | GRAVITY BASED WATER SUPPLY SCHEME FOR TURZUN TEA GARDEN PWSS IN JOREBUNGLOW SUKIAPOKHARI BLOCK UNDER DARJEELING DISTRICT. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000233/2022-2023 | 1449/NKWSMD | 29/09/2022 | 850 | SRINIWAS AGARWAL | 748.35 | 0 | 99
1737 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000111/2022-2023 | 1888/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.24 | 0 | 0
1738 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000170/2022-2023 | 2607/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.24 | 0 | 0
1739 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Water Supply Scheme for MIM Tea Garden PWSS In Jore Bunglow Sukhiapokhari Under Darjeeling District. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000255/2022-2023 | 1618/NKWSMD | 03/11/2022 | 360 | GARGO TRADERS | 1270.33 | 0 | 95
1740 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000119/2022-2023 | 1896/NKWSMD | 15/12/2022 | 0 | Resource Division | 6.1 | 0 | 0
1741 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000178/2022-2023 | 2612/NKWSMD | 17/02/2023 | 0 | Resource Division | 6.1 | 0 | 0
1742 | Neorakhola W/S & Mtc.Div. |  | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Musey Khola Gaon, Dokan Dhura. School Dhura Gram Panchayat - Maneydanra, Block - Rungli Rungliot. |  |  | ORD/000230/2023-2024 | 1306/NKWSMD | 31/10/2023 | 792 | JANG BAHADUR GURUNG | 46.23 | 0 | 100
1743 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Jholy Busty, Latpunchor, Sittong - III with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000178/2022-2023 | 954/NKWSMD | 12/07/2022 | 60 | BIRU KHAWAS | 38.21 | 0 | 100
1744 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000144/2022-2023 | 2064/NKWSMD | 05/01/2023 | 0 | Resource Division | 0.59 | 0 | 0
1745 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PWS Scheme at Sittong - III Naspatti Gaon with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | ORD/000177/2022-2023 | 953/NKWSMD | 12/07/2022 | 240 | MS. SURYA I PVT. LTD COMPANY | 62.8 | 0 | 82
1746 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer2,Sub-Assistant Engineer | RTOR000145/2022-2023 | 2065/NKWSMD | 05/01/2023 | 0 | Resource Division | 1.23 | 0 | 0
1747 | Siliguri W/S Division | Siliguri Sub-Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Bansgaon Mangachh Piped water supply schemes at the uncovered mouzas under Phansidewa Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000151/2022-2023 | 267/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.23 | 0 | 100
1748 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system allied with functional house hold tap connection (FHTC) including boring of new tube well and Iron elimination plant under JJM at BANSGAON MANGACHH and Adjoining Mouzas Water Supply Scheme within Phansidewa block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000278/2022-2023 | 2656/SWSD | 02/03/2023 | 105 | CUBES 'N' PYRAMIDS | 119.4 | 0 | 10
1749 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000036/2022-2023 | 1466/SWSD | 29/09/2022 | 0 | Resource Division | 1.33 | 0 | 0
1750 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | RTOR000039/2022-2023 | 1951/SWSD | 07/12/2022 | 0 | Resource Division | 2.58 | 0 | 0
1751 | Northern Mechanical | Siliguri Sub-Division | Additional Charges For New service connection At BANSHGAON MANGACHH Water Supply scheme Under NMD, PHE Dte. Application No -4003194676 Ref ID- 403046883 | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00374/2024-2025 | BP/24-25/78 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0 | 0 | 0
1752 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for BANSGAON MANGACHH, T.W. No. I under PHANSIDEWA CCC, [APPLICATION NO. 4003194676, Reference ID : 403046883] | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | BILL/00598/2023-2024 | BP/23-24/75 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.07 | 0 | 0
1753 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BANSHGAON MANGACHH PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer ,Assistant Engineer(Civil) | Junior Engineer,Junior Engineer(Civil) | ORD/000437/2023-2024 | 1376/NMD | 09/08/2023 | 784 | M/S DILIP MITRA | 10.61 | 0 | 90
1754 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR MOONDA KOTHI TEA GARDEN PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKIAPOKRI DISTRICT-DARJEELING UNDER KURSEONG DIVISION PHED GTA. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000033/2025-2026 | 635/NKWSMD | 05/05/2025 | 90 | SRINIWAS AGARWAL | 38.65 | 0 | 0
1755 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MOONDA KOTTE TEA GARDEN PIPED WATER SUPPLY SCHEME IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. | Assistant Engineer 2 | Sub-Assistant Engineer | ORD/000337/2022-2023 | 2734/NKWSMD | 03/03/2023 | 545 | SRINIWAS AGARWAL | 1366.07 | 0 | 70
1756 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 2 | Sub-Assistant Engineer | RTOR000253/2022-2023 | 2746/NKWSMD | 06/03/2023 | 0 | Resource Division | 7.15 | 0 | 0
1757 | Siliguri W/S Division | Siliguri W/S Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF CHUCHUR MUCHUR PIPED WATER SUPPLY SCHEME UNDER KHARIBARI BLOCK, SILIGURI SUB DIVISION, P.H.E. DTE | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000059/2023-2024 | 252/SSD | 05/06/2023 | 10 | SUBHANKAR GHOSH | 2.71 | 0 | 100
1758 | Siliguri W/S Division | Siliguri W/S Division | Construction of Pump House 2 Nos. Rig Bord 2 nos. big dia T/W by Odex-165 method, Boundary walls, Laying distribution system HDPE pipe, rising main, Providing FHTC & Supplying Fabrication on suitable RCC foundation & commissioning with (three) month trial run IEP (20 cu.m./hr) and allied works for Augmentation of Chuchur Muchur PWSS at Kharibari block under Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000272/2022-2023 | 2576/SWSD | 23/02/2023 | 105 | UJJWAL ROY | 142.67 | 0 | 95
1759 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000056/2022-2023 | 2036/SWSD | 16/12/2022 | 0 | Resource Division | 15.11 | 0 | 0
1760 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for CHUCHUR MUCHUR, T.W. No. II under KHARIBARI CCC, [APPLICATION NO. 4003193651, Reference ID : 403046162] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00592/2023-2024 | BP/23-24/78 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.56 | 0 | 0
1761 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for CHUCHUR MUCHUR, T.W. No. I under KHARIBARI CCC, [APPLICATION NO. 4003193712, Reference ID : 403046161] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00593/2023-2024 | BP/23-24/78 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.89 | 0 | 0
1762 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHUCHUR MUCHUR PWSS , TW No I and II in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000069/2023-2024 | 644/NMD | 29/05/2023 | 30 | PRATIK ROY | 23.35 | 0 | 100
1763 | Northern Mechanical | Siliguri W/S Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
1764 | Northern Mechanical | Siliguri W/S Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Darjeeling District (KHARIBARI Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000997/2024-2025 | 16/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 41.15 | 0 | 0
1765 | Northern Mechanical | Siliguri W/S Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KHARIBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001069/2024-2025 | 37/NMD | 06/01/2025 | 30 | S.P. ENTERPRISE | 12.18 | 0 | 0
1766 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.08.2024 to 31.08.2024 |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000097/2024-2025 | 1347/NKWSMD | 31/07/2024 | 31 | YAMA CONSTRUCTIONS LLP | 0.2 | 0 | 100
1767 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | WATER SUPPLY SCHEME FOR PARMAGURI KHASMAHAL PWSS IN BLOCK JOREBUNGLOW SUKIAPOKRI UNDER DISTRICT DARJEELING. |  | Junior Engineer-IV,Sub-Assistant Engineer | ORD/000238/2022-2023 | 1454/NKWSMD | 29/09/2022 | 300 | MADAN SHARMA | 1011.5 | 0 | 99
1768 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000117/2022-2023 | 1894/NKWSMD | 15/12/2022 | 0 | Resource Division | 3.56 | 0 | 0
1769 | Neorakhola W/S & Mtc.Div. | Darjeeling Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-IV,Sub-Assistant Engineer | RTOR000176/2022-2023 | 2608/NKWSMD | 17/02/2023 | 0 | Resource Division | 3.56 | 0 | 0
1770 | Siliguri W/S Division | Siliguri Sub-Division | Construction of household tap connection (FHTC)at different mouzas under different piped water supply scheme (Part A) in connection with Jal Jeevan Mission under Siliguri W/S Division P.H.E DTE. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000157/2023-2024 | 364/SSD | 10/08/2023 | 45 | SEBU CHAKRABORTY | 0.98 | 0 | 100
1771 | Siliguri W/S Division | Siliguri Sub-Division | CONSTRUCTION OF HOUSE HOLD TAP CONNECTION (FHTC) AT DIFFERENT MOUZAS UNDER DIFFERENT PIPED WATER SUPPLY SCHEME (PART -C) IN CONNECTION WITH JAL JEEVAN MISSION UNDER SILIGURI W/S DIVISION P.H.E Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000162/2023-2024 | 364./SSD | 10/08/2023 | 45 | SEBU CHAKRABORTY | 0.98 | 0 | 100
1772 | Siliguri W/S Division | Siliguri Sub-Division | Acceptance cum work order for Laying of rising main, distribution system of pipe line, construction of pump house, boundary wall, sinking of rig bore deep tube well by ODEX-165 method of drilling, development of land and othar works for Augmentation of Damdama nPiped W/S Scheme within Naxalbari Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000194/2023-2024 | 1903/SWSD | 11/10/2023 | 535 | K.K.GHOSH & CO. | 31.94 | 0 | 85
1773 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000009/2023-2024 | 208/SWSD | 25/04/2023 | 0 | Resource Division | 1.59 | 0 | 0
1774 | Northern Mechanical | Siliguri Sub-Division | Quotation for new service connection at Damdama w/s scheme T.W N0_ I in the dist. Darjeeling | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00322/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.81 | 0 | 0
1775 | Northern Mechanical | Siliguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Darjeeling District in West Bengal. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000092/2025-2026 | 1114/NMD | 19/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 96.27 | 0 | 0
1776 | Northern Mechanical | Siliguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAMDAMA PIPED WATER SUPPLY SCHEME, TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000442/2023-2024 | 1381/NMD | 09/08/2023 | 602 | ASHWIRBAD WOOD CRAFT | 10.38 | 0 | 85
1777 | Northern Mechanical | Siliguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAXALBARI, DISTRICT: DARJEELING under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/001067/2024-2025 | 35/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.2 | 0 | 0
1778 | Siliguri W/S Division | Siliguri W/S Division | Construction of 350 cu.m. capacity R.C.C. Elevated Reservoir, 20 mtrs. Staging Height at the head works site including distribution system (HDPE) with Rising Main, Rig bore 2 nos. big dia T/W by Odex-165 method, Providing Functional Household Connection (FHTC), Pump Houses 2 Nos., Blower Room, IEP 70 cu.m./hr., Boundary Walls, Soil Testing and allied works at KHUNIA PUKHARI PWSS, Kharibari block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000119/2023-2024 | 1211/SWSD | 11/08/2023 | 782 | THE TEESTA CONSTRUCTION | 667.04 | 0 | 70
1779 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Khunia Pukhari Piped water supply schemes at the uncovered mouzas under Kharibari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000321/2022-2023 | 264/SSD | 18/05/2022 | 20 | ENVIROTECH SOLUTIONS | 3.87 | 0 | 0
1780 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000012/2023-2024 | 210/SWSD | 25/04/2023 | 0 | Resource Division | 29.44 | 0 | 0
1781 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000045/2023-2024 | 70/SWSD | 10/01/2024 | 0 | Resource Division | 17.92 | 0 | 0
1782 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1783 | Northern Mechanical | Siliguri W/S Division | Additional Charges For New service connection at Khunia Pukhori pwss TW-II under NMD PHE Dte. Application no- 4003320195 Ref id- 860301418 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00385/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0
1784 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KHUNIA PUKHORI, T/W No. I, under KADAMTALA CCC, [APPLICATION NO. 4003320147, Reference ID : 403147072] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01962/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.72 | 0 | 0
1785 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KHUNIA PUKHORI, T/W No. II, under KHARIBARI CCC, [APPLICATION NO. 4003320195, Reference ID : 403147070] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01963/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.82 | 0 | 0
1786 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHUNIA PUKHARI PIPED WATER SUPPLY SCHEME, TW No.- I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000753/2023-2024 | 1581/NMD | 08/09/2023 | 30 | S.G.TECHNICAL SERVICES | 13.8 | 0 | 0
1787 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1788 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR CASTLETON TEA GARDEN PWSS IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | ORD/000276/2022-2023 | 2003/NKWSMD | 23/12/2022 | 180 | SRINIWAS AGARWAL | 280.33 | 0 | 80
1789 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer5,Sub-Assistant Engineer | RTOR000230/2022-2023 | 2603/NKWSMD | 17/02/2023 | 0 | Resource Division | 0.22 | 0 | 0
1790 | Siliguri W/S Division | Siliguri W/S Division | Laying of distribution pipeline and Rising Main allied with construction of 1 no. big dia rig bore tube well by ODEX-165, Pump House (5.4 X 3.60 m), Iron Elimination Plant (10 cu.m./hr.), Boundary Wall including FHTC at DALKAJHAR FOREST Piped Water Supply Scheme under Naxalbari block, Darjeeling dist. in connection with Jal Jeevan Mission under Siliguri Sub Division,, P.H.E. Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000041/2023-2024 | 1041/SWSD | 27/07/2023 | 900 | SUDIP BASAK | 59.15 | 0 | 50
1791 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Dalkajhar Forest Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000154/2022-2023 | 273/SSD | 20/05/2022 | 20 | SUBHANKAR GHOSH | 2.26 | 0 | 100
1792 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000042/2023-2024 | 61/SWSD | 09/01/2024 | 0 | Resource Division | 0.94 | 0 | 0
1793 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000073/2022-2023 | 2052/SWSD | 16/12/2022 | 0 | Resource Division | 0.87 | 0 | 0
1794 | Northern Mechanical | Siliguri W/S Division | Quotation for new service Connection at T.W No- I of Dalkajhar Forest w/s scheme. | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00321/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0
1795 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DALKAJHAR FOREST PIPED WATER SUPPLY SCHEME , TW No I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000435/2023-2024 | 1374/NMD | 09/08/2023 | 604 | SAIKAT SINHA | 10.66 | 0 | 100
1796 | Neorakhola W/S & Mtc.Div. | Kurseong Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1797 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME UNDER BLOCK KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED-GTA. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000035/2025-2026 | 651/NKWSMD | 05/05/2025 | 180 | MAGMA CONSORTIUM | 61.66 | 0 | 0
1798 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR GIDDA PAHAR FOREST PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | ORD/000316/2022-2023 | 2520/NKWSMD | 15/02/2023 | 1275 | VINAYAK CONSTRUCTION | 1768.52 | 0 | 85
1799 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000210/2022-2023 | 2558/NKWSMD | 17/02/2023 | 0 | Resource Division | 5.83 | 0 | 0
1800 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer7,Sub-Assistant Engineer | RTOR000242/2022-2023 | 2715/NKWSMD | 03/03/2023 | 0 | Resource Division | 5.83 | 0 | 0
1801 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Additional work of Piped Water Supply Scheme for Bloomfield Tea Garden Piped Water Supply Scheme in Pulbazar Block under Darjeeling District. |  | Sub-Assistant Engineer | ORD/000002/2024-2025 | 966/NKWSMD | 14/06/2024 | 198 | HARI PRASAD CHETTRI | 59.7 | 0 | 100
1802 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR BLOOMFIELD PIPED WATER SUPPLY SCHEME IN PULBAZAR BLOCK UNDER DARJEELING DISTRICT. |  | Sub-Assistant Engineer | ORD/000097/2023-2024 | 720/NKWSMD | 18/07/2023 | 540 | HARI PRASAD CHETTRI | 369.22 | 0 | 100
1803 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | (Continuation) Engagement of 01 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong from 01.09.2024 to 31.10.2024. |  | Sub-Assistant Engineer | ORD/000104/2024-2025 | 1550/NKWSMD | 30/08/2024 | 61 | YAMA CONSTRUCTIONS LLP | 0.39 | 0 | 100
1804 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division |  | Sub-Assistant Engineer | RTOR000088/2023-2024 | 812/NKWSMD | 24/07/2023 | 0 | Resource Division | 3.42 | 0 | 0
1805 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR RESHOP BAZAR PIPED WATER SUPPLY SCHEME RANGLI RANGLIOT BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer | Junior Engineer6,Sub-Assistant Engineer | ORD/000024/2023-2024 | 123/NKWSMD | 28/04/2023 | 605 | VAISHNO CONSTRUCTION | 416.96 | 0 | 100
1806 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer6,Sub-Assistant Engineer | RTOR000016/2023-2024 | 214/NKWSMD | 10/05/2023 | 0 | Resource Division | 1.11 | 0 | 0
1807 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR OKAITY TEA GARDEN PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00216/2024-2025 | BP-2024-25-172 | 01/08/2024 | 0 | WBSEDCL | 50.95 | 0 | 0
1808 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000029/2023-2024 | 248/NKWSMD | 12/05/2023 | 0 | Resource Division | 7.85 | 0 | 0
1809 | Siliguri W/S Division | Siliguri W/S Division | Construction of 250 cu.m. Capacity R.C.C. Elevated Reservosir, 20 mtrs. Staging height at head works site, laying Rising Main, Laying distribution pipe line with Functional House Hold Tap Connection (FHTC), construction of three numbers Pump House (5.40 m X 3.60 m), 2 (two) nos. Iron Elimination Plant (IEP) with Blower Room Sinking of 3 (three) nos. Tube Well (ODEX-165 method) and Boundary Wall for KILARAM PWSS (Zone-I & II), Block Naxalbari, Dist. Darjeeling under Siliguri W/S Division, P.H.E. Dte | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000112/2023-2024 | 1159/SWSD | 09/08/2023 | 240 | RAMESH KUMAR AGARWAL & CO | 645.57 | 0 | 55
1810 | Siliguri W/S Division | Siliguri W/S Division | Preparation of Details Project Report (DPR) incl. route survey in connection with proposed Kilaram Piped water supply schemes at the uncovered mouzas under Naxalbari Block of Siliguri Sub Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000318/2022-2023 | 251/SSD | 12/05/2022 | 20 | ENVIROTECH SOLUTIONS | 3.36 | 0 | 0
1811 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000005/2023-2024 | 205/SWSD | 25/04/2023 | 0 | Resource Division | 67.51 | 0 | 0
1812 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000031/2023-2024 | 2290/SWSD | 11/12/2023 | 0 | Resource Division | 2.9 | 0 | 0
1813 | Siliguri W/S Division | Siliguri W/S Division | Material Requisition To Resource Division | Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000049/2023-2024 | 74/SWSD | 10/01/2024 | 0 | Resource Division | 13.27 | 0 | 0
1814 | Central Drilling | Siliguri W/S Division | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 11
1815 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KILARAM, T/W No. II, under NAXALBARI CCC, [APPLICATION NO. 4003313623, Reference ID : 403145716] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01970/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.53 | 0 | 0
1816 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KILARAM, T/W No. III, under NAXALBARI CCC, [APPLICATION NO. 4003313552, Reference ID : 403145729] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01971/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.2 | 0 | 0
1817 | Northern Mechanical | Siliguri W/S Division | New Service Connection Charge for KILARAM, T/W No. I, under NAXALBARI CCC, [APPLICATION NO. 4003313640, Reference ID : 403145711] | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/01972/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.56 | 0 | 0
1818 | Northern Mechanical | Siliguri W/S Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KILARAM PIPED WATER SUPPLY SCHEME, (Zone-I) TW No. I, II and (Zone-II) TW-I in the district of Darjeeling under Northern Mechanical Division, PHE Dte. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000801/2023-2024 | 1658/NMD | 29/09/2023 | 460 | B.B. CONCERNED | 27.15 | 0 | 100
1819 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOY DHURA TEA GARDEN IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000032/2025-2026 | 633/NKWSMD | 05/05/2025 | 180 | MS CHAMLING CONSTRUCTION | 66.89 | 0 | 0
1820 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SEPOYDHURA (ST MARYS -I) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN KURSEONG BLOCK. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000332/2022-2023 | 2706/NKWSMD | 02/03/2023 | 760 | SHAKTI CONSTRUCTION | 442.13 | 0 | 90
1821 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000250/2022-2023 | 2727/NKWSMD | 03/03/2023 | 0 | Resource Division | 2.33 | 0 | 0
1822 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000260/2022-2023 | 2778/NKWSMD | 10/03/2023 | 0 | Resource Division | 2.33 | 0 | 0
1823 | Neorakhola W/S & Mtc.Div. | Kurseong Division | MONGPOO CINKONA PLANTATION PIPED WATER SUPPLY SCHEME SPRING WATER SUPPLY SCHEME. | Assistant Engineer1 | Junior Engineer4 | ORD/000010/2023-2024 | 98/NKWSMD | 28/04/2023 | 830 | VAISHNO CONSTRUCTION | 230.27 | 0 | 100
1824 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED EDENVALE TEA GARDEN PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. | Assistant Engineer 4 | Sub-Assistant Engineer | ORD/000160/2023-2024 | 894/NKWSMD | 07/08/2023 | 180 | YAMA CONSTRUCTIONS LLP | 139.48 | 0 | 50
1825 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer 4 | Sub-Assistant Engineer | RTOR000124/2023-2024 | 1298/NKWSMD | 30/10/2023 | 0 | Resource Division | 0.67 | 0 | 0
1826 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PIPED WATER SUPPLY SCHEME AT LOWER SIRUBARI WITH FUNCTIONAL HOUSEHOLD TAP CONNECTION UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME UNDER KURSEONG DIVISION PHED-GTA, DARJEELING. | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | ORD/000269/2022-2023 | 1748/NKWSMD | 25/11/2022 | 60 | BITIS PRADHAN AND BROTHERS | 24.69 | 0 | 100
1827 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer1 | Junior Engineer1,Sub-Assistant Engineer | RTOR000265/2022-2023 | 2813/NKWSMD | 14/03/2023 | 0 | Resource Division | 0.46 | 0 | 0
1828 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MALUTAR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000048/2025-2026 | 637/NKWSMD | 05/05/2025 | 60 | SURAJMULL PRABHUDAYAL | 13.02 | 0 | 100
1829 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | WATER SUPPLY SCHEME FOR MALOTAR TEA GARDEN PIPED WATER SUPPLY SCHEME IN KURSEONG BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000154/2023-2024 | 882/NKWSMD | 03/08/2023 | 365 | SHAKTI CONSTRUCTION | 1026.53 | 0 | 100
1830 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | forest clearance of JJM schemes under kurseong Division PHED GTA. | Assistant Engineer5 | Sub-Assistant Engineer | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1831 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR SEPOYDHURA TEA GARDEN, CHAMPASARI FOREST, KHARIA BUSTY, CHAITA PANI TEA GARDEN & BAMAN DHURA FOREST UNDER KURSEONG DIVISION, PHED-GTA | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000046/2025-2026 | 634/NKWSMD | 05/05/2025 | 180 | VAJRA ENTERPRISES | 59.3 | 0 | 95
1832 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | SURFACE WATER BASED SEPOYDHURA (D.R.) TEA GARDEN, KHARIA BUSTY CHAITAPANI TEA GARDEN & BAMAN DHURA FOREST PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSOENG BLOCK. | Assistant Engineer5 | Sub-Assistant Engineer | ORD/000167/2023-2024 | 920/NKWSMD | 11/08/2023 | 645 | SHAKTI CONSTRUCTION | 1345.85 | 0 | 50
1833 | Neorakhola W/S & Mtc.Div. | Neorakhola W/S Mnt. Division | Material Requisition To Resource Division | Assistant Engineer5 | Sub-Assistant Engineer | RTOR000108/2023-2024 | 969/NKWSMD | 21/08/2023 | 0 | Resource Division | 4.73 | 0 | 0
1834 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00821/2023-2024 | BP-2023-24-530 | 26/02/2024 | 0 | WBSEDCL | 6.32 | 0 | 0
1835 | Neorakhola W/S & Mtc.Div. | Kurseong Division | ADDITIONAL WORK FOR WATER SUPPLY SCHEME FOR MANJUA FOREST SOURINI-II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000027/2025-2026 | 595/NKWSMD | 29/04/2025 | 60 | ALLIED INSTRUMENTS | 13.7 | 0 | 0
1836 | Neorakhola W/S & Mtc.Div. | Kurseong Division | WATER SUPPLY SCHEME FOR MANJUA FOREST SOURENI -II PIPED WATER SUPPLY SCHEME IN MIRIK BLOCK UNDER DARJEELING DISTRICT. | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000035/2023-2024 | 109/NKWSMD | 28/04/2023 | 635 | MAA MANASA VYAPAAR | 1093.84 | 0 | 50
1837 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000028/2023-2024 | 245/NKWSMD | 12/05/2023 | 0 | Resource Division | 5.91 | 0 | 0
1838 | Neorakhola W/S & Mtc.Div. | Kurseong Division | PAYMENT FOR WBSEDCL | Assistant Engineer 2 | Junior Engineer3,Sub-Assistant Engineer | BILL/00956/2023-2024 | BP-2023-24-658 | 23/03/2024 | 0 | WBSEDCL | 12.27 | 0 | 0
1839 | Neorakhola W/S & Mtc.Div. | Kurseong Division | SURFACE WATER BASED MIRIK KHASMAHAL (P) PIPED WATER SUPPLY SCHEME TO ACCOMODATE FHTC IN MIRIK BLOCK. | Assistant Engineer 2 | Junior Engineer3,Sub-Assistant Engineer | ORD/000165/2023-2024 | 918/NKWSMD | 11/08/2023 | 365 | SHAKTI CONSTRUCTION | 1224.81 | 0 | 90
1840 | Neorakhola W/S & Mtc.Div. | Kurseong Division | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer3,Sub-Assistant Engineer | RTOR000091/2023-2024 | 973/NKWSMD | 21/08/2023 | 0 | Resource Division | 8.04 | 0 | 0
1841 | Neorakhola W/S & Mtc.Div. |  | Augmentation of 4 Nos Piped Water Supply Schemes (Simulbari Tea Garden, Pairikumari, Garidhura (M.Bari) Tea Garden & Nipania) Within Darjeeling District under Kurseong Division, PHE-GTA. |  |  | ORD/000121/2024-2025 | 114/NKWSMD | 21/01/2025 | 240 | M/S KAMAK ENGINEERS AND CO. | 585.79 | 0 | 30
1842 | Neorakhola W/S & Mtc.Div. |  | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 0 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0
1843 | Neorakhola W/S & Mtc.Div. |  | ADDITIONAL WORK FOR GROUND WATER RESERVOIR HAVING CAPACITY OF 20 ML AT DURPIN LAKE TO ACCOMMODATE 5 MOUZAS IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA. |  |  | ORD/000058/2025-2026 | 826/NKWSMD | 09/06/2025 | 180 | INTERIOR'S NEST | 318.4 | 0 | 0
1844 | Neorakhola W/S & Mtc.Div. |  | Ground Water Reservoir having capacity of 20 ML at Durpin Lake to accommodate 5 Mouzas in Kurseong Block within Darjeeling District under Kurseong Division, P.H.E.D- GTA. |  |  | ORD/000267/2023-2024 | 100/NKWSMD | 15/01/2024 | 765 | INTERIOR'S NEST | 2672.64 | 0 | 35
Total | [10 empty] | 1010488.99 | 243.12