## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | Assistant Engineer,HQ | Junior Engineer | ORD/000083/2020-2021 | 1268/JD | 18/11/2020 | 90 | NARAYAN CHAKRABORTY | 36.96 | 13.76 | 1
2 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Sajnapara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000190/2020-2021 | 1543/JD | 31/12/2020 | 75 | RAGHU DAS | 39.54 | 71.4 | 1
3 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000311/2020-2021 | 289/JD | 23/02/2021 | 30 | HARIPADA BANERJEE | 24.4 | 47.06 | 1
4 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Pradhanpara Mouza under SAJNAPARA piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000327/2020-2021 | 221/JD | 12/02/2021 | 30 | RAGHU DAS | 23.09 | 0 | 1
5 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). | Assistant Engineer,HQ | Junior Engineer | ORD/000477/2020-2021 | 61/RWS | 09/02/2021 | 15 | NEW KUNDU ENTERPRISE | 4.09 | 8.18 | 1
6 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000215/2020-2021 | 1549/JD | 31/12/2020 | 60 | CALCON CONSTRUCTIONS | 40.32 | 0 | 0
7 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000216/2020-2021 | 1550/JD | 31/12/2020 | 30 | PARAMJYOTI ENTERPRISE | 12.27 | 24.51 | 1
8 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Jiti T.G. piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000250/2020-2021 | 563/JSSD | 01/02/2021 | 15 | NARAYAN CHANDRA ADHIKARY | 4.44 | 8.85 | 0
9 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 5th Tubewell site of Mallicksova PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000024/2023-2024 | 124/JD | 28/04/2023 | 14 | PINTU DAS | 5.01 | 1.76 | 100
10 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250 mm x 150mm dia 3rd tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000031/2022-2023 | 977/JD | 20/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 7.45 | 1
11 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250 mm x 150mm dia 4th tube well by Reverse Rotary method of drilling for Rejuvenation of Mallicksova PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000032/2022-2023 | 985/JD | 21/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 7.95 | 7.14 | 1
12 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000075/2022-2023 | 1314/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 11.69 | 1
13 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of 3rd Tube Well Site, 2nd Tube Well Site and Head Work Site Pump House at Mallicksova Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000496/2024-2025 | 2374/JD | 18/12/2024 | 20 | SUKUMAR KUNDU | 2.88 | 0 | 0
14 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000510/2021-2022 | 93/JD | 10/01/2022 | 60 | TECHNO CRACY | 4.65 | 4.69 | 100
15 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Mallicksova P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000511/2021-2022 | 94/JD | 10/01/2022 | 60 | DEBABRATA SARKAR | 4.64 | 4.73 | 100
16 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna of Khathiar line, Girza line and Chamru line within the command area of Jogesh Ch. T.G. PWSS at Mal Block under Jalpaiguri Division, P.H.E. Dte. (Part-C) | Assistant Engineer,HQ | Junior Engineer | ORD/000573/2021-2022 | 730/JD | 17/03/2022 | 21 | SANDIP BANIK | 17.59 | 16.99 | 1
17 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MALLIK SOBHA, TW No. V, DHUPGURI CCC, [APPLICATION NO. 4003123385, Reference ID : 402994381] | Assistant Engineer,HQ | Junior Engineer | BILL/00059/2023-2024 | BP/23-24/16 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
18 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for MALLIK SOBHA, TW No. V, DHUPGURI CCC, [APPLICATION NO. 100000076675, Reference ID : 860268405] | Assistant Engineer,HQ | Junior Engineer | BILL/00060/2023-2024 | BP/23-24/16 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.21 | 0 | 0
19 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for MALLICK SOVA, T/W IV, under DHUPGURI CCC [APPLICATION NO. 100000076670 , Reference ID : 860268400] | Assistant Engineer,HQ | Junior Engineer | BILL/00249/2023-2024 | BP/23-24/27 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.41 | 0 | 0
20 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MALLICK SOVA, T/W IV, under DHUPGURI CCC, [APPLICATION NO. 4003123372, Reference ID : 402997124] | Assistant Engineer,HQ | Junior Engineer | BILL/00505/2023-2024 | BP/23-24/55 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
21 | Northern Mechanical | Jalpaiguri Division | Fuel charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :004/2024-2025 ,Dt - 31/07/2024 | Assistant Engineer,HQ | Junior Engineer | BILL/01050/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.34 | 0 | 0
22 | Northern Mechanical | Jalpaiguri Division | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0090/2023-2024 ,Dt - 31/01/2024 | Assistant Engineer,HQ | Junior Engineer | BILL/01051/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.28 | 0 | 0
23 | Northern Mechanical | Jalpaiguri Division | Fuel,lubricants charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0001/2023-2024 ,Dt - 30/04/24 | Assistant Engineer,HQ | Junior Engineer | BILL/01054/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.29 | 0 | 0
24 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for MALLICKSOBHA (REJU) PWSS, at TW no. V, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000575/2022-2023 | 1127/NMD | 12/09/2022 | 30 | BLUE PINE | 8.26 | 8.23 | 100
25 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for MALLICKSOBHA (REJU) PWSS, at TW no. IV, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000577/2022-2023 | 1126/NMD | 12/09/2022 | 30 | DAS CONSTRUCTION | 8.25 | 8.22 | 91
26 | Northern Mechanical | Jalpaiguri Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under MALLICKSOBHA (Reju) WS Scheme at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000779/2022-2023 | 100/NMD | 03/02/2023 | 21 | M/S ROYAL ENTERPRISE | 2.91 | 2.91 | 100
27 | Northern Mechanical | Jalpaiguri Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under MALLICKSOBHA (Reju) WS Scheme at TW No. V in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000780/2022-2023 | 101/NMD | 03/02/2023 | 21 | BLUE PINE | 2.91 | 2.91 | 100
28 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
29 | Jalpaiguri Division | Jalpaiguri Division | Laying of Paver Block with development of approach pathway as a restoration work due to delivery main and Rising main laying for Augmentation of Purba Daukimari Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000102/2023-2024 | 445/JD. | 08/06/2023 | 21 | TARAKESWAR PRASAD | 4.59 | 0 | 0
30 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Purba Daukimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000289/2021-2022 | 1258/JD | 10/08/2021 | 15 | RABINDRANATH DUTTA | 4.81 | 4.78 | 0
31 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with FHTC work for Augmentation of Purba Daukimari Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000373/2021-2022 | 333/JD | 02/02/2022 | 120 | SUKES BASU MAJUMDAR | 328.7 | 227.41 | 1
32 | Jalpaiguri Division | Jalpaiguri Division | Construction of 250 CuM. Capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) for the Head Works Site and other related works including pump connection of different pump for Augmentation of Purba Daukimari Piped Water Supply Scheme of Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2021-2022 | 196/JD | 21/01/2022 | 180 | PRADIP SAHA | 75.21 | 72.89 | 1
33 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including culvert crossing and road restoration for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) | Assistant Engineer,HQ | Junior Engineer | ORD/000389/2023-2024 | 1553/JD | 01/11/2023 | 21 | B.M CONSTRUCTION | 9.41 | 9.65 | 100
34 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including road boaring, Supplying and fitting fixing specials, Jeffy Coupling and other miscelleneous works for Augmentation of Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-C) | Assistant Engineer,HQ | Junior Engineer | ORD/000391/2023-2024 | 1555/JD | 01/11/2023 | 30 | B.M CONSTRUCTION | 14.3 | 14.33 | 100
35 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000520/2021-2022 | 156/RWS | 24/02/2022 | 15 | ANUP SARKAR | 4.73 | 4.73 | 0
36 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works related to FHTC in connection with Jalsapna at different locations of Chanadipa Mouza of Dakshin Salbari W/S/S Under Jalpaiguri Division ,P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000521/2021-2022 | 157/RWS | 24/02/2022 | 15 | ANUP SARKAR | 4.73 | 4.72 | 0
37 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna at Purba Daukimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III | Assistant Engineer,HQ | Junior Engineer | ORD/000532/2021-2022 | 130/JD | 14/01/2022 | 21 | RABINDRANATH DUTTA | 4.84 | 4.83 | 1
38 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 1 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Daukimari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000561/2021-2022 | 441/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 7.92 | 6.67 | 100
39 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000690/2021-2022 | 1064/JSSD | 24/01/2022 | 20 | G. TECH INDIA | 1.83 | 0.74 | 0
40 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000019/2021-2022 | 556/JD | 01/03/2022 | 0 | Resource Division | 17.98 | 0 | 0
41 | Jalpaiguri Division | Jalpaiguri Division | b-wall for kharija berubari pwsss | Assistant Engineer,HQ | Junior Engineer | VCH/000023/2022-2023 | BP-2021-23-4 | 21/04/2022 | 0 | GANAPATI ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.41 | 0 | 0
42 | Jalpaiguri Division | Jalpaiguri Division | IEP FOR MAYNAGURI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001249/2021-2022 | BP-2021-22-388 | 17/03/2022 | 0 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0
43 | Jalpaiguri Division | Jalpaiguri Division | REJUNATION 2ND TUBE WELL SITE CHALSA | Assistant Engineer,HQ | Junior Engineer | VCH/001291/2021-2022 | BP-2021-22-422 | 25/03/2022 | 0 | SUKUMAR KUNDU | 0.94 | 0 | 0
44 | Jalpaiguri Division | Jalpaiguri Division | IEP MAYNAGURI ZONE II | Assistant Engineer,HQ | Junior Engineer | VCH/001319/2021-2022 | BP-2021-22-388 | 17/03/2022 | 0 | SUKES BASU MAJUMDAR | 26.7 | 0 | 0
45 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AUGMENTATION OF DAUKIMARI PWSS, TW no I, under DHUPGURI CCC APPLICATION NO. 4003391338 Reference ID : 403203884 | Assistant Engineer,HQ | Junior Engineer | BILL/00510/2024-2025 | BP/24-25/111 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.32 | 0 | 0
46 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAUKIMARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000234/2023-2024 | 1248/NMD | 31/07/2023 | 30 | MAA ENTERPRISES | 10.87 | 0 | 0
47 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | FUEL SUPPLY |  | Junior Engineer | BILL/00128/2022-2023 | BP-2022-23-403 | 17/01/2023 | 0 | FILL & SMILE | 1.71 | 0 | 0
48 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ETDS |  | Junior Engineer | BILL/00129/2022-2023 | BP-2022-23-405 | 17/01/2023 | 0 | SUSHIL KUMAR SINGHA | 0.08 | 0 | 0
49 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ETDS |  | Junior Engineer | BILL/00130/2022-2023 | BP-2022-23-406 | 17/01/2023 | 0 | SUSHIL KUMAR SINGHA | 0.13 | 0 | 0
50 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF SHARP TONNER CARTRIDGE |  | Junior Engineer | BILL/00131/2022-2023 | BP-2022-23-404 | 17/01/2023 | 0 | QUATTRON | 0.17 | 0 | 0
51 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | hire chages |  | Junior Engineer | BILL/00247/2022-2023 | BP-2022-23-438 | 03/02/2023 | 0 | LOKNATH CONSTRUCTION | 0.52 | 0 | 0
52 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 250mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000010/2022-2023 | 871/JD | 04/04/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 8 | 7.72 | 100
53 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Dakshin Chak Moulani PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000022/2024-2025 | 671/JD | 16/07/2024 | 625 | M/S S. G. ENTERPRISE | 19.97 | 3.26 | 80
54 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Dakshin Chakmoulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000107/2022-2023 | 83/JSSD | 22/07/2022 | 20 | CHANDAN GHOSH | 4.56 | 4.41 | 100
55 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Rig approach for Installation of tubewell 3rd Tube Well site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000108/2022-2023 | 85/JSSD | 22/07/2022 | 7 | ALICK DUTTA | 0.81 | 0.81 | 100
56 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work i.c.w Laying Rising Main from 1st, 2nd & 3rd Tubewell site OHR Aug. of Dakshin Chak Moulani PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000117/2024-2025 | 230/JSSD | 10/09/2024 | 10 | SADHAN KARMAKAR | 0.64 | 0 | 0
57 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jal Swapna / JJM for Augmentation of Dakhin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000348/2021-2022 | 211/JD | 24/01/2022 | 60 | UNIBRO INFRASERV PRIVATE LIMITED | 426.83 | 307.35 | 80
58 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000349/2023-2024 | 1437/JD | 05/10/2023 | 667 | M/S. D.K. DEY & CO.. | 91.09 | 29.66 | 35
59 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work ¿Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub- Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)¿ from 01.10.2022 to 31.12.2022. |  | Junior Engineer | ORD/000358/2022-2023 | 248/JSSD | 28/09/2022 | 93 | TANMOY CHOUDHURY | 0.46 | 0.33 | 0
60 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 |  | Junior Engineer | ORD/000368/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.44 | 0.4 | 0
61 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Dakshin Chalk Moulani P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000691/2021-2022 | 1066/JSSD | 24/01/2022 | 20 | ASIS ENTERPRISE | 1.83 | 1.81 | 0
62 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000811/2023-2024 | 566/JSSD | 05/03/2024 | 30 | GOURAV CONSTRUCTION CO. | 4.03 | 2.32 | 90
63 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Dakshin Chak Moulani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000831/2021-2022 | 1109/W/JSSD | 27/01/2022 | 45 | M/S M G CONSTRUCTION | 4.76 | 4.71 | 100
64 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PREPARATION OF DPR DAKHIN CHAKMOULANI |  | Junior Engineer | VCH/001282/2021-2022 | BP-2021-22-490 | 09/04/2022 | 0 | SUBHANKAR GHOSH | 1.56 | 0 | 0
65 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for AUGMENTATION OF DAKSHIN CHAK MOULANI, T/W No. III, under KRANTI CCC, [APPLICATION NO. 4003266328, Reference ID : 403105517] |  | Junior Engineer | BILL/01275/2023-2024 | 23-24/153&162 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
66 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for AUGMENTATION OF DAKSHIN CHAK MOULANI, T/W No. III, under KRANTI CCC, [APPLICATION NO. 100000093179, Reference ID : 860284829] |  | Junior Engineer | BILL/01276/2023-2024 | 23-24/153&162 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.87 | 0 | 0
67 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAKSHIN CHAK MOULANI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000444/2023-2024 | 1383/NMD | 09/08/2023 | 30 | M/S ROYAL ENTERPRISE | 10.32 | 10.31 | 60
68 | Jalpaiguri Division | Jalpaiguri Division | supply for fuel | Assistant Engineer,HQ | Junior Engineer | BILL/00264/2023-2024 | BP-2023-24-250 | 21/07/2023 | 0 | FILL & SMILE | 0.58 | 0 | 0
69 | Jalpaiguri Division | Jalpaiguri Division | TEMPORARY HIRING OF ONE MAXI CAB WITH DRIVER | Assistant Engineer,HQ | Junior Engineer | BILL/00265/2023-2024 | BP-2023-24-251 | 21/07/2023 | 0 | RUPA PRASAD | 0.34 | 0 | 0
70 | Jalpaiguri Division | Jalpaiguri Division |  | Assistant Engineer,HQ | Junior Engineer | BILL/00266/2023-2024 | BP-2023-24-252 | 21/07/2023 | 0 | APIKUL ALI | 0.35 | 0 | 0
71 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Kathapara Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000016/2022-2023 | 972/JD | 20/04/2022 | 1199 | SCEC BOENTER KDAS JOINT VENTURE | 430.18 | 104.72 | 60
72 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall with ancillary works for the Pump House No. 1 Premises of the Bhatia para Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000128/2020-2021 | 1196/JD | 06/11/2020 | 30 | RABINDRANATH DUTTA | 4.99 | 5.09 | 100
73 | Jalpaiguri Division | Jalpaiguri Division | Restoration of damaged DI Pipeline at Kathapara Piped W/S at Dhupguri Development Block Under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000128/2022-2023 | 1320/JD | 16/06/2022 | 15 | SADHAN KARMAKAR | 0.96 | 0.96 | 1
74 | Jalpaiguri Division | Jalpaiguri Division | Shifting and Laying of Parallel pipeline in place of partially damaged pipeline for widening and strengthening BRO Road from Chamurchi to Banerhat more including minor retrofitting works to the Division line under Haritalguri T.G. P.W.S.S. command area under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000148/2022-2023 | 1553/JD | 05/08/2022 | 21 | NARAYAN CHANDRA SAHA | 25.32 | 25.28 | 0
75 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C. Over Head Reservoir for the Head Works Site of Augmentation of Kathapara P.W.S.S. under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000190/2022-2023 | 1693/JD | 06/09/2022 | 21 | MOYTEC | 0.97 | 0.71 | 100
76 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000229/2022-2023 | 1746/JD | 08/09/2022 | 1058 | SCEC BOENTER KDAS JOINT VENTURE | 76.15 | 0 | 15
77 | Jalpaiguri Division | Jalpaiguri Division | Land Developmrent at Head Works site under Jabramali Piped Water Supply Scheme whithin Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000280/2022-2023 | 645/RWS | 21/10/2022 | 15 | M/S RATAN KUMAR DAS GUPTA AND CO | 2.59 | 2.56 | 0
78 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Kathapara at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000324/2022-2023 | 2411/JD | 19/12/2022 | 30 | SAUMENDU DUTTA | 8.61 | 8.02 | 0
79 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site for Kathapara PWSS i.c.w. Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000374/2022-2023 | 299/JD | 10/02/2023 | 45 | ABHIK BHOWMIK | 4.64 | 4.73 | 100
80 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of 2nd Tube Well Site and Head Work Site Pump House at Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000378/2024-2025 | 2027/JD | 19/11/2024 | 20 | ABHIK BHOWMIK | 2.41 | 0 | 0
81 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd TW Site for Kathapara PWSS i.c.w. JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000488/2024-2025 | 2427/JD | 24/12/2024 | 261 | ABHIK BHOWMIK | 11.54 | 0 | 80
82 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main of 3rd Tube Well site of Kathapara PWSS, in connection with Rejuvenation of Kathapara Piped Water Supply Scheme under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000529/2023-2024 | 1850/JD | 15/12/2023 | 383 | ABHIK BHOWMIK | 4.73 | 0 | 100
83 | Jalpaiguri Division | Jalpaiguri Division | Construction of 400 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing at Head Works site for Augmentation of Kathapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000585/2021-2022 | 734/JD | 17/03/2022 | 180 | SCEC BOENTER KDAS JOINT VENTURE | 82.2 | 34.61 | 75
84 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000007/2024-2025 | 58/JD | 09/04/2024 | 0 | Resource Division | 18.24 | 0 | 0
85 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for KATHAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147726, Reference ID : 403014087] | Assistant Engineer,HQ | Junior Engineer | BILL/00057/2023-2024 | BP/23-24/17 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
86 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for KATHAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077916, Reference ID : 860269056] | Assistant Engineer,HQ | Junior Engineer | BILL/00058/2023-2024 | BP/23-24/17 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.38 | 0 | 0
87 | Northern Mechanical | Jalpaiguri Division | Fuel ,lubrication charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0002/2024-2025 ,Dt - 31/05/24 | Assistant Engineer,HQ | Junior Engineer | BILL/01055/2024-2025 |  | 16/08/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.51 | 0 | 0
88 | Northern Mechanical | Jalpaiguri Division | Fuel charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0003/2024-2025 ,Dt - 30/06/24 | Assistant Engineer,HQ | Junior Engineer | BILL/01056/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.35 | 0 | 0
89 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KATHAPARA PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000877/2022-2023 | 341/NMD | 29/03/2023 | 491 | TAPAN BISWAS | 10.9 | 10.88 | 100
90 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
91 | Jalpaiguri Division | Jalpaiguri Division | Shifting and repairing of damaged/chokage pipe line due to development, widening of roads and agricultural land related to L.D.S. within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000209/2022-2023 | 1799/JD | 14/09/2022 | 21 | ARATI CONSTRUCTION | 4.85 | 4.87 | 0
92 | Jalpaiguri Division | Jalpaiguri Division | Permanent restoration of G.I. lines across the small stream in two places along with others ancillary works related to distribution system, strengthening of valve chambers due to strengthening of village/PWD roads and culvert works in various places within the command area of rejuvenation of Purba Magurmari P.W.S.S. under Jalpaiguri Division,P.H.E. Dte.Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000210/2022-2023 | 1800/JD | 14/09/2022 | 21 | ARATI CONSTRUCTION | 4.5 | 4.44 | 0
93 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 30
94 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000503/2021-2022 | 104/JD | 11/01/2022 | 60 | LOKNATH CONSTRUCTION | 4.65 | 4.78 | 1
95 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 5th Tube well site for Purba Magurmari P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000506/2021-2022 | 105/JD | 11/01/2022 | 60 | PRITAM DUTTA | 4.65 | 4.76 | 1
96 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 2 No. 250mm x 150mm x 133 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000562/2021-2022 | 442/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 15.63 | 15.19 | 1
97 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PURBA MAGURMARI W/S Scheme, T/W No. V, under DHUPGURI CCC, [APPLICATION NO. 4003018653, Reference ID : 402927251] | Assistant Engineer,HQ | Junior Engineer | BILL/00038/2022-2023 | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
98 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for PURBA MAGURMARI W/S Scheme, T/W No. V, under DHUPGURI CCC, [APPLICATION NO. 100000066800, Reference ID : 860257020] | Assistant Engineer,HQ | Junior Engineer | BILL/00039/2022-2023 | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.04 | 0 | 0
99 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PURBA MAGURMARI W/S Scheme, T/W No. IV, under DHUPGURI CCC, [APPLICATION NO. 4003018663, Reference ID : 402928488] | Assistant Engineer,HQ | Junior Engineer | BILL/00040/2022-2023 | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
100 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for PURBA MAGURMARI W/S Scheme, T/W No. IV, under DHUPGURI CCC, [APPLICATION NO. 100000066800, Reference ID : 860257020] | Assistant Engineer,HQ | Junior Engineer | BILL/00041/2022-2023 | BP/22-23/131 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.93 | 0 | 0
101 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for PURBO MAGURMARI, T/W IV, under DHUPGURI CCC, [APPLICATION NO. 100000086997, Reference ID : 860278198] | Assistant Engineer,HQ | Junior Engineer | BILL/01067/2023-2024 | BP/23-24/108 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.63 | 0 | 0
102 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
103 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA MAGURMARI (REJU) PWSS, at TW no. V, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000578/2022-2023 | 1125/NMD | 12/09/2022 | 1023 | UTTAM PAUL | 8.01 | 5.3 | 60
104 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA MAGURMARI (REJU) PWSS, at TW no. IV, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000773/2022-2023 | 82/NMD | 27/01/2023 | 736 | MIHIR SARKAR | 8 | 6.53 | 100
105 | Northern Mechanical | Jalpaiguri Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA MAGURMARI (Reju) WS Scheme at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000782/2022-2023 | 103/NMD | 03/02/2023 | 729 | MIHIR SARKAR | 2.27 | 2.26 | 100
106 | Northern Mechanical | Jalpaiguri Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA MAGURMARI (Reju) WS Scheme at TW No. V in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000783/2022-2023 | 104/NMD | 03/02/2023 | 817 | UTTAM PAUL | 2.27 | 1.67 | 100
107 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No. Tube Well by ODEX-165 Method of drilling and Construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement for direct boosting under the command area of Manabari Chaa Sundari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000097/2024-2025 | 1293/JD | 05/09/2024 | 90 | RANJEET SINGH BENIWAL | 13.9 | 0 | 100
108 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Land development of H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000268/2022-2023 | 207/JSSD | 14/09/2022 | 30 | M/S A.B.G. CONSTRUCTION | 1.41 | 1.4 | 100
109 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 100 cum OHR as per departmental design & drawing switch room, laying distribution system sinking of tube well etc. supply of potable drinking water to Manabari Tea Garden in relation with CHAA Sundari Project Piped Water Supply Scheme Block. Nagrakata Dist. Jalpaiguri. |  | Junior Engineer | ORD/000335/2020-2021 | 321/JD | 25/02/2021 | 120 | RANJIT SINGH BENIWAL | 72.76 | 51.53 | 0
110 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for Manabari TG Chaa Sundari W/S Scheme, T/W No. I, under ODLABARI CCC [APPLICATION NO. 4003043871 ; Reference ID : 402922125] |  | Junior Engineer | BILL/00021/2022-2023 | BP/22-23/133 | 10/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
111 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for Manabari TG Chaa Sundari W/S Scheme, T/W No. I, under ODLABARI CCC [APPLICATION NO.100000066241 ; Reference ID : 860255931] |  | Junior Engineer | BILL/00022/2022-2023 | BP/22-23/133 | 10/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.12 | 0 | 0
112 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for MANABARI TG (CHAA SUNDARI) PROJECT, TW NO-II, OODLABARI CCC APPLICATION NO. 4003491173 Reference ID : 403275174 |  | Junior Engineer | BILL/01397/2024-2025 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
113 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at Manabari TG (CHAA SUNDARI) PROJECT, TW NO-II, OODLABARI CCC APPLICATION NO. 100000118548 Reference ID : 860312788 |  | Junior Engineer | BILL/01465/2024-2025 | BP/24-25/246 | 02/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.44 | 0 | 0
114 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at MANABARI TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block MAL, district Jalpaiguri. |  | Junior Engineer | ORD/000040/2022-2023 | 355/NMD | 23/05/2022 | 30 | S.P. ENTERPRISE | 14.27 | 9.72 | 0
115 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL FOR THEB HIRED VEHICLES UNDER JALPAIGURI DIVISION AND SUB DIVISION |  | Junior Engineer | BILL/00480/2023-2024 | BP-2023-24-375 | 19/09/2023 | 0 | FILL & SMILE | 0.7 | 0 | 0
116 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL AND LUBRICANTS FOR THE VEHICLES UNDER JALPAIGURI |  | Junior Engineer | BILL/00610/2023-2024 | BP-2023-24-416 | 06/10/2023 | 0 | FILL & SMILE | 2.41 | 0 | 0
117 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of 1(one) Maxi cab with engine capacity less than or equal to 2000c.c on hire basis including driver for the Executive Engineer ,planing & Design Division-III, P.H.E. Dte., silliguri |  | Junior Engineer | BILL/00664/2023-2024 | BP-2023-24-467 | 17/10/2023 | 0 | SHREYANSH AUTO MOBILE | 1.14 | 0 | 0
118 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL BILL |  | Junior Engineer | BILL/00685/2023-2024 | BP-2023-24-491 | 08/11/2023 | 0 | FILL & SMILE | 0.32 | 0 | 0
119 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL & LUBRICANT FOR THE VEHICLE RUNNING UNDER JALPAIGURI RWS FOR THE MONTH OF OCTOBER-2023 |  | Junior Engineer | BILL/00894/2023-2024 | BP-2023-24-508 | 29/11/2023 | 0 | FILL & SMILE | 0.22 | 0 | 0
120 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250 mm X 150 mm dia tube well by Reverse Rotary method of drilling at 4th Site of A Dakshin Berubari PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000204/2024-2025 | 1591/JD | 23/10/2024 | 30 | NARESH SEN | 9.11 | 0 | 0
121 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) |  | Junior Engineer | ORD/000252/2023-2024 | 683/JD | 11/07/2023 | 184 | RAKESH SARKAR | 0.88 | 1.04 | 50
122 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.07.2023) |  | Junior Engineer | ORD/000253/2023-2024 | 672/JD | 10/07/2023 | 184 | APIKUL ALI | 0.88 | 0.82 | 30
123 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Soil Investigation Work, Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall (H/W and 2nd Site) along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Satkhaya Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000284/2023-2024 | 1255/JD | 13/09/2023 | 626 | B RAI CONSTRUCTION COMPANY | 183 | 0 | 14
124 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 4th Tubewell site for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000352/2022-2023 | 164/JD | 19/01/2023 | 45 | KAUSHIK SEN | 10.78 | 0 | 0
125 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000367/2021-2022 | 347/JD | 03/02/2022 | 1518 | M/S RATAN KUMAR DAS GUPTA AND CO | 175.44 | 136.33 | 100
126 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-B). |  | Junior Engineer | ORD/000368/2021-2022 | 340/JD | 03/02/2022 | 1518 | M/S RATAN KUMAR DAS GUPTA AND CO | 162.92 | 83.77 | 100
127 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works at Jakhai bari, Kathal Tali, Kalirhat & adjacent area of Dwarikamari W/S/S under Jalpaiguri Division , P.H.E .Dte. (Part-F). Block-Maynaguri. District- Jalpaiguri. |  | Junior Engineer | ORD/000426/2022-2023 | 625/JD | 13/03/2023 | 45 | ARATI CONSTRUCTION | 45 | 0 | 100
128 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections (at 4th TW site) including other necessary arrangement for Augmentation of Dakshin Berubari Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000436/2022-2023 | 167/RWS | 28/02/2023 | 14 | SAPTASWA SARKAR | 1.58 | 0 | 1
129 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000455/2021-2022 | 337/JD | 02/02/2022 | 120 | M/S RATAN KUMAR DAS GUPTA AND CO | 143.72 | 110.73 | 100
130 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-C). |  | Junior Engineer | ORD/000461/2021-2022 | 341/JD | 03/02/2022 | 1468 | M/S A.B.G. CONSTRUCTION | 174.6 | 92.67 | 100
131 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000462/2021-2022 | 343/JD | 03/02/2022 | 90 | SUKES BASU MAJUMDAR | 177.1 | 94.69 | 100
132 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-E). |  | Junior Engineer | ORD/000463/2021-2022 | 344/JD | 03/02/2022 | 749 | R.S CONSTRUCTION | 177.82 | 124.31 | 100
133 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF DAKSHIN BERUBARI PIPED WATER SUPPLY SCHEME BLOCK JALPAIGURI DISTRICT JALPAIGURI (PART-F). |  | Junior Engineer | ORD/000464/2021-2022 | 346/JD | 03/02/2022 | 1518 | M/S SURAJIT DEY AND CO. | 197.49 | 67.35 | 100
134 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional work of OHR including IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Dakshin Berubari Pipe Water Supply Scheme under Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000548/2024-2025 | 128/JD | 16/01/2025 | 440 | M/S RATAN KUMAR DAS GUPTA AND CO | 78.71 | 0 | 85
135 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000011/2021-2022 | 560/JD | 01/03/2022 | 0 | Resource Division | 53.75 | 0 | 0
136 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000086/2024-2025 | 2213/JD | 01/12/2024 | 0 | Resource Division | 30.21 | 0 | 0
137 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC GHASMARI |  | Junior Engineer | VCH/001355/2021-2022 | BP-2021-22-499 | 29/03/2022 | 0 | M/S R.N. TRADERS | 56.2 | 0 | 0
138 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for DAKSHIN BERUBARI, T/W IV, under HALDIBARI CCC, [APPLICATION NO. 4003215403, Reference ID : 403062802] |  | Junior Engineer | BILL/01116/2023-2024 | BP/23-24/123 | 10/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0
139 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Sinking of Shallow Tubewell for the Contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Augmentation Dakshin Berubari PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. |  | Junior Engineer | ORD/000128/2023-2024 | 42/DSD | 14/07/2023 | 10 | SARKAR ELECTRIC | 0.08 | 0 | 0
140 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tube well (BDTW) by the Reverse Rotary Circulation method of drilling at Augmentation Dakshin Berubari PWSS TW-IV, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000129/2023-2024 | 43/DSD | 14/07/2023 | 10 | SARKAR ELECTRIC | 0.79 | 0 | 0
141 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF DAKSHIN BERUBARI PWSS,TW No IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000882/2022-2023 | 365/NMD | 29/03/2023 | 30 | SARKAR ELECTRIC | 11.14 | 8.61 | 70
142 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING INSPECTION VEHICLE FOR OFFICIAL USE OF THE OFFICE OF THE EXECUTIVE ENGINEER,JALPAIGURI DIVISION, P.H.E. Dte. |  | Junior Engineer | BILL/00621/2023-2024 | BP-2023-24-426 | 10/10/2023 | 0 | SADHAN KARMAKAR | 0.16 | 0 | 0
143 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of 1(one) Maxi cab on hire basis including driver for the office of the Executive Engineer , planning & Design Division -III,P.H.E. Dte. Silliguri |  | Junior Engineer | BILL/00904/2023-2024 | BP-2023-24-515 | 06/12/2023 | 0 | SHREYANSH AUTO MOBILE | 1.15 | 0 | 0
144 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2023 to 31/10/2023 |  | Junior Engineer | ORD/000117/2023-2024 | 44/JSSD | 27/04/2023 | 183 | MRITYUNJAY SIKDAR | 0.88 | 0.88 | 34
145 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) |  | Junior Engineer | ORD/000202/2022-2023 | 1741/JD | 08/09/2022 | 45 | PROVA CONSTRUCTION | 75.59 | 47.84 | 100
146 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional pipeline works for Augmentation of Baikur (Part-I) Piped Water Supply Scheme. |  | Junior Engineer | ORD/000239/2022-2023 | 1861/JD | 20/09/2022 | 30 | PRADIP KR SEN | 18 | 18.53 | 1
147 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000286/2022-2023 | 2014/JD | 01/11/2022 | 45 | M/S R.N. TRADERS | 17.88 | 17.37 | 100
148 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000340/2022-2023 | 275/JD | 22/11/2022 | 15 | DREAM CONSTRUCTION | 6.32 | 5.15 | 0
149 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (40m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Baikur water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000344/2022-2023 | 137/JD | 17/01/2023 | 45 | SADHAN KARMAKAR | 17.86 | 17.27 | 100
150 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-II) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000360/2021-2022 | 323/JD | 02/02/2022 | 90 | UNIBRO INFRASERV PRIVATE LIMITED | 224.83 | 217.04 | 1
151 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-I) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000361/2021-2022 | 322/JD | 02/02/2022 | 90 | UNIBRO INFRASERV PRIVATE LIMITED | 224.8 | 210.42 | 100
152 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-III) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000362/2021-2022 | 324/JD | 02/02/2022 | 90 | CALCON CONSTRUCTIONS | 218.39 | 175.31 | 50
153 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-IV) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000363/2021-2022 | 325/JD | 02/02/2022 | 90 | NARAYAN CHANDRA SAHA | 221.81 | 146.12 | 1
154 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-V) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000364/2021-2022 | 326/JD | 02/02/2022 | 719 | MINTU CHAKRABORTY | 220.34 | 68.71 | 100
155 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BAIKUR (PART-VI) PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI. |  | Junior Engineer | ORD/000365/2021-2022 | 327/JD | 02/02/2022 | 799 | M/S S.G. CONSTRUCTION | 213.61 | 142.01 | 100
156 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Minor Repairing work for Pump House & construction of CC path for Baikur Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000365/2022-2023 | 191/JD | 20/01/2023 | 15 | DREAM CONSTRUCTION | 2.55 | 1.79 | 0
157 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of Additional 75 mm dia pipeline for providing FHTC for Augmentation of Baikur PWSS for Part-VI area. |  | Junior Engineer | ORD/000530/2023-2024 | 1876/JD | 20/12/2023 | 21 | PRADIP KR SEN | 13.08 | 12.47 | 100
158 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional Laying Distribution System and Providing Functional House Hold Tap Connection at Baikur (Part-V) PWSS Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000609/2024-2025 | 483/JD | 11/03/2025 | 296 | DREAM CONSTRUCTION | 19.67 | 0 | 85
159 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000616/2021-2022 | 2238/JD | 29/12/2021 | 60 | ABHIJIT SARKAR | 11.44 | 9.84 | 1
160 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Baikur Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000710/2021-2022 | 2223/JD | 27/12/2021 | 60 | DREAM CONSTRUCTION | 11.43 | 10.39 | 1
161 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000009/2021-2022 | 557/JD | 01/03/2022 | 0 | Resource Division | 1.82 | 0 | 0
162 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000088/2024-2025 | 2219/JD | 01/12/2024 | 0 | Resource Division | 44.19 | 0 | 0
163 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | TUBE WELL BILL |  | Junior Engineer | VCH/001151/2021-2022 | BP-2021-22-266 | 16/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0
164 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS MOGALKATA T.G PWSS |  | Junior Engineer | VCH/001262/2021-2022 | BP-2021-22-554 | 31/03/2022 | 0 | DULAL CHOUDHURY | 10.11 | 0 | 0
165 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | AUG LATAGURI ZONE III |  | Junior Engineer | VCH/001396/2021-2022 | BP-2021-22-552 | 31/03/2022 | 0 | RAGHU DAS | 22.91 | 0 | 0
166 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-I) PWSS UNDER CDD, PHE DTE. |  | Junior Engineer | ORD/000177/2021-2022 | 753/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 8.69 | 0
167 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-III) PWSS UNDER CENTRAL DRILLING DIVISION, PHE DTE. |  | Junior Engineer | ORD/000179/2021-2022 | 755/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 8.32 | 0
168 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BAIKUR (TW-II) PWSS UNDER CDD, PHE DTE. |  | Junior Engineer | ORD/000181/2021-2022 | 754/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 8.33 | 0
169 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS ( 1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-II) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000184/2021-2022 | 471/CMSD-II (D) | 26/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.85 | 0.77 | 0
170 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION OF BENTONITE AFTER 200 KM FOR (4X3)=12 MT BENTONITE AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000185/2021-2022 | 473/CMSD-II (D) | 26/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.3 | 0.28 | 0
171 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200KM FOR 20 M3 GRAVELS (1 M3 = 1.68MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-III) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000186/2021-2022 | 472/CMSD-II (D) | 26/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.85 | 0.77 | 0
172 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 10M3 GRAVELS (1 M3 = 1.68MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000187/2021-2022 | 464/CMSD-II (D) | 25/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.42 | 0.03 | 0
173 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BAIKUR (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000188/2021-2022 | 463/CMSD-II (D) | 25/10/2021 | 7 | PADMA ENGINEERING & CO. | 0.85 | 0.85 | 0
174 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for augmentation of BAIKUR W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000003/2022-2023 | 206/NMD | 04/04/2022 | 21 | R.K.ENTERPRISES | 2.77 | 2.77 | 0
175 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for augmentation of BAIKUR W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000004/2022-2023 | 207/NMD | 04/04/2022 | 21 | MALAY KUMAR SAHA | 2.77 | 2.77 | 0
176 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of BAIKUR PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000011/2022-2023 | 279/NMD | 26/04/2022 | 30 | INDTECH ASSOCIATES | 8.74 | 8.74 | 0
177 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of BAIKUR PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000012/2022-2023 | 280/NMD | 26/04/2022 | 30 | M/S P.P. ELECTRICALS | 8.74 | 8.74 | 0
178 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BAIKUR PWSS, at TW No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000068/2022-2023 | 443/NMD | 14/06/2022 | 21 | BONANZA ENTERPRISE | 2.76 | 2.76 | 0
179 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BAIKUR PWSS, at TW No. IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000082/2022-2023 | 540/NMD | 08/07/2022 | 30 | SARKAR ELECTRIC | 8.31 | 8.31 | 0
180 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. IV of JORPAKRI BAZAR W/S Scheme under BHOPATTY CCC [APPLICATION NO. 4002923158 ; Reference ID : 402820488] |  | Junior Engineer | VCH/000171/2022-2023 | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
181 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of Infrastructure IRO NSC application T/W No. IV of JORPAKRI BAZAR W/S Scheme under BHOPATTY CCC [APPLICATION NO. 100000052276 ; Reference ID : 860241546] |  | Junior Engineer | VCH/000172/2022-2023 | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0
182 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. IV of BAIKUR JORPAKRI BAZER W/S Scheme under BHOPATTY CCC [APPLICATION NO. 4002923158 ; Reference ID : 402820488] |  | Junior Engineer | VCH/000173/2022-2023 | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
183 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of Infrastructure IRO NSC application T/W No. III of BAIKUR GOURGRAM HELAPAKRI BAZER W/S Scheme under BHOPATTY CCC [APPLICATION NO. 100000052275 ; Reference ID : 860241545] |  | Junior Engineer | VCH/000174/2022-2023 | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.73 | 0 | 0
184 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of existing LDS under the command area of Khalaigram Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) | Assistant Engineer,HQ | Junior Engineer | ORD/000249/2021-2022 | 1990/JD | 03/12/2021 | 30 | M/S R.N. TRADERS | 47.9 | 9.31 | 1
185 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000314/2020-2021 | 296/JD | 24/02/2021 | 30 | M/S SIBU DEY AND CO. | 24.41 | 0 | 1
186 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KHALAIGRAM piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000315/2020-2021 | 290/JD | 23/02/2021 | 20 | PARESH CHANDRA ROY | 12.8 | 0 | 1
187 | Jalpaiguri Division | Jalpaiguri Division | IEP FOR RAIPUR T.G | Assistant Engineer,HQ | Junior Engineer | VCH/000060/2022-2023 | BP-2021-22-24 | 26/04/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 2.39 | 0 | 0
188 | Jalpaiguri Division | Jalpaiguri Division | shifting of pipe line khalaigram | Assistant Engineer,HQ | Junior Engineer | VCH/000341/2021-2022 |  | 05/10/2021 | 0 | LOKNATH CONSTRUCTION | 9.83 | 0 | 0
189 | Jalpaiguri Division | Jalpaiguri Division | FHTC KHALAIGRAM | Assistant Engineer,HQ | Junior Engineer | VCH/000482/2021-2022 |  | 29/10/2021 | 0 | M/S SIBU DEY AND CO. | 22.47 | 0 | 0
190 | Jalpaiguri Division | Jalpaiguri Division | SHIFTING OF PIPE LINE FOR KHALAIGRAM PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000673/2021-2022 | BP-2021-22-77 | 08/10/2021 | 0 | LOKNATH CONSTRUCTION | 9.83 | 0 | 0
191 | Jalpaiguri Division | Jalpaiguri Division | fhtc khalaigram | Assistant Engineer,HQ | Junior Engineer | VCH/000807/2021-2022 | BP-2021-22-94 | 13/11/2021 | 0 | M/S SIBU DEY AND CO. | 22.47 | 0 | 0
192 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Barogari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000166/2025-2026 | 1958/JD | 18/09/2025 | 45 | DEBASISH DEY | 29.65 | 0 | 0
193 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of MADHYA BORAGARI ZONE-II PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division, P.H.E DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000239/2025-2026 | 2345/JD | 04/11/2025 | 210 | BISWANATH GHOSH | 327.82 | 0 | 0
194 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000037/2023-2024 | 1110/JD | 24/08/2023 | 0 | Resource Division | 14.91 | 0 | 0
195 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000129/2023-2024 | 1843/JD | 15/12/2023 | 0 | Resource Division | 8.21 | 0 | 0
196 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MADHYA BORAGARI PWSS, ZONE-II, TW NO II, under DHUPGURI CCC APPLICATION NO. 4003460802 Reference ID : 403255266 | Assistant Engineer,HQ | Junior Engineer | BILL/00971/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.3 | 0 | 0
197 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MADHYA BORAGARI PWSS, ZONE-II, TW NO I, under DHUPGURI CCC APPLICATION NO. 4003460793 Reference ID : 403255267 | Assistant Engineer,HQ | Junior Engineer | BILL/00972/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.21 | 0 | 0
198 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA BORAGARI PWSS, ZONE-II, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000241/2023-2024 | 1255/NMD | 31/07/2023 | 30 | RMD TRADING | 21.74 | 13.8 | 60
199 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
200 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
201 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Gaurgram PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000453/2024-2025 | 633/JD | 28/03/2025 | 45 | RABINDRA NATH DUTTA | 34.39 | 0 | 0
202 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Gaurgram PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal JeevanMission at Block- Maynaguri under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000476/2022-2023 | 787/JD | 27/03/2023 | 1062 | M/S S.G. CONSTRUCTION | 346.83 | 168.71 | 100
203 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd site of GAUGRAM PWSS in connection with Jal Jeevan Mission at Block - MAYNAGURI under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000686/2023-2024 | 152/RWS | 15/02/2024 | 30 | JAGORAN SARKAR | 5.23 | 5.22 | 100
204 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000015/2023-2024 | 159/JD | 28/04/2023 | 0 | Resource Division | 62.06 | 0 | 0
205 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000191/2023-2024 | 2040/JD | 09/01/2024 | 0 | Resource Division | 14.78 | 0 | 0
206 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Gourgram, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003375840 Reference ID : 403191702 |  | Junior Engineer | BILL/00289/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.64 | 0 | 0
207 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for GOURGRAM, T/W No. I under BHOTPATTY CCC [APPLICATION NO. 4003305799 ; Reference ID : 403134434] |  | Junior Engineer | BILL/01856/2023-2024 | BP/23-24/294 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.37 | 0 | 0
208 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
209 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
210 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAURGRAM PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000415/2023-2024 | 1329/NMD | 08/08/2023 | 678 | DIPALI CONSTRUCTION | 22.21 | 17.48 | 100
211 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
212 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0
213 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
214 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
215 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain, at 2nd site of Shakati PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000111/2025-2026 | 489/RWS | 29/05/2025 | 30 | MS DEBABRATA SARKAR | 6.24 | 0 | 0
216 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Shakati PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000465/2022-2023 | 753/JD | 24/03/2023 | 902 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 346.92 | 250.01 | 95
217 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Shakati PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000676/2024-2025 | 468/JD | 11/03/2025 | 40 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 17.67 | 0 | 0
218 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000042/2023-2024 | 1107/JD | 24/08/2023 | 0 | Resource Division | 25.88 | 0 | 0
219 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000146/2023-2024 | 2002/JD | 08/01/2024 | 0 | Resource Division | 7.26 | 0 | 0
220 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAKATI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4400307494, Reference ID : 403056595] |  | Junior Engineer | BILL/00626/2023-2024 | BP/23-24/87 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
221 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for SAKATI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000086241, Reference ID : 860277651] |  | Junior Engineer | BILL/00627/2023-2024 | BP/23-24/87 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0
222 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAKATI, T/W I, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003212055, Reference ID : 403060258] |  | Junior Engineer | BILL/01069/2023-2024 | BP/23-24/105 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.53 | 0 | 0
223 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SHAKATI PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000021/2023-2024 | 463/NMD | 25/04/2023 | 30 | SUMON ELECTRICAL | 22.07 | 17.9 | 100
224 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
225 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at SHAKATI and other adjacent water supply scheme UNDER JJM under JALPAIGURI SADAR Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/000887/2024-2025 | 79/SMSD | 07/02/2025 | 15 | SUMON ELECTRICAL | 1.57 | 0 | 0
226 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
227 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Amguri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc.i.c.w. Jal Jeevan Missionat Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte |  | Junior Engineer | ORD/000011/2023-2024 | 29/JD | 10/04/2023 | 1088 | SUKES BASU MAJUMDAR | 514.99 | 337.97 | 77
228 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of RCC Pillers for Delivery & Rising Line and Laying Distribution System for Amguri Piped Water Supply Scheme in connection with Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000169/2025-2026 | 2003/JD | 25/09/2025 | 30 | SUKES BASU MAJUMDAR | 44.57 | 0 | 100
229 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional Household Tap Connection in connection with Jal Jeevan Mission at Amguri PWSS in Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000512/2024-2025 | 45/JD | 09/01/2025 | 416 | B. M CONSTRUCTION | 70.87 | 0 | 60
230 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site Including raising main and interconnection of Amguri PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000674/2023-2024 | 165/RWS | 15/02/2024 | 30 | DEEP CONSTRUCTION | 6.17 | 6.16 | 100
231 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000007/2023-2024 | 151/JD | 28/04/2023 | 0 | Resource Division | 105.47 | 0 | 0
232 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000170/2023-2024 | 2056/JD | 09/01/2024 | 0 | Resource Division | 14.62 | 0 | 0
233 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for AMGURI, T/W No. I, under MAYNAGURI CCC, [APPLICATION NO. 4003266414, Reference ID : 403108583] |  | Junior Engineer | BILL/01283/2023-2024 | 23-24/155&163 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.24 | 0 | 0
234 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for AMGURI, T/W No. II, under MAYNAGURI CCC [APPLICATION NO. 4003297950 , Reference ID : 403128266] |  | Junior Engineer | BILL/01780/2023-2024 | BP/23-24/217 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.49 | 0 | 0
235 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
236 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
237 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
238 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AMGURI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000843/2022-2023 | 271/NMD | 21/03/2023 | 30 | TALUKDER ENTERPRISE | 22.92 | 21.83 | 100
239 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0
240 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Drainage arrangement for back wash water from Iron Elemation Plant at 3rd & 4th tube well site of Charerbari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000033/2023-2024 | 387/RWS | 25/04/2023 | 14 | PRITAM DUTTA | 2.73 | 2.73 | 100
241 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000144/2022-2023 | 1578/JD | 12/08/2022 | 45 | NEW KUNDU ENTERPRISE | 14.43 | 13.22 | 0
242 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Charerbari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000150/2022-2023 | 1563/JD | 10/08/2022 | 45 | A.P CONSTRUCTION | 14.45 | 13.19 | 0
243 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000288/2022-2023 | 2012/JD | 01/11/2022 | 15 | M/S DEY & ROY CHOUDHURY | 3.7 | 3.1 | 1
244 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Minor Repairing work for OHR, Pump Houses, Boundary walls, Blower Room, IEP etc. for Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000400/2022-2023 | 605/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.69 | 0 | 0
245 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Approach road by Paver Block inside the Reservior Compound at Charerbari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000402/2022-2023 | 603/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.92 | 3.84 | 100
246 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000479/2021-2022 | 2212/JD | 27/12/2021 | 60 | M/S DEY & ROY CHOUDHURY | 11.44 | 11.38 | 1
247 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Charerbari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000480/2021-2022 | 2213/JD | 27/12/2021 | 60 | JAYA SARKAR | 11.42 | 11.38 | 1
248 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Charerbari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000730/2021-2022 | 634/JD | 07/03/2022 | 30 | MECHANO TRADING CO. | 15.51 | 12.5 | 1
249 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000083/2023-2024 | 1059/JD | 24/08/2023 | 0 | Resource Division | 3.24 | 0 | 0
250 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Charerbari Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000100/2022-2023 | 568/NMD | 14/07/2022 | 21 | SUNLIT | 2.16 | 2.16 | 50
251 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Charerbari Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000102/2022-2023 | 569/NMD | 14/07/2022 | 21 | SUDIP DUTTA | 2.16 | 2.16 | 0
252 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for CHARERBARI PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000120/2022-2023 | 857/NMD | 18/07/2022 | 30 | DAWA DUKPA | 7.87 | 0 | 80
253 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for CHARERBARI PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000121/2022-2023 | 858/NMD | 18/07/2022 | 30 | SUBHRANGSHU GUHARAJA | 7.87 | 7.87 | 0
254 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for TW-IV of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941281 , Reference ID : 402831979] |  | Junior Engineer | VCH/000333/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
255 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for TW-IV of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053963 ; Reference ID : 860243613] |  | Junior Engineer | VCH/000334/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.92 | 0 | 0
256 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for TW-III of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941279 ; Reference ID : 402831974] |  | Junior Engineer | VCH/000335/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
257 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for TW-III of CHARERBARI W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053962 ; Reference ID : 860243612] |  | Junior Engineer | VCH/000336/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.21 | 0 | 0
258 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | HIRE CHARGES BILL OF VEHICLE UNDER NBC-I,PHE Dte. |  | Junior Engineer | BILL/00912/2023-2024 | BP-2023-24-517 | 07/12/2023 | 0 | RUPA PRASAD | 0.62 | 0 | 0
259 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
260 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Different components of Dharmapur Zone-I PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. I.c.w. Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000029/2023-2024 | 96/JD | 25/04/2023 | 857 | GLOBAL POWER & CONSTRUCTION CO. | 314.13 | 168.71 | 70
261 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
262 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dharmmapur Zone-I PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000451/2024-2025 | 2330./JD | 12/12/2024 | 639 | BISWAJIT BHADURI | 41.39 | 0 | 70
263 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd site of Dharamapur Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000684/2023-2024 | 154/RWS | 15/02/2024 | 287 | ARATI CONSTRUCTION | 7.29 | 7.2 | 100
264 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W Site including Rising main interconnection of Dharamapur Zone - I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000707/2023-2024 | 2460/JD | 23/02/2024 | 768 | ARUP SARKAR | 22.91 | 0 | 0
265 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000183/2023-2024 | 2037/JD | 09/01/2024 | 0 | Resource Division | 6.57 | 0 | 0
266 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for DHARMAPUR, T/W No. I, ZONE-I under BHOTPATTY CCC [APPLICATION NO. 4003305851 ; Reference ID : 403134433] |  | Junior Engineer | BILL/01857/2023-2024 | BP/23-24/287 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.82 | 0 | 0
267 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for DHARMAPUR, T/W No. II, ZONE-I under BHOTPATTY CCC [APPLICATION NO. 4003305854 ; Reference ID : 403134431] |  | Junior Engineer | BILL/01860/2023-2024 | BP/23-24/288 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.12 | 0 | 0
268 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
269 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
270 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHARMMAPUR PWSS, TW NO I and II (ZONE-I) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000242/2023-2024 | 1256/NMD | 31/07/2023 | 459 | M/S UTPAL CHAKRABORTY & CO. | 21.53 | 20.45 | 100
271 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
272 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0
273 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
274 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
275 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance Laying Distribution System with providing Functional Household Tap Connection (FHTC) including sinking of One No Additional Tube Well by ODEX-165 method of drilling, construction of Pump House (3.60m x 2.40m) with sanitary plumbing arrangement, Boundary Wall and direct boosting for 5th site in the command area of Ranichera Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000681/2024-2025 | 460/JD | 11/03/2025 | 142 | GOEL CONSTRUCTION CO. | 80.53 | 0 | 90
276 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000061/2023-2024 | 1098/JD | 24/08/2023 | 0 | Resource Division | 49.85 | 0 | 0
277 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000141/2023-2024 | 1887/JD | 20/12/2023 | 0 | Resource Division | 16.42 | 0 | 0
278 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266411, Reference ID : 403105529] |  | Junior Engineer | BILL/01259/2023-2024 | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
279 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093887, Reference ID : 860285547] |  | Junior Engineer | BILL/01260/2023-2024 | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.25 | 0 | 0
280 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003266404, Reference ID : 403105524] |  | Junior Engineer | BILL/01261/2023-2024 | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
281 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093888, Reference ID : 860285548] |  | Junior Engineer | BILL/01262/2023-2024 | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0
282 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266407, Reference ID : 403105523] |  | Junior Engineer | BILL/01263/2023-2024 | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
283 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for RANICHERA TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093890, Reference ID : 860285650] |  | Junior Engineer | BILL/01264/2023-2024 | 23-24/157&165 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0
284 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at RANICHERA TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 100000117729 Reference ID : 860312409 |  | Junior Engineer | BILL/01415/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.39 | 0 | 0
285 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for RANICHERA TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 4003482909 Reference ID : 403269953 |  | Junior Engineer | BILL/01416/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
286 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
287 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Additional Works in connection with supply, installation, commissioning and trial operation of electro mechanical components along with copper own line voltage corrector for RANICHERA T.G PWSS in the Dist. of JALPAIGURI under Northern Mechanical Division PHE Dte. |  | Junior Engineer | ORD/000072/2024-2025 | 1061/HQ/NMD | 21/06/2024 | 7 | M/S PARITOSH BHOWMICK AND CO. | 0.89 | 0.88 | 100
288 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RANICHERA TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000673/2023-2024 | 1488/NMD | 17/08/2023 | 30 | M/S PARITOSH BHOWMICK AND CO. | 37.96 | 35.04 | 70
289 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
290 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
291 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dakshin Dangapara PWSS Zone- I i.e, TW, Pump Houses, Water distribution Network, OHR, IEP, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block Maynaguri under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000065/2023-2024 | 375/A/JD | 30/05/2023 | 763 | PARESH CHANDRA GUHA | 384.43 | 248.47 | 100
292 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dakshin Dangapara Zone-I PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000448/2024-2025 | 2163/JD | 27/11/2024 | 287 | PARESH CHANDRA GUHA | 49.63 | 0 | 0
293 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000167/2023-2024 | 2031/JD | 09/01/2024 | 0 | Resource Division | 9.97 | 0 | 0
294 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for DAKSHIN DANGAPARA ZONE-I, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003397683 Reference ID : 403208960 |  | Junior Engineer | BILL/00283/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.85 | 0 | 0
295 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for DAKSHIN DANGAPARA ZONE-I, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003397121 Reference ID : 403208946 |  | Junior Engineer | BILL/00284/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.98 | 0 | 0
296 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
297 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
298 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN DANGAPARA PWSS, ZONE-I, TW no I, II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000354/2023-2024 | 1315/NMD | 04/08/2023 | 547 | DIAMOND ELECTRICAL WORKS | 21.72 | 16.14 | 80
299 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
300 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0
301 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Arji Maria Kamala Pukhari PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) |  | Junior Engineer | ORD/000079/2023-2024 | 432/JD. | 08/06/2023 | 28 | GOUTAM DAS | 55.33 | 55.47 | 100
302 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Washout line at 4th Site and Replacement of damaged higher dia pipeline at Arjimaria Kamalapukuri Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri District, PHE Dte. |  | Junior Engineer | ORD/000187/2025-2026 | 2169/JD | 30/10/2025 | 153 | SOUVIK SAHA | 14 | 0 | 100
303 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of 2 Nos of Iron Elimination Plant (20m3/hr.) including construction of 2 nos of Blower room (3.60MX3.00M) Size & concrete platform , drain, valve chamber etc at 3rd and 4th Site of Arji maria kamala pukhari piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000560/2023-2024 | 2175/JD | 22/01/2024 | 60 | R.S CONSTRUCTION | 28.19 | 28.12 | 100
304 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Chotachand Fapri PWSS i.e, TW, Pump House, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000044/2023-2024 | 221/JD | 03/05/2023 | 943 | NARENDRA KUMAR | 196.33 | 42.77 | 45
305 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000002/2024-2025 | 52/JD | 09/04/2024 | 0 | Resource Division | 12.25 | 0 | 0
306 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000184/2023-2024 | 2047/JD | 09/01/2024 | 0 | Resource Division | 4.67 | 0 | 0
307 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for CHOTA FAPTI NEPALI SCHOOL, T/W-I, under POWER HOUSE CCC, [APPLICATION NO. 4003352320, Reference ID : 403172860] | Assistant Engineer,HQ | Junior Engineer | BILL/02176/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0
308 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for CHOTA FAPTI NEPALI SCHOOL, T/W-II, under POWER HOUSE CCC, [APPLICATION NO. 4003352332, Reference ID : 403172862] | Assistant Engineer,HQ | Junior Engineer | BILL/02177/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.85 | 0 | 0
309 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHOTA FAPRI PWSS, AT TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000310/2023-2024 | 1275/NMD | 02/08/2023 | 761 | M/S BHOWMICK & CO. | 20.44 | 3.89 | 70
310 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
311 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
312 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Rangamati Tea Garden PWSS i.e. Tube Well, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000012/2025-2026 | 894/JD | 08/05/2025 | 90 | UMA CONSTRUCTION | 41.93 | 0 | 0
313 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
314 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rangamati Tea Garden PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000262/2023-2024 | 940/JD | 08/08/2023 | 718 | M/S SARKAR ENTERPRISE | 360.92 | 70.39 | 22
315 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution Network and Functional Household Tap Connection (FHTC) of Rangamati Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000432/2024-2025 | 2273/JD | 05/12/2024 | 60 | LAKSHMI IRON | 26.64 | 0 | 0
316 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000151/2023-2024 | 2019/JD | 09/01/2024 | 0 | Resource Division | 12.63 | 0 | 0
317 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at RANGAMATI TG,T/W-III, OODLABARI CCC APPLICATION NO. 100000110603 Reference ID : 860303203 |  | Junior Engineer | BILL/00489/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.49 | 0 | 0
318 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for RANGAMATI TG,T/W-III, OODLABARI CCC APPLICATION NO. 4003437136 Reference ID : 403237579 |  | Junior Engineer | BILL/00490/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
319 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for RANGAMATI TEA GARDEN, T/W No. II, under MAL CCC [APPLICATION NO. 4003325230 , Reference ID : 403151421] |  | Junior Engineer | BILL/01990/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0
320 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for RANGAMATI TEA GARDEN, T/W No.II, under MAL CCC [APPLICATION NO. 100000099050 , Reference ID : 860290250] |  | Junior Engineer | BILL/01991/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.28 | 0 | 0
321 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for RANGAMATI TEA GARDEN, T/W No. I, under MAL CCC [APPLICATION NO. 4003325220 , Reference ID : 403151422] |  | Junior Engineer | BILL/01992/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0
322 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for RANGAMATI TEA GARDEN, T/W No. I, under MAL CCC [APPLICATION NO. 100000098979 , Reference ID : 860290249] |  | Junior Engineer | BILL/01993/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0
323 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RANGAMATI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000671/2023-2024 | 1486/NMD | 17/08/2023 | 899 | M/S UTPAL CHAKRABORTY & CO. | 36.59 | 0 | 50
324 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
325 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site of Kaoagap PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000007/2025-2026 | 679/JD | 04/04/2025 | 45 | M/S RATAN KUMAR DAS GUPTA AND CO | 23.37 | 0 | 100
326 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
327 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site of Kaoagap PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000100/2024-2025 | 831/RWS | 28/08/2024 | 30 | TAPASH MOHANTA | 7.46 | 0 | 0
328 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Kaoagap PWSS i.e. TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. .C.W. Jal Jeevan Mission at Block:- Maynaguri under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000474/2022-2023 | 777/JD | 27/03/2023 | 1101 | M/S RATAN KUMAR DAS GUPTA AND CO | 412.26 | 231.75 | 80
329 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Kaoagap PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000480/2024-2025 | 2428/JD | 24/12/2024 | 464 | ALICK DUTTA | 34.87 | 0 | 0
330 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000011/2023-2024 | 155/JD | 28/04/2023 | 0 | Resource Division | 41.26 | 0 | 0
331 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000173/2023-2024 | 2028/JD | 09/01/2024 | 0 | Resource Division | 6.06 | 0 | 0
332 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for KAOAGAP, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376062 Reference ID : 403191649 |  | Junior Engineer | BILL/00155/2024-2025 | BP/24-25/121 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.82 | 0 | 0
333 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for KAOAGAP, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003356525 Reference ID : 403175897 |  | Junior Engineer | BILL/00186/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0
334 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
335 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
336 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
337 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KAOAGAP PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000840/2022-2023 | 269/NMD | 21/03/2023 | 711 | MIHIR SARKAR | 21.61 | 5.23 | 100
338 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0
339 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Char Charabari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block ¿ Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000051/2023-2024 | 243JD | 08/05/2023 | 732 | SRINIWAS AGARWAL | 328.17 | 205.15 | 50
340 | Jalpaiguri Division | Northern Mechanical Division | Balance work of distribution system and Functional House Hold Tap Connection (FHTC) including Construction of Boundary wall, drain, footpath at 2 nd site of Charchara Bari PWSS at Banarhat Block under Jalapiguri Division PHE. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000459/2024-2025 | 2345/JD | 12/12/2024 | 60 | SRINIWAS AGARWAL | 70.88 | 0 | 0
341 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Char Chara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000586/2024-2025 | 634/JD | 28/03/2025 | 45 | JITENDRA NATH ROY | 30.36 | 0 | 0
342 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000040/2023-2024 | 1108/JD | 24/08/2023 | 0 | Resource Division | 9.53 | 0 | 0
343 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000131/2023-2024 | 1845/JD | 15/12/2023 | 0 | Resource Division | 8.44 | 0 | 0
344 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for CHARCHARABARI, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003365758 Reference ID : 403183039 | Assistant Engineer , Head Quarters , NMD |  | BILL/00129/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.21 | 0 | 0
345 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for CHARCHARABARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003364338 Reference ID : 403181777 | Assistant Engineer , Head Quarters , NMD |  | BILL/00130/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.23 | 0 | 0
346 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
347 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD |  | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
348 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0
349 | Jalpaiguri Division | Jalpaiguri Division | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000179/2022-2023 | 558/RWS | 01/09/2022 | 30 | SAHA CONSTRUCTION | 3.5 | 0 | 1
350 | Jalpaiguri Division | Jalpaiguri Division | Construction of different balance component of PASCHIM SALBARI ZONE-I PWSS i.e. Pump Houses, water distribution Network, OHR, Rising Main, FHTC etc.in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000240/2025-2026 | 2346/JD | 04/11/2025 | 120 | MD HAKIMUDDIN | 227.97 | 0 | 0
351 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Paschim Salbari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000608/2024-2025 | 635/JD | 28/03/2025 | 45 | GOURAB GUHA ROY | 22.72 | 0 | 0
352 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000035/2023-2024 | 1114/JD | 24/08/2023 | 0 | Resource Division | 9.67 | 0 | 0
353 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000123/2023-2024 | 1837/JD | 15/12/2023 | 0 | Resource Division | 5.41 | 0 | 0
354 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PASCHIM SALBARI ZONE:- I, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003417554 Reference ID : 403224815 | Assistant Engineer,HQ | Junior Engineer | BILL/00509/2024-2025 | BP/24-25/111 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.9 | 0 | 0
355 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PASCHIM SALBARI ZONE:- I, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003420142 Reference ID : 403226820 | Assistant Engineer,HQ | Junior Engineer | BILL/00511/2024-2025 | BP/24-25/111 | 05/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.31 | 0 | 0
356 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
357 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM SALBARI PWSS, ZONE-I, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000350/2023-2024 | 1311/NMD | 04/08/2023 | 30 | DIAMOND ELECTRICAL WORKS | 21.32 | 14.8 | 50
358 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0
359 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
360 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000211/2023-2024 | 2073/JD | 10/01/2024 | 0 | Resource Division | 5.79 | 0 | 0
361 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 4003293345 ; Reference ID : 403125584] |  | Junior Engineer | BILL/01733/2023-2024 | BP/23-24/254 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
362 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for AIBHEEL TG, T/W No. IV, under METELLI CCC [APPLICATION NO. 100000095978 ; Reference ID : 860287638] |  | Junior Engineer | BILL/01734/2023-2024 | BP/23-24/255 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.4 | 0 | 0
363 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 4003293341 ; Reference ID : 403125586] |  | Junior Engineer | BILL/01735/2023-2024 | BP/23-24/256 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
364 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for AIBHEEL TG, T/W No. III, under METELLI CCC [APPLICATION NO. 100000095977 ; Reference ID : 860287637] |  | Junior Engineer | BILL/01736/2023-2024 | BP/23-24/257 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10 | 0 | 0
365 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AIBHIL PWSS, TW NO III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000352/2023-2024 | 1313/NMD | 04/08/2023 | 630 | UTTAM PAUL | 24.24 | 20.02 | 90
366 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Paharpur Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000026/2024-2025 | 739/JD | 26/07/2024 | 614 | GOUTAM DAS | 108.29 | 17.91 | 60
367 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PAHARPUR ZONE - I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000109/2025-2026 | 487/RWS | 29/05/2025 | 30 | GURUKUL INFOTECH | 4.32 | 0 | 0
368 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 4.9 | 90
369 | Jalpaiguri Division |  | Construction of different components of Paharpur Zone - I Piped Water Supply Scheme i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  |  | ORD/000437/2023-2024 | 1820/JD | 14/12/2023 | 535 | UNIBRO INFRASERV PRIVATE LIMITED | 616.92 | 141.91 | 80
370 | Jalpaiguri Division |  | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Paharpur Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000531/2024-2025 | 113/JD | 16/01/2025 | 40 | TEESTA CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCITY LIMITED. | 17.91 | 0 | 0
371 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 1081/JD | 24/08/2023 | 0 | Resource Division | 40.23 | 0 | 0
372 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 2005/JD | 08/01/2024 | 0 | Resource Division | 20.68 | 0 | 0
373 | Northern Mechanical |  | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341737, Reference ID : 403171420] |  |  | BILL/02152/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.18 | 0 | 0
374 | Northern Mechanical |  | New Service Connection Charge for PAHARPUR, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 40033441732, Reference ID : 403172479] |  |  | BILL/02153/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.37 | 0 | 0
375 | Northern Mechanical |  | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  |  | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
376 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
377 | Northern Mechanical |  | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0
378 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-I, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/001416/2023-2024 | 487/NMD | 12/02/2024 | 30 | SUMON ELECTRICAL | 23.55 | 19.16 | 100
379 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
380 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
381 | Jalpaiguri Division |  | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain , Land Development etc. at HW Site for Kumarpara PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000074/2024-2025 | 1296/JD | 05/09/2024 | 60 | M/S BOSE ENTERPRISE | 22.73 | 0 | 0
382 | Jalpaiguri Division |  | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 2nd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000084/2024-2025 | 803/RWS | 20/08/2024 | 377 | RANA DEY | 7.43 | 0 | 70
383 | Jalpaiguri Division |  | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, etc. at 3rd TW Site for Kumar para PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000102/2024-2025 | 839/RWS | 29/08/2024 | 412 | SUKUMAR KUNDU | 7.46 | 0 | 90
384 | Jalpaiguri Division |  | Construction of different components of Kumarpara PWSS i.e, TW, Pump Houses, Water distribution network , OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. |  |  | ORD/000269/2023-2024 | 945/JD | 08/08/2023 | 966 | SCEC BOENTER KDAS JOINT VENTURE | 601.28 | 288.21 | 25
385 | Jalpaiguri Division |  | Balance Laying Distribution System including Providing Functional Household Tap Connection in connection with JJM under Kumarpara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000621/2024-2025 | 467/JD | 11/03/2025 | 50 | M/S BOSE ENTERPRISE | 40.13 | 0 | 0
386 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 57/JD | 09/04/2024 | 0 | Resource Division | 31.48 | 0 | 0
387 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 2052/JD | 09/01/2024 | 0 | Resource Division | 14.78 | 0 | 0
388 | Northern Mechanical |  | New Service Connection Charge for KUMARPARA, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003376070 Reference ID : 403191653 |  |  | BILL/00152/2024-2025 | BP/24-25/78 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.13 | 0 | 0
389 | Northern Mechanical |  | New Service Connection Charge for KUMARPARA, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376595 Reference ID : 403191665 |  |  | BILL/00154/2024-2025 | BP/24-25/78 | 06/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.49 | 0 | 0
390 | Northern Mechanical |  | New Service Connection Charge for KUMARPARA, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003435868 Reference ID : 403237472 |  |  | BILL/00460/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.25 | 0 | 0
391 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
392 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
393 | Jalpaiguri Division |  | Construction of different components of Basusuba (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000179/2023-2024 | 850/JD. | 28/07/2023 | 1131 | R.S CONSTRUCTION | 200.42 | 67.6 | 37
394 | Jalpaiguri Division |  | Construction of different components of Basusuba Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000180/2023-2024 | 846/JD | 28/07/2023 | 1131 | R.S CONSTRUCTION | 368.89 | 144.41 | 40
395 | Jalpaiguri Division |  | Construction of different components of Basusuba Zone- II PWSS i.e . TW, Pump House, Water distribution Network, OHR, Boundary wall, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000181/2023-2024 | 851/JD | 28/07/2023 | 180 | R.S CONSTRUCTION | 303.82 | 0 | 0
396 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1083/JD | 24/08/2023 | 0 | Resource Division | 60.79 | 0 | 0
397 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 2075/JD | 10/01/2024 | 0 | Resource Division | 17.38 | 0 | 0
398 | Northern Mechanical |  | New Service Connection Charge for BASUSUBA, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 4003391439 Reference ID : 403203861 |  |  | BILL/00234/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
399 | Northern Mechanical |  | Infrastructure development cost for new service connection at BASUSUBA, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 100000105733 Reference ID : 860297933 |  |  | BILL/00235/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.19 | 0 | 0
400 | Northern Mechanical |  | New Service Connection Charge for BASUSUBA, ZONE-I,TW NO-II, KRANTI CCC APPLICATION NO. 4003391463 Reference ID : 403203857 |  |  | BILL/00236/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
401 | Northern Mechanical |  | Infrastructure development cost for new service connection at BASUSUBA, ZONE-I,TW NO-II, KRANTI CCC APPLICATION NO. 100000105734 Reference ID : 860297934 |  |  | BILL/00237/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.29 | 0 | 0
402 | Northern Mechanical |  | New Service Connection Charge for BASUSUBA, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 4003391480 Reference ID : 403203860 |  |  | BILL/00238/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
403 | Northern Mechanical |  | Infrastructure development cost for new service connection at BASUSUBA, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 100000105735 Reference ID : 860297935 |  |  | BILL/00239/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0
404 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
405 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BASUSUBA PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000446/2023-2024 | 1385/NMD | 09/08/2023 | 30 | M/S RATAN KUMAR DASGUPTA AND CO. | 40.19 | 0 | 60
406 | Northern Mechanical |  | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/001008/2024-2025 | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0
407 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000024/2024-2025 | 741/JD | 26/07/2024 | 614 | PRADIP SAHA | 152.08 | 0 | 60
408 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PATKATA ZONE - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000108/2025-2026 | 486/RWS | 29/05/2025 | 30 | EDIFICE ENTERPRISE | 8.05 | 0 | 0
409 | Jalpaiguri Division |  | Construction of different components of Patkata Zone- II Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  |  | ORD/000445/2023-2024 | 1707/JD | 04/12/2023 | 462 | M/S KAMAK ENGINEERS AND CO. | 650.27 | 215.91 | 65
410 | Jalpaiguri Division |  | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000549/2024-2025 | 114/JD | 16/01/2025 | 40 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 23.77 | 0 | 0
411 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 1079/JD | 24/08/2023 | 0 | Resource Division | 42.92 | 0 | 0
412 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 2000/JD | 08/01/2024 | 0 | Resource Division | 26.02 | 0 | 0
413 | Northern Mechanical |  | New Service Connection Charge for PATKATA, ZONE-II, T/W-III under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003365627 Reference ID : 403187095 |  |  | BILL/00308/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0
414 | Northern Mechanical |  | New Service Connection Charge for PATKATA, ZONE-II, T/W-II under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003341677 Reference ID : 403172273 |  |  | BILL/00309/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.2 | 0 | 0
415 | Northern Mechanical |  | New Service Connection Charge for PATKATA, ZONE-II, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341680, Reference ID : 403172795] |  |  | BILL/02148/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.12 | 0 | 0
416 | Northern Mechanical |  | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  |  | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
417 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000464/2023-2024 | 1440/NMD | 10/08/2023 | 30 | SUMON ELECTRICAL | 36.33 | 29.21 | 70
418 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
419 | Northern Mechanical |  | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-II)of PATKATA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  |  | ORD/001704/2023-2024 | 437/SMSD | 28/03/2024 | 7 | M/S PALIDEB ENGINEERING WORKS | 0.73 | 0 | 0
420 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte.(Phase-I) |  | Junior Engineer | ORD/000033/2021-2022 | 07/JSSD | 13/04/2021 | 20 | R.S CONSTRUCTION | 4.13 | 8.24 | 0
421 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting work of pipeline at Yongtong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte.(Phase-II). |  | Junior Engineer | ORD/000034/2021-2022 | 09/JSSD | 13/04/2021 | 20 | M/S PAMPA CONSTRUCTION | 3.52 | 7.01 | 0
422 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of YOUNGTONG T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte |  | Junior Engineer | ORD/000161/2020-2021 | 1080/JD | 15/10/2020 | 45 | ASHIT KUMAR SINGHA | 26.73 | 35.62 | 0
423 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | iep for young tong t.g pwss |  | Junior Engineer | VCH/000377/2021-2022 | 291 | 05/09/2021 | 0 | ASHIT KUMAR SINGHA | 3.74 | 0 | 0
424 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fhtc mohit nagar |  | Junior Engineer | VCH/000526/2022-2023 | BP-2021-22-168 | 29/09/2022 | 0 | M/S DEY & ROY CHOUDHURY | 1.14 | 0 | 0
425 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | supply stesonarry |  | Junior Engineer | VCH/000541/2022-2023 | BP-2021-23-169 | 29/09/2022 | 0 | NEW KUNDU ENTERPRISE | 0.03 | 0 | 0
426 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ADDITIONAL LDS FOR YOUNGTONG T.G PWSS |  | Junior Engineer | VCH/000549/2021-2022 | 338/21-22 | 01/10/2021 | 0 | M/S PAMPA CONSTRUCTION | 0.75 | 0 | 0
427 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PROVIDING FHTC AT YOUNGTONG T.G PWSS |  | Junior Engineer | VCH/001154/2020-2021 | 1102 | 22/01/2021 | 0 | M/S.PAMPA CONSTRACTION | 4.49 | 0 | 0
428 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Paschim Mullickpara Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. |  |  | ORD/000208/2020-2021 | 41/JD | 06/01/2021 | 60 | BALAJI UDDYOG | 36.46 | 30.51 | 1
429 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dakshin Altagram Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. |  |  | ORD/000209/2020-2021 | 51/JD | 08/01/2021 | 60 | UMWELT ENGINEER PRIVATE LIMITED | 38.7 | 66.45 | 1
430 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Maynatali Mouza under Mainatali piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  |  | ORD/000325/2020-2021 | 310/JD | 26/02/2021 | 30 | SANJIT SAHA | 22.93 | 0 | 1
431 | Jalpaiguri Division |  | Construction of Drain, Plinth Protection, Guard wall including Land Development at H/W site and stand posts for samsing T.G W/S/S under Jalpaiguri Division P.H.E.Dte. |  |  | ORD/000891/2021-2022 | 1009/W/JSSD | 10/01/2022 | 20 | SUBIR GHOSH | 4.65 | 4.34 | 1
432 | Jalpaiguri Division |  | fhtc for khalaigram pwss |  |  | VCH/000363/2021-2022 | 348 | 13/09/2021 | 0 | PARESH CHANDRA GUHA | 12 | 0 | 0
433 | Jalpaiguri Division |  | RETROFITTING OF DISTRIBUTION PIPE LINE DAKSHIN DANGA PARAMOUZA |  |  | VCH/001347/2021-2022 | BP-2021-22-444 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 4.77 | 0 | 0
434 | Jalpaiguri Division |  | FHTC DAKSHIN DANGA PARA |  |  | VCH/001348/2021-2022 | BP-2021-22-442 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 2.6 | 0 | 0
435 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at balance portion of Arjimaria Kamalapokhori W/S Scheme in connection with JJM under Jalpaiguri Division, PHE Dte (Part-G). |  | Junior Engineer | ORD/000138/2023-2024 | 707/JD | 13/07/2023 | 30 | M/S R.K SINGHA & SONS | 30.55 | 0 | 90
436 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna including retrofitting of existing LDS under the command area of Dabgram-II piped Water Supply Scheme (South Zone) at Rajganj Block under Jalpaiguri Division, PHE Dte. Phase-I |  | Junior Engineer | ORD/000141/2020-2021 | 1250/JD | 11/11/2020 | 21 | ASIM GUPTA . | 4.32 | 6.09 | 0
437 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Argimaria Kamalapokori Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000166/2020-2021 | 469/RWS | 15/10/2020 | 30 | PINTU DAS | 4.73 | 4.85 | 1
438 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000186/2020-2021 | 1494/JD | 22/12/2020 | 45 | R.S CONSTRUCTION | 23.66 | 23.9 | 1
439 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-D) |  | Junior Engineer | ORD/000193/2020-2021 | 1545/JD | 31/12/2020 | 45 | R.S CONSTRUCTION | 28.69 | 57.89 | 1
440 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Argimaria Kamolapokori piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000200/2020-2021 | 1536/JD | 31/12/2020 | 30 | PRADIP SAHA | 15.67 | 31.2 | 1
441 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Repairing of Pipe Line With Other allied works related to Pipeline Under Luksaan Bazaar water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000392/2020-2021 | 612/JSSD | 18/02/2021 | 20 | MONOTOSH ROY | 4.9 | 9.72 | 0
442 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works at related to FHTC for Arjimaria Kamalapukuri Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000434/2020-2021 | 67/RWS | 12/02/2021 | 10 | R.S CONSTRUCTION | 4.17 | 4.25 | 1
443 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000639/2020-2021 | 19/JD | 14/01/2021 | 60 | BILTU DAS | 36.92 | 0 | 1
444 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing FHTC for arajimaria Kamla Pukhari |  | Junior Engineer | VCH/001171/2021-2022 | BP-2021-22-238 | 23/02/2022 | 0 | R.S CONSTRUCTION | 4.94 | 0 | 0
445 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000025/2021-2022 | 745/JD | 13/05/2021 | 20 | GOURAB GUHA ROY | 14.13 | 14.12 | 1
446 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Ambari Falakata piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000043/2021-2022 | 1069/JD | 02/07/2021 | 21 | PRAHLAD PRASAD SAHA | 4.83 | 0 | 1
447 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000102/2021-2022 | 1340 /JD | 23/08/2021 | 30 | MONTOSH GHOSH | 30.21 | 0 | 1
448 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- V) | Assistant Engineer,HQ | Junior Engineer | ORD/000132/2021-2022 | 1441/JD | 09/09/2021 | 30 | RAGHU DAS | 31.64 | 0 | 1
449 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting with Jal Sapna under the command area of Husludanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-E) | Assistant Engineer,HQ | Junior Engineer | ORD/000233/2022-2023 | 1906/JD | 27/09/2022 | 25 | SWAPAN SAHA | 17.2 | 14.03 | 0
450 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2022-2023 | 702/JD | 17/03/2023 | 45 | SUBIR GHOSH | 52.54 | 0 | 20
451 | Jalpaiguri Division | Jalpaiguri Division | FHTC BARADIGHI WORK | Assistant Engineer,HQ | Junior Engineer | VCH/000288/2022-2023 | BP-2022-23-115 | 17/08/2022 | 0 | PRIYABRATA KARMAKAR | 4.6 | 0 | 0
452 | Jalpaiguri Division | Jalpaiguri Division | FHTC SAMSING TG | Assistant Engineer,HQ | Junior Engineer | VCH/000289/2022-2023 | BP-2022-23-116 | 18/08/2022 | 0 | PINTU DAS | 4.75 | 0 | 0
453 | Jalpaiguri Division | Jalpaiguri Division | FHTC KILKOTE | Assistant Engineer,HQ | Junior Engineer | VCH/000290/2022-2023 | BP-2022-23-118 | 18/08/2022 | 0 | VEDATRAYEE AND CO. | 1.11 | 0 | 0
454 | Jalpaiguri Division | Jalpaiguri Division | FHTC FOR LUKSHAN BAZAR . | Assistant Engineer,HQ | Junior Engineer | VCH/000311/2022-2023 | BP-2022-23-89 | 02/08/2022 | 0 | ANUP SARKAR | 24.13 | 0 | 0
455 | Jalpaiguri Division | Jalpaiguri Division | fhtc for ambari falakata | Assistant Engineer,HQ | Junior Engineer | VCH/000463/2021-2022 |  | 21/10/2021 | 0 | NARAYAN SARKAR | 23.7 | 0 | 0
456 | Jalpaiguri Division | Jalpaiguri Division | LDS AMBARI FALAKATA PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000479/2021-2022 |  | 29/10/2021 | 0 | GOURAB GUHA ROY | 4.72 | 0 | 0
457 | Jalpaiguri Division | Jalpaiguri Division | AMBARIFALAKATA FHTC | Assistant Engineer,HQ | Junior Engineer | VCH/000796/2021-2022 | BP-2021-22-88 | 01/11/2021 | 0 | NARAYAN SARKAR | 23.7 | 0 | 0
458 | Jalpaiguri Division | Jalpaiguri Division | ambarifalakata fhtc | Assistant Engineer,HQ | Junior Engineer | VCH/000810/2021-2022 | BP-2021-22-98 | 16/11/2021 | 0 | GOURAB GUHA ROY | 4.72 | 0 | 0
459 | Jalpaiguri Division | Jalpaiguri Division | AMBARI FALAKATA | Assistant Engineer,HQ | Junior Engineer | VCH/001051/2021-2022 | BP-2021-22-186 | 14/01/2022 | 0 | RAGHU DAS | 31.53 | 0 | 0
460 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi Tea Garden piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-C) | Assistant Engineer,HQ | Junior Engineer | VCH/001154/2021-2022 | BP-2021-22-272 | 22/02/2022 | 0 | R.S CONSTRUCTION | 13.45 | 0 | 0
461 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Songachi T.G. piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte. (PART-D) | Assistant Engineer,HQ | Junior Engineer | VCH/001155/2021-2022 | BP-2021-22-271 | 22/02/2022 | 0 | R.S CONSTRUCTION | 5.04 | 0 | 0
462 | Jalpaiguri Division | Jalpaiguri Division | FHTC AMBARI FALAKATA | Assistant Engineer,HQ | Junior Engineer | VCH/001197/2021-2022 | BP-2021-22-329 | 28/02/2022 | 0 | SAPTASWA SARKAR | 21.58 | 0 | 0
463 | Jalpaiguri Division | Jalpaiguri Division | FHTC DAKSHIN SALBARI | Assistant Engineer,HQ | Junior Engineer | VCH/001254/2021-2022 | BP-2021-22-409 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 4.8 | 0 | 0
464 | Jalpaiguri Division | Jalpaiguri Division | FHTC PURBADURAMARI | Assistant Engineer,HQ | Junior Engineer | VCH/001263/2021-2022 | BP-2021-22-465 | 27/03/2022 | 0 | SIBU DEY | 28.4 | 0 | 0
465 | Jalpaiguri Division | Jalpaiguri Division | FHTC PATKIDAHA | Assistant Engineer,HQ | Junior Engineer | VCH/001380/2021-2022 | BP-2021-22-544 | 31/03/2022 | 0 | PRABIR SHOME | 5.89 | 0 | 0
466 | Jalpaiguri Division | Jalpaiguri Division | FHTC JOGESH CH T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001391/2021-2022 | BP-2021-22-535 | 31/03/2022 | 0 | SANDIP BANIK | 19.98 | 0 | 0
467 | Jalpaiguri Division | Jalpaiguri Division | FHTC RAIPUR T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001406/2021-2022 | BP-2021-22-549 | 31/03/2022 | 0 | ANUP KUMAR KUNDU | 2.19 | 0 | 0
468 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORK FOR DAKSHIN SHALBARI | Assistant Engineer,HQ | Junior Engineer | VCH/001436/2021-2022 | BP-2021-22-409 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 4.8 | 0 | 0
469 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergency repairing of existing pipelines at different locations damaged due to road development works including cleaning chokages of blocked pipelines for smooth running of drinking water under Paschim Salbari (zone-I) water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000179/2022-2023 | 558/RWS | 01/09/2022 | 30 | SAHA CONSTRUCTION | 3.5 | 3.49 | 1
470 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Caron T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000213/2020-2021 | 1548/JD | 31/12/2020 | 45 | SANDIP BANIK | 28.61 | 57.21 | 0
471 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 3 No. 250 mm x 150 mm x 132 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Goralbari Piped Water Supply Scheme (I, II, III) under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2022-2023 | 1217/JD | 26/05/2022 | 30 | JAYANTA GHOSH | 22.7 | 21.88 | 0
472 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Repair works of O.H.R. Pump Houses and Boundary walls .at Goralbari Zone-III Piped Water Supply Scheme Under Jalpaiguri Division PHE Dte. (2nd Call) |  | Junior Engineer | ORD/000154/2023-2024 | 814/RWS | 14/07/2023 | 21 | TAPASH MOHANTA | 4.33 | 0 | 100
473 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting at Barodhighi,CWC Road, Baroghoria, Koharapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000238/2022-2023 | 1890/JD | 22/09/2022 | 30 | MONOJ GHOSH | 26.94 | 26.87 | 100
474 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works including FHTC at Shubhachandi, Futkibari Including FHTC for Garalbari Zone ¿ II . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000274/2021-2022 | 818/RWS | 30/11/2021 | 15 | BISWAJIT BHADURI | 4.38 | 0 | 1
475 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 3 Nos. 20.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc for Rejuvenation of Garalbari water supply scheme (for Zone-I, Zone-II & Zone-III) under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000438/2022-2023 | 678/JD | 16/03/2023 | 45 | D. S. ENTERPRISE | 53.46 | 31.31 | 100
476 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(3 Nos.) including other necessary arrangement for Rejuvenation of Goralbari Piped Water Supply Scheme( Zone-I, Zone-II & Zone-III) under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000491/2022-2023 | 290/RWS | 29/03/2023 | 21 | BAJRANG ENTERPRISE | 5.97 | 0 | 100
477 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Sarkar Para, along PWD Road, Pranabananda Para, Baruapara, Moulani, Konpakri, Berubari More, Dangapara, Dhapganj etc. within Garalbari Zone-III W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000514/2021-2022 | 538/JD | 25/02/2022 | 60 | ASIM GUPTA | 92.47 | 30.02 | 1
478 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Pradhan Para, Choudhury Para, Haripukuri, Uttar & Dakshin Danga para, Jamuri bari and Camperhat within Garalbari Zone-II W/S Scheme under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000515/2021-2022 | 539/JD | 25/02/2022 | 30 | BISWAJIT BHADURI | 29.32 | 0 | 100
479 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Garalbari Zone-I W/S Scheme under Jalpaiguri Division PHE Dte. (Part-E) |  | Junior Engineer | ORD/000541/2021-2022 | 545/JD | 28/02/2022 | 21 | RABINDRANATH DUTTA | 15.82 | 0 | 1
480 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | rep. and renovetion of garalbari zone-ii |  | Junior Engineer | VCH/000045/2022-2023 | BP-2021-22-17 | 26/04/2022 | 0 | ASIT PAUL | 4.35 | 0 | 0
481 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI PWSS |  | Junior Engineer | VCH/000242/2022-2023 | bp2022-23-52 | 08/06/2022 | 0 | BISWAJIT BHADURI | 14.47 | 0 | 0
482 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BHANDANI |  | Junior Engineer | VCH/000250/2022-2023 | BP-2022-23-71 | 04/07/2022 | 0 | DULAL CHOUDHURY | 3.34 | 0 | 0
483 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REP OF PUMP HOUSE FOR GORALBARI PWSS |  | Junior Engineer | VCH/000318/2022-2023 | BP-2022-23-127 | 25/08/2022 | 0 | ASIT PAUL | 0.48 | 0 | 0
484 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RE OF PUMP HOUSE B-WAAL FOR GORALBARI PWSS |  | Junior Engineer | VCH/000323/2022-2023 | bp2022-23 | 25/08/2022 | 0 | PRADIP SAHA | 0.47 | 0 | 0
485 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REP OF PUMP HOUSE FOR GORALBARI PWSS |  | Junior Engineer | VCH/000324/2022-2023 | BP-2022-23-128 | 23/08/2022 | 0 | BISWAJIT BHADURI | 0.42 | 0 | 0
486 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ. GORALBARI PWSS |  | Junior Engineer | VCH/000907/2021-2022 | BP-2021-22-138 | 14/12/2021 | 0 | BISWAJIT BHADURI | 3.12 | 0 | 0
487 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ, GORALBARI |  | Junior Engineer | VCH/000908/2021-2022 | BP-2021-22-139 | 14/12/2021 | 0 | BISWAJIT BHADURI | 2.66 | 0 | 0
488 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ. GORALBARI PWSS |  | Junior Engineer | VCH/000913/2021-2022 | BP-2021-22-136 | 14/12/2021 | 0 | RANJIT KARMAKAR | 4.88 | 0 | 0
489 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORALBARI |  | Junior Engineer | VCH/001204/2021-2022 | BP-2021-22-322 | 28/02/2022 | 0 | DREAM CONSTRACTION | 3.85 | 0 | 0
490 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORAL BARI |  | Junior Engineer | VCH/001205/2021-2022 | BP-2021-22-323 | 28/02/2022 | 0 | RAGHU DAS | 3.87 | 0 | 0
491 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORAL BARI |  | Junior Engineer | VCH/001206/2021-2022 | BP-2021-22-319 | 28/02/2022 | 0 | BISWAJIT BHADURI | 3.85 | 0 | 0
492 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC AUG BAIKUR PART V |  | Junior Engineer | VCH/001317/2021-2022 | BP-2021-22-438 | 26/03/2022 | 0 | MINTU CHAKRABORTY | 78.25 | 0 | 0
493 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REPAIRING H/W GORALBARI ZONE -II |  | Junior Engineer | VCH/001375/2021-2022 | BP-2021-22-538 | 31/03/2022 | 0 | ASIT PAUL | 4.35 | 0 | 0
494 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REPAIRING & RENOVATION OHR GORALBARI ZONE -II |  | Junior Engineer | VCH/001376/2021-2022 | BP-2021-22-539 | 31/03/2022 | 0 | BISWAJIT BHADURI | 3.76 | 0 | 0
495 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REPAIRING & MAINTENANCE GORALBARI WSS |  | Junior Engineer | VCH/001378/2021-2022 | BP-2021-22-537 | 31/03/2022 | 0 | PRADIP SAHA | 4.2 | 0 | 0
496 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI ZONE-I |  | Junior Engineer | VCH/001387/2021-2022 | BP-2021-22-548 | 31/03/2022 | 0 | RABINDRANATH DUTTA | 14.9 | 0 | 0
497 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for GARALBARI , T/W III,ZONE-II under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000079173, Reference ID : 860270383] |  | Junior Engineer | BILL/00506/2023-2024 | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.58 | 0 | 0
498 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for GARALBARI , T/W III,ZONE-II under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003119639, Reference ID : 403023006] |  | Junior Engineer | BILL/00507/2023-2024 | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
499 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for GARALBARI , T/W III,ZONE-III under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000077688, Reference ID : 860269318] |  | Junior Engineer | BILL/00510/2023-2024 | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.89 | 0 | 0
500 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for GARALBARI , T/W III,ZONE-III under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003132474, Reference ID : 403012261] |  | Junior Engineer | BILL/00511/2023-2024 | BP/23-24/56 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
501 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for GARALBARI, ZONE-I , T/W III, under MASKALAIBARI CCC, [APPLICATION NO. 4003154244, Reference ID : 403015424] |  | Junior Engineer | BILL/00588/2023-2024 | BP/23-24/73 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
502 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for GARALBARI, ZONE-I , T/W III, under MASKALAIBARI CCC, [APPLICATION NO. 100000078007, Reference ID : 860269067] |  | Junior Engineer | BILL/00589/2023-2024 | BP/23-24/73 | 11/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 23.18 | 0 | 0
503 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
504 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GARALBARI PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000878/2022-2023 | 342/NMD | 29/03/2023 | 30 | SUMON ELECTRICAL | 31.97 | 31.87 | 100
505 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in Connection with Jal Jeevan Mission under the command area of Ambari Falakata Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000006/2024-2025 | 472/JD | 20/06/2024 | 20 | SUBIR GHOSH | 63.03 | 0 | 0
506 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with Functional Household Tap Connection for Sitaguri of Ambari Falakata Water Supply Scheme i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000372/2022-2023 | 297/JD | 10/02/2023 | 14 | RAGHU DAS | 2.53 | 2.52 | 1
507 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings works in connection with Functional House Hold Tap connection and 4th Pump House under "JAL JEEVAN MISSION " for Boloram, Bandhurngar ,Vandarigacch of Ambari Falakata Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2022-2023 | 702/JD | 17/03/2023 | 45 | SUBIR GHOSH | 52.54 | 4.9 | 20
508 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway including laying pipe line for 5th tubewell at Amabari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte i.c.w. JJM . | Assistant Engineer,HQ | Junior Engineer | ORD/000511/2024-2025 | 1214 | 24/12/2024 | 30 | KANAI LAL SEN | 0 | 0 | 0
509 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000613/2021-2022 | 665/JD | 09/03/2022 | 30 | STAR CONSTRUCTION | 9.34 | 8.09 | 1
510 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300mm x 200mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Ambari Falakata PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000614/2021-2022 | 666/JD | 09/03/2022 | 30 | BONANZA ENTERPRISE | 9.34 | 7.86 | 1
511 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000616/2023-2024 | 2313/JD | 07/02/2024 | 30 | SOUVIK SAHA | 8.28 | 7.19 | 100
512 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 4th tubewell site at Ambari Falakata piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000617/2023-2024 | 2314/JD | 07/02/2024 | 30 | ARUP SARKAR | 8.34 | 6.88 | 100
513 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000046/2023-2024 | 1103/JD | 24/08/2023 | 0 | Resource Division | 2.95 | 0 | 0
514 | Central Drilling | Jalpaiguri Division | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ambari Falakata W/S Scheme (T/W-I ), Rajganj Block under Jalpaiguri District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000160/2023-2024 | 1343/CDD | 13/09/2023 | 180 | PADMA ENGINEERING & CO. | 16.67 | 8.37 | 100
515 | Central Drilling | Jalpaiguri Division | Providing drilling crews for construction of Tube Well (250mmX150mmX 127 Mtrs depth) by Utilizing Departmental Machineries for Ambari Falakata W/S Scheme (T/W-II ), Rajganj Block under Jalpaiguri District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000503/2022-2023 | 1777/CDD | 02/01/2023 | 450 | PADMA ENGINEERING & CO. | 12.19 | 11.23 | 100
516 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 4003135750 ; Reference ID : 403001370] | Assistant Engineer,HQ | Junior Engineer | BILL/00012/2023-2024 | BP/23-24/30 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
517 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 100000076455 ; Reference ID : 860267595] | Assistant Engineer,HQ | Junior Engineer | BILL/00013/2023-2024 | BP/23-24/45 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0
518 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC [APPLICATION NO. 4003135787 ; Reference ID : 403001372] | Assistant Engineer,HQ | Junior Engineer | BILL/00014/2023-2024 | BP/23-24/30 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
519 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC [APPLICATION NO. 100000076457 ; Reference ID : 860267597] | Assistant Engineer,HQ | Junior Engineer | BILL/00015/2023-2024 | BP/23-24/45 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0
520 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC, [APPLICATION NO. 100000076455, Reference ID : 860267595] | Assistant Engineer,HQ | Junior Engineer | BILL/00466/2023-2024 |  | 07/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0
521 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000076457, Reference ID : 860267597] | Assistant Engineer,HQ | Junior Engineer | BILL/00467/2023-2024 |  | 07/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0
522 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for AMBARI FALAKATA, T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000087936, Reference ID : 860279647] | Assistant Engineer,HQ | Junior Engineer | BILL/01161/2023-2024 | BP/23-24/145 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.92 | 0 | 0
523 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for AMBARI FALAKATA, T/W IV, under FULBARIHAT CCC, [APPLICATION NO. 100000087938, Reference ID : 860279649] | Assistant Engineer,HQ | Junior Engineer | BILL/01162/2023-2024 | BP/23-24/145 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.1 | 0 | 0
524 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AMBARI FALAKATA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000750/2022-2023 | 50/NMD | 24/01/2023 | 30 | SAIKAT SINHA | 11.68 | 10.06 | 100
525 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF AMBARI FALAKATA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000751/2022-2023 | 51/NMD | 24/01/2023 | 30 | BONANZA ENTERPRISE | 11.68 | 11.65 | 100
526 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of CHAKIAVITA piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000020/2021-2022 | 754/JD | 13/05/2021 | 21 | ANUP SARKAR | 23.75 | 0 | 1
527 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000100/2021-2022 | 1339/JD | 23/08/2021 | 30 | PRADIP SAHA | 30.16 | 25.87 | 1
528 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chakiavita Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase- III) | Assistant Engineer,HQ | Junior Engineer | ORD/000110/2021-2022 | 1404/JD | 03/09/2021 | 30 | SAPTASWA SARKAR | 30.86 | 1.79 | 1
529 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna within the area of Chakiavita and Kamarvita village under the command area of Chakiavita piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000270/2021-2022 | 2045/JD | 07/12/2021 | 21 | BARUN KUMAR DUTTA | 39.68 | 32.95 | 1
530 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with Functional House Hold Tap connection under "JAL SWAPNA" for Baniapara of Chakiavita Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000283/2021-2022 | 1827/JD | 18/11/2021 | 21 | JAYDEB SAHA | 11.32 | 0 | 1
531 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works related to FHTC inconnection with Jalsapna at different locations of Chanadipa and Madhya Salbari Mouza of Dakshin Salbari water Supply Scheme under Jalpaiguri Division , P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000518/2021-2022 | 163/RWS | 28/02/2022 | 15 | NARAYAN SARKAR | 4.47 | 4.49 | 1
532 | Jalpaiguri Division | Jalpaiguri Division | FHTC ENGO | Assistant Engineer,HQ | Junior Engineer | VCH/000324/2021-2022 |  | 01/10/2021 | 0 | BIMAN DAS | 2.2 | 0 | 0
533 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000472/2021-2022 |  | 29/10/2021 | 0 | PRADIP SAHA | 25.87 | 0 | 0
534 | Jalpaiguri Division | Jalpaiguri Division | RETREOFITTING WORK FOR BOAL MARI | Assistant Engineer,HQ | Junior Engineer | VCH/000476/2021-2022 |  | 29/10/2021 | 0 | KANAI LAL SEN | 9.37 | 0 | 0
535 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORK FOR ARAGI GORALBARI | Assistant Engineer,HQ | Junior Engineer | VCH/000483/2021-2022 |  | 29/10/2021 | 0 | NARAYAN CHAKRABORTY | 4.84 | 0 | 0
536 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORK FOR ARAJI GORALBARI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000484/2021-2022 |  | 29/10/2021 | 0 | SAPTASWA SARKAR | 11.02 | 0 | 0
537 | Jalpaiguri Division | Jalpaiguri Division | CHAKIAVITA FHTC | Assistant Engineer,HQ | Junior Engineer | VCH/000797/2021-2022 | BP-2021-22-111 | 16/11/2021 | 0 | SAPTASWA SARKAR | 4.86 | 0 | 0
538 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000799/2021-2022 | BP-2021-22-109 | 16/11/2021 | 0 | SAPTASWA SARKAR | 4.37 | 0 | 0
539 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000800/2021-2022 | BP-2021-22-112 | 16/11/2021 | 0 | NARAYAN CHAKRABORTY | 4.84 | 0 | 0
540 | Jalpaiguri Division | Jalpaiguri Division | fhtc chakiavita | Assistant Engineer,HQ | Junior Engineer | VCH/000808/2021-2022 | BP-2021-22-95 | 16/11/2021 | 0 | KANAI LAL SEN | 4.59 | 0 | 0
541 | Jalpaiguri Division | Jalpaiguri Division | fhtc chakiavita | Assistant Engineer,HQ | Junior Engineer | VCH/000809/2021-2022 | BP-2021-22-96 | 16/11/2021 | 0 | KANAI LAL SEN | 4.78 | 0 | 0
542 | Jalpaiguri Division | Jalpaiguri Division | CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/000922/2021-2022 | BP-2021-22-116 | 03/12/2021 | 0 | SAPTASWA SARKAR | 3.98 | 0 | 0
543 | Jalpaiguri Division | Jalpaiguri Division | FHTC CHAKIAVITA | Assistant Engineer,HQ | Junior Engineer | VCH/001096/2021-2022 | BP-2021-22-167 | 14/01/2022 | 0 | SAPTASWA SARKAR | 29.39 | 0 | 0
544 | Jalpaiguri Division | Jalpaiguri Division | FHTC JITI | Assistant Engineer,HQ | Junior Engineer | VCH/001185/2021-2022 | BP-2021-22-280 | 23/02/2022 | 0 | CALCON CONSTRUCTIONS | 22.07 | 0 | 0
545 | Jalpaiguri Division | Jalpaiguri Division | FHTC MADHYA KHUTTIMARI | Assistant Engineer,HQ | Junior Engineer | VCH/001187/2021-2022 | BP-2021-22-280 | 23/02/2022 | 0 | KAMALESH SEN | 9.42 | 0 | 0
546 | Jalpaiguri Division | Jalpaiguri Division | FHTC RIABARI | Assistant Engineer,HQ | Junior Engineer | VCH/001251/2021-2022 | BP-2021-22-394 | 22/03/2022 | 0 | SAPTASWA SARKAR | 5.63 | 0 | 0
547 | Jalpaiguri Division | Jalpaiguri Division | FHTC RIABARI TG PWSS (PHASE-II) | Assistant Engineer,HQ | Junior Engineer | VCH/001294/2021-2022 | BP-2021-22-394 | 22/03/2022 | 0 | SAPTASWA SARKAR | 5.63 | 0 | 0
548 | Jalpaiguri Division | Jalpaiguri Division | FHTC NAKHATI T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001302/2021-2022 | BP-2021-22-348 | 08/03/2022 | 0 | R.S CONSTRUCTION | 4.81 | 0 | 0
549 | Jalpaiguri Division | Jalpaiguri Division | FHTC JOGESH CHANDRA T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001350/2021-2022 | BP-2021-22-357 | 09/03/2022 | 0 | M/S SURAJIT DEY AND CO. | 28.14 | 0 | 0
550 | Jalpaiguri Division | Jalpaiguri Division | FHTC BHANGAMALI WSS | Assistant Engineer,HQ | Junior Engineer | VCH/001358/2021-2022 | BP-2021-22-496 | 29/03/2022 | 0 | RABINDRANATH DUTTA | 16.94 | 0 | 0
551 | Jalpaiguri Division | Jalpaiguri Division | CONST RCC JURANTI T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001365/2021-2022 | BP[-2021-22-463 | 27/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 3.43 | 0 | 0
552 | Jalpaiguri Division | Jalpaiguri Division | FHTC BARADIGHI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001366/2021-2022 | BP-2021-22-476 | 28/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 41.29 | 0 | 0
553 | Jalpaiguri Division | Jalpaiguri Division | FHTC AWC IN MAYNAGURI BLOCK | Assistant Engineer,HQ | Junior Engineer | VCH/001389/2021-2022 | BP-2021-22-502 | 30/03/2022 | 0 | DREAM CONSTRUCTION | 4.84 | 0 | 0
554 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 300 mm x 200 mm x 123 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Boalmari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000062/2022-2023 | 1231/JD | 02/06/2022 | 30 | JAYANTA GHOSH | 17.43 | 16.72 | 0
555 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000300/2021-2022 | 73/JD | 06/01/2022 | 60 | NARESH SEN | 11.21 | 11.2 | 0
556 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000301/2021-2022 | 42/JD | 04/01/2022 | 60 | NARESH SEN | 11.16 | 10.95 | 0
557 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Boalmari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000428/2022-2023 | 624/JD | 13/03/2023 | 45 | KANAI LAL SEN | 33.83 | 30.02 | 100
558 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Maintenance O.H.R.Boundary walls and pump house for rejuvenation of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000694/2021-2022 | 212/RWS | 11/03/2022 | 30 | NARAYAN CHAKRABORTY | 4.8 | 4.91 | 1
559 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000050/2023-2024 | 1101/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0
560 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BOALMARI, T/W No - III W/S Scheme, under HALDIBARI CCC |  | Junior Engineer | BILL/00709/2022-2023 | BP/23-24/02 | 18/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
561 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BOALMARI, T/W No - III W/S Scheme, under HALDIBARI CCC |  | Junior Engineer | BILL/00711/2022-2023 | BP/23-24/02 | 18/04/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.15 | 0 | 0
562 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BOALMARI (REJU) W/S Scheme, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 4003078086, Reference ID : 402978692] |  | Junior Engineer | BILL/00779/2022-2023 | BP/22-23/167 | 28/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
563 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BOALMARI (REJU) W/S Scheme, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO.100000073857, Reference ID : 860264957] |  | Junior Engineer | BILL/00780/2022-2023 | BP/22-23/167 | 28/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.92 | 0 | 0
564 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BOALMARI PWSS, TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000872/2022-2023 | 336/NMD | 29/03/2023 | 30 | DEY ENTERPRISE(MALDA) | 20.32 | 20.29 | 100
565 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000138/2022-2023 | 1442/JD | 20/07/2022 | 45 | SADHAN KARMAKAR | 15.34 | 13.83 | 0
566 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 4th tube well site of Rejuvenation of Dwarikamari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000141/2022-2023 | 1447/JD | 20/07/2022 | 45 | SADHAN KARMAKAR | 15.34 | 14.29 | 0
567 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Shifting of Pipeline damaged due to construction of Rest area and Truck lay bye by the NHAI in between Maynaguri BDO Office and Tekatuli for Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000198/2022-2023 | 1739/JD | 08/09/2022 | 21 | BARUN KUMAR DUTTA | 6.49 | 6.29 | 1
568 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Dwarikamari Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000273/2022-2023 | 2010/JD | 01/11/2022 | 15 | ABHIJIT SARKAR | 5.77 | 4.43 | 1
569 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Dwarikamari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000466/2021-2022 | 2285JD | 31/12/2021 | 30 | SUBRATA GOSWAMI | 17.42 | 7.23 | 1
570 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000483/2021-2022 | 2216/JD | 27/12/2021 | 60 | BARUN KUMAR DUTTA | 11.45 | 11.47 | 1
571 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Dwarikamari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000484/2021-2022 | 2217/JD | 27/12/2021 | 60 | PINTU DAS | 11.44 | 11.42 | 1
572 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | TUBE WELL BILL |  | Junior Engineer | VCH/001151/2021-2022 | BP-2021-22-266 | 16/02/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 45.75 | 0 | 0
573 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF DWARIKAMARI (TW-I) PWSS UNDER CDD, PHE DTE. |  | Junior Engineer | ORD/000178/2021-2022 | 722/ CDD | 05/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.57 | 9.53 | 0
574 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF DWARIKAMARI (TW-II) PWSS UNDER CDD, PHE DTE. |  | Junior Engineer | ORD/000180/2021-2022 | 739/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.57 | 7.61 | 0
575 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL MOBILISATION OF ALL MACHINERIES & ACCESSORIES INCLUDING LOADING & UNLOADING FROM STORE TO DRILLING SITE DWARIKAMARI (TW-I) PWSS. |  | Junior Engineer | ORD/000183/2021-2022 | 457/CMSD-II (D) | 08/10/2021 | 10 | PADMA ENGINEERING & CO. | 0.46 | 0.37 | 0
576 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Charges for shifting of LTOH Line for Dwarikamari P/H -I site under MAYNAGURI CCC APPLICATION NO. 100000120271 Reference ID : 860314461 |  | Junior Engineer | BILL/01400/2024-2025 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.01 | 0 | 0
577 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for augmentation of DWARIKAMARI W/S Scheme at T/W No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000001/2022-2023 | 205/NMD | 04/04/2022 | 21 | PRATIK ROY | 2.16 | 2.16 | 0
578 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for augmentation of DWARIKAMARI W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000002/2022-2023 | 204/NMD | 04/04/2022 | 21 | M/S ANJALI ENTERPRISE | 2.16 | 2.16 | 0
579 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of DWARIKAMARI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000009/2022-2023 | 277/NMD | 26/04/2022 | 30 | M/S PARITOSH BHOWMICK AND CO. | 8.37 | 8.37 | 0
580 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of DWARIKAMARI PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000010/2022-2023 | 278/NMD | 26/04/2022 | 30 | SUMON ELECTRICAL | 8.35 | 8.35 | 0
581 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/05/2024 to 31/07/2024 = 3 Months. |  | Junior Engineer | ORD/000014/2024-2025 | 827/HQ/NMD | 30/04/2024 | 92 | UTTAM PAUL | 0.95 | 0 | 100
582 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Air conditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/05/2025 to 31/07/2025 = 3 Months. |  | Junior Engineer | ORD/000139/2025-2026 | 1047/HQ/NMD | 30/04/2025 | 92 | UTTAM PAUL | 0.45 | 0 | 0
583 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/08/2024 to 31/10/2024 = 3 Months. |  | Junior Engineer | ORD/000197/2024-2025 | 1306/HQ/NMD | 31/07/2024 | 92 | UTTAM PAUL | 0.95 | 0 | 0
584 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte |  | Junior Engineer | ORD/000985/2023-2024 | 1734/HQ/NMD | 30/10/2023 | 92 | UTTAM PAUL | 0.95 | 0.93 | 100
585 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/02/2025 to 30/04/2025 = 3 Months. |  | Junior Engineer | ORD/001107/2024-2025 | 115/HQ/NMD | 17/01/2025 | 90 | UTTAM PAUL | 0.45 | 0 | 0
586 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte Vehicle No. WB 73 G 6590 01/02/2024 to 30/04/2024 = 3 Months. |  | Junior Engineer | ORD/001137/2023-2024 | 430/HQ/NMD | 31/01/2024 | 90 | UTTAM PAUL | 0.95 | 0 | 100
587 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for T/W No. III of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 100000052514, Reference ID : 860241674 |  | Junior Engineer | VCH/000251/2022-2023 | BP/2022-23/21 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.4 | 0 | 0
588 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. IV of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 4002932370, Reference ID : 402825217 |  | Junior Engineer | VCH/000252/2022-2023 | BP/2022-23/21 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
589 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. III of DWARIKAMARI under MAYNAGURI CCC, APPLICATION NO. 4002932367, Reference ID : 402825216 |  | Junior Engineer | VCH/000253/2022-2023 | BP/2022-23/21 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
590 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF ALL TYPES OF PETROLEUM PRODUCTS |  | Junior Engineer 2 | BILL/00354/2022-2023 | BP-2023-24-112 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 1.03 | 0 | 0
591 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte. |  | Junior Engineer 2 | BILL/00391/2024-2025 | BP-2024-25-242 | 26/07/2024 | 0 | FILL & SMILE | 0.29 | 0 | 0
592 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply mobil to vehicle no WB 71 A 5774 |  | Junior Engineer 2 | BILL/00392/2024-2025 | BP-2024-25-241 | 26/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
593 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF DIFFERENT STATINARY ITEMS FOR OFFICE USE UNDER JALPAIGURI DIVISION P.H.E DTE. |  | Junior Engineer 2 | BILL/00963/2023-2024 | BP-2023-24-548 | 20/12/2023 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 3.53 | 0 | 0
594 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL (DIESEL) FOR VEHICLES FOR P.H.E JALPAIGURI |  | Junior Engineer 2 | BILL/00985/2023-2024 | BP-2023-24-563 | 05/01/2024 | 0 | FILL & SMILE | 2.6 | 0 | 0
595 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF DIFFERENT STATIONARY ITEMS FOR OFFICE USE UNDER JALPAIGURI R.W.S SUB DIVISION, P.H.E. Dte. |  | Junior Engineer 2 | BILL/01006/2023-2024 | BP-2023-24-573 | 09/01/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.21 | 0 | 0
596 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL BILL FOR GOVT. VEHICLE FOR THE MONTH OF NOVEMBER-2023 |  | Junior Engineer 2 | BILL/01007/2023-2024 | BP-2023-24-571 | 09/01/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0
597 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) |  | Junior Engineer 2 | BILL/01016/2023-2024 | BP-2023-24-574 | 09/01/2024 | 0 | APIKUL ALI | 0.37 | 0 | 0
598 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  | Junior Engineer 2 | BILL/01017/2023-2024 | BP-2023-24-575 | 09/01/2024 | 0 | SOUMEN GHOSH | 0.68 | 0 | 0
599 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & lubricant for EXECUTIVE ENGINEER , P.H.E Dte. JALPAIGURI |  | Junior Engineer 2 | BILL/01018/2023-2024 | BP-2023-24-578 | 10/01/2024 | 0 | FILL & SMILE | 0.83 | 0 | 0
600 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Extension of pipe lines at different locations and provision of a new by pass line near NBSTC Bus Depot to facilitate FHTC L.c.w. JJM under Augmentation of Maynaguri Water Supply Scheme, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000007/2023-2024 | 331/RWS | 10/04/2023 | 14 | ARUP SARKAR | 2.96 | 2.96 | 100
601 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Replacement of old damaged pipe by new HDPE Pipe line at Sahidgarh area, Ward no. 15 under Augmentation of Maynaguri Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000008/2023-2024 | 333/RWS | 10/04/2023 | 21 | SUKES BASU MAJUMDAR | 4.95 | 5.06 | 100
602 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution line crossing through Bridge and main distribution connections at Augmentation of Maynaguri Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000095/2024-2025 | 814/RWS | 22/08/2024 | 30 | M/S SURAJIT DEY AND CO. | 8.68 | 0 | 100
603 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall, Pump House and Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60M x 3.00M) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000126/2022-2023 | 1392/JD | 05/07/2022 | 30 | SUKES BASU MAJUMDAR | 77.4 | 63.44 | 1
604 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 300 mm x 200 mm x 128 m deep Rig Bored tubewell by Reverse Rotary method of drilling for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer 2 | ORD/000127/2022-2023 | 1393/JD | 05/07/2022 | 21 | B.M CONSTRUCTION | 19.95 | 19.62 | 1
605 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Rig approach with partial land development for 1st site & 2nd site under Maynaguri piped Water Supply Scheme within Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer 2 | ORD/000183/2022-2023 | 562/RWS | 01/09/2022 | 15 | B.M CONSTRUCTION | 3.56 | 3.54 | 1
606 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of new pipe line beside diversion of PWD road (damaged by PWD for connection of sasan road culvert under Maynaguri Water Supply Scheme (Zone-I). |  | Junior Engineer 2 | ORD/000184/2022-2023 | 563/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 1.16 | 1.03 | 1
607 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  | Junior Engineer 2 | ORD/000275/2022-2023 | 640/RWS | 21/10/2022 | 30 | M/S SURAJIT DEY AND CO. | 4 | 4 | 0
608 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System with higher dia HDPE pipe to promot Augmentation of Maynaguri (Zone-I) Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. (Part-B) |  | Junior Engineer 2 | ORD/000276/2022-2023 | 641/RWS | 21/10/2022 | 30 | M/S SURAJIT DEY AND CO. | 3.27 | 2.18 | 0
609 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Bleaching Powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/000290/2022-2023 | 13/RWS | 03/11/2022 | 92 | BHOWMIK ENTERPRISES | 0.4 | 0.4 | 0
610 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MAYNAGURI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer 2 | ORD/000333/2021-2022 | 205/JD | 24/01/2022 | 120 | SUKES BASU MAJUMDAR | 97.41 | 94.45 | 1
611 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System and Functional House Hold Connection for Augmentation of Maynaguri (Zone-I) Piped Water Supply Scheme Block- Maynaguri, Dist. Jalpaiguri. |  | Junior Engineer 2 | ORD/000349/2021-2022 | 225/JD | 25/01/2022 | 1224 | M/S SURAJIT DEY AND CO. | 197.12 | 107.65 | 100
612 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System and Functional House Hold Tap Connection for Augmentation of Maynaguri (Zone-II) Piped Water Supply Scheme. Block- Maynaguri. District - Jalpaiguri. |  | Junior Engineer 2 | ORD/000350/2021-2022 | 226/JD | 25/01/2022 | 1224 | M/S SURAJIT DEY AND CO. | 197.94 | 66.23 | 100
613 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connection for Augmentation of Maynaguri (Zone-I) piped Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri |  | Junior Engineer 2 | ORD/000378/2022-2023 | 243/JD | 04/02/2023 | 30 | ARATI CONSTRUCTION | 3.57 | 3.56 | 100
614 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (IEP) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. in addition ancillary pipe line works (i.e. CIDF pipe line, construction of valve chamber etc.) at Head Work Site Augmentation of Maynaguri (Zone-II) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000474/2021-2022 | 397/JD | 10/02/2022 | 45 | SUKES BASU MAJUMDAR | 39.13 | 12.95 | 1
615 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation work order for "Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01/02/2025 to 31/07/2025)" |  | Junior Engineer 2 | ORD/000673/2024-2025 | 76/RWS | 30/01/2025 | 181 | ASHIM SARKAR | 0.88 | 0.44 | 32
616 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 2nd Tube well site of Augmentation Maynaguri (Zone-I) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000708/2021-2022 | 2208/JD | 27/12/2021 | 60 | PRIYABRATA KARMAKAR | 11.45 | 7.78 | 1
617 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Alam) for I.E.P at Head Work site under Maynaguri W/S/S for 3 months under Jalpaiguri Division P.H.E. Dte. Period from - 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001055/2021-2022 | 08/RWS | 04/01/2022 | 90 | SUKES BASU MAJUMDAR | 0.67 | 0.67 | 1
618 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001056/2021-2022 | 07/RWS | 04/01/2022 | 90 | SUKES BASU MAJUMDAR | 0.73 | 0.73 | 1
619 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Bleaching powder) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001057/2021-2022 | 11/RWS | 04/01/2022 | 90 | SADHAN KARMAKAR | 0.4 | 0.4 | 1
620 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Alam) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001058/2021-2022 | 10/RWS | 04/01/2022 | 90 | A.P CONSTRUCTION | 0.24 | 0.24 | 1
621 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different Chemicals (Lime) for I.E.P at head work site under Maynaguri W/S/S for Three months under Jalpaiguri Division P.H.E. Dte. Period form 01.01.2022 to 31.03.2022 |  | Junior Engineer 2 | ORD/001059/2021-2022 | 09/RWS | 04/01/2022 | 90 | PROFULLA GHOSH | 0.26 | 0.26 | 1
622 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000005/2021-2022 | 178/JD | 21/01/2022 | 0 | Resource Division | 69.48 | 0 | 0
623 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000079/2024-2025 | 2210/JD | 01/12/2024 | 0 | Resource Division | 44.3 | 0 | 0
624 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of fuel |  | Junior Engineer 2 | VCH/000595/2022-2023 | BP-2022-23-375 | 18/11/2022 | 0 | FILL & SMILE | 0.29 | 0 | 0
625 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | KAYING OF PIPELINE FOR MADHABDANGA PWSS |  | Junior Engineer 2 | VCH/001258/2021-2022 | BP-2021-22-404 | 23/03/2022 | 0 | M/S SIBU DEY AND CO. | 2.65 | 0 | 0
626 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC RAMSAI PART - II |  | Junior Engineer 2 | VCH/001315/2021-2022 | BP-2021-22-427 | 25/03/2022 | 0 | ASHIT KUMAR SINGHA | 64.85 | 0 | 0
627 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST RCC KHALAIGRAM |  | Junior Engineer 2 | VCH/001397/2021-2022 | BP-2021-22-555 | 31/03/2022 | 0 | DULAL CHOUDHURY | 4.48 | 0 | 0
628 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING OF NEW PIPE LINE CHAMURCHI BAZAR W/S/S |  | Junior Engineer 2 | VCH/001405/2021-2022 | BP-2021-22-556 | 31/03/2022 | 0 | NARAYAN CHANDRA SAHA | 13.02 | 0 | 0
629 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST MAYNAGURI PWSS |  | Junior Engineer 2 | VCH/001441/2021-2022 | BP-2021-22-484 | 29/03/2022 | 0 | PRIYA ASSOCITED | 1.69 | 0 | 0
630 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under MAYNAGURI (AUG) W/S Scheme, at ZONE-I, TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer 2 | ORD/000065/2022-2023 | 440/NMD | 14/06/2022 | 21 | UTTAM PAUL | 2.99 | 2.99 | 0
631 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under MAYNAGURI (AUG) W/S Scheme, at ZONE-I, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer 2 | ORD/000066/2022-2023 | 441/NMD | 14/06/2022 | 21 | M/S P.P. ELECTRICALS | 2.99 | 2.99 | 0
632 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of MAYNAGURI (ZONE-I) PWSS, at TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer 2 | ORD/000079/2022-2023 | 537/NMD | 08/07/2022 | 30 | ALPHA ENTERPRISE | 8.6 | 8.6 | 0
633 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for augmentation of MAYNAGURI (ZONE-I) PWSS, at TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer 2 | ORD/000080/2022-2023 | 538/NMD | 08/07/2022 | 30 | B.B. CONCERNED | 8.6 | 8.6 | 0
634 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for T/W No. I of MAYNAGURI SUPER MARKET under MAYNAGURI CCC, APPLICATION NO. 100000052512, Reference ID : 860241672 |  | Junior Engineer 2 | VCH/000250/2022-2023 | BP/2022-23/20 | 23/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.65 | 0 | 0
635 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. II of MAYNAGURI NEAR DHARMASHALA under MAYNAGURI CCC, APPLICATION NO. 4002932365, Reference ID : 402825215 |  | Junior Engineer 2 | VCH/000254/2022-2023 | BP/2022-23/22 | 28/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
636 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No.I of MAYNAGURI SUPER MARKET under MAYNAGURI CCC, APPLICATION NO. 4002930314, Reference ID : 402824634 |  | Junior Engineer 2 | VCH/000255/2022-2023 | BP/2022-23/22 | 28/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
637 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for TW-II, of MAYNAGURI NEAR DHARMASAKA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000057038 , Reference ID : 860246648] |  | Junior Engineer 2 | VCH/000773/2022-2023 | BP/2022-23/29 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
638 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Nagaisuree Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000008/2022-2023 | 869/JD | 04/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 12.19 | 0
639 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different for Rejuvenation of Nagaisuree Tea Garden Piped Water Supply Scheme i.e. 2 (Two) Nos Pump House, Boundary Wall, Rising Main including Functional Household Tap Connection (FHTC) etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000182/2025-2026 | 2165/JD | 30/10/2025 | 45 | PRASENJIT BASAK | 30.87 | 0 | 0
640 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000269/2022-2023 | 217/JSSD | 16/09/2022 | 60 | ARUP SARKAR | 4.65 | 4.65 | 100
641 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Nagaisuree TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000270/2022-2023 | 216/JSSD | 16/09/2022 | 60 | BAJRANG ENTERPRISE | 4.65 | 4.65 | 0
642 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works for laying Distribution System of Rejuvenation of Nagaisuree T.G. Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000700/2021-2022 | 767/JD | 23/03/2022 | 1145 | SADHAN KARMAKAR | 64.75 | 50.42 | 60
643 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGAISUREE TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000765/2022-2023 | 71/NMD | 27/01/2023 | 30 | TALUKDER ENTERPRISE | 11.31 | 11.31 | 100
644 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGAISUREE TG AREA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000766/2022-2023 | 72/NMD | 27/01/2023 | 30 | M/S PALIDEB ENGINEERING WORKS | 10.76 | 10.76 | 80
645 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NAGAISUREE TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 4002964334, Reference ID :402851949] |  | Junior Engineer | VCH/000975/2022-2023 | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
646 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at NAGAISUREE TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 100000059931, Reference ID : 860249351] |  | Junior Engineer | VCH/000976/2022-2023 | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.16 | 0 | 0
647 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NAGAISUREE TEA GARDEN NEAR MANDAKINI FIELD W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 4002964306, Reference ID :402851943] |  | Junior Engineer | VCH/000977/2022-2023 | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
648 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at NAGAISUREE TEA GARDEN NEAR MANDAKINI FIELD W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 100000059480, Reference ID : 860249200] |  | Junior Engineer | VCH/000978/2022-2023 | BP/22-23/90 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0
649 | Jalpaiguri Division | Jalpaiguri Division | Replacement of existing defunct sluice valve for Gairkata Water Supply Scheme at Banarhat Development block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000027/2023-2024 | 127/JD | 28/04/2023 | 7 | SHANTI CONSTRUCTION | 1.66 | 1.49 | 100
650 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation Gairkata P.W.S.S under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000049/2022-2023 | 1191/JD | 20/05/2022 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.65 | 4.65 | 100
651 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including providing CI/DI Rising Main connection and providing FHTC in connection with JJM for Augmentation of Gairkata Piped Water Supply Scheme at Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000442/2022-2023 | 695/JD | 17/03/2023 | 730 | M/S R.N. TRADERS | 333.21 | 58.05 | 8
652 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Sluice Valve, Pathway, Drain etc. at 3rd Tube Well Site of Gairkata Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000495/2024-2025 | 2057/JD | 25/11/2024 | 401 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 8.51 | 0 | 60
653 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Gairkata PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000563/2021-2022 | 455/JD | 18/02/2022 | 21 | MAA ENTERPRISES | 7.93 | 5.71 | 100
654 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000017/2021-2022 | 554/JD | 01/03/2022 | 0 | Resource Division | 14.26 | 0 | 0
655 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003196195, Reference ID : 403048167] | Assistant Engineer,HQ | Junior Engineer | BILL/00569/2023-2024 | BP/23-24/70 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.42 | 0 | 0
656 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for GAIRKATA, T/W I, under DHUPGURI CCC [APPLICATION NO. 4003208335 ; Reference ID : 403057217] | Assistant Engineer,HQ | Junior Engineer | BILL/00990/2023-2024 | BP/23-24/93 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0
657 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for GAIRKATA, T/W II, under DHUPGURI CCC [APPLICATION NO. 4003208338 ; Reference ID : 403057218] | Assistant Engineer,HQ | Junior Engineer | BILL/00991/2023-2024 | BP/23-24/93 | 29/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0
658 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0
659 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0
660 | Jalpaiguri Division | Jalpaiguri Division | Laying of New Pipeline adjacent to the National Highway for implementation of Jalswapa programme along with minor retrofitting works(laying of parallel line)within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000162/2022-2023 | 1448/JD | 20/07/2022 | 15 | JAYDEB SAHA | 4.85 | 3.46 | 1
661 | Jalpaiguri Division | Jalpaiguri Division | Minor Repairing of Distribution System along with FHTC works under Jalswapna Programme along with other retrofitting works ,chokage removal alog ,repairing of partially damaged C.I.D.F delivery main with other ancillary works within the command area of Devpara T.G.P.W.S.S under Jalpaiguri Division, P.H.E.Dte.(Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000216/2022-2023 | 1806/JD | 14/09/2022 | 21 | JAYDEB SAHA | 4.84 | 4.85 | 1
662 | Jalpaiguri Division | Jalpaiguri Division | Construction of One no Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Rejuvenation of Debpara TG Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000276/2023-2024 | 1268/JD | 13/09/2023 | 45 | BOSE ENTERPRISE | 17.67 | 4.9 | 20
663 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of old demage distribution system and other allied work related to pipe line at gara line area of Devpara PWSS in conection with Jal Jeevan Mission Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000315/2024-2025 | 1652/JD | 29/10/2024 | 20 | JAYDEB SAHA | 10.16 | 4.46 | 70
664 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000041/2024-2025 | 2066/JD | 25/11/2024 | 0 | Resource Division | 0.67 | 0 | 0
665 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DEBPARA TEA GARDEN, T/W III, under BANARHAT CCC [APPLICATION NO. 4003193586 ; Reference ID : 403045949] | Assistant Engineer,HQ | Junior Engineer | BILL/00997/2023-2024 | BP/23-24/96 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
666 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for DEBPARA TEA GARDEN, T/W III, under BANARHAT CCC [APPLICATION NO. 100000083812 ; Reference ID : 860275312] | Assistant Engineer,HQ | Junior Engineer | BILL/00998/2023-2024 | BP/23-24/96 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.2 | 0 | 0
667 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DEBPARA TG PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000453/2023-2024 | 1392/NMD | 09/08/2023 | 30 | UTTAM PAUL | 12.15 | 0 | 60
668 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000004/2022-2023 | 881/JD | 05/04/2022 | 1214 | CALCON CONSTRUCTIONS | 234.41 | 104.98 | 75
669 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with Providing Functional Household Tap Connection with Jalswapna for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000005/2022-2023 | 880/JD | 05/04/2022 | 1367 | M/S SURAJIT DEY AND CO. | 275.87 | 134.75 | 70
670 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Oodlabari (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/000040/2022-2023 | 1067/JD | 28/04/2022 | 979 | TARAKESWAR PRASAD | 84.41 | 56.54 | 70
671 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at HW site of Aug. of Oodlabari PWSS (Z-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000088/2025-2026 | 101/JSSD | 30/05/2025 | 30 | PRIYABRATA KARMAKAR | 6.59 | 0 | 0
672 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
673 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000104/2022-2023 | 80/JSSD | 22/07/2022 | 20 | BIMAN DAS | 4.57 | 4.38 | 100
674 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Oodlabari (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000105/2022-2023 | 81/JSSD | 22/07/2022 | 20 | BIMAN DAS | 4.57 | 4.39 | 100
675 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari-Kranti Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-III) |  | Junior Engineer | ORD/000246/2022-2023 | 162/JSSD | 24/08/2022 | 30 | BIMAN DAS | 4.77 | 4.76 | 0
676 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from 1st, 2nd & 3rd Tubewell site to OHR for Augmentation of Oodlabari (Zone-II) PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000254/2023-2024 | 1259/JD | 13/09/2023 | 21 | PRITAM DUTTA | 11.83 | 11.73 | 100
677 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Damdim Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-II) |  | Junior Engineer | ORD/000263/2022-2023 | 186/JSSD | 31/08/2022 | 30 | BIMAN DAS | 4.83 | 4.82 | 0
678 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM beside Oodlabari More towards Bagrakote Road under Augmentation of Oodlabari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Ph-I) |  | Junior Engineer | ORD/000264/2022-2023 | 191/JSSD | 02/09/2022 | 30 | BIMAN DAS | 3.83 | 3.81 | 100
679 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 3 Nos. Deep Rig Bored Tube well by Odex - 165 Method of drilling for Augmentation of Oodlabari (Zone-II) Piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000392/2022-2023 | 2527/JD | 30/12/2022 | 30 | MS S R CONSTRUCTION CO | 16.6 | 17.1 | 0
680 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Water Distribution Network for Node No 200 to 130 Along the NH-17 from Ghish to Chell River for Augmentation of Odlabari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000434/2024-2025 | 2312./JD | 11/12/2024 | 45 | SRINIWAS AGARWAL | 16.84 | 0 | 0
681 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Facelifting and Interior furnishing works for Establishment Section and computer Room in ground floor at PHE Division Office under Jal;paiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000557/2023-2024 | 504/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 10.3 | 9.84 | 100
682 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m X2.40 m) size including Sanitary and Plumbing works at 3rd Tube-Well site for Augmentation of Oodlabari (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PH.E. Dte. |  | Junior Engineer | ORD/000656/2022-2023 | 100/JSSD | 25/07/2022 | 45 | BIMAN DAS | 4.75 | 4.64 | 100
683 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60mx2.40m) size including sanitary and plumbing works at 2nd Tube well site for Augmentation of Oolabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000706/2021-2022 | .1051/JSSD | 24/01/2022 | 45 | BIMAN DAS | 4.75 | 4.64 | 100
684 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at H/W site for Augmentation of Oodlabari(Zone-I) piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000809/2023-2024 | 565/JSSD | 05/03/2024 | 30 | SUBHANKAR DEY | 2.76 | 2.73 | 100
685 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No Big dia tube well (200mm x 150mm) by Modified DTH - ODEX method of drilling at H/W Site in Augmentation of Oodlabari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000825/2023-2024 | 2751/JD | 14/03/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 14.01 | 100
686 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing Over Head Reservoir (OHR) with 2 Nos Pump House Head Works Boundary Wall and other ancillary works related to H/W site at Oodlabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001070/2021-2022 | 165/JD | 20/01/2022 | 45 | U TURN CONSTRUCTION | 18.63 | 18.64 | 0
687 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM Over Head Reservoir (OHR) for Augmentation of Oodlabari (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001072/2021-2022 | 1070/JSSD | 25/01/2022 | 20 | SHINE ENGINEERING CONSULTANT | 1.83 | 1.51 | 1
688 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000056/2023-2024 | 1088/JD | 24/08/2023 | 0 | Resource Division | 100.49 | 0 | 0
689 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000082/2024-2025 | 2220/JD | 01/12/2024 | 0 | Resource Division | 20.62 | 0 | 0
690 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for Oldabari, Zone-II, TW No. II, ODLABARI CCC, [APPLICATION NO. 4003145975, Reference ID : 403012266] |  | Junior Engineer | BILL/00032/2023-2024 | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
691 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for Oldabari, Zone-II, TW No. III, ODLABARI CCC, [APPLICATION NO. 4003145978, Reference ID : 403012265] |  | Junior Engineer | BILL/00033/2023-2024 | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
692 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for Oldabari, Zone-II, TW No. I, ODLABARI CCC, [APPLICATION NO. 4003145968, Reference ID : 403012267] |  | Junior Engineer | BILL/00034/2023-2024 | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
693 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for Oldabari, Zone-II, TW No. I, ODLABARI CCC, [APPLICATION NO. 100000077681, Reference ID : 860269311] |  | Junior Engineer | BILL/00035/2023-2024 | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0
694 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for Oldabari, Zone-II, TW No. III, ODLABARI CCC, [APPLICATION NO. 100000077680, Reference ID : 860269310] |  | Junior Engineer | BILL/00036/2023-2024 | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.16 | 0 | 0
695 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for Oldabari, Zone-II, TW No. II, ODLABARI CCC, [APPLICATION NO. 10000077682, Reference ID : 860269312] |  | Junior Engineer | BILL/00037/2023-2024 | BP/23-24/14 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.4 | 0 | 0
696 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ODLABARI PWSS, ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000890/2022-2023 | 373/NMD | 29/03/2023 | 30 | B.B. CONCERNED | 37.59 | 37.59 | 95
697 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
698 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different components of Neora Majhiali (Zone-I, II and III) PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Matiali under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000052/2023-2024 | 244/JD | 08/05/2023 | 696 | SRINIWAS AGARWAL | 424.24 | 226.64 | 55
699 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
700 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Laying distribution system along with providing FHTC at Zone I , II & III of Neora Majhiali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000433/2024-2025 | 2315./JD | 11/12/2024 | 45 | SRINIWAS AGARWAL | 55.21 | 0 | 0
701 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000032/2023-2024 | 145/JD | 28/04/2023 | 0 | Resource Division | 14.77 | 0 | 0
702 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000175/2023-2024 | 2030/JD | 09/01/2024 | 0 | Resource Division | 9.41 | 0 | 0
703 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for NEORA MAJHIALI,Z1 TW NO-I, MAL CCC " APPLICATION NO. 4003377483 Reference ID : 403192834 |  | Junior Engineer | BILL/00163/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
704 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,Z1 TW NO-I, MAL CCC APPLICATION NO. 100000104807 Reference ID : 860297127 " |  | Junior Engineer | BILL/00164/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.11 | 0 | 0
705 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for NEORA MAJHIALI,Z1 TW NO-II, MAL CCC " APPLICATION NO. 4003377487 Reference ID : 403192832 |  | Junior Engineer | BILL/00165/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
706 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,Z-I TW NO-II, MAL CCC " APPLICATION NO. 100000104808 Reference ID : 860297128 |  | Junior Engineer | BILL/00166/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.93 | 0 | 0
707 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for NEORA MAJHIALI,Z II TW NO-I, MAL CCC " APPLICATION NO. 4003377491 Reference ID : 403192835 |  | Junior Engineer | BILL/00167/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
708 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,ZII TW NO-I, MAL CCC " APPLICATION NO. 100000104910 Reference ID : 860297130 |  | Junior Engineer | BILL/00168/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.81 | 0 | 0
709 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for NEORA MAJHIALI,ZII TW NO-II, MAL CCC " APPLICATION NO. 4003377495 Reference ID : 403192837 |  | Junior Engineer | BILL/00169/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
710 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT NEORA MAJHIALI,ZII TW NO-II, MAL CCC " APPLICATION NO. 100000104809 Reference ID : 860297129 |  | Junior Engineer | BILL/00170/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0
711 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for NEORA MAJHIALI,ZIII TW NO-I,METELI CCC " APPLICATION NO.100000108813 Reference ID : 860301243 |  | Junior Engineer | BILL/00419/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.58 | 0 | 0
712 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for NEORA MAJHIALI,ZIII TW NO-I, METELI CCC " APPLICATION NO.4003416347 Reference ID : 403224096 |  | Junior Engineer | BILL/00420/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
713 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NEORA MAJHIALI, T/W No. I, ZONE-I, under METELLI CCC [APPLICATION NO. 4003293335 ; Reference ID : 403125585] |  | Junior Engineer | BILL/01731/2023-2024 | BP/23-24/230 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
714 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for NEORA MAJHIALI, T/W No. I, ZONE-I, under METELLI CCC [APPLICATION NO. 100000095976 ; Reference ID : 860287636] |  | Junior Engineer | BILL/01732/2023-2024 | BP/23-24/231 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.58 | 0 | 0
715 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
716 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEORA MAJHIALI PWSS, TW NO I,II,III,IV,V AND VI in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000423/2023-2024 | 1338/NMD | 08/08/2023 | 570 | CHOWDHURY AND BASU ENTERPRISE | 73.75 | 0.88 | 60
717 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0
718 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
719 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dharmapur (Zone-II) PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc I.c.w. Jal Jeevan Mission at Block :- Maynaguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000028/2023-2024 | 95/JD | 25/04/2023 | 921 | K.R. ENTERPRISE | 322.05 | 155.86 | 70
720 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
721 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dharmapur Zone II PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000424/2024-2025 | 2267/JD | 04/12/2024 | 45 | SOMNATH ROY | 32.43 | 0 | 0
722 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd site of Dharamapur Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000685/2023-2024 | 153/RWS | 15/02/2024 | 286 | SANKAR DAS | 5.32 | 5.26 | 100
723 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W Site including Rising main interconnection of Dharamapur Zone - II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000708/2023-2024 | 2461/JD | 23/02/2024 | 45 | PINTU DAS | 14.74 | 0 | 10
724 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000185/2023-2024 | 2048/JD | 09/01/2024 | 0 | Resource Division | 6.84 | 0 | 0
725 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for DHARMAPUR, T/W No. I, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305834 ; Reference ID : 403134445] |  | Junior Engineer | BILL/01859/2023-2024 | BP/23-24/289 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.07 | 0 | 0
726 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for DHARMAPUR, T/W No. II, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305839 ; Reference ID : 403134438] |  | Junior Engineer | BILL/01861/2023-2024 | BP/23-24/290 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.96 | 0 | 0
727 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
728 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
729 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHARMMAPUR PWSS, TW NO I and II (ZONE-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000243/2023-2024 | 1257/NMD | 31/07/2023 | 30 | M/S BHOWMICK & CO. | 21.55 | 17.87 | 100
730 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
731 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0
732 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Nipuchhapur PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000049/2023-2024 | 242/JD | 08/05/2023 | 821 | M/S SURAJIT DEY AND CO. | 335.86 | 179.3 | 60
733 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
734 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Nipucchapur TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000176/2025-2026 | 175/JSSD | 25/07/2025 | 30 | TEESTA CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCITY LIMITED. | 7.59 | 0 | 0
735 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Nipucchapur TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000420/2024-2025 | 2266/JD | 04/12/2024 | 70 | MALAY BHOWMIK | 49.56 | 0 | 0
736 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000071/2023-2024 | 1076/JD | 24/08/2023 | 0 | Resource Division | 32.73 | 0 | 0
737 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000194/2023-2024 | 2039/JD | 09/01/2024 | 0 | Resource Division | 11.29 | 0 | 0
738 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NIPUCHHAPUR TG, TW NO-I, MAL CCC APPLICATION NO. 4003352325 Reference ID : 403172833 |  | Junior Engineer | BILL/00175/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
739 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at NIPUCHHAPUR TG, TW NO-I, MAL CCC APPLICATION NO. 100000104478 Reference ID : 860297008 |  | Junior Engineer | BILL/00176/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.67 | 0 | 0
740 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NIPUCHHAPUR TG, TW NO-II, MAL CCC APPLICATION NO. 4003352328 Reference ID : 403172832 |  | Junior Engineer | BILL/00177/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
741 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at NIPUCHHAPUR TG, TW NO-II, MAL CCC APPLICATION NO. 100000104479 Reference ID : 860297009 |  | Junior Engineer | BILL/00178/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.89 | 0 | 0
742 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
743 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NIPUCHHAPUR PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000461/2023-2024 | 1437/NMD | 10/08/2023 | 30 | S.P. ENTERPRISE | 27.2 | 18.04 | 80
744 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Barokamat, Dhaurapara for Argi Garalbari W/S Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) |  | Junior Engineer | ORD/000040/2023-2024 | 392/RWS | 25/04/2023 | 14 | BISWAJIT BHADURI | 3.54 | 3.53 | 100
745 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Arji Garalbari PWSS i.e. TW, Pump Houses, IEP, Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri sadar under Jalpaiguri Division, P.H.E.Dte |  | Junior Engineer | ORD/000109/2023-2024 | 434/JD. | 08/06/2023 | 568 | ASIM GUPTA | 40.15 | 9.44 | 40
746 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 15.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site for Rejuvenation of Araji Garalbari water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000255/2023-2024 | 941/JD | 08/08/2023 | 45 | LOKNATH CONSTRUCTION | 17.31 | 17.24 | 100
747 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60M X 2.40M) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Arji Garalbari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000379/2022-2023 | 169/JD | 19/01/2023 | 30 | ABHIJIT SARKAR | 10.88 | 10.82 | 100
748 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap connection (FHTC) at Paharer Hat in connection with JJM at Arji Garalbari Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P.H.E. Dte.(Part-I) |  | Junior Engineer | ORD/000420/2022-2023 | 600/JD | 09/03/2023 | 21 | RANJIT KARMAKAR | 4.85 | 4.82 | 100
749 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(at 3rd TW site) including other necessary arrangement for Rejuvenation of Araji Garalbari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000490/2022-2023 | 289/RWS | 29/03/2023 | 14 | ALICK DATTA | 1.81 | 1.79 | 100
750 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 4003103534 ; Reference ID : 402988696] |  | Junior Engineer | BILL/00006/2023-2024 | BP/23-24/33 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
751 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] |  | Junior Engineer | BILL/00007/2023-2024 | BP/23-24/47 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0
752 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for ARJI GARALBARI (REJU), T/W IV, under PANDAPARA CCC [APPLICATION NO. 100000075210 ; Reference ID : 860266620] |  | Junior Engineer | BILL/00493/2023-2024 |  | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.97 | 0 | 0
753 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 4003099007 ; Reference ID : 402983422] |  | Junior Engineer | BILL/00520/2023-2024 | BP/23-24/115 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
754 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for ARGI GARALBARI, T/W III, under PANDAPARA CCC [APPLICATION NO. 100000074333 ; Reference ID : 860264763] |  | Junior Engineer | BILL/00521/2023-2024 | BP/23-24/115 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0
755 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
756 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI Piped Water Supply Scheme, TW No.- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000133/2023-2024 | 812/NMD | 20/07/2023 | 30 | M/S ANJALI ENTERPRISE | 11.53 | 11.5 | 100
757 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF ARJI GARALBARI PWSS,at TW NO IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000134/2023-2024 | 813/NMD | 20/07/2023 | 30 | SARKAR ELECTRIC | 11.71 | 11.71 | 100
758 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
759 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System including Providing FHTC and other allied work related to pipe line at Bhangerhat PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000450/2024-2025 | 103/JD | 15/01/2025 | 300 | ARATI CONSTRUCTION | 34.03 | 0 | 0
760 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for balanced DI pipeline from Ranirhat More towards Dhupguri for Bhangarhat PWSS at Maynaguri Block under Jalapaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000734/2023-2024 | 2454/JD | 23/02/2024 | 14 | DIPAK KUMAR CHAKRABORTY | 11.62 | 11.9 | 100
761 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000100/2023-2024 | 1053/JD | 24/08/2023 | 0 | Resource Division | 2.59 | 0 | 0
762 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for REJUVENATION OF BHANGARHAT, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376107 Reference ID : 403191657 | Assistant Engineer,HQ | Junior Engineer | BILL/00153/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.2 | 0 | 0
763 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
764 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANGARHAT PWSS, TW NO- I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000183/2023-2024 | 1220/NMD | 26/07/2023 | 584 | GURUKRIPA ENTERPRISE | 11.5 | 0 | 80
765 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Purba Dolaigaon PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000070/2023-2024 | 355/JD | 24/05/2023 | 861 | BHUWALKA DEVELOPMENTS PRIVATE LIMITED | 423.12 | 120.16 | 50
766 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
767 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Purba Dolaigaon PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000101/2025-2026 | 480/RWS | 29/05/2025 | 30 | ADITRI ENTERPRISE | 8.36 | 0 | 0
768 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Kranti block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000475/2023-2024 | 1294/RWS | 29/11/2023 | 30 | SUKES BASU MAJUMDAR | 2.34 | 2.34 | 100
769 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance Laying Distribution Network including Construction of Additional Components of Purba Dolaigaon PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000677/2024-2025 | 487/JD | 11/03/2025 | 60 | DEBASISH DEY | 47.56 | 0 | 0
770 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000108/2023-2024 | 1368/JD | 27/09/2023 | 0 | Resource Division | 22.35 | 0 | 0
771 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000149/2023-2024 | 2018/JD | 09/01/2024 | 0 | Resource Division | 12.97 | 0 | 0
772 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for Purba Dalaigaon, TW NO-I, KRANTI CCC APPLICATION NO. 4003373951 Reference ID : 403190123 |  | Junior Engineer | BILL/00212/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
773 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at Purba Dalaigaon, TW NO-I, KRANTI CCC APPLICATION NO. 100000103006 Reference ID : 860295356 |  | Junior Engineer | BILL/00213/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0
774 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PURBA DOLAIGAON,TW NO-II, KRANTI CCC APPLICATION NO. 4003373939 Reference ID : 403190122 |  | Junior Engineer | BILL/00514/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
775 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at PURBA DOLAIGAON,TW NO-II, KRANTI CCC APPLICATION NO. 100000112283 Reference ID : 860304193 |  | Junior Engineer | BILL/00515/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.89 | 0 | 0
776 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at PURBA DOLAIGAON PWSS for T/W No. I and II in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000847/2024-2025 | 586/NMD | 07/02/2025 | 144 | S.P. ENTERPRISE | 23.88 | 0 | 80
777 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001008/2024-2025 | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0
778 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Kranti Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001412/2024-2025 | 56/HQ/NMD | 06/01/2025 | 7 | SUMON ELECTRICAL | 0.31 | 0 | 0
779 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Paschim Salbari PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer 2 | ORD/000039/2023-2024 | 129/JD | 28/04/2023 | 734 | NARAYAN CHANDRA SAHA | 112.5 | 0 | 50
780 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Emergency repairing of pipe line damaged due to rural road construction and provision for laying of Gas pipe line at different location under Paschim Salbari (Zone - I) Water Supply Scheme under Jalpaiguri Division, PHE Dte. (2nd Call) |  | Junior Engineer 2 | ORD/000148/2023-2024 | 812/RWS | 14/07/2023 | 21 | SAHA CONSTRUCTION | 2.99 | 2.84 | 100
781 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | "Restoration of DI pipeline earlier damaged under Paschim Salbari Water Supply Scheme (Zone-1) under Jalpaiguri Division PHE Dte. " |  | Junior Engineer 2 | ORD/000188/2022-2023 | 554/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 3.28 | 2.56 | 0
782 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000418/2022-2023 | 170/RWS | 28/02/2023 | 21 | SAHA CONSTRUCTION | 4.91 | 4.51 | 1
783 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Paschim Salbari (Zone-II) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000486/2022-2023 | 284/RWS | 29/03/2023 | 21 | PARAMJYOTI ENTERPRISE | 4.94 | 4.91 | 100
784 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Reju. of Paschim Salbari, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003531577 Reference ID : 403306437 |  | Junior Engineer 2 | BILL/01466/2024-2025 | BP/24-25/246 | 02/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.65 | 0 | 0
785 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
786 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PASCHIM SALBARI PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer 2 | ORD/000057/2023-2024 | 572/NMD | 17/05/2023 | 30 | M/S JIT ENTERPRISE | 23.04 | 17.48 | 50
787 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply and Delivery of C.I special as when as required at T/W No-I of PASCHIM SALBARI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. |  | Junior Engineer 2 | ORD/000070/2024-2025 | 1059/HQ/NMD | 21/06/2024 | 7 | CHOWDHURY AND BASU ENTERPRISE | 0.73 | 0.73 | 100
788 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer 2 | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
789 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
790 | Jalpaiguri Division | Jalpaiguri Division | Emergency restoration work of pucca road that was damaged during pipe laying at Uttar Dangapara & Dakshin Sakoajhora Piped Water Supply Scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000022/2023-2024 | 122/JD | 28/04/2023 | 14 | PARESH CHANDRA GUHA | 3.91 | 3.9 | 100
791 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Uttar Dangapara & Dakshin Sakoajhora PWSS , in connection with Rejuvenation of Uttar Dangapara & Dakshin Sakoajhora PWSS under Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000093/2023-2024 | 2000/JD | 19/05/2023 | 60 | NARESH SEN | 19.29 | 9.08 | 15
792 | Jalpaiguri Division | Jalpaiguri Division | Providing FHTC with LDS for direct boosting and Installation of Sluice Valve at different strategic point in connection with JJM of Uttar Dangapara and Dakshin Sakoajhora Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000533/2024-2025 | 124/JD | 16/01/2025 | 50 | SUNIL ROY | 26.06 | 0 | 0
793 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000097/2023-2024 | 1056/JD | 24/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
794 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 4003441947 Reference ID : 403241902 | Assistant Engineer,HQ | Junior Engineer | BILL/00589/2024-2025 | BP/24-25/143 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
795 | Northern Mechanical | Jalpaiguri Division | Infrastructure development cost for new service connection at REJUVENATION OF UTTAR DANGAPARA AND DAKSHIN SAKOJHORA PWSS, TW no III GAIRKATA CCC APPLICATION NO. 100000111357 Reference ID : 860303377 | Assistant Engineer,HQ | Junior Engineer | BILL/00590/2024-2025 | BP/24-25/143 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.74 | 0 | 0
796 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
797 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
798 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0
799 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Samarnagar Pwss (Zone-I and II) i.e.TW,Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc. under Jal Jeevan Mission at Block-Rajganj under Jalpaiguri Division,P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000451/2022-2023 | 714/JD | 20/03/2023 | 180 | SANTALALL & BROTHERS | 431.94 | 199.78 | 52
800 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000021/2023-2024 | 165/JD | 28/04/2023 | 0 | Resource Division | 36.86 | 0 | 0
801 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000115/2023-2024 | 1509/JD | 13/10/2023 | 0 | Resource Division | 16.29 | 0 | 0
802 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SAMAR NAGAR, T/W-III, PRADHAN NAGAR CCC APPLICATION NO. 4003420228 Reference ID : 403226828 | Assistant Engineer,HQ | Junior Engineer | BILL/00475/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.37 | 0 | 0
803 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for new service connection at SAMAR NAGAR, T/W-IV, PRADHAN NAGAR CCC APPLICATION NO. 4003420236 Reference ID : 403226827 | Assistant Engineer,HQ | Junior Engineer | BILL/00525/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 14.67 | 0 | 0
804 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SAMARNAGAR, T/W /W No. II, under PRADHAN NAGAR CCC [APPLICATION NO.4003283658 , Reference ID : 403118308] | Assistant Engineer,HQ | Junior Engineer | BILL/01987/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.41 | 0 | 0
805 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SAMARNAGAR, T/W /W No. I, under PRADHAN NAGAR CCC [APPLICATION NO.4003283650 ; Reference ID : 403118307] | Assistant Engineer,HQ | Junior Engineer | BILL/01988/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.87 | 0 | 0
806 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
807 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
808 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SAMAR NAGAR PWSS, AT TW NO-I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000885/2022-2023 | 368/NMD | 29/03/2023 | 764 | B.B. CONCERNED | 30.72 | 28.71 | 100
809 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain,Land development and pathway and laying pipe line at Zone- I (H/W Site , 2 nd TW site) Zone_II,(H/W Site,2nd TW Site,3rd TW Site) and Zone-III (H/W Site,2nd TW site, 3rd TW site ) of PANIKAURI piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. inconnection with JJM. | Assistant Engineer,HQ | Junior Engineer | ORD/000023/2025-2026 | 2152/JD | 17/10/2025 | 75 | KAMAL GHOSH | 113.94 | 0 | 0
810 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000036/2025-2026 | 823/JD | 30/04/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
811 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Rajgang & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000126/2025-2026 | 1502/JD | 30/06/2025 | 31 | PRADIP SAHA | 0.4 | 0 | 0
812 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Panikauri PWSS Zone-I,II and III PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block -Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2023-2024 | 1764/JD | 08/12/2023 | 481 | UNIBRO INFRASERV PRIVATE LIMITED | 822.43 | 219.6 | 25
813 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.04.2025 to 30.04.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000788/2024-2025 | 109-HQ/JD | 28/03/2025 | 31 | MD AMIRUL ISLAM | 0.15 | 0 | 0
814 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation of proposed 150 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000798/2024-2025 | 85-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
815 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Panikauri Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000799/2024-2025 | 86-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
816 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000002/2023-2024 | 146/JD | 28/04/2023 | 0 | Resource Division | 32.86 | 0 | 0
817 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000177/2023-2024 | 2043/JD | 09/01/2024 | 0 | Resource Division | 23.97 | 0 | 0
818 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PANIKAURI, T/W-II, ZONE-II, under BELAKOBA CCC APPLICATION NO. 4003372528 Reference ID : 403188999 | Assistant Engineer,HQ | Junior Engineer | BILL/00122/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.9 | 0 | 0
819 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PANIKAURI, T/W-III, ZONE-II, under BELAKOBA CCC APPLICATION NO. 4003372640 Reference ID : 403189001 | Assistant Engineer,HQ | Junior Engineer | BILL/00123/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.08 | 0 | 0
820 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PANIKAURI, T/W-I, ZONE-I, under BELAKOBA CCC APPLICATION NO. 4003372565 Reference ID : 403188998 | Assistant Engineer,HQ | Junior Engineer | BILL/00124/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0
821 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PANIKOURI, ZONE-I, TW NO-II, BELAKOBA CCC APPLICATION NO. 4003377413 Reference ID : 403192847 | Assistant Engineer,HQ | Junior Engineer | BILL/00254/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.59 | 0 | 0
822 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PANIKAURI ,ZONE:-III, T/W-I, under BELAKOBA CCC APPLICATION NO. 4003321772 Reference ID : 403174731 | Assistant Engineer,HQ | Junior Engineer | BILL/00328/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8 | 0 | 0
823 | Northern Mechanical | Jalpaiguri Division | Additional Quotation of New Service Connection Charge for PANIKAURI, T/W-II, ZONE-III, under BELAKOBA CCC APPLICATION NO. 100000108541 Reference ID : 860300421 | Assistant Engineer,HQ | Junior Engineer | BILL/00381/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.59 | 0 | 0
824 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for new service connection at PANIKOURI, T/W-I, ZONE-II, BELAKOBA CCC APPLICATION NO. 4003372650 Reference ID : 403188995 | Assistant Engineer,HQ | Junior Engineer | BILL/00526/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.49 | 0 | 0
825 | Northern Mechanical | Jalpaiguri Division | Additional Quotation of New Service Connection Charge for PANIKAURI, T/W-II, ZONE-III, under BELAKOBA CCC APPLICATION NO. 100000121879 ; Reference ID : 860316809 | Assistant Engineer,HQ | Junior Engineer | BILL/01451/2024-2025 | BP/24-25/245 | 26/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.08 | 0 | 0
826 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PANIKOURI, ZONE-III, T/W- III, under BELAKOBA CCC, [APPLICATION NO. 4003321780, Reference ID : 403171055] | Assistant Engineer,HQ | Junior Engineer | BILL/02139/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.24 | 0 | 0
827 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PANIKOURI, ZONE-III, T/W- II, under BELAKOBA CCC, [APPLICATION NO. 4003321779, Reference ID : 403171726] | Assistant Engineer,HQ | Junior Engineer | BILL/02140/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.62 | 0 | 0
828 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
829 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PANI KAURI (ZONE-I,II and III) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000712/2023-2024 | 1512/NMD | 24/08/2023 | 800 | ORIENTAL ENGINEERING CO. | 98.07 | 76.35 | 75
830 | Northern Mechanical | Jalpaiguri Division | Supply and Delivery of C.I special for attending breakdown maintenance as when as required at t/w no-I (zone-II) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/001712/2023-2024 | 434/SMSD | 28/03/2024 | 7 | SAHA ENTERPRISE | 0.73 | 0 | 0
831 | Northern Mechanical | Jalpaiguri Division | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-III) of PANIKAURI and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/001713/2023-2024 | 435/SMSD | 28/03/2024 | 7 | SARKAR ELECTRIC | 0.73 | 0 | 0
832 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Sonakhuli PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte | Assistant Engineer , Head Quarters , NMD |  | ORD/000013/2023-2024 | 39/JD | 13/04/2023 | 812 | JAYANTA GHOSH | 196.47 | 35.42 | 11
833 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Sonakhuli Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000452/2024-2025 | 2332./JD | 12/12/2024 | 45 | ABHIJIT SARKAR | 20.17 | 0 | 0
834 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000013/2023-2024 | 157/JD | 28/04/2023 | 0 | Resource Division | 12.08 | 0 | 0
835 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD |  | RTOR000126/2023-2024 | 1840/JD | 15/12/2023 | 0 | Resource Division | 4.51 | 0 | 0
836 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 4003424435 Reference ID : 403230061 | Assistant Engineer , Head Quarters , NMD |  | BILL/00485/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
837 | Northern Mechanical | Northern Mechanical Division | Infrastructure development cost for new service connection at SONAKHULI,T/W-I, GAIRKATA CCC APPLICATION NO. 100000110438 Reference ID : 860302768 | Assistant Engineer , Head Quarters , NMD |  | BILL/00486/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.53 | 0 | 0
838 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 4003424430 Reference ID : 403230062 | Assistant Engineer , Head Quarters , NMD |  | BILL/00487/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
839 | Northern Mechanical | Northern Mechanical Division | Infrastructure development cost for new service connection at SONAKHULI,T/W-II, GAIRKATA CCC APPLICATION NO. 100000110437 Reference ID : 860302767 | Assistant Engineer , Head Quarters , NMD |  | BILL/00488/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.17 | 0 | 0
840 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
841 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD |  | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
842 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SONAKHULI PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/000239/2023-2024 | 1253/NMD | 31/07/2023 | 30 | GOENKA ENTERPRISE | 20.65 | 14.24 | 60
843 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD |  | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0
844 | Northern Mechanical | Northern Mechanical Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
845 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Paharpur Zone - II PWSS i.e TW, pump houses,water distribution network, OHR, Rising Main, FHTC etc. at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000050/2023-2024 | 130/JD | 28/04/2023 | 706 | GARGO TRADERS | 459.33 | 89.61 | 50
846 | Jalpaiguri Division | Northern Mechanical Division | Balance Work of Distribution System for Paharpur Zone - II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000052/2024-2025 | 945/JD | 07/08/2024 | 240 | PRIYABRATA KARMAKAR | 24.12 | 0 | 95
847 | Jalpaiguri Division | Northern Mechanical Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000122/2023-2024 | 383/A/JD | 01/06/2023 | 183 | RUPA PRASAD | 0.88 | 0.38 | 50
848 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 90
849 | Jalpaiguri Division | Northern Mechanical Division | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2023 to 31.05.2024)". | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000533/2023-2024 | 1677/JD | 24/11/2023 | 182 | RUPA PRASAD | 0.88 | 2.11 | 100
850 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000072/2023-2024 | 1077/JD | 24/08/2023 | 0 | Resource Division | 35.1 | 0 | 0
851 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000114/2023-2024 | 1508/JD | 13/10/2023 | 0 | Resource Division | 13.79 | 0 | 0
852 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000137/2023-2024 | 1886/JD | 20/12/2023 | 0 | Resource Division | 13.79 | 0 | 0
853 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for new service connection at PAHARPUR, T/W-I, ZONE-II, UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003427350 Reference ID : 403231842 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00481/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.78 | 0 | 0
854 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
855 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PAHARPUR PIPED WATER SUPPLY SCHEME , ZONE-II, TW No I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000131/2023-2024 | 811/NMD | 20/07/2023 | 774 | M/S RATAN KUMAR DASGUPTA AND CO. | 21.52 | 0 | 60
856 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
857 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0
858 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different stationary items for office use under Jalpaiguri R.W.S Sub Division, P.H.E Dte. |  | Junior Engineer | BILL/00185/2024-2025 | BP-2024-25-121 | 05/06/2024 | 0 | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 0.25 | 0 | 0
859 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00385/2024-2025 | BP-2024-25-226 | 15/07/2024 | 0 | FILL & SMILE | 0.18 | 0 | 0
860 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 78 3405) |  | Junior Engineer | BILL/00386/2024-2025 | BP-2024-25-225 | 15/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
861 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 78 3405) |  | Junior Engineer | BILL/00387/2024-2025 | BP-2024-25-227 | 15/07/2024 | 0 | FILL & SMILE | 0.18 | 0 | 0
862 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month May'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00388/2024-2025 | BP-2024-25-228 | 15/07/2024 | 0 | FILL & SMILE | 0.14 | 0 | 0
863 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (Diesel) of Vehicle No. WB 25 K 9449 for the Month of July 2024. |  | Junior Engineer | BILL/00542/2024-2025 | BP-2024-25-311 | 20/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
864 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000025/2024-2025 | 735/JD | 26/07/2024 | 75 | PROVA CONSTRUCTION | 103.17 | 0 | 0
865 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000107/2025-2026 | 485/RWS | 29/05/2025 | 30 | DEEP CONSTRUCTION | 8.05 | 0 | 0
866 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Barapatina Nutanbus Zone-I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000118/2023-2024 | 352/JD | 05/06/2023 | 667 | JAYANTA GHOSH | 379.06 | 139.2 | 70
867 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 90
868 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/08/2025 to 30/09/2025) |  | Junior Engineer | ORD/000154/2025-2026 | 1735/JD | 31/07/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 100
869 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". |  | Junior Engineer | ORD/000202/2025-2026 | 2001/JD | 25/09/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 50
870 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.11.2023 to 31.03.2024) |  | Junior Engineer | ORD/000400/2023-2024 | 1601/JD | 08/11/2023 | 152 | SOMNATH ROY | 0.94 | 0.94 | 100
871 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri R.W.S. Sub Division, P.H.E. Dte. for inspection of different PWSS under Jalpaiguri Sadar, Maynaguri, Kranti & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". |  | Junior Engineer | ORD/000475/2025-2026 | 2404/JD | 19/11/2025 | 30 | AJIJUL HAQUE | 0.4 | 0 | 0
872 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Barapatina Nutanbus Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000551/2024-2025 | 118/JD | 16/01/2025 | 40 | ALOKE DEY | 18.75 | 0 | 0
873 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." |  | Junior Engineer | ORD/000570/2023-2024 | 2197/JD | 25/01/2024 | 182 | SOUMEN GHOSH | 0.88 | 0.39 | 0
874 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.04.2024 to 30.08.2024) |  | Junior Engineer | ORD/000837/2023-2024 | 2946/JD | 28/03/2024 | 152 | SOMNATH ROY | 0.93 | 0.93 | 100
875 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000013/2024-2025 | 2017/JD | 19/11/2024 | 0 | Resource Division | 36.79 | 0 | 0
876 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000138/2023-2024 | 1885/JD | 20/12/2023 | 0 | Resource Division | 12.09 | 0 | 0
877 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341706, Reference ID : 403171321] |  | Junior Engineer | BILL/02144/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.99 | 0 | 0
878 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341713, Reference ID : 403171394] |  | Junior Engineer | BILL/02145/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.36 | 0 | 0
879 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
880 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
881 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No Big Dia Tube Well by Modified DTH - ODEX method for 3rd tube well site at Rejuvenation of Gatia Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000029/2025-2026 | 2154/JD | 17/10/2025 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 16.63 | 0 | 100
882 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000085/2023-2024 | 1060/JD | 24/08/2023 | 0 | Resource Division | 3.73 | 0 | 0
883 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GATIA TEA GARDEN PWSS, TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000851/2023-2024 | 1803/NMD | 31/10/2023 | 30 | SANJIB SAHA | 20.9 | 0 | 0
884 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Porapara piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-E) |  | Junior Engineer 2 | ORD/000028/2021-2022 | 748/JD | 13/05/2021 | 30 | DEBASISH DEY | 30 | 0 | 1
885 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalswapna, retrofitting of LDS and rising main connection of 3rd tube well & 4th Tube well site under Porapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-I) |  | Junior Engineer 2 | ORD/000072/2022-2023 | 1298/JD | 14/06/2022 | 60 | B.M CONSTRUCTION | 91.26 | 82.32 | 0
886 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PORAPARA Water Supply Scheme at Sadar Block under under Jalpaiguri Division, PHE Dte. (PART-F) |  | Junior Engineer 2 | ORD/000095/2021-2022 | 1334/JD | 23/08/2021 | 15 | B.M CONSTRUCTION | 14.64 | 16 | 1
887 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional House hold tap Connection (FHTC ) in connection with Jaldhara/ Jalsapna under the command area of PORAPARA W/S/S at Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) |  | Junior Engineer 2 | ORD/000165/2021-2022 | 674/RWS | 27/09/2021 | 15 | SUKES BASU MAJUMDAR | 4.98 | 4.98 | 0
888 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting work related to FHTC in connection to Jalswapna at Haldibari Bypass, Najir Para under Pora para Piped Water Supply under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000279/2022-2023 | 644/RWS | 21/10/2022 | 20 | B.M CONSTRUCTION | 4.34 | 4.34 | 0
889 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Porapara PWSS at block- Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000538/2023-2024 | 1973/JD | 03/01/2024 | 21 | B.M CONSTRUCTION | 21.19 | 21.15 | 100
890 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000083/2024-2025 | 2218/JD | 01/12/2024 | 0 | Resource Division | 36.07 | 0 | 0
891 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PORA PARA PWSS |  | Junior Engineer 2 | VCH/000332/2021-2022 |  | 01/10/2021 | 0 | B.M CONSTRUCTION | 8 | 0 | 0
892 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PORA PARA |  | Junior Engineer 2 | VCH/000919/2021-2022 | BP-2021-22-117 | 03/12/2021 | 0 | SUKES BASU MAJUMDAR | 4.56 | 0 | 0
893 | Jalpaiguri Division | Jalpaiguri Division | Construction of 250 CuM Over Head Reservoir (OHR) (Staging height 20 Mtr.) as per departmental design and drawing for Augmentation of Jalapara Piped Water Supply Scheme at Block - Dhupguri in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000139/2023-2024 | 700/JD | 13/07/2023 | 859 | M/S. D.K. DEY & CO.. | 78.88 | 34.14 | 20
894 | Jalpaiguri Division | Jalpaiguri Division | Retrofiting works i.c.w.FHTC under Jalsapna including repair of damaged pipe lines during road construction at different areas under Dakshin Salbari Piped W/S Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000175/2022-2023 | 553/RWS | 01/09/2022 | 30 | NEW KUNDU ENTERPRISE | 3.16 | 3.14 | 1
895 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Jalapara Piped Water Supply Scheme at Nagrakata & Dhupguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000286/2023-2024 | 1413/JD | 03/10/2023 | 90 | BOSE ENTERPRISE | 256.04 | 175.93 | 25
896 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of 2nd Tube Well Site and Head Work Site Pump House at Jalapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000497/2024-2025 | 2375/JD | 18/12/2024 | 177 | BALARAM GHOSH & SONS | 2.88 | 0 | 90
897 | Jalpaiguri Division | Jalpaiguri Division | Construction of different balance components of Jalapara PWSS in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000829/2023-2024 | 2757/JD | 15/03/2024 | 746 | ANUP KUMAR KUNDU | 88.77 | 0 | 5
898 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000008/2024-2025 | 54/JD | 09/04/2024 | 0 | Resource Division | 114.02 | 0 | 0
899 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AUGMENTATION OF JALAPARA, T/W-I, under BANARHAT CCC APPLICATION NO. 4003418441 Reference ID : 403225407 | Assistant Engineer,HQ | Junior Engineer | BILL/00368/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.58 | 0 | 0
900 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF JALAPARA PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000871/2022-2023 | 335/NMD | 29/03/2023 | 30 | MUSTAFI CONCERN | 21.8 | 0 | 0
901 | Siliguri W/S Division |  | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PURBA PASCHIM DHANTALA PIPED WATER SUPPLY SCHEME UNDER RAJGANJ BLOCK, JALPAIGURI DISTRICT UNDER SILIGURI W/S DIVISION, P.H.E. DTE |  |  | ORD/000070/2023-2024 | 263/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 3.6 | 0 | 30
902 | Siliguri W/S Division |  | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-C) |  |  | ORD/000103/2023-2024 | 1034/SWSD | 26/07/2023 | 45 | ROYAL ENTERPRISE | 10.03 | 0 | 0
903 | Siliguri W/S Division |  | Laying distribution system, rising main, construction of pump house and tubewells along with other allied works inconnection with Jal Jeevan Mission of Augmentation PURBA PASCHIM DHANTALA Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte |  |  | ORD/000106/2023-2024 | 1140/SWSD | 07/08/2023 | 150 | UNIBRO INFRASERV PRIVATE LIMITED | 181.57 | 0 | 0
904 | Siliguri W/S Division |  | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-B) |  |  | ORD/000123/2023-2024 | 1232/SWSD | 14/08/2023 | 30 | SHREYANSH AUTOMOBILE | 4.95 | 0 | 0
905 | Siliguri W/S Division |  | Laying distribution system, rising main, construction of pump house and boundary wall, installation of Iron Elimination Plant, repairing of OHR, pump house and boundary wall, sinking of tubewell along with other allied works in connection with Jal Jeevan Mission Programme for Augmentation of PURBA PASCHIM DHANTALA Piped Water Supply Scheme (Zone-I) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte |  |  | ORD/000132/2023-2024 | 1367/SWSD | 18/08/2023 | 240 | UNIBRO INFRASERV PRIVATE LIMITED | 549.31 | 0 | 0
906 | Siliguri W/S Division |  | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme under Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-II) at Rajganj Block under Siliguri W/S Division, P.H.E. Dte. (Part-A) |  |  | ORD/000140/2023-2024 | 1413/SWSD | 22/08/2023 | 30 | SANJAY KUMAR BHADRA | 4.95 | 0 | 0
907 | Siliguri W/S Division |  | Providing Functional Household Tap Connection (FHTC) and other allied works inconnection with Jal Jeevan Mission Programme for Augmentation of Purba Paschim Dhantala Piped Water Supply Scheme (Zone-I) at Rajganj Block Under Siliguri W/S Division, P.H.E. Dte. |  |  | ORD/000200/2023-2024 | 2049/SWSD | 07/11/2023 | 45 | S.G.CONSTRUCTION | 11.87 | 0 | 0
908 | Siliguri W/S Division |  | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 2213/SWSD | 05/01/2023 | 0 | Resource Division | 76.69 | 0 | 0
909 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
910 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA PASCHIM DHANTALA (ZONE-II and III) PWSS, ZONE-II, TW No I,II AND ZONE-III,TW NO- I in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. |  |  | ORD/000670/2023-2024 | 1485/NMD | 17/08/2023 | 30 | SARKAR ELECTRIC | 34.22 | 28.26 | 70
911 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
912 | Jalpaiguri Division |  | Construction of different components of Changmarihat Zone-III PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. In connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000176/2023-2024 | 847/JD | 28/07/2023 | 882 | S & P ENTERPRISE | 234.9 | 10.29 | 10
913 | Jalpaiguri Division |  | Construction of different components of Changmarihat Zone-II PWSS i.e. TW, Pump Houses,Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000177/2023-2024 | 848/JD. | 28/07/2023 | 882 | S & P ENTERPRISE | 367.87 | 118.79 | 65
914 | Jalpaiguri Division |  | Construction of different components of changmarihat Zone-I PWSS i.e TW, Pump House , Water distribution Network , OHR , Boundary wall , RISING MAIN , FHTC etc . In connection with Jal Jeevan Mission at Block kranti under Jalpaiguri Division , P.H.E Dte. |  |  | ORD/000178/2023-2024 | 849/JD. | 28/07/2023 | 882 | S & P ENTERPRISE | 398.61 | 241.91 | 25
915 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 148/JD | 28/04/2023 | 0 | Resource Division | 76.45 | 0 | 0
916 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 2071/JD | 10/01/2024 | 0 | Resource Division | 22.22 | 0 | 0
917 | Northern Mechanical |  | New Service Connection Charge for CHENGMARIHAT, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 4003391522 Reference ID : 403203856 |  |  | BILL/00240/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
918 | Northern Mechanical |  | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-I,TW NO-I, KRANTI CCC APPLICATION NO. 100000105710 Reference ID : 860298010 |  |  | BILL/00241/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.1 | 0 | 0
919 | Northern Mechanical |  | New Service Connection Charge for CHENGMARIHAT, ZONE-II,TW NO-I, KRANTI CCC APPLICATION NO. 4003391511 Reference ID : 403203859 |  |  | BILL/00242/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
920 | Northern Mechanical |  | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-II,TW NO-I, KRANTI CCC APPLICATION NO. 100000105736 Reference ID : 860297936 |  |  | BILL/00243/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.88 | 0 | 0
921 | Northern Mechanical |  | New Service Connection Charge for CHENGMARIHAT, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 4003391518 Reference ID : 403203858 |  |  | BILL/00244/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
922 | Northern Mechanical |  | Infrastructure development cost for new service connection at CHENGMARIHAT, ZONE-III,TW NO-I, KRANTI CCC APPLICATION NO. 100000105737 Reference ID : 860297937 |  |  | BILL/00245/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.44 | 0 | 0
923 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
924 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHENGMARIHAT PWSS, TW no I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000419/2023-2024 | 1333/NMD | 08/08/2023 | 602 | ORIENTAL ENGINEERING CO. | 38.65 | 0 | 100
925 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-II) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000050/2021-2022 | 1073/JD | 02/07/2021 | 30 | BISWAJIT BHADURI | 27.41 | 0 | 0
926 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000053/2021-2022 | 1072/JD | 02/07/2021 | 30 | SAHA CONSTRUCTION | 23.05 | 0 | 1
927 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Goralbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-F) |  | Junior Engineer | ORD/000054/2021-2022 | 1074/JD | 02/07/2021 | 45 | M/S SIBU DEY AND CO. | 36.93 | 0 | 0
928 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under Arji Garalbari piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. (Part ¿ E) |  | Junior Engineer | ORD/000122/2021-2022 | 521/RWS | 30/07/2021 | 15 | RANJIT KARMAKAR | 4.75 | 0 | 0
929 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting work related to FHTC at Balipara, Hazaripara and adjacent area within Garalbari zone-II W/S Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000133/2022-2023 | 1552/JD | 05/08/2022 | 21 | BISWAJIT BHADURI | 18.01 | 18 | 0
930 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing functional household tap connection (FHTC ) in connetion with jaldhara / jal sapna under garalbari Zone- iii piped water supply scheme at Jalpaiguri Block under JAlpaiguri Division , PHE,Dte. ( part - c) |  | Junior Engineer | ORD/000158/2021-2022 | 479/RWS | 23/07/2021 | 15 | NARAYAN SARKAR | 2.53 | 0 | 0
931 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing and renovation of Boundary walls ( 2nd site ),pump house , including O.H.R for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte Jalpaiguri. |  | Junior Engineer | ORD/000175/2021-2022 | 681/RWS | 27/09/2021 | 30 | BISWAJIT BHADURI | 4.67 | 0 | 1
932 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Over Hauling of the Iron Elimination plant at 2nd site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000176/2021-2022 | 682/RWS | 27/09/2021 | 20 | BISWAJIT BHADURI | 3.9 | 0 | 0
933 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Over Hauling of the Iron Elimination plant at H/W site for Garalbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000179/2021-2022 | 684/RWS | 27/09/2021 | 20 | BISWAJIT BHADURI | 3.9 | 0 | 1
934 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri |  | Junior Engineer | ORD/000200/2019-2020 | 302/JD | 17/03/2020 | 120 | BILTU DAS | 47.59 | 0 | 0
935 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Jamuribari, Sovabhita, Pakuritala, Chandanidanga, Nayabari, Kohorapara and adjacent area within Garalbari Zone-II under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-D) |  | Junior Engineer | ORD/000202/2022-2023 | 1741/JD | 08/09/2022 | 45 | PROVA CONSTRUCTION | 75.59 | 0 | 100
936 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) including Retrofitting at Krishimandi, Petrol pump and adjacent area within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (Part-L) |  | Junior Engineer | ORD/000234/2022-2023 | 1862/JD | 20/09/2022 | 25 | ASIM GUPTA | 15.65 | 15.64 | 1
937 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-G) |  | Junior Engineer | ORD/000268/2021-2022 | 2035/JD | 07/12/2021 | 21 | SOMNATH ROY | 17.26 | 0 | 0
938 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Garalbari (Zone-III) piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-H) |  | Junior Engineer | ORD/000269/2021-2022 | 2036/JD | 07/12/2021 | 21 | J.M. CONSTRUCTION | 13.14 | 0 | 0
939 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Garalbari Zone ¿ I . W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ C ) |  | Junior Engineer | ORD/000323/2021-2022 | 874/RWS | 08/12/2021 | 10 | SAPTASWA SARKAR | 2.71 | 0 | 0
940 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Goralbari (Zone-III) Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000354/2020-2021 | 34/RWS | 28/01/2021 | 15 | NARAYAN SARKAR | 4.82 | 0 | 0
941 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Nijbari,Hazari Para,Ambari,Harinagar for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000517/2021-2022 | 161/RWS | 28/02/2022 | 15 | BISWAJIT BHADURI | 4.85 | 0 | 0
942 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Baraghaoria, Bhutiakhola for Garalbari Zone-II W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000519/2021-2022 | 164/RWS | 28/02/2022 | 15 | BISWAJIT BHADURI | 2.21 | 0 | 0
943 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofiting works at Tariapara, Barua para, Nawa para, Khansaheb para related to FHTC for Garalbari Zone ¿I WSS under Jalpaiguri Division , P.H.E. Dte. |  | Junior Engineer | ORD/000523/2021-2022 | 171/RWS | 03/03/2022 | 15 | SAPTASWA SARKAR | 3.84 | 0 | 0
944 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal sapna under the command area of Garalbari zone - I. Water Supply Scheme under Jalpaiguri Division , P.H.E. Dte ( Part - D ) |  | Junior Engineer | ORD/000524/2021-2022 | 172/RWS | 03/03/2022 | 15 | SAHA CONSTRUCTION | 3.41 | 0 | 0
945 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001084/2021-2022 | BP-2021-22-160 | 14/01/2022 | 0 | NARAYAN SARKAR | 2.6 | 0 | 0
946 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001092/2021-2022 | BP-2021-22-145 | 14/01/2022 | 0 | M/S SIBU DEY AND CO. | 37.86 | 0 | 0
947 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001093/2021-2022 | BP-2021-22-146 | 14/01/2022 | 0 | SAHA CONSTRUCTION | 23.03 | 0 | 0
948 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | retrofitting work for goralbari pwss |  | Junior Engineer | VCH/001156/2021-2022 | BP-2021-22-253 | 22/02/2022 | 0 | NEW KUNDU ENTERPRISE | 1.33 | 0 | 0
949 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing fhtc for boalmari pwss |  | Junior Engineer | VCH/001157/2021-2022 | BP-2021-22-254 | 22/02/2022 | 0 | KANAI LAL SEN | 3.62 | 0 | 0
950 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FROVIDING FHTC FOR SAMSING T.G |  | Junior Engineer | VCH/001160/2021-2022 | BP-2021-22-258 | 22/02/2022 | 0 | M/S. D.K. DEY & CO.. | 29.06 | 0 | 0
951 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC PORAPARA |  | Junior Engineer | VCH/001164/2021-2022 | BP-2021-22-270 | 22/02/2022 | 0 | DEBASISH DEY | 5.57 | 0 | 0
952 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | water sup[ply arrangement for angawari center |  | Junior Engineer | VCH/001167/2021-2022 | BP-2021-22-277 | 22/02/2022 | 0 | R.S CONSTRUCTION | 18.98 | 0 | 0
953 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | retrofittinbg work for kajaldighi |  | Junior Engineer | VCH/001168/2021-2022 | BP-2021-22-237 | 22/02/2022 | 0 | R.S CONSTRUCTION | 4.54 | 0 | 0
954 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing fhtc yong tong t.g |  | Junior Engineer | VCH/001170/2021-2022 | BP-2021-22-236 | 23/02/2022 | 0 | ASHIT KUMAR SINGHA | 8.71 | 0 | 0
955 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DABGRAM |  | Junior Engineer | VCH/001181/2021-2022 | BP-2021-22-282 | 23/02/2022 | 0 | NARAYAN CHAKRABORTY | 24.81 | 0 | 0
956 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SONGACHI T.GG |  | Junior Engineer | VCH/001184/2021-2022 | BP-2021-22-2291 | 23/02/2022 | 0 | M/S M.B. DESIGN | 15.73 | 0 | 0
957 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | IEP GORALBARI |  | Junior Engineer | VCH/001209/2021-2022 | BP-2021-22-324 | 28/02/2022 | 0 | BISWAJIT BHADURI | 3.87 | 0 | 0
958 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBA MAGURMARI |  | Junior Engineer | VCH/001220/2021-2022 | BP-2021-22-335 | 03/03/2022 | 0 | MONOJ GHOSH | 7.74 | 0 | 0
959 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBA MAGURMARI |  | Junior Engineer | VCH/001221/2021-2022 | BP-2021-22-334 | 03/03/2022 | 0 | ARATI CONSTRUCTION | 7.42 | 0 | 0
960 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC NAYASYLI |  | Junior Engineer | VCH/001222/2021-2022 | BP-2021-22-336 | 03/03/2022 | 0 | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0
961 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc rej nagrakata |  | Junior Engineer | VCH/001226/2021-2022 | BP-2021-22-338 | 03/03/2022 | 0 | ANUP KUMAR KUNDU | 28.29 | 0 | 0
962 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc charer bari |  | Junior Engineer | VCH/001227/2021-2022 | BP-2021-22-337 | 03/03/2022 | 0 | NEW KUNDU ENTERPRISE | 2.44 | 0 | 0
963 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc bhangarhat |  | Junior Engineer | VCH/001228/2021-2022 | BP-2021-22-341 | 03/03/2022 | 0 | BILTU DAS | 26.16 | 0 | 0
964 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORKS GORALBARI ZONE II |  | Junior Engineer | VCH/001344/2021-2022 | BP-2021-22-413 | 23/03/2022 | 0 | BISWAJIT BHADURI | 2.21 | 0 | 0
965 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001428/2021-2022 | BP-2021-22-448 | 26/03/2022 | 0 | ASHIM GUPTA | 62.4 | 0 | 0
966 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GORALBARI |  | Junior Engineer | VCH/001429/2021-2022 | BP-2021-22-450 | 26/03/2022 | 0 | BISWAJIT BHADURI | 27 | 0 | 0
967 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORKS FHTC GORALBARI ZONE II |  | Junior Engineer | VCH/001800/2020-2021 | BP-2021-22- 414 | 23/03/2022 | 0 | BISWAJIT BHADURI | 4.84 | 0 | 0
968 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-D) |  | Junior Engineer | ORD/000067/2021-2022 | 59/JSSD | 12/05/2021 | 15 | PRITAM DUTTA | 1.87 | 3.47 | 0
969 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-C) |  | Junior Engineer | ORD/000072/2021-2022 | 63/JSSD | 13/05/2021 | 15 | BIMAN DAS | 2.34 | 0 | 0
970 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of ENGO T.G. Area Piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte (PART-B) |  | Junior Engineer | ORD/000075/2021-2022 | 68/JSSD | 19/05/2021 | 15 | NABIN PRODHAN | 2.35 | 0 | 0
971 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Engo T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000243/2020-2021 | 561/JSSD | 01/02/2021 | 15 | JOYDEB SAHA | 4.64 | 9.28 | 0
972 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Preparation of D.P.R. (consultancy work) in connection with Augmentation of Matially PWSS (Matially block) under Jalpaiguri Division PHED |  | Junior Engineer | ORD/000539/2021-2022 | .93/JSSD | 10/06/2021 | 30 | SUBHANKAR GHOSH | 1.99 | 0 | 0
973 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000055/2021-2022 | 1075/JD | 02/07/2021 | 30 | ARATI CONSTRUCTION | 24.34 | 17.45 | 1
974 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works at various mouza under command area of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2022-2023 | 1291/JD | 14/06/2022 | 21 | ARATI CONSTRUCTION | 4.8 | 4.78 | 1
975 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna at Purba Magurmari and Paschim Magurmari village under the command area of Purba Magurmari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000188/2021-2022 | 1690/JD | 28/10/2021 | 30 | ANUP SARKAR | 24.44 | 0 | 1
976 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Purba Magurmari and Paschim Magurmari and Jhar Magurmari village under the command area of Purba Magurmari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000266/2021-2022 | 2044/JD | 07/12/2021 | 21 | ARATI CONSTRUCTION | 39.59 | 0 | 1
977 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PURBA MAGURMARI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000313/2020-2021 | 291/JD | 23/02/2021 | 30 | A.P CONSTRUCTION | 24.41 | 0 | 1
978 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 30
979 | Jalpaiguri Division | Jalpaiguri Division | Laying of Distribution System along with Functional Household Tap Connection (Phase-VI) in connection with Jal Jeevan Mission under Rejuvenation of Purba Magurmari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000425/2022-2023 | 628/JD | 13/03/2023 | 765 | SANKAR DAS | 43.78 | 35.59 | 60
980 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000074/2024-2025 | 2205/JD | 01/12/2024 | 0 | Resource Division | 28.93 | 0 | 0
981 | Jalpaiguri Division | Jalpaiguri Division | fhtc for purba magurmari pwsws | Assistant Engineer,HQ | Junior Engineer | VCH/000461/2021-2022 |  | 21/10/2021 | 0 | ARATI CONSTRUCTION | 17.45 | 0 | 0
982 | Jalpaiguri Division | Jalpaiguri Division | fhtc for purba magurmari pwss | Assistant Engineer,HQ | Junior Engineer | VCH/000462/2021-2022 |  | 21/10/2021 | 0 | MONOJ GHOSH | 16.71 | 0 | 0
983 | Jalpaiguri Division | Jalpaiguri Division | FHTC PURBA MAGURMARI | Assistant Engineer,HQ | Junior Engineer | VCH/000793/2021-2022 | BP-2021-22-90 | 01/11/2021 | 0 | MANOJ GHOSH | 16.71 | 0 | 0
984 | Jalpaiguri Division | Jalpaiguri Division | Construction of Different Components of Supply Of Potable Drinking Water To Red Bank Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000589/2023-2024 | 2331/JD | 08/02/2024 | 449 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 90.89 | 35.71 | 75
985 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000022/2024-2025 | 2104/JD | 25/11/2024 | 0 | Resource Division | 3.02 | 0 | 0
986 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for RED BANK TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, T/W-II, under BANARHAT CCC APPLICATION NO. 4003418390 Reference ID : 403225711 | Assistant Engineer,HQ | Junior Engineer | BILL/00367/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.64 | 0 | 0
987 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for RED BANK TEA GARDEN (CHAA SUNDARI), T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003333225 , Reference ID : 403157470] | Assistant Engineer,HQ | Junior Engineer | BILL/02002/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.76 | 0 | 0
988 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at RED BANK TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block - DHUPGURI, district Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/000042/2022-2023 | 357/NMD | 23/05/2022 | 1166 | M/S BHOWMICK & CO. | 12.59 | 0 | 90
989 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF DIFFERENT STATIONARY FOR OFFICE USE |  | Junior Engineer | BILL/00462/2023-2024 | BP-2023-24-363 | 13/09/2023 | 0 | JALPAIGURI WHOLE SALE CONSUMER CO-OPERATIVE SOC. LTD. | 4.59 | 0 | 0
990 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & lubricant for Vehicle No:- WMA-2539, WB-71A-5774 FOR THE MONTH OF APRIL, MAY ,& OCTOBER |  | Junior Engineer | BILL/00948/2023-2024 | BP-2023-24-545 | 18/12/2023 | 0 | FILL & SMILE | 0.54 | 0 | 0
991 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF ONE MAXI CAB WITH ENGINE CAPACITY LESS THAN OR EQUAL TO 2000 C.C. ON HIRE BESIS INCLUDING DRIVER UNDER OFFICE OF THE ASSISTANT ENGINEER ,JALPAIGURI SADAR SUB DIVISION , P.H.E Dte. |  | Junior Engineer | BILL/01046/2023-2024 | BP-2023-24-592 | 16/01/2024 | 0 | MRITYUNJAY SIKDAR | 0.54 | 0 | 0
992 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL for vehicle FOR OFFICE OF THE ASSISTANT ENGINEER , JALPAIGURI SADAR SUB DIVISION, P.H.E Dte. |  | Junior Engineer | BILL/01047/2023-2024 | BP-2023-24-591 | 16/01/2024 | 0 | FILL & SMILE | 1.02 | 0 | 0
993 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250mm x 150mm dia tube wells by Reverse Rotary method of drilling for Augmentation of Kharija Berubari Zone-I PWSS within Jalpaiguri Sadar Block under the PHE Dte. Jalpaiguri Division (H/W and 2nd Site) |  | Junior Engineer | ORD/000003/2023-2024 | 848/JD | 06/04/2023 | 30 | SHYAMAL KUMARSAHA | 17.39 | 17.17 | 100
994 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of Additional 1 No Tube Well by Reverse Rotary Method including construction Pump House, Boundary Wall and installation of Iron Elimination Plant (IEP) and Inter Connection work at Gosaimore under Nagar Berubari GP of Augmentation of Kharija Berubari Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000006/2025-2026 | 678/JD | 04/04/2025 | 120 | KANAI LAL SEN | 38.97 | 0 | 0
995 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution system and functional household tap connection for Augmentation of Kharija Berubari Zone-I piped Water Supply Scheme Block- Jalapiguri, District - Jalpaiguri. |  | Junior Engineer | ORD/000019/2022-2023 | 1066/JD | 28/04/2022 | 1283 | M/S R.N. TRADERS | 605.44 | 385.99 | 85
996 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection for Augmentation of Kharija Berubari Zone-II Piped Water Supply Scheme Block - Jalpaiguri District - Jalpaiguri. |  | Junior Engineer | ORD/000038/2022-2023 | 1099/JD | 12/05/2022 | 120 | BANSBERIA CONSTRUCTION CO. | 554.56 | 503.06 | 90
997 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of IEP, Blower Room, Footpath, Land filling, Drain at HW Site of Kharija Berubari - II Pipe Water Supply Scheme under Jalpaiguri Sadar Block Within Jalpaiguri PHE Division, Jalpaiguri. |  | Junior Engineer | ORD/000086/2024-2025 | 1176/JD | 23/08/2024 | 586 | NARAYAN CHANDRA SAHA | 72.2 | 0 | 80
998 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement and Boundary Wall, Foot Path, Drain of 2nd Site at Kharija - I Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000124/2024-2025 | 1369/JD | 13/09/2024 | 566 | ALICK DUTTA | 12.67 | 6.41 | 65
999 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 400 m3 OHR as per Departmental Design & Drawing & Pump House (3.60m x 2.40m) internal size with sanitary & Plumbing arrangement at Head Work site for AUGMENTATION OF KHARIJA BERUBARI (Zone-I) Piped Water Supply Scheme Block- Jalpaiguri, District : Jalpaiguri. |  | Junior Engineer | ORD/000250/2022-2023 | 1845//JD | 15/09/2022 | 180 | SUKES BASU MAJUMDAR | 87.97 | 89.05 | 100
1000 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF KHARIJA BERUBARI PIPED WATER SUPPLY SCHEME (ZONE-II), Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000454/2021-2022 | 335/JD | 02/02/2022 | 120 | NARAYAN CHANDRA SAHA | 97.85 | 71.39 | 100
1001 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.01.2024 to 29.02.2024) |  | Junior Engineer | ORD/000563/2023-2024 | 2121/JD | 17/01/2024 | 60 | GURUKUL INFOTECH | 3.16 | 3.16 | 50
1002 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of different forms for office use under jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000822/2023-2024 | 2721/JD | 12/03/2024 | 7 | SUBRATA ART PRESS | 0.7 | 0.7 | 100
1003 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.03.2024 to 30.04.2024)" |  | Junior Engineer | ORD/000865/2023-2024 | 2488/JD | 27/02/2024 | 60 | GURUKUL INFOTECH | 3.16 | 3.16 | 100
1004 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall including repairing of Pump House at 2nd Site for Kharija Berubari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001044/2021-2022 | 1438/JD | 09/09/2021 | 30 | PROFULLA GHOSH | 9.74 | 0 | 0
1005 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000012/2021-2022 | 559/JD | 01/03/2022 | 0 | Resource Division | 96.47 | 0 | 0
1006 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000087/2024-2025 | 2215/JD | 01/12/2024 | 0 | Resource Division | 35.61 | 0 | 0
1007 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION |  | Junior Engineer | VCH/001199/2021-2022 | BP-2021-22-316 | 28/02/2022 | 0 | MOYTEC | 2.03 | 0 | 0
1008 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK AUGMENTATION KHARIJA BERUBARI (ZONE -I) PWSS |  | Junior Engineer | VCH/001276/2021-2022 | BP-2021-22-353 | 08/03/2022 | 0 | GEOCON INDIA | 2.03 | 0 | 0
1009 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003207489, Reference ID : 403056596] |  | Junior Engineer | BILL/00624/2023-2024 | BP/23-24/86 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1010 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for KHARIJA BERUBARI, T/W II, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000086246, Reference ID : 860277656] |  | Junior Engineer | BILL/00625/2023-2024 | BP/23-24/86 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.05 | 0 | 0
1011 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for NANDANPUR,KHARIJA BERUBARI, T/W I, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003212076, Reference ID : 403060257] |  | Junior Engineer | BILL/01070/2023-2024 | BP/23-24/103 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0
1012 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply delivery of the different UPVC materials for Reverse Rotary Circulation method of drilling for construction of BDTW for the Augmentation of KharijaBerubari PWSS (Zone-I), Block - Jalpaiguri, Dist.- Jalpaiguri, at deptt. Stack-Yard at Fulbari under NMSD (D), PHE, Dte. |  | Junior Engineer | ORD/000668/2022-2023 | 1411/NMD | 13/12/2022 | 30 | ALPHA ENTERPRISE | 11.43 | 11.43 | 0
1013 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of fuel |  | Junior Engineer | BILL/00209/2023-2024 | BP-2023-24-117 | 01/06/2023 | 0 | FILL & SMILE | 0.66 | 0 | 0
1014 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Caron Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000009/2022-2023 | 870/JD | 04/04/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 13.85 | 13.46 | 100
1015 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of rejuvenation of Carron Tea Garden PWSS at 4th TW site i.e. Steel staging OHR, Water Distribution Network, FHTC, interconnection, etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000036/2024-2025 | 939/JD | 07/08/2024 | 603 | SANKAR DAS | 15.03 | 0 | 90
1016 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at CARRON Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. |  | Junior Engineer | ORD/000114/2022-2023 | 112/JSSD | 27/07/2022 | 15 | SANDIP BANIK | 4.75 | 3.32 | 100
1017 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under command area of Carron T.G piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000197/2021-2022 | 470/JSSD | 05/10/2021 | 15 | SANDIP BANIK | 4.63 | 9.07 | 0
1018 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.01.2023 to 31.03.2023 |  | Junior Engineer | ORD/000368/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.44 | 0 | 0
1019 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Rejuvenation of Carron Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000481/2022-2023 | 800/JD.. | 29/03/2023 | 614 | TECHNO CRACY | 2.84 | 1.89 | 100
1020 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of (one) Maxi Cab with engine capacity more than 2000 C.C on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Sub-Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi Permit)" from 01.04.2023 to 30.04.2023. |  | Junior Engineer | ORD/000510/2022-2023 | 503/JSSD | 30/03/2023 | 30 | TANMOY CHOUDHURY | 0.15 | 0.24 | 0
1021 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 |  | Junior Engineer | ORD/000597/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.45 | 0.06 | 0
1022 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall with gate, drain and pathway for 4th tube well site at Caron T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000727/2021-2022 | 1042/JSSD | 24/01/2022 | 20 | SK. MOBIN HUSSAIN | 3.75 | 0 | 0
1023 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M X 2.40 M)size with sanitary & plumbing arrangement at 3rd Tube-Well site for Caron T.G.PWSS under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000893/2021-2022 | 1027/W/JSSD | 31/01/2022 | 1021 | SARKAR ASSOCIATES | 4.64 | 4.64 | 100
1024 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Caron T.G. P.W.S.S under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/001127/2021-2022 | 1011/W/JSSD | 27/01/2022 | 1071 | GOURAB GUHA ROY | 3.76 | 0 | 100
1025 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000027/2024-2025 | 2096/JD | 25/11/2024 | 0 | Resource Division | 5.22 | 0 | 0
1026 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for CARON TEA GARDEN, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 4003320133, Reference ID : 403147059] |  | Junior Engineer | BILL/01935/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
1027 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for CARON TEA GARDEN, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000098886, Reference ID : 860291136] |  | Junior Engineer | BILL/01936/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.52 | 0 | 0
1028 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for CARON, T/W-III, under NAGRAKATA CCC, [APPLICATION NO. 4003352267, Reference ID : 403172839] |  | Junior Engineer | BILL/02136/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
1029 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for CARON, T/W-III, under NAGRAKATA CCC, [APPLICATION NO. 100000101246, Reference ID : 860293456] |  | Junior Engineer | BILL/02137/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.21 | 0 | 0
1030 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CARON TG PWSS, TW No III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000856/2023-2024 | 1811/NMD | 31/10/2023 | 30 | M/S B.ENTERPRISE | 30.99 | 9.39 | 80
1031 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
1032 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1033 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
1034 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Additional work for Laying pipe line at Dakshin Putimari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000081/2024-2025 | 1171/JD | 23/08/2024 | 586 | PAMPA CONSTRUCTION | 20.26 | 0 | 65
1035 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dakshin Putimari PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN , FHTC etc. in connection with JJM at Block - Maynaguri under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000467/2022-2023 | 778/JD | 27/03/2023 | 1102 | ASHIT KUMAR SINGHA | 363.4 | 145.33 | 45
1036 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with gate, drain, Land development, pathway at H/W site and 2nd site including laying pipe line and FHTC work at Dakshin Putimari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte i.c.w. JJM . |  | Junior Engineer | ORD/000561/2024-2025 | 115/JD | 16/01/2025 | 440 | ASHIT KUMAR SINGHA | 35.9 | 0 | 65
1037 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000017/2023-2024 | 161/JD | 28/04/2023 | 0 | Resource Division | 131.96 | 0 | 0
1038 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000176/2023-2024 | 2058/JD | 09/01/2024 | 0 | Resource Division | 8.7 | 0 | 0
1039 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Dakshin Putimari, T/W-I under BHOTPATTY CCC APPLICATION NO. 4003378682 Reference ID : 403193481 |  | Junior Engineer | BILL/00206/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.99 | 0 | 0
1040 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Dakshin Putimari, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003388138 Reference ID : 403201474 |  | Junior Engineer | BILL/00207/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.63 | 0 | 0
1041 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
1042 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1043 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
1044 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN PUTIMARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000845/2022-2023 | 333/NMD | 29/03/2023 | 856 | RIPON DAS | 21.5 | 18.66 | 100
1045 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0
1046 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1047 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1048 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of IEP and Blower Room of Uttar Dhupjhora PWSS in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000232/2024-2025 | 2329./JD | 12/12/2024 | 264 | BOSE ENTERPRISE | 17.26 | 0 | 20
1049 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Uttar Dhupjhora PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000446/2022-2023 | 716/JD | 20/03/2023 | 835 | BOSE ENTERPRISE | 231.68 | 202.41 | 50
1050 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000001/2023-2024 | 176/JD | 28/04/2023 | 0 | Resource Division | 16.8 | 0 | 0
1051 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000169/2023-2024 | 2035/JD | 09/01/2024 | 0 | Resource Division | 7.13 | 0 | 0
1052 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for JOHURUL PARA UTTAR DHUPJHORA, T/W I, under METELLI CCC, [APPLICATION NO. 4003177288, Reference ID : 403033824] |  | Junior Engineer | BILL/00616/2023-2024 | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1053 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for JOHURUL PARA UTTAR DHUPJHORA, T/W I, under METELLI CCC, [APPLICATION NO. 100000082758, Reference ID : 860274518] |  | Junior Engineer | BILL/00617/2023-2024 | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.77 | 0 | 0
1054 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for JOHURUL PARA UTTAR DHUPJHORA, T/W II, under METELLI CCC, [APPLICATION NO. 4003177279, Reference ID : 403033822] |  | Junior Engineer | BILL/00618/2023-2024 | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1055 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for JOHURUL PARA UTTAR DHUPJHORA, T/W II, under METELLI CCC, [APPLICATION NO. 100000082757, Reference ID : 860274517] |  | Junior Engineer | BILL/00619/2023-2024 | BP/23-24/84 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0
1056 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "ADDITIONAL INFRA COST IRO NSC for UTTAR DHUPJHORA TW-II,METELI CCC " APPLICATION NO.100000115577 Reference ID : 860310307 |  | Junior Engineer | BILL/00881/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.55 | 0 | 0
1057 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri |  | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0
1058 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1059 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0
1060 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0
1061 | Jalpaiguri Division | Jalpaiguri Division | Balance work of Distribution System for Uttar Altagram Piped Water Supply Scheme within Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000167/2025-2026 | 2002/JD | 25/09/2025 | 90 | KAMAL DAS | 72.36 | 0 | 60
1062 | Jalpaiguri Division | Jalpaiguri Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Dhupguri block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer,HQ | Junior Engineer | ORD/000473/2023-2024 | 1293/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
1063 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000036/2023-2024 | 1116/JD | 24/08/2023 | 0 | Resource Division | 23.05 | 0 | 0
1064 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000127/2023-2024 | 1841/JD | 15/12/2023 | 0 | Resource Division | 11.08 | 0 | 0
1065 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003332348 , Reference ID : 403156800] | Assistant Engineer,HQ | Junior Engineer | BILL/01996/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.65 | 0 | 0
1066 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003332367 , Reference ID : 403156921] | Assistant Engineer,HQ | Junior Engineer | BILL/01998/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.73 | 0 | 0
1067 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for UTTAR ALTAGRAM, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003328084 , Reference ID : 403153544] | Assistant Engineer,HQ | Junior Engineer | BILL/01999/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.26 | 0 | 0
1068 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
1069 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1070 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR ALTAGRAM PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000432/2023-2024 | 1371/NMD | 09/08/2023 | 754 | M/S SAJAHAN CHOWDHURY | 33.24 | 27.46 | 95
1071 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0
1072 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
1073 | Jalpaiguri Division | Jalpaiguri Division | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000030/2024-2025 | 692/JD | 19/07/2024 | 120 | B.M CONSTRUCTION | 50.78 | 50.78 | 100
1074 | Jalpaiguri Division | Jalpaiguri Division | Additional work of Water Distribution Network in Madhya Daukimari PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. (Part- B) | Assistant Engineer,HQ | Junior Engineer | ORD/000177/2024-2025 | 1533/JD | 01/10/2024 | 45 | SUKES BASU MAJUMDAR | 66.83 | 24.95 | 100
1075 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Sinking of Additional Tube Well by Reverse Rotary including construction of Pump House and laying Rising Main etc. in connection with Jal Jeevan Mission of Madhya Daukimari PWSS at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000606/2024-2025 | 456/JD | 10/03/2025 | 387 | B. M CONSTRUCTION | 71.85 | 0 | 0
1076 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000018/2023-2024 | 162/JD | 28/04/2023 | 0 | Resource Division | 103.77 | 0 | 0
1077 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000133/2023-2024 | 1879/JD | 20/12/2023 | 0 | Resource Division | 11.14 | 0 | 0
1078 | Northern Mechanical | Jalpaiguri Division | Additional New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 100000103797 Reference ID : 860296017 | Assistant Engineer,HQ | Junior Engineer | BILL/00127/2024-2025 |  | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.01 | 0 | 0
1079 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MADHYA DAUKIMARI, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003388992 Reference ID : 403201630 | Assistant Engineer,HQ | Junior Engineer | BILL/00292/2024-2025 |  | 06/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0
1080 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MADHYA DAUKIMARI, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003256198, Reference ID : 403097555] | Assistant Engineer,HQ | Junior Engineer | BILL/01652/2023-2024 | 23-24/169&172 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.83 | 0 | 0
1081 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for MADHYA DAUKIMARI , T/W-I, under DHUPGURI CCC [APPLICATION NO. 4003269038 , Reference ID : 403107836] | Assistant Engineer,HQ | Junior Engineer | BILL/02030/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.3 | 0 | 0
1082 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
1083 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1084 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0
1085 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
1086 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with FHTC works for the habitation of Dangar Bari , Fokkorer Bari , near Chandrakanta School & Providing balanced Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangamali Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000167/2022-2023 | 1418/JD | 14/07/2022 | 15 | MRINMOY KANTI DUTTA | 4.62 | 2.11 | 1
1087 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for BHANGAMALI (REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003401391 Reference ID : 403212005 | Assistant Engineer,HQ | Junior Engineer | BILL/00285/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0
1088 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
1089 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1090 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BHANGAMALI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000460/2023-2024 | 1436/NMD | 10/08/2023 | 479 | SAIKAT SINHA | 11.5 | 10.22 | 80
1091 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORK SITES OF DIFFERENT PWSS AT NAGRAKATA ,MATIALI , AND MAL BLOCK UNDER JALPAIGURI |  | Junior Engineer | BILL/00936/2024-2025 |  | 22/11/2024 | 0 | DR. AMBARISH GHOSH | 17.82 | 0 | 0
1092 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.05.2024 to 30.06.2024)" |  | Junior Engineer | ORD/000037/2024-2025 | 143/JD | 29/04/2024 | 61 | GURUKUL INFOTECH | 3.16 | 3.16 | 100
1093 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Gajoldoba Tea Garden Piped Water Supply Scheme i.e, TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000071/2023-2024 | 422/A/JD | 07/06/2023 | 938 | M/S SIBU DEY AND CO. | 262.74 | 89.62 | 20
1094 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1095 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Gajoldoba TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000317/2024-2025 | 2038/JD | 21/11/2024 | 90 | M/S SIBU DEY AND CO. | 83.02 | 0 | 50
1096 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Protective Boulder Work, Land Development and approach road inside the premises at H/W Site for Gajaldoba Tea Garden PWSS in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000478/2024-2025 | 2429/JD | 24/12/2024 | 45 | M/S SIBU DEY AND CO. | 23.79 | 1.56 | 50
1097 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sub-Soil Investigation of proposed 300 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Gajaldoba Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000801/2024-2025 | 88-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
1098 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000077/2023-2024 | 1080/JD | 24/08/2023 | 0 | Resource Division | 25.38 | 0 | 0
1099 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000159/2023-2024 | 2025/JD | 09/01/2024 | 0 | Resource Division | 12.26 | 0 | 0
1100 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at GAJOLDOBA TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000110463 Reference ID : 860303003 |  | Junior Engineer | BILL/00452/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.41 | 0 | 0
1101 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for GAJOLDOBA TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003425403 Reference ID : 403230603 |  | Junior Engineer | BILL/00453/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1102 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at GAJOLDOBA TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000110462 Reference ID : 860303002 |  | Junior Engineer | BILL/00454/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.65 | 0 | 0
1103 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for GAJOLDOBA TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003425397 Reference ID : 403230604 |  | Junior Engineer | BILL/00455/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1104 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
1105 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1106 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAJOLDOBA TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000448/2023-2024 | 1387/NMD | 09/08/2023 | 570 | SUBODH KUMAR BANIK | 27.14 | 12.21 | 70
1107 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
1108 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Washabari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000115/2023-2024 | 395/A/JD | 05/06/2023 | 844 | S.S. CONSTRUCTION | 269.38 | 0 | 65
1109 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000067/2023-2024 | 1072/JD | 24/08/2023 | 0 | Resource Division | 27.2 | 0 | 0
1110 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000157/2023-2024 | 2021/JD | 09/01/2024 | 0 | Resource Division | 8.08 | 0 | 0
1111 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at WASHABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000114552 Reference ID : 860309142 |  | Junior Engineer | BILL/00621/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.95 | 0 | 0
1112 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for WASHABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003460295 Reference ID : 403254629 |  | Junior Engineer | BILL/00622/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1113 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at WASHABARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000114551 Reference ID : 860309141 |  | Junior Engineer | BILL/00623/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0
1114 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for WASHABARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003460294 Reference ID : 403254628 |  | Junior Engineer | BILL/00624/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1115 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
1116 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1117 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for WASHABARI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000416/2023-2024 | 1330/NMD | 08/08/2023 | 755 | SANJIB SAHA | 24.81 | 7.61 | 50
1118 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Rejuvenation of Jabramali PWSS i.e. TW, Pump Houses, Water distribution Network, Boundary wall, RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000361/2023-2024 | 1435/JD | 05/10/2023 | 910 | RAGHU DAS | 83.33 | 17.58 | 80
1119 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works & other ancillary works related to FHTC at different places of Jabramali PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000433/2022-2023 | 629/JD | 13/03/2023 | 30 | DREAM CONSTRUCTION | 12.41 | 12.39 | 100
1120 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Drainage line for IEP & other ancillary works at Head work site of JABRAMALI PWSS under Jalpaiguri Divisiopn PHE Dte. |  | Junior Engineer | ORD/000447/2023-2024 | 1281/RWS | 28/11/2023 | 20 | RAGHU DAS | 3.04 | 2.96 | 100
1121 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000094/2023-2024 | 1050/JD | 24/08/2023 | 0 | Resource Division | 4.8 | 0 | 0
1122 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for JABRAMALI(REJU), T/W-IV under MAYNAGURI CCC APPLICATION NO. 4003397114 Reference ID : 403208952 |  | Junior Engineer | BILL/00281/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.69 | 0 | 0
1123 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for JABRAMALI(REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003397105 Reference ID : 403208949 |  | Junior Engineer | BILL/00282/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0
1124 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply and Delivery of C.I special as when as required at T/W No-I of JABRAMALI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. |  | Junior Engineer | ORD/000066/2024-2025 | 1055/HQ/NMD | 21/06/2024 | 7 | B.B. CONCERNED | 0.73 | 0 | 100
1125 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JABRAMALI PWSS, TW NO-III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000173/2023-2024 | 1215/NMD | 26/07/2023 | 30 | SUNLIT | 22.15 | 0 | 0
1126 | Jalpaiguri Division | Jalpaiguri Division | Construction of 4th Pump House Site Boundary Wall, Foot Path, Drain pipeline for washout including interconnection works at Chauhaddi PWSS in connection with Jal Jeevan Mission at Block - Dhupguri Block under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000044/2025-2026 | 76/JSSD | 02/06/2025 | 30 | HARIPADA BANERJEE | 9.54 | 0 | 0
1127 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main/Direct Boosting Line for The Rejuvenation of Purba Magurmari P.W.S.S and Rejuvenation of Chouhaddi P.W.S.S. along with FHTC(PhaseVII) within the command area of Rejuventaion of Purba Magurmari P.W.S.S. in connection with Jal Jeevan Mission under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000397/2023-2024 | 1587/JD | 06/11/2023 | 726 | SAHA CONSTRUCTION | 37.11 | 0 | 30
1128 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for REJUVENATION OF CHAUHADDI PWSS, TW NO IV, under DHUPGURI CCC APPLICATION NO. 4003460809 Reference ID : 403255219 | Assistant Engineer,HQ | Junior Engineer | BILL/00970/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.39 | 0 | 0
1129 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
1130 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Samsing Tea Garden Piped Water Supply Scheme i.e TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000140/2023-2024 | 698/JD | 13/07/2023 | 903 | M/S. D.K. DEY & CO.. | 137.45 | 16.12 | 38
1131 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Samsing T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000170/2020-2021 | 1304/JD | 24/11/2020 | 60 | LOKNATH CONSTRUCTIOIN | 32.08 | 0 | 1
1132 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Water Distribution Network in Chalsa Zone-I in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000838/2023-2024 | 1938/JD | 02/01/2024 | 30 | ALICK DUTTA | 17.21 | 17.08 | 50
1133 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000081/2023-2024 | 1070/JD | 24/08/2023 | 0 | Resource Division | 19.77 | 0 | 0
1134 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) SAMSOING TG TW NO-III, METELI CCC " APPLICATION NO.100000107272 Reference ID : 860298682 |  | Junior Engineer | BILL/00323/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.79 | 0 | 0
1135 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | " New Service Connection Charge for (REJU) SAMSING TG TW NO-III, METELI CCC " APPLICATION NO.4003402763 Reference ID :403213198 |  | Junior Engineer | BILL/00327/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1136 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) SAMSING TG TW NO- V, METELI CCC " APPLICATION NO.100000108221 Reference ID : 860300681 |  | Junior Engineer | BILL/00379/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.82 | 0 | 0
1137 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | " New Service Connection Charge for (REJU) SAMSING TG TW NO- V, METELI CCC " APPLICATION NO.4003402758 Reference ID : 403213197 |  | Junior Engineer | BILL/00380/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1138 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SAMSING TG AREA PWSS, TW no III,IV,V,VI,VII in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000864/2023-2024 | 1810/NMD | 31/10/2023 | 732 | M/S P.P. ELECTRICALS | 56.9 | 24.7 | 50
1139 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Dakshin Kantadighi Kumarpara PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Mal under |  | Junior Engineer | ORD/000468/2022-2023 | 754/JD | 24/03/2023 | 817 | B RAI CONSTRUCTION COMPANY | 134.73 | 48.21 | 50
1140 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000005/2023-2024 | 149/JD | 28/04/2023 | 0 | Resource Division | 13.53 | 0 | 0
1141 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000153/2023-2024 | 2011/JD | 09/01/2024 | 0 | Resource Division | 2.64 | 0 | 0
1142 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for DAKSHIN KANTADIGHI KUMARPARA, TW NO-I, MAL CCC APPLICATION NO. 4003352329 Reference ID : 403172831 |  | Junior Engineer | BILL/00197/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1143 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at DAKSHIN KANTADIGHI KUMARPARA, TW NO-I, MAL CCC APPLICATION NO. 100000102150 Reference ID : 860294700 |  | Junior Engineer | BILL/00198/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.3 | 0 | 0
1144 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for DAKSHIN KANTADIGHI KUMARPARA, TW NO-II, MAL CCC APPLICATION NO. 4003352331 Reference ID : 403172836 |  | Junior Engineer | BILL/00199/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1145 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at DAKSHIN KANTADIGHI KUMARPARA, TW NO-II, MAL CCC APPLICATION NO. 100000102151 Reference ID : 860294701 |  | Junior Engineer | BILL/00200/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.83 | 0 | 0
1146 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
1147 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1148 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0
1149 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1150 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
1151 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Uttar Mouamari PWSS i.e TW, Pump Houses,Water distribution Network,OHR,RISING MAIN,FHTC etc,i.c.w.Jal Jeevan Mission at Block-Maynaguri under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000072/2023-2024 | 699/JD | 13/07/2023 | 993 | M/S SIBU DEY AND CO. | 250.23 | 149.78 | 60
1152 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall with gate, drain, Land Development and pathway and Laying Pipe line at H/W site of Uttar Mouamari Piped Water Supply Scheme under Jalpaiguri Division PHE, DTE. |  | Junior Engineer | ORD/000088/2024-2025 | 1298/JD | 05/09/2024 | 191 | M/S SIBU DEY AND CO. | 24 | 3.02 | 85
1153 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000075/2023-2024 | 1084/JD | 24/08/2023 | 0 | Resource Division | 47.75 | 0 | 0
1154 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000196/2023-2024 | 2059/JD | 10/01/2024 | 0 | Resource Division | 7.17 | 0 | 0
1155 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for UTTAR MAUAMARI, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376055 Reference ID : 403191647 |  | Junior Engineer | BILL/00150/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.2 | 0 | 0
1156 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for UTTAR MOUAMARI, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003401393 Reference ID : 403212002 |  | Junior Engineer | BILL/00286/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.05 | 0 | 0
1157 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
1158 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1159 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MAUAMARI PWSS, TW NO I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000457/2023-2024 | 1433/NMD | 10/08/2023 | 541 | RAJEEV RANJAN OJHA | 20.68 | 13.18 | 50
1160 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
1161 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0
1162 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000059/2021-2022 | 1085/JD | 05/07/2021 | 20 | GOUTAM DAS | 10.27 | 0 | 0
1163 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of KAJALDIGI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-C). |  | Junior Engineer | ORD/000088/2020-2021 | 1276/JD | 18/11/2020 | 90 | NISHITH RANJAN KARMAKAR | 39.12 | 78.21 | 0
1164 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldigi Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000106/2020-2021 | 442/RWS | 09/10/2020 | 30 | M/S.PAMPA CONSTRACTION | 4.73 | 4.71 | 0
1165 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Kajaldighi piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-D). |  | Junior Engineer | ORD/000398/2020-2021 | 74/RWS | 19/02/2021 | 15 | R.S CONSTRUCTION | 4.76 | 9.5 | 0
1166 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc jiti |  | Junior Engineer | VCH/000347/2021-2022 |  | 05/10/2021 | 0 | CALCON CONSTRUCTIONS | 17.1 | 0 | 0
1167 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC KAJAL DIGHI |  | Junior Engineer | VCH/000906/2021-2022 | BP-2021-22-133 | 14/12/2021 | 0 | PRAHLAD PRASAD SAHA | 4.83 | 0 | 0
1168 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC KAJALDIGHI |  | Junior Engineer | VCH/000909/2021-2022 | BP-2021-22-131 | 14/12/2021 | 0 | R.S CONSTRUCTION | 4.71 | 0 | 0
1169 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING HOUSE CONNECYTION AT KAJALDIGHI PWSS |  | Junior Engineer | VCH/001152/2020-2021 | 1055 | 11/01/2021 | 0 | R.S CONSTRUCTION | 4.44 | 0 | 0
1170 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC LATAGURI, MOULANI, KRANTI GP |  | Junior Engineer | VCH/001298/2021-2022 | BP-2021-22-467 | 28/03/2022 | 0 | SAHA CONSTRUCTION | 2.2 | 0 | 0
1171 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Simulguri PWSS Zone-I, II and III i.e. TW, Pump Houses, Water distribution , Water distribution Network , OHR, Rising Main , FHTC etc. Block - Rajganj under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000493/2022-2023 | 823/JD | 30/03/2023 | 733 | S.S. CONSTRUCTION | 709.21 | 586.27 | 75
1172 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall with gate, Drain, Land development ,Pathway at H/W Site & 2nd T/W site at Zone-I, H/W site , 2nd T/W & 3rd T/W site at Zone-II and H/W Site & 2nd T/W site at Zone-III including balance portion of laying distribution system with providing FHTC at SIMULGURI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000537/2024-2025 | 571/JD | 25/03/2025 | 372 | NEW KUNDU ENTERPRISE | 165.71 | 0 | 55
1173 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000009/2023-2024 | 153/JD | 28/04/2023 | 0 | Resource Division | 38.37 | 0 | 0
1174 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000180/2023-2024 | 2045/JD | 09/01/2024 | 0 | Resource Division | 18.16 | 0 | 0
1175 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SIMULGURI, T/W I,ZONE I under BELAKOBA CCC, [APPLICATION NO. 4003200020, Reference ID : 403051286] | Assistant Engineer,HQ | Junior Engineer | BILL/00620/2023-2024 | BP/23-24/81 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.5 | 0 | 0
1176 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SIMULGURI, T/W II,ZONE I under BELAKOBA CCC, [APPLICATION NO. 4003200017, Reference ID : 403051285] | Assistant Engineer,HQ | Junior Engineer | BILL/00621/2023-2024 | BP/23-24/81 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.04 | 0 | 0
1177 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SIMULGURI, T/W IIZONE II under BELAKOBA CCC, [APPLICATION NO. 4003200012, Reference ID : 403051284] | Assistant Engineer,HQ | Junior Engineer | BILL/00622/2023-2024 | BP/23-24/81 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.03 | 0 | 0
1178 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MANTABARI BFP SCHOOL, SIMULGURI,ZONE III, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003227613, Reference ID : 403072694] | Assistant Engineer,HQ | Junior Engineer | BILL/01164/2023-2024 | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0
1179 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SHINGIVISA NEAR MASJID, SIMULGURI,ZONE II, T/W III, under BELAKOBA CCC, [APPLICATION NO. 4003227623, Reference ID : 403072705] | Assistant Engineer,HQ | Junior Engineer | BILL/01165/2023-2024 | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.49 | 0 | 0
1180 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SIMULGURI,ZONE III, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003219227, Reference ID : 403065768] | Assistant Engineer,HQ | Junior Engineer | BILL/01166/2023-2024 | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.74 | 0 | 0
1181 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SIMULGURI,ZONE II, T/W II, under BELAKOBA CCC, [APPLICATION NO. 4003219239, Reference ID : 403065766] | Assistant Engineer,HQ | Junior Engineer | BILL/01167/2023-2024 | BP/23-24/144 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.14 | 0 | 0
1182 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIMULGURI PWSS, ZONE-I,TW NO I,II AND ZONE-II, TW NO- I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000024/2023-2024 | 466/NMD | 25/04/2023 | 30 | WEST BENGAL ENGINEERING CO. | 61.4 | 55.78 | 100
1183 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1184 | Northern Mechanical | Jalpaiguri Division | Additional work in connection with Supply, installation, commissioning and trial operation of electro-mechanical components for SIMULGURI PWSS, at TW no I (Z-I),and TW NO I,II,III (Z-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000181/2024-2025 | 693/SMSD | 14/06/2024 | 7 | WEST BENGAL ENGINEERING CO. | 0.87 | 0 | 100
1185 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SIMULGURI PWSS, ZONE-III, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000883/2022-2023 | 366/NMD | 29/03/2023 | 30 | M/S P.P. ELECTRICALS | 21.77 | 16.95 | 100
1186 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1187 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 0 | 100
1188 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Dakshin Dangapara PWSS Zone- II i.e, TW, Pump Houses, Water distribution Network, OHR, IEP, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block Maynaguri under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000084/2023-2024 | 296/JD | 15/05/2023 | 903 | M/S SURAJIT DEY AND CO. | 375.71 | 223.28 | 60
1189 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site of Dakhindangapara Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, PHE DTE. |  | Junior Engineer | ORD/000087/2024-2025 | 1172/JD | 23/08/2024 | 528 | M/S SURAJIT DEY AND CO. | 23.37 | 0 | 80
1190 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Dakshin Dangapara Zone II PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000527/2024-2025 | 109/JD | 16/01/2025 | 45 | M/S SURAJIT DEY AND CO. | 48.72 | 0 | 0
1191 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000193/2023-2024 | 2032/JD | 09/01/2024 | 0 | Resource Division | 8.53 | 0 | 0
1192 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Dakshin Dangapara,Zone-II T/W-I under BHOTPATTY CCC APPLICATION NO. 4003374121 Reference ID : 403190147 |  | Junior Engineer | BILL/00290/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.26 | 0 | 0
1193 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Dakshin Dangapara,Zone-II T/W-II under BHOTPATTY CCC APPLICATION NO. 4003374101 Reference ID : 403190146 |  | Junior Engineer | BILL/00291/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.25 | 0 | 0
1194 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
1195 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1196 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
1197 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0
1198 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Bhemtia PWSS i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000005/2023-2024 | 02/JD | 06/04/2023 | 947 | SCEC BOENTER KDAS JOINT VENTURE | 209.41 | 0 | 30
1199 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation including liquefaction due to close proximity of railway track near the proposed 100 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Bhemtia Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000803/2024-2025 | 93-HQ/JD | 17/03/2025 | 20 | R.B TESTING | 0.98 | 0 | 0
1200 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000012/2023-2024 | 156/JD | 28/04/2023 | 0 | Resource Division | 16.82 | 0 | 0
1201 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000135/2023-2024 | 1882/JD | 20/12/2023 | 0 | Resource Division | 4.11 | 0 | 0
1202 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
1203 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0
1204 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
1205 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Purba Dobbari PWSS i.e. TW, Pump Houses, Water distribution Network, Stand alone Mini OHR, RISING MAIN, FHTC etc.i.c.w. Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000076/2023-2024 | 946/JD | 08/08/2023 | 693 | SOMNATH ROY | 38.25 | 8.92 | 70
1206 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000195/2023-2024 | 2054/JD | 09/01/2024 | 0 | Resource Division | 0.18 | 0 | 0
1207 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
1208 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PURBA DOBBARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000427/2023-2024 | 1344/NMD | 08/08/2023 | 30 | S.D. CONCERN | 6.11 | 0 | 0
1209 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall at H/W site including rising main and interconnections of Tandu Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000013/2024-2025 | 474/JD | 21/06/2024 | 45 | PRADIP SAHA | 15.98 | 16.2 | 100
1210 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1211 | Jalpaiguri Division | Northern Mechanical Division | Sinking of 2 (Two) Nos. Big Dia Tube well by Modified DTH - ODEX Method at 1st & 2nd tube well site of Chhar Tandu and adjacent area Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000110/2024-2025 | 1415/JD | 20/09/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 27.63 | 100
1212 | Jalpaiguri Division | Northern Mechanical Division | Laying Distribution System along with laying of Rising Main, Pump Connection & Construction of 2 Nos. Pump House at 1st & 2nd Tube Well Site of Adjacent area of Chhar Tandu and Adjacent area Piped Water Sypply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000465/2025-2026 | 2498/JD | 09/12/2025 | 75 | ARUP SARKAR | 36.8 | 0 | 0
1213 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall at H/W site of Upper Tendu Forest (M) PWSS in connection with Jal Jeevan Mission at Block Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000540/2023-2024 | 295/JSSD | 27/09/2023 | 45 | NISHITH RANJAN KARMAKAR | 7.99 | 7.96 | 100
1214 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1215 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHAR TANDU PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000422/2023-2024 | 1336/NMD | 08/08/2023 | 30 | THE BANERJEE CONCERN | 24.53 | 0 | 0
1216 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0
1217 | Northern Mechanical | Northern Mechanical Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
1218 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1219 | Jalpaiguri Division | Northern Mechanical Division | Construction of Different Components of Tesimla PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000266/2023-2024 | 938/JD | 08/08/2023 | 180 | M/S RATAN KUMAR DAS GUPTA AND CO | 218.57 | 105.44 | 68
1220 | Jalpaiguri Division | Northern Mechanical Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including different components of Tesimala PWSS i.e. Tube Well, Pump House, Boundary Wall in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000547/2024-2025 | 104/JD | 15/01/2025 | 70 | APEX ENGINEERING | 39.7 | 0 | 0
1221 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000161/2023-2024 | 2014/JD | 09/01/2024 | 0 | Resource Division | 7.02 | 0 | 0
1222 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for TESIMLA, TW NO-I, MAL CCC APPLICATION NO. 4003352315 Reference ID : 403172834 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00201/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1223 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for TESIMLA, TW NO-II, MAL CCC APPLICATION NO. 4003352318 Reference ID : 403172835 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00202/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1224 | Northern Mechanical | Northern Mechanical Division | Infrastructure development cost for new service connection at TESIMLA,, TW NO-I & II, MAL CCC APPLICATION NO. 100000102139 Reference ID : 860293899 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00203/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.86 | 0 | 0
1225 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House, Sinking Tube Well, Laying Rising Main etc of Maynatali PWSS , in connection with Rejuvenation of Maynatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000132/2023-2024 | 405/A/JD | 06/06/2023 | 792 | ABHIJIT SARKAR | 47.88 | 36.8 | 25
1226 | Jalpaiguri Division | Jalpaiguri Division | Providing FHTC and Installation of Sluice Valve at different strategic point in connection with JJM of Mainatali Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000591/2024-2025 | 466/JD | 11/03/2025 | 385 | ARUP SARKAR | 24.16 | 0 | 0
1227 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000101/2023-2024 | 1057/JD | 24/08/2023 | 0 | Resource Division | 4.7 | 0 | 0
1228 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retrofitting of existing LDS under the command area of BHANDANI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-II |  |  | ORD/000207/2020-2021 | 42/JD | 06/01/2021 | 90 | DULAL CHOUDHURY | 38.46 | 12.41 | 1
1229 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Bhandani piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- III) |  |  | ORD/000210/2020-2021 | 49/JD | 07/01/2021 | 60 | ASIM GUPTA | 39.45 | 78.83 | 1
1230 | Jalpaiguri Division |  | FHTC BHANDANI |  |  | VCH/000249/2022-2023 | BP-2022-23-66 | 04/07/2022 | 0 | DULAL CHOUDHURY | 8.03 | 0 | 0
1231 | Jalpaiguri Division |  | FHTC BHANDABNI PWSS |  |  | VCH/000325/2021-2022 |  | 01/10/2021 | 0 | ASIM GUPTA | 18.14 | 0 | 0
1232 | Jalpaiguri Division |  | FHTC BHANDANI PWSS |  |  | VCH/000339/2021-2022 |  | 04/10/2021 | 0 | ASIM GUPTA | 18.14 | 0 | 0
1233 | Jalpaiguri Division |  | providing fhtc for Mathachulka pwss |  |  | VCH/000376/2021-2022 | 281 | 26/09/2021 | 0 | DEEP CONSTRUCTION | 4.67 | 0 | 0
1234 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00760/2024-2025 | BP-2024-25-448 | 03/10/2024 | 0 | FILL & SMILE | 0.09 | 0 | 0
1235 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00852/2024-2025 | BP-2024-25-484 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1236 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1991 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00985/2024-2025 | BP-2024-25-549 | 17/12/2024 | 0 | FILL & SMILE | 0.16 | 0 | 0
1237 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19/08/2024 to 18/02/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000079/2024-2025 | 1025/JD | 16/08/2024 | 184 | AJIJUL HAQUE | 0.88 | 0.91 | 0
1238 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Salugara PWSS zone-II i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000282/2023-2024 | 1256/JD | 13/09/2023 | 180 | S. N. POLYMERS PVT. LTD. | 335.88 | 61.22 | 25
1239 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Salugara PWSS zone-I i.e TW, Pump House distribution Network,OHR , RISING MAIN FHTC etc. in connection with Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000283/2023-2024 | 1258/JD | 13/09/2023 | 180 | S. N. POLYMERS PVT. LTD. | 346.56 | 100.54 | 35
1240 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (for the period of 19.02.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000689/2024-2025 | 53/HQ/JD | 18/02/2025 | 41 | AJIJUL HAQUE | 0.2 | 0.05 | 0
1241 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000045/2023-2024 | 1102/JD | 24/08/2023 | 0 | Resource Division | 65.27 | 0 | 0
1242 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000113/2023-2024 | 1507/JD | 13/10/2023 | 0 | Resource Division | 32.56 | 0 | 0
1243 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SALUGARA, ZONE-I,T/W No. II, under POWER HOUSE CCC , [APPLICATION NO. 4003334685, Reference ID : 403158908] | Assistant Engineer,HQ | Junior Engineer | BILL/02038/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.9 | 0 | 0
1244 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SALUGARA, ZONE-II,T/W No. I, under POWER HOUSE CCC , [APPLICATION NO. 4003334683, Reference ID : 403158637] | Assistant Engineer,HQ | Junior Engineer | BILL/02039/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.7 | 0 | 0
1245 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SALUGARA, ZONE-I,T/W No. I, under POWER HOUSE CCC , [APPLICATION NO. 4003334689, Reference ID : 403158907] | Assistant Engineer,HQ | Junior Engineer | BILL/02040/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.17 | 0 | 0
1246 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SALUGARA , T/W-II, ZONE-II under POWER HOUSE CCC [APPLICATION NO. 4003341484 , Reference ID : 403163817] | Assistant Engineer,HQ | Junior Engineer | BILL/02041/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0
1247 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1248 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
1249 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SALUGARA PWSS, ZONE-I AND II, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000660/2023-2024 | 1474/NMD | 17/08/2023 | 868 | CHOWDHURY AND BASU ENTERPRISE | 43.27 | 29.47 | 85
1250 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF DIFFERENT COMPONENTS OF DAKSHIN JHARALTA PWSS i.e, TW, PUMP HOUSES, WATER DISTRIBUTION NETWORK, OHR, RISING MAIN, FHTC etc. IN CONNECTION WITH JAL JEEVAN MISSION AT BLOCK- DHUPGURI UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000378/2023-2024 | 1540/JD | 23/10/2023 | 914 | SCEC BOENTER AND KDAS JOINT VENTURE | 864.13 | 286.94 | 70
1251 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000004/2024-2025 | 55/JD | 09/04/2024 | 0 | Resource Division | 108.57 | 0 | 0
1252 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000128/2023-2024 | 1842/JD | 15/12/2023 | 0 | Resource Division | 21.75 | 0 | 0
1253 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DAKSHIN JHARALTA, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003356729 Reference ID : 403176999 | Assistant Engineer,HQ | Junior Engineer | BILL/00128/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.35 | 0 | 0
1254 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DAKSHIN JHARALTA, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003328082 , Reference ID : 403153543] | Assistant Engineer,HQ | Junior Engineer | BILL/01995/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.97 | 0 | 0
1255 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DAKSHIN JHARALTA, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003328083 ; Reference ID : 403153545] | Assistant Engineer,HQ | Junior Engineer | BILL/02017/2023-2024 | BP/23-24/311 | 21/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.33 | 0 | 0
1256 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN JHARALTA PWSS,at TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000855/2023-2024 | 1805/NMD | 31/10/2023 | 701 | PADMA ENGINEERING CO. | 34.35 | 22.16 | 95
1257 | Jalpaiguri Division | Jalpaiguri Division | CONST OF OHR FOR DABGRAM SOUTH ZONE PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000518/2021-2022 | 448/21-22 | 04/10/2021 | 0 | PARESH CHANDRA GUHA | 1.57 | 0 | 0
1258 | Jalpaiguri Division | Jalpaiguri Division | FHTC PATKIDAHA | Assistant Engineer,HQ | Junior Engineer | VCH/001430/2021-2022 | BP-2021-22-441 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 4.77 | 0 | 0
1259 | Jalpaiguri Division | Jalpaiguri Division | FHTC PATKIDAHA | Assistant Engineer,HQ | Junior Engineer | VCH/001431/2021-2022 | BP-2021-22-442 | 26/03/2022 | 0 | SUKES BASU MAJUMDAR | 2.6 | 0 | 0
1260 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Dambari Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000197/2020-2021 | 1541/JD | 31/12/2020 | 45 | KULDIP KAPOOR | 24.3 | 32.14 | 80
1261 | Jalpaiguri Division | Jalpaiguri Division | PROVIDING FHTC UNDER PORA PARA | Assistant Engineer,HQ | Junior Engineer | VCH/001174/2020-2021 | 1044 | 11/01/2021 | 0 | SUKES BASU MAJUMDAR | 4.45 | 0 | 0
1262 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Chrarbari Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-A). |  | Junior Engineer | ORD/000107/2020-2021 | 466/RWS | 15/10/2020 | 30 | M/S.DEY & ROY CHOUDHURY | 4.71 | 8.84 | 0
1263 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHARERBARI piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000112/2020-2021 | 1284/JD | 18/11/2020 | 45 | RAGHU DAS | 15.22 | 14.94 | 0
1264 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Part-D) |  | Junior Engineer | ORD/000192/2020-2021 | 1552/JD | 31/12/2020 | 45 | NEW KUNDU ENTERPRISE | 27.7 | 55.03 | 1
1265 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000222/2020-2021 | 100/JD | 18/01/2021 | 45 | SANKAR DAS | 21.16 | 19.59 | 100
1266 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHRERBARI piped Water Supply Scheme at Maynaguri Block under under Jalpaiguri Division, PHE Dte. (Part-F) |  | Junior Engineer | ORD/000227/2020-2021 | 91/JD | 14/01/2021 | 45 | KAMALESH SEN | 20.95 | 20.58 | 100
1267 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with under the command area of Charerbari Water Supply Scheme at Managuri Block under Jalpaiguri Division, P.H.E. Dte. (PHASE - G) |  | Junior Engineer | ORD/000285/2022-2023 | 650/RWS | 21/10/2022 | 20 | NEW KUNDU ENTERPRISE | 2.42 | 1.83 | 100
1268 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna for providing drinking water under the command area of Charerbari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000328/2020-2021 | 222/JD | 12/02/2021 | 45 | M/S DEY & ROY CHOUDHURY | 24.4 | 11.28 | 40
1269 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Restoration work in connection with FHTC works for the habitation of Bideshi Para,Chobarbari, Thonthonerbari and Dakshin Ghutkara under Charerbari W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000530/2021-2022 | 176/RWS | 03/03/2022 | 15 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0
1270 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing fhtc for charer bari pwss |  | Junior Engineer | VCH/000316/2021-2022 |  | 01/10/2021 | 0 | NEW KUNDU ENTERPRISE | 2.02 | 0 | 0
1271 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC CHARERBARI WSS |  | Junior Engineer | VCH/001295/2021-2022 | BP-2021-22-415 | 23/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.16 | 0 | 0
1272 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DWARIKAMARI |  | Junior Engineer | VCH/001362/2021-2022 | BP-2021-22-524 | 30/03/2022 | 0 | SUBRATA GOSWAMI | 8.41 | 0 | 0
1273 | Siliguri W/S Division | Siliguri Sub-Division | I ssue of fuel for office vehicles of E.E, AE-I Division and AE sub division Month of september(20/09/24 to 27/09/24) & october ( 01/10/24 to 04/10/24)and 1)vehical no WB -76A4921 2) )vehical no-WB-769630 3)vehical no WB-76A-7170 4)vehical no-WB -73D0335 | Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/00343/2024-2025 | BP-2024-25-125 | 11/11/2024 | 0 | SONA PETROL PUMP | 0.42 | 0 | 0
1274 | Siliguri W/S Division | Siliguri Sub-Division | Further continuation order for hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of The Executive Engineer, Siliguri W/S Division, P.H.E. Dte. for the period from 01.09.2023 to 31.12.2023 (for Assistant Engineer, Siliguri W/S Division, P.H.E. Dte. i.e. 04 (four) months. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000207/2023-2024 | 1428/SWSD | 24/08/2023 | 122 | HIMADRI DAM | 0.59 | 0 | 0
1275 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JALDHARA /JAL SAPNA UNDER THE COMMAND AREA OF HILLA T.G. AREA PIPED WATER SUPPLY SCHEME AT NAGRAKATA BLOCK UNDER JALPAIGURI DIVISION, PHE DTE. |  | Junior Engineer | ORD/000326/2021-2022 | 149/JD | 19/01/2022 | 30 | SCEC BOENTER KDAS JOINT VENTURE | 26.95 | 0 | 100
1276 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | hire charge |  | Junior Engineer | VCH/000534/2022-2023 | BP-2021-22-208 | 29/09/2022 | 0 | RAKESH SARKAR | 0.34 | 0 | 0
1277 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | car hire charge |  | Junior Engineer | VCH/000535/2022-2023 | BP-2021-22-207 | 29/09/2022 | 0 | APIKUL ALI | 0.34 | 0 | 0
1278 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No WB 76 9978 for the Month of July 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00589/2024-2025 | BP-2024-25-338 | 30/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1279 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 15.07.2024 to 14.10.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000020/2024-2025 | 561/JD | 03/07/2024 | 92 | APIKUL ALI | 0.44 | 0.27 | 0
1280 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-I) udner Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000033/2022-2023 | 967/JD | 20/04/2022 | 90 | NARAYAN CHANDRA SAHA | 85.51 | 59.46 | 100
1281 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-III) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000041/2022-2023 | 864/JD | 01/04/2022 | 1007 | M/S. D.K. DEY & CO.. | 63.77 | 35.4 | 100
1282 | Jalpaiguri Division | Jalpaiguri Division | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 2nd tube well site of Chamurchi Piped Water Supply Scheme (Zone-III, Chunabhati) of Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000063/2024-2025 | 932/JD | 07/08/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 17.61 | 17.99 | 100
1283 | Jalpaiguri Division | Jalpaiguri Division | Construction of 200 Cu.M. R.C.C. Over Head Reservoir of 16 Mtr. Staging Height one No Pump House (5.40m x 3.60m) and other related works at Zone - I of Chamurchi Tea Garden Area Augmentation P.W.S.S. udner Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000147/2022-2023 | 1540/JD | 04/08/2022 | 180 | SAPTASWA SARKAR | 63.69 | 62.46 | 100
1284 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Chamurchi Tea Garden Area Augmentation Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000149/2022-2023 | 1423/JD | 15/07/2022 | 1267 | M/S A.B.G. CONSTRUCTION | 151.77 | 50.68 | 10
1285 | Jalpaiguri Division | Jalpaiguri Division | Construction of rig approach road for the various zone of augmentation Chamurchi T.G.PWSS under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000159/2022-2023 | 1500/JD | 27/07/2022 | 15 | PARAMJYOTI ENTERPRISE | 1.77 | 1.78 | 0
1286 | Jalpaiguri Division | Jalpaiguri Division | Sinking of one no. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at chunavati chamurchi Zone-III under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000163/2023-2024 | 801/JD. | 24/07/2023 | 30 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 16.55 | 16.03 | 80
1287 | Jalpaiguri Division | Jalpaiguri Division | Sinking of two nos. Big dia Tube Well (200 x 150mm dia) by Modified DTH - ODEX method of drilling at Siv Mandir area of Chamurchi zone-II under ¿Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour colony)¿ under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2023-2024 | 802/JD. | 24/07/2023 | 30 | EFFLUENT AND WATTERTREATEMENT ENGINEERS(P) LTD. | 33.1 | 32.57 | 54
1288 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall at 3rd T/W site of Chamurchi Tea Garden Piped W/S scheme (Zone-II, Gumpha Line) along with pipeline repairing and other allied works in connection with JJM at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000190/2025-2026 | 2156/JD | 29/10/2025 | 30 | DITIPRIYA CHOWDHURY | 11.72 | 0 | 0
1289 | Jalpaiguri Division | Jalpaiguri Division | Shifting of Rising main due to widening and Construction of New Culvert at Hatinala and other ancillary works related to the Rising main inside the Head works site of Chamurchi Bazar P.W.S.S. under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000217/2022-2023 | 1807/JD | 14/09/2022 | 21 | RANA DEY | 3.57 | 3.56 | 0
1290 | Jalpaiguri Division | Jalpaiguri Division | Two nos Pump House with restoration of Sanitary Plumbing System including repairing of C.W.R. raising of valve chamber height and making of Cement Concrete Pathway at Chamurchi Forest Busty Head Works Site under Augmentation of Chamurchi T.G. Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000218/2022-2023 | 1808/JD | 14/09/2022 | 21 | M/S KARMAKAR CONSTRACTION | 4.17 | 3.69 | 100
1291 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Chamurchi T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000224/2022-2023 | 1853/JD | 16/09/2022 | 45 | PARAMJYOTI ENTERPRISE | 4.65 | 4.78 | 0
1292 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (Phase - II ) in connection with Jal Jeevan Mission for Augmentation of Chamurchi T.G. P.W.S.S (Zone -III) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000368/2023-2024 | 1463/JD | 06/10/2023 | 697 | MALAY BHOWMIK | 27.18 | 0 | 50
1293 | Jalpaiguri Division | Jalpaiguri Division | Laying of Individual D.I. Rising Main Including common manifold from 1st Tube Well to 2nd Tube Well and to Head Works site including internal connection of 1st and 2nd Tube Well site with Functional Household Tap Connection in connection with Jal Jeevan Mission under Augmentation of Chamurchi T.G. Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000399/2022-2023 | 627/JD | 13/03/2023 | 45 | SANKAR DAS | 47.49 | 35.55 | 50
1294 | Jalpaiguri Division | Jalpaiguri Division | Special repairing of RCC Over Head Reservoir for Chamurchi Bazar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte.. | Assistant Engineer,HQ | Junior Engineer | ORD/000443/2021-2022 | 284/JD | 02/02/2022 | 60 | SUKES BASU MAJUMDAR | 8.29 | 8.32 | 1
1295 | Jalpaiguri Division | Jalpaiguri Division | Construction of Two Nos Boundary Wall (at OHR site and alternate 1 st tube well Site) including construction of surface drain,making of pathway,Land development work,with supplying fitting fixing CIDF pipe,modification of pump house and constructionof rest rooms with construction of culvert along with scouring prevention work on the approach way including development of approach way with other allied works for the various site within the command area of augmentation of Chamurchi T.G. Area P.W.S.S.Zone - I under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000523/2023-2024 | 1819/JD | 14/12/2023 | 45 | SAPTASWA SARKAR | 64.94 | 54.31 | 100
1296 | Jalpaiguri Division | Jalpaiguri Division | Resistivity Test for Four Nos.Tube Well for Chamurchi Tea Garden area Augmentation Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000576/2021-2022 | 142/JD | 18/01/2022 | 15 | PARAMJYOTI ENTERPRISE | 0.6 | 0.6 | 0
1297 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000600/2023-2024 | 1982/JD | 03/01/2024 | 182 | APIKUL ALI | 0.88 | 1.01 | 30
1298 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) (w.e.f. 14.01.2024) | Assistant Engineer,HQ | Junior Engineer | ORD/000601/2023-2024 | 1983/JD | 03/01/2024 | 182 | RAKESH SARKAR | 0.88 | 1.11 | 30
1299 | Jalpaiguri Division | Jalpaiguri Division | Construction of 3rd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2023-2024 | 2303/JD | 07/02/2024 | 45 | DITIPRIYA CHOWDHURY | 4.9 | 4.9 | 100
1300 | Jalpaiguri Division | Jalpaiguri Division | Construction of 2nd Tubewell site Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement for at airtel site of Chunavati Chamurchi Zone-II under "Augmentation of Chamurchi Tea Garden (Chamurchi Bazar & Chamurchi Forest Busty & Labour Colony)" under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000603/2023-2024 | 2304/JD | 07/02/2024 | 45 | MAA SHANTI BUILDERS | 4.9 | 4.9 | 100
1301 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000049/2023-2024 | 1105/JD | 24/08/2023 | 0 | Resource Division | 160.42 | 0 | 0
1302 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000091/2024-2025 | 2222/JD | 01/12/2024 | 0 | Resource Division | 21.08 | 0 | 0
1303 | Jalpaiguri Division | Jalpaiguri Division | CHAMURCHI BAZAR | Assistant Engineer,HQ | Junior Engineer | VCH/000085/2022-2023 | BP-2022-2023-42 | 24/05/2022 | 0 | RANA DEY | 3.83 | 0 | 0
1304 | Northern Mechanical | Jalpaiguri Division | Installation of Infrastructure COST at CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. I, Zone I under BANARHAT CCC [APPLICATION NO. 100000064277 ; Reference ID : 860253067] | Assistant Engineer,HQ | Junior Engineer | BILL/00003/2022-2023 | BP/22-23/107 | 08/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.12 | 0 | 0
1305 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. I, Zone I under BANARHAT CCC [APPLICATION NO. 4003023651 ; Reference ID : 402902659] | Assistant Engineer,HQ | Junior Engineer | BILL/00004/2022-2023 | BP/22-23/107 | 08/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0
1306 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for CHAMURCHI TEA GARDEN W/S SCHEME, T/W No. II, Zone I under BANARHAT CCC [APPLICATION NO. 4003019807 ; Reference ID : 402902658] | Assistant Engineer,HQ | Junior Engineer | BILL/00006/2022-2023 | BP/22-23/107 | 08/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0
1307 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for CHAMURCHI (CHUNABHATI) ZONE:-III, T/W-III, under BANARHAT CCC APPLICATION NO. 4003418431 Reference ID : 403225913 | Assistant Engineer,HQ | Junior Engineer | BILL/00394/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.07 | 0 | 0
1308 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AUG CHAMURCHI TEA GARDEN, T/W No. II, ZONE II under BANARHAT CCC [APPLICATION NO. 4003333013 , Reference ID : 403157465] | Assistant Engineer,HQ | Junior Engineer | BILL/02004/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0
1309 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AUG CHAMURCHI TEA GARDEN, T/W No. I, ZONE II under BANARHAT CCC [APPLICATION NO. 4003333005 , Reference ID : 403157463] | Assistant Engineer,HQ | Junior Engineer | BILL/02005/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 16 | 0 | 0
1310 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TEA GARDEN (CHAMURCHI BAZAR and CHAMURCHI FOREST BUSTY and LABOUR COLONY) PWSS, ZONE-II, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000441/2023-2024 | 1380/NMD | 09/08/2023 | 30 | THE BANERJEE CONCERN | 26.24 | 11.08 | 40
1311 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000558/2022-2023 | 64/DSD | 23/05/2022 | 15 | M/S ROYAL ENTERPRISE | 0.71 | 0.49 | 0
1312 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000583/2022-2023 | 29/DSD | 21/04/2022 | 15 | SAHA ENTERPRISE | 0.71 | 0.21 | 0
1313 | Northern Mechanical | Jalpaiguri Division | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000642/2022-2023 | 152/DSD | 26/07/2022 | 7 | SUMON ELECTRICAL | 0.41 | 0.41 | 0
1314 | Northern Mechanical | Jalpaiguri Division | Carrying out Surging, Development and Yield Testing works for a Rig Bored Big Dia Tube well (BDTW) by Odex-165 method of drilling for Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000643/2022-2023 | 183/DSD | 18/08/2022 | 7 | SUMON ELECTRICAL | 0.41 | 0.41 | 0
1315 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHAMURCHI TG PWSS, ZONE-I, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000690/2022-2023 | 1449/NMD | 21/12/2022 | 30 | SARKAR ELECTRIC | 26.26 | 26.26 | 100
1316 | Northern Mechanical | Jalpaiguri Division | Additional work in connection Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of CHAMURCHI TG (Z-I) PWSS, at TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000793/2023-2024 | 228/HQ/NMD | 15/09/2023 | 15 | SARKAR ELECTRIC | 1.44 | 1.43 | 100
1317 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000823/2021-2022 | 313/DSD | 24/01/2022 | 15 | SAHA ENTERPRISE | 0.49 | 0.16 | 0
1318 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-II (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000824/2021-2022 | 315/DSD | 25/01/2022 | 15 | SAHA ENTERPRISE | 0.49 | 0.49 | 0
1319 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000872/2021-2022 | 327/DSD | 07/02/2022 | 15 | SAHA ENTERPRISE | 0.49 | 0.16 | 0
1320 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000908/2021-2022 | 346/DSD | 22/02/2022 | 15 | SAHA ENTERPRISE | 0.16 | 0.09 | 0
1321 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Tubewell (BDTW) by deparmental Rig M/C ITH-20, by Odex-115 method of drilling at Augmentation of Chamurchi TG W/S Scheme, TW-I (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000911/2021-2022 | 360/DSD | 02/03/2022 | 15 | SAHA ENTERPRISE | 0.16 | 0.09 | 100
1322 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction Of approach roads for Arjimaria Kamala Pokhari Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(3rd & 4thSite) |  | Junior Engineer | ORD/000411/2022-2023 | 166/RWS | 28/02/2023 | 14 | R.S CONSTRUCTION | 1.61 | 1.3 | 1
1323 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Araji Maria Kamala Pukhari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000489/2022-2023 | 288/RWS | 29/03/2023 | 21 | JAYDEB SAHA | 3.54 | 3.53 | 100
1324 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIMARIA KAMOLAPOKORI piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000640/2020-2021 | 19/JD | 14/01/2021 | 60 | BILTU DAS | 36.92 | 1.99 | 1
1325 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000716/2021-2022 | 2229/JD | 27/12/2021 | 60 | SABITA ENTERPRISE | 11.43 | 11.52 | 1
1326 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Argimaria Kamolapokori Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000884/2021-2022 | 386/JD | 10/02/2022 | 60 | SUSANTA GHOSH | 11.44 | 11.34 | 100
1327 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000053/2023-2024 | 1086/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0
1328 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | REJ. ARAJIMARIA KAMLA PUKARI PWSS |  | Junior Engineer | VCH/000912/2021-2022 | BP-2021-22-137 | 14/12/2021 | 0 | R.S CONSTRUCTION | 5.05 | 0 | 0
1329 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000007/2022-2023 | 210/NMD | 04/04/2022 | 21 | SAIKAT SINHA | 1.92 | 1.92 | 0
1330 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for TW NO. III, ARJI MARIA KAMALA PUKHARI (REJU) PIPED WATER SUPPLY SCHEME, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000122/2022-2023 | 859/NMD | 18/07/2022 | 30 | THE BANERJEE CONCERN | 7.61 | 7.61 | 100
1331 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for TW NO. IV, ARJI MARIA KAMALA PUKHARI (REJU) PIPED WATER SUPPLY SCHEME, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000123/2022-2023 | 860/NMD | 18/07/2022 | 30 | M/S UTPAL CHAKRABORTY & CO. | 7.6 | 7.6 | 100
1332 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000269/2022-2023 | 1013/NMD | 28/07/2022 | 21 | MAA ENTERPRISES | 1.87 | 0 | 0
1333 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of ARJI MARIA KAMALA PUKHARI W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000270/2022-2023 | 1014/NMD | 28/07/2022 | 21 | M/S ANJALI ENTERPRISE | 1.89 | 1.88 | 100
1334 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply delivery of the different UPVC materials for Reverse Rotary Circulation method of drilling for construction of BDTW for the Rejuvenation of Arji Maria Kamala Pukhari PWSS, Block - Jalpaiguri, Dist.- Jalpaiguri, at deptt. Stack-Yard at Fulbari under NMSD (D), PHE, Dte. |  | Junior Engineer | ORD/000654/2022-2023 | 1363/NMD | 02/12/2022 | 30 | SARKAR ELECTRIC | 11.59 | 11.59 | 0
1335 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. III, under PANDAPARA CCC, [APPLICATION NO. 400296685, Reference ID : 402852995] |  | Junior Engineer | VCH/000846/2022-2023 | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.46 | 0 | 0
1336 | Northern Mechanical | RWS Jalpaiguri Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. III, under PANDAPARA CCC, [APPLICATION NO. 10000057368, Reference ID :860239578] |  | Junior Engineer | VCH/000847/2022-2023 | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.48 | 0 | 0
1337 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 4002964712, Reference ID : 402852793] |  | Junior Engineer | VCH/000848/2022-2023 | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
1338 | Northern Mechanical | RWS Jalpaiguri Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT ARAJI MARIA KAMALA PUKHARI (REJU) W/S SCHEME, T/W No. IV, under PANDAPARA CCC, [APPLICATION NO. 10000057368, Reference ID :860239578] |  | Junior Engineer | VCH/000849/2022-2023 | BP/22-23/45 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.45 | 0 | 0
1339 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation Banerhat Bazar Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000008/2024-2025 | 421/JD | 12/06/2024 | 30 | PRADIP SAHA | 19.04 | 0 | 60
1340 | Jalpaiguri Division | Jalpaiguri Division | Emergent minor repairing of Pump House and Chlorine room with Construction of Toilet and Sanitary plumbing system located near Banarhat Thana and repairing works of Pump House near Banarhat Panchayat Office with other ancillary works for Augmentation of Banarhat Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2022-2023 | 1305/JD | 14/06/2022 | 21 | SANKAR DAS | 3.54 | 3.5 | 100
1341 | Jalpaiguri Division | Jalpaiguri Division | Minor Repairing of Overhead Reservoir, Boundary Wall and Pathway and Allied Works under Augmentation of Banarhat Bazar Zone - I in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000121/2024-2025 | 1266/JD | 02/09/2024 | 30 | PRADIP SAHA | 8.05 | 7.69 | 100
1342 | Jalpaiguri Division | Jalpaiguri Division | Construction of Approach Culvert at Head Work Site of Banarhat Bazar Zone-II PWSS in Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000123/2024-2025 | 1273 | 03/09/2024 | 30 | PRADIP SAHA | 8.67 | 6.41 | 100
1343 | Jalpaiguri Division | Jalpaiguri Division | Shifting and Extension of pipeline for widening and strengthening of B.R.O Road From Chamurchi More to Moraghat More along with other L.D.S. Repairing and other anciellary works related to L.D.S. within the command area of Augmentation of Banerhat Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000242/2022-2023 | 1949/JD | 13/10/2022 | 902 | SANKAR DAS | 8.96 | 5.79 | 100
1344 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with Rising Main Connection of Banarhat Bazar (Zone-II) Piped water supply Scheme, at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000293/2022-2023 | 2051/JD | 02/11/2022 | 842 | GLOBAL POWER & CONSTRUCTION CO. | 108.22 | 71.76 | 41
1345 | Jalpaiguri Division | Jalpaiguri Division | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing and Boundary Wall with land development at Head Works site for Augmentation of Banarhat Bazar (zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000331/2022-2023 | 2486/JD | 28/12/2022 | 150 | PRADIP SAHA | 107.22 | 102.52 | 95
1346 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with Rising Main Connection, of Banarhat Bazar ( Zone-I) Piped water Supply Scheme , at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000338/2022-2023 | 2518/JD | 30/12/2022 | 1099 | PRADIP SAHA | 68.1 | 33.17 | 70
1347 | Jalpaiguri Division | Jalpaiguri Division | Laying of Rising Main Connection between Head works Pump House site and Tube Well site including Internal Pump Connection along with Construction of Pump House for Zone-I of Augmentation of Banarhat PWSS i.c.w. Jal Jeevan Mission at under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000393/2022-2023 | 569/JD | 03/03/2023 | 21 | PARAMJYOTI ENTERPRISE | 9.04 | 8.42 | 100
1348 | Jalpaiguri Division | Jalpaiguri Division | Emergency reparing and laying of distribution system near Gadi khana parallel to the Hatinala and indian oil pipeline in connection with for augmentation of Banarhat Bazar PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000439/2022-2023 | 681/JD | 16/03/2023 | 21 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 5.54 | 5.53 | 100
1349 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (5.40m x 3.60m) internal size with sanitary & plumbing arrangement at Head work site and Providing Functional Household Tap Connection (FHTC) for Augmentation of Banarhat Piped Water Supply Scheme (Zone-II) under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000531/2023-2024 | 1851/JD | 15/12/2023 | 262 | SOUVIK SAHA | 10.02 | 9.65 | 100
1350 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Augmentation of Banerhat Bazar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000586/2023-2024 | 2335/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 16.67 | 100
1351 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in Connection with Jal Jeevan Mission for Augmentation of Banerhat Bazar Piped Water Supply Scheme (Zone-I) under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000667/2023-2024 | 2459/JD | 23/02/2024 | 192 | PRADIP SAHA | 19.04 | 0 | 100
1352 | Jalpaiguri Division | Jalpaiguri Division | Interconnection work to connect Pump House, reservoir and distribution network and other allied work of Banarhat Bazar zone- II piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000824/2023-2024 | 2752/JD | 14/03/2024 | 15 | PRADIP SAHA | 18.08 | 16.27 | 100
1353 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000054/2023-2024 | 1096/JD | 24/08/2023 | 0 | Resource Division | 106.7 | 0 | 0
1354 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000080/2024-2025 | 2211/JD | 01/12/2024 | 0 | Resource Division | 24.1 | 0 | 0
1355 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 4003103092, Reference ID : 402976412] | Assistant Engineer,HQ | Junior Engineer | BILL/00464/2023-2024 | BP/23-24/31 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1356 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 100000073457, Reference ID : 860265207] | Assistant Engineer,HQ | Junior Engineer | BILL/00465/2023-2024 | BP/23-24/46 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.12 | 0 | 0
1357 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 4003103092, Reference ID : 402976412] | Assistant Engineer,HQ | Junior Engineer | BILL/00785/2022-2023 |  | 20/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1358 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for BANARHAT BAZAR NEAR PHE BUNGLOW, ZONE-II, T/W I, under BANARHAT CCC, [APPLICATION NO. 100000073457, Reference ID : 860265207] | Assistant Engineer,HQ | Junior Engineer | BILL/00786/2022-2023 |  | 20/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.12 | 0 | 0
1359 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for BANERHAT BAZAR NEAR BDO OFFICE, T/W IV, ZONE - I, under BANARHAT CCC [APPLICATION NO. 4003103095 ; Reference ID : 402976411] | Assistant Engineer,HQ | Junior Engineer | BILL/00999/2023-2024 | BP/23-24/114 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1360 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for BANERHAT BAZAR NEAR BDO OFFICE, T/W IV, ZONE - I, under BANARHAT CCC [APPLICATION NO. 100000083816 ; Reference ID : 860275316] | Assistant Engineer,HQ | Junior Engineer | BILL/01000/2023-2024 | BP/23-24/114 | 06/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.11 | 0 | 0
1361 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig m/c ITH-20, by Odex-165 method of drilling at Banerhat Bazar PWSS at TW-IV (Zone-I), Block - Dhupguri, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000812/2022-2023 | 313/DSD | 06/03/2023 | 10 | M/S MATRI CONSTRUCTION | 0.49 | 0.49 | 100
1362 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BANERHAT BAZAR PWSS, AT TW no IV (ZONE-I) AND AT TW NO I (ZONE-II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000889/2022-2023 | 372/NMD | 29/03/2023 | 30 | ANIMA ENTERPRISE | 20.46 | 20.46 | 100
1363 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAYASAILYA T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-IV) |  | Junior Engineer | ORD/000032/2021-2022 | 752/JD | 13/05/2021 | 1183 | GAP ENGINEERS ENTERPRISE | 22.63 | 0 | 90
1364 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasailya T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000219/2020-2021 | 13/JD | 04/01/2021 | 45 | GOUTAM DAS | 26.22 | 52.25 | 0
1365 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) |  | Junior Engineer | ORD/000223/2020-2021 | 94/JD | 14/01/2021 | 45 | SAPTASWA SARKAR | 28 | 33.18 | 0
1366 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Nayasaily T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  | Junior Engineer | ORD/000245/2020-2021 | 560/JSSD | 01/02/2021 | 15 | PRIYABRATA KARMAKAR | 4.84 | 9.66 | 0
1367 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) |  | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0.37 | 0
1368 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fuel charges |  | Junior Engineer | BILL/00249/2022-2023 | BP-2022-23-469 | 23/02/2023 | 0 | FILL & SMILE | 0.8 | 0 | 0
1369 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | supply of fuel |  | Junior Engineer | BILL/00395/2022-2023 | BP-2022-23-557 | 29/03/2023 | 0 | FILL & SMILE | 0.36 | 0 | 0
1370 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1371 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Rising Main, Internal Delivery & Iron Elimination Plant (IEP) connection for Zone-II under Augmentation of Kranti Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000009/2025-2026 | 892/JD | 08/05/2025 | 20 | BIMAN DAS | 14.85 | 0 | 0
1372 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repairing of 3rd T/W site Pump House with Sanitary and Plumbing arrangement for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000020/2023-2024 | 253/JD | 10/05/2023 | 21 | NARAYAN CHANDRA ADHIKARY | 2.34 | 2.32 | 100
1373 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent restoration of pipeline at Kodalkati area under Kranti GP and construction of periferial boundary including retaining structure at H/W Site for Augmentation of Kranti zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000024/2022-2023 | 1033/JD | 27/04/2022 | 30 | D. S. ENTERPRISE | 29.73 | 30.17 | 0
1374 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Kranti (Zone-II) Piped Water supply scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000029/2022-2023 | 914/JD | 07/04/2022 | 120 | M/S A.B.G. CONSTRUCTION | 468.36 | 328.8 | 70
1375 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No. WB71B-8742) |  | Junior Engineer | ORD/000078/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 0.15 | 0 | 0
1376 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1377 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall including Rising main Interconnection of Existing 2nd TW Site of Augmentation of Kranti Zone-I PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000136/2024-2025 | 1526/JD | 01/10/2024 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.61 | 0 | 0
1378 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at 2(two) Nos. Head Works sites for Augmentation works of Kranti (Zone-I and II) Piped Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000161/2023-2024 | 797/JD. | 24/07/2023 | 982 | MD HAKIMUDDIN | 291.65 | 64.39 | 50
1379 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) |  | Junior Engineer | ORD/000343/2021-2022 | 207/JD | 24/01/2022 | 60 | M/S A.B.G. CONSTRUCTION | 239.47 | 196.16 | 70
1380 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000344/2021-2022 | 209/JD | 24/01/2022 | 90 | M/S SIBU DEY AND CO. | 130.99 | 94.27 | 0
1381 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-C) |  | Junior Engineer | ORD/000345/2021-2022 | 210/JD | 24/01/2022 | 90 | BOSE ENTERPRISE | 156.83 | 107.43 | 80
1382 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) |  | Junior Engineer | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0.74 | 1
1383 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Guard Wall at pond side for existing Boundary Wall and joining the pipeline at Kodalkati for Augmentation of Kranti Zone - II Piped Water Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000369/2023-2024 | 291/JSSD | 26/09/2023 | 30 | D. S. ENTERPRISE | 1.55 | 1.49 | 100
1384 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of approach for Head Works Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000386/2022-2023 | 361/JD | 20/02/2023 | 7 | LOKNATH CONSTRUCTION | 0.61 | 0.61 | 100
1385 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent Laying Distribution System for inter connection to main line at Bhujari Para and Cana bridge at Kranti zone-II P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000550/2021-2022 | 1050/JSSD | 24/01/2022 | 15 | BARUN KUMAR DUTTA | 4.71 | 0 | 0
1386 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supplying and Installation of 45 nos. Display Board at different piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000550/2023-2024 | 497/JSSD | 02/01/2024 | 30 | GOUTAM DAS | 7.17 | 7.13 | 100
1387 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of pipeline near at Debijhora High School towards Kranti Bazar including Jhora Crossing under Kranti Zone-II Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000592/2021-2022 | 992/JSSD | 03/01/2022 | 15 | NARAYAN CHANDRA ADHIKARY | 2.5 | 2.14 | 0
1388 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Shifting of pipeline due to widening and strengthening of PWD road from Jhak Para Petrol Pump towards Head Work Site Pump House at Kranti zone- I Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000593/2021-2022 | 993/JSSD | 03/01/2022 | 20 | NARAYAN CHANDRA ADHIKARY | 3.96 | 3.9 | 0
1389 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000610/2021-2022 | 410/JD | 15/02/2022 | 21 | LOKNATH CONSTRUCTION | 7.62 | 7.49 | 0
1390 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 200mm x 150mm x 138m deep Rig Bored tube well by Reverse Rotary method of drilling at 3rd Site for Augmentation of Kranti (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000612/2021-2022 | 411/JD | 15/02/2022 | 21 | LOKNATH CONSTRUCTION | 7.62 | 7.38 | 100
1391 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-II Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000808/2023-2024 | 571/JSSD | 05/03/2024 | 378 | SIDDHARTHA KAR | 8.44 | 4.06 | 85
1392 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Kranti Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000812/2023-2024 | 567/JSSD | 05/03/2024 | 30 | KOHINOOR ISLAM | 3.22 | 0.97 | 70
1393 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | LDS FHTC PURBA DURAMARI |  | Junior Engineer | VCH/001287/2021-2022 | BP-2021-22-493 | 29/03/2022 | 0 | SUKES BASU MAJUMDAR | 46.78 | 0 | 0
1394 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | DPR PREPARATION FOR ANGRABHASA PWSS |  | Junior Engineer | VCH/001411/2021-2022 | BP-2021-22-547 | 31/03/2022 | 0 | SUBHANKAR GHOSH | 1.05 | 0 | 0
1395 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | LDS FHTC AUG MONDALGHAT |  | Junior Engineer | VCH/001418/2021-2022 | BP-2021-22-462 | 27/03/2022 | 0 | M/S R.N. TRADERS | 38.53 | 0 | 0
1396 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for AUGMENTATION OF KRANTI, ZONE-II, T/W No. I, under KRANTI CCC, [APPLICATION NO. 4003266348, Reference ID : 403105518] |  | Junior Engineer | BILL/01277/2023-2024 | 23-24/154&171 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1397 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for AUGMENTATION OF KRANTI, ZONE-II, T/W No. I, under KRANTI CCC, [APPLICATION NO. 100000093177, Reference ID : 860284827] |  | Junior Engineer | BILL/01278/2023-2024 | 23-24/154&171 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.78 | 0 | 0
1398 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF KRANTI PWSS, ZONE-II ,TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000876/2022-2023 | 340/NMD | 29/03/2023 | 30 | SAIKAT SINHA | 10.18 | 10.14 | 90
1399 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for KRANTI W/S SCHEME, T/W No. II, under KRANTI CCC, [APPLICATION NO. 400295553, Reference ID : 402862646] |  | Junior Engineer | VCH/000904/2022-2023 | BP/22-23/94 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
1400 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at KRANTI W/S SCHEME, T/W No. II, under KRANTI CCC, [APPLICATION NO. 100000059310, Reference ID : 860248970] |  | Junior Engineer | VCH/000905/2022-2023 | BP/22-23/94 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0
1401 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system and construction of Boundary Wall ,Foot Path, Drain at HW site of Bhagatpur Zone-II PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000011/2024-2025 | 427/JD | 13/06/2024 | 30 | LOKNATH CONSTRUCTION | 34.67 | 4.96 | 45
1402 | Jalpaiguri Division | Jalpaiguri Division | Restoration of existing damaged pipeline near railway crossing at Jhahaji line in connection with Jal Jeevan Mission under Bhagatpur Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000012/2024-2025 | 428/JD | 13/06/2024 | 657 | LOKNATH CONSTRUCTION | 25.24 | 0 | 25
1403 | Jalpaiguri Division | Jalpaiguri Division | Construction of 150 Cu.M. Capacity R.C.C. Over Head Reservoir of 17 Mtr. Staging Height, Construction of One No Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site Zone-II of Bhagatpur PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000023/2022-2023 | 1055/JD | 27/04/2022 | 1161 | LOKNATH CONSTRUCTION | 63.09 | 24.54 | 50
1404 | Jalpaiguri Division | Jalpaiguri Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1405 | Jalpaiguri Division | Jalpaiguri Division | Rising Main and FHTC at Bhagatpur PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2025-2026 | 1953/JD | 18/09/2025 | 195 | ADITRI ENTERPRISE | 14.59 | 0 | 30
1406 | Jalpaiguri Division | Jalpaiguri Division | Construction of approach road including development of the approach way for the Head works site of Bhagatpur T.G. Piped water supply Scheme Zone -II under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000208/2022-2023 | 1798/JD | 14/09/2022 | 21 | ASIT PAUL | 2.84 | 2.83 | 0
1407 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Bhagatpur T.G. P.W.S.S. zone-II under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000225/2022-2023 | 1854/JD | 16/09/2022 | 45 | RANA DEY | 4.65 | 4.77 | 1
1408 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 2nd tube well site for Augmentation of Bhagatpur T.G. P.W.S.S. zone-I under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000226/2022-2023 | 1855/JD | 16/09/2022 | 45 | ADITRI ENTERPRISE | 4.65 | 4.75 | 1
1409 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer,HQ | Junior Engineer | ORD/000300/2022-2023 | 2189/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.5 | 2.5 | 1
1410 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer,HQ | Junior Engineer | ORD/000302/2022-2023 | 2191/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.17 | 2.17 | 1
1411 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Jeeven Mission under Bhagatpur Piped Water Supply Scheme Zone-II Command area under Jalpaiguri Division P.H.E. Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000328/2022-2023 | 2458/JD | 22/12/2022 | 952 | UDAYAN BOSE | 23.71 | 17.05 | 100
1412 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with Rising Main Connection, of Bhagatpur Piped water Supply Scheme , Zone-II at Nagrakata Block under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000337/2021-2022 | 212/JD | 24/01/2022 | 60 | LOKNATH CONSTRUCTION | 93.12 | 87.08 | 100
1413 | Jalpaiguri Division | Jalpaiguri Division | Resistivity Test for Four Nos.Tube Well for Bhagatpur Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000495/2021-2022 | 1938/JD | 29/11/2021 | 15 | PARAMJYOTI ENTERPRISE | 0.6 | 0.6 | 0
1414 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000212/2023-2024 | 2060/JD | 10/01/2024 | 0 | Resource Division | 11.74 | 0 | 0
1415 | Jalpaiguri Division | Jalpaiguri Division | shifting of pipe line pwd nagrakata | Assistant Engineer,HQ | Junior Engineer | VCH/000580/2022-2023 | 342/22-23 | 15/09/2022 | 0 | PRADIP SAHA | 0.04 | 0 | 0
1416 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-I, TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000059/2022-2023 | 434/NMD | 14/06/2022 | 21 | MIHIR SARKAR | 2.77 | 2.19 | 70
1417 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-I, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000060/2022-2023 | 435/NMD | 14/06/2022 | 21 | SANJIB SAHA | 2.77 | 0 | 0
1418 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-II, TW No. I in the dist. of Jalpaiguri under under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000061/2022-2023 | 436/NMD | 14/06/2022 | 21 | BLUE PINE | 2.39 | 1.82 | 70
1419 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under BHAGATPUR T.G W/S Scheme, at ZONE-II, TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000062/2022-2023 | 437/NMD | 14/06/2022 | 21 | SAIKAT SINHA | 2.39 | 2.39 | 0
1420 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-I, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000075/2022-2023 | 533/NMD | 08/07/2022 | 30 | CHOWDHURY AND BASU ENTERPRISE | 10.3 | 6.91 | 50
1421 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-II, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000076/2022-2023 | 534/NMD | 08/07/2022 | 30 | SUBODH KUMAR BANIK | 10.02 | 9.02 | 100
1422 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-II, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000077/2022-2023 | 535/NMD | 08/07/2022 | 30 | RIPON DAS | 9.99 | 9.99 | 100
1423 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BHAGATPUR T.G W/S Scheme, ZONE-I, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000125/2022-2023 | 867/NMD | 20/07/2022 | 30 | ANUP BASU | 10.29 | 9.77 | 0
1424 | Northern Mechanical | Jalpaiguri Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig unit 32B-R-1302, by Odex-165 method of drilling at TW-II (2nd Site) under Bhagatpur TG PWSS (Zone-II), Block - Nagrakata, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000778/2021-2022 | 257/DSD | 17/12/2021 | 15 | RUDOLF DIESEL ENGINEERING SERVICE | 0.49 | 0.49 | 100
1425 | Northern Mechanical | Jalpaiguri Division | Carrying out Development works and Yield Test for a RBTW (BDTW) at Shyamdhan W/S Scheme (H/W Site) & (2nd Site), Replacement TW, G.P.- Raniganj Panisali, Block - Kharibari, Dist- Darjeeling and Bhagatpur TG PWSS (Zone-I), TW-I (H/W Site) & TW-II (2nd Site), Block - Nagrakata, Dist- Jalpaiguri and Naxalbari RH W/S Scheme, Block - Naxalbari, Dist- Darjeeling, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000779/2021-2022 | 262/DSD | 22/12/2021 | 21 | ALPHA ENTERPRISE | 0.53 | 0.53 | 100
1426 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-I, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC , APPLICATION NO. 4002939096 , Reference ID : 860242793 | Assistant Engineer,HQ | Junior Engineer | VCH/000317/2022-2023 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.05 | 0 | 0
1427 | Northern Mechanical | Jalpaiguri Division | Infrustructure cost for New Service Connection Charge for TW-I, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000053303,Reference ID : 402830565 | Assistant Engineer,HQ | Junior Engineer | VCH/000318/2022-2023 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.8 | 0 | 0
1428 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-II, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 4002939102,Reference ID : 860242791 | Assistant Engineer,HQ | Junior Engineer | VCH/000319/2022-2023 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.83 | 0 | 0
1429 | Northern Mechanical | Jalpaiguri Division | Infrustructure cost for New Service Connection Charge for TW-II, ZONE-II of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000053301,Reference ID : 402838302 | Assistant Engineer,HQ | Junior Engineer | VCH/000320/2022-2023 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.94 | 0 | 0
1430 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-I, ZONE-I of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 4002953412,Reference ID : 860244395 | Assistant Engineer,HQ | Junior Engineer | VCH/000321/2022-2023 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.06 | 0 | 0
1431 | Northern Mechanical | Jalpaiguri Division | Infrastructure cost for New Service Connection Charge for TW-I, ZONE-I of BHAGATPUR TEA GARDEN W/S Scheme under NAGRAKATA CCC,APPLICATION NO. 100000055565, Reference ID : 860244395 | Assistant Engineer,HQ | Junior Engineer | VCH/000322/2022-2023 | BP/2022-23/32 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.91 | 0 | 0
1432 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for BHAGATPUR T.G. W/S SCHEME, T/W No. II, Zone-I, [APPLICATION NO. 4002950622, Reference ID : 402840877] | Assistant Engineer,HQ | Junior Engineer | VCH/000844/2022-2023 | BP/22-23/44 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.56 | 0 | 0
1433 | Northern Mechanical | Jalpaiguri Division | Proposal for Approval W.O & E.O for New Three Phase Connection Work MII.R.O BHAGATPOORN DEEPA LINE, TW NO. 02 at BHAGATPUR T.G., [APPLICATION NO. 100000055158, Reference ID : 860244738] | Assistant Engineer,HQ | Junior Engineer | VCH/000863/2022-2023 | BP/22-23/44 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.58 | 0 | 0
1434 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Madhya Boragari Zone-I PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000285/2023-2024 | 1521/JD | 16/10/2023 | 899 | R.S CONSTRUCTION | 430.92 | 155.57 | 65
1435 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Madhya Boragari Zone-I Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000541/2024-2025 | 110/JD | 16/01/2025 | 45 | BISWANATH GHOSH | 47.44 | 0 | 0
1436 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000038/2023-2024 | 1109/JD | 24/08/2023 | 0 | Resource Division | 25.74 | 0 | 0
1437 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000143/2023-2024 | 2004/JD | 08/01/2024 | 0 | Resource Division | 13.46 | 0 | 0
1438 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003378751 Reference ID : 403193482 | Assistant Engineer,HQ | Junior Engineer | BILL/00157/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.36 | 0 | 0
1439 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003376713 Reference ID : 403191839 | Assistant Engineer,HQ | Junior Engineer | BILL/00159/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.13 | 0 | 0
1440 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MADHYA BORAGARI,ZONE:-I, T/W-III, under DHUPGURI CCC APPLICATION NO. 4003390202 Reference ID : 403202832 | Assistant Engineer,HQ | Junior Engineer | BILL/00306/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.73 | 0 | 0
1441 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
1442 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MADHYA BORAGARI PWSS, ZONE-I, TW no I, II, III, IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000433/2023-2024 | 1372/NMD | 09/08/2023 | 30 | EASTERN INDIA SALES & SERVICE | 43.5 | 19.52 | 45
1443 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0
1444 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
1445 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month June'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00454/2024-2025 | BP-2024-25-279 | 01/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1446 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1447 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Commissioning of Baradighi Tea Garden Area Piped water supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000253/2022-2023 | 173/JSSD | 25/08/2022 | 60 | PRIYABRATA KARMAKAR | 4.59 | 4.57 | 0
1448 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of BaraDighi PWSS i.e. TW, Pump Houses, Water distribution Network,OHR,RISING MAIN,FHTC etc. i.c.w Jal Jeevan Mission at Block-Matiali under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000471/2022-2023 | 775/JD | 27/03/2023 | 1099 | RAGHU DAS | 107.46 | 73.31 | 90
1449 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000027/2023-2024 | 171/JD | 28/04/2023 | 0 | Resource Division | 3.55 | 0 | 0
1450 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000179/2023-2024 | 2044/JD | 09/01/2024 | 0 | Resource Division | 1.29 | 0 | 0
1451 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00525/2024-2025 | BP-2024-25-297 | 14/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1452 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00866/2024-2025 | BP-2024-25-487 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1453 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1454 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 |  | Junior Engineer | ORD/000001/2024-2025 | 022/JSSD | 30/04/2024 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0.17 | 70
1455 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Dhumpara (N) (Zone-I & II) PWSS i.e, TW Pump House , Water distribution Network, OHR, RISING MAIN , FHTC etc. I.c.w Jal Jeevan Mission at Block - Nagrakata Under Jalpaiguri Divison P.H.E Dte. |  | Junior Engineer | ORD/000055/2023-2024 | 262/JD | 10/05/2023 | 180 | S. N. POLYMERS PVT. LTD. | 471.75 | 135.86 | 33
1456 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Construction of Boundary Wall & Rising main with inter connection at 2nd TW & 3rd TW site of Dhumpara(Zone -II) PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000077/2025-2026 | 98/JSSD | 30/05/2025 | 30 | ARUP SARKAR | 3.01 | 0 | 100
1457 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1458 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 |  | Junior Engineer | ORD/000113/2024-2025 | .142/2/JSSD | 29/07/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0.16 | 0
1459 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/11/2023 to 31/01/2025 |  | Junior Engineer | ORD/000470/2024-2025 | 326/JSSD | 30/10/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0 | 0
1460 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/11/2024 to 31/01/2025 |  | Junior Engineer | ORD/000471/2024-2025 | 325/1/JSSD | 30/10/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0.44 | 0
1461 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 |  | Junior Engineer | ORD/000511/2023-2024 | 378/JSSD | 30/10/2023 | 180 | MRITYUNJAY SIKDAR | 0.88 | 0.41 | 0
1462 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/02/2025 to 30/04/2025(Vehicle No WB 71B 9430) |  | Junior Engineer | ORD/000700/2024-2025 | 416/JSSD | 28/01/2025 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0.63 | 0
1463 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall & Rising main with inter connection at 2nd TW & 3rd TW site of Dhumpara(Zone -II) PWSS in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000803/2023-2024 | 570/JSSD | 05/03/2024 | 45 | ARUP SARKAR | 8.23 | 8.3 | 100
1464 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000019/2023-2024 | 163/JD | 28/04/2023 | 0 | Resource Division | 44.06 | 0 | 0
1465 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000165/2023-2024 | 2055/JD | 09/01/2024 | 0 | Resource Division | 14.08 | 0 | 0
1466 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for DHUMPARA, T/W No. I, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321209 ; Reference ID : 403147529] |  | Junior Engineer | BILL/01846/2023-2024 | BP/23-24/299 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.95 | 0 | 0
1467 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for DHUMPARA, T/W No. II, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321417 ; Reference ID : 403147621] |  | Junior Engineer | BILL/01847/2023-2024 | BP/23-24/300 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0
1468 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for DHUMPARA, T/W No. III, ZONE-II under BANARHAT CCC [APPLICATION NO. 4003321422 ; Reference ID : 403147798] |  | Junior Engineer | BILL/01848/2023-2024 | BP/23-24/301 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0
1469 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHUMPARA PWSS , Zone-I (TW No. I, II) and Zone-II (TW No- I, II and III) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000425/2023-2024 | 1340/NMD | 08/08/2023 | 30 | A.G. ENTERPRISE | 60.95 | 35.92 | 50
1470 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0
1471 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0
1472 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
1473 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1474 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Neoranadi Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000045/2023-2024 | 238/JD | 08/05/2023 | 878 | PRASENJIT BASAK | 286.38 | 232.92 | 100
1475 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1476 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Neoranadi TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000175/2025-2026 | 174/JSSD | 25/07/2025 | 30 | ADWIJA CONSTRUCTION | 7.51 | 0 | 0
1477 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Neoranadi TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000431/2024-2025 | 2275/JD | 05/12/2024 | 90 | PRASENJIT BASAK | 67.08 | 0 | 0
1478 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000065/2023-2024 | 1074/JD | 24/08/2023 | 0 | Resource Division | 47.59 | 0 | 0
1479 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000155/2023-2024 | 2013/JD | 09/01/2024 | 0 | Resource Division | 8.43 | 0 | 0
1480 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NEORA NODI TEA GARDEN, T/W No. I under MAL CCC [APPLICATION NO. 4003256029 ; Reference ID : 403097550] |  | Junior Engineer | BILL/01715/2023-2024 | BP/23-24/239 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1481 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for NEORA NODI TEA GARDEN, T/W No. I under MAL CCC [APPLICATION NO. 100000091998 ; Reference ID : 860283908] |  | Junior Engineer | BILL/01716/2023-2024 | BP/23-24/238 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.37 | 0 | 0
1482 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NEORA NADI, T/W No. II, under MAL CCC [APPLICATION NO. 4003302999 , Reference ID : 403132352] |  | Junior Engineer | BILL/01789/2023-2024 | BP/23-24/237 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1483 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for NEORA NADI, T/W No. II, under MAL CCC [APPLICATION NO. 100000096819 , Reference ID : 860287689] |  | Junior Engineer | BILL/01790/2023-2024 | BP/23-24/236 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.18 | 0 | 0
1484 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
1485 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1486 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEORA NADI PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000862/2023-2024 | 1806/NMD | 31/10/2023 | 459 | S.P. ENTERPRISE (KOLKATA) | 24.79 | 0 | 100
1487 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF 1(ONE) MAXI CAB WITH ENGINE CAPACITY MORE THAN 2000C.C ON HIRE BASIS INCLUDING DRIVER FOR ASSISTANT ENGINEER (SADAR), JALPAIGURI SADAR SUB DIVISION, P.H.E. DTE. DIST-JALPAIGURI (WITH VALID PERMIT) |  | Junior Engineer | BILL/00322/2023-2024 | BP-2023-24-292 | 10/08/2023 | 0 | MANIK RAY | 0.25 | 0 | 0
1488 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  | Junior Engineer | BILL/00356/2022-2023 | BP-2023-24-111 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 2.85 | 0 | 0
1489 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 71 B 9430) |  | Junior Engineer | BILL/00855/2024-2025 | BP-2024-25-499 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
1490 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF FUEL(DISEL) FOR THE VEHICLE NO. WB-78-3405 FOR THE MONTH OF FEBRUARY2024 FOR THE OFFICE USE OF THE ASSISTANT ENGINEER ,SADAR SUB DIVISION, UNDER EXECUTIVE ENGINEER ,JALPAIGURI DIVISION. |  | Junior Engineer | BILL/01356/2023-2024 | BP-2024-25-15 | 12/04/2024 | 0 | FILL & SMILE | 0.25 | 0 | 0
1491 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/05/2024 to 30/07/2024 |  | Junior Engineer | ORD/000001/2024-2025 | 022/JSSD | 30/04/2024 | 90 | MRITYUNJAY SIKDAR | 0.44 | 0.22 | 70
1492 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000006/2022-2023 | 877/JD | 05/04/2022 | 1367 | SCEC BOENTER KDAS JOINT VENTURE | 237.94 | 126.1 | 88
1493 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Rejuvenation of different components of PWSS of Over Head Reservoir site at Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000010/2024-2025 | 423/JD | 12/06/2024 | 45 | APEX ENGINEERING | 22.45 | 3.28 | 100
1494 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 350 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-II) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000022/2022-2023 | 1031/JD | 26/04/2022 | 180 | RAGHU DAS | 96.77 | 98.75 | 1
1495 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary wall with Land development at Head Works site for Augmentation of Lataguri (Zone-III) Piped Water Sipply Scheme under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/000069/2022-2023 | 1922/JD | 28/09/2022 | 180 | J.M. CONSTRUCTION | 84.24 | 83.45 | 100
1496 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.6x2.4) m with Land Development, Boundary Wall, approach, Retrofitting work of Lataguri Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte |  | Junior Engineer | ORD/000092/2021-2022 | 1331/JD | 23/08/2021 | 1472 | R.K. SINGHA & SONS | 15.94 | 11.1 | 100
1497 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1498 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 2nd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000099/2022-2023 | 78/JSSD | 22/07/2022 | 20 | SURAJIT KUNDU | 4.57 | 4.52 | 100
1499 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Lataguri (zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000103/2022-2023 | 79/JSSD | 22/07/2022 | 20 | SURAJIT KUNDU | 4.57 | 4.47 | 100
1500 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Rig approach for Installation of tubewell of Head Works, 2nd Tubewell and 3rd Tube Well site for Augmentation of Lataguri Piped Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000109/2022-2023 | 86/JSSD | 22/07/2022 | 7 | ALICK DUTTA | 1.46 | 1.45 | 1
1501 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent Laying of pipeline at Purba Lataguri Station Para and repairing old stand post (broken)due to widening and strengthening of PWD lataguri-Kranti Road at Lataguri Water Supply Scheme under Jalpaiguri Division,PHE Dte. |  | Junior Engineer | ORD/000110/2022-2023 | 87/JSSD | 22/07/2022 | 10 | KAMALESH SEN | 1.11 | 1.11 | 1
1502 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 3rd & 4th TW including Rising main for Augmentation of Lataguri PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000111/2024-2025 | 1417/JD | 20/09/2024 | 236 | M/S SIBU DEY AND CO. | 40.12 | 0 | 40
1503 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 01/08/2024 to 31/10/2024 |  | Junior Engineer | ORD/000113/2024-2025 | .142/2/JSSD | 29/07/2024 | 92 | MRITYUNJAY SIKDAR | 0.44 | 0.16 | 0
1504 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/06/2023 to 31/07/2023. |  | Junior Engineer | ORD/000134/2023-2024 | 558/RWS | 31/05/2023 | 61 | APIKUL ALI | 0.29 | 0.29 | 100
1505 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work for Laying Distribution System with Providing FHTC for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.¿. Dte. |  | Junior Engineer | ORD/000198/2024-2025 | 298/JSSD | 03/10/2024 | 15 | CALCON CONSTRUCTIONS | 8.06 | 0 | 100
1506 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of 2nd Pump House, office-cum-godown, IEP platform and construction of drain with earth filling in H/W site and ancillary works with over hauling of 3-unit IEP plant for Augmentation of Lataguri (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000230/2022-2023 | 1946/JD | 13/10/2022 | 21 | D. S. ENTERPRISE | 18.91 | 18.8 | 0
1507 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000289/2022-2023 | 1899/JD | 26/09/2022 | 90 | CALCON CONSTRUCTIONS | 267.26 | 211.29 | 80
1508 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmentation of Lataguri (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000291/2022-2023 | 2059/JD | 03/11/2022 | 993 | M/S SURAJIT DEY AND CO. | 383.43 | 260.59 | 95
1509 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of Rising Main from 1st, 2nd & 3rd Tube Well site to OHR for Augmentation of Lataguri (Zone-I) PWSS in connection with Jal Jeevan Mission at Block -Kranti under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000359/2023-2024 | 277/JSSD | 21/09/2023 | 30 | ARUP SARKAR | 6.5 | 0 | 0
1510 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Lataguri (Zone-III) in connection with PWSS in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000365/2023-2024 | 281/JSSD | 26/09/2023 | 30 | GOPRO CONSTRUCTION | 3.62 | 3.55 | 100
1511 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of approach for Head Works Site for Augmentation of Lataguri (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000384/2022-2023 | 360/JD | 20/02/2023 | 7 | RAGHU DAS | 0.56 | 0.56 | 0
1512 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte, (with valid Taxi permit) from 1/11/2023-30/04/2024 |  | Junior Engineer | ORD/000511/2023-2024 | 378/JSSD | 30/10/2023 | 180 | MRITYUNJAY SIKDAR | 0.88 | 0.42 | 0
1513 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Rising Line Connection with wash line and balance work in Head Works site at Augmentation of Lataguri(zone-II) PWSS under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000549/2023-2024 | 506/JSSD | 02/01/2024 | 30 | RAGHU DAS | 9.22 | 9.2 | 100
1514 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent Laying of diverted line damaged by excavator due to construction of Market Complex at Lataguri Bazar and replacing the damaged GI line at Lal Setu at Lataguri Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000552/2021-2022 | 990/JSSD | 03/01/2022 | 10 | LOKNATH CONSTRUCTION | 1.47 | 1.12 | 100
1515 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Minor repairing and renovation of 3rd T/W site and H/W site Pump Houses at Lataguri Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000553/2021-2022 | 987/JSSD | 03/01/2022 | 20 | D. S. ENTERPRISE | 2.63 | 2.64 | 0
1516 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in HW site at Zone-III of Augmentation of Lataguri PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000590/2024-2025 | 455/JD | 10/03/2025 | 30 | J.M. CONSTRUCTION | 16.72 | 0 | 0
1517 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M x 2.40 M) size including sanitary plumbing works at 2nd tube well site for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000596/2021-2022 | 1054/JSSD | 24/01/2022 | 45 | KABYA ENTERPRISE | 4.76 | 4.76 | 100
1518 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M x 2.40 M) size including sanitary and Plumbing Works at 3rd tube well site for Augmentation of Lataguri (zone-II) PWSS under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000600/2021-2022 | 1066/JSSD | 24/02/2022 | 45 | ROY CONSTRUCTION | 4.76 | 4.7 | 1
1519 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM Over Head Reservoir Augmentation of Lataguri (Zone-III) PWSS, under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000692/2021-2022 | 1067/JSSD | 24/01/2022 | 20 | MABCO CONSULTANT | 1.83 | 1.73 | 1
1520 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 350 CuM Over Head Reservoir for Augmentation of Lataguri (Zone-II) PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000702/2021-2022 | 1069/JSSD | 25/01/2022 | 20 | GLORY ENGINEERS SYNDICATE | 1.83 | 1.62 | 1
1521 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jalswapna with retrofitting work for Mahalaxmi Colony, Lataguri for Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001064/2021-2022 | 995/JSSD | 05/01/2022 | 15 | ALICK DATTA | 4.6 | 0 | 0
1522 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional House hold Tap connection in connection with Jalswapna with retroffiting work for Mahalaxmi Colony, Lataguri for Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001065/2021-2022 | 995/JSSD | 05/01/2022 | 15 | ALICK DATTA | 4.6 | 4.7 | 1
1523 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000088/2023-2024 | 1066/JD | 24/08/2023 | 0 | Resource Division | 342.41 | 0 | 0
1524 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000090/2024-2025 | 2216/JD | 01/12/2024 | 0 | Resource Division | 30.66 | 0 | 0
1525 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LATAGURI, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 4003078500, Reference ID : 402950395] |  | Junior Engineer | BILL/00578/2022-2023 | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
1526 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LATAGURI, ZONE-II,T/W No - III W/S Scheme, under KRANTI CCC, [APPLICATION NO. 4003071675, Reference ID : 402950393] |  | Junior Engineer | BILL/00579/2022-2023 | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
1527 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for LATAGURI W/S Scheme, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 100000070391, Reference ID : 860261321] |  | Junior Engineer | BILL/00580/2022-2023 | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.57 | 0 | 0
1528 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for LATAGURI W/S Scheme, ZONE-II,T/W No - I W/S Scheme, under KRANTI CCC, [APPLICATION NO. 100000070390, Reference ID : 860261320] |  | Junior Engineer | BILL/00581/2022-2023 | BP/22-23/136 | 28/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.94 | 0 | 0
1529 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no I, Z-III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000754/2022-2023 | 54/NMD | 24/01/2023 | 30 | S.P. ENTERPRISE | 10.73 | 10.73 | 80
1530 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no I, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000755/2022-2023 | 55/NMD | 24/01/2023 | 30 | SUMON ELECTRICAL | 10.74 | 10.74 | 90
1531 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no II, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000756/2022-2023 | 56/NMD | 24/01/2023 | 30 | SUDIP DUTTA | 10.71 | 10.71 | 60
1532 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no III, Z-II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000757/2022-2023 | 57/NMD | 24/01/2023 | 30 | INDRANI ENTERPRISE | 10.74 | 10.74 | 100
1533 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LATAGURI PWSS, TW no III, Z-I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000767/2022-2023 | 73/NMD | 27/01/2023 | 278 | MUSTAFI CONCERN | 10.7 | 10.7 | 100
1534 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. II,Zone I under KRANTI CCC, [APPLICATION NO. 4002975542, Reference ID : 402862648] |  | Junior Engineer | VCH/000985/2022-2023 | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
1535 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. II, Zone I under KRANTI CCC , [APPLICATION NO. 100000059310, Reference ID : 860248970] |  | Junior Engineer | VCH/000986/2022-2023 | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.9 | 0 | 0
1536 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. III, Zone III under KRANTI CCC, [APPLICATION NO. 4002975529, Reference ID : 402862647] |  | Junior Engineer | VCH/000987/2022-2023 | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
1537 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. III, Zone III under KRANTI CCC , [APPLICATION NO. 100000059310, Reference ID : 860248970] |  | Junior Engineer | VCH/000988/2022-2023 | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0
1538 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. II, Zone II under KRANTI CCC, [APPLICATION NO. 4002975542, Reference ID : 402862648] |  | Junior Engineer | VCH/001004/2022-2023 |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
1539 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. II, Zone-II under KRANTI CCC , [APPLICATION NO. 100000059309, Reference ID : 860248969] |  | Junior Engineer | VCH/001005/2022-2023 |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.9 | 0 | 0
1540 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. I, Zone III under KRANTI CCC, [APPLICATION NO. 4002975529, Reference ID : 402862647] |  | Junior Engineer | VCH/001006/2022-2023 |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
1541 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. I, Zone-III under KRANTI CCC , [APPLICATION NO. 100000059308, Reference ID : 860248968] |  | Junior Engineer | VCH/001007/2022-2023 |  | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.01 | 0 | 0
1542 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LATAGURI W/S SCHEME, T/W No. III, Zone I under KRANTI CCC, [APPLICATION NO. 4002941867, Reference ID : 402838302] |  | Junior Engineer | VCH/001008/2022-2023 | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.4 | 0 | 0
1543 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at LATAGURI W/S SCHEME, T/W No. III, Zone I under KRANTI CCC, [APPLICATION NO. 4100000054083, Reference ID : 860243703] |  | Junior Engineer | VCH/001009/2022-2023 | BP/22-23/95 | 18/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.49 | 0 | 0
1544 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Tunbari Tea Garden (P) PWSS i.e. TW, Pump Houses, IEP, Blower Room, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block ¿ Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000060/2023-2024 | 265/JD | 10/05/2023 | 180 | M/S SARKAR ENTERPRISE | 304.78 | 0 | 70
1545 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1546 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system with other allied works in connection with Jal Jeevan Mission at Tunbari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000092/2025-2026 | 105/JSSD | 30/05/2025 | 45 | GURUKUL INFOTECH | 4.97 | 0 | 0
1547 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Malbazar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000463/2023-2024 | 1291/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
1548 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Tunbari Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000469/2023-2024 | 1762/JD | 08/12/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 31.58 | 100
1549 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000062/2023-2024 | 1091/JD | 24/08/2023 | 0 | Resource Division | 35.62 | 0 | 0
1550 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000142/2023-2024 | 1888/JD | 20/12/2023 | 0 | Resource Division | 9.92 | 0 | 0
1551 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for TUNBARI TG, TW NO-I, MAL CCC APPLICATION NO. 4003299893 Reference ID : 403130044 |  | Junior Engineer | BILL/00193/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1552 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at TUNBARI TG, TW NO-I, MAL CCC APPLICATION NO. 100000102137 Reference ID : 860293897 |  | Junior Engineer | BILL/00194/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.85 | 0 | 0
1553 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for TUNBARI TG, TW NO-II, MAL CCC APPLICATION NO. 4003299902 Reference ID : 403130042 |  | Junior Engineer | BILL/00195/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1554 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at TUNBARI TG, TW NO-II, MAL CCC APPLICATION NO. 100000102138 Reference ID : 860293898 |  | Junior Engineer | BILL/00196/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.32 | 0 | 0
1555 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
1556 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1557 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TUNBARI TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000449/2023-2024 | 1388/NMD | 09/08/2023 | 30 | M/S CHANDRANATH MUKHERJEE | 25.75 | 20.66 | 80
1558 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting by replacement of lower (63 mm ,75mm) dia UPVC pipe of Mahit Nagar PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. (Part-A) |  | Junior Engineer | ORD/000080/2023-2024 | 433/JD. | 08/06/2023 | 28 | RAGHU DAS | 52.95 | 52.93 | 98
1559 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at balance portion of Mohitnagar W/S Scheme in connection with Jaldhara/ Jal Sapna under Jalpaiguri Division PHE Dte. (PART-J) |  | Junior Engineer | ORD/000259/2023-2024 | 1269/JD | 13/09/2023 | 30 | M/S DEY & ROY CHOUDHURY | 63.37 | 22.41 | 90
1560 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply mobil to vehicle no WB 71 A 5774 |  | Junior Engineer | BILL/00518/2024-2025 | BP-2024-25-296 | 14/08/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
1561 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of July 2024 |  | Junior Engineer | BILL/00519/2024-2025 | BP-2024-25-295 | 14/08/2024 | 0 | FILL & SMILE | 0.2 | 0 | 0
1562 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FUEL BILL |  | Junior Engineer | BILL/00631/2023-2024 | BP-2023-24-433 | 11/10/2023 | 0 | FILL & SMILE | 0.53 | 0 | 0
1563 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of deep tube well by ODEX-195 method of drilling for Songachi T.G. Piped Water Supply Scheme, Block- Matiali, Dist- Jalpaiguri. |  | Junior Engineer | ORD/000195/2022-2023 | 1592/JD | 17/08/2022 | 21 | R.S CONSTRUCTION | 9.32 | 7.76 | 100
1564 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.08.2023 to 31.01.2024) |  | Junior Engineer | ORD/000268/2023-2024 | 877/RWS | 31/07/2023 | 184 | ASHIM SARKAR | 0.88 | 0.88 | 20
1565 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 (Two) Nos Additional Tube Well by ODEX-165 method including Construction of different components i.e. Pump Houses, Boundary Walls, Rising Mains etc. for 4th and 5th site of Songachi Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000701/2024-2025 | 630/JD | 28/03/2025 | 60 | PINAKI MITRA | 36.19 | 0 | 0
1566 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R.W.S Sub-Division P.H.E. Dte. Jalpaiguri for 6 month (Period from 01.02.2024 to 31.07.2024) |  | Junior Engineer | ORD/000793/2023-2024 | 93/RWS | 29/01/2024 | 182 | ASHIM SARKAR | 0.88 | 0.88 | 50
1567 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000095/2023-2024 | 1049/JD | 24/08/2023 | 0 | Resource Division | 2.45 | 0 | 0
1568 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 4003220150, Reference ID : 403066255] |  | Junior Engineer | BILL/01071/2023-2024 | BP/23-24/107 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1569 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for SOONGACHI TEA GARDEN (REJU), T/W III, under MAL CCC, [APPLICATION NO. 100000088108, Reference ID : 860279669] |  | Junior Engineer | BILL/01072/2023-2024 | BP/23-24/107 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.96 | 0 | 0
1570 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1571 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SONGACHI TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000418/2023-2024 | 1332/NMD | 08/08/2023 | 30 | ASHWIRBAD WOOD CRAFT | 12.01 | 11.35 | 90
1572 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0
1573 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Kurti Tea Garden (Zone-I, II and III) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000056/2023-2024 | 263/JD | 10/05/2023 | 180 | S. N. POLYMERS PVT. LTD. | 308.54 | 0 | 0
1574 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000023/2023-2024 | 167/JD | 28/04/2023 | 0 | Resource Division | 56.03 | 0 | 0
1575 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000166/2023-2024 | 2038/JD | 09/01/2024 | 0 | Resource Division | 6.64 | 0 | 0
1576 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KURTI TEA GARDEN PWSS(TW No- I, II and III), in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000860/2023-2024 | 1804/NMD | 31/10/2023 | 30 | SARKAR ELECTRIC | 37.45 | 0 | 0
1577 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0
1578 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0
1579 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
1580 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1581 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 3rd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000102/2025-2026 | 481/RWS | 29/05/2025 | 30 | GOURAV CONSTRUCTION CO. | 6.98 | 0 | 0
1582 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Land development, pathway, surface drain etc. i.c.w. Dakshin Hanskhali PWSS 2nd TW Site under Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000104/2025-2026 | 482/RWS | 29/05/2025 | 30 | M/S. D.K. DEY & CO.. | 8.36 | 0 | 0
1583 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Dakshin Hanskhali PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc.In connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000162/2023-2024 | 799/JD. | 24/07/2023 | 1135 | M/S. D.K. DEY & CO.. | 465.94 | 161.43 | 45
1584 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution Network and Providing Functional Household Tap connection (FHTC) including Construction of additional components of Dakshin Hanskhali PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block- Kranti under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000678/2024-2025 | 465/JD | 11/03/2025 | 60 | M/S. D.K. DEY & CO.. | 74.53 | 0 | 0
1585 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Land Development, Pathway, Surface Drain etc. at H/W site of Dakshin Hanskhali PWSS i.c.w. Jal Jeevan Mission at block- Kranti under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000684/2024-2025 | 484/JD | 11/03/2025 | 45 | M/S. D.K. DEY & CO.. | 21.14 | 0 | 0
1586 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000111/2023-2024 | 1370/JD | 27/09/2023 | 0 | Resource Division | 87.93 | 0 | 0
1587 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000150/2023-2024 | 2016/JD | 09/01/2024 | 0 | Resource Division | 17.2 | 0 | 0
1588 | Northern Mechanical | Northern Mechanical Division | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-III, KRANTI CCC APPLICATION NO. 100000112207 Reference ID : 860304707 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00516/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.52 | 0 | 0
1589 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-III, KRANTI CCC APPLICATION NO. 4003445819 Reference ID : 403244352 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00517/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1590 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-II, KRANTI CCC APPLICATION NO. 4003445808 Reference ID : 403244351 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00518/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1591 | Northern Mechanical | Northern Mechanical Division | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-II, KRANTI CCC APPLICATION NO. 100000112206 Reference ID : 860304706 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00519/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.16 | 0 | 0
1592 | Northern Mechanical | Northern Mechanical Division | Infrastructure development cost for new service connection at DAKSHIN HANSKHALI,TW NO-I, KRANTI CCC APPLICATION NO. 100000112205 Reference ID : 860304705 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00520/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.93 | 0 | 0
1593 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for DAKSHIN HANSKHALI,TW NO-I, KRANTI CCC APPLICATION NO. 4003445776 Reference ID : 403244353 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00521/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
1594 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
1595 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
1596 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN HANSKHALI PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000672/2023-2024 | 1487/NMD | 17/08/2023 | 30 | HARA PROSAD DAS | 40.27 | 0 | 80
1597 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001008/2024-2025 | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0
1598 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Khuklung Mini PWSS ie. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Dhupguri Block, under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000274/2023-2024 | 1265/JD | 13/09/2023 | 656 | DEBASISH DEY | 63.25 | 34.97 | 90
1599 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000144/2023-2024 | 2001/JD | 08/01/2024 | 0 | Resource Division | 0.73 | 0 | 0
1600 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHUKHLUNG PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000680/2023-2024 | 1492/NMD | 17/08/2023 | 30 | SANJIB SAHA | 6.09 | 0 | 0
1601 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of HAIHAIPATHAR PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000048/2023-2024 | 454/JD. | 08/06/2023 | 663 | M/S R.N. TRADERS | 444.76 | 221.18 | 75
1602 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1603 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 (Two) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of Hai Hai Pather PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000435/2024-2025 | 2311./JD | 11/12/2024 | 70 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 34.93 | 0 | 0
1604 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000069/2023-2024 | 1085/JD | 24/08/2023 | 0 | Resource Division | 28.59 | 0 | 0
1605 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000160/2023-2024 | 2022/JD | 09/01/2024 | 0 | Resource Division | 14.2 | 0 | 0
1606 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Additional Quotation for Infrastructure development cost for new service connection at Hai Hai Pather, TW NO-II, MAL CCC APPLICATION NO. 100000103229 Reference ID : 860295639 |  | Junior Engineer | BILL/00214/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.78 | 0 | 0
1607 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for HAI HAI PATHAR, T/W No. II under MAL CCC [APPLICATION NO. 4003255985 ; Reference ID :403097549] |  | Junior Engineer | BILL/01717/2023-2024 | BP/23-24/250 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1608 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for HAI HAI PATHAR, T/W No. II under MAL CCC [APPLICATION NO. 100000092012 ; Reference ID :860283912] |  | Junior Engineer | BILL/01718/2023-2024 | BP/23-24/251 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.17 | 0 | 0
1609 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for HAI HAI PATHAR, T/W No. I under MAL CCC [APPLICATION NO. 4003255959 ; Reference ID :403097548] |  | Junior Engineer | BILL/01719/2023-2024 | BP/23-24/252 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1610 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for HAI HAI PATHAR, T/W No. I under MAL CCC [APPLICATION NO. 100000091999 ; Reference ID :860283909] |  | Junior Engineer | BILL/01720/2023-2024 | BP/23-24/253 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.11 | 0 | 0
1611 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for HAIHAIPATHAR PWSS, TW No I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000677/2023-2024 | 1490/NMD | 17/08/2023 | 30 | ANIMA ENTERPRISE | 25.32 | 25.32 | 100
1612 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0
1613 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Sukani Piped Water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000035/2022-2023 | 1102/JD | 12/05/2022 | 1420 | M/S A.B.G. CONSTRUCTION | 886.96 | 593.17 | 78
1614 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System including FHTC for Augmentation of Sukani Piped Water Supply Scheme Zone-III at Rajganj Block Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000037/2022-2023 | 1101/JD | 12/05/2022 | 120 | BANSBERIA CONSTRUCTION CO. | 668.61 | 433.35 | 1
1615 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000051/2022-2023 | 1196/JD | 20/05/2022 | 45 | SHYAMAL KUMARSAHA | 4.64 | 4.64 | 0
1616 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000052/2022-2023 | 1198/JD | 20/05/2022 | 45 | DILIP SINGHA | 4.65 | 4.65 | 1
1617 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary &Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000054/2022-2023 | 1201/JD | 20/05/2022 | 45 | KABYA ENTERPRISE | 4.64 | 4.64 | 100
1618 | Jalpaiguri Division | Jalpaiguri Division | HDD Boring with MS pipe and other ancillary work at post office more of rajganj and fatapukur to belakoba road of sukani pwss under jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2024-2025 | 937/JD | 07/08/2024 | 60 | SANKAR DAS | 34.63 | 34.47 | 100
1619 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone II Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000057/2022-2023 | 1197/JD | 20/05/2022 | 45 | UNIQUE CONSTRUCTION | 4.64 | 0 | 0
1620 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Sukhani Zone I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000058/2022-2023 | 1200/JD | 20/05/2022 | 45 | M/S A.P. DEVELOPERS | 4.65 | 4.65 | 0
1621 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System with FHTC for Augmentation of Sukhani Piped Water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000059/2022-2023 | 1229/JD | 01/06/2022 | 120 | MINTU CHAKRABORTY | 746.92 | 569 | 88
1622 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site (ZONE-I) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT ¿ JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/000068/2022-2023 | 1273/JD | 07/06/2022 | 45 | M/S SURAJIT DEY AND CO. | 29.51 | 0 | 0
1623 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd tube well site ( ZONE-II) of SUKANI piped water supply scheme under JALPAIGURI Division PHE Dte. BLOCK ¿ RAJGANJ, DISTRICT - JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000070/2022-2023 | 1272/JD | 07/06/2022 | 45 | MINTU CHAKRABORTY | 17.91 | 16.88 | 100
1624 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sukhani Zone III Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000077/2022-2023 | 1373/JD | 30/06/2022 | 45 | PARESH CHAND GHOSH ROY | 4.64 | 4.64 | 1
1625 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with sanitary & Plumbing arrangement at 3rd Tube Well site for Sukhani Piped Water Supply Scheme Zone-II at Rajganj block under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000114/2023-2024 | 449/JD. | 08/06/2023 | 45 | JAGORAN SARKAR | 4.9 | 4.9 | 100
1626 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall with drain, land development including interconnection work at Augmentation of Sukani PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000125/2024-2025 | 1414/JD | 20/09/2024 | 30 | D. S. ENTERPRISE | 10.17 | 0 | 100
1627 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-1) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000142/2023-2024 | 709/JD | 13/07/2023 | 629 | MRINMOY KANTI DUTTA | 29.51 | 10.46 | 55
1628 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-II zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000165/2022-2023 | 1433/JD | 18/07/2022 | 15 | MOYTEC | 2.25 | 2.03 | 100
1629 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (750 cum) at Sukhani Zone-III under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000166/2022-2023 | 1424/JD | 15/07/2022 | 15 | M S PRANTIK ASSOCIATES | 2.22 | 2.12 | 100
1630 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir(750 cum) at Sukhani zone-I zone under Sukhani piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000173/2022-2023 | 1400/JD | 11/07/2022 | 15 | AGAC | 2.26 | 2.24 | 100
1631 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site to sukhanii zone - II (H/W site T/W ) under Jalpaiguri Division PHE Dte. Part B ( Left & Right) | Assistant Engineer,HQ | Junior Engineer | ORD/000179/2019-2020 | 291/JD | 13/03/2020 | 60 | SADHAN KARMAKAR | 9.7 | 0 | 1
1632 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant (IEP) with Construction of Blower Room, Drain, Road including necessary connections and other ancillary work at Zone-I 4th Site of Sukani Piped Water Supply Scheme in connection with Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000186/2025-2026 | 2503/JD | 09/12/2025 | 120 | D. S. ENTERPRISE | 25.17 | 0 | 0
1633 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall, Additional Laying distribution system adjacent to H/W site for " SUKHANI ZONE-II WATER SUPPLY SCHEME ( H/ W SITE T/W )" under Jalpaiguri Divition , P.H.E. Dte. Part-"A" (Front Side) | Assistant Engineer,HQ | Junior Engineer | ORD/000187/2019-2020 | 248/JD | 03/03/2020 | 60 | SUBRATA GOSWAMI | 14.17 | 13.81 | 1
1634 | Jalpaiguri Division | Jalpaiguri Division | Support 300 mm DI pipe line near Fatapukur and construction 1 no. stand post and other ancillary works at Sukani Zone I under Rajganj block under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000219/2022-2023 | 1809/JD | 14/09/2022 | 21 | R.K. SARKAR | 1.8 | 1.2 | 1
1635 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessary connections for Augmentation of Sukhani Zone-I Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000249/2023-2024 | 1270/JD | 13/09/2023 | 810 | SANJIT SAHA | 30.41 | 25.29 | 55
1636 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-3) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000250/2023-2024 | 1263/JD | 13/09/2023 | 931 | ANUP KUMAR KUNDU | 40.53 | 0 | 0
1637 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000256/2023-2024 | 1264/JD | 13/09/2023 | 45 | A P CONSTRUCTION | 31.69 | 31.02 | 100
1638 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-4) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000260/2023-2024 | 1262/JD | 13/09/2023 | 705 | BILTU DAS | 40.83 | 0 | 50
1639 | Jalpaiguri Division | Jalpaiguri Division | Fitting fixing DI specials along with laying distribution for Augmentation of Sukhani Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/000263/2023-2024 | 948/JD | 08/08/2023 | 60 | MINTU CHAKRABORTY | 82.49 | 60.5 | 45
1640 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) for Augmentation at 3rd tubewell site Sukani (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000277/2023-2024 | 1358/JD | 26/09/2023 | 45 | D. S. ENTERPRISE | 18.23 | 18.23 | 100
1641 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at 4th Tubewell site Sukhani PWSS (Zone-II) under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000278/2023-2024 | 1359/JD | 26/09/2023 | 45 | SANDIP BANIK | 17.65 | 17.58 | 100
1642 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Missiion under the command area of Sukhani (Zone-I) (Part-2) Piped Water Supply Scheme at Rajgang Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000280/2023-2024 | 1434/JD | 05/10/2023 | 786 | SUBRATA GOSWAMI | 29.29 | 0 | 40
1643 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer,HQ | Junior Engineer | ORD/000295/2023-2024 | 855/JD | 31/07/2023 | 184 | SOUMEN GHOSH | 0.88 | 0.79 | 20
1644 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-III) PIPED WATER SUPPLY SCHEME. | Assistant Engineer,HQ | Junior Engineer | ORD/000372/2023-2024 | 1519/JD | 16/10/2023 | 481 | M/S. SURYA I PVT. LTD COMPANY | 147.2 | 64.02 | 68
1645 | Jalpaiguri Division | Jalpaiguri Division | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) | Assistant Engineer,HQ | Junior Engineer | ORD/000391/2022-2023 | 2186/JD | 10/11/2022 | 151 | SUKES BASU MAJUMDAR | 0.94 | 0.47 | 0
1646 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000472/2022-2023 | 780/JD | 27/03/2023 | 21 | ASIT PAUL | 19.36 | 18.41 | 100
1647 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sukhani (Zone-III) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000485/2022-2023 | 804/JD | 29/03/2023 | 734 | JITENDRA NATH ROY | 13.79 | 11.26 | 100
1648 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000504/2021-2022 | 511/JD | 23/02/2022 | 21 | B.M CONSTRUCTION | 8.09 | 0 | 1
1649 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000505/2021-2022 | 512/JD | 23/02/2022 | 21 | B.M CONSTRUCTION | 8.09 | 0 | 1
1650 | Jalpaiguri Division | Jalpaiguri Division | Fitting fixing DI specials along with laying distribution and Pump House (5.40m x 3.60 m) at Head work site for Augmentation of Sukhani Piped water supply scheme Zone-III at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000564/2023-2024 | 2391/JD | 16/02/2024 | 20 | BANSBERIA CONSTRUCTION CO. | 96.25 | 0 | 0
1651 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III head work site at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000582/2021-2022 | 513/JD | 23/02/2022 | 21 | M/S R.N. TRADERS | 8.09 | 7.35 | 1
1652 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 2nd Tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- III at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000583/2021-2022 | 514/JD | 23/02/2022 | 21 | M/S R.N. TRADERS | 8.09 | 7.33 | 1
1653 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying pipe line for H/W Site at Sukani zone III PWSS site piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000591/2023-2024 | 2329/JD | 08/02/2024 | 45 | LOPCHAN ENTERPRISE | 18.11 | 0 | 0
1654 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000607/2023-2024 | 2308/JD | 07/02/2024 | 30 | M/S A.P. DEVELOPERS | 7.76 | 0 | 0
1655 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000608/2023-2024 | 2309/JD | 07/02/2024 | 30 | D. S. ENTERPRISE | 7.78 | 7.61 | 100
1656 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000609/2023-2024 | 2310/JD | 07/02/2024 | 30 | JAGORAN SARKAR | 8.51 | 7.82 | 100
1657 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Sukhani (zone-III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000612/2023-2024 | 2311/JD | 07/02/2024 | 30 | R.K. SINGHA & SONS | 8.42 | 8.1 | 100
1658 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Providing guarding arrangement at Stack Yard under Resource Division at the Head Work Site of SUKHANI PWSS (ZONE-I) under Jalpaiguri Division P.H.E. Dte. for the period from 01/08/2022 to 31/07/2023." | Assistant Engineer,HQ | Junior Engineer | ORD/000642/2022-2023 | 1504/A/JD | 28/07/2022 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD. | 16.62 | 0 | 0
1659 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVER HEAD RESERVOUR CAPACITY 700 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKHANI (ZONE-II) PIPED WATER SUPPLY SCHEME . | Assistant Engineer,HQ | Junior Engineer | ORD/000690/2023-2024 | 2392/JD | 16/02/2024 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 145.22 | 0 | 0
1660 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 750 CUM AND 20 M STAGGING HEIGHT AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SUKANI (ZONE I) PIPED WATER SUPPLY SCHEME IN CONNECTION WITH JAL JEEVAN MISSION AT BLOCK: RAJGANJ UNDER JALPAIGURI DIVISION, P.H.E DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000694/2023-2024 | 2411/JD | 19/02/2024 | 548 | AMINUL HOQUE | 207.67 | 81.6 | 50
1661 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd TubeWell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS zone -III at Rajganj Block under Jalpaiguri Division P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000701/2021-2022 | 766/JD | 23/03/2022 | 21 | M/S KARMAKAR CONSTRACTION | 8.09 | 7.6 | 1
1662 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell site at Sukani Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000730/2023-2024 | 2452/JD | 23/02/2024 | 30 | M/S SAHA ENTERPRISE | 8.31 | 0 | 0
1663 | Jalpaiguri Division | Jalpaiguri Division | Shifting AC pipes ,Coumpound clearing, Cutting trees and other ancillary works at Sukani zone -II under Sukani piped water supply scheme under Jalpaiguri water supply Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000732/2023-2024 | 2453/JD | 23/02/2024 | 14 | NEW KUNDU ENTERPRISE | 2.83 | 2.9 | 100
1664 | Jalpaiguri Division | Jalpaiguri Division | Interconnection work for Iron Elimination Plant to Rising main, Construction Platform land development and other ancillary works at Sukani zone I and zone II in connection with Jal Jeevan Mission at sukani PWSS at Rajganj Block,under Jalpaiguri Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000792/2023-2024 | 2633/JD | 07/03/2024 | 15 | D. S. ENTERPRISE | 12.81 | 12.74 | 100
1665 | Jalpaiguri Division | Jalpaiguri Division | Shifting AC pipes, Coumpound clearing ,Cutting trees ,Land development ,inter connection of IEP and other ancillary works at Sukani zone -II Head work site under Sukani piped water supply scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000806/2023-2024 | 2635/JD | 07/03/2024 | 15 | A P CONSTRUCTION | 6.53 | 6.68 | 100
1666 | Jalpaiguri Division | Jalpaiguri Division | Construction of Different Component like Pump House, Tube Well, IEP, Boundary wall and ancillary work at Mogradangi of Sukani PWSS (Zone-I) of Raiganj Block under Jalpaiguri Division, PHE, Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000821/2023-2024 | 2729/JD | 13/03/2024 | 748 | D. S. ENTERPRISE | 54.2 | 0 | 20
1667 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell site at Sukani Zone- III piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000832/2023-2024 | 08/01/JD | 15/03/2024 | 30 | PARESH CHAND GHOSH ROY | 8.32 | 0 | 100
1668 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000885/2021-2022 | 842/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 7.79 | 1
1669 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 4th tubewell by Reverse Rotary method of drilling for Augmentation of Sukhani PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000886/2021-2022 | 843/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 7.7 | 1
1670 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000055/2023-2024 | 1097/JD | 24/08/2023 | 0 | Resource Division | 208.46 | 0 | 0
1671 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000081/2024-2025 | 2221/JD | 01/12/2024 | 0 | Resource Division | 88.05 | 0 | 0
1672 | Jalpaiguri Division | Jalpaiguri Division | LDS PURBA DAUKIMARI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000093/2022-2023 | BP-2022-23-45 | 24/05/2022 | 0 | SUKES BASU MAJUMDAR | 58.14 | 0 | 0
1673 | Jalpaiguri Division | Jalpaiguri Division | LDS FHTC DAKHIN CHAK MAULANI | Assistant Engineer,HQ | Junior Engineer | VCH/001271/2021-2022 | BP-2021-22-472 | 28/03/2022 | 0 | UNIBRO INFRASERV PRIVATE LIMITED | 21.09 | 0 | 0
1674 | Jalpaiguri Division | Jalpaiguri Division | SINKING OF 300MM X 200MM DIA 3RD T/WELL SUKHANI PWSS ZONE-II | Assistant Engineer,HQ | Junior Engineer | VCH/001280/2021-2022 | BP-2021-22-479 | 29/03/2022 | 0 | B.M CONSTRUCTION | 6.93 | 0 | 0
1675 | Jalpaiguri Division | Jalpaiguri Division | CONST 250 M3 B/WALL BARADIGHI T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001369/2021-2022 | BP-2021-22-471 | 28/03/2022 | 0 | BOSE ENTERPRISE | 49.78 | 0 | 0
1676 | Jalpaiguri Division | Jalpaiguri Division | LDS BARADIGHI TG PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001374/2021-2022 | BP-2021-22-475 | 31/03/2022 | 0 | DIPAK KUMAR CHAKRABORTY | 7.66 | 0 | 0
1677 | Jalpaiguri Division | Jalpaiguri Division | EXT PIPE LINE SUKHANI ZONE - II | Assistant Engineer,HQ | Junior Engineer | VCH/001399/2021-2022 | BP-2021-22-503 | 30/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0
1678 | Jalpaiguri Division | Jalpaiguri Division | TUBE WELL SUKHANI ZONE-II | Assistant Engineer,HQ | Junior Engineer | VCH/001438/2021-2022 | BP-2021-22-479 | 29/03/2022 | 0 | SUKES BASU MAJUMDAR | 6.93 | 0 | 0
1679 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SUKHANI,T/W-I,ZONE-III under MAL CCC [APPLICATION NO. 100000101510, Reference ID : 860293810] | Assistant Engineer,HQ | Junior Engineer | BILL/02495/2023-2024 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2 | 0 | 0
1680 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000260/2022-2023 | 1004/NMD | 28/07/2022 | 21 | SUMON ELECTRICAL | 2.79 | 2.79 | 100
1681 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. IV, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000261/2022-2023 | 1005/NMD | 28/07/2022 | 21 | CHOWDHURY AND BASU ENTERPRISE | 2.79 | 2.79 | 100
1682 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000262/2022-2023 | 1006/NMD | 28/07/2022 | 21 | M/S SAJAHAN CHOWDHURY | 2.41 | 2.39 | 100
1683 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. IV, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000263/2022-2023 | 1007/NMD | 28/07/2022 | 21 | DAWA DUKPA | 2.39 | 0 | 0
1684 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. I, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000264/2022-2023 | 1008/NMD | 28/07/2022 | 978 | B.B. CONCERNED | 2.79 | 2.5 | 100
1685 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. II, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000265/2022-2023 | 1009/NMD | 28/07/2022 | 21 | SARKAR ELECTRIC | 2.79 | 2.79 | 100
1686 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SUKHANI W/S Scheme at T/W No. III, Zone-III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000267/2022-2023 | 1010/NMD | 28/07/2022 | 21 | ANUP BASU | 2.77 | 0 | 0
1687 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no IIin the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000523/2022-2023 | 1059/NMD | 24/08/2022 | 30 | ABHISEK ENGINEERING CONCERN | 8.26 | 8.26 | 100
1688 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000560/2022-2023 | 1108/NMD | 07/09/2022 | 30 | M/S P.P. ELECTRICALS | 8.26 | 8.26 | 100
1689 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-III) PWSS, at TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000561/2022-2023 | 1107/NMD | 07/09/2022 | 937 | M/S PARITOSH BHOWMICK AND CO. | 8.26 | 0 | 100
1690 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-II) PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000562/2022-2023 | 1106/NMD | 07/09/2022 | 30 | M/S ROYAL ENTERPRISE | 8.12 | 8.12 | 100
1691 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-II) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000563/2022-2023 | 1105/NMD | 07/09/2022 | 30 | TAPAN BISWAS | 8.09 | 8.09 | 70
1692 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-I) PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000564/2022-2023 | 1104/NMD | 07/09/2022 | 967 | SANJIB SAHA | 8.26 | 6.41 | 100
1693 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SUKHANI (Z-I) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000565/2022-2023 | 1103/NMD | 07/09/2022 | 30 | BONANZA ENTERPRISE | 8.26 | 8.26 | 100
1694 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-III, ZONE-II of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951589,Reference ID : 860244513 | Assistant Engineer,HQ | Junior Engineer | VCH/000324/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1695 | Northern Mechanical | Jalpaiguri Division | Infrustructure cost for New Service Connection Charge for TW-III, ZONE-II of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054733,Reference ID : 402840890 | Assistant Engineer,HQ | Junior Engineer | VCH/000325/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.44 | 0 | 0
1696 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-IV, ZONE-II of SUKHANI (SARIUM KALIBARI) W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002950741,Reference ID : 860244518 | Assistant Engineer,HQ | Junior Engineer | VCH/000326/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1697 | Northern Mechanical | Jalpaiguri Division | Infrastructure cost for New Service Connection Charge for TW-IV, ZONE-II of SUKHANI (SARIUM KALIBARI) W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054738,Reference ID : 402840893 | Assistant Engineer,HQ | Junior Engineer | VCH/000327/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0
1698 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-III, ZONE-I of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951616,Reference ID : 860244512 | Assistant Engineer,HQ | Junior Engineer | VCH/000328/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1699 | Northern Mechanical | Jalpaiguri Division | Infrastructure cost for New Service Connection Charge for TW-III, ZONE-I of SUKHANI W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054732,Reference ID : 402840892 | Assistant Engineer,HQ | Junior Engineer | VCH/000329/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.89 | 0 | 0
1700 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-II, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002957097 , Reference ID : 402849241] | Assistant Engineer,HQ | Junior Engineer | VCH/000769/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1701 | Northern Mechanical | Jalpaiguri Division | Infrastructure cost for New Service Connection Charge for TW-II, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000056936 , Reference ID : 860245496] | Assistant Engineer,HQ | Junior Engineer | VCH/000770/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0
1702 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-I, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002957084 , Reference ID : 402849240] | Assistant Engineer,HQ | Junior Engineer | VCH/000771/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1703 | Northern Mechanical | Jalpaiguri Division | Infrustructure cost for New Service Connection Charge for TW-I, ZONE-III of SUKHANI W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000056935 , Reference ID : 860245495] | Assistant Engineer,HQ | Junior Engineer | VCH/000772/2022-2023 | BP/2022-23/33 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0
1704 | Northern Mechanical | Jalpaiguri Division | Installation of Infrastructure IRO NSC Application 4002960888 at Nawapara, Chaulhati under UMCCC ¿ Sukhani , Zone-III, T/W No. III, [APPLICATION NO. 100000057238, Reference ID : 860246418] | Assistant Engineer,HQ | Junior Engineer | VCH/000842/2022-2023 | BP/22-23/57 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.78 | 0 | 0
1705 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for Sukhani , Zone-III, T/W No. III near Nawapara, [APPLICATION NO. 4002960888, Reference ID : 402852055] | Assistant Engineer,HQ | Junior Engineer | VCH/000843/2022-2023 | BP/22-23/57 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1706 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SUKHANI W/S SCHEME, T/W No. IV, under BELAKOBA CCC, [APPLICATION NO. 4002974096, Reference ID :402863303] | Assistant Engineer,HQ | Junior Engineer | VCH/000894/2022-2023 | BP/22-23/60 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1707 | Northern Mechanical | Jalpaiguri Division | Installation of Infrastructure COST at SUKHANI W/S SCHEME, T/W No. IV, under BELAKOBA CCC, [APPLICATION NO. 100000058353, Reference ID : 860248265] | Assistant Engineer,HQ | Junior Engineer | VCH/000895/2022-2023 | BP/22-23/60 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0
1708 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Part-B of Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000034/2024-2025 | 941/JD | 07/08/2024 | 15 | PRITAM DUTTA | 4.83 | 4.83 | 100
1709 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000083/2024-2025 | 802/RWS | 20/08/2024 | 30 | TECHNO CRACY | 7.49 | 0 | 0
1710 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 3rd Pump House site of Brahmapur PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division PHE, DTE. |  | Junior Engineer | ORD/000098/2024-2025 | 1299/JD | 05/09/2024 | 60 | M/S KARMAKAR CONSTRUCTION | 10.93 | 0 | 0
1711 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Brahmapur PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000436/2023-2024 | 1670/JD | 24/11/2023 | 495 | NARAYAN CHANDRA SAHA | 597.49 | 147.47 | 50
1712 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Brahmapur PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000458/2024-2025 | 2335./JD | 12/12/2024 | 60 | SANDIP BANIK | 61.25 | 0 | 0
1713 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000043/2023-2024 | 1112/JD | 24/08/2023 | 0 | Resource Division | 122.36 | 0 | 0
1714 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000112/2023-2024 | 1506/JD | 13/10/2023 | 0 | Resource Division | 15.68 | 0 | 0
1715 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000192/2023-2024 | 2053/JD | 09/01/2024 | 0 | Resource Division | 15.68 | 0 | 0
1716 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Brahmapur, T/W-II under BHOTPATTY CCC APPLICATION NO. 4003375994 Reference ID : 403191703 |  | Junior Engineer | BILL/00208/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.64 | 0 | 0
1717 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Brahmapur, T/W-III under BHOTPATTY CCC APPLICATION NO. 4003377837 Reference ID : 403192843 |  | Junior Engineer | BILL/00288/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.64 | 0 | 0
1718 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
1719 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
1720 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BRAHAMPURI PWSS, TW no I, II and III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000825/2022-2023 | 267/NMD | 21/03/2023 | 895 | DAS ENTERPRISE | 32.59 | 0 | 65
1721 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001006/2024-2025 | 26/NMD | 06/01/2025 | 30 | M/S SWAPAN BANERJEE | 15.35 | 0 | 0
1722 | Jalpaiguri Division |  | Supply of Fuel (Petrol) of Vehicle No. WB 49 K 9449 for the Month of August 2024. |  |  | BILL/00648/2024-2025 | BP-2024-25-365 | 13/09/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
1723 | Jalpaiguri Division |  | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of September 2024. |  |  | BILL/00851/2024-2025 | BP-2024-25-486 | 07/10/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
1724 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
1725 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000023/2024-2025 | 737/JD | 26/07/2024 | 524 | ASIM GUPTA | 166.13 | 0 | 100
1726 | Jalpaiguri Division |  | Distribution System and Functional Household Tap Connection (FHTC) for Sathkumar Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  |  | ORD/000027/2024-2025 | 738/JD | 26/07/2024 | 615 | ANUP KUNDU CONSTRUCTION CO | 142.74 | 0 | 95
1727 | Jalpaiguri Division |  | Construction of Boundary wall, Foot Path, Drain, pipeline for washout at HW site Satkhamar - II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, PHE Dte. |  |  | ORD/000089/2024-2025 | 1174/JD | 23/08/2024 | 587 | M/S A.B.G. CONSTRUCTION | 31.86 | 0 | 0
1728 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
1729 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  |  | ORD/000101/2024-2025 | 874/JD | 31/07/2024 | 184 | SOUMEN GHOSH | 0.88 | 0.51 | 0
1730 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - II of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000112/2025-2026 | 490/RWS | 29/05/2025 | 30 | CHANDAN GHOSH | 5.77 | 0 | 0
1731 | Jalpaiguri Division |  | Construction of Boundary Wall ,Foot Path,Drain at 2nd site at zone - I of Satkhamar PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000113/2025-2026 | 491/RWS | 29/05/2025 | 308 | SUKES BASU MAJUMDAR | 6.1 | 0 | 100
1732 | Jalpaiguri Division |  | Laying Additional Distribution line with providing and installation of Sluice Valve and Specials at Zone-I of Satkhamar Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block - Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000170/2025-2026 | 2108/JD | 15/10/2025 | 168 | SUKES BASU MAJUMDAR | 32.96 | 0 | 100
1733 | Jalpaiguri Division |  | Construction of different components of Satkhamar Zone- II Piped Water Supply Scheme i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  |  | ORD/000440/2023-2024 | 1705/JD | 04/12/2023 | 850 | M/S A.B.G. CONSTRUCTION | 590.4 | 0 | 90
1734 | Jalpaiguri Division |  | Construction of Iron Elemination Plant (IEP) including interconnection work and washout line at H/W site in Zone-II Satkhamar PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000529/2024-2025 | 46/JD | 09/01/2025 | 240 | M/S M.B. DESIGN | 43.97 | 0 | 80
1735 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000201/2023-2024 | 2063/JD | 10/01/2024 | 0 | Resource Division | 43.48 | 0 | 0
1736 | Northern Mechanical |  | New Service Connection Charge for SATKHAMAR, ZONE-I,T/W-II, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003338890 Reference ID : 403162909 |  |  | BILL/00158/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.26 | 0 | 0
1737 | Northern Mechanical |  | New Service Connection Charge for SATKHAMAR, ZONE-I,T/W-III, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003341662 Reference ID : 403174732 |  |  | BILL/00160/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.96 | 0 | 0
1738 | Northern Mechanical |  | New Service Connection Charge for SATKHAMAR, ZONE-I, T/W-I under UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003351968 Reference ID : 403174734 |  |  | BILL/00305/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.49 | 0 | 0
1739 | Northern Mechanical |  | New Service Connection Charge for SATKHAMAR, T/W- VI, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341729, Reference ID : 403172439] |  |  | BILL/02149/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.69 | 0 | 0
1740 | Northern Mechanical |  | New Service Connection Charge for SATKHAMAR, T/W- V, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341726, Reference ID : 403171912] |  |  | BILL/02150/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0
1741 | Northern Mechanical |  | New Service Connection Charge for SATKHAMAR, T/W- IV, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341723, Reference ID : 403171803] |  |  | BILL/02151/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0
1742 | Jalpaiguri Division |  | Construction of Boundary Wall Rising Main Interconnection, Pathway, Drain etc. at HW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000075/2024-2025 | 1297/JD | 05/09/2024 | 60 | KAMAL DAS | 20.16 | 0 | 0
1743 | Jalpaiguri Division |  | Construction of different components of Singimari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000328/2023-2024 | 1349/JD | 26/09/2023 | 548 | M/S R.N. TRADERS | 724.62 | 217.56 | 15
1744 | Jalpaiguri Division |  | Construction of Boundary Wall, Rising Main Interconnection, Pathway, Drain, Land Development etc. at 2nd TW Site for Singimari PWSS icw JJM under Jalpaiguri Division, PHE Dte. |  |  | ORD/000429/2024-2025 | 1152/RWS | 03/12/2024 | 30 | PRABIR SHOME | 9.14 | 0 | 0
1745 | Jalpaiguri Division |  | Balance Laying Distribution System including providing Functional Household Tap Connection in connection with JJM under Singimari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000550/2024-2025 | 127/JD | 16/01/2025 | 60 | SWAPAN SAHA | 34.8 | 0 | 0
1746 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 56/JD | 09/04/2024 | 0 | Resource Division | 21.92 | 0 | 0
1747 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 2042/JD | 09/01/2024 | 0 | Resource Division | 17.33 | 0 | 0
1748 | Northern Mechanical |  | New Service Connection Charge for SINGIMARI, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003376114 Reference ID : 403191660 |  |  | BILL/00149/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.73 | 0 | 0
1749 | Northern Mechanical |  | New Service Connection Charge for SINGIMARI, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003376577 Reference ID : 403191663 |  |  | BILL/00156/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.21 | 0 | 0
1750 | Northern Mechanical |  | New Service Connection Charge for SINGIMARI, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003379454 Reference ID : 403196948 |  |  | BILL/00204/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.38 | 0 | 0
1751 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SINGIMARI PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000937/2023-2024 | 1751/NMD | 31/10/2023 | 579 | M/S PARITOSH BHOWMICK AND CO. | 32.98 | 0 | 50
1752 | Jalpaiguri Division |  | Supply of Toner and Mouse for Office use. |  |  | BILL/00819/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.08 | 0 | 0
1753 | Jalpaiguri Division |  | Supply of Printer Teflon, Toner for Office use. |  |  | BILL/00820/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1754 | Jalpaiguri Division |  | Supply of Toner, SSD and Ink for Office use. |  |  | BILL/00821/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1755 | Jalpaiguri Division |  | Supply of Processor, RAM, SMPS and SSD for Office use. |  |  | BILL/00822/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.06 | 0 | 0
1756 | Jalpaiguri Division |  | Supply of RAM, Logic Board, Pickup Roller and Teflon for Office use. |  |  | BILL/00823/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1757 | Jalpaiguri Division |  | Supply of Magnetic Relay, Logic Board and Pickup Roller for Office use. |  |  | BILL/00824/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1758 | Jalpaiguri Division |  | Supply of Printer Logic Board and Pickup Roller for Office use. |  |  | BILL/00825/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1759 | Jalpaiguri Division |  | Supply of Printer Power Supply, Teflon for Office use. |  |  | BILL/00826/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1760 | Jalpaiguri Division |  | Supply of Motherboard and Power Supply Unit for Office use. |  |  | BILL/00827/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1761 | Jalpaiguri Division |  | Supply of Toner and Desktop RAM for Office use. |  |  | BILL/00828/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1762 | Jalpaiguri Division |  | Supply of Brother 263 Toner, 88A Toner, 110A Toner, Keyboard and Mouse for Office use. |  |  | BILL/00829/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1763 | Jalpaiguri Division |  | Supply of Motherboard, SSD & Keyboard and Mouse for Office use. |  |  | BILL/00830/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1764 | Jalpaiguri Division |  | Supply of 88A Compatible Toner for Office use. |  |  | BILL/00831/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.07 | 0 | 0
1765 | Jalpaiguri Division |  | Supply of Motherboard, RAM and Printer Relay Unit for Office use. |  |  | BILL/00832/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1766 | Jalpaiguri Division |  | Supply of Motherboard, Toner and Printer Fuser Unit for Office use. |  |  | BILL/00833/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1767 | Jalpaiguri Division |  | Supply of SSD, Hard Disk and Printer Power Supply Board for Office use. |  |  | BILL/00834/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1768 | Jalpaiguri Division |  | Supply of SSD, Motherboard, Processor, SMPS and Mouse for Office use. |  |  | BILL/00835/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1769 | Jalpaiguri Division |  | Supply of Motherboard, RAM, Pickup Roller and Toner for Office use. |  |  | BILL/00836/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1770 | Jalpaiguri Division |  | Supply of Brother Toner and SMPS for Office use. |  |  | BILL/00837/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1771 | Jalpaiguri Division |  | Supply of Toner for Office use. |  |  | BILL/00838/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1772 | Jalpaiguri Division |  | Supply of Logic Board, Power Supply and Teflon for Office use. |  |  | BILL/00839/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1773 | Jalpaiguri Division |  | Supply of Logic Board, Magnetic Relay and Teflon for Office use. |  |  | BILL/00840/2024-2025 | BP-2024-25-500 | 07/10/2024 | 0 | WEBFLEX CONSULTANCY SERVICE PRIVATE LIMITED. | 0.1 | 0 | 0
1774 | Jalpaiguri Division |  | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Rajganj block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  |  | ORD/000467/2023-2024 | 1292/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
1775 | Jalpaiguri Division |  | Construction of different components of Shikarpur Bhandarpur Zone - I PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block - RAJGANJ under Jalpaiguri Division, P.H.E.Dte. of North Bengal Circle-I, PHE Dte under JJM Programme. |  |  | ORD/000817/2023-2024 | 2623/JD | 07/03/2024 | 908 | ASHIT KUMAR SINGHA | 682.9 | 363.2 | 85
1776 | Jalpaiguri Division |  | Construction of different components of Shikarpur Bhandarpur Zone - II PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block - RAJGANJ under Jalpaiguri Division, P.H.E.Dte. of North Bengal Circle-I, PHE Dte under JJM Programme. |  |  | ORD/000818/2023-2024 | 2624/JD | 07/03/2024 | 600 | M/S SURAJIT DEY AND CO. | 714.03 | 204.87 | 65
1777 | Northern Mechanical |  | New Service Connection Charge for SHIKARPUR PWSS, ZONE-I, TW NO. II, under BELAKOBA CCC APPLICATION NO. 4003430834 Reference ID : 403234011 |  |  | BILL/01071/2024-2025 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0
1778 | Northern Mechanical |  | New Service Connection Charge for SHIKARPUR PWSS, ZONE-I, TW NO. I, under BELAKOBA CCC APPLICATION NO. 4003430831 Reference ID : 403234013 |  |  | BILL/01072/2024-2025 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.26 | 0 | 0
1779 | Northern Mechanical |  | New Service Connection Charge for SHIKARPUR PWSS, ZONE-II, TW NO. I, under BELAKOBA CCC APPLICATION NO. 4003430829 Reference ID : 403234010 |  |  | BILL/01073/2024-2025 | BP/24-25/167 | 29/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.73 | 0 | 0
1780 | Northern Mechanical |  | New Service Connection Charge for SHIKARPUR, ZONE-II, TW NO-II, BELAKOBA CCC APPLICATION NO. 4003430808 Reference ID : 403234012 |  |  | BILL/01267/2024-2025 | BP/24-25/204 | 12/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.58 | 0 | 0
1781 | Northern Mechanical |  | New Service Connection Charge for SHIKARPUR, ZONE-I, TW NO-III, BELAKOBA CCC APPLICATION NO. 4003453987 Reference ID : 403250072 |  |  | BILL/01268/2024-2025 | BP/24-25/204 | 12/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.05 | 0 | 0
1782 | Northern Mechanical |  | New Service Connection Charge for SHIKARPUR, ZONE-II, TW NO-III, BELAKOBA CCC APPLICATION NO. 4003453990 Reference ID : 403250073 |  |  | BILL/01367/2024-2025 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.38 | 0 | 0
1783 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for SHIKARPUR BHANDARPUR PWSS at TW NO I,II,III (ZONE-I,II) in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000210/2024-2025 | 1404/NMD | 21/08/2024 | 30 | ALPHA ENTERPRISE | 68.61 | 0 | 0
1784 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
1785 | Northern Mechanical |  | Installation of two tank chlorination system at SHIKARPUR and other adjacent water supply scheme UNDER JJM under RAJGANJ Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  |  | ORD/000888/2024-2025 | 80/SMSD | 07/02/2025 | 15 | CHOWDHURY AND BASU ENTERPRISE | 1.57 | 0 | 0
1786 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (Petrol) of Vehicle No. WB 25 K 9449 for the Month of October 2024. |  | Junior Engineer | BILL/00938/2024-2025 | BP-2024-25-525 | 29/11/2024 | 0 | FILL & SMILE | 0.13 | 0 | 0
1787 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at HW site of Barapatina Nutanbus Zone-II PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000011/2025-2026 | 895/JD | 08/05/2025 | 40 | PRADIP KUMAR SHIL | 18.52 | 0 | 0
1788 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection (FHTC) for Barapatina Nutunbas Zone-II Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000029/2024-2025 | 736/JD | 26/07/2024 | 524 | MOTI INDUSTRIES | 128.89 | 82.7 | 85
1789 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) |  | Junior Engineer | ORD/000033/2025-2026 | 820/JD | 30/04/2025 | 61 | SUKES BASU MAJUMDAR | 0.8 | 0 | 0
1790 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  | Junior Engineer | ORD/000101/2024-2025 | 874/JD | 31/07/2024 | 184 | SOUMEN GHOSH | 0.88 | 0.44 | 0
1791 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site BARAPATINA NATUNBUS ZONE -II PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000106/2025-2026 | 484/RWS | 29/05/2025 | 307 | JAYA SARKAR | 8.04 | 0 | 0
1792 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Balance portion of Jalpaiguri Sadar Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000122/2024-2025 | 1421/JD | 20/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 4.93 | 0 | 90
1793 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri RWS Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" |  | Junior Engineer | ORD/000123/2025-2026 | 1499/JD | 30/06/2025 | 31 | SUKES BASU MAJUMDAR | 0.4 | 0 | 0
1794 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Barapatina Nutanbus Zone-II PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000128/2023-2024 | 408/A/JD | 07/06/2023 | 705 | UNIBRO INFRASERV PRIVATE LIMITED | 434.44 | 213.71 | 70
1795 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). |  | Junior Engineer | ORD/000295/2023-2024 | 855/JD | 31/07/2023 | 184 | SOUMEN GHOSH | 0.88 | 0 | 20
1796 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit)." |  | Junior Engineer | ORD/000570/2023-2024 | 2197/JD | 25/01/2024 | 182 | SOUMEN GHOSH | 0.88 | 0.56 | 0
1797 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000012/2024-2025 | 2016/JD | 19/11/2024 | 0 | Resource Division | 156.48 | 0 | 0
1798 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000139/2023-2024 | 1884/JD | 20/12/2023 | 0 | Resource Division | 14.51 | 0 | 0
1799 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341742, Reference ID : 403172228] |  | Junior Engineer | BILL/02146/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.01 | 0 | 0
1800 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BARAPATINA NUTANBUS, ZONE-II, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003351981, Reference ID : 403172665] |  | Junior Engineer | BILL/02147/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.85 | 0 | 0
1801 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
1802 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at BARAPATINA NATUNBUS PWSS for T/W No. I and II, ZONE-II in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000843/2024-2025 | 582/NMD | 07/02/2025 | 30 | SARKAR ELECTRIC | 23.55 | 0 | 0
1803 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
1804 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0
1805 | Jalpaiguri Division |  | Surveying, Planning, Designing, Construction, Supply and installation and commissioning of surface (River) based water treatment unit to yield 1430 KLD drinking water (Phase-I) on EPC- Turnkey basis for Augmentation of Chengmari Tea Garden Pipe Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000205/2024-2025 | 1590/JD | 23/10/2024 | 504 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 936.29 | 0 | 0
1806 | Jalpaiguri Division |  | Construction of Intake Well for Sub-Surface Water Source at River Bed of Diana under Nagrakata Block of Jalpaiguri District i.c.w Chengmari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000740/2023-2024 | 2495/JD | 28/02/2024 | 21 | GOUTAM DAS | 37.37 | 37.49 | 100
1807 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF CHENGMARI TG AREA PWSS, TW no 1 to 9 in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000869/2023-2024 | 1817/NMD | 01/11/2023 | 30 | CONCORD ENGINEERING | 103.77 | 0 | 0
1808 | Jalpaiguri Division |  | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing with Soil Investigation Work, Sinking 2 Nos Rig Bore TubeWell by ODEX-165 method of dirlling, 2 Nos Pump House (5.4m x 3.6m) and 2 Nos Boundary Wall (H/W and 2nd Site) along with Laying Distribution System including Rising Main with providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of Satkhaya Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000284/2023-2024 | 1255/JD | 13/09/2023 | 626 | B RAI CONSTRUCTION COMPANY | 183 | 13.3 | 14
1809 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 1063/JD | 24/08/2023 | 0 | Resource Division | 8.3 | 0 | 0
1810 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000210/2023-2024 | 2067/JD | 10/01/2024 | 0 | Resource Division | 6.28 | 0 | 0
1811 | Northern Mechanical |  | "INFRA COST IRO NSC for (REJU) SATHKAYA TG TW NO-III, METELI CCC " APPLICATION NO.100000107270 Reference ID : 860298680 |  |  | BILL/00324/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.07 | 0 | 0
1812 | Northern Mechanical |  | " New Service Connection Charge for (REJU) SATHKAYA TG TW NO-IV, METELI CCC " APPLICATION NO.4003401337 Reference ID : 403212023 |  |  | BILL/00325/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1813 | Northern Mechanical |  | " New Service Connection Charge for (REJU) SATHKAYA TG TW NO-III, METELI CCC " APPLICATION NO.4003401332 Reference ID : 403212025 |  |  | BILL/00326/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1814 | Northern Mechanical |  | "INFRA COST IRO NSC for (REJU) SATHKAYA TG TW NO-IV, METELI CCC " APPLICATION NO.100000107273 Reference ID : 860298683 |  |  | BILL/00329/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.43 | 0 | 0
1815 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SATHKAYA TEA GARDEN AREA PWSS, TW NO III, IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000458/2023-2024 | 1434/NMD | 10/08/2023 | 30 | SUBODH KUMAR BANIK | 24.25 | 0 | 95
1816 | Northern Mechanical |  | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  |  | ORD/000665/2025-2026 | 1084/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.79 | 0 | 0
1817 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.06.2024 to 30.11.2024)". | Assistant Engineer,HQ | Junior Engineer | ORD/000005/2024-2025 | 347/JD | 31/05/2024 | 183 | RUPA PRASAD | 0.88 | 2.22 | 100
1818 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Nowapara Piped Water Supply Scheme Block - Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000010/2025-2026 | 893/JD | 08/05/2025 | 328 | SAHA CONSTRUCTION | 75.34 | 0 | 0
1819 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000034/2025-2026 | 821/JD | 30/04/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0
1820 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000035/2025-2026 | 822/JD | 30/04/2025 | 61 | AJIJUL HAQUE | 0.8 | 0 | 0
1821 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000124/2025-2026 | 1500/JD | 30/06/2025 | 31 | MD AMIRUL ISLAM | 0.4 | 0 | 0
1822 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000125/2025-2026 | 1501/JD | 30/06/2025 | 31 | AJIJUL HAQUE | 0.4 | 0 | 0
1823 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000150/2025-2026 | 1731/JD | 31/07/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0
1824 | Jalpaiguri Division | Jalpaiguri Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000198/2025-2026 | 1997/JD | 25/09/2025 | 61 | MD AMIRUL ISLAM | 0.8 | 0 | 0
1825 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Nowapara PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN , FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Divison , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000444/2023-2024 | 1775/JD | 08/12/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 686.37 | 0 | 0
1826 | Jalpaiguri Division | Jalpaiguri Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Dhupguri, Banarhat & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000471/2025-2026 | 2438/JD | 27/11/2025 | 30 | MD AMIRUL ISLAM | 0.4 | 0 | 0
1827 | Jalpaiguri Division | Jalpaiguri Division | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 100
1828 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000044/2023-2024 | 1106/JD | 24/08/2023 | 0 | Resource Division | 28.96 | 0 | 0
1829 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000188/2023-2024 | 2033/JD | 09/01/2024 | 0 | Resource Division | 22.38 | 0 | 0
1830 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for NAWAPARA, TW NO-I, NJP GB CCC APPLICATION NO. 4003354727 Reference ID : 403174711 | Assistant Engineer,HQ | Junior Engineer | BILL/00433/2024-2025 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0
1831 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
1832 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NOWAPARA PWSS, TW no I , II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000658/2023-2024 | 1472/NMD | 17/08/2023 | 30 | M/S RATAN KUMAR DASGUPTA AND CO. | 32.15 | 0 | 0
1833 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Dwarikamari Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000160/2020-2021 | 476/RWS | 15/10/2020 | 30 | GOUTAM DAS | 4.84 | 0 | 0
1834 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Dwarikamari piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-E) |  | Junior Engineer | ORD/000185/2020-2021 | 1497/JD | 22/12/2020 | 30 | GOUTAM DAS | 21.72 | 41.14 | 1
1835 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System Mogalkata Tea Garden Area Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Part-K) |  | Junior Engineer | ORD/000203/2021-2022 | 1655/JD | 08/10/2021 | 15 | PRABIR SHOME | 9.87 | 0.94 | 0
1836 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works at Jakhai bari, Kathal Tali, Kalirhat & adjacent area of Dwarikamari W/S/S under Jalpaiguri Division , P.H.E .Dte. (Part-F). Block-Maynaguri. District- Jalpaiguri. |  | Junior Engineer | ORD/000426/2022-2023 | 625/JD | 13/03/2023 | 45 | ARATI CONSTRUCTION | 45 | 22.64 | 100
1837 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PREPARATION OF DPR FOR SOUTH BERUBARI PWSS |  | Junior Engineer | VCH/000505/2021-2022 | 440/21-22 | 04/10/2021 | 0 | SUBHANKAR GHOSH | 2.32 | 0 | 0
1838 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC under Dwarikamari WSS |  | Junior Engineer | VCH/001146/2020-2021 | 1053 | 11/01/2021 | 0 | BARUN KUMAR DUTTA | 4.43 | 0 | 0
1839 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC AT DWARIKAMARI PWSS |  | Junior Engineer | VCH/001293/2020-2021 | 1189 | 02/02/2021 | 0 | GOUTAM DAS | 4.83 | 0 | 0
1840 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Madabdanga Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000168/2020-2021 | 471/RWS | 15/10/2020 | 30 | ALICK DUTTA | 4.72 | 9.48 | 1
1841 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madab danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000202/2020-2021 | 1537/JD | 31/12/2020 | 60 | ANUP SARKAR | 32.76 | 59.31 | 1
1842 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna for providing drinking water under the command area of Madabdanga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000211/2020-2021 | 48/JD | 07/01/2021 | 60 | M/S SIBU DEY AND CO. | 39.4 | 0 | 0
1843 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of store below OHR , plinth protection and construction of valve chamber etc. including through reparing of pipe line with cleaning to provide water facility near Jalpesh more under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000319/2021-2022 | 870/RWS | 08/12/2021 | 15 | M/S SURAJIT DEY AND CO. | 4.85 | 0 | 0
1844 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works in connection with FHTC at Kadamtala, Indira More and Baman para under Madhabdanga W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000395/2021-2022 | 849/RWS | 03/12/2021 | 10 | ANUP SARKAR | 2.25 | 0 | 0
1845 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC FOR JURANTI T.G PWSS |  | Junior Engineer | VCH/000336/2021-2022 |  | 04/10/2021 | 0 | NARAYAN CH SAHA & SONS | 18.42 | 0 | 0
1846 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC AT MADHABDANGA PWSS |  | Junior Engineer | VCH/001156/2020-2021 | 1054 | 11/01/2021 | 0 | BHOWMIK ENTERPRISES | 4.41 | 0 | 0
1847 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MADHAB DANFGA |  | Junior Engineer | VCH/001179/2021-2022 | BP-2021-22-234 | 23/02/2022 | 0 | ANUP SARKAR | 3.99 | 0 | 0
1848 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST SULICE VALVE CHEMBER FOR DAKSHIN SHALBARI PWSS |  | Junior Engineer | VCH/001248/2021-2022 | BP-2021-22-389 | 17/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0
1849 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORK MADHAB DANGA PWSS |  | Junior Engineer | VCH/001257/2021-2022 | BP-2021-22-405 | 23/03/2022 | 0 | ANUP SARKAR | 2.25 | 0 | 0
1850 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST. SLUICE VALVE DAKSHIN SALBARI |  | Junior Engineer | VCH/001320/2021-2022 | BP-2021-22-389 | 17/03/2022 | 0 | NEW KUNDU ENTERPRISE | 4.82 | 0 | 0
1851 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MADHYA KHUTTIMARI |  | Junior Engineer | VCH/001326/2021-2022 | BP-2021-22-369 | 16/03/2022 | 0 | ALOKE DEY | 16.81 | 0 | 0
1852 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fuel bill |  | Junior Engineer | BILL/00030/2023-2024 | BP-2023-24-30 | 12/04/2023 | 0 | FILL & SMILE | 1.9 | 0 | 0
1853 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Bhangarhat piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000056/2021-2022 | 1076/JD | 02/07/2021 | 30 | DIPANKAR DUTTA | 24.38 | 46.35 | 0
1854 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Hope T.G. Area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000220/2020-2021 | 30/JD | 05/01/2021 | 75 | UMWELT ENGINEER PRIVATE LIMITED | 43.55 | 0 | 0
1855 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | FHTC FOR BHANGARHAT PWSS |  | Junior Engineer | VCH/000367/2021-2022 | 376/21-22 | 20/09/2021 | 0 | MRINMOY KANTI DUTTA | 23.75 | 0 | 0
1856 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall gate, drain and pathway for 4th Tube well site of Rejuvenation of Pora Para Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000028/2022-2023 | 913/JD | 07/04/2022 | 60 | JAYDEB SAHA | 11.2 | 10.27 | 100
1857 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Guard Shed including supply and installation of 300 dia Sluice valve and chamber and the other allied works under Porapara Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000176/2022-2023 | 555/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 4.81 | 4.64 | 0
1858 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of C.C. pathway repairing drain and boundary wall etc. at Head work site campus of Porapara W/S Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000180/2022-2023 | 559/RWS | 01/09/2022 | 30 | SOMNATH ROY | 2.22 | 2.18 | 1
1859 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rectrofting and reparing of pipe line, IEP and other allied works at Fakir Para, Bairagi danga, Brahatal Para due to widening and new construction of road by P.W.D. under Porapara Water Supply Scheme Jalpaiguri Division PHE Dte |  | Junior Engineer 2 | ORD/000182/2022-2023 | 561/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 4.82 | 4.65 | 1
1860 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Rig approach with partial land development for 3rd tube well site under Porapara piped Water Supply Scheme within Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer 2 | ORD/000185/2022-2023 | 564/RWS | 01/09/2022 | 15 | B.M CONSTRUCTION | 4.32 | 2.74 | 1
1861 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Pora Para water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer 2 | ORD/000327/2022-2023 | 1932/JD | 29/09/2022 | 45 | SUKES BASU MAJUMDAR | 16.22 | 16.21 | 0
1862 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of Tubewell at 4th Tube Well site for Rejuvenation of Porapara PWSS in connection with JJM at block - Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000376/2023-2024 | 1517/JD | 16/10/2023 | 30 | RANJEET SINGH BENIWAL | 9.79 | 9.77 | 100
1863 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying new pipe line from Canal near OHR to Taltala near Haldibari Road to facilitate Functional Household Tap Connection in connection with JJM under Porapara Piped Water Supply Scheme under Jalpaiguri |  | Junior Engineer 2 | ORD/000437/2022-2023 | 682/JD | 16/03/2023 | 30 | B.M CONSTRUCTION | 14.92 | 14.92 | 0
1864 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Rejuvenation of Pora Para Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000779/2021-2022 | 473/JD | 22/02/2022 | 60 | SOMNATH ROY | 11.28 | 16.23 | 1
1865 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for PORAPARA , T/W IV, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 100000079172, Reference ID : 860270382] |  | Junior Engineer 2 | BILL/00508/2023-2024 | BP/23-24/44 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.66 | 0 | 0
1866 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PORAPARA , T/W IV, under NAYABASTI PANDAPARA CCC, [APPLICATION NO. 4003163097, Reference ID : 403023007] |  | Junior Engineer 2 | BILL/00509/2023-2024 | BP/23-24/44 | 04/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1867 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PORAPARA, T/W V under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003205927, Reference ID : 403055575] |  | Junior Engineer 2 | BILL/00623/2023-2024 | BP/23-24/83 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.6 | 0 | 0
1868 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of PORAPARA W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer 2 | ORD/000028/2022-2023 | 270/NMD | 22/04/2022 | 21 | SUBHRANGSHU GUHARAJA | 2.77 | 2.77 | 0
1869 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF PORAPARA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer 2 | ORD/000038/2022-2023 | 353/NMD | 23/05/2022 | 30 | CHOWDHURY AND BASU ENTERPRISE | 9.18 | 9.18 | 90
1870 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Sinking of Shallow Tubewell for the Contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Pora Para PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. |  | Junior Engineer 2 | ORD/000555/2022-2023 | 65/DSD | 24/05/2022 | 7 | ALPHA ENTERPRISE | 0.07 | 0.07 | 100
1871 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Pora Para PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. |  | Junior Engineer 2 | ORD/000556/2022-2023 | 66/DSD | 24/05/2022 | 7 | ALPHA ENTERPRISE | 0.95 | 0.95 | 100
1872 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tube well (BDTW) by the Reverse Rotary Circulation method of drilling at Rejuvenation of Pora Para PWSS TW-IV, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000557/2022-2023 | 67/DSD | 24/05/2022 | 7 | ALPHA ENTERPRISE | 0.77 | 0.28 | 100
1873 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of Infrastructure IRO NSC Application 4002893861 at PORAPARA for T/W No. III W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050876, Reference ID : 860240746] |  | Junior Engineer 2 | VCH/000144/2022-2023 | BP/2022-23/16 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.85 | 0 | 0
1874 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for TW-III of Porapara (Reju) under UKILPARA MASKALAIBARI CCC, APPLICATION NO. 4002893861, Reference ID : 402797316 |  | Junior Engineer 2 | VCH/000249/2022-2023 | BP/2022-23/18 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.96 | 0 | 0
1875 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works in connection with FHTC works for the habitation of Monosha Mandir para & Bura Amtolar Gali under Bhuskadanga W/S/S under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000018/2022-2023 | 307/RWS | 28/04/2022 | 15 | BALARAM GHOSH | 0.77 | 0.77 | 0
1876 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF UTTAR BHUSKADANGA & GARTALI JALPESH PIPED WATER SUPPLY SCHEME, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000030/2022-2023 | 976/JD | 20/04/2022 | 120 | UNIBRO INFRASERV PRIVATE LIMITED | 57.66 | 57.61 | 100
1877 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of cement concrete drain , pathway , store below OHR and culvert etc. at H/W site campus of Dakshin Salbari W/S/S under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000170/2021-2022 | 679/RWS | 27/09/2021 | 30 | R.S CONSTRUCTION | 4.85 | 4.86 | 1
1878 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone- III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-J) |  | Junior Engineer | ORD/000277/2022-2023 | 642/RWS | 21/10/2022 | 20 | SOMNATH ROY | 4.82 | 4.68 | 0
1879 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) within Garalbari Zone-III under Jalpaiguri Sadar Block in connection with Jal Sapna under Jalpaiguri Division PHE Dte. (Part-K) |  | Junior Engineer | ORD/000278/2022-2023 | 643/RWS | 21/10/2022 | 20 | J.M. CONSTRUCTION | 3.73 | 3.1 | 0
1880 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works in connection with FHTC of Natun para , Borobari and Malar Math under Uttar Bhuskadanga W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000332/2021-2022 | 743/RWS | 08/10/2021 | 15 | BALARAM GHOSH | 2.86 | 0 | 0
1881 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF UTTAR BHUSKADANGA PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000356/2021-2022 | 254/JD | 31/01/2022 | 1246 | MRINMOY KANTI DUTTA | 79.88 | 35.24 | 90
1882 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PHE Dte Jalpaiguri (with valid Taxi permit). Period from 01/02/2023 to 31/05/2023. |  | Junior Engineer | ORD/000496/2022-2023 | 72/RWS | 31/01/2023 | 120 | APIKUL ALI | 0.59 | 0.59 | 100
1883 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | UTTAR BHUSKA DANGA |  | Junior Engineer | VCH/000924/2021-2022 | BP-2021-22-114 | 03/12/2021 | 0 | BALARAM GHOSH | 4.8 | 0 | 0
1884 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Restoration of pipe line at different places including construction of sluice valve chamber with supply of sluice valv etc.at head work site campus under Mohitnagar W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000017/2022-2023 | 306/RWS | 28/04/2022 | 15 | M/S DEY & ROY CHOUDHURY | 4.83 | 4.83 | 1
1885 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Renovation of Boundary wall including Approach Road, Earth filling, Valve Chambers at Head Work Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000236/2022-2023 | 1813/JD | 14/09/2022 | 21 | M/S DEY & ROY CHOUDHURY | 8.1 | 7.79 | 1
1886 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000296/2021-2022 | 38/JD | 04/01/2022 | 60 | SAUMENDU DUTTA | 10.87 | 0 | 100
1887 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  | Junior Engineer | ORD/000301/2022-2023 | 2190/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.32 | 3.32 | 0
1888 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  | Junior Engineer | ORD/000305/2022-2023 | 2194/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.56 | 3.56 | 0
1889 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) |  | Junior Engineer | ORD/000325/2021-2022 | 879/RWS | 10/12/2021 | 10 | M/S DEY & ROY CHOUDHURY | 1.28 | 0 | 1
1890 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply, Installation, Commissioning (Trial run for 3 months) including testing of 2Nos. 25.00 cum per hour capacity pressure type IEP with accessories including construction of Blower Rooms (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd & 4th tube well site for Rejuvenation of Mohitnagar water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000347/2022-2023 | 132/JD | 17/01/2023 | 45 | R.S CONSTRUCTION | 30.33 | 18.18 | 100
1891 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000403/2022-2023 | 598/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 4.79 | 0 | 100
1892 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections (at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Mohit Nagar Water Supply Scheme under Jalpaiguri Division P.H.E.Dte Jalpaiguri. |  | Junior Engineer | ORD/000405/2022-2023 | 165/RWS | 28/02/2023 | 21 | SOUVIK SAHA | 3.28 | 3.24 | 100
1893 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000408/2022-2023 | 602/JD | 09/03/2023 | 15 | M/S DEY & ROY CHOUDHURY | 3.33 | 0 | 100
1894 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at Sebagram in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-H) |  | Junior Engineer | ORD/000409/2022-2023 | 599/JD | 09/03/2023 | 21 | M/S DEY & ROY CHOUDHURY | 4.51 | 0 | 100
1895 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at Gomosta Para in connection with JJM under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) |  | Junior Engineer | ORD/000410/2022-2023 | 601/JD | 09/03/2023 | 21 | M/S DEY & ROY CHOUDHURY | 4.84 | 0 | 100
1896 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Guard wall including additional part of Boundary wall at 3rd Tubewell Site of Mohitnagar Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000457/2022-2023 | 743/JD | 23/03/2023 | 15 | SAUMENDU DUTTA | 1.76 | 0 | 0
1897 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Mohit Nagar Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Part-G) |  | Junior Engineer | ORD/000513/2021-2022 | 537/JD | 25/02/2022 | 30 | M/S DEY & ROY CHOUDHURY | 21.77 | 0 | 0
1898 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001068/2021-2022 | 39/JD | 04/12/2021 | 60 | NARESH SEN | 11.12 | 11.45 | 1
1899 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Mohitnagar Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001074/2021-2022 | 38/JD | 04/01/2022 | 60 | SAUMENDU DUTTA | 10.87 | 0.28 | 1
1900 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000033/2023-2024 | 1117/JD | 24/08/2023 | 0 | Resource Division | 3.55 | 0 | 0
1901 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SAMSING |  | Junior Engineer | VCH/001149/2021-2022 | BP-2021-22-235 | 16/02/2022 | 0 | SUJAN LAMA | 4.79 | 0 | 0
1902 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FHTC LIKSAN BAZAR (ZONE - III) |  | Junior Engineer | VCH/001394/2021-2022 | BP-2021-22515 | 30/03/2022 | 0 | ALICK DUTTA | 13.19 | 0 | 0
1903 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | DEV LAND & REPAIRING SANITARY & PLUMBING ARRANGEMENT |  | Junior Engineer | VCH/001402/2021-2022 | BP-2021-22-506 | 30/03/2022 | 0 | SANDIP BANIK | 4.55 | 0 | 0
1904 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of MAHITNAGAR W/S Scheme at T/W No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000026/2022-2023 | 268/NMD | 22/04/2022 | 21 | S.P. ENTERPRISE | 2.77 | 2.77 | 0
1905 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector for REJUVENATION of MAHITNAGAR W/S Scheme at T/W No. IV in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000027/2022-2023 | 269/NMD | 22/04/2022 | 21 | SARKAR ELECTRIC | 2.77 | 2.77 | 0
1906 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF MAHITNAGAR PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000036/2022-2023 | 351/NMD | 23/05/2022 | 30 | M/S SAJAHAN CHOWDHURY | 9.19 | 9.19 | 0
1907 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for REJUVENATION OF MAHITNAGAR PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000037/2022-2023 | 352/NMD | 23/05/2022 | 30 | ALPHA ENTERPRISE | 9.18 | 9.18 | 0
1908 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Mahitnagar PWSS TW-III, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. |  | Junior Engineer | ORD/000718/2021-2022 | 283/DSD | 03/01/2022 | 7 | SUMON ELECTRICAL | 0.95 | 0 | 100
1909 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery of Pea-size Gravels (Local Variety) for the contruction of Big Dia Tubewell by Reverse Rotary Circulation Method of Drilling at Rejuvenation of Mahitnagar PWSS TW-IV, Dist- Jalpaiguri, under N.M.S.D.(D), P.H.E. Dte. |  | Junior Engineer | ORD/000743/2021-2022 | 330/DSD | 08/02/2022 | 7 | S.P. ENTERPRISE | 0.95 | 0 | 100
1910 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Carrying out Surging, Development and Y.T. works for a Rig Bored Big Dia Tube well (BDTW) by reverse rotary method of drilling for Rejuvenation of Porapara PWSS TW-III, Rejuvenation of Mahitnagar PWSS TW-III & IV, Rejuvenation of Arji Maria Kamala Pukhari PWSS TW-III & IV, Block - Jalpaiguri, Dist.- Jalpaiguri under different water supply scheme under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000821/2021-2022 | 311/DSD | 21/01/2022 | 21 | UTTAM PAUL | 0.73 | 0.73 | 100
1911 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. IV of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 4002923185, Reference ID : 402817973] |  | Junior Engineer | VCH/000145/2022-2023 | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.95 | 0 | 0
1912 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of Infrastructure IRO NSC Application 4002923185 at T/W No. IV of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050946, Reference ID : 860240066] |  | Junior Engineer | VCH/000146/2022-2023 | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.62 | 0 | 0
1913 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. III of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO.4002923192, Reference ID : 402817972] |  | Junior Engineer | VCH/000147/2022-2023 | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.95 | 0 | 0
1914 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installtion of Infrastructure IRO NSC application 4002923192 at T/W No. III of MAHITNAGAR (REJU) W/S Scheme under UKILPARA MASKALAIBARI CCC [APPLICATION NO. 100000050946, Reference ID : 860240066] |  | Junior Engineer | VCH/000148/2022-2023 | BP/2022-23/15 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.09 | 0 | 0
1915 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 9 (nine) villages under different blocks having less than 100 households under Jalpaiguri district in connection with Jal Swapna |  | Junior Engineer | ORD/000063/2022-2023 | 1226/JD | 01/06/2022 | 30 | M/S NANDY ENTERPRISE | 355.27 | 40.51 | 0
1916 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Implementation of MINI PIPED WATER SUPPLY SCHEME in 4 (Four) no. village under different blocks having less than 100 household under Jalpaiguri district in connection with Jal Swapna. |  | Junior Engineer | ORD/000064/2022-2023 | 1227/JD | 01/06/2022 | 1400 | M/S SIBU DEY AND CO. | 142.11 | 34.23 | 60
1917 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
1918 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 4th tube well site for Juranteeee TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000019/2023-2024 | 252/JD | 10/05/2023 | 45 | SARKAR CONSTRUCTION | 4.64 | 4.64 | 100
1919 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing balance Functional Household Tap Connection (FHTC) at Juranti TG PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000095/2025-2026 | 115/JSSD | 03/06/2025 | 30 | ASIT PAUL | 9.61 | 0 | 100
1920 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate,drain and pathway for 3rd tube-well site of Rejuvenation of Jurantee tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000320/2022-2023 | 62/JSSD | 19/07/2022 | 20 | ARINDAM CHATTERJEE | 3.88 | 3.86 | 100
1921 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System of Rejuvenation of Jurantee Tea Garden Area piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000325/2022-2023 | 2456/JD | 22/12/2022 | 30 | SANDIP BANIK | 71.54 | 71.52 | 100
1922 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Jurantee Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000590/2021-2022 | 737/JD | 17/03/2022 | 30 | ASHIS DUTTA | 13.5 | 9.81 | 100
1923 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation of Jurantee Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000596/2022-2023 | 05/JSSD | 16/05/2022 | 45 | RAJAT GHOSH | 4.65 | 0 | 0
1924 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Jurantee Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000798/2023-2024 | 2628/JD | 07/03/2024 | 45 | ASIT PAUL | 5.61 | 4.65 | 100
1925 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NEORA LINE ZURRANTEE TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 4003197405, Reference ID : 403049083] |  | Junior Engineer | BILL/00611/2023-2024 | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1926 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for NEORA LINE ZURRANTEE TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 100000085207, Reference ID : 860276427] |  | Junior Engineer | BILL/00613/2023-2024 | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.19 | 0 | 0
1927 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NEORA LINE ZURRANTEE TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 4003197409, Reference ID : 403049081] |  | Junior Engineer | BILL/00614/2023-2024 | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1928 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for NEORA LINE ZURRANTEE TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 100000084451, Reference ID : 860276312] |  | Junior Engineer | BILL/00615/2023-2024 | BP/23-24/82 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.74 | 0 | 0
1929 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of peripherial drain with Land development and RBT at 4th tubewell site of Hila Tea Garden in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000021/2023-2024 | 254/JD | 10/05/2023 | 14 | GOPAL DEY | 1.19 | 1.19 | 100
1930 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 4th tube-well site of Rejuvenation of Piped Water Supply Scheme for HILA under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000086/2022-2023 | 1364/JSSD | 19/04/2022 | 20 | GOPAL DEY | 3.89 | 3.91 | 100
1931 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 6th tube well site of Rejuvenation of Hila Tea Garden Piped Water Supply Scheme of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000107/2024-2025 | 1389/JD | 18/09/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0
1932 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 5th tube well site for Hila TG P.W.S.S. under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000271/2022-2023 | 215/JSSD | 16/09/2022 | 60 | U TURN CONSTRUCTION | 4.65 | 4.65 | 100
1933 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall at 3rd Tube well site for Hila T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000417/2020-2021 | 552/JSSD | 29/01/2021 | 30 | SAHA CONSTRUCTION | 4.55 | 3.66 | 1
1934 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works for Laying Distribution System of Rejuvenation of water supply scheme for Hilla Tea Garden Mouza under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000441/2022-2023 | 733/JD | 22/03/2023 | 30 | PROFULLA GHOSH | 32.91 | 24.85 | 100
1935 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works of 3rd Pump House site at Hila Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000553/2023-2024 | 503/JSSD | 02/01/2024 | 30 | SCEC BOENTER AND KDAS JOINT VENTURE | 6.04 | 0 | 0
1936 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hila Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000611/2021-2022 | 561/JD | 01/03/2022 | 30 | ASHIS DUTTA | 13.22 | 13.51 | 1
1937 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection 261Nos. in Connection with Jal Jeevan Mission Hila Tea Garden Piped Water Supply Scheme Under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000799/2023-2024 | 564/JSSD | 05/03/2024 | 30 | SAHA CONSTRUCTION | 9.52 | 9.46 | 100
1938 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m X 2.40m size with sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Water Supply Scheme for HILA Tea Garden under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000835/2021-2022 | 1105/W/JSSD | 27/01/2022 | 45 | TECHNOCRACY ELECTRICAL CONTRACTOR & GENERAL ORDER SUPPLIER | 4.64 | 4.64 | 1
1939 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | FHTC HILLA T.G PWSS |  | Junior Engineer | VCH/001356/2021-2022 | BP-2021-22-473 | 28/03/2022 | 0 | SCEC BOENTER KDAS JOINT VENTURE | 19.05 | 0 | 0
1940 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RECONNECTION OF PIPE LINE RETROFITTING HILLA T.G WSS |  | Junior Engineer | VCH/001357/2021-2022 | BP-2021-22-474 | 28/03/2022 | 0 | SCEC BOENTER KDAS JOINT VENTURE | 17.01 | 0 | 0
1941 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | EARTH FILLING WORK H/W DAKSHIN SALBARI WSS |  | Junior Engineer | VCH/001381/2021-2022 | BP-2021-22-534 | 31/03/2022 | 0 | R.S CONSTRUCTION | 4.66 | 0 | 0
1942 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY INSTALATION COMMISSIONING AND TRIAL OPERATION OF HILA T.G PWSS |  | Junior Engineer | VCH/001443/2021-2022 | BP-2021-22-483 | 29/03/2022 | 0 | S P ENTERPRISE | 8.09 | 0 | 0
1943 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, delivery & installation of 30KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Hila Tea Garden Area Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000142/2022-2023 | 562/NMD | 14/07/2022 | 21 | ALPHA ENTERPRISE | 2.99 | 2.99 | 0
1944 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HILA TG AREA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000769/2022-2023 | 75/NMD | 27/01/2023 | 30 | GURUKRIPA ENTERPRISE | 11.38 | 10.84 | 0
1945 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HILA TG AREA PWSS, TW no V in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000770/2022-2023 | 76/NMD | 27/01/2023 | 30 | HARA PROSAD DAS | 12.38 | 12.37 | 70
1946 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for HILA T.G (REJU) W/S SCHEME, T/W No. V, under NAGRAKATA CCC, [APPLICATION NO. 4002969966, Reference ID :402856020] |  | Junior Engineer | VCH/000850/2022-2023 | BP/22-23/46 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1947 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. V, under NAGRAKATA CCC, [APPLICATION NO. 100000058117, Reference ID : 860247827] |  | Junior Engineer | VCH/000851/2022-2023 | BP/22-23/46 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0
1948 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000058152, Reference ID :860247832] |  | Junior Engineer | VCH/000852/2022-2023 |  | 26/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.39 | 0 | 0
1949 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC, [APPLICATION NO. 100000058152, Reference ID :860247832] |  | Junior Engineer | VCH/000889/2022-2023 |  | 16/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.68 | 0 | 0
1950 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 4002969959 ; Reference ID :402856023] |  | Junior Engineer | VCH/000965/2022-2023 | BP/22-23/46 | 08/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1951 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 100000058152 ; Reference ID :860247832] [PART-II] |  | Junior Engineer | VCH/000966/2022-2023 | BP/22-23/58 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.71 | 0 | 0
1952 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT HILA T.G (REJU) W/S SCHEME, T/W No. IV, under NAGRAKATA CCC [APPLICATION NO. 100000058152 ; Reference ID :860247832] [PART-I] |  | Junior Engineer | VCH/000967/2022-2023 | BP/22-23/59 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.98 | 0 | 0
1953 | Jalpaiguri Division | Northern Mechanical Division | SUPPLY OF FUEL | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00396/2022-2023 | BP-2022-23-545 | 25/03/2023 | 0 | FILL & SMILE | 0.3 | 0 | 0
1954 | Jalpaiguri Division | Northern Mechanical Division | SUPPLY OF FUEL | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00397/2022-2023 | BP-2022-23-544 | 25/03/2023 | 0 | FILL & SMILE | 0.25 | 0 | 0
1955 | Jalpaiguri Division | Northern Mechanical Division | Work of DI Pipe (Raising main), Drain, Chamber, flower block & other ancillary works at 4th site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000151/2023-2024 | 816/RWS | 14/07/2023 | 14 | ARATI CONSTRUCTION | 2.65 | 2.65 | 100
1956 | Jalpaiguri Division | Northern Mechanical Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Madhya khagrabari piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. (2nd Call) | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000152/2023-2024 | 817/RWS | 14/07/2023 | 14 | SOMNATH ROY | 2.65 | 2.6 | 100
1957 | Jalpaiguri Division | Northern Mechanical Division | Continuation Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer R.W.S Sub-Division PH.E Dte Jalpaiguri (with valid Taxi permit). Period from 01/10/2022 to 31/01/2023 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000249/2022-2023 | 616/RWS | 29/09/2022 | 122 | APIKUL ALI | 0.59 | 0.49 | 1
1958 | Jalpaiguri Division | Northern Mechanical Division | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MADHYA KHAGRABARI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000329/2021-2022 | 186/JD | 21/01/2022 | 120 | M/S A.B.G. CONSTRUCTION | 108.63 | 69.86 | 1
1959 | Jalpaiguri Division | Northern Mechanical Division | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-B). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000335/2021-2022 | 189/JD | 21/01/2022 | 1530 | M/S A.B.G. CONSTRUCTION | 181.29 | 94.98 | 100
1960 | Jalpaiguri Division | Northern Mechanical Division | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-A). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000336/2021-2022 | 194/JD | 21/01/2022 | 1166 | M/S A.B.G. CONSTRUCTION | 173.57 | 51.19 | 100
1961 | Jalpaiguri Division | Northern Mechanical Division | LAYING DISTRIBUTION SYSTEM AND PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK UNDER JALPAIGURI DIVISION P.H.E. DTE. (PART-C`). | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000339/2021-2022 | 213/JD | 24/01/2022 | 1142 | NARAYAN CHANDRA SAHA | 169.95 | 98.07 | 75
1962 | Jalpaiguri Division | Northern Mechanical Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000419/2022-2023 | 135/JD | 17/01/2023 | 45 | M/S SURAJIT DEY AND CO. | 16.44 | 15.36 | 100
1963 | Jalpaiguri Division | Northern Mechanical Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th T/W Site of Madhya Khagrabari water supply scheme under Jalpaiguri Division PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000423/2022-2023 | 680/JD | 16/03/2023 | 45 | M/S RATAN KUMAR DAS GUPTA AND CO | 16.43 | 15.36 | 80
1964 | Jalpaiguri Division | Northern Mechanical Division | ADDITIONAL WORK FOR LAYING & DISTRIBUTION SYSTEM IN MADHYA KHAGRABARI PIPED WATER SUPPLY SCHEME BLOCK : MAYNAGURI DISTRICT : JALPAIGURI. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000536/2023-2024 | 1895/JD | 20/12/2023 | 15 | JAYA SARKAR | 9 | 9.1 | 100
1965 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000711/2021-2022 | 223/JD | 24/01/2022 | 60 | SOMNATH ROY | 11.44 | 0 | 0
1966 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000712/2021-2022 | 2225/JD | 27/12/2021 | 60 | ARATI CONSTRUCTION | 11.44 | 11.42 | 1
1967 | Jalpaiguri Division | Northern Mechanical Division | Construction of pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Madyakagrabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/001107/2021-2022 | 2224/JD | 23/12/2021 | 60 | SOMNATH ROY | 11.44 | 11.43 | 100
1968 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000006/2021-2022 | 179/JD | 21/01/2022 | 0 | Resource Division | 127.45 | 0 | 0
1969 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000013/2021-2022 | 551/JD | 01/03/2022 | 0 | Resource Division | 27.35 | 0 | 0
1970 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000084/2024-2025 | 2214/JD | 01/12/2024 | 0 | Resource Division | 22.14 | 0 | 0
1971 | Jalpaiguri Division | Northern Mechanical Division | Providing car on daily hire basis @12.00/Km for official use of the office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000555/2022-2023 | BP-2022-23-155 | 02/09/2022 | 0 | RAKESH SARKAR | 0.19 | 0 | 0
1972 | Jalpaiguri Division | Northern Mechanical Division | LDS REJ NAGRAKATA | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/001261/2021-2022 | BP-2021-22-517 | 30/03/2022 | 0 | UDAYAN BOSE | 6.91 | 0 | 0
1973 | Central Drilling | Northern Mechanical Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHYA KHAGRABARI W/S SCHEME (TW-II), MAYNAGURI BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000014/2022-2023 | 473/CDD | 25/05/2022 | 30 | PADMA ENGINEERING & CO. | 10.64 | 8.15 | 0
1974 | Central Drilling | Northern Mechanical Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOT CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MADHYA KHAGRABARI W/S SCH (TW-I), MAYNAGURI BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000171/2022-2023 | 472/CDD | 25/05/2022 | 30 | PADMA ENGINEERING & CO. | 10.64 | 9.34 | 0
1975 | Central Drilling | Northern Mechanical Division | ADDITIONAL TRANSPORTATION OF DEPARTMENTAL RIG M/C & ACCESSORIES INCLUDING LOADING & UNLOADING FROM MADHYA KHAGRABARI TW-II SITE TO UTTARTAJPUR W/S SCH, UNDER CDD, PHE DTE. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000225/2022-2023 | 186/CMSD-I | 10/06/2022 | 7 | PADMA ENGINEERING & CO. | 0.8 | 0.77 | 0
1976 | Central Drilling | Northern Mechanical Division | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000261/2021-2022 | 575/CMSD-II | 30/11/2021 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0.48 | 0
1977 | Central Drilling | Northern Mechanical Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 250 mtrs. Depth) by utilising Departmental machineries for Kharagpur SG Hospital W/S Scheme, under Paschim Midnapore District, CDD PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000434/2022-2023 | 1350/CDD | 24/11/2022 | 30 | PADMA ENGINEERING & CO. | 18.38 | 3.54 | 0
1978 | Northern Mechanical | Northern Mechanical Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Madhya Khagrabari W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2022-2023 | 563/NMD | 14/07/2022 | 871 | MUSTAFI CONCERN | 2.16 | 0 | 100
1979 | Northern Mechanical | Northern Mechanical Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Madhya Khagrabari W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000094/2022-2023 | 564/NMD | 14/07/2022 | 21 | SUBODH KUMAR BANIK | 2.19 | 0 | 100
1980 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHYA KHAGRABARI PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000118/2022-2023 | 855/NMD | 18/07/2022 | 867 | GOENKA ENTERPRISE | 7.87 | 6.32 | 100
1981 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHYA KHAGRABARI PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000119/2022-2023 | 856/NMD | 18/07/2022 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 7.87 | 7.01 | 80
1982 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for MADHA KHAGRABARI W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 4002941289, Reference ID : 402831971] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000896/2022-2023 | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1983 | Northern Mechanical | Northern Mechanical Division | Installation of Infrastructure COST at MADHA KHAGRABARI W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 100000059498, Reference ID : 860245058] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000897/2022-2023 | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.04 | 0 | 0
1984 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for MADHA KHAGRABARI W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 4002941293, Reference ID : 402831977] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000898/2022-2023 | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
1985 | Northern Mechanical | Northern Mechanical Division | Installation of Infrastructure COST at MADHA KHAGRABARI W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 100000059497, Reference ID : 860245057] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000899/2022-2023 | BP/22-23/62 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0
1986 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of valve chember & Blower room(3.60MX3.00M ) Size for Iron Elimination Plant at Head Work Site of Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000043/2023-2024 | 390/RWS | 25/04/2023 | 14 | SWAPAN SAHA | 4.8 | 4.49 | 100
1987 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall and land development at Head Work Site for Mandalghat Water Supply Scheme under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/000136/2021-2022 | 1442/JD | 09/09/2021 | 30 | M/S UNITED CONSTRUCTION | 10.53 | 10.53 | 100
1988 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing of pump houses & construction of Boundary wall at 2nd site for Mandalghat W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000278/2021-2022 | 820/RWS | 30/11/2021 | 30 | ALICK DUTTA | 4.83 | 4.6 | 99
1989 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with drain for 3rd site of Mondal ghat piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000283/2022-2023 | 648/RWS | 21/10/2022 | 30 | ALICK DUTTA | 4.84 | 4.81 | 100
1990 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Augmentation of Mandolghat PWSS under JJM work at Jalpaiguri sadar Block under PHE Dte., Jalpaiguri Division |  | Junior Engineer | ORD/000334/2023-2024 | 1082/RWS | 19/09/2023 | 30 | TIRTHANKAR CHOWDHURY | 9.24 | 9.03 | 100
1991 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000446/2021-2022 | 342/JD | 03/02/2022 | 90 | M/S R.N. TRADERS | 158.04 | 65.57 | 1
1992 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 550 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF MANDALGHAT PWSS, Block- Jalpaiguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000447/2021-2022 | 336/JD | 02/02/2022 | 120 | M/S R.N. TRADERS | 110.23 | 110.18 | 1
1993 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-C). |  | Junior Engineer | ORD/000459/2021-2022 | 338/JD | 03/02/2022 | 1343 | SIBU DEY | 212.74 | 138.86 | 100
1994 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000460/2021-2022 | 339/JD | 03/02/2022 | 1518 | BISWANATH GHOSH | 150.63 | 91.81 | 60
1995 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF MONDALGHAT PIPED WATER SUPPLY SCHEME BLOCK SADAR DISTRICT JALPAIGURI (PART-B). |  | Junior Engineer | ORD/000465/2021-2022 | 345/JD | 03/02/2022 | 1518 | M/S SURAJIT DEY AND CO. | 195.6 | 74.55 | 85
1996 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Repair work of Pump house , bath room of H/W site & ancilliary works at Mondalghat PWSS under Jalpaiguri Division. |  | Junior Engineer | ORD/000487/2022-2023 | 285/RWS | 29/03/2023 | 14 | M/S UNITED CONSTRUCTION | 1.53 | 1.47 | 100
1997 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site for Augmentation Mondalghat piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000615/2021-2022 | 402/JD | 11/02/2022 | 357 | M/S R.N. TRADERS | 27.54 | 22.98 | 100
1998 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for MondalghatP/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 |  | Junior Engineer | ORD/000723/2021-2022 | 400/RWS | 30/06/2021 | 184 | UNITED CONSTRUCTION | 2.01 | 0 | 1
1999 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000014/2021-2022 | 550/JD | 01/03/2022 | 0 | Resource Division | 60.75 | 0 | 0
2000 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000033/2024-2025 | 2095/JD | 25/11/2024 | 0 | Resource Division | 70.02 | 0 | 0
2001 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000085/2024-2025 | 2212/JD | 01/12/2024 | 0 | Resource Division | 23.36 | 0 | 0
2002 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | providing drainage system for mondalghat pwss |  | Junior Engineer | VCH/000021/2022-2023 | BP-2021-23-7 | 21/04/2022 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0
2003 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING DRAINAGE SYSTEM FOR MONDALGHAT PWSS |  | Junior Engineer | VCH/000057/2022-2023 | BP-2021-22-7 | 21/04/2022 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 1.72 | 0 | 0
2004 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC GRASS MORE |  | Junior Engineer | VCH/000061/2022-2023 | BP-2021-22-25 | 26/04/2022 | 0 | M/S R.N. TRADERS | 7.08 | 0 | 0
2005 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONSTRUCTION 550 M3 AUG MANDALGHAT PWSS |  | Junior Engineer | VCH/001306/2021-2022 | BP-2021-22-391 | 17/03/2022 | 0 | R.N.TRADER'S | 51.64 | 0 | 0
2006 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST FOR MANDALGHAT |  | Junior Engineer | VCH/001437/2021-2022 | BP-2021-22 | 22/03/2022 | 0 | R.B TESTING | 2.02 | 0 | 0
2007 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF MANDALGHAT PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000235/2023-2024 | 1250/NMD | 31/07/2023 | 30 | M/S ANJALI ENTERPRISE | 11.6 | 11.57 | 100
2008 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  | Junior Engineer | BILL/00355/2022-2023 | BP-2023-24-109 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.55 | 0 | 0
2009 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | supply of one maxi cab on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar sub Division,P.H.E Dte. |  | Junior Engineer | BILL/00623/2023-2024 | BP-2023-24-428 | 11/10/2023 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0
2010 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Barnish piped Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000010/2023-2024 | 335/RWS | 10/04/2023 | 14 | SADHAN KARMAKAR | 3.21 | 3.21 | 100
2011 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with gate,drain, Pipe line,rising line, Approach road & other ancillary works for OHR site of Barnish piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000017/2023-2024 | 60/JD | 18/04/2023 | 30 | ASHIT KUMAR SINGHA | 25.62 | 25.6 | 100
2012 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Pathway, Drain,Chember,flower block,Partial land Development , approach & other ancillary works at 4th site of Barnish Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000035/2023-2024 | 388/RWS | 25/04/2023 | 14 | JITENDRA NATH ROY | 5.18 | 4.81 | 100
2013 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 4th T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. |  | Junior Engineer | ORD/000320/2023-2024 | 1266/JD | 13/09/2023 | 45 | ASHIT KUMAR SINGHA | 16.44 | 16.38 | 100
2014 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (30m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain...etc. at 3rd T/W Site of Barnesh piped water supply scheme under JALPAIGURI Division PHE Dte. |  | Junior Engineer | ORD/000339/2022-2023 | 2519/JD | 30/12/2022 | 45 | GIYASUDDIN SEKH | 16.44 | 15.94 | 100
2015 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-B). |  | Junior Engineer | ORD/000359/2021-2022 | 329/JD | 02/02/2022 | 90 | ASHIT KUMAR SINGHA | 146.7 | 121.15 | 80
2016 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-C). |  | Junior Engineer | ORD/000371/2021-2022 | 330/JD | 02/02/2022 | 90 | R.S CONSTRUCTION | 170.45 | 156.41 | 100
2017 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-D). |  | Junior Engineer | ORD/000445/2021-2022 | 331/JD | 02/02/2022 | 90 | SUKES BASU MAJUMDAR | 155.8 | 58.03 | 1
2018 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME BLOCK MAYNAGURI DISTRICT JALPAIGURI (PART-A). |  | Junior Engineer | ORD/000452/2021-2022 | 328/JD | 02/02/2022 | 1304 | ASHIT KUMAR SINGHA | 163.38 | 125.78 | 100
2019 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at different places of Barnes PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000454/2022-2023 | 731/JD | 22/03/2023 | 30 | ASHIT KUMAR SINGHA | 17.49 | 17.49 | 100
2020 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Extention of pipe line at different places of Barnes PWSS under Jalpiaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000484/2022-2023 | 803/JD | 29/03/2023 | 21 | R.S CONSTRUCTION | 10.28 | 10.28 | 100
2021 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (IEP) including construction of concrete platform & drain at Head work site of Augmentation Barnish piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000603/2021-2022 | 409/JD | 15/02/2022 | 45 | ASHIT KUMAR SINGHA | 26.37 | 25.86 | 20
2022 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000713/2021-2022 | 2226/JD | 27/12/2021 | 60 | JITENDRA NATH ROY | 11.44 | 11.45 | 1
2023 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Barnes Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000714/2021-2022 | 2227/JD | 27/12/2021 | 60 | SADHAN KARMAKAR | 11.45 | 11.38 | 1
2024 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Continuation order for Maintenance of pipe line & others Mise. Work related to pipe line Mtc. Of I.E plant for Barnish P/ W/S/S under Jalpaiguri Division PHE Dte. Period from 01.07.2021 to 31.12.2021 |  | Junior Engineer | ORD/000717/2021-2022 | 408/RWS | 30/06/2021 | 184 | JITENDRA NATH ROY | 0.86 | 0 | 1
2025 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 700 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF BARNES PIPED WATER SUPPLY SCHEME, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte |  | Junior Engineer | ORD/001015/2021-2022 | 185/JD | 21/01/2022 | 120 | ASHIT KUMAR SINGHA | 141.66 | 176.05 | 1
2026 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000010/2021-2022 | 558/JD | 01/03/2022 | 0 | Resource Division | 124.02 | 0 | 0
2027 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000073/2024-2025 | 2204/JD | 01/12/2024 | 0 | Resource Division | 24.92 | 0 | 0
2028 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PREPARATION OF DPR ODLABARI PWSS |  | Junior Engineer | VCH/001283/2021-2022 | BP-2021-22-492 | 09/04/2022 | 0 | SUBHANKAR GHOSH | 1.94 | 0 | 0
2029 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION AUG BARNES PWSS |  | Junior Engineer | VCH/001338/2021-2022 | BP-2021-22-398 | 22/03/2022 | 0 | M S PRANTIK ASSOCIATES | 2.02 | 0 | 0
2030 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | BARNESH PWSS |  | Junior Engineer | VCH/001442/2021-2022 | BP-2021-22- | 24/03/2022 | 0 | EXECUTIVE ENGINEER CENTRAL DRILLING DIVISION | 16.99 | 0 | 0
2031 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BARNES (TW-I) PWSS UNDER CDD, PHE DTE. |  | Junior Engineer | ORD/000190/2021-2022 | 756/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 8.39 | 0
2032 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X200MM) BY DEPARTMENTAL RIG MACHINE FOR AUGMENTATION OF BARNES (TW-II) PWSS UNDER CDD, PHE DTE. |  | Junior Engineer | ORD/000191/2021-2022 | 757/ CDD | 07/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.61 | 8.77 | 0
2033 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BARNES (TW-II) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000197/2021-2022 | 596/CMSD-II (D) | 07/12/2021 | 10 | PADMA ENGINEERING & CO. | 0.92 | 0.92 | 0
2034 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION AFTER 200 KM FOR BENTONITE AND OTHERS FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000198/2021-2022 | 607/CMSD-II (D) | 10/12/2021 | 10 | PADMA ENGINEERING & CO. | 0.68 | 0.57 | 0
2035 | Central Drilling | RWS Jalpaiguri Sub-Division | ADDITIONAL TRANSPORTATION OF GRAVELS AFTER 200 KM FOR 20 M3 GRAVELS (1 M3 = 1.68 MT) AT SITE FOR CONSTRUCTION OF TUBE WELL IN MAYNAGURI BLOCK IN JALPAIGURI DISTRICT OF BARNES (TW-I) PWSS UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000199/2021-2022 | 597/CMSD-II (D) | 07/12/2021 | 10 | PADMA ENGINEERING & CO. | 0.92 | 0.87 | 0
2036 | Central Drilling | RWS Jalpaiguri Sub-Division | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 15 | PADMA ENGINEERING & CO. | 4.52 | 1.54 | 0
2037 | Central Drilling | RWS Jalpaiguri Sub-Division | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000261/2021-2022 | 575/CMSD-II | 30/11/2021 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0.12 | 0
2038 | Central Drilling | RWS Jalpaiguri Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. |  | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 30 | DEY ENTERPRISE | 13.83 | 0.01 | 0
2039 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under BARNES PWSS, at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000069/2022-2023 | 444/NMD | 14/06/2022 | 21 | TALUKDER ENTERPRISE | 2.16 | 2.16 | 0
2040 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BARNES PWSS, at TW No. III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000083/2022-2023 | 541/NMD | 08/07/2022 | 30 | SUMON ELECTRICAL | 7.86 | 7.86 | 100
2041 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of Barnes W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000099/2022-2023 | 567/NMD | 14/07/2022 | 21 | S.D. CONCERN WORKSHOP | 2.16 | 2.16 | 0
2042 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BARNES PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000117/2022-2023 | 854/NMD | 18/07/2022 | 30 | SAIKAT SINHA | 7.87 | 7.87 | 100
2043 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BARNISH W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 4002941264, Reference ID : 402831973] |  | Junior Engineer | VCH/000900/2022-2023 | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2044 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of Infrastructure COST at BARNISH W/S SCHEME, T/W No. IV, under MAYNAGURI CCC, [APPLICATION NO. 100000059561, Reference ID : 860249301] |  | Junior Engineer | VCH/000901/2022-2023 | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.97 | 0 | 0
2045 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BARNISH W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 4002941261, Reference ID : 402831975] |  | Junior Engineer | VCH/000902/2022-2023 | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2046 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of Infrastructure COST at BARNISH W/S SCHEME, T/W No. III, under MAYNAGURI CCC, [APPLICATION NO. 100000059398, Reference ID : 860248698] |  | Junior Engineer | VCH/000903/2022-2023 | BP/22-23/61 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0
2047 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna including retrofitting of Laying Distribution System for Rejuvenation of Purba Salbari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000003/2022-2023 | 879/JD | 05/04/2022 | 210 | M/S GARGO TRADERS | 417.6 | 418.3 | 64
2048 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System with Providing Functional House Hold Tap Connection in connection with JJM at Purbba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000008/2025-2026 | 677/JD | 04/04/2025 | 45 | A P CONSTRUCTION | 36.26 | 0 | 0
2049 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation of Purba Salbari PWSS i.e. RISING MAIN, Boundary wall etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000039/2024-2025 | 986/JD | 14/08/2024 | 595 | SAHA CONSTRUCTION | 29.57 | 12.95 | 50
2050 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 3rd Tubewell site of Purba Salbari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000057/2023-2024 | 323/JD | 18/05/2023 | 14 | ABHIJIT SARKAR | 4.59 | 3.31 | 80
2051 | Jalpaiguri Division | Jalpaiguri Division | Shifting of DI pipeline due to widening of road of Purba Salbari Area Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000154/2022-2023 | 1534/JD | 02/08/2022 | 15 | ABHIJIT SARKAR | 1.52 | 1.51 | 1
2052 | Jalpaiguri Division | Jalpaiguri Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing for Rejuvenation of Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000201/2022-2023 | 1964/JD | 18/10/2022 | 180 | SAHA CONSTRUCTION | 69.07 | 66.66 | 60
2053 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Rejuvenation Purba Salbari P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000212/2022-2023 | 1802/JD | 14/09/2022 | 21 | ABHIJIT SARKAR | 4.65 | 4.74 | 0
2054 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tubewell by Reverse Rotary method of drilling for Rejuvenation of Purba Salbari PWSS at Dhupguri Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000475/2021-2022 | 349/JD | 22/02/2022 | 21 | ABHIJIT SARKAR | 7.97 | 0 | 0
2055 | Jalpaiguri Division | Jalpaiguri Division | Repairing of 2 nos. of Pump House (Head Work site & 2nd site) ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement and other allied works at Purba Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000641/2020-2021 | 251/JD | 19/02/2021 | 30 | ABHIJIT SARKAR | 4.85 | 0.46 | 1
2056 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000018/2021-2022 | 553/JD | 01/03/2022 | 0 | Resource Division | 39.86 | 0 | 0
2057 | Jalpaiguri Division | Jalpaiguri Division | FUEL BILL | Assistant Engineer,HQ | Junior Engineer | VCH/000665/2022-2023 | BP-2022-23-350 | 09/12/2022 | 0 | FILL & SMILE | 0.62 | 0 | 0
2058 | Jalpaiguri Division | Jalpaiguri Division | CONST H/W BHANGARHAT WSS | Assistant Engineer,HQ | Junior Engineer | VCH/001371/2021-2022 | BP-2021-22-516 | 30/03/2022 | 0 | SAHA CONSTRUCTION | 4.83 | 0 | 0
2059 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for JURAPANI,SALBARI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018659, Reference ID : 402928489] | Assistant Engineer,HQ | Junior Engineer | BILL/00036/2022-2023 | BP/22-23/128 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
2060 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for JURAPANI,SALBARI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 100000066802, Reference ID : 860257022] | Assistant Engineer,HQ | Junior Engineer | BILL/00037/2022-2023 | BP/22-23/128 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.01 | 0 | 0
2061 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for PURBA SALBARI (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000579/2022-2023 | 1124/NMD | 12/09/2022 | 30 | DIAMOND ELECTRICAL WORKS | 8.02 | 7.99 | 100
2062 | Northern Mechanical | Jalpaiguri Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under PURBA SALBARI (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000784/2022-2023 | 105/NMD | 03/02/2023 | 21 | DIAMOND ELECTRICAL WORKS | 2.27 | 2.27 | 100
2063 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 250mm x 150mm x 132m deep Rig Bored tube well by Reverse Rotary method of drilling for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000011/2022-2023 | 872/JD | 04/04/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 7.8 | 7.58 | 0
2064 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supplying and Installation of 77 nos Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division PHE Dte |  | Junior Engineer | ORD/000014/2024-2025 | 88/JSSD | 20/06/2024 | 10 | GOUTAM DAS | 14.3 | 14.25 | 100
2065 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Supplying and Installation of 24 nos. Display Board at different piped water supply scheme in connection with JJM under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000015/2024-2025 | 89/JSSD | 20/06/2024 | 10 | GURUKUL INFOTECH | 4.46 | 4.43 | 100
2066 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jalswapna for Augmention of Purba Batabati Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-A) |  | Junior Engineer | ORD/000025/2022-2023 | 863/JD | 01/04/2022 | 1280 | UNIBRO INFRASERV PRIVATE LIMITED | 236.61 | 176.55 | 100
2067 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2068 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Sluice Valves at Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000115/2024-2025 | 331/JSSD | 10/09/2024 | 7 | SWAPAN SAHA | 0.55 | 0 | 100
2069 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at 3rd Pump House site with land development, inside peripheral drain, gate, pathway and other ancillary works for Augmentation Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000124/2022-2023 | 84/JSSD | 22/07/2022 | 20 | N S CONSTRUCTION & SUPPLIER | 4.57 | 4.51 | 100
2070 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/08/2025 to 30/09/2025) |  | Junior Engineer | ORD/000153/2025-2026 | 1734/JD | 31/07/2025 | 61 | APIKUL ALI | 0.8 | 0 | 0
2071 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 300 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with land development works for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000160/2023-2024 | 793/JD | 24/07/2023 | 180 | TIRTHANKAR CHOWDHURY | 91.24 | 40.38 | 70
2072 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". |  | Junior Engineer | ORD/000201/2025-2026 | 2000/JD | 25/09/2025 | 61 | APIKUL ALI | 0.8 | 0 | 0
2073 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main from 1st & 2nd Tubewell site to OHR for Augmentation of Purba Batabari PWSS in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000404/2023-2024 | 388/JSSD | 09/11/2023 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 3.64 | 0 | 0
2074 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with Pump House (3.6mx2.4m) and Sinking of tube well by reverse rotary method of Drilling for 4th TW including Delivery main for Augmentation of Purba Batabari PWSS under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000461/2024-2025 | 108/JD | 16/01/2025 | 60 | M/S. S.D. ENTERPRISE | 19.96 | 0 | 0
2075 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". |  | Junior Engineer | ORD/000474/2025-2026 | 2405/JD | 19/11/2025 | 30 | APIKUL ALI | 0.4 | 0 | 0
2076 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of paver block approach road with land development, inside drain etc. and fixing R.B.T. in boundary wall at H/W Site for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000531/2021-2022 | 134/JD | 14/01/2022 | 15 | SUNIL ROY | 4.46 | 3.52 | 0
2077 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Restoration of pipeline at Purba Batabari PWSS (damaged part) under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000551/2021-2022 | 991/JSSD | 03/01/2022 | 10 | BIMAN DAS | 2.99 | 0 | 0
2078 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000551/2023-2024 | 499/JSSD | 02/01/2024 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 0 | 0 | 0
2079 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Estimate for the Construction of Box Culvert for making approach to Purba Batabari HW Site under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000552/2023-2024 | 499/JSSD | 02/01/2024 | 30 | TIRTHANKAR CHOWDHURY | 2.8 | 0 | 0
2080 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of Pump House (2nd T/W Site) and extension of pipeline repairing of pipeline under Purba Batabari Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000560/2020-2021 | 169/JSSD | 13/08/2020 | 30 | BIMAN DAS | 4.77 | 0 | 0
2081 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System with providing Functional Household Tap Connection (FHTC) in connection with Jalswapna for Augmentation of Purba Batabari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Part-B) |  | Junior Engineer | ORD/000788/2021-2022 | 667/JD | 09/03/2022 | 1394 | BOSE ENTERPRISE | 221.99 | 176.41 | 90
2082 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m X 2.40 m) size including Sanitary and Plumbing works at 3rd TubeWell site for Augmentation of Purbba Batabari Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. |  | Junior Engineer | ORD/000830/2021-2022 | 1108/W/JSSD | 27/01/2022 | 45 | N S CONSTRUCTION & SUPPLIER | 4.75 | 4.75 | 100
2083 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain, culvert, Pipe line for H/W site of Purba Batabari piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001010/2021-2022 | 1332/JD | 23/08/2021 | 30 | R.S CONSTRUCTION | 15.53 | 14.66 | 0
2084 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Sluice valve Chamber and GI line over culvert for Batabari Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001047/2021-2022 | 1931/JD | 29/11/2021 | 15 | SUNIL ROY | 1.63 | 1.58 | 0
2085 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 300 CuM OHR for Augmentation of Purba Batabari PWSS under Jalpaiguri Diviion, P.H.E. Dte. |  | Junior Engineer | ORD/001066/2021-2022 | 1064/JSSD | 24/01/2022 | 20 | G. TECH INDIA | 1.83 | 0.74 | 0
2086 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RENOVATION OF B-WALL SOUTH BERUBARI |  | Junior Engineer | VCH/000088/2022-2023 | BP-2022-2023-46 | 24/05/2022 | 0 | A.P CONSTRUCTION | 2.2 | 0 | 0
2087 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | HIRE CHARGES |  | Junior Engineer | VCH/000663/2022-2023 | BP-2022-23-344 | 09/12/2022 | 0 | APIKUL ALI | 0.34 | 0 | 0
2088 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | HIRE CHARGES |  | Junior Engineer | VCH/000664/2022-2023 | BP-2022-23-344 | 09/12/2022 | 0 | RAKESH SARKAR | 0.33 | 0 | 0
2089 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | AUG PURBA BATABARI |  | Junior Engineer | VCH/001080/2021-2022 | BP-2021-22-169 | 14/01/2022 | 0 | BIMAN DAS | 4.36 | 0 | 0
2090 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RESTORATION OF PIPE LINE PURBA BATABARI PWSS |  | Junior Engineer | VCH/001275/2021-2022 | BP-2021-22-508 | 30/03/2022 | 0 | BIMAN DAS | 2.99 | 0 | 0
2091 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PREPARATION OF DPR PURBA BATABARI PWSS |  | Junior Engineer | VCH/001281/2021-2022 | BP-2021-22-489 | 29/03/2022 | 0 | SUBHANKAR GHOSH | 1.57 | 0 | 0
2092 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | PROVIDING DRINKING ARRANGEMENT AWC MAL SUB-DIVISION |  | Junior Engineer | VCH/001363/2021-2022 | BP-2021-22-541 | 31/03/2022 | 0 | DREAM CONSTRUCTION | 4.61 | 0 | 0
2093 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SINKING OF TUBEWELL FOR LATAGURI |  | Junior Engineer | VCH/001403/2021-2022 | BP-2021-22-542 | 31/03/2022 | 0 | DREAM CONSTRUCTION | 7.63 | 0 | 0
2094 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF PURBA BATABARI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000768/2022-2023 | 74/NMD | 27/01/2023 | 30 | M/S MATRI CONSTRUCTION | 10.98 | 10.98 | 100
2095 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PURBO BATABARI NEAR DIGHIR PAR W/S SCHEME, T/W No. III, under MATELLI CCC, [APPLICATION NO. 4002964283, Reference ID :402851945] |  | Junior Engineer | VCH/000979/2022-2023 | BP/22-23/91 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2096 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at PURBO BATABARI NEAR DIGHIR PAR W/S SCHEME, T/W No. III, under MATELLI CCC, [APPLICATION NO. 100000059481, Reference ID : 860249201] |  | Junior Engineer | VCH/000980/2022-2023 | BP/22-23/91 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0
2097 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM at various House hold and Govt. Aided Educational/ Health Institute under the command area of Rejuvenation of Kathalguri T.G. Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000094/2022-2023 | 1300/JD | 14/06/2022 | 15 | SAHA CONSTRUCTION | 2.15 | 2.18 | 0
2098 | Jalpaiguri Division | Jalpaiguri Division | Repairing of Damaged distribution line due to drain construction by T.G. authority, Land development, re modification of distribution main along with other ancillary works within the command area of rejuvenation of Kathalguri T.G. P.W.S.S. under Jalpaiguri Division, P.H.E.Dte.and I.E.Plant etc. under Jalpaiguri Division, P.H.E.Dte. (from 01.08.2022 to 31.01.2023) | Assistant Engineer,HQ | Junior Engineer | ORD/000215/2022-2023 | 1805/JD | 14/09/2022 | 21 | RABINDRANATH DUTTA | 4.83 | 4.83 | 0
2099 | Jalpaiguri Division | Jalpaiguri Division | Resistivity test at two alternative Site and two reserved sites for sinking of Tube Well at Zone-II for Augmentation of Chamurchi Tea Garden Area Piped Water Supply Scheme and at Two Sites for Rejuvenation of Khthalguri T.G. P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000227/2022-2023 | 1856/JD | 16/09/2022 | 21 | PARAMJYOTI ENTERPRISE | 1.25 | 1.25 | 0
2100 | Jalpaiguri Division | Jalpaiguri Division | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000284/2022-2023 | 649/RWS | 21/10/2022 | 20 | PARAMJYOTI ENTERPRISE | 4.32 | 4.32 | 1
2101 | Jalpaiguri Division | Jalpaiguri Division | Laying of Distribution Line, Along with Rising Main Connection between Head works pump House site and Additional tube well site including common manifold with balanced Functional Household Tap Connection (Phase -IV) in connection with Jal Jeevan Mission under Rejuvenation of Kathalguri T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000429/2022-2023 | 630/JD | 13/03/2023 | 920 | J.M. CONSTRUCTION | 46.3 | 0 | 80
2102 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Kathalguri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000508/2021-2022 | 107/JD | 11/01/2022 | 60 | JITENDRA NATH ROY | 4.65 | 4.65 | 100
2103 | Jalpaiguri Division | Jalpaiguri Division | Construction of 200 Cu.M. capacity R.C.C. Over Head Reservoir of 20 Mtr. Staging Height, Construction of One No. Pump House (5.40m x 3.60m) Boundary wall for the Head Works Site and other related works including pump connection of different pump for Rejuvenation of Kathalguri Tea Garden area piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000512/2021-2022 | 352/JD | 03/03/2022 | 180 | NEW KUNDU ENTERPRISE | 81.56 | 72.38 | 100
2104 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (5.40m x 3.60m) with sanitary & plumbing arrangement including Rising Main & interconnections at Head Work site for Augmentation of Kathalguri Water Supply Scheme at Banarhat Block in connection with Jal Jeevan Mission under Jalpaiguri Division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000604/2023-2024 | 2305/JD | 07/02/2024 | 45 | NEW KUNDU ENTERPRISE | 7.39 | 6.62 | 100
2105 | Jalpaiguri Division | Jalpaiguri Division | Shifting of existing pipeline of Khalaigram W/S Scheme between the Khalaigram Khetifullbari P.W.D. Road under Jalpaiguri Division P.H.E. Dte. (PART - A) | Assistant Engineer,HQ | Junior Engineer | ORD/000633/2020-2021 | 423/JD | 04/06/2020 | 90 | LOKNATH CONSTRUCTION | 28.18 | 1.75 | 0
2106 | Jalpaiguri Division | Jalpaiguri Division | Construction of Foot Path, Drain including rising main interconnections at HW site of Kathalguri PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000813/2023-2024 | 2634/JD | 07/03/2024 | 21 | NEW KUNDU ENTERPRISE | 13.52 | 8.51 | 100
2107 | Jalpaiguri Division | Jalpaiguri Division | LDS FHTC AUG KRANTI (ZONE -I) | Assistant Engineer,HQ | Junior Engineer | VCH/001372/2021-2022 | BP-2021-22-527 | 30/03/2022 | 0 | M/S SIBU DEY AND CO. | 9.39 | 0 | 0
2108 | Jalpaiguri Division | Jalpaiguri Division | LDS BARADIGHI | Assistant Engineer,HQ | Junior Engineer | VCH/001385/2021-2022 | BP-2021-22-528 | 30/03/2022 | 0 | GOUTAM DAS | 4.52 | 0 | 0
2109 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for KATHALGURI TG,T/W II, under BANARHAT CCC [APPLICATION NO. 4003103099 ; Reference ID : 402976404] | Assistant Engineer,HQ | Junior Engineer | BILL/00801/2022-2023 | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2110 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for KATHALGURI TG,T/W II, under BANARHAT CCC [APPLICATION NO. 100000073456 ; Reference ID : 860265206] | Assistant Engineer,HQ | Junior Engineer | BILL/00802/2022-2023 | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.11 | 0 | 0
2111 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for KATHALGURI T.G (REJU) W/S Scheme, T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003103082 ; Reference ID : 402976414] | Assistant Engineer,HQ | Junior Engineer | BILL/00805/2022-2023 | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2112 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for KATHALGURI T.G (REJU) W/S Scheme, T/W No. I, under BANARHAT CCC [APPLICATION NO.100000074460 ; Reference ID : 860265550] | Assistant Engineer,HQ | Junior Engineer | BILL/00806/2022-2023 | BP/22-23/169 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.72 | 0 | 0
2113 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2114 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF KATHALGURI TG PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000873/2022-2023 | 337/NMD | 29/03/2023 | 30 | SUBODH KUMAR BANIK | 29.9 | 23.93 | 60
2115 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 3rd Tubewell site of Mainatali PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000059/2023-2024 | 324/JD | 18/05/2023 | 14 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.64 | 2.39 | 50
2116 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 183 mm x 125mm dia tube well by ODEX-165 method of drilling for Rejuvenation of Mainatali PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000450/2021-2022 | 198/JD | 21/01/2022 | 30 | M/S BABUN BISWAS | 7.89 | 5.33 | 100
2117 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Mainatali P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000500/2021-2022 | 95/JD | 10/01/2022 | 60 | ABHIJIT SARKAR | 4.65 | 4.68 | 100
2118 | Jalpaiguri Division | Jalpaiguri Division | Construction of Blower Room & IEP (40m3/hr.) of Mainatali PWSS, in connection with Rejuvenation of Mainatali PWSS under Jal Jeevan Mission at Dhupguri Block under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000510/2023-2024 | 1778/JD | 08/12/2023 | 60 | D. S. ENTERPRISE | 16.9 | 15.26 | 75
2119 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MAYNATALI, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147727, Reference ID : 403014098] | Assistant Engineer,HQ | Junior Engineer | BILL/00063/2023-2024 | BP/23-24/18 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
2120 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for MAYNATALI, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077915, Reference ID : 860269055] | Assistant Engineer,HQ | Junior Engineer | BILL/00064/2023-2024 | BP/23-24/18 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.27 | 0 | 0
2121 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for Rejuvenation of Mainatali, T/W-IV under DHUPGURI CCC APPLICATION NO. 4003336981 Reference ID :- 403161218 | Assistant Engineer,HQ | Junior Engineer | BILL/00209/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.18 | 0 | 0
2122 | Northern Mechanical | Jalpaiguri Division | Additional New Service Connection Charge for REJUVENATION OF MAINATALI PWSS, at TW NO IV, under DHUPGURI CCC APPLICATION NO. 100000113878 Reference ID : 860306078 | Assistant Engineer,HQ | Junior Engineer | BILL/00642/2024-2025 | BP/24-25/156 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.74 | 0 | 0
2123 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MAINATALI, T/W-IV, under DHUPGURI CCC, [APPLICATION NO. 4003336981, Reference ID : 403161218] | Assistant Engineer,HQ | Junior Engineer | BILL/02135/2023-2024 |  | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.18 | 0 | 0
2124 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
2125 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MAINATALI PWSS, at TW NO III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000893/2022-2023 | 392/NMD | 29/03/2023 | 734 | BLUE PINE | 24.99 | 11.94 | 100
2126 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Chhaophali PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000042/2023-2024 | 138/JD | 28/04/2023 | 180 | RANJEET SINGH BENIWAL | 131.18 | 58.34 | 50
2127 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of Rising Main along with pump connection for commissioning of the scheme and remaining part of laying distribution system with providing FHTC at Chhaoaphali Piped W/S Scheme in connection with JJM at Matiali Block, under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000139/2024-2025 | 1531/JD | 01/10/2024 | 30 | PRIYABRATA KARMAKAR | 18.45 | 18.94 | 100
2128 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with approach road at H/W site including rising main and interconnections of Chhaophali PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000699/2023-2024 | 2412/JD | 19/02/2024 | 45 | RANJEET SINGH BENIWAL | 19.17 | 0 | 0
2129 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000034/2023-2024 | 1115/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0
2130 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000182/2023-2024 | 2041/JD | 09/01/2024 | 0 | Resource Division | 2.85 | 0 | 0
2131 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for CHHAOAPHALI, T/W No. I under METELLI CCC [APPLICATION NO. 4003292351 , Reference ID : 403124700] |  | Junior Engineer | BILL/01801/2023-2024 | BP/23-24/270 | 23/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2132 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for CHHAOAPHALI, T/W No. I under METELLI CCC [APPLICATION NO. 100000097045 , Reference ID : 860289125] |  | Junior Engineer | BILL/01802/2023-2024 | BP/23-24/271 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.12 | 0 | 0
2133 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHHAOAPHALI PWSS, TW NO I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000308/2023-2024 | 1273/NMD | 02/08/2023 | 30 | M/S PALIDEB ENGINEERING WORKS | 24.43 | 21.08 | 75
2134 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0
2135 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0
2136 | Jalpaiguri Division |  | Construction of different components of Gadang Pratham Khanda PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000475/2022-2023 | 779/JD | 27/03/2023 | 180 | M/S. DOLPHIN CONSTRUCTION CO. | 222.91 | 127.77 | 20
2137 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 152/JD | 28/04/2023 | 0 | Resource Division | 26.83 | 0 | 0
2138 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000124/2023-2024 | 1838/JD | 15/12/2023 | 0 | Resource Division | 2.62 | 0 | 0
2139 | Northern Mechanical |  | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS , T/W-I under DHUPGURI CCC, APPLICATION NO. 4003412908 Reference ID : 403221510 |  |  | BILL/00388/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.3 | 0 | 0
2140 | Northern Mechanical |  | New Service Connection Charge for GADANG PRATHAM KHANDA PWSS, TW no II, under DHUPGURI CCC APPLICATION NO. 4003290916 Consumer ID : 403123851 |  |  | BILL/00536/2024-2025 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0
2141 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
2142 | Northern Mechanical |  | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0
2143 | Northern Mechanical |  | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
2144 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
2145 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Maynaguri Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000061/2024-2025 | 944/JD | 07/08/2024 | 15 | GURUKUL INFOTECH | 4.43 | 0 | 100
2146 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection at Paschimbaragila PWSS in Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000455/2024-2025 | 2334./JD | 12/12/2024 | 45 | PRITAM DUTTA | 21.76 | 0 | 0
2147 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Paschim Baragila PWSS i.e. TW, pump Houses, Water distribution network, OHR, RISING MAIN, FHTC etc. under Jal Jeeban Mission at Block - Maynaguri under Jalpaiguri Divission, P.H.E. Dte. |  | Junior Engineer | ORD/000470/2022-2023 | 776/JD | 27/03/2023 | 180 | TIRTHANKAR CHOWDHURY | 234.57 | 159.05 | 75
2148 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000672/2023-2024 | 167/RWS | 15/02/2024 | 358 | EDIFICE ENTERPRISE | 7.52 | 0 | 100
2149 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site including rising main and interconnections of PASCHIM BARAGILA PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000779/2023-2024 | 2496/JD | 28/02/2024 | 45 | TIRTHANKAR CHOWDHURY | 16.53 | 0 | 0
2150 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000022/2023-2024 | 166/JD | 28/04/2023 | 0 | Resource Division | 15.92 | 0 | 0
2151 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000187/2023-2024 | 2050/JD | 09/01/2024 | 0 | Resource Division | 2.89 | 0 | 0
2152 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PASCHIM BOROGILA, T/W No. II, under MAYNAGURI CCC, [APPLICATION NO. 4003266398, Reference ID : 403105500] |  | Junior Engineer | BILL/01284/2023-2024 | 23-24/156&164 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0
2153 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PASCHIM BOROGILA, T/W No. I, under MAYNAGURI CCC, [APPLICATION NO. 4003266412, Reference ID : 403105853] |  | Junior Engineer | BILL/01285/2023-2024 | 23-24/156&164 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.99 | 0 | 0
2154 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
2155 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
2156 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
2157 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PASCHIM BARAGILA PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000844/2022-2023 | 272/NMD | 21/03/2023 | 30 | S.P. ENTERPRISE | 20.63 | 16.5 | 80
2158 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAYNAGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001007/2024-2025 | 27/NMD | 06/01/2025 | 30 | M/S BHOWMICK & CO. | 18.4 | 0 | 0
2159 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. 183 mm x 125mm dia 120 m Deep tube well by ODEX-165 method of drilling at Chilaoni TG area Piped Water Supply Scheme under PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000075/2022-2023 | 1314/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 0 | 1
2160 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 3rd tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000087/2022-2023 | 74/JSSD | 22/07/2022 | 45 | SUJAN LAMA | 4.65 | 4.65 | 100
2161 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 x2.40) size with sanitary & plumbing arrangement at 4th tube well site for Chilouni TG P.W.S.S. under Jalpaiguri Division,P.H.E Dte. |  | Junior Engineer | ORD/000123/2022-2023 | 75/JSSD | 22/07/2022 | 45 | SUJOY CHOWDHURY | 4.65 | 4.65 | 100
2162 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Chilouni Tea Garden PWSS i.e. OHR, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000182/2023-2024 | 852/JD | 28/07/2023 | 569 | NARAYAN CHANDRA SAHA | 147.52 | 118.57 | 58
2163 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retroffitting works, repairing of 2 nos pump house 2 nos boundary wall, repairing of Rising main line and other allied works at Chilaoni TG Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000398/2022-2023 | 607/JD | 09/03/2023 | 30 | SUJAN LAMA | 29.35 | 0 | 0
2164 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Matiali block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000454/2023-2024 | 1286/RWS | 28/11/2023 | 30 | B.M CONSTRUCTION | 3.11 | 3.11 | 100
2165 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000082/2023-2024 | 1069/JD | 24/08/2023 | 0 | Resource Division | 15.45 | 0 | 0
2166 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for CHALOUNI T.G NEW LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 4002964337, Reference ID : 402851946] |  | Junior Engineer | BILL/00702/2022-2023 | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2167 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for CHALOUNI T.G NEW LINE W/S Scheme, T/W No. IV, under METELLI CCC W/S Scheme, , [APPLICATION NO. 100000066826, Reference ID : 860257226] |  | Junior Engineer | BILL/00703/2022-2023 | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0
2168 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for CHALOUNI T.G RANA LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 4002964336, Reference ID : 402851948] |  | Junior Engineer | BILL/00704/2022-2023 | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2169 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for CHALOUNI T.G RANA LINE W/S Scheme, T/W No. IV, under METELLI CCC, [APPLICATION NO. 100000066825, Reference ID : 860257225] |  | Junior Engineer | BILL/00705/2022-2023 | BP/22-23/144 | 04/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.29 | 0 | 0
2170 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHILOUNI TG AREA PWSS, TW no III,IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000029/2023-2024 | 477/NMD | 26/04/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 22.76 | 22.74 | 100
2171 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri |  | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0
2172 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system along with ancillary works for Rejuvenation of Bhandani Piped water supply scheme in connection with Jal Jeevan mission at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000009/2024-2025 | 422/JD | 12/06/2024 | 323 | SANJIT SAHA | 29.06 | 0 | 50
2173 | Jalpaiguri Division | Jalpaiguri Division | Providing FHTC Including Restoration of Existing FHTC in the Command Area of Bhandani PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000505/2024-2025 | 2398/JD | 19/12/2024 | 30 | SANJIT SAHA | 6.96 | 0 | 0
2174 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000099/2023-2024 | 1054/JD | 24/08/2023 | 0 | Resource Division | 1.25 | 0 | 0
2175 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
2176 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2177 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0
2178 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2179 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary Wall, Drain, Footpath including Balance Portion of Distribution Network and other Allied Works related to Pipe Line at Diana Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000362/2024-2025 | 2012/JD | 18/11/2024 | 30 | VISHAL ENTERPRISES | 9.7 | 0 | 0
2180 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Diana Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Banerhat under Jalpaiguri Division. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000477/2022-2023 | 750/JD | 24/03/2023 | 180 | VISHAL ENTERPRISES | 227.13 | 130.75 | 50
2181 | Jalpaiguri Division | Northern Mechanical Division | Continuation order for the work of supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No. WB71B-8742) (From 01.04.2025 to 30.04.2025) | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000787/2024-2025 | 108-HQ/JD | 28/03/2025 | 31 | RAKESH SARKAR | 0.15 | 0.15 | 0
2182 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000006/2023-2024 | 150/JD | 28/04/2023 | 0 | Resource Division | 15.68 | 0 | 0
2183 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000119/2023-2024 | 1830/JD | 15/12/2023 | 0 | Resource Division | 5.95 | 0 | 0
2184 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for DIANA TEA GAEDEN, T/W I, under BANARHAT CCC [APPLICATION NO. 4003193588 ; Reference ID : 403045950] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/00995/2023-2024 | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2185 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for DIANA TEA GAEDEN, T/W I, under BANARHAT CCC [APPLICATION NO. 100000083813 ; Reference ID : 860275313] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/00996/2023-2024 | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.15 | 0 | 0
2186 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for DIANA TEA GAEDEN, T/W II, under BANARHAT CCC [APPLICATION NO. 4003193593 ; Reference ID : 403045952] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01007/2023-2024 | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2187 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for DIANA TEA GAEDEN, T/W II, under BANARHAT CCC [APPLICATION NO. 100000083815 ; Reference ID : 860275315] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01008/2023-2024 | BP/23-24/99 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.32 | 0 | 0
2188 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2189 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DIANA TG(D) PWSS, TW NO- I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000886/2022-2023 | 369/NMD | 29/03/2023 | 30 | THE BANERJEE CONCERN | 24.35 | 0 | 0
2190 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
2191 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0
2192 | Northern Mechanical | Northern Mechanical Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0
2193 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2194 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Lakhipara Tea Garden PWSS i.e. TW, Pump House, Water distribution Network, OHR , Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000492/2022-2023 | 824/JD | 30/03/2023 | 1007 | S.S. CONSTRUCTION | 297.96 | 225.12 | 60
2195 | Jalpaiguri Division | Northern Mechanical Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1991), (From 01.04.2025 to 30.04.2025) | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000789/2024-2025 | 110-HQ/JD | 28/03/2025 | 31 | AJIJUL HAQUE | 0.15 | 0 | 0
2196 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000025/2023-2024 | 169/JD | 28/04/2023 | 0 | Resource Division | 12.25 | 0 | 0
2197 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000120/2023-2024 | 1834/JD | 15/12/2023 | 0 | Resource Division | 7.44 | 0 | 0
2198 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for LAKSHMIPARA T.G., T/W No. I, under BAHARHAT CCC [APPLICATION NO. 4003254880 ; Reference ID : 403095717] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01723/2023-2024 | BP/23-24/246 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2199 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for LAKSHMIPARA T.G., T/W No. I, under BAHARHAT CCC [APPLICATION NO. 100000091681 ; Reference ID : 860283231] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01724/2023-2024 | BP/23-24/247 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.26 | 0 | 0
2200 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for LAKSHMIPARA T.G., T/W No. II, under BAHARHAT CCC [APPLICATION NO. 4003254888 ; Reference ID : 403095711] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01725/2023-2024 | BP/23-24/248 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2201 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for LAKSHMIPARA T.G., T/W No. II, under BAHARHAT CCC [APPLICATION NO. 100000091682 ; Reference ID : 860283232] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01726/2023-2024 | BP/23-24/249 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.71 | 0 | 0
2202 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2203 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
2204 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0
2205 | Northern Mechanical | Northern Mechanical Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0
2206 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Kholachand Fapri PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. under Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000064/2023-2024 | 266/JD | 10/05/2023 | 180 | M/S SARKAR ENTERPRISE | 262.01 | 0 | 35
2207 | Jalpaiguri Division | Jalpaiguri Division | Sub-Soil Investigation of proposed 200 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Kholachand Fapri Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000800/2024-2025 | 87-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
2208 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000005/2024-2025 | 53/JD | 09/04/2024 | 0 | Resource Division | 13.2 | 0 | 0
2209 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000186/2023-2024 | 2049/JD | 09/01/2024 | 0 | Resource Division | 7.47 | 0 | 0
2210 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-II, Powe House CCC APPLICATION NO. 4003352425 Reference ID : 403172863 | Assistant Engineer,HQ | Junior Engineer | BILL/00435/2024-2025 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.71 | 0 | 0
2211 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for KHOLA CHAND FAPRI, TW NO-I, POWER HOUSE CCC APPLICATION NO. 4003352414 Consumer ID : 403172861 | Assistant Engineer,HQ | Junior Engineer | BILL/00524/2024-2025 | BP/24-25/123 | 16/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.99 | 0 | 0
2212 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHOLACHAND FAPRI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000311/2023-2024 | 1276/NMD | 02/08/2023 | 608 | P.K.ENGINEERING | 22.11 | 8.22 | 50
2213 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
2214 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation Of Palashbari Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000082/2023-2024 | 435/JD. | 08/06/2023 | 798 | LOKNATH CONSTRUCTION | 77.09 | 21.8 | 41
2215 | Jalpaiguri Division | Jalpaiguri Division | Consturction of 3rd Tube Well site Boundary wall, Drain, Pathway at Palashbari PWSS i.c.w. Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000535/2024-2025 | 126/JD | 16/01/2025 | 30 | LOKNATH CONSTRUCTION | 11.68 | 0 | 0
2216 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall Surface, Drain, Pathway with related ancillary work at Head Works site of Palashbari Tea Garden Area PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000783/2021-2022 | 839/JD | 31/03/2022 | 30 | DULAL CHOUDHURY | 28.53 | 13.25 | 1
2217 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for REJU PALASHBARI, T/W No. III, under BANARHAT CCC [APPLICATION NO. 400333017 , Reference ID : 403157467] | Assistant Engineer,HQ | Junior Engineer | BILL/02000/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0
2218 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2219 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PALASBARI TEA GARDEN AREA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000667/2023-2024 | 1482/NMD | 17/08/2023 | 30 | SUDIP DUTTA | 10.76 | 0 | 0
2220 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
2221 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Different Stationary Items for Office Use under Jalpaiguri RWS Sub Division. PHE Dte. |  | Junior Engineer 2 | BILL/00927/2024-2025 | BP-2024-25-515 | 14/11/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.23 | 0 | 0
2222 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of one No. tube well (250mm x 200mm) by Reverse Rotary Method of Drilling and Construction of Pump House (5.40m x 3.60m) and Iron Elimination Plant for direct boosting arrangement for Augmentation of Porapara Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000069/2024-2025 | 988/JD | 14/08/2024 | 120 | SADHAN KARMAKAR | 38.03 | 0 | 0
2223 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Porapara PWSS I.e. TW, Pump Houses, Boundary wall IEP, Rising main etc. at Block - Jalpaiguri Sadar under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000075/2023-2024 | 1003/JD | 17/05/2023 | 45 | B.M CONSTRUCTION | 51.2 | 51.2 | 100
2224 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supplying and Installation of Display Boards at different piped water supply schemes in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000100/2025-2026 | 479/RWS | 29/05/2025 | 30 | JAYDEB SAHA | 7.95 | 0 | 100
2225 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Emergency extension and reparing of pipe line to facilite FHTC at different location Pora Para Water Supply Scheme under Jalpaiguri Division, PHE Dte. Under JJM. |  | Junior Engineer 2 | ORD/000448/2023-2024 | 1282/RWS | 28/11/2023 | 20 | B.M CONSTRUCTION | 6.16 | 6.12 | 100
2226 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Sadar block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer 2 | ORD/000457/2023-2024 | 1290/RWS | 29/11/2023 | 30 | B.M CONSTRUCTION | 3.89 | 3.89 | 100
2227 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000077/2024-2025 | 2208/JD | 01/12/2024 | 0 | Resource Division | 24.23 | 0 | 0
2228 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer 2 | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2229 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PORAPARA PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer 2 | ORD/000236/2023-2024 | 1251/NMD | 31/07/2023 | 30 | TAPAN BISWAS | 10.86 | 10.83 | 100
2230 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PORAPARA PWSS, TW no V in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer 2 | ORD/000327/2023-2024 | 1298/NMD | 03/08/2023 | 30 | M/S ANJALI ENTERPRISE | 12.62 | 12.62 | 100
2231 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Khasjangal-I PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Mal under Jalpaiguri Division. |  | Junior Engineer | ORD/000257/2023-2024 | 942/JD | 08/08/2023 | 721 | A. K. INDUSTRIES | 133.2 | 0 | 30
2232 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000066/2023-2024 | 1082/JD | 24/08/2023 | 0 | Resource Division | 8.97 | 0 | 0
2233 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000156/2023-2024 | 2024/JD | 09/01/2024 | 0 | Resource Division | 2.81 | 0 | 0
2234 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
2235 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHAS JANGAL PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000659/2023-2024 | 1473/NMD | 17/08/2023 | 684 | NIRMAN | 25.2 | 0 | 50
2236 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at P.H No.-I under KHAS JANGAL PWSS of JJM in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001062/2024-2025 | 112/HQ/NMD | 17/01/2025 | 7 | SARKAR ELECTRIC | 0.16 | 0 | 0
2237 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Augmentation of Angrabhasa PWSS i.e. TW, Pump Houses, Boundary Walls. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000362/2023-2024 | 1436/JD | 05/10/2023 | 60 | M/S ROY & SARKAR CONSTRUCTION | 27.72 | 11.42 | 35
2238 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Nagrakata block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. |  | Junior Engineer | ORD/000453/2023-2024 | 1287/RWS | 28/11/2023 | 30 | B.M CONSTRUCTION | 3.11 | 3.11 | 100
2239 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000091/2023-2024 | 1071/JD | 24/08/2023 | 0 | Resource Division | 41.27 | 0 | 0
2240 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New service connection charge for (reju) Angrabhasa PWSS tw-IV Application No-4003418417 Reference Id-403225912 |  | Junior Engineer | BILL/00366/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9 | 0 | 0
2241 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2242 | Jalpaiguri Division |  | Construction of different components of Ellenburry Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000270/2023-2024 | 939/JD | 08/08/2023 | 966 | NARENDRA KUMAR | 175.96 | 44.96 | 55
2243 | Jalpaiguri Division |  | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 3rd tube well site of Ellenbari Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  |  | ORD/000442/2024-2025 | 2318/JD | 11/12/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 0
2244 | Jalpaiguri Division |  | Balance laying Distribution Network and Providing Functional House Hold Tap Connection including TW, Pump House, Boundary Wall of Ellenbari Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000478/2025-2026 | 2511/JD | 10/12/2025 | 60 | NARENDRA KUMAR | 40.39 | 0 | 0
2245 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 2020/JD | 09/01/2024 | 0 | Resource Division | 4.28 | 0 | 0
2246 | Northern Mechanical |  | Infrastructure development cost for new service connection at ELLENBARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109308 Reference ID : 860301268 |  |  | BILL/00413/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.19 | 0 | 0
2247 | Northern Mechanical |  | New Service Connection Charge for ELLENBARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424570 Reference ID : 403230051 |  |  | BILL/00414/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2248 | Northern Mechanical |  | Infrastructure development cost for new service connection at ELLENBARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 100000109307 Reference ID : 860301267 |  |  | BILL/00415/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.76 | 0 | 0
2249 | Northern Mechanical |  | New Service Connection Charge for ELLENBARI TG, TW NO-I, OODLABARI CCC APPLICATION NO. 4003424572 Reference ID : 403230052 |  |  | BILL/00416/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2250 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
2251 | Northern Mechanical |  | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  |  | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
2252 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ELLENBURY TEA GARDEN PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000420/2023-2024 | 1334/NMD | 08/08/2023 | 30 | SUBODH KUMAR BANIK | 21.95 | 0 | 0
2253 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Patharjhora Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000067/2023-2024 | 346/JD. | 23/05/2023 | 180 | SRINIWAS AGARWAL | 208.93 | 99.4 | 62
2254 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2255 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of one no. Tube Well by Modified DTH - ODEX big dia tube well 200x150 mm dia for Pathorjhora piped water supply scheme i.c.w. Jal jeevan Mission at Mal Block under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000300/2023-2024 | 1357/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.54 | 15.48 | 100
2256 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 (Two) Nos Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Patharjohra Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000826/2023-2024 | 2750/JD | 14/03/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.26 | 33.38 | 100
2257 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Drilling of 200mm Big Dia Tube Well by Modified DTH-ODEX method at 2nd tube well site of Pathorjhora Tea Garden Piped Water Supply Scheme of Mal Block in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000976/2023-2024 | 588/A/AE/JSSD/CAMP | 18/03/2024 | 2 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 4.36 | 4.36 | 100
2258 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000203/2023-2024 | 2062/JD | 10/01/2024 | 0 | Resource Division | 6.09 | 0 | 0
2259 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PATHORJHORA TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003482918 Reference ID : 403269952 |  | Junior Engineer | BILL/01417/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2260 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at PATHORJHORA TG, TW NO-III,, OODLABARI CCC APPLICATION NO. 100000117770 Reference ID : 860312410 |  | Junior Engineer | BILL/01419/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.61 | 0 | 0
2261 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PATHORJHORA, T/W- I, under ODLABARI CCC, [APPLICATION NO. 4003343265, Reference ID : 403165544] |  | Junior Engineer | BILL/02160/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2262 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PATHORJHORA, T/W- I, under ODLABARI CCC, [APPLICATION NO. 100000100929, Reference ID : 860293129] |  | Junior Engineer | BILL/02161/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.03 | 0 | 0
2263 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PATHORJHORA, T/W-II, under ODLABARI CCC, [APPLICATION NO. 4003344810, Reference ID : 403166839] |  | Junior Engineer | BILL/02162/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2264 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PATHORJHORA, T/W-II, under ODLABARI CCC, [APPLICATION NO. 100000101095, Reference ID : 860293135] |  | Junior Engineer | BILL/02163/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.24 | 0 | 0
2265 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
2266 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHARJHORA TG PWSS at TW No. III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000400/2024-2025 | 1841/NMD | 05/11/2024 | 30 | CHOWDHURY AND BASU ENTERPRISE | 14.14 | 11 | 70
2267 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHARJOHRA TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000857/2023-2024 | 1812/NMD | 31/10/2023 | 30 | CHOWDHURY AND BASU ENTERPRISE | 29.21 | 22.37 | 60
2268 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Additional Works in connection with Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATHARJOHRA TEA GARDEN PWSS, ,TW no I,II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/001368/2024-2025 | 817/HQ/NMD | 25/03/2025 | 7 | CHOWDHURY AND BASU ENTERPRISE | 0.54 | 0 | 0
2269 | Jalpaiguri Division | Northern Mechanical Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
2270 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2271 | Jalpaiguri Division | Northern Mechanical Division | Sinking of 1 (One) No Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling at Meanglass Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000106/2024-2025 | 1416/JD | 20/09/2024 | 20 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 20.88 | 0 | 0
2272 | Jalpaiguri Division | Northern Mechanical Division | Sinking of Modified Big Dia Tube Well 250 X 200 mm dia using MS Slotted Strainer at required depth by Reverse Rotary method of drilling for one no. tube well at Meenglass Tea Garden Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000468/2023-2024 | 1761/JD | 08/12/2023 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.46 | 19.19 | 100
2273 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000202/2023-2024 | 2072/JD | 10/01/2024 | 0 | Resource Division | 6.75 | 0 | 0
2274 | Northern Mechanical | Northern Mechanical Division | Infrastructure development cost for new service connection at MENGLASS TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109304 Reference ID : 860301264 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00411/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.47 | 0 | 0
2275 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for MENGLASS TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424052 Reference ID : 403230050 | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00412/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2276 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for MENGLASS TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266406, Reference ID : 403105525] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/01279/2023-2024 | 23-24/158&166 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2277 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for MENGLASS TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093891, Reference ID : 860285651] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/01280/2023-2024 | 23-24/158&166 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.72 | 0 | 0
2278 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
2279 | Northern Mechanical | Northern Mechanical Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
2280 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) BATABARI TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105525 Reference ID : 860297575 |  | Junior Engineer | BILL/00247/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.24 | 0 | 0
2281 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) BATABARI TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.100000105522 Reference ID : 860297572 |  | Junior Engineer | BILL/00248/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.99 | 0 | 0
2282 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge fo(REJU) BATABARI TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.4003386376 Reference ID : 403200294 |  | Junior Engineer | BILL/00390/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2283 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge fo(REJU) BATABARI TG PWSS TW NO-III, METELI CCC " APPLICATION NO.4003385771 Reference ID : 403199268 |  | Junior Engineer | BILL/00391/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2284 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
2285 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2286 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Sisubari Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000145/2023-2024 | 710/JD | 13/07/2023 | 180 | PRADIP SAHA | 148.34 | 71.73 | 48
2287 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000162/2023-2024 | 2015/JD | 09/01/2024 | 0 | Resource Division | 4.08 | 0 | 0
2288 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for SISOBARI TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003266403, Reference ID : 403105522] |  | Junior Engineer | BILL/01265/2023-2024 | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2289 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for SISOBARI TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093882, Reference ID : 860285542] |  | Junior Engineer | BILL/01266/2023-2024 | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.31 | 0 | 0
2290 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for SISOBARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266400, Reference ID : 403105526] |  | Junior Engineer | BILL/01267/2023-2024 | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2291 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for SISOBARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093881, Reference ID : 860285541] |  | Junior Engineer | BILL/01268/2023-2024 | 23-24/159&167 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0
2292 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
2293 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
2294 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0
2295 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001005/2024-2025 | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0
2296 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of June 2024 |  |  | BILL/00397/2024-2025 | BP-2024-25-232 | 18/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2297 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of April 2024 |  |  | BILL/00398/2024-2025 | BP-2024-25-233 | 18/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2298 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00399/2024-2025 | BP-2024-25-270 | 30/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
2299 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of August 2024 |  |  | BILL/00650/2024-2025 | BP-2024-25-363 | 13/09/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
2300 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00651/2024-2025 | BP-2024-25-362 | 13/09/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
2301 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of September 2024 |  |  | BILL/00868/2024-2025 | BP-2024-25-494 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2302 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00869/2024-2025 | BP-2024-25-495 | 07/10/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
2303 | Jalpaiguri Division |  | Supply mobil to vehicle no WB 71 A 5774 |  |  | BILL/00934/2024-2025 | BP-2024-25-519 | 25/11/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
2304 | Jalpaiguri Division |  | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of October 2024 |  |  | BILL/00935/2024-2025 | BP-2024-25-520 | 25/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2305 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  |  | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
2306 | Jalpaiguri Division |  | Continuation Work order for Supply of 1 (One) Maxi cub with Engine capacity Less than or equal to 2000 CC. on hire basis including driver for Assistant Engineer Jalpaiguri R. W.S Sub-Division P.HE. Dte. for 6 month (Period from 01/08/2024 to 31/01/2025) |  |  | ORD/000054/2024-2025 | 709/RWS | 31/07/2024 | 184 | ASHIM SARKAR | 0.88 | 0.88 | 0
2307 | Jalpaiguri Division |  | Construction of different components of Chapgar (Zone-I & II) PWSS i.e. TW, Pump Houses, Water distribution Network , OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block -Maynaguri under Jalpaiguri Division, P.H.E Dte. |  |  | ORD/000264/2023-2024 | 944/JD | 08/08/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 488 | 89.09 | 34
2308 | Jalpaiguri Division |  | Facelifting and Interior furishing works for Junior Engineer Room-1 and DPMU Room under Jalpaiguri Division, PHE Dte. |  |  | ORD/000555/2023-2024 | 501/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.65 | 8.58 | 100
2309 | Jalpaiguri Division |  | Facelifting and Interior furnishing works for Junior Engineer Room-2 and Estimating Section under Jal;paiguri Division,P.H.E.Dte. |  |  | ORD/000556/2023-2024 | 502/JSSD | 02/01/2024 | 45 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.66 | 9.5 | 100
2310 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 2061/JD | 10/01/2024 | 0 | Resource Division | 9.79 | 0 | 0
2311 | Northern Mechanical |  | New Service Connection Charge for CHAPGAR, ZONE-I,T/W-I under MAYNAGURI CCC APPLICATION NO. 4003376095 Reference ID : 403191643 |  |  | BILL/00151/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.54 | 0 | 0
2312 | Northern Mechanical |  | New Service Connection Charge for CHAPGAR, ZONE-I,T/W-II under MAYNAGURI CCC APPLICATION NO. 4003379456 Reference ID : 403196953 |  |  | BILL/00205/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0
2313 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for CHAPGAR PWSS, Zone-I,II at TW no I & II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000611/2023-2024 | 1343/NMD | 08/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 43.76 | 0 | 0
2314 | Jalpaiguri Division | Jalpaiguri Division | Shifting of pipeline in connection with PWD road widning work from Domohani PWSS at Moynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000027/2022-2023 | 975/JD | 20/04/2022 | 45 | PROVA CONSTRUCTION | 38.07 | 0 | 0
2315 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement at 3rd tube well site of Augmentation Domohoni W/S Scheme under Jalpaiguri Division , P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000048/2022-2023 | 1193/JD | 20/05/2022 | 45 | GANAPATI CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.65 | 4.65 | 100
2316 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Domohani piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000051/2021-2022 | 1066/JD | 02/07/2021 | 21 | PRADIP KR SEN | 4.82 | 4.57 | 0
2317 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) with retrofitting works in connection with Jaldhara / Jal Sapna under the command area of Domohani Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, P.H.E Dte. (Phase-IV) | Assistant Engineer,HQ | Junior Engineer | ORD/000055/2022-2023 | 939/JD | 18/04/2022 | 45 | PRADIP KR SEN | 4.85 | 4.85 | 1
2318 | Jalpaiguri Division | Jalpaiguri Division | ADDITIONAL RISING MAIN FOR AUGMENTATION OF DOMOHANI PIPED WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000199/2024-2025 | 1592/JD | 23/10/2024 | 20 | M/S PRAFULLA GHOSH | 10.26 | 0 | 0
2319 | Jalpaiguri Division | Jalpaiguri Division | Renovation of front side boundary wall and construction of shade over front door of the pump house and ancillary works of the 2nd tube well site of Domohani Water Supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000213/2022-2023 | 1803/JD | 14/09/2022 | 21 | M/S SURAJIT DEY AND CO. | 2.41 | 0 | 0
2320 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna/JJM with minor retrofitting works under Domohani Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. (Phase-V) | Assistant Engineer,HQ | Junior Engineer | ORD/000232/2022-2023 | 2008/JD | 01/11/2022 | 30 | ALOKE DEY | 40.21 | 33.14 | 1
2321 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary wall, Blower Room, IEP of 3rd Pump House & Providing FHTC of Domohani PWSS, in connection with Augmentation of Domohani PWSS under Jal Jeevan Mission at Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000390/2023-2024 | 1554/JD | 01/11/2023 | 60 | B.M CONSTRUCTION | 67.78 | 68.45 | 100
2322 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation of different components of Head Work Site of Domohani PWSS under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000537/2023-2024 | 1972/JD | 03/01/2024 | 45 | SUKES BASU MAJUMDAR | 39.34 | 40.38 | 100
2323 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Domohani Piped Water Supply Scheme at Moynaguri Block under Jalpaiguri Division, PHE Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000546/2021-2022 | 661/JD | 09/03/2022 | 90 | SUKES BASU MAJUMDAR | 335.53 | 345.54 | 1
2324 | Jalpaiguri Division | Jalpaiguri Division | Sinking of One No. tube Well (250mm x 200mm) by Reverse Rotary Method of Drilling and others components for boosting in Augmentation of Domohoni Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000802/2023-2024 | 2629/JD | 07/03/2024 | 542 | M/S PRAFULLA GHOSH | 52.42 | 10.12 | 50
2325 | Jalpaiguri Division | Jalpaiguri Division | Engagement of Block Level Staff (Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Maynaguri block in Connection with JJM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. (2nd Call) | Assistant Engineer,HQ | Junior Engineer | ORD/000804/2023-2024 | 256/RWS | 07/03/2024 | 30 | B.M CONSTRUCTION | 3.11 | 3.11 | 100
2326 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000004/2021-2022 | 54/JD | 05/01/2022 | 0 | Resource Division | 5.5 | 0 | 0
2327 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000031/2024-2025 | 2099/JD | 25/11/2024 | 0 | Resource Division | 80.22 | 0 | 0
2328 | Jalpaiguri Division | Jalpaiguri Division | fhtc domohani | Assistant Engineer,HQ | Junior Engineer | VCH/000024/2022-2023 | BP-2021-23-1 | 21/04/2022 | 0 | PRADIP KR SEN | 4.57 | 0 | 0
2329 | Jalpaiguri Division | Jalpaiguri Division | DPR PREPARATION | Assistant Engineer,HQ | Junior Engineer | VCH/001143/2021-2022 | BP-2021-22-262 | 16/02/2022 | 0 | SUBHANKAR GHOSH | 2.37 | 0 | 0
2330 | Jalpaiguri Division | Jalpaiguri Division | SINKING REJ CHOUHADDI | Assistant Engineer,HQ | Junior Engineer | VCH/001379/2021-2022 | BP-2021-22-545 | 31/03/2022 | 0 | J.M. CONSTRUCTION | 7 | 0 | 0
2331 | Jalpaiguri Division | Jalpaiguri Division | FHTC MOGOLKATA T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001383/2021-2022 | BP-2021-22-498 | 29/03/2022 | 0 | PROFULLA GHOSH | 30.06 | 0 | 0
2332 | Jalpaiguri Division | Jalpaiguri Division | LDS INDONG T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001412/2021-2022 | BP-2021-22-546 | 31/03/2022 | 0 | KANAI LAL SEN | 16.3 | 0 | 0
2333 | Central Drilling | Jalpaiguri Division | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Mech./Elect. Planning Wing, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000031/2025-2026 | 133/S&WSD | 01/07/2025 | 182 | NEMAI CHANDRA NAIYA | 0.86 | 0 | 0
2334 | Central Drilling | Jalpaiguri Division | Continuation for Hiring of Diesel Driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Mech./Elect. Planning Wing, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2024-2025 | 244/S&WSD | 30/12/2024 | 184 | NEMAI CHANDRA NAIYA | 0.87 | 1.98 | 0
2335 | Central Drilling | Jalpaiguri Division | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 123 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR DOMOHANI PWSS, JALPAIGURI DISTRICT, CDD, PHE DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000339/2022-2023 | 1775/CDD | 02/01/2023 | 30 | PADMA ENGINEERING & CO. | 11.99 | 10.56 | 0
2336 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DOMOHANI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003107329, Reference ID : 402974759] | Assistant Engineer,HQ | Junior Engineer | BILL/00570/2023-2024 | BP/23-24/68 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2337 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for DOMOHANI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084156, Reference ID : 860276006] | Assistant Engineer,HQ | Junior Engineer | BILL/00571/2023-2024 | BP/23-24/68 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.96 | 0 | 0
2338 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of DOMOHANI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000851/2022-2023 | 266/NMD | 21/03/2023 | 30 | HARAGOURI ENTERPRISE | 10.12 | 10.12 | 50
2339 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel (diesel) of vehicle no-WB 71 A 5774 for the month of May 2024 | Assistant Engineer | Junior Engineer | BILL/00365/2024-2025 | BP-2024-25-191 | 08/07/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2340 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply mobil to vehicle no WB 71 A 5774 | Assistant Engineer | Junior Engineer | BILL/00366/2024-2025 | BP-2024-25-271 | 30/07/2024 | 0 | FILL & SMILE | 0.02 | 0 | 0
2341 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. | Assistant Engineer | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
2342 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Saptibari Zone- II Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2024-2025 | 987/JD | 14/08/2024 | 360 | MONOJ GHOSH | 59.77 | 0 | 85
2343 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Saptibari Zone- III Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000188/2024-2025 | 1534/JD | 01/10/2024 | 243 | KAMALESH SEN | 52.66 | 0 | 90
2344 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Saptibari (Zone-I) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2023-2024 | 1350/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 571.97 | 214.5 | 90
2345 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Saptibari (Zone-II) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000326/2023-2024 | 1351/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 445.3 | 317.61 | 90
2346 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Saptibari (Zone-III) PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. In connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000327/2023-2024 | 1352/JD | 26/09/2023 | 918 | SCEC BOENTER KDAS JOINT VENTURE | 432.29 | 224.47 | 79
2347 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Saptibari Zone-I Piped Water Supply Scheme within Maynaguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000674/2024-2025 | 486/JD | 11/03/2025 | 120 | DIPAK KUMAR CHAKRABORTY | 71.83 | 0 | 0
2348 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000687/2023-2024 | 151/RWS | 15/02/2024 | 30 | DEBABRATA SARKAR | 6.97 | 5.62 | 100
2349 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd Tubewell site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000688/2023-2024 | 150/RWS | 15/02/2024 | 30 | SOUVIK SAHA | 7.24 | 7.23 | 100
2350 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000777/2023-2024 | 2498/JD | 28/02/2024 | 45 | M/S BOSE ENTERPRISE | 22.62 | 0 | 0
2351 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-I PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2023-2024 | 2497/JD | 28/02/2024 | 45 | KAMAL DAS | 23.41 | 0 | 100
2352 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, Pipeline for Washout at HW Site Saptibari Zone-III PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2023-2024 | 2627/JD | 07/03/2024 | 45 | SWAPAN SAHA | 23.15 | 0 | 0
2353 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain, pipeline for washout at 2nd Tubewell site Saptibari Zone-II PWSS in connection with Jal Jeevan Mission at Block - Maynaguri Block under Jalpaiguri Division, P.H.E.Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000805/2023-2024 | 257/RWS | 07/03/2024 | 30 | UCO LABOUR CO-OPERATIVE SOCIETY LTD. | 7.24 | 7 | 100
2354 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2024-2025 | 51/JD | 09/04/2024 | 0 | Resource Division | 64.27 | 0 | 0
2355 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000168/2023-2024 | 2036/JD | 09/01/2024 | 0 | Resource Division | 37.59 | 0 | 0
2356 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAPTIBARI ZONE-I, T/W-I under MAYNAGURI CCC APPLICATION NO. 4003356521 Reference ID : 403175893 | Assistant Engineer | Junior Engineer | BILL/00184/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.98 | 0 | 0
2357 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAPTIBARI ZONE-I, T/W-II under MAYNAGURI CCC APPLICATION NO. 4003356527 Reference ID : 403175900 | Assistant Engineer | Junior Engineer | BILL/00185/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.3 | 0 | 0
2358 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAPTIBARI, T/W No. I, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305806 ; Reference ID : 403134432] | Assistant Engineer | Junior Engineer | BILL/01862/2023-2024 | BP/23-24/291 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.26 | 0 | 0
2359 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAPTIBARI, T/W No. II, ZONE-II under BHOTPATTY CCC [APPLICATION NO. 4003305811 ; Reference ID : 403134435] | Assistant Engineer | Junior Engineer | BILL/01863/2023-2024 | BP/23-24/292 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0
2360 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAPTIBARI, T/W No. I, ZONE-III under BHOTPATTY CCC [APPLICATION NO. 4003305819 ; Reference ID : 403134444] | Assistant Engineer | Junior Engineer | BILL/01864/2023-2024 | BP/23-24/293 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0
2361 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for SAPTIBARI, T/W No. II, ZONE-III under BHOTPATTY CCC [APPLICATION NO. 4003305829 ; Reference ID : 403134442] | Assistant Engineer | Junior Engineer | BILL/01865/2023-2024 | BP/23-24/295 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.59 | 0 | 0
2362 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) | Assistant Engineer,HQ | Junior Engineer | ORD/000024/2021-2022 | 744/JD | 13/05/2021 | 30 | KAMALESH SEN | 23.73 | 0 | 1
2363 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000026/2021-2022 | 746/JD | 13/05/2021 | 20 | RABINDRANATH DUTTA | 13.97 | 6.15 | 1
2364 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2021-2022 | 1065/JD | 02/07/2021 | 21 | GANAPATI CO-OP LABOUR CONT. & CONST. SOCIETY LTD. | 4.83 | 0 | 1
2365 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-III) | Assistant Engineer,HQ | Junior Engineer | ORD/000098/2021-2022 | 1337/JD | 23/08/2021 | 30 | DULAL CHOUDHURY | 30.23 | 0 | 0
2366 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Madhya Khuttimari piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-IV. | Assistant Engineer,HQ | Junior Engineer | ORD/000106/2021-2022 | 1257/JD | 10/08/2021 | 15 | ALICK DUTTA | 4.81 | 0 | 1
2367 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Madhya Khuttimari Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- V) | Assistant Engineer,HQ | Junior Engineer | ORD/000135/2021-2022 | 1444/JD | 09/09/2021 | 30 | ALOKE DEY | 30.23 | 0 | 1
2368 | Jalpaiguri Division | Jalpaiguri Division | FHTC MADHYAKHUTTIMARI PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/000475/2021-2022 |  | 29/10/2021 | 0 | RABINDRANATH DUTTA | 5.9 | 0 | 0
2369 | Jalpaiguri Division | Jalpaiguri Division | fhtc madhyakhuttimari | Assistant Engineer,HQ | Junior Engineer | VCH/000803/2021-2022 | BP-2021-22-107 | 16/11/2021 | 0 | KAMALESH SEN | 11.92 | 0 | 0
2370 | Jalpaiguri Division | Jalpaiguri Division | fhtc madhya khuttimari pwss | Assistant Engineer,HQ | Junior Engineer | VCH/000804/2021-2022 | BP-2021-22-106 | 16/11/2021 | 0 | RABINDRANATH DUTTA | 5.9 | 0 | 0
2371 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-C) |  | Junior Engineer | ORD/000091/2020-2021 | 1278/JD | 18/11/2020 | 60 | SANDIP BANIK | 28.51 | 0 | 1
2372 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of AMBARI T. G. piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000092/2020-2021 | 1279/JD | 18/11/2020 | 30 | NEW KUNDU ENTERPRISE | 14.38 | 0 | 1
2373 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS FOR PURBA DURAMARI PWSS |  | Junior Engineer | VCH/000045/2021-2022 | 08 | 07/05/2021 | 0 | SANJIT SAHA | 8.91 | 0 | 0
2374 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC FOR AMBARI T.G PWSS |  | Junior Engineer | VCH/001128/2020-2021 | 1077 | 14/01/2021 | 0 | SAHA CONSTRUCTION | 4.03 | 0 | 0
2375 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PRIVIDING FHTC AT AMBARI T.G PWWSS |  | Junior Engineer | VCH/001194/2020-2021 | 919 | 04/01/2021 | 0 | SANDIP BANIK | 4.21 | 0 | 0
2376 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PROVIDING FHTC AT AMBARI T.G PWSS |  | Junior Engineer | VCH/001213/2020-2021 | 1123 | 22/01/2021 | 0 | SANDIP BANIK | 28.5 | 0 | 0
2377 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC Ambari TG Part D |  | Junior Engineer | VCH/001214/2020-2021 | 1124 | 22/01/2021 | 0 | NEW KUNDU ENTERPRISE | 11.95 | 0 | 0
2378 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SADAR BLOCK ZONE II |  | Junior Engineer | VCH/001345/2021-2022 | BP-2021-22- 412 | 23/03/2022 | 0 | BISWAJIT BHADURI | 4.92 | 0 | 0
2379 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works & other ancillary works related to FHTC at different places of Ambari TG PWSS.under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | VCH/001485/2020-2021 | 1589 | 23/04/2021 | 0 | SANDIP BANIK | 1.82 | 0 | 0
2380 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETROFITTING WORK & OTHER ANCILLARY WORK RELATED FHTC FOR AMBARI T.G PWSS |  | Junior Engineer | VCH/001795/2020-2021 | 1589 | 21/03/2021 | 0 | SANDIP BANIK | 1.82 | 0 | 0
2381 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara / Jal Sapna under the command area of Boalmari Piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division P.H.E. Dte.( Part-B). |  | Junior Engineer | ORD/000151/2020-2021 | 475/RWS | 15/10/2020 | 30 | KABYA ENTERPRISE | 4.7 | 4.23 | 1
2382 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of BOALMARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  | Junior Engineer | ORD/000173/2020-2021 | 1105/JD | 20/10/2020 | 90 | UMWEL ENGINEER PRIVATE LIMITED | 39.23 | 45.87 | 1
2383 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising Main Connections(at 3rd & 4th TW site) including other necessary arrangement for Rejuvenation of Boalmari Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte Jalpaiguri.(3rd Call) |  | Junior Engineer | ORD/000294/2023-2024 | 971/RWS | 18/08/2023 | 200 | KANAI LAL SEN | 3.13 | 0 | 100
2384 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing house connection under Boalmari Water Supply Scheme at Sadar Block under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000486/2021-2022 | 296/RWS | 20/04/2021 | 15 | DEBABRATA GHOSH | 4.44 | 0 | 0
2385 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing functional household tap connection (FHTC) with Jalsapna including Retrofitting works under the command area of Boalmari W/S/S under Jalpaiguri Division P.H.E. Dte.(Part ¿ F) |  | Junior Engineer | ORD/000571/2021-2022 | 182/RWS | 04/03/2022 | 15 | KANAI LAL SEN | 4.51 | 0 | 0
2386 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BOALMARI |  | Junior Engineer | VCH/000327/2021-2022 |  | 01/10/2021 | 0 | KANAI LAL SEN | 22.04 | 0 | 0
2387 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting Boalmari WSS |  | Junior Engineer | VCH/000465/2021-2022 |  | 26/10/2021 | 0 | KANAI LAL SEN | 4.78 | 0 | 0
2388 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of ARGIGORALBARI piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (Part-C) |  | Junior Engineer | ORD/000083/2020-2021 | 1268/JD | 18/11/2020 | 90 | NARAYAN CHAKRABORTY | 36.96 | 60.24 | 1
2389 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional House hold tap Connection(FHTC) In connection with Jaldhara/ Jalsapna at Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ G) |  | Junior Engineer | ORD/000178/2021-2022 | 683/RWS | 27/09/2021 | 15 | BISWAJIT BHADURI | 3.4 | 0 | 1
2390 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional House hold tap Connection (FHTC)in connection with Jaldhara/ Jalsapna a t Arji Goralbari piped W/S/S within Jalpaiguri Sadar Block under Jalpaiguri Division , P.H.E Dte. (part ¿ H) |  | Junior Engineer | ORD/000180/2021-2022 | 685/RWS | 27/09/2021 | 15 | NARAYAN CHAKRABORTY | 4.25 | 3.47 | 1
2391 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  | Junior Engineer | ORD/000183/2020-2021 | 1498/JD | 22/12/2020 | 30 | BISWAJIT BHADURI | 17.51 | 13.16 | 1
2392 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing & renovation of Boundary wall, approach At H/W site for Goralbari Zone ¿ II W/S/S under Jalpaiguri Division , P.H.E Dte |  | Junior Engineer | ORD/000212/2021-2022 | 699/RWS | 27/09/2021 | 30 | ASIT PAUL | 4.84 | 0 | 1
2393 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works related to FHTC at Kamar para, Taltala line , Purba Madati para, Purba Kamar Para for Argi Garalbari . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000273/2021-2022 | 817/RWS | 30/11/2021 | 10 | BISWAJIT BHADURI | 4.85 | 0 | 1
2394 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement of Rejuvenation Garalbari . W/S/S ( zone - I ) 3rd T/W site under Jalpaiguri Division , P.H.E. Dte. |  | Junior Engineer | ORD/000318/2021-2022 | 869/RWS | 08/12/2021 | 30 | ABHIJIT SARKAR | 4.65 | 9.37 | 0
2395 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBAMAGURMARI PWSS |  | Junior Engineer | VCH/001312/2021-2022 | BP-2021-22-334 | 03/03/2022 | 0 | ARATI CONSTRUCTION | 7.42 | 0 | 0
2396 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PURBAMAGUR MARI PWSS |  | Junior Engineer | VCH/001313/2021-2022 | BP-2021-22-335 | 03/03/2022 | 0 | MONOJ GHOSH | 7.74 | 0 | 0
2397 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC NAYASAILYA T.G PWSS |  | Junior Engineer | VCH/001314/2021-2022 | BP-2021-22-336 | 03/03/2022 | 0 | GAP ENGINEERS ENTERPRISES | 12.52 | 0 | 0
2398 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC ENGO T.G PWSS |  | Junior Engineer | VCH/001327/2021-2022 | BP-2021-22-464 | 27/03/2022 | 0 | NABIN PRODHAN | 2.26 | 0 | 0
2399 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna including retroftting of existing LDS under the command area of Red Bank Tea Garden area piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- II) | Assistant Engineer,HQ | Junior Engineer | ORD/000176/2020-2021 | 1295/JD | 23/11/2020 | 90 | M/S R.N. TRADERS | 39.75 | 15.72 | 1
2400 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NGAISUREE T.G. Area piped Water Supply Scheme at Matiali Block under Jalpaiguri Division, PHE Dte.(Phase-II). |  | Junior Engineer | ORD/000085/2020-2021 | 1273/JD | 18/11/2020 | 1625 | SADHAN KARMAKAR | 43.64 | 0 | 100
2401 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of GORALBARI (Zone-I) piped Water Supply Scheme at Jalpaiguri Block under under Jalpaiguri Division, PHE Dte. (PART-A) |  | Junior Engineer | ORD/000223/2020-2021 | 94/JD | 14/01/2021 | 45 | SAPTASWA SARKAR | 28 | 24.49 | 0
2402 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | providing fhtc for maynatali pwss |  | Junior Engineer | VCH/000362/2021-2022 | 357/21-22 | 16/09/2021 | 0 | SANJIT SAHA | 19.92 | 0 | 0
2403 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | LDS FOR D-SHALBARI PWSS |  | Junior Engineer | VCH/000509/2021-2022 | 336/21-22 | 04/10/2021 | 0 | ROY & SARKAR CONSTRUCTION | 5.85 | 0 | 0
2404 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORK AT BOALMARI PWSS |  | Junior Engineer | VCH/001782/2020-2021 | 1564 | 19/03/2021 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 4.34 | 0 | 0
2405 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORK RELATED FHTC FOR BOALMARI PWSS |  | Junior Engineer | VCH/001786/2020-2021 | 1563 | 19/03/2021 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 4.21 | 0 | 0
2406 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | NH Road(4 Lane) crossing through underpass at Assam More .i.c.w. FHTC of Mohit Nagar W/S Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000281/2022-2023 | 646/RWS | 21/10/2022 | 30 | M/S DEY & ROY CHOUDHURY | 3.86 | 0 | 0
2407 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) at Sebagram In connection with Jaldhara/ Jal Sapna under the command area of Mohit Nagar W/S Scheme under Jalpaiguri Division PHE Dte. (PART-I) |  | Junior Engineer | ORD/000333/2023-2024 | 1081/RWS | 19/09/2023 | 30 | M/S DEY & ROY CHOUDHURY | 6.68 | 0 | 100
2408 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Thorough repairing and overhauling of the Iron Elimination Plant (double Unit) at Mohitnagar Water Supply Scheme (H/W Site), under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000335/2023-2024 | 1083/RWS | 19/09/2023 | 15 | M/S DEY & ROY CHOUDHURY | 5.41 | 0 | 100
2409 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MOHITNAGAR |  | Junior Engineer | VCH/000087/2022-2023 | BP-2022-2023-41 | 24/05/2022 | 0 | M/S DEY & ROY CHOUDHURY | 7.1 | 0 | 0
2410 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC SATHKAYA TG PWSS |  | Junior Engineer | VCH/000338/2021-2022 |  | 04/10/2021 | 0 | LOKNATH CONSTRUCTION | 22.44 | 0 | 0
2411 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MOHIT NAGAR |  | Junior Engineer | VCH/001147/2021-2022 | BP-2021-22-252 | 16/02/2022 | 0 | ANUP KUMAR KUNDU | 20.15 | 0 | 0
2412 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC CHALAUNI |  | Junior Engineer | VCH/001161/2021-2022 | BP-2021-22-240 | 22/02/2022 | 0 | BILTU DAS | 10.56 | 0 | 0
2413 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BATABARI T.G |  | Junior Engineer | VCH/001162/2021-2022 | BP-2021-22-264 | 22/02/2022 | 0 | PRIYABRATA KARMAKAR | 7.52 | 0 | 0
2414 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc matiali bazar |  | Junior Engineer | VCH/001173/2021-2022 | BP-2021-22-233 | 23/02/2022 | 0 | M/S DEY & ROY CHOUDHURY | 15.39 | 0 | 0
2415 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC JABRAMALI |  | Junior Engineer | VCH/001210/2021-2022 | BP-2021-22-332 | 28/02/2022 | 0 | SUKES BASU MAJUMDAR | 12.67 | 0 | 0
2416 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DABGRAM-II |  | Junior Engineer | VCH/001256/2021-2022 | BP-2021-22-410 | 23/03/2022 | 0 | SAHA CONSTRUCTION | 52.17 | 0 | 0
2417 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DAKSHIN SALBARI PWSS |  | Junior Engineer | VCH/001259/2021-2022 | BP-2021-22-402 | 23/03/2022 | 0 | NARAYAN SARKAR | 20.51 | 0 | 0
2418 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BHANGARHAT PWSS |  | Junior Engineer | VCH/001311/2021-2022 | BP-2021-22-341 | 03/03/2022 | 0 | BILTU DAS | 26.16 | 0 | 0
2419 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC DAKSHIN SALBARI PWSS |  | Junior Engineer | VCH/001342/2021-2022 | BP-2021-22402 | 23/03/2022 | 0 | NARAYAN SARKAR | 20.51 | 0 | 0
2420 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC MOHIT NAGAR PWSS |  | Junior Engineer | VCH/001392/2021-2022 | BP-2021-22-550 | 31/03/2022 | 0 | M/S DEY & ROY CHOUDHURY | 15.24 | 0 | 0
2421 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000214/2020-2021 | 1547/JD | 31/12/2020 | 75 | SCEC BOENTER KDAS JOINT VENTURE | 42.4 | 38.32 | 0
2422 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Lukshan T.G. area PWSS at Nagrakata Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000341/2020-2021 | 566/JSSD | 01/02/2021 | 15 | ALICK DUTTA | 4.61 | 0 | 0
2423 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORK FOR FHTC FOR JABRAMALI PWSS |  | Junior Engineer | VCH/000121/2021-2022 | 124/21-22 | 07/07/2021 | 0 | M/S RATAN KUMAR DAS GUPTA AND CO | 13.89 | 0 | 0
2424 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | ADD BILL |  | Junior Engineer | VCH/000769/2021-2022 | 536/21-22 | 17/11/2021 | 0 | GENESIS ADVERTISING PVT LTD | 2.89 | 0 | 0
2425 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection in connection with Jal Swapna under the command area of Sajnapara Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E. Dte. (Phase-II) | Assistant Engineer,HQ | Junior Engineer | ORD/000211/2022-2023 | 1801/JD | 14/09/2022 | 21 | RAGHU DAS | 4.37 | 4.36 | 1
2426 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sajnapara P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000502/2021-2022 | 97/JD | 10/01/2022 | 60 | DEEP CONSTRUCTION | 4.65 | 4.65 | 0
2427 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SAJNAPARA (REJU), T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003123372, Reference ID : 402997124] | Assistant Engineer,HQ | Junior Engineer | BILL/00029/2023-2024 |  | 04/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
2428 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SAJNAPARA (REJU), T/W III, under DHUPGURI CCC, [APPLICATION NO. 100000076670, Reference ID : 860268400] | Assistant Engineer,HQ | Junior Engineer | BILL/00030/2023-2024 |  | 04/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.41 | 0 | 0
2429 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SAJNAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 4003147721, Reference ID : 403014075] | Assistant Engineer,HQ | Junior Engineer | BILL/00061/2023-2024 | BP/23-24/15 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
2430 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SAJNAPARA, TW No. III, DHUPGURI CCC, [APPLICATION NO. 100000077914, Reference ID : 860269054] | Assistant Engineer,HQ | Junior Engineer | BILL/00062/2023-2024 | BP/23-24/15 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.52 | 0 | 0
2431 | Northern Mechanical | Jalpaiguri Division | Fuel ,Lubricant ,Gear Oil & steering oil charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 0063/2023-2024 , Dt. 31.10.2023 | Assistant Engineer,HQ | Junior Engineer | BILL/01018/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.24 | 0 | 0
2432 | Northern Mechanical | Jalpaiguri Division | fuel Charges for Government Inspection Vehicle under NMD PHE Dte. Invoice No- 0033/2023-24 ,Dt. 1.07.2023 | Assistant Engineer,HQ | Junior Engineer | BILL/01019/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.06 | 0 | 0
2433 | Northern Mechanical | Jalpaiguri Division | Fuel, Lubricant & coolant charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 00047/2023-2024 , Dt. 31.08.2023 | Assistant Engineer,HQ | Junior Engineer | BILL/01020/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.21 | 0 | 0
2434 | Northern Mechanical | Jalpaiguri Division | Fuel & Lubricant oil charges for Government Inspection vehicle under NMD PHE Dte. invoice No- 0069/2023-2024 , Dt. 30.11.2023 | Assistant Engineer,HQ | Junior Engineer | BILL/01021/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.32 | 0 | 0
2435 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2436 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF SAJNAPARA PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000888/2022-2023 | 371/NMD | 29/03/2023 | 30 | M/S MATRI CONSTRUCTION | 11.25 | 11.25 | 100
2437 | Jalpaiguri Division | Jalpaiguri Division | Supply of fuel against vehicle WB-71B-3112 under Assistant Engineer Jalpaiguri Sadar Sub-Division PHE Dte for the month April 2023 | Assistant Engineer,HQ | Junior Engineer | BILL/00208/2023-2024 | BP-2023-24-116 | 01/06/2023 | 0 | FILL & SMILE | 0.26 | 0 | 0
2438 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | Assistant Engineer,HQ | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0.36 | 0
2439 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) | Assistant Engineer,HQ | Junior Engineer | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0.34 | 1
2440 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000533/2021-2022 | 131/JD | 14/01/2022 | 60 | SUKUMAR KUNDU | 4.65 | 4.65 | 100
2441 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000558/2021-2022 | 452/JD | 18/02/2022 | 30 | MECHANO TRADING CO. | 7.79 | 7.36 | 1
2442 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 4th Tube well for Rejuvenation of Chakiavita PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000559/2021-2022 | 453/JD | 18/02/2022 | 30 | MECHANO TRADING CO. | 7.79 | 6.18 | 1
2443 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 4th Tube well site for Chakiavita P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000577/2021-2022 | 143/JD | 18/01/2022 | 60 | PRIYABRATA KARMAKAR | 4.65 | 4.65 | 0
2444 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 3rd tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000605/2023-2024 | 2306/JD | 07/02/2024 | 30 | SUKUMAR KUNDU | 8.82 | 6.77 | 100
2445 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for 4th tubewell at Chakiavita piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000606/2023-2024 | 2307/JD | 07/02/2024 | 30 | PRIYABRATA KARMAKAR | 9.03 | 8.72 | 100
2446 | Jalpaiguri Division | Jalpaiguri Division | RETROFITTING WORKS SAMSING T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001269/2021-2022 | BP-2021-22-518 | 30/03/2022 | 0 | SUJAN LAMA | 11.66 | 0 | 0
2447 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for CHAKIABHITA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 4003135861 ; Reference ID : 403001371] | Assistant Engineer,HQ | Junior Engineer | BILL/00010/2023-2024 | BP/23-24/06 | 03/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.73 | 0 | 0
2448 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for CHAKIABHITA, T/W IV, under FULBARIHAT CCC [APPLICATION NO. 100000076456 ; Reference ID : 860267596] | Assistant Engineer,HQ | Junior Engineer | BILL/00011/2023-2024 | BP/23-24/06 | 03/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.65 | 0 | 0
2449 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 30 KVA Servo Motor operated Copper wound line voltage corrector Chakiabhita W/S Scheme, TW No. I in the dist. of Jalpaiguri under NMD PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000392/2020-2021 | 1905/NMD | 07/01/2021 | 30 | MAA DURGA CONCERN | 3.03 | 3.03 | 0
2450 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for CHAKIABHITA (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000582/2022-2023 | 1121/NMD | 12/09/2022 | 30 | CHOWDHURY AND BASU ENTERPRISE | 7.95 | 7.93 | 100
2451 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF CHAKIABHITA PWSS, TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000752/2022-2023 | 52/NMD | 24/01/2023 | 30 | M/S B.ENTERPRISE | 11.67 | 9.75 | 100
2452 | Northern Mechanical | Jalpaiguri Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under CHAKIABHITA (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000778/2022-2023 | 99/NMD | 03/02/2023 | 21 | CHOWDHURY AND BASU ENTERPRISE | 2.52 | 2.52 | 100
2453 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for TW-III, of CHAKIAVITA W/S Scheme under BELAKOBA CCC,APPLICATION NO. 4002951612,Reference ID : 860244515 | Assistant Engineer,HQ | Junior Engineer | VCH/000315/2022-2023 | BP/2022-23/31 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2454 | Northern Mechanical | Jalpaiguri Division | Infrustructure cost for New Service Connection Charge for TW-III, of CHAKIAVITA W/S Scheme under BELAKOBA CCC,APPLICATION NO. 100000054735,Reference ID : 402843365 | Assistant Engineer,HQ | Junior Engineer | VCH/000316/2022-2023 | BP/2022-23/31 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.79 | 0 | 0
2455 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two No. 183 mm x 125mm dia 120 m Deep Tube well by ODEX-165 drilling Method, at Indong TG area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000074/2022-2023 | 1313/JD | 16/06/2022 | 30 | S. N. POLYMERS PVT. LTD. | 13.84 | 13.47 | 0
2456 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system (Phase - II) & Rising Main for Ingdong Tea Garden piped water supply scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000137/2023-2024 | 705/JD | 13/07/2023 | 21 | KANAI LAL SEN | 21.42 | 21.76 | 100
2457 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m X 3.60 m) size with Sanitary & Plumbing arrangement at Head Works Site for Indong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000356/2022-2023 | 856/JD | 01/04/2022 | 60 | SUJOY CHOWDHURY | 5.61 | 5.61 | 0
2458 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system including Providing Functional Household Tap Connection in connection with Jal Swapna for Indong Tea Garden Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000566/2021-2022 | 690/JD | 15/03/2022 | 1236 | KANAI LAL SEN | 112.93 | 79.86 | 90
2459 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) at Indong T.G. Area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000695/2021-2022 | 1068/JSSD | 25/01/2022 | 20 | MOYTEC | 2.02 | 2.02 | 0
2460 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 200 Cum OHR as per Departmental Design & Drawing for INDONG Tea Garden Area Piped Water Supply Scheme Block : Matiali District- Jalpaiguri. |  | Junior Engineer | ORD/000697/2021-2022 | 472/JD | 21/02/2022 | 180 | M/S SIBU DEY AND CO. | 54.95 | 49.29 | 100
2461 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size with Sanitary & Plumbing arrangement at 2nd Tube well site for Indong T.G. area of P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000709/2021-2022 | 1043/JSSD | 24/01/2022 | 45 | ABHISEK KUNDU | 4.63 | 4.63 | 0
2462 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 2nd tubewell site of Indong Tea Garden Area piped water supply scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001008/2021-2022 | 1039/JSSD | 21/01/2022 | 20 | BISWAJIT MANDAL | 3.76 | 0 | 0
2463 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000001/2022-2023 | 1064/JD | 28/04/2022 | 0 | Resource Division | 37.54 | 0 | 0
2464 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000031/2023-2024 | 175/JD | 28/04/2023 | 0 | Resource Division | 14.68 | 0 | 0
2465 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000206/2023-2024 | 2065/JD | 10/01/2024 | 0 | Resource Division | 7.61 | 0 | 0
2466 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil investigation work for 200 CUM Over head reservoir (OHR) at Indong TG |  | Junior Engineer | VCH/000365/2022-2023 |  | 27/09/2022 | 0 | MOYTEC | 1.01 | 0 | 0
2467 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for INDONG TG AREA PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000771/2022-2023 | 77/NMD | 27/01/2023 | 30 | B.B. CONCERNED | 10.86 | 10.86 | 100
2468 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for INDONG TG AREA PWSS, TW no II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000772/2022-2023 | 78/NMD | 27/01/2023 | 30 | ALPHA ENTERPRISE | 10.86 | 10.86 | 100
2469 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 4002964298, Reference ID :402851947] |  | Junior Engineer | VCH/000971/2022-2023 | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2470 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. I, under MATELLI CCC, [APPLICATION NO. 100000059409, Reference ID : 860248999] |  | Junior Engineer | VCH/000972/2022-2023 | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.22 | 0 | 0
2471 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 4002964293, Reference ID :402851944] |  | Junior Engineer | VCH/000973/2022-2023 | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2472 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of Infrastructure COST at INDONG TEA GARDEN NEAR TANKI LINE W/S SCHEME, T/W No. II, under MATELLI CCC, [APPLICATION NO. 100000059407, Reference ID : 860248997] |  | Junior Engineer | VCH/000974/2022-2023 | BP/22-23/89 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.55 | 0 | 0
2473 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA pipe water Supply schme at Matialy Block under Jalpaiguri Division, P.H.E Dte.(Phase-IX) |  | Junior Engineer | ORD/000088/2022-2023 | 76/JSSD | 22/07/2022 | 15 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.84 | 4.67 | 0
2474 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) inconnection with JJM/Jalswapna under command area of MATHACHULKA (GOBRABUSTY,UPORDHARA areas) pipe water supply scheme at Matiali Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000116/2022-2023 | 93/JSSD | 22/07/2022 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 3.61 | 3.32 | 0
2475 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of valve and valve Chamber at different location under command area of MATHACHULKA pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000119/2022-2023 | 96/JSSD | 22/07/2022 | 30 | DEEP CONSTRUCTION | 1.97 | 1.93 | 0
2476 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection(FHTC) in connection with Jaldhara/Jal Swapna under Command area of Mathachulka Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,PHE Dte(Phase-I) |  | Junior Engineer | ORD/000234/2021-2022 | 510/JSSD | 03/11/2021 | 15 | DEEP CONSTRUCTION | 4.65 | 0 | 0
2477 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of MATHACHULKA (Gobra Busty & Salbari Part) at Mathachulka pipe water supply scheme at Matialy Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000247/2022-2023 | 163/JSSD | 24/08/2022 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 4.78 | 4.28 | 0
2478 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000340/2020-2021 | 453JSSD | 30/12/2020 | 15 | DEEP CONSTRUCTION | 4.6 | 0 | 0
2479 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Mathachulka T.G. area PWSS at Matiali Block under Jalpaiguri Division, PHE Dte. (Phase-III) |  | Junior Engineer | ORD/000342/2020-2021 | 570/JSSD | 01/02/2021 | 15 | ARUP SARKAR | 4.39 | 0 | 0
2480 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of MATHACHULKA T.G Area piped Water Supply Scheme at Matially Block under Jalpaiguri Division, PHE Dte. (Phase-IV) |  | Junior Engineer | ORD/000426/2020-2021 | 654/JSSD | 25/02/2021 | 15 | DEEP CONSTRUCTION | 4.69 | 0 | 0
2481 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka ( Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase - VIII) |  | Junior Engineer | ORD/000890/2021-2022 | 1029/W/JSSD | 31/01/2022 | 15 | SUBIR GHOSH | 4.82 | 4.82 | 0
2482 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household tap connection of connection with Jalswapna JJM under command area of Mathachulka (Purba Deema Para ) PWSS at Matiali Block Under Jalpaiguri Division P.H.E Dte. (Phase-VIII) |  | Junior Engineer | ORD/001075/2021-2022 | .1029/W/JSSD | 31/01/2022 | 15 | SUBIR GHOSH | 4.82 | 0 | 0
2483 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-B) | Assistant Engineer,HQ | Junior Engineer | ORD/000002/2022-2023 | 882/JD | 05/04/2022 | 60 | M/S NANDY ENTERPRISE | 182.16 | 69.91 | 0
2484 | Jalpaiguri Division | Jalpaiguri Division | Shifting of pipeline by PWD road widening work from Thuta Pakri to Nirashi Via comperhat at Goralbari Zone- II piped Water Supply Scheme Jalpaiguri Sadar Block under Jalpaiguri | Assistant Engineer,HQ | Junior Engineer | ORD/000200/2019-2020 | 302/JD | 17/03/2020 | 120 | BILTU DAS | 47.59 | 15.74 | 0
2485 | Jalpaiguri Division | Jalpaiguri Division | Partial Retrofitting work for Riabari T.G.Area with repairing of rising main, including damaged/Chokage line repairing due to local developmnet works, direct Pumping arrangement from 2nd pump within the command area of Riabari T.G. P.W.S.S. under Jalsapna programme at Dhupguri Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000203/2022-2023 | 1742/JD | 08/09/2022 | 21 | SAPTASWA SARKAR | 15.65 | 15.81 | 1
2486 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) including retrofitting works in connection with Jal Sapna under the command area of Mallicksova Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000338/2021-2022 | 193/JD | 21/01/2022 | 60 | BOSE ENTERPRISE | 172.88 | 62.22 | 1
2487 | Jalpaiguri Division | Jalpaiguri Division | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000377/2021-2022 | 350/JD | 03/02/2022 | 120 | NARENDRA KUMAR | 57.75 | 8.61 | 100
2488 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000008/2021-2022 | 180/JD | 21/01/2022 | 0 | Resource Division | 2.99 | 0 | 0
2489 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000075/2024-2025 | 2206/JD | 01/12/2024 | 0 | Resource Division | 26.77 | 0 | 0
2490 | Jalpaiguri Division | Jalpaiguri Division | FHTC GRASSMORE T.G PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001330/2021-2022 | BP-2021-22-469 | 28/03/2022 | 0 | SWAPAN SAHA | 9.59 | 0 | 0
2491 | Jalpaiguri Division | Jalpaiguri Division | FHTC MALLICKSOVA PWSS | Assistant Engineer,HQ | Junior Engineer | VCH/001353/2021-2022 | BP-2021-22-466 | 27/03/2022 | 0 | BOSE ENTERPRISE | 65.35 | 0 | 0
2492 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 250mm x 150mm dia Two nos tube well by Reverse Rotary method of drilling for Augmentation at 3rd & 4th Tube well site of Kajaldighi PWSS within Maynaguri Block under PHE Dte. Jalpaiguri Division. |  | Junior Engineer | ORD/000004/2023-2024 | 850/JD | 06/04/2023 | 45 | M/S S. G. ENTERPRISE | 16.86 | 15.78 | 100
2493 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline at Kajaldighi Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000097/2025-2026 | 476/RWS | 29/05/2025 | 30 | M/S TRINATH CONSTRUCTION AND CO. | 4.03 | 0 | 0
2494 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of approach Road for 3rd & 4th site for Kajaldighi Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000098/2025-2026 | 477/RWS | 29/05/2025 | 30 | M/S S. G. ENTERPRISE | 0.5 | 0 | 0
2495 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000145/2022-2023 | 1562/JD | 08/08/2022 | 936 | DEBASISH DEY | 13.78 | 10.4 | 80
2496 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd tube well site of Rejuvenation of Kajaldighi water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000199/2022-2023 | 1740/JD | 08/09/2022 | 997 | SAHA CONSTRUCTION | 14.44 | 10.87 | 100
2497 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000481/2021-2022 | 2214/JD | 27/12/2021 | 60 | SUBIR GHOSH | 11.45 | 11.44 | 100
2498 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Kajaldighi Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000482/2021-2022 | 2215/JD | 27/12/2021 | 60 | M/S TRINATH CONSTRUCTION AND CO. | 11.44 | 11.43 | 100
2499 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for KAJALDHIGHI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003164171, Reference ID : 403024432] |  | Junior Engineer | BILL/00572/2023-2024 | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2500 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for KAJALDHIGHI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084435, Reference ID : 860276015] |  | Junior Engineer | BILL/00573/2023-2024 | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.17 | 0 | 0
2501 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for KAJALDHIGHI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 4003164175, Reference ID : 403024433] |  | Junior Engineer | BILL/00578/2023-2024 | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2502 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for KAJALDHIGHI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 100000084436, Reference ID : 860276016] |  | Junior Engineer | BILL/00579/2023-2024 | BP/23-24/69 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.27 | 0 | 0
2503 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply and Delivery of C.I special as when as required at T/W No-I of KAJALDIGI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. |  | Junior Engineer | ORD/000071/2024-2025 | 1060/HQ/NMD | 21/06/2024 | 7 | SARKAR ELECTRIC | 0.75 | 0.75 | 100
2504 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of KAJALDIGHI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000839/2022-2023 | 268/NMD | 21/03/2023 | 30 | INDTECH ASSOCIATES | 21.38 | 0 | 0
2505 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing With Functional Household Tap Connection (FHTC) in connection with Jalswapna/JJM for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000007/2022-2023 | 878/JD | 05/04/2022 | 1368 | M/S R.N. TRADERS | 282.14 | 193.85 | 1
2506 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying of dedicated pipeline along with commissioning of Augmentation of Angrabhasa Piped W/S Scheme in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000079/2025-2026 | 99/JSSD | 30/05/2025 | 30 | RAGHU DAS | 12.42 | 0 | 0
2507 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Angrabhasa Piped Water Supply Scheme Block- Dhupguri, District - Jalpaiguri. |  | Junior Engineer | ORD/000137/2022-2023 | 1554/JD | 05/08/2022 | 1336 | SWAPAN SAHA | 54.69 | 31.22 | 100
2508 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 3rd tubewell Site for Augmentation of Angrabhasa PWSS, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000192/2022-2023 | .99/JSSD | 22/07/2022 | 864 | CHANDAN GHOSH | 4.78 | 0 | 100
2509 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Augmenmtation of Angrabhasa piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000479/2022-2023 | 798/JD.. | 29/03/2023 | 14 | M/S ROY & SARKAR CONSTRUCTION | 6.39 | 2.72 | 70
2510 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 No. 250 mm x 200 mm x 147 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for the Augmentation of Angrabhasa piped water supply scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000785/2021-2022 | 840/JD | 31/03/2022 | 21 | MALAY BHOWMIK | 8.83 | 5.52 | 100
2511 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil investigation work for 200 Cum over head Reservoir (OHR)for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division PHE.Dte. |  | Junior Engineer | ORD/000834/2021-2022 | 1183/W/JSSD | 08/03/2022 | 20 | G MITRA & ASSOCIATES | 2 | 1.99 | 0
2512 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division. |  | Junior Engineer | ORD/001000/2021-2022 | 1242/JSSD | 25/03/2022 | 45 | SURAJIT KUNDU | 4.65 | 0 | 0
2513 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Angrabhasa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001006/2021-2022 | 1262/JSSD | 25/03/2022 | 20 | SURAJIT KUNDU | 4.8 | 0 | 0
2514 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Replacing Old Damaged Pipeline With Laying New UPVC Pipeline Due To Construction of Rural Road at Angravasa Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/001032/2021-2022 | 56 /JSSD | 12/05/2021 | 30 | ROY & SARKAR CONSTRUCTION | 3.76 | 1.17 | 1
2515 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Continuation Work order for the work of Annual Maintenance of pipe line and other misc. work related to pipe line including maintenance of I.E.Plant (if any)for Angravasa T.G. PWSS under Jalpaiguri Division, P.H.E Dte. period from 15/07/2021 to 31/12/2021. |  | Junior Engineer | ORD/001037/2021-2022 | 162 /JSSD | 15/07/2021 | 170 | ROY & SARKAR CONSTRUCTION | 2.23 | 0 | 1
2516 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000016/2021-2022 | 555/JD | 01/03/2022 | 0 | Resource Division | 52.27 | 0 | 0
2517 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for PUMP HOUSE IN ANGRABHASA w/s scheme under BANARHAT CCC, [APPLICATION NO. 4002813842, Reference ID : 422058156] |  | Junior Engineer | BILL/00463/2023-2024 | BP/23-24/32 | 09/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.46 | 0 | 0
2518 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for ANGRABHASA, T/W No.III, under BANARHAT CCC, [APPLICATION NO. 4003323154, Reference ID : 403149195] |  | Junior Engineer | BILL/01937/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.34 | 0 | 0
2519 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF ANGRABHASA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000880/2022-2023 | 363/NMD | 29/03/2023 | 690 | M/S ROYAL ENTERPRISE | 10.1 | 10.04 | 100
2520 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Tow Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme of Jiti Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000067/2022-2023 | 1222/JD | 31/05/2022 | 30 | M/S BABUN BISWAS | 13.84 | 0 | 0
2521 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related to Functional Household Tap Connection(FHTC) in connection with JJM/Jalswapna under command area of JITI pipe water supply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000106/2022-2023 | 82/JSSD | 22/07/2022 | 20 | ARUP SARKAR | 4.85 | 4.71 | 100
2522 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works and installation of valerelated to Functional Household Tap Connection(FHTC)inconnection with JJM/Jalswapna under command area of Jiti pipe watersupply scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000117/2022-2023 | 94/JSSD | 22/07/2022 | 30 | ARUP SARKAR | 3.25 | 1.98 | 100
2523 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big dia Tube Well by Modified DTH-ODEX method at 3rd & 4th tube well site in connection with Jal Jeevan Mission of JITI Tea Garden piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000299/2023-2024 | 1356/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 32.57 | 24.77 | 100
2524 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of 2 nos of Pump House (1st site & 2nd site ), 2Nos boundary wall (1st site & 2nd site) and other Allied works at Jiti TG Piped Water Supply Scheme under Jalpaiguri Division .P.H.E. Dte. |  | Junior Engineer | ORD/000308/2022-2023 | 90/JSSD | 22/07/2022 | 15 | SOUVIK SAHA | 4.7 | 3.61 | 0
2525 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Rejuvenation of Jiti Tea Garden piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000482/2022-2023 | 801/JD.. | 29/03/2023 | 914 | KSMC CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION | 2.48 | 0 | 100
2526 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 M x 2.40 M) size with sanitary & Plumbing arrangement at 3rd Tube well site for Jiti T.G. PWSS under Jalpaiguri Division, |  | Junior Engineer | ORD/000597/2021-2022 | 1055/JSSD | 24/01/2022 | 45 | ADWIJA CONSTRUCTION | 4.64 | 4.64 | 100
2527 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate drain and pathway for 3rd tube well site of Jiti T.G. P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000707/2021-2022 | 1044/JSSD | 24/01/2022 | 20 | ADWIJA CONSTRUCTION | 3.76 | 3.82 | 100
2528 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000104/2023-2024 | 1374/JD | 27/09/2023 | 0 | Resource Division | 9.21 | 0 | 0
2529 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | lds jabarmali pwss |  | Junior Engineer | VCH/000542/2022-2023 | BP-2021-22-170 | 29/09/2022 | 0 | BOSE ENTERPRISE | 2.43 | 0 | 0
2530 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | RETROFITTING WORKS BHANGARHAT PWSS |  | Junior Engineer | VCH/001289/2021-2022 | BP-2021-22-500 | 29/03/2022 | 0 | MRINMOY KANTI DUTTA | 1.55 | 0 | 0
2531 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SINKING 250MX150 MM DIA PURBASALBARI PWSS |  | Junior Engineer | VCH/001307/2021-2022 | BP-2021-22- 470 | 28/03/2022 | 0 | ABHIJIT SARKAR | 7.92 | 0 | 0
2532 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. III, under MAL CCC [APPLICATION NO. 100000099255 ; Reference ID : 860291235] |  | Junior Engineer | BILL/02018/2023-2024 | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.56 | 0 | 0
2533 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. IV, under MAL CCC [APPLICATION NO. 100000099256 ; Reference ID : 860291236] |  | Junior Engineer | BILL/02019/2023-2024 | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.8 | 0 | 0
2534 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for REJU JITI TEA GARDEN, T/W No. III, under MAL CCC [APPLICATION NO. 403330231 ; Reference ID : 403155154] |  | Junior Engineer | BILL/02020/2023-2024 | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2535 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for REJU JITI TEA GARDEN, T/W No. IV, under MAL CCC [APPLICATION NO. 4003330215 ; Reference ID : 403155155] |  | Junior Engineer | BILL/02021/2023-2024 | BP/23-24/309 | 16/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2536 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JITI T.G. PWSS, TW No III and IV in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000884/2022-2023 | 367/NMD | 29/03/2023 | 690 | MIHIR SARKAR | 25.02 | 21.97 | 90
2537 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
2538 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SUPPLY OF FUEL AND OTHER CONSUMABLE ITEMS |  | Junior Engineer | BILL/00357/2022-2023 | BP-2023-24-110 | 17/05/2023 | 0 | M/S MILLENNIUM FUEL CENTRE | 4.99 | 0 | 0
2539 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with Sanitary & Plumbing arrangement at Head works site for Augmentation of Luksan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000039/2022-2023 | 1080/JD | 29/04/2022 | 60 | MONOTOSH ROY | 5.61 | 5.61 | 1
2540 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Redevelopment of Boundary Wall with gate, drain and pathway for Existing tubewell (2nd site as per new drawing) site for Augmentation of Luksan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000058/2024-2025 | 959/JD | 09/08/2024 | 602 | ALICK DUTTA | 22.33 | 3.46 | 75
2541 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall at Head Work (OHR) site of Augmentation of Luksan Bazar (Zone-II) i.c.w. Jal Jeevan Mission at block Nagrakata in Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000059/2024-2025 | 960/JD | 09/08/2024 | 601 | ALICK DUTTA | 12.36 | 0 | 0
2542 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 2nd tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000065/2022-2023 | 1218/JD | 26/05/2022 | 21 | J.M. CONSTRUCTION | 7.16 | 5.53 | 1
2543 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- II) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000066/2022-2023 | 1232/JD | 02/06/2022 | 21 | J.M. CONSTRUCTION | 7.16 | 4.67 | 1
2544 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Land development works at the Zone-II H/W Site along with pump connection and other allied works at Augmentation of Luksan Bazar Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000142/2024-2025 | 257/JSSD | 25/09/2024 | 464 | ARUP SARKAR | 2.61 | 0 | 0
2545 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | -Interconnection work including FHTC with allied works at Augmentation of Looksan Bazar Piped W/S Scheme ( zone-I & III) in connection with JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000148/2024-2025 | 267/JSSD | 25/09/2024 | 15 | GOURAV CONSTRUCTION CO. | 2.25 | 0 | 0
2546 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Laying Rising Main for Augmentation of Luksan Bazar (Zone -I ,Zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000150/2024-2025 | 263/JSSD | 25/09/2024 | 99 | MONTOSH GHOSH | 2.78 | 1.5 | 100
2547 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big Dia 2nd Tube well by Modified DTH - ODEX Method at 1st tube well site of Augmentation of Luksan Bazar Piped Water Supply Scheme of (zone-I) of Nagrakata Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000441/2024-2025 | 2319/JD | 11/12/2024 | 15 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 17.61 | 0 | 100
2548 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Rising Main for Augmenmtation of Luksan Bazar (Zone -I ,zone - II & Zone - III) piped water supply scheme in connection with Jal Jeevan Mission under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000478/2022-2023 | 797/JD.. | 29/03/2023 | 599 | MONTOSH GHOSH | 7.71 | 7.5 | 100
2549 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repair of damage pipe line and FHTC at Lukshan Bazar (Zone-III) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000547/2023-2024 | 498/JSSD | 02/01/2024 | 30 | ALICK DUTTA | 4.81 | 2.61 | 100
2550 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work for construction of Pump House (3.60m x 2.40m) with sanitary & plumbing arrangement at 2nd T/W site for Augmentation of Lukshan Bazar (Zone - II) Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000554/2023-2024 | 505/JSSD | 02/01/2024 | 335 | ARUP SARKAR | 2.75 | 2.75 | 100
2551 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000570/2021-2022 | 548/JD | 28/02/2022 | 1312 | GAP ENGINEERS ENTERPRISES | 79.03 | 18.53 | 75
2552 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System providing with Functional Household Tap Connection (FHTC) in connection with Jalswapna /JJM for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000581/2021-2022 | 547/JD | 28/02/2022 | 30 | ALICK DUTTA | 21.58 | 4.67 | 15
2553 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | 200 Cum OHR as per Departmental Design & Drawing for Augmentation of Lukshan Bazar Piped Water Supply Scheme at Zone-II Block- Nagrakata, District - Jalpaiguri. |  | Junior Engineer | ORD/000587/2021-2022 | 735/JD | 17/03/2022 | 180 | SCEC BOENTER KDAS JOINT VENTURE | 55.08 | 22.21 | 100
2554 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- III) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000704/2021-2022 | 817/JD | 30/03/2022 | 21 | PINAKI MITRA | 7.15 | 6.25 | 1
2555 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by ODEX-165 Method of drilling at 1st tubewell site for Augmentation of Luksan Bazar (zone- I) piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000705/2021-2022 | 818/JD | 30/03/2022 | 21 | PINAKI MITRA | 7.15 | 7.01 | 1
2556 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-1) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000827/2021-2022 | 1184/W/JSSD | 08/03/2022 | 20 | MABCO CONSULTANT | 2.02 | 0.85 | 0
2557 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation Work for 200 Cu M Over Head Reservoir (OHR) for Augmentation of Lukshan Bazar(Zone-11) Pipe Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000833/2021-2022 | 1182/W/JSSD | 08/03/2022 | 20 | M K KAYAL & ASSOCIATES | 2.02 | 2 | 0
2558 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m ) size with sanitary & plumbing arrangement at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-I) Piped Water Supply Scheme for under Jalpaiguri Division. |  | Junior Engineer | ORD/001002/2021-2022 | 1243/JSSD | 25/03/2022 | 45 | KABYA ENTERPRISE | 4.64 | 4.64 | 100
2559 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at Lukshan Bazar (Zone-III) for Augmentation of Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001003/2021-2022 | 1244/JSSD | 25/03/2022 | 45 | SURAJIT KUNDU | 4.65 | 4.65 | 100
2560 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60m x 2.40m) size including sanitary & plumbing works at 2nd Tube well site for Augmentation of Lukshan Bazar (Zone-II) Piped water supply Scheme for under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001004/2021-2022 | 1245/JSSD | 25/03/2022 | 45 | DEBABRATA SARKAR | 4.65 | 0 | 100
2561 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 2nd tube-well site for Augmentation of Lukshan Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/001005/2021-2022 | 1261/JSSD | 25/03/2022 | 20 | SURAJIT KUNDU | 4.79 | 3.37 | 100
2562 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 1st tube-well site for Augmentation of Lukshan Bazar (Zone-III) Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/001007/2021-2022 | 1263/JSSD | 25/03/2022 | 20 | JAYA SARKAR | 4.79 | 4.24 | 100
2563 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 4003095902, Reference ID : 402966241] |  | Junior Engineer | BILL/00759/2022-2023 | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2564 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-I, under NAGRAKATA CCC, [APPLICATION NO. 100000072620, Reference ID : 860263640] |  | Junior Engineer | BILL/00760/2022-2023 | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.27 | 0 | 0
2565 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 4003097549, Reference ID : 402966979] |  | Junior Engineer | BILL/00761/2022-2023 | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2566 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for LUKSAN BAZER,T/W I,ZONE-III, under NAGRAKATA CCC, [APPLICATION NO. 100000072602, Reference ID : 860263632] |  | Junior Engineer | BILL/00762/2022-2023 | BP/22-23/159 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.49 | 0 | 0
2567 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF LUKSAN BAZAR PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000800/2022-2023 | 163/NMD | 17/02/2023 | 30 | CHOWDHURY AND BASU ENTERPRISE | 41.3 | 37.91 | 80
2568 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
2569 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 4002969971, Reference ID :402856021] |  | Junior Engineer | VCH/000890/2022-2023 | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2570 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. I, under NAGRAKATA CCC, [APPLICATION NO. 100000058118, Reference ID : 860247828] |  | Junior Engineer | VCH/000891/2022-2023 | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.79 | 0 | 0
2571 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 4002966831, Reference ID :402856022] |  | Junior Engineer | VCH/000892/2022-2023 | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2572 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | ERRECTION OF NEW 25 KVA DTR FOR EFFECTION 3 PH SERVICE CONNECTION AT LAKSAN BAZER W/S SCHEME, T/W No. II, under NAGRAKATA CCC, [APPLICATION NO. 100000056975, Reference ID : 860246285] |  | Junior Engineer | VCH/000893/2022-2023 | BP/22-23/63 | 23/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0
2573 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Uttar Khuttimari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000129/2023-2024 | 405/JD | 06/06/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 280.55 | 163.06 | 45
2574 | Jalpaiguri Division | Jalpaiguri Division | Providing Balance Functional Household Tap Connection (FHTC) in the command area of Uttar Kuttimari PWSS in connection with Jal Jeevan Mission at Block Dhupguri under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000605/2024-2025 | 485/JD | 11/03/2025 | 25 | KABYA ENTERPRISE | 12.58 | 0 | 0
2575 | Jalpaiguri Division | Jalpaiguri Division | Supply and Delivery at site of UPVC pipe of 250mm dia for tube well of Uttar Khuttimari PWSS under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000736/2023-2024 | 2456/JD | 23/02/2024 | 7 | UNIBRO INFRASERV PRIVATE LIMITED | 2.46 | 0 | 0
2576 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000020/2023-2024 | 164/JD | 28/04/2023 | 0 | Resource Division | 13.57 | 0 | 0
2577 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000132/2023-2024 | 1881/JD | 20/12/2023 | 0 | Resource Division | 6.62 | 0 | 0
2578 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-II, under GAIRKATA CCC, [APPLICATION NO. 4003356873, Reference ID : 403176987] | Assistant Engineer,HQ | Junior Engineer | BILL/02168/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0
2579 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-II, under GAIRKATA CCC, [APPLICATION NO. 100000101602, Reference ID : 860292662] | Assistant Engineer,HQ | Junior Engineer | BILL/02169/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.42 | 0 | 0
2580 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-I, under GAIRKATA CCC, [APPLICATION NO. 4003356966, Reference ID : 403176985] | Assistant Engineer,HQ | Junior Engineer | BILL/02170/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0
2581 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for UTTAR KHUTTIMARI, T/W-I, under GAIRKATA CCC, [APPLICATION NO. 100000101600, Reference ID : 860292660] | Assistant Engineer,HQ | Junior Engineer | BILL/02171/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3 | 0 | 0
2582 | Jalpaiguri Division | Jalpaiguri Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2583 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Gairkhata Tea Garden (D) PWSS i.e. T.W. Pump House, Water Distribution Network, OHR, Rising Main,FHTC etc. In connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000440/2022-2023 | 677/JD | 16/03/2023 | 455 | SUKES BASU MAJUMDAR | 448.24 | 432.96 | 100
2584 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Rising Main, Laying Distribution System at 3rd Tube Well Site and Providing Functional Household Tap Connection of Sajnapara around Gairkata Tea Garden Piped Water Supply Scheme in connection with Jal Jeevan Mission at Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000680/2024-2025 | 459/JD | 11/03/2025 | 143 | ALOKE DEY | 56.41 | 0 | 20
2585 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000003/2023-2024 | 147/JD | 28/04/2023 | 0 | Resource Division | 32.33 | 0 | 0
2586 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000117/2023-2024 | 1828/JD | 15/12/2023 | 0 | Resource Division | 14.29 | 0 | 0
2587 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for GAIRKATA, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003214185, Reference ID : 403062249] | Assistant Engineer,HQ | Junior Engineer | BILL/01068/2023-2024 | BP/23-24/106 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.66 | 0 | 0
2588 | Northern Mechanical | Jalpaiguri Division | Fuel Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0007/2024-2025 , Dt - 31/10/2024 Vechile no - WGX4997 for the month of OCtober 2024 | Assistant Engineer,HQ | Junior Engineer | BILL/01679/2024-2025 |  | 06/12/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.09 | 0 | 0
2589 | Northern Mechanical | Jalpaiguri Division | Fuel, Lubricant Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0007(A)/2024-2025 , Dt - 31/10/2024 Vechile no - WB73B/7824 for the month of october 2024 | Assistant Engineer,HQ | Junior Engineer | BILL/01680/2024-2025 |  | 06/12/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.1 | 0 | 0
2590 | Northern Mechanical | Jalpaiguri Division | Fuel Charges for Government Inspection Vechile under NMD PHE Dte Invoice No : 0006/2024-2025 , Dt - 30/09/2024 Vechile no - WGX4997 for the month of september 2024 | Assistant Engineer,HQ | Junior Engineer | BILL/01681/2024-2025 |  | 06/12/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.2 | 0 | 0
2591 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GAIRKHATA TEA GARDEN (D) PWSS, at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000140/2023-2024 | 1194/NMD | 21/07/2023 | 30 | SARKAR ELECTRIC | 40.62 | 40.54 | 100
2592 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of GAIRKATA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000874/2022-2023 | 338/NMD | 29/03/2023 | 795 | M/S ROYAL ENTERPRISE | 10.24 | 7.78 | 100
2593 | Northern Mechanical | Jalpaiguri Division | Additional works in connection with supply, installation and commissioning and trial operation of electromechanical accessories of W/S system at GAIRKATA W/S scheme for T.W No. -I, II & III in the dist. of Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001041/2023-2024 | 01/DSD | 04/01/2024 | 7 | SARKAR ELECTRIC | 0.93 | 0.93 | 100
2594 | Jalpaiguri Division | Northern Mechanical Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
2595 | Jalpaiguri Division | Northern Mechanical Division | Balance Laying Distribution System and Functional Household Tap Connection in connection with Jal Jeevan Mission for Gendrapara Tea Garden Piped Water Supply Scheme Block - Banarhat under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000528/2024-2025 | 125/JD | 16/01/2025 | 50 | SANJIT SAHA | 56.46 | 0 | 0
2596 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000060/2023-2024 | 1093/JD | 24/08/2023 | 0 | Resource Division | 27.95 | 0 | 0
2597 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000118/2023-2024 | 1829/JD | 15/12/2023 | 0 | Resource Division | 14.72 | 0 | 0
2598 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 4003193569 ; Reference ID : 403045945] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01001/2023-2024 | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2599 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W I under BANARHAT CCC [APPLICATION NO. 100000083816 ; Reference ID : 860275316] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01002/2023-2024 | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.68 | 0 | 0
2600 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 4003193576 ; Reference ID : 403045947] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01003/2023-2024 | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2601 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W II under BANARHAT CCC [APPLICATION NO. 100000083810 ; Reference ID : 860275310] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01004/2023-2024 | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.03 | 0 | 0
2602 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 4003193581 ; Reference ID : 403045948] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01005/2023-2024 | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2603 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for GENDRAPARA TEA GAEDEN, T/W III under BANARHAT CCC [APPLICATION NO. 100000083811 ; Reference ID : 860275311] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01006/2023-2024 | BP/23-24/98 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.38 | 0 | 0
2604 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
2605 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0
2606 | Northern Mechanical | Northern Mechanical Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under BANARHAT Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001136/2024-2025 | 52/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.39 | 0 | 0
2607 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different components of Upper Tandu Forest (M) i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc i.e.w. Jal Jeevan Mission at Block:- Nagrakata under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000444/2022-2023 | 676/JD | 16/03/2023 | 180 | NISHITH RANJAN KARMAKAR | 96 | 76.78 | 100
2608 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000016/2023-2024 | 160/JD | 28/04/2023 | 0 | Resource Division | 2.08 | 0 | 0
2609 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000171/2023-2024 | 2057/JD | 09/01/2024 | 0 | Resource Division | 2.22 | 0 | 0
2610 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 4003177258 ; Reference ID : 403033825] |  | Junior Engineer | BILL/01009/2023-2024 | BP/23-24/97 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2611 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for UPPER TENDU FOREST NEW KHUNIA MAHABARI, under MATELLI CCC [APPLICATION NO. 100000082756 ; Reference ID : 860274516] |  | Junior Engineer | BILL/01010/2023-2024 | BP/23-24/97 | 12/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.11 | 0 | 0
2612 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2613 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UPPER TENDU FOREST PWSS, TW No I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000881/2022-2023 | 364/NMD | 29/03/2023 | 30 | SAIKAT SINHA | 12.05 | 12.03 | 100
2614 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0
2615 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0
2616 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation Of Grassmore Tea Garden PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000126/2023-2024 | 413/A/JD | 07/06/2023 | 60 | JAYDEB SAHA | 30.89 | 23.73 | 90
2617 | Jalpaiguri Division | Jalpaiguri Division | Direct boosting arrangement from 2 nd Pump to the Nandu more to Ghasmari Road area due to low tail end pressure along with leftout distribution system and FHTC at Grassmore T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000135/2023-2024 | 794/JD | 24/07/2023 | 617 | SUNIL ROY | 11.3 | 0 | 100
2618 | Jalpaiguri Division | Jalpaiguri Division | Construction of Hume Pipe Culvert along with approach way development at 2 nd Pump House Site of Grassmore T.G. Piped water supply Scheme under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000164/2022-2023 | 1434/JD | 18/07/2022 | 15 | DEEP CONSTRUCTION | 1.18 | 1.17 | 1
2619 | Jalpaiguri Division | Jalpaiguri Division | Remaining part of Laying Distribution System (PART-C ) for Grassmore T.G. AREA P.W.S.S. under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000181/2020-2021 | 1266/JD | 18/11/2020 | 60 | ASHIT KUMAR SINGHA | 61.96 | 0 | 1
2620 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for GRASSMORE TG, T/W No. III, under NAGRAKATA CCC [APPLICATION NO. 4003285470 ; Reference ID : 403120243] | Assistant Engineer,HQ | Junior Engineer | BILL/01727/2023-2024 | BP/23-24/240 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2621 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for GRASSMORE TG, T/W No. III, under NAGRAKATA CCC [APPLICATION NO. 100000096116 ; Reference ID : 860288226] | Assistant Engineer,HQ | Junior Engineer | BILL/01728/2023-2024 | BP/23-24/241 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.21 | 0 | 0
2622 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2623 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF GRASSMORE TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000429/2023-2024 | 1346/NMD | 08/08/2023 | 30 | BONANZA ENTERPRISE | 11.36 | 11.33 | 100
2624 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0
2625 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
2626 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Work of Distribution System for Patkata Zone- III Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000055/2024-2025 | 957/JD | 09/08/2024 | 601 | JAYA SARKAR | 49.34 | 0 | 80
2627 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Patkata Zone-III PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc In connection with Jal Jeevan Mission at Block- Jalpaiguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000069/2023-2024 | 398/A/JD | 06/06/2023 | 1037 | GARGO TRADERS | 434.09 | 191.65 | 70
2628 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain,pipeline for washout at 2nd site of PATKATA ZONE - III PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000110/2025-2026 | 488/RWS | 29/05/2025 | 30 | PARESH CHANDRA GHOSH ROY | 5.49 | 0 | 0
2629 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-III PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000530/2024-2025 | 117/JD | 16/01/2025 | 440 | PRADIP KUMAR SEN | 26.83 | 0 | 90
2630 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000110/2023-2024 | 1369/JD | 27/09/2023 | 0 | Resource Division | 23.28 | 0 | 0
2631 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000136/2023-2024 | 1883/JD | 20/12/2023 | 0 | Resource Division | 15.62 | 0 | 0
2632 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for new service connection at PATKATA, T/W-II, ZONE-III, UKILPARA MASKALAIBARI CCC APPLICATION NO. 4003426181 Reference ID : 403231210 |  | Junior Engineer | BILL/00482/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.94 | 0 | 0
2633 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PATKATA, ZONE-III, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341668, Reference ID : 403171646] |  | Junior Engineer | BILL/02141/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.89 | 0 | 0
2634 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000180/2023-2024 | 1217/NMD | 26/07/2023 | 30 | MALAY KUMAR SAHA | 24.37 | 17.71 | 70
2635 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling for Karbala Tea Garden Pipe Water Supply Scheme in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000297/2023-2024 | 1355/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 20.38 | 15.96 | 100
2636 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000057/2023-2024 | 1095/JD | 24/08/2023 | 0 | Resource Division | 12.32 | 0 | 0
2637 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for REJU KARBALA TEA GARDEN, T/W No. I, under BANARHAT CCC [APPLICATION NO. 4003333217 , Reference ID : 403157469] |  | Junior Engineer | BILL/02003/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.61 | 0 | 0
2638 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF KARBALA TG PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000414/2023-2024 | 1328/NMD | 08/08/2023 | 30 | AHALYA ENGINEERING WORKS | 23.83 | 17.11 | 60
2639 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of Pipe line in uncovered area including installation of Sluice Valves at different strategic point within the command area of Mogolkata T.G. P.W.S.S. at Dhupguri Block under Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000191/2022-2023 | 1694/JD | 06/09/2022 | 21 | DIPAK KUMAR CHAKRABORTY | 4.1 | 4.11 | 1
2640 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC including retrofitting works near Totapara Bazar for Mogalkata Piped Water Supply Scheme at Banarhat Block in under Jalpaiguri Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000539/2023-2024 | 1971/JD | 03/01/2024 | 20 | JITENDRA NATH ROY | 12.57 | 9.73 | 100
2641 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000051/2023-2024 | 1099/JD | 24/08/2023 | 0 | Resource Division | 2.59 | 0 | 0
2642 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for REJUVENATION OF MOGALKATA TG, T/W-III, under BANARHAT CCC APPLICATION NO. 4003374000 Reference ID : 403189743 | Assistant Engineer | Junior Engineer | BILL/00134/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.02 | 0 | 0
2643 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2644 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
2645 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 250 cum capacity 20 m staging height OHR, tube well, pump house 3.60x2.40m with sanitary arrangement, boundary wall, Laying distribution system, Rising Main for BARADIGHI T.G. under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000042/2020-2021 | 1060/JD | 13/10/2020 | 120 | BOSE ENTERPRISE | 126.27 | 0 | 1
2646 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Baradighi Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000110/2023-2024 | 404/A/JD | 06/06/2023 | 1030 | ALICK DUTTA | 32.52 | 10.25 | 25
2647 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (150 nos) in connection with JJM near Dipu line, Mangla line, Bhouka line and allied areas for Barodighi T.G. Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000351/2022-2023 | 613/JD | 09/03/2023 | 15 | PRIYABRATA KARMAKAR | 7.12 | 7.05 | 1
2648 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jaldhara/Jalswapna near factory line and allied areas for Barodighi TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000387/2022-2023 | 362/JD | 20/02/2023 | 14 | PRIYABRATA KARMAKAR | 6.38 | 6.37 | 1
2649 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Conctruction of approach road with paver block inside the premises and outside approach, R.B.T fixing in boundary wall and inside drain at H/W site for Barodighi TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000406/2022-2023 | 612/JD | 09/03/2023 | 21 | BOSE ENTERPRISE | 13.4 | 13.34 | 100
2650 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000058/2023-2024 | 1089/JD | 24/08/2023 | 0 | Resource Division | 5.42 | 0 | 0
2651 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for BARADIGHI T/W No. I under MATELI CCC [APPLICATION NO. 4003279994 ; Reference ID :403115813] |  | Junior Engineer | BILL/01721/2023-2024 | BP/23-24/234 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2652 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for BARADIGHI T/W No. I under MATELI CCC [APPLICATION NO. 100000094585 ; Reference ID :860286265] |  | Junior Engineer | BILL/01722/2023-2024 | BP/23-24/235 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.51 | 0 | 0
2653 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF BARADIGHI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000169/2023-2024 | 1211/NMD | 26/07/2023 | 30 | ASHWIRBAD WOOD CRAFT | 11.45 | 0 | 0
2654 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: METELI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000883/2024-2025 | 24/NMD | 06/01/2025 | 30 | EASTERN INDIA SALES & SERVICE | 15.33 | 0 | 0
2655 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARADIGHI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000974/2023-2024 | 1896/NMD | 30/11/2023 | 30 | S.P. ENTERPRISE | 11.3 | 11.23 | 100
2656 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0
2657 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Manabari Tea Garden PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000267/2023-2024 | 937/JD | 08/08/2023 | 754 | TARAKESWAR PRASAD | 97.86 | 0 | 60
2658 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Approach Culvert with Guard Wall at H/W site for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000381/2022-2023 | 359/JD | 20/02/2023 | 21 | M/S A.B.G. CONSTRUCTION | 2.93 | 2.92 | 100
2659 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of G. I. line & concrete block & piller for culvert for Manabari Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000483/2022-2023 | 802/JD | 29/03/2023 | 21 | M/S A.B.G. CONSTRUCTION | 3.02 | 2.98 | 100
2660 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Rejuvenation of Manabari Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000593/2023-2024 | 2332/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 14.02 | 100
2661 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000089/2023-2024 | 1064/JD | 24/08/2023 | 0 | Resource Division | 19.68 | 0 | 0
2662 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at REJU. OF MANABARI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 100000118549 Reference ID : 860312789 |  | Junior Engineer | BILL/01398/2024-2025 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0
2663 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for REJU. OF MANABARI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003491167 Reference ID : 403275173 |  | Junior Engineer | BILL/01399/2024-2025 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2664 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
2665 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MANABARI TEA GARDEN PWSS, AT TW no III AND IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000426/2023-2024 | 1341/NMD | 08/08/2023 | 30 | S.P. ENTERPRISE | 20.63 | 0 | 0
2666 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0
2667 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001005/2024-2025 | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0
2668 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
2669 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Uttar Marichbari PWSS i.e, TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC, etc. in connection with Jal Jeevan Mission at Block- Maynaguri under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000501/2022-2023 | 773/JD | 27/03/2023 | 710 | UNIBRO INFRASERV PRIVATE LIMITED | 182.48 | 93.19 | 80
2670 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at H/W site including rising main and interconnections of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000565/2023-2024 | 2174/JD | 22/01/2024 | 679 | SUBRATA GOSWAMI | 15.52 | 0 | 100
2671 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall at 2nd Pump House site including raising main and interconnection of Uttar Marichbari PWSS in connection with Jal Jeevan Mission at Block - Maynaguri under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000673/2023-2024 | 166/RWS | 15/02/2024 | 30 | PINTU DAS | 6.14 | 6.11 | 100
2672 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000026/2023-2024 | 170/JD | 28/04/2023 | 0 | Resource Division | 15.65 | 0 | 0
2673 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000181/2023-2024 | 2046/JD | 09/01/2024 | 0 | Resource Division | 5.49 | 0 | 0
2674 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for UTTAR MARICH BARI MAYNAGURI, T/W II, under MAYNAGURI CCC, [APPLICATION NO. 4003164173, Reference ID : 403024437] |  | Junior Engineer | BILL/00580/2023-2024 | BP/23-24/72 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2675 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for UTTAR MARICH BARI MAYNAGURI, T/W II, under MAYNAGURI CCC, [APPLICATION NO. 100000084433, Reference ID : 860276013] |  | Junior Engineer | BILL/00581/2023-2024 | BP/23-24/72 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.09 | 0 | 0
2676 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for UTTAR MARICHBARI MAYNAGURI, T/W I, under MAYNAGURI CCC, [APPLICATION NO. 4003164169, Reference ID : 403024436] |  | Junior Engineer | BILL/01065/2023-2024 | BP/23-24/104 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2677 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for UTTAR MARICHBARI MAYNAGURI, T/W I, under MAYNAGURI CCC, [APPLICATION NO. 100000088138, Reference ID : 860278838] |  | Junior Engineer | BILL/01066/2023-2024 | BP/23-24/104 | 30/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.26 | 0 | 0
2678 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
2679 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
2680 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for UTTAR MARICHBARI PWSS, TW no I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000431/2023-2024 | 1370/NMD | 09/08/2023 | 389 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 20.62 | 18.67 | 100
2681 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
2682 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Distribution System and Functional Household Tap Connection (FHTC) for Patkata Zone-I Piped Water Supply Scheme within Jalpaiguri Sadar Block under Jalpaiguri Division, P. H. E. Dte. |  | Junior Engineer | ORD/000028/2024-2025 | 740/JD | 26/07/2024 | 150 | M/S SIBU DEY AND CO. | 118.85 | 18.19 | 60
2683 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall ,Foot Path,Drain at 2nd site of PATKATA ZONE -I PWSS in connection with Jal Jeevan Mission at Block - Sadar Block under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000105/2025-2026 | 483/RWS | 29/05/2025 | 30 | PINTU DAS | 7.76 | 0 | 0
2684 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Patkata Zone- I Piped Water Supply Scheme i.e TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc. In connection with Jal Jeevan Mission at Block- Jalpaiguri Sadar under jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000441/2023-2024 | 1706/JD | 04/12/2023 | 637 | GARGO TRADERS | 546.65 | 109.05 | 60
2685 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including Iron Elemination Plant and interconnection work at 3rd site of Patkata Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000466/2025-2026 | 2497/JD | 09/12/2025 | 120 | KANAI LAL SEN | 21.13 | 0 | 0
2686 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary Wall, Foot Path, Drain including interconnection work at H/W site of Patkata Zone-I PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000534/2024-2025 | 112/JD | 16/01/2025 | 440 | DINABANDHU ROY | 17.84 | 0 | 0
2687 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000109/2023-2024 | 1371/JD | 27/09/2023 | 0 | Resource Division | 48.31 | 0 | 0
2688 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000199/2023-2024 | 2076/JD | 10/01/2024 | 0 | Resource Division | 26.02 | 0 | 0
2689 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PATKATA, ZONE-I, TW NO-III, MASKALAIBARI CCC APPLICATION NO. 4003483369 Reference ID : 403270691 |  | Junior Engineer | BILL/01320/2024-2025 | BP/24-25/217 | 27/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 19.61 | 0 | 0
2690 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PATKATA, ZONE-I, T/W- I, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 4003341718, Reference ID : 403171608] |  | Junior Engineer | BILL/02142/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.15 | 0 | 0
2691 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PATKATA, ZONE-I, T/W- II, under UKILPARA MASKALAIBARI CCC, [APPLICATION NO. 40033417720, Reference ID : 403172408] |  | Junior Engineer | BILL/02143/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.09 | 0 | 0
2692 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2693 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PATKATA PWSS ZONE-I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000315/2023-2024 | 1279/NMD | 02/08/2023 | 761 | M/S BHOWMICK & CO. | 35.98 | 0 | 60
2694 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
2695 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I)of PATKATA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. |  | Junior Engineer | ORD/001703/2023-2024 | 436/SMSD | 28/03/2024 | 7 | M/S ANJALI ENTERPRISE | 0.73 | 0 | 0
2696 | Jalpaiguri Division | Jalpaiguri Division | Construction of diferent components of Paschim Salbari Zone-II pwss i.e TW, Pump Houses, water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block-Dhupguri under Jalpaiguri Division , P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000058/2023-2024 | 264/JD | 10/05/2023 | 1057 | ANUP SARKAR | 213 | 163.63 | 35
2697 | Jalpaiguri Division | Jalpaiguri Division | Arrangement for disposal of waste water of IEP at H/W site of Paschim Salbari(zone-II) W/S/S under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000284/2022-2023 | 649/RWS | 21/10/2022 | 20 | PARAMJYOTI ENTERPRISE | 4.32 | 0 | 1
2698 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM under Paschim Salbari Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000457/2024-2025 | 2333./JD | 12/12/2024 | 475 | ANUP SARKAR | 18.22 | 0 | 100
2699 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000041/2023-2024 | 1113/JD | 24/08/2023 | 0 | Resource Division | 9.93 | 0 | 0
2700 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000134/2023-2024 | 1880/JD | 20/12/2023 | 0 | Resource Division | 4.77 | 0 | 0
2701 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PASCHIM SALBARI ,ZONE:-II, T/W-I, under DHUPGURI CCC APPLICATION NO. 4003379309 Reference ID : 403193837 | Assistant Engineer,HQ | Junior Engineer | BILL/00307/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.77 | 0 | 0
2702 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for PASCHIM SALBARI PWSS, ZONE-II, TW NO II, under DHUPGURI CCC APPLICATION NO. 4003289711 Consumer ID : 403122966 | Assistant Engineer,HQ | Junior Engineer | BILL/00535/2024-2025 | BP/24-25/130 | 24/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.75 | 0 | 0
2703 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2704 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001049/2024-2025 | 31/NMD | 06/01/2025 | 30 | ANIMA ENTERPRISE | 15.32 | 0 | 0
2705 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rejuvenation work for Pump House & Additional Backwash line for Uttar Bhuskadanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000683/2023-2024 | 155/RWS | 15/02/2024 | 30 | MRINMOY KANTI DUTTA | 6.13 | 6.01 | 100
2706 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Additional pipeline to improve the water distribution network for Uttar Bhuskadanga Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000702/2024-2025 | 631/JD | 28/03/2025 | 218 | MRINMOY KANTI DUTTA | 23.85 | 0 | 0
2707 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000098/2023-2024 | 1055/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0
2708 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for UTTAR BHUSKADANGA(REJU), T/W-III under MAYNAGURI CCC APPLICATION NO. 4003401398 Reference ID : 403211999 |  | Junior Engineer | BILL/00287/2024-2025 | BP/24-25/36 | 14/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.97 | 0 | 0
2709 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF UTTAR BHUSKADANGA AND GARTALI JALPESH PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000171/2023-2024 | 1213/NMD | 26/07/2023 | 30 | MAA ENTERPRISES | 11.18 | 0 | 0
2710 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 M X 2.40 M ) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Bagrakote T.G. W/S/S under Jalpaiguri Division , P.H.E. Dte. |  | Junior Engineer | ORD/000293/2021-2022 | 825/RWS | 30/11/2021 | 1187 | BIMAN DAS | 4.65 | 0 | 100
2711 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Emergency water supply arrangement to the dengue effected area related to Bagrakote water supply Scheme for 45 days . ( from 29.06.2022 to 12.08.2022) |  | Junior Engineer | ORD/000299/2022-2023 | 437/RWS | 07/07/2022 | 45 | SWAPAN SAHA | 4.47 | 0 | 0
2712 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall, drain and pathway for 2nd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000349/2022-2023 | 134/JD | 17/01/2023 | 30 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.01 | 6.44 | 100
2713 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 3 Nos. Tubewell by ODEX-165 method for Bagrakote W/S Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000375/2023-2024 | 1516/JD | 16/10/2023 | 30 | RANJEET SINGH BENIWAL | 20.54 | 16.66 | 100
2714 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution system and functional household tap connection for Bagrakote Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. |  | Junior Engineer | ORD/000378/2021-2022 | 351/JD | 03/02/2022 | 1305 | M/S GARGO TRADERS | 184.25 | 48.31 | 60
2715 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK FOR BAGRAKOTE T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000398/2021-2022 | 852/RWS | 03/12/2021 | 15 | G. TECH INDIA | 2.03 | 1.63 | 1
2716 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House ( 3.60M X 2.40M ) Size with sanitary & plumbing arrangement including Boundary wall, drain and pathway for 3rd Tubewell site of Bagrakote T.G. Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000433/2023-2024 | 1674/JD | 24/11/2023 | 45 | KAPIL MANI BRAHMAN | 11.66 | 9.48 | 100
2717 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. .(H/W Site) .(4th Call) |  | Junior Engineer | ORD/000438/2023-2024 | 1275/RWS | 24/11/2023 | 14 | RANJEET SINGH BENIWAL | 1.37 | 0 | 100
2718 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of rig approach road for Bagrakote T.G Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. .(2nd Site) .(4th Call) |  | Junior Engineer | ORD/000439/2023-2024 | 1274/RWS | 24/11/2023 | 14 | RANJEET SINGH BENIWAL | 0.8 | 0 | 100
2719 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 400 CuM Capacity R.C.C. Over Head Reservoir (OHR) of 20 Mtr Staging Height at Bagrakote Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000590/2023-2024 | 2410/JD | 19/02/2024 | 180 | D.C RAKSHIT AND SONS INDIA PRIVATE LTD. | 106.62 | 0 | 0
2720 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000001/2021-2022 | 1940/JD | 02/12/2021 | 0 | Resource Division | 12.32 | 0 | 0
2721 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000028/2023-2024 | 172/JD | 28/04/2023 | 0 | Resource Division | 82.59 | 0 | 0
2722 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000208/2023-2024 | 2068/JD | 10/01/2024 | 0 | Resource Division | 14.15 | 0 | 0
2723 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 4003266408, Reference ID : 403105530] |  | Junior Engineer | BILL/01269/2023-2024 | BP/23-24/150 | 05/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2724 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. III, under ODLABARI CCC, [APPLICATION NO. 100000093885, Reference ID : 860285545] |  | Junior Engineer | BILL/01270/2023-2024 | BP/23-24/151 | 05/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.98 | 0 | 0
2725 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000093777, Reference ID : 860285647] |  | Junior Engineer | BILL/01272/2023-2024 | 23-24/152&161 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0
2726 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266397, Reference ID : 403105521] |  | Junior Engineer | BILL/01273/2023-2024 | 23-24/152&161 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
2727 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BAGRAKOTE TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093883, Reference ID : 860285543] |  | Junior Engineer | BILL/01274/2023-2024 | 23-24/152&161 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.39 | 0 | 0
2728 | Jalpaiguri Division | Jalpaiguri Division | Supply of Different stationary for office under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | BILL/00119/2024-2025 | BP-2024-25-84 | 17/05/2024 | 0 | JALPAIGURI WHOLESALE CONSUMER'S CO-OPERATIVE SOCIETY LTD. | 0.85 | 0 | 0
2729 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No WB 71 B 8742 for the Month of July 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00594/2024-2025 | BP-2024-25-341 | 30/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
2730 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00658/2024-2025 | BP-2024-25-368 | 13/09/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
2731 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00857/2024-2025 | BP-2024-25-496 | 07/10/2024 | 0 | FILL & SMILE | 0.22 | 0 | 0
2732 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 8742 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00986/2024-2025 | BP-2024-25-548 | 17/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0
2733 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00996/2024-2025 | BP-2024-25-552 | 17/12/2024 | 0 | FILL & SMILE | 0.09 | 0 | 0
2734 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00999/2024-2025 | BP-2024-25-550 | 17/12/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
2735 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 B 1578 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/01000/2024-2025 | BP-2024-25-551 | 17/12/2024 | 0 | FILL & SMILE | 0.13 | 0 | 0
2736 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Executive Engineer, Jalpaiguri Division, P.H.E. Dte.(For the period from01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000030/2025-2026 | 817/JD | 30/04/2025 | 61 | BISWANATH GHOSH | 0.8 | 0 | 0
2737 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000031/2025-2026 | 818/JD | 30/04/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
2738 | Jalpaiguri Division | Jalpaiguri Division | Continuation for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.07.2024 to 13.01.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000072/2024-2025 | 649/JD | 11/07/2024 | 184 | RAKESH SARKAR | 0.88 | 0.97 | 0
2739 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (one) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. For inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/08/2024 to 09/02/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000077/2024-2025 | 963/JD | 09/08/2024 | 184 | RABINDRA NATH DUTTA | 0.88 | 0.79 | 0
2740 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Supply of 1 (One) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit) (w.e.f. 01.06.2025 to 30.11.2025)." | Assistant Engineer,HQ | Junior Engineer | ORD/000116/2025-2026 | 983/JD | 26/05/2025 | 184 | RUPA PRASAD | 0.88 | 0 | 0
2741 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" | Assistant Engineer,HQ | Junior Engineer | ORD/000120/2025-2026 | 1496/JD | 30/06/2025 | 31 | BISWANATH GHOSH | 0.4 | 0 | 0
2742 | Jalpaiguri Division | Jalpaiguri Division | Thorough repair and overhauling of the IEP reparing Pump House and other ancillary work at Dabgram Central zone at Dabgram -II G.P. under Dabgram piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000146/2023-2024 | 795/JD | 24/07/2023 | 861 | NARENDRA KUMAR | 6.8 | 0 | 0
2743 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings works including Functional House Hold Tap connection under JJM for Dabgram Water Supply Scheme ( Central Zone ) under Jalpaiguri Division , P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000147/2023-2024 | 796/JD | 24/07/2023 | 21 | NARENDRA KUMAR | 36.22 | 27.87 | 100
2744 | Jalpaiguri Division | Jalpaiguri Division | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/08/2025 to 30/09/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000151/2025-2026 | 1732/JD | 31/07/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
2745 | Jalpaiguri Division | Jalpaiguri Division | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000199/2025-2026 | 1998/JD | 25/09/2025 | 61 | PRADIP SAHA | 0.8 | 0 | 0
2746 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Dabgram PWSS (Central Zone) i.e. TW, Pump Houses, Water Distribution Network, RISING MAIN, FHTC etc. i.c.w. Jal Jeevan Mission at Block, Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000248/2023-2024 | 936/JD | 08/08/2023 | 779 | MAA MANASA VYAPAAR | 708.57 | 69.05 | 43
2747 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Dabgram PWSS (North Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000395/2023-2024 | 1552/JD | 01/11/2023 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 414.28 | 0 | 0
2748 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Dabgram PWSS (South Zone) i.e, TW, Pump Houses, Water Distribution Network, Rising main, FHTC etc. i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000446/2023-2024 | 1708/JD | 04/12/2023 | 759 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 526.38 | 138.18 | 45
2749 | Jalpaiguri Division | Jalpaiguri Division | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under Rajganj, Nagrakata & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000472/2025-2026 | 2428/JD | 25/11/2025 | 30 | PRADIP SAHA | 0.4 | 0 | 0
2750 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of "Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Superintending Engineer, NBC-I, P.H.E. Dte. for the use of the Deputy Superintending Engineer, NBC-I, P.H.E. Dte. (with valid Taxi permit)". (w.e.f. 01.12.2024 to 31.05.2025)". | Assistant Engineer,HQ | Junior Engineer | ORD/000516/2024-2025 | 2201/JD | 30/11/2024 | 182 | RUPA PRASAD | 0.88 | 1.77 | 0
2751 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 14.01.2025 to 28.02.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000553/2024-2025 | 04/HQ/JD | 13/01/2025 | 46 | RAKESH SARKAR | 0.23 | 0.23 | 0
2752 | Jalpaiguri Division | Jalpaiguri Division | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 100
2753 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of The Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi Permit). (Vehicle No.-WB71B-8742) (From 01.03.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000686/2024-2025 | 70/HQ/JD | 28/02/2025 | 31 | RAKESH SARKAR | 0.15 | 0.28 | 0
2754 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 10/02/2025 to 31/03/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000688/2024-2025 | 41/HQ/JD | 09/02/2025 | 50 | RABINDRA NATH DUTTA | 0.25 | 0 | 0
2755 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. monthly hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. | Assistant Engineer,HQ | Junior Engineer | ORD/000695/2024-2025 | 212/JD | 29/01/2025 | 181 | SOUMEN GHOSH | 0.88 | 0.44 | 0
2756 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for the work of hiring of 1 (one) number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver, in good condition under the Assistant Engineer (HQ), Jalpaiguri Division, P.H.E. Dte. for inspection of different PWSS under AE(HQ). (Vehicle No. WB-71B-1578) (for the period of 01/04/2025 to 30/04/2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000786/2024-2025 | 107-HQ/JD | 28/03/2025 | 31 | RABINDRA NATH DUTTA | 0.15 | 0 | 0
2757 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000047/2023-2024 | 1104/JD | 24/08/2023 | 0 | Resource Division | 184.96 | 0 | 0
2758 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000116/2023-2024 | 1827/JD | 14/12/2023 | 0 | Resource Division | 121.48 | 0 | 0
2759 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DABGRAM CENTRAL ZONE, T/W-VII, under SUBHASPALLY CCC APPLICATION NO. 4003412903 Reference ID : 403221491 | Assistant Engineer,HQ | Junior Engineer | BILL/00335/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.6 | 0 | 0
2760 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DABGRAM SOUTH ZONE, T/W-VI, under SUBHASPALLY CCC APPLICATION NO. 4003412817 Reference ID : 403221494 | Assistant Engineer,HQ | Junior Engineer | BILL/00336/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.57 | 0 | 0
2761 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DABGRAM CENTRAL ZONE, T/W-VI, under SUBHASPALLY CCC APPLICATION NO. 4003412861 Reference ID : 403221492 | Assistant Engineer,HQ | Junior Engineer | BILL/00337/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.25 | 0 | 0
2762 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DABGRAM SOUTH ZONE, T/W-IV, under SUBHASPALLY CCC APPLICATION NO. 4003412749 Reference ID : 403221493 | Assistant Engineer,HQ | Junior Engineer | BILL/00338/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.23 | 0 | 0
2763 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for DABGRAM SOUTH ZONE , T/W-V , Bhoot Para, Thakur Nagar, Behind GC Tiles under SUBHASPALLY CCC APPLICATION NO. 4003511149 , Reference ID : 403289730 | Assistant Engineer,HQ | Junior Engineer | BILL/01429/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.61 | 0 | 0
2764 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DABGRAM-II (CENTRAL ZONE,SOUTH ZONE,NORTH ZONE) PWSS, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000713/2023-2024 | 1513/NMD | 24/08/2023 | 930 | ALPHA ENTERPRISE | 143.91 | 72.63 | 60
2765 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of NAKHATI T.G. Area piped Water Supply Scheme (Phase-II) at Matiali Block under Jalpaiguri Division, PHE Dte |  | Junior Engineer | ORD/000163/2020-2021 | 1118/JD | 02/11/2020 | 60 | R.S CONSTRUCTION | 38.19 | 20.56 | 0
2766 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | fhtc nakhati |  | Junior Engineer | VCH/000351/2021-2022 |  | 05/10/2021 | 0 | R.S CONSTRUCTION | 10 | 0 | 0
2767 | Jalpaiguri Division |  | Providing Functional Household Tap Connection in connection with Jal Swapna/ JJM with minor retrofitting works under Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-V) |  |  | ORD/000093/2022-2023 | 1292/JD | 14/06/2022 | 15 | ASIT PAUL | 1.69 | 1.72 | 0
2768 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-II) |  |  | ORD/000099/2021-2022 | 1338/JD | 23/08/2021 | 30 | ASIT PAUL | 30.22 | 44.3 | 1
2769 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara/Jal Sapna under the command area of Chauhaddi piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. Phase-III |  |  | ORD/000105/2021-2022 | 1256/JD | 10/08/2021 | 15 | HARIPADA BANERJEE | 4.81 | 0 | 1
2770 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Chauhaddi Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase- IV) |  |  | ORD/000111/2021-2022 | 1405/JD | 03/09/2021 | 30 | RABINDRANATH DUTTA | 23.6 | 19.54 | 1
2771 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of CHAUHADDI piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  |  | ORD/000311/2020-2021 | 289/JD | 23/02/2021 | 30 | HARIPADA BANERJEE | 24.4 | 0 | 1
2772 | Jalpaiguri Division |  | fhtc chauhaddi |  |  | VCH/000344/2021-2022 |  | 06/10/2021 | 0 | RABINDRANATH DUTTA | 9.77 | 0 | 0
2773 | Jalpaiguri Division |  | fhtc chauhaddi |  |  | VCH/000345/2021-2022 |  | 05/10/2021 | 0 | ASIT PAUL | 22.15 | 0 | 0
2774 | Jalpaiguri Division |  | HDPE UTTAR ANGRAVASA PWSS |  |  | VCH/001328/2021-2022 | BP-2021-22-461 | 27/03/2022 | 0 | ROY & SARKAR CONSTRUCTION | 4.89 | 0 | 0
2775 | Jalpaiguri Division |  | FHTC GORALBARI |  |  | VCH/001349/2021-2022 | BP-2021-22-454 | 27/03/2022 | 0 | SAPTASWA SARKAR | 2.69 | 0 | 0
2776 | Jalpaiguri Division |  | FHTC KAMARVITA VILLAGE RAJGANJ BLOCK |  |  | VCH/001382/2021-2022 | BP-2021-22-444 | 26/03/2022 | 0 | BARUN KUMAR DUTTA | 3.63 | 0 | 0
2777 | Jalpaiguri Division |  | FHTC GORALBARI ZONE - I |  |  | VCH/001419/2021-2022 | BP-2021-22-453 | 27/03/2022 | 0 | SAHA CONSTRUCTION | 3.49 | 0 | 0
2778 | Jalpaiguri Division |  | RETRO FITTING WOR FOR GORALBARI ZONE -I |  |  | VCH/001427/2021-2022 | BP-2021-22-455 | 27/03/2022 | 0 | SAPTASWA SARKAR | 3.67 | 0 | 0
2779 | Jalpaiguri Division | Northern Mechanical Division | fuel charges | Assistant Engineer , Head Quarters , NMD | Junior Engineer | BILL/00253/2022-2023 | BP-2022-23-439 | 06/02/2023 | 0 | FILL & SMILE | 0.29 | 0 | 0
2780 | Jalpaiguri Division | Northern Mechanical Division | Rig approach for Installation of tube well at Ghasmari Piped water supply Scheme head works site & 2nd site under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000120/2022-2023 | 97/JSSD | 22/07/2022 | 30 | ALICK DUTTA | 1.22 | 1.22 | 0
2781 | Jalpaiguri Division | Northern Mechanical Division | Construction of 150 CUM Capacity R.C.C. Elevated Reservoir, 20 Mtrs staging Height including pump house (5.4x3.6) size, Boundary wall and Drain for GHASMARI Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000127/2023-2024 | 708/JD | 13/07/2023 | 612 | M/S R.N. TRADERS | 76.58 | 20.58 | 85
2782 | Jalpaiguri Division | Northern Mechanical Division | Installation of R.B.T fixing in boundary wall and other allied works at 2nd site for Ghasmari TG Area Piped Water Supply Scheme under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000259/2022-2023 | 183/JSSD | 29/08/2022 | 30 | PRITAM DUTTA | 1.78 | 1.77 | 100
2783 | Jalpaiguri Division | Northern Mechanical Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000303/2022-2023 | 2192/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 2.97 | 2.97 | 0
2784 | Jalpaiguri Division | Northern Mechanical Division | Laying distribution system with Rising Main Connection and Providing Functional Household Tap Connection (FHTC) in connection with Jal Swapna for Ghasmari Area Piped water supply Scheme under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000346/2021-2022 | 208/JD | 24/01/2022 | 1123 | M/S R.N. TRADERS | 118.35 | 20.51 | 100
2785 | Jalpaiguri Division | Northern Mechanical Division | Construction of Boundary wall with gate drain and pathway for 2nd tube well site of Ghasmari P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000644/2021-2022 | 1061/JSSD | 24/01/2022 | 20 | PRITAM DUTTA | 3.76 | 3.78 | 0
2786 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60m x 2.40m) size with sanitary and plumbing arrangement at 2nd Tube well site for Ghasmari PWSS under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000726/2021-2022 | 1071/JSSD | 25/01/2022 | 45 | ARUP SARKAR | 4.65 | 4.65 | 0
2787 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000029/2023-2024 | 173/JD | 28/04/2023 | 0 | Resource Division | 17.75 | 0 | 0
2788 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | RTOR000205/2023-2024 | 2064/JD | 10/01/2024 | 0 | Resource Division | 4.8 | 0 | 0
2789 | Jalpaiguri Division | Northern Mechanical Division | Maintainance of Jalpaiguri division office including RWS/ Sadar Sub-Division | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000557/2022-2023 | BP-2022-23-180 | 15/09/2022 | 0 | SUKUMAR KUNDU | 1.64 | 0 | 0
2790 | Jalpaiguri Division | Northern Mechanical Division | supply of fuel | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000593/2022-2023 | BP-2022-23-261 | 17/11/2022 | 0 | FILL & SMILE | 1.26 | 0 | 0
2791 | Jalpaiguri Division | Northern Mechanical Division | supply of fuel | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000594/2022-2023 | BP-2022-23-262 | 17/11/2022 | 0 | FILL & SMILE | 0.98 | 0 | 0
2792 | Jalpaiguri Division | Northern Mechanical Division | HIRE CHARGES | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000622/2022-2023 | BP-2022-23-348 | 09/12/2022 | 0 | APIKUL ALI | 0.29 | 0 | 0
2793 | Jalpaiguri Division | Northern Mechanical Division | CONST OF OHR FOR UTTAR DANGAPRA DAKSHIN SAKOAJHORA PWSS | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/001260/2021-2022 | BP-2021-22-403 | 23/03/2022 | 0 | PARESH CHANDRA GUHA | 25.96 | 0 | 0
2794 | Jalpaiguri Division | Northern Mechanical Division | CONST 250 MM CAPACITY UTTAR DANGA PARA & DAKSHIN SAKOJHORA | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/001309/2021-2022 | BP-2021-22-403 | 23/03/2022 | 0 | PARESH CHANDRA GUHA | 25.96 | 0 | 0
2795 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components for GHASMARI PWSS, TW no I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000014/2022-2023 | 282/NMD | 26/04/2022 | 30 | DEY ENTERPRISE (BALLY) | 8.67 | 7.1 | 100
2796 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components for GHASMARI PWSS, TW no II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000015/2022-2023 | 283/NMD | 26/04/2022 | 30 | M/S BHOWMICK & CO. | 8.67 | 8.67 | 100
2797 | Northern Mechanical | Northern Mechanical Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for GHASMARI W/S Scheme at T/W No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000024/2022-2023 | 266/NMD | 22/04/2022 | 21 | M/S PALIDEB ENGINEERING WORKS | 2.16 | 2.16 | 100
2798 | Northern Mechanical | Northern Mechanical Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for GHASMARI W/S Scheme at T/W No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000025/2022-2023 | 267/NMD | 22/04/2022 | 21 | GURUKRIPA ENTERPRISE | 2.16 | 2.16 | 0
2799 | Northern Mechanical | Northern Mechanical Division | Carrying out Drilling allied works for Construction of a Rig Bored Big Dia Deep Tubewell (BDTW) by deparmental Rig unit 32B-R-1302, by Odex-165 method of drilling, at Ghasmari PWSS, TW-II (2nd Site), Block - Nagrakata, Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E., Dte. | Assistant Engineer , Head Quarters , NMD | Junior Engineer | ORD/000728/2021-2022 | 356/DSD | 28/02/2022 | 15 | S.P. ENTERPRISE | 0.49 | 0 | 100
2800 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for R.O. PHE Pump House No. I & II of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 100000050449, Reference ID : 860240039] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000137/2022-2023 | BP/2022-23/19 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.82 | 0 | 0
2801 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for TW-I of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 4002921737, Reference ID : 402816203] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000138/2022-2023 | BP/2022-23/19 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.85 | 0 | 0
2802 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for TW-II of Ghasmari Basty under GHASMARI W/S Scheme under NAGRAKATA CCC [APPLICATION NO. 4002921741, Reference ID : 402816204] | Assistant Engineer , Head Quarters , NMD | Junior Engineer | VCH/000139/2022-2023 | BP/2022-23/19 | 21/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.55 | 0 | 0
2803 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main at 3rd Tubewell site of Madhya Khuttimari PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000061/2023-2024 | 325/JD | 18/05/2023 | 14 | CHOWDHURY CONSTRUCTION | 4.63 | 3.34 | 10
2804 | Jalpaiguri Division | Jalpaiguri Division | Laying of higher dia. pipeline within the Command Area of Madhya Khuttimary and adjoining mouzas Piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000237/2025-2026 | 2163/JD | 30/10/2025 | 75 | BILTU DAS | 152.02 | 0 | 0
2805 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Madhya Khattimari PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000449/2021-2022 | 197/JD | 21/01/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 7.1 | 1
2806 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Madhya Khattiamri P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000501/2021-2022 | 96/JD | 10/01/2022 | 60 | ALICK DUTTA | 4.65 | 4.75 | 0
2807 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for Rejuvenation of Madhya Khutttimari, T/W III, under DHUPGURI CCC, [APPLICATION NO. 4003123382, Reference ID : 402998142] | Assistant Engineer,HQ | Junior Engineer | BILL/00027/2023-2024 | BP/23-24/09 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
2808 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for Rejuvenation of Madhya Khutttimari, T/W III, under DHUPGURI CCC, [APPLICATION NO. 100000076479, Reference ID : 860267199] | Assistant Engineer,HQ | Junior Engineer | BILL/00028/2023-2024 | BP/23-24/09 | 16/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.22 | 0 | 0
2809 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF MADHYA KHUTTIMARI PWSS, TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000892/2022-2023 | 391/NMD | 29/03/2023 | 30 | M/S DILIP MITRA | 11.07 | 11.07 | 100
2810 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting works in connection with Rejuvination of Chauhaddi PWSS for FHTC work of Jal Swapna at Dhupguri Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000015/2022-2023 | 971/JD | 20/04/2022 | 90 | SCEC BOENTER KDAS JOINT VENTURE | 168.05 | 127.33 | 1
2811 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pathway inside the Head Works Site of Chauhaddi and adjoining mouzas .P.W.S.S. under Jalpaiguri Division,P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000161/2022-2023 | 1468/JD | 25/07/2022 | 21 | HARIPADA BANERJEE | 3.53 | 3.53 | 100
2812 | Jalpaiguri Division | Jalpaiguri Division | Repairing of choakaged and damaged branch lines due to road development and widening of near by area of Garialtari within the command area of Chauhaddi and adjoining mouzas Piped Water Supply Scheme under Jalpaiguri Division. P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000163/2022-2023 | 1435/JD | 18/07/2022 | 21 | HARIPADA BANERJEE | 4.84 | 4.84 | 0
2813 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB76-9978) | Assistant Engineer,HQ | Junior Engineer | ORD/000359/2022-2023 | 1415/JD | 14/07/2022 | 365 | APIKUL ALI | 1.76 | 0.34 | 0
2814 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (Phase - VI) in connection with Jal Jeevan Mission for Rejuvenation of Chouhaddi and adjoining Mouzas P.W.S.S under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000431/2022-2023 | 626/JD | 13/03/2023 | 30 | SOMNATH ROY | 17.57 | 0 | 0
2815 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 1 No. 250mm x 150mm x 135 m deep Rig Bored tube well by Reverse Rotary method of drilling for Rejuvenation of Chauhaddi Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000476/2021-2022 | 348/JD | 03/02/2022 | 30 | J.M. CONSTRUCTION | 7.85 | 0 | 1
2816 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Chauhaddi P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000507/2021-2022 | 106/JD | 11/01/2022 | 60 | J.M. CONSTRUCTION | 4.65 | 4.78 | 1
2817 | Jalpaiguri Division | Jalpaiguri Division | Repairing of damaged line near Harinkhwa School with other ancillary repairing work related to the Laying Distribution System at Chauhaddi P.W.S.S. under Jalpaiguri Division, | Assistant Engineer,HQ | Junior Engineer | ORD/000580/2021-2022 | 166/JD | 20/01/2022 | 21 | HARIPADA BANERJEE | 3.68 | 3.63 | 1
2818 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the work "Supply of 1 (one) Maxi Cab with engine capacity more than 2000 C.C. on hire basis including driver for Assistant Engineer, Jalpaiguri Sadar Division, P.H.E. Dte. Dist. Jalpaiguri (with valid Taxi permit) from 01.01.2023 to 31.03.2023 | Assistant Engineer,HQ | Junior Engineer | ORD/000597/2022-2023 | 348/JSSD | 27/12/2022 | 90 | TANMOY CHOUDHURY | 0.45 | 0.39 | 0
2819 | Jalpaiguri Division | Jalpaiguri Division | FUEL BILL | Assistant Engineer,HQ | Junior Engineer | VCH/000281/2022-2023 | BP-2022-23-137 | 25/08/2022 | 0 | FILL & SMILE | 0.74 | 0 | 0
2820 | Jalpaiguri Division | Jalpaiguri Division | BOUNDARY WALL 2ND T/WELL SITE RED BANK T.G | Assistant Engineer,HQ | Junior Engineer | VCH/001308/2021-2022 | BP-2021-22- 459 | 27/03/2022 | 0 | DEEP CONSTRUCTION | 3.58 | 0 | 0
2821 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for CARITALTARI,CHUHADDI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018642, Reference ID : 402927988] | Assistant Engineer,HQ | Junior Engineer | BILL/00032/2022-2023 | BP/22-23/129 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
2822 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for CARITALTARI,CHUHADDI W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO.100000066801, Reference ID : 860257021] | Assistant Engineer,HQ | Junior Engineer | BILL/00033/2022-2023 | BP/22-23/129 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.81 | 0 | 0
2823 | Northern Mechanical | Jalpaiguri Division | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0091/2023-2024 ,Dt - 29/02/24 | Assistant Engineer,HQ | Junior Engineer | BILL/01052/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.41 | 0 | 0
2824 | Northern Mechanical | Jalpaiguri Division | Fuel,lubricant charges for Government Inspection vehicle under NMD ,PHE,DTE Invoice No :0092/2023-2024 ,Dt - 31/03/24 | Assistant Engineer,HQ | Junior Engineer | BILL/01053/2024-2025 | BP/24-25/199 | 12/09/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.34 | 0 | 0
2825 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for CHAUHADDI (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000581/2022-2023 | 1122/NMD | 12/09/2022 | 30 | SUMON ELECTRICAL | 8.14 | 8.11 | 100
2826 | Northern Mechanical | Jalpaiguri Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under CHAUHADDI (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000781/2022-2023 | 102/NMD | 03/02/2023 | 21 | SUMON ELECTRICAL | 2.94 | 2.93 | 100
2827 | Jalpaiguri Division | Northern Mechanical Division | Laying Rising Main at 3rd Tube Well site of Khalaigram PWSS in connection with JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000023/2023-2024 | 123/JD | 28/04/2023 | 14 | PRIYABRATA KARMAKAR | 8.33 | 6.11 | 80
2828 | Jalpaiguri Division | Northern Mechanical Division | Construction of Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement at 3rd tube well site for Khalaigram P.W.S.S. under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000222/2022-2023 | 1851/JD | 16/09/2022 | 45 | MANAB BAKSHI | 4.65 | 4.72 | 0
2829 | Jalpaiguri Division | Northern Mechanical Division | Sinking of 250 mm x 150mm dia tube well by Reverse Rotary method of drilling for Rejuvenation of Khalaigram PWSS at Dhupguri Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000451/2021-2022 | 199/JD | 21/01/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 8.02 | 7.05 | 1
2830 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for KHALAIGRAM,DHUBGURU W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO. 4003018666, Reference ID : 402928492] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/00034/2022-2023 | BP/22-23/130 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.38 | 0 | 0
2831 | Northern Mechanical | Northern Mechanical Division | Infrastructure Cost for KHALAIGRAM,DHUBGURU W/S Scheme, T/W No. III, under DHUPGURI CCC, [APPLICATION NO.100000066803, Reference ID : 860257023] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/00035/2022-2023 | BP/22-23/130 | 20/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.24 | 0 | 0
2832 | Northern Mechanical | Northern Mechanical Division | ADDITIONAL WORK Infrastructure Cost for KHALAIGRAM, T/W III, under DHUPGURI CCC [APPLICATION NO. 100000090647, Reference ID : 860281557] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01118/2023-2024 | BP/23-24/124 | 10/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.64 | 0 | 0
2833 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components for KHALAIGRAM (REJU) PWSS, at TW no. III, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000580/2022-2023 | 1123/NMD | 12/09/2022 | 30 | S.P. ENTERPRISE (KOLKATA) | 8.13 | 8.13 | 100
2834 | Northern Mechanical | Northern Mechanical Division | Supply, delivery and installation of Servo Motor operated Copper wound line voltage corrector under KHALAIGRAM (Reju) WS Scheme at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000667/2022-2023 | 1400/NMD | 09/12/2022 | 30 | S.D. CONCERN | 2.91 | 2.91 | 100
2835 | Northern Mechanical | Northern Mechanical Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
2836 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | PAYMENT FOR FUEL BILL |  | Junior Engineer | BILL/00360/2023-2024 | BP-2023-24-315 | 18/08/2023 | 0 | FILL & SMILE | 3.34 | 0 | 0
2837 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection for Jaldhara/Jal Sapna under the command area of Jabramali piped Water Supply Scheme at MATIALI Block under Jalpaiguri Division, PHE Dte. (Part-E) |  | Junior Engineer | ORD/000186/2022-2023 | 565/RWS | 01/09/2022 | 30 | B.M CONSTRUCTION | 2.65 | 2.58 | 0
2838 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall Path way, block drain for 2 nd site of kumlai T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Die. |  | Junior Engineer | ORD/000282/2022-2023 | 647/RWS | 21/10/2022 | 20 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.83 | 4.83 | 1
2839 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Supply of Fuel & Other Consumable items Bhagatpur Tea Garden, Ghoshmari Tea Garden, Kumlai Tea Graden, Rejuvenetion Mohit Nagar PWSS. |  | Junior Engineer | ORD/000304/2022-2023 | 2193/JD | 11/11/2022 | 30 | M/S MILLENNIUM FUEL CENTRE | 3.42 | 3.42 | 0
2840 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Model estimate for construction of pump house ( 3.60 m X 2.40 m) Size With Sanitary & Plumbing Arrangement at 2nd tube well site for Kumlai T.G . W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000324/2021-2022 | 875/RWS | 08/12/2021 | 30 | BREATHING SPACE DESIGN & VAASTA CONSULTANTS | 4.65 | 4.65 | 1
2841 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jalsapna under the command area of Mohit Nagar W/S/S under Jalpaiguri Division , P.H.E. Dte ( part ¿ F ) |  | Junior Engineer | ORD/000325/2021-2022 | 879/RWS | 10/12/2021 | 10 | M/S DEY & ROY CHOUDHURY | 1.28 | 0.13 | 1
2842 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Rising main connection for Kumlai TG PWSS including supply of Sluice valve/ Jeffy coupling ,C.I.D.F. Specials etc. under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000334/2022-2023 | 27/JD | 05/01/2023 | 21 | ADITRI ENTERPRISE | 4.81 | 3.6 | 100
2843 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution system and functional household tap connection for Kumlai Tea Garden piped Water Supply Scheme Block- Mal District ¿ Jalpaiguri. |  | Junior Engineer | ORD/000340/2021-2022 | 192/JD | 21/01/2022 | 60 | R.S CONSTRUCTION | 116.87 | 92.64 | 70
2844 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 150 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing RCC including pipe connection and cost of pipes, specials, Construction of Pump House (5.4m x 3.60 m) & Boundary wall at H/W site Kumlai Tea Garden Area Piped Water Supply Scheme, Block- Mal, Dist. Jalpaiguri. Under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000354/2021-2022 | 252/JD | 31/01/2022 | 150 | SANDIP BANIK | 64.43 | 64.71 | 1
2845 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK FOR KUMLAI T.G. PIPED WATER SUPPLY SCHEME BLOCK : MAL DISTRICT : JALPAIGURI |  | Junior Engineer | ORD/000401/2021-2022 | 853/RWS | 03/12/2021 | 15 | G. TECH INDIA | 2.03 | 0 | 0
2846 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000030/2023-2024 | 174/JD | 28/04/2023 | 0 | Resource Division | 21.11 | 0 | 0
2847 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000207/2023-2024 | 2066/JD | 10/01/2024 | 0 | Resource Division | 6.1 | 0 | 0
2848 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RENOVATION B/W H/W SOUTH BERUBARI WSS |  | Junior Engineer | VCH/001377/2021-2022 | BP-2021-22-540 | 31/03/2022 | 0 | A.P CONSTRUCTION | 19.8 | 0 | 0
2849 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under KUMLAI T.G W/S Scheme, at TW No. I in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000063/2022-2023 | 438/NMD | 14/06/2022 | 21 | TAPAN BISWAS | 2.39 | 2.39 | 0
2850 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under KUMLAI T.G W/S Scheme, at TW No. II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000064/2022-2023 | 439/NMD | 14/06/2022 | 21 | M/S B.ENTERPRISE | 2.37 | 2.37 | 0
2851 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for KUMLAI T.G W/S Scheme, TW No. II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000078/2022-2023 | 536/NMD | 08/07/2022 | 30 | RAJEEV RANJAN OJHA | 9.62 | 8.76 | 70
2852 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for KUMLAI T.G W/S Scheme, TW No. I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000112/2022-2023 | 861/NMD | 18/07/2022 | 30 | PRATIK ROY | 9.2 | 9.2 | 100
2853 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Carrying out Development works and Yield Test for a BDTW at Kumlai TG W/S Scheme, TW-I & II, Bhagatpur TG PWSS (Zone-II), TW-I & II, Ghasmari PWSS, TW-I & II , Dist- Jalpaiguri, under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000820/2021-2022 | 328/DSD | 07/02/2022 | 21 | M/S ANJALI ENTERPRISE | 0.63 | 0.63 | 100
2854 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for T/W No. I of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 100000050872, Reference ID : 860240742] |  | Junior Engineer | VCH/000140/2022-2023 | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.59 | 0 | 0
2855 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for T/W No. II of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 100000050873, Reference ID : 860240743] |  | Junior Engineer | VCH/000141/2022-2023 | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.05 | 0 | 0
2856 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. I of KUMLAI T.G. W/S Scheme under ODLABARI CCC [APPLICATION NO. 4002922582, Reference ID : 402818172] |  | Junior Engineer | VCH/000142/2022-2023 | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.32 | 0 | 0
2857 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for T/W No. II of KUMLAI T.G. W/S Scheme under ODLABARI CCI [APPLICATION NO. 4002922585, Reference ID : 402817968] |  | Junior Engineer | VCH/000143/2022-2023 | BP/2022-23/13 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.88 | 0 | 0
2858 | Jalpaiguri Division | Jalpaiguri Division | SUPPLY OF FUEL | Assistant Engineer,HQ | Junior Engineer | BILL/00398/2022-2023 | BP-2022-23-522 | 15/03/2023 | 0 | FILL & SMILE | 0.33 | 0 | 0
2859 | Jalpaiguri Division | Jalpaiguri Division | SUPPLY OF FUEL (DIESEL) FOR VEHICLES UNDER JALPAIGURI DIVISION PHE DTE. FOR THE MONTH OF DECEMBER 2023 AND JANUARY 2024 | Assistant Engineer,HQ | Junior Engineer | BILL/01247/2023-2024 | BP-2023-24-665 | 22/02/2024 | 0 | FILL & SMILE | 1.9 | 0 | 0
2860 | Jalpaiguri Division | Jalpaiguri Division | Supply of Sluice valve C.I. Specials at Binnaguri for laying of DI line from OHR to UPVC Pipe line in connection with Augmentation of Binnaguri W/S Scheme under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000036/2023-2024 | 389/RWS | 25/04/2023 | 14 | B.M CONSTRUCTION | 3.31 | 3.31 | 0
2861 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall with gate, drain for 3rd Tube well site of Binnaguri Piped water supply scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000101/2023-2024 | 444/JD. | 08/06/2023 | 21 | ETHERIA EDIFICE (OPC) PVT. LTD. | 5.29 | 0 | 0
2862 | Jalpaiguri Division | Jalpaiguri Division | Extra Laying of Water Distribution System, construction of valve chamber and other ancillary works for Augmentation of Binnaguri PWSS at Binnaguri at Block - Rajganj under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000136/2023-2024 | 706/JD | 13/07/2023 | 21 | M/S KARMAKAR CONSTRUCTION | 29.75 | 25.32 | 80
2863 | Jalpaiguri Division | Jalpaiguri Division | Repairing of OHR and repairing valve chamber & other ancillary works Binnaguri Head Work site under Binnaguri Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000316/2023-2024 | 1228/JD | 11/09/2023 | 21 | KANAI LAL SEN | 6.87 | 6.54 | 100
2864 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant (Capacity 20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at 3 rd Tubewell site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT - JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/000348/2022-2023 | 136/JD | 17/01/2023 | 45 | SUBIR GHOSH | 14.72 | 11.2 | 0
2865 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) with sanitary & plumbing arrangement at 3rd Tube well site for Binnaguri (Fulbari) Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000350/2022-2023 | 133/JD | 17/01/2023 | 45 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 4.65 | 100
2866 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant (capacity-50m3/hr.) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain for augmentation at head work site of BINNAGURI piped water supply scheme under JALPAIGURI Division PHE Dte . BLOCK - RAJGANJ DISTRICT JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000353/2022-2023 | 165/JD | 19/01/2023 | 45 | KANAI LAL SEN | 19.8 | 19.46 | 100
2867 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Binnaguri Piped water Supply Scheme at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000453/2021-2022 | 332/JD | 02/02/2022 | 120 | M/S NANDY ENTERPRISE | 458.51 | 274.45 | 1
2868 | Jalpaiguri Division | Jalpaiguri Division | Laying of Water Distribution System and other ancillary works for Augmentation of Binnaguri PWSS at Block-Rajganj under Jalpaiguri Division, P.H.E. Dte. (Part-A) | Assistant Engineer,HQ | Junior Engineer | ORD/000482/2024-2025 | 2408./JD | 20/12/2024 | 224 | M/S KARMAKAR CONSTRUCTION | 40.9 | 0 | 100
2869 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission under the command area of Binnaguri (Fulbari-II) for Augmentation of Binnaguri Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000532/2023-2024 | 1852/JD | 15/12/2023 | 45 | SUNIL ROY | 17.04 | 0 | 0
2870 | Jalpaiguri Division | Jalpaiguri Division | Repairing of pump house, boundary wall, land development and construction of drain, repairing valve chamber & other ancillary works at Augmentation of Binnaguri head works site under Binnaguri piped water supply scheme under Jalpaiguri Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000543/2023-2024 | 1934/JD | 02/01/2024 | 21 | GOPRO CONSTRUCTION | 4.2 | 4.12 | 100
2871 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000029/2024-2025 | 2102/JD | 25/11/2024 | 0 | Resource Division | 101.9 | 0 | 0
2872 | Central Drilling | Jalpaiguri Division | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BINNAGURI (W/S SCHEME) , RAJGANJ BLOCK, UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000112/2022-2023 | 395/CMSD-II (D) | 01/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.53 | 4.13 | 0
2873 | Central Drilling | Jalpaiguri Division | PROVIDING DRILLING CREWS INCLUDING OTHERS MATERIALS & WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 100 MTR DEPTH) BY DEPARTMENTAL RIG MACHINE FOR AUG. OF BINNAGURI (W/S SCHEME) , RAJGANJ BLOCK UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000113/2022-2023 | 394/CMSD-II (D) | 01/08/2022 | 15 | PADMA ENGINEERING & CO. | 4.3 | 2.82 | 0
2874 | Central Drilling | Jalpaiguri Division | PROVIDING ADDITIONAL BENTONITE & OTHER ADDITIONAL WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF BINNAGURI W/S SCH UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000144/2022-2023 | 408/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0.96 | 0
2875 | Central Drilling | Jalpaiguri Division | ADDITIONAL WORK FOR DRILLING BOLDER/SAND STONE ZONE AT AUG. OF BINNAGURI W/S SCH, UNDER JALPAIGURI DISTRICT, CDD, PHE DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000145/2022-2023 | 407/CMSD-II | 12/08/2022 | 10 | PADMA ENGINEERING & CO. | 0.97 | 0.97 | 0
2876 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 20KVA Servo Motor operated Copper wound line voltage corrector under Binnaguri (Rajganj Block) W/S Scheme at T/W No. I & II in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000005/2022-2023 | 208/NMD | 04/04/2022 | 21 | BONANZA ENTERPRISE | 4.78 | 4.78 | 0
2877 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under BINNAGURI (AUG) W/S Scheme, at TW No. III in the dist. of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000067/2022-2023 | 442/NMD | 14/06/2022 | 21 | MALAY KUMAR SAHA | 2.77 | 2.77 | 0
2878 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF BINNAGURI PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000753/2022-2023 | 53/NMD | 24/01/2023 | 30 | SUNLIT | 10.1 | 8.37 | 100
2879 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for T/W No. V of MORAGHAT TEA GARDEN NEAR HOSPITAL W/S Scheme under BANRHAT CCC [APPLICATION NO.4002888889, Reference ID : 402788875] | Assistant Engineer,HQ | Junior Engineer | VCH/000149/2022-2023 | BP/2022-23/14 | 16/06/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2880 | Jalpaiguri Division | Jalpaiguri Division | VEHICLE DRIVER | Assistant Engineer,HQ | Junior Engineer | BILL/01178/2023-2024 |  | 25/01/2024 | 0 | RAKESH SARKAR | 0.37 | 0 | 0
2881 | Jalpaiguri Division | Jalpaiguri Division | VEHICLE BILL | Assistant Engineer,HQ | Junior Engineer | BILL/01179/2023-2024 |  | 25/01/2024 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0
2882 | Jalpaiguri Division | Jalpaiguri Division | FUEL BILL | Assistant Engineer,HQ | Junior Engineer | BILL/01181/2023-2024 | BP-2023-24-631 | 06/02/2024 | 0 | FILL & SMILE | 0.82 | 0 | 0
2883 | Jalpaiguri Division | Jalpaiguri Division | Rejuvenation work for Pump houses and laying UPVC pipe line at H/W site of Augmentation of Shikarpur Piped Water Supply Scheme at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000019/2024-2025 | 519/JD | 27/06/2024 | 115 | KANAI LAL SEN | 7.02 | 6.86 | 100
2884 | Jalpaiguri Division | Jalpaiguri Division | Dismantiling old IEP, old Pump house and filling old CWR and other ancillary works at Sikarpur under Sikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000111/2023-2024 | 446/JD. | 08/06/2023 | 14 | GOUTAM DAS | 6 | 6 | 100
2885 | Jalpaiguri Division | Jalpaiguri Division | Construction of Room and other ancillary work at Belakoba primary school near H/W site for Shikarpur piped water supply schemer at Rajganj block under Jalpaiguri division PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000112/2023-2024 | 447/JD. | 08/06/2023 | 45 | DEBABRATA SARKAR | 2.94 | 2.99 | 100
2886 | Jalpaiguri Division | Jalpaiguri Division | Continuation Order for the Work of "Providing Contractual Monthly Salary basis Agency personnel for day to day work in Estimate Section, under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 01.07.2025 to 29.11.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000142/2025-2026 | 1495/JD | 30/06/2025 | 152 | SOMNATH ROY | 0.94 | 0 | 0
2887 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall with gate, drain, land development, pathway including interconnection work and laying pipe line at Augmentation of Shikarpur PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000156/2024-2025 | 1530/JD | 01/10/2024 | 76 | GOUTAM DAS | 16.48 | 0 | 100
2888 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir (350 cum) at Shikarpur under Shikarpur piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000170/2022-2023 | 1411/JD | 12/07/2022 | 15 | MABCO CONSULTANT | 2.26 | 2.11 | 1
2889 | Jalpaiguri Division | Jalpaiguri Division | Thorough repair and overhauling of the Iron Elimination Plant installed at Shikarpur Water Supply Scheme, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000207/2022-2023 | 1797/JD | 14/09/2022 | 21 | KANAI LAL SEN | 3.04 | 2.89 | 1
2890 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60m x 2.40m) size with sanitary & plumbing arrangement at 3rd Tube Well site of Shikarpur PWSS i.c.w. Jal Jeevan Mission at Block - Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000373/2022-2023 | 298/JD | 10/02/2023 | 45 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 4.69 | 4.69 | 1
2891 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) for Augmentation of Shikarpur Piped Water Supply Scheme at Block- Rajganj under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000542/2023-2024 | 1933/JD | 02/01/2024 | 45 | JAYA SARKAR | 17.09 | 0 | 0
2892 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 250mm x 150mm dia tube well by Reverse Rotary method of drilling for 3rd Tube well for Augmentation of Shikarpur PWSS at Rajganj Block under PHE Dte. Jalpaiguri Division. | Assistant Engineer,HQ | Junior Engineer | ORD/000560/2021-2022 | 440/JD | 17/02/2022 | 30 | MALAY BHOWMIK | 7.23 | 7 | 1
2893 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOIUR CAPACITY 350 CUM AND 20 M STAGGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SHIKARPUR PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT:JALPAIGURI, UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000584/2021-2022 | 733/JD | 17/03/2022 | 1046 | GOUTAM DAS | 83.34 | 75.13 | 100
2894 | Jalpaiguri Division | Jalpaiguri Division | Supplying and Installation of 70 Nos. Display Board at Different Piped Water Supply Schemes in connection with JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000602/2024-2025 | 271/JD | 07/02/2025 | 15 | SAPTASWA SARKAR | 13.75 | 0 | 100
2895 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 3rd tubewell site at Shikarpur piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000619/2023-2024 | 2315/JD | 07/02/2024 | 30 | DOMOHANI YOUNG CO-OPLAB.CONT.&CONST SO. LTD | 8.28 | 7.21 | 100
2896 | Jalpaiguri Division | Jalpaiguri Division | Laying of Water Distribution System with Functional Household Tap Connection (FHTC) including construction valve chamber and other ancillary works in connection with Jal Jeevan Mission for Augumentation of Shikarpur Piped Water Supply Scheme at Block - Rajganj under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000816/2023-2024 | 2622/JD | 07/03/2024 | 600 | SCEC BOENTER AND KDAS JOINT VENTURE | 559.19 | 158.28 | 59
2897 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SHIKARPUR W/S Scheme, T/W No. III, under BELAKOBA CCC [APPLICATION NO. 4003114721 ; Reference ID : 402982646] | Assistant Engineer,HQ | Junior Engineer | BILL/00807/2022-2023 | BP/22-23/170 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2898 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for SHIKARPUR W/S Scheme, T/W No. III, under BELAKOBA CCC [APPLICATION NO.100000074416 ; Reference ID : 860265926] | Assistant Engineer,HQ | Junior Engineer | BILL/00808/2022-2023 | BP/22-23/170 | 29/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.9 | 0 | 0
2899 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF SHIKARPUR PWSS, at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000879/2022-2023 | 362/NMD | 29/03/2023 | 30 | SAIKAT SINHA | 11.07 | 11.06 | 100
2900 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 3rd site of Madhab danga Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000009/2023-2024 | 334/RWS | 10/04/2023 | 14 | M/S KARMAKAR CONSTRACTION | 2.62 | 2.62 | 1
2901 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Work of DI Pipe (Raising main), Drain,Chember,flower block & other ancillary works at 4th site of Mathab danga Water supply scheme within Jalpaiguri Division. P.H.E. Dte. |  | Junior Engineer | ORD/000038/2023-2024 | 391/RWS | 25/04/2023 | 14 | NISHITH RANJAN KARMAKAR | 2.62 | 2.62 | 100
2902 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Madhabdanga piped water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000196/2022-2023 | 1593/JD | 18/08/2022 | 45 | M/S SIBU DEY AND CO. | 14.4 | 13.76 | 100
2903 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works including Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Madhab Danga Piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. (Phase-F) |  | Junior Engineer | ORD/000243/2022-2023 | 1898/JD | 26/09/2022 | 21 | ANUP SARKAR | 6.48 | 6.23 | 0
2904 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection(FHTC) in connection for JJM under the command area of Madhab Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000394/2022-2023 | 399/JD | 24/02/2023 | 21 | M/S SIBU DEY AND CO. | 4.75 | 3.78 | 1
2905 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retro fitting works due to FHTC in connection and other ancillary works for JJM under the command area of Madhab Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000395/2022-2023 | 400/JD | 24/02/2023 | 15 | M/S SIBU DEY AND CO. | 1.64 | 1.64 | 0
2906 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Madhab Danga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000477/2021-2022 | 2210/JD | 27/12/2021 | 60 | M/S KARMAKAR CONSTRACTION | 12.24 | 12.4 | 1
2907 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Madhab Danga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000478/2021-2022 | 2211/JD | 21/12/2021 | 60 | NISHITH RANJAN KARMAKAR | 12.26 | 12.25 | 0
2908 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250 MM X 150 MM) BY DEPARTMENTAL RIG MACHINE FOR MAYNAGURI BLOCK TW-II UNDER CENTRAL DRILLING DIVISION, PHE DTE. |  | Junior Engineer | ORD/000193/2021-2022 | 781 /CDD | 08/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.42 | 8.39 | 0
2909 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR MAYNAGURI BLOCK TW-I UNDER CDD, PHE DTE. |  | Junior Engineer | ORD/000196/2021-2022 | 780/ CDD | 08/10/2021 | 30 | PADMA ENGINEERING & CO. | 10.42 | 8.2 | 0
2910 | Central Drilling | RWS Jalpaiguri Sub-Division | SINKING OF 800MM DIA SHALLOW TUBEWELL FOR REQUIREMENT OF DRILLING WATER FOR DIFFERENT CONSTRUCTION OF TUBE WELL AT MAYNAGURI BLOCK IN JALPAIGURI DISTRICT, UNDER CMSD-II (D), CDD, PHE DTE. |  | Junior Engineer | ORD/000261/2021-2022 | 575/CMSD-II | 30/11/2021 | 10 | PADMA ENGINEERING & CO. | 0.96 | 0.36 | 0
2911 | Central Drilling | RWS Jalpaiguri Sub-Division | Supply & Delivery of lubricant for drilling work at Madhabdanga PWSS, Dist-Jalpaiguri and other PWSS under CDD, PHE Dte. |  | Junior Engineer | ORD/000305/2022-2023 | 262/CMSD-I(D) | 27/06/2022 | 15 | UTTAM KUMAR CHATTERJEE | 4.47 | 4.47 | 0
2912 | Central Drilling | RWS Jalpaiguri Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCHEME (TW0II) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. |  | Junior Engineer | ORD/000393/2022-2023 | 1077/CDD | 28/10/2022 | 30 | PADMA ENGINEERING & CO. | 16.51 | 3.55 | 0
2913 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Madhabdanga Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000096/2022-2023 | 565/NMD | 14/07/2022 | 21 | R.K.ENTERPRISES | 2.16 | 2.16 | 0
2914 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Madhabdanga Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000098/2022-2023 | 566/NMD | 14/07/2022 | 21 | GEETA CONSTRUCTION | 2.16 | 2.16 | 0
2915 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHABDANGA PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000115/2022-2023 | 852/NMD | 18/07/2022 | 30 | M/S BHOWMICK & CO. | 8 | 8 | 0
2916 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for MADHABDANGA PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000116/2022-2023 | 853/NMD | 18/07/2022 | 30 | MAA ENTERPRISES | 7.99 | 7.99 | 98
2917 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Maynaguri Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000776/2024-2025 | 290/HQ/NMD | 24/01/2025 | 30 | S.P. ENTERPRISE | 2 | 0 | 0
2918 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for TW-III of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941282 ; Reference ID : 402831978] |  | Junior Engineer | VCH/000341/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2919 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for W-III of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053961 ; Reference ID : 860243611] |  | Junior Engineer | VCH/000342/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.85 | 0 | 0
2920 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for TW-IV of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941284 ; Reference ID : 402831976] |  | Junior Engineer | VCH/000343/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2921 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for TW-IV of MADHABDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053937 ; Reference ID : 860243607] |  | Junior Engineer | VCH/000344/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.4 | 0 | 0
2922 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No WB 71 A 5131 for the Month of July 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00583/2024-2025 | BP-2024-25-333 | 28/08/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2923 | Jalpaiguri Division | Jalpaiguri Division | HIRE CHARGES BILL OF VEHICLE UNDER NBC-I, PHE Dte. For the month of june to august 2023 | Assistant Engineer,HQ | Junior Engineer | BILL/00615/2023-2024 | BP-2023-24-418 | 06/10/2023 | 0 | RUPA PRASAD | 1.03 | 0 | 0
2924 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) ofVehicle No. WB 71 A 5131 for the Month of August 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00656/2024-2025 | BP-2024-25-370 | 13/09/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2925 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of September 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00853/2024-2025 | BP-2024-25-482 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
2926 | Jalpaiguri Division | Jalpaiguri Division | Supply of Fuel (Diesel) of Vehicle No. WB 71 A 5131 for the Month of October 2024. | Assistant Engineer,HQ | Junior Engineer | BILL/00940/2024-2025 | BP-2024-25-524 | 29/11/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0
2927 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOIR CAPACITY 400 CUM AND 20 M STAGING HEIGHT INCLUDING CONSTRUCTION OF PUMP HOUSE (5.40 M X 3.60M) AS PER DEPARMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE I) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ DISTRICT:JALPAIGURI UNDER JALPAIGURI DIVISION, P.H.E. DTE. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2022-2023 | 876/JD | 05/04/2022 | 180 | UMWELT ENGINEER PRIVATE LIMITED | 94.23 | 84.1 | 100
2928 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-I) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P. H. E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2023-2024 | 840/JD | 04/04/2023 | 697 | ARUP SARKAR | 10.16 | 7.98 | 50
2929 | Jalpaiguri Division | Jalpaiguri Division | Laying Rising Main from Pump Houses to Over Head Reservoir with necessity connections for Augmentation of Sannyasikata (Zone-II) Piped Water Supply Scheme i.c.w. Jal Jeevan Mission at Rajganj Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000018/2023-2024 | 62/JD | 18/04/2023 | 928 | RANJIT KARMAKAR | 31.21 | 24.05 | 100
2930 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.07.2024 to 21.01.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000033/2024-2025 | 659/JD | 12/07/2024 | 184 | MD AMIRUL ISLAM | 0.88 | 0.92 | 0
2931 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Sannyasikata Piped water Supply Scheme Zone-I at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000034/2022-2023 | 1100/JD | 12/05/2022 | 90 | UMWELT ENGINEER PRIVATE LIMITED | 540.04 | 506.81 | 100
2932 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- II at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000036/2022-2023 | 1020/JD | 26/04/2022 | 21 | NARESH SEN | 8.09 | 7.92 | 1
2933 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-I Water Supply Scheme under Jalpaiguri Division, P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000050/2022-2023 | 1194/JD | 20/05/2022 | 45 | MANAB BAKSHI | 4.65 | 0 | 0
2934 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m x 2.40 m ) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Sannyasikata Zone-ii Water Supply Scheme under Jalpaiguri Division , P.H.Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000056/2022-2023 | 1195/JD | 20/05/2022 | 45 | ETHERIA EDIFICE (OPC) PVT. LTD. | 4.65 | 4.65 | 1
2935 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system with FHTC for Augmentation of Sannyasikata Piped water Supply Scheme Zone-II at Rajganj Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000060/2022-2023 | 1228/JD | 01/06/2022 | 120 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 788.85 | 629.96 | 100
2936 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying pipe line for Sannyasikata zone II H/W Site at Sannyasikata PWSS Site piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000120/2024-2025 | 1419/JD | 20/09/2024 | 147 | PRABIR SHOME | 18.38 | 0 | 0
2937 | Jalpaiguri Division | Jalpaiguri Division | Interconnection of Iron Elimination Plant to Rising Main, and other Ancillary Works at Sannyasikata Zone-II Head Work Site at Sannyasikata PWSS Rajganj Block, under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000131/2024-2025 | 1285/JD | 03/09/2024 | 30 | RAGHU DAS | 8.11 | 7.98 | 100
2938 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-I under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000168/2022-2023 | 1414/JD | 13/07/2022 | 15 | M.K. KAYAL & ASSOCIATES | 2.26 | 2.11 | 1
2939 | Jalpaiguri Division | Jalpaiguri Division | Soil Investigation for the work of Construction of R.C.C Over head Reservoir at Sannyasikata Zone-II under Sannyasikata piped water supply scheme under Jalpaiguri water supply Division PHE,Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000169/2022-2023 | 1413/JD | 13/07/2022 | 15 | MABCO CONSULTANT | 2.26 | 2.11 | 1
2940 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-I under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000279/2023-2024 | 1020/JD | 21/08/2023 | 45 | M/S M.B. DESIGN | 33.17 | 0 | 0
2941 | Jalpaiguri Division | Jalpaiguri Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain for Augmentation at head work site of Sannyasikata PWSS Zone-II under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000332/2023-2024 | 1353/JD | 26/09/2023 | 45 | RAGHU DAS | 48.86 | 49.55 | 100
2942 | Jalpaiguri Division | Jalpaiguri Division | Providing Contractor's personnel as Field Supervisor engaged in different water supply Schemes under Jalpaiguri Division, P.H.E. Dte. (w.e.f. 10.11.2022 to 10.04.2023) | Assistant Engineer,HQ | Junior Engineer | ORD/000391/2022-2023 | 2186/JD | 10/11/2022 | 151 | SUKES BASU MAJUMDAR | 0.94 | 0.47 | 0
2943 | Jalpaiguri Division | Jalpaiguri Division | Supply of different stationary for office use under Jalpaiguri Division, P.H.E. Dte. as per Annexure- I. | Assistant Engineer,HQ | Junior Engineer | ORD/000502/2022-2023 | 357/JD | 17/02/2023 | 7 | JAGRITI PRESS | 1.71 | 1.71 | 1
2944 | Jalpaiguri Division | Jalpaiguri Division | Supply of different stationary for office use under Jalpaiguri division, P.H.E. Dte. as per annexure- I. | Assistant Engineer,HQ | Junior Engineer | ORD/000503/2022-2023 | 358/JD | 17/02/2023 | 7 | SUBRATA ART PRESS | 1.64 | 0 | 1
2945 | Jalpaiguri Division | Jalpaiguri Division | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. Dist. For the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). | Assistant Engineer,HQ | Junior Engineer | ORD/000566/2023-2024 | 2128/JD | 18/01/2024 | 182 | MD AMIRUL ISLAM | 0.88 | 0.98 | 30
2946 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 22.01.2025 to 28.02.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000595/2024-2025 | 15/HQ/JD | 20/01/2025 | 38 | MD AMIRUL ISLAM | 0.19 | 0.19 | 0
2947 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain and pathway and laying Pipe line for 2nd tubewell Site at Sannyasikata Zone- II piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000613/2023-2024 | 2312/JD | 07/02/2024 | 30 | ETHERIA EDIFICE (OPC) PVT. LTD. | 7.81 | 0 | 100
2948 | Jalpaiguri Division | Jalpaiguri Division | Continuation order for Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. for the use of the Assistant Engineer(HQ), Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (From 01.03.2025 to 31.03.2025) | Assistant Engineer,HQ | Junior Engineer | ORD/000687/2024-2025 | 71/HQ/JD | 28/02/2025 | 31 | MD AMIRUL ISLAM | 0.15 | 0 | 0
2949 | Jalpaiguri Division | Jalpaiguri Division | CONSTRUCTION OF RCC OVERHEAD RESERVOUR CAPACITY 550 CUM AND 20 M STAGING HEIGHT INCLUDING AS PER DEPERMENTAL DESIGN & DRAWING FOR AUGMENTATION OF SANNYASIKATA (ZONE- II) PIPED WATER SUPPLY SCHEME BLOCK:RAJGANJ ,DISTRICT,JALPAIGURI | Assistant Engineer,HQ | Junior Engineer | ORD/000691/2023-2024 | 2393/JD | 16/02/2024 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 113.02 | 0 | 0
2950 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate,drain and pathway and laying Pipe line for H/W Site at Sannyasikata Zone- I piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000810/2023-2024 | 2630/JD | 07/03/2024 | 294 | SADHAN KARMAKAR | 26.72 | 18.21 | 85
2951 | Jalpaiguri Division | Jalpaiguri Division | Construction of Different Component of water supply work and other ancillary work at Kalinagar Hospital More at Sannyasikata Zone-II under Sannyasikata PWSS of Rajganj Block under Jalpaiguri Division PHE, Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000828/2023-2024 | 2756/JD | 15/03/2024 | 550 | SHREE KRISHNA ENTERPRISE | 75.06 | 0 | 75
2952 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 300 mm x 200 mm dia 3rd Tubewell by Reverse Rotary method of drilling for Augmentation of Sannyasikata PWSS Zone- I at Rajganj Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000887/2021-2022 | 844/JD | 31/03/2022 | 21 | DEBASISH DEY | 8.09 | 7.77 | 1
2953 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000076/2024-2025 | 2207/JD | 01/12/2024 | 0 | Resource Division | 39.29 | 0 | 0
2954 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000103/2023-2024 | 1233/JD | 12/09/2023 | 0 | Resource Division | 41 | 0 | 0
2955 | Northern Mechanical | Jalpaiguri Division | ADDITIONAL Infrastructure Cost for SANYASHI KATA, ZONE-I,T/W III, under FULBARIHAT CCC, [APPLICATION NO. 100000091299, Reference ID : 860282879] | Assistant Engineer,HQ | Junior Engineer | BILL/01168/2023-2024 | BP/23-24/143 | 06/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.08 | 0 | 0
2956 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SANNYASIKATA W/S Scheme at T/W No. III, Zone-I in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000266/2022-2023 | 1011/NMD | 28/07/2022 | 21 | M/S CHANDRANATH MUKHERJEE | 2.18 | 2.18 | 100
2957 | Northern Mechanical | Jalpaiguri Division | Supply, delivery & installation of 25KVA Servo Motor operated Copper wound line voltage corrector under Augmentation of SANNYASIKATA W/S Scheme at T/W No. III, Zone-II in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000268/2022-2023 | 1012/NMD | 28/07/2022 | 21 | M/S RATAN KUMAR DASGUPTA AND CO. | 2.77 | 2.77 | 0
2958 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SANNYASIKATA (Z-I) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000531/2022-2023 | 1067/NMD | 29/08/2022 | 30 | DEY ENTERPRISE(MALDA) | 8.01 | 8.01 | 100
2959 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components for AUGMENTATION of SANNYASIKATA (Z-II) PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000559/2022-2023 | 1109/NMD | 07/09/2022 | 30 | MALAY KUMAR SAHA | 8.26 | 8.26 | 100
2960 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SANYASIKATA ZONE-II W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 4002970357, Reference ID :402858305] | Assistant Engineer,HQ | Junior Engineer | VCH/000981/2022-2023 | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
2961 | Northern Mechanical | Jalpaiguri Division | Installation of Infrastructure COST at SANYASIKATA ZONE-II W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 100000060680, Reference ID : 860250380] | Assistant Engineer,HQ | Junior Engineer | VCH/000982/2022-2023 | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.1 | 0 | 0
2962 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for SANYASIKATA ZONE-I W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 4002969126, Reference ID :402855384] | Assistant Engineer,HQ | Junior Engineer | VCH/000983/2022-2023 | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.66 | 0 | 0
2963 | Northern Mechanical | Jalpaiguri Division | Installation of Infrastructure COST at SANYASIKATA ZONE-I W/S SCHEME, T/W No. III, under FULBARI CCC, [APPLICATION NO. 100000060668, Reference ID : 860250378] | Assistant Engineer,HQ | Junior Engineer | VCH/000984/2022-2023 | BP/22-23/92 | 01/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.55 | 0 | 0
2964 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Mahanbhita (Zone-I and II) PWSS i.e, TW, Pump House, Water Distribution Network, OHR, Rising Main, FHTC etc under Jal Jeevan Mission at Block- Rajganj under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000066/2023-2024 | 367/JD | 26/05/2023 | 965 | MINTU CHAKRABORTY | 512 | 206.47 | 40
2965 | Jalpaiguri Division | Jalpaiguri Division | Construction of boundary wall with gate, drain, Land development and pathway including laying pipe line at Mahanbhita Zone-I (HW site & 2nd site) and Mahanbhita Zone-II (HW site, 2nd site and 3rd site) of Mahanbhita piped water supply scheme i.c.w. JJM under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000585/2024-2025 | 270/JD | 07/02/2025 | 75 | SANKAR DAS | 80.69 | 0 | 30
2966 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000024/2023-2024 | 168/JD | 28/04/2023 | 0 | Resource Division | 23.28 | 0 | 0
2967 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000189/2023-2024 | 2051/JD | 09/01/2024 | 0 | Resource Division | 13.02 | 0 | 0
2968 | Northern Mechanical | Jalpaiguri Division | Additional New Service Connection Charge for MOHANBHITA, T/W-III, ZONE-I,under FULBARI CCC APPLICATION NO. 4003338759 Reference ID : 860296643 | Assistant Engineer,HQ | Junior Engineer | BILL/00125/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.23 | 0 | 0
2969 | Northern Mechanical | Jalpaiguri Division | Additional New Service Connection Charge for MOHANBHITA, T/W-I, ZONE-II,under FULBARI CCC APPLICATION NO. 4003338806 Reference ID : 860296639 | Assistant Engineer,HQ | Junior Engineer | BILL/00126/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.23 | 0 | 0
2970 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MAHANVITA,ZONE-II,T/W-II, under FULBARIHAT CCC APPLICATION NO. 4003365271 Reference ID : 403182689 | Assistant Engineer,HQ | Junior Engineer | BILL/00162/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.49 | 0 | 0
2971 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MOHANVITA,ZONE-I, T/W-I, under FULBARIHAT CCC APPLICATION NO. 4003359104 Reference ID : 403178079 | Assistant Engineer,HQ | Junior Engineer | BILL/00332/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.06 | 0 | 0
2972 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for MOHANVITA,ZONE-I, T/W-II, under FULBARIHAT CCC APPLICATION NO. 4003359089 Reference ID : 403178078 | Assistant Engineer,HQ | Junior Engineer | BILL/00333/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.78 | 0 | 0
2973 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for MOHONVITA, ZONE-I T/W-III, under FULBARI CCC [APPLICATION NO. 4003338759 , Reference ID : 403161865] | Assistant Engineer,HQ | Junior Engineer | BILL/02045/2023-2024 | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.79 | 0 | 0
2974 | Northern Mechanical | Jalpaiguri Division | Infrastructure Cost for MOHONVITA, ZONE-II T/W-I, under FULBARI CCC [APPLICATION NO. 4003338806 , Reference ID : 403162021] | Assistant Engineer,HQ | Junior Engineer | BILL/02046/2023-2024 | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 1.89 | 0 | 0
2975 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for MAHANBHITA PWSS, ZONE-I AND II, TW NO I,II AND III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000025/2023-2024 | 467/NMD | 25/04/2023 | 982 | M/S P.P. ELECTRICALS | 73.36 | 60.7 | 95
2976 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
2977 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (RAJGANJ Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000627/2024-2025 | 9/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 45.53 | 0 | 0
2978 | Northern Mechanical | Jalpaiguri Division | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-I) of MAHANBHITA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/001706/2023-2024 | 439/SMSD | 28/03/2024 | 7 | CHOWDHURY AND BASU ENTERPRISE | 0.73 | 0 | 0
2979 | Northern Mechanical | Jalpaiguri Division | Supply and Delivery of C.I special for attending breakdown maintanance as when as required at t/w no-I (zone-II) of MAHANBHITA and other adjacent W/S Scheme under JJM WORKS in the Dist of JALPAIGURI. | Assistant Engineer,HQ | Junior Engineer | ORD/001707/2023-2024 | 440/SMSD | 28/03/2024 | 7 | S.P. ENTERPRISE | 0.73 | 0 | 0
2980 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big dia Tube well 250x200mm dia using MS Slotted strainer at required depth by Reverse Rotary method of drilling i.c.w Rejuvenation of Syli Tea Garden Water Supply Scheme under Jal Jeevan Mission, Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000296/2023-2024 | 1354/JD | 26/09/2023 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 40.77 | 40.41 | 60
2981 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repairing of Over Head Reservior(OHR) at Syli Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000382/2022-2023 | 346/JD | 16/02/2023 | 30 | RAGHU DAS | 4.12 | 4.11 | 1
2982 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000059/2023-2024 | 1094/JD | 24/08/2023 | 0 | Resource Division | 9.89 | 0 | 0
2983 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for REJU. OF SYLI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 4003343254 Reference ID : 403165543 |  | Junior Engineer | BILL/00189/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2984 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at REJU. OF SYLI TG, TW NO-III, OODLABARI CCC APPLICATION NO. 100000101048 Reference ID : 860293438 |  | Junior Engineer | BILL/00190/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.89 | 0 | 0
2985 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for REJU. OF SYLI TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 4003343252 Reference ID : 403165542 |  | Junior Engineer | BILL/00191/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
2986 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at REJU. OF SYLI TG, TW NO-IV, OODLABARI CCC APPLICATION NO. 100000101047 Reference ID : 860293437 |  | Junior Engineer | BILL/00192/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.81 | 0 | 0
2987 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply and Delivery of C.I special for as when as required at T/W No-I of SYLI TG and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. |  | Junior Engineer | ORD/000069/2024-2025 | 1058/HQ/NMD | 21/06/2024 | 7 | BONANZA ENTERPRISE | 0.73 | 0.73 | 100
2988 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation of Ambari Falakata PWSS ie. TW, Pump Houses, Water distribution Network, IEP etc. in connection with Jal Jeevan Mission at Rajganj Block, under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000074/2023-2024 | 429/JD. | 08/06/2023 | 663 | KANAI LAL SEN | 82.62 | 9.86 | 85
2989 | Jalpaiguri Division | Jalpaiguri Division | Overhauling and Reconditioning of The IEP (2 Unit) other Ancillary Works at Ambari Falakata H/W Site at Block Rajganj, under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000133/2024-2025 | 1292/JD | 04/09/2024 | 30 | BAJRANG ENTERPRISE | 12.02 | 11.56 | 100
2990 | Jalpaiguri Division | Jalpaiguri Division | Construction of Pump House (3.60 m X 2.40 m) size with Sanitary & Plumbing arrangement at 3rd Tube well site for Ambari Falakata P.W.S.S. under Jalpaiguri Division, P. H. Engineering Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000578/2021-2022 | 158/JD | 19/01/2022 | 60 | MAA ENTERPRISES | 4.65 | 0 | 100
2991 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AMBARI FALAKATA, T/WNO. V under FULBARIHAT CCC APPLICATION NO. 4003385989 Reference ID : 403199279 | Assistant Engineer,HQ | Junior Engineer | BILL/00182/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.12 | 0 | 0
2992 | Siliguri W/S Division | Siliguri Sub-Division | PREPARATION OF DETAILS PROJECT REPORT (DPR) INCLUDING ROUTE SURVEY IN CONNECTION WITH AUGMENTATION OF PORJHAR PIPED WATER SUPPLY SCHEME UNDER RAJGANJ BLOCK, JALPAIGURI DISTRICT UNDER SILIGURI W/S DIVISION, P.H.E. DTE | Assistant Engineer , Head Quarters , NMD,Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000071/2023-2024 | 264/SSD | 05/06/2023 | 10 | ENVIROTECH SOLUTIONS | 2.77 | 2.77 | 30
2993 | Siliguri W/S Division | Siliguri Sub-Division | Laying distribution system,risingmain,installation of iron elemination plant, pump houses ,boundary walls ,functional house hold tap connection (FHTC) and other allied works under Jal Jeevan Mission (JJM) for Augmentation of PORJHAR Piped Water Supply Scheme under Rajganj Block under Siliguri Sub Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000111/2023-2024 | 1158/SWSD | 09/08/2023 | 874 | AKASH ENTERPRISE | 356.29 | 101.93 | 90
2994 | Siliguri W/S Division | Siliguri Sub-Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer(Civil) | Junior Engineer (Civil) | RTOR000086/2022-2023 | 2211/SWSD | 05/01/2023 | 0 | Resource Division | 31.37 | 0 | 0
2995 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PORAJHAR, T/W No. I, under SHIVMANDIR CCC [APPLICATION NO. 4003332364 , Reference ID : 403156961] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02007/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.78 | 0 | 0
2996 | Northern Mechanical | Siliguri Sub-Division | New Service Connection Charge for PORAJHAR, T/W No. II, under SHIVMANDIR CCC [APPLICATION NO. 4003332377 , Reference ID : 403156964] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer(Civil) | Junior Engineer (Civil) | BILL/02008/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.14 | 0 | 0
2997 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of Pump House ( 1st site ), boundary wall ( 1st site ) and other Allied works at MATHACHULKA Piped Water Supply Scheme under Jalpaiguri Division ,P.H.E. Dte. |  | Junior Engineer | ORD/000115/2022-2023 | 92/JSSD | 22/07/2022 | 15 | DEBABRATA SARKAR | 4.62 | 0 | 100
2998 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Mathachulka PWSS i.e. TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Metali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000141/2023-2024 | 701/JD | 13/07/2023 | 539 | M/S. D.K. DEY & CO.. | 77.02 | 48.5 | 85
2999 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with Laying Distribution System at Mathachulka Piped Water Supply Scheme in connection with Jal Jeevan Mission at Matiali Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000180/2025-2026 | 2166/JD | 30/10/2025 | 30 | DEEP CONSTRUCTION | 24.8 | 0 | 0
3000 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000086/2023-2024 | 1067/JD | 24/08/2023 | 0 | Resource Division | 17.44 | 0 | 0
3001 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000209/2023-2024 | 2069/JD | 10/01/2024 | 0 | Resource Division | 4 | 0 | 0
3002 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) MATHACHULKA TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105524 Reference ID : 860297574 |  | Junior Engineer | BILL/00246/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.59 | 0 | 0
3003 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge fo MATHACHULKA PWSS TW NO-III, METELI CCC " APPLICATION NO.4003386724 Reference ID : 403200293 |  | Junior Engineer | BILL/00389/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3004 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for MATHACHULKA TW-IV(NEW MASJID),METELI CCC Reference ID:403285589 Application Id:4003505421 |  | Junior Engineer | BILL/01392/2024-2025 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3005 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC POLECASE for MATHACHULKA TW-IV(NEW MASJID),METELI CCC " Reference No-860314555 Application No-100000120355 |  | Junior Engineer | BILL/01393/2024-2025 | BP/24-25/237 | 25/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0
3006 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri |  | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0
3007 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
3008 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Nidam Jhora Tea Garden Pwss i.e TW, Pump House, Water Distribution Network,OHR, BW, Rising Main, FHTC etc. i.c.w Jal Jeevan mission at Block - Mal under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000258/2023-2024 | 943/JD | 08/08/2023 | 602 | J.M. CONSTRUCTION | 138.12 | 60.56 | 80
3009 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 1 (One) No Big Dia (200mm x 150mm) Tube Well by Modified DTH - ODEX Method of drilling at Nidam Jhora Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000587/2023-2024 | 2334/JD | 08/02/2024 | 15 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 16.63 | 16.9 | 100
3010 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000068/2023-2024 | 1073/JD | 24/08/2023 | 0 | Resource Division | 17.26 | 0 | 0
3011 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000158/2023-2024 | 2023/JD | 09/01/2024 | 0 | Resource Division | 3.63 | 0 | 0
3012 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NIDAM JHORA TG, TW NO-I, MAL CCC APPLICATION NO. 4003299874 Reference ID : 403130047 |  | Junior Engineer | BILL/00179/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3013 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at NIDAM JHORA TG, TW NO-I & II, MAL CCC APPLICATION NO. 100000104805 Reference ID : 860297125 |  | Junior Engineer | BILL/00180/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.19 | 0 | 0
3014 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NIDAM JHORA TG, TW NO-II, MAL CCC APPLICATION NO. 4003299885 Reference ID : 403130043 |  | Junior Engineer | BILL/00181/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3015 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
3016 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
3017 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NIDAM JHORA TEA GARDEN PWSS, TW No I AND II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000351/2023-2024 | 1312/NMD | 04/08/2023 | 789 | MERCURY ENGINEERING COMPANY | 24.55 | 0 | 70
3018 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0
3019 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Land devlopment at 2nd site under Raipur T.G. Piped Water Supply Scheme under Jalpiaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000494/2022-2023 | 286/RWS | 29/03/2023 | 10 | NEW KUNDU ENTERPRISE | 0.98 | 0.98 | 100
3020 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for RAIPUR TEA GARDEN,T/W-III, under UKILPARA MASKALIBARI CCC APPLICATION NO. 4003343597 Reference ID : 403174733 |  | Junior Engineer | BILL/00161/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.87 | 0 | 0
3021 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF RAIPUR TEA GARDEN PWSS,at TW NO III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000722/2023-2024 | 1544/NMD | 01/09/2023 | 30 | SAIKAT SINHA | 12.42 | 8.62 | 100
3022 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
3023 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying of Wash out line and distribution line over jhora at Dakshin Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000021/2024-2025 | 518/JD | 27/06/2024 | 14 | NEW KUNDU ENTERPRISE | 1.9 | 1.48 | 100
3024 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of C.C. drain (extension) at front side of head work site along the road to drain out over flow water of OHR under Dakshin Salbari Water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer 2 | ORD/000032/2023-2024 | 386/RWS | 25/04/2023 | 14 | NEW KUNDU ENTERPRISE | 2.41 | 2.44 | 100
3025 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components for Rejuvenation of Dakshin Shalbari PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block ¿ Banarhat under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer 2 | ORD/000106/2023-2024 | 437/JD. | 08/06/2023 | 784 | RABINDRANATH DUTTA | 56.71 | 15.41 | 70
3026 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Dakshin Salbari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer 2 | ORD/000415/2022-2023 | 169/RWS | 28/02/2023 | 21 | NEW KUNDU ENTERPRISE | 2.99 | 2.46 | 100
3027 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000084/2023-2024 | 1068/JD | 24/08/2023 | 0 | Resource Division | 3.99 | 0 | 0
3028 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for new service connection at REJUVENATION OF DAKSHIN SALBARI,T/W-III, GAIRKATA CCC APPLICATION NO. 4003438171 Reference ID : 403238894 |  | Junior Engineer 2 | BILL/00483/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
3029 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure development cost for new service connection at REJUVENATION OF DAKSHIN SALBARI,T/W-III, GAIRKATA CCC APPLICATION NO. 100000110784 Reference ID : 860303154 |  | Junior Engineer 2 | BILL/00484/2024-2025 | BP/24-25/101 | 25/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.33 | 0 | 0
3030 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Fuel,lubricant, stearing oil charges for Government inspection vehicle,NMD,PHE,Dte Invoice no-0059/2023-2024, Dt-30/09/23 |  | Junior Engineer 2 | BILL/01082/2024-2025 |  | 22/08/2024 | 0 | M/S MILLENNIUM FUEL CENTRE | 0.3 | 0 | 0
3031 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer 2 | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3032 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF DAKSHIN SALBARI PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer 2 | ORD/000181/2023-2024 | 1218/NMD | 26/07/2023 | 30 | SUDIP DUTTA | 11.49 | 0 | 0
3033 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT FOR 42 NOS. SITE AT DIFFERENT HEAD WORKS OF DIFFERENT PIPED WATER SUPPLY SCHEMES LOCATED AT JALPAIGURI SADAR BLOCK,MAYNAURI BLOCK AND KRANTI BLOCK UNDER JALPAIGURI DIVISION ,P.H.E Dte. |  | Junior Engineer | BILL/01426/2023-2024 | BP-2024-25-1 | 03/04/2024 | 0 | DR. AMBARISH GHOSH | 44.43 | 0 | 0
3034 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of different components of Binnaguri PWSS i.e. TW Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. at Block Jalpaiguri Sadar under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000469/2022-2023 | 751/JD | 24/03/2023 | 725 | BISWANATH GHOSH | 226.15 | 130.79 | 100
3035 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Balance Laying Distribution System and Functional Household Tap Connection for Binnaguri PWSS in connection with Jal Jeevan Mission at Sadar Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000599/2024-2025 | 482/JD | 11/03/2025 | 333 | BISWANATH GHOSH | 18.65 | 0 | 0
3036 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000010/2023-2024 | 154/JD | 28/04/2023 | 0 | Resource Division | 17.1 | 0 | 0
3037 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000147/2023-2024 | 2003/JD | 08/01/2024 | 0 | Resource Division | 6.23 | 0 | 0
3038 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BINNAGURI T/W-I, under HALDIBARI CCC , [APPLICATION NO. 4003341115, Reference ID : 403164679] |  | Junior Engineer | BILL/02031/2023-2024 | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.66 | 0 | 0
3039 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BINNAGURI T/W-II, under HALDIBARI CCC , [APPLICATION NO. 4003341205, Reference ID : 403165171] |  | Junior Engineer | BILL/02032/2023-2024 | BP/23-24/313 | 28/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.38 | 0 | 0
3040 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3041 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (JALPAIGURI SADAR Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000986/2024-2025 | 10/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 55.65 | 0 | 0
3042 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: JALPAIGURI SADAR, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001001/2024-2025 | 22/NMD | 06/01/2025 | 30 | SUMON ELECTRICAL | 12.23 | 0 | 0
3043 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of differet components of Baragharia Zone-II PWSS i.e TW, Pump Houses, Water distribution Network, OHR, Boundary Wall, RISING MAIN, FHTC etc. in connection with JJM at Block-Kranti under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000053/2023-2024 | 357/JD. | 25/05/2023 | 180 | M.S ENTERPRISE | 166.28 | 64.33 | 65
3044 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of differet components of Baragharia Zone-I PWSS i.e TW, Pump Houses , Water distribution Network, OHR, Boundary Wall , RISING MAIN , FHTC etc. in connection with Jal Jeevan Mission at Block Kranti under Jalpaiguri Division , P.H.E Dte. |  | Junior Engineer | ORD/000054/2023-2024 | 356/JD | 25/05/2023 | 860 | M.S ENTERPRISE | 246.82 | 113.98 | 40
3045 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
3046 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Additional Components for uncovered TANTY PARA AREA of BARAGHARIA PWSS i.e. TW, Pump House ,Boundary Wall, Water distribution Network ,FHTC, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000543/2024-2025 | 570/JD | 25/03/2025 | 75 | SADHAN KARMAKAR | 113.85 | 0 | 0
3047 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000073/2023-2024 | 1078/JD | 24/08/2023 | 0 | Resource Division | 38.3 | 0 | 0
3048 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000204/2023-2024 | 2074/JD | 10/01/2024 | 0 | Resource Division | 8.03 | 0 | 0
3049 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 100000109544 Reference ID : 860302004 |  | Junior Engineer | BILL/00405/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.98 | 0 | 0
3050 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 100000109538 Reference ID : 860301298 |  | Junior Engineer | BILL/00406/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0
3051 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for BARA GHARIA,TW NO-II, KRANTI CCC APPLICATION NO. 4003426943 Reference ID : 403231623 |  | Junior Engineer | BILL/00407/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3052 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for BARA GHARIA,TW NO-I, KRANTI CCC APPLICATION NO. 4003426904 Reference ID : 403231622 |  | Junior Engineer | BILL/00408/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3053 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at BARA GHARIA ,ZONE-II,TW-I, MAL CCC APPLICATION NO. 100000117353 Reference ID : 860311643 |  | Junior Engineer | BILL/01420/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.85 | 0 | 0
3054 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for BARA GHARIA ,ZONE-II,TW-II, MAL CCC APPLICATION NO. 4003477836 Reference ID : 403266830 |  | Junior Engineer | BILL/01421/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3055 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for BARA GHARIA ,ZONE-II,TW-I, MAL CCC APPLICATION NO. 4003477826 Reference ID : 403266831 |  | Junior Engineer | BILL/01422/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3056 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at BARA GHARIA ,ZONE-II,TW-II, MAL CCC APPLICATION NO. 100000117355 Reference ID : 860311645 |  | Junior Engineer | BILL/01423/2024-2025 | BP/24-25/240 | 30/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.68 | 0 | 0
3057 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BARA GHARIA PWSS at TW NO I,II, in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/001570/2023-2024 | 654/NMD | 15/03/2024 | 382 | SUBHRANGSHU GUHARAJA | 23.9 | 14.06 | 50
3058 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Rejuvenation Of Haritalguri Tea Garden Area PWSS i.e. TW, Pump Houses, Water distribution Network, RISING MAIN, etc. in connection with Jal Jeevan Mission at Block - Banarhat under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000131/2023-2024 | 418/A/JD | 07/06/2023 | 60 | M/S ROY & SARKAR CONSTRUCTION | 69.21 | 20.04 | 11
3059 | Jalpaiguri Division | Jalpaiguri Division | Engagement of Block Level Staff(Field Surveyor) through Implementation Agency for House hold survey (under ISA supervision) at Banarhat block in Connection with JIM under Jalpaiguri Division, PHE Dte with in Jalpaiguri District. | Assistant Engineer,HQ | Junior Engineer | ORD/000451/2023-2024 | 1288/RWS | 28/11/2023 | 30 | SUKES BASU MAJUMDAR | 3.11 | 3.11 | 100
3060 | Jalpaiguri Division | Jalpaiguri Division | Balance work of Laying pipeline & providing FHTC with allied works at Haritalguri Piped Water Supply Scheme in connection with JJM within Banarhat Block under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000487/2024-2025 | 2425/JD | 24/12/2024 | 45 | M/S ROY & SARKAR CONSTRUCTION | 32.68 | 0 | 0
3061 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for HARITALGURI, T/W No. III, under BANARHAT CCC [APPLICATION NO. 4003332995 , Reference ID : 403157461] | Assistant Engineer,HQ | Junior Engineer | BILL/02001/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.07 | 0 | 0
3062 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3063 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
3064 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU)ENGO TG PWSS TW NO-III, METELI CCC " APPLICATION NO.100000105439 Reference ID : 860297569 |  | Junior Engineer | BILL/00249/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.71 | 0 | 0
3065 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) ENGO TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.100000105521 Reference ID : 860297571 |  | Junior Engineer | BILL/00250/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.14 | 0 | 0
3066 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for(REJU)ENGO TG PWSS TW NO-IV, METELI CCC " APPLICATION NO.4003385787 Reference ID : 403199269 |  | Junior Engineer | BILL/00392/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3067 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for(REJU)ENGO TG PWSS TW NO-III, METELI CCC " APPLICATION NO.4003385947 Reference ID : 403199267 |  | Junior Engineer | BILL/00393/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3068 | Jalpaiguri Division | Northern Mechanical Division | Construction of different components of Baragharia PWSS i.e. TW, Pump Houses, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000026/2023-2024 | 93/JD | 25/04/2023 | 1096 | SCEC BOENTER KDAS JOINT VENTURE | 431.11 | 223.45 | 75
3069 | Jalpaiguri Division | Northern Mechanical Division | Balance work for Laying Distribution System at Baragharia Piped Water Supply Scheme in connection with Jal Jeevan Mission at Block- Dhupguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000179/2025-2026 | 2167/JD | 30/10/2025 | 30 | S. DUTTA | 26.33 | 0 | 0
3070 | Jalpaiguri Division | Northern Mechanical Division | Providing FHTC in the command area of Baragharia PWSS in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000540/2024-2025 | 111/JD | 16/01/2025 | 45 | SWAPAN SAHA | 22.58 | 0 | 0
3071 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000125/2023-2024 | 1839/JD | 15/12/2023 | 0 | Resource Division | 12.71 | 0 | 0
3072 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for BARAGHARIA, T/W No. I, under DHUPGURI CCC [APPLICATION NO. 4003248664, Reference ID : 403090252] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01650/2023-2024 | BP/23-24/170 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.51 | 0 | 0
3073 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for BARAGHARIA, T/W No. II, under DHUPGURI CCC [APPLICATION NO. 4003249150, Reference ID : 403091826] | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01651/2023-2024 | BP/23-24/170 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.88 | 0 | 0
3074 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
3075 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of JuLY,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00756/2024-2025 | BP-2024-25-416 | 01/10/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
3076 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of June,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00758/2024-2025 | BP-2024-25-418 | 01/10/2024 | 0 | FILL & SMILE | 0.17 | 0 | 0
3077 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of August'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01032/2024-2025 | BP-2024-25-563 | 20/12/2024 | 0 | FILL & SMILE | 0.24 | 0 | 0
3078 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
3079 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
3080 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) |  |  | ORD/000112/2024-2025 | 142/1/JSSD | 29/07/2024 | 184 | APIKUL ALI | 0.88 | 0.47 | 0
3081 | Jalpaiguri Division |  | Construction of different components of New Clenco T.G. (P) (Zone-I & II) PWSS i.e. TW, Pump Housese,Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block- Mal under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000159/2023-2024 | 798/JD. | 24/07/2023 | 601 | MD HAKIMUDDIN | 554.35 | 438.04 | 100
3082 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000212/2024-2025 | 137/JSSD | 29/07/2024 | 60 | DHIRAJ BISWAS | 0.88 | 0.44 | 50
3083 | Jalpaiguri Division |  | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including construction of Hume Pipe Culvert at New Clenco Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000225/2024-2025 | 1571/JD | 04/10/2024 | 244 | MD HAKIMUDDIN | 88.52 | 0 | 80
3084 | Jalpaiguri Division |  | Sinking of 3 (Three) Nos Tube Well by ODEX-165 method of drilling and construction of Pump House (3.60m x 2.40m) size with sanitary plumbing arrangement and boundary wall for direct boosting in the command area of New Clenco TG PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000484/2024-2025 | 2432/JD | 24/12/2024 | 373 | MD HAKIMUDDIN | 53.54 | 0 | 100
3085 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  |  | ORD/000819/2023-2024 | 524/JSSD | 29/01/2024 | 182 | APIKUL ALI | 0.88 | 0.56 | 70
3086 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000820/2023-2024 | 525/JSSD | 29/01/2024 | 182 | DHIRAJ BISWAS | 0.88 | 0.59 | 0
3087 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 1373/JD | 27/09/2023 | 0 | Resource Division | 39.87 | 0 | 0
3088 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 2026/JD | 09/01/2024 | 0 | Resource Division | 20.96 | 0 | 0
3089 | Northern Mechanical |  | New Service Connection Charge for NEW GLENCO TG, T/W No. I, ZONE-I, under MAL CCC [APPLICATION NO. 4003299833 , Reference ID : 403130048] |  |  | BILL/01797/2023-2024 | BP/23-24/266 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3090 | Northern Mechanical |  | Infrastructure Cost for NEW GLENCO TG, T/W No. I, ZONE-I, under MAL CCC [APPLICATION NO. 100000096848 , Reference ID : 860287698] |  |  | BILL/01798/2023-2024 | BP/23-24/267 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.83 | 0 | 0
3091 | Northern Mechanical |  | New Service Connection Charge for NEW GLENCO TG, T/W No. II, ZONE-I, under MAL CCC [APPLICATION NO. 4003299838 , Reference ID : 403130049] |  |  | BILL/01799/2023-2024 | BP/23-24/268 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3092 | Northern Mechanical |  | Infrastructure Cost for NEW GLENCO TG, T/W No. II, ZONE-I, under MAL CCC [APPLICATION NO. 100000096849 , Reference ID : 860287699] |  |  | BILL/01800/2023-2024 | BP/23-24/269 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.91 | 0 | 0
3093 | Northern Mechanical |  | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-II,ZONE-II under ODLABARI CCC, [APPLICATION NO. 4003344833, Reference ID : 403166837] |  |  | BILL/02164/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3094 | Northern Mechanical |  | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-I,ZONE-II under ODLABARI CCC, [APPLICATION NO. 100000101049, Reference ID : 860293439] |  |  | BILL/02165/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.92 | 0 | 0
3095 | Northern Mechanical |  | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-I,ZONE-II under ODLABARI CCC, [APPLICATION NO. 4003344844, Reference ID : 403166840] |  |  | BILL/02166/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3096 | Northern Mechanical |  | New Service Connection Charge for NEW CLENCO TEA GARDEN, T/W-II,ZONE-II under ODLABARI CCC, [APPLICATION NO. 100000101170, Reference ID : 860293440] |  |  | BILL/02167/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.67 | 0 | 0
3097 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
3098 | Northern Mechanical |  | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  |  | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
3099 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEW CALENCO TG PWSS, ZONE I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000758/2023-2024 | 1586/NMD | 08/09/2023 | 754 | ANUP BASU | 52.66 | 23.47 | 70
3100 | Northern Mechanical |  | Installation of two tank chlorination system at different water supply scheme of JJM under Mal Block in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/001002/2024-2025 | 55/HQ/NMD | 06/01/2025 | 7 | SARKAR ELECTRIC | 0.95 | 0 | 0
3101 | Northern Mechanical |  | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/001005/2024-2025 | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0
3102 | Northern Mechanical |  | Additional Works in connection with Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for NEW CALENCO TG PWSS, ZONE I AND II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/001414/2024-2025 | 690/HQ/NMD | 28/02/2025 | 7 | ANUP BASU | 0.91 | 0 | 0
3103 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | 200 Cum OHR as per Departmental Design & Drawing for Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme Block- Nagrakata, District - Jalpaiguri. |  | Junior Engineer | ORD/000043/2022-2023 | 1081/JD | 29/04/2022 | 180 | SABITA ENTERPRISE | 55.26 | 33.84 | 100
3104 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Tap Water Supply Connection in Connection with Jaldhara /Jalswapna in School, ICDS Centre and Health Centre at Hope TG,Naya Sily TG, Jiti TG,Nagrakata & Nagrakata TG Water Supply Scheme at Nagrakata Block under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/000111/2022-2023 | 88/JSSD | 22/07/2022 | 10 | GOUTAM DAS | 3.64 | 3.63 | 0
3105 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40m) size with sanitary and plumbing arrangement at 3rd tubewell site for Rejuvenation of Water Supply of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000125/2022-2023 | 24/JSSD | 21/06/2022 | 45 | SANJIT SARKAR | 4.76 | 4.76 | 100
3106 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with providing Functional Household Tap Connection (FHTC) i.c.w. Jal Jeevan Mission under the command area of Rejuvenation of Nayasayli T.G. Area Piped W/S Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. (Phase-IV). |  | Junior Engineer | ORD/000138/2024-2025 | 1527/JD | 01/10/2024 | 20 | GAP ENGINEERS ENTERPRISES | 14.48 | 12.05 | 90
3107 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work in connection with laying rising main with other allied works for Rejuvenation of Nayasayli Tea Garden Piped W/S Scheme under JJM at Nagrakata Block, under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000146/2024-2025 | 259/JSSD | 25/09/2024 | 280 | GOLDEN KEY ENTERPRISE | 7.07 | 0 | 75
3108 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Replacement of UPVC pipeline with other allied works at Jungle Busty area i.c.w. Rejuvenation of Nayasaili Piped W/S Scheme under JJM at Nagrakata BLOCK, under Jalpaiguri Division,P.H.E.Dte. |  | Junior Engineer | ORD/000154/2024-2025 | 266/JSSD | 25/09/2024 | 38 | NEW KUNDU ENTERPRISE | 2.24 | 2.24 | 100
3109 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (3.60 m x 2.40 m) size including sanitary & plumbing arrangement at 4th tube well site for Rejuvenation of Nayasaily Tea Garden Water Supply Scheme for under Jalpaiguri Division, P.H.E Dte. |  | Junior Engineer | ORD/000310/2022-2023 | 63/JSSD | 19/07/2022 | 45 | N.M. CONSTRUCTION | 4.75 | 4.75 | 100
3110 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of boundary wall with gate, drain and pathway for 4th tube-well site for Rejuvenation of Nayasaily Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000311/2022-2023 | 64/JSSD | 19/07/2022 | 20 | N.M. CONSTRUCTION | 4.77 | 3.39 | 100
3111 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of a Rig Bored Tubewell by ODEX-165 method of drilling along with pump connection and other allied works at Champaguri Bazar area (5th TW Site) in connection with Jal Jeevan Mission of Rejuvenation of Naya Saily TG Piped Water Supply Scheme, Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000624/2024-2025 | 463/JD | 11/03/2025 | 30 | NARESH SEN | 10.09 | 0 | 0
3112 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Soil Investigation work for 200 CuM Over Head Reservoir (OHR) for Nayasaily T.G. PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000693/2021-2022 | .1065/JSSD | 24/01/2022 | 20 | R.B TESTING | 2.01 | 2.01 | 100
3113 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube well by Odex - 165 Method of drilling at 3rd tube well site for Rejuvenation of Nayasily Tea Garden Piped water Supply scheme under Jalpaiguri Division, P.H.E. Dte." |  | Junior Engineer | ORD/000773/2021-2022 | 837/JD | 31/03/2022 | 21 | M/S S. G. ENTERPRISE | 7.61 | 6.14 | 0
3114 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Deep Tube Well by Odex -165 Method of drilling at 4th tube well site for Rejuvenation of Nayasily Tea Garden Piped water supply scheme under Jalpaiguri Division, P.H.E. Dte." |  | Junior Engineer | ORD/000774/2021-2022 | 838/JD | 31/03/2022 | 21 | M/S S. G. ENTERPRISE | 7.62 | 6.05 | 0
3115 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary Wall with gate, drain, and pathway for 3rd tube-well site of Rejuvenation of Nayasaily Tea Garden Area Piped Water Supply Scheme under Jalpaiguri Division,P.H.E. Dte. |  | Junior Engineer | ORD/001001/2021-2022 | 1260/JSSD | 25/03/2022 | 20 | ROY CONSTRUCTION | 4.79 | 3.57 | 100
3116 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000024/2024-2025 | 2110/JD | 25/11/2024 | 0 | Resource Division | 5.22 | 0 | 0
3117 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NAYASAILY,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 4003097516, Reference ID : 402966975] |  | Junior Engineer | BILL/00757/2022-2023 | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3118 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for NAYASAILY,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 100000072600, Reference ID : 860263630] |  | Junior Engineer | BILL/00758/2022-2023 | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.36 | 0 | 0
3119 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for NAYASYLEE,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 4003098584, Reference ID : 402967280] |  | Junior Engineer | BILL/00763/2022-2023 | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3120 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for NAYASYLEE,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 100000072608, Reference ID : 860263638] |  | Junior Engineer | BILL/00764/2022-2023 | BP/22-23/158 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.51 | 0 | 0
3121 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAYASAILY TEA GARDEN PWSS,TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000869/2022-2023 | 334/NMD | 29/03/2023 | 30 | HARA PROSAD DAS | 21.5 | 20.77 | 70
3122 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
3123 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) |  | Junior Engineer | ORD/000432/2022-2023 | 631/JD | 13/03/2023 | 45 | PARESH CHANDRA GUHA | 40.48 | 25.68 | 100
3124 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc basilar danga |  | Junior Engineer | VCH/000343/2021-2022 |  | 05/10/2021 | 0 | PARESH CHANDRA GUHA | 15 | 0 | 0
3125 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | fhtc basilardanga |  | Junior Engineer | VCH/000464/2021-2022 |  | 21/10/2021 | 0 | PARESH CHANDRA GUHA | 16.39 | 0 | 0
3126 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BASILARDANGA |  | Junior Engineer | VCH/000794/2021-2022 | BP-2021-22-87 | 01/11/2021 | 0 | PARESH CHANDRA GUHA | 16.39 | 0 | 0
3127 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC BHANGARHAT PWSS |  | Junior Engineer | VCH/001359/2021-2022 | BP-2021-22-497 | 29/03/2022 | 0 | M/S DEY & ROY CHOUDHURY | 10.33 | 0 | 0
3128 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC PALASBARI PWSS |  | Junior Engineer | VCH/001395/2021-2022 | BP-2021-22-553 | 30/03/2022 | 0 | SANKAR DAS | 4.73 | 0 | 0
3129 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver under Office of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. For the use of the Executive Engineer, Jalpaiguri Division, P.H.E. Dte. (with valid Taxi permit). (Vehicle No.-WB71B-8742) |  |  | ORD/000360/2022-2023 | 1416/JD | 14/07/2022 | 365 | RAKESH SARKAR | 1.76 | 0.35 | 1
3130 | Jalpaiguri Division |  | Retrofitting works in connection with FHTC works along with PWD road from Prodhan Para to Putimari and different places at Bhangamali under Bhangamali Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000569/2021-2022 | 1811/JD | 18/11/2021 | 15 | RABINDRANATH DUTTA | 17.81 | 0.05 | 1
3131 | Jalpaiguri Division |  | BHANGAMALI |  |  | VCH/001052/2021-2022 | BP-2021-22-203 | 19/01/2022 | 0 | MRINMOY KANTI DUTTA | 14.38 | 0 | 0
3132 | Jalpaiguri Division |  | PROVIDING FHTC FOR BHANGAMALI PWSS |  |  | VCH/001333/2020-2021 | 1195 | 04/02/2021 | 0 | MRINMOY KANTI DUTTA | 14.66 | 0 | 0
3133 | Siliguri W/S Division | Siliguri Sub-Division | Continuation order for Hiring of 01 (one) no. Maxi Cab with engine capacity less than or equal to 2000 CC (with air condition) for the Office of the Chief Engineer (Civil), Northern Zone, P.H.E. Dte. Vivekananda Bhawan (2nd floor), Hill Cart Road, Siliguri for the period from 01.01.2024 to 31.07.2024 for Chief Engineer (Civil), Northern Zone, P.H.E. Dte. i.e.07 (seven) months. | Assistant Engineer(Civil) | Junior Engineer (Civil) | ORD/000323/2023-2024 | 2396/SWSD | 16/12/2023 | 213 | PINKI DAM | 1.03 | 0 | 0
3134 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of 250 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for REJUVENATION OF KILKOT TEA GARDEN AREA PIPED WATER SUPPLY SCHEME, Block- Matiali, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000377/2021-2022 | 350/JD | 03/02/2022 | 120 | NARENDRA KUMAR | 57.75 | 39.59 | 100
3135 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of boundary wall with gate,drain, Pipe line for H/W site of KILLKOTE T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000562/2020-2021 | 202/JD | 10/02/2021 | 30 | M/S SURAJIT DEY AND CO. | 14.94 | 14.98 | 0
3136 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | soil test for kilkote |  | Junior Engineer | VCH/000239/2022-2023 | bp2022-23- | 14/06/2022 | 0 | G. TECH INDIA | 2.03 | 0 | 0
3137 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST OF RISING MAIN CONNECTION FOR KILKOTE T.G |  | Junior Engineer | VCH/000240/2022-2023 | bp2022-23-49 | 07/06/2022 | 0 | GOUR KUMAR MITRA | 4.8 | 0 | 0
3138 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | FHTC KILKOTE |  | Junior Engineer | VCH/001201/2021-2022 | BP-2021-22-328 | 28/02/2022 | 0 | M/S SURAJIT DEY AND CO. | 11.92 | 0 | 0
3139 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | RETRO FITTING WORK HOPE |  | Junior Engineer | VCH/001202/2021-2022 | BP-2021-22-327 | 28/02/2022 | 0 | UMWELT ENGINEER PRIVATE LIMITED | 0.7 | 0 | 0
3140 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | INSTALLATION IRON ELIMINATION PLANT |  | Junior Engineer | VCH/001288/2021-2022 | BP-2021-22-519 | 30/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 5.1 | 0 | 0
3141 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION BHUSKA DANGA PWSS |  | Junior Engineer | VCH/001305/2021-2022 | BP-2021-22-424 | 25/03/2022 | 0 | MABCO CONSULTANT | 2.01 | 0 | 0
3142 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | SOIL INVESTIGATION WORK KILKOTE T.G |  | Junior Engineer | VCH/001318/2021-2022 | BP-2021-22-436 | 26/03/2022 | 0 | MABCO CONSULTANT | 2.01 | 0 | 0
3143 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | CONST BLOWER ROOM PURBA DURAMARI WSS |  | Junior Engineer | VCH/001368/2021-2022 | BP-2021-22-520 | 30/03/2022 | 0 | MONDAL PRECISION PRIVATE LIMITED | 5.78 | 0 | 0
3144 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain etc. at 3rd tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000140/2022-2023 | 1603/JD | 18/08/2022 | 45 | SANDIP BANIK | 13.65 | 12.43 | 0
3145 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Interconnection with Delivery Line of Tube Well ( 3rd and 4th ) to Distribution Pipeline & Backwash line at Basilardanga Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000274/2022-2023 | 2011/JD | 01/11/2022 | 15 | SANKAR DAS | 6.64 | 4.9 | 1
3146 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th tube well site of Rejuvenation of Basilardanga water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000294/2022-2023 | 2067/JD | 04/11/2022 | 45 | R.S CONSTRUCTION | 13.65 | 13.6 | 100
3147 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retrofitting works & other ancillary works related to FHTC at different places of Basilardanga PWSS under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000383/2022-2023 | 368/JD | 20/02/2023 | 15 | DIPAK KUMAR CHAKRABORTY | 1.81 | 1.81 | 0
3148 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Providing FHTC and Retrofitting works in connection with FHTC works under JJM at Binnaguri colony, Nirendarpur, Tekatuli of Basilardanga W/S/S under Jalpaiguri Division, P.H.E.Dte. Block-Maynaguri, District - Jalpaiguri.(Part-D) |  | Junior Engineer | ORD/000432/2022-2023 | 631/JD | 13/03/2023 | 45 | PARESH CHANDRA GUHA | 40.48 | 1.67 | 100
3149 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 4th Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000473/2021-2022 | 2219/JD | 27/12/2021 | 60 | PARESH CHANDRA ROY | 11.45 | 11.44 | 1
3150 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate,drain and pathway for 3rd Tube well site of Rejuvenation of Basilardanga Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000485/2021-2022 | 2218/JD | 27/12/2021 | 60 | M/S DEY & ROY CHOUDHURY | 11.44 | 11.43 | 1
3151 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Reparing on OHR , pump house , IEP Room , boundary wall , construction of pathway , & other ancillary works for Basilardanga piped W/S/S under Jalpaiguri Division , P.H.E. Dte |  | Junior Engineer | ORD/000588/2021-2022 | 178/RWS | 03/03/2022 | 30 | PARESH CHANDRA GUHA | 4.85 | 4.02 | 0
3152 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 250 mm x 150 mm x 132 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Rejuvenation of Basilardanga Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000731/2021-2022 | 642/JD | 08/03/2022 | 30 | MECHANO TRADING CO. | 15.51 | 12.87 | 1
3153 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte |  | Junior Engineer | ORD/000042/2023-2024 | 21/HQ/NMD | 20/04/2023 | 91 | UTTAM PAUL | 0.95 | 0.85 | 100
3154 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Basilardanga Piped W/S Scheme at T/W No. III in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000103/2022-2023 | 570/NMD | 14/07/2022 | 21 | GURUKRIPA ENTERPRISE | 1.87 | 1.87 | 0
3155 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, delivery & installation of 10KVA Servo Motor operated Copper wound line voltage corrector under Rejuvenation of Basilardanga Piped W/S Scheme at T/W No. IV in the district of Jalpaiguri under Northern Mechanical Division, P.H. Engineering Dte. |  | Junior Engineer | ORD/000104/2022-2023 | 571/NMD | 14/07/2022 | 21 | HARAGOURI ENTERPRISE | 1.87 | 1.87 | 0
3156 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BASILARDANGA PWSS, at TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000113/2022-2023 | 850/NMD | 18/07/2022 | 30 | S.P. ENTERPRISE | 7.74 | 7.74 | 0
3157 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components for BASILARDANGA PWSS, at TW no IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000114/2022-2023 | 851/NMD | 18/07/2022 | 30 | M/S ANJALI ENTERPRISE | 7.6 | 7.6 | 0
3158 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Hiring of Maxi Cab vehicle (Non-Airconditioned) for the Implementation of JJM Works at different district under NMD,PHE,Dte |  | Junior Engineer | ORD/000725/2023-2024 | 146/HQ/NMD | 31/07/2023 | 92 | UTTAM PAUL | 0.95 | 0 | 0
3159 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for TW-III of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941265 ; Reference ID : 402831972] |  | Junior Engineer | VCH/000337/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3160 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for TW-III of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053960 ; Reference ID : 860243610] |  | Junior Engineer | VCH/000338/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.06 | 0 | 0
3161 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for TW-IV of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 4002941268 ; Reference ID : 402831980] |  | Junior Engineer | VCH/000339/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3162 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for TW-IV of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000053938 ; Reference ID : 860243608] |  | Junior Engineer | VCH/000340/2022-2023 | RTGS 01 | 07/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.92 | 0 | 0
3163 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure cost for New Service Connection Charge for TW-III, of BASILARDANGA W/S Scheme under MAYNAGURI CCC [APPLICATION NO. 100000057050 , Reference ID : 860246650] |  | Junior Engineer | VCH/000774/2022-2023 | BP/2022-23/30 | 16/08/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.57 | 0 | 0
3164 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Different Components of Supply Of Potable Drinking Water To Dharanipur Tea Garden PWSS In Relation With Chaa Sundari Project i.e. T.W, Pump Houses, Water Distribution Network, Rising Main, FHTC etc. i.c.w. Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000827/2023-2024 | 2755/JD | 15/03/2024 | 413 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 71.04 | 35.75 | 55
3165 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "3 P H NEW SERVICE CONNECTION WORK AT DHARANIPUR TG " APPLICATION NO.100000110433 Reference ID : 860302763 |  | Junior Engineer | BILL/00444/2024-2025 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.31 | 0 | 0
3166 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT " APPLICATION NO.4003435519 Reference ID : 403236673 |  | Junior Engineer | BILL/00445/2024-2025 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
3167 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "3 P H NEW SERVICE CONNECTION WORK AT DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT TW-II " APPLICATION NO.100000110436 Reference ID : 860302766 |  | Junior Engineer | BILL/00446/2024-2025 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.34 | 0 | 0
3168 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for DHARANIPUR TG IN RELATION WITH CHA SUNDARI PROJECT TW-II " APPLICATION NO.4003435908 Reference ID : 403236934 |  | Junior Engineer | BILL/00447/2024-2025 | BP/24-25/87 | 18/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
3169 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and Trial operation of Electro Mechanical components for water supply scheme at DHARANIPUR TEA GARDEN IN RELATION WITH CHAA SUNDARI PROJECT, Block NAGRAKATA, district Jalpaiguri. |  | Junior Engineer | ORD/000041/2022-2023 | 356/NMD | 23/05/2022 | 30 | SUBODH KUMAR BANIK | 16.28 | 0 | 0
3170 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 4th Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000287/2022-2023 | 2015/JD | 01/11/2022 | 927 | M/S R.N. TRADERS | 14.7 | 12.61 | 100
3171 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Boundary wall at H/W Site & 500 m3 capacity 20 Mtr. Staging height RCC Over Head Reservoir as per Departmental Design & drawing including pipe connection and cost of pipes, specials for AUGMENTATION OF RAMSAI PWSS, Block- Maynaguri, District : Jalpaiguri, under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000330/2021-2022 | 187/JD | 21/01/2022 | 120 | PARESH CHANDRA GUHA | 108.89 | 108.02 | 100
3172 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-II) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT - JALPAIGURI. |  | Junior Engineer | ORD/000334/2021-2022 | 206/JD | 24/01/2022 | 90 | ASHIT KUMAR SINGHA | 221.07 | 139.13 | 100
3173 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) FOR AUGMENTATION OF RAMSAI (PART-III) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT, JALPAIGURI. |  | Junior Engineer | ORD/000341/2021-2022 | 191/JD | 21/01/2022 | 1319 | M/S R.N. TRADERS | 187.78 | 126.62 | 100
3174 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LAYING DISTRIBUTION SYSTEM AND FUNCTIONAL HOUSEHOLD TAP CONNECTION FOR AUGMENTATION OF RAMSAI (PART-I) PIPED WATER SUPPLY SCHEME AT MAYNAGURI BLOCK, DISTRICT ¿ JALPAIGURI. |  | Junior Engineer | ORD/000342/2021-2022 | 190/JD | 21/01/2022 | 1118 | PARESH CHANDRA GUHA | 203.47 | 189.67 | 100
3175 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (20m3/hr) including construction of Blower Room (3.60MX3.00M ) Size, concrete platform & drain ...etc at 3rd Tubewell Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000343/2022-2023 | 140/JD | 17/01/2023 | 850 | R.S CONSTRUCTION | 14.7 | 12.74 | 60
3176 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Installation of Iron Elimination Plant (35 m3/hr) including construction of Blower Room (3.60MX3.00M) Size, concrete platform & drain...etc at H/W Site of Ramsai water supply scheme under Jalpaiguri Division PHE Dte. |  | Junior Engineer | ORD/000380/2022-2023 | 2268/JD | 21/11/2022 | 585 | M/S A.B.G. CONSTRUCTION | 29.33 | 29.32 | 100
3177 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Laying Distribution System ( node 2-4-287-288-289-290-291-292 & node 5-134) for Augmentation of Ramsai Piped Water Supply Scheme under Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. Block-Maynaguri. District- Jalpaiguri. |  | Junior Engineer | ORD/000452/2022-2023 | 730/JD | 22/03/2023 | 45 | R.S CONSTRUCTION | 25.64 | 25.64 | 100
3178 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 3rd Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000715/2021-2022 | 2228/JD | 27/12/2021 | 60 | SANKAR DAS | 11.45 | 11.33 | 100
3179 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Sinking of 2 No. 250 mm x 150 mm x 123 m deep Rig Bored Tube Well by Reverse Rotary method of drilling for Augmentation of Ramsai Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000729/2021-2022 | 633/JD | 07/03/2022 | 30 | MECHANO TRADING CO. | 15.35 | 13.91 | 0
3180 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Construction of Pump House (3.60 m x 2.40 m) internal size with sanitary & plumbing arrangement including Construction of boundary wall with gate, drain and pathway for 4th Tube well site of Augmentation Ramsai Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000883/2021-2022 | 217/JD | 24/01/2022 | 60 | GOURAB GUHA ROY | 11.44 | 11.36 | 100
3181 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000007/2021-2022 | 181/JD | 21/01/2022 | 0 | Resource Division | 31.71 | 0 | 0
3182 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000015/2021-2022 | 552/JD | 01/03/2022 | 0 | Resource Division | 28.13 | 0 | 0
3183 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000089/2024-2025 | 2217/JD | 01/12/2024 | 0 | Resource Division | 20.02 | 0 | 0
3184 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | LDS BHUJARI PARA KRANTI ZONE II |  | Junior Engineer | VCH/001417/2021-2022 | BP-2021-22-439 | 26/03/2022 | 0 | BARUN KUMAR DUTTA | 4.7 | 0 | 0
3185 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for PRADHANERBARI RAMSAI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 4003164165, Reference ID : 403024434] |  | Junior Engineer | BILL/00574/2023-2024 | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3186 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for PRADHANERBARI RAMSAI MAYNAGURI, T/W III, under MAYNAGURI CCC, [APPLICATION NO. 100000084431, Reference ID : 860276011] |  | Junior Engineer | BILL/00575/2023-2024 | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.71 | 0 | 0
3187 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for BAROHATI MORE RAMSAI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 4003164167, Reference ID : 403024435] |  | Junior Engineer | BILL/00576/2023-2024 | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3188 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure Cost for BAROHATI MORE RAMSAI MAYNAGURI, T/W IV, under MAYNAGURI CCC, [APPLICATION NO. 100000084158, Reference ID : 860276008] |  | Junior Engineer | BILL/00577/2023-2024 | BP/23-24/71 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.73 | 0 | 0
3189 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply and Delivery of C.I special as when as required at T/W No-I of RAMSAI and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. |  | Junior Engineer | ORD/000068/2024-2025 | 1057/HQ/NMD | 21/06/2024 | 7 | SUMON ELECTRICAL | 0.73 | 0 | 100
3190 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for AUGMENTATION OF RAMSAI PWSS, TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000841/2022-2023 | 270/NMD | 21/03/2023 | 346 | M/S PARITOSH BHOWMICK AND CO. | 20.2 | 18.4 | 100
3191 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125 mm dia 120 m deep Tube well by ODEX-165 drilling Method of Rejuvenation of water supply scheme for Hope Tea Garden under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000132/2022-2023 | 1467/JD | 25/07/2022 | 30 | PROSENJIT BASAK | 13.84 | 13.14 | 0
3192 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Urgent Retrofitting works at LW Bungalow back side under Hope T.G. Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000261/2022-2023 | 187/JSSD | 31/08/2022 | 30 | NARAYAN CHANDRA ADHIKARY | 1.91 | 1.89 | 0
3193 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection 257 Nos. in connection with Jal Jeevan Mission at Hope Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte |  | Junior Engineer | ORD/000347/2023-2024 | 293/JSSD | 27/09/2023 | 30 | GOUTAM DAS | 9.47 | 7.29 | 91
3194 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | EMERGENT REPAIRING OF PIPE LINE INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER HOPE TG PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE. |  | Junior Engineer | ORD/000350/2023-2024 | 299/JSSD | 27/09/2023 | 45 | GOUTAM DAS | 3.37 | 3.37 | 100
3195 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Disconnecting illegeal connections and street stand posts with repairing of distribution line at Rejuvenation of Chalsa (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000390/2022-2023 | 363/JD | 20/02/2023 | 14 | ALICK DATTA | 2.91 | 2.9 | 100
3196 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 2 nos. Pump House (3.60 m x 2.40 m) size with sanitary & plumbing arrangement and 2 nos. boundary wall with gate,drain and pathway for 3rd & 4th tubewell site of Hope TG piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000430/2022-2023 | 632/JD | 13/03/2023 | 60 | PRADIP KUMAR SHIL | 16.98 | 17.3 | 100
3197 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Repairing of 2 nos. of pump house (1st site & 2nd site) 3 nos. Boundary wall (Head work site, 1st site & 2nd site) with sanitary & plumbing arrangement and other allied works at Hope T.G. piped water supply scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000547/2021-2022 | 1065/JSSD | 24/02/2022 | 30 | GOUTAM DAS | 4.08 | 4.03 | 0
3198 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jalswapna near 18 no. line 15 no. line and allied areas for Hope T.G. PWSS under Jalpaiguri Division, PHE Dte. (Part-B) |  | Junior Engineer | ORD/000549/2021-2022 | 1049/JSSD | 24/01/2022 | 15 | GOUTAM DAS | 4.75 | 4.75 | 0
3199 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for HOPE TEA GARDEN,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 4003097490, Reference ID : 402966973] |  | Junior Engineer | BILL/00753/2022-2023 | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3200 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for HOPE TEA GARDEN,T/W IV, under NAGRAKATA CCC, [APPLICATION NO. 100000072368, Reference ID : 860263628] |  | Junior Engineer | BILL/00754/2022-2023 | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.68 | 0 | 0
3201 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for HOPE TEA GARDEN,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 4003097475, Reference ID : 402966977] |  | Junior Engineer | BILL/00755/2022-2023 | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3202 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for HOPE TEA GARDEN,T/W III, under NAGRAKATA CCC, [APPLICATION NO. 100000072607, Reference ID : 860263637] |  | Junior Engineer | BILL/00756/2022-2023 | BP/22-23/157 | 23/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.56 | 0 | 0
3203 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HOPE T.G PWSS, TW No III and IV in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000023/2023-2024 | 465/NMD | 25/04/2023 | 30 | M/S P.P. ELECTRICALS | 21.6 | 21.5 | 100
3204 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2023-2024 | 849/JD | 06/04/2023 | 45 | M/S YADAV CONSTRUCTION | 5.44 | 5.44 | 100
3205 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system For Rejuvenation Of Meteli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division P.H.E.Dte. |  | Junior Engineer | ORD/000021/2022-2023 | 1030/JD | 26/04/2022 | 1158 | NARAYAN CHAKRABORTY | 97.34 | 86.6 | 100
3206 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 3 Nos. Big Dia Tube well by Modified DTH - ODEX Method at 6th, 7th & 8th tube well site of Rejuvenation of Mateli Bazar (Zone- I & II) Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000062/2024-2025 | 931/JD | 07/08/2024 | 45 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 52.84 | 50.1 | 100
3207 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Water Tap Connection including laying pipeline in the command area of Metelibazar PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000091/2025-2026 | 104/JSSD | 30/05/2025 | 30 | SUJAN LAMA | 4.83 | 0 | 100
3208 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in Connection with Jaldhara/Jal Swapna near Jyoti Colony for Matiali Bazar Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000189/2022-2023 | 89/JSSD | 22/07/2022 | 10 | GOURAB GUHA ROY | 4.53 | 4.51 | 100
3209 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Urgent Retrofitting works at Prem Nagar & Thakur line under Meteli Bazar Area Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000255/2022-2023 | 175/JSSD | 25/08/2022 | 30 | SUJAN LAMA | 3.14 | 3.03 | 1
3210 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying distribution system For Rejuvenation Of Meteli Bazar (Zone-I) Piped water supply Scheme under Jalpaiguri Division.P.H.E.Dte. |  | Junior Engineer | ORD/000295/2022-2023 | 2061/JD | 03/11/2022 | 1245 | SAHA CONSTRUCTION | 115.22 | 16.97 | 45
3211 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-I) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000345/2022-2023 | 138/JD | 17/01/2023 | 30 | KNIGHT CO OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.88 | 0 | 0
3212 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Boundary wall reservoir at Head works site for Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000346/2022-2023 | 139//JD | 17/01/2023 | 30 | M/S KARMAKAR CONSTRACTION | 14.88 | 0 | 0
3213 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Emergent repairing of HW site & 1st site Pump House with Sanitary and plumbing arrangement for Augmentation of Mateli Bazar(Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000360/2023-2024 | 283/JSSD | 26/09/2023 | 366 | M/S YADAV CONSTRUCTION | 6.32 | 0 | 100
3214 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of 200 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per Departmental Design and Drawing including Rising Main in connection with Jal Jeevan Mission for Meteli Bazar Zone-II area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000396/2023-2024 | 1582/JD | 03/11/2023 | 180 | UNIVERSAL ENTERPRISES | 73.78 | 0 | 0
3215 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of Pump House (5.40 m x 3.60 m) size with sanitary & plumbing arrangement at Head works site for Mateli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000398/2023-2024 | 1586/JD | 06/11/2023 | 45 | M/S SUNSHINE | 5.61 | 0 | 0
3216 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Household Tap Connection 846 Nos. in connection with Jal Jeevan Mission at Mateli Bazar Zone-II Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000402/2023-2024 | 1669/JD | 24/11/2023 | 30 | DIPAK KUMAR CHAKRABORTY | 30.54 | 0 | 0
3217 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Restoration work of damaged road due to lying of pipeline, GI works and other allied works under Rejuvenatioin of Mateli Bazar (Zone-II) Piped water supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000545/2023-2024 | 496/JSSD | 02/01/2024 | 30 | NARAYAN CHAKRABORTY | 8.47 | 8.35 | 100
3218 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of One No. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000556/2021-2022 | 457/JD | 18/02/2022 | 21 | UNIBRO INFRASERV PRIVATE LIMITED | 6.38 | 0 | 100
3219 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Two Nos. 183 mm x 125mm dia 109 m Deep Tube well by ODEX-165 drilling Method of Rejuvenation of Meteli Bazar (Zone-II) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000557/2021-2022 | 456/JD | 18/02/2022 | 30 | UNIBRO INFRASERV PRIVATE LIMITED | 12.75 | 13.11 | 100
3220 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting works related with Jal swapna / JJM for Mateli Bazar area P.W.S.S. under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/001031/2021-2022 | 1053 /JSSD | 24/01/2022 | 15 | GOURAB GUHA ROY | 3.1 | 3.03 | 0
3221 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for METELLI TEA GARDEN GAHADI LINE, TW No. II, MATELLI CCC, [APPLICATION NO.4003117034, Reference ID : 403006109] |  | Junior Engineer | BILL/00065/2023-2024 | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3222 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for METELLI TEA GARDEN GAHADI LINE, TW No. II, MATELLI CCC, [APPLICATION NO. 100000075619, Reference ID : 860267309] |  | Junior Engineer | BILL/00066/2023-2024 | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.93 | 0 | 0
3223 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for METELLI BANGLA SCHOOL, TW No. I, MATELLI CCC, [APPLICATION NO.4003117033, Reference ID : 403006110] |  | Junior Engineer | BILL/00067/2023-2024 | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3224 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for METELLI BANGLA SCHOOL, TW No. I, MATELLI CCC, [APPLICATION NO. 100000075618, Reference ID : 860267308] |  | Junior Engineer | BILL/00068/2023-2024 | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.28 | 0 | 0
3225 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for METELLI TEA GARDEN LASAN LINE, TW No. III, MATELLI CCC, [APPLICATION NO.4003117038, Reference ID : 403006108] |  | Junior Engineer | BILL/00069/2023-2024 | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3226 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for METELLI TEA GARDEN LASAN LINE, TW No. III, MATELLI CCC, [APPLICATION NO. 100000076010, Reference ID : 860267310] |  | Junior Engineer | BILL/00070/2023-2024 | BP/23-24/19 | 24/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.72 | 0 | 0
3227 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at REJUVENATION OF METELI BAZAR PWSS(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri |  | Junior Engineer | ORD/000095/2025-2026 | 1085/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.63 | 0 | 0
3228 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF METELI BAZAR PWSS, ZONE-I, TW No II AND ZONE-II,TW NO- I and II in the district of JALPAIGURI under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000887/2022-2023 | 370/NMD | 29/03/2023 | 946 | ASHUTOSH DAS AND CO. | 38.04 | 0 | 30
3229 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000052/2023-2024 | 1087/JD | 24/08/2023 | 0 | Resource Division | 9.2 | 0 | 0
3230 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for (REJU)NAKHATI TG TW NO-III , MAL CCC " APPLICATION NO. 4003377472 Reference ID : 403192833 |  | Junior Engineer | BILL/00171/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3231 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT (REJU)NAKHATI TG TW NO-III , MAL CCC " APPLICATION NO. 100000104920 Reference ID : 860296940 |  | Junior Engineer | BILL/00172/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.8 | 0 | 0
3232 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for (REJU)NAKHATI TG TW NO-IV, MAL CCC " APPLICATION NO. 4003377480 Reference ID : 403192836 |  | Junior Engineer | BILL/00173/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3233 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRASTRUCTURE DEVELOPMENT COST FOR NSC AT(REJU)NAKHATI TG TW NO-IV, MAL CCC " APPLICATION NO.100000104806 Reference ID : 860297126 |  | Junior Engineer | BILL/00174/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 13.52 | 0 | 0
3234 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3235 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0
3236 | Jalpaiguri Division | Jalpaiguri Division | Construction of 450 CuM Over Head Reservoir (OHR) (Staging Height 20 Mtr.) as per departmental design and drawing with Pump House (5.4mx3.6m) with sanitary & plumbing arrangement and Boundary Wall with land development at Head Works site for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme in connection with Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2023-2024 | 240/JD | 08/05/2023 | 721 | JAYANTA GHOSH | 140.51 | 44.48 | 60
3237 | Jalpaiguri Division | Jalpaiguri Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
3238 | Jalpaiguri Division | Jalpaiguri Division | Minor repairing of Two nos. Pump House with Construction of Toilet and Sanitary Plumbing System located at head work site including Land Development work at 2nd Pummp house site and adjacent area along with ancillary work of Augmentation of Bhatiapara Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000098/2022-2023 | 1306/JD | 14/06/2022 | 21 | RABINDRANATH DUTTA | 3.93 | 3.88 | 100
3239 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara (Zone-II ) Piped water Supply Scheme(Part-B) at Nagrakata Block under Jalpaiguri Division. P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000146/2022-2023 | 1889/JD | 22/09/2022 | 1073 | RANA DEY | 65.49 | 63.94 | 97
3240 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-II )Piped water Supply Scheme (Part-E) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000240/2022-2023 | 1959/JD | 17/10/2022 | 21 | M/S SIBU DEY AND CO. | 81.95 | 79.77 | 95
3241 | Jalpaiguri Division | Jalpaiguri Division | Laying Distribution System for Augmentation of Bhatiapara (Zone-II) Piped Water Supply Scheme (Part A & D) at Nagrakata Block Under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000260/2022-2023 | 1948/JD | 13/10/2022 | 120 | JAYANTA GHOSH | 241.53 | 179.67 | 60
3242 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000272/2022-2023 | 2013/JD | 01/11/2022 | 21 | NEW KUNDU ENTERPRISE | 58.51 | 56.08 | 96
3243 | Jalpaiguri Division | Jalpaiguri Division | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-I under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000272/2023-2024 | 1260/JD | 13/09/2023 | 719 | NARAYAN CHAKRABORTY | 56.64 | 4.9 | 6
3244 | Jalpaiguri Division | Jalpaiguri Division | Construction of One No Pump House along with internal connection and Functional Household Tap Connection work in connection with Jal Jeevan Missiion under Augmentation of Bhatiapara PWSS Zone-II under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000273/2023-2024 | 1261/JD | 13/09/2023 | 718 | RANA DEY | 90.44 | 4.9 | 50
3245 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-I )Piped water Supply Scheme (Part-B) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000296/2022-2023 | 2060/JD | 03/11/2022 | 21 | SAPTASWA SARKAR | 74.86 | 71.6 | 100
3246 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of Bhatiapara ( Zone-II ) Piped water Supply Scheme (Part-C) at Nagrakata Block under Jalpaiguri Division.P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000319/2022-2023 | 2004/JD | 28/10/2022 | 21 | GOURAB GUHA ROY | 33.43 | 23.05 | 100
3247 | Jalpaiguri Division | Jalpaiguri Division | Providing Functional Household Tap Connection (FHTC) in connection with JJM under the command area of Bhatia Para (Zone-II) Piped Water Supply Scheme at Nagrakata Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000525/2023-2024 | 1970/JD | 03/01/2024 | 21 | RABINDRANATH DUTTA | 18.51 | 0 | 0
3248 | Jalpaiguri Division | Jalpaiguri Division | Laying distribution system for Augmentation of BHATIAPARA (ZONE-I) Piped Water Supply Scheme (PART-A) at Banarhut Block under Jalpaiguri Division, P.H.E Dte | Assistant Engineer,HQ | Junior Engineer | ORD/000536/2024-2025 | 569/JD | 25/03/2025 | 372 | ANUP SARKAR | 146.75 | 0 | 0
3249 | Jalpaiguri Division | Jalpaiguri Division | Construction of 2nd Tube well site Boundary wall, Drain, Pathway and Laying of Rising main at Zone-I of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000596/2024-2025 | 268/JD | 07/02/2025 | 328 | RANA DEY | 9.33 | 0 | 0
3250 | Jalpaiguri Division | Jalpaiguri Division | Construction of 3rd site Tube well Boundary wall, Drain, Pathway and Laying of Rising main at Zone-II of Bhatiapara PWSS in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000597/2024-2025 | 269/JD | 07/02/2025 | 147 | RANA DEY | 9.24 | 0 | 0
3251 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000078/2024-2025 | 2209/JD | 01/12/2024 | 0 | Resource Division | 31.51 | 0 | 0
3252 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000092/2023-2024 | 1065/JD | 24/08/2023 | 0 | Resource Division | 7.18 | 0 | 0
3253 | Central Drilling | Jalpaiguri Division | Providing additional Tubewell materials conforming to IS: 12818:2010 with other works at site for construction of Tubewell for Bhatiapara (Zone-I) PWSS (TW-II), Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000045/2023-2024 | 133/CMSD-II | 23/05/2023 | 10 | PADMA ENGINEERING & CO. | 0.87 | 0.86 | 100
3254 | Central Drilling | Jalpaiguri Division | Additional work for drilling bolder/sand stone Zone at Bhatiapara (Zone-I) PWSS (TW-II), Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000046/2023-2024 | 132/CMSD-II(D) | 23/05/2023 | 10 | PADMA ENGINEERING & CO. | 0.72 | 0.72 | 100
3255 | Central Drilling | Jalpaiguri Division | Additional work for drilling bolder/sand stone Zone at Bhatiapara (Zone-I) PWSS (TW-I) HW, Jalpaiguri District , under CMSD-II (D), Central Drilling Division, P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2023-2024 | 131/CMSD-II(D) | 23/05/2023 | 10 | PADMA ENGINEERING & CO. | 0.79 | 0.79 | 100
3256 | Central Drilling | Jalpaiguri Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 130 mtrs. Depth) by utilising Departmental machineries for Bhatiapara W/S Scheme (Z-II,TW-III), Nagrakata block under Jalpaiguri District, CDD PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000053/2023-2024 | 875/CDD | 11/07/2023 | 30 | PADMA ENGINEERING & CO. | 13.53 | 11.2 | 100
3257 | Central Drilling | Jalpaiguri Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 135 mtrs. Depth) by utilising Departmental machineries for Bhatipara PWSS, Dhupguri block under Jalpaiguri District, CDD PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000460/2022-2023 | 1776/CDD | 20/01/2023 | 30 | PADMA ENGINEERING & CO. | 12.61 | 11.58 | 100
3258 | Central Drilling | Jalpaiguri Division | Providing drilling crews for construction of Tube Well (250 mm x 150 mm x 88 mtrs depth) by SUPER RR Rig machine for Bhatiyapara PWSS Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000496/2022-2023 | 219/CMSD-I | 15/03/2023 | 15 | PADMA ENGINEERING & CO. | 4.64 | 3.7 | 100
3259 | Central Drilling | Jalpaiguri Division | Providing Tube Well materials conforming to IS : 12818 : 2010 with other works at site for construction of Tube well for Bhatiyapara Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000497/2022-2023 | 221/CMSD-I | 15/03/2023 | 15 | PADMA ENGINEERING & CO. | 2.64 | 2.63 | 100
3260 | Central Drilling | Jalpaiguri Division | Providing strainer conforming to IS : 12818 : 2010 with other materials & works at site for construction of Tube well at Bhatipara Block Nagrakata District Jalpaiguri under CDD, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000498/2022-2023 | 220/CMSD-I | 15/03/2023 | 15 | PADMA ENGINEERING & CO. | 2.13 | 2.09 | 100
3261 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AUGMENTATION OF BHATIAPARA, T/W-I, under BANARHAT CCC APPLICATION NO. 4003373981 Reference ID : 403189738 | Assistant Engineer,HQ | Junior Engineer | BILL/00132/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.13 | 0 | 0
3262 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for AUGMENTATION OF BHATIAPARA, T/W-III, under BANARHAT CCC APPLICATION NO. 4003373992 Reference ID : 403189742 | Assistant Engineer,HQ | Junior Engineer | BILL/00133/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.53 | 0 | 0
3263 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for BHATIAPARA T/W-II, under GAIRKATA CCC, [APPLICATION NO. 4003356887, Reference ID : 403176984] | Assistant Engineer,HQ | Junior Engineer | BILL/02172/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.71 | 0 | 0
3264 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for BHATIAPARA T/W-II, under GAIRKATA CCC, [APPLICATION NO. 100000101603, Reference ID : 860292663] | Assistant Engineer,HQ | Junior Engineer | BILL/02173/2023-2024 | BP/23-24/324 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.21 | 0 | 0
3265 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
3266 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Tandu PWSS i.e TW Pump Houses, Water distribution Network, OHR,RISING MAIN,FHTC etc. i.c.w JAL JEEVAN MISSION at Block - Nagrakata under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000466/2022-2023 | 755/JD | 24/03/2023 | 1015 | PRADIP SAHA | 114.12 | 63.69 | 35
3267 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000014/2023-2024 | 158/JD | 28/04/2023 | 0 | Resource Division | 2.39 | 0 | 0
3268 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000174/2023-2024 | 2029/JD | 09/01/2024 | 0 | Resource Division | 2.44 | 0 | 0
3269 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for TANDU TG, T/W No. I, under NAGRAKATA CCC [APPLICATION NO. 4003285461 ; Reference ID : 403120244] |  | Junior Engineer | BILL/01729/2023-2024 | BP/23-24/232 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.74 | 0 | 0
3270 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for TANDU TG, T/W No. I, under NAGRAKATA CCC [APPLICATION NO. 100000096118 ; Reference ID : 860288228] |  | Junior Engineer | BILL/01730/2023-2024 | BP/23-24/233 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.65 | 0 | 0
3271 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3272 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for TANDU PWSS, TW No I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000424/2023-2024 | 1339/NMD | 08/08/2023 | 30 | BLUE PINE | 12.03 | 11.84 | 100
3273 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (NAGRAKATA Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000991/2024-2025 | 12/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 29.71 | 0 | 0
3274 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: NAGRAKATA, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001003/2024-2025 | 23/NMD | 06/01/2025 | 30 | SARKAR ELECTRIC | 15.78 | 0 | 0
3275 | Jalpaiguri Division |  | Construction of different components of Niranjan Pat PWSS i.e TW, Pump Houses, Water Distribution Network, OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000130/2023-2024 | 406/JD | 06/06/2023 | 180 | UNIBRO INFRASERV PRIVATE LIMITED | 231.81 | 102.99 | 65
3276 | Jalpaiguri Division |  | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Niranjanpat Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000682/2024-2025 | 632/JD | 28/03/2025 | 45 | TIRTHANKAR CHOWDHURY | 24.06 | 0 | 0
3277 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 1375/JD | 27/09/2023 | 0 | Resource Division | 18.27 | 0 | 0
3278 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000122/2023-2024 | 1836/JD | 15/12/2023 | 0 | Resource Division | 5.33 | 0 | 0
3279 | Northern Mechanical |  | Infrastructure development cost for new service connection at NIRANJANPATH PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 100000115928 Reference ID : 860309778 |  |  | BILL/00976/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.13 | 0 | 0
3280 | Northern Mechanical |  | New Service Connection Charge for new service connection at NIRANJANPATH PWSS,T/W-I, GAIRKATA CCC APPLICATION NO. 4003470466 Reference ID : 403261884 |  |  | BILL/00977/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
3281 | Northern Mechanical |  | New Service Connection Charge for new service connection at NIRANJANPATH PWSS,T/W-II, GAIRKATA CCC APPLICATION NO. 4003470493 Reference ID : 403261885 |  |  | BILL/00978/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
3282 | Northern Mechanical |  | Infrastructure development cost for new service connection at NIRANJANPATH PWSS,T/W-II, GAIRKATA CCC APPLICATION NO. 100000115926 Reference ID : 860309776 |  |  | BILL/00979/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 5.91 | 0 | 0
3283 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
3284 | Northern Mechanical |  | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  |  | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3285 | Northern Mechanical |  | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/001045/2024-2025 | 30/NMD | 06/01/2025 | 30 | GEETA CONSTRUCTION | 12.33 | 0 | 0
3286 | Northern Mechanical |  | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  |  | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
3287 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different Components of ANANDAPUR T.G. PWSS i.e. 2 Nos Tube well, 2 Nos Pump house, Iron Elimination plant, 2 Nos Boundary Wall, Blower Room, Water distribution Network, 350 Cum OHR, Rising Main, FHTC etc. in connection with Jal Jeevan Mission at Block-Kranti under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000024/2025-2026 | 2153/JD | 17/10/2025 | 210 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 481.86 | 0 | 0
3288 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
3289 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sub-Soil Investigation of proposed 350 cum capacity Over Head Reservoir with 20 mtr. staging height, below the depth greater than 10 mtr. to 30 mtr. from G. L. at the Head Works site of Anandapur Tea Garden Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000802/2024-2025 | 89-HQ/JD | 11/03/2025 | 20 | APEX ENGINEERING | 0.98 | 0 | 0
3290 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000106/2023-2024 | 1372/JD | 27/09/2023 | 0 | Resource Division | 27.51 | 0 | 0
3291 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
3292 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ANANDAPUR TG PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000356/2023-2024 | 1317/NMD | 04/08/2023 | 30 | ABHISEK ENGINEERING CONCERN | 27.18 | 0 | 0
3293 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: KRANTI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001008/2024-2025 | 28/NMD | 06/01/2025 | 30 | M/S PARITOSH BHOWMICK AND CO. | 12.16 | 0 | 0
3294 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Chalsa Tea Graden PWSS i.e. TW, Pump Houses, Water Distribution Network, OHR, BW, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block Matiali under Jalpaiguri Division. |  | Junior Engineer | ORD/000006/2023-2024 | 24/JD | 10/04/2023 | 905 | PRASENJIT BASAK | 195.5 | 118.79 | 90
3295 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
3296 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance work of Distribution System and Functional Household Tap Connection (FHTC) of Chalsa Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000184/2025-2026 | 2157/JD | 29/10/2025 | 30 | PRASENJIT BASAK | 14.85 | 0 | 0
3297 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos Deep Rig Bored Tube Well by ODEX-195 method of drilling with 2 Nos Pump House(3.6m X 2.4m) and Boundary Wall including Pump House to distribution Line Connection for Rejuvenation of Chalsa Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000275/2023-2024 | 614/JD | 30/06/2023 | 30 | S. N. POLYMERS PVT. LTD. | 40.47 | 13.79 | 35
3298 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Retrofitting and Repairing work related to Laying Distribution System in Mangal Bar market area at Chalsa Rejuvenation Water Supply Scheme under Jalpaiguri Division, PHE DTE. |  | Junior Engineer | ORD/000829/2021-2022 | 1072/W/JSSD | 25/01/2022 | 20 | DEEP CONSTRUCTION | 4.14 | 4.09 | 0
3299 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000172/2023-2024 | 2034/JD | 09/01/2024 | 0 | Resource Division | 6.65 | 0 | 0
3300 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 4003197396, Reference ID : 403049082] |  | Junior Engineer | BILL/00607/2023-2024 | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3301 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for CHALSA TEA GARDEN, T/W I, under METTALI CCC, [APPLICATION NO. 100000084427, Reference ID : 860276303] |  | Junior Engineer | BILL/00608/2023-2024 | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.14 | 0 | 0
3302 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 4003197399, Reference ID : 403049084] |  | Junior Engineer | BILL/00609/2023-2024 | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3303 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for CHALSA TEA GARDEN, T/W II, under METTALI CCC, [APPLICATION NO. 100000084429, Reference ID : 860276310] |  | Junior Engineer | BILL/00610/2023-2024 | BP/23-24/85 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6 | 0 | 0
3304 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3305 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (MATIALI Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000993/2024-2025 | 13/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 36.03 | 0 | 0
3306 | Jalpaiguri Division | Jalpaiguri Division | Relaying of Rising Main from Head Works Site to Pump House No.-II due to the Damage of HDPE Pipeline at Riabari T.G PWSS under Jalpaiguri Division, P.H.E. | Assistant Engineer,HQ | Junior Engineer | ORD/000507/2024-2025 | 2403/JD | 20/12/2024 | 20 | SAPTASWA SARKAR | 1.32 | 0 | 0
3307 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for REJU RIA BARI TEA GARDEN, T/W No. III, under BANARHAT CCC [APPLICATION NO. 4003333061 , Reference ID : 403157468] | Assistant Engineer,HQ | Junior Engineer | BILL/02006/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.73 | 0 | 0
3308 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3309 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
3310 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000016/2024-2025 | 532/JD | 28/06/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 26.33 | 100
3311 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components for Rejuvenation of Yongtong Tea garden PWSS i.e. TW, Pump Housese, Boundary Wall, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block- Matiali under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000087/2023-2024 | 439/JD. | 08/06/2023 | 605 | ASHIS DUTTA | 69.4 | 0 | 50
3312 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of drain, development of land, Painting works of 250 Cu.M. capacity R.C.C. Elevated Reservoir, Pump House & Boundary Wall at Head works site for YongTong TG Piped Water Supply Scheme under Jalpaiguri Divition , P.H.E. Dte. |  | Junior Engineer | ORD/000434/2022-2023 | 606/JD | 09/03/2023 | 30 | PAMPA CONSTRUCTION | 6.2 | 6.16 | 0
3313 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission for Rejuvenation of YongTong Tea Garden area Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000548/2023-2024 | 500/JSSD | 02/01/2024 | 30 | D. S. ENTERPRISE | 2.34 | 2.29 | 100
3314 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000048/2023-2024 | 1100/JD | 24/08/2023 | 0 | Resource Division | 14.64 | 0 | 0
3315 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) YONGTONG TG TW NO- III, METELI CCC " APPLICATION NO.100000108223 Reference ID : 860300683 |  | Junior Engineer | BILL/00375/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.72 | 0 | 0
3316 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | " New Service Connection Charge for (REJU) YONGTONG TG TW NO- III, METELI CCC " APPLICATION NO.4003419056 Reference ID : 403225904 |  | Junior Engineer | BILL/00376/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3317 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "INFRA COST IRO NSC for (REJU) YONGTONG TG TW NO- IV, METELI CCC " APPLICATION NO.100000108225 Reference ID : 860300685 |  | Junior Engineer | BILL/00377/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.74 | 0 | 0
3318 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | " New Service Connection Charge for (REJU) YONGTONG TG TW NO- IV, METELI CCC " APPLICATION NO.4003401347 Reference ID : 403212024 |  | Junior Engineer | BILL/00378/2024-2025 | BP/24-25/73 | 30/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3319 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/000665/2025-2026 | 1084/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.79 | 0 | 0
3320 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components for Rejuvenation of Nagrakata Tea garden PWSS i.e. TW, Pump Housese, Boundary Wall, Water distribution Network, RISING MAIN etc. in connection with Jal Jeevan Mission at Block- Nagrakata under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000108/2023-2024 | 438/JD. | 08/06/2023 | 573 | NARAYAN CHANDRA SAHA | 85.68 | 75.36 | 90
3321 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Commissioning of Rejuvenation of Nagrakata Area Piped water supply Scheme under Jalpaiguri Division. P.H.E. Dte. (Phase-I) |  | Junior Engineer | ORD/000351/2023-2024 | 300/JSSD | 27/09/2023 | 30 | PARAMJYOTI ENTERPRISE | 9.59 | 4.89 | 100
3322 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Laying Distribution System (Part-L) along with 120 nos FHTC related to Rejuvenation of Nagrakata PWSS in connection with Jal Jeevan Mission at Block-Nagrakata under under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000353/2023-2024 | 294/JSSD | 27/09/2023 | 30 | BREATHING SPACE DESIGN & VAASTU CONSULTANTS | 9.68 | 9.67 | 60
3323 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | EMERGENT REPAIRING OF PIPE LINE, R.B.T FIXING IN BOUNDARY WALL, INSTALLATION OF VALVE ALONG WITH OTHER ALLIED WORKS RELATED TO PIPELINE UNDER NAGRAKATA T.G. PIPE WATER SUPPLY SCHEME UNDER JALPAIGURI DIVISION, PHE DTE |  | Junior Engineer | ORD/000354/2023-2024 | 301/JSSD | 27/09/2023 | 30 | PARAMJYOTI ENTERPRISE | 5.37 | 5.37 | 100
3324 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000080/2023-2024 | 1058/JD | 24/08/2023 | 0 | Resource Division | 11.54 | 0 | 0
3325 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for (REJU)NAGRAKATA TG TW NO-IV,NAGRAKATA CCC " APPLICATION NO.4003390273 Reference ID : 403202824 |  | Junior Engineer | BILL/00310/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3326 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "Deposite works,other than service connection for (REJU)NAGRAKATA TG TW NO-IV,NAGRAKATA CCC " APPLICATION NO.100000107213 Reference ID : 860298383 |  | Junior Engineer | BILL/00311/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.41 | 0 | 0
3327 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "New Service Connection Charge for (REJU)NAGRAKATA TG TW NO-III,NAGRAKATA CCC " APPLICATION NO.4003390283 Reference ID : 403202825 |  | Junior Engineer | BILL/00312/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3328 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | "Deposite works,other than service connection for (REJU)NAGRAKATA TG TW NO-III,NAGRAKATA CCC " APPLICATION NO.100000107214 Reference ID : 860298384 |  | Junior Engineer | BILL/00313/2024-2025 | BP/24-25/43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.32 | 0 | 0
3329 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Water Supply Scheme of JITI TEA GARDEN MOUZA and other Adjacent Water Supply Scheme under JJM under Nagrakata Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/001135/2024-2025 | 51/DSD | 10/03/2025 | 15 | D.K. & SONS | 1.23 | 0 | 0
3330 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF NAGRAKATA TG PWSS, TW no III & IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/001635/2023-2024 | 668/NMD | 15/03/2024 | 472 | DEY ENTERPRISE(MALDA) | 24.07 | 18.87 | 95
3331 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Retro fitting works due to FHTC in connection for JJM under the command area of Huslu Danga piped Water Supply Scheme at Maynaguri Block under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000435/2022-2023 | 675/JD | 16/03/2023 | 15 | M/S ROY & SARKAR CONSTRUCTION | 2.92 | 2.92 | 0
3332 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000102/2023-2024 | 1048/JD | 24/08/2023 | 0 | Resource Division | 4.8 | 0 | 0
3333 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for HUSLUDANGA, T/W-III under MAYNAGURI CCC APPLICATION NO. 4003356512 Reference ID : 403175904 |  | Junior Engineer | BILL/00187/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 7.32 | 0 | 0
3334 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for HUSLUDANGA, T/W-IV under MAYNAGURI CCC APPLICATION NO. 4003356517 Reference ID : 403175891 |  | Junior Engineer | BILL/00188/2024-2025 | BP/24-25/14 | 23/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.84 | 0 | 0
3335 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Maynaguri Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000002/2025-2026 | 961/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 93.06 | 0 | 0
3336 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply and Delivery of C.I special as when as required at T/W No-I of HASLUDANGA and other adjacent W/S Scheme under in the Dist. of JALPAIGURI. |  | Junior Engineer | ORD/000067/2024-2025 | 1056/HQ/NMD | 21/06/2024 | 7 | B.B. CONCERNED | 0.73 | 0.39 | 100
3337 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
3338 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF HASLURDANGA PWSS, TW no III and IV in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000443/2023-2024 | 1382/NMD | 09/08/2023 | 30 | BLUE PINE | 20.22 | 20.2 | 100
3339 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  | Junior Engineer | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
3340 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
3341 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Kantadighi Kumarpara T.G. PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  | Junior Engineer | ORD/000063/2023-2024 | 247/JD | 10/05/2023 | 875 | S.S. CONSTRUCTION | 465.21 | 350.39 | 20
3342 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Balance works Distribtion System and Functional Household Tap Connection (FHTC) including Different Components of Kantadighi Kumar Para TG PWSS i.e. TW, Pump House, Boundary Wall, Rising Main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E. Dte. |  | Junior Engineer | ORD/000456/2024-2025 | 2037/JD | 21/11/2024 | 496 | SAPTASWA SARKAR | 82.16 | 0 | 40
3343 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000064/2023-2024 | 1092/JD | 24/08/2023 | 0 | Resource Division | 60.02 | 0 | 0
3344 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000154/2023-2024 | 2012/JD | 09/01/2024 | 0 | Resource Division | 15.28 | 0 | 0
3345 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 4003303019 , Reference ID : 403132354] |  | Junior Engineer | BILL/01791/2023-2024 | BP/23-24/261 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3346 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. I, under MAL CCC [APPLICATION NO. 100000096843 , Reference ID : 860287693] |  | Junior Engineer | BILL/01792/2023-2024 | BP/23-24/260 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.14 | 0 | 0
3347 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 4003303022 , Reference ID : 403132353] |  | Junior Engineer | BILL/01793/2023-2024 | BP/23-24/262 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3348 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. II, under MAL CCC [APPLICATION NO. 100000096844 , Reference ID : 860287694] |  | Junior Engineer | BILL/01794/2023-2024 | BP/23-24/263 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.18 | 0 | 0
3349 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 4003303010 , Reference ID : 403132351] |  | Junior Engineer | BILL/01795/2023-2024 | BP/23-24/264 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.68 | 0 | 0
3350 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure Cost for KANTADIGHI KUMARPARA TG PWSS, T/W No. III, under MAL CCC [APPLICATION NO. 100000096846 , Reference ID : 860287696] |  | Junior Engineer | BILL/01796/2023-2024 | BP/23-24/265 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0
3351 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
3352 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
3353 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKSHIN KANTADIGHI KUMARPARA TEA GARDEN PWSS in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000996/2023-2024 | 1994/NMD | 21/12/2023 | 436 | SUBODH KUMAR BANIK | 25.51 | 0 | 70
3354 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: MAL, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/001005/2024-2025 | 25/NMD | 06/01/2025 | 30 | CHOWDHURY AND BASU ENTERPRISE | 15.33 | 0 | 0
3355 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Inspection Vehicle WB-71B-9586 for JJM on daily basis @12.00/Km for Official use of the Assistant Engineer, Jalpaiguri Sadar-Sub Division P.H.E. Dte (OCT 2023 TO DEC 2023) |  | Junior Engineer | BILL/01202/2023-2024 | BP-2023-24-637 | 09/02/2024 | 0 | DHIRAJ BISWAS | 1.2 | 0 | 0
3356 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of 2 Nos. Big Dia Tube Well by Modified DTH - ODEX Method at Yong Tong Tea Gargen Piped Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. |  | Junior Engineer | ORD/000016/2024-2025 | 532/JD | 28/06/2024 | 30 | EFFLUENT AND WATERTREATEMENT ENGINEERS(P) LTD. | 33.23 | 0 | 100
3357 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 3rd Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-A) |  | Junior Engineer | ORD/000096/2023-2024 | 335/JD | 22/05/2023 | 30 | BAJRANG ENTERPRISE | 7.79 | 7.73 | 100
3358 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Sinking of Big Dia Tube well by Modified DTH - ODEX Method at 5th & 6th tube well site of Nagaisuree Tea Garden Piped Water Supply Scheme of Matiali Block in connection with Jal Jeevan Mission under Jalpaiguri Division, PHE Dte. |  | Junior Engineer | ORD/000108/2024-2025 | 1361/JD | 11/09/2024 | 30 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 35.23 | 27.14 | 100
3359 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Construction of different components of Rejuvenation of Nagaisuree Tea Garden PWSS i.e. 4th Site Boundary Walls, Rising Main etc. in connection with Jal Jeevan Mission at Block - Matiali under Jalpaiguri Division, P.H.E.Dte. (Part-B) |  | Junior Engineer | ORD/000293/2023-2024 | 1414/JD | 03/10/2023 | 30 | ARUP SARKAR | 7.02 | 6.97 | 100
3360 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000093/2023-2024 | 1052/JD | 24/08/2023 | 0 | Resource Division | 23.38 | 0 | 0
3361 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Installation of two tank chlorination system at Rejuvenation of Nagaisuree Tea Garden Area Piped Water Supply Scheme(TW-I) and other adjacent water supply scheme UNDER JJM under METELI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. |  | Junior Engineer | ORD/000665/2025-2026 | 1084/HQ/NMD | 15/05/2025 | 7 | D.K. & SONS | 0.79 | 0 | 0
3362 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector at REJUVENATION OF NAGAISUREE TEA GARDEN PWSS for T/W No. V and VI in the district of Jalpaiguri under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000848/2024-2025 | 587/NMD | 07/02/2025 | 30 | ALPHA ENTERPRISE | 27.14 | 0 | 0
3363 | Jalpaiguri Division | RWS Jalpaiguri Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000079/2023-2024 | 1061/JD | 24/08/2023 | 0 | Resource Division | 1.25 | 0 | 0
3364 | Northern Mechanical | RWS Jalpaiguri Sub-Division | New Service Connection Charge for Reju. of Jogeshchandra TG, TW NO-III, KRANTI CCC APPLICATION NO. 4003373903 Reference ID : 403190124 |  | Junior Engineer | BILL/00210/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3365 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Infrastructure development cost for new service connection at Reju. of Jogeshchandra TG, TW NO-III, KRANTI CCC APPLICATION NO. 100000103458 Reference ID : 860295868 |  | Junior Engineer | BILL/00211/2024-2025 | BP/24-25/25 | 09/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 11.46 | 0 | 0
3366 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  | Junior Engineer | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
3367 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  | Junior Engineer | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
3368 | Northern Mechanical | RWS Jalpaiguri Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF JOGESH CHANDRA TG AREA PWSS, TW no III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  | Junior Engineer | ORD/000428/2023-2024 | 1345/NMD | 08/08/2023 | 481 | SAIKAT SINHA | 11.35 | 7.83 | 50
3369 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Dakhsin Dangapara Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000047/2022-2023 | 940/JD | 18/04/2022 | 15 | SUKES BASU MAJUMDAR | 1.25 | 1.25 | 100
3370 | Jalpaiguri Division | Jalpaiguri Division | Restoration of damaged DI pipeline at Patkidaha Piped W/S Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000100/2022-2023 | 1312/JD | 15/06/2022 | 15 | M/S SIBU DEY AND CO. | 1.82 | 1.24 | 100
3371 | Jalpaiguri Division | Jalpaiguri Division | Construction of Boundary Wall, Pathway, Drain, Providing FHTC, IEP Washout etc. at 3rd TW Site for Patkidaha PWSS icw JJM under Jalpaiguri Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000140/2024-2025 | 1529/JD | 01/10/2024 | 273 | SADHAN KARMAKAR | 15.77 | 0 | 40
3372 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000223/2022-2023 | 1852/JD | 16/09/2022 | 21 | SADHAN KARMAKAR | 2.8 | 2.58 | 1
3373 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Dambari Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000492/2021-2022 | 1935/JD | 29/11/2021 | 15 | KULDIP KAPOOR | 1.47 | 0 | 100
3374 | Jalpaiguri Division | Jalpaiguri Division | Retrofitting of distribution pipeline network within Patkidaha Mouza (Phase-I) of Patkidaha Water Supply Scheme at Dhupguri Development Block under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000493/2021-2022 | 1936/JD | 29/11/2021 | 15 | PRABIR SHOME | 3.75 | 3.63 | 1
3375 | Jalpaiguri Division | Jalpaiguri Division | Retrofittings of distribution pipeline network within Dambari Mouza (Phase-II) of Patkidaha Water Supply Scheme at Dhupguri development Block under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000527/2023-2024 | 1786/JD | 08/12/2023 | 21 | KULDIP KAPOOR | 4.3 | 4.03 | 100
3376 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000090/2023-2024 | 1062/JD | 24/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
3377 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for REJU PATKIDHAHA, T/W No. III, under DHUPGURI CCC [APPLICATION NO. 4003328075 , Reference ID : 403153542] | Assistant Engineer,HQ | Junior Engineer | BILL/01997/2023-2024 | BP/23-24/308 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.63 | 0 | 0
3378 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
3379 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for REJUVENATION OF PATKIDAHA PWSS, TW NO- III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000026/2023-2024 | 476/NMD | 26/04/2023 | 30 | BONANZA ENTERPRISE | 11.5 | 11.49 | 100
3380 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3381 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection in connection with Jaldhara / Jalswapna near Dhangkali road, Simul Jhora and allied area for Purba Duramari Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. (Phase-IV) |  | Junior Engineer | ORD/000125/2023-2024 | 803/JD. | 24/07/2023 | 207 | DEEP CONSTRUCTION | 10.93 | 4.19 | 40
3382 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000096/2023-2024 | 1051/JD | 24/08/2023 | 0 | Resource Division | 3.45 | 0 | 0
3383 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | New Service Connection Charge for new service connection at REJUVENATION OF PURBA DURAMARI PWSS,T/W-III, GAIRKATA CCC APPLICATION NO. 4003460491 Reference ID : 403255265 |  | Junior Engineer | BILL/00974/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.82 | 0 | 0
3384 | Northern Mechanical | Jalpaiguri Sadar Sub-Division | Infrastructure development cost for new service connection at REJUVENATION OF PURBA DURAMARI PWSS,T/W-III, GAIRKATA CCC APPLICATION NO. 100000115667 Reference ID : 860308377 |  | Junior Engineer | BILL/00975/2024-2025 | BP/24-25/166 | 14/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 15.66 | 0 | 0
3385 | Jalpaiguri Division | Jalpaiguri Division | Construction of different components of Jhar Salbari PWSS i.e. TW, Pump House, Water distribution Network, OHR, RISING MAIN, FHTC etc. in connection with Jal Jeevan Mission at Block - Dhupguri Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000041/2023-2024 | 139/JD | 28/04/2023 | 795 | ALLIED INSTRUMENTS | 310.52 | 157.24 | 10
3386 | Jalpaiguri Division | Jalpaiguri Division | Balance Laying Distribution System and Providing Functional House Hold Tap Connection in connection with JJM at Jhar Salbari Piped Water Supply Scheme under Jalpaiguri Division, P.H.E.Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000425/2024-2025 | 2268/JD | 04/12/2024 | 45 | J.M. CONSTRUCTION | 32.13 | 0 | 0
3387 | Jalpaiguri Division | Jalpaiguri Division | Sinking of 3rd Tube well by Reverse Rotary Method of drilling inlucing Construction of Pump House (3.6m x 2.4m) and Laying Rising main for Jhar Salbari PWSS under Dhupguri Block icw Jal Jeevan Mission under Jalpaiguri Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000607/2024-2025 | 454/JD | 10/03/2025 | 50 | M/S S. G. ENTERPRISE | 17.55 | 0 | 0
3388 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000039/2023-2024 | 1111/JD | 24/08/2023 | 0 | Resource Division | 20.09 | 0 | 0
3389 | Jalpaiguri Division | Jalpaiguri Division | Material Requisition To Resource Division | Assistant Engineer,HQ | Junior Engineer | RTOR000130/2023-2024 | 1844/JD | 15/12/2023 | 0 | Resource Division | 8.57 | 0 | 0
3390 | Northern Mechanical | Jalpaiguri Division | New Service Connection Charge for JHAR SHALBARI, T/W-II, under DHUPGURI CCC APPLICATION NO. 4003364367 Reference ID : 403181756 | Assistant Engineer,HQ | Junior Engineer | BILL/00131/2024-2025 | BP/24-25/01 | 10/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.75 | 0 | 0
3391 | Northern Mechanical | Jalpaiguri Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Dhupguri Block) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000001/2025-2026 | 960/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 86.31 | 0 | 0
3392 | Northern Mechanical | Jalpaiguri Division | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. | Assistant Engineer,HQ | Junior Engineer | ORD/000097/2025-2026 | 1108/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 547.59 | 0 | 0
3393 | Northern Mechanical | Jalpaiguri Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for JHAR SALBARI PWSS, TW no I and II in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/000165/2023-2024 | 1207/NMD | 26/07/2023 | 829 | SUBODH KUMAR BANIK | 20.26 | 0 | 60
3394 | Northern Mechanical | Jalpaiguri Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: DHUPGURI, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer,HQ | Junior Engineer | ORD/001050/2024-2025 | 32/NMD | 06/01/2025 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 15.32 | 0 | 0
3395 | Northern Mechanical | Jalpaiguri Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
3396 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000070/2023-2024 | 1075/JD | 24/08/2023 | 0 | Resource Division | 1.55 | 0 | 0
3397 | Jalpaiguri Division | Northern Mechanical Division | Material Requisition To Resource Division | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | RTOR000121/2023-2024 | 1835/JD | 15/12/2023 | 0 | Resource Division | 0.71 | 0 | 0
3398 | Northern Mechanical | Northern Mechanical Division | New Service Connection Charge for PRAYAGPUR PWSS, TW NO I, BANARHAT CCC. APPLICATION NO. 4003506434 Reference ID : 403286480 | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | BILL/01351/2024-2025 | BP/24-25/244 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.66 | 0 | 0
3399 | Northern Mechanical | Northern Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for PRAYAGPUR PWSS, TW NO I in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000237/2023-2024 | 1249/NMD | 31/07/2023 | 763 | KARMAKAR CONSTRUCTION | 10.96 | 0 | 90
3400 | Northern Mechanical | Northern Mechanical Division | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District (BANARHAT Block ) under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/000987/2024-2025 | 11/NMD | 06/01/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 57.53 | 0 | 0
3401 | Northern Mechanical | Northern Mechanical Division | Yard lighting arrangement at Head Work Site for Different PWSS under JJM in the BLOCK: BANARHAT, DISTRICT: JALPAIGURI under Northern Mechanical Division, P.H.E. Dte. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001041/2024-2025 | 29/NMD | 06/01/2025 | 30 | DIAMOND ELECTRICAL WORKS | 12.26 | 0 | 0
3402 | Northern Mechanical | Northern Mechanical Division | Installation of two tank chlorination system at different water supply scheme UNDER JJM under DHUPGURI Block under Northern Mechanical Division, P.H.E. Dte., Dist.- Jalpaiguri. | Assistant Engineer , Head Quarters , NMD,Assistant Engineer,HQ | Junior Engineer | ORD/001137/2024-2025 | 53/DSD | 10/03/2025 | 15 | ASHWIRBAD WOOD CRAFT | 2.47 | 0 | 0
3403 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of JURANTI T.G. Area piped Water Supply Scheme at Metiali Block under Jalpaiguri Division, PHE Dte. (PART-B) |  | Junior Engineer | ORD/000093/2020-2021 | 1277/JD | 18/11/2020 | 90 | NARAYAN CHANDRA SAHA | 43.68 | 0 | 80
3404 | Jalpaiguri Division | Jalpaiguri Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of PALASHBARI TEA GARDEN area piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte. (Phase-I) |  | Junior Engineer | ORD/000115/2020-2021 | 1280/JD | 18/11/2020 | 45 | SANKAR DAS | 16.96 | 33.88 | 0
3405 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
3406 | Jalpaiguri Division |  | Construction approach with paver block inside the premises and land development at HW site & 2nd TW Site of Damdim TG Piped Water Supply Scheme under Jalpaiguri Division, P.H.E. Dte. |  |  | ORD/000081/2025-2026 | 100/JSSD | 30/05/2025 | 306 | JAYA SARKAR | 6.37 | 0 | 0
3407 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Kranti, Matiali, Nagrakata & balance of Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000092/2024-2025 | 1177/JD | 23/08/2024 | 65 | RANGALIBAZNA UNEMPLOYED YOUTH WELFARE SOCIETY | 28.65 | 0 | 0
3408 | Jalpaiguri Division |  | Construction of different components of Damdim Tea Garden PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000281/2023-2024 | 1257/JD | 13/09/2023 | 607 | PRASENJIT BASAK | 297.11 | 188.6 | 40
3409 | Jalpaiguri Division |  | Balance work of Distribution System and Functional Household Tap Connection (FHTC) including Different Components of Damdim TG PWSS i.e. TW, Pump House, Boundary Wall, Rising main etc. in connection with Jal Jeevan Mission at Block-Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000430/2024-2025 | 2274/JD | 05/12/2024 | 90 | PRASENJIT BASAK | 91.26 | 0 | 0
3410 | Jalpaiguri Division |  | Estimate for Balance work of Water Distribution Network in Damdim Tea Garden PWSS in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000801/2023-2024 | 569/JSSD | 05/03/2024 | 30 | PRABIR SHOME | 9.05 | 7.79 | 100
3411 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000051/2024-2025 | 2071/JD | 25/11/2024 | 0 | Resource Division | 38.02 | 0 | 0
3412 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 2017/JD | 09/01/2024 | 0 | Resource Division | 12.02 | 0 | 0
3413 | Northern Mechanical |  | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No.I, under ODLABARI CCC, [APPLICATION NO. 4003325562, Reference ID : 403151430] |  |  | BILL/01983/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3414 | Northern Mechanical |  | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000098645, Reference ID : 860290455] |  |  | BILL/01984/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4 | 0 | 0
3415 | Northern Mechanical |  | New Service Connection Charge for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 4003325572, Reference ID : 403151429] |  |  | BILL/01985/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3416 | Northern Mechanical |  | Infrastructure Cost for DAMDIM TEA GARDEN, T/W No. II, under ODLABARI CCC, [APPLICATION NO. 100000098644, Reference ID : 860290454] |  |  | BILL/01986/2023-2024 | BP/23-24/306 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.25 | 0 | 0
3417 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
3418 | Northern Mechanical |  | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  |  | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
3419 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara /Jal Sapna under the command area of Argi Goralbari piped Water Supply Scheme at Jalpaiguri Block under Jalpaiguri Division, PHE Dte. (PART-D) |  |  | ORD/000183/2020-2021 | 1498/JD | 22/12/2020 | 30 | BISWAJIT BHADURI | 17.51 | 21.53 | 1
3420 | Jalpaiguri Division |  | Providing Functional Household Tap Connection (FHTC) in connection with Jal Sapna under the command area of Patkidaha and Jakhaikona Mouza under Patkidaha piped Water Supply Scheme at Dhupguri Block under Jalpaiguri Division, PHE Dte |  |  | ORD/000326/2020-2021 | 209/JD | 11/02/2021 | 30 | PRABIR SHOME | 21.88 | 0 | 1
3421 | Jalpaiguri Division |  | PROVIDING FHTC FOR PURBA MAGURMARI PWSS |  |  | VCH/000239/2021-2022 | 192/21-22 | 02/08/2021 | 0 | A.P CONSTRUCTION | 25.1 | 0 | 0
3422 | Jalpaiguri Division |  | Supply of fuel (Diesel) for vehicle no. WB-71B-9430 for the month of February-2024 |  |  | BILL/00097/2024-2025 | BP-2024-25-64 | 14/05/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3423 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month April'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00130/2024-2025 | BP-2024-25-97 | 22/05/2024 | 0 | FILL & SMILE | 0.36 | 0 | 0
3424 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00131/2024-2025 | BP-2024-25-98 | 22/05/2024 | 0 | FILL & SMILE | 0.28 | 0 | 0
3425 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of March,2024 Vide Vehicle no-WB71B9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00320/2024-2025 | BP-2024-25-182 | 28/06/2024 | 0 | FILL & SMILE | 0.14 | 0 | 0
3426 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of April,2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/00321/2024-2025 | BP-2024-25-183 | 28/06/2024 | 0 | FILL & SMILE | 0.29 | 0 | 0
3427 | Jalpaiguri Division |  | Supply of Engine oil, Gear Oil and Kool plus Bill for the Month of April,2024 vide Vehicle No-WMA-2539 under Assistant Engineer RWS, Jalpaiguri RWS Sub Division, PHE Dte |  |  | BILL/00324/2024-2025 | BP-2024-25-181 | 28/06/2024 | 0 | FILL & SMILE | 0.07 | 0 | 0
3428 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month March'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00384/2024-2025 | BP-2024-25-269 | 30/07/2024 | 0 | FILL & SMILE | 0.19 | 0 | 0
3429 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month January'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00402/2024-2025 | BP-2024-25-240 | 26/07/2024 | 0 | FILL & SMILE | 0.19 | 0 | 0
3430 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month July'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00523/2024-2025 | BP-2024-25-294 | 14/08/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
3431 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00873/2024-2025 | BP-2024-25-497 | 07/10/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3432 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 76 7338) |  |  | BILL/00929/2024-2025 | BP-2024-25-522 | 29/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3433 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00932/2024-2025 | BP-2024-25-523 | 29/11/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3434 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Aug'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00965/2024-2025 | BP-2024-25-532 | 13/12/2024 | 0 | FILL & SMILE | 0.21 | 0 | 0
3435 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 78 3405) |  |  | BILL/00966/2024-2025 | BP-2024-25-530 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3436 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 76 7338) |  |  | BILL/00969/2024-2025 | BP-2024-25-529 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3437 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Nov'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00979/2024-2025 | BP-2024-25-533 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3438 | Jalpaiguri Division |  | Bill for supply of fuel (HSD) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Oct'2024 (Vehicle No. WB 71 B 9430) |  |  | BILL/00980/2024-2025 | BP-2024-25-531 | 13/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3439 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of October'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01036/2024-2025 | BP-2024-25-560 | 20/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0
3440 | Jalpaiguri Division |  | Supply of Fuel bill for the Month of November'2024 Vide Vehicle no-WB71B-9586 under Jalpaiguri Sadar Sub-Division, PHE Dte |  |  | BILL/01037/2024-2025 | BP-2024-25-561 | 20/12/2024 | 0 | FILL & SMILE | 0.15 | 0 | 0
3441 | Jalpaiguri Division |  | Bill for supply of fuel (Petrol) for the official vehicle of Office of the Assistant Engineer , Jalpaiguri Sadar Sub Division, PHE Dte. for the month Sept'2024 (Vehicle No. WB 71 B 9586) |  |  | BILL/01038/2024-2025 | BP-2024-25-559 | 20/12/2024 | 0 | FILL & SMILE | 0.23 | 0 | 0
3442 | Jalpaiguri Division |  | SOIL TEST CONDUCTION AND SUBMISSION OF REPORT AT DIFFERENT HEAD WORKS SITE OF DIFFERENT PWSS. |  |  | BILL/01301/2023-2024 | BP-2023-24-693 | 07/03/2024 | 0 | DR. AMBARISH GHOSH | 34.33 | 0 | 0
3443 | Jalpaiguri Division |  | Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/05/2025 to 30/06/2025) |  |  | ORD/000032/2025-2026 | 819/JD | 30/04/2025 | 61 | PARAMJYOTI ENTERPRISE | 0.8 | 0.4 | 100
3444 | Jalpaiguri Division |  | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle)with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/05/2025 to 30/06/2025) |  |  | ORD/000037/2025-2026 | 824/JD | 30/04/2025 | 61 | PARAMJYOTI ENTERPRISE | 0.8 | 0.79 | 100
3445 | Jalpaiguri Division |  | Designing, fabrication and erection of Display Board including vinyl pasting ( 0.9 mtr x 0.6 mtr) for demarcation of land at different PWSS work sites in connection with JJM at MALBAZAR BLOCK in the district of Jalpaiguri, under Jalpaiguri Division , P.H.E. Dte. |  |  | ORD/000048/2025-2026 | 80/JSSD | 30/05/2025 | 30 | GURUKUL INFOTECH | 3.66 | 0 | 100
3446 | Jalpaiguri Division |  | Execution of Wall writing for creating awareness program in connection with Jal Jeevan Mission for Mal Block under Jalpaiguri Division P.H.E. Dte. |  |  | ORD/000060/2024-2025 | 943/JD | 07/08/2024 | 491 | GURUKUL INFOTECH | 4.83 | 0 | 100
3447 | Jalpaiguri Division |  | Construction of different components of Oodlabari Tea Garden (Zone-I) PWSS i.e. OHR,TW, Pump Houses, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E. Dte. of North Bengal Circle-I, PHE Dte. |  |  | ORD/000065/2024-2025 | 936/JD | 07/08/2024 | 300 | SUJIT KUMAR SAHA | 183.05 | 0 | 0
3448 | Jalpaiguri Division |  | Continuation order for the work of "Providing support service for survey work using Total Station & Auto level instruments and other moderate instruments, machinery along with Surveyor and Surveyor Assistant, Tools and Plants & machinery all complete for providing PHE Services at different Water Supply Scheme under Jalpaiguri Division P.H.E. Dte. (From 01.07.2024 to 31.08.2024)" |  |  | ORD/000091/2024-2025 | 531/JD | 28/06/2024 | 61 | GURUKUL INFOTECH | 3.16 | 3.16 | 100
3449 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission. Period from 01/08/2024 to 31/01/2025. |  |  | ORD/000093/2024-2025 | 125/JSSD | 18/07/2024 | 184 | APIKUL ALI | 0.88 | 1.29 | 0
3450 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st August 2024 to 31st January 2025) |  |  | ORD/000112/2024-2025 | 142/1/JSSD | 29/07/2024 | 184 | APIKUL ALI | 0.88 | 0.29 | 0
3451 | Jalpaiguri Division |  | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition used as an Inspection Vehicle of Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (For the period from 01/07/2025 to 31/07/2025)" |  |  | ORD/000122/2025-2026 | 1498/JD | 30/06/2025 | 31 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 100
3452 | Jalpaiguri Division |  | Continuation Order for the Work "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali, Nagrakata, Banarhat, Dhupguri & other Blocks. (For the period from 01/07/2025 to 31/07/2025)" |  |  | ORD/000127/2025-2026 | 1503/JD | 30/06/2025 | 31 | PARAMJYOTI ENTERPRISE | 0.4 | 0 | 100
3453 | Jalpaiguri Division |  | Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali & other Blocks. (For the period from 01/08/2025 to 30/09/2025) |  |  | ORD/000152/2025-2026 | 1733/JD | 31/07/2025 | 61 | DHIRAJ BISWAS | 0.8 | 0 | 50
3454 | Jalpaiguri Division |  | Construction of different components of Oodlabari Tea Garden (Zone-II) PWSS i.e. TW, Pump Houses, OHR, Boundary Walls, Water Distribution Network, FHTC, Rising Main etc. in connection with Jal Jeevan Mission at Block - Mal under Jalpaiguri Division, P.H.E.Dte. |  |  | ORD/000158/2023-2024 | 800/JD. | 24/07/2023 | 892 | GHANASHYAM SARKAR | 281.55 | 178.49 | 40
3455 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C.on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM From 01.09.2024 to 28.02.2025 (Vehicle No.: - WB 76 9978) |  |  | ORD/000159/2024-2025 | 206/JSSD | 30/08/2024 | 182 | APIKUL ALI | 0.88 | 2.1 | 0
3456 | Jalpaiguri Division |  | Construction approach with paver block inside the premises and land ment at HW site & 2nd TW Site of Oodlabari TG (Z-I) Piped Water Supply Scheme under Jalpaiguri Division, PHE Dte. |  |  | ORD/000178/2025-2026 | 170/JSSD | 24/07/2025 | 30 | SUBHANKAR DEY | 6.57 | 0 | 0
3457 | Jalpaiguri Division |  | Continuation Work Order for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali & other Blocks. (For the period from 01/10/2025 to 30/11/2025)". |  |  | ORD/000200/2025-2026 | 1999/JD | 25/09/2025 | 61 | DHIRAJ BISWAS | 0.8 | 0 | 0
3458 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000212/2024-2025 | 137/JSSD | 29/07/2024 | 60 | DHIRAJ BISWAS | 0.88 | 0.44 | 50
3459 | Jalpaiguri Division |  | Continuation for "Hiring of 1 (One) Number Maxi Cab (Inspection Vehicle) with engine capacity less than or equal to 2000 C.C. on hire basis including driver and fuel in good condition under the Assistant Engineer, Jalpaiguri Sadar Sub Division, P.H.E. Dte. for inspection of different PWSS under Mal, Kranti, Matiali & other Blocks. (For the period from 01/12/2025 to 31/12/2025)". |  |  | ORD/000473/2025-2026 | 2423/JD | 21/11/2025 | 30 | DHIRAJ BISWAS | 0.4 | 0 | 0
3460 | Jalpaiguri Division |  | Continuation work of " Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte.(with valid Taxi permit) for supervision and different works at different blocks under Jal Jeevan Mission". Period from 01.02.2025 to 31.07.2025. (Vichle No. WB 78 3405) |  |  | ORD/000696/2024-2025 | 418/JSSD | 28/01/2025 | 181 | APIKUL ALI | 0.88 | 0.69 | 0
3461 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission.(w.e.f 1st February 2025 to 31st July 2025) |  |  | ORD/000697/2024-2025 | 417/JSSD | 28/01/2025 | 181 | APIKUL ALI | 0.88 | 0.79 | 0
3462 | Jalpaiguri Division |  | Continuation of Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. (Vehicle No-WB 71B 9586) w.e.f. 1.02.2025-31.07.2025. |  |  | ORD/000703/2024-2025 | 434/JSSD | 31/01/2025 | 181 | DHIRAJ BISWAS | 0.88 | 0.15 | 30
3463 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under Jal Jeevan Mission. |  |  | ORD/000819/2023-2024 | 524/JSSD | 29/01/2024 | 182 | APIKUL ALI | 0.88 | 0.54 | 70
3464 | Jalpaiguri Division |  | Supply of 1 (one) Maxi Cab with engine capacity less than or equal to 2000 C.C. on monthly basis including driver under Office of the Assistant Engineer, Jalpaiguri sadar sub Division, P.H.E. Dte. (with valid Taxi permit) for supervision and inspection of different works at different blocks under JJM. |  |  | ORD/000820/2023-2024 | 525/JSSD | 29/01/2024 | 182 | DHIRAJ BISWAS | 0.88 | 0.77 | 0
3465 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 2029/JD | 19/11/2024 | 0 | Resource Division | 108.92 | 0 | 0
3466 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1090/JD | 24/08/2023 | 0 | Resource Division | 24.92 | 0 | 0
3467 | Jalpaiguri Division |  | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 2070/JD | 10/01/2024 | 0 | Resource Division | 17.24 | 0 | 0
3468 | Northern Mechanical |  | Infrastructure development cost for new service connection at ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 100000109306 Reference ID : 860301266 |  |  | BILL/00409/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 4.48 | 0 | 0
3469 | Northern Mechanical |  | New Service Connection Charge for ODLABARI TG, TW NO-II, OODLABARI CCC APPLICATION NO. 4003424001 Reference ID : 403230049 |  |  | BILL/00410/2024-2025 | BP/24-25/81 | 07/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.69 | 0 | 0
3470 | Northern Mechanical |  | New Service Connection Charge for ODLABARI TEA GARDEN, T/W No. I, under ODLABARI CCC, [APPLICATION NO. 4003266395, Reference ID : 403105528] |  |  | BILL/01281/2023-2024 | 23-24/160&168 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.91 | 0 | 0
3471 | Northern Mechanical |  | Infrastructure Cost for ODLABARI TEA GARDEN,T/W No. I, under ODLABARI CCC, [APPLICATION NO. 100000093886, Reference ID : 860285546] |  |  | BILL/01282/2023-2024 | 23-24/160&168 | 12/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.88 | 0 | 0
3472 | Northern Mechanical |  | Solarisation of WBSEDCL Energised Electrical Installation at different piped water supply schemes in connection with Jal Jeevan Mission in the Jalpaiguri District( Mal Block) under Northern Mechanical Division, P.H.E. Dte. |  |  | ORD/000003/2025-2026 | 962/NMD | 03/04/2025 | 120 | SILIGURI VYAPAR PRIVATE LIMITED | 132.34 | 0 | 0
3473 | Northern Mechanical |  | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages under Different Water Supply Schemes at Different Block of Jalpaiguri District in West Bengal. |  |  | ORD/000096/2025-2026 | 1106/NMD | 16/05/2025 | 180 | WEBEL TECHNOLOGY LIMITED | 357.12 | 0 | 0
3474 | Northern Mechanical |  | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for ODLABARI TEA GARDEN PWSS,at TW NO I,II,III in the district of Jalpaiguri under Northern Mechanical Division, PHE Dte. |  |  | ORD/000757/2023-2024 | 1585/NMD | 08/09/2023 | 754 | CHOWDHURY AND BASU ENTERPRISE | 42.08 | 23.04 | 68
Total | [10 empty] | 145139.81 | 39549.22