## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Balurghat Division | Balurghat Sadar Sub-Division | Formal work order for the work of Providing Functional Household Tap Connection Under Saila Pipe Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ | ORD/000055/2020-2021 | 1901/BD | 09/12/2020 | 60 | M/S. ANWESHA ENTERPRISE | 93.45 | 154.5 | 1
2 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for Siala PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer 1 HQ | ORD/000251/2021-2022 | 2196/BD | 28/09/2021 | 30 | RABIN KAMETH | 6.4 | 6.39 | 1
3 | Balurghat Division | Balurghat Division | Formal work order for the work of Providing Functional House Hold Tap Connection under Jal Swapna Programme for Alipur Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000159/2020-2021 | 193/BD | 20/01/2021 | 45 | KHITISH KARMAKAR | 48.46 | 76.24 | 1
4 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For ALIPUR PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000242/2021-2022 | 1809/BSSD | 01/10/2021 | 20 | KHITISH KARMAKAR | 4.78 | 4.7 | 1
5 | Balurghat Division | Balurghat Sadar Sub-Division | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for DANGRAM Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000023/2020-2021 | 1588/BD | 16/10/2020 | 45 | DIPESH BHOWMIK | 83.94 | 83.25 | 100
6 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for DANGRAM Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1588/BD dt. 16/10/2020 & Tender No. 102 of 2020-2021] |  | Junior Engineer Kushmandi | VCH/000504/2021-2022 | 8443/55 | 29/03/2022 | 0 | DIPESH BHOWMIK | 19.46 | 0 | 0
7 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection in connection with Retrofitting for K.D. Trimohini Zone-II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000252/2022-2023 | 3942/BD | 31/03/2023 | 45 | SAPTADIP CONSTRUCTION | 50.3 | 0 | 0
8 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for K. D. Trimohini Zone II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) |  | Junior Engineer Hili | ORD/000339/2021-2022 | 1919/BSSD | 01/12/2021 | 25 | APURBA KUMAR SARKAR | 4.85 | 0.94 | 0
9 | Balurghat Division | Balurghat Division | Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of K.D Trimohini Piped Water Supply Scheme (Zone - II) at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000537/2021-2022 | 549/RWS | 03/12/2021 | 15 | M/S. SOBHA & CO. | 4.31 | 4.31 | 1
10 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for K. D. Trimohini Zone II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1919/BSSD Dated :- 01/12/2021 & Tender No. 414 of 2021-2022] |  | Junior Engineer Hili | VCH/000163/2022-2023 | BP-2022-23-21 | 16/04/2022 | 0 | APURBA KUMAR SARKAR | 3.52 | 0 | 0
11 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase-II). |  | Junior Engineer Balurghat | ORD/000167/2022-2023 | 4005/BD | 09/01/2023 | 60 | M/S. SARKAR ENTERPRISE | 52.66 | 0 | 0
12 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Balurghat | ORD/000320/2021-2022 | 2064/BD | 17/09/2021 | 15 | ENVIROTECH SOLUTIONS | 2.82 | 2.28 | 1
13 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division |  | Junior Engineer Balurghat | RTOR000008/2022-2023 | 832/BD | 11/05/2022 | 0 | Resource Division | 3.36 | 0 | 0
14 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1920/BSSD Dated :- 01/12/2021 & Tender No. 375 of 2021-2022] |  | Junior Engineer Balurghat | VCH/000161/2022-2023 | BP-2022-23-24 | 16/04/2022 | 0 | MAYA CONSTRUCTION | 4.18 | 0 | 0
15 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-XV by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000024/2023-2024 | 315/BD | 15/05/2023 | 60 | SUBODH KUMAR SAHA | 85.66 | 0 | 0
16 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-VIII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000034/2023-2024 | 452/BD | 01/06/2023 | 709 | KHITISH KARMAKAR | 92.95 | 0 | 20
17 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-IX by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000036/2023-2024 | 440/BD | 31/05/2023 | 60 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 95.24 | 0 | 0
18 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-XII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000102/2023-2024 | 1133/BD | 11/08/2023 | 60 | CHIRANJIB DAS | 87.92 | 0 | 0
19 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection of Zone-III by Retrofitting of Tapan Eastern Sector under Sub - Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000104/2023-2024 | 1143/BD | 14/08/2023 | 825 | CHOWDHURY CONSTRUCTION | 94.7 | 0 | 65
20 | Balurghat Division | Balurghat Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Hili & Tapan Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000134/2024-2025 | 1942/BD | 27/09/2024 | 20 | M/S. A.D. ENTERPRISE | 3.83 | 0 | 100
21 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - IX under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000135/2024-2025 | 1945/BD | 27/09/2024 | 20 | SUKUMAR GOSWAMI | 2.98 | 0 | 0
22 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - III under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000136/2024-2025 | 1946/BD | 27/09/2024 | 186 | M/S. BANI CONSTRUCTIUON | 3.43 | 0 | 100
23 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - XII under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000137/2024-2025 | 1947/BD | 27/09/2024 | 20 | ANIMA CONSTRUCTION | 2.87 | 0 | 0
24 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - XI under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000138/2024-2025 | 1948/BD | 27/09/2024 | 20 | AMITAVA MITRA CONTRACTOR & ORDER SUPPLIER | 2.74 | 0 | 0
25 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone ¿ VII under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000139/2024-2025 | 1949/BD | 27/09/2024 | 20 | MAA CHANCHALA CONSTRUCTION | 2.74 | 0 | 0
26 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - XIII under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000145/2024-2025 | 2033/BD | 01/10/2024 | 20 | SARKAR ENTERPRISE | 2.87 | 0 | 0
27 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - XV under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000151/2024-2025 | 2113/BD | 23/10/2024 | 20 | A.K & COMPANY | 2.6 | 0 | 0
28 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - VIII under Tapan Eastern Sector of Tapan Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000168/2024-2025 | 2255/BD | 13/11/2024 | 20 | N H CONSTRUCTION | 3.43 | 0 | 0
29 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection at Zone- X of Tapan Eastern Sector under Sub Surface Water Based Piped Water Supply Scheme for Tapan Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000182/2024-2025 | 2433/BD | 11/12/2024 | 60 | PRADIP KUMAR PAUL | 51.04 | 0 | 0
30 | Balurghat Division | Balurghat Division | Widenning and strengthing of existing road for movement of heavy vehicle near WTP and towards Intake well site of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000226/2022-2023 | 3831/BD | 24/03/2023 | 20 | B M CONSTRUCTION | 2.68 | 2.67 | 1
31 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-XIII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000234/2022-2023 | 3902/BD | 29/03/2023 | 60 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 64.4 | 0 | 20
32 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-XIV by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000242/2022-2023 | 3925/BD | 30/03/2023 | 60 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 76.54 | 0 | 0
33 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-VII by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000245/2022-2023 | 3943/BD | 31/03/2023 | 960 | NILKAMAL BASAK | 82.45 | 0 | 20
34 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection of Zone-X by Retrofitting of Tapan Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000255/2022-2023 | 3963/BD | 31/03/2023 | 898 | TARAMA CONSTRUCTION | 69.71 | 0 | 15
35 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
36 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
37 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 121.85 | 55
38 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Tapan`,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
39 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Tapan`,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
40 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
41 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
42 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
43 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
44 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.94 | 55
45 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
46 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.8 | 55
47 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
48 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
49 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
50 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
51 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
52 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 10.76 | 55
53 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
54 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.31 | 55
55 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
56 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
57 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 9.21 | 55
58 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
59 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
60 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
61 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 17.89 | 55
62 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Hili,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
63 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Hili,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
64 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Hili,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
65 | Balurghat Division | Balurghat Sadar Sub-Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Patun More to Jordighi Road via Badalpur from (chainage 1.70 K.M to 13.50 K.M). | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | BILL/00192/2024-2025 | BP-2024-25-125 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 16.99 | 0 | 0
66 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 250 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Chakla Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000243/2022-2023 | 3922/BD | 30/03/2023 | 1216 | CALCON CONSTRUCTIONS | 445.61 | 117.75 | 65
67 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of additional distribution pipeline for the left out area, construction of approach road and other allied works within command area of Chakla Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000285/2024-2025 | 595/BD | 27/03/2025 | 60 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 58.81 | 0 | 0
68 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | RTOR000034/2023-2024 | 1839/BD | 18/06/2024 | 0 | Resource Division | 10.41 | 0 | 0
69 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | RTOR000061/2022-2023 | 2885/BD | 06/01/2023 | 0 | Resource Division | 15.55 | 0 | 0
70 | Malda Mechanical | Balurghat Sadar Sub-Division | : Payment for the quotation of PH NO-II of Chakla PWSS under Harirampur CCC | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | BILL/03553/2023-2024 | BP-2023-24-557 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 8.46 | 0 | 0
71 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of PH NO-I of Chakla PWSS under Harirampur CCC | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | BILL/03554/2023-2024 | BP-2023-24-558 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.42 | 0 | 0
72 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Chakla Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011982) | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000390/2023-2024 | 2398/MLMD | 28/07/2023 | 854 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 28.26 | 0 | 40
73 | Balurghat Division | Balurghat Division | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 842 | GHOSH BROTHERS | 2425.67 | 0 | 30
74 | Balurghat Division | Balurghat Division | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Trikul Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000162/2024-2025 | 2233/BD | 12/11/2024 | 30 | M/S. S. CONSTRUCTION | 15.59 | 0 | 0
75 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | RTOR000026/2024-2025 | 2316/BD | 22/11/2024 | 0 | Resource Division | 3.33 | 0 | 0
76 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | RTOR000045/2022-2023 | 2899/BD | 06/01/2023 | 0 | Resource Division | 8.82 | 0 | 0
77 | Malda Mechanical | Balurghat Division | Payment for the quotation of New Connection of PH NO-I of Trikul PWSS under Balurghat CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/03728/2023-2024 | BP-2023-24-698 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.79 | 0 | 0
78 | Malda Mechanical | Balurghat Division | Payment for the quotation of New Connection of PH NO-II of Trikul PWSS under Balurghat CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/03729/2023-2024 | BP-2023-24-699 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.43 | 0 | 0
79 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Trikul Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014305) | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000800/2023-2024 | 2560/MLMD | 04/08/2023 | 802 | M/S. KUNDU CONSTRACTION | 26.56 | 0 | 80
80 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
81 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
82 | Balurghat Division | RWS Balurghat Sub-Division | Restoration of Udaipur Mahipaldighi road from chainage 0.70 km to 4.00 km (L/S) under Chandipur PWSS at Kushmandi Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00203/2024-2025 | BP-2024-25-130 | 12/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.75 | 0 | 0
83 | Balurghat Division | RWS Balurghat Sub-Division | Restoration of Udaipur Mahipaldighi road from chainage 0.00 km to 8.00 km under Chandipur PWSS at Kushmandi Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00212/2024-2025 | BP-2024-25-133 | 13/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 11.36 | 0 | 0
84 | Balurghat Division | RWS Balurghat Sub-Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Chandipur Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000217/2022-2023 | 3874/BD | 28/03/2023 | 918 | ALOK ENTERPRISE | 1145.24 | 0 | 15
85 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000035/2023-2024 | 1841/BD | 18/06/2024 | 0 | Resource Division | 23.01 | 0 | 0
86 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000066/2022-2023 | 2892/BD | 06/01/2023 | 0 | Resource Division | 27.21 | 0 | 0
87 | Central Drilling | RWS Balurghat Sub-Division | Providing drilling crew and other allied works for construction of tube well (250mm x 150mm x 120 mtrs. depth) by utilising Departmental machineries for Chandipur W/S Scheme (TW-II) Kushmandi block under Dakshin Dinajpur district, CDD, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000428/2022-2023 | 1834/CDD | 06/01/2023 | 30 | CHANDA ENTERPRISE | 9.69 | 7.33 | 0
88 | Central Drilling | RWS Balurghat Sub-Division | Providing drilling crew and other allied works for construction of tube well (250mm x 150mm x 120 mtrs. depth) by utilising Departmental machineries for Chandipur W/S Scheme (TW-I) Kushmandi block under Dakshin Dinajpur district, CDD, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000429/2022-2023 | 1833/CDD | 06/01/2023 | 30 | CHANDA ENTERPRISE | 9.69 | 7.38 | 0
89 | Central Drilling | RWS Balurghat Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Chandipur W/S Scheme (TW-III), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000442/2022-2023 | 1938/CDD | 31/01/2023 | 30 | M/S P P ELECTRICALS | 9.42 | 7.11 | 0
90 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Chandipur, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000274/2023-2024 | 4003194054 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 7.63 | 7.63 | 100
91 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Chandipur, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000275/2023-2024 | 4003194056 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.1 | 6.1 | 100
92 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Chandipur, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000276/2023-2024 | 4003194055 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.86 | 4.86 | 100
93 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Chandipur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013174) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/001534/2023-2024 | 2099/MLMD | 04/07/2023 | 900 | PADMA ENGINEERING CO. | 38.21 | 24.38 | 63
94 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
95 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
96 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
97 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
98 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
99 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
100 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 10.94 | 55
101 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
102 | Balurghat Division | Balurghat Sadar Sub-Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Fatepur - Dehaband Road from (Chainage 0.00 KM to 10.00 Km) | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00125/2024-2025 | BP-2024-25-88 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 13.67 | 0 | 0
103 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.77 | 55
104 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000006/2024-2025 | 1840/BD | 18/06/2024 | 0 | Resource Division | 24.82 | 0 | 0
105 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000071/2022-2023 | 2890/BD | 06/01/2023 | 0 | Resource Division | 39.36 | 0 | 0
106 | Malda Mechanical | Balurghat Sadar Sub-Division | Additional quotation for PH-I of Baldu PWSS under Harirampur CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/01823/2024-2025 | BP-2024-25-456 | 23/08/2024 | 0 | W.B.S.E.D.C.LTD | 2.73 | 0 | 0
107 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of New Connection of PH NO-I of Baldu PWSS under Harirampur CCC in the District of dakshin Dinajpur | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/03662/2023-2024 | BP-2023-24-638 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.89 | 0 | 0
108 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of New Connection of PH NO-II of Baldu PWSS under Harirampur CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/03663/2023-2024 | BP-2023-24-639 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.1 | 0 | 0
109 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Baldu Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013519) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000349/2023-2024 | 2339/MLMD | 26/07/2023 | 120 | DAS ENTERPRISE. | 40.31 | 0 | 60
110 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
111 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
112 | Balurghat Division | Balurghat Sadar Sub-Division | Formal Work Order for the work of "Providing Functional House Hold Tap Connection for JAHARPUR piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte." |  | Junior Engineer (Civil) | ORD/000006/2020-2021 | 1371/BD | 29/09/2020 | 45 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 44.54 | 0 | 100
113 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Display Board at the entry point of different Swajal Gram (Har Ghar Jal Villages) as per departmental design and drawing in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. (For 78 nos Villages). |  | Junior Engineer (Civil) | ORD/000072/2023-2024 | 869/BD | 24/07/2023 | 30 | M/S. A.D. ENTERPRISE | 8.22 | 8.14 | 100
114 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water based Mini Piped Water Supply Scheme for Suripukur Mouza i.c.w. Retrofitting of Jaharpur PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil) | ORD/000240/2022-2023 | 3944/BD | 31/03/2023 | 985 | SARADA ENTERPRISE | 35.22 | 0 | 80
115 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing left out Functional House Hold Tap connection to make all the villages Swajal Gram under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur. |  | Junior Engineer (Civil) | ORD/000466/2021-2022 | 151/BD | 28/01/2022 | 35 | JUVENILE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 9.99 | 0 | 100
116 | Balurghat Division | Balurghat Division | Formal Work Order for the work of "Providing Functional House Hold Tap Connection for MAJHIGRAM piped water supply scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte." |  | Junior Engineer Balurghat | ORD/000010/2020-2021 | 1375/BD | 29/09/2020 | 45 | M/S. S. CONSTRUCTION | 47.43 | 0 | 100
117 | Balurghat Division | Balurghat Division | Restoration of damaged pipeline and allied works for retrofitting of Majhigram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer Balurghat | ORD/000228/2022-2023 | 3854/BD | 27/03/2023 | 45 | M/S. R.D. CONSTRUCTION | 21.08 | 0 | 75
118 | Balurghat Division | Balurghat Division | Installation of IEP, construction of Blower room, surface drain & platform including 03 months trial run for Improvement of Siala Piped Water Supply Scheme at Balurghat Block in District of Dakshin Dinajpur under Balurghat Division, PHE Dte, Govt. of West Bengal. |  | Junior Engineer 1 HQ,Junior Engineer Balurghat | ORD/000032/2023-2024 | 437/BD | 31/05/2023 | 585 | ZEOLITE FRESH INDIA | 18.69 | 0 | 96
119 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Instalation of IEP, Pump House, Boundary Wall & Approach Road for implementation of Saraihat Bajedonor Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000232/2022-2023 | 3906/BD | 29/03/2023 | 1277 | CHIRANJIB DAS | 660.02 | 335.39 | 85
120 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000015/2024-2025 | 2308/BD | 22/11/2024 | 0 | Resource Division | 2.94 | 0 | 0
121 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000033/2023-2024 | 831/BD | 14/07/2023 | 0 | Resource Division | 13.98 | 0 | 0
122 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000062/2022-2023 | 2874/BD | 06/01/2023 | 0 | Resource Division | 32.96 | 0 | 0
123 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000073/2023-2024 | 460/BD | 18/03/2024 | 0 | Resource Division | 10.43 | 0 | 0
124 | Central Drilling | Balurghat Sadar Sub-Division | Providing drilling crew and other allied works for construction of tube well (250mm x 150mm x 120 mtrs. depth) by utilising Departmental machineries for Saraihat Bajedonor W/S Scheme (TW-I & II) Kushmandi block under Dakshin Dinajpur district, CDD, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000430/2022-2023 | 1808/CDD | 04/01/2023 | 30 | PADMA ENGINEERING & CO. | 20.01 | 14.28 | 0
125 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Saraihat Bajedonor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013134) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000185/2023-2024 | 2111/MLMD | 05/07/2023 | 636 | ANIMA ENTERPRISE | 26.98 | 17.02 | 100
126 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SARAIHAT BAJEDONOR, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000284/2023-2024 | 4003194057 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.95 | 3.95 | 100
127 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SARAIHAT BAJEDONOR, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000285/2023-2024 | 4003194061 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.76 | 3.76 | 100
128 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
129 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.06 | 55
130 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
131 | Balurghat Division | Balurghat Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Fatepur - Dehaband Road from (Chainage 0.00 KM to 10.00 Km) | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00125/2024-2025 | BP-2024-25-88 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 13.67 | 0 | 0
132 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
133 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.84 | 55
134 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
135 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Makail & adjoining mouzas for Araziminapara Mouza at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000046/2020-2021 | 1882/BD | 07/12/2020 | 35 | M/S. R.D. CONSTRUCTION | 8.69 | 14.27 | 1
136 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000047/2020-2021 | 1883/BD | 07/12/2020 | 45 | MANAS KUMAR SAHA | 39.31 | 75.63 | 1
137 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Keshabpur Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000048/2020-2021 | 1884/BD | 07/12/2020 | 45 | SARADA ENTERPRISE | 14.89 | 26.32 | 1
138 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bhikanpur Mouza under Makail Piped Water Based Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000051/2020-2021 | 1887/BD | 07/12/2020 | 35 | RAJ KUMAR KUNDU | 3.17 | 5.33 | 1
139 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nakarna Mouza under Makail Piped Water Based Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000065/2020-2021 | 1976/BD | 18/12/2020 | 35 | RANJAN SARKAR | 3.02 | 5.59 | 1
140 | Balurghat Division |  | Allied pipe line laying work and washout pipe line work in connection with providing Functional House Hold Tap Connection for Makail PWSS under Jal Swapna Programme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  |  | ORD/000087/2022-2023 | 305/RWS | 02/06/2022 | 55 | RANJAN SARKAR | 1.94 | 0 | 100
141 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Mandahar Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000099/2020-2021 | 103/BD | 11/01/2021 | 35 | EIGHTY EIGHT CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.01 | 13.33 | 100
142 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Sarenga Mouza under Makail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000100/2020-2021 | 104/BD | 11/01/2021 | 35 | DIPU PRASAD. | 6.79 | 2.96 | 100
143 | Balurghat Division |  | Allied Work In Connection With Providing Functional House Hold Tap Connection for MAKAIL PWSS Under Jal Swapna Programme at KUSHMANDI Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000355/2021-2022 | 546/RWS | 03/12/2021 | 30 | MONDAL ENTERPRISE | 4.22 | 0.65 | 0
144 | Balurghat Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2020-2021 | 1997/BD | 22/12/2020 | 0 | Resource Division | 10.31 | 0 | 0
145 | Balurghat Division |  | Payment to Resource Division for Supply of Materials. (Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Makail Piped Water Supply Scheme) |  |  | VCH/000350/2021-2022 | BP-2021-22-78 | 11/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, PHED. | 4.81 | 0 | 0
146 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil) | ORD/000322/2021-2022 | 2066/BD | 17/09/2021 | 15 | ENVIROTECH SOLUTIONS | 2.77 | 2.77 | 1
147 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer (Civil) | RTOR000020/2023-2024 | 833/BD | 14/07/2023 | 0 | Resource Division | 1.94 | 0 | 0
148 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) (Work Order No. 1914/BSSD Dated - 01/12/2021 & Tender No. 408 of 2021-2022) |  | Junior Engineer (Civil) | VCH/000214/2022-2023 | BP-2022-23-33 | 18/05/2022 | 0 | RATAN CHANDRA SARKAR | 3.97 | 0 | 0
149 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection in connection with Retrofitting for K.D. Trimohini Zone I Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000073/2023-2024 | 872/BD | 24/07/2023 | 721 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 27.8 | 0 | 35
150 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for K. D. Trimohini Zone I Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) |  | Junior Engineer Hili | ORD/000338/2021-2022 | 1918/BSSD | 01/12/2021 | 25 | SARADA ENTERPRISE | 4.85 | 4.55 | 100
151 | Balurghat Division | Balurghat Division | Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of K.D Trimohini Piped Water Supply Scheme (Zone - I) at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000536/2021-2022 | 542/RWS | 03/12/2021 | 15 | M/S. SOBHA & CO. | 3.54 | 3.54 | 1
152 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - IV under Tapan Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000079/2023-2024 | 893/BD | 25/07/2023 | 30 | M/S. BANI CONSTRUCTIUON | 4.55 | 1.71 | 100
153 | Balurghat Division | Balurghat Division | Face lifting related works of Head Works Site compound for Zone - VI under Tapan Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000105/2023-2024 | 1247/BD | 24/08/2023 | 30 | MAA CHANCHALA CONSTRUCTION | 4.52 | 0 | 100
154 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection work by Retrofitting of Zone- II at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000150/2022-2023 | 2864/BD | 05/01/2023 | 780 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 63.68 | 21.37 | 55
155 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection work by Retrofitting of Zone- IV at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000151/2022-2023 | 2851/BD | 02/01/2023 | 60 | NEOGI ENTERPRISE | 61.1 | 30.1 | 85
156 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection work by Retrofitting of Zone- V at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000152/2022-2023 | 2852/BD | 02/01/2023 | 60 | ALOK ENTERPRISE | 74.44 | 0 | 10
157 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection work by Retrofitting of Zone- VI at Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000153/2022-2023 | 2849/BD | 02/01/2023 | 60 | SHYAMAL SHIL | 62.77 | 26.76 | 100
158 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection work by Retrofitting of Zone- I of Tapan Western Sector under Sub Surface Based Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000154/2022-2023 | 2850/BD | 02/01/2023 | 45 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 26.55 | 12.96 | 62
159 | Balurghat Division | Balurghat Division | Laying of HDPE pipeline (for drinking water purpose) by using Horizontal Direct Drilling (HDD) method at different location on Tapan Kardaha Road & Kardaha Vikahar Road under Zone- IV of Tapan Sub Surface based Piped Water Supply Scheme at Tapan Block in the district of Dakshin Dinajpur. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000182/2022-2023 | 3290/BD | 09/02/2023 | 30 | SAJEDUR RAHAMAN | 4.49 | 0 | 100
160 | Balurghat Division | Balurghat Division | Construction of approach road from main road to H/W site (outside portion) and allied work for 05 nos Zones of Tapan Western sector under Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000189/2022-2023 | 3516/BD | 04/03/2023 | 30 | J. CHATTERJEEE & CO. | 23 | 22.25 | 0
161 | Balurghat Division | Balurghat Division | Construction of Support Structure with placing of GI pipe at various Khari crossing and Culvert Crossing of Distribution Pipeline of different place under Zone-I of Tapan Western Sector under Tapan Sub-Surface water based Piped Water Supply Scheme in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000199/2022-2023 | 3521/BD | 04/03/2023 | 30 | M/S. SARKAR CONSTRUCTION | 12.48 | 6.27 | 100
162 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Various Piped Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. (Part I) |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000349/2021-2022 | 1927/BSSD | 01/12/2021 | 25 | RADHARANI ENTERPRISE. | 4.79 | 4.66 | 100
163 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Various Piped Piped Water Supply Scheme at Tapan Block in the District of Dakshin Dinajpur. (Part II) |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | ORD/000350/2021-2022 | 1928/BSSD | 01/12/2021 | 38 | AJANTA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 4.84 | 4.78 | 0
164 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division |  | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Tapan` | RTOR000083/2022-2023 | 3537/BD | 10/03/2023 | 0 | Resource Division | 40.35 | 0 | 0
165 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
166 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.11 | 55
167 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
168 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
169 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
170 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
171 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
172 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
173 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
174 | Balurghat Division | Balurghat Sadar Sub-Division | Laying distribution pipe line for piped water supply scheme for Baragram PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/00185/2024-2025 | BP-2024-25-118 | 04/09/2024 | 0 | ASHIT KUMAR DEBSHARMA | 9.43 | 0 | 0
175 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main , Providing FHTC, Construction of 200 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House for implementation of Baragram Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000004/2023-2024 | 49/BD | 10/04/2023 | 1076 | BRISTI CONSTRUCTION | 172.1 | 0 | 15
176 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Banshihari Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000133/2024-2025 | 1944/BD | 27/09/2024 | 20 | RANJAN SARKAR | 5.25 | 0 | 100
177 | Balurghat Division | Balurghat Sadar Sub-Division | Laying distribution pipe line for piped water supply scheme for Baragram PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000138/2022-2023 | 2331/BD | 17/10/2022 | 90 | ASHIT KUMAR DEBSHARMA | 182.34 | 0 | 1
178 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Baragram Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000161/2024-2025 | 2234/BD | 12/11/2024 | 284 | SARADA ENTERPRISE | 26.22 | 0 | 95
179 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000031/2022-2023 | 2562/BD | 06/12/2022 | 0 | Resource Division | 18.28 | 0 | 0
180 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000048/2022-2023 | 2889/BD | 06/01/2023 | 0 | Resource Division | 34.83 | 0 | 0
181 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000051/2023-2024 | 254/BD | 21/02/2024 | 0 | Resource Division | 8.55 | 0 | 0
182 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000072/2022-2023 | 3446/BD | 01/03/2023 | 0 | Resource Division | 0.69 | 0 | 0
183 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BARAGRAM W/S SCH (TW-II), BANSHIHARI BLOCK DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000256/2022-2023 | 1144/CDD | 07/11/2022 | 30 | PADMA ENGINEERING & CO. | 14.08 | 11.81 | 1
184 | Central Drilling | Balurghat Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X150mm X 245 Mtrs. Depth) by utilising Departmental Machineries for Baragram W/S Scheme (HW ) , Banshihari Block under Dakshin Dinajpur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000500/2022-2023 | 1143/CDD | 07/11/2022 | 480 | PADMA ENGINEERING & CO. | 14.08 | 0 | 100
185 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Baragram, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/02475/2023-2024 | BP-2023-24-405 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.72 | 0 | 0
186 | Malda Mechanical | Balurghat Sadar Sub-Division | Quotation Payment for Pump House No I of Baragram PWSS under Buniadpur CCC. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/03501/2023-2024 | BP-2023-24-521 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.35 | 0 | 0
187 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial run of electro-mechanical components of BARAGRAM Water Supply Scheme T/W no. I in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011705) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000232/2023-2024 | 2251/MLMD | 18/07/2023 | 90 | R.N.S. TRADING. | 11.94 | 0 | 0
188 | Malda Mechanical | Balurghat Sadar Sub-Division | Making compound lighting arrangement with allied works at T/W no. I of Baragram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011705) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000601/2023-2024 | 2648/MLMD | 10/08/2023 | 45 | M/S. MAYUKH BHADURI | 3.86 | 0 | 0
189 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial run of electro-mechanical components of BARAGRAM Water Supply Scheme T/W no. II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/001100/2022-2023 | 417/MLMD | 14/03/2023 | 556 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 11.96 | 9.62 | 96
190 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
191 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 11.18 | 55
192 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
193 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
194 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
195 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
196 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
197 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
198 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
199 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
200 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 20 | 55
201 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
202 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.76 | 55
203 | Balurghat Division | Balurghat Division | Laying of Rising Main, Providing FHTC, Construction of 300 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Brahmangaon Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000018/2023-2024 | 202/BD | 28/04/2023 | 1128 | DURJOY MITRA | 215.09 | 0 | 80
204 | Balurghat Division | Balurghat Division | Laying of additional distribution pipeline for the left out area, construction of approach road and other allied works within command area of Brahmangaon Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000165/2024-2025 | 2230/BD | 12/11/2024 | 300 | MATIUR RAHAMAN | 51.46 | 0 | 60
205 | Balurghat Division | Balurghat Division | Laying distribution pipe line for piped water supply scheme at BRAHMANGRAM under Ground Water Based Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000174/2022-2023 | 3292/BD | 09/02/2023 | 90 | BOSE CONSTRUCTION | 329.6 | 261.21 | 82
206 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | RTOR000052/2022-2023 | 2875/BD | 06/01/2023 | 0 | Resource Division | 10.16 | 0 | 0
207 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | RTOR000054/2023-2024 | 248/BD | 21/02/2024 | 0 | Resource Division | 16.65 | 0 | 0
208 | Central Drilling | Balurghat Division | Providing drilling crew & other allied works for construction of TW (250mm x 150mm x 120mtr. depth) by utilising Departmental machineries for Brahmangaon WS Scheme (TW-II), harirampur Block under Dakshin Dinajpur District, CDD, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000336/2022-2023 | 1397/CDD | 28/11/2022 | 30 | CHANDA ENTERPRISE | 8.26 | 6.32 | 1
209 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BRAHMANGAON W/S SCH TW-I, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000358/2022-2023 | 1170/CDD | 09/11/2022 | 30 | M/S S.K.GHOSH & CO. | 8.28 | 6.67 | 0
210 | Central Drilling | Balurghat Division | Additional carraige of gravels for Construction of Tube well at BRAHMANGAON PWSS TW-II, Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000479/2022-2023 | 588/CMSD-I(D) | 30/11/2022 | 7 | M/S S.K.GHOSH & CO. | 0.59 | 0 | 100
211 | Central Drilling | Balurghat Division | Additional carraige of gravels for Construction of Tube well at BRAHMANGAON PWSS , Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000481/2022-2023 | 587/CMSD-I(D) | 30/11/2022 | 7 | CHANDA ENTERPRISE | 0.59 | 0 | 100
212 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Brahmangaon Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011983) | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000016/2023-2024 | 779/MLMD | 27/04/2023 | 1155 | ANIMA ENTERPRISE | 26.58 | 18.97 | 65
213 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BRAHMANGAON, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000286/2023-2024 | 4003193779 | 15/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.85 | 0 | 100
214 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BRAHMANGAON, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000287/2023-2024 | 4003193767 | 15/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.03 | 3.03 | 100
215 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BRAHMANGAON, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000305/2023-2024 | 4003193779 | 15/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.85 | 4.85 | 100
216 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 450 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Musan Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000025/2023-2024 | 329/BD | 16/05/2023 | 1231 | CHIRANJIB DAS | 666.63 | 165.64 | 45
217 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000060/2022-2023 | 2877/BD | 06/01/2023 | 0 | Resource Division | 16.35 | 0 | 0
218 | Malda Mechanical | Balurghat Sadar Sub-Division | : Additional quotation for PH-II of Musan PWSS under Harirampur CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/01825/2024-2025 | BP-2024-25-454 | 23/08/2024 | 0 | W.B.S.E.D.C.LTD | 1.5 | 0 | 0
219 | Malda Mechanical | Balurghat Sadar Sub-Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000408/2024-2025 | 3388/MLMD | 28/10/2024 | 61 | RAMCHANDRA BASAK | 0.78 | 0 | 100
220 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Musan PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000787/2023-2024 | 4003201659 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.59 | 3.59 | 100
221 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Musan PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000788/2023-2024 | 4003200276 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.56 | 3.56 | 100
222 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
223 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.69 | 55
224 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Karai Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II). |  | Junior Engineer 1 Sadar | ORD/000263/2021-2022 | 2560/BD | 09/11/2021 | 45 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.31 | 39.13 | 1
225 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 1 Sadar | RTOR000032/2021-2022 | 2964/BD | 31/12/2021 | 0 | Resource Division | 2.2 | 0 | 0
226 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 1 Sadar | RTOR000044/2021-2022 | 205/BD | 02/02/2022 | 0 | Resource Division | 2.75 | 0 | 0
227 | Balurghat Division | Balurghat Division | Restoration of Teor - Binsira-Maniko- Bangalipur Road from chainage 5 KM TO 7.5 KM Km under K. D. Trimohini PWSS at Hili Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | BILL/00207/2024-2025 | BP-2024-25-131 | 12/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.57 | 0 | 0
228 | Balurghat Division | Balurghat Division | Restoration of Trimohini Dhanhati Maniko Road from chainage 2.50 KM TO 5.50 KM under K. D. Trimohini PWSS at Hili Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | BILL/00305/2024-2025 | BP-2024-25-196 | 27/11/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 9.17 | 0 | 0
229 | Balurghat Division | Balurghat Division | Sinking of Tubewell, Laying of Rising Main, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of K.D. Trimohini Zone-II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000098/2023-2024 | 1094/BD | 10/08/2023 | 870 | MINATI CONSTRUCTION | 446.32 | 0 | 12
230 | Balurghat Division | Balurghat Division | Laying distribution pipe line for augmentation of K.D. Trimohini pipe Water Supply Scheme(Zone-I) at Hili Dev. Block in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000157/2022-2023 | 2702/BD | 21/12/2022 | 630 | M/S. JAN MAHAMMAD | 376.92 | 212.64 | 78
231 | Balurghat Division | Balurghat Division | Laying distribution pipe line for augmentation of K.D. Trimohini Pipe Water Supply Scheme(Zone-II) at Hili Dev. Block in the district of Dakhin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000158/2022-2023 | 2703/BD | 21/12/2022 | 891 | J.D.J. ENTERPRISE | 659.64 | 0 | 18
232 | Balurghat Division | Balurghat Division | Sinking of 02 nos 300 mm dia X 200mm dia 81.00 mtr depth Rig Bored Tubewell for Augmentation of KD Trimohini Zone II Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000198/2023-2024 | 92/BD | 24/01/2024 | 45 | M/S. SARKAR ENTERPRISE | 18.68 | 0 | 100
233 | Balurghat Division | Balurghat Division | Laying of Rising Main, Providing FHTC, Repairing of 300 Cum capacity OHR with 20m Staging Height, Repairing of Pump House & Blower Room, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of K.D. Trimohini Zone-I Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000223/2022-2023 | 3819/BD | 23/03/2023 | 840 | VENUS CONSTRUCTION | 119.41 | 32.27 | 45
234 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | RTOR000001/2024-2025 | 875/BD | 03/05/2024 | 0 | Resource Division | 25.7 | 0 | 0
235 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | RTOR000015/2023-2024 | 575/BD | 19/06/2023 | 0 | Resource Division | 6.47 | 0 | 0
236 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | RTOR000021/2023-2024 | 837/BD | 14/07/2023 | 0 | Resource Division | 9.52 | 0 | 0
237 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | RTOR000080/2022-2023 | 3487/BD | 03/03/2023 | 0 | Resource Division | 114.92 | 0 | 0
238 | Malda Mechanical | Balurghat Division | Supply, installation & commissioning of electro-mechanical components at T/W no. I & II, making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Kismatdapat Trimohini (Zone- I) Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011528) | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000118/2023-2024 | 1137/MLMD | 26/06/2023 | 2005 | MANIK CHANDRA SAHA. | 23.34 | 13.86 | 59
239 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II & III, making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Kismatdapat Trimohini (Zone- II) Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011528) | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000625/2023-2024 | 2661/MLMD | 10/08/2023 | 2005 | GHOSH BROTHERS... | 46.8 | 0 | 0
240 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Kismat Dapat Trimohini,Zone-II, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/002009/2023-2024 | 4003286546 | 17/12/2023 | 90 | W.B.S.E.D.C.LTD | 4.38 | 0 | 100
241 | Balurghat Division | Balurghat Division | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 558 | GHOSH BROTHERS | 3593.49 | 0 | 30
242 | Balurghat Division | Balurghat Division | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Dasul Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000163/2024-2025 | 2232/BD | 12/11/2024 | 30 | ABHIJIT HAZRA | 23.28 | 0 | 0
243 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | RTOR000029/2024-2025 | 2323/BD | 22/11/2024 | 0 | Resource Division | 17.3 | 0 | 0
244 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | RTOR000036/2022-2023 | 2897/BD | 06/01/2023 | 0 | Resource Division | 25.08 | 0 | 0
245 | Malda Mechanical | Balurghat Division | Payment for the quotation of New Connection of PH NO-I of Dasul PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00037/2024-2025 | BP-2024-25-49 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 2.93 | 0 | 0
246 | Malda Mechanical | Balurghat Division | : Payment for the quotation of New Connection of PH NO-II of Dasul PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00038/2024-2025 | BP-2024-25-50 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.32 | 0 | 0
247 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dasul Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014362) | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000368/2023-2024 | 2374/MLMD | 28/07/2023 | 874 | PADMA ENGINEERING CO. | 28.31 | 0 | 80
248 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
249 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
250 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.47 | 55
251 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
252 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.84 | 55
253 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
254 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.35 | 55
255 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
256 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
257 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
258 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.84 | 55
259 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
260 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
261 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.79 | 55
262 | Balurghat Division | Balurghat Sadar Sub-Division | Special repairing and realignment of existing distribution Pipe Line for Bagduar Piped Water Supply Scheme at Banshihari Block, in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000171/2023-2024 | 1855/BD | 17/11/2023 | 45 | ASHIT KUMAR DEBSHARMA | 4.15 | 0 | 10
263 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tube Well, Construction of Pump House, Laying of Pipe Line, Installation of IEP including 03 months trial run & construction of Blower room, surface drain & platfrom for Source Augmentation of Bagduar Piped Water Supply Scheme at Banshihari Block in District of Dakshin Dinajpur under Balurghat Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000233/2022-2023 | 3905/BD | 29/03/2023 | 303 | ASHOK MITRA | 37.26 | 0 | 95
264 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000039/2023-2024 | 1485/BD | 19/09/2023 | 0 | Resource Division | 0.66 | 0 | 0
265 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of PH NO-III of Bagduar PWSS under Buniadpur CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/00746/2024-2025 | BP-2024-25-210 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 8.84 | 0 | 0
266 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Bartakkigram Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000093/2023-2024 | 1086/BD | 09/08/2023 | 955 | DIPESH BHOWMIK | 822.67 | 213.52 | 65
267 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of additional distribution pipeline for the left out area , construction of approach road and other allied works within command area of Bartakkigram Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000175/2024-2025 | 2074/BD | 20/11/2024 | 116 | BISWARUP SAHA | 56.99 | 0 | 60
268 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | RTOR000003/2024-2025 | 1836/BD | 18/06/2024 | 0 | Resource Division | 25.78 | 0 | 0
269 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | RTOR000049/2022-2023 | 2888/BD | 06/01/2023 | 0 | Resource Division | 37.69 | 0 | 0
270 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of New Connection of PH NO-I of Bartakkigram PWSS under Harirampur CCC. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | BILL/03664/2023-2024 | BP-2023-24-636 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.04 | 0 | 0
271 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of New Connection of PH NO-II of Bartakkigram PWSS under Harirampur CCC | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | BILL/03665/2023-2024 | BP-2023-24-637 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.03 | 0 | 0
272 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Bartakkigram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012731) | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000350/2023-2024 | 2340/MLMD | 26/07/2023 | 120 | NUPUR CHANDRA HALDER | 38.61 | 0 | 50
273 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
274 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Restoration of Distribution System, Laying of pipe line in connection with 3rd TW, Pump House, Boundary Wall & Repairing works for Augmentation of Dangram Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000221/2022-2023 | 3817/BD | 23/03/2023 | 676 | PRADIP KUMAR PAUL | 155.13 | 100.47 | 88
275 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000041/2023-2024 | 1487/BD | 19/09/2023 | 0 | Resource Division | 3.86 | 0 | 0
276 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Danagram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016072) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000443/2023-2024 | 2454/MLMD | 04/08/2023 | 120 | PABITRA MANDAL | 12.87 | 10.49 | 100
277 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Dangram , Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/001876/2023-2024 | 4003201055 | 22/08/2023 | 90 | W.B.S.E.D.C.LTD | 8.09 | 0 | 100
278 | Balurghat Division | Malda Mechanical Division | Sinking of Tubewell, Laying of Rising Main, Providing FHTC, Construction of 450 Cum capacity OHR with 20m Staging Height including Soil Investigation, Construction of blower room and Pump House, Renovation of Boundary Wall, Construction of Approach Road and installation of IEP for implementation for Augmentation of Kamarpara Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000100/2023-2024 | 1105/BD | 11/08/2023 | 1135 | S. DUTTA | 777.83 | 0 | 35
279 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000061/2023-2024 | 245/BD | 21/02/2024 | 0 | Resource Division | 14.77 | 0 | 0
280 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000079/2022-2023 | 3488/BD | 03/03/2023 | 0 | Resource Division | 36.7 | 0 | 0
281 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-III of Kamarpara PWSS under Balurghat CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/00211/2024-2025 | BP-2024-25-64 | 15/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.76 | 0 | 0
282 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Kamarpara Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014570) | Assistant Engineer - I | Junior Engineer-01 | ORD/000469/2023-2024 | 2555/MLMD | 04/08/2023 | 832 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 24.74 | 0 | 80
283 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Kamarpara Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014570) | Assistant Engineer - I | Junior Engineer-01 | ORD/000473/2023-2024 | 2556/MLMD | 04/08/2023 | 120 | NEOGI ENTERPRISE. | 11.35 | 0 | 50
284 | Balurghat Division | Balurghat Division | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 60 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 0 | 100
285 | Balurghat Division | Balurghat Division | Laying distribution pipe line for piped water supply scheme for Shyampur PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000172/2022-2023 | 3267/BD | 08/02/2023 | 90 | MOHANTA BUILDERS | 231.18 | 226.16 | 99
286 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | RTOR000028/2023-2024 | 835/BD | 14/07/2023 | 0 | Resource Division | 14.37 | 0 | 0
287 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | RTOR000056/2022-2023 | 2880/BD | 06/01/2023 | 0 | Resource Division | 27.64 | 0 | 0
288 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCH UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000349/2022-2023 | 1608/CDD | 15/12/2022 | 30 | DEY ENTERPRISE | 13.8 | 0 | 1
289 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCH, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000352/2022-2023 | 1607/CDD | 15/12/2022 | 30 | DEY ENTERPRISE | 13.8 | 0 | 1
290 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCHEME (TW-II), BANSHIHARI BLOCK, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000371/2022-2023 | 1608/ CDD | 15/12/2022 | 30 | DEY ENTERPRISE | 13.8 | 10.75 | 0
291 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCHEME (TW-I), BANSHIHARI BLOCK, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000372/2022-2023 | 1607/ CDD | 15/12/2022 | 30 | DEY ENTERPRISE | 13.8 | 10.59 | 0
292 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Shyampur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011902) | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000119/2023-2024 | 1125/MLMD | 23/06/2023 | 120 | DEVI ENTERPRISE... | 26.57 | 19.19 | 72
293 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SHYAMPUR, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000265/2023-2024 | 4003193516 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.77 | 2.77 | 100
294 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SHYAMPUR, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000266/2023-2024 | 4003194835 | 18/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.98 | 2.98 | 100
295 | Malda Mechanical | Balurghat Division | Supply & Delivery of accesories of Pumping Machinery and installation of Voltage stabilizer and other Electro Mechanical components at T/W No-I & II of SHYAMPUR W/S scheme in the District of Dakshin Dinajpur under Malda Mechanical Division P.H.E Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/002625/2023-2024 | 1048/MLMD | 15/03/2024 | 14 | MAA BHABOTARINE ENTERPRISE | 3.69 | 0 | 100
296 | Malda Mechanical | Balurghat Division | Supply, delivery and making lighting arrangement at T/W No-I of Shyampur W/S scheme in the District of Dakshin Dinajpur under Malda Mechanical Division P.H.E Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/002626/2023-2024 | 1049/MLMD | 15/03/2024 | 14 | MAA BHABOTARINE ENTERPRISE | 4.39 | 0 | 0
297 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
298 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
299 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
300 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
301 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara & adjoining mouzas for Purba Kalikapur Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000042/2020-2021 | 1856/BD | 07/12/2020 | 35 | CHOUDHURY CONSTRUCTION | 7.68 | 10.83 | 1
302 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara & its adjoining Mouzas for Laskarpur Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000044/2020-2021 | 1864/BD | 07/12/2020 | 554 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 14.52 | 20.8 | 100
303 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara & its adjoining Mouzas for Dhalpara Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000045/2020-2021 | 1865/BD | 07/12/2020 | 45 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 16.51 | 27.33 | 1
304 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara and adjoining mouzas for Purba Gobindapur Mouja at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000050/2020-2021 | 1886/BD | 07/12/2020 | 35 | RABIN KAMETH | 3.6 | 4.64 | 1
305 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara and adjoining mouzas for Srikrishnapur Mouja at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000062/2020-2021 | 1973/BD | 18/12/2020 | 35 | MAYA CONSTRUCTION | 4.45 | 8.66 | 1
306 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Dhalpara and adjoining mouzas for Uttar Jamalpur Mouza at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000072/2020-2021 | 2038/BD | 29/12/2020 | 35 | SHYAMAL CHANDRA MONDAL. | 6.13 | 8.91 | 1
307 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection (F.H.T.C) for 5 (Five) Numbers of Mouza under Dhalpara PWSS Under Jal Swapna Programme at Hili Block under Balurghat Division P.H. Engineering Dte. in the District of Dakshin Dinajpur |  | Junior Engineer Hili | ORD/000262/2021-2022 | 2561/BD | 09/11/2021 | 40 | PACIFIC ENGINEERS' CO-OPERATIVE SOCIETY LTD. | 8.08 | 7.44 | 1
308 | Balurghat Division | Balurghat Division | Acceptance cum Work Order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for NUNAIL PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer 1 Sub Division | ORD/000373/2021-2022 | 2935/BD | 28/12/2021 | 45 | TARAMA CONSTRUCTION | 8.07 | 7.99 | 1
309 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for NUNAIL Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1592/BD Dated :- 16/10/2020 & Tender No. 144 of 2020-2021] |  | Junior Engineer 1 Sub Division | VCH/000178/2022-2023 | BP-2022-23-10 | 12/04/2022 | 0 | TARAMA CONSTRUCTION | 12.65 | 0 | 0
310 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for Badmuluk Kismat PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer Balurghat | ORD/000256/2021-2022 | 2313/BD | 05/10/2021 | 40 | BALURGHAT BUILDERS | 7.64 | 7.64 | 1
311 | Balurghat Division | Balurghat Division | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Kalikamora Zone II Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | ORD/000185/2020-2021 | 507/BD | 25/02/2021 | 60 | DURJOY MITRA | 57.09 | 2.03 | 0
312 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Kalikamora Zone II Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II) |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | ORD/000272/2021-2022 | 2603/BD | 12/11/2021 | 60 | MANAS KUMAR SAHA | 80.63 | 47.14 | 85
313 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for DOMRAN & NAWAPARA and any other piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | ORD/000458/2021-2022 | 2169/BSSD | 20/01/2022 | 7 | MOHANTA BUILDERS | 1.11 | 0.66 | 1
314 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | RTOR000033/2021-2022 | 2965/BD | 31/12/2021 | 0 | Resource Division | 2.2 | 0 | 0
315 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division |  | Junior Engineer 1 HQ,Junior Engineer 3 Sub Division | RTOR000042/2021-2022 | 203/BD | 02/02/2022 | 0 | Resource Division | 8.24 | 0 | 0
316 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Jabaripur Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000013/2020-2021 | 1491/BD | 10/10/2020 | 40 | SUBODH KUMAR SAHA | 28.79 | 51.47 | 1
317 | Balurghat Division | Balurghat Sadar Sub-Division | Repairing works of Pump House at Head Work Site for Patiram Piped water supply scheme within Balurghat Block under Balurghat Division P.H.E. Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000192/2022-2023 | 3519/BD | 04/03/2023 | 180 | BIPUL SARKAR | 1.1 | 0 | 100
318 | Balurghat Division | Balurghat Sadar Sub-Division | Repairing works of Blower Room at Head Work Site for Patiram Piped water supply scheme within Balurghat Block under Balurghat Division P.H.E. Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000198/2022-2023 | 3513/BD | 04/03/2023 | 20 | AMITAVA MITRA CONTRACTOR & ORDER SUPPLIER | 1.08 | 0 | 99
319 | Balurghat Division | Balurghat Sadar Sub-Division | Repairing works of Pump House and Latrine at 2nd Tube Well Site for Patiram Piped water supply scheme within Balurghat Block under Balurghat Division P.H.E. Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000219/2022-2023 | 3818/BD | 23/03/2023 | 180 | SUBHRA KANTI GHOSH | 1.4 | 0 | 100
320 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Laying of Rising Main System, Repairing & Renovation of existing 182 Cum capacity OHR with Construction of Pump House, Blower Room, Construction & Repairing of Boundary Wall, Installation of IEP & Providing FHTC for Part Retrofitting and for Augmentation of Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000259/2022-2023 | 3953/BD | 31/03/2023 | 1032 | M/S. ANWESHA ENTERPRISE | 242.56 | 11.91 | 25
321 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | RTOR000024/2023-2024 | 829/BD | 14/07/2023 | 0 | Resource Division | 28.95 | 0 | 0
322 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | RTOR000081/2022-2023 | 3486/BD | 03/03/2023 | 0 | Resource Division | 23.75 | 0 | 0
323 | Central Drilling | Balurghat Sadar Sub-Division | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 180 Mtrs. Depth) by utilising Departmental Machineries for Patiram W/S Scheme ( T/W- I ) , Balurghat Block under Dakshin Dinajpur District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000501/2022-2023 | 1316/CDD | 23/11/2022 | 479 | PADMA ENGINEERING & CO. | 14.21 | 0 | 100
324 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of New Connection of PH NO-III of Patiram PWSS under Patiram CCC in the district of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | BILL/00227/2024-2025 | BP-2024-25-99 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.03 | 0 | 0
325 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning & trial operation of electro-mechanical components at T/W no. I of Augmentation of Patiram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/010064) | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000021/2023-2024 | 772/MLMD | 26/04/2023 | 380 | FUTURE | 13.05 | 10.22 | 100
326 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Patiram Water Supply Scheme, (Zone- II) in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/010064) | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000023/2023-2024 | 773/MLMD | 26/04/2023 | 523 | SOVON KUMAR DAS. | 10.3 | 9.06 | 100
327 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning & trial operation of electro-mechanical components at T/W no. III of Augmentation of Patiram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/010064) | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000248/2023-2024 | 2252/MLMD | 18/07/2023 | 900 | M/S PARIMAL DAS. | 12.86 | 0 | 70
328 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap connection under Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur (Phase - II). | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/000033/2022-2023 | 854/BD | 12/05/2022 | 45 | USHA ENTERPRISE | 43.26 | 35.19 | 98
329 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum Work Order for Laying of HDPE pipe for water supply system by trenchless method using Horizontal Direct Drilling (HDD) method at different road crossing and congested areas on PWD road from Mollapara to Mahugram brick field under Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block under Balurghat Division, PHE Dte in the district of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/000128/2022-2023 | 1774/HQ/BD | 30/08/2022 | 15 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.81 | 4.81 | 1
330 | Balurghat Division | Balurghat Sadar Sub-Division | Repairing and Renovation of 2nd TW site Pump house at Banshihari PWSS of Banshihari Block under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/000191/2022-2023 | 3515/BD | 04/03/2023 | 20 | MOTAHAR HOSSAIN | 2.67 | 0 | 100
331 | Balurghat Division | Balurghat Sadar Sub-Division | Construction of 350 Cum Capacity OHR with 20mtr. Staging height, including with Soil Investigation for Augmentation of Banshihari piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. in the district of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/000224/2022-2023 | 3816/BD | 23/03/2023 | 270 | MATIUR RAHAMAN | 144.62 | 0 | 85
332 | Balurghat Division | Balurghat Sadar Sub-Division | Repairing and Renovation of Head Work site Pump house at Banshihari PWSS of Banshihari Block under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/000253/2022-2023 | 3947/BD | 31/03/2023 | 20 | BHASKAR BHOWMIK | 2.58 | 0 | 100
333 | Balurghat Division | Balurghat Sadar Sub-Division | Formal work order for the work of Laying distribution pipe line for Augmentation of Bansihari piped water supply scheme at Bansihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/000420/2021-2022 | 74/BD | 11/01/2022 | 90 | NEOGI ENTERPRISE | 150.48 | 141.09 | 98
334 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | RTOR000002/2022-2023 | 836/BD | 11/05/2022 | 0 | Resource Division | 6.87 | 0 | 0
335 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | RTOR000021/2024-2025 | 2314/BD | 22/11/2024 | 0 | Resource Division | 7.69 | 0 | 0
336 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | RTOR000049/2021-2022 | 343/BD | 22/02/2022 | 0 | Resource Division | 1.6 | 0 | 0
337 | Malda Mechanical | Balurghat Sadar Sub-Division | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Banshihari Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/001226/2021-2022 | 546 /MLMD | 28/03/2022 | 30 | MANIK CHANDRA SAHA | 6.04 | 5.55 | 1
338 | Malda Mechanical | Balurghat Sadar Sub-Division | Modification & upgradation of electro-mechanical installation work at Pump House No. II of Banshihari Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/001227/2021-2022 | 547 /MLMD | 28/03/2022 | 30 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 6.03 | 5.43 | 1
339 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, delivery and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Bansihari piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/001266/2021-2022 | 476 /MLMD | 24/03/2022 | 30 | JOYSHREE CONCERN | 2.74 | 2.73 | 1
340 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, delivery and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at pump house no. II of Banshihari piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/001268/2021-2022 | 477 /MLMD | 24/03/2022 | 30 | JOY MAA SANTOSHI ENTERPRISE | 2.74 | 2.71 | 1
341 | Malda Mechanical | Balurghat Sadar Sub-Division | claim for purchase of fuel for different site visigiet under Malda Mechanical Division, P.H.E. Dte., | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/001486/2021-2022 | 1808/MLMD | 26/10/2021 | 56 | SHAKTI FILLING STATION | 1.77 | 0 | 0
342 | Malda Mechanical | Balurghat Sadar Sub-Division | Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/001544/2023-2024 | 1145/MLMD | 26/06/2023 | 183 | RAMCHANDRA BASAK | 0.86 | 0 | 100
343 | Malda Mechanical | Balurghat Sadar Sub-Division | Claim for purchase of fuel for different site visit under Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer 3,Junior Engineer-01 | ORD/001611/2021-2022 | 1808/ MLMD | 26/10/2021 | 182 | SHAKTI FILLING STATION | 0.91 | 0.91 | 0
344 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection in connection with Retrofitting for Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000083/2023-2024 | 906/BD | 25/07/2023 | 45 | M/S. SARKAR CONSTRUCTION | 22.06 | 0 | 0
345 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Preparation of DPR to provide FHTC in connection with Augmentation of Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000114/2022-2023 | 530/BD | 01/04/2022 | 30 | M/S. SOBHA & CO. | 3.25 | 3.25 | 1
346 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Hili Piped Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur. |  | Junior Engineer Hili | ORD/000344/2021-2022 | 1923/BSSD | 01/12/2021 | 25 | JUVENILE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.81 | 4.48 | 1
347 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
348 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
349 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
350 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 842 | GHOSH BROTHERS | 2425.67 | 0 | 30
351 | Balurghat Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. Through 600 mm dia R.C.C. Hume pipe (NP4)/ M.S. pipe by Hydraulic Jacking Technique method across Railway Track near Khir pukhur (KM/TP -80/1- 80/2) between Mallickpur Hat(MKRH) and Balurghat(BLGT) station for Durlabhpur Piped Water Supply Scheme in the Disrtict of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000178/2024-2025 | 2303/BD | 22/11/2024 | 60 | M/S. TRILOCHAN CONSTRUCTION CO. | 25.34 | 0 | 0
352 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000038/2022-2023 | 2903/BD | 06/01/2023 | 0 | Resource Division | 17.62 | 0 | 0
353 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-II of DURLABHPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00033/2024-2025 | BP-2024-25-60 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.51 | 0 | 0
354 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-I , DURLABHPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00034/2024-2025 | BP-2024-25-61 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.28 | 0 | 0
355 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Durllabhpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013547) | Assistant Engineer - I | Junior Engineer-01 | ORD/001805/2023-2024 | 3692/MLMD | 29/11/2023 | 700 | MERCURY ENGINEERING COMPANY. | 28.26 | 0 | 60
356 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
357 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
358 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
359 | Balurghat Division | Balurghat Sadar Sub-Division | Laying distribution pipe line for piped water supply scheme for Uttar Daulatpur PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000139/2022-2023 | 2421/BD | 09/11/2022 | 60 | ASHOK MITRA | 99.22 | 25.89 | 95
360 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main & Providing FHTC, Construction of Pump House, Boundary wall, C.C. Road and Land filling for implementation of Uttar Daulatpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000249/2022-2023 | 3946/BD | 31/03/2023 | 60 | DURJOY MITRA | 65.44 | 0 | 75
361 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000027/2023-2024 | 834/BD | 14/07/2023 | 0 | Resource Division | 3.35 | 0 | 0
362 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000047/2022-2023 | 2884/BD | 06/01/2023 | 0 | Resource Division | 10.38 | 0 | 0
363 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR UTTAR DAULATPUR W/S SCH (HW), Bansihari Block, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000337/2022-2023 | 1313/CDD | 23/11/2022 | 30 | PADMA ENGINEERING & CO. | 15.55 | 12.74 | 1
364 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR UTTAR DAULATPUR W/S SCH (TW-II), BANSHIHARI BLOCK, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000338/2022-2023 | 1314/CDD | 23/11/2022 | 30 | PADMA ENGINEERING & CO. | 15.55 | 11.41 | 1
365 | Central Drilling | Balurghat Sadar Sub-Division | Providing Pipes 250mm dia. and other works for construction of Tube Well for Uttar Daulatpur W/S Scheme (HW) , in Banshihari Block under Dakshin Dinajpur District , Central Drilling Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000523/2022-2023 | 67/CMSD-I(D) | 14/03/2023 | 10 | PADMA ENGINEERING & CO. | 0.19 | 0 | 100
366 | Malda Mechanical | Balurghat Sadar Sub-Division | Additional Quotation For PH-II Of Uttar Daulatpur w/s Scheme Under Buniadpur CCC | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/03552/2023-2024 | BP-2023-24-556 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 2.72 | 0 | 0
367 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no II of Uttar Daulatpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000051/2024-2025 | 3416/MLMD | 23/10/2024 | 180 | PABITRA MANDAL | 11.51 | 0 | 100
368 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of of Uttar Daulatpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011659) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000260/2023-2024 | 2233/MLMD | 19/07/2023 | 120 | DEY ENTERPRISE.. | 13.14 | 9.13 | 69
369 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Uttar Daulatpur,PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000988/2023-2024 | 4003194886 | 18/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.1 | 3.1 | 100
370 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Uttar Daulatpur,PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000989/2023-2024 | 4003193495 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.77 | 2.77 | 100
371 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
372 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
373 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
374 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
375 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
376 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
377 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 6.05 | 55
378 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
379 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 9.38 | 55
380 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
381 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
382 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
383 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 20.04 | 55
384 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
385 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
386 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
387 | Balurghat Division | RWS Balurghat Sub-Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Panchhata Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000001/2023-2024 | 16/BD | 04/04/2023 | 1184 | ANUGRAH CONSTRUCTION PVT. LTD. | 739.63 | 308.83 | 45
388 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000043/2023-2024 | 1488/BD | 19/09/2023 | 0 | Resource Division | 5.08 | 0 | 0
389 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000050/2023-2024 | 39/BD | 09/01/2024 | 0 | Resource Division | 15.15 | 0 | 0
390 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000064/2022-2023 | 2896/BD | 06/01/2023 | 0 | Resource Division | 15.53 | 0 | 0
391 | Central Drilling | RWS Balurghat Sub-Division | Providing drilling crew and other allied works for construction of Tube Well(250mm x 150 mm x 120Mtrs Depth) by utilising Departmental Machineries for Panchhata W/S (TW I&II) ,Kushmandi Block under Dakshin Dinajpur,CDD,PHE DTE. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000446/2022-2023 | 1806/CDD | 04/01/2023 | 30 | PADMA ENGINEERING & CO. | 20.01 | 14.64 | 100
392 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Panchhata, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/03236/2023-2024 | BP-2023-24-490 | 30/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.21 | 0 | 0
393 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Panchhata Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013076) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000183/2023-2024 | 2110/MLMD | 05/07/2023 | 120 | ANIMA ENTERPRISE | 28.18 | 20.87 | 90
394 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PANCHHATA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000290/2023-2024 | 4003194048 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.48 | 2.48 | 100
395 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
396 | Balurghat Division | RWS Balurghat Sub-Division | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Anantpur Zone 1 Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000183/2020-2021 | 504/BD | 25/02/2021 | 60 | DIPESH BHOWMIK | 61.21 | 0 | 95
397 | Balurghat Division | RWS Balurghat Sub-Division | Laying of allied pipe line & restoration of damaged pipe line for providing FHTC including other related works for retrofitting of Anantapur PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000251/2022-2023 | 3948/BD | 31/03/2023 | 481 | BHASKAR BHOWMIK | 1.1 | 0 | 100
398 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Work of Allied pipe Line for FHTC work under Anantapur Zone1 PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Department. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000467/2021-2022 | 152/BD | 28/01/2022 | 35 | LOKNATH ENTERPRISE | 9.99 | 0 | 100
399 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
400 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 24.02 | 55
401 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
402 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
403 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 13.4 | 55
404 | Balurghat Division | Malda Mechanical Division | Restoration of Gopalpur Binsira road from chainage 2.00 km to 4.60 km under Purba Mustafapur PWSS at Hili Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/00204/2024-2025 | BP-2024-25-128 | 12/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 15.17 | 0 | 0
405 | Balurghat Division | Malda Mechanical Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 100 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Purba Mustafapur Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000013/2023-2024 | 188/BD | 28/04/2023 | 1244 | M/S. ANWESHA ENTERPRISE | 237.23 | 51.3 | 70
406 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000030/2023-2024 | 35/BD | 09/01/2024 | 0 | Resource Division | 5.73 | 0 | 0
407 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000065/2022-2023 | 2876/BD | 06/01/2023 | 0 | Resource Division | 19.44 | 0 | 0
408 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of PURBA MUSTAFAPUR, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/02471/2023-2024 | BP-2023-24-408 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.45 | 0 | 0
409 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of PURBA MUSTAFAPUR, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/02472/2023-2024 | BP-2023-24-409 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.66 | 0 | 0
410 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Purba Mustafapur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014637) | Assistant Engineer - I | Junior Engineer-01 | ORD/001801/2023-2024 | 3688/MLMD | 29/11/2023 | 760 | MANIK CHANDRA SAHA. | 25.51 | 0 | 72
411 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 558 | GHOSH BROTHERS | 3593.49 | 0 | 30
412 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000028/2024-2025 | 2311/BD | 22/11/2024 | 0 | Resource Division | 17.63 | 0 | 0
413 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000044/2022-2023 | 2908/BD | 06/01/2023 | 0 | Resource Division | 15.37 | 0 | 0
414 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-I of Sobrashyampur PWSS under Balurghat CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/03725/2023-2024 | BP-2023-24-702 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 7.68 | 0 | 0
415 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sobrasyampur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014531) | Assistant Engineer - I | Junior Engineer-01 | ORD/000372/2023-2024 | 2379/MLMD | 28/07/2023 | 915 | CREATIVE WATER & PROCESS TECH. PVT. LTD. | 25.31 | 0 | 70
416 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Jangalpur (2) Faridpur (3) Dhulatair at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000068/2023-2024 | 820/BD | 13/07/2023 | 1083 | R.K. ENTERPRISE | 2125.46 | 0 | 55
417 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000037/2022-2023 | 2902/BD | 06/01/2023 | 0 | Resource Division | 28.99 | 0 | 0
418 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000059/2023-2024 | 246/BD | 21/02/2024 | 0 | Resource Division | 20.49 | 0 | 0
419 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of DHULATAIR, patiram C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/02566/2023-2024 | BP-2023-24-461 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.47 | 0 | 0
420 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dhultair Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014386) | Assistant Engineer - I | Junior Engineer-01 | ORD/000446/2023-2024 | 2546/MLMD | 04/08/2023 | 840 | HANNAN BUILDERS PVT. LTD. | 26.78 | 0 | 74
421 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DHULATAIR, Patiram C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/002006/2023-2024 | 4003205877 | 07/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.48 | 0 | 100
422 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 842 | GHOSH BROTHERS | 2425.67 | 0 | 30
423 | Balurghat Division | Malda Mechanical Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Balurghat Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000131/2024-2025 | 1906/BD | 26/09/2024 | 20 | R.P. CHOUDHURY CONSTRUCTION. | 8.55 | 0 | 100
424 | Balurghat Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. Through 600 mm dia R.C.C. Hume pipe (NP4)/ M.S. pipe by Hydraulic Jacking Technique method across Railway Track near Basanti tala (KM/TP -73/6- 73/7) between Rampur Bazar(RMPB) and Mallickpur Hat(MKRH) station for Bolla Piped Water Supply Scheme in the Disrtict of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000179/2024-2025 | 2310/BD | 22/11/2024 | 60 | M/S. TRILOCHAN CONSTRUCTION CO. | 28.27 | 0 | 0
425 | Balurghat Division | Malda Mechanical Division | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Bolla Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000195/2024-2025 | 48/BD | 06/01/2025 | 135 | M/S PINKI CONSTRUCTION | 31.76 | 0 | 50
426 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000025/2024-2025 | 2317/BD | 22/11/2024 | 0 | Resource Division | 19.99 | 0 | 0
427 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000035/2022-2023 | 2901/BD | 06/01/2023 | 0 | Resource Division | 25.57 | 0 | 0
428 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-II of Bolla PWSS under Patiram CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/01519/2024-2025 | BP-2024-25-377 | 18/07/2024 | 0 | W.B.S.E.D.C.LTD | 3.98 | 0 | 0
429 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-I of Bolla PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/01520/2024-2025 | BP-2024-25-378 | 18/07/2024 | 0 | W.B.S.E.D.C.LTD | 3.74 | 0 | 0
430 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bolla Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014315) | Assistant Engineer - I | Junior Engineer-01 | ORD/000605/2023-2024 | 2650/MLMD | 10/08/2023 | 991 | M/S. KUNDU CONSTRACTION | 28.39 | 0 | 80
431 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
432 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.58 | 55
433 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
434 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
435 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
436 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
437 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
438 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
439 | Balurghat Division | Balurghat Sadar Sub-Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Aminpur- Dehaband Road via Kantason, Sarala from (Chainage 0.00 KM to 15.45 Km) | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00108/2024-2025 | BP-2024-25-82 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 2.95 | 0 | 0
440 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
441 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
442 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
443 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.84 | 55
444 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
445 | Balurghat Division | Balurghat Sadar Sub-Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Fatepur - Dehaband Road from (Chainage 0.00 KM to 10.00 Km) | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00125/2024-2025 | BP-2024-25-88 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 13.67 | 0 | 0
446 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
447 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.8 | 55
448 | Balurghat Division | RWS Balurghat Sub-Division | Restoration of Kushmandi - Mahipaldighi road from chainage 4.4 km to 11.30 km under NAHIT at Kushmandi Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00112/2024-2025 | BP-2024-25-86 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.22 | 0 | 0
449 | Balurghat Division | RWS Balurghat Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase- II) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000140/2024-2025 | 1951/BD | 27/09/2024 | 20 | KINSHIP CONSTRUCTION | 2.39 | 0 | 100
450 | Balurghat Division | RWS Balurghat Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000146/2024-2025 | 2052/BD | 03/10/2024 | 20 | GOUTAM SAHA | 2.39 | 0 | 100
451 | Balurghat Division | RWS Balurghat Sub-Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Nahit Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000222/2022-2023 | 3820/BD | 23/03/2023 | 1165 | ANUGRAH CONSTRUCTION PVT. LTD. | 984.89 | 404.52 | 68
452 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000013/2024-2025 | 1767/BD | 20/09/2024 | 0 | Resource Division | 1.77 | 0 | 0
453 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000022/2023-2024 | 830/BD | 14/07/2023 | 0 | Resource Division | 21.25 | 0 | 0
454 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000044/2023-2024 | 1489/BD | 19/09/2023 | 0 | Resource Division | 3.56 | 0 | 0
455 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000063/2023-2024 | 264/BD | 22/02/2024 | 0 | Resource Division | 1.11 | 0 | 0
456 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000070/2022-2023 | 2886/BD | 06/01/2023 | 0 | Resource Division | 31.54 | 0 | 0
457 | Central Drilling | RWS Balurghat Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR NAHIT W/S SCHEME (TW-I & II), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000413/2022-2023 | 1807/CDD | 04/01/2023 | 30 | PADMA ENGINEERING & CO. | 20.01 | 14.32 | 0
458 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nahit, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/03235/2023-2024 | BP-2023-24-489 | 30/01/2024 | 0 | W.B.S.E.D.C.LTD | 1.25 | 0 | 0
459 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Nahit Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013113) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000013/2023-2024 | 748/MLMD | 24/04/2023 | 120 | DEY ENTERPRISE.. | 30.2 | 22.66 | 75
460 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nahit,Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000272/2023-2024 | 4003194074 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 7.31 | 7.31 | 100
461 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Nahit,Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000273/2023-2024 | 4003194075 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.89 | 2.89 | 100
462 | Balurghat Division | Balurghat Division | Sinking of tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing & Construction of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000092/2023-2024 | 1026/BD | 01/08/2023 | 884 | NILKAMAL BASAK | 630.03 | 92.86 | 35
463 | Balurghat Division | Balurghat Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Hili & Tapan Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000134/2024-2025 | 1942/BD | 27/09/2024 | 20 | M/S. A.D. ENTERPRISE | 3.83 | 0 | 100
464 | Balurghat Division | Balurghat Division | Dismantling of existing dilapidated 340.50 Cum capacity OHR for facilitating the construction of Proposed OHR under JJM at Head Work Site of Hili Piped Water Supply Scheme at Hili Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000165/2023-2024 | 1633/BD | 10/10/2023 | 45 | M/S. S. CONSTRUCTION | 13.38 | 0 | 48
465 | Balurghat Division | Balurghat Division | Erection of Permanent Type village wise Scheme Information Board at different Piped Water Supply Schemes under JJM as per departmental design and drawing for Balurghat, Hili, Tapan & Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000188/2023-2024 | 2069/BD | 16/12/2023 | 45 | M.A. ENTERPRISE | 12.1 | 0 | 98
466 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | RTOR000048/2023-2024 | 37/BD | 09/01/2024 | 0 | Resource Division | 17.03 | 0 | 0
467 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | RTOR000082/2022-2023 | 3495/BD | 03/03/2023 | 0 | Resource Division | 106.52 | 0 | 0
468 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Hili Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015982) | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000457/2023-2024 | 2550/MLMD | 04/08/2023 | 870 | MANIK CHANDRA SAHA. | 28.77 | 0 | 77
469 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Hili Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015982) | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000458/2023-2024 | 2551/MLMD | 04/08/2023 | 120 | SUBRATA KUMAR DAS. | 11.85 | 0 | 80
470 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Hili, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/002008/2023-2024 | 4003295116 | 20/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.74 | 0 | 100
471 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of allied pipe line & restoration of damaged pipe line for providing FHTC including other related works for retrofitting of Kasba Bairhatta PWSS at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2,Junior Engineer Kushmandi | ORD/000238/2022-2023 | 3928/BD | 30/03/2023 | 30 | RANJAN SARKAR | 7.44 | 0 | 72
472 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2,Junior Engineer Kushmandi | RTOR000019/2023-2024 | 839/BD | 14/07/2023 | 0 | Resource Division | 0.37 | 0 | 0
473 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
474 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 15.86 | 55
475 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 558 | GHOSH BROTHERS | 3593.49 | 0 | 30
476 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000027/2024-2025 | 2320/BD | 22/11/2024 | 0 | Resource Division | 17.69 | 0 | 0
477 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000046/2022-2023 | 2910/BD | 06/01/2023 | 0 | Resource Division | 27.93 | 0 | 0
478 | Malda Mechanical | Malda Mechanical Division | : Payment for the quotation of New Connection of PH NO-II of KHANPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00039/2024-2025 | BP-2024-25-55 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.39 | 0 | 0
479 | Malda Mechanical | Malda Mechanical Division | : Payment for the quotation of New Connection of PH NO-I of KHANPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00040/2024-2025 | BP-2024-25-56 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.91 | 0 | 0
480 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Uttar Khanpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014389) | Assistant Engineer - I | Junior Engineer-01 | ORD/000490/2023-2024 | 2562/MLMD | 04/08/2023 | 817 | M/S PARIMAL DAS. | 27.03 | 0 | 70
481 | Balurghat Division | Balurghat Division | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 558 | GHOSH BROTHERS | 3593.49 | 0 | 30
482 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | RTOR000043/2022-2023 | 2907/BD | 06/01/2023 | 0 | Resource Division | 26.14 | 0 | 0
483 | Malda Mechanical | Balurghat Division | : Payment for the quotation of New Connection of PH NO-II of MARGRAM PWSS under BALURGHAT CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00032/2024-2025 | BP-2024-25-39 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.13 | 0 | 0
484 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I&II and making compound lighting arrangement at T/W no. I of Margram (Zone-I&II) Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015069) | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000480/2023-2024 | 2558/MLMD | 04/08/2023 | 1057 | GHOSH BROTHERS... | 45.44 | 0 | 100
485 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
486 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.92 | 55
487 | Balurghat Division | Malda Mechanical Division | Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion of all civil, electrical and mechanical works including all allied and related works of Sub- Surface Water Based Piped Water Supply Scheme in Kumarganj block of Dakshin Dinajpur district followed by three (3) months trial run and Five (05) year operation and maintenance. | Assistant Engineer - I | Junior Engineer-01 | ORD/000146/2023-2024 | 1469/BD | 15/09/2023 | 898 | ECO PROTECTION ENGINEERS PVT. LTD. | 18555.31 | 0 | 38
488 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000011/2024-2025 | 1545/BD | 28/08/2024 | 0 | Resource Division | 61.6 | 0 | 0
489 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000018/2024-2025 | 2304/BD | 22/11/2024 | 0 | Resource Division | 61.6 | 0 | 0
490 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000037/2023-2024 | 1145/BD | 14/08/2023 | 0 | Resource Division | 191.42 | 0 | 0
491 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000038/2023-2024 | 1146/BD | 14/08/2023 | 0 | Resource Division | 2202.73 | 0 | 0
492 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000045/2023-2024 | 1548/BD | 03/10/2023 | 0 | Resource Division | 985.63 | 0 | 0
493 | Malda Mechanical | Malda Mechanical Division | Quotation for Shifting of 11KV HTOH & LTOH lines at 4(Four)nos OHR site Under Kumarganj Sub Surface in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/00019/2024-2025 | BP-2024-25-33 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 9.77 | 0 | 0
494 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Palashi OHR Site (Zone-I), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03776/2023-2024 | BP-2024-25-1 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.81 | 0 | 0
495 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Krishnapur OHR Site (Zone-X), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03777/2023-2024 | BP-2024-25-2 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.3 | 0 | 0
496 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Udaypur OHR Site (Zone-XIII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03778/2023-2024 | BP-2024-25-3 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.81 | 0 | 0
497 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Deor OHR Site (Zone-XVII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03779/2023-2024 | BP-2024-25-4 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.4 | 0 | 0
498 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Pojahar OHR Site (Zone-XVI), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03780/2023-2024 | BP-2024-25-5 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.19 | 0 | 0
499 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Paikjhara OHR Site (Zone-XV), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03781/2023-2024 | BP-2024-25-6 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.62 | 0 | 0
500 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Lakhankuri OHR Site (Zone-XIV), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03782/2023-2024 | BP-2024-25-7 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 9.43 | 0 | 0
501 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Azadpur OHR Site (Zone-XII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03783/2023-2024 | BP-2024-25-8 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.74 | 0 | 0
502 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Kulahari OHR Site (Zone-XI), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03784/2023-2024 | BP-2024-25-9 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.65 | 0 | 0
503 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Ujirpur OHR Site (Zone-IX), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03785/2023-2024 | BP-2024-25-10 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0
504 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Damodarpur OHR Site (Zone-VIII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03786/2023-2024 | BP-2024-25-11 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.54 | 0 | 0
505 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Bhagabatipur OHR Site (Zone-VII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03787/2023-2024 | BP-2024-25-12 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.67 | 0 | 0
506 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Tajpur OHR Site (Zone-VI), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03788/2023-2024 | BP-2024-25-13 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.67 | 0 | 0
507 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Uthrail OHR Site (Zone-IV), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03789/2023-2024 | BP-2024-25-14 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 7.02 | 0 | 0
508 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at Brahmanpara OHR Site (Zone-III), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/03790/2023-2024 | BP-2024-25-15 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 9.1 | 0 | 0
509 | Malda Mechanical | Malda Mechanical Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer-01 | ORD/000055/2024-2025 | 1335/MLMD | 25/04/2024 | 61 | RAMCHANDRA BASAK | 0.78 | 0 | 100
510 | Malda Mechanical | Malda Mechanical Division | Providing Electrical Equipments with all ancillaries and auxiliaries for 2 x 315 KVA (11KV/0.433KV) Sub- Station at WTP of Kumarganj Eastern Sector under Sub-Surface Water Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001680/2023-2024 | 3417/MLMD | 01/11/2023 | 365 | ORIENTAL ENGINEERING CO. | 201.01 | 0 | 0
511 | Malda Mechanical | Malda Mechanical Division | Providing Eletro-Mechanical Components and Making Compound Lighting Arrangement at ten (10) nos Ground Water Based Piped W/S Scheme at Different Distribution Zone (I to X) for Eastern Sector of Kumarganj Sub-surface Water Based Piped W/S Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001681/2023-2024 | 3418/MLMD | 01/11/2023 | 788 | EASTERN INDIA SALES & SERVICE. | 136.12 | 0 | 85
512 | Malda Mechanical | Malda Mechanical Division | Supply, installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for Distribution Zone-I, III & X (OHR Site) at Eastern Sector of Kumarganj Sub-Surface Water Based Piped W/S Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001692/2023-2024 | 3420/MLMD | 01/11/2023 | 365 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 91.39 | 0 | 70
513 | Malda Mechanical | Malda Mechanical Division | Supply, installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for Distribution Zone-XV & XVII (OHR Site) at Western Sector of Kumarganj Sub-Surface Water Based Piped W/S Scheme in the District of Dakshin Dinajpur under malda Mechanical division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001694/2023-2024 | 3421/MLMD | 01/11/2023 | 365 | DEY ENTERPRISE.. | 60.96 | 0 | 70
514 | Balurghat Division |  | Acceptance cum work order for the work of Withdrawn, Relaying /laying of distribution pipe line and Rising main due to Bank Protection work of river Tangon under the commandary of Dhumpara piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000015/2022-2023 | 2553/BSSD | 11/04/2022 | 25 | SARADA ENTERPRISE | 2.18 | 2.16 | 1
515 | Balurghat Division |  | Acceptance cum work order for the work of Estimate for collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for different piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [PART - II (1st PHASE DPR)] |  |  | ORD/000078/2021-2022 | 924/BD | 10/05/2021 | 61 | MOHANTA BUILDERS | 1.69 | 0.83 | 1
516 | Balurghat Division |  | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dhumpara Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. [Work Order No. 1492/BD Dated 10/10/2020 & Tender No. 200 of 2020-2021] |  |  | VCH/000157/2022-2023 | BP-2022-23-26 | 16/04/2022 | 0 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 1.82 | 0 | 0
517 | Balurghat Division | RWS Balurghat Sub-Division | Providing Functional House Hold Tap connection under Augmentation of Kumarganj Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur (Phase - I) |  | Junior Engineer Kumarganj | ORD/000044/2022-2023 | 921/BD | 26/05/2022 | 45 | ABHIJIT HAZRA | 28.06 | 26.52 | 100
518 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Kumarganj Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kumarganj | ORD/000310/2021-2022 | 2041/BD | 15/09/2021 | 15 | M/S. SOBHA & CO. | 2.82 | 2.75 | 1
519 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kumarganj | RTOR000009/2022-2023 | 833/BD | 11/05/2022 | 0 | Resource Division | 3.27 | 0 | 0
520 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Kumarganj Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1912/BSSD dt. 01/12/2021 & Tender No. 424 of 2021-2022] |  | Junior Engineer Kumarganj | VCH/000563/2021-2022 | BP-2021-22-127 | 22/03/2022 | 0 | RABIN KAMETH | 4.86 | 0 | 0
521 | Balurghat Division | RWS Balurghat Sub-Division | Providing Functional House Hold Tap connection under Augmentation of Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur (Phase - II) | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000043/2022-2023 | 919/BD | 26/05/2022 | 1096 | NARENDRANATH PAUL | 67.68 | 0 | 90
522 | Balurghat Division | RWS Balurghat Sub-Division | Laying of Rising Main, Construction of 350 cum capacity OHR with 20m Staging Height Including with Soil Investigation, Repairing of Pump House (H/W site & 2nd TW site), Blower Room, repairing of Boundary Wall for Augmentation of Agachha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000097/2023-2024 | 1095/BD | 10/08/2023 | 784 | BOSE CONSTRUCTION | 170.22 | 0 | 18
523 | Balurghat Division | RWS Balurghat Sub-Division | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at different locations of Kumarganj and Agachha Piped Water Supply Scheme under Kumarganj Block , Balurghat Division, PHE Dte in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000145/2023-2024 | 1429/BD | 08/09/2023 | 30 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 9.69 | 0 | 100
524 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000001/2022-2023 | 835/BD | 11/05/2022 | 0 | Resource Division | 8.88 | 0 | 0
525 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000013/2023-2024 | 145/BD | 24/04/2023 | 0 | Resource Division | 31.59 | 0 | 0
526 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000024/2024-2025 | 2318/BD | 22/11/2024 | 0 | Resource Division | 9.95 | 0 | 0
527 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000047/2021-2022 | 346/BD | 22/02/2022 | 0 | Resource Division | 1.65 | 0 | 0
528 | Malda Mechanical | RWS Balurghat Sub-Division | Shifting & diversion of 11KV HTOH line from the PHE site at Agacha, PS-Kumarganj | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | BILL/02478/2024-2025 | BP-2024-25-572 | 14/11/2024 | 0 | W.B.S.E.D.C.LTD | 4.24 | 0 | 0
529 | Malda Mechanical | RWS Balurghat Sub-Division | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000085/2023-2024 | 645/MLMD | 06/04/2023 | 61 | RAMCHANDRA BASAK | 0.29 | 0.28 | 100
530 | Malda Mechanical | RWS Balurghat Sub-Division | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-I ,Under Mechanical Division, P.H.E. Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000447/2023-2024 | 645/MLMD. | 06/04/2023 | 60 | RAMCHANDRA BASAK | 0.51 | 0.51 | 100
531 | Malda Mechanical | RWS Balurghat Sub-Division | Making compound lighting arrangement with allied works at T/W no. I of Agachha Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009294) | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000603/2023-2024 | 2649/MLMD | 10/08/2023 | 45 | M/S. MAYUKH BHADURI | 2.27 | 0 | 0
532 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of AGACHA Water Supply Scheme T/W no.II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000726/2022-2023 | 2272/MLMD | 31/08/2022 | 45 | KARMAKAR CONSTRICTION | 7.37 | 7.37 | 100
533 | Malda Mechanical | RWS Balurghat Sub-Division | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Agacha Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/001230/2021-2022 | 550 /MLMD | 28/03/2022 | 30 | PABITRA MANDAL | 6.19 | 5.7 | 1
534 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. II of Agacha piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/001254/2021-2022 | 479 /MLMD | 24/03/2022 | 30 | M/S D.G.B. ENTERPRISE | 3.1 | 3.09 | 1
535 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Agachha piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/001260/2021-2022 | 478 /MLMD | 24/03/2022 | 30 | HANNAN BUILDERS PVT. LTD. | 3.1 | 3.09 | 1
536 | Balurghat Division | Balurghat Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of Pump House for implementation of Piped Water Supply Scheme for Elahabad Mouza in connection with parent Scheme of Pond Based Piped Water Supply Scheme Using Nandan Bill Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000204/2022-2023 | 3508/BD | 04/03/2023 | 726 | NILKAMAL BASAK | 219.05 | 165.25 | 78
537 | Balurghat Division | Balurghat Division | Consultancy Service for Preparation of Revised drawing of Distribution network followed by detail Survey and design of pipe line for Ellahbad Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.E. Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000373/2022-2023 | 896/BD | 23/05/2022 | 30 | M/S SOBHA & CO. | 2.47 | 0 | 100
538 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | RTOR000025/2023-2024 | 832/BD | 14/07/2023 | 0 | Resource Division | 6.2 | 0 | 0
539 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | RTOR000084/2022-2023 | 3538/BD | 10/03/2023 | 0 | Resource Division | 38.09 | 0 | 0
540 | Malda Mechanical | Balurghat Division | SUPPLY,DELIVERY,INSTALLATION OF SUBMERSIBLE PUMPING MACHINERY AND OTHER ALLIED ACCESSORIES AT ELAHABAD WATER SUPPLY SCHEME IN THE DISTRICT OF DAKSHIN DINAJPUR UNDER MALDA MECHANICAL DIVISION, PHED. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/001783/2023-2024 | 3453/MLMD | 03/11/2023 | 180 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 11.54 | 0 | 96
541 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Elahabad W/S Sch Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/001873/2023-2024 | 4003270120 | 17/11/2023 | 90 | W.B.S.E.D.C.LTD | 11.54 | 0 | 100
542 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Balurghat | ORD/000112/2022-2023 | 526/BD | 01/04/2022 | 30 | M/S. SOBHA & CO. | 3.04 | 3.04 | 1
543 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
544 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Jangalpur (2) Faridpur (3) Dhulatair at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000068/2023-2024 | 820/BD | 13/07/2023 | 1083 | R.K. ENTERPRISE | 2125.46 | 0 | 55
545 | Balurghat Division | Malda Mechanical Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Balurghat Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000131/2024-2025 | 1906/BD | 26/09/2024 | 20 | R.P. CHOUDHURY CONSTRUCTION. | 8.55 | 0 | 100
546 | Balurghat Division | Malda Mechanical Division | Laying of additional Distribution pipe line for the left out area and other allied works within command area of Faridpur Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000172/2024-2025 | 2272/BD | 20/11/2024 | 30 | M/S. SARKAR CONSTRUCTION | 14.68 | 0 | 0
547 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000039/2022-2023 | 2904/BD | 06/01/2023 | 0 | Resource Division | 22.22 | 0 | 0
548 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000058/2023-2024 | 251/BD | 21/02/2024 | 0 | Resource Division | 24.98 | 0 | 0
549 | Malda Mechanical | Malda Mechanical Division | QUOTATION PAYMENT FOR PH NO-1 FARIDPUR PWSS UNDER PATIRAM CCC IN THE DISTRICT OF DAKSHIN DINAJPUR. | Assistant Engineer - I | Junior Engineer-01 | BILL/00205/2024-2025 | BP-2024-25-90 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.06 | 0 | 0
550 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of FARIDPUR, patiram C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/02565/2023-2024 | BP-2023-24-460 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.38 | 0 | 0
551 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Faridpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014480) | Assistant Engineer - I | Junior Engineer-01 | ORD/000452/2023-2024 | 2548/MLMD | 04/08/2023 | 120 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 30.21 | 0 | 93
552 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 558 | GHOSH BROTHERS | 3593.49 | 0 | 30
553 | Balurghat Division | Malda Mechanical Division | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Jantigram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000183/2024-2025 | 2454/BD | 17/12/2024 | 30 | M/S. A.D. ENTERPRISE | 22.42 | 0 | 0
554 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000041/2022-2023 | 2906/BD | 06/01/2023 | 0 | Resource Division | 24.94 | 0 | 0
555 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-II of Jantigram PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-53 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.51 | 0 | 0
556 | Malda Mechanical | Malda Mechanical Division | : Payment for the quotation of New Connection of PH NO-I OF Jantigram PWSS under Patiram CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00036/2024-2025 | BP-2024-25-54 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.06 | 0 | 0
557 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Jantigram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014494) | Assistant Engineer - I | Junior Engineer-01 | ORD/000369/2023-2024 | 2376/MLMD | 28/07/2023 | 1064 | ANIMA ENTERPRISE | 26.58 | 0 | 100
558 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
559 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
560 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 6.68 | 55
561 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
562 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 18.68 | 55
563 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
564 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 12.96 | 55
565 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
566 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.01 | 55
567 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
568 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
569 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 25.45 | 55
570 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
571 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 17.69 | 55
572 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
573 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
574 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 14.77 | 55
575 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
576 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 15.38 | 55
577 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
578 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 24.92 | 55
579 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
580 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
581 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.8 | 55
582 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of allied pipe line & restoration of damaged pipe line for providing FHTC including other related works for retrofitting of Pundari PWSS at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000241/2022-2023 | 3924/BD | 30/03/2023 | 45 | ABHIJIT HAZRA | 20.77 | 17.91 | 90
583 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kushmandi | RTOR000001/2023-2024 | 09/BD | 04/04/2023 | 0 | Resource Division | 1.51 | 0 | 0
584 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kushmandi | RTOR000017/2023-2024 | 841/BD | 14/07/2023 | 0 | Resource Division | 0.89 | 0 | 0
585 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
586 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
587 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
588 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.73 | 55
589 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
590 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
591 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
592 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.68 | 55
593 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
594 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
595 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
596 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
597 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
598 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Baghichapur Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000038/2020-2021 | 1877/BD | 07/12/2020 | 45 | SUBODH KUMAR SAHA | 23.25 | 34.28 | 1
599 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Dolgaon Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000039/2020-2021 | 1878/BD | 07/12/2020 | 45 | J. CHATTERJEEE & CO. | 17.71 | 27.45 | 1
600 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Nendra Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000043/2020-2021 | 1857/BD | 07/12/2020 | 35 | LOKNATH ENTERPRISE | 8.61 | 9.44 | 1
601 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chhatrakunda Mouza under Baghichapur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000058/2020-2021 | 1945/BD | 16/12/2020 | 45 | BOSE CONSTRUCTION | 11.42 | 19.13 | 1
602 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Muknair Mouza under Bagichapur Piped Water Based Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000063/2020-2021 | 1974/BD | 18/12/2020 | 35 | KRISHNA PAUL | 3.76 | 6.9 | 1
603 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bahadurpur Mouza under Bagichapur Piped Water Based Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000064/2020-2021 | 1975/BD | 18/12/2020 | 35 | SARKAR CONSTRUCTION | 3.54 | 6.07 | 1
604 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Baghichapur & adjoining mouzas for Bhebrahar Mouza at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000073/2020-2021 | 2039/BD | 29/12/2020 | 35 | M/S. A.D. ENTERPRISE | 9.19 | 17.11 | 1
605 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bahadurpur Mouza under Bagichapur Piped Water Based Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | VCH/000053/2021-2022 | 8443/32 | 21/06/2021 | 0 | SARKAR CONSTRUCTION | 0.15 | 0 | 0
606 | Balurghat Division | Balurghat Sadar Sub-Division | Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for different piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [PART - IV (For On-Going PWSS)] [Work Order No. 926/BD dt. 10/05/2021 & Tender No. 52 of 2021-2022] |  | Junior Engineer 2 | VCH/000490/2021-2022 | 8443/33 | 15/03/2022 | 0 | M/S. S.D. CONSTRUCTION | 2.25 | 0 | 0
607 | Balurghat Division | Balurghat Division | Source Augmentation of Nawapara Piped Water Supply Scheme comprising of Sinking of One Big Dia Tubewell, Construction of (3.6mtr. X 3.00 mtr.) Pump House and Construction of Boundary wall for 3rd Tubewell Site at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000229/2022-2023 | 3876/BD | 28/03/2023 | 514 | MOHANTA BUILDERS | 36.78 | 0 | 90
608 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Nawapara, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | BILL/02473/2023-2024 | BP-2023-24-407 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.62 | 0 | 0
609 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Nawapara Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016324) | Assistant Engineer - I | Junior Engineer Hili,Junior Engineer-01 | ORD/000483/2023-2024 | 2559/MLMD | 04/08/2023 | 120 | JIBU SINGHA | 10.01 | 0 | 82
610 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Jangalpur (2) Faridpur (3) Dhulatair at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000068/2023-2024 | 820/BD | 13/07/2023 | 1083 | R.K. ENTERPRISE | 2125.46 | 0 | 55
611 | Balurghat Division | Malda Mechanical Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Balurghat Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000131/2024-2025 | 1906/BD | 26/09/2024 | 20 | R.P. CHOUDHURY CONSTRUCTION. | 8.55 | 0 | 100
612 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000040/2022-2023 | 2905/BD | 06/01/2023 | 0 | Resource Division | 42.57 | 0 | 0
613 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000057/2023-2024 | 250/BD | 21/02/2024 | 0 | Resource Division | 27.23 | 0 | 0
614 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of JANGALPUR, Balurghat C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/02477/2023-2024 | BP-2023-24-403 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 8.28 | 0 | 0
615 | Malda Mechanical | Malda Mechanical Division | Quotation Payment for jangalpur PH No II under Balurghat CCC. | Assistant Engineer - I | Junior Engineer-01 | BILL/03502/2023-2024 | BP-2023-24-523 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 7.94 | 0 | 0
616 | Malda Mechanical | Malda Mechanical Division | Quotation Payment for JANGALPUR PH NO1 under Balurghat ccc | Assistant Engineer - I | Junior Engineer-01 | BILL/03503/2023-2024 | BP-2023-24-522 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 7.93 | 0 | 0
617 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Jangalpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014518) | Assistant Engineer - I | Junior Engineer-01 | ORD/001667/2023-2024 | 2592/MLMD | 08/08/2023 | 873 | DEY ENTERPRISE.. | 41.21 | 0 | 95
618 | Balurghat Division | RWS Balurghat Sub-Division | Formal Work Order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for KALIBARI Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Balurghat | ORD/000095/2020-2021 | 79/BD | 08/01/2021 | 45 | PRADIP KUMAR PAUL | 72.87 | 91.14 | 1
619 | Balurghat Division | RWS Balurghat Sub-Division | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for PANJUL Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Hili | ORD/000025/2020-2021 | 1586/BD | 16/10/2020 | 791 | M/S. ANWESHA ENTERPRISE | 84.95 | 121.31 | 1
620 | Balurghat Division | RWS Balurghat Sub-Division | Restoration of Distribution Pipeline at Agra and Kharun Mouza within Panjul Piped Water Supply Scheme at Hili Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. |  | Junior Engineer Hili | ORD/000074/2023-2024 | 870/BD | 24/07/2023 | 30 | SARKAR CONSTRUCTION | 4.69 | 0 | 100
621 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for Panjul PWSS, under Jal Swapna Programme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer Hili | ORD/000252/2021-2022 | 2197/BD | 28/09/2021 | 30 | M/S. R.D. CONSTRUCTION | 9.08 | 8.56 | 100
622 | Balurghat Division |  | Formal work order for the work of Providing Functional Household Tap Connection Under Khidirpur Pipe Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000056/2020-2021 | 1902/BD | 09/12/2020 | 60 | MOHANTA BUILDERS | 84.28 | 157.51 | 1
623 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Deulabari Mouza under Hansrail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000040/2020-2021 | 1879/BD | 07/12/2020 | 45 | SARADA ENTERPRISE | 14.13 | 26.02 | 1
624 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Sarala Mouza under Hansrail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000041/2020-2021 | 1880/BD | 07/12/2020 | 45 | NARENDRANATH PAUL | 28.29 | 50.08 | 1
625 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Hansrail Mouza under Hansrail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000076/2020-2021 | 2042/BD | 29/12/2020 | 35 | CHHAYA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 6.89 | 11.92 | 100
626 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Allied Work to resolve complain under PARAY SAMADHAN In Connection With Providing Functional House Hold Tap Connection For Hansrail PWSS (Deulabari Mouza and Sarala Mouza)Under Jal Swapna Programme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000163/2020-2021 | 230/BD | 25/01/2021 | 25 | SARADA ENTERPRISE | 1.38 | 2.64 | 0
627 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Hansrail PWSS Under Jal Swapna Programme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000245/2021-2022 | 1812/BSSD | 01/10/2021 | 20 | MAYA CONSTRUCTION | 2.31 | 2.28 | 1
628 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Anantapur Zone I Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II) |  | Junior Engineer Kushmandi | ORD/000221/2020-2021 | 509/BD | 25/02/2021 | 45 | M/S. ANWESHA ENTERPRISE | 21.9 | 0 | 1
629 | Balurghat Division | RWS Balurghat Sub-Division | Supply of CI / DI specials for Rising Main Interconnection pipe line for Anantapur Zone - I & II piped water supply scheme at Kushmandi Block in the District of Dakshin Dinajpur Under Balurgaht Division P.H.E. Dte. |  | Junior Engineer Kushmandi | ORD/000237/2021-2022 | 417/RWS | 27/08/2021 | 7 | THE NEW LOKNATH CONSTRUCTION | 1.09 | 1.06 | 1
630 | Balurghat Division | RWS Balurghat Sub-Division | Work of Allied pipe Line for FHTC work under Anantapur Zone1 PWSS at Jamundanga and Balapukur mouza at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Department. |  | Junior Engineer Kushmandi | ORD/000257/2021-2022 | 494/RWS | 05/10/2021 | 30 | M/S. ANWESHA ENTERPRISE | 2.65 | 0 | 1
631 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection for Anantapur Zone 2 Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000258/2021-2022 | 2333/BD | 07/10/2021 | 45 | CHOUDHURY CONSTRUCTION | 15.87 | 15.86 | 1
632 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kushmandi | RTOR000034/2021-2022 | 2966/BD | 31/12/2021 | 0 | Resource Division | 2.2 | 0 | 0
633 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kushmandi | RTOR000043/2021-2022 | 204/BD | 02/02/2022 | 0 | Resource Division | 5.49 | 0 | 0
634 | Balurghat Division | RWS Balurghat Sub-Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Anantpur Zone 1 Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 504/BD dated :- 25/02/2021 & Tender No. 06 of 2021-2022] |  | Junior Engineer Kushmandi | VCH/000254/2022-2023 |  | 21/07/2022 | 0 | DIPESH BHOWMIK | 11.5 | 0 | 0
635 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000341/2021-2022 | 1921/BSSD | 01/12/2021 | 25 | SREEMAA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.78 | 3.32 | 1
636 | Balurghat Division | Balurghat Division | Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Patiram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000538/2021-2022 | 550/RWS | 03/12/2021 | 15 | ENVIROTECH SOLUTIONS | 3.4 | 2.99 | 1
637 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap connection under Augmentation of Sayedpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur (Phase - I) |  | Junior Engineer 2 | ORD/000032/2022-2023 | 845/BD | 12/05/2022 | 30 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 10.27 | 8.97 | 1
638 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Sayedpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000319/2021-2022 | 2050/BD | 15/09/2021 | 15 | ENVIROTECH SOLUTIONS | 2.7 | 2.19 | 1
639 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer 2 | RTOR000010/2022-2023 | 834/BD | 11/05/2022 | 0 | Resource Division | 1.3 | 0 | 0
640 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Saidpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1917/BSSD Dated :- 01/12/2021 & Tender No. 415 of 2021-2022] |  | Junior Engineer 2 | VCH/000164/2022-2023 | BP-2022-23-19 | 16/04/2022 | 0 | DIPU PRASAD. | 4.86 | 0 | 0
641 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap connection under Augmentation of Sayedpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur (Phase - II). | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000031/2022-2023 | 844/BD | 12/05/2022 | 45 | SADHURHAT CO OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 34.57 | 34.08 | 1
642 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum Work Order for Allied work for Laying Distribution pipe line for Saidpur P.W.S.S. at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000079/2022-2023 | 2627/BSSD | 26/05/2022 | 15 | ASHIT KUMAR DEBSHARMA | 2.32 | 2.3 | 1
643 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main, Construction of 300 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Sayedpur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000218/2022-2023 | 3789/BD | 22/03/2023 | 651 | ASHIT KUMAR DEBSHARMA | 124.93 | 0 | 100
644 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Laying of distribution pipe line for Augmentation of Saidpur piped water supply scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000415/2021-2022 | 75/BD | 11/01/2022 | 60 | ASHIT KUMAR DEBSHARMA | 79.45 | 79.25 | 1
645 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000005/2022-2023 | 839/BD | 11/05/2022 | 0 | Resource Division | 4.69 | 0 | 0
646 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000011/2023-2024 | 127/BD | 18/04/2023 | 0 | Resource Division | 5.62 | 0 | 0
647 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000050/2021-2022 | 344/BD | 22/02/2022 | 0 | Resource Division | 0.57 | 0 | 0
648 | Central Drilling | Balurghat Sadar Sub-Division | ADDITIONAL TRANSPORTATION OF WASHED GRAVELS BEYOND 200 KM FOR SAIDPUR W/S SCH REPLACEMENT TUBE WELL UNDER CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000311/2022-2023 | 582/CMSD-I | 30/11/2022 | 7 | C.M. ENTERPRISE | 0.79 | 0.38 | 1
649 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILIZING MACHINERIES FOR SAIDPUR W/S SCH (REPLACEMENT TW), UNDER DAKSHIN DINAJPUR DISTRICT, UNDER CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000317/2022-2023 | 1167/CDD | 09/11/2022 | 30 | C.M. ENTERPRISE | 8.55 | 6.07 | 1
650 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Saidpur, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000784/2023-2024 | 4003209051 | 10/08/2023 | 90 | W.B.S.E.D.C.LTD | 0.4 | 0.4 | 100
651 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Saidpur, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000785/2023-2024 | 4003209047 | 10/08/2023 | 90 | W.B.S.E.D.C.LTD | 0.44 | 0.44 | 100
652 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SAYEDPUR Water Supply Scheme T/W no. II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000962/2022-2023 | 2948/MLMD | 28/12/2022 | 663 | MANIK CHANDRA SAHA. | 10.47 | 9.22 | 100
653 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, delivery and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Saidpur piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/001398/2021-2022 | 475/MLMD | 24/03/2022 | 10 | J.K ENGINEERING CO. | 2.75 | 2.73 | 1
654 | Malda Mechanical | Balurghat Sadar Sub-Division | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Saidpur Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/001400/2021-2022 | 551/MLMD | 28/03/2022 | 30 | DAS CONSTRUCTION | 6.04 | 5.43 | 1
655 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
656 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
657 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 15.01 | 55
658 | Balurghat Division | RWS Balurghat Sub-Division | Providing Functional House Hold Tap connection under Augmentation of Agachha Piped Water Supply Scheme at Kumarganj Block in the District of DakshinDinajpur (Phase - I) |  | Junior Engineer Kumarganj | ORD/000042/2022-2023 | 918/BD | 26/05/2022 | 710 | MAA CHANCHALA CONSTRUCTION | 22.55 | 12.73 | 1
659 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Agaccha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kumarganj | ORD/000311/2021-2022 | 2046/BD | 15/09/2021 | 15 | M/S. SOBHA & CO. | 2.83 | 2.83 | 1
660 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kumarganj | RTOR000006/2022-2023 | 830/BD | 11/05/2022 | 0 | Resource Division | 2.46 | 0 | 0
661 | Balurghat Division | RWS Balurghat Sub-Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Agacha Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) [Work Order No. 1915/BSSD dt. 01/12/2021 & Tender No. 378 of 2021-2022] |  | Junior Engineer Kumarganj | VCH/000568/2021-2022 | BP-2021-22-147 | 25/03/2022 | 0 | R.P. CHOUDHURY CONSTRUCTION. | 4.27 | 0 | 0
662 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
663 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
664 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
665 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
666 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 12.23 | 55
667 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
668 | Balurghat Division | Malda Mechanical Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Aminpur- Dehaband Road via Kantason, Sarala from (Chainage 0.00 KM to 15.45 Km) | Assistant Engineer - I | Junior Engineer-01 | BILL/00109/2024-2025 | BP-2024-25-81 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 6.91 | 0 | 0
669 | Balurghat Division | Malda Mechanical Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase- II) | Assistant Engineer - I | Junior Engineer-01 | ORD/000140/2024-2025 | 1951/BD | 27/09/2024 | 20 | KINSHIP CONSTRUCTION | 2.39 | 0 | 100
670 | Balurghat Division | Malda Mechanical Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) | Assistant Engineer - I | Junior Engineer-01 | ORD/000146/2024-2025 | 2052/BD | 03/10/2024 | 20 | GOUTAM SAHA | 2.39 | 0 | 100
671 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000014/2024-2025 | 2305/BD | 22/11/2024 | 0 | Resource Division | 2.5 | 0 | 0
672 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000055/2023-2024 | 255/BD | 21/02/2024 | 0 | Resource Division | 15.12 | 0 | 0
673 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000057/2022-2023 | 2872/BD | 06/01/2023 | 0 | Resource Division | 16.94 | 0 | 0
674 | Central Drilling | Malda Mechanical Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Jarail W/S Scheme (TW-I & II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000472/2022-2023 | 1809/CDD | 04/01/2023 | 30 | PADMA ENGINEERING & CO. | 20.01 | 14.86 | 100
675 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of JARAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000270/2023-2024 | 4003194070 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.96 | 2.96 | 100
676 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of JARAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000271/2023-2024 | 4003194072 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.43 | 3.43 | 100
677 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Jarail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013052) | Assistant Engineer - I | Junior Engineer-01 | ORD/000455/2023-2024 | 2549/MLMD | 04/08/2023 | 812 | M/S PARIMAL DAS. | 26.77 | 0 | 90
678 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House for implementation of Dilkunthi Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000029/2023-2024 | 370/BD | 22/05/2023 | 770 | M/S. NANDY ENTERPRISE | 689.75 | 0 | 10
679 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | RTOR000058/2022-2023 | 2879/BD | 06/01/2023 | 0 | Resource Division | 19.3 | 0 | 0
680 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DILKUNTHI, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | BILL/02563/2023-2024 | BP-2023-24-458 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.02 | 0 | 0
681 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of DILKUNTHI, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | BILL/02564/2023-2024 | BP-2023-24-459 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.35 | 0 | 0
682 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dilkunthi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013332) | Assistant Engineer - I | Junior Engineer 2,Junior Engineer-01 | ORD/000351/2023-2024 | 2341/MLMD | 26/07/2023 | 1035 | ANIMA ENTERPRISE | 26.85 | 0 | 90
683 | Balurghat Division | Malda Mechanical Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Daulatpur-Harirampur-Dehaband Road from (chainage 7.00 K.M to 20.60 K.M). | Assistant Engineer - I | Junior Engineer-01 | BILL/00193/2024-2025 | BP-2024-25-124 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 17.47 | 0 | 0
684 | Balurghat Division | Malda Mechanical Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Harirampur-Beldangi Road from (Chainage 0.0 K.M to 9.40 K.M). | Assistant Engineer - I | Junior Engineer-01 | BILL/00210/2024-2025 | BP-2024-25-134 | 13/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 19.58 | 0 | 0
685 | Balurghat Division | Malda Mechanical Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 400 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for Augmentation of Harirampur Piped Water Supply Scheme at Harirampur Block in the District of DakshinDinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000091/2023-2024 | 991/BD | 31/07/2023 | 964 | ASHIT KUMAR DEBSHARMA | 635.33 | 0 | 55
686 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000049/2023-2024 | 38/BD | 09/01/2024 | 0 | Resource Division | 12.81 | 0 | 0
687 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000074/2022-2023 | 3493/BD | 03/03/2023 | 0 | Resource Division | 37.69 | 0 | 0
688 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Harirampur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014718) | Assistant Engineer - I | Junior Engineer-01 | ORD/000459/2023-2024 | 2552/MLMD | 04/08/2023 | 810 | MANIK CHANDRA SAHA. | 24.85 | 0 | 78
689 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
690 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.84 | 55
691 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
692 | Balurghat Division |  | Extension of pipe line & Providing FHTC under Augmentation of Domran Piped Water Supply Scheme at Hili Block, in the District of Dakshin Dinajpur under Balurghat division,PHE Dte. |  |  | ORD/000230/2022-2023 | 3875/BD | 28/03/2023 | 45 | MAMTAJ ALI | 21 | 19.89 | 0
693 | Balurghat Division |  | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 840/BD | 14/07/2023 | 0 | Resource Division | 0.86 | 0 | 0
694 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
695 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 10.37 | 55
696 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
697 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
698 | Balurghat Division | Balurghat Division | Laying of Rising Main, Providing FHTC, Construction of 200 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Sundail Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000012/2023-2024 | 189/BD | 28/04/2023 | 1083 | M/S. ANWESHA ENTERPRISE | 163.05 | 21.41 | 36
699 | Balurghat Division | Balurghat Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Gangarampur & Harirampur Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000125/2024-2025 | 1914/BD | 26/09/2024 | 20 | ASHIT KUMAR DEBSHARMA | 8.35 | 0 | 100
700 | Balurghat Division | Balurghat Division | Laying of additional distribution pipeline and construction of approach road and other allied works within command area of Sundail Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000169/2024-2025 | 2258/BD | 13/11/2024 | 225 | RABIN KAMETH | 27.44 | 0 | 80
701 | Balurghat Division | Balurghat Division | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 60 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 0 | 100
702 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | RTOR000023/2023-2024 | 836/BD | 14/07/2023 | 0 | Resource Division | 7.34 | 0 | 0
703 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | RTOR000051/2022-2023 | 2883/BD | 06/01/2023 | 0 | Resource Division | 11.06 | 0 | 0
704 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUNDAIL W/S SCH TW-II, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000359/2022-2023 | 1169/CDD | 09/11/2022 | 30 | M/S SAIKAT ENTERPRISE | 8.28 | 6.25 | 0
705 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SUNDAIL W/S SCH TW-I, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000361/2022-2023 | 1168/CDD | 09/11/2022 | 30 | S B S ENTERPRISE | 8.2 | 6.1 | 0
706 | Central Drilling | Balurghat Division | Additional carraige of gravels for Construction of Tube well at SUNDAIL PWSS TW-II, Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000478/2022-2023 | 586/CMSD-I(D) | 30/11/2022 | 7 | M/S SAIKAT ENTERPRISE | 0.59 | 0 | 100
707 | Central Drilling | Balurghat Division | Additional carraige of gravels for Construction of Tube well at SUNDAIL PWSS TW-I, Harirampur block, Dakshin Dinajpur District under CMSD-I (D), CDD PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000480/2022-2023 | 585/CMSD-I(D) | 30/11/2022 | 7 | S B S ENTERPRISE | 0.59 | 0 | 100
708 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sundail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011985) | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2023-2024 | 2097/MLMD | 04/07/2023 | 1088 | GHOSH BROTHERS... | 26.29 | 0 | 90
709 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SUNDAIL, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000268/2023-2024 | 4003195607 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.61 | 6.61 | 100
710 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SUNDAIL, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000269/2023-2024 | 4003195612 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.85 | 6.85 | 100
711 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
712 | Balurghat Division | Balurghat Sadar Sub-Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Fatepur - Dehaband Road from (Chainage 0.00 KM to 10.00 Km) | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00125/2024-2025 | BP-2024-25-88 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 13.67 | 0 | 0
713 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.54 | 55
714 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
715 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
716 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
717 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
718 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
719 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
720 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 5.54 | 55
721 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
722 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
723 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
724 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.68 | 55
725 | Balurghat Division | RWS Balurghat Sub-Division | Restoration of Mahipal Chourange more to Kantabari road from chainage 0.0 km to 7.0 km under LOHANGANJ PWSS at Kushmandi Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00113/2024-2025 | BP-2024-25-85 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 18.15 | 0 | 0
726 | Balurghat Division | RWS Balurghat Sub-Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Lohaganja Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000220/2022-2023 | 3821/BD | 23/03/2023 | 1196 | M/S. KAMAK ENGINEERS & CO. | 1213.03 | 507.79 | 85
727 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000012/2024-2025 | 1766/BD | 20/09/2024 | 0 | Resource Division | 0.42 | 0 | 0
728 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000042/2023-2024 | 1490/BD | 19/09/2023 | 0 | Resource Division | 3.61 | 0 | 0
729 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000046/2023-2024 | 30/BD | 09/01/2024 | 0 | Resource Division | 24.23 | 0 | 0
730 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000065/2023-2024 | 266/BD | 22/02/2024 | 0 | Resource Division | 5.37 | 0 | 0
731 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000069/2022-2023 | 2887/BD | 06/01/2023 | 0 | Resource Division | 40.66 | 0 | 0
732 | Central Drilling | RWS Balurghat Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Lohaganja W/S Scheme (TW-I), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000443/2022-2023 | 1939/CDD | 31/01/2023 | 30 | M/S P P ELECTRICALS | 9.42 | 6.93 | 0
733 | Central Drilling | RWS Balurghat Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Lohaganja W/S Scheme (TW-III), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000444/2022-2023 | 1941/CDD | 31/01/2023 | 30 | UNIVERSAL ENTERPRISES | 9.7 | 7.12 | 0
734 | Central Drilling | RWS Balurghat Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Lohaganja W/S Scheme (TW-II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000445/2022-2023 | 1940/CDD | 31/01/2023 | 30 | UNIVERSAL ENTERPRISES | 9.7 | 7.04 | 0
735 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of LOHAGANJA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/02536/2023-2024 | BP-2023-24-439 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 2.6 | 0 | 0
736 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of LOHAGANJA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000277/2023-2024 | 4003194053 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.62 | 4.62 | 100
737 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of LOHAGANJA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000278/2023-2024 | 4003194052 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.2 | 3.2 | 100
738 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Lohaganja Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013122) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000370/2023-2024 | 2377/MLMD | 28/07/2023 | 180 | CONCORD ENGINEERING | 40.59 | 0 | 91
739 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 400 Cum capacity OHR with 20m Staging Height including Soil Investigation, Repairing and Renovation work of Existing Pump House, Construction of new Pump House, Boundary Wall & Approach Road for implementation of Augmentation of Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000231/2022-2023 | 3904/BD | 29/03/2023 | 960 | ASHOK MITRA | 502.17 | 0 | 45
740 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000019/2024-2025 | 1312/BD | 22/11/2024 | 0 | Resource Division | 13.98 | 0 | 0
741 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000074/2023-2024 | 461/BD | 18/03/2024 | 0 | Resource Division | 1.5 | 0 | 0
742 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000076/2022-2023 | 3491/BD | 03/03/2023 | 0 | Resource Division | 44.15 | 0 | 0
743 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Dhiltail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015236) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000444/2023-2024 | 2455/MLMD | 04/08/2023 | 832 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 25.21 | 0 | 70
744 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Dhiltail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015236) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000445/2023-2024 | 2545/MLMD | 04/08/2023 | 817 | M/S SABANA CONSTRUCTION | 10.72 | 0 | 70
745 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
746 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
747 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 9.24 | 55
748 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection in connection with Retrofitting for Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2 | ORD/000028/2023-2024 | 371/BD | 22/05/2023 | 45 | LOKNATH ENTERPRISE | 21.86 | 0 | 0
749 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2 | ORD/000307/2021-2022 | 2040/BD | 15/09/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.86 | 2.83 | 100
750 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
751 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.9 | 55
752 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
753 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
754 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
755 | Balurghat Division |  | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for SALGAON Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000020/2020-2021 | 1591/BD | 16/10/2020 | 45 | MOHANTA BUILDERS | 62.99 | 0.69 | 1
756 | Balurghat Division |  | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for SALGAON Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Work Order No. 1591/BD, Dated :- 16/10/2020 & TenderNo. 134 of 2020-21). |  |  | VCH/000177/2021-2022 | BP-2021-22-37 | 03/11/2021 | 0 | MOHANTA BUILDERS | 22.31 | 0 | 0
757 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Bilbarail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II) |  |  | ORD/000071/2021-2022 | 989/BD | 18/05/2021 | 45 | CALCON CONSTRUCTION. | 40.02 | 68.88 | 1
758 | Balurghat Division |  | Material Requisition To Resource Division |  |  | RTOR000035/2021-2022 | 2967/BD | 31/12/2021 | 0 | Resource Division | 2.2 | 0 | 0
759 | Balurghat Division | RWS Balurghat Sub-Division | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Mahindra Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000082/2021-2022 | 1061/BD | 02/06/2021 | 60 | J.D.J. ENTERPRISE | 116.26 | 143.71 | 1
760 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Pundari PWSS Under Jal Swapna Programme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000093/2021-2022 | 1539/BD | 27/07/2021 | 45 | DIPESH BHOWMIK | 31.43 | 31.42 | 1
761 | Balurghat Division | RWS Balurghat Sub-Division | Formal work order for the work of "Providing Functional Household Tap Connection Under Pundari Pipe Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte." |  | Junior Engineer Kushmandi | ORD/000176/2020-2021 | 278/BD | 01/02/2021 | 60 | PROJECT INDIA | 90.77 | 103.86 | 1
762 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kushmandi | RTOR000031/2021-2022 | 2963/BD | 31/12/2021 | 0 | Resource Division | 5.78 | 0 | 0
763 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division |  | Junior Engineer Kushmandi | RTOR000045/2021-2022 | 206/BD | 02/02/2022 | 0 | Resource Division | 5.49 | 0 | 0
764 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Buniadpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 | ORD/000116/2022-2023 | 532/BD | 01/04/2022 | 30 | M/S. SOBHA & CO. | 3.58 | 3.58 | 0
765 | Balurghat Division | Balurghat Sadar Sub-Division | Urgent restoration of shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Sitahar Behera Pukur Road from chainage 5.4 Km to 7.20 km |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | BILL/00209/2024-2025 | BP-2024-25-132 | 12/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 10.31 | 0 | 0
766 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection work at ZONE-X of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000001/2022-2023 | 533/BD | 04/04/2022 | 90 | ASHIT KUMAR DEBSHARMA | 106.13 | 35.83 | 100
767 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection by retrofitting at ZONE-VII of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (PHASE-I) |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000002/2023-2024 | 43/BD | 08/04/2023 | 725 | M/S. MAA TARA CONSTRUCTION | 98.85 | 0 | 98
768 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection by retrofitting at ZONE-VI of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I) |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000005/2023-2024 | 42/BD | 08/04/2023 | 90 | AJIT PRAMANICK | 208.5 | 0 | 0
769 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection by retrofitting of Zone-VIII of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000006/2022-2023 | 1249/BD | 14/06/2022 | 60 | M/S. N. ISLAM AND CO. | 54.27 | 54.15 | 1
770 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection by retrofitting of Zone-XIV of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000009/2022-2023 | 2868/BD | 05/01/2023 | 760 | M/S. NANDY ENTERPRISE | 54.66 | 0 | 90
771 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional Household Tap connection by retrofitting at ZONE-IV of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte. (PHASE-I). |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000037/2022-2023 | 912/BD | 25/05/2022 | 90 | DURJOY MITRA | 119.41 | 72.99 | 70
772 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting of existing OHR and other allied structures at Zone - II (600 CUM) of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000075/2023-2024 | 875/BD | 24/07/2023 | 30 | SARKAR CONSTRUCTION | 5.16 | 0 | 100
773 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - III under Gangarampur Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000080/2023-2024 | 894/BD | 25/07/2023 | 30 | M/S. PRASANNA CONSTRUCTION | 4.62 | 0 | 100
774 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone ¿ I under Gangarampur Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000085/2023-2024 | 904/BD | 25/07/2023 | 30 | POPY ENTERPRISE | 4.12 | 0 | 90
775 | Balurghat Division | Balurghat Sadar Sub-Division | Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for Gangarampur Sub Surface piped water supply scheme eastern sector in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000086/2022-2023 | 304/RWS | 02/06/2022 | 30 | MOHANTA CONSTRUCTION | 4.66 | 0 | 100
776 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - IV under Gangarampur Western Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000086/2023-2024 | 916/BD | 26/07/2023 | 30 | RABIN KAMETH | 4.4 | 0 | 100
777 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Headwork Site compound for Zone - V under Gangarampur Western Sector of Sub Surface Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000106/2023-2024 | 1333/BD | 25/08/2023 | 30 | RANJAN CONSTRUCTION | 5.42 | 0 | 0
778 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Gangarampur & Harirampur Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000125/2024-2025 | 1914/BD | 26/09/2024 | 20 | ASHIT KUMAR DEBSHARMA | 8.35 | 0 | 100
779 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - VII under Gangarampur Eastern Sector of Gangarampur Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000126/2024-2025 | 1915/BD | 26/09/2024 | 155 | M/S. PRASANNA CONSTRUCTION | 7.17 | 0 | 100
780 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - XI under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000127/2024-2025 | 1909/BD | 26/09/2024 | 57 | POPY ENTERPRISE | 6.88 | 0 | 100
781 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - VIII under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000128/2024-2025 | 1908/BD | 26/09/2024 | 30 | M/S. BANI CONSTRUCTIUON | 6.81 | 0 | 100
782 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - XIV under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000129/2024-2025 | 1907/BD | 26/09/2024 | 30 | HENA CONSTRUCTION | 6.48 | 0 | 100
783 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - X under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000130/2024-2025 | 1905/BD | 26/09/2024 | 30 | RABIN KAMETH | 5.96 | 0 | 100
784 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - IX under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000142/2024-2025 | 1970/BD | 27/09/2024 | 120 | RANJIT BARMAN | 6.04 | 0 | 100
785 | Balurghat Division | Balurghat Sadar Sub-Division | Construction of Approach road, and other allied works of Head Works Site compound for Zone - XII under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000143/2024-2025 | 1993/BD | 30/09/2024 | 30 | M/S. SAHA CONSTRUCTION | 2.86 | 0 | 100
786 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection by retrofitting of Zone-X of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000149/2022-2023 | 3520/BD | 04/03/2023 | 60 | M/S. ANWESHA ENTERPRISE | 76.03 | 24.08 | 35
787 | Balurghat Division | Balurghat Sadar Sub-Division | Face lifting related works of Head Works Site compound for Zone - VI under Gangarampur Eastern Sector of Sub-Surface Based Piped Water Supply Scheme, in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000158/2024-2025 | 2215/BD | 05/11/2024 | 30 | MAA TARA ENTERPRISE | 4.11 | 0 | 100
788 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection by retrofitting of Zone-XI of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000164/2024-2025 | 2231/BD | 12/11/2024 | 60 | MATIUR RAHAMAN | 49.4 | 0 | 0
789 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection by retrofitting at ZONE-XII of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte.(PHASE-I) |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000168/2022-2023 | 3966/BD | 31/03/2023 | 90 | DURJOY MITRA | 98.11 | 77.91 | 82
790 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection by retrofitting at ZONE-XIII of Gangarampur Eastern Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I) |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000170/2022-2023 | 3965/BD | 31/03/2023 | 90 | M/S. TRILOCHAN CONSTRUCTION CO. | 96.19 | 0 | 0
791 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of additional Distribution Pipe Line for providing balance FHTC at ZONE X of Gangarampur Sub Surface based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000173/2024-2025 | 2267/BD | 20/11/2024 | 135 | MAA CHANCHALA CONSTRUCTION | 24.42 | 0 | 75
792 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of additional Distribution Pipe Line for providing balance FHTC at ZONE IX of Gangarampur Sub Surface based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000174/2024-2025 | 2073/BD | 20/11/2024 | 140 | MINATI CONSTRUCTION | 25.75 | 0 | 30
793 | Balurghat Division | Balurghat Sadar Sub-Division | Collection of Functional House Hold Tap Connection details in prescribed format under JJM Programme including uploading in IMIS portal for Gangarampur Sub Surface piped water supply scheme in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase ¿ III) |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000180/2023-2024 | 1958/BD | 08/12/2023 | 30 | SHYAMAL CHANDRA MANDAL | 3.46 | 0 | 75
794 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Support Structure by driving Bullah piles for Khari Crossing at Sukdevpur, Maharajpur, Thengapara, Pargaon, Joypur, Karial, Nildanga Mouza under Zone-II, III & IV of Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000184/2022-2023 | 3344/BD | 17/02/2023 | 30 | SATELLITE CONSTRUCTION | 31.34 | 10.87 | 40
795 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of HDPE pipeline in Various Zone under Gangarampur Sub Surface Based Piped Water Supply Scheme by using Horizontal Direct Drilling (HDD) method at Gangarampur Block, in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000185/2022-2023 | 3345/BD | 17/02/2023 | 30 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 25.42 | 22.71 | 100
796 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of distribution pipeline at Ramchandrapur Mouza for Gap closing near Railway Crossing of Zone-VI under Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, P.H. Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000187/2023-2024 | 2043/BD | 14/12/2023 | 30 | A.B. ENTERPRISE | 9.92 | 0 | 100
797 | Balurghat Division | Balurghat Sadar Sub-Division | Extension of overflow and washout pipeline at Zone I, Zone V Gangarampur OHR of Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000190/2022-2023 | 3517/BD | 04/03/2023 | 20 | MOTAHAR HOSSAIN | 3.24 | 3.24 | 100
798 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Support Structure and allied work adjacent to Patan Bridge at Narayanpur under Zone - II & III of Gangarampur Sub-surface based Piped Water supply Scheme under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000199/2023-2024 | 275/BD | 23/02/2024 | 30 | SUSHANTA SAHA | 18.04 | 0 | 100
799 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of balance portion of distribution pipe line at Jalilpur Mouza to connect with the existing pipeline under Zone-V of Gangarampur Sub-surface Piped Water supply Scheme under Balurghat Division, PHE Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000200/2022-2023 | 3511/BD | 04/03/2023 | 20 | ANIMA CONSTRUCTION | 1.71 | 1.7 | 0
800 | Balurghat Division | Balurghat Sadar Sub-Division | Laying pipe line for drainage of excess water from GLR site of Gangarampur Sub Surface Based Piped Water Supply Scheme of Eastern Sector at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000227/2022-2023 | 3836/BD | 24/03/2023 | 30 | GOUTAM SAHA | 6.69 | 6.2 | 100
801 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Various Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur. |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000394/2021-2022 | 595/RWS | 31/12/2021 | 30 | GOUTAM SAHA | 4.6 | 3.7 | 0
802 | Balurghat Division | Balurghat Sadar Sub-Division | Formal work order for the work of Providing Functional household Tap connection by retrofitting at ZONE-III of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I). |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000463/2021-2022 | 134/BD | 25/01/2022 | 90 | ASHOK MITRA | 161.08 | 30.22 | 93
803 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection by retrofitting at ZONE-V of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte.(PHASE-I) |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000535/2021-2022 | 428/BD | 10/03/2022 | 90 | DIPESH BHOWMIK | 120.42 | 84.45 | 1
804 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection by retrofitting of Zone-IX of Gangarampur Eastern Sector under Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur (PHASE-I). |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | ORD/000539/2021-2022 | 438/BD | 14/03/2022 | 60 | M/S. N. ISLAM AND CO. | 57.84 | 57.45 | 1
805 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | RTOR000006/2023-2024 | 100/BD | 13/04/2023 | 0 | Resource Division | 14.92 | 0 | 0
806 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | RTOR000007/2023-2024 | 105/BD | 17/04/2023 | 0 | Resource Division | 12.36 | 0 | 0
807 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | RTOR000027/2022-2023 | 2133/BD | 21/09/2022 | 0 | Resource Division | 86.24 | 0 | 0
808 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | RTOR000039/2021-2022 | 140/BD | 27/01/2022 | 0 | Resource Division | 5.97 | 0 | 0
809 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | RTOR000040/2021-2022 | 166/BD | 31/01/2022 | 0 | Resource Division | 22.51 | 0 | 0
810 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | RTOR000041/2021-2022 | 202/BD | 02/02/2022 | 0 | Resource Division | 21.96 | 0 | 0
811 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection by retrofitting at ZONE-III of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I). [Work Order No. 134/BD Dated :- 25/01/2022 & Tender No. 459 of 2021-2022] |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | VCH/000158/2022-2023 | BP-2022-23-15 | 16/04/2022 | 0 | ASHOK MITRA | 50.12 | 0 | 0
812 | Balurghat Division | Balurghat Sadar Sub-Division | Supply of different dia. Sluice Valve for piped water supply scheme for Zone-IV (Phase-I) of Gangarampur Sub-Surface Based Piped Water Supply Scheme at Gangarampur Block, in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte. [Work Order No. 114/RWS Dated :- 28/02/2022 & Tender No. 526 of 2021-2022] |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | VCH/000159/2022-2023 | BP-2022-23-25 | 16/04/2022 | 0 | JUVENILE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 3.73 | 0 | 0
813 | Balurghat Division | Balurghat Sadar Sub-Division | Collection of Functional House Hold Tap Connection details in prescribed format under Jal Swapna Programme including uploading in IMIS website for Gangarampur Sub-Surface piped water supply scheme western sector in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) [Work Order No. 116/RWS Dated :- 28/02/2022 & Tender No. 517 of 2021-2022] |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | VCH/000160/2022-2023 | BP-2022-23-17 | 16/04/2022 | 0 | MOHANTA BUILDERS | 2.22 | 0 | 0
814 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional household Tap connection by retrofitting at ZONE-II of Gangarampur Western Sector under Sub Surface Based Piped Water Supply Scheme at Gangarampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte.(PHASE-I) [Work Order No. 133/BD Dated :- 25/01/2022 & Tender No. 432 of 2021-2022] |  | Junior Engineer (Civil),Junior Engineer 2,Junior Engineer Kushmandi | VCH/000173/2022-2023 | BP-2022-23-3 | 12/04/2022 | 0 | MOHANTA BUILDERS | 84.34 | 0 | 0
815 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Sarangbari Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000049/2020-2021 | 1885/BD | 07/12/2020 | 35 | SUSHANTA CHOUDHURY | 0.97 | 1.55 | 1
816 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chakdurga Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000052/2020-2021 | 1888/BD | 07/12/2020 | 35 | BALURGHAT BUILDERS | 3.11 | 4.91 | 1
817 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chakram Mouza under Chakramprasad Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000059/2020-2021 | 1946/BD | 16/12/2020 | 45 | BIPUL SARKAR | 21.35 | 35.13 | 1
818 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Gazipur Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000066/2020-2021 | 1977/BD | 18/12/2020 | 35 | SUKUMAR GOSWAMI | 2.99 | 3.82 | 1
819 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Mollapara Mouza under Chakramprosad Piped Water Based Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000067/2020-2021 | 1978/BD | 18/12/2020 | 35 | MALAYADRI SARKAR | 4.25 | 4.56 | 1
820 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Ground Water Based Water Supply Scheme for Chakramprasad and adjoining mouzas for Chakismail Mouza at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000074/2020-2021 | 2040/BD | 29/12/2020 | 35 | R.P. CHOUDHURY CONSTRUCTION. | 6.25 | 9.92 | 1
821 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chakshyam Mouza under Chakramprasad Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000075/2020-2021 | 2041/BD | 29/12/2020 | 35 | TECHNO ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.86 | 17.4 | 1
822 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Chak Ramprosad Mouza under Chakramprasad Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000101/2020-2021 | 105/BD | 11/01/2021 | 45 | M/S. A.D. ENTERPRISE | 10.7 | 12 | 1
823 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Mouza Gazipur, Chakramprasad & Mollapara within CHAKRAMPRASAD PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000248/2021-2022 | 1814/BSSD | 01/10/2021 | 80 | SUKUMAR GOSWAMI | 2.5 | 1.83 | 1
824 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
825 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
826 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 11.95 | 55
827 | Balurghat Division | Balurghat Sadar Sub-Division | Laying distribution pipe line for augmentation of Daulatpur Pipe Water Supply Scheme at Banshihari & Harirampur Dev. Block in the district of Dakhin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000144/2022-2023 | 2433/BD | 11/11/2022 | 60 | DIPESH BHOWMIK | 170.15 | 162.49 | 100
828 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 60 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 0 | 100
829 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Permanent Type village wise Scheme Information Board at different Piped Water Supply Schemes under JJM as per departmental design and drawing for Gangarampur, Banshihari, Harirampur & Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000189/2023-2024 | 2070/BD | 16/12/2023 | 45 | M.A. ENTERPRISE | 10.09 | 0 | 91
830 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main, Providing FHTC, Construction of 150 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House repairing, Construction of Boundary Wall for Augmentation of DAULATPUR Piped Water Supply Scheme at Banshihari and Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000248/2022-2023 | 3945/BD | 31/03/2023 | 823 | DURJOY MITRA | 188.44 | 34.97 | 38
831 | Balurghat Division | Balurghat Sadar Sub-Division | Providing FHTC by retrofitting of parent scheme of Daultapur Piped Water Supply Scheme under Banshihari & Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000257/2022-2023 | 3950/BD | 31/03/2023 | 45 | R.P. CHOUDHURY CONSTRUCTION. | 12.1 | 11.13 | 100
832 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000060/2023-2024 | 253/BD | 21/02/2024 | 0 | Resource Division | 10.71 | 0 | 0
833 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000073/2022-2023 | 3494/BD | 03/03/2023 | 0 | Resource Division | 29.32 | 0 | 0
834 | Malda Mechanical | Balurghat Sadar Sub-Division | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No.- I of Augmentation of Daulatpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000197/2023-2024 | 2133/MLMD | 07/07/2023 | 1915 | KARMAKAR CONSTRICTION. | 6.97 | 0 | 0
835 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation and commissioning of electro-mechanical components of Augmentation of DAULATPUR Water Supply Scheme T/W no. I in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000228/2023-2024 | 2248/MLMD | 18/07/2023 | 90 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 11.07 | 0 | 0
836 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation and commissioning of electro-mechanical components of Augmentation of DAULATPUR Water Supply Scheme T/W no. II in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000229/2023-2024 | 2249/MLMD | 18/07/2023 | 90 | JOY MAA SANTOSHI ENTERPRISE. | 8.06 | 0 | 85
837 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation and commissioning of electro-mechanical components of Augmentation of DAULATPUR Water Supply Scheme T/W no. III in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011521) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000230/2023-2024 | 2250/MLMD | 18/07/2023 | 90 | JIBON GHOSH. | 8.07 | 0 | 100
838 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
839 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 842 | GHOSH BROTHERS | 2425.67 | 0 | 30
840 | Balurghat Division | Malda Mechanical Division | Laying of additional distribution of pipeline for the left out area, and allied works within command area of Boaldar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000121/2024-2025 | 1910/BD | 26/09/2024 | 150 | SARKAR CONSTRUCTION | 7.21 | 0 | 100
841 | Balurghat Division | Malda Mechanical Division | Jack Pushing of M.S. pipe of 200 mm dia. Through 600 mm dia R.C.C. Hume pipe (NP4)/ M.S. pipe by Hydraulic Jacking Technique method across Railway Track near Boalder (KM/TP -84/3- 84/4) between Mallickpur Hat(MKRH) and Balurghat(BLGT) station for Boalder Piped Water Supply Scheme in the Disrtict of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000180/2024-2025 | 2481/BD | 20/12/2024 | 60 | RAY CONSTRUCTION &CO. | 31.41 | 0 | 0
842 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000034/2022-2023 | 2900/BD | 06/01/2023 | 0 | Resource Division | 25.3 | 0 | 0
843 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-I of Boalder PWSS under Balurghat CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/03726/2023-2024 | BP-2023-24-700 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.81 | 0 | 0
844 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-II of Boalder PWSS under Balurghat CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/03727/2023-2024 | BP-2023-24-701 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.46 | 0 | 0
845 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Boalder Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013551) | Assistant Engineer - I | Junior Engineer-01 | ORD/000340/2023-2024 | 2338/MLMD | 26/07/2023 | 120 | WEST BENGAL ENGINEERING COMPANY. | 26.56 | 0 | 0
846 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
847 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
848 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
849 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 100 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Kakhar Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000010/2023-2024 | 164/BD | 27/04/2023 | 949 | M/S. TRILOCHAN CONSTRUCTION CO. | 199.03 | 0 | 90
850 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000031/2023-2024 | 36/BD | 09/01/2024 | 0 | Resource Division | 3.87 | 0 | 0
851 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000054/2022-2023 | 2873/BD | 06/01/2023 | 0 | Resource Division | 11.92 | 0 | 0
852 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KAKHAR W/S SCH (TW-II), BANSHIHARI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000380/2022-2023 | 1306/CDD | 22/11/2022 | 30 | MENAKA ENTERPRISE | 13.83 | 9.24 | 0
853 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHAKAR W/S SCH, (TW-I), BLOCK - BANSHIHARI, DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000381/2022-2023 | 1315/CDD | 23/11/2022 | 30 | PADMA ENGINEERING & CO. | 14.08 | 9.72 | 0
854 | Central Drilling | Balurghat Sadar Sub-Division | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000418/2022-2023 | 25/S&WSD | 09/02/2023 | 15 | ASHUTOSH DAS & CO | 0.24 | 0.47 | 0
855 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Khakar, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/02474/2023-2024 | BP-2023-24-406 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.65 | 0 | 0
856 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Khakar Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011751) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000177/2023-2024 | 2096/MLMD | 04/07/2023 | 728 | DILIP MAHATO. | 24.32 | 0 | 96
857 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of KHAKAR, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000267/2023-2024 | 4003193522 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.06 | 4.06 | 100
858 | Balurghat Division | Malda Mechanical Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 250 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for Augmentation of Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000070/2023-2024 | 825/BD | 14/07/2023 | 1145 | DIPESH BHOWMIK | 691.66 | 128.56 | 60
859 | Balurghat Division | Malda Mechanical Division | Repairing of Pump House, IEP Blower room and other allied works for HW site and 2nd TW site of Augmentation of Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000170/2024-2025 | 2269/BD | 20/11/2024 | 45 | M.A. ENTERPRISE | 19.03 | 0 | 30
860 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000002/2024-2025 | 876/BD | 03/05/2024 | 0 | Resource Division | 33.16 | 0 | 0
861 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000047/2023-2024 | 31/BD | 09/01/2024 | 0 | Resource Division | 15.68 | 0 | 0
862 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000077/2022-2023 | 3490/BD | 03/03/2023 | 0 | Resource Division | 20.15 | 0 | 0
863 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Kushmandi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014720) | Assistant Engineer - I | Junior Engineer-01 | ORD/000460/2023-2024 | 2553/MLMD | 04/08/2023 | 817 | SUDIP DEY | 24.16 | 0 | 83
864 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Kushmandi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014720) | Assistant Engineer - I | Junior Engineer-01 | ORD/000464/2023-2024 | 2554/MLMD | 04/08/2023 | 120 | SOVON KUMAR DAS. | 11.46 | 0 | 85
865 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
866 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
867 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 16.63 | 55
868 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
869 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
870 | Balurghat Division | Balurghat Sadar Sub-Division | Providing left out Functional House Hold Tap connection to make all the villages Swajal Gram with allied pipe line under BILBARAIL Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur. | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 3 | ORD/000183/2022-2023 | 3291/BD | 09/02/2023 | 30 | SATELLITE CONSTRUCTION | 9.33 | 8.57 | 99
871 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum Work Order for the work of Land Devlopment by the Carried Earth including Construction of approach Road for Headworks site and 2nd Tubewell Site of BILBARAIL PWSS at Banshihari Block in the District of Dakshin Dinajpr under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 3 | ORD/000368/2021-2022 | 2858/BD | 16/12/2021 | 30 | M/S. SARKAR CONSTRUCTION | 6.96 | 3.12 | 1
872 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 3 | RTOR000002/2023-2024 | 10/BD | 04/04/2023 | 0 | Resource Division | 0.72 | 0 | 0
873 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 3 | RTOR000016/2023-2024 | 842/BD | 14/07/2023 | 0 | Resource Division | 0.72 | 0 | 0
874 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 60 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 0 | 100
875 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of additional distribution pipeline for the left out area , construction of approach road and other allied works within command area of Gurkhair Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000184/2024-2025 | 2474/BD | 19/12/2024 | 60 | TRIYA CONSTRUCTION | 38.77 | 0 | 0
876 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000029/2023-2024 | 29/BD | 09/01/2024 | 0 | Resource Division | 8.6 | 0 | 0
877 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000063/2022-2023 | 2893/BD | 06/01/2023 | 0 | Resource Division | 18.86 | 0 | 0
878 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000070/2023-2024 | 400/BD | 07/03/2024 | 0 | Resource Division | 10.32 | 0 | 0
879 | Malda Mechanical | Balurghat Sadar Sub-Division | Additional quotation for PH-I of Gurkhair PWSS under Harirampur CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/01824/2024-2025 | BP-2024-25-455 | 23/08/2024 | 0 | W.B.S.E.D.C.LTD | 1.22 | 0 | 0
880 | Malda Mechanical | Balurghat Sadar Sub-Division | Payment for the quotation of New Connection of PH NO-II of Gurkhair PWSS under Harirampur CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/03724/2023-2024 | BP-2023-24-703 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 2.92 | 0 | 0
881 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Gurkhair Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012011) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000394/2023-2024 | 2402/MLMD | 28/07/2023 | 1033 | ANIMA ENTERPRISE | 26.85 | 0 | 100
882 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of GURKHAIR PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000786/2023-2024 | 4003201662 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.21 | 3.21 | 100
883 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
884 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
885 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
886 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
887 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 16.92 | 55
888 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
889 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
890 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
891 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
892 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 11.22 | 55
893 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
894 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
895 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
896 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 2 Sub Division | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
897 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 2 Sub Division | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.68 | 55
898 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
899 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
900 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
901 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.85 | 55
902 | Balurghat Division | Malda Mechanical Division | Restoration of Fatepur - Dehaband Road from chainage 0.00 km to 10.00 km under Manikor PWSS at Kushmandi Block, Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00126/2024-2025 | BP-2024-25-87 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.81 | 0 | 0
903 | Balurghat Division | Malda Mechanical Division | Restoration of Fatepur - Dehaband Road from chainage 10.00 km to 14.40 km under Manikor PWSS at Kushmandi Block, Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/00306/2024-2025 | BP-2024-25-197 | 27/11/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 24.26 | 0 | 0
904 | Balurghat Division | Malda Mechanical Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Installation of IEP, Construction of Pump House & Blower Room, Boundary Wall & Approach Road for implementation of MANIKOR Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000101/2023-2024 | 1106/BD | 11/08/2023 | 843 | GHOSH BROTHERS | 1047.18 | 0 | 40
905 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000068/2022-2023 | 2891/BD | 06/01/2023 | 0 | Resource Division | 36.47 | 0 | 0
906 | Central Drilling | Malda Mechanical Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Manikor W/S Scheme (TW-III), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000467/2022-2023 | 1810/CDD | 04/01/2023 | 30 | CHANDA ENTERPRISE | 9.69 | 7.27 | 100
907 | Central Drilling | Malda Mechanical Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Manikor W/S Scheme (TW-I), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000468/2022-2023 | 1936/CDD | 31/01/2023 | 30 | UNIVERSAL ENTERPRISES | 9.7 | 7.23 | 100
908 | Central Drilling | Malda Mechanical Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Manikor W/S Scheme (TW-II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000469/2022-2023 | 1937/CDD | 31/01/2023 | 30 | UNIVERSAL ENTERPRISES | 9.7 | 7.15 | 100
909 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-III of Manikor PWSS under Kushmandi CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/00210/2024-2025 | BP-2024-25-84 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 2.67 | 0 | 0
910 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-I of Manikor PWSS under Kushmandi CCC in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/02474/2024-2025 | BP-2024-25-570 | 14/11/2024 | 0 | W.B.S.E.D.C.LTD | 2.98 | 0 | 0
911 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-II of Manikor PWSS under Kushmandi CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/02475/2024-2025 | BP-2024-25-571 | 14/11/2024 | 0 | W.B.S.E.D.C.LTD | 2.93 | 0 | 0
912 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Manikor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013190) | Assistant Engineer - I | Junior Engineer-01 | ORD/000184/2023-2024 | 2109/MLMD | 05/07/2023 | 938 | CREATIVE WATER & PROCESS TECH. PVT. LTD. | 38.23 | 0 | 70
913 | Balurghat Division | Balurghat Division | Restoration of Balurghat to Laskarhat road from chainage 8.00 km to 20.73 km at BALURGHAT & TAPAN Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | BILL/00205/2024-2025 | BP-2024-25-127 | 12/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 4.59 | 0 | 0
914 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection in connection with Retrofitting for Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000067/2023-2024 | 816/BD | 13/07/2023 | 510 | KRISHNA PAUL | 12.2 | 0 | 100
915 | Balurghat Division | Balurghat Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 150 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000203/2022-2023 | 3512/BD | 04/03/2023 | 1187 | M/S. ANWESHA ENTERPRISE | 379.27 | 102.77 | 40
916 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | RTOR000022/2024-2025 | 2315/BD | 22/11/2024 | 0 | Resource Division | 5.09 | 0 | 0
917 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | RTOR000075/2022-2023 | 3492/BD | 03/03/2023 | 0 | Resource Division | 16.59 | 0 | 0
918 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Jalghar Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015959) | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000735/2023-2024 | 2797/MLMD | 17/08/2023 | 864 | M/S PARIMAL DAS. | 24.02 | 19.38 | 81
919 | Balurghat Division | Balurghat Division | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 558 | GHOSH BROTHERS | 3593.49 | 0 | 30
920 | Balurghat Division | Balurghat Division | Laying of additional distribution of pipeline for the left out area, and allied works within command area of Mahadipur Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000122/2024-2025 | 1911/BD | 26/09/2024 | 30 | EIGHTY EIGHT CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 6.31 | 0 | 0
921 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | RTOR000042/2022-2023 | 2898/BD | 06/01/2023 | 0 | Resource Division | 23.04 | 0 | 0
922 | Malda Mechanical | Balurghat Division | Payment for the quotation of New Connection of PH NO-II of Mahadipur PWSS under Balurghat CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/01069/2024-2025 | BP-2024-25-296 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.07 | 0 | 0
923 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Mahadipur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014998) | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000478/2023-2024 | 2557/MLMD | 04/08/2023 | 120 | DAS CONSTRUCTION | 26.83 | 0 | 0
924 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
925 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
926 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
927 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.71 | 55
928 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Allied Work In Connection With Providing Functional House Hold Tap Connection For Goalgaon PWSS Under Jal Swapna Programme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer Kushmandi | ORD/000265/2021-2022 | 2495/BD | 02/11/2021 | 40 | R.P. CHOUDHURY CONSTRUCTION. | 4.93 | 4.76 | 1
929 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for GOALGAON Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1587/BD Dated :- 16/10/2020 & Tender No. 158 of 2020-2021] |  | Junior Engineer 1 HQ,Junior Engineer Kushmandi | VCH/000179/2022-2023 | BP-2022-23-12 | 12/04/2022 | 0 | CHIRANJIB DAS | 11.14 | 0 | 0
930 | Balurghat Division |  | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Deulbari Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase - II) |  |  | ORD/000090/2021-2022 | 1691/BD | 09/08/2021 | 45 | M/S. A.D. ENTERPRISE | 20.82 | 0 | 1
931 | Balurghat Division |  | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 2968/BD | 31/12/2021 | 0 | Resource Division | 2.2 | 0 | 0
932 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme with Augmentation for Chakvrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase-II). | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000167/2022-2023 | 4005/BD | 09/01/2023 | 60 | M/S. SARKAR ENTERPRISE | 52.66 | 0 | 0
933 | Balurghat Division | Balurghat Division | Special Repairing and Overhauling of Existing Filter Media for the 02 nos vessel as well as change of MNO2 for Oxidation Chamber i.c.w. better running of IEP in all respect at Chakvrigu Piped Water Supply Scheme in the District of Dakshin Dinajpur, under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000175/2023-2024 | 1878/BD | 22/11/2023 | 30 | ZEOLITE FRESH INDIA | 11.86 | 0 | 97
934 | Balurghat Division | Balurghat Division | Laying of Rising Main, Repairing of existing 600 Cum capacity OHR with 20m Staging Height, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Chak Bhrigu Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000225/2022-2023 | 3828/BD | 24/03/2023 | 60 | M/S. S. CONSTRUCTION | 33.85 | 13.52 | 45
935 | Balurghat Division | Balurghat Division | Formal work order for the work of Laying of distribution system for the proposed Augmentation of Chak Bhrigu water supply scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (2nd Call) | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/000511/2021-2022 | 227/BD | 08/02/2022 | 90 | BHOLANATH CONSTRUCTION. | 143.42 | 0 | 20
936 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | RTOR000003/2022-2023 | 837/BD | 11/05/2022 | 0 | Resource Division | 7.22 | 0 | 0
937 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | RTOR000003/2023-2024 | 08/BD | 04/04/2023 | 0 | Resource Division | 10.38 | 0 | 0
938 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | RTOR000046/2021-2022 | 347/BD | 22/02/2022 | 0 | Resource Division | 2.01 | 0 | 0
939 | Malda Mechanical | Balurghat Division | Modification & upgradation of electro-mechanical installation work at Pump House No. I of Chakvrigu Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/001228/2021-2022 | 548 /MLMD | 28/03/2022 | 903 | MERCURY ENGINEERING COMPANY | 6.24 | 5.58 | 60
940 | Malda Mechanical | Balurghat Division | Modification & upgradation of electro-mechanical installation work at Pump House No. II of Chakvrigu Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/001229/2021-2022 | 549 /MLMD | 28/03/2022 | 30 | SUBRATA KUMAR DAS. | 6.17 | 5.57 | 100
941 | Malda Mechanical | Balurghat Division | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. I of Chakvrigu piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/001243/2021-2022 | 480 /MLMD | 24/03/2022 | 30 | SUDIP DEY | 3.1 | 3.09 | 1
942 | Malda Mechanical | Balurghat Division | Supply, delivery and installation of 25 KVA servo motor operated copper wound line voltage stabilizer at pump house no. II of Chakvrigu piped water supply scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Balurghat,Junior Engineer-01 | ORD/001263/2021-2022 | 481 /MLMD | 24/03/2022 | 30 | DEVI ENTERPRISE... | 3.11 | 3.09 | 1
943 | Balurghat Division | Balurghat Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Hili & Tapan Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer Hili | ORD/000134/2024-2025 | 1942/BD | 27/09/2024 | 20 | M/S. A.D. ENTERPRISE | 3.83 | 0 | 100
944 | Balurghat Division | Balurghat Division | Consultancy Service for Preparation of DPR followed by detail Survey and design of pipe line network for Augmentation of Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division P.H.E. Dte. |  | Junior Engineer Hili | ORD/000374/2022-2023 | 897/BD | 23/05/2022 | 30 | ENVIROTECH SOLUTIONS | 3.72 | 0 | 100
945 | Balurghat Division | Balurghat Division | Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under various Piped Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur. |  | Junior Engineer Hili | ORD/000393/2021-2022 | 594/RWS | 31/12/2021 | 30 | BALURGHAT BUILDERS | 4.61 | 4.09 | 100
946 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
947 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
948 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.2 | 55
949 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
950 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.29 | 55
951 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Banshihari Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000133/2024-2025 | 1944/BD | 27/09/2024 | 20 | RANJAN SARKAR | 5.25 | 0 | 100
952 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of balance Distribution pipe line and Construction of Boundary Wall and allied works at Bhoir Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000147/2024-2025 | 2053/BD | 03/10/2024 | 180 | THE NEW LOKNATH CONSTRUCTION | 236.45 | 0 | 85
953 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main, Partial Distribution of pipeline, Providing FHTC, Construction of 300 Cum capacity OHR with 20m Staging Height including Soil Investigation, Construction of Pump House for implementation of Bhoir Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000201/2022-2023 | 3507/BD | 04/03/2023 | 1019 | M/S. ANWESHA ENTERPRISE | 406.64 | 171.46 | 45
954 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000050/2022-2023 | 2894/BD | 06/01/2023 | 0 | Resource Division | 13.65 | 0 | 0
955 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000052/2023-2024 | 247/BD | 21/02/2024 | 0 | Resource Division | 13.02 | 0 | 0
956 | Central Drilling | Balurghat Sadar Sub-Division | Hiring of Diesel Driven Motor Cab (BS-IV & Above) hiving contract carriage permit along with driver for office of the Store & Workshop Sub Division, Central Drilling Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000210/2023-2024 | 12/S&WSD | 15/01/2024 | 198 | SULEKHA GHOSH | 0.94 | 0 | 15
957 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BHOIR W/S SCH (HW), BANSHIHARI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000271/2022-2023 | 1145/CDD | 07/11/2022 | 30 | PADMA ENGINEERING & CO. | 14.08 | 9.58 | 1
958 | Central Drilling | Balurghat Sadar Sub-Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 230 mtrs. Depth) by utilising Departmental machineries for Bhoir W/S Scheme (TW-II), Banshihari block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000470/2022-2023 | 306/CDD | 27/04/2022 | 30 | PADMA ENGINEERING & CO. | 10.33 | 8.23 | 100
959 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bhoir PWSS , Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | BILL/02467/2023-2024 | BP-2023-24-395 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 10.48 | 0 | 0
960 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bhoir PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000437/2023-2024 | 4003196923 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.6 | 5.6 | 100
961 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Bhoir Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011765) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/001125/2022-2023 | 508/MLMD | 20/03/2023 | 180 | DAS CONSTRUCTION | 25.78 | 19.17 | 70
962 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
963 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
964 | Balurghat Division | Malda Mechanical Division | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 558 | GHOSH BROTHERS | 3593.49 | 0 | 30
965 | Balurghat Division | Malda Mechanical Division | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Barakali Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000176/2024-2025 | 2283/BD | 21/11/2024 | 30 | MAYA CONSTRUCTION | 22 | 0 | 0
966 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000033/2022-2023 | 2909/BD | 06/01/2023 | 0 | Resource Division | 15.8 | 0 | 0
967 | Malda Mechanical | Malda Mechanical Division | : Payment for the quotation of New Connection of PH NO-I of Barkail PWSS under Balurghat CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/01070/2024-2025 | BP-2024-25-306 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.56 | 0 | 0
968 | Malda Mechanical | Malda Mechanical Division | Payment for the quotation of New Connection of PH NO-II of Barakali PWSS under Balurghat CCC in the District of Dakshin Dinajpur | Assistant Engineer - I | Junior Engineer-01 | BILL/03730/2023-2024 | BP-2023-24-697 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.66 | 0 | 0
969 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Barakali Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014478) | Assistant Engineer - I | Junior Engineer-01 | ORD/000367/2023-2024 | 2373/MLMD | 28/07/2023 | 180 | WEST BENGAL ENGINEERING COMPANY. | 26.56 | 0 | 0
970 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
971 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.83 | 55
972 | Balurghat Division | Balurghat Division | Laying of Rising Main, Providing FHTC, Construction of 300 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Bagbari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000008/2023-2024 | 95/BD | 13/04/2023 | 1169 | CREATION CONSTRUCTION | 199.5 | 0 | 80
973 | Balurghat Division | Balurghat Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Gangarampur & Harirampur Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000125/2024-2025 | 1914/BD | 26/09/2024 | 20 | ASHIT KUMAR DEBSHARMA | 8.35 | 0 | 100
974 | Balurghat Division | Balurghat Division | Laying of additional distribution of pipeline for the left out area, construction of approach road, and other allied works within command area of Bagbari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000166/2024-2025 | 2256/BD | 13/11/2024 | 122 | RELIABLE CONSTRUCTION | 88.24 | 0 | 70
975 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | RTOR000040/2023-2024 | 1486/BD | 19/09/2023 | 0 | Resource Division | 1.09 | 0 | 0
976 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | RTOR000053/2022-2023 | 2882/BD | 06/01/2023 | 0 | Resource Division | 14.86 | 0 | 0
977 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | RTOR000053/2023-2024 | 249/BD | 21/02/2024 | 0 | Resource Division | 11.46 | 0 | 0
978 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAGBARI W/S SCH (TW-I), UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000312/2022-2023 | 1395/CDD | 28/11/2022 | 30 | CHANDA ENTERPRISE | 8.26 | 6.77 | 1
979 | Central Drilling | Balurghat Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM 120 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAGBARI W/S SCH (TW-II), UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000357/2022-2023 | 1396/CDD | 28/11/2022 | 30 | CHANDA ENTERPRISE | 8.26 | 6.57 | 0
980 | Central Drilling | Balurghat Division | Additional Carraige of Gravels for Construction of TW at Bagbari PWSS TW-I, harirampur Block, Dakshin Dinajpur District under CMSD-I, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000476/2022-2023 | 583/CMSD-I(D) | 30/11/2022 | 7 | CHANDA ENTERPRISE | 0.59 | 0.42 | 100
981 | Central Drilling | Balurghat Division | Additional Carraige of Gravels for Construction of TW at Bagbari PWSS TW-II, harirampur Block, Dakshin Dinajpur District under CMSD-I, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000477/2022-2023 | 584/CMSD-I(D) | 30/11/2022 | 7 | CHANDA ENTERPRISE | 0.59 | 0.39 | 100
982 | Malda Mechanical | Balurghat Division | Additional Quotation For BAGBARI-I PHE | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/03555/2023-2024 | BP-2023-24-559 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 1.31 | 0 | 0
983 | Malda Mechanical | Balurghat Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Bagbari Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012004) | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000181/2023-2024 | 2107/MLMD | 05/07/2023 | 120 | WEST BENGAL ENGINEERING COMPANY. | 26.29 | 0 | 82
984 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BAGBARI, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000288/2023-2024 | 4003193809 | 15/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.29 | 3.29 | 100
985 | Malda Mechanical | Balurghat Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BAGBARI, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000289/2023-2024 | 4003193816 | 15/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.04 | 3.04 | 100
986 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
987 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
988 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
989 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
990 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
991 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
992 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
993 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.08 | 55
994 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Banshihari Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000133/2024-2025 | 1944/BD | 27/09/2024 | 20 | RANJAN SARKAR | 5.25 | 0 | 100
995 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of additional distribution pipeline for the left out area and other allied works for Amai Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000193/2024-2025 | 01/BD | 02/01/2025 | 85 | CHHAYA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.85 | 0 | 100
996 | Balurghat Division | Balurghat Sadar Sub-Division | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 100 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Amai Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000205/2022-2023 | 3509/BD | 04/03/2023 | 850 | ASHIT KUMAR DEBSHARMA | 228.04 | 97.42 | 85
997 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000004/2024-2025 | 1838/BD | 18/06/2024 | 0 | Resource Division | 4.6 | 0 | 0
998 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | RTOR000055/2022-2023 | 2881/BD | 06/01/2023 | 0 | Resource Division | 8.58 | 0 | 0
999 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Amai Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011883) | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000339/2023-2024 | 2337/MLMD | 26/07/2023 | 120 | DEY ENTERPRISE [HOWRAH] | 25.31 | 0 | 80
1000 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Amai PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000789/2023-2024 | 4003195530 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 9.2 | 9.2 | 100
1001 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Amai PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer (Civil),Junior Engineer-01 | ORD/000790/2023-2024 | 4003196353 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 9.46 | 9.46 | 100
1002 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1003 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1004 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1005 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.68 | 55
1006 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1007 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1008 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1009 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1010 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.84 | 55
1011 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1012 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1013 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 10.94 | 55
1014 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1015 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1016 | Balurghat Division | Balurghat Sadar Sub-Division | Formal Work Order for the work of "Providing Functional House Hold Tap Connection for KAIL piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte." |  | Junior Engineer (Civil),Junior Engineer 3 | ORD/000007/2020-2021 | 1372/BD | 29/09/2020 | 45 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 41.22 | 0 | 100
1017 | Balurghat Division | Balurghat Sadar Sub-Division | Restoration of damaged pipe line and allied works under Retrofitting of Kail PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 3 | ORD/000007/2023-2024 | 272/BD | 05/05/2023 | 30 | M/S. GHOSH ENTERPRISE | 2.03 | 0 | 90
1018 | Balurghat Division | Balurghat Sadar Sub-Division | Allied Work In Connection With Providing Functional House Hold Tap Connection For Kail PWSS Under Jal Swapna Programme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer (Civil),Junior Engineer 3 | ORD/000358/2021-2022 | 547/RWS | 03/12/2021 | 15 | AMITAVA MITRA CONTRACTOR & ORDER SUPPLIER | 0.78 | 0 | 100
1019 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1020 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1021 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.68 | 55
1022 | Balurghat Division | Malda Mechanical Division | Sinking of tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 450 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000099/2023-2024 | 1096/BD | 10/08/2023 | 1169 | M/S. ANWESHA ENTERPRISE | 738.35 | 0 | 63
1023 | Balurghat Division | Malda Mechanical Division | Providing Functional House Hold Tap Connection in connection with Retrofitting for Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000244/2022-2023 | 3951/BD | 31/03/2023 | 45 | SREEMAA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 24.48 | 0 | 0
1024 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000020/2024-2025 | 2313/BD | 22/11/2024 | 0 | Resource Division | 15.3 | 0 | 0
1025 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000078/2022-2023 | 3489/BD | 03/03/2023 | 0 | Resource Division | 51.59 | 0 | 0
1026 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Tior, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | BILL/02476/2023-2024 | BP-2023-24-404 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 11.94 | 0 | 0
1027 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Augmentation of Teor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014550) | Assistant Engineer - I | Junior Engineer-01 | ORD/000489/2023-2024 | 2561/MLMD | 04/08/2023 | 390 | UTTAM KUMAR GHOSH | 20.49 | 0 | 100
1028 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Teor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/002487/2023-2024 | 812/MLMD | 15/02/2024 | 180 | SUDIP DEY | 10.81 | 0 | 70
1029 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1030 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1031 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 18.25 | 55
1032 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1033 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 4.04 | 55
1034 | Balurghat Division | Balurghat Sadar Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Purba Hariharpur Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000012/2020-2021 | 1490/BD | 10/10/2020 | 40 | CHOUDHURY CONSTRUCTION | 11.39 | 9.72 | 0
1035 | Balurghat Division | Balurghat Sadar Sub-Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Purba Hariharpur Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1490/BD Dated :- 10/10/2020 & Tender No. 202 of 2020-2021] |  | Junior Engineer 2 HQ,Junior Engineer Balurghat | VCH/000180/2022-2023 | BP-2022-23-13 | 12/04/2022 | 0 | CHOUDHURY CONSTRUCTION | 3.62 | 0 | 0
1036 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap connection under Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur (Phase - I). |  | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 3 Sub Division | ORD/000083/2022-2023 | 1248/BD | 14/06/2022 | 30 | R.K. CONSTRUCTION | 9.02 | 8.24 | 1
1037 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 3 Sub Division | ORD/000321/2021-2022 | 2065/BD | 17/09/2021 | 15 | ENVIROTECH SOLUTIONS | 2.92 | 2.66 | 1
1038 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Banshihari Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) |  | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 3 Sub Division | ORD/000330/2021-2022 | 1913/BSSD | 01/12/2021 | 25 | RANJAN SARKAR | 4.83 | 4.73 | 100
1039 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division |  | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 3 Sub Division | RTOR000007/2022-2023 | 831/BD | 11/05/2022 | 0 | Resource Division | 1.66 | 0 | 0
1040 | Balurghat Division | RWS Balurghat Sub-Division | Laying of Rising Main, Construction of 400 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House (H/W site & 2nd TW site) and construction of Boundary Wall for Augmentation of KUMARGANJ Piped Water Supply Scheme at Kumaragnj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000077/2023-2024 | 887/BD | 24/07/2023 | 1012 | MOHANTA BUILDERS | 148.99 | 0 | 25
1041 | Balurghat Division | RWS Balurghat Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000132/2024-2025 | 2095/BD | 22/10/2024 | 20 | BIPUL SARKAR | 5.17 | 0 | 100
1042 | Balurghat Division | RWS Balurghat Sub-Division | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at different locations of Kumarganj and Agachha Piped Water Supply Scheme under Kumarganj Block , Balurghat Division, PHE Dte in the District of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000145/2023-2024 | 1429/BD | 08/09/2023 | 30 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 9.69 | 0 | 100
1043 | Balurghat Division | RWS Balurghat Sub-Division | Providing Functional House Hold Tap connection under Augmentation of Kumarganj Piped Water Supply Scheme at Kumarganj Block in the District of Dakshin Dinajpur (Phase - II). | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000166/2022-2023 | 2933/BD | 11/01/2023 | 959 | KAMIRUL SK AND CO. | 77.7 | 0 | 56
1044 | Balurghat Division | RWS Balurghat Sub-Division | Formal work order for the work of Laying distribution pipe line for Augmentation of Kumarganj piped water supply scheme at Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division P.H. Engineering Dte | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000418/2021-2022 | 73/BD | 11/01/2022 | 1089 | PRADIP KUMAR PAUL | 179.77 | 151.34 | 96
1045 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000004/2022-2023 | 838/BD | 11/05/2022 | 0 | Resource Division | 10.77 | 0 | 0
1046 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000012/2023-2024 | 144/BD | 24/04/2023 | 0 | Resource Division | 16.05 | 0 | 0
1047 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000014/2023-2024 | 574/BD | 19/06/2023 | 0 | Resource Division | 3.34 | 0 | 0
1048 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000023/2024-2025 | 2319/BD | 22/11/2024 | 0 | Resource Division | 12.06 | 0 | 0
1049 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | RTOR000048/2021-2022 | 345/BD | 22/02/2022 | 0 | Resource Division | 8.08 | 0 | 0
1050 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of KUMARGANJ Water Supply Scheme T/W no.I in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000961/2022-2023 | 2947/MLMD | 28/12/2022 | 60 | DEVI ENTERPRISE... | 10.72 | 9.09 | 1
1051 | Malda Mechanical | RWS Balurghat Sub-Division | Modification & upgradation of electro-mechanical installation work at Pump House No. II of Kumarganj Water Supply Scheme in the district of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/001225/2021-2022 | 545 /MLMD | 28/03/2022 | 30 | M/S. KUNDU CONSTRACTION | 6.19 | 5.58 | 1
1052 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, Installation & Commissioning of electro-mechanical components at T/W No-I of Kumarganj W/S Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kumarganj,Junior Engineer-01 | ORD/002627/2023-2024 | 1050/MLMD | 15/03/2024 | 14 | D.R. ENTERPRISE. | 1.7 | 0 | 100
1053 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Harirampur Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 Sub Division | ORD/000111/2022-2023 | 525/BD | 01/04/2022 | 30 | ENVIROTECH SOLUTIONS | 3.22 | 3.22 | 1
1054 | Balurghat Division | Balurghat Division | Providing Functional Household Tap Connection by Retrofitting of present scheme of Harirampur Piped Water Supply Scheme under Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer 2 Sub Division | ORD/000260/2022-2023 | 3962/BD | 31/03/2023 | 45 | SATELLITE CONSTRUCTION | 16.02 | 0 | 0
1055 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Providing Functional Tap connection for School/ AWC/ Health Centre/ Madrasa under Harirampur Piped Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur. |  | Junior Engineer 2 Sub Division | ORD/000343/2021-2022 | 1922/BSSD | 01/12/2021 | 25 | SARKAR CONSTRUCTION (GRP) | 4.84 | 3.65 | 1
1056 | Balurghat Division | Balurghat Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Prepartion of DPR to provide FHTC in connection with Augmentation of Kamarpara Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 1 Sub Division | ORD/000113/2022-2023 | 527/BD | 01/04/2022 | 30 | ENVIROTECH SOLUTIONS | 3.82 | 3.82 | 100
1057 | Balurghat Division | Balurghat Division | Providing FHTC by retrofitting of Kamarpara Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer 1 Sub Division | ORD/000237/2022-2023 | 3927/BD | 30/03/2023 | 45 | MAA CHANCHALA CONSTRUCTION | 24.49 | 0 | 68
1058 | Balurghat Division | Balurghat Division | Material Requisition To Resource Division |  | Junior Engineer 1 Sub Division | RTOR000069/2023-2024 | 401/BD | 07/03/2024 | 0 | Resource Division | 4.77 | 0 | 0
1059 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Conducting Route Survey, investigation of existing scheme, Design of distribution Network and Preparation of DPR to provide FHTC in connection with Augmentation of Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer Kushmandi | ORD/000115/2022-2023 | 531/BD | 01/04/2022 | 30 | ENVIROTECH SOLUTIONS | 2.96 | 2.96 | 1
1060 | Balurghat Division | RWS Balurghat Sub-Division | Providing Functional Household Tap Connection by Retrofitting of present scheme of Kushmandi Piped Water Supply Scheme under Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer Kushmandi | ORD/000258/2022-2023 | 3952/BD | 31/03/2023 | 45 | M/S. A.D. ENTERPRISE | 17.6 | 0 | 0
1061 | Balurghat Division | RWS Balurghat Sub-Division | Acceptance cum work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme under Augmentation for Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Phase- I) |  | Junior Engineer Kushmandi | ORD/000328/2021-2022 | 1911/BSSD | 01/12/2021 | 25 | KRISHNA PAUL | 4.88 | 4.86 | 1
1062 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer Kushmandi,Junior Engineer Tapan`,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1063 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer Kushmandi,Junior Engineer Tapan`,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1064 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer Kushmandi,Junior Engineer Tapan`,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 80.29 | 55
1065 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1066 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.88 | 55
1067 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 2 Sub Division,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1068 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 2 Sub Division,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1069 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 2 Sub Division,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 18.88 | 55
1070 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1071 | Balurghat Division | Balurghat Division | Allied Work In Connection With Providing Functional House Hold Tap Connection For Harigaon PWSS Under Jal Swapna Programme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  | Junior Engineer 2 Sub Division | ORD/000356/2021-2022 | 548/RWS | 03/12/2021 | 30 | GOUTAM SAHA | 4.34 | 0.25 | 1
1072 | Balurghat Division | Balurghat Division | Providing Functional House Hold Tap Connection Under Jal Swapna Programme for HARIGAON Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. [Work Order No. 1590/BD, Dated :- 16/10/2020 & Tender No. 103 of 2020-2021] |  | Junior Engineer 2 Sub Division | VCH/000402/2021-2022 | 8443/7 | 10/01/2022 | 0 | BHOLANATH CONSTRUCTION. | 8.95 | 0 | 0
1073 | Balurghat Division | Balurghat Division | Allied Work In Connection With Providing Functional House Hold Tap Connection ForHarigaon PWSS Under Jal Swapna Programme at Balurghat Block in the District ofDakshin Dinajpur under Balurghat Division P.H.Engineering Dte. (Work Order No. 548/RWS, Dated :- 03/12/2021 & Tender No. 372 of 2021-2022) |  | Junior Engineer 2 Sub Division | VCH/000430/2021-2022 | 8443/3 | 02/02/2022 | 0 | GOUTAM SAHA | 4 | 0 | 0
1074 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1075 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1076 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer 1 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1077 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1078 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1079 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1080 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1081 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1082 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 7.24 | 55
1083 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1084 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 15.55 | 55
1085 | Balurghat Division | Malda Mechanical Division | Restoration of Udaipur Mahipaldighi road from chainage 0.00 km to 8.00 km under Mahipaldighi PWSS at Kushmandi Block, Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer-01 | BILL/00211/2024-2025 | BP-2024-25-135 | 13/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 17.04 | 0 | 0
1086 | Balurghat Division | Malda Mechanical Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase- II) | Assistant Engineer - I | Junior Engineer-01 | ORD/000140/2024-2025 | 1951/BD | 27/09/2024 | 20 | KINSHIP CONSTRUCTION | 2.39 | 0 | 100
1087 | Balurghat Division | Malda Mechanical Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) | Assistant Engineer - I | Junior Engineer-01 | ORD/000146/2024-2025 | 2052/BD | 03/10/2024 | 20 | GOUTAM SAHA | 2.39 | 0 | 100
1088 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000005/2024-2025 | 1837/BD | 18/06/2024 | 0 | Resource Division | 15.68 | 0 | 0
1089 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000059/2022-2023 | 2878/BD | 06/01/2023 | 0 | Resource Division | 23.09 | 0 | 0
1090 | Balurghat Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-01 | RTOR000068/2023-2024 | 269/BD | 22/02/2024 | 0 | Resource Division | 5.01 | 0 | 0
1091 | Central Drilling | Malda Mechanical Division | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Mahipaldighi W/S Scheme (TW-I & II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000471/2022-2023 | 1805/CDD | 04/01/2023 | 30 | PADMA ENGINEERING & CO. | 20.01 | 15.54 | 100
1092 | Malda Mechanical | Malda Mechanical Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Mahipaldighi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013181) | Assistant Engineer - I | Junior Engineer-01 | ORD/000182/2023-2024 | 2108/MLMD | 05/07/2023 | 840 | M/S D.G.B. ENTERPRISE. | 28.17 | 0 | 90
1093 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of MAHIPALDIGHI, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000282/2023-2024 | 4003194078 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.51 | 4.51 | 100
1094 | Malda Mechanical | Malda Mechanical Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of MAHIPALDIGHI, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/000283/2023-2024 | 4003194079 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.5 | 4.5 | 100
1095 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1096 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1097 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1098 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 23.9 | 55
1099 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 1 HQ,Junior Engineer 3 HQ,Junior Engineer Kumarganj,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1100 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1101 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1102 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.73 | 55
1103 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1104 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1105 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.03 | 55
1106 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1107 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
1108 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1109 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00280/2024-2025 | BP-2024-25-188 | 30/10/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 11.81 | 0 | 0
1110 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
1111 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1112 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1113 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1114 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 Sub Division,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
1115 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1116 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
1117 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1118 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 3.86 | 55
1119 | Balurghat Division | Balurghat Sadar Sub-Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer Sadar | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 0 | 55
1120 | Balurghat Division | Balurghat Sadar Sub-Division | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Aminpur- Dehaband Road via Kantason, Sarala from (Chainage 0.00 KM to 15.45 Km) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00110/2024-2025 | BP-2024-25-83 | 01/07/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 12.84 | 0 | 0
1121 | Balurghat Division | Balurghat Sadar Sub-Division | Restoration of Hard Shoulder for Daulatpur-Harirampur-Dehaband Road from 7.00 Km to 20.60 Km under Berail PWSS at Kushmandi Block, in the district of Dakshin Dinajpur. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | BILL/00190/2024-2025 | BP-2024-25-123 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 7.89 | 0 | 0
1122 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase- II) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000140/2024-2025 | 1951/BD | 27/09/2024 | 20 | KINSHIP CONSTRUCTION | 2.39 | 0 | 100
1123 | Balurghat Division | Balurghat Sadar Sub-Division | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000146/2024-2025 | 2052/BD | 03/10/2024 | 20 | GOUTAM SAHA | 2.39 | 0 | 100
1124 | Balurghat Division | Balurghat Sadar Sub-Division | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Berail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000212/2022-2023 | 3643/BD | 15/03/2023 | 1176 | S & P ENTERPRISE | 1138.61 | 0 | 35
1125 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000016/2024-2025 | 2307/BD | 22/11/2024 | 0 | Resource Division | 1.02 | 0 | 0
1126 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000056/2023-2024 | 252/BD | 21/02/2024 | 0 | Resource Division | 25.67 | 0 | 0
1127 | Balurghat Division | Balurghat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | RTOR000067/2022-2023 | 2895/BD | 06/01/2023 | 0 | Resource Division | 44.9 | 0 | 0
1128 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BERAIL W/S SCH (TW-III), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000407/2022-2023 | 1935/CDD | 31/01/2023 | 30 | UNIVERSAL ENTERPRISES | 9.7 | 7.12 | 0
1129 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BERAIL W/S SCH (TW-I), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000408/2022-2023 | 1933/CDD | 31/01/2023 | 30 | M/S P P ELECTRICALS | 9.42 | 6.78 | 0
1130 | Central Drilling | Balurghat Sadar Sub-Division | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BERAIL W/S SCH (TW-II), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000409/2022-2023 | 1934/CDD | 31/01/2023 | 30 | M/S P P ELECTRICALS | 9.42 | 6.78 | 0
1131 | Malda Mechanical | Balurghat Sadar Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Berail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013060) | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000179/2023-2024 | 2098/MLMD | 04/07/2023 | 120 | MERCURY ENGINEERING COMPANY. | 41.04 | 0 | 100
1132 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BERAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000279/2023-2024 | 4003194082 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.15 | 4.15 | 100
1133 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BERAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000280/2023-2024 | 4003194083 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.41 | 4.41 | 100
1134 | Malda Mechanical | Balurghat Sadar Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of BERAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer Kushmandi,Junior Engineer-01 | ORD/000281/2023-2024 | 4003194068 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.78 | 2.78 | 100
1135 | Balurghat Division | RWS Balurghat Sub-Division | Source Augmentation of Deulbari Piped Water Supply Scheme comprising of Sinking of One Big Dia Tubewell, Construction of (3.6mtr. X 3.00 mtr.) Pump House and Construction of Boundary wall for 3rd Tubewell Site at Deulbari Mouza, Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer - I | Junior Engineer 2 Sadar,Junior Engineer-01 | ORD/000236/2022-2023 | 3926/BD | 30/03/2023 | 45 | BOSE CONSTRUCTION | 35.56 | 0 | 70
1136 | Balurghat Division | RWS Balurghat Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer 2 Sadar,Junior Engineer-01 | RTOR000036/2023-2024 | 926/BD | 27/07/2023 | 0 | Resource Division | 0.66 | 0 | 0
1137 | Malda Mechanical | RWS Balurghat Sub-Division | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Deulbari Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016346) | Assistant Engineer - I | Junior Engineer 2 Sadar,Junior Engineer-01 | ORD/000450/2023-2024 | 2547/MLMD | 04/08/2023 | 302 | BEE GEE CONSTRUCTION. | 10.9 | 0 | 100
1138 | Malda Mechanical | RWS Balurghat Sub-Division | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Deulbari PWSS ,Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer 2 Sadar,Junior Engineer-01 | ORD/001875/2023-2024 | 4003270146 | 13/11/2023 | 90 | W.B.S.E.D.C.LTD | 3.73 | 0 | 100
1139 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 0 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0
1140 | Balurghat Division | Balurghat Division | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer-01 | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 1146 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 20.47 | 55
Total | [10 empty] | 2131492.96 | 8759.12